7068A_IPR | Jalan Luangan | DU00006040536 | Sabah | Sabah | 5.370194 | 116.167695 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x1. | IDU-IPRAN | Perform LAG at CP site for IDU 7068A-JALAN LUANGAN-RTN05 to 7068A-MAC-001 Jalan Luangan 1) Patch 7068A-JALAN LUANGAN-RTN05 GE2 to new CP port 2) Create LAG 3) Impact sites: 7063D | Perform LAG at CP site for IDU 7068A-JALAN LUANGAN-RTN05 to 7068A-MAC-001 Jalan Luangan 1) Patch 7068A-JALAN LUANGAN-RTN05 GE2 to new CP port 2) Create LAG 3) Impact sites: 7063D | [6 empty] | NR services | SQ202510230970-NR Services | NR services | SQ202510150302-NR Services | 2026-01-14 | 2026-01-14 | Completed | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-16 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100934 |  | 2025-10-10 | 2025-10-10 | Completed | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-16 | 2025-11-16 | 2025-10-16 | 2025-10-16 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-16 | 2025-11-16 | 2025-10-16 | 2025-10-16 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-16 | 2025-10-16 | 2025-11-16 | 2025-10-16 | 2025-10-16 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-09-30: 2025-10-16; 2025-09-30: 2025-11-16; 2025-09-30: 2025-10-16; 2025-10-08: 2025-10-16 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509260798-GCI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | CHEONG/SENG/WAH/7018000306
7308R_AD | Kg Lapasan | DU00006111152 | Sabah | Sabah | 6.233070 | 116.326819 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_112M_128QAM_676M. Site Impacted : 7308R & 7077K/S01749 NE_7308R 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. FE_7643A 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_112M_128QAM_676M. Site Impacted : 7308R & 7077K/S01749 NE_7308R 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_112M_128QAM_676M. Site Impacted : 7308R & 7077K/S01749 FE_7643A 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | XMC-3E | MAC | 18G | 18G_SP_1.2M(MAC) x1. | 18G_SP_0.6M(MAC) x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202509260812-GTSB
4578C_AD | Taman Sg Bakap | DU00006111153 | Northern | Penang | 5.237069 | 100.497144 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M. NE_4578C 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1 FE_4188A 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW New Link / Reroute | Current link required to reroute new FE_4234B/P00360 due to Old FE 4188A have space constraint issue. Redeploy equipment to new FE_4234B/P00360. ( Refer DU ID 4578C_HU_1) NE_4578C 1.Install 15G_DP_1.2M(MDD). 2.Install new RTN910A ,7_ISM8-2+0 (RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo for ant 1. 4.Create service cross connect and EPLA. 5.Migrate traffic to new 15G_2+0_28M. FE_4234B/P00360 1.Redeploy equipment 15G_2+0_28M link from FE 4188A to 4234B/P00360 2.Install 15G_DP_1.2M(MDD). 3.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by MSP team). 4.Install new XMC_5D , Sub A_Hi for ant 1. 5.Create service cross connect and EPLA. 6.Create New In Band DCN. 7.Enable GE1, ETH patching to Cisco Fiber port Gi 0/0/8. 8.Traffic migrate to new 15G_2+0_28M. | Current link required to reroute new FE_4234B/P00360 due to Old FE 4188A have space constraint issue. Redeploy equipment to new FE_4234B/P00360. ( Refer DU ID 4578C_HU_1) NE_4578C 1.Install 15G_DP_1.2M(MDD). 2.Install new RTN910A ,7_ISM8-2+0 (RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo for ant 1. 4.Create service cross connect and EPLA. 5.Migrate traffic to new 15G_2+0_28M. | Current link required to reroute new FE_4234B/P00360 due to Old FE 4188A have space constraint issue. Redeploy equipment to new FE_4234B/P00360. ( Refer DU ID 4578C_HU_1) FE_4234B/P00360 1.Redeploy equipment 15G_2+0_28M link from FE 4188A to 4234B/P00360 2.Install 15G_DP_1.2M(MDD). 3.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by MSP team). 4.Install new XMC_5D , Sub A_Hi for ant 1. 5.Create service cross connect and EPLA. 6.Create New In Band DCN. 7.Enable GE1, ETH patching to Cisco Fiber port Gi 0/0/8. 8.Traffic migrate to new 15G_2+0_28M. 9.Decom existing MW link. | XMC_5D | MDD | 15G | 1.2 | 1.2 | NWAVE | SQ202509260779-N-Wave // SQ202510310495-N-Wave | NWAVE | SQ202509260770-N-Wave // SQ202509260774-N-Wave // SQ202510160486-N-Wave | 2026-03-04 | 2026-03-04 | Completed | 2025-11-06 | 2025-12-07 | 2025-11-06 | 2025-11-26 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092458 |  | 2025-09-25 | 2025-09-29 | Completed | 2025-09-24 | 2025-09-25 | 2025-09-24 | 2025-09-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-06 | 2025-12-07 | 2025-11-06 | 2025-11-24 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-11-06 | 2025-12-07 | 2025-11-06 | 2026-02-04 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-11 | 2025-11-06 | 2025-12-07 | 2025-11-06 | 2026-02-12 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | 2025-09-30: 2025-11-06; 2025-09-30: 2025-12-07; 2025-09-30: 2025-11-06; 2025-10-08: 2025-11-12 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | CHEONG/SENG/WAH/7018000306
Q01596_EB_1 | QS50225_4_1-KGSRIARJUNA | DU00006111306 | Sarawak | Sarawak | 1.405430 | 110.323220 | [7 empty] | 00. Integrated/RFS Done | 10/1/2026 : Pending pointing 9/1/2026 : Cancel proceed due to team at site decom 13/1/2026 : Cutover done 20/12/2025 : Plan to do MW IDU Patching - Cancel proceed due to site down (RSL-97 existing) 19/12/2025 : Plan to do MW IDU Patching - Team at site Q00646 17/12/2025 : Plan to do MW IDU Patching - Cancel CRQ pending approval 16/12/2025 : Plan to do MW IDU Patching - Cancel proceed due to CRQ not approved 10/12/2025 : Plan to do MW IDU Patching - Cancel proceed | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | At FE: - Patching xC HW_RTN910A link Q01596-Q00132 to xD MW Link IDU 9414A POI Needed : No | [7 empty] | Trintel | SQ202512120299-Trintel | Trintel | SQ202512190093-Trintel | 2026-01-15 | 2026-01-14 | Completed | 2025-12-06 | 2025-12-08 | 2025-12-06 | 2025-12-08 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2025-11-27 | 2025-12-29 | Completed | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-12-29 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2026-01-10 | LAW KIM CHANG7667000035 | Trintel TI | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2026-01-19 | LAW KIM CHANG7667000035 | Trintel TI | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2026-01-17 | LAW KIM CHANG7667000035 | 2025-09-30: 2025-12-05; 2025-09-30: 2025-12-05; 2025-09-30: 2025-12-05; 2025-10-08: 2025-12-20 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202601210786-GCI
1085A | Pekan Meru | DU00003632645 | Central | Selangor | 3.137070 | 101.443357 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 11/6/2024 : Drop. Pass to MSP |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7014A | BUKITKELAPA | DU00003632646 | Sabah | Sabah | 6.892066 | 116.837584 |  |  |  |  | Drop/Cancel | Drop. Pass to MSP |  | 00. Site Out/Drop | Drop. Pass to MSP |  |  | 2x Fiber 1G 1330nm 40km Module 2x Fiber Patch Cord cable | Cancel / Drop | 1G IPRAN port reengineering at IBeam 7014A for RTN06 NE (7014A) at IBeam: 1) 1G port at GE0/2/2. 2) Insert new Fiber SFP module 1G SFP SM 1330 40km at port GE0/2/2. NE (7014) at new Huawei RTN 910A(RTN06): 1) Insert new Fiber SFP module 1G SFP SM 13300 40km at 8-EM6-5(Port 5). 3) Remove cascade between IDU RTN06 and RTN IDU07. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2777C | JBA Bukit Lipat TX Relocation | DU00003632647 | Central | Selangor | 3.021173 | 101.448501 |  |  | WK32-WK35 | AUG 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 16/8: D1: Cutover done. Post-CO T/Shooting WIP | TSS+TI | L1+ATP+PAC | 1x new suitable Fiber 1G SFP SM 1550 40km Module 1x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN reengineering at IBeam 2777C. FE (2777C) at IBeam: 1) Insert new Fiber SFP module 1G SF at new 1G port GE (GE0/5/6). 2) Re-patching existing Fiber patch cord cable to new 1G port (GE0/5/6). Impact sites: 3178B,1384H,1406H,1607B,1765H,2722B,3039M | [7 empty] | Datasco | SQ202411140206-Datasco | Datasco | SQ202408140506-Datasco | 2025-07-05 | 2025-07-03 | Completed | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071010 |  | 2024-07-11 | 2024-08-09 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-08-09 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-16 | 2024-08-31 | 2024-08-16 |  | NORSHAMSUDIN//BIN DAUD/7019000007 | Datasco TI | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-09-23 | NORSHAMSUDIN//BIN DAUD/7019000007 | Datasco TI | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-08-16 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-08-16 | NORSHAMSUDIN//BIN DAUD/7019000007 | 2025-09-30: 2024-08-16; 2025-09-30: 2024-08-31; 2025-09-30: 2024-08-16; 2025-10-08: 2024-08-16 |  |  | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202506050715-GTSB | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
1073A | KTM Padang Jawa | DU00003632648 | Central | Selangor | 3.052823 | 101.488887 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 11/6/2024 : Drop. Pass to MSP |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2715B | Kajang Prima WaterTank | DU00003632649 | Central | Selangor | 2.979738 | 101.809462 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4536A | Tasek Industrial RDD | DU00003632650 | Northern | Perak | 4.653460 | 101.109840 |  |  |  |  | RFS |  |  | 00. Integrated/RFS Done | 22/5: D1: Cutover done | TSS+TI | L1+ATP+PAC | 1x IDU 910A 2x Fiber 1G 1330nm 10km Module 2x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN port reengineering at IBeam 4536A for RTN01 NE (4563A) at IBeam: 1) 1G port at GE0/3/1. 2) Insert new Fiber SFP module 1G SFP SM 1330 10km at port GE0/3/1. NE (4536A) at new Huawei RTN 910A(RTN01 & New 910A): 1) Install new IDU 910A. Reengineering link 4996C-4536A from RTN01 to new IDU 910A. 1) Insert new Fiber SFP module 1G SFP SM 13300 10km at 8-EM6-5(Port 5). Impact sites: 4996C,4264H | [7 empty] | GCI | SQ202407010442-GCI | GCI | SQ202407020120-GCI | 2024-11-28 | 2024-11-28 | Completed | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24051901 |  | 2024-05-20 | 2024-05-21 | Completed | 2024-05-19 | 2024-05-20 | 2024-05-19 | 2024-05-21 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-21 | 2024-05-31 | 2024-05-21 | 2024-05-29 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-05-21 | 2024-05-31 | 2024-05-21 | 2024-05-29 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-05-21 | 2024-05-31 | 2024-05-21 | 2024-06-05 | team21gcitechnicalteam21gcitechnical | 2025-09-30: 2024-05-21; 2025-09-30: 2024-05-31; 2025-09-30: 2024-05-21; 2025-10-08: 2024-05-22 |  |  | 2024-11-16 | 2024-12-16 | 2024-11-16 | 2024-11-16 | ASTI//GANIS PUTRIANI/6237001358
1122A | Jenjarum | DU00003632651 | Central | Selangor | 2.865711 | 101.508320 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 11/6/2024 : Drop. Pass to MSP |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4448B | Blue Valley | DU00003632652 | Northern | Pahang | 4.594540 | 101.432920 |  |  |  | JUN 24 |  |  |  | 00. Integrated/RFS Done | 21/6: D1: Cutover done | TSS+TI | L1+ATP+PAC | 1x IDU 910A 2x Fiber 1G 1330nm 10km Module 2x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN port reengineering at IBeam 4448B for RTN04 NE (4448B) at IBeam: 1) 1G port at GE0/3/4. 2) Insert new Fiber SFP module 1G SFP SM 1330 10km at port GE0/3/4. NE (4448B) at new Huawei RTN 910A(RTN04 & New 910A): 1) Install new IDU 910A. Reengineering link 4065D-4448B from RTN04 to new IDU 910A. 1) Insert new Fiber SFP module 1G SFP SM 13300 10km at 8-EM6-5(Port 5). Impact sites: 4065D | [7 empty] | GCI | SQ202407010442-GCI | GCI | SQ202409100506-GCI | 2024-11-28 | 2024-11-28 | Completed | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24051902 |  | 2024-05-20 | 2024-05-21 | Completed | 2024-05-19 | 2024-05-20 | 2024-05-19 | 2024-05-21 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-06-21 | 2024-06-28 | 2024-06-21 | 2024-07-10 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2024-06-21 | 2024-06-28 | 2024-06-21 | 2024-07-17 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-13 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-06-21 | 2024-06-28 | 2024-06-21 | 2024-06-23 | JUTI//ANAK RICHARD/6800000216 | 2025-09-30: 2024-06-21; 2025-09-30: 2024-06-28; 2025-09-30: 2024-06-21; 2025-10-08: 2024-07-11 |  |  | 2024-11-16 | 2024-12-16 | 2024-11-16 | 2024-11-16 | ASTI//GANIS PUTRIANI/6237001358
4273A | Kepala Batas 2 | DU00003632653 | Northern | Penang | 5.498550 | 100.432710 |  |  | WK32-WK35 | AUG 24 | Planning |  |  | 00. Integrated/RFS Done | 20/8: D1: Cutover done. Post-CO T/shooting WIP | TSS+TI | L1+ATP+PAC | 1x new suitable Fiber 1G SFP SM 1550 40km Module 1x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN reengineering at IBeam 4273A. FE (4273A) at IBeam: 1) Insert new Fiber SFP module 1G SF at new 1G port GE (GE0/3/0). 2) Re-patching existing Fiber patch cord cable to new 1G port (GE0/3/0). Impact sites: 4632A,4945A | [7 empty] | GCI | SQ202410010446-GCI | GCI | SQ202409070069-GCI | 2024-11-28 | 2024-11-28 | Completed | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2024-09-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2024-09-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071007 |  | 2024-07-11 | 2024-08-17 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-08-17 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-09-04 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-08-30 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-09-20 | HIMAN//BIN ADAM/6800000183 | 2025-09-30: 2024-08-16; 2025-09-30: 2024-08-31; 2025-09-30: 2024-08-16; 2025-10-08: 2024-08-17 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402
2631A | Samarinda | DU00003632654 | Central | Selangor | 3.026252 | 101.473680 |  |  | WK36-40 | SEP 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 11/9: Cutover done 5/9: Collection done, pending CRQ approval - rejected by CAB. Plan W37 10/9 | TSS+TI | L1+ATP+PAC | 4x new suitable Fiber 1G SFP SM 1550 40km Module 4x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN reengineering at IBeam 2631A from GE0/5/5 to GE0/3/0 & GE0/3/1. Required 1G+1G LAG configuration. At Huawei IDU 2631A RTN04, Re-patching existing Fiber patch cord cable to 8-EM6-1 & 8-EM6-2. Required 1G+1G LAG configuration. Impact sites: 1387H,3063M,3656B,3041C | [7 empty] | MTK | SQ202409251045-MTK | MTK | SQ202409020182-MTK | 2025-01-03 | 2025-01-02 | Completed | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-30 | 2024-12-31 | 2024-12-30 | 2024-12-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-12-30 | 2024-12-31 | 2024-12-30 | 2024-12-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-01-02 | 2025-01-03 | 2025-01-02 | 2025-01-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24082734 |  | 2024-08-28 | 2024-08-29 | Completed | 2024-08-27 | 2024-08-28 | 2024-08-27 | 2024-08-29 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-11 | 2024-10-08 | 2024-09-11 | 2024-10-08 | MUHAMMAD HAFIZUL/BIN/MAT RUDIN/8225000018 | MTK TI | 2024-09-11 | 2024-10-08 | 2024-09-11 | 2024-10-08 | MUHAMMAD HAFIZUL/BIN/MAT RUDIN/8225000018 | MTK TI | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-09-13 | SHUJAAT//ALI/6800000124 |  |  | 2024-09-11 | 2024-10-01 | 2024-09-11 | 2024-09-25 | MUHAMMAD HAFIZUL/BIN/MAT RUDIN/8225000018 | 2025-09-30: 2024-09-11; 2025-09-30: 2024-10-01; 2025-09-30: 2024-09-11; 2025-10-08: 2024-09-12 |  |  | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358
1099A | Hong Fatt Auto | DU00003632655 | Central | Selangor | 3.111114 | 101.442775 |  | JUN 24 |  | JUN 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 12/6: D2: Continue TI 11/6: D1: MOS & TI WIP | TSS+TI | L1+ATP+PAC | 2x Fiber 1G 1330nm 40km Module 2x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN port reengineering at IBeam 1099A for RTN04 NE (1099A) at IBeam: 1) 1G port at GE0/5/5. 2) Insert new Fiber SFP module 1G SFP SM 1330 40km at port GE0/1/1. NE (1099A) at new Huawei RTN 910A(RTN04): 1) Insert new Fiber SFP module 1G SFP SM 13300 40km at 8-EM6-5(Port 5). 3) Remove cascade between IDU RTN04 and RTN IDU03. | [7 empty] | Datasco | SQ202411140206-Datasco | Datasco | SQ202407050171-Datasco |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24051557 |  | 2024-05-16 | 2024-05-18 | Completed | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-05-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-06-11 | 2024-07-31 | 2024-06-11 |  | TAN//SWEE LOON/7019000028 | Datasco TI | 2024-06-11 | 2024-07-31 | 2024-06-11 | 2024-09-23 | TAN//SWEE LOON/7019000028 | Datasco TI | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-12 | SHUJAAT//ALI/6800000124 |  |  | 2024-06-11 | 2024-07-31 | 2024-06-11 | 2024-06-12 | TAN//SWEE LOON/7019000028 | 2025-09-30: 2024-06-11; 2025-09-30: 2024-07-31; 2025-09-30: 2024-06-11; 2025-10-08: 2024-06-11 |  |  | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
4689A | Taman Desa Impian | DU00003632656 | Northern | Kedah | 5.349378 | 100.533908 | [7 empty] | 00. Integrated/RFS Done | 19/6: D1: Cutover done 13/6:D1: Replan MOS & TI. EB CRQ for NE site pending approval | TSS+TI | L1+ATP+PAC | 1x IDU 910A 2x Fiber 1G 1330nm 40km Module 2x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN port reengineering at IBeam 4689A for RTN02 NE (4689A) at IBeam: 1) 1G port at GE0/1/7. 2) Insert new Fiber SFP module 1G SFP SM 1330 40km at port GE0/1/7. NE (4689A) at new Huawei RTN 950(RTN02: 1) Install new IDU 910A. Reengineering link 4960C-4689A to new IDU 910A. 1) Insert new Fiber SFP module 1G SFP SM 13300 40km at 8-EM6-5(Port 5). Impact site: 4960C | [7 empty] | GCI | SQ202407010442-GCI | GCI | SQ202407020120-GCI | 2024-11-28 | 2024-11-28 | Completed | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24060619 |  | 2024-06-07 | 2024-06-11 | Completed | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-06-11 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-06-13 | 2024-06-30 | 2024-06-12 | 2024-08-08 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2024-06-13 | 2024-09-30 | 2024-06-12 | 2024-09-23 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-19 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-06-13 | 2024-06-30 | 2024-06-12 | 2024-06-20 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2025-09-30: 2024-06-13; 2025-09-30: 2024-06-30; 2025-09-30: 2024-06-12; 2025-10-08: 2024-06-19 |  |  | 2024-11-16 | 2024-12-16 | 2024-11-16 | 2024-11-16 | ASTI//GANIS PUTRIANI/6237001358
1364B | Subang Bestari(Maxis) | DU00003632657 | Central | Selangor | 3.186100 | 101.543800 |  |  |  | MAY 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 12/6: Rectification work for divert traffic 31/5: D1: Cutover done 20/5: Collection done, MOS & TI In Plan | TSS+TI | L1+ATP+PAC | 2x Fiber 1G 1330nm 40km Module 2x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN port reengineering at IBeam 1364B for RTN14 NE (1364B) at IBeam: 1) 1G port at GE0/3/0. 2) Insert new Fiber SFP module 1G SFP SM 1330 40km at port GE0/3/0. NE (1364B) RTN 910A(RTN14): 1) Insert new Fiber SFP module 1G SFP SM 13300 40km at 8-EM6-5(Port 5). 3) Remove cascade between IDU RTN14 and RTN IDU04. | [7 empty] | Datasco | SQ202411140206-Datasco | Datasco | SQ202407050171-Datasco |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24051558 |  | 2024-05-16 | 2024-05-18 | Completed | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-05-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-31 | 2024-05-31 | 2024-05-31 |  | TAN//SWEE LOON/7019000028 | Datasco TI | 2024-05-31 | 2024-09-30 | 2024-05-31 | 2024-09-23 | TAN//SWEE LOON/7019000028 | Datasco TI | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-12 | SHUJAAT//ALI/6800000124 |  |  | 2024-05-31 | 2024-05-31 | 2024-05-31 | 2024-06-01 | TAN//SWEE LOON/7019000028 | 2025-09-30: 2024-05-31; 2025-09-30: 2024-05-31; 2025-09-30: 2024-05-31; 2025-10-08: 2024-05-31 |  |  | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
7625A | Kalabakan Town | DU00003632658 | Sabah | Sabah | 4.441353 | 117.480318 |  |  |  |  | Drop/Cancel | Drop. Pass to MSP |  | 00. Site Out/Drop | Drop. Pass to MSP |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | HSU//MYET CHAE/6799000011
1458A | Endah Parade | DU00003632659 | Central | Kuala Lumpur | 3.063580 | 101.695559 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  | At CP(1458A) 1) 2xsuitable Fiber 10G SFP SM 1550 40km Module. 2) 2xsuitable Fiber Patch Cord cable required. | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2536A | Centro IB | DU00003632660 | Central | Selangor | 3.052112 | 101.462886 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 11/6/2024 : Drop. Pass to MSP |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1110A | Berjaya Industrial Park | DU00003632661 | Central | Selangor | 2.983918 | 101.513484 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  | 2x 10G SFP SM 1550 40km Module 2x Fiber Patch Cord cable | Cancel / Drop | 10G IPRAN port upgrade at IBeam 1110A and RTN01 at 1249B. FE (1110A) at IBeam: 1) Insert new Fiber SFP module 10G SFP SM 1550 40km at new 10G port GE0/2/2. 2)Re-patching existing Fiber patch cord cable to new 10G port GE0/2/2. NE (1249B) at Huawei RTN 910A(RTN01): 1) Insert new Fiber SFP module 10G SFP SM 1550 40km at 8-EM6-3(Port 3). 2) Re-patching existing Fiber patch cord cable to 8-EM6-3(Port 3). | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4276A | Sungai Dua 2 | DU00003632662 | Northern | Penang | 5.447447 | 100.426514 |  |  | WK32-WK35 | AUG 24 | Planning |  |  | 00. Integrated/RFS Done | 16/8: D1: Cutover done. Post-CO T/Shooting WIP | TSS+TI | L1+ATP+PAC | 1x new suitable Fiber 1G SFP SM 1550 40km Module 1x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN reengineering at IBeam 4276A. FE (4276A) at IBeam: 1) Insert new Fiber SFP module 1G SF at new 1G port GE (GE0/3/0). 2) Re-patching existing Fiber patch cord cable to new 1G port (GE0/3/0). Impact sites: 4059R,4272A | [7 empty] | GCI | SQ202409070068-GCI | GCI | SQ202409060591-GCI | 2024-11-29 | 2024-11-29 | Completed | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-09-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071008 |  | 2024-07-11 | 2024-08-17 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-08-17 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-08-27 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-08-27 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-08-16 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-08-17 | HIMAN//BIN ADAM/6800000183 | 2025-09-30: 2024-08-16; 2025-09-30: 2024-08-31; 2025-09-30: 2024-08-16; 2025-10-08: 2024-08-16 |  |  | 2024-11-16 | 2024-12-16 | 2024-11-16 | 2024-11-16 | ASTI//GANIS PUTRIANI/6237001358
9368A | Salim Road Sacofa | DU00003632663 | Sarawak | Sarawak | 2.267322 | 111.866617 |  |  |  |  | Planning | Drop. Pass to MSP |  | 00. Site Out/Drop | Drop. Pass to MSP |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | HSU//MYET CHAE/6799000011
4000A | MSC Prai | DU00003632664 | Northern | Penang | 5.379858 | 100.385358 |  |  | WK32-WK35 | AUG 24 |  |  |  | 00. Integrated/RFS Done | 22/8: D2: Cutover done. Post-CO T/shooting WIP 28/6: D1: Need additional cable LC-E2K & IDU RTN910A | TSS+TI | L1+ATP+PAC | 1x IDU 910A 2x Fiber 10G 1330nm 10km Module 2x Fiber Patch Cord cable | IDU-IPRAN | Tx SOW: 1G IPRAN port reengineering at IBeam 4000A-MAC(CX)-001 MSC Prai/GigabitEthernet0/2/0 NE (4000A) at IBeam: 1) 10G port at GE0/7/1 (4000A). 2) Insert new Fiber SFP module 10G SFP SM 1330 10km at port GE0/7/1 (4000A). FE: 1) Swap existing IDU 910A RTN01 4166A with new 910A IDU. Required 10G port connection. Impacted site: 4166A,4194B,4183B | [7 empty] | GCI | SQ202410010446-GCI | GCI | SQ202409070069-GCI | 2024-11-29 | 2024-11-29 | Completed | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24060617 |  | 2024-06-07 | 2024-06-27 | Completed | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-06-27 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-06-13 | 2024-06-30 | 2024-06-12 | 2024-08-27 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2024-06-13 | 2024-09-30 | 2024-06-12 | 2024-08-30 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-06-13 | 2024-06-30 | 2024-06-12 | 2024-09-20 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2025-09-30: 2024-06-13; 2025-09-30: 2024-06-30; 2025-09-30: 2024-06-12; 2025-10-08: 2024-08-22 |  |  | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358
1145A | Batang Kali | DU00003632665 | Central | Selangor | 3.466897 | 101.641404 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 11/6/2024 : Drop. Pass to MSP |  |  |  | Cancel / Drop | Same task as: 3726A-2435A MW IDU Patching at FE. Migrate MW Link 3726A-2435A to new xC PTN B00308. To propose new port at xC PTN B00308. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7628A | Kabogan Junction | DU00003632666 | Sabah | Sabah | 4.444532 | 118.611001 |  |  |  |  | Drop/Cancel | Drop. Pass to MSP |  | 00. Site Out/Drop | Drop. Pass to MSP |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | HSU//MYET CHAE/6799000011
1002A | Sri Murni | DU00003632667 | Central | Kuala Lumpur | 3.234415 | 101.661529 |  |  | WK22 | JUN 24 | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 5/6: Planner DROP (Seow info) 4/6: BoM ready, Pending DO |  |  | At CP(1002A) 1) 2xsuitable Fiber 10G SFP SM 1550 40km Module. 2) 2xsuitable Fiber Patch Cord cable required. | Cancel / Drop | 1) Insert new Fiber SFP module 1G SFP SM 1550 40k at new 1G port. 2) Lay new suitable Fiber patch cord cable and patching to new 1G port. | [7 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24060492 |  | 2024-06-05 | 2024-06-12 | Completed | 2024-06-04 | 2024-06-05 | 2024-06-04 | 2024-06-12 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed
1409A | Kota Damansara | DU00003632668 | Central | Selangor | 3.158529 | 101.573970 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 11/6/2024 : Drop. Pass to MSP |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1084A | Bt 5 3 | DU00003632669 | Central | Selangor | 3.087897 | 101.394641 |  |  |  | JUN 24 | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 10/6: Link Drop. SOW done by MSP |  |  | 1x IDU 910A 2x Fiber 1G SFP SM 1550 40km Module 2x Fiber Patch Cord cable | Cancel / Drop | 1) Insert new Fiber SFP module 1G SFP SM 1550 40k at new 1G port GE0/2/6. 2) Lay new suitable Fiber patch cord cable and patching to new 1G port GE0/2/6. NE (1084A) at new RTN 910AF(RTN03): 1) Install new RTN910AF(RTN03) and configure it. 2) Insert new Fiber SFP module 1G SFP SM 1550 40k at 8-EM6-3(Port 3). 3) Patching other end of new Fiber patch cord cable to 8-EM6-3(Port 3). 4) Shifting existing IF cable for MW Link 1084A<--1010C from RTN01 slot 4 to new RTN03 slot 7 port 1. | [9 empty] | Datasco | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24051559 |  | 2024-05-16 | 2024-05-18 | Completed | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-05-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed
1701A | Kerling (Trunk) | DU00003632670 | Central | Selangor | 3.583226 | 101.610391 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  | At CP(1701A) 1) 2xsuitable Fiber 10G SFP SM 1550 40km Module. 2) 2xsuitable Fiber Patch Cord cable required. | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4374A | LAP Talang RDD | DU00003632671 | Northern | Perak | 4.779051 | 100.919286 |  |  | WK32-WK35 | AUG 24 | Planning |  |  | 00. Site Out/Drop | 26/8: MSP feedback no PL |  |  | 2x new suitable Fiber 1G SFP SM 1550 40km Module 2x Fiber Patch Cord cable | Cancel / Drop | Found at IBeam 4374A already got 1G+1G LAG Config. FE (4372B): 1) Required re-engineering port from SIAE IDU to HUAWEI IDU for 1G+1G LAG Config. 2) Insert new 2x Fiber SFP module 1G+1G SF at new 1G port GE (Port to be advised by IPRAN team). 3) Re-patching existing Fiber patch cord cable to new 1G port (Port to be advised by IPRAN team). 4) Configure Huawei IDU for LAG config. Impact sites: 4372B,4371B,4438B,4152H,4019R,4017R | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24071009 |  | 2024-07-11 | 2024-08-17 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-08-17 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-16 | 2024-08-31 | 2024-08-16 |  | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-08-16 | 2024-08-31 | 2024-08-16 |  | team21gcitechnicalteam21gcitechnical | GCI TI | [7 empty] | 2024-08-16 | 2024-08-31 | 2024-08-16 |  | team21gcitechnicalteam21gcitechnical | 2025-09-30: 2024-08-16; 2025-09-30: 2024-08-31; 2025-09-30: 2024-08-16; 2025-10-08: 2024-08-16
4241A | Juru Tower | DU00003632672 | Northern | Penang | 5.315704 | 100.432916 |  | JUN 24 |  | JUN 24 |  |  |  | 00. Site Out/Drop | 21/6: Link Drop. SOW done by MSP |  |  | 1x new suitable Fiber 1G SFP SM 1550 40km Module 1x Fiber Patch Cord cable | Cancel / Drop | 1G IPRAN port reengineering at IBeam 4241A for RTN01 NE (4241A) at IBeam: 1) 1G port at GE0/3/3. 2) Insert new Fiber SFP module 1G SFP SM 1330 40km at port GE0/3/3. Impact sites: 4085B,4187D,4260E | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24052489 |  | 2024-05-25 | 2024-05-28 | Completed | 2024-05-24 | 2024-05-25 | 2024-05-24 | 2024-05-28 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-06-21 | 2024-06-28 | 2024-06-21 |  | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-06-21 | 2024-09-30 | 2024-06-21 |  | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | [7 empty] | 2024-06-21 | 2024-06-28 | 2024-06-21 |  | ANWAR//BIN ABDUL RASID/6800000149 | 2025-09-30: 2024-06-21; 2025-09-30: 2024-06-28; 2025-09-30: 2024-06-21; 2025-10-08: 2024-06-21
4241A_IPR | Juru Tower | DU00006499461 | Northern | Penang | 5.315704 | 100.432916 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X PATCH CORD | MW IDU Patching | Perform LAG at CP site for IDU 4241A-JURU TOWER-RTN04 to 4241A-MAC-001 Juru Tower 1) Patch IDU 4241A RTN04 GE2 to new CP port 2) Create LAG 3) Impact sites: 4292C | Perform LAG at CP site for IDU 4241A-JURU TOWER-RTN04 to 4241A-MAC-001 Juru Tower 1) Patch IDU 4241A RTN04 GE2 to new CP port 2) Create LAG 3) Impact sites: 4292C | [6 empty] | GTSB | SQ202601130151-GTSB | GTSB | SQ202601130146-GTSB | 2026-01-31 | 2026-01-27 | Completed | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-22 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Completed |  | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-01-28 | 2026-01-27 | 2026-01-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-01-28 | 2026-01-27 | 2026-01-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010603 |  | 2026-01-07 | 2026-01-10 | Completed | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-17 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-17 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-16 | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-17 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-09-30: 2026-01-14; 2025-09-30: 2026-01-31; 2025-09-30: 2026-01-14; 2025-10-08: 2026-01-16 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601070319-GCI | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
4939C_IPR | WismaGanda RT | DU00006499462 | Northern | Perak | 4.215874 | 100.695958 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_4939C New CAT6 cable with suitable length(IDU HW to IBeam) x1. New SFP Module 1.25G/1G 1310nm 10Km x2.(For IDU Huawei & IBeam) New Optical Patchcord with suitable type and length x1. | MW IDU Patching | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 4939C_IPR 2ND - DU 4457C_HU_1. 3RD - DU 4457C_HU_2**** Perform 3+0 LAG for 3x port(1x existing & 2x new) of HW IDU & IBeam. Site Impacted: 4412D. NE_4939C 1.Enable port 8-EM6-2 of existing RTN910AF(RTN04, NEID 9-28194). 2.Enable port 8-EM6-5 of existing RTN910AF(RTN04, NEID 9-28194). 3.Insert new SFP Module 1.25G/1G 1310nm 10Km x1 into 8-EM6-5 of existing RTN910AF(RTN04, NEID 9-28194). 4.Request 2x new IBeam port in which 1x Electrical port and 1x Optical port from ZTE IPRAN Team. 5.Insert new SFP Module 1.25G/1G 1310nm 10Km x1 into new IBeam Optical port. 6.Patching port 8-EM6-2 of existing RTN910AF(RTN04, NEID 9-28194) to new IBeam Electrical port. 7.Patching port 8-EM6-5 of existing RTN910AF(RTN04, NEID 9-28194) to new IBeam Optical port. 8.Create LAG 3+0 between 3xport(1x existing & 2x new) of IDU-IBeam. 9.Traffic 4412D will backhaul into 3x LAG of IDU-IBeam. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 4939C_IPR 2ND - DU 4457C_HU_1. 3RD - DU 4457C_HU_2**** Perform 3+0 LAG for 3x port(1x existing & 2x new) of HW IDU & IBeam. Site Impacted: 4412D. NE_4939C 1.Enable port 8-EM6-2 of existing RTN910AF(RTN04, NEID 9-28194). 2.Enable port 8-EM6-5 of existing RTN910AF(RTN04, NEID 9-28194). 3.Insert new SFP Module 1.25G/1G 1310nm 10Km x1 into 8-EM6-5 of existing RTN910AF(RTN04, NEID 9-28194). 4.Request 2x new IBeam port in which 1x Electrical port and 1x Optical port from ZTE IPRAN Team. 5.Insert new SFP Module 1.25G/1G 1310nm 10Km x1 into new IBeam Optical port. 6.Patching port 8-EM6-2 of existing RTN910AF(RTN04, NEID 9-28194) to new IBeam Electrical port. 7.Patching port 8-EM6-5 of existing RTN910AF(RTN04, NEID 9-28194) to new IBeam Optical port. 8.Create LAG 3+0 between 3xport(1x existing & 2x new) of IDU-IBeam. 9.Traffic 4412D will backhaul into 3x LAG of IDU-IBeam. | [6 empty] | GTSB | SQ202601130151-GTSB | GTSB | SQ202601130146-GTSB | 2026-03-02 | 2026-02-23 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-13 | 2026-02-20 | 2026-02-13 | 2026-02-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010604 |  | 2026-01-07 | 2026-01-10 | Completed | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-14 | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-17 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-09-30: 2026-01-12; 2025-09-30: 2026-01-31; 2025-09-30: 2026-01-12; 2025-10-08: 2026-01-13 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601070337-GTSB
4457C_HU_1 | PekanGurney | DU00006499463 | Northern | Perak | 4.224830 | 100.738505 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_4457C New CAT6 cable x1. | BBU Patching | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 4939C_IPR 2ND - DU 4457C_HU_2. 3RD - DU 4457C_HU_1**** Site Impacted :4457C. NE_4457C 1.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-41694). 2.Patching existing BBU 4457C to port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-41694). 3.Request new xD Vlan Services. 4.Divert traffic 4457C from xC A00110 to xD CP 4939C via existing HW MW Link 4457C(RTN01, NEID 9-41694)-4939C(RTN02, NEID 9-41839) 15G_4+0_28MHZ_512QAM_EPLA_896M. FE_4939C 1.Port 8-EM6-1 and 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-41839) already enable and UP and connected to 2x existing IBeam port(2+0 LAG). 2.Therefore, request new xD Vlan Services with regards to 2x existing IBeam port(2+0 LAG). 3.Divert traffic 4457C from xC A00110 to xD CP 4939C via existing 2+0 LAG existing port of IBeam. | 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 4939C_IPR 2ND - DU 4457C_HU_2. 3RD - DU 4457C_HU_1**** Site Impacted :4457C. NE_4457C 1.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-41694). 2.Patching existing BBU 4457C to port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-41694). 3.Request new xD Vlan Services. 4.Divert traffic 4457C from xC A00110 to xD CP 4939C via existing HW MW Link 4457C(RTN01, NEID 9-41694)-4939C(RTN02, NEID 9-41839) 15G_4+0_28MHZ_512QAM_EPLA_896M. | 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 4939C_IPR 2ND - DU 4457C_HU_2. 3RD - DU 4457C_HU_1**** Site Impacted :4457C. FE_4939C 1.Port 8-EM6-1 and 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-41839) already enable and UP and connected to 2x existing IBeam port(2+0 LAG). 2.Therefore, request new xD Vlan Services with regards to 2x existing IBeam port(2+0 LAG). 3.Divert traffic 4457C from xC A00110 to xD CP 4939C via existing 2+0 LAG existing port of IBeam. | [5 empty] | GTSB | SQ202601130151-GTSB | GTSB | SQ202601130146-GTSB | 2026-03-02 | 2026-02-23 | Completed | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-13 | 2026-02-20 | 2026-02-13 | 2026-02-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010605 |  | 2026-01-07 | 2026-01-10 | Completed | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-16 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-15 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-13 | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-17 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-09-30: 2026-01-12; 2025-09-30: 2026-01-31; 2025-09-30: 2026-01-12; 2025-10-08: 2026-01-13 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601070337-GTSB
4457C_HU_2 | PekanGurney | DU00006499464 | Northern | Perak | 4.224830 | 100.738505 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 18G_3+0_110M_512QAM_EPLA_2667M NE_4457C New RTN910AF(RTN03) New ISM8 x1. New IF cable x3 RUN with suitable type and length.(If existing IF cable short in length) Nre CAT6 cable x1. FE_4939C New ISM8 x1. New IF cable x1 RUN with suitable type and length.(If existing IF cable short in length) | MW Hardware Upgrade | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 4939C_IPR 2ND - DU 4457C_HU_2. 3RD - DU 4457C_HU_1**** To create HW MW Link HW 18G_3+0_110M_512QAM_EPLA. Site Impacted : 4412D NE_4457C 1.Install new RTN910AF(RTN03) and insert new ISM8 into slot 03. Configure it. 2.Perform cascading between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-28158) and port 8-EM6-1 of new RTN910AF(RTN03). 3.Shifting existing IF cable from slot 03 Port 1&2 of existing RTN910AF(RTN02, NEID 9-28158) to slot 07 Port 1&2 of new RTN910AF(RTN03). If IF cable length short, lay 2x new RUN IF cables from existing ODU to slot 07 Port 1&2 of new RTN910AF(RTN03). 4.At existing RTN910AF(RTN01, NEID 9-41694), break the EPLA between all(5+0) in which channel slot 07 Port 1 currently Main Port and create new 4+0 EPLA for existing HW MW Link 4457C(RTN01, NEID 9-41694)-4939C(RTN02, NEID 9-41839) from 18G&15G_5+0 to 15G_4+0. Use channel slot 03 Port 1 become Main Port for 15G_4+0 EPLA. 5.Later, shifting existing IF cable from slot 07 Port 1 of existing RTN910AF(RTN01, NEID 9-41694) to slot 03 Port 1 of new RTN910AF(RTN03). If existing IF cable length short, lay 1x new RUN IF cables from existing ODU to slot 03 Port 1 of new RTN910AF(RTN03). 6.Create new HW MW Link 4457C(new RTN03)-4939C(RTN04, NEID 9_28194),18G_3+0_110M_512QAM_EPLA. FE_4939C 1.Insert new ISM8 card into slot 03 of existing RTN910AF(RTN04, NEID 9-28194). 2.At existing RTN910AF(RTN02, NEID 9-41839), break the EPLA between all(5+0) in which channel slot 07 Port 1 currently Main Port and create new 4+0 EPLA for existing HW MW Link 4457C(RTN01, NEID 9-41694)-4939C(RTN02, NEID 9-41839) from 18G&15G_5+0 to 15G_4+0. Use channel slot 03 Port 1 become Main Port for 15G_4+0 EPLA. 3.Later, shifting existing IF cable from slot 07 Port 1 of existing RTN910AF(RTN02, NEID 9-41839) to slot 03 Port 1 of existing RTN910AF(RTN04, NEID 9_28194). If existing IF cable length short, lay 1x new RUN IF cables from existing ODU to slot 03 Port 1 of existing RTN910AF(RTN04, NEID 9_28194). 4.Create new HW MW Link 4457C(new RTN03)-4939C(RTN04, NEID 9_28194),18G_3+0_110M_512QAM_EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 4939C_IPR 2ND - DU 4457C_HU_2. 3RD - DU 4457C_HU_1**** To create HW MW Link HW 18G_3+0_110M_512QAM_EPLA. Site Impacted : 4412D NE_4457C 1.Install new RTN910AF(RTN03) and insert new ISM8 into slot 03. Configure it. 2.Perform cascading between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-28158) and port 8-EM6-1 of new RTN910AF(RTN03). 3.Shifting existing IF cable from slot 03 Port 1&2 of existing RTN910AF(RTN02, NEID 9-28158) to slot 07 Port 1&2 of new RTN910AF(RTN03). If IF cable length short, lay 2x new RUN IF cables from existing ODU to slot 07 Port 1&2 of new RTN910AF(RTN03). 4.At existing RTN910AF(RTN01, NEID 9-41694), break the EPLA between all(5+0) in which channel slot 07 Port 1 currently Main Port and create new 4+0 EPLA for existing HW MW Link 4457C(RTN01, NEID 9-41694)-4939C(RTN02, NEID 9-41839) from 18G&15G_5+0 to 15G_4+0. Use channel slot 03 Port 1 become Main Port for 15G_4+0 EPLA. 5.Later, shifting existing IF cable from slot 07 Port 1 of existing RTN910AF(RTN01, NEID 9-41694) to slot 03 Port 1 of new RTN910AF(RTN03). If existing IF cable length short, lay 1x new RUN IF cables from existing ODU to slot 03 Port 1 of new RTN910AF(RTN03). 6.Create new HW MW Link 4457C(new RTN03)-4939C(RTN04, NEID 9_28194),18G_3+0_110M_512QAM_EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 4939C_IPR 2ND - DU 4457C_HU_2. 3RD - DU 4457C_HU_1**** To create HW MW Link HW 18G_3+0_110M_512QAM_EPLA. Site Impacted : 4412D FE_4939C 1.Insert new ISM8 card into slot 03 of existing RTN910AF(RTN04, NEID 9-28194). 2.At existing RTN910AF(RTN02, NEID 9-41839), break the EPLA between all(5+0) in which channel slot 07 Port 1 currently Main Port and create new 4+0 EPLA for existing HW MW Link 4457C(RTN01, NEID 9-41694)-4939C(RTN02, NEID 9-41839) from 18G&15G_5+0 to 15G_4+0. Use channel slot 03 Port 1 become Main Port for 15G_4+0 EPLA. 3.Later, shifting existing IF cable from slot 07 Port 1 of existing RTN910AF(RTN02, NEID 9-41839) to slot 03 Port 1 of existing RTN910AF(RTN04, NEID 9_28194). If existing IF cable length short, lay 1x new RUN IF cables from existing ODU to slot 03 Port 1 of existing RTN910AF(RTN04, NEID 9_28194). 4.Create new HW MW Link 4457C(new RTN03)-4939C(RTN04, NEID 9_28194),18G_3+0_110M_512QAM_EPLA. |  |  | 18G |  |  | GTSB | SQ202601130151-GTSB | GTSB | SQ202601130143-GTSB // SQ202601130146-GTSB |  |  | Ongoing | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-30 | 2026-04-04 | 2026-03-30 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-21 | 2026-04-14 | 2026-04-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010606 |  | 2026-01-07 | 2026-01-10 | Completed | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-14 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-14 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-19 | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-02-23 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-09-30: 2026-01-12; 2025-09-30: 2026-01-31; 2025-09-30: 2026-01-12; 2025-10-08: 2026-01-13 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601070337-GTSB
9125A_IPR_1 | Bkt Tunggong | DU00006509051 | Sarawak | Sarawak | 3.048315 | 112.936752 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module x2 Fiber Patch Cord x 1 Pairs. | MW IDU Patching | Upgrade 9125A-RHCHABI-RTN01 patching to LL port from 1G to 10G | Upgrade 9125A-RHCHABI-RTN01 patching to LL port from 1G to 10G | [6 empty] | Trintel | SQ202601210184-Trintel | Trintel | SQ202601210180-Trintel |  |  | Ongoing | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26011214 |  | 2026-01-13 | 2026-01-16 | Completed | 2026-01-12 | 2026-01-13 | 2026-01-12 | 2026-01-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-23 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-26 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-24 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2025-09-30: 2026-01-22; 2025-09-30: 2026-01-22; 2025-09-30: 2026-01-22; 2025-10-08: 2026-01-23 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202601070323-GCI | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | CHEONG/SENG/WAH/7018000306
7655B-7194A | HOSPITAL TAWAU RT | DU00003549986 | Sabah | Sabah | 4.250341 | 117.879100 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | HSU//MYET CHAE/6799000011
4648D-4597A | Taman Lagenda Teluk Intan | DU00003549987 | Northern | Perak | 3.948296 | 101.036900 |  |  |  | AUG 24 | Planning | Pending BOQ Solution | ZTE | 00. Integrated/RFS Done | 20/8: D2: Cutover done. Post-CO T/shooting WIP 19/8: MOS & Pre-installation WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1) 1 x XMC3E sub B Hi FE: 1) 1 x RTN910A 2) 1 x XMC3E sub B Lo | MW Hardware Upgrade | Existing link 4648D-4597A 1+0 56MHz (4648D RTN01-4597A RTN03) 1) To replace ODU with XMC3E 2) To upgrade link to 112MHz 3) To install new IDU at FE site Impact site: 4648D NE (4648D RTN01) 1. Replace ODU with new XMC3E 2. Upgrade link to 112MHz FE (4597A new RTN) 1. Install new RTN910A (ops team to assign RTN number) 2. Transfer IF cable from RTN03 3-ISM8-1 to new RTN 7-ISM8-1 3. Replace ODU with new 112MHz ODU 4. Upgrade link to 112MHz 5. Patch new IDU to new CP port. Migrate traffic to new link and created DCN | [7 empty] | CCSMY | SQ202408220933-CCS | CCSMY | SQ202408150340-CCS | 2024-11-26 | 2024-11-26 | Completed | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240806AC |  | 2024-08-07 | 2024-08-15 | Completed | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-08-15 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-19 | 2024-08-31 | 2024-08-19 | 2024-08-21 | Usman MUMTAZ7021000053 | CCS TI | 2024-08-19 | 2024-08-31 | 2024-08-19 | 2024-08-21 | Usman MUMTAZ7021000053 | CCS TI | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-08-19 | 2024-08-31 | 2024-08-19 | 2024-09-07 | Usman MUMTAZ7021000053 | 2024-08-19 | 2024-08-31 | 2024-08-19 | 2024-08-19 | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | NG HONG JIE7018000036 | Logistic Team | 2024-10-16 | 2024-11-16 | 2024-10-16 | 2024-10-16 | ASTI//GANIS PUTRIANI/6237001358
3475C-7227A | pBTS D Sri Gayang (KM) | DU00003549988 | Sabah | Sabah | 6.113757 | 116.151300 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | HSU//MYET CHAE/6799000011
7675B-7194A | Taman Semarak | DU00003549989 | Sabah | Sabah | 4.290434 | 117.893200 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | Pass to Huawei and current link util: 47.84% | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | AB.RAHMAN//BIN MAT NOOH/6237001519
7271B-7039A | Taman Penampang Phase 4 | DU00003549990 | Sabah | Sabah | 5.928278 | 116.101200 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | 9-July'25: Link pass to Huawei and current util 52.7% | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | AB.RAHMAN//BIN MAT NOOH/6237001519
4197C-4952B | Kg Batu 6 Ulu Selama Perak | DU00003549991 | Northern | Perak | 5.293581 | 100.739200 |  |  |  | AUG 24 | Planning | Pending BOQ Solution | ZTE | 00. Integrated/RFS Done | 20/9: Cutover done 12/9: D3: Team on site, no power TNB. Activity Postponed 9/9: Continue TI with new solution 4/9: New DO & DR released. Proceed with material collection 29/8: Revise solution. Proceed upgrade 4+0 use MDD antenna at existing location 23/8: D2: TI done, LOS issue. RSL not meet expected | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G 4+0 CA 1.8m/1.8m NE: 1) 2xISM8 card 2) 1x13GHz XMC5D Sub A Lo 3) 1x13GHz 1.8m MDD FE: 1) 1xISM8 card 2) 1x13GHz XMC5D Sub A Hi 3) 1x13GHz 1.8m MDD | MW Swap | *change solution from parallel to swap due to no space for additional antenna at 4952B Existing link 4197C-4952B 2+0 (4197C RTN02-4952B RTN05) Swap existing 2+0 link with 4+0 CA Impact sites: 4197C,4151R,4132R NE (4197C) 1. Add ISM8 card at RTN03 slot 3 and 4 2. Install new 4+0 CA link at RTN03 3-ISM8 and 4-ISM8 3. Swap existing DP antenna with new MDD antenna 4. Configure new link 4+0 CA. 5. Transfer 4197C BBU from RTN02 GE1 to RTN03 GE2 6. Re-configure service to go through 4197C RTN03-4952B RTN05 FE (4952B RTN05) 1. Add ISM8 card slot 4 2. Swap existing DP antenna with new MDD antenna 3. Install new 4+0 CA link at RTN05 3-ISM8 and 4-ISM8 4. Configure new link 4+0 CA. 5. Migrate traffic to new link. Remain existing CP port | [7 empty] | CCSMY | SQ202408220933-CCS | CCSMY | SQ202409060588-CCS | 2025-12-17 | 2025-12-16 | Completed | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-06 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240814AG |  | 2024-08-15 | 2024-09-06 | Completed | 2024-08-14 | 2024-08-15 | 2024-08-14 | 2024-09-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-20 | 2024-08-31 | 2024-08-20 | 2024-12-05 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2024-08-20 | 2024-08-31 | 2024-08-20 | 2024-12-05 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-08-20 | 2024-08-31 | 2024-08-20 | 2024-10-07 | MUHAMMAD//MUZAMMAL/7021000054 | 2024-08-20 | 2024-08-31 | 2024-08-20 |  | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | NG HONG JIE7018000036 | Logistic Team | 2024-10-16 | 2024-11-16 | 2024-10-16 | 2024-10-16 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050701-GCI | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | EZRIN TASNIM BIN ABDUL GANI6798000128
3887A-1085A | Tmn Mesra Jln Meru | DU00003549992 | Central | Selangor | 3.136355 | 101.446500 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 31/7: D1: Cutover done. Remote upgrade | AA | PAC | N/A | MW Remote Upgrade | Perform SW upgrade 112MHz and IS6 for 1) 3887A RTN03-1085A RTN01 (V) 2) 3887A RTN03-1085A RTN01 (H) Impact site: 3887A, 1475H, 3636A | [7 empty] | Allstar | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
9103A-9106A | Kg Sibiu | DU00003549993 | Sarawak | Sarawak | 3.166491 | 113.050000 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  | TSS |  |  | BBU Patching | BBU Patching to xD 9103A LL | [7 empty] | Trintel | SQ202409100111-Trintel |  |  | 2024-08-23 | 2024-08-19 | Completed | 2024-06-08 | 2024-06-08 | 2024-06-08 | 2024-06-08 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-06-12 | 2024-06-14 | 2024-06-12 | 2024-06-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-06-12 | 2024-06-14 | 2024-06-12 | 2024-06-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-19 | 2024-08-23 | 2024-08-19 | 2024-08-19 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3219B-2448A | Cheras Sentral IB | DU00004271744 | Central | Kuala Lumpur | 3.078548 | 101.744812 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop |  |  | Solution follow TX Roll out. | Cancel / Drop | Solution follow TX Roll out. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2843C-1851B | Masjid Bandar Rinching (REL) | DU00004261150 | Central | Selangor | 2.929054 | 101.846472 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 12/11: D3: Link ready, pending integration for 1770A_LOS 8/11: MOS & Pre-installation in progress 9/10: New intermediate link route for TX Mini 1770A_LOS | TSS+AA+TI | L1+ATP+PAC | Install parallel link 18G_2+0_112M due to for 3rd leg protection and 1G cap requirements. NE_2843C 1.Install new 18G_DP_0.6m(MDD) x1. 2.Install new 18G_XMC_5D, Sub_A_Hi x1. 3.Install new RTN910A x1. FE_1851B 1.Install new 18G_DP_0.6m.(MDD) x1. 2.Install new 18G_XMC_5D, Sub_A_Lo x1. 3.Install new RTN910A x1. | MW Parallel Link | Install parallel link 18G_2+0_112M due to for 3rd leg protection and 1G cap requirements. For 2843C , prioritize install this northbound parallel link (2843C-1851B) before making intermediate link connection for 1770A-2843C. NE_2843C 1.Install new 18G_DP_0.6m(MDD) 2.Install new 18G_XMC_5D-2+0 , Sub_A_Hi 3.Install new RTN910A, 7-ISM8-2+0.(RTN no provide by the MSP team). 4.Config 112M_2+0 5.Create EPLA and service cross connect. FE_1851B 1.Install new 18G_DP_0.6m.(MDD) 2.Install new 18G_XMC_5D-2+0 , Sub_A_Lo. 3.Install new RTN910A, 7_ISM8-2+0. 4.Config 112M_2+0. 5.Create EPLA and service cross connect. 6.Enable GE port 1 and Create new In-band DCN. | [7 empty] | GCI | SQ202411140211-GCI | GCI | SQ202411150539-GCI // SQ202504150088-GCI | 2024-12-05 | 2024-12-04 | Completed | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-27 | 2024-11-26 | 2024-11-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-12-04 | 2024-12-05 | 2024-12-04 | 2024-12-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24103020 |  | 2024-10-31 | 2024-11-05 | Completed | 2024-10-30 | 2024-10-31 | 2024-10-30 | 2024-11-05 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-08 | 2024-11-14 | 2024-11-07 | 2024-11-13 | MUHAMMAD//MUBEEN/6800000279 | GCI TI | 2024-11-08 | 2024-11-14 | 2024-11-07 | 2024-11-13 | MUHAMMAD//MUBEEN/6800000279 | GCI TI | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-11-08 | 2024-11-14 | 2024-11-07 | 2024-11-23 | MUHAMMAD//MUBEEN/6800000279 | 2025-09-30: 2024-11-08; 2025-09-30: 2024-11-14; 2025-09-30: 2024-11-07; 2025-10-08: 2024-11-08 |  |  | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
S00330-7604A | S00330_BUKIT TOWER_BUKIT RASUL | DU00004261151 | Sabah | Sabah | 5.158721 | 118.480627 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | New parallel link from the existing 8G_2+0_28Mhz and add a new 8G_2+0_28Mhz with EPLA to create a config 4+0. NE_S00330 1.Install new DP_2.4m(MS) x1. 2.Install new ISM8 x1. 3.Install 8G_XMC-3 , Sub_A_Lo x2. 4.Install waveguide for channel V & H x 2. FE_7604A 1.Install new DP_2.4m(MS) x1. 2.Install new ISM8 x1. 3.Install 8G_XMC-3, Sub A_Hi x2. 4.Install waveguide for channel V & H x2. | MW Parallel Link | Existing link 8G_2+0_28MHz New parallel link 8G_2+0_28Mhz with EPLA to create a config 4+0. NE_S00330 1.Install new 8G_DP_2.4m(MS). 2.Install new 3_ISM8-2+0 on existing RTN01 3.Install 8G_XMC-3_2+0 ,Sub_A,B_Lo 4.Install New waveguide for channel V & H. 5.Create EPLA to 4+0 links and service cross connect FE_7604A 1.Install new 8G_DP_2.4m. 2.Install new 8G_3_ISM8-2+0 on existing RTN01. 3.Install XMC-3_2+0 , Sub A,B_Hi. 4.Install waveguide for channel V & H. 5.Create EPLA to 4+0 links and service cross connect. | [7 empty] | NR services | SQ202502260432-NR Services | NR services | SQ202504080137-NR Services // SQ202504080147-NR Services | 2025-05-29 | 2025-05-29 | Completed | 2025-02-19 | 2025-02-24 | 2025-02-23 | 2025-02-23 | MUHD//KHAIRUL NIZAM/7023000104 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-11 | 2025-03-14 | 2025-03-11 | 2025-03-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-11 | 2025-03-14 | 2025-03-11 | 2025-03-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022497 |  | 2025-02-25 | 2025-02-26 | Completed | 2025-02-24 | 2025-02-25 | 2025-02-24 | 2025-02-26 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-19 | 2025-04-19 | 2025-03-19 | 2025-04-09 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-03-19 | 2025-04-19 | 2025-03-19 | 2025-04-09 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-20 | 2025-03-19 | 2025-04-19 | 2025-03-19 | 2025-04-21 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-09-30: 2025-03-19; 2025-09-30: 2025-04-19; 2025-09-30: 2025-03-19; 2025-10-08: 2025-03-22 |  |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GCI_AA | SQ202510300170-GCI | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | HSU//MYET CHAE/6799000011
2901A-2049B | Saujana Putra (Watertank) | DU00004293842 | Central | Selangor | 2.957096 | 101.582449 |  |  |  |  | Cancel / Drop | Inder TX Mini | ZTE | 00. Site Out/Drop | 6/3/2025 : SOW done under TX Mini BAU HU 2049B-2901A |  |  | Existing link 18G_2+0_56M. Remote software upgrade from 18G_2+0_56M to 18G_2+0_112M with 256QAM. | Cancel / Drop | Existing link 18G_2+0_56M Software upgrade to 18G_2+0_112M_256QAM from 2901A-2049B Same SOW and NE identifier with DU ID 2049B-2901A. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4398A-4391A | Bagan Tiang RDD | DU00004293843 | Northern | Perak | 5.111484 | 100.411399 |  |  | W49-52 | DEC 24 |  | Integrated/RFS | ZTE | 00. Integrated/RFS Done | 2/12: SOW done under TX NIC 4398A | TSS+AA+TI | L1+ATP+PAC | Install new parallel link for 13G_4+0_28M_CA. New parallel link 13G_4+0_28M_CA for 4979C. NE_4398A. 1.Install new 13G_DP_1.2m(MDD) x1. 2.Install new RTN910A x1 3.Install ISM8 x2. 4.Install new XMC_5D , Sub_B_Lo x1. FE_4391A. 1.Install new 13G_DP_1.2m(MDD) x1. 2.Install new RTN910A x1. 3.Install ISM8 x2. 4.Install new XMC_5D , Sub_B_Hi x1. | MW Parallel Link | Install new parallel link for 13G_4+0_28M_CA. New parallel link 13G_4+0_28M_CA for 4979C. NE_4398A. 1.Install new 13G_DP_1.2m(MDD). 2.Install new RTN910A , 3_ISM8-2+0 and 4_ISM8-2+0. 3.Install new XMC_5D , Sub_B_Lo. 4.Enable GE port interconnect between RTN (4398A-4979C). 5.Enable EPLA , CA and service cross connect. FE_4391A. 1.Install new 13G_DP_1.2m(MDD). 2.Install new RTN910A, 3_ISM8-2+0 and 4_ISM8-2+0. 3.Install new XMC_5D , Sub_B_Hi. 4.Enable EPLA , CA and service cross connect. 5.Create In-Band DCN. | [7 empty] | CCSMY | SQ202502260411-CCS | CCSMY | SQ202504260061-CCS // SQ202504260064-CCS | 2024-12-23 | 2024-12-23 | Completed | 2024-12-23 | 2024-12-23 | 2024-12-23 | 2024-12-23 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Disabled | [9 empty] | Unassigned | Disabled | [9 empty] | Unassigned | Disabled |  |  | DOWMY25041367 |  | 2025-04-14 | 2025-04-15 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2025-05-21 | Saleem//Muhammed/7021000077 | CCS TI | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2025-07-06 | Saleem//Muhammed/7021000077 | CCS TI | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2026-04-01 | Saleem//Muhammed/7021000077 | 2025-09-30: 2025-05-16; 2025-09-30: 2025-05-31; 2025-09-30: 2025-05-16; 2025-10-08: 2025-05-16 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 |  | Assign Subcon
4480B_IPR_1 | ​Perpaduan Ria Ipoh RCC | DU00006400469 | Northern | Perak | 4.634950 | 101.142240 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | SFP 10G Module x 2 Fiber Patch Cord x 1 Pairs | BBU Patching | Impact site: 4480B Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Impact site: 4480B Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | [6 empty] | GCI | SQ202601080397-GCI | GCI | SQ202601080374-GCI | 2026-01-14 | 2026-01-13 | Completed | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121673 |  | 2025-12-17 | 2026-01-02 | Completed | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2026-01-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-13 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-13 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | SHIV KUMAR6800000084 |  | 2026-01-06 | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-14 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-09-30: 2026-01-04; 2025-09-30: 2026-01-13; 2025-09-30: 2026-01-04; 2025-10-08: 2026-01-06 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170724-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | CHEONG/SENG/WAH/7018000306
Q00344_IPR | ​Q132A_Q00344OD_CB_TMLAMBIR | DU00006400470 | Sarawak | Sarawak | 4.213900 | 114.046400 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x 1G SFP 2X PATCH CORD | MW IDU Patching | Split traffic at IDU Huawei RTN Q00344_TM BKT LAMBIR - Q00639_BELURU GE2 to PTN 30161-TMBKTLAMBIR GigabitEthernet0/0/2 Patch IDU Huawei RTN Q00344_TM BKT LAMBIR - Q00639_BELURU GE5 to new PTN 30161-TMBKTLAMBIR optical port and transfer traffic from sites below: 1) Q01826 (2690-2695) 2) Q01127 (3430-3435) remarks: require optical SFP and patchcord Impacted site: 1) Q01826 2) Q01127 | Split traffic at IDU Huawei RTN Q00344_TM BKT LAMBIR - Q00639_BELURU GE2 to PTN 30161-TMBKTLAMBIR GigabitEthernet0/0/2 Patch IDU Huawei RTN Q00344_TM BKT LAMBIR - Q00639_BELURU GE5 to new PTN 30161-TMBKTLAMBIR optical port and transfer traffic from sites below: 1) Q01826 (2690-2695) 2) Q01127 (3430-3435) remarks: require optical SFP and patchcord Impacted site: 1) Q01826 2) Q01127 | [6 empty] | Allstar | SQ202601280703-Allstar | Allstar | SQ202601080404-Allstar | 2026-02-23 | 2026-02-23 | Completed | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-02 | 2026-02-08 | 2026-02-02 | 2026-02-02 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122952 |  | 2025-12-31 | 2026-01-03 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-03 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-17 | 2026-01-23 | 2026-01-20 | 2026-01-20 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-17 | 2026-01-23 | 2026-01-26 | 2026-01-26 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | SHIV KUMAR6800000084 |  | 2026-01-21 | 2026-01-17 | 2026-01-23 | 2026-01-26 | 2026-01-26 | ROYSTON//AHHOLE/6000038561 | 2025-09-30: 2026-01-17; 2025-09-30: 2026-01-23; 2025-09-30: 2026-01-17; 2025-10-08: 2026-01-17 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202512170742-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
7209A_IPR | ​Bubul Road Semporna (Maxis) | DU00006400471 | Sabah | Sabah | 4.477580 | 118.606350 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_7209A New CAT6 cable with suitable length(IDU HW to IBeam) x1. | MW IDU Patching | Perform LAG for 2x port(existing & new) of IDU & IBeam. Site Impacted: 7647C & 7172D. NE_7209A 1.Enable port 8-EM6-2 of existing RTN910AF(RTN07, NEID 9-23075). 2.Request new IBeam port from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN07, NEID 9-23075) and new IBeam port. 4.Create LAG between 2xport(existing & new) of IDU-IBeam. 5.Traffics 7647C & 7172D will backhaul into LAG of IDU-IBeam. | Perform LAG for 2x port(existing & new) of IDU & IBeam. Site Impacted: 7647C & 7172D. NE_7209A 1.Enable port 8-EM6-2 of existing RTN910AF(RTN07, NEID 9-23075). 2.Request new IBeam port from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN07, NEID 9-23075) and new IBeam port. 4.Create LAG between 2xport(existing & new) of IDU-IBeam. 5.Traffics 7647C & 7172D will backhaul into LAG of IDU-IBeam. | [6 empty] | NR services | SQ202602250627-NR Services | NR services | SQ202602090125-NR Services |  |  | Ongoing | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-07 | 2026-04-14 | 2026-04-07 | 2026-04-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-21 | 2026-04-14 | 2026-04-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26012150 |  | 2026-01-22 | 2026-02-27 | Completed | 2026-01-21 | 2026-01-22 | 2026-01-21 | 2026-02-27 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-02-27 | RANA//WAQAS/6000006187 | NR Service TI | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-02-27 | RANA//WAQAS/6000006187 | NR Service TI | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-11 | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-02-27 | RANA//WAQAS/6000006187 | 2025-09-30: 2026-01-30; 2025-09-30: 2026-02-28; 2025-09-30: 2026-01-30; 2025-10-08: 2026-02-23 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202512180098-GTSB
Q00236_IPR | ​Q139A_Q00236OD_CB_KRUSEN | DU00006400472 | Sarawak | Sarawak | 1.049240 | 110.505160 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New SFP Module 1.25G/1G 1310nm 10Km x2.(For IDU Huawei & Cisco) New Optical Patchcord with suitable type and length x1. | MW IDU Patching | Perform re-engineering by doing migration at Q00236 RTN910AF(NEID 82-35241) of existing HW MW Link_ID SW03677, Q00642-Q00236. Site Impacted: Q01009/9205P ONLY. NE_Q00236 1.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into port 8-EM6-6 of RTN910AF(NEID 82-35241). Enable port. 2.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into new port Gi0/0/7 of Cisco Router(PTN ID 30463). Enable port. 3.Patching port 8-EM6-6 of RTN910AF(NEID 82-35241) and new port Gi0/0/7 of Cisco Router(PTN ID 30463). 4.Request new xC Vlan services for traffic Q01009/9205P ONLY. 5.Divert traffics Q01009/9205P ONLY to new port of port Gi0/0/7 of Cisco Router(PTN ID 30463). | Perform re-engineering by doing migration at Q00236 RTN910AF(NEID 82-35241) of existing HW MW Link_ID SW03677, Q00642-Q00236. Site Impacted: Q01009/9205P ONLY. NE_Q00236 1.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into port 8-EM6-6 of RTN910AF(NEID 82-35241). Enable port. 2.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into new port Gi0/0/7 of Cisco Router(PTN ID 30463). Enable port. 3.Patching port 8-EM6-6 of RTN910AF(NEID 82-35241) and new port Gi0/0/7 of Cisco Router(PTN ID 30463). 4.Request new xC Vlan services for traffic Q01009/9205P ONLY. 5.Divert traffics Q01009/9205P ONLY to new port of port Gi0/0/7 of Cisco Router(PTN ID 30463). | [6 empty] | Allstar | SQ202601150559-Allstar | Allstar | SQ202601080404-Allstar |  |  | Ongoing | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25122953 |  | 2025-12-31 | 2026-01-03 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-03 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-06 | 2026-01-12 | 2026-01-06 | 2026-01-06 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-06 | 2026-01-12 | 2026-02-27 | 2026-02-27 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-06 | 2026-01-06 | 2026-01-12 | 2026-03-01 | 2026-03-01 | ROYSTON//AHHOLE/6000038561 | 2025-09-30: 2026-01-06; 2025-09-30: 2026-01-12; 2025-09-30: 2026-02-26; 2025-10-08: 2026-02-26 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202512180102-GTSB
B02499_IPR_1 | ​B058E_B02499OD_JLNSKLHKGJENJAROM | DU00006400473 | Central | Selangor | 2.884510 | 101.518034 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x1. | IDU-IPRAN | Impacted site: 1) 1006P/B02043 MN_BUSUTBARU Split traffic at IDU Huawei RTN 1046K/B02499_JLNSKLHKGJENJAROM - 2728C-KG.JENJAROM 2 GE1 to PTN 70658-JLNSEKOLAHJJRM/GigabitEthernet0/0/4 Transfer traffic 1006P from existing B02499 RTN01 GE1 - PTN 70658 GE0/0/4 to B02499 RTN01 GE5 - PTN 70658 GE0/0/6 | Impacted site: 1) 1006P/B02043 MN_BUSUTBARU Split traffic at IDU Huawei RTN 1046K/B02499_JLNSKLHKGJENJAROM - 2728C-KG.JENJAROM 2 GE1 to PTN 70658-JLNSEKOLAHJJRM/GigabitEthernet0/0/4 Transfer traffic 1006P from existing B02499 RTN01 GE1 - PTN 70658 GE0/0/4 to B02499 RTN01 GE5 - PTN 70658 GE0/0/6 | [6 empty] | GTSB | SQ202601130167-GTSB | GTSB | SQ202601130159-GTSB | 2026-02-04 | 2026-01-23 | Completed | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-21 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-02-04 | 2026-01-21 | 2026-01-21 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25120847 |  | 2026-01-09 | 2026-01-10 | Completed | 2025-12-08 | 2026-01-09 | 2025-12-08 | 2026-01-10 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-26 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-26 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-20 | 2026-01-22 | 2026-02-22 | 2026-01-24 | 2026-01-24 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-09-30: 2026-01-19; 2025-09-30: 2026-01-20; 2025-09-30: 2026-01-19; 2025-10-08: 2026-01-20 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170715-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | CHEONG/SENG/WAH/7018000306
3367B-3569B | Giant Hypermarket Shah Alam Outdoor | DU00004254807 | Central | Selangor | 3.066780 | 101.488638 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 18/11: D1: Cutover done. Post-CO T/S ongoing 24/10: DM materials from Tx Mini W01442-W00145 (DO issued 18G) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Swap existing link to 23G_2+0_112M. NE_3367B 18G_DP_0.6m(MAC)+OMT x1. RTN910A XMC_3E-1+0 , Sub B_Hi x1. FE_3569B 18G_DP_0.6m(MAC)+OMT x1. XMC_3E-1+0,Sub B_Lo x1. RTN910A x1. | MW Swap | Swap existing link to 18G_1+0_112M. Site Impacted:3367B,3569B,3464B,1171C. NE_3367B 1.Install new 18G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-1+0.(RTN no provide by MSP team). 3.Install XMC_3E-1+0 , Sub _B_Hi. 4.Migrate traffic to new link 18G_1+0_112M. 5.Create service cross connect and migrate traffic to new link. 6.Decom existing Ant , IDU and ODU. FE_3569B 1.Install new 18G_DP_0.6m(MAC)+OMT. 2.Install XMC_3E-1+0,Sub_B_Lo. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Create service cross connect and migrate traffic from existing 3569B_RTN01 to new RTN910A.(1171C,3367B & 3464B). 5.Enable GE1 , patching ETH cable to existing 3569B_RTN03. 6.Decom existing IDU , Ant and ODU.(Pls confirm all traffic are migrate to new link with stable and no alrm before decom the existing link). | [7 empty] | GTSB | SQ202411190744-GTSB | GTSB | SQ202411190299-GTSB // SQ202504260131-GTSB | 2025-10-08 | 2025-10-07 | Completed | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-11-26 | 2024-12-10 | 2024-11-26 | 2024-12-29 | KANNAN A/L RAMACHANDRAN6799000115 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2024-11-19 | 2024-11-19 | Completed | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2024-12-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-19 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-19 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-11-17 | 2024-11-30 | 2024-11-19 | 2024-11-19 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2024-11-17 | 2024-11-30 | 2024-11-18 | 2024-11-18 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
1726C_LOS | BBCC Mall (lalaport) IB | DU00006404353 | Central | Kuala Lumpur | 3.141252 | 101.707621 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M_512QAM_EPLA NE_1726C New 23G_0.6M(MAC)+OMT x1. New RTN910AF(RTN01). New XMC_3E, Sub A&B_Hi x1. New CAT6 cable x1. FE_1461A New 23G_0.6M(MAC)+OMT x1. New RTN910AF(RTN05). New ISM8 x1. New XMC_3E, Sub A&B_Lo x1. | MW New Link / Reroute | Existing HW MW Link 1726C-1334A, 23G_2+0_112MHZ_512QAM_EPLA. Install new HW MW Link 1726C-1461A, 23G_2+0_112MHZ_512QAM_EPLA. Later, decom existing HW MW Link 1726C-1334A, 23G_2+0_112MHZ_512QAM_EPLA. Site Impacted : 1726C. NE_1726C 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A&B_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching existing BBU 1726C to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic 17126C via new HW MW Link 1726C-1461A, 23G_2+0_112MHZ_512QAM_EPLA. 8.Decom existing HW MW Link 1726C-1334A, 23G_2+0_112MHZ_512QAM_EPLA. FE_1461A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN05) x1. 3.Install new XMC_3E, Sub A&B_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN05). 5.Patching port 8-EM6-1 of new RTN910A(RTN05) to new port of IBeam(request from ZTE IPRAN Team). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic 1726C to new IBeam port. 8.Decom existing HW MW Link 1726C-1334A, 23G_2+0_112MHZ_512QAM_EPLA. | Existing HW MW Link 1726C-1334A, 23G_2+0_112MHZ_512QAM_EPLA. Install new HW MW Link 1726C-1461A, 23G_2+0_112MHZ_512QAM_EPLA. Later, decom existing HW MW Link 1726C-1334A, 23G_2+0_112MHZ_512QAM_EPLA. Site Impacted : 1726C. NE_1726C 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A&B_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching existing BBU 1726C to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic 17126C via new HW MW Link 1726C-1461A, 23G_2+0_112MHZ_512QAM_EPLA. 8.Decom existing HW MW Link 1726C-1334A, 23G_2+0_112MHZ_512QAM_EPLA. | Existing HW MW Link 1726C-1334A, 23G_2+0_112MHZ_512QAM_EPLA. Install new HW MW Link 1726C-1461A, 23G_2+0_112MHZ_512QAM_EPLA. Later, decom existing HW MW Link 1726C-1334A, 23G_2+0_112MHZ_512QAM_EPLA. Site Impacted : 1726C. FE_1461A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN05) x1. 3.Install new XMC_3E, Sub A&B_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN05). 5.Patching port 8-EM6-1 of new RTN910A(RTN05) to new port of IBeam(request from ZTE IPRAN Team). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic 1726C to new IBeam port. 8.Decom existing HW MW Link 1726C-1334A, 23G_2+0_112MHZ_512QAM_EPLA. | XMC_3E | MAC | 23G | 23G_0.6M(MAC)+OMT x1 | 23G_0.6M(MAC)+OMT x1 | GCI | SQ202601280642-GCI | GCI | SQ202601210049-GCI // SQ202601210050-GCI | 2026-03-23 | 2026-03-17 | Completed | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-03 | 2026-03-10 | 2026-03-03 | 2026-03-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-16 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011433 |  | 2026-01-15 | 2026-01-15 | Completed | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-26 | 2026-02-02 | 2026-01-25 | 2026-01-27 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-26 | 2026-02-02 | 2026-01-25 | 2026-02-05 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-28 | 2026-01-26 | 2026-02-02 | 2026-01-25 | 2026-02-05 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2026-01-26 | 2026-02-02 | 2026-01-25 | 2026-01-27 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512180092-GTSB
1434B_LOS | Sek 16 Suria Apt | DU00006404354 | Central | Selangor | 3.057870 | 101.507497 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_1434B 23G_DP_0.3M(MAC)+OMT x1. RTN901A x1. XMC_3E , Sub A & B_Hi x2. FE_1073A 23G_DP_0.3M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A_Hi x1. | MW New Link / Reroute | Link reroute to new FE 2640A due to exsiting FE being LOS Block. Install new MW link config 23G_2+0_112M to new FE 2640A. Site Impacted : 1434B , 3982B , 3839B. NE_1434B 1.Install new 23G_DP_0.3M(MAC)+OMT. 2.Install new RTN901A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.All traffic migrate to new MW link and New FE routing. (1434B , 3982B , 3839B). 6.Decom existing MW (1434B-1073A). FE_2640A 1.Install new 23G_DP_0.3M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching to existing 2604A_RTN01_GE1. 6.All traffic migrate to new MW link and New FE routing. 7.Decom existing MW (1073A-1434B). | Link reroute to new FE 2640A due to exsiting FE being LOS Block. Install new MW link config 23G_2+0_112M to new FE 2640A. Site Impacted : 1434B , 3982B , 3839B. NE_1434B 1.Install new 23G_DP_0.3M(MAC)+OMT. 2.Install new RTN901A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.All traffic migrate to new MW link and New FE routing. (1434B , 3982B & 3839B). 6.Decom existing MW (1434B-1073A). | Link reroute to new FE 2640A due to exsiting FE being LOS Block. Install new MW link config 23G_2+0_112M to new FE 2640A. Site Impacted : 1434B , 3982B , 3839B. FE_2640A 1.Install new 23G_DP_0.3M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching to existing 2604A_RTN01_GE1. 6.All traffic migrate to new MW link and New FE routing. 7.Decom existing MW (1073A-1434B). | XMC | XMC_3E | 23G | 0.3 | 0.3 | GCI | SQ202512160937-GCI | GCI | SQ202601130175-GCI // SQ202601130180-GCI | 2026-01-23 | 2026-01-23 | Completed | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2026-01-11 | 2026-01-11 | Completed | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-24 | 2025-12-31 | 2025-12-24 | 2026-01-11 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-24 | 2025-12-31 | 2025-12-24 | 2026-01-11 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-12-24 | 2025-12-31 | 2025-12-24 | 2026-01-12 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-12-24 | 2025-12-31 | 2025-12-24 | 2025-12-26 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170715-GCI | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | CHEONG/SENG/WAH/7018000306
​1726C_LOS | ​BBCC Mall (lalaport) IB | DU00006409265 | Central | Kuala Lumpur | 3.141252 | 101.707621 | [7 empty] | 08. Pending RFS | [13 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
​1434B_LOS | ​Sek 16 Suria Apt | DU00006409266 | Central | Selangor | 3.057870 | 101.507497 | [7 empty] | 08. Pending RFS | [13 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2727A-1362A | Extreme Park Shah Alam | DU00003384234 | Central | Selangor | 3.086592 | 101.541617 | WK12 | MAR 24 | WK06 | MAR 24 | RFS | Pending L1 | ZTE | 00. Integrated/RFS Done | 3/9: Cutover not completed. Traffic still running on SM link. Planner to release new DU /solutions 19/3: Cutover done, RSL rectification required. Current RSL -44dbm | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6/0.6_MDD_2+0_112MHZ_256QAM | MW Swap | NE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 2+0 112MHZ 5. DISMANTLE EXISTING LINK FE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 2+0 112MHZ 5. DISMANTLE EXISTING LINK 6. REPATCH NEW RTN 910A TO CP PORT | [7 empty] | GTSB | SQ202403260089-GTSB | GTSB | SQ202402270719-GTSB | 2024-09-03 | 2024-09-02 | Completed | 2024-02-26 | 2024-03-15 | 2024-03-15 | 2024-03-15 | FAHRURRADZI HELMY BIN SUHAIZAD6799000123 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-03-20 | 2024-03-21 | 2024-03-20 | 2024-03-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-20 | 2024-03-21 | 2024-03-20 | 2024-03-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-09-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020128 |  | 2024-02-02 | 2024-03-08 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-03-08 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-04-26 | IMRAN//ALI/6799000249 | GTSB TI | 2024-03-14 | 2024-06-30 | 2024-03-14 | 2024-03-19 | IMRAN//ALI/6799000249 | GTSB TI | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | C.PRATHABAN///6798000081 |  |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2025-07-09 | IMRAN//ALI/6799000249 | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-16 | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | NG HONG JIE7018000036 | Logistic Team | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358
2433A | Kg Kubu Gajah | DU00003384235 | Central | Selangor | 3.195798 | 101.527598 | WK06 | FEB 24 | WK05 | FEB 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+TI | L1+ATP+PAC |  | BBU Patching | [8 empty] | MTK | SQ202402140176-MTK | MTK | SQ202402190118-MTK | 2025-07-02 | 2025-07-01 | Completed | 2024-02-02 | 2024-02-02 | 2024-02-03 | 2024-02-03 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24013158 |  | 2024-02-01 | 2024-02-01 | Completed | 2024-01-31 | 2024-02-01 | 2024-01-31 | 2024-02-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-03 | 2024-02-29 | 2024-02-03 | 2024-02-03 | MOHD//GHADAFI BIN ISMAIL/8225000014 | MTK TI | 2024-02-03 | 2024-02-29 | 2024-02-03 | 2024-02-03 | MOHD//GHADAFI BIN ISMAIL/8225000014 | MTK TI | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2024-02-03 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  |  | 2024-02-03 | 2024-02-29 | 2024-02-03 | 2024-02-06 | MOHD//GHADAFI BIN ISMAIL/8225000014 | 2025-09-30: 2024-02-03; 2025-09-30: 2024-02-29; 2025-09-30: 2024-02-03; 2025-10-08: 2024-02-06 |  |  | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050696-GCI
1372C-1605B | Syabas Rimbayu (REL) | DU00003384236 | Central | Selangor | 2.931495 | 101.538495 | WK08 | MAR 24 | WK08 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_0.6/1.2 MDD_4+0_28MHz | MW Swap | NE 1. INSTALL 1 UNIT ISM8 CARD AT RTN01 SLOT 4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. REUSE EXISTING ISM8 SLOT 3 4. CONFIGURE LINK 15G 4+0 28MHZ WITH CA SLOT 3 & 4 5. DISMANTLE EXISTING LINK FE 1. INSTALL 2 UNIT ISM8 CARD AT RTN03 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 4+0 28MHZ WITH CA 5. DISMANTLE EXISTING LIN | [7 empty] | MTK | SQ202407050120-MTK | MTK | SQ202402190118-MTK | 2024-06-15 | 2024-06-14 | Completed | 2024-02-19 | 2024-05-31 | 2024-04-16 | 2024-04-16 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | MTK COMMUNICATION SDN. BHD. |  | Assigned | Completed |  | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-06-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-06-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-06-14 | 2024-06-15 | 2024-06-14 | 2024-06-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020132 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-20 | 2024-02-29 | 2024-02-20 | 2024-02-21 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-02-20 | 2024-02-29 | 2024-02-20 | 2024-02-20 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-02-16 | 2024-02-23 | 2024-02-29 | 2024-02-29 | RONALD SHAN A/L AMBUROSE6800000089 | MTK TI |  | 2024-02-20 | 2024-02-29 | 2024-02-20 | 2024-02-21 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-02-20 | 2024-02-29 | 2024-02-20 | 2024-02-21 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-08 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
1936B-1922B | Sijangkang Batu 9 (Celcom) | DU00003384237 | Central | Selangor | 2.925889 | 101.515583 | WK06 | FEB 24 | WK06 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_64QAM_112MHZ_1.2M/1.2M | MW Swap | MW SWAP MW LINK 1936B-1922B WITH HUAWEI_18G_2+0_64QAM_112MHZ_1.2M/1.2M WITH CA NE: 1. INSTALL 2 UNIT ISM8 CARD AT NEW RTN910 SLOT 3 & 4 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 2+0 112MHZ WITH CA (USING BOTH CHANNEL V) 5. DISMANTLE EXISTING LINK FE: 1. INSTALL 2 UNIT ISM8 CARD AT NEW RTN910 SLOT 3 & 4 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 2+0 112MHZ WITH CA (USING BOTH CHANNEL V) 5. DISMANTLE EXISTING LINK | [7 empty] | MTK | SQ202402140176-MTK | MTK | SQ202402190118-MTK | 2024-09-03 | 2024-09-02 | Completed | 2024-02-02 | 2024-02-02 | 2024-02-01 | 2024-02-01 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-02-15 | 2024-02-22 | 2024-02-19 | 2024-02-19 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | MTK COMMUNICATION SDN. BHD. |  | Assigned | Completed |  | 2024-05-17 | 2024-05-18 | 2024-05-17 | 2024-05-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-09-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020131 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-15 | 2024-02-22 | 2024-02-15 | 2024-02-15 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-02-15 | 2024-02-22 | 2024-02-15 | 2024-02-16 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-02-15 | 2024-02-22 | 2024-02-15 | 2024-02-16 | RONALD SHAN A/L AMBUROSE6800000089 | MTK TI |  | 2024-02-15 | 2024-02-22 | 2024-02-19 | 2024-02-19 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-02-15 | 2024-02-22 | 2024-02-15 | 2024-02-15 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-08 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
2069B-1612B | WT_UITMPNCKALAM | DU00003384238 | Central | Selangor | 3.204196 | 101.453258 |  | MAR 24 | WK13 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 28/3: D2: Cutover done | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112MHZ_0.6m/1.2m_128QAM | MW Parallel Link | NE 1) Install new RTN910A (ops team to assign new RTN number) 2) Install new 18G 0.6 antenna 3) Install new 18G 2+0 112MHz at new RTN 7-ISM8 4) Migrate 2069B BBU only to new link FE 1) Install new RTN910A (ops team to assign new RTN number) 2) Install new 18G 1.2 antenna 3) Install new 18G 2+0 112MHz at new RTN 7-ISM8 4) Migrate 2069B BBU only to new link 5) Patch new IDU to new CP port and establish new DCN | [7 empty] | MTK | SQ202404170286-MTK | MTK | SQ202402270725-MTK // SQ202409110359-MTK | 2024-04-04 | 2024-04-04 | Completed | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-04-04 | MOHD//GHADAFI BIN ISMAIL/8225000014 |  | MTK COMMUNICATION SDN. BHD. |  | Unassigned | Completed |  | 2024-03-20 | 2024-03-21 | 2024-03-20 | 2024-03-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-20 | 2024-03-21 | 2024-03-20 | 2024-03-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-26 | 2024-03-27 | 2024-03-26 | 2024-03-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021506 |  | 2024-02-16 | 2024-02-19 | Completed | 2024-02-15 | 2024-02-16 | 2024-02-15 | 2024-02-19 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-27 | 2024-03-31 | 2024-03-27 | 2024-04-03 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-03-27 | 2024-03-31 | 2024-03-27 | 2024-04-03 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-27 | 2024-03-31 | 2024-03-27 | 2024-03-29 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-09-30: 2024-03-27; 2025-09-30: 2024-03-31; 2025-09-30: 2024-03-27; 2025-10-08: 2024-03-27 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
2434A-1412A | Bdr Tasik Puteri (Celcom) | DU00003384239 | Central | Selangor | 3.276914 | 101.504516 | WK13 | MAR 24 | WK13 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 26/3: Cutover done | TSS+AA+TI | L1+ATP+PAC | 15G_1.2/1.2_MDD_4+0_28MHZ | MW Parallel Link | NE 1) INSTALL NEW RTN910A (OPS TEAM TO ASSIGN NEW RTN NUMBER) 2) INSTALL NEW 15G 4+0 28MHZ AT NEW RTN 3- ISM8 AND 4-ISM8 WITH CA 3) INSTALL NEW ANTENNA 15G 1.2M AND ODU SUBBAND B 4) MIGRATE 2434A BBU ONLY TO NEW LINK FE 1) INSTALL NEW RTN910A (OPS TEAM TO ASSIGN NEW RTN NUMBER) 2) INSTALL NEW 15G 4+0 28MHZ AT NEW RTN 3-ISM8 AND 4-ISM8 WITH CA 3) INSTALL NEW ANTENNA 15G 1.2M AND ODU SUBBAND B 4) MIGRATE 2434A BBU ONLY TO NEW LINK 5) PATCH NEW IDU TO NEW CP PORT AND ESTABLISH NEW DCN | [7 empty] | MTK | SQ202407050120-MTK | MTK | SQ202402270725-MTK // SQ202409110359-MTK | 2024-05-28 | 2024-05-27 | Completed | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-04-04 | MOHD//GHADAFI BIN ISMAIL/8225000014 |  | MTK COMMUNICATION SDN. BHD. |  | Unassigned | Completed |  | 2024-04-03 | 2024-04-04 | 2024-04-03 | 2024-04-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-27 | 2024-05-28 | 2024-05-27 | 2024-05-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021020 |  | 2024-02-12 | 2024-02-19 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-02-19 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-22 | 2024-03-31 | 2024-03-22 | 2024-04-18 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-03-22 | 2024-06-30 | 2024-03-22 | 2024-04-23 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-22 | 2024-03-31 | 2024-03-22 | 2024-04-07 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-09-30: 2024-03-22; 2025-09-30: 2024-03-31; 2025-09-30: 2024-03-22; 2025-10-08: 2024-03-25 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
2008B-1413A | Rawang Intgr Ind Park (Maxis) | DU00003384240 | Central | Selangor | 3.307804 | 101.560714 |  | MAR 24 |  | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 1/8: D3: Cutover done. Post-CO Tshooting WIP 30/7: MOS & Pre-installation WIP 20/6: Subcon req CR for approval (manual carry) | TSS+AA+TI | L1+ATP+PAC | 23G 2+0 112Mhz 0.6m/0.6m 128QAM | MW Swap | NE 1. REUSE EXISTING RTN01 2. INSTALL NEW 23G 0.6m DP ANTENNA 3. INSTALL NEW ODU 23G 112MHz XMC-3 ODU SUBBAND A 4. INSTALL IF CABLE TO RTN01-7-ISM8-2 5. CONFIGURE LINK 23G 2+0 112MHz 128QAM EPLA WITH EXISTING 1+0 FE 1. REUSE EXISTING RTN07 2. INSTALL NEW 23G 0.6m DP ANTENNA 3. INSTALL NEW ODU 23G 112MHz XMC-3 ODU SUBBAND A 4. INSTALL IF CABLE TO RTN07-7-ISM8-2 5. CONFIGURE LINK 23G 2+0 112MHz 128QAM EPLA WITH EXISTING 1+0 NO DECOM DUE TO SOW PARALLEL. EXISTING LINK CARRY OTHERS TRAFFIC | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202402190118-MTK // SQ202412240115-MTK | 2024-10-02 | 2024-10-01 | Completed | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-21 | 2024-09-22 | 2024-09-21 | 2024-09-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-21 | 2024-09-22 | 2024-09-21 | 2024-09-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020319 |  | 2024-02-05 | 2024-02-06 | Completed | 2024-02-03 | 2024-02-05 | 2024-02-03 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-18 | 2024-08-02 | 2024-03-18 | 2024-08-02 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-03-18 | 2024-09-30 | 2024-03-18 | 2024-08-23 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-13 | SHUJAAT//ALI/6800000124 |  |  | 2024-03-18 | 2024-03-31 | 2024-03-18 | 2024-09-04 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-09-30: 2024-03-18; 2025-09-30: 2024-03-31; 2025-09-30: 2024-03-18; 2025-10-08: 2024-03-20 |  |  | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
1873B-1475A | Zon Akademik Utara | DU00003384241 | Central | Selangor | 3.005252 | 101.709471 | WK06 |  | WK06 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 23/10: Interim solution: MW Remote upgrade done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 1+0 112Mhz 0.6m/0.6m 256QAM | MW Hardware Upgrade | NE 1. SWAP OLD RTN01 WITH NEW RTN910A 2. SWAP EXISTING ODU WITH NEW 23G 112MHz XMC-3 ODU SUBBAND A 3. REUSE EXISTING 23G 0.6m SP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHz 256QAM FE 1. INSTALL NEW RTN910 2. SHIFT CABLE LINK 1873B-1475A RTN04 SLOT 5 TO NEW RTN910 SLOT 7 3. SWAP EXISTING ODU WITH NEW 23G 112MHz XMC-3 ODU SUBBAND A 4. REUSE EXISTING 23G 0.6m SP ANTENNA 5. CONFIGURE LINK 23G 1+0 112MHz 256QAM | [7 empty] | GTSB | SQ202409100255-GTSB | GTSB | SQ202402190113-GTSB // SQ202511270674-GTSB | 2024-05-25 | 2024-05-24 | Completed | 2024-02-05 | 2024-02-05 | 2024-05-05 | 2024-05-05 | FAHRURRADZI HELMY BIN SUHAIZAD6799000123 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-02-21 | 2024-02-22 | 2024-02-21 | 2024-02-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-02-21 | 2024-02-22 | 2024-02-21 | 2024-02-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-24 | 2024-05-25 | 2024-05-24 | 2024-05-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020130 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-06 | 2024-02-29 | 2024-02-06 | 2024-02-08 | angahmeal@gmail.comangahmeal@gmail.com | GTSB TI | 2024-02-06 | 2024-02-29 | 2024-02-06 | 2024-02-08 | angahmeal@gmail.comangahmeal@gmail.com | GTSB TI | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-08 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-06 | 2024-02-29 | 2024-02-06 | 2024-02-10 | angahmeal@gmail.comangahmeal@gmail.com | 2024-02-06 | 2024-02-29 | 2024-02-06 | 2024-02-07 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4065B14-1461A | pBTS Setia Kemajuan TRX (REL) | DU00003384242 | Central | Kuala Lumpur | 3.141871 | 101.715109 | WK09 | MAR 24 | WK09 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 1+0 112Mhz 0.3m/0.3m 512QAM | MW Hardware Upgrade | NE 1. REUSE EXISTING RTN01 2. REUSE EXISTING ODU 3. REUSE EXISTING 23G 0.3 m DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHz 512QAM FE 1. REUSE EXISTING RTN01 2. SWAP EXISTING ODU TO NEW ODU 23G 112MHz XMC-3 ODU SUBBAND A LO AT EXISTING ANTENNA 3. REUSE EXISTING 23G 0.3m DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHz 512QAM | [7 empty] | MTK | SQ202407050120-MTK | MTK | SQ202402190118-MTK | 2024-04-30 | 2024-05-06 | Completed | 2024-02-26 | 2024-03-01 | 2024-04-16 | 2024-04-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. |  | Unassigned | Completed |  | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-29 | 2024-04-30 | 2024-04-29 | 2024-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020135 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-26 | 2024-02-29 | 2024-02-26 | 2024-04-18 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2024-02-26 | 2024-02-29 | 2024-02-26 | 2024-02-29 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-27 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-26 | 2024-02-29 | 2024-02-26 | 2024-03-14 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | 2024-02-26 | 2024-02-29 | 2024-02-26 | 2024-03-15 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
2007B-1892B | Tmn Bunga Raya | DU00003384243 | Central | Selangor | 3.445272 | 101.542199 | WK06 | FEB 24 | WK19 | JUN 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 15/6: D4: Cutover done 25/5: Repeal DO issued, ASC proceed collection and continue TI 13/5: Flat OMT 13G missing. Pending new release 2/5: Repeal DO issued, ASC proceed collection and continue TI 22/4: D1: MOS & TI In Plan. ODU missing (13G) | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28MHZ_1.2/1.2_SUB B | MW Parallel Link | NE 1. INSTALL NEW 1 UNIT ISM8 CARD AT RTN04 SLOT 3 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW 13G XMC-5D SUB BAND B 4. CONFIGURE LINK 13G 2+0 28MHZ 5. EPLA NEW 13G 2+0 28MHZ WITH EXISTING 15G 2+0 28MHz FE 1. INSTALL NEW RTN 910A + 1 UNIT ISM8 CARD 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW 13G XMC-5D SUB BAND B 4. CONFIGURE LINK 13G 2+0 28MHZ 5. SHIFT 2007B-1892B IF CABLE AND CONFIGURATION FROM RTN04 3-ISM6 TO NEW RTN 910A 7-ISM8 6. EPLA NEW 13G 2+0 28MHZ WITH EXISTING 15G 2+0 28MHZ | [7 empty] | Ascentrack | SQ202411040286-Ascentrack | Ascentrack | SQ202402270713-Ascentrack // SQ202411040283-Ascentrack | 2024-09-28 | 2024-09-27 | Completed | 2024-02-09 | 2024-02-09 | 2024-02-05 | 2024-02-05 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-08 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-09-04 | 2024-09-05 | 2024-09-04 | 2024-09-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-27 | 2024-09-28 | 2024-09-27 | 2024-09-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021013 |  | 2024-02-12 | 2024-02-16 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-02-16 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-06 | 2024-03-13 | 2024-03-03 | 2024-03-04 | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | Ascentrack TI | 2024-03-06 | 2024-09-30 | 2024-03-03 | 2024-06-14 | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | Ascentrack TI | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-08-30 | C.PRATHABAN///6798000081 |  |  | 2024-03-06 | 2024-03-13 | 2024-03-03 | 2024-10-08 | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | 2024-03-03 | 2024-03-31 | 2024-03-03 | 2024-03-04 | 2024-03-06 | 2024-06-30 |  |  | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | Ascentrack TI | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
3256A-2476A | COUNTRYHOMES1 | DU00003384244 | Central | Selangor | 3.331739 | 101.535194 | WK06 | FEB 24 | WK10 | MAR 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28MHZ_0.6M/1.2M | MW Parallel Link | MW PARALLEL LINK 3256A-2476A WITH HUAWEI_15G_4+0_28MHZ_0.6M/1.2M_5.47KM NE: 1. INSTALL 1 UNIT ISM8 CARD AT RTN03 SLOT 4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 4+0 28MHZ FE: 1. INSTALL 2 UNIT ISM8 CARD AT RTN03 SLOT 3&4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 4+0 28MHZ | [7 empty] | Ascentrack | SQ202411040286-Ascentrack | Ascentrack | SQ202402270713-Ascentrack | 2024-02-08 | 2024-02-08 | Completed | 2024-02-07 | 2024-02-07 | 2024-02-02 | 2024-02-02 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-08 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed | [9 empty] | Unassigned | Disabled | [9 empty] | Unassigned | Disabled |  |  | DOWMY24021014 |  | 2024-02-12 | 2024-02-16 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-02-16 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-06 | 2024-03-13 | 2024-02-29 | 2024-11-21 | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | Ascentrack TI | 2024-03-06 | 2024-03-13 | 2024-02-29 | 2024-04-30 | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | Ascentrack TI | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-06 | 2024-03-13 | 2024-02-29 | 2024-08-12 | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-03-06 | 2024-03-06 | 2024-06-30 |  |  | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | Ascentrack TI | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
1766B-1009A | Ladang Sg Tua(Maxis) | DU00003384245 | Central | Selangor | 3.271417 | 101.654471 | WK07 | FEB 24 | WK09 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI | L1+ATP+PAC | 18G 2+0 112Mhz 0.6m/1.2m 128QAM | MW Parallel Link | MW Parallel Huawei 18G 2+0 112Mhz 0.6m/1.2m 1766B-1009A to carry traffic of 1766B BBU only NE: 1. INSTALL NEW RTN910A (OPS TEAM TO ASSIGN NEW RTN NUMBER) 2. INSTALL NEW 18G 0.6 ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. INSTALL NEW 18G 2+0 112MHZ AT NEW RTN 7-ISM8 5. MIGRATE 1766B BBU ONLY TO NEW LINK FE: 1. INSTALL NEW RTN910A (OPS TEAM TO ASSIGN NEW RTN NUMBER) 2. INSTALL NEW 18G 1.2 ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. INSTALL NEW 18G 2+0 112MHZ AT NEW RTN 7-ISM8 5. MIGRATE 1766B BBU ONLY TO NEW LINK 6. PATCH NEW IDU TO NEW CP PORT AND ESTABLISH NEW DCN | [7 empty] | Ascentrack | SQ202402190087-Ascentrack | Ascentrack | SQ202402270713-Ascentrack // SQ202409100362-Ascentrack | 2025-01-22 | 2025-01-21 | Completed | 2024-02-09 | 2024-02-09 | 2024-02-15 | 2024-02-15 | Nor//Syamsyairi Bin Hashim/7539000044 |  | ASCENTRACK SDN. BHD. |  | Unassigned | Completed |  | 2024-02-15 | 2024-02-16 | 2024-02-15 | 2024-02-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-02-17 | 2024-02-18 | 2024-02-17 | 2024-02-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2025-01-21 | 2025-01-22 | 2025-01-21 | 2025-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021015 |  | 2024-02-12 | 2024-02-23 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-02-23 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-27 | 2024-03-31 | 2024-03-27 | 2024-05-08 | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | Ascentrack TI | 2024-03-27 | 2024-06-30 | 2024-03-27 | 2024-11-21 | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | Ascentrack TI | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-27 | 2024-03-31 | 2024-03-27 | 2024-04-05 | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | 2025-09-30: 2024-03-27; 2025-09-30: 2024-03-31; 2025-09-30: 2024-03-27; 2025-10-08: 2024-05-06 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
W01010_HU | W066N_W01010IB_BANKISLAM | DU00005180161 | Central | Kuala Lumpur | 3.153400 | 101.710600 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | SOW DONE UNDER NIC W01010 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
A00235_HU | A041A_A00235OD_TMPDGRENGAS | DU00005180162 | Northern | Perak | 4.770700 | 100.850000 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Drop Under NIC ; A00235 MW Swap | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505020432-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
K00161_HU | K011A_K00161OD_KEBUN500 | DU00005180163 | Northern | Kedah | 6.144400 | 100.472200 |  |  |  |  | TI IN PLAN | ZTE |  | 00. Integrated/RFS Done | 01/07: CO Done | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M_CA. NE_K00161. 15G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2 XMC_5D , Sub A_Lo x1. FE_4678A 15G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2 XMC_5D , Sub A_Hi x1.. | MW New Link / Reroute | Existing SM link 15G_2+0_28M Reroute link with 15G_4+0_28M_CA to 4678A which is colo site K00088. Site Impacted : K00161. NE_K00161. 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new link 15G_4+0_28M_CA. 7.No Decom existing SM link due to support child site for K00816 FE_4678A 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new link 15G_4+0_28M_CA. 7.Create new In Band DCN. 8.No Decom existing SM link due to support child site for K00816 | Existing SM link 15G_2+0_28M Reroute link with 15G_4+0_28M_CA to 4678A which is colo site K00088. Site Impacted : K00161. NE_K00161. 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new link 15G_4+0_28M_CA. 7.No Decom existing SM link due to support child site for K00816 | Existing SM link 15G_2+0_28M Reroute link with 15G_4+0_28M_CA to 4678A which is colo site K00088. Site Impacted : K00161. FE_4678A 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new link 15G_4+0_28M_CA. 7.Create new In Band DCN. 8.No Decom existing SM link due to support child site for K00816 | XMC_5D | MDD | 15G | 1.2 | 1.2 | GCI | SQ202507030705-GCI | GCI | SQ202506300562-GCI // SQ202506300570-GCI | 2025-11-28 | 2025-11-27 | Completed | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Material DM from R00130//Cancel DO | 2025-05-21 | 2025-07-07 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-07-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-28 | 2025-06-30 | 2025-06-28 | 2025-07-07 | team7gcitechnicalteam7gcitechnical | GCI TI | 2025-06-28 | 2025-06-30 | 2025-06-28 | 2025-07-07 | team7gcitechnicalteam7gcitechnical | GCI TI | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AKMAL//BIN RAZALI/6794000078 |  |  | 2025-06-28 | 2025-06-30 | 2025-06-28 | 2025-07-07 | team7gcitechnicalteam7gcitechnical | 2025-09-30: 2025-06-28; 2025-09-30: 2025-06-30; 2025-09-30: 2025-06-28; 2025-10-08: 2025-07-01 |  |  | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-06 | CHEONG/SENG/WAH/7018000306
K00123_HU | K006A_K00123OD_TUNJANGTOWN | DU00005180164 | Northern | Kedah | 6.283111 | 100.376197 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Existing HW link 15G_4+0_28M_XPIC+CA. Link is 15G have an interference, Existing TX route K00123-K00142. K00123 is colo site with 4959A. 4959A was prepared solution under TX Mini Project for 4959A_HU. And RAN K00123 will be decom , so this K00123_HU will be drop. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505020432-GCI | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-25 | CHEONG/SENG/WAH/7018000306
Q01672_HU | Q132C_Q01672OD_JLNPUJUTBGRAYA | DU00005180165 | Sarawak | Sarawak | 4.402860 | 114.011634 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Operational Issue - link operating at 4QAM 80Mbps | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
W00714_HU | W066L_W00714IB_BGNMARA | DU00005180166 | Central | Kuala Lumpur | 3.157100 | 101.695000 | WK13 | MAR 25 | WK13 | MAR 25 | Cancel / Drop | Done under DU W00714 TX NIC | ZTE | 00. Site Out/Drop | 25/3/2025 : Mo need proceed. Done under DU W00714 TX NIC 19/3/2025 : CELCOM AXIATA BERHAD - INBUILDING - NE site W00714 W066L_W00714IB_BGNMARA, EDOTCO (M) SDN BHD - TRIPOD 9M ROOFTOP - FE site W00171 W066L_W00171OD_JLNTAR |  |  |  | Cancel / Drop | CANCEL/DROP DUE TO DONE UNDER NIC W00714 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25031549 |  | 2025-03-17 | 2025-03-25 | Completed | 2025-03-15 | 2025-03-17 | 2025-03-15 | 2025-03-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed
Q00782_HU | Q126A_Q00782OD_CB_KGMERITAM | DU00005180167 | Sarawak | Sarawak | 4.729430 | 114.869910 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-06-30 | HSU//MYET CHAE/6799000011
7170A_HU | Eden Condo | DU00005180168 | Sabah | Sabah | 5.934756 | 116.074330 |  |  |  |  | Pending TSSR |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | "15G_2+0_28M NE_7170A New 15G_0.6M(MS) x1. New RTN910A x1. New XMC_3, Sub A_Lo x2. FE_7000A New 15G_1.2M(MS) x1. New RTN910A x1. New XMC_3, Sub A_Hi x2. New CAT6 Cable with suitable length x1." | MW Parallel Link | "Existing HW Link 13G_4+0_28MHz_512QAM_CA&EPLA. Build new parallel link, HW MW Link 15G_2+0_28MHz_256QAM_EPLA. Combine existing HW MW Link and new HW MW Link and become HW MW Link 13G+15G_6+0_28MHz_512QAM+256QAM_CA&EPLA. Site Impacted : 7170A.(Ensure another traffic 7127D will not impacted as it share same RTN910A(RTN03) ISM8 slot 07 port 1 at CP site, 7000A). NE_7170A 1.Install new 15G_0.6M(MS) x1. 2.Install new 1xRTN910A(RTN02). Configure it. 3.Install new 2x XMC_3, Sub A_Lo and using ISM8 slot 07 port 1 & 2. Configure it. 4.Shifting existing ISM8 card from slot 03 & slot 04 of existing RTN910A(RTN01) into slot 03 & slot 04 of new RTN910A(RTN02). Configure it. 5.Configure CA & EPLA for existing 13G_4+0_28MHz_512QAM_CA&EPLA. Ensure modulation configured 512QAM. 6.Configure EPLA for new 15G_2+0_28MHz_256QAM_EPLA. Ensure modulation configured 256QAM. 7.Later will become 13G+15G_6+0_28MHz_512QAM+256QAM_CA&EPLA. 8.Configure DCN Inband. 9.Enable port 8-EM6-1 of new RTN910A(RTN02) and patching to BBU 7170A. 10.Migrate RAN Traffics(7170A)traffic to HW MW Link 13G+15G_6+0_28MHz_512QAM+256QAM_CA&EPLA. Configure it. 11.Existing RTN910A(RTN01) may proceed decom and send to warehouse. FE_7000A 1.Install new 15G_1.2M(MS) x1. 2.Install new 1xRTN910A(RTN07). Configure it. 3.Install new 2x XMC_3, Sub A_Hi and using ISM8 slot 07 port 1 & 2. Configure it. 4.Shifting existing ISM8 card from slot 03 & slot 04 of existing RTN910A(RTN03) into slot 03 & slot 04 of new RTN910A(RTN07). Configure it. 5.Configure CA & EPLA for existing 13G_4+0_28MHz_512QAM_CA&EPLA. Ensure modulation configured 512QAM. 6.Configure EPLA for new 15G_2+0_28MHz_256QAM_EPLA. Ensure modulation configured 256QAM. 7.Later will become 13G+15G_6+0_28MHz_512QAM+256QAM_CA&EPLA. 8.Configure DCN Inband. 9.Request new port at IBeam and new vlan services from ZTE IPRAN Team. 10.Enable port 8-EM6-1 of new RTN910A(RTN07) and patching to new port at IBeam. 11.Migrate RAN Traffics(7170A)traffic into new port at IBeam. Configure it. 12.Do not decom existing RTN910A(RTN03) as it still carry another traffic(7127D)." | "Existing HW Link 13G_4+0_28MHz_512QAM_CA&EPLA. Build new parallel link, HW MW Link 15G_2+0_28MHz_256QAM_EPLA. Combine existing HW MW Link and new HW MW Link and become HW MW Link 13G+15G_6+0_28MHz_512QAM+256QAM_CA&EPLA. Site Impacted : 7170A.(Ensure another traffic 7127D will not impacted as it share same RTN910A(RTN03) ISM8 slot 07 port 1 at CP site, 7000A). NE_7170A 1.Install new 15G_0.6M(MS) x1. 2.Install new 1xRTN910A(RTN02). Configure it. 3.Install new 2x XMC_3, Sub A_Lo and using ISM8 slot 07 port 1 & 2. Configure it. 4.Shifting existing ISM8 card from slot 03 & slot 04 of existing RTN910A(RTN01) into slot 03 & slot 04 of new RTN910A(RTN02). Configure it. 5.Configure CA & EPLA for existing 13G_4+0_28MHz_512QAM_CA&EPLA. Ensure modulation configured 512QAM. 6.Configure EPLA for new 15G_2+0_28MHz_256QAM_EPLA. Ensure modulation configured 256QAM. 7.Later will become 13G+15G_6+0_28MHz_512QAM+256QAM_CA&EPLA. 8.Configure DCN Inband. 9.Enable port 8-EM6-1 of new RTN910A(RTN02) and patching to BBU 7170A. 10.Migrate RAN Traffics(7170A)traffic to HW MW Link 13G+15G_6+0_28MHz_512QAM+256QAM_CA&EPLA. Configure it. 11.Existing RTN910A(RTN01) may proceed decom and send to warehouse." | "Existing HW Link 13G_4+0_28MHz_512QAM_CA&EPLA. Build new parallel link, HW MW Link 15G_2+0_28MHz_256QAM_EPLA. Combine existing HW MW Link and new HW MW Link and become HW MW Link 13G+15G_6+0_28MHz_512QAM+256QAM_CA&EPLA. Site Impacted : 7170A.(Ensure another traffic 7127D will not impacted as it share same RTN910A(RTN03) ISM8 slot 07 port 1 at CP site, 7000A). FE_7000A 1.Install new 15G_1.2M(MS) x1. 2.Install new 1xRTN910A(RTN07). Configure it. 3.Install new 2x XMC_3, Sub A_Hi and using ISM8 slot 07 port 1 & 2. Configure it. 4.Shifting existing ISM8 card from slot 03 & slot 04 of existing RTN910A(RTN03) into slot 03 & slot 04 of new RTN910A(RTN07). Configure it. 5.Configure CA & EPLA for existing 13G_4+0_28MHz_512QAM_CA&EPLA. Ensure modulation configured 512QAM. 6.Configure EPLA for new 15G_2+0_28MHz_256QAM_EPLA. Ensure modulation configured 256QAM. 7.Later will become 13G+15G_6+0_28MHz_512QAM+256QAM_CA&EPLA. 8.Configure DCN Inband. 9.Request new port at IBeam and new vlan services from ZTE IPRAN Team. 10.Enable port 8-EM6-1 of new RTN910A(RTN07) and patching to new port at IBeam. 11.Migrate RAN Traffics(7170A)traffic into new port at IBeam. Configure it. 12.Do not decom existing RTN910A(RTN03) as it still carry another traffic(7127D)." | XMC_3 | MS | 15G | 0.6 | 1.2 | NR services | SQ202504170485-NR Services | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services | 2026-01-26 | 2026-01-21 | Completed | 2025-04-09 | 2025-04-16 | 2025-04-13 | 2025-04-13 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-28 | 2025-12-05 | 2025-11-28 | 2025-11-28 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090209 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-09 | 2025-10-09 | 2025-09-09 | 2025-09-11 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-09-09 | 2025-10-09 | 2025-09-09 | 2025-09-13 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-17 | 2025-09-09 | 2025-10-09 | 2025-09-09 | 2025-09-22 | RALPH O'BRYAN HILARY7167000030 | 2025-09-09 | 2025-10-09 | 2025-09-09 | 2025-09-12 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506160769-GTSB
Q01639_HU | QS50209_4_1-KGPUNAU | DU00005180169 | Sarawak | Sarawak | 1.344360 | 110.305950 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB
Q01919_HU | Q141A_Q01919OD_SMKGEDONG | DU00005180170 | Sarawak | Sarawak | 1.215181 | 110.693025 |  |  |  |  | Pending SOW |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6m/0.6m_MDD_1+0_110Mhz_512Q_778Mbps (XMC 5D sub B) | MW Swap | MW SWAP Q01919-Q00510 WITH 18G_1+0_0.6/0.6_MDD_110mHZ_256QAM | MW SWAP Q01919-Q00510 WITH 18G_1+0_0.6/0.6_MDD_110mHZ_256QAM NE: 1. Swap exisitng IDU with RTN910A. 2. Swap existing ODU with XMC_5D_SB B 3. Swap exisitng antenna with 18G-0.6 MDD. 4. Configure 18G_1+0_0.6/0.6_110Mhz_256QAM | MW SWAP Q01919-Q00510 WITH 18G_1+0_0.6/0.6_MDD_110mHZ_256QAM FE: 1. Swap exisitng IDU with RTN910A. 2. Swap existing ODU with XMC_5D_SB B 3. Swap exisitng antenna with 18G-0.6 MDD. 4. Configure 18G_1+0_0.6/0.6_110Mhz_256QAM | XMC-5D B | MDD | 18G | 0.6 | 0.6 | Trintel | SQ202507140747-Trintel | Allstar | SQ202507190104-Allstar // SQ202507190105-Allstar | 2025-07-18 | 2025-07-18 | Completed | 2025-07-10 | 2025-07-12 | 2025-07-10 | 2025-07-12 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-18 | 2025-07-14 | 2025-07-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-18 | 2025-07-14 | 2025-07-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071437 |  | 2025-07-15 | 2025-07-18 | Completed | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-18 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-18 | 2025-07-24 | 2025-07-19 | 2025-07-19 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-07-18 | 2025-07-24 | 2025-07-19 | 2025-07-24 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-24 | 2025-07-18 | 2025-07-24 | 2025-08-13 | 2025-08-13 | BONG NEE NYEEbong.allstar@gmail.com | 2025-07-18 | 2025-07-24 | 2025-07-21 | 2025-07-21 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-07 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202505020435-GTSB | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | HSU//MYET CHAE/6799000011
Q00236_HU | Q139A_Q00236OD_CB_KRUSEN | DU00005180171 | Sarawak | Sarawak | 1.049240 | 110.505160 |  |  |  |  | Pending SOW |  |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | PTN WIP | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | HSU//MYET CHAE/6799000011
7512A_HU | Morisem | DU00005180172 | Sabah | Sabah | 5.504748 | 118.395624 | [5 empty] | Link perf under monitoring |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G 2+0 1.8m/1.8m MAC DP XMC3 sub A/B NE: 1) 1 x RTN910A 2) 1 x ISM8 cards 2) 1 x 13G XMC3 sub A Lo 4) 1 x 13G XMC3 sub B Lo 5) 1 x 13G 1.8m MAC DP FE: 1) 1 x ISM8 cards 2) 1 x 13G XMC3 sub A Hi 4) 1 x 13G XMC3 sub B Hi 5) 1 x 13G 1.8m MAC DP | MW Parallel Link | Add parallel 2+0 to existing 2+0 link NE install new IDU and transfer IF card for existing link FE add ISM card to existing IDU Create 4+0 EPLA NE (7512A): 1) Install new RTN910A 2) Add ISM8 card slot 3 3) Install new link at 3-ISM8 4) Transfer existing link from 7512A RTN06 3-ISM8 to new RTN 7-ISM8 5) Create 4+0 EPLA 6) Patch 7512A RTN13 GE1 to new RTN GE1 7) Patch 7512A MORISEM RTN510 EB to new RTN GE2 FE (7585A SUKAU RTN13): 1) Add ISM8 card slot 3 2) Install new link at 3-ISM8 3) Create 4+0 EPLA | NE (7512A): 1) Install new RTN910A 2) Add ISM8 card slot 3 3) Install new link at 3-ISM8 4) Transfer existing link from 7512A RTN06 3-ISM8 to new RTN 7-ISM8 5) Create 4+0 EPLA 6) Patch 7512A RTN13 GE1 to new RTN GE1 7) Patch 7512A MORISEM RTN510 EB to new RTN GE2 | FE (7585A SUKAU RTN13): 1) Add ISM8 card slot 3 2) Install new link at 3-ISM8 3) Create 4+0 EPLA | XMC3 | MAC DP | 13G | 1.8m | 1.8m | GCI | SQ202510010671-GCI | GCI | SQ202509130054-GCI // SQ202509130055-GCI | 2025-12-23 | 2025-12-16 | Completed | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | Ling/Tao6800000135 | GCI TI | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Ling/Tao6800000135 | GCI TI | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-10 | 2025-12-03 | 2025-12-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090222 |  | 2025-09-08 | 2025-09-08 | Completed | 2025-09-08 | 2025-09-08 | 2025-09-02 | 2025-09-08 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-08 | 2025-09-30 | 2025-09-12 | 2025-09-12 | JACKSON//BIN MAKANSIM/6000027984 | GCI TI | 2025-09-08 | 2025-09-30 | 2025-10-08 | 2025-10-08 | JACKSON//BIN MAKANSIM/6000027984 | GCI TI | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-14 | 2025-09-08 | 2025-09-30 | 2025-10-21 | 2025-10-21 | JACKSON//BIN MAKANSIM/6000027984 | 2025-09-30: 2025-09-08; 2025-09-30: 2025-09-30; 2025-09-30: 2025-09-12; 2025-10-08: 2025-09-12 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
Q01323_HU | Q122A_Q01323OD_CB_RHBENYAMIN | DU00005180173 | Sarawak | Sarawak | 2.068747 | 112.148411 |  |  |  |  | Pending SOW |  | ZTE | 03. Pending TSS |  | TSS+AA+TI+Dismantle |  | 15G_2+0_1.2/0.6_DP 2xRTN910A 2xXMC_3_SB A | MW Swap | MW SWAP Q01323-Q00206 WITH 15G_2+0_1.2/0.6_DP_SB A,B | MW SWAP Q01323-Q00206 WITH 15G_2+0_1.2/0.6_DP_SB A,B NE: 1. Swap exisiting RTN910 with RTN910A. 2. Install new XMC-3_SB A and reuse exisitng SB B. 3. Swap existing antenna with 15G_1.2_DP. 4. Configure 15G_2+0_1.2/0.6_1024QAM_EPLA. | MW SWAP Q01323-Q00206 WITH 15G_2+0_1.2/0.6_DP_SB A,B FE: 1. Swap exisiting RTN910 with RTN910A. 2. Install new XMC-3_SB A and reuse exisitng SB B. 3. Swap existing antenna with 15G_1.2_DP. 4. Configure 15G_2+0_1.2/0.6_1024QAM_EPLA. | XMC-3 | DP_MS | 15G | 1.2 | 0.6 | Trintel | SQ202509040637-Trintel | YPTT | SQ202509040643-YPTT // SQ202509040648-YPTT |  |  | Ongoing | 2025-12-19 | 2025-12-31 | 2025-12-19 | 2025-12-22 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-24 | 2025-12-31 | 2025-12-24 | 2025-12-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26032631 | DO Canceled (More than 30 days) | 2026-03-27 |  | Ongoing | 2026-03-26 | 2026-03-27 | 2026-03-26 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | HSU//MYET CHAE/6799000011
Q00792_HU | Q144A_Q00792OD_CB_KUALATATAU | DU00005180174 | Sarawak | Sarawak | 3.078503 | 112.814830 |  |  |  |  | Pending SOW |  |  | 03. Pending TSSR Approval |  | TSS+AA+TI+Dismantle |  | 13G_4+0_1.2/1.8_MDD_SB A 2xRTN910A 3xISM8 | MW New Link / Reroute | 1st MW NEWLINK/REROUTE TO Q00792-9125A WITH 13G_4+0_1.2/1.8_MDD_SB A.DSMANTLE Q00792-Q00258 LINK. | 1st MW NEWLINK/REROUTE TO Q00792-9125A WITH 13G_4+0_1.2/1.8_MDD_SB A NE: 1. Install new RTN910A 2. Install new 2xISM8 at slot 3 and 4. 3. Install new antenna 13G_1.2_MDD. 4. Configure 13G_4+0_1.2/1.8_MDD_CA 5. Dismantle Q00792-Q00258 | 1st MW NEWLINK/REROUTE TO Q00792-9125A WITH 13G_4+0_1.2/1.8_MDD_SB A FE: 1. Install new RTN910A 2. Install new 1xISM8 at slot 3. 3. Install new antenna 13G_1.2_MDD. 4. Configure 13G_4+0_1.2/1.8_MDD_CA 5. Dismantle Q00792-Q00258 | XMC-5D A | MDD | 13G | 1.2 | 1.8 | Allstar | SQ202506260783-Allstar | Magicell | SQ202510240603-Magicell // SQ202510240608-Magicell | 2025-12-02 | 2025-11-26 | Completed | 2025-06-23 | 2025-06-25 | 2025-06-25 | 2025-06-25 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-09-08 | 2025-09-12 | 2025-09-08 | 2025-09-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-08 | 2025-09-12 | 2025-09-08 | 2025-09-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102357 |  | 2025-10-25 | 2025-10-24 | Completed | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | HSU//MYET CHAE/6799000011
S00183_HU | S089A_S00183OD_CB_KUALASAPI | DU00005180175 | Sabah | Sabah | 5.823174 | 117.440578 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020434-GTSB | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | HSU//MYET CHAE/6799000011
S01485_HU | S091A_S01485OD_CB_AMPLEVALLEY | DU00005180176 | Sabah | Sabah | 5.598600 | 118.077200 |  |  |  |  | Pending TSS | 2X 1.2M MDD ANTENNA (15G) |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2x IDU RTN910A 2X 1.2M MDD ANTENNA (15G) 1x ODU 15G XMC-5D SB_B HI 1x ODU 15G XMC-5D SB_B LO | MW Swap | SWAP LINK S01485-S00210 WITH HUAWEI_15G_2+0_28MHZ_512QAM_448Mbps_1.2M/1.2M_MDD_XMC-5D_SUB B_5.32KM IMPACTED: S01485 DISMANTLE EXISTING LINK (SM) | NE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. DISMANTLE EXISTING LINK (SM) | FE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. CONNECT IDU TO CISCO ROUTER FOLLOW EXISTING CONNECTION 6. DISMANTLE EXISTING LINK (SM) | XMC-5D | MDD | 15G | 1.2m | 1.2m | NR services | SQ202507080871-NR Services | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-07-04 | 2025-07-06 | 2025-07-04 | 2025-07-06 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-25 | 2025-07-24 | 2025-07-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090218 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-17 | 2025-10-17 | 2025-09-17 | 2025-09-18 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-09-17 | 2025-10-17 | 2025-09-17 | 2025-09-30 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-25 | 2025-09-17 | 2025-10-17 | 2025-09-17 | 2025-09-30 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-09-17 | 2025-10-17 | 2025-09-17 | 2025-09-18 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505020434-GTSB | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | AB.RAHMAN//BIN MAT NOOH/6237001519
A00286_HU | A041A_A00286OD_KGRAMBAI | DU00005180177 | Northern | Perak | 4.688900 | 100.981700 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_2+0_28M NE_A00286 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub_A_Lo x1. FE_A00211. 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW Swap | Existing link 13G_1+0_28M Swap existing link to 13G_2+0_28M Site Impacted : A00286 NE_A00286 1.Install new 13G_DP_1.2M(MDD) 2.Install new RTN910A , 7_ISM8_2+0. 3.Install new XMC_5D , Sub_A_Lo. 4.Create service cross connect and EPLA. 5.Traffic A00286_BBU migrate to new link 13G_2+0_28M. 6.Decom existing MW link (A00286 - A00211)_NT02613. FE_A00211. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Migrate tarffic to new link 13G_2+0_28M. 6.Enable GE1 , ETH patching to existing (NT05967) A00211 RTN910_GE3 (ID : 31090). 7.Decom existing MW link (A00211 - A00286)_NT02613. | Existing link 13G_1+0_28M Swap existing link to 13G_2+0_28M Site Impacted : A00286 NE_A00286 1.Install new 13G_DP_1.2M(MDD) 2.Install new RTN910A , 7_ISM8_2+0. 3.Install new XMC_5D , Sub_A_Lo. 4.Create service cross connect and EPLA. 5.Traffic A00286_BBU migrate to new link 13G_2+0_28M. 6.Decom existing MW link (A00286 - A00211)_NT02613. | Existing link 13G_1+0_28M Swap existing link to 13G_2+0_28M Site Impacted : A00286 FE_A00211. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Migrate tarffic to new link 13G_2+0_28M. 6.Enable GE1 , ETH patching to existing (NT05967) A00211 RTN910_GE3 (ID : 31090). 7.Decom existing MW link (A00211 - A00286)_NT02613. | XMC_5D | MDD | 13G | 1.2 | 1.2 | Magicell | SQ202506050553-Magicell | Magicell | SQ202505240109-Magicell // SQ202505240110-Magicell // SQ202507290130-Magicell | 2025-12-10 | 2025-12-10 | Completed | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250520AA |  | 2025-05-21 | 2025-05-22 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-30 | 2026-05-19 | 2025-05-30 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 | Magicell TI | 2025-05-30 | 2026-05-19 | 2025-05-30 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 | Magicell TI | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-03 | 2025-05-30 | 2026-05-19 | 2025-05-30 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 | 2025-09-30: 2025-05-30; 2025-09-30: 2026-05-19; 2025-09-30: 2025-05-30; 2025-10-08: 2025-06-20 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505020432-GCI | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-11 | CHEONG/SENG/WAH/7018000306
A00481_HU | A041A_A00481OD_CB_BEKUT | DU00005180178 | Northern | Perak | 4.914800 | 100.991900 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Existing SM link 13G_1+0_28M (NT04365) has swapped to Huawei link 13G_2+0_28M 4281K/A00481 - 4434B/A00464 , History Utilization 22 % (Apr 28 - 5 May) , low than 70%. | Existing SM link 13G_1+0_28M (NT04365) has swapped to Huawei link 13G_2+0_28M 4281K/A00481 - 4434B/A00464 , History Utilization 22 % (Apr 28 - 5 May) , low than 70%. | [12 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505020432-GCI | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-06 | CHEONG/SENG/WAH/7018000306
7221R_HU | Kg Terusan | DU00005180179 | Sabah | Sabah | 4.991430 | 118.272380 |  |  |  |  | RFS | DONE |  | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | To perform remote upgrade from 56MHz to 112MHz | To perform remote upgrade from 56MHz to 112MHz | To perform remote upgrade from 56MHz to 112MHz | [5 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 | [17 empty] | 2025-05-29 | 2025-06-29 | 2025-05-29 | 2025-05-29 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202512290823-GTSB
7337B_HU | Kg Tamau | DU00005180180 | Sabah | Sabah | 6.421362 | 116.418631 |  |  |  |  | Cancel/Drop |  |  | 00. Site Out/Drop |  |  |  | 15G 2+0 1.2m/1.2m DP XMC3 sub A&B NE: 1) 1 x 15G XMC3 sub A Lo 2) 1 x 15G XMC3 sub B Lo 3) 1 x 15G 1.2m MAC DP FE: 1) 1 x 15G XMC3 sub A Hi 2) 1 x 15G XMC3 sub B Hi 3) 1 x 15G 1.2m MAC DP | Cancel / Drop | 03 Jul 2025 - Cancel/drop. Under Huawei Add parallel 2+0 to existing 4+0 link Use existing IDU Create 6+0 EPLA NE (7337B-KG TAMAU-RTN01): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA FE (7401A-RTM STATION-RTN01): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA | NE (7337B-KG TAMAU-RTN01): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA | FE (7401A-RTM STATION-RTN01): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA | XMC3 | MAC DP | 15G | 1.2m | 1.2m | NR services | No PR required-Site drop/cancel |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S00607_HU | S090A_S00607OD_CB_TMSIGAPON | DU00005180181 | Sabah | Sabah | 5.268200 | 116.055600 |  |  |  |  | Pending TM Permit | TM Access |  | 02. Pending Access |  | TSS+AA+TI+Dismantle |  | 2x IDU RTN910A 2x ISM8 2x 1.8M MDD ANTENNA (13G) 2x COUPLER 13G 1x ODU 13G XMC-5D SB_A HI 1X ODU 13G XMC-5D SB_A LO 1x ODU 13G XMC-5D SB_B HI 1x ODU 13G XMC-5D SB_B LO 1x Cat6 cable | MW New Link / Reroute | BUILD NEW MW LINKS00607-7063A WITH HUAWEI_13G_4+0_28MHZ_128QAM_688Mbps_1.8/1.8M_MDD_XMC-5D SB A+B_14.3KM IMPACT SITE: S00607 THIS NEW LINK ONLY CARRY S00607 BBU, OTHER CHILD SITE REMAIN AT EXISTNG MW | NE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ISM8 CARD AT SLOT 3 3. INSTALL NEW 13G 1.8M MDD ANTENNA 4. INSTALL NEW 13G XMC-5D SUB BAND A AND B 5. CONFIGURE LINK 13G 4+0 28MHZ 128QAM 6. BBU WILL CONNECT TO NEW IDU | FE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ISM8 CARD AT SLOT 3 3. INSTALL NEW 13G 1.8M MDD ANTENNA 4. INSTALL NEW 13G XMC-5D SUB BAND A AND B 5. CONFIGURE LINK 13G 4+0 28MHZ 128QAM 6. CONNECT NEW IDU TO NEW PORT IPRAN | XMC-5D | MDD | 13G | 1.8m | 1.8m | YPTT | SQ202509090114-YPTT | YPTT | SQ202511190841-YPTT // SQ202511190844-YPTT | 2025-11-24 | 2025-11-17 | Completed | 2025-09-07 | 2025-09-07 | 2025-09-07 | 2025-09-07 | DOMINIC DAVIES6794000049 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-17 | 2025-11-24 | 2025-11-17 | 2025-11-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111008 |  | 2025-11-11 | 2025-11-15 | Completed | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | DOMINIC DAVIES6794000049 | YPTT TI | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | DOMINIC DAVIES6794000049 | YPTT TI | [7 empty] | 2025-11-23 | 2025-11-23 | 2025-11-23 |  | RUDDY TUIS @ YUIS7023000023 | 2025-09-30: 2026-01-29; 2025-09-30: 2026-01-29; 2025-09-30: 2026-01-29; 2025-10-08: 2026-01-29 | [7 empty] | GTSB | SQ202505020434-GTSB | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | AB.RAHMAN//BIN MAT NOOH/6237001519
K00813_HU | K008A_K00813OD_CB_JLN_ISTANABKT_MALUT | DU00005180182 | Northern | Kedah | 6.313324 | 99.784553 | [7 empty] | 00. Integrated/RFS Done | 04/07: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Existing SM link 18G_1+0_56M (NT05094) Swap existing to 18G_2+0_112M Site impacted : 4012D NE_K00813 18G_DP_0.6M(MDD) x1. 2.Install new RTN910A x1. XMC_5D , Sub B_Lo. FE_K00662 18G_DP_0.6M(MDD). RTN910A x1. XMC_5D , Sub B_Hi. | MW Swap | Existing SM link 18G_1+0_56M (NT05094) Swap existing to 18G_2+0_112M Site impacted : K00813. NE_K00813 1.Install new 18G_DP_0.6M(MDD) 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link 18G_2+0_112M. 6.Decom existing SM link(NT05094). FE_K00662 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross connect and EPLA. 5.Migrate traffic to new link 18G_2+0_112M. 6.Create new In band DCN, 7.Decom existing SM link(NT05094).] | Existing SM link 18G_1+0_56M (NT05094) Swap existing to 23G_2+0_112M Site impacted : K00813. NE_K00813 1.Install new 23G_DP_0.6M(MAC) 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link 23G_2+0_112M. 6.Decom existing SM link(NT05094). | Existing SM link 18G_1+0_56M (NT05094) Swap existing to 23G_2+0_112M Site impacted : K00813. FE_K00662 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Migrate traffic to new link 23G_2+0_112M. 6.Create new In band DCN, 7.Decom existing SM link(NT05094).] | XMC_5D | MDD | 218G | 0.6 | 0.6 | GCI | SQ202507250118-GCI | GCI | SQ202506160513-GCI // SQ202506160540-GCI // SQ202507160767-GCI | 2026-01-20 | 2026-01-19 | Completed | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051997 |  | 2025-05-20 | 2025-05-23 | Completed | 2025-05-19 | 2025-05-20 | 2025-05-19 | 2025-05-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-16 | 2025-06-30 | 2025-06-16 | 2025-07-24 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-06-16 | 2025-06-30 | 2025-06-16 | 2025-07-16 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AKMAL//BIN RAZALI/6794000078 |  |  | 2025-06-16 | 2025-06-30 | 2025-06-16 | 2025-12-19 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-06-16 | 2025-06-30 | 2025-06-16 | 2025-07-07 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | CHEONG/SENG/WAH/7018000306
B02424_HU | B061M_B02424OD_PSRN_DSARAINDAH | DU00005180183 | Central | Selangor | 3.143301 | 101.591401 | WK13 | APR 25 | WK16 | APR 25 | TI | Doable | ZTE | 00. Integrated/RFS Done | 19/3/2025 : KONSORTIUM INFRASTRUKTUR W.P. SDN BHD - LAMP POLE 30M LAND - NE site B02424 B061M_B02424OD_PSRN_DSARAINDAH, SBC KJS - 24M Lampole - FE site 2104A Sek4 Kota Damansara, EDOTCO (M) SDN BHD - LAMP POLE 24M ROOFTOP - Patching site B00443 B061M_B00443OD_SEK4KOTADSARA | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 1X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO FE IDU PATCHING TO OB FIBER | MW New Link / Reroute | MW NEWLINK B02424-2104A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB A_1.45KM FE IDU PATCHING AT 2104A TO B00443 OB FIBER IMPACTED: B02424 | 1. INSTALL NEW RTN910 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK B02424-B00443 | 1. INSTALL NEW RTN910 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. IDU PATCHING AT 2104A TO B00443 OB FIBER 6. DISMANTLE EXISTING LINK B02424-B00443 | XMC3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202504280336-GCI | GCI | SQ202505190285-GCI // SQ202505190292-GCI | 2025-10-25 | 2025-10-27 | Completed | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-29 | 2025-05-30 | 2025-05-29 | 2025-05-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031546 |  | 2025-03-17 | 2025-03-27 | Completed | 2025-03-15 | 2025-03-17 | 2025-03-15 | 2025-03-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-17 | 2025-05-24 | 2025-05-16 | 2025-05-21 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-05-17 | 2025-05-24 | 2025-05-16 | 2025-05-21 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-18 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-17 | 2025-05-24 | 2025-05-16 | 2025-05-26 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-05-17 | 2025-05-24 | 2025-05-16 | 2025-05-17 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00675_HU | Q132A_Q00675OD_T3_BT46BTUMYY | DU00005180184 | Sarawak | Sarawak | 3.450041 | 113.557902 |  |  |  |  | Pending SOW |  |  | 02. Pending EB CRQ | 19/9/2025 : Alignment done, pending cutover 18/9/2025 : Plan to continue alignment and cutover - Cancel due to late receive keys 17/9/2025 : Plan to continue alignment and cutover - Cancel proceed 13/9/2025 : Plan to continue alignment and cutover - Re-plan due to raining day 26/8/2025 : Alignment still not complete, need 2 pices ISM8 - cancel proceed 25/8/2025 : Alignment still not complete, need 2 pices ISM8 23/8/2025 : Alignment WIP 22/8/2025 : Installation complete, pending alignment 20/8/2025 : Plan to do MW Swap - MOS activity only | TSS+AA+TI+Dismantle |  | 15G_4+0_28M_512QAM_CA NE_Q00675 New 15G_1.2M(MDD) x1. New RTN910AF x1. New ISM8 x1. New XMC_5D, Sub A_Lo x2. New CAT6 cable x1. FE_Q00509 New 15G_1.2M(MDD) x1. New RTN910AF x1. New ISM8 x1. New XMC_5D, Sub A_Hi x2. New CAT6 cable x1. | MW Swap | ***IMPORTANT NOTE:*** 1.NEED TO INSTALL NEW MW PARALLEL UPLINK FIRST FOR Q00509-Q00268 AND PERFORM LOAD BALANCING. 2.PHYSICAL FREQ SCANNING REQUIRE IN ORDER TO OBTAIN FREE CHANNEL FROM INTERFERENCES. Existing HW MW Link Q00675-Q00509, 15G_2+0_28MHZ_2048QAM_546. Swap to new HW MW Link Q00675-Q00509, 15G_4+0_28MHZ_512QAM_896. Later, decom existing HW MW Link Q00675-Q00509, 15G_2+0_28MHZ_2048QAM_546. Site Impacted : Q01815, Q02113(EB PEKAKA ESTATE) & Q02116(EB SDP CHARTQUEST ESTATE). NE_Q00675 1.Install New 15G_1.8M(MS) x1. 2.Install new RTN910AF(RTN01) x1 and insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01). 3.Install new XMC_3, Sub A&B_Lo x2. 4.Build new HW MW Link Q00675-Q00509, 15G_4+0_28MHZ_512QAM_896. 5.Disconnect cascade between port 8-EM6-2 of existing RTN910AF(NEID 28441)and port 8-EM6-1 of existing RTN910AF(NEID 38347). 6.Remove RTN910AF((NEID 28441). 8.Enable port 8-EM6-1 of new RTN910AF(RTN01). Cascade to existing RTN910AF(NEID (NEID 38347). 9.Re-use existing Vlan DCN and Vlan Services. 10.Migrate traffics Q01815 and EB Q02113(EB PEKAKA ESTATE) into new HW MW Link Q00675-Q00509, 15G_4+0_28MHZ_512QAM_896. 11.Need to request CRQ for 2x EB sites which are Q02113(EB PEKAKA ESTATE) and Q02116(EB SDP CHARTQUEST ESTATE). FE_Q00509 1.Install New 15G_1.8M(MS) x1. 2.Install new RTN910AF(RTN02) x1 and insert new ISM8 x1 into slot 03 of new RTN910AF(RTN02). 3.Install new XMC_3, Sub A&B_Hi x2. 4.Build new HW MW Link Q00675-Q00509, 15G_4+0_28MHZ_512QAM_896. 5.Disconnect cascade between port 8-EM6-1 of existing RTN910AF(NEID 28442)and port 8-EM6-1 of existing RTN910AF(NEID 35136). 6.Disconnect existing CAT6 cable for site EB Chartquest Estate from port 8-EM6-2 of existing RTN910AF(NEID 28442) 7.Remove RTN910AF((NEID 28442). 8.Enable port 8-EM6-1 of new RTN910AF(RTN02). Cascade to port 8-EM6-1 of existing RTN910AF(NEID 35136). 9.Enable port 8-EM6-2 of new RTN910AF(RTN02). Patching to site EB Chartquest Estate. 10.Re-use existing Vlan DCN and Vlan Services. 11.Migrate traffics Q01815, EB Q02113(EB PEKAKA ESTATE) & Q02116(EB SDP CHARTQUEST ESTATE) into new HW MW Link Q00675-Q00509 , 15G_4+0_28MHZ_512QAM_896. 12.Need to request CRQ for 2x EB sites which are Q02113(EB PEKAKA ESTATE) and Q02116(EB SDP CHARTQUEST ESTATE). | ***IMPORTANT NOTE:*** 1.NEED TO INSTALL NEW MW PARALLEL UPLINK FIRST FOR Q00509-Q00268 AND PERFORM LOAD BALANCING. 2.PHYSICAL FREQ SCANNING REQUIRE IN ORDER TO OBTAIN FREE CHANNEL FROM INTERFERENCES. Existing HW MW Link Q00675-Q00509, 15G_2+0_28MHZ_2048QAM_546. Swap to new HW MW Link Q00675-Q00509, 15G_4+0_28MHZ_512QAM_896. Later, decom existing HW MW Link Q00675-Q00509, 15G_2+0_28MHZ_2048QAM_546. Site Impacted : Q01815, Q02113(EB PEKAKA ESTATE) & Q02116(EB SDP CHARTQUEST ESTATE). NE_Q00675 1.Install New 15G_1.8M(MS) x1. 2.Install new RTN910AF(RTN01) x1 and insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01). 3.Install new XMC_3, Sub A&B_Lo x2. 4.Build new HW MW Link Q00675-Q00509, 15G_4+0_28MHZ_512QAM_896. 5.Disconnect cascade between port 8-EM6-2 of existing RTN910AF(NEID 28441)and port 8-EM6-1 of existing RTN910AF(NEID 38347). 6.Remove RTN910AF((NEID 28441). 8.Enable port 8-EM6-1 of new RTN910AF(RTN01). Cascade to existing RTN910AF(NEID (NEID 38347). 9.Re-use existing Vlan DCN and Vlan Services. 10.Migrate traffics Q01815 and EB Q02113(EB PEKAKA ESTATE) into new HW MW Link Q00675-Q00509, 15G_4+0_28MHZ_512QAM_896. 11.Need to request CRQ for 2x EB sites which are Q02113(EB PEKAKA ESTATE) and Q02116(EB SDP CHARTQUEST ESTATE). | ***IMPORTANT NOTE:*** 1.NEED TO INSTALL NEW MW PARALLEL UPLINK FIRST FOR Q00509-Q00268 AND PERFORM LOAD BALANCING. 2.PHYSICAL FREQ SCANNING REQUIRE IN ORDER TO OBTAIN FREE CHANNEL FROM INTERFERENCES. Existing HW MW Link Q00675-Q00509, 15G_2+0_28MHZ_2048QAM_546. Swap to new HW MW Link Q00675-Q00509, 15G_4+0_28MHZ_512QAM_896. Later, decom existing HW MW Link Q00675-Q00509, 15G_2+0_28MHZ_2048QAM_546. Site Impacted : Q01815, Q02113(EB PEKAKA ESTATE) & Q02116(EB SDP CHARTQUEST ESTATE). FE_Q00509 1.Install New 15G_1.8M(MS) x1. 2.Install new RTN910AF(RTN02) x1 and insert new ISM8 x1 into slot 03 of new RTN910AF(RTN02). 3.Install new XMC_3, Sub A&B_Hi x2. 4.Build new HW MW Link Q00675-Q00509, 15G_4+0_28MHZ_512QAM_896. 5.Disconnect cascade between port 8-EM6-1 of existing RTN910AF(NEID 28442)and port 8-EM6-1 of existing RTN910AF(NEID 35136). 6.Disconnect existing CAT6 cable for site EB Chartquest Estate from port 8-EM6-2 of existing RTN910AF(NEID 28442) 7.Remove RTN910AF((NEID 28442). 8.Enable port 8-EM6-1 of new RTN910AF(RTN02). Cascade to port 8-EM6-1 of existing RTN910AF(NEID 35136). 9.Enable port 8-EM6-2 of new RTN910AF(RTN02). Patching to site EB Chartquest Estate. 10.Re-use existing Vlan DCN and Vlan Services. 11.Migrate traffics Q01815, EB Q02113(EB PEKAKA ESTATE) & Q02116(EB SDP CHARTQUEST ESTATE) into new HW MW Link Q00675-Q00509 , 15G_4+0_28MHZ_512QAM_896. 12.Need to request CRQ for 2x EB sites which are Q02113(EB PEKAKA ESTATE) and Q02116(EB SDP CHARTQUEST ESTATE). | XMC-5D A | MDD | 15G | 15G_1.2M(MDD) x1 | 15G_1.2M(MDD) x1 | Allstar | SQ202506260783-Allstar | Magicell | SQ202508200602-Magicell // SQ202508200604-Magicell | 2026-01-26 | 2026-01-21 | Completed | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-07-10 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-29 | 2026-01-05 | 2025-12-29 | 2025-12-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081176 |  | 2025-08-12 | 2025-08-18 | Completed | 2025-08-11 | 2025-08-12 | 2025-08-11 | 2025-08-18 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-31 | 2025-08-20 | 2026-01-29 | MOHAMMAD AMIR RAZDIMAN7018000263 | Magicell TI | 2025-08-20 | 2025-08-31 | 2025-08-20 |  | MOHAMMAD AMIR RAZDIMAN7018000263 | Magicell TI | [7 empty] | 2025-08-20 | 2025-08-31 | 2025-08-20 |  | MOHAMMAD AMIR RAZDIMAN7018000263 | 2025-09-30: 2025-08-20; 2025-09-30: 2025-08-31; 2025-09-30: 2025-08-20; 2025-10-08: 2025-08-22 | [7 empty] | GTSB | SQ202505020435-GTSB | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | HSU//MYET CHAE/6799000011
S00186_HU | S112A_S00186OD_CB_SOGOSOGO | DU00005180185 | Sabah | Sabah | 5.362920 | 116.960800 |  |  |  |  | Pending TSS | MwODU-ODU XMC-5D_13G_Subband B_High |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_1.8/1.2_MDD_XMC-5D SB B | MW Parallel Link | MW PARALLEL LINK S00186-S00219 WITH 13G_2+0_1.8/1.2_MDD_XMC-5D_SB B_EPLA WITH EXISITNG LINKS | MW PARALLEL LINK S00186-S00219 WITH 13G_2+0_1.8/1.2_MDD_XMC-5D_SB B_EPLA NE: 1. Reuse existing RTN910A 2. install new ISM 8 at sslot 4. 3. Install new XMC-5D_SB B. 4. Install 13G_1.8m_MDD. 5. Configure 13G_2+0_1.8/1.2_256QAM_EPLA with existing tx. | MW PARALLEL LINK S00186-S00219 WITH 13G_2+0_1.8/1.2_MDD_XMC-5D_SB B_EPLA FE: 1. Reuse existing RTN910A 2. install new ISM 8 at sslot 4. 3. Install new XMC-5D_SB B. 4. Install 13G_1.8m_MDD. 5. Configure 13G_2+0_1.8/1.2_256QAM_EPLA with existing tx. | XMC-5D_SB B |  | 13G | 1.8 | 1.2 | NR services | SQ202507080871-NR Services | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090215 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-10 | 2025-10-10 | 2025-09-10 | 2025-09-12 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-09-10 | 2025-10-10 | 2025-09-10 | 2025-09-22 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-24 | 2025-09-10 | 2025-10-10 | 2025-09-10 | 2025-09-29 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-09-30: 2025-09-10; 2025-09-30: 2025-10-10; 2025-09-30: 2025-09-10; 2025-10-08: 2025-09-12 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505020434-GTSB | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | HSU//MYET CHAE/6799000011
Q00269_HU | Q142A_Q00269OD_RH_DINGON | DU00005180186 | Sarawak | Sarawak | 2.840140 | 112.781700 |  |  |  |  | Pending SOW |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 8G_2+0_1.8/1.8 DP_SB A,B 2xISM8 | MW Parallel Link | MW PARALLEL LINK Q00269-Q00865 WITH 8G_2+0_1.8/1.8 DP_SB A,B | MW PARALLEL LINK Q00269-Q00865 WITH 8G_2+0_1.8/1.8 DP_SB A,B | MW PARALLEL LINK Q00269-Q00865 WITH 8G_2+0_1.8/1.8 DP_SB A,B FE: 1. Reuse exisitng RTN910A. 2. Install new ISM8 at slot 3. 3. Install new XMC-3 _SB A,B. 4. Install new 7G_1.8m DP. 5. Configure 8G_2+0_1.8/1.8_512QAM_EPLA with exizitng 2+0 link. | XMC_3 |  | 8 | 1,8 | 1.8 | Allstar | SQ202506260783-Allstar | Trintel | SQ202509040608-Trintel // SQ202509040617-Trintel | 2025-11-17 | 2025-11-10 | Completed | 2025-06-24 | 2025-06-25 | 2025-06-25 | 2025-06-25 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25101647 |  | 2025-10-17 | 2025-11-20 | Completed | 2025-10-16 | 2025-10-17 | 2025-10-16 | 2025-11-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-25 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-12-02 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-02 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-12-17 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2025-09-30: 2025-11-12; 2025-09-30: 2025-11-12; 2025-09-30: 2025-11-12; 2025-10-08: 2025-11-25 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202505020435-GTSB | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | HSU//MYET CHAE/6799000011
A00521_HU | FELDABESOUT4 | DU00005180187 | Northern | Perak | 3.778200 | 101.276400 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | BBU Patching | BBU PATCHING FROM EXISTING SM IDU A00521 TO HW IDU 4781B RTN01 TO USE LINK 4781B-A00553 | BBU PATCHING FROM EXISTING SM IDU A00521 TO HW IDU 4781B RTN01 TO USE LINK 4781B-A00553 | [6 empty] | Magicell | SQ202506250171-Magicell | Magicell | SQ202505240110-Magicell |  |  | Ongoing | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-06-30 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052037 |  | 2025-05-21 | 2025-05-22 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-19 | 2026-06-17 | 2025-06-19 | 2025-06-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 | Magicell TI | 2025-06-19 | 2026-06-17 | 2025-06-19 | 2025-06-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 | Magicell TI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-23 | 2025-06-19 | 2026-06-17 | 2025-06-19 | 2025-06-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 | 2025-09-30: 2025-06-19; 2025-09-30: 2026-06-17; 2025-09-30: 2025-06-19; 2025-10-08: 2025-06-22 |  |  | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00616_HU | Q141A_Q00616OD_CB_TMSEBANGAN | DU00005180188 | Sarawak | Sarawak | 1.557000 | 110.772200 |  |  |  |  | Pending SOW |  |  | 00. Site Out/Drop |  |  |  | 2xISM8 | Cancel / Drop | 03 Jul 2025 - Cancel/drop. Under Huawei MW HARDWARE UPGRADE Q00616-Q00023 FROM 15G_2+0 TO 15G_4+0 USING EXISITNG XMC-5D. | MW HARDWARE UPGRADE Q00616-Q00023 FROM 15G_2+0 TO 15G_4+0 NE: 1. Install new 1xISM8 at slot 3. 2. reuse exisitng XMC-5D_SB A. 3. Configure 15G_4+0_512QAM_CA | MW HARDWARE UPGRADE Q00616-Q00023 FROM 15G_2+0 TO 15G_4+0 FE: 1. Install new 1xISM8 at slot 3. 2. reuse exisitng XMC-5D_SB A. 3. Configure 15G_4+0_512QAM_CA | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | HSU//MYET CHAE/6799000011
Q00699_HU | Q135A_Q00699OD_KGEMPILA | DU00005180189 | Sarawak | Sarawak | 1.431193 | 110.507921 |  |  |  |  | Pending SOW |  | ZTE | 00. Site Out/Drop | 17/9/2025 : Site Cancel/Drop. Based on Mazelan rough analysis..Q00699_HU need to Cancel/Drop due to below reason: 1. Q00699(Decom) and Child sites (Q00693-Decom & Q00090-New Link/Reroute). 2. 9029B(Pair Site for Q00699) solution/sow - swap NEC to HW(Integrated already in Y2024). 3. 9528B(Pair Site for Q00693) solution/sow - swap NEC to HW(Integrated already in Y2024). 4. Q00090(Unpair) having plan for tx sow-New Link/Reroute to new FE(from Q00693 to 9528B) - not integrated yet. | TSS+AA+TI+Dismantle |  | 18G_2+0_0.6/0.6_DP_SB A,B | MW Swap | MW SWAP Q00699-Q00025 WITH 18G_2+0_0.6/0.6_DP_SB A,B DISMANTLE EXISITNG SM LINK. | MW SWAP Q00699-Q00025 WITH 18G_2+0_0.6/0.6_DP_SB A,B NE: 1. Install new RTN910A. 2. Install XMC_3E_SB A and B. 3. Install new 18G_antenna 0.6_DP. 4. Configure 18G_2+0_0.6/0.6_DP_128QAM_110Mhz. 5. Dismantle SM link. | MW SWAP Q00699-Q00025 WITH 18G_2+0_0.6/0.6_DP_SB A,B FE: 1. Install new RTN910A. 2. Install XMC_3E_SB A and B. 3. Install new 18G_antenna 0.6_DP. 4. Configure 18G_2+0_0.6/0.6_DP_128QAM_110Mhz. 5. Dismantle SM link. | XMC_3E A,B | DP_MAC | 18G | 0.6 | 0.6 | Trintel | SQ202509040637-Trintel | Trintel | No PR required-Work at TSS only | 2025-12-02 | 2025-11-26 | Completed | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Full site Return | 2025-09-10 | 2025-09-17 | Completed | 2025-09-09 | 2025-09-10 | 2025-09-09 | 2025-09-17 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-15 | 2025-09-20 |  |  | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-09-15 | 2025-09-20 |  |  | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | [7 empty] | 2025-09-15 | 2025-09-20 |  |  | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | 2025-09-30: 2025-09-15; 2025-09-30: 2025-09-20; 2025-09-30: 2025-09-18; 2025-10-08: 2025-09-18 | [7 empty] | GTSB | SQ202505020435-GTSB | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | HSU//MYET CHAE/6799000011
7355C_HU | Pulau Mataking | DU00005180190 | Sabah | Sabah | 4.579300 | 118.948700 | [5 empty] | 7GHz 1.8m DP x 2pc |  | 04. BOM / Material Issue |  | TSS+AA+TI+Dismantle |  | 7G 2x(1+1 SD) 28MHz 1.8m/1.8m DP XMC3 NE: 1) 2xISM8 card 2) 4x7GHz ODU (Subband TBC pending frequency scanning) 3) 2x7GHz 1.8m DP FE: 1) 1xRTN910A 2) 1xISM8 card 3) 4x7GHz ODU (Subband TBC pending frequency scanning) 4) 2x7GHz 1.8m DP | MW Swap | To perform 7GHz frequency scanning and request for approval from CD and MCMC. Swap existing 1+0 link with new 2x(1+1 SD) link Reuse existing channel for vertical NE (7355C Pulau Mataking-RTN01): 1) Add ISM8 card slot 3 and 4 2) Install new link at slot 3 and 4 3) Migrate 7355C traffic to new link 4) Decom existing link FE (7625B): 1) Install new RTN910A 2) Add ISM8 card to slot 3 3) Install new link at slot 7 and 3 4) Patch new RTN GE1 to 7625B RTN01 GE2 5) Migrate 7355C traffic to new link 6) Decom existing link | NE (7355C Pulau Mataking-RTN01): 1) Add ISM8 card slot 3 and 4 2) Install new link at slot 3 and 4 3) Migrate 7355C traffic to new link 4) Decom existing link | FE (7625B): 1) Install new RTN910A 2) Add ISM8 card to slot 3 3) Install new link at slot 7 and 3 4) Patch new RTN GE1 to 7625B RTN01 GE2 5) Migrate 7355C traffic to new link 6) Decom existing link | XMC3 | MAC DP | 7G | 1.8m Main 1.8m Diversity | 1.8m Main 1.8m Diversity | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300153-GTSB
K01076_HU | KG BAROKAS | DU00005180191 | Northern | Kedah | 6.234692 | 100.631600 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M. NE_K01076. 18G_SP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A_Lo x1. FE_4999A/K00119. 18G_SP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A_Hi x1. | MW Swap | Existing link 18G_1+0_56M.Not Support For Remote Software Upgrade. Swap existing to 18G_1+0_112M. Site Impacted : K01076. NE_K01076. 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link 18G_1+0_112M. 6.Decom existing MW link. FE_4999A/K00119. 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link 18G_1+0_112M. 6.Decom existing MW link. | Existing link 18G_1+0_56M.Not Support For Remote Software Upgrade. Swap existing to 18G_1+0_112M. Site Impacted : K01076. NE_K01076. 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link 18G_1+0_112M. 6.Decom existing MW link. | Existing link 18G_1+0_56M.Not Support For Remote Software Upgrade. Swap existing to 18G_1+0_112M. Site Impacted : K01076. FE_4999A/K00119. 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link 18G_1+0_112M. 6.Decom existing MW link. | XMC_3E | MAC | 18G | 0.6 | 0.6 | NWAVE | SQ202508140681-N-Wave | NWAVE | SQ202508140678-N-Wave // SQ202508140679-N-Wave | 2025-11-25 | 2025-11-24 | Completed | 2025-08-28 | 2025-09-29 | 2025-08-28 | 2025-08-28 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072954 |  | 2025-07-30 | 2025-08-06 | Completed | 2025-07-29 | 2025-07-30 | 2025-07-29 | 2025-08-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-09-25 | 2025-08-25 | 2025-08-28 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-08-25 | 2025-09-25 | 2025-08-25 | 2025-09-12 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | AKMAL//BIN RAZALI/6794000078 |  | 2025-09-11 | 2025-08-25 | 2025-09-25 | 2025-08-25 | 2025-09-19 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | 2025-08-25 | 2025-09-25 | 2025-08-25 | 2025-08-25 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | CHEONG/SENG/WAH/7018000306
3782A_HU | Taman Makmur | DU00005180192 | Central | Selangor | 3.418544 | 101.186333 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap | MW SWAP LINK 3782A-3781A WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_1.3KM IMPACTED: 3782A,2609A2 DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. PATCH NEW IDU TO B00518 AND INSTALL 10G SFP 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202504280360-Magicell | Magicell | SQ202505240081-Magicell // SQ202505240082-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051378 |  | 2025-05-14 | 2025-05-15 | Completed | 2025-05-13 | 2025-05-14 | 2025-05-13 | 2025-05-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-20 | 2026-05-21 | 2025-05-20 | 2025-05-26 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-05-20 | 2026-05-21 | 2025-05-20 | 2025-05-26 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-23 | 2025-05-20 | 2026-05-21 | 2025-05-20 | 2025-05-27 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-05-20 | 2026-05-21 | 2025-05-20 | 2025-05-22 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01350_HU | Q135A_Q01350OD_TMNUNI | DU00005180193 | Sarawak | Sarawak | 1.463440 | 110.412150 |  |  |  |  | Pending SOW |  | ZTE | 00. Site Out/Drop | 14/10 -link swap cancel install due celcom Link already decom after MOCN | TSS |  | 2x IDU RTN910A 2X 0.6m MAC_SP ANTENNA (23G) 1x ODU 23G XMC-3E SB_A HI 1x ODU 23G XMC-3E SB_A LO | MW Swap | 10 Oct 2025: Cancel/drop due to site already decom under NIC | NE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW 23G 0.6m SP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A 4. CONFIGURE LINK 23G 1+0 56Mhz 512QAM 5. DISMANTLE EXISTING LINK (HW) 15G_1+0 | FE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW 23G 0.6m SP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A 4. CONFIGURE LINK 23G 1+0 56Mhz 512QAM 5. RE-CONNECT LL FROM OLD IDU TO NEW IDU 6. DISMANTLE EXISTING LINK (HW) 15G_1+0 | XMC-3E | MAC | 23G | 0.6m | 0.6m | Allstar | SQ202507100507-Allstar | Allstar | No PR required-Site drop/cancel | 2026-01-28 | 2026-02-03 | Completed | 2025-07-28 | 2025-07-28 | 2026-01-13 | 2026-01-13 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-01-13 | 2026-01-19 | 2026-01-13 | 2026-01-13 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-02-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Full site DR | 2025-10-09 | 2025-10-10 | Completed | 2025-10-08 | 2025-10-09 | 2025-10-08 | 2025-10-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q00931_HU | Q132A_Q00931OD_KGPDG | DU00005180194 | Sarawak | Sarawak | 4.003649 | 113.782229 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | AB.RAHMAN//BIN MAT NOOH/6237001519
A00505_HU | A040D_A00505OD_CB_KGBLANGKOR_RCC | DU00005180195 | Northern | Perak | 4.371803 | 101.058007 | [7 empty] | 00. Integrated/RFS Done | 04/07: CO Done | TSS+AA+TI | L1+ATP+PAC | 15G_4+0-28M to become 15G_6+0_28M with EPLA 15G_2+0_28M with refer DU ID A00505_HU_1 Under DU Code DU00005591141. NE_A00505 15G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Lo x1. FE_A00155. 15G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing SM link 13G_4+0_28M_XPIC Parallel link to 15G_4+0-28M to become 15G_6+0_28M with EPLA 15G_2+0_28M with refer DU ID A00505_HU_1 Under DU Code DU00005591141. Site Impacted : A00505. NE_A00505 1.Install new 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Lo for ant 2 with CA. 4.Create service cross connect , CA and EPLA. 5.BBU patching to new link. FE_A00155. 1.Install new 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Hi for ant 2 with CA. 4.Create service cross connect , CA and EPLA. 5.Traffic migrate to new link. | Existing SM link 13G_4+0_28M_XPIC Parallel link to 15G_4+0-28M to become 15G_6+0_28M with EPLA 15G_2+0_28M with refer DU ID A00505_HU_1 Under DU Code DU00005591141. Site Impacted : A00505. NE_A00505 1.Install new 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Lo for ant 2 with CA. 4.Create service cross connect , CA and EPLA. 5.BBU patching to new link. | Existing SM link 13G_4+0_28M_XPIC Parallel link to 15G_4+0-28M to become 15G_6+0_28M with EPLA 15G_2+0_28M with refer DU ID A00505_HU_1 Under DU Code DU00005591141. Site Impacted : A00505. FE_A00155. 1.Install new 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Hi for ant 2 with CA. 4.Create service cross connect , CA and EPLA. 5.Traffic migrate to new link. | XMC_5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202506050553-Magicell | Magicell | SQ202505240109-Magicell // SQ202505240110-Magicell // SQ202511030393-Magicell | 2025-11-28 | 2025-11-27 | Completed | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250520A9 |  | 2025-05-21 | 2025-05-22 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-13 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-18 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-18 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-09-30: 2025-07-04; 2025-09-30: 2025-07-04; 2025-09-30: 2025-07-04; 2025-10-08: 2025-07-12 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | CHEONG/SENG/WAH/7018000306
Q00612_HU | Q144A_Q00612OD_KEMSEKAWIE | DU00005180196 | Sarawak | Sarawak | 2.518444 | 112.830920 |  |  |  |  | Pending SOW |  | ZTE | 00. Site Out/Drop | 22/8: No more HU in live network |  |  |  | Cancel / Drop | 22/8: No more HU in live network 6/8: link down, requested TT to KK. 36km distance | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB
7547B_HU | KKIP Barat | DU00005180197 | Sabah | Sabah | 6.092959 | 116.154548 |  |  |  |  | Drop/Cancel | Cancel/Drop |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | To perform remote upgrade from 23G 2+0 28MHz to 2+0 56MHz Use IS3 mode with 512QAMLight modulation | To perform remote upgrade from 23G 2+0 28MHz to 2+0 56MHz Use IS3 mode with 512QAMLight modulation | To perform remote upgrade from 23G 2+0 28MHz to 2+0 56MHz Use IS3 mode with 512QAMLight modulation | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
K00871_HU | K002A_K00871OD_CB_KG_KEJAI | DU00005180198 | Northern | Kedah | 5.547483 | 100.718952 | [7 empty] | 00. Integrated/RFS Done | 26/8: CO, | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO | MW Swap | MW SWAP LINK K00871-K00399 WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_778MBPS_XMC3E_SUB_A_3.31KM DISMANTLE EXISTING LINK IMPACTED: K00871 | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK 6. PATCH NEW IDU TO NEW PORT | XMC3E | MAC | 18G | 0.6 | 0.6 | GTSB | SQ202507110773-GTSB | GTSB | SQ202507110777-GTSB // SQ202507110781-GTSB // SQ202509260767-GTSB | 2026-01-22 | 2026-01-22 | Completed | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072948 |  | 2025-07-30 | 2025-08-27 | Completed | 2025-07-29 | 2025-07-30 | 2025-07-29 | 2025-08-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-09-03 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-09-03 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-26 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-09-01 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-25 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
7968A_HU | Kg Indera Sabah | DU00005180199 | Sabah | Sabah | 4.299505 | 118.169798 |  |  |  |  | TI WIP | Alignment WIP |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G 2+0 1.8m/1.8m MAC DP XMC3 sub A/B NE: 1) 1 x ISM8 cards 2) 1 x 13G XMC3 sub A Lo 4) 1 x 13G XMC3 sub B Lo 5) 1 x 13G 1.8m MAC DP FE: 1) 1 x ISM8 cards 2) 1 x 13G XMC3 sub A Hi 4) 1 x 13G XMC3 sub B Hi 5) 1 x 13G 1.8m MAC DP | MW Parallel Link | Add parallel 2+0 to existing 4+0 link Use existing IDU add ISM8 card Create 6+0 EPLA NE (7968A-KG INDERA SABAH-RTN01): 1) Add ISM8 card slot 4 2) Install new link at 4-ISM8 3) Create 6+0 EPLA FE (7626A-BUKIT 700 TRUNK-RTN01): 1) Add ISM8 card slot 4 2) Install new link at 4-ISM8 3) Create 6+0 EPLA | NE (7968A-KG INDERA SABAH-RTN01): 1) Add ISM8 card slot 4 2) Install new link at 4-ISM8 3) Create 6+0 EPLA | FE (7626A-BUKIT 700 TRUNK-RTN01): 1) Add ISM8 card slot 4 2) Install new link at 4-ISM8 3) Create 6+0 EPLA | XMC3 | MAC DP | 13G | 1.8m | 1.8m | NR services | SQ202505020374-NR Services | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services | 2025-12-09 | 2025-12-02 | Completed | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-24 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090212 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-08 | 2025-10-08 | 2025-09-08 | 2025-09-13 | LEONARD//EDUAN/6000038538 | NR Service TI | 2025-09-08 | 2025-10-08 | 2025-09-08 | 2025-12-01 | LEONARD//EDUAN/6000038538 | NR Service TI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-25 | 2025-09-08 | 2025-10-08 | 2025-09-08 | 2026-04-02 | LEONARD//EDUAN/6000038538 | 2025-08-23: 2025-09-08; 2025-08-23: 2025-10-08; 2025-08-23: 2025-09-08; 2025-08-25: 2025-11-24 |  |  | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-16 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506050733-GTSB | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | HSU//MYET CHAE/6799000011
S01445_HU | S106A_S01445OD_T3_KGPAKALANGAN | DU00005180200 | Sabah | Sabah | 4.375600 | 118.560100 |  |  |  |  | Pending SOW |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_1.2/1.2_DP XMC-3 SB B/B 2x ISM8 | MW Parallel Link | MW PARALLEL LINK S01445-S00468 (SB02728) WITH 15G_2+0_1.2/1.2_DP_XMC-3_SB B/B_EPLA with existing link | MW PARALLEL LINK S01445-S00468 (SB02728) WITH 15G_2+0_1.2/1.2_DP_XMC-3_SB B/B NE: 1. Reuse existing RTN910A 2. Install new 1xISM8 at slot 4. 3. Install new XMC-3 SB B. 4. Install new antenna 15G_1.2m_DP. 5. Configure 15G_2+0_1.2_DP_EPLA with exisitng link. | MW PARALLEL LINK S01445-S00468 (SB02728) WITH 15G_2+0_1.2/1.2_DP_XMC-3_SB B/B FE: 1. Reuse existing RTN910A 2. Install new 1xISM8 at slot 4. 3. Install new XMC-3 SB B. 4. Install new antenna 15G_1.2m_DP. 5. Configure 15G_2+0_1.2_DP_EPLA with exisitng link. | XMC_3_SB B |  | 15G | 1.2 | 1.2 | NR services | SQ202509300151-NR Services | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-17 | 2025-10-14 | 2025-10-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-17 | 2025-10-14 | 2025-10-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090217 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-20 | 2025-10-20 | 2025-09-20 | 2025-09-21 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-09-20 | 2025-10-20 | 2025-09-20 | 2025-09-30 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-26 | 2025-09-20 | 2025-10-20 | 2025-09-20 | 2025-10-02 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2025-08-23: 2025-09-20; 2025-08-23: 2025-10-20; 2025-08-23: 2025-09-20; 2025-08-25: 2025-09-22 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505020434-GTSB | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | HSU//MYET CHAE/6799000011
Q00587_HU | Q135A_Q00587OD_CB_SGENTINGGAN | DU00005180201 | Sarawak | Sarawak | 1.404041 | 110.402710 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB
Q01002_HU | Q127A_Q01002OD_CB_NGSANPANJAI | DU00005180202 | Sarawak | Sarawak | 1.037722 | 111.789606 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | HSU//MYET CHAE/6799000011
K00781_HU | K009A_K00781OD_CB_KGBIDAN_PDGTERAP | DU00005180203 | Northern | Kedah | 6.153821 | 100.700576 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Drop Under K00781_NIC | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505020432-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
Q00604_HU | Q125A_Q00604OD_CB_KGAWATAWAT | DU00005180204 | Sarawak | Sarawak | 4.939150 | 115.234300 |  |  |  |  | Pending SOW |  |  | 00. Site Out/Drop | 09/6: Closed on WK22 by CDB Tracker. No activity done |  |  |  | Cancel / Drop | Closed on WK22 by CDB Tracker. No activity done. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | HSU//MYET CHAE/6799000011
B00198_HU | B058E_B00198OD_PR_LBHNDAGANG | DU00005180205 | Central | Selangor | 2.806780 | 101.621730 |  | APR 25 |  | APR 25 | DO | Doable, just waiting material | ZTE | 00. Integrated/RFS Done | 7/4/2025 : KONSORTIUM JARINGAN SELANGOR SDN BHD - TOWER 61M LAND - NE site B00198 B058E_B00198OD_PR_LBHNDAGANG, SBC KJS - TOWER 61M LAND - FE site B00269 B058E_B00269OD_PR_KGKUBANGBERAS | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 1X 18G 0.6M MDD ANTENNA 1X 18G 1.2M MDD ANTENNA 1x ODU 18G XMC5D SUB A HI 1X ODU 18G XMC5D SUB A LO | MW Swap | MW SWAP LINK B00198-B00269 WITH HUAWEI_18G_2+0_0.6M/1.2M_MDD_112MHZ_256QAM_1556MBPS_XMC5D_SUB A_4.03KM IMPACTED: B00198 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 18G | 1.2 | 1.2 | Magicell | SQ202504170467-Magicell | Magicell | SQ202507100543-Magicell // SQ202507100546-Magicell | 2025-06-18 | 2025-06-18 | Completed | 2025-04-10 | 2025-04-10 | 2025-04-09 | 2025-05-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-07 | 2025-05-08 | 2025-05-07 | 2025-05-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-17 | 2025-06-18 | 2025-06-17 | 2025-06-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070707 |  | 2025-07-09 | 2025-07-21 | Completed | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-21 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-21 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-21 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-14 | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-21 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506050696-GCI | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | CHEONG/SENG/WAH/7018000306
A00866_HU | A040C_A00866OD_KGKEPAYANGIPH2 | DU00005180206 | Northern | Perak | 4.618737 | 101.096778 | [7 empty] | 00. Integrated/RFS Done | 08/07: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO | MW Swap | MW SWAP LINK A00866-A00348 WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_778MBPS_XMC3E_SUB_A_2.99KM DISMANTLE EXISTING LINK IMPACTED: A00866 | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK 6. PATCH NEW IDU TO NEW PORT | XMC3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202507020660-GCI | GCI | SQ202506230425-GCI // SQ202506230447-GCI | 2026-01-21 | 2026-01-21 | Completed | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-06-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-06-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061177 |  | 2025-06-12 | 2025-06-13 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-21 | 2025-06-30 | 2025-06-21 | 2025-07-15 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-06-21 | 2025-06-30 | 2025-06-21 | 2025-07-11 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-08 | 2025-06-21 | 2025-06-30 | 2025-06-21 | 2025-12-17 | ANAS FIKRI ADHA BIN RAZMI6000009598 | 2025-06-21 | 2025-06-30 | 2025-06-21 | 2025-06-21 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01493_HU | Q132C_Q01493OD_RHSINJU | DU00005180207 | Sarawak | Sarawak | 3.763300 | 113.769762 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | HSU//MYET CHAE/6799000011
N00359_HU | N00359OD_CB_KG_JIJAN | DU00005180208 | Central | Sembilan | 2.762933 | 101.776300 | WK13 | MAR 25 | WK13 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 27/3/2025 : Cutover done 19/3/2025 : EDOTCO (M) SDN BHD - TOWER 76M LAND - NE site N00359 N00359OD_CB_KG_JIJAN, MAXIS COMMUNICATION BERHAD - TOWER 61M LAND - FE site N00041 ENSTEK SCITEX CITY | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK N00359-N00041 WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB A_1.37KM IMPACTED: N00359 DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 3. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 4. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 3. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 4. PATCH NEW LINK TO NEW CP PORT 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202504170453-GCI | GCI | SQ202503280384-GCI // SQ202503280397-GCI // SQ202505150098-GCI // SQ202509020092-GCI | 2025-05-01 | 2025-04-30 | Completed | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-08 | 2025-04-09 | 2025-04-08 | 2025-04-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-30 | 2025-05-01 | 2025-04-30 | 2025-04-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031917 |  | 2025-03-20 | 2025-03-22 | Completed | 2025-03-19 | 2025-03-20 | 2025-03-19 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-27 | 2025-04-03 | 2025-03-27 | 2025-04-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-27 | 2025-04-03 | 2025-03-27 | 2025-04-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-27 | 2025-03-27 | 2025-04-03 | 2025-03-27 | 2025-04-07 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-27 | 2025-04-03 | 2025-03-27 | 2025-03-27 | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
A00408_HU | A042A_A00408OD_CB_LDGMALAYA | DU00005180209 | Northern | Perak | 5.107200 | 100.717800 | [7 empty] | 00. Integrated/RFS Done | 26/6: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 13G 2.4M DP ANTENNA 1x ODU 13G XMC3 SUB A HI 1X ODU 13G XMC3 SUB A LO 1x ODU 13G XMC3 SUB B HI 1X ODU 13G XMC3 SUB B LO | MW Swap | MW SWAP LINK A00408-A00466 WITH HUAWEI_13G_2+0_2.4M/2.4M_DP MS_28MHZ_512QAM_448MBPS_XMC3_SUB_A & B_14.98KM DISMANTLE EXISTING LINK SM IMPACTED: A00408 | 1. INSTALL NEW RTN910 2. INSTALL NEW 13G 2.4M DP ANTENNA 3. INSTALL NEW ODU 2.4G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 13G 2+0 28MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 2. INSTALL NEW 13G 2.4M DP ANTENNA 3. INSTALL NEW ODU 2.4G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 13G 2+0 28MHZ 512QAM 5. DISMANTLE EXISTING LINK 6. PATCH NEW IDU TO NEW PORT | XMC3 | MS DP | 13G | 2.4 | 2.4 | NWAVE | SQ202507160641-N-Wave | NWAVE | SQ202506180109-N-Wave // SQ202506180111-N-Wave | 2025-11-28 | 2025-11-27 | Completed | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-09 | 2025-07-15 | 2025-08-28 | 2025-08-28 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052633 |  | 2025-05-27 | 2025-05-29 | Completed | 2025-05-26 | 2025-05-27 | 2025-05-26 | 2025-05-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-16 | 2025-06-24 | 2025-06-16 | 2025-06-17 | ABDUL LATIF//ARSHAD/6000026740 | NWAVE TI | 2025-06-16 | 2025-06-24 | 2025-06-16 | 2025-07-06 | ABDUL LATIF//ARSHAD/6000026740 | NWAVE TI | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-02 | 2025-06-16 | 2025-06-24 | 2025-06-16 | 2025-12-17 | ABDUL LATIF//ARSHAD/6000026740 | 2025-06-16 | 2025-06-24 | 2025-06-16 | 2025-06-18 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | EZRIN TASNIM BIN ABDUL GANI6798000128
1399H_LOS_1 | 99 Speedmart KG PENDAMAR | DU00005180210 | Central | Selangor | 2.979160 | 101.430350 | WK13 | MAR 25 | WK13 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 25/3/2025 : Cutover done 24/3/2025 : Digi OB - Small Cell - NE site 1399H 99 Speedmart KG PENDAMAR, MAXIS - 60M 3 Legged Tower - FE site 2492A Tmn Pandamaran Indah 2 | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS RTN510 NE_1399H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_2492A 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Existing Link is Cambium. Swap existing link to NLOS RTN510 due to LOS Block and Old equipment. Site Impacted : 1399H. NE_1399H 1.Install new NLOS equipment (Indoor & Outdoor). 2.capture existing radio config and parameters. 3.Perform alignment direct towards FE 2492A. 4.Create service cross connect. 5.Migrate service to new NLOS link. 6.Decom existing Cambium Link.Ensure traffic migrate completely before decom. FE_2492A 1.Install new NLOS equipment (Indoor & Outdoor). 2.Capture existing radio config and parameters. 3.Install ant height at 50M and perform alignment direct towards 1399H. 4.Create service cross connect. 5.Enable GE port , ETH patching to existing Fiber Port. 6.Create New In Band DCN. 7.Traffic migrate to new NLOS link. 8.Decom existing cambium link. Ensure traffic migrate completely before decom. | Existing Link is Cambium. Swap existing link to NLOS RTN510 due to LOS Block and Old equipment. Site Impacted : 1399H. NE_1399H 1.Install new NLOS equipment (Indoor & Outdoor). 2.capture existing radio config and parameters. 3.Perform alignment direct towards FE 2492A. 4.Create service cross connect. 5.Migrate service to new NLOS link. 6.Decom existing Cambium Link.Ensure traffic migrate completely before decom. | Existing Link is Cambium. Swap existing link to NLOS RTN510 due to LOS Block and Old equipment. Site Impacted : 1399H. FE_2492A 1.Install new NLOS equipment (Indoor & Outdoor). 2.Capture existing radio config and parameters. 3.Install ant height at 50M and perform alignment direct towards 1399H. 4.Create service cross connect. 5.Enable GE port , ETH patching to existing Fiber Port. 6.Create New In Band DCN. 7.Traffic migrate to new NLOS link. 8.Decom existing cambium link. Ensure traffic migrate completely before decom. | [5 empty] | Magicell | SQ202503270787-Magicell | Magicell | SQ202503280442-Magicell // SQ202503280449-Magicell // SQ202504260146-Magicell | 2025-06-27 | 2025-06-27 | Completed | 2025-03-19 | 2025-03-19 | 2025-03-12 | 2025-03-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-06-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-06-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031909 |  | 2025-03-20 | 2025-03-20 | Completed | 2025-03-19 | 2025-03-20 | 2025-03-19 | 2025-03-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-04-17 | 2025-03-24 | 2025-04-08 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 |  | 2025-03-24 | 2025-04-17 | 2025-03-24 | 2025-04-08 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 |  | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-25 | 2025-03-24 | 2025-04-17 | 2025-03-24 | 2025-04-09 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-03-24 | 2025-04-17 | 2025-03-24 | 2025-03-25 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-06 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202507080517-GCI | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
B02503_HU | B064H_B02503OD_KUIS | DU00005180211 | Central | Selangor | 2.890869 | 101.783750 |  | APR 25 |  | JUN 25 | DO | Doable, just waiting material | ZTE | 00. Integrated/RFS Done | 7/4/2025 : KONSORTIUM INFRASTRUKTUR W.P. SDN BHD - LAMP POLE 24M LAND - NE site B02503 B064H_B02503OD_KUIS, Celcom CSU (Digi) - TOWER 61M LAND - FE site B00141 B064G_B00141OD_TERASJERNANG | TSS+AA+TI | L1+ATP+PAC | 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK B02503-1057A WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB A_2.76KM_ IMPACTED: B02503 | 1. REUSE EXISTING IDU RTN910 2. REUSE EXISTING 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A AT EXISTING ANTENNA 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM EPLA WITH EXISTING 18G 1+0 | 1. REUSE EXISTING IDU RTN910 2. REUSE EXISTING 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A AT EXISTING ANTENNA 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM EPLA WITH EXISTING 18G 1+0 | XMC3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202504170467-Magicell | Magicell | SQ202508070545-Magicell // SQ202508070551-Magicell | 2025-05-21 | 2025-05-21 | Completed | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-05-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051360 |  | 2025-05-14 | 2025-06-25 | Completed | 2025-05-13 | 2025-05-14 | 2025-05-13 | 2025-06-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-25 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-25 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-26 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-17 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-25 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-07-09: 2025-06-11; 2025-07-09: 2025-06-11; 2025-07-09: 2025-06-11; 2025-07-14: 2025-06-17 |  |  | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202506050715-GTSB
B02254_HU | B061D_B02254OD_JLNJUBLIPERAKSHLM | DU00005180212 | Central | Selangor | 3.069450 | 101.555400 |  | APR 25 |  | JUN 25 | DO | Pending edotco and TM PTW approval | ZTE | 00. Integrated/RFS Done | 19/3/2025 : EDOTCO (M) SDN BHD - TRIPOD 6M ROOFTOP - NE site B02254 B061D_B02254OD_JLNJUBLIPERAKSHLM, TELEKOM MALAYSIA BERHAD - TOWER 76M LAND - FE site B00395 B061I_B00395OD_TMBKTGUGUP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 1X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO | MW Swap | MW SWAP LINK B02254-B00395 WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM_954MBPS_XMC3E_SUB A_0.95KM IMPACTED: B02254 | 1. INSTALL NEW RTN910 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202504170454-GTSB | GTSB | SQ202504240805-GTSB // SQ202504240806-GTSB | 2025-11-25 | 2025-11-24 | Completed | 2025-06-24 | 2025-07-08 | 2025-06-24 | 2025-06-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-24 | 2025-07-08 | 2025-06-24 | 2025-06-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052163 |  | 2025-05-22 | 2025-05-27 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-10 | 2025-06-30 | 2025-06-10 | 2025-06-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-06-10 | 2025-06-30 | 2025-06-10 | 2025-06-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-20 | 2025-06-10 | 2025-06-30 | 2025-06-10 | 2025-06-26 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-06-10 | 2025-06-30 | 2025-06-10 | 2025-06-11 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01895_HU | Q124F_Q01895OD_BDRBARUSAMARIANG | DU00005180213 | Sarawak | Sarawak | 1.636110 | 110.338300 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Not in HU GOP list | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020435-GTSB | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | AB.RAHMAN//BIN MAT NOOH/6237001519
S01748_HU | S100A_S01748SC_KUALALUMAGAR | DU00005180214 | Sabah | Sabah | 5.510580 | 115.876400 |  |  |  |  | Drop/Cancel | Cancel/Drop |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Link already reroute under NIC | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2727A_AD | Extreme Park Shah Alam | DU00005182762 | Central | Selangor | 3.086592 | 101.541617 | WK11 | MAR 25 | WK11 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 12/3/2025 : Cutover done | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6/0.6_MDD_2+0_112MHZ_256QAM | MW Swap | RELOCATE LINK 2727A-1362A HW LINK TO SM LINK 2727A-1362A. REPATCH NLOS 1603H TO HW IDU 2727A-1362A 18G_0.6/0.6_MDD_2+0_112MHZ_256QAM_SUB A DISMANTLE EXISTING SM LINK CARRY NLOS | RELOCATE LINK 2727A-1362A HW LINK TO SM LINK 2727A-1362A. REPATCH NLOS 1603H TO HW IDU 2727A-1362A 18G_0.6/0.6_MDD_2+0_112MHZ_256QAM_SUB A DECOM UNUSED 2 SM LINK | DECOM UNUSED 2 LINK SM | [5 empty] | GTSB | SQ202504170454-GTSB | GTSB | SQ202503240695-GTSB // SQ202503240700-GTSB // SQ202504260131-GTSB // SQ202511210026-GTSB | 2025-06-23 | 2025-06-24 | Completed | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-06-06 | 2025-06-20 | 2025-06-06 | 2025-06-06 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2025-03-24 | 2025-03-24 | Completed | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-12 | 2025-03-31 | 2025-03-12 | 2025-03-24 | ERVIN CHRISTOPHER//AL ALFANSO/6799000302 | GTSB TI | 2025-03-12 | 2025-03-31 | 2025-03-12 | 2025-03-27 | ERVIN CHRISTOPHER//AL ALFANSO/6799000302 | GTSB TI | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-03-13 | 2025-03-12 | 2025-03-31 | 2025-03-12 | 2025-05-06 | ERVIN CHRISTOPHER//AL ALFANSO/6799000302 | 2025-03-12 | 2025-03-31 | 2025-03-12 | 2025-03-27 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202507080560-GTSB
4481A_HU | Sek Agama Rakyat Nurul Sera Ma | DU00005191256 | Northern | Perak | 4.177783 | 100.652360 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M. NE_4481A 15G_DP_1.2M(MAC)+OMT x1. XMC_3E , Sub A & B_Lo x2. FE_4476B 15G_DP_.12M(MAC)+OMT x1. XMC_3E , Sub A & B_Hi x2. | MW Parallel Link | Existing link 13G_4+0_28M. Install parallel link 15G_2+0_28M. Site Impacted : 4481A. NE_4481A 1.Install new 15G_DP_1.2M(MAC)+OMT. 2.Install XMC_3E , Sub A & B_Lo. 3.Reuse existing 4481A_RTN03 , 7_ISM8-2+0. 4.Create service cross connect and EPLA new 15G_2+0 and existing 13G_4+0. 5.No decom existing MW link. FE_4476B 1.Install new 15G_DP_.12M(MAC)+OMT. 2.Install XMC_3E , Sub A & B_Hi. 3.Reuse existing 4476B_RTN04 , 7_ISM8-2+0. 4.Create service cross connect and EPLA new 15G_2+0 and existing 13G_4+0. 5.No decom existing MW link. | Existing link 13G_4+0_28M. Install parallel link 15G_2+0_28M. Site Impacted : 4481A. NE_4481A 1.Install new 15G_DP_1.2M(MAC)+OMT. 2.Install XMC_3E , Sub A & B_Lo. 3.Reuse existing 4481A_RTN03 , 7_ISM8-2+0. 4.Create service cross connect and EPLA new 15G_2+0 and existing 13G_4+0. 5.No decom existing MW link. | Existing link 13G_4+0_28M. Install parallel link 15G_2+0_28M. Site Impacted : 4481A. FE_4476B 1.Install new 15G_DP_.12M(MAC)+OMT. 2.Install XMC_3E , Sub A & B_Hi. 3.Reuse existing 4476B_RTN04 , 7_ISM8-2+0. 4.Create service cross connect and EPLA new 15G_2+0 and existing 13G_4+0. 5.No decom existing MW link. | XMC_3 | MAC | 15G | 1.2 | 1.2 | Magicell | SQ202507180627-Magicell | Magicell | SQ202505290496-Magicell // SQ202505290514-Magicell // SQ202511030393-Magicell | 2026-01-20 | 2026-01-19 | Completed | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051489 |  | 2025-05-15 | 2025-05-16 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-26 | MUHAMMAD//SHAFIQ/7018000167 | Magicell TI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-07-06 | MUHAMMAD//SHAFIQ/7018000167 | Magicell TI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-05-26 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2026-03-09 | MUHAMMAD//SHAFIQ/7018000167 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-24 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | NG HONG JIE7018000036 | Logistic Team | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | CHEONG/SENG/WAH/7018000306
9128B_HU | Samalaju-Lodging | DU00005191260 | Sarawak | Sarawak | 3.541144 | 113.329585 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 2+0 0.6m/0.6m XMC3E NE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 4) 1x18GHz 0.6m DP FE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 4) 1x18GHz 0.6m DP 5) 1xCat6 cable | MW Swap | Swap existing 1+0 to 2+0 link Create LAG at IDU-IBEAM at FE site NE (9128B-SAMALAJU LODGING-RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9128B to new 2+0 link 5) Dismantle existing link FE (9363B-SIMILAJAU INDUSTRY JUNCTION_RTN03): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9167B to new 2+0 link 5) Patch RTN03 GE2 to new CP port. Create LAG 6) Dismantle existing link | NE (9128B-SAMALAJU LODGING-RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9128B to new 2+0 link 5) Dismantle existing link | FE (9363B-SIMILAJAU INDUSTRY JUNCTION_RTN03): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9167B to new 2+0 link 5) Patch RTN03 GE2 to new CP port. Create LAG 6) Dismantle existing link | XMC3E | MAC DP | 18G | 0.6m | 0.6m | Allstar | SQ202506200666-Allstar | Allstar | SQ202505240120-Allstar // SQ202505240121-Allstar | 2025-10-31 | 2025-10-28 | Completed | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-07-10 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-08-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250508AH |  | 2025-05-09 | 2025-05-14 | Completed | 2025-05-08 | 2025-05-09 | 2025-05-08 | 2025-05-14 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-16 | 2025-05-22 | 2025-05-16 | 2025-05-22 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-05-16 | 2025-05-22 | 2025-05-19 | 2025-05-22 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-21 | 2025-05-16 | 2025-05-22 | 2025-05-28 | 2025-05-28 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | 2025-05-16 | 2025-05-22 | 2025-05-21 | 2025-05-21 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-11 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-06-19 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB_AA | SQ202510300154-GTSB
7509B_HU | Kg. Jawa | DU00005191261 | Sabah | Sabah | 5.919030 | 117.957740 |  |  |  |  | TI DONE | Plan TI |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G 2+0 1.2m/1.2m DP XMC3 sub A&B NE: 1) 1 x 15G XMC3 sub A Lo 2) 1 x 15G XMC3 sub B Lo 3) 1 x 15G 1.2m MAC DP FE: 1) 1 x 15G XMC3 sub A Hi 2) 1 x 15G XMC3 sub B Hi 3) 1 x 15G 1.2m MAC DP | MW Parallel Link | Add parallel 2+0 to existing 4+0 link Use existing IDU Create 6+0 EPLA NE (7509B KG JAWA RTN02): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA FE (7566A MILE 9 SANDAKAN RTN06): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA | NE (7509B KG JAWA RTN02): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA | FE (7566A MILE 9 SANDAKAN RTN06): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA | XMC3 | MAC DP | 15G | 1.2m | 1.2m | NR services | SQ202506050556-NR Services | NR services | SQ202506190740-NR Services // SQ202506190744-NR Services | 2025-07-11 | 2025-07-07 | Completed | 2025-06-03 | 2025-06-05 | 2025-06-03 | 2025-06-05 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-04 | 2025-06-06 | 2025-06-04 | 2025-06-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-04 | 2025-06-06 | 2025-06-04 | 2025-06-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061205 |  | 2025-06-13 | 2025-06-16 | Completed | 2025-06-12 | 2025-06-13 | 2025-06-12 | 2025-06-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-18 | 2025-07-18 | 2025-06-18 | 2025-06-20 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-06-18 | 2025-07-18 | 2025-06-18 | 2025-06-30 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-21 | 2025-06-18 | 2025-07-18 | 2025-06-18 | 2025-07-03 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-05-19: 2025-06-18; 2025-05-19: 2025-07-18; 2025-05-19: 2025-06-18; 2025-05-24: 2025-06-19 |  |  | 2025-07-24 | 2025-08-24 | 2025-07-24 | 2025-07-24 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507080638-GTSB | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
9167B_HU | Bandar Baru Samariang | DU00005191262 | Sarawak | Sarawak | 1.632612 | 110.339086 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 2+0 0.6m/0.6m XMC3E NE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 4) 1x18GHz 0.6m DP FE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 4) 1x18GHz 0.6m DP | MW Swap | Swap existing 1+0 to 2+0 link NE (9167B-Bandar Baru Samariang-RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9167B to new 2+0 link 5) Dismantle existing link FE (9125B SEMARIAN AMAN_RTN01): 1) Add new ISM8 card at existing RTN01 slot 4 2) Install new link at 4-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9167B to new 2+0 link 5) Dismantle existing link | NE (9167B-Bandar Baru Samariang-RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9167B to new 2+0 link 5) Dismantle existing link | FE (9125B SEMARIAN AMAN_RTN01): 1) Add new ISM8 card at existing RTN01 slot 4 2) Install new link at 4-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9167B to new 2+0 link 5) Dismantle existing link | XMC3E | MAC DP | 18G | 0.6m | 0.6m | Allstar | SQ202506160462-Allstar | Allstar | SQ202505290519-Allstar // SQ202505290524-Allstar | 2025-10-31 | 2025-10-28 | Completed | 2025-05-27 | 2025-05-27 | 2025-06-13 | 2025-06-13 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250508AI |  | 2025-05-09 | 2025-05-26 | Completed | 2025-05-08 | 2025-05-09 | 2025-05-08 | 2025-05-26 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-26 | 2025-06-01 | 2025-05-29 | 2025-06-09 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-05-26 | 2025-06-01 | 2025-05-28 | 2025-06-09 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-28 | 2025-05-26 | 2025-06-01 | 2025-07-15 | 2025-07-15 | KENISTON//ANAK SPANCER/6798000184 | 2025-05-26 | 2025-06-01 | 2025-05-27 | 2025-05-27 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-11 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-06-19 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507080651-GTSB | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
9422B_HU | UiTM Samarahan New | DU00005191263 | Sarawak | Sarawak | 1.453056 | 110.429211 | [6 empty] | ZTE | 00. Integrated/RFS Done | 16/10 - closed 14/10 - LOS for FE not visible | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_0.6/0.6_MDD_XMC-5D_SB A | MW Swap | MW SWAP WITH 18G_2+0_0.6/0.6_MDD_256QAM_1352M. | MW SWAP WITH 18G_2+0_0.6/0.6_MDD_256QAM_1352M. NE: 1. Reuse existing RTN910A. 2. Swap exisitging ODU with XMC-5D_SB A. 3. Swap exisiting antenna with 0.6m_MDD. 4. Configure 18G_2+0_0.6_MDD_EPLA. | MW SWAP WITH 18G_2+0_0.6/0.6_MDD_256QAM_1352M. FE: 1. Reuse existing RTN910A. 2. Swap exisitging ODU with XMC-5D_SB A. 3. Swap exisiting antenna with 0.6m_MDD. 4. Configure 18G_2+0_0.6_MDD_EPLA. | XMC-5D_SB A |  | 18G | 0.6 | 0.6 | Trintel | SQ202509040637-Trintel | Allstar | SQ202510100597-Allstar // SQ202510100599-Allstar | 2025-10-31 | 2025-10-28 | Completed | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-08 | 2025-08-04 | 2025-08-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-08 | 2025-08-04 | 2025-08-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25101329 |  | 2025-10-14 | 2025-10-14 | Completed | 2025-10-13 | 2025-10-14 | 2025-10-13 | 2025-10-14 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-14 | 2025-10-21 | 2025-10-21 | 2025-10-21 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-10-14 | 2025-10-21 | 2025-10-16 | 2025-10-21 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-16 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-16 | 2025-10-14 | 2025-10-21 | 2025-10-21 | 2025-10-21 | BONG NEE NYEEbong.allstar@gmail.com | 2025-10-14 | 2025-10-21 | 2025-10-14 | 2025-10-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-21 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507080651-GTSB | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | HSU//MYET CHAE/6799000011
7529A_HU | TMB Bkt Mikki | DU00005191264 | Sabah | Sabah | 5.684351 | 115.954356 |  |  |  |  | Drop/Cancel |  |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01835_HU | YMCA | DU00005895475 | Sarawak | Sarawak | 2.289350 | 112.036800 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_56M_256QAM_EPLA NE_Q01835 New 23G_DP_1.2M(MAC)+OMT x1. New RTN910A(RTN01). New XMC_3E, Sub A&B_Lo x2. FE_9546A New 23G_DP_1.2M(MAC)+OMT x1. New RTN910A(RTN01). New XMC_3E, Sub A&B_Hi x2. New CAT6 1x with suitable length. | MW New Link / Reroute | Existing SM MW Link_ID SW02954, Q01835-Q00193, 13G_1+0_28MHZ_256QAM_170M. Install new HW MW Link Q01835-9369A, 23G_2+0_56MHZ_256QAM_EPLA. Later, decom existing SM MW Link_ID SW02954, Q01835-Q00193, 13G_1+0_28MHZ_256QAM_170M. **IMPORTANT NOTE: NEED TO PATCHING CAT 6 CABLE FROM XD CABINET(RTN910A-RTN01) TO XC CABINET AS RELOCATION PTN/CISCO WILL NOT DONE YET BY DECOM TEAM. ENSURE SUFFICIENT LENGTH OF CAT6 CABLE PROVIDED**. Site Impacted : Q01835. NE_Q01835 1.Install new 23G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 2x XMC_3E, Sub A&B_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Re-use existing xC vlan dcn and vlan services. 7.Migrate traffic Q01835 via new HW MW Link Q01835-9369A, 23G_2+0_56MHZ_256QAM_EPLA. 8.Decom existing SM MW Link_ID SW02954, Q01835-Q00193, 13G_1+0_28MHZ_256QAM_170M. FE_9369A 1.Install new 23G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 2x XMC_3E, Sub A&B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port at PTN/Cisco at xC Cabinet. Configure it. 6.Re-use existing xC vlan dcn and vlan services. 7.Decom existing SM MW Link_ID SW02954, Q01835-Q00193, 13G_1+0_28MHZ_256QAM_170M. | Existing SM MW Link_ID SW02954, Q01835-Q00193, 13G_1+0_28MHZ_256QAM_170M. Install new HW MW Link Q01835-9369A, 23G_2+0_56MHZ_256QAM_EPLA. Later, decom existing SM MW Link_ID SW02954, Q01835-Q00193, 13G_1+0_28MHZ_256QAM_170M. **IMPORTANT NOTE: NEED TO PATCHING CAT 6 CABLE FROM XD CABINET(RTN910A-RTN01) TO XC CABINET AS RELOCATION PTN/CISCO WILL NOT DONE YET BY DECOM TEAM. ENSURE SUFFICIENT LENGTH OF CAT6 CABLE PROVIDED**. Site Impacted : Q01835. NE_Q01835 1.Install new 23G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 2x XMC_3E, Sub A&B_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Re-use existing xC vlan dcn and vlan services. 7.Migrate traffic Q01835 via new HW MW Link Q01835-9369A, 23G_2+0_56MHZ_256QAM_EPLA. 8.Decom existing SM MW Link_ID SW02954, Q01835-Q00193, 13G_1+0_28MHZ_256QAM_170M. | Existing SM MW Link_ID SW02954, Q01835-Q00193, 13G_1+0_28MHZ_256QAM_170M. Install new HW MW Link Q01835-9369A, 23G_2+0_56MHZ_256QAM_EPLA. Later, decom existing SM MW Link_ID SW02954, Q01835-Q00193, 13G_1+0_28MHZ_256QAM_170M. **IMPORTANT NOTE: NEED TO PATCHING CAT 6 CABLE FROM XD CABINET(RTN910A-RTN01) TO XC CABINET AS RELOCATION PTN/CISCO WILL NOT DONE YET BY DECOM TEAM. ENSURE SUFFICIENT LENGTH OF CAT6 CABLE PROVIDED**. Site Impacted : Q01835. FE_9369A 1.Install new 23G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 2x XMC_3E, Sub A&B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port at PTN/Cisco at xC Cabinet. Configure it. 6.Re-use existing xC vlan dcn and vlan services. 7.Decom existing SM MW Link_ID SW02954, Q01835-Q00193, 13G_1+0_28MHZ_256QAM_170M. | XMC_3E | MAC | 23G | 23G_DP_1.2M(MAC)+OMT x1. | 23G_DP_1.2M(MAC)+OMT x1. | Allstar | SQ202509040277-Allstar | Allstar | SQ202509040262-Allstar // SQ202509040270-Allstar |  |  | Ongoing | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25101735 |  | 2025-10-18 | 2025-10-25 | Completed | 2025-10-17 | 2025-10-18 | 2025-10-17 | 2025-10-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-09 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-11-25 | 2025-12-02 | 2026-03-06 | 2026-03-06 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-19 | 2025-11-25 | 2025-12-02 | 2026-03-09 | 2026-03-09 | TONI//ANAK KUMBONG/6798000163 | 2025-05-19: 2025-11-25; 2025-05-19: 2025-12-02; 2025-05-19: 2025-11-25; 2025-05-24: 2025-11-25 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202508150549-GTSB
Q01701_HU | CB_JLNCOASTALBTU1 | DU00005895476 | Sarawak | Sarawak | 3.357130 | 113.267050 | [6 empty] | ZTE | 06. Other Issue | 27/10 - FE Done, NE need BM Access (TSS) | TSS+AA+TI+Dismantle |  | 13G_2+0_28M_256QAM_EPLA NE_Q01701 New 13G_1.8M(MDD) x1. New RTN910A(RTN01). New XMC_5D, Sub B_Lo x1. FE_Q00267 New 13G_1.8M(MDD) x1. New RTN910A(RTN01). New XMC_5D, Sub B_Hi x1. New CAT6 1x with suitable length. | MW Swap | Existing SM MW Link_ID SW02897, Q01701-Q00267, 13G_1+0_28MHZ_512QAM_200M. Install new HW MW Link Q01701-Q00267, 13G_2+0_28MHZ_256QAM_EPLA. Later, decom existing SM MW Link_ID SW02897, Q01701-Q00267, 13G_1+0_28MHZ_512QAM_200M. **IMPORTANT NOTE: Q00267 IS AGG SITE, RAN SOW DECOM, ANYWAY OTHER EQUIPMENT WILL NOT DECOM**. Site Impacted : Q01701. NE_Q01701 1.Install new 13G_1.8M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Re-use existing xC vlan dcn and vlan services. 7.Migrate traffic Q01701 via new HW MW Link Q01701-Q00267, 13G_2+0_28MHZ_256QAM_EPLA. 8.Decom existing SM MW Link_ID SW02897, Q01701-Q00267, 13G_1+0_28MHZ_512QAM_200M. FE_Q00267 1.Install new 13G_1.8M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port at PTN/Cisco at xC Cabinet. Configure it. 6.Re-use existing xC vlan dcn and vlan services. 7.Decom existing SM MW Link_ID SW02897, Q01701-Q00267, 13G_1+0_28MHZ_512QAM_200M. | Existing SM MW Link_ID SW02897, Q01701-Q00267, 13G_1+0_28MHZ_512QAM_200M. Install new HW MW Link Q01701-Q00267, 13G_2+0_28MHZ_256QAM_EPLA. Later, decom existing SM MW Link_ID SW02897, Q01701-Q00267, 13G_1+0_28MHZ_512QAM_200M. **IMPORTANT NOTE: Q00267 IS AGG SITE, RAN SOW DECOM, ANYWAY OTHER EQUIPMENT WILL NOT DECOM**. Site Impacted : Q01701. NE_Q01701 1.Install new 13G_1.8M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Re-use existing xC vlan dcn and vlan services. 7.Migrate traffic Q01701 via new HW MW Link Q01701-Q00267, 13G_2+0_28MHZ_256QAM_EPLA. 8.Decom existing SM MW Link_ID SW02897, Q01701-Q00267, 13G_1+0_28MHZ_512QAM_200M. | Existing SM MW Link_ID SW02897, Q01701-Q00267, 13G_1+0_28MHZ_512QAM_200M. Install new HW MW Link Q01701-Q00267, 13G_2+0_28MHZ_256QAM_EPLA. Later, decom existing SM MW Link_ID SW02897, Q01701-Q00267, 13G_1+0_28MHZ_512QAM_200M. **IMPORTANT NOTE: Q00267 IS AGG SITE, RAN SOW DECOM, ANYWAY OTHER EQUIPMENT WILL NOT DECOM**. Site Impacted : Q01701. FE_Q00267 1.Install new 13G_1.8M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port at PTN/Cisco at xC Cabinet. Configure it. 6.Re-use existing xC vlan dcn and vlan services. 7.Decom existing SM MW Link_ID SW02897, Q01701-Q00267, 13G_1+0_28MHZ_512QAM_200M. | XMC_5D | MDD | 13G | 13G_1.8M(MDD) x1. | 13G_1.8M(MDD) x1. | Magicell | SQ202509030212-Magicell | iEzzpro | SQ202604010642-Iezzpro // SQ202604010645-Iezzpro | 2026-01-14 | 2026-01-07 | Completed | 2025-09-03 | 2025-09-30 | 2025-12-01 | 2025-12-01 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-31 | 2026-01-07 | 2025-12-31 | 2025-12-31 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25101752 |  | 2025-10-18 | 2025-10-25 | Completed | 2025-10-17 | 2025-10-18 | 2025-10-17 | 2025-10-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-05-02 | 2026-04-02 | 2026-04-05 | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | 2026-04-02 | 2026-05-02 | 2026-04-02 |  | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | [7 empty] | 2026-04-02 | 2026-05-02 | 2026-04-02 |  | MOHAMAD TARMIZI//ISWANDI/6000060946 | 2025-05-19: 2026-04-02; 2025-05-19: 2026-05-02; 2025-05-19: 2026-04-02; 2025-05-24: 2026-04-04 | [7 empty] | GTSB | SQ202508150549-GTSB
K00023_HU_1 | CB_SERAKO | DU00005895477 | Northern | Kedah | 5.680833 | 100.862583 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 2X RTN910A 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1X ODU 15G XMC5D SUB B LO | MW Swap | MW SWAP K00023-K00185 WITH HUAWEI_15G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_B_WITH CA_4.85KM IMPACTED: K00023 DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910A WITH 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 128MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512AM WITH CA 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910A WITH 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 128MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512AM WITH CA 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK | 5D | MDD | 15G | 1.2 | 1.2 | GTSB | SQ202508220499-GTSB | GTSB | SQ202508220494-GTSB // SQ202508220496-GTSB | 2025-12-03 | 2025-12-03 | Completed | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081202 |  | 2025-08-16 | 2025-08-23 | Completed | 2025-08-15 | 2025-08-16 | 2025-08-15 | 2025-08-23 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-23 | 2025-08-31 | 2025-08-23 | 2025-12-13 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-08-23 | 2025-08-31 | 2025-08-23 | 2025-09-04 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-26 | 2025-08-23 | 2025-08-31 | 2025-08-23 | 2025-09-04 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-08-23 | 2025-08-31 | 2025-08-23 | 2025-08-25 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | EZRIN TASNIM BIN ABDUL GANI6798000128
K00119_IPR_2 | K009A_K00119OD_JKRKUALANERANG | DU00005895478 | Northern | Kedah | 6.251197 | 100.614711 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1) 2 x SFP 1G 1km 2) 2 pair optical patch cord | MW IDU Patching | Split traffic at IDU Huawei NT05948 K00119_JKRKUALANERANG - K00780_KGKUBANGJULUK GE5 to PTN 60087-JKRKUALANERANG/GigabitEthernet0/0/3 Patch IDU Huawei NT05948 K00119_JKRKUALANERANG - K00780_KGKUBANGJULUK GE4 to new PTN 60087-JKRKUALANERANG port and transfer traffic from sites below: 1) 4727D DESA NAKA (ZTE BBU) | Patch IDU Huawei NT05948 K00119_JKRKUALANERANG - K00780_KGKUBANGJULUK GE4 to new PTN 60087-JKRKUALANERANG port and transfer traffic from sites below: 1) 4727D DESA NAKA (ZTE BBU) | N/A | [5 empty] | Magicell | SQ202509180710-Magicell | Magicell | SQ202509180692-Magicell | 2025-12-23 | 2025-12-16 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | AHMAD RASHIDI BIN SAFRI7018000135 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092321 |  | 2025-09-24 | 2025-10-07 | Completed | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-10-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-20 | MHD FARID/BIN/NGADININ ADININ/6000054868 | Magicell TI | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-21 | MHD FARID/BIN/NGADININ ADININ/6000054868 | Magicell TI | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-20 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-20 | MHD FARID/BIN/NGADININ ADININ/6000054868 | 2025-05-19: 2025-10-30; 2025-05-19: 2025-10-30; 2025-05-19: 2025-10-30; 2025-05-24: 2025-11-20 |  |  | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512180096-GTSB
4706C_LOS | The Lexis Suites RT | DU00005895479 | Northern | Penang | 5.286409 | 100.232612 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_4706C 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , sub B_Hi x1. FE_4097A. 18G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub B_Lo x1. | MW New Link / Reroute | The existing link reroute to new FE 4097A due to LOS Block. New link install with 18G_2+0_112M to new FE routing. Site Impacted : 4706C. NE_4706C 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , sub B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new and new FE routing. 6.Decom existing MW link. FE_4097A. 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4097A_RTN03 (ID : 23673). 3.Install new 3_ISM8-2+0 into existing 4097A_RTN03. 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | The existing link reroute to new FE 4097A due to LOS Block. New link install with 18G_2+0_112M to new FE routing. Site Impacted : 4706C. NE_4706C 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , sub B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new and new FE routing. 6.Decom existing MW link. | The existing link reroute to new FE 4097A due to LOS Block. New link install with 18G_2+0_112M to new FE routing. Site Impacted : 4706C. FE_4097A. 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4097A_RTN03 (ID : 23673). 3.Install new 3_ISM8-2+0 into existing 4097A_RTN03. 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | [5 empty] | GCI | SQ202508290691-GCI | GCI | SQ202510070041-GCI // SQ202510070042-GCI | 2025-11-12 | 2025-11-11 | Completed | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | 2025-09-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-11 | 2025-11-12 | 2025-11-11 | 2025-11-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092319 |  | 2025-09-24 | 2025-09-24 | Completed | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-08 | 2025-10-13 | 2025-10-08 | 2025-10-12 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-10-08 | 2025-10-13 | 2025-10-08 | 2025-10-12 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-09 | 2025-10-08 | 2025-10-13 | 2025-10-08 | 2025-10-16 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-10-08 | 2025-10-13 | 2025-10-08 | 2025-10-08 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | NG HONG JIE7018000036 | Logistic Team | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-28 | 2025-08-29 | 2025-08-29 | 2025-08-29 | CHEONG/SENG/WAH/7018000306
1607H_LOS | 99 Speedmart Puchong Taming Boulevard | DU00005895480 | Central | Selangor | 2.979411 | 101.606203 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS Radio NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH LAN cable x1. FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH LAN Cable x 1. | MW New Link / Reroute | NLOS Link reroute to new FE 13728 due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 1607H. NE_1607H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (1607H-NLOS-2657B). FE_1372B. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new Inband DCN. 5.Traffic migrate to new route FE and with new NLOS. 6.ETH cable patching to Ibeam new Port Gi 0/2/24. 7.Decom existing NLOS Radio (2657B-NLOS-1607H). | NLOS Link reroute to new FE 13728 due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 1607H. NE_1607H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (1607H-NLOS-2657B). | NLOS Link reroute to new FE 13728 due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 1607H. FE_1372B. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new Inband DCN. 5.Traffic migrate to new route FE and with new NLOS. 6.ETH cable patching to Ibeam new Port Gi 0/2/24. 7.Decom existing NLOS Radio (2657B-NLOS-1607H). | [5 empty] | GTSB | SQ202508010563-GTSB | GTSB | SQ202508200506-GTSB // SQ202508200516-GTSB | 2025-08-27 | 2025-08-20 | Completed | 2025-08-13 | 2025-08-27 | 2025-08-13 | 2025-08-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-27 | 2025-08-13 | 2025-08-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-14 | 2025-08-15 | 2025-08-14 | 2025-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080803 |  | 2025-08-09 | 2025-08-20 | Completed | 2025-08-08 | 2025-08-09 | 2025-08-08 | 2025-08-20 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-22 | 2025-08-31 | 2025-08-22 | 2025-08-25 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-08-22 | 2025-08-31 | 2025-08-22 | 2025-09-03 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-26 | 2025-08-22 | 2025-08-31 | 2025-08-22 | 2025-09-02 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-08-22 | 2025-08-31 | 2025-08-22 | 2025-08-25 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202508150527-GCI | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | CHEONG/SENG/WAH/7018000306
2069B_HU | WT_UITMPNCKALAM | DU00005895481 | Central | Selangor | 3.204196 | 101.453258 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 1X ISM8 CARD 1X RTN910A 1X 18G 0.6M DP ANTENNA 1X 18G 1.2M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Parallel Link | MW PARALLEL LINK 2069B-1612B WITH HUAWEI_18G_2+0_0.6M/1.2M_DP_112MHZ_256QAM_1556MBPS_XMC3E_SUB_A & B_3.88KM IMPACTED: 2680B, 1518C, 3804A THIS LINK TO CARRY TRAFFIC 2680B, 1518C, 3804A | 1. INSTALL NEW 1PCS ISM8 AT SLOT 3 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 512AM 5. CANCEL CASCADE BETWEEN RTN01 AND RTN03 6. THIS LINK TO CARRY TRAFFIC 2680B, 1518C, 3804A | 1. INSTALL NEW RTN910A 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 512AM 5. PATCH TO NEW CP PORT AND DO PORT LAG 2G 6. THIS LINK TO CARRY TRAFFIC 2680B, 1518C, 3804A | XMC3E | MAC | 18G | 1.2 | 0.6 | GCI | SQ202508040476-GCI | GCI | SQ202508040515-GCI // SQ202508040517-GCI | 2025-11-06 | 2025-11-05 | Completed | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-05 | 2025-11-06 | 2025-11-05 | 2025-11-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082269 | No 18G_2+0_1.2/0.6 | 2025-08-23 | 2025-08-28 | Completed | 2025-08-22 | 2025-08-23 | 2025-08-22 | 2025-08-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-24 | 2025-09-30 | 2025-09-23 | 2025-09-25 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-09-24 | 2025-09-30 | 2025-09-23 | 2025-10-13 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | SITI HAFIZAH BINTI NOH6237001145 |  |  | 2025-09-24 | 2025-09-30 | 2025-09-23 | 2025-10-13 | Ragunalan//A/L L.Krisnan6000006720 | 2025-05-19: 2025-09-24; 2025-05-19: 2025-09-30; 2025-05-19: 2025-09-23; 2025-05-24: 2025-09-24 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202508150527-GCI | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
4393A_HU_1 | Tg Piandang RDD | DU00005895482 | Northern | Perak | 5.066460 | 100.382480 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M NE_4393A 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , sub A_Lo x1. FE_4141R 13G_DP_1.2M(MDD). x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing link 13G_4+0_28M (4393A - 4396A) Link reroute to FE 4141R with swap existing link to 13G_6+0_28M. Create 2nd DU ID for 2nd ant (4393A_HU) and upgrade uplink to new parallel link 18G_2+0 (DU ID 4141R_AD). Link Config 13G_2+0_28M (NCA) with refer DU ID 4393A_HU (DU Code : DU00005862746) to EPLA with 13G_4+0_28M (CA) for complete 13G_6+0_28M full configuration. TSS for FE reroute to 4141R is required. Install Uplink 4141R-4396A is priority. Site Impacted : 4393A NE_4393A 1.Install new 13G_DP_1.2M(MDD) x1. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by Ops team). 3.Install new XMC_5D , sub A_Lo for ant 2. 4.Create service cross connect and EPLA to become 13G_6+0_28M. 5.Enable GE1 , traffic 4393B_BBU migrate to new link and new FE routing. FE_4141R 1.Install new 13G_DP_1.2M(MDD). x1. 2.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by Ops team). 3.Install new XMC_5D , Sub A_Hi for ant 2. 4.Create service cross connect and EPLA to become 13G_6+0_28M. 5.Enable GE1 , ETH patching to existing 4141R_RTN02_GE1 (ID : 13787). 6.Traffic migrate to new link and New FE routing. | Existing link 13G_4+0_28M (4393A - 4396A) Link reroute to FE 4141R with swap existing link to 13G_6+0_28M. Create 2nd DU ID for 2nd ant (4393A_HU) and upgrade uplink to new parallel link 18G_2+0 under DU ID 4141R_AD. Link Config 13G_2+0_28M (NCA) with refer DU ID 4393A_HU (DU Code : DU00005862746) EPLA with 13G_4+0_28M (CA) to complete 13G_6+0_28M full configuration. TSS for FE reroute to 4141R is required. Install Uplink 4141R - 4396A is priority. Site Impacted : 4393A NE_4393A 1.Install new 13G_DP_1.2M(MDD) x1. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by Ops team). 3.Install new XMC_5D , sub A_Lo for ant 2. 4.Create service cross connect and EPLA to become 13G_6+0_28M. 5.Enable GE1 , traffic 4393B_BBU migrate to new link and new FE routing. | Existing link 13G_4+0_28M (4393A - 4396A) Link reroute to FE 4141R with swap existing link to 13G_6+0_28M. Create 2nd DU ID for 2nd ant (4393A_HU) and upgrade uplink to new parallel link 18G_2+0 under DU ID 4141R_AD. Link Config 13G_2+0_28M (NCA) with refer DU ID 4393A_HU (DU Code : DU00005862746) EPLA with 13G_4+0_28M (CA) to complete 13G_6+0_28M full configuration. TSS for FE reroute to 4141R is required. Install Uplink 4141R - 4396A is priority. Site Impacted : 4393A FE_4141R 1.Install new 13G_DP_1.2M(MDD). x1. 2.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by Ops team). 3.Install new XMC_5D , Sub A_Hi for ant 2. 4.Create service cross connect and EPLA to become 13G_6+0_28M. 5.Enable GE1 , ETH patching to existing 4141R_RTN02_GE1 (ID : 13787). 6.Traffic migrate to new link and NE FE route. | XMC_5D | MDD | 13G | 1.8 | 1.8 | GCI | SQ202511110794-GCI | GCI | SQ202508270947-GCI // SQ202508270956-GCI | 2025-12-10 | 2025-12-10 | Completed | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250821AG |  | 2025-08-22 | 2025-08-23 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-09-08 | 2025-08-25 | 2025-08-30 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-08-25 | 2025-09-08 | 2025-08-25 | 2025-08-30 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-15 | 2025-08-25 | 2025-09-08 | 2025-08-25 | 2025-11-07 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-05-19: 2025-08-25; 2025-05-19: 2025-09-08; 2025-05-19: 2025-08-25; 2025-05-24: 2025-11-11 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | CHEONG/SENG/WAH/7018000306
4141R_AD | Kg. Kedai Dua | DU00005895483 | Northern | Perak | 5.022992 | 100.468223 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M NE_4141R. 18G_DP_1.2M(MDD) x1. ISM8 x1 XMC_5D , Sub A _Lo x1. FE_4396A/A00216. 18G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub A _Hi x1. | MW Parallel Link | Existing link 18G_2+0_112M Install Parallel link 18G_2+0_112M to support additional child site for 4393A & existing 4334A child sites. Site Impacted : 4393A & 4334A. NE_4141R. 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 4141R_RTN02 (ID : 13787). 3.Install new 4_ISM8-2+0 into existing 4141R_RTN02 (ID : 13787). 4.Install new XMC_5D , Sub A _Lo. 5.Create service cross connect and EPLA with existing link. 6.No decom link. FE_4396A/A00216. 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4396A/A00216_RTN910A (ID : 23787). 3.Install new 3_ISM8-2+0 into existing 4396A/A00216_RTN910A (ID : 23787). 4.Install new XMC_5D , Sub A _Hi. 5.Create service cross connect and EPLA with existing link. 6.No decom link. | Existing link 18G_2+0_112M Install Parallel link 18G_2+0_112M to support additional child site for 4393A & existing 4334A child sites. Site Impacted : 4393A & 4334A. NE_4141R. 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 4141R_RTN02 (ID : 13787). 3.Install new 4_ISM8-2+0 into existing 4141R_RTN02 (ID : 13787). 4.Install new XMC_5D , Sub A _Lo. 5.Create service cross connect and EPLA with existing link. 6.No decom link. | Existing link 18G_2+0_112M Install Parallel link 18G_2+0_112M to support additional child site for 4393A & existing 4334A child sites. Site Impacted : 4393A & 4334A. FE_4396A/A00216. 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4396A/A00216_RTN910A (ID : 23787). 3.Install new 3_ISM8-2+0 into existing 4396A/A00216_RTN910A (ID : 23787). 4.Install new XMC_5D , Sub A _Hi. 5.Create service cross connect and EPLA with existing link. 6.No decom link. | XMC_5D | MDD | 18G | 1.2 | 0.6 | Magicell | SQ202508010577-Magicell | Magicell | SQ202509110832-Magicell // SQ202509110840-Magicell | 2026-01-20 | 2026-01-21 | Completed | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082136 |  | 2025-08-22 | 2025-08-25 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-05 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-26 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-13 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-05-19: 2025-09-23; 2025-05-19: 2025-09-23; 2025-05-19: 2025-09-23; 2025-05-24: 2025-10-06 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | CHEONG/SENG/WAH/7018000306
A00525_HU | CB_SGSIPUTEH | DU00005895484 | Northern | Perak | 5.260500 | 100.811410 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M NE_A00525 13G_DP_2.4M(MS) + ODU Mounting x1. ISM8-x1. XMC_3E , Sub A & B_Hi x1. Waveguide x1. FE_K00262. 13G_DP_1.8M(MS) + ODU Mounting x1. ISM8 x1. XMC_3E , Sub A & B _Lo x1. Waveguide x1. | MW Parallel Link | Link existing 13G_2+0_28M. Install parallel link 13G_2+0_28M with EPLA to existing link 13G_2+0_28M. Site Impacted : A00525. NE_A00525 1.Install new 13G_DP_2.4M(MS) + ODU Mounting + Waveguide. 2.Reuse existing A00525_RTN910A (ID : 13848). 3.Install new 3_ISM8-2+0 into existing A00525_RTN910A (ID: 13848). 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new EPLA link (New link + Existing link). 7.No link to be decom. FE_K00262. 1.Install new 13G_DP_1.8M(MS) + ODU Mounting + Waveguide. 2.Reuse existing K00262_RTN910A (ID : 23848). 3.Install new 3_ISM8-2+0 into existing K00262_RTN910A (ID : 23848). 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to EPLA link (New link + Existing Link). 7.No link to be decom. | Link existing 13G_2+0_28M. Install parallel link 13G_2+0_28M with EPLA to existing link 13G_2+0_28M. Site Impacted : A00525. NE_A00525 1.Install new 13G_DP_2.4M(MS) + ODU Mounting + Waveguide. 2.Reuse existing A00525_RTN910A (ID : 13848). 3.Install new 3_ISM8-2+0 into existing A00525_RTN910A (ID: 13848). 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new EPLA link (New link + Existing link). 7.No link to be decom. | Link existing 13G_2+0_28M. Install parallel link 13G_2+0_28M with EPLA to existing link 13G_2+0_28M. Site Impacted : A00525. FE_K00262. 1.Install new 13G_DP_1.8M(MS) + ODU Mounting + Waveguide. 2.Reuse existing K00262_RTN910A (ID : 23848). 3.Install new 3_ISM8-2+0 into existing K00262_RTN910A (ID : 23848). 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to EPLA link (New link + Existing Link). 7.No link to be decom. | XMC_3E | MS | 13G | 2.4M | 1.8M | GCI | SQ202509180678-GCI | GCI | SQ202509180657-GCI // SQ202509180667-GCI | 2025-11-28 | 2025-11-27 | Completed | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082831 |  |  |  | Disabled | [8 empty] | Unassigned | Disabled |  | 2025-09-04 | 2025-09-18 | 2025-09-04 | 2026-01-29 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-09-04 | 2025-09-18 | 2025-09-04 | 2025-09-20 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-09-04 | 2025-09-18 | 2025-09-04 | 2025-09-23 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-05-19: 2025-09-04; 2025-05-19: 2025-09-18; 2025-05-19: 2025-09-04; 2025-05-24: 2025-09-09 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | CHEONG/SENG/WAH/7018000306
B01049_IPR | B062A_B01049OD_BT37SEKENDI | DU00005895485 | Central | Selangor | 3.740100 | 100.946600 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | Upgrade patching from IDU to PTN 1G to 10G. Existing: IDU 1107K/B01049-BT37 SEKENDI-RTN01 GE5 to PTN 71450-BT37_SEKENDI GigabitEthernet0/0/4 Integration team to assign new port at IDU and PTN during upgrade. Transfer all sites currently on 0/0/4 to new port | Upgrade patching from IDU to PTN 1G to 10G. Existing: IDU 1107K/B01049-BT37 SEKENDI-RTN01 GE5 to PTN 71450-BT37_SEKENDI GigabitEthernet0/0/4 Integration team to assign new port at IDU and PTN during upgrade. Transfer all sites currently on 0/0/4 to new port | N/A | [5 empty] | GTSB | SQ202508010563-GTSB | GTSB | SQ202508010602-GTSB | 2025-10-09 | 2025-10-08 | Completed | 2025-09-22 | 2025-10-06 | 2025-09-22 | 2025-09-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-10-06 | 2025-09-22 | 2025-09-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-08 | 2025-10-09 | 2025-10-08 | 2025-10-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080587 |  | 2025-08-06 | 2025-08-20 | Completed | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-04 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-04 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-08 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-05-19: 2025-09-02; 2025-05-19: 2025-09-02; 2025-05-19: 2025-09-02; 2025-05-24: 2025-09-03 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202508150527-GCI | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
7494B_HU | Kg Koya | DU00005895486 | Sabah | Sabah | 5.275170 | 118.105220 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_1.2/1.2_MS 1xISM8 2xXMC_3_SB A,B | MW Swap | MW SWAP EXISTING 13G_1+0 WITH 13G_4+0_1.2/1.2_MS_256QAM_800M_EPLAN WITH EXISTING MW 13G_2+0 (total 6+0) | MW SWAP EXISTING 13G_1+0 WITH 13G_4+0_1.2/1.2_MS_256QAM_800M_EPLAN WITH EXISTING MW 13G_2+0 NE: 1. Reuse exisitng RTN910A_RTN04. 2. Install 1xISM8 at slot 4. 3. Swap existing antenna with 13G_MAC 4. Swap exisitng ODU with new XMC-3_SB A,B 5. Configure 13G_4+0_1.2/1.2_MS_256QAM_800M_ EPLA with existing 13G_2+0 link. | MW SWAP EXISTING 13G_1+0 WITH 13G_4+0_1.2/1.2_MS_256QAM_800M_EPLAN WITH EXISTING MW 13G_2+0 FE: 1. Reuse exisitng RTN910A_RTN07. 2. use existing ISM8 at slot 3 and Slot 7 3. Swap existing antenna with 13G_MAC 4. Swap exisitng ODU with new XMC-3_SB A,B 5. Configure 13G_4+0_1.2/1.2_MS_256QAM_800M_ EPLA with existing 13G_2+0 link. | XMC-3_SB A,B |  | 13 | 1.2 | 1.2 | GCI | SQ202508270911-GCI | GCI | SQ202508250325-GCI // SQ202508250330-GCI | 2025-11-24 | 2025-11-17 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-05 | 2025-11-12 | 2025-11-05 | 2025-11-05 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-17 | 2025-11-24 | 2025-11-17 | 2025-11-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080514 |  | 2025-08-06 | 2025-08-18 | Completed | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-18 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-28 | JACKSON//BIN MAKANSIM/6000027984 | GCI TI | 2025-08-19 | 2025-08-22 | 2025-08-19 | 2025-08-28 | JACKSON//BIN MAKANSIM/6000027984 | GCI TI | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-03 | 2025-08-19 | 2025-08-22 | 2025-08-19 | 2025-10-13 | JACKSON//BIN MAKANSIM/6000027984 | 2025-05-19: 2025-08-19; 2025-05-19: 2025-08-22; 2025-05-19: 2025-08-19; 2025-05-24: 2025-08-22 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202508150543-GTSB | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | HSU//MYET CHAE/6799000011
7996B57_EVT | MBTS FESTIVAL KEBUDAYAAN RUMPUN BAJAUSAMA | DU00005901523 | Sabah | Sabah | 6.166550 | 116.186430 | [13 empty] | Planning and integration support only for event site 7996B57 MBTS FESTIVAL KEBUDAYAAN RUMPUN BAJAUSAMA Tx route: 7996B57/7996B57-7155A 1) New port at 7155A-MAC-001 Maxi Purpose Tuaran 2) New DCN IP 7155A RTN03 3) New DCN VLAN 7155A RTN03 4) New NE ID FE IDU 7155A RTN03 5) New NE ID NE IDU 7996B57 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
7996B53_EVT | MBTS_PESTA KAAMATAN KDCA 2025 | DU00005560586 | Sabah | Sabah | 5.922372 | 116.090589 | [11 empty] | NE RTN910A x1 XMC_3E , 23G_A_Lo 23G_SP_0.6(MAC). FE NE RTN910A x1 XMC_3E , 23G_A_Lo 23G_SP_0.6(MAC). |  | 7996B53 Tx route: 7996B53-7039A 1) New port at 7039A-MAC-001 Donggongon 2) New DCN IP 7039A RTN10 3) New DCN VLAN 7039A RTN10 4) New NE ID FE IDU 7039A RTN10 5) New NE ID NE IDU 7996B53 RTN01 |  |  | XMC_3E | MAC | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505190529-GCI | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | CHEONG/SENG/WAH/7018000306
7365B_HU_1 | Richard Lind Tower SBC | DU00005560587 | Sabah | Sabah | 5.341290 | 118.482297 |  |  |  | JUN 25 | TI DONE | 28/05: TI WIP, day 6 | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2 x IDU 910A 2 x MODU 13G subband A and B 2 x 13G 2.4m MS antenna IF cable & Accessories 4 x ISM8 card | MW Hardware Upgrade | To replace existing hardware as part of troubleshooting | To replace existing hardware as part of troubleshooting | To replace existing hardware as part of troubleshooting | XMC5D | MS DP | 13G | 2.4m | 2.4m | NR services | SQ202505280540-NR Services | NR services | SQ202505280544-NR Services // SQ202505280545-NR Services |  |  | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25052175 |  | 2025-05-22 | 2025-05-22 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-22 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2025-07-03 | MUHAMMAD ROBBIL AKRIZAN//BIN SHAARI/7167000044 | NR Service TI | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2025-07-12 | MUHAMMAD ROBBIL AKRIZAN//BIN SHAARI/7167000044 | NR Service TI | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-29 | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2025-09-02 | MUHAMMAD ROBBIL AKRIZAN//BIN SHAARI/7167000044 | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2025-06-13 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | tseping//wang/6819000006 | Logistic Team | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 |  | Assign Subcon
2979B_PL | Traders Hotel | DU00005384520 | Central | Kuala Lumpur | 3.153877 | 101.714873 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | BBU Patching | BBU PATCHING FOR 2979B TO W00358 DUE TO PL PREVIOUS ROUTE: 2979B-FESHARING-1271A | [7 empty] | GTSB | SQ202505050010-GTSB | GTSB | SQ202505050009-GTSB | 2025-07-11 | 2025-07-03 | Completed | 2025-05-21 | 2025-06-04 | 2025-05-21 | 2025-05-21 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-21 | 2025-06-04 | 2025-05-21 | 2025-05-21 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-03 | 2025-07-11 | 2025-07-03 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250507A0 |  | 2025-05-08 | 2025-05-21 | Completed | 2025-05-07 | 2025-05-08 | 2025-05-07 | 2025-05-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-08 | 2025-05-31 | 2025-05-08 | 2025-05-21 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-05-08 | 2025-05-31 | 2025-05-08 | 2025-05-21 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-10 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  | 2025-05-10 | 2025-05-08 | 2025-05-31 | 2025-05-08 | 2025-05-19 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2025-06-08: 2025-05-08; 2025-06-08: 2025-05-31; 2025-06-08: 2025-05-08; 2025-06-13: 2025-05-09 |  |  | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505070146-GCI | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
4725B_Decom | Wang Tepus | DU00003874776 | Northern | Kedah | 6.244348 | 100.476747 | [7 empty] | 06. Other Issue | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [35 empty] | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | RIZAL//FA'IZ BIN RAMLI/6799000024
7996B56_EVT | MBTS SAMBUTAN FESTIVAL KEBUDAYAAN ANTARABANGSA TAWAU (FKAT) 2025 | DU00005887780 | Sabah | Sabah | 5.793560 | 116.820122 | [13 empty] | Planning and integration support only for event site 7996B56 MBTS SAMBUTAN FESTIVAL KEBUDAYAAN ANTARABANGSA TAWAU (FKAT) 2025 Tx route: 7996B56-S00221 1) New port at PTN S00221 20291-TAI_TAI 2) New DCN IP S00221 RTN01 3) New DCN VLAN S00221 RTN01 4) New NE ID FE IDU S00221 RTN01 5) New NE ID NE IDU 7996B56 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
4470A_AD_1 | Beruas(Maxis) | DU00005927276 | Northern | Kedah | 4.498551 | 100.782910 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | ETH Lan Cable x1 | BBU Patching | NE_4470A 1.Enable GE2 , 4470A_RTN01 (ID : 13875). 2.ETH Patching BBU_4470A to 4470A_RTN01_GE2 ( ID: 13875). 3.Create cross connect and traffic migrate to new MW routing. 4.Decom existing SM link (4470A - 4490A MW1). Refer DU ID 4470A_AD , DU Code : DU00005927277). | NE_4470A 1.Enable GE2 , 4470A_RTN01 (ID : 13875). 2.ETH Patching BBU_4470A to 4470A_RTN01 ( ID: 13875). 3.Create cross connect and traffic migrate to new MW routing. 4.Decom existing SM link (4470A - 4490A MW1). Refer DU ID 4470A_AD , DU Code : DU00005927277). | [6 empty] | GCI | SQ202508110937-GCI | GCI | SQ202508110934-GCI | 2025-11-28 | 2025-11-27 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081204 |  | 2025-08-16 | 2025-08-14 | Completed | 2025-08-15 | 2025-08-16 | 2025-08-13 | 2025-08-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-21 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-21 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-23 | MOHD SAIDI BIN ABD RAZAK6800000181 | 2025-06-08: 2025-08-19; 2025-06-08: 2025-08-26; 2025-06-08: 2025-08-19; 2025-06-13: 2025-08-19 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | CHEONG/SENG/WAH/7018000306
4470A_AD | Beruas(Maxis) | DU00005927277 | Northern | Kedah | 4.498551 | 100.782910 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | MRCF+PAC |  | MW Dismantle | 1.BBU_4470A migrate to new MW routing , refer DU ID 4470A_AD_1 ( DU Code : DU00005927276). 2. Decom MW link 4470A - 4490A MW1 | .BBU_4470A migrate to new MW routing , refer DU ID 4470A_AD_1 ( DU Code : DU00005927276). 2. Decom MW link 4470A - 4490A MW1 | .BBU_4470A migrate to new MW routing , refer DU ID 4470A_AD_1 ( DU Code : DU00005927276). 2. Decom MW link 4490A-4470A MW1 | [5 empty] | GCI | SQ202509130051-GCI | GCI | SQ202508250280-GCI // SQ202508250285-GCI // SQ202511060458-GCI | 2025-12-04 | 2025-12-03 | Completed | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081205 |  | 2025-08-16 | 2025-08-14 | Completed | 2025-08-15 | 2025-08-16 | 2025-08-13 | 2025-08-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-21 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-21 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2026-03-31 | MOHD SAIDI BIN ABD RAZAK6800000181 | 2025-06-08: 2025-08-19; 2025-06-08: 2025-08-26; 2025-06-08: 2025-08-19; 2025-06-13: 2025-08-19 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | CHEONG/SENG/WAH/7018000306
Q00792_HU_1 | Q144A_Q00792OD_CB_KUALATATAU | DU00005932716 | Sarawak | Sarawak | 3.078503 | 112.814830 | [7 empty] | 03. Pending TSS |  | TSS+AA+TI |  | 13G_2+0_1.8/1.2_MDD_SB B 1x ISM8 | MW Parallel Link | MW PARALLEL LINK TO Q00792-9125A WITH 13G_2+0_1.8/1.2_MDD_SB B Configure EPLA with 1st 13G_4+0 link to become 6+0. | MW PARALLEL LINK TO Q00792-9125A WITH 13G_4+0_1.8/1.2_MDD_SB A NE: 1. Reuse RTN910A_RTN use Slot 7( from 1st new link installation) 2. Install new XMC-5D_SB B. 3. Install new antenna 13G_1.8_MDD. 4. Configure 13G_2+0_1.8/1.2_MDD_EPLA with 1st New link 13G_4+0 to become 6+0 links carry Q00792 and Q01119 | MW PARALLEL LINK TO Q00792-9125A WITH 13G_4+0_1.8/1.2_MDD_SB A NE: 1. Reuse new RTN910A_RTN (from 1st New link installation). 2. Install new XMC-5D_SB B. 3. Install new antenna 13G_1.2_MDD. 4. Configure 13G_2+0_1.8/1.2_MDD_EPLA with 1st New link 13G_4+0 to become 6+0 links carry Q00792 and Q01119. | XMC-5D B | MDD | 13G | 1.8 | 1.2 | Magicell | SQ202509180716-Magicell |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2025-10-28 | 2025-11-07 |  |  | DAMIEN OH BOON PAR7018000155 | Magicell TI | 2025-10-29 | 2025-11-08 |  |  | WATSON ANAK MAMBA7018000213 | Magicell TI | [7 empty] | 2025-10-29 | 2025-11-08 |  |  | WATSON ANAK MAMBA7018000213 | 2025-06-08: 2025-10-29; 2025-06-08: 2025-11-08; 2025-06-08: 2026-02-27; 2025-06-13: 2026-02-27 | [7 empty] | GTSB | SQ202508150549-GTSB | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | HSU//MYET CHAE/6799000011
7649B_HU_1 | Seafest Hotel | DU00006222360 | Sabah | Sabah | 4.478526 | 118.617523 |  |  |  |  | DT February |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M_256QAM_EPLA NE_7649B Re-use existing XMC-3, Sub B_Lo(18G) - support BW 112MHz. Perhaps require new IF cable with suitable length 2x if required(due to short length of existing IF cable when shifting to other RTN910AF(RTN01). FE_7209A New XMC_3E, Sub B_Hi x1.(18G) | MW Hardware Upgrade | ****IMPORTANT NOTE: 1.NEED TO APPLY CRQ AS CHILD SITE IS EB 7801E. 2.NEED TO IMPLEMENT SIMULTANEOUSLY DU 7649B_HU_1 & DU 7649B_HU BY SAME TEAM/SUB CON. 3.REFER DU 7649B_HU FOR TX SOW**** Existing HW MW link 18G_2+0_112M&56M_256QAM_EPLA(2nd HW MW Parallel Link).. MW Hardware Upgrade for 2nd channel from BW 56MHz to 112MHz. Site Impacted : 7649B, 7230C, 7801E, 7360A & 7213R. NE_7649B 1.Shifting existing ISM8 slot 04 of existing RTN910AF(RTN03) to slot 03 of RTN910A(RTN01). 2.Ensure existing IF cables can reach slot 03 of RTN910A(RTN01). If NOT, please request new IF cable. 3.Build HW MW Link 18G_2+0_112M_256QAM_EPLA. 4.Build combination of HW MW Link 18G_2+0_112M_256QAM_EPLA(under DU 7649B_HU-1) and HW MW Link 23G_2+0_112M_512QAM_EPLA(Under DU 7649B_HU). 5.Later, Radio config will be 18G&23G_4+0_112M_256QAM&512QAM_EPLA. FE_7209A 1.Remove existing XMC_3(not support BW 112MHz) and install new XMC_3E, Sub B_Hi x1 for CH2(Horizontal Polarization 3-ISM8-2). 2.Do not touch existing XMC_3, Sub B_Hi for CH1(Vertical Polarization 3-ISM8-1). Remain used. 3.Build new config of HW MW Link 18G_2+0_112M_256QAM_EPLA. 4.Build combination of HW MW Link 18G_2+0_112M_256QAM_EPLA(under DU 7649B_HU-1) and HW MW Link 23G_2+0_112M_512QAM_EPLA(Under DU 7649B_HU). 5.Later, Radio config will be 18G&23G_4+0_112M_256QAM&512QAM_EPLA. | ****IMPORTANT NOTE: 1.NEED TO APPLY CRQ AS CHILD SITE IS EB 7801E. 2.NEED TO IMPLEMENT SIMULTANEOUSLY DU 7649B_HU_1 & DU 7649B_HU BY SAME TEAM/SUB CON. 3.REFER DU 7649B_HU FOR TX SOW**** Existing HW MW link 18G_2+0_112M&56M_256QAM_EPLA(2nd HW MW Parallel Link).. MW Hardware Upgrade for 2nd channel from BW 56MHz to 112MHz. Site Impacted : 7649B, 7230C, 7801E, 7360A & 7213R. NE_7649B 1.Shifting existing ISM8 slot 04 of existing RTN910AF(RTN03) to slot 03 of RTN910A(RTN01). 2.Ensure existing IF cables can reach slot 03 of RTN910A(RTN01). If NOT, please request new IF cable. 3.Build HW MW Link 18G_2+0_112M_256QAM_EPLA. 4.Build combination of HW MW Link 18G_2+0_112M_256QAM_EPLA(under DU 7649B_HU-1) and HW MW Link 23G_2+0_112M_512QAM_EPLA(Under DU 7649B_HU). 5.Later, Radio config will be 18G&23G_4+0_112M_256QAM&512QAM_EPLA. | ****IMPORTANT NOTE: 1.NEED TO APPLY CRQ AS CHILD SITE IS EB 7801E. 2.NEED TO IMPLEMENT SIMULTANEOUSLY DU 7649B_HU_1 & DU 7649B_HU BY SAME TEAM/SUB CON. 3.REFER DU 7649B_HU FOR TX SOW**** Existing HW MW link 18G_2+0_112M&56M_256QAM_EPLA(2nd HW MW Parallel Link).. MW Hardware Upgrade for 2nd channel from BW 56MHz to 112MHz. Site Impacted : 7649B, 7230C, 7801E, 7360A & 7213R. FE_7209A 1.Remove existing XMC_3(not support BW 112MHz) and install new XMC_3E, Sub B_Hi x1 for CH2(Horizontal Polarization 3-ISM8-2). 2.Do not touch existing XMC_3, Sub B_Hi for CH1(Vertical Polarization 3-ISM8-1). Remain used. 3.Build new config of HW MW Link 18G_2+0_112M_256QAM_EPLA. 4.Build combination of HW MW Link 18G_2+0_112M_256QAM_EPLA(under DU 7649B_HU-1) and HW MW Link 23G_2+0_112M_512QAM_EPLA(Under DU 7649B_HU). 5.Later, Radio config will be 18G&23G_4+0_112M_256QAM&512QAM_EPLA. | XMC_3E | MAC | 18G | 18G_0.6M(MAC)+OMT x1. | 18G_0.6M(MAC)+OMT x1. | Seri Pancar | SQ202602090132-Seri Pancar | NR services | SQ202602160087-NR Services // SQ202602160089-NR Services | 2026-04-02 | 2026-03-30 | Completed | 2026-02-04 | 2026-02-28 | 2026-02-06 | 2026-02-06 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-16 | 2026-03-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26021230 |  | 2026-02-15 | 2026-02-14 | Completed | 2026-02-14 | 2026-02-15 | 2026-02-14 | 2026-02-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-16 | 2026-03-15 | 2026-02-15 | 2026-02-27 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-16 | 2026-03-15 | 2026-02-15 | 2026-02-27 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-03-01 | 2026-02-16 | 2026-03-15 | 2026-02-15 | 2026-03-09 | RALPH O'BRYAN HILARY7167000030 | 2025-06-08: 2026-02-16; 2025-06-08: 2026-03-15; 2025-06-08: 2026-02-15; 2025-06-13: 2026-02-26 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202510300419-GTSB
S00945-S00163 | BUKIT IJAI | DU00004758498 | Sabah | Sabah | 6.408910 | 116.790110 |  |  |  |  | Pending Material | MwAntenna HW-15G_1.2M/MDD | ZTE | 03. TSS Only | Non-doable | TSS |  | 15G_4+0_1.2/1.2_MDD_28MHZ_SB A | MW Parallel Link | hange from [] to [MW PARARLLEL LINK S00945-S00163 WITH 15G_4+0_1.2/1.2_MDD_28MHZ. NE: 1. Install new RTN910A. 2. Install 2xISM8 at slot 3 and 4. 3. Install 15G_XMC_5D_SB A. 4. Install new 15G_1.2_MDD antanna. 5. Configure 15G_4+0_1.2_MDD_CA. 6. Carry traffic S00945. FE: 1. Install new RTN910A. 2. Install 2xISM8 at slot 3 and 4. 3. Install 15G_XMC_5D_SB A. 4. Install new 15G_1.2_MDD antanna. 5. Configure 15G_4+0_1.2_MDD_CA. 6. Carry traffic S00945.] Handler:HSU//MYET CHAE/6799000011 | [7 empty] | NR services | SQ202505210177-NR Services |  |  | 2025-06-27 | 2025-06-26 | Completed | 2025-05-18 | 2025-05-20 | 2025-05-18 | 2025-05-20 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Unassigned | Completed |  | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-06-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050733-GTSB | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | HSU//MYET CHAE/6799000011
S00197 | S112A_S00197OD_TMTELUPID | DU00004758499 | Sabah | Sabah | 5.632500 | 117.129400 |  |  |  |  | RFS | DONE | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_1.2/1.2_SB A | MW New Link / Reroute | MW REROUT LINK S00197-7324A WITH HW 13G_4+0_1.2/1.2_SB A DUE TO FE S00174 WILL BE DISMANTLE. NE: 1. Install new RTN910A. 2. Install XMC-5D_SB A. 3. Install new antenna 13G_1.2m_MDD. 4. Configure 13G_4+0_1.2_CA. FE: 1. Install new RTN910A. 2. Install XMC-5D_SB A 3. Install new antenna 13G_1.2m_MDD. 4. Configure 13G_4+0_1.2_CA. | [7 empty] | NR services | SQ202502050337-NR Services | NR services | SQ202504210220-NR Services // SQ202504210225-NR Services // SQ202504260199-NR Services | 2025-02-21 | 2025-02-17 | Completed | 2025-02-04 | 2025-02-04 | 2025-02-04 | 2025-02-04 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-05 | 2025-02-07 | 2025-02-05 | 2025-02-05 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-05 | 2025-02-07 | 2025-02-05 | 2025-02-05 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250220BX |  | 2025-02-21 | 2025-02-24 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-24 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-26 | 2025-04-19 | 2025-03-26 | 2025-03-28 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-03-26 | 2025-04-19 | 2025-03-26 | 2025-04-05 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-03-28 | 2025-03-26 | 2025-04-19 | 2025-03-26 | 2025-04-07 | RALPH O'BRYAN HILARY7167000030 | 2025-03-26 | 2025-04-19 | 2025-03-26 | 2025-03-28 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
7510A-7511A | Tomanggong (Celcom) | DU00004767239 | Sabah | Sabah | 5.388301 | 118.648010 |  |  |  | JUN 25 | TI WIP | Alignment WIP(RSL -50dBm) | Digi | 05. TI WIP |  | TSS+AA+TI |  | 8G_2+0_2.4/2.4_SB A,B 2xISM8 | MW Parallel Link | MW PARALLEL LINK 7510A-7511A WITH 8G_2+0_2.4/2.4m _SB A,B and config EPLA with existing 7G link. | MW PARALLEL LINK 7510A-7511A WITH 8G_2+0_2.4/2.4m _SB A,B NE: 1. Reuse existing RTN910A_RTN02. 2. Install new ISM8 at slot 3. 3. Install XMC-3_SB A,B. 4. Install new 8G_2.4m antenna. 5. Configure 8G_2+0_2.4m_256QAM_EPLA with existing 7G_2+0 link. | MW PARALLEL LINK 7510A-7511A WITH 8G_2+0_2.4/2.4m _SB A,B FE: 1. Reuse existing RTN910A_RTN03. 2. Install new ISM8 at slot 3. 3. Install XMC-3_SB A,B. 4. Install new 8G_2.4m antenna. 5. Configure 8G_2+0_2.4m_256QAM_EPLA with existing 7G_2+0 link. | XMC-3 | MS | 8G | 2.4 | 2.4 | NR services | SQ202504170485-NR Services | NR services | SQ202504080137-NR Services // SQ202504080147-NR Services | 2025-09-04 | 2025-09-04 | Completed | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021404 |  | 2025-02-15 | 2025-02-24 | Completed | 2025-02-14 | 2025-02-15 | 2025-02-14 | 2025-02-24 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-25 | 2025-03-25 | 2025-03-25 |  | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-03-19 | 2025-04-19 | 2025-03-19 |  | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | [7 empty] | 2025-03-19 | 2025-04-19 | 2025-03-19 |  | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-06-08: 2025-03-19; 2025-06-08: 2025-04-19; 2025-06-08: 2025-03-19; 2025-06-13: 2025-03-27 | [7 empty] | GTSB_AA | SQ202510300153-GTSB
3294B-1626B | Jln Sungai Batu | DU00003822916 | Central | Selangor | 3.088801 | 101.414610 |  |  |  |  | Cancel / Drop | No need proceed. Done under DU 3294B-2662B TX Mini | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 3294B-2662B TX Mini 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2593B-1166B | Saujana Putra LP | DU00003822917 | Central | Selangor | 2.939883 | 101.586910 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 29/10: Cutover done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | Remote Software Upgrade to 18G_2+0_128QAM_112M | MW Remote Upgrade | Remote Software Upgrade to 18G_2+0_128QAM_112M | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | CHEONG/SENG/WAH/7018000306
4759B-4457A | Kamunting Bus Station (Maxis) | DU00003822918 | Northern | Perak | 4.899510 | 100.718110 | [7 empty] | 00. Integrated/RFS Done | 10/07 : CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_4759B 23G_DP_0.6M(MAC)+OMT x1. ISM8 x1 XMC_3E , Sub A & B_Hi x2 FE_4457A. 23G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. | MW Swap | Existing link 23G_1+0_112M Swap existing link to 23G_2+0_112M Site impacted : 4759B , 4161R. NE_4759B 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4759B_RTN01. 3.Install new 4_ISM8-2+0 into existing 4759B_RTN01. 4.Install XMC_3E , Sub A & B_Hi. 5.Traffic migrate to new MW link 23G_2+0_112M. 6.Decom existing ODU and Ant. FE_4457A. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4457A_RTN03. 3.Install new 3_ISM8-2+0 into existing 4457A_RTN03. 4.Install new XMC_3E , Sub A & B_Lo. 5.Tarffic migrate to new MW link 23G_2+0_112M. 6.Decom existing ODU and Ant. | Existing link 23G_1+0_112M Swap existing link to 23G_2+0_112M Site impacted : 4759B , 4161R. NE_4759B 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4759B_RTN01. 3.Install new 4_ISM8-2+0 into existing 4759B_RTN01. 4.Install XMC_3E , Sub A & B_Hi. 5.Traffic migrate to new MW link 23G_2+0_112M. 6.Decom existing ODU and Ant. | Existing link 23G_1+0_112M Swap existing link to 23G_2+0_112M Site impacted : 4759B , 4161R. FE_4457A. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4457A_RTN03. 3.Install new 3_ISM8-2+0 into existing 4457A_RTN03. 4.Install new XMC_3E , Sub A & B_Lo. 5.Tarffic migrate to new MW link 23G_2+0_112M. 6.Decom existing ODU and Ant. | XMC_3E | MAC | 23G | 0.6 | 0.6 | CCSMY | SQ202504280454-CCS | CCSMY | SQ202507020646-CCS |  |  | Ongoing | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25061153 |  | 2025-06-12 | 2025-06-19 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-31 | 2025-07-01 |  | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | CCS TI | 2025-07-01 | 2025-07-31 | 2025-07-01 | 2025-07-11 | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | CCS TI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-10 | 2025-07-01 | 2025-07-31 | 2025-07-01 | 2025-07-28 | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | 2025-07-01 | 2025-07-31 | 2025-07-01 | 2025-07-01 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | CHEONG/SENG/WAH/7018000306
3208B-2722A | Petronas Kota Kemuning (REL) | DU00003822919 | Central | Selangor | 2.985850 | 101.542810 |  |  |  |  | Cancel / Drop | MSP still observe | ZTE | 00. Site Out/Drop | 28/2/2025 : Under observation |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4769B-4678A | Jln Tun Razak (maxis) | DU00003822920 | Northern | Kedah | 6.143663 | 100.380210 | W49-52 | DEC 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M. NE_4769B 18G_DP_0.6m(MDD) x1. ISM8 x1. XMC_5D-2+0 , Sub_A_Hi x1. FE_4678A. 18G_DP_1.2m(MDD) x1. ISM8 x1. XMC_5D-2+0, SUb A_Lo x1. | MW Swap | Existing link 18G_1+0_112M with SP ant size. Swap existing link to 18G_2+0_112M. Site Impacted:4769B,4086K/K00063. NE_4769B 1.Install new 18G_DP_0.6m(MDD). 2.Reuse existing 4769B_RTN01. 3.Install 4_ISM8-2+0 into existing 4769B_RTN01. 4.Install new XMC_5D-2+0 , Sub_A_Hi. 5.Enable EPLA and service cross connect. 6.Traffic migrate to new 18G_2+0_112M link. 7.Decom existing ODU and Ant. FE_4678A. 1.Install new 18G_DP_1.2m(MDD). 2.Reuse existing 4678A_RTN20. 3.Install new 3_ISM8-2+0 into existing 4678A_RTN20. 4.Install new XMC_5D-2+0, SUb A_Lo. 5.Enable EPLA and service cross connect. 6.Traffic migrate to new 18G_2+0_112M link. 7.Decom existing ODU and Ant. | [7 empty] | CCSMY | SQ202501140160-CCS | CCSMY | SQ202503050475-CCS // SQ202504260175-CCS | 2025-12-03 | 2025-12-03 | Completed | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-09 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022652 |  | 2025-02-27 | 2025-03-07 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-03-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-03 | 2025-03-29 | 2025-03-07 | 2025-03-07 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2025-03-03 | 2025-03-29 | 2025-03-07 | 2025-03-07 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-04 | 2025-03-03 | 2025-03-29 | 2025-03-19 | 2025-03-19 | MUHAMMAD//MUZAMMAL/7021000054 | 2025-03-03 | 2025-03-29 | 2025-03-03 | 2025-03-03 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
9367B-9122A | RPR Sg Plant | DU00003822921 | Sarawak | Sarawak | 3.271827 | 113.115610 | [7 empty] | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1377H_LOS | 99 Speedmart SUBANG U5 (2) | DU00005381347 | Central | Selangor | 3.178926 | 101.536118 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS RTN905 NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Link reroute to new FE 2362A due to LOS Block NLOS RTN510 Site Impacted : 1377H. NE_1377H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new FE route site. 6.Decom existing NLOS radio (1377H-NLOS-1226B). FE_2362A 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create Service cross connect. 5.GE port , ETH patching to Ibeam new port. 6.Create new In Band DCN 7.Traffic migrate to new FE. 8.Decom existing NLOS Radio (1226B-NLOS-1377H). | Link reroute to new FE 2362A due to LOS Block NLOS RTN510 Site Impacted : 1377H. NE_1377H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new FE route site. 6.Decom existing NLOS radio (1377H-NLOS-1226B). | Link reroute to new FE 2362A due to LOS Block NLOS RTN510 Site Impacted : 1377H. FE_2362A 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create Service cross connect. 5.GE port , ETH patching to Ibeam new port. 6.Create new In Band DCN 7.Traffic migrate to new FE. 8.Decom existing NLOS Radio (1226B-NLOS-1377H). | [5 empty] | GTSB | SQ202505280173-GTSB | GTSB | SQ202505280180-GTSB // SQ202505280186-GTSB | 2025-07-11 | 2025-07-03 | Completed | 2025-06-19 | 2025-07-03 | 2025-06-19 | 2025-06-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-11 | 2025-06-25 | 2025-06-11 | 2025-06-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-03 | 2025-07-11 | 2025-07-03 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052735 |  | 2025-05-28 | 2025-05-31 | Completed | 2025-05-27 | 2025-05-28 | 2025-05-27 | 2025-05-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-03 | 2025-06-30 | 2025-06-03 | 2025-06-04 | PUWANESWARAN//A/L SUKUMARAN6000018484 | GTSB TI | 2025-06-03 | 2025-06-30 | 2025-06-03 | 2025-06-28 | PUWANESWARAN//A/L SUKUMARAN6000018484 | GTSB TI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-12 | 2025-06-03 | 2025-06-30 | 2025-06-03 | 2025-06-26 | PUWANESWARAN//A/L SUKUMARAN6000018484 | 2025-06-03 | 2025-06-30 | 2025-06-03 | 2025-06-12 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505070146-GCI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-06-10 | CHEONG/SENG/WAH/7018000306
2551A_LOS | Chin Hock Auto | DU00005381348 | Central | Kuala Lumpur | 3.195910 | 101.679340 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_2551A 18G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. FE_2869A 18G+DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. | MW New Link / Reroute | Link reroute to new FE 2869A due to existing LOS Block. Link reroute to new FE with 18G_2+0_112M configuration. Site Impacted : 2551A NE_2551A 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new FE route and new link. 6.Decom existing MW link (2551A - 1273A). FE_2869A 1.Install new 18G+DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8_2+0. 3Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.ENable GE 1 , ETH cable patching to existing 2869A_RTN01 (GE2). 6.Migrate traffic to new link and New FE routing. 7.Decom existing MW link (1273A - 2551A). | Link reroute to new FE 2869A due to existing LOS Block. Link reroute to new FE with 18G_2+0_112M configuration. Site Impacted : 2551A NE_2551A 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new FE route and new link. 6.Decom existing MW link (2551A - 1273A). | Link reroute to new FE 2869A due to existing LOS Block. Link reroute to new FE with 18G_2+0_112M configuration. Site Impacted : 2551A FE_2869A 1.Install new 18G+DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8_2+0. 3Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.ENable GE 1 , ETH cable patching to existing 2869A_RTN01 (GE2). 6.Migrate traffic to new link and New FE routing. 7.Decom existing MW link (1273A - 2551A). | XMC_3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202504240784-GCI | GCI | SQ202505190285-GCI //SQ202505190292-GCI | 2025-07-02 | 2025-07-01 | Completed | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-27 | 2025-05-28 | 2025-05-27 | 2025-05-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051474 |  | 2025-05-15 | 2025-05-16 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-19 | 2025-05-26 | 2025-05-18 | 2025-05-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-05-19 | 2025-05-26 | 2025-05-18 | 2025-05-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-19 | 2025-05-26 | 2025-05-18 | 2025-05-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-05-19 | 2025-05-26 | 2025-05-18 | 2025-05-19 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505070146-GCI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | CHEONG/SENG/WAH/7018000306
1725C_LOS | Gamudaland Quayside Mall IB | DU00005381349 | Central | Selangor | 2.956799 | 101.552414 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G+1+0_56M NE RTN910 x1 XMC_3E , SubB_Lo 18G_SP_0.6M(MAC) x1 FE RTN910 x1 XMC_3E , Sub_Hi 18G_SP_0.6M(MAC) x1. | MW New Link / Reroute | Link reroute to new FE 1228A due to LOS Block. Link reroute to new FE 1228A with 18G_1+0_56M config. Site Impacted : 1725C , 1472B NE_1725C 1.New 18G_SP_0.6M(MAC). 2.Install New RTN910A , 7_ISM8-1+0. 3.New XMC_3E , Sub B_Lo. 4.Create service cross connect. 5.Migrate traffic to new FE route. 6.Decom existing MW. FE_1228A. 1.New existing 18G_DP_0.6M(MAC). 2.Install New RTN910A , 7_ISM8-1+0. 3.New existing XMC_3E , Sub B_Hi. 4.Create service cross connect. 5.Create In Band DCN. 6.Traffic migrate to new FE route. 7.Reuse existing MW link (1472B - 1725C). Please note that , existing 1472B_BBU require direct patching to DDF Fiber port. Ensure 1472B traffics are completely migrated before decom existing MW link. 8. Decom existing MW. | Link reroute to new FE 1228A due to LOS Block. Link reroute to new FE 1228A with 18G_1+0_56M config. Site Impacted : 1725C , 1472B. NE_1725C 1.New 18G_SP_0.6M(MAC). 2. Install new RTN910A , 7_ISM8-1+0. 3.New XMC_3E , Sub B_Lo. 4.Create service cross connect. 5.Migrate traffic to new FE route. | Link reroute to new FE 1228A due to LOS Block. Link reroute to new FE 1228A with 18G_1+0_56M config. Site Impacted : 1725C , 1472B FE_1228A. 1.Install new 18G_DP_0.6M(HAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect. 5.Create In Band DCN. 6.Traffic migrate to new FE route. 7.Existing 1472B_BBU require direct patching to DDF Fiber port. Ensure 1472B traffics are completely migrated before decom existing MW link. | XMC_3E | MAC | 18G | 0.6 | 0.6 | GTSB | SQ202504240787-GTSB | Magicell | SQ202505150537-Magicell // SQ202507300765-Magicell // SQ202507300766-Magicell | 2025-11-12 | 2025-11-13 | Completed | 2025-04-24 | 2025-05-02 | 2025-05-02 | 2025-05-02 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-06 | 2025-05-20 | 2025-05-06 | 2025-05-06 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2025-07-18 | 2025-07-18 | Completed | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-07 | 2025-05-31 | 2025-05-07 | 2025-07-18 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-05-07 | 2025-05-31 | 2025-05-07 | 2025-07-18 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-07 | 2025-05-31 | 2025-05-07 | 2025-07-16 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-06-08: 2025-05-07; 2025-06-08: 2025-05-31; 2025-06-08: 2025-05-07; 2025-06-13: 2025-05-08 |  |  | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505070146-GCI | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | CHEONG/SENG/WAH/7018000306
3495B_LOS | Jalan Gembira (REL) | DU00005381350 | Central | Kuala Lumpur | 3.082289 | 101.678867 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M config. NE_3495B. 23G_DP_0.6M(MAC). RTN910A . 7_ISM8-2+0. XMC_3E , Sub A & B_Hi x2. FE_W01367 23G_DP_0.6M(MAC) x1. RTN910A x1 XMC_3E , Sub A & B_Lo x2. | MW New Link / Reroute | Link reroute to new FE W01367 due to LOS Block Link reroute new FE W01367 with 23G_2+0_112M config. Site Impacted : 3495B NE_3495B. 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A . 7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Decom existing IDU , ODU and ANT(3495B-1255A). FE_W01367 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Enable GE1 , ETH patching to existing SM lDU and create In Band DCN. 7.Decom existing ODU , ANT and 3_ISV3 (1255A - 3495A). | Link reroute to new FE W01367 due to LOS Block Link reroute new FE W01367 with 23G_2+0_112M config. Site Impacted : 3495B NE_3495B. 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A . 7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Decom existing IDU , ODU and ANT(3495B-1255A). | Link reroute to new FE W01367 due to LOS Block Link reroute new FE W01367 with 23G_2+0_112M config. Site Impacted : 3495B FE_W01367 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Enable GE1 , ETH patching to existing SM lDU and create In Band DCN. 7.Decom existing ODU , ANT and 3_ISV3 (1255A - 3495A). | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202504240787-GTSB | GTSB | SQ202505050130-GTSB // SQ202505050134-GTSB | 2025-11-12 | 2025-11-13 | Completed | 2025-04-24 | 2025-05-02 | 2025-05-02 | 2025-05-02 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-23 | 2025-06-06 | 2025-05-23 | 2025-05-26 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050539 |  | 2025-05-06 | 2025-05-08 | Completed | 2025-05-05 | 2025-05-06 | 2025-05-05 | 2025-05-08 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-12 | 2025-05-31 | 2025-05-12 | 2025-06-08 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-05-12 | 2025-05-31 | 2025-05-12 | 2025-06-08 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-12 | 2025-05-31 | 2025-05-12 | 2025-06-08 | Aminuddin bin che azibA0563734967123169280 | 2025-05-12 | 2025-05-31 | 2025-05-12 | 2025-05-14 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505070146-GCI | 2025-05-04 | 2025-05-04 | 2025-05-04 | 2025-05-04 | CHEONG/SENG/WAH/7018000306
3119B-1299B | Jalan Kamunting (HSR) | DU00004181006 | Central | Kuala Lumpur | 3.157447 | 101.701084 |  |  |  |  | Cancel / Drop | Done under DU 3119B TX NIC | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 3119B TX NIC |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3714A-1299B | Hospital KL Macro | DU00004181007 | Central | Kuala Lumpur | 3.170684 | 101.699173 |  |  |  |  | Cancel / Drop | Done under DU 3714A_PostMOCN TX NIC | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 3714A_PostMOCN TX NIC |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
K00332_EB | TNB FLEET MANAGEMENT LANGKAWI | DU00004473069 | Northern | Kedah | 6.341303 | 99.723906 | [7 empty] | 06. Other Issue |  | TSS+TI |  |  | MW IDU Relocation | At NE: - Relocate xC SM ALC+2E MW link NT05218 to EB Cabinet. | [7 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4591C-4045C | Masjid Jamek Al-Istiglal | DU00004473070 | Northern | Perak | 4.884700 | 100.715101 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_4591C 23G_DP_0.6m(MAC)+OMT x1. XMC-3E-2+0 . Sub A & B_Lo x2. RTN910A x1. FE_4045C 23G_DP_0.6m(MAC)+OMT x1. XMC-3E-2+0 , Sub A & B_Hi x2. RTN910A x1 | MW Swap | Existing SM link 23G_1+0_112M. Swap existing link to 23G_2+0_112M. Site Impacted : 4591C,4373H,4467C,4045C. NE_4591C 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new XMC-3E-2+0 . Sub A & B_Lo. 3.Install new RTN910A,7_ISM8-2+0. 4.Enable EPLA and service cross connect. 5.Enable GE1, patching interconnect to RTN510. 6.Migrate traffic to new link. 7.Decom existing SM link.(Pls ensure all traffic full migrated and stable before decom existing link). FE_4045C 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new XMC-3E-2+0 , Sub A & B_Hi. 3.Install new RTN910A,7_ISM8-2+0. 4.Enable EPLA and service cross connect. 5.Enable GE1 , patching to existing 4045C_RTN01 (GE3). 6.Create In-band DCN. 7.Traffic migrate to new link. 8.Decom existing SM link.(Pls ensure all traffic full migrated and stable before decom existing link). | Existing SM link 23G_1+0_112M. Swap existing link to 23G_2+0_112M. Site Impacted : 4591C,4373H,4467C,4045C. NE_4591C 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new XMC-3E-2+0 . Sub A & B_Lo. 3.Install new RTN910A,7_ISM8-2+0. 4.Enable EPLA and service cross connect. 5.Enable GE1, patching interconnect to RTN510. 6.Migrate traffic to new link. 7.Decom existing SM link.(Pls ensure all traffic full migrated and stable before decom existing link). | Existing SM link 23G_1+0_112M. Swap existing link to 23G_2+0_112M. Site Impacted : 4591C,4373H,4467C,4045C. FE_4045C 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new XMC-3E-2+0 , Sub A & B_Hi. 3.Install new RTN910A,7_ISM8-2+0. 4.Enable EPLA and service cross connect. 5.Enable GE1 , patching to existing 4045C_RTN01 (GE3). 6.Create In-band DCN. 7.Traffic migrate to new link. 8.Decom existing SM link.(Pls ensure all traffic full migrated and stable before decom existing link). | XMC_3E | DP | 21280-TX NE 23072-TX FE | 0.6M | 0.6M | CCSMY | SQ202502180251-CCS | CCSMY | SQ202502270734-CCS // SQ202504260175-CCS |  |  | Ongoing | 2025-02-10 | 2025-02-15 | 2025-02-12 | 2025-02-12 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  |  | 2025-02-15 | 2025-02-15 | Completed | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-15 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-02-15 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-02-28 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-05-04 | MUHAMMAD//MUZAMMAL/7021000054 | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-05-06 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | NG HONG JIE7018000036 | Logistic Team | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
2443A-2675B | Ijok (CELCOM) | DU00004473071 | Central | Selangor | 3.296836 | 101.447680 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 21/1/2025 : Cutover done 20/1/2025 : Installation complete, pending alignment 13/1/2025 : EDOTCO(M)-CSU - Tower - NE site 2443A Ijok (CELCOM), Digi OB - 3M Bipod - RT - FE site 2675B BdrTasik Puteri 1 (celcom) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M. NE_2675B 18G_DP_0.6m(MDD) x1. XMC_5D-2+0 , Sub_A_Lo x1 ISM8 into existing 2675B_RTN01. FE_2443A 18G_DP_1.2m(MDD) x1 XMC_5D-2+0 , Sub_A_Hi x1. | MW Swap | Existing SM link 18G_2+0_56M. Swap existing link to 18G_2+0_112M. Site Impacted: 1584C,3685C,2675B. NE_2675B 1.Install new 18G_DP_0.6m(MDD). 2.Install new XMC_5D-2+0 , Sub_A_Lo. 3.Reuse existing 2675B_RTN01. 4.Install 4_ISM8 into existing 2675B_RTN01. 5.Create EPLA and service cross connect. 6.Traffic migrate to new link. 7.Decom existing SM link. FE_2443A 1.Install new 18G_DP_1.2m(MDD). 2.Install new XMC_5D-2+0 , Sub_A_Hi. 3.Reuse existing 2443A_RTN05,7_ISM8-2+0. 4.Create EPLA and service cross connect. 5.Traffic migrates to new link. 6.Decom existing SM link. | [7 empty] | GCI | SQ202503270731-GCI | GCI | SQ202501210455-GCI // SQ202504150088-GCI | 2025-04-08 | 2025-04-07 | Completed | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-27 | 2025-03-28 | 2025-03-27 | 2025-03-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-07 | 2025-04-08 | 2025-04-07 | 2025-04-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010848 |  | 2025-01-09 | 2025-01-08 | Completed | 2025-01-08 | 2025-01-09 | 2025-01-08 | 2025-01-08 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-20 | 2025-01-27 | 2025-01-20 | 2025-02-05 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-01-20 | 2025-01-27 | 2025-01-20 | 2025-02-05 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-21 | 2025-01-20 | 2025-01-27 | 2025-01-20 | 2025-01-21 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-01-20 | 2025-01-27 | 2025-01-20 | 2025-01-20 | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
3366B-1122A | Giant Hypermarket Banting Outdoor | DU00004473073 | Central | Selangor | 2.832086 | 101.529461 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 28/2/2025 : Cutover done 27/2/2025 : Installation WIP, stuck due to waiting raining stop 26/2/2025 : NE installation complete, FE installation WIP 10/2/2025 : EDOTCO (M) - 45M 3 Legged Tower - NE site 3366B Giant Hypermarket Banting Outdoor, Digi OB - 76M Tower - FE site 1122A Jenjarum | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_3366B 18G_DP_0.6m(MAC). XMC_3E-2+0 , Sub A_Lo. ISM8 x1. FE_1122A 18G_DP_1.2m(MAC) x1. XMC_3E-2+0 , Sub A_Hi x1. ISM8 x1 | MW Swap | Existing link 18G_1+0_112M. Swap existing link to 18G_2+0_112M Site Impacted : 1054K,3366B. NE_3366B 1.Install new 18G_DP_0.6m(MAC). 2.Install new XMC_3E-2+0 , Sub A_Lo. 3.Reuse exiting 3366B_RTN02. 4.Install new 4_ISM8-2+0 into existing 3366B_RTN02. 5.Enable EPLA and service cross connect. 6.Traffic migrate to new link 18G_2+0_112M. 7.Decom existing Ant and ODU. FE_1122A 1.Install new 18G_DP_1.2m(MAC). 2.Install XMC_3E-2+0 , Sub A_Hi. 3.Reuse existing 1122A_RTN07. 4.Insatll new 3_ISM8-2+0 into existing 1122A_RTN07. 5.Enable EPLA and service cross connect. 6.Traffic migrate to new link. 7.Decom existing Ant and ODU. | [7 empty] | GCI | SQ202503060118-GCI | GCI | SQ202503050449-GCI // SQ202504150088-GCI |  |  | Ongoing | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-12 | 2025-03-13 | 2025-03-12 | 2025-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25022021 |  | 2025-02-21 | 2025-02-21 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-26 | 2025-03-04 | 2025-02-25 | 2025-02-26 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-26 | 2025-03-04 | 2025-02-25 | 2025-03-03 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-28 | 2025-02-26 | 2025-03-04 | 2025-02-25 | 2025-03-03 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-02-26 | 2025-03-04 | 2025-02-25 | 2025-02-26 | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358
A00878_EB | TNB PANTAI REMIS | DU00004473075 | Northern | Perak | 4.452265 | 100.628117 | [7 empty] | 06. Other Issue |  | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | . Reroute & build new MW link A00878-4485A with Huawei 23G_28MHz_1+0_0.3M_0.2KM . Dismantle Old Microwave link A00878-A00250 POI Needed : Yes | [7 empty] | MTK | SQ202412090526-MTK | MTK |  | 2025-12-04 | 2025-11-27 | Completed | 2024-12-03 | 2024-12-31 | 2024-12-03 | 2024-12-30 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-14 | 2025-08-21 | 2025-08-14 | 2025-08-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-14 | 2025-08-21 | 2025-08-14 | 2025-08-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-11-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300144-GTSB
Q01168_EB | Q140B_Q01168OD_T3_JLNULUPASAI | DU00004476895 | Sarawak | Sarawak | 2.407530 | 112.030050 | [7 empty] | 05. Doable |  | TSS+TI |  |  | MW IDU Relocation | "At FE: - Relocate xC HW_RTN910A 201 MW link SW03581 to xD Cabinet. - Patching xC HW_RTN910A link SW03581 to xC MW Link IDU SW01523 POI Needed : Yes" | [7 empty] | MTK | SQ202412090540-MTK | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2024-11-29 | 2024-11-26 | Completed | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-29 | 2024-11-26 | 2024-11-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-29 | 2024-11-26 | 2024-11-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-29 | 2024-11-26 | 2024-11-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032802 |  | 2025-03-29 | 2025-04-05 | Completed | 2025-03-28 | 2025-03-29 | 2025-03-28 | 2025-04-05 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed
9257Z_SL | T3E_0853 BUDUK BUI | DU00005191001 | Sarawak | Sarawak | 4.020454 | 115.621606 | [6 empty] | ZTE | 03. Pending TSS |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01030_SL | BAU-VQ_MURUMPWRH_E_Q01030 | DU00005191002 | Sarawak | Sarawak | 2.667200 | 114.296800 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9259Z_SL | T3E_0855 (S1) KG PADANG PASIR BARIO | DU00005191003 | Sarawak | Sarawak | 3.736700 | 115.461800 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [9 empty] | Trintel |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9250Z_SL | T3E_0846 BA MUBOI | DU00005191004 | Sarawak | Sarawak | 3.178330 | 115.044940 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7092Z_SL | T3E_0232_ Pinangan Estet | DU00005191005 | Sabah | Sabah | 5.117140 | 116.797140 |  |  |  |  | On Hold |  |  | 07. Solution Changed |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9253Z_SL | T3E_0849 LONG RAYAH | DU00005191006 | Sarawak | Sarawak | 4.145442 | 115.216390 | [6 empty] | ZTE | 03. Pending TSS |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9249Z_SL | T3E_0845 LONG LUTENG | DU00005191007 | Sarawak | Sarawak | 3.534120 | 114.753254 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01247_SL | BAU-VQ_LDGKAMINSKY_E_Q01247 | DU00005191008 | Sarawak | Sarawak | 3.408500 | 113.756200 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3499A2_SL | pBTS Shin Yang | DU00005191009 | Sarawak | Sarawak | 2.421260 | 114.529960 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S01003_SL | BAU-VR_T3PAGALUNGAN_E_S01003 | DU00005191010 | Sabah | Sabah | 4.498800 | 116.424900 |  |  |  |  | On Hold |  |  | 07. Solution Changed |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01428_SL | T3-MN_NANGAMUJUNG_E_Q01428 | DU00005191011 | Sarawak | Sarawak | 2.030190 | 113.177890 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3950B4_SL | pBTS Menawan Wood | DU00005191012 | Sarawak | Sarawak | 2.693750 | 114.680860 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01554_SL | T3-MN_NANGATEKALIT_E_Q01449 (Q01554) | DU00005191013 | Sarawak | Sarawak | 1.905020 | 112.637800 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01147_SL | BAU-VQ_T3_SEBANGKAT_E_Q01147 | DU00005191014 | Sarawak | Sarawak | 1.949674 | 112.225760 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9260Z_SL | T3E_0855 PA LUNGAN | DU00005191015 | Sarawak | Sarawak | 3.806090 | 115.523480 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [9 empty] | Trintel |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q00904_SL | BAU-VQ_LDGBS_E_Q00904 | DU00005191016 | Sarawak | Sarawak | 2.660870 | 112.782940 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9261Z_SL | T3E_0855 (S2) PA UMOR | DU00005191017 | Sarawak | Sarawak | 3.736760 | 115.507680 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [9 empty] | Trintel |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01716_SL | BAU-VQ_KG SADIR PEDAWAN | DU00005191018 | Sarawak | Sarawak | 1.112040 | 110.277330 | [7 empty] | 03. TSS Only |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [7 empty] | Trintel | SQ202505260290-Trintel |  |  |  |  | Ongoing | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01149_SL | BAU-VQ_T3_MANGUT_E_Q01149 | DU00005191019 | Sarawak | Sarawak | 1.953851 | 112.045084 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S00522_SL | BAU-VR_MALIAUBASIN_E_S00522 | DU00005191020 | Sabah | Sabah | 4.736550 | 116.976556 |  |  |  |  | On Hold |  |  | 07. Solution Changed |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01430_SL | T3-MN_SMKBALEH_E_Q01430 | DU00005191021 | Sarawak | Sarawak | 1.883480 | 113.449290 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S00581_SL | BAU-VR_SERUDONGEST_E_S00581 | DU00005191022 | Sabah | Sabah | 4.355964 | 117.345264 |  |  |  |  | On Hold |  |  | 07. Solution Changed |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01555_SL | T3-MN_SMKKATIBAS_E_Q01450 (Q01555) | DU00005191023 | Sarawak | Sarawak | 1.900670 | 112.560130 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q00758_SL | BAU-VQ_LDGSEGARMAS_E_Q00758 | DU00005191024 | Sarawak | Sarawak | 3.469400 | 113.803600 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7096Z_SL | T3E_0236_ Kg Inarad | DU00005191025 | Sabah | Sabah | 5.017160 | 116.865880 |  |  |  |  | On Hold |  |  | 07. Solution Changed |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S01004_SL | BAU-VR_T3_KGSALUNG_E_S01004 | DU00005191026 | Sabah | Sabah | 4.585720 | 116.451280 |  |  |  |  | On Hold |  |  | 07. Solution Changed |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01133_SL | BAU-VQ_T3_LONGPELUAN_E_Q01133 | DU00005191027 | Sarawak | Sarawak | 3.260600 | 115.415000 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S00397_SL | BAU-VR_PULLAYANG-2_E_S00397 | DU00005191028 | Sabah | Sabah | 7.372900 | 113.845500 |  |  |  |  | On Hold |  |  | 07. Solution Changed |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01674_SL | BAU-VQ_METANIK MILL_E_Q001674 | DU00005191029 | Sarawak | Sarawak | 2.784697 | 114.447043 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01365_SL | BAU-VQ_KGLONGBEDIAN_E_Q01365 | DU00005191030 | Sarawak | Sarawak | 3.794520 | 114.734291 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01552_SL | T3-MN_NANGASUT_E_Q01446 (Q01552) | DU00005191031 | Sarawak | Sarawak | 1.990580 | 113.306230 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9251Z_SL | T3E_0847 LONG LIAM | DU00005191032 | Sarawak | Sarawak | 3.327810 | 114.758410 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q00540_SL | BAU-VQ_MULU_E_Q00540 | DU00005191033 | Sarawak | Sarawak | 4.030201 | 114.799639 | [6 empty] | ZTE | 06. Other Issue |  | TSS+TI |  |  | New Starlink | VSAT conversion to Starlink | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4998C_HU | Jelapang Jaya | DU00005191035 | Northern | Perak | 4.639170 | 101.073930 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_28M NE_4998C 15G_DP_1.2M(MDD) x1. RTN910 x1. XMC_5D , Sub A_Hi x1. FE_4521A 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. | MW Swap | Existing SM link 13G_1+0_28M. Swap existing link to 15G_2+0_28M. Site Impacted : 4998C. NE_4998C 1.Install 15G_DP_1.2M(MDD). 2.Install RTN910 , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Migrate traffic to new link. 6.Decom existing SM link. FE_4521A 1.Install 15G_DP_1.2M(MDD). 2.Install RTN910A , 7_ISM8-2+0.9RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.Migrate traffic to new link. 7.Decom existing SM link. | Existing SM link 13G_1+0_28M Swap existing link to 15G_2+0_28M Site Impacted : 4998C. NE_4998C 1.Install 15G_DP_1.2M(MDD). 2.Install RTN910 , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Migrate traffic to new link. 6.Decom existing SM link. | Existing SM link 13G_1+0_28M. Swap existing link to 15G_2+0_28M. Site Impacted : 4998C. FE_4521A 1.Install 15G_DP_1.2M(MDD). 2.Install RTN910A , 7_ISM8-2+0.9RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.Migrate traffic to new link. 7.Decom existing SM link. | XMC_5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202505130133-Magicell | Magicell | SQ202504230253-Magicell // SQ202504230255-Magicell // SQ202504260184-Magicell // SQ202511030393-Magicell | 2025-08-15 | 2025-08-14 | Completed | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-14 | 2025-08-15 | 2025-08-14 | 2025-08-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041378 |  | 2025-04-14 | 2025-04-15 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-22 | 2026-04-09 | 2025-04-22 | 2025-04-23 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-04-22 | 2026-04-09 | 2025-04-22 | 2025-04-23 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-22 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-22 | 2025-04-22 | 2026-04-09 | 2025-04-22 | 2025-05-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-04-22 | 2026-04-09 | 2025-04-22 | 2025-04-24 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | CHEONG/SENG/WAH/7018000306
7733B_HU | Ladang Tas | DU00005191036 | Sabah | Sabah | 5.244283 | 118.276176 |  |  |  |  | Drop/Cancel | Duplicate DU |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Site reroute under 7733B_LOS DU00004807611 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2025-04-18 | 2025-04-30 | 2025-04-18 |  | WILFRED BALANG7167000026 | Quality Team | 2025-04-18 | 2025-04-30 | 2025-04-18 |  | WILFRED BALANG7167000026 | Quality Team | [7 empty] | 2025-04-18 | 2025-04-30 | 2025-04-18 |  | WILFRED BALANG7167000026 | 2025-06-08: 2025-04-18; 2025-06-08: 2025-04-30; 2025-06-08: 2025-04-18; 2025-06-13: 2025-04-19 | [7 empty] | GTSB | SQ202507190087-GTSB | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | AB.RAHMAN//BIN MAT NOOH/6237001519
4966A | Kulim Hi-Tech Tower | DU00003202291 | Northern | Kedah | 5.406363 | 100.571695 | WK05 | MAR 24 |  |  | Planning | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 21/6: Link Drop. SOW done by MSP |  |  |  | Cancel / Drop | 0% as of 04 Dec 2023 | [13 empty] | Not started | 2024-02-01 | 2024-02-01 | [6 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24020905 | Material done DR | 2024-02-10 | 2024-02-13 | Completed | 2024-02-09 | 2024-02-10 | 2024-02-09 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed | [7 empty] | 2024-02-28 | 2024-03-02
7064A | Pulutan | DU00003202297 | Sabah | Sabah | 5.375699 | 116.184565 |  |  |  |  | Drop/Cancel | Drop. Pass to MSP |  | 00. Site Out/Drop | Drop. Pass to MSP |  |  |  | Cancel / Drop | WK17: 7064A-MAC-001 Pulutan/GigabitEthernet0/2/21 Utilization reduced <70% | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7209A | Bubul Road Semporna (Maxis) | DU00003202300 | Sabah | Sabah | 4.477580 | 118.606350 |  |  |  |  | Drop/Cancel | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 14/8: Cutover done. Solution done with 10G SFP port 10/6: Link Drop. SOW done by MSP | TSS |  | 1x IDU 910A 2x Fiber 1G SFP SM 1550 40km Module 2x Fiber Patch Cord cable | IDU-IPRAN | 1) Insert new Fiber SFP module 1G SFP SM 1550 40k at new 1G port GE0/2/11. 2) Lay new suitable Fiber patch cord cable and patching to new 1G port GE0/2/11. NE (7209A) at new RTN 910AF(RTN03): 1) Install new RTN910AF(RTN03) and configure it. 2) Insert new Fiber SFP module 1G SFP SM 1550 40km(Nazril will confirm SFP Module type) at 8-EM6-3(Port 3). 3) Patching other end of new Fiber patch cord cable to 8-EM6-3(Port 3). 4) Shifting existing IF cable for MW Link 7209A<--3748C from RTN08 slot 3 to new RTN03 slot 7 port 1. | [7 empty] | NR services | SQ202408220955-NR Services | NR services | No PR required-Work at TSS only | 2025-10-25 | 2025-10-24 | Completed | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-15 | 2024-08-16 | 2024-08-15 | 2024-08-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-15 | 2024-08-16 | 2024-08-15 | 2024-08-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24081408 |  | 2024-08-15 | 2024-08-15 | Completed | 2024-08-14 | 2024-08-15 | 2024-08-14 | 2024-08-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-13 | 2024-08-31 |  |  | MARTO FERDANEND BIN MOTIAS7167000021 | NR Service TI | 2024-08-13 | 2024-08-31 | 2024-08-13 |  | MARTO FERDANEND BIN MOTIAS7167000021 | NR Service TI | [7 empty] | 2024-08-13 | 2024-08-31 | 2024-08-13 |  | MARTO FERDANEND BIN MOTIAS7167000021 | 2025-06-08: 2024-08-13; 2025-06-08: 2024-08-31; 2025-06-08: 2024-08-13
4678A | Jalan Langgar | DU00003202301 | Northern | Kedah | 6.149601 | 100.414287 |  |  |  |  | Planning | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  |  | Cancel / Drop | 4678A-MAC-001 Jalan Langgar Alor Setar/GigabitEthernet0/2/4 Utilization reduced <70% | [13 empty] | Ongoing | 2025-07-28 | 2025-07-28 | 2025-07-28 |  | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Assigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1087A | Rantau Panjang | DU00003202302 | Central | Selangor | 3.052220 | 101.399680 |  | FEB 25 |  | FEB 25 | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 11/6/2024 : Drop. Pass to MSP 10/2/2025 : Digi OB - 45M 4 Legged Tower - NE site 1087A Rantau Panjang |  |  |  | Cancel / Drop | [8 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7447A | Patikang | DU00003202307 | Sabah | Sabah | 5.344083 | 116.128778 |  |  |  |  | Drop/Cancel | Cancel/Drop | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  |  | Cancel / Drop | 7447A-MAC-001 Patikang/GigabitEthernet0/2/20: RAN site 7447A | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1646B_IPR | Kg Sg Pandan | DU00005920968 | Central | Selangor | 2.923939 | 101.311892 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) Impact site: 1646B | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) Impact site: 1646B | N/A | [5 empty] | GTSB | SQ202508110926-GTSB | GTSB | SQ202508110923-GTSB | 2025-11-19 | 2025-11-18 | Completed | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-10-28 | 2025-10-29 | 2025-10-28 | 2025-10-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081977 |  | 2025-08-20 | 2025-08-23 | Completed | 2025-08-19 | 2025-08-20 | 2025-08-19 | 2025-08-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-14 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-06-08: 2025-10-13; 2025-06-08: 2025-10-13; 2025-06-08: 2025-10-13; 2025-06-13: 2025-10-14 |  |  | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202508150527-GCI | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | EZRIN TASNIM BIN ABDUL GANI6798000128
4396A_IPR | Jalan Siakap RDD | DU00005920969 | Northern | Perak | 5.019917 | 100.504622 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) Impact site: 4396A | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) Impact site: 4396A | N/A | [5 empty] | GCI | SQ202508110937-GCI | GCI | SQ202508110934-GCI | 2025-11-19 | 2025-11-18 | Completed | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-18 | 2025-08-19 | 2025-08-18 | 2025-08-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081201 |  | 2025-08-16 | 2025-08-14 | Completed | 2025-08-15 | 2025-08-16 | 2025-08-13 | 2025-08-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-14 | 2025-08-28 | 2025-08-14 | 2025-08-21 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-08-14 | 2025-08-28 | 2025-08-14 | 2025-08-21 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-16 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-16 | 2025-08-14 | 2025-08-28 | 2025-08-14 | 2025-08-21 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-06-08: 2025-08-14; 2025-06-08: 2025-08-28; 2025-06-08: 2025-08-14; 2025-06-13: 2025-08-15 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
A00530_IPR | A044A_A00530OD_KGTGBIDARA | DU00005920970 | Northern | Perak | 4.210000 | 100.918300 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x Patch Cord(Pair) | MW IDU Patching | Split traffic at IDU Huawei RTN 4105R/A00530_KG TG BIDARA - 4194C_MATA TOK EMBIN GE5 to PTN 666232-KGTGBIDARA/GigabitEthernet0/0/2 Patch IDU Huawei RTN 4105R/A00530_KG TG BIDARA - 4194C_MATA TOK EMBIN GE6 to new PTN 666232-KGTGBIDARA port and transfer traffic from sites below: 1) 4367A_KG GAJAH(CELCOM) (ZTE BBU) | Split traffic at IDU Huawei RTN 4105R/A00530_KG TG BIDARA - 4194C_MATA TOK EMBIN GE5 to PTN 666232-KGTGBIDARA/GigabitEthernet0/0/2 Patch IDU Huawei RTN 4105R/A00530_KG TG BIDARA - 4194C_MATA TOK EMBIN GE6 to new PTN 666232-KGTGBIDARA port and transfer traffic from sites below: 1) 4367A_KG GAJAH(CELCOM) (ZTE BBU) | N/A | [5 empty] | GCI | SQ202508110937-GCI | GCI | SQ202508110934-GCI | 2025-11-19 | 2025-11-20 | Completed | 2025-08-26 | 2025-08-27 | 2025-08-26 | 2025-08-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081207 |  | 2025-08-16 | 2025-08-14 | Completed | 2025-08-15 | 2025-08-16 | 2025-08-13 | 2025-08-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-31 | 2025-08-18 | 2025-08-26 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-08-18 | 2025-08-31 | 2025-08-18 | 2025-08-26 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-08-18 | 2025-08-31 | 2025-08-18 | 2025-08-26 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-06-08: 2025-08-18; 2025-06-08: 2025-08-31; 2025-06-08: 2025-08-18; 2025-06-13: 2025-08-18 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
B02499_IPR | B058E_B02499OD_JLNSKLHKGJENJAROM | DU00005920971 | Central | Selangor | 2.884510 | 101.518034 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x Patch Cord(Pair) | MW IDU Patching | Split traffic at IDU Huawei RTN 1046K/B02499_JLNSKLHKGJENJAROM - 2728C-KG.JENJAROM 2 GE1 to PTN 70658-JLNSEKOLAHJJRM/GigabitEthernet0/0/4 Patch IDU Huawei RTN 1046K/B02499_JLNSKLHKGJENJAROM - 2728C-KG.JENJAROM 2 GE5 to new PTN 70658-JLNSEKOLAHJJRM port and transfer traffic from sites below: 1) 1133C PETRONAS SAUJANA PUTRA (ZTE BBU) | Split traffic at IDU Huawei RTN 1046K/B02499_JLNSKLHKGJENJAROM - 2728C-KG.JENJAROM 2 GE1 to PTN 70658-JLNSEKOLAHJJRM/GigabitEthernet0/0/4 Patch IDU Huawei RTN 1046K/B02499_JLNSKLHKGJENJAROM - 2728C-KG.JENJAROM 2 GE5 to new PTN 70658-JLNSEKOLAHJJRM port and transfer traffic from sites below: 1) 1133C PETRONAS SAUJANA PUTRA (ZTE BBU) | N/A | [5 empty] | GTSB | SQ202508110926-GTSB | GTSB | SQ202508110923-GTSB | 2025-10-09 | 2025-10-08 | Completed | 2025-09-23 | 2025-10-07 | 2025-09-23 | 2025-09-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-23 | 2025-10-07 | 2025-09-23 | 2025-09-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-08 | 2025-10-09 | 2025-10-08 | 2025-10-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081978 |  | 2025-08-20 | 2025-08-23 | Completed | 2025-08-19 | 2025-08-20 | 2025-08-19 | 2025-08-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-09 | 2025-09-30 | 2025-09-09 | 2025-09-10 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-09-09 | 2025-09-30 | 2025-09-09 | 2025-09-18 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-10 | 2025-09-09 | 2025-09-30 | 2025-09-09 | 2025-09-16 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2025-06-08: 2025-09-09; 2025-06-08: 2025-09-30; 2025-06-08: 2025-09-09; 2025-06-13: 2025-09-10 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202508150527-GCI | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | EZRIN TASNIM BIN ABDUL GANI6798000128
B00550_IPR | B063B_B00550OD_SALAKTINGGI | DU00005920972 | Central | Selangor | 2.809280 | 101.743520 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module x2 Fiber Patch Cord x1 Pairs | MW IDU Patching | Split traffic at IDU Huawei RTN 1621K/B00550_SALAK TINGGI 1 - 2043B_MAS CARGO GE1 to PTN 70278-SALAKTINGGI/GigabitEthernet0/0/17 Patch IDU Huawei RTN 1621K/B00550_SALAK TINGGI 1 - 2043B_MAS CARGO GE5 to new PTN 70278-SALAKTINGGI port and transfer traffic from sites below: 1) 2043B_MAS CARGO (ZTE BBU) | Split traffic at IDU Huawei RTN 1621K/B00550_SALAK TINGGI 1 - 2043B_MAS CARGO GE1 to PTN 70278-SALAKTINGGI/GigabitEthernet0/0/17 Patch IDU Huawei RTN 1621K/B00550_SALAK TINGGI 1 - 2043B_MAS CARGO GE5 to new PTN 70278-SALAKTINGGI port and transfer traffic from sites below: 1) 2043B_MAS CARGO (ZTE BBU) | [6 empty] | GTSB | SQ202508110926-GTSB | GTSB | SQ202508110923-GTSB | 2025-10-30 | 2025-10-29 | Completed | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-10-28 | 2025-10-29 | 2025-10-28 | 2025-10-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-30 | 2025-10-29 | 2025-10-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081982 |  | 2025-08-20 | 2025-08-23 | Completed | 2025-08-19 | 2025-08-20 | 2025-08-19 | 2025-08-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-29 | 2025-09-30 | 2025-09-29 | 2025-10-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-09-29 | 2025-09-30 | 2025-09-29 | 2025-10-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-30 | 2025-09-29 | 2025-09-30 | 2025-09-29 | 2025-10-11 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-06-08: 2025-09-29; 2025-06-08: 2025-09-30; 2025-06-08: 2025-09-29; 2025-06-13: 2025-09-30 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202508150527-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | CHEONG/SENG/WAH/7018000306
4063A_IPR | Komplek Tabung Haji | DU00005920973 | Northern | Penang | 5.300616 | 100.260407 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x Patch Cord(Pair) | MW IDU Patching | Perform LAG at CP site for IDU 4063A-KOMPLEKS TABUNG HAJI-RTN01 to 4063A-MAC-001 Kompleks Tabung Haji 1) Patch RTN01 GE2 to new CP port 2) Create LAG 3) Impact sites: 4992C,4026L | Perform LAG at CP site for IDU 4063A-KOMPLEKS TABUNG HAJI-RTN01 to 4063A-MAC-001 Kompleks Tabung Haji 1) Patch RTN01 GE2 to new CP port 2) Create LAG 3) Impact sites: 4992C,4026L | N/A | [5 empty] | GCI | SQ202508110937-GCI | GCI | SQ202508110934-GCI | 2025-11-19 | 2025-11-20 | Completed | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081208 |  | 2025-08-16 | 2025-08-14 | Completed | 2025-08-15 | 2025-08-16 | 2025-08-12 | 2025-08-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-26 | 2025-09-02 | 2025-08-26 | 2025-08-30 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-08-26 | 2025-09-02 | 2025-08-26 | 2025-08-30 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-27 | 2025-08-26 | 2025-09-02 | 2025-08-26 | 2025-08-30 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-06-08: 2025-08-26; 2025-06-08: 2025-09-02; 2025-06-08: 2025-08-26; 2025-06-13: 2025-08-26 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
1221A_IPR | Mentari Plaza | DU00005920974 | Central | Selangor | 3.074816 | 101.610602 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IDU Fiber 1221A-FIBER-1184A port upgrade to 10G NE (1221A): 10G SFP x1 Fiber Patch Cord x1 pairs. FE (1184A): 10G SFP x1 Fiber Patch cord x1 pairs | MW IDU Patching | IDU Fiber 1221A-FIBER-1184A port upgrade to 10G Impact sites: 1041E,1221A,1746H,2648A,3761B,1282H,1001T74 NE (1221A): 1) Install 10G SFP at 1221A MENTARI PLAZA RTN02 2) Upgrade IDU Fiber 1221A-FIBER-1184A to 10G 3) Remove existing 1G fiber from RTN01 FE (1184A): 1) Install 10G SFP at 1184A-MAC-001 (ops team to assign port) 2) Upgrade IDU Fiber 1221A-1184A to 10G | IDU Fiber 1221A-FIBER-1184A port upgrade to 10G Impact sites: 1041E,1221A,1746H,2648A,3761B,1282H,1001T74 NE (1221A): 1) Install 10G SFP at 1221A MENTARI PLAZA RTN02 2) Upgrade IDU Fiber 1221A-FIBER-1184A to 10G 3) Remove existing 1G fiber from RTN01 | IDU Fiber 1221A-FIBER-1184A port upgrade to 10G Impact sites: 1041E,1221A,1746H,2648A,3761B,1282H,1001T74 FE (1184A): 1) Install 10G SFP at 1184A-MAC-001 (ops team to assign port) 2) Upgrade IDU Fiber 1221A-1184A to 10G | [5 empty] | MTK | SQ202602250643-MTK | MTK | SQ202511110787-MTK | 2026-03-13 | 2026-03-12 | Completed | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081983 |  | 2025-08-20 | 2025-08-23 | Completed | 2025-08-19 | 2025-08-20 | 2025-08-19 | 2025-08-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-04 | 2026-02-14 | 2026-02-16 | 2026-02-16 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2026-02-04 | 2026-02-14 | 2026-02-13 | 2026-02-19 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-02-11 | 2026-02-04 | 2026-02-14 | 2026-02-19 | 2026-02-19 | RIDHUAN//BIN MANSOR/8225000011 | 2025-06-08: 2026-02-04; 2025-06-08: 2026-02-14; 2025-06-08: 2026-02-04; 2025-06-13: 2026-02-04 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150527-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | CHEONG/SENG/WAH/7018000306
4188A_IPR | Nibong Tebal 2 | DU00005920975 | Northern | Penang | 5.166596 | 100.497963 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x Patch Cord(Pair) | MW IDU Patching | Perform LAG at CP site for IDU 4188A-NIBONG TEBAL 2-RTN12 to 4188A-MAC-001 Nibong Tebal 2 1) Patch RTN12 GE2 to new CP port 2) Create LAG 3) Impact sites: 4014B,4372D,4399E remarks: child sites involving EB sites | Perform LAG at CP site for IDU 4188A-NIBONG TEBAL 2-RTN12 to 4188A-MAC-001 Nibong Tebal 2 1) Patch RTN12 GE2 to new CP port 2) Create LAG 3) Impact sites: 4014B,4372D,4399E remarks: child sites involving EB sites | N/A | [5 empty] | GCI | SQ202508200564-GCI | GCI | SQ202508200559-GCI | 2025-11-19 | 2025-11-20 | Completed | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081973 |  | 2025-08-20 | 2025-08-22 | Completed | 2025-08-19 | 2025-08-20 | 2025-08-19 | 2025-08-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-18 | 2025-09-25 | 2025-09-18 | 2025-09-18 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-09-18 | 2025-09-25 | 2025-09-18 | 2025-09-19 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-09-18 | 2025-09-25 | 2025-09-18 | 2025-09-20 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-06-08: 2025-09-18; 2025-06-08: 2025-09-25; 2025-06-08: 2025-09-18; 2025-06-13: 2025-09-18 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | EZRIN TASNIM BIN ABDUL GANI6798000128
2659A_LOS | Jayajusco Maluri | DU00004206243 | Central | Kuala Lumpur | 3.125867 | 101.728085 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 7/10: Cutover done. Post-CO T/S WIP Material released under TX NIC 2659A DOWMY24061309 2659A-1437A(LOS BLOCKING) - MW SWAP - GCI - TT INC000091441545 Proceed reroute under NIC. Proposed FE: W00416/ | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112MHz_512QAM_0.6M/0.6M_XMC3 SUB A_889MBPS | MW New Link / Reroute | MW NEW LINK 2659A-3290D WITH HUAWEI_23G_1+0_112MHz_512QAM_0.6M/0.6M_XMC3 SUB A_889MBPS_0.44KM NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 112MHZ SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DECOM EXISTING LINK 2659A-1437A FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 112MHZ SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT 6. DECOM EXISTING LINK 2659A-1437A | [7 empty] | GCI | SQ202410280469-GCI | GCI | SQ202410280563-GCI // SQ202509020092-GCI | 2024-10-24 | 2024-10-23 | Completed | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-21 | 2024-10-21 | 2024-10-21 | 2024-10-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-23 | 2024-10-24 | 2024-10-23 | 2024-10-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Disabled |  |  |  |  | 2024-12-21 | 2024-12-21 | Completed | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-04 | 2024-10-11 | 2024-10-04 | 2024-10-07 | SYEDMOHAMAD//FARISAIMAN/6800000274 | GCI TI | 2024-10-04 | 2024-10-11 | 2024-10-04 | 2024-10-14 | SYEDMOHAMAD//FARISAIMAN/6800000274 | GCI TI | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-17 | SHUJAAT//ALI/6800000124 |  |  | 2024-10-04 | 2024-10-11 | 2024-10-04 | 2024-10-14 | SYEDMOHAMAD//FARISAIMAN/6800000274 | 2024-10-04 | 2024-10-11 | 2024-10-04 | 2024-10-04 | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | NG HONG JIE7018000036 | Logistic Team | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
1900B_LOS | Sunway Semenyih (KJS) | DU00004206244 | Central | Selangor | 2.971258 | 101.844845 |  |  |  |  | Cancel / Drop | Done under DU 1900B TX NIC | ZTE | 00. Site Out/Drop | 25/9: Solution done under Tx NIC 1900B |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
W01176_LOS | MENARASKM | DU00004206245 | Central | Kuala Lumpur | 3.153748 | 101.666095 |  | FEB 25 |  | FEB 25 | Cancel / Drop | Reroute done under TX NIC DU W01176_Additional | ZTE | 00. Site Out/Drop | 19/2/2025 : Reroute done under TX NIC DU W01176_Additional 10/2/2025 : MAXIS COMMUNICATION BERHAD - INBUILDING - NE site W01176 MENARASKM, EDOTCO (M) SDN BHD - INBUILDING - FE site W00379 W066F_W00379OD_MENARAHPDSARAOD, Digi OB - 3M Bipod - RT - Patching site 3801A Menara HP 25/10: Proceed solution under NIC W01176_Additional// 20/9: Pending Tx Solution for HU |  |  | NE_W01176 1.Install 18G_SP_0.6m(MAC) x1. 2.Install RTN910A x1. 3.Install XMC_3-1+0 , Sub A_Lo x1. FE_W00379/3801A. 1.Install 18G_SP_0.6(MAC) x1. 2.Install RTN910A x1. 3.Install XMC_3-1+0, Sub A_Hi x1. | Cancel / Drop | Link reroute to new FE W00379 (site colo with 3801A). Link design using outbound materials. Swap existing link to 18G_1+0_112M. NE_W01176 1.Install 18G_SP_0.6m(MAC). 2.Install RTN910A, 7_ISM8-1+0 3.Install XMC_3-1+0 , Sub A_Lo. 4.Traffic reroute to new FE W00379/3801A. 5.Decom existing SM MW link. FE_W00379/3801A. 1.Install 18G_SP_0.6(MAC). 2.Install RTN910A,7_ISM8-1+0. 3.Install XMC_3-1+0, Sub A_Hi. 4.Enable GE port and patching to existing RTN03. 5.Decom existing SM MW link. | [7 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | Cancel DO | 2025-02-20 |  | Ongoing | 2025-02-19 | 2025-02-20 | 2025-02-19 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing
3300B_LOS | Jln 1_13a (REL) | DU00004206246 | Central | Kuala Lumpur | 3.088810 | 101.673870 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 24/10: Post-CO & L1 rectification 23/10: Cutover done. Post-CO T/S WIP 24/9: Materials from TX NIC 3300B GTSB | TSS+AA+TI | L1+ATP+PAC | Link reroute with config 23G_1+0_112Mhz NE_3300B 1. New RTN910AF x 1. 2. New XMC_3_1+0 , sub A_Hi x 1. 3. 23G_0.6m x 1 (Follow Material delivered on site). FE_W00026 1. New RTN910AF x 1. 2. New XMC_3_1+0 , sub A_Lo x 1. 3. 23G_0.6m x 1 (Follow Material delivered on site). | MW New Link / Reroute | Existing link 23G_1+0_56Mhz (3300B-2737A). Link reroute to new FE with 23G_1+0_112Mhz due to LOS block. MW Parallel due to MSP already reroute after Planning SOW complete No Decom NE_3300B 1. Install new RTN910AF , 7_ISM8-1+0 (RTN naming convention provide by MSP team). 2. Install new DP 23G_0.6m. 3. Install new XMC_3_1+0 , sub A_Hi. FE_W00026 1. Install new RTN910AF , 7_ISM8-1+0 (RTN naming convention provide by MSP team). 2. Install new DP 23G_0.6m. 3. Install new XMC_3_1+0 , sub A_Lo. 4. Enable GE port 1 connect to Cisco router. 5. Create new In-band DCN & service connect. | [7 empty] | GTSB | SQ202410280475-GTSB | GTSB | SQ202410280571-GTSB | 2024-10-31 | 2024-11-05 | Completed | 2024-10-24 | 2024-10-31 | 2024-10-24 | 2024-10-24 | laina@girobumi.com.mylaina@girobumi.com.my | GTSB TI |  | 1.00 | Assigned | Completed |  | 2024-10-24 | 2024-10-31 | 2024-10-24 | 2024-10-24 | laina@girobumi.com.mylaina@girobumi.com.my | GTSB TI |  | 1.00 | Assigned | Completed |  | 2024-10-24 | 2024-10-24 | 2024-10-24 | 2024-10-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-29 | 2024-10-30 | 2024-10-29 | 2024-11-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2024-12-29 | 2024-12-29 | Completed | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2024-12-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-08 | 2024-10-31 | 2024-12-29 | 2024-12-29 | DINIE SYAHMI BIN NORZAMRI6799000171 | GTSB TI | 2024-10-08 | 2024-10-31 | 2024-12-29 | 2024-12-29 | DINIE SYAHMI BIN NORZAMRI6799000171 | GTSB TI | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-10-23 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-10-08 | 2024-10-31 | 2024-12-12 | 2024-12-12 | DINIE SYAHMI BIN NORZAMRI6799000171 | 2025-06-08: 2024-10-08; 2025-06-08: 2024-10-31; 2025-06-08: 2024-10-08; 2025-06-13: 2024-10-08 |  |  | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
W01357_LOS | MRT_JLNMAAROF | DU00004206247 | Central | Kuala Lumpur | 3.141650 | 101.662290 |  |  |  |  | Cancel / Drop | Done under TX NIC W01357_PostMOCN | ZTE | 00. Site Out/Drop | 14/11: Solution done under TX NIC W01357_PostMOCN |  |  | New NLOS RTN510 Equipment NE_W01357 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_W00493. 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH Cable / LAN cable & Fiber Patch cord. | Cancel / Drop | Link reroute to new FE W00493 with New NLOS RTN510 equipment due to LOS block. NE_W01357 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. FE_W00493. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.Patch cord direct patching to existing Fiber. 6.Decom existing NLOS Radio | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300116-GTSB
2655B_LOS | Jalan Putra Prima Tengah | DU00004206248 | Central | Selangor | 2.968977 | 101.587810 |  |  |  |  | Cancel / Drop | Done under TX NIC 2655B_Additional | ZTE | 00. Site Out/Drop | 25/9: Solution done under TX NIC 2655B_Additional |  |  | Reroute to new FE 1309B with 18G_1+0_112Mhz due to LOS block. NE_2655B 1. Install new XMC_3E , sub B_Lo x 1. 2.Install 18G_SP_0.6m x1. 3.Install new RTN910AF x1. FE_1309B 1. Install new RTN910AF x 1. 2. Install new XMC_3E , sub B_Hi x1. 3.Install 18G_SP_0.6m | Cancel / Drop | Existing link 18G_1+0_56Mhz (2655B-2049B LOS Block) Reroute to new FE 1390B with 18G_1+0_112Mhz due to LOS block. NE_2655B 1. Install SP 18G_0.6m direct towards new FE 1309B. 2. Install new XMC_3E , sub B_Lo. 3. config 56Mhz to 112Mhz. 4. Install new RTN910AF , 7_ISM8-1+0 (RTN naming provide by MSP team). 5. Decom existing link. FE_1309B 1. Install new RTN910AF , 7_ISM8-1+0 (RTN naming convention provide by MSP team). 2. Install SP 18G_0.6m. 3. Install new XMC_3E , sub B_Hi. 4. Create new In-band DCN & service cross connect. 5. Enable GE port 1 connect to Ibeam / PFS. | [7 empty] | GCI | No PR required-Site drop/cancel |  |  |  |  | Disabled | 2024-10-08 | 2024-10-08 | 2024-10-08 |  | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Disabled |  | 2024-10-11 | 2024-10-11 | 2024-10-11 |  | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Disabled | [9 empty] | Unassigned | Disabled | [9 empty] | Unassigned | Disabled | [6 empty] | Not started | [8 empty] | Unassigned | Not started
2675B-2443A | BdrTasik Puteri 1 (celcom) | DU00004206249 | Central | Selangor | 3.284797 | 101.472842 |  | FEB 25 |  | FEB 25 | Cancel / Drop | Done under DU 2443A-2675B | ZTE | 00. Site Out/Drop | 21/2/2025 : Done under DU 2443A-2675B 10/2/2025 : Digi OB - 3M Bipod - RT - NE site 2675B BdrTasik Puteri 1 (celcom), EDOTCO(M)-CSU - Tower - FE site 2443A Ijok (CELCOM) |  |  | 18G_2+0_112M NE_2675B 18G_DP_0.6m(MDD) x1. XMC_5D-2+0 , Sub_A_Lo x1. ISM8 x1. FE_2443A 18G_DP_1.2m(MDD) x1. XMC_5D-2+0 , Sub_A_Hi x1. Reuse existing RTN910A ,7_ISM8-1+0 | Cancel / Drop | ALREADY DONE UNDER DU 2443A-2675B TX MINI | [7 empty] | MTK | No PR required-Site drop/cancel | MTK | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | Cancel DO | 2025-02-21 | 2025-10-27 | Completed | 2025-02-20 | 2025-02-21 | 2025-10-27 | 2025-10-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed
3741B_LOS | Taman Desa Business Park | DU00004206250 | Central | Kuala Lumpur | 3.097948 | 101.675780 |  |  |  |  | Cancel / Drop | Under MSP | ZTE | 00. Site Out/Drop | 22/11: Link done reroute under MSP 14/11: Cutover link TX NIC 3741B done 15/8/24 (MW Hardware Upgrade) - RSL low 20/9: Pending Tx Solution for HU |  |  | NA | Cancel / Drop | Link was reroute completed and it believe was done by MSP team (3741B-3298B). | [9 empty] | MSP completed |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01121-Q00865 | Q144A_Q01121OD_CB_KUALAANAU | DU00004207779 | Sarawak | Sarawak | 2.935210 | 112.827510 |  | FEB 25 |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 4/9/2025 : Cutover done, pending declare due to ipcore not yet configure 29/8/2025 : Patching done, pending feedback CD config ipcore 2/9: Pending Tx Solution for HU | TSS+TI | L1+ATP+PAC | SFP 1km and patch cord | MW IDU Patching | MW link SM SW03337 (Q00865-Q00254) congested To divert child site Q01121 to parallel link Huawei SW03784 (Q00865-Q00254) Tx route: Q01121-Q00865-Q00254 Impact sites: Q01121 NE (Q01121): 1) Remain existing FE (Q00865): 1) At IDU Huawei SW03532 Q00865 patch new port GE5 (optical) to IDU Huawei SW03784 GE6 (optical) 2) Divert Q01121 to new port/link remarks: at Q00254 traffic to route to GE5 going to PTN0/3/0/3) | [7 empty] | Trintel | SQ202508200611-Trintel | Trintel | SQ202508200609-Trintel | 2025-12-02 | 2025-11-26 | Completed | 2025-09-02 | 2025-11-06 | 2025-09-02 | 2025-11-06 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080798 |  | 2025-08-08 | 2025-08-27 | Completed | 2025-08-07 | 2025-08-08 | 2025-08-07 | 2025-08-27 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-11-06 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-09-20 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-19 | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-09-20 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2025-06-08: 2025-08-29; 2025-06-08: 2025-08-29; 2025-06-08: 2025-08-29; 2025-06-13: 2025-08-29 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202511040438-GTSB
4907B_LOS | Kg Palas | DU00004216486 | Northern | Perak | 4.589250 | 101.313910 | [7 empty] | 00. Site Out/Drop | 23/9: Disable DU for _LOS. Proceed with 4907B-4566A | TSS |  | BOQ follow TX Rollout 4907B | MW New Link / Reroute | Follow TX Rollout NIC Solution 4907B-4904B | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4540B-4535B | POS SLIM 13 RCC | DU00004216487 | Northern | Perak | 4.554803 | 101.168310 | [7 empty] | 00. Integrated/RFS Done | 23/9: To proceed with installation parallel link only after LOS 4907B-4540B confirmed (New Link/Reroute) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4540B 1. New antenna 18G_1.2m x 1.(MAC) 2. ODU_XMC_3E x 2 , Sub (A & B_Lo). 3. ISM8-1&2 x 1. 4.OMT coupler x1. 5.RTN910A x1. 4535B_CP Site 1.New antenna 18G_1.2m x1.(MAC) 2.ODU_XMC_3E x2 , Sub (A & B_Hi). 3.New RTN910AF x 1. 4.OMT Coupler x1. | MW New Link / Reroute | Created new DU link ID 4540B-4535B. Install new link 18G_112M_2+0. TSS survey is required. This link to serve for 4907B. Site Impacted:4542B,4905B,4904B,4907B. 4540B 1.Install new antenna 18G_1.2m + 2xODU_XMC_3E , Sub (A & B_Lo). 2.Install 3_ISM8-2+0 and configure EPLA direct towards 4535B. 3.Install new RTN910A. (RTN no provide by MSP team). 4.Install OMT Coupler. 5.Perform service cross connect and apply EPLA for slot_7 & Slot_3 on RTN910AF. 6.Decomm existing SM link (4540B-4535B) 4535B/A00316_CP Site 1.Install new antenna 18G_1.2m + 2xODU_XMC_3E , Sub (A & B_Hi). 2.Install new RTN910AF , 7_ISM8-2+0 and configure EPLA direct towards 4540B. 3.Install OMT Coupler. 4.Enable 10G_GE3 Optical port connect to Cisco_Fiber physical LAG for GE ports 1 & 2. 5.Create/configure as new In-band DCN (RTN convention name provide by integration team). 6.Decomm existing SM link (4535B-4540B). | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202412030134-GCI // SQ202504150095-GCI // SQ202504160579-GCI | 2025-11-28 | 2025-11-27 | Completed | 2025-04-03 | 2025-04-03 | 2025-04-03 | 2025-04-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-03 | 2025-04-03 | 2025-04-03 | 2025-04-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250320AW |  | 2025-03-21 | 2025-03-22 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-25 | 2025-03-31 | 2025-03-25 | 2025-04-09 | team41gcitechnicalteam41gcitechnical | GCI TI | 2025-03-25 | 2025-03-31 | 2025-03-25 | 2025-04-09 | team41gcitechnicalteam41gcitechnical | GCI TI | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-27 | 2025-03-25 | 2025-03-31 | 2025-03-25 | 2025-04-07 | team41gcitechnicalteam41gcitechnical | 2025-03-25 | 2025-03-31 | 2025-03-25 | 2025-03-28 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402
9364A | Ulu Sg Merah (SACOFA) | DU00004992703 | Sarawak | Sarawak | 2.329164 | 111.864771 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP and patch cord | MW IDU Patching | 9364A IDU to IDU 1G connection congested. To replace with 10G port Tx route: 9364A-LL-9368A Impact sites: 9364A,9280B NE (9364A): 1) Existing connection: RTN01 GE1 to RTN GE1 2) Change to: RTN01 GE4 to RTN GE4 (10G) | NE (9364A): 1) Existing connection: RTN01 GE1 to RTN GE1 2) Change to: RTN01 GE4 to RTN GE4 (10G) | [6 empty] | Allstar | SQ202506160462-Allstar | Allstar | SQ202506130280-Allstar | 2025-07-04 | 2025-07-02 | Completed | 2025-06-13 | 2025-06-20 | 2025-06-13 | 2025-06-13 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-04 | 2025-07-02 | 2025-07-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2025-06-11 | 2025-06-11 | Completed | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-13 | 2025-06-18 | 2025-06-13 | 2025-06-13 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-06-13 | 2025-06-18 | 2025-06-13 | 2025-06-13 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-13 | 2025-06-13 | 2025-06-18 | 2025-07-15 | 2025-07-15 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | 2025-06-08: 2025-06-13; 2025-06-08: 2025-06-18; 2025-06-08: 2025-06-13; 2025-06-13: 2025-06-13 |  |  | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507080651-GTSB | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | AB.RAHMAN//BIN MAT NOOH/6237001519
3557B-1202B | Surau Ar-Rahman Presint Inang | DU00003927185 | Central | Selangor | 3.080208 | 101.429410 |  | JUL 24 | WK32-WK35 | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 9/8: Cutover done 8/8: EB CRQ approved. MOS & Pre-Installation WIP 24/7: Material transfer from Tx NIC W00414 (MTK) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz 0.6m SP FE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz 0.6m SP | MW Swap | Existing link 3557B-1202B 2+0 (3557B RTN01-1202B RTN02) Swap existing 13G 2+0 with new 18G 112MHz Impact sites: 3557B NE (3557B) 1. Add ISM8 card RTN01 slot 3 2. Install new link at RTN01 3-ISM8-1 3. Cutover traffic to new link FE (1202B) 1. Add ISM8 card RTN01 slot 3 2. Install new link at RTN01 3-ISM8-1 3. Remove connection RTN01-RTN02 4. Cutover traffic to new link | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202408140523-MTK | 2024-09-27 | 2024-09-25 | Completed | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-13 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-09-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-09-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-25 | 2024-09-27 | 2024-09-25 | 2024-09-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Full site material DM from W00414 |  |  | Disabled | [8 empty] | Unassigned | Disabled |  | 2024-08-08 | 2024-08-31 | 2024-08-07 | 2024-08-16 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-08-08 | 2024-08-31 | 2024-08-07 | 2024-08-13 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-08-09 | SHUJAAT//ALI/6800000124 |  |  | 2024-08-08 | 2024-08-31 | 2024-08-07 | 2024-08-10 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-08-08 | 2024-08-31 | 2024-08-07 | 2024-08-27 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 | NG HONG JIE7018000036 | Logistic Team | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
2069B-1612B_1 | WT_UITMPNCKALAM | DU00003936699 | Central | Selangor | 3.204196 | 101.453258 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 24/7: EB CRQ approved. MOS & TI WIP 18/7: Reapply new EB CRQ (Non service impact) - pending approval | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1) 1x18G XMC3E Sub A Hi 2) 1x18G XMC3E Sub B Hi FE: 1) 1x18G XMC3E Sub A Lo 2) 1x18G XMC3E Sub B Lo | MW Hardware Upgrade | Existing link 2069B-1612B 4+0 56MHz (2069B RTN03-1612B RTN04) To convert link at slot 3 to 2+0 112MHz (Vertical 512QAM Horizontal 256QAM) Impact site: 3804A,2680B,1518C,3651A_6,1608B,1020L NE (2069B RTN03) 1. Swap ODU slot 23 and 43 to XMC3E 2. Upgrade link slot 3-ISM8 to 112MHZ FE (1612B RTN04) 1. Swap ODU slot 27 and 47 to XMC3E 2. Upgrade link slot 7-ISM8 | [7 empty] | GTSB | SQ202410100836-GTSB | GTSB | SQ202408080491-GTSB | 2024-12-06 | 2024-12-05 | Completed | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | KANNAN A/L RAMACHANDRAN6799000115 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-20 | 2024-11-21 | 2024-11-20 | 2024-11-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-20 | 2024-11-21 | 2024-11-20 | 2024-11-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-12-05 | 2024-12-06 | 2024-12-05 | 2024-12-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071051 |  | 2024-07-11 | 2024-07-12 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-12 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-16 | 2024-07-31 | 2024-07-16 | 2024-07-16 | MOHD//AMIR BIN SAMSI/6799000184 | GTSB TI | 2024-07-16 | 2024-07-31 | 2024-07-16 | 2024-09-30 | MOHD//AMIR BIN SAMSI/6799000184 | GTSB TI | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-08-30 | C.PRATHABAN///6798000081 |  |  | 2024-07-16 | 2024-07-31 | 2024-07-16 | 2024-10-26 | MOHD//AMIR BIN SAMSI/6799000184 | 2024-07-16 | 2024-07-31 | 2024-07-16 | 2024-07-24 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | NG HONG JIE7018000036 | Logistic Team | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358
1424A-1412A_1 | Maxis Tower Batu Arang | DU00003936700 | Central | Selangor | 3.315091 | 101.468470 | WK03 | JAN 25 | WK03 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 13/1/2025 : Cutover done 9/1/2025 : Cancel proceed due to waiting replacement ODU 8/1/2025 : Alignment cannot done due to inteferance, still troubleshoot 7/1/2025 : Installation complete, pending alignment due to raining day 6/1/2025 : FE installation complete, NE installation WIP 14/10: Pending Site DO | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M with CA. NE_1424A 13G_DP_1.2m antenna (MDD) x1. XMC_5D , Sub A_Hi x1. ISM8 x2. NE_1412A 13G_DP_1.2m antenna.(MDD) x1. XMC_5D , Sub_A_Lo x1. Install new RTN910A x1 ISM8 x2. | MW Parallel Link | 1424A-1412A Existing 13G_4+0_28Mhz Create Parallel link 13G_4+0_28Mhz for 1424A-1412A to carry child site 3682C. NE_1424A 1.Install new 13G_DP_1.2m antenna (MDD). 2.Install XMC_5D , Sub A_Hi. 3.Install 3_ISM8-2+0 and 4_ISM8-2+0 on existing 1424A_RTN910_RTN02. 5.Configure EPLA and service cross connect and CA. 6.Migrate 3682C traffic to new Parallel link. 7.Remove the cascade RTN02 to RTN03 Eth cable. NE_1412A 1.Install new 13G_DP_1.2m antenna.(MDD). 2.Install XMC_5D , Sub_A_Lo. 3.Install new RTN910A 5.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 6.Configure EPLA & service cross connect and CA. 7.Enable GE port 1 connect to PFS. 8.Create new Inband DCN for 1412A new parallel link. | [7 empty] | Magicell | SQ202501140157-Magicell | Magicell | SQ202412180538-Magicell // SQ202504260146-Magicell | 2025-10-01 | 2025-09-30 | Completed | 2025-01-06 | 2025-01-14 | 2025-01-14 | 2025-01-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-06-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-10-01 | 2025-09-30 | 2025-09-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24121808 | 13G_1.2/1.2_DP_4+0. wip 13G 1.2m MS⏸️ | 2024-12-19 | 2025-02-07 | Completed | 2024-12-18 | 2024-12-19 | 2024-12-18 | 2025-02-07 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-06 | 2025-01-31 | 2025-01-08 | 2025-02-07 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2025-01-06 | 2025-01-31 | 2025-01-08 | 2025-02-07 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-01-06 | 2025-01-31 | 2025-01-08 | 2025-01-17 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | 2025-06-08: 2025-01-06; 2025-06-08: 2025-01-31; 2025-06-08: 2025-01-08; 2025-06-13: 2025-01-08 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202507080517-GCI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
7649B-7628A_1 | Seafest Hotel | DU00003936701 | Sabah | Sabah | 4.478526 | 118.617520 |  |  |  |  | Drop/Cancel | DU cancel |  | 00. Site Out/Drop | 21/8: Solutions have been repealed. Planner to create new DU for new HU solutions | TSS |  | NE: 1) 1xISM8 card FE: 1) 1xISM8 card | MW Hardware Upgrade | Update 13 Jan 2025: To proceed up to survey only. Site has been rerouted by other vendor Existing link 1: 7649B-7628A 1+0 (7649B RTN03-7628A RTN02) Existing link 2: 7649B-7628A 2+0 (7649B RTN05-7628A RTN05 To combine all 3 links into single IDU 7628A RTN02 already have LAG created to CP port Eth-Trunk5 Impact sites: 7649B,7360A,7230C NE (7649B): 1) Transfer ISM8 from RTN05 slot 3 to RTN03 slot 4 2) Replace ISM6 at RTN03 slot 3 with new ISM8 3) Create EPLA 3+0 4) Patch RTN06 GE1 to RTN03 GE2 5) Migrate 7230C to 7628A Eth-Trunk5 6) RTN05 can be reused for re-deployment FE (7628A): 1) Transfer ISM8 from RTN05 slot 3 to RTN02 slot 4 2) Replace ISM6 at RTN02 slot 3 with new ISM8 3) Create EPLA 3+0 4) Migrate 7230C to 7628A Eth-Trunk5 5) RTN05 can be reused for re-deployment | [7 empty] | NR services | SQ202408300881-NR Services | NR services | No PR required-Work at TSS only | 2025-07-11 | 2025-07-07 | Completed | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-16 | 2024-08-23 | 2024-08-16 | 2024-08-16 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-16 | 2024-08-23 | 2024-08-16 | 2024-08-16 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | DR | 2024-08-14 | 2024-08-15 | Completed | 2024-08-13 | 2024-08-14 | 2024-08-13 | 2024-08-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-13 | 2024-08-31 | 2024-08-13 |  | MARTO FERDANEND BIN MOTIAS7167000021 | NR Service TI | 2024-08-13 | 2024-08-31 | 2024-08-13 |  | MARTO FERDANEND BIN MOTIAS7167000021 | NR Service TI | [7 empty] | 2024-08-13 | 2024-08-31 | 2024-08-13 |  | MARTO FERDANEND BIN MOTIAS7167000021 | 2025-06-08: 2024-08-13; 2025-06-08: 2024-08-31; 2025-06-08: 2024-08-13; 2025-06-13: 2024-08-16
3354A-4770A | pBTS SP Heights | DU00003936702 | Northern | Kedah | 5.630889 | 100.545160 | [7 empty] | 00. Integrated/RFS Done | 18/7: D1: Cutover done. Remote upgrade | AA | PAC |  | MW Remote Upgrade | MW Remote Upgrade Modulation 128QAM to 256QAM | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-07-17 | 2024-07-17 | 2024-07-18 | 2024-07-18 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
2049B-1372B | Taman Mas Sepang(Celcom) | DU00003936703 | Central | Selangor | 2.968462 | 101.581550 |  | SEP 24 | WK36-40 | SEP 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 24/9: NMS Rectification plan 27/9 (NSA EB CRQ) 19/9: Cutover done. Pending rectify NMS losscomm | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1) 1x18GHz XMC3E Sub A Hi 2) 1x18GHz XMC3E Sub B Hi FE: 1) 1x18GHz XMC3E Sub A Lo 2) 1x18GHz XMC3E Sub B Lo 3) 1xcat6 cable | MW Hardware Upgrade | Perform hardware upgrade for 2049B RTN02-1372B RTN04 1) Replace ODU with XMC3E for higher Tx power 2) Patch 2nd GE port from 1372B RTN04 to new GE port and create LAG Impact site: 2901A,1641H NE (2049B RTN02): 1) Replace existing ODU with XMC3E 2) Configure link as 2+0 112MHz FE (1372B RTN04): 1) Replace existing ODU with XMC3E 2) Configure link as 2+0 112MHz 3) Patch GE2 to new CP port and create LAG | [7 empty] | Allstar | SQ202409070066-Allstar | Allstar | SQ202410080228-Allstar // SQ202510070055-Allstar | 2024-10-02 | 2024-10-01 | Completed | 2024-09-02 | 2024-09-03 | 2024-09-03 | 2024-09-03 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-04 | 2024-09-05 | 2024-09-04 | 2024-09-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24083051 |  | 2024-08-31 | 2024-09-03 | Completed | 2024-08-30 | 2024-08-31 | 2024-08-30 | 2024-09-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-09 | 2024-09-30 | 2024-09-09 | 2024-10-17 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | Allstar TI | 2024-09-09 | 2024-09-30 | 2024-09-09 | 2024-11-19 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | Allstar TI | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-24 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-09-09 | 2024-09-30 | 2024-09-09 | 2024-10-11 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | 2024-09-09 | 2024-09-30 | 2024-09-09 | 2024-09-10 | 2024-12-23 | 2024-12-23 | 2024-12-23 | 2024-12-23 | NG HONG JIE7018000036 | Logistic Team | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358
1431B-1367A_1 | Sek 13 Shah Alam Club | DU00003936704 | Central | Selangor | 3.074506 | 101.535310 |  |  | WK32-WK35 | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 7/8: D2: Cutover done 6/8: MOS & Pre-Installation WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 2+0 112MHz 0.6m/0.6m DP NE: 1) 1xISM8 card 2) 1x23GHz XMC3 Sub A Lo 3) 1x23GHz XMC3 Sub B Lo 4) 1x23GHz 0.6m DP FE: 1) 1xISM8 card 2) 1x23GHz XMC3 Sub A Hi 3) 1x23GHz XMC3 Sub B Hi 4) 1x23GHz 0.6m DP | MW Swap | Existing link SM 1431B-1367A MW1 Swap existing 23G 1+0 with new 23G 2+0 Impact sites: 1075C,3364C,1758H NE (1431B) 1. Add ISM8 card RTN01 slot 3 2. Install new link at RTN01 3-ISM8 (to reuse SM channel for Vertical) 3. Remove connection RTN01 to SM IDU. Cutover traffic to new link FE (1367A) 1. Add ISM8 card RTN11 slot 3 2. Install new link at RTN11 3-ISM8. RTN11 already using 10G connection to CP 3. Remove connection RTN11 to SM IDU. Cutover traffic to new link | [7 empty] | Allstar | SQ202408220872-Allstar | Allstar | SQ202408140500-Allstar // SQ202510070055-Allstar | 2024-07-31 | 2024-07-30 | Completed | 2024-07-18 | 2024-07-18 | 2024-07-17 | 2024-07-18 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-07-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240730A9 |  | 2024-07-31 | 2024-08-05 | Completed | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-08-05 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-06 | 2024-08-31 | 2024-08-06 | 2024-09-12 | ALI//HAMZA/6798000192 | Allstar TI | 2024-08-06 | 2024-08-31 | 2024-08-06 | 2024-11-19 | ALI//HAMZA/6798000192 | Allstar TI | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-19 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-08-06 | 2024-08-31 | 2024-08-06 | 2024-11-30 | ALI//HAMZA/6798000192 | 2024-08-06 | 2024-08-31 | 2024-08-06 | 2025-03-11 | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-08-16 | NG HONG JIE7018000036 | Logistic Team | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
4679B-4669A | Sg Kedah | DU00003936705 | Northern | Kedah | 6.113120 | 100.287270 | [7 empty] | 00. Integrated/RFS Done | 29/7: Cutover done. EPLA 6+0 done 25/7: D1: TI done. Cannot config 6+0 EPLA due hardware limitation. Replan W31 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G 2+0 1.2m/1.2m DP NE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Lo 3) 1x15GHz XMC3 Sub B Lo 4) 1x15GHz 1.2m DP 5) 1xRTN910A FE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Hi 3) 1x15GHz XMC3 Sub B Hi 4) 1x15GHz 1.2m DP 5) 1xRTN910A | MW Parallel Link | Existing link 4679B-4669A 4+0 (4679B RTN02-4669A RTN06) Swap existing RTN910A CSHR with new RTN910A CSHRF Add parallel link 2+0 to existing 4+0 link Patch 2nd port at 4669A RTN06 to CP port and create LAG Final config will be 6+0 Impact sites: 4679B NE (4679B RTN02) 1. Swap old RTN910A CSHR with new RTN910A CSHRF 2. Add ISM8 card at RTN02 slot 4 3. Install new link at RTN02 4-ISM8 4. Create EPLA 6+0 FE (4669A RTN06) 1. Swap old RTN910A CSHR with new RTN910A CSHRF 2. Add ISM8 card at RTN06 slot 4 3. Install new link at RTN06 4-ISM8 4. Create EPLA 6+0 5. Patch GE2 to new IBEAM port 6. Create LAG | [7 empty] | CCSMY | SQ202410010443-CCS | CCSMY | SQ202408080059-CCS | 2024-11-26 | 2024-11-26 | Completed | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24072009 |  | 2024-07-22 | 2024-07-23 | Completed | 2024-07-21 | 2024-07-22 | 2024-07-21 | 2024-07-23 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-25 | 2024-07-31 | 2024-07-25 |  | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2024-07-25 | 2024-07-31 | 2024-07-25 | 2024-07-26 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-07-25 | 2024-07-31 | 2024-07-25 | 2025-02-15 | Muhamad//rais bin mat isa/7021000043 | 2024-07-25 | 2024-07-31 | 2024-07-25 | 2024-07-27 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | NG HONG JIE7018000036 | Logistic Team | 2024-09-09 | 2024-10-09 | 2024-09-09 | 2024-09-09 | ASTI//GANIS PUTRIANI/6237001358
1922B-1122A | Kg Seri Cheedings | DU00003936706 | Central | Selangor | 2.889994 | 101.551852 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 14/7: D2: Cutover done 13/7: D1: MOS & TI In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1922B-1122A 18G 2+0 1.2m/1.2m DP NE: 1) 1x18GHz XMC3E Sub A Hi 2) 1x18GHz XMC3E Sub B Hi 3) 1x18GHz 1.2m DP FE: 1) 1x18GHz XMC3E Sub A Lo 2) 1x18GHz XMC3E Sub B Lo 3) 1x18GHz 1.2m DP | MW Swap | Existing link 1) 1922B-1122A MW3 2+0 56MHz 2) 1922B-1122A 2+0 112MHz (1922B RTN01-1122A RTN08) SOW: 1) Swap SM 2+0 56MHz to Huawei 2+0 112MHz (256QAM Vertical 32QAM Horizontal. Reuse SM frequency channel) 2) Combine new 2+0 link with existing 2+0 112MHz and create 4+0 EPLA Impact sites: 1922B, 1936B DU: 1922B-1122A (swap SM 2+0 56MHz with Huawei 2+0 112MHz) NE (1922B RTN02) 1. Install new link at 7-ISM8 2. Remove cascade to SM IDU 3. Migrate traffic to new link 4. Remove GNE configuration FE (1122A RTN10) 1. Install new link at 7-ISM8 2. Remove cascade to SM IDU 3. Migrate traffic to new link using GE3 (10G port) DU: 1922B-1122A_1 (Combine existing 2+0 Huawei with new 2+0 and create 4+0 EPLA) NE (1922B RTN02) 1. Transfer IF cable from RTN01 7-ISM8-1 to RTN02 4-ISM8-1 2. Transfer IF cable from RTN01 7-ISM8-2 to RTN02 4-ISM8-2 3. Create 4+0 for 7-ISM8 and 3-ISM8 4. Migrate 1922B traffic to new formed link 5. Decom RTN01 for re-deployment FE (1122A RTN10) 1. Add ISM8 card at slot 3 2. Transfer IF cable from RTN08 7-ISM8-1 to RTN10 3-ISM8-1 3. Transfer IF cable from RTN08 7-ISM8-2 to RTN10 3-ISM8-2 4. Create 4+0 for 7-ISM8 and 3-ISM8 5. Migrate 1922B traffic to new formed link/new CP port 6. Decom RTN08 for re-deployment | [7 empty] | GTSB | SQ202411140220-GTSB | GTSB | SQ202408080491-GTSB | 2026-01-06 | 2026-01-05 | Completed | 2025-12-23 | 2026-01-06 | 2025-12-23 | 2025-12-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-23 | 2026-01-06 | 2025-12-23 | 2025-12-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-23 | 2025-12-24 | 2025-12-23 | 2025-12-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071049 |  | 2024-07-11 | 2024-07-12 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-12 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-13 | 2024-07-31 | 2024-07-13 | 2024-09-23 | ADEEL//ISLAM/6799000145 | GTSB TI | 2024-07-13 | 2024-07-31 | 2024-07-13 | 2024-09-23 | ADEEL//ISLAM/6799000145 | GTSB TI | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-08-30 | SHUJAAT//ALI/6800000124 |  |  | 2024-07-13 | 2024-07-31 | 2024-07-13 | 2024-07-23 | ADEEL//ISLAM/6799000145 | 2025-06-08: 2024-07-13; 2025-06-08: 2024-07-31; 2025-06-08: 2024-07-13; 2025-06-13: 2024-07-15 |  |  | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
1922B-1122A_1 | Kg Seri Cheedings | DU00003936707 | Central | Selangor | 2.889994 | 101.551852 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 16/7: D1: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1922B-1122A_1 Hardware upgrade NE: 1) N/A FE: 1) 1xISM8 card | MW Hardware Upgrade | Existing link 1) 1922B-1122A MW3 2+0 56MHz 2) 1922B-1122A 2+0 112MHz (1922B RTN01-1122A RTN08) SOW: 1) Swap SM 2+0 56MHz to Huawei 2+0 112MHz (256QAM Vertical 32QAM Horizontal. Reuse SM frequency channel) 2) Combine new 2+0 link with existing 2+0 112MHz and create 4+0 EPLA Impact sites: 1922B, 1936B DU: 1922B-1122A (swap SM 2+0 56MHz with Huawei 2+0 112MHz) NE (1922B RTN02) 1. Install new link at 7-ISM8 2. Remove cascade to SM IDU 3. Migrate traffic to new link 4. Remove GNE configuration FE (1122A RTN10) 1. Install new link at 7-ISM8 2. Remove cascade to SM IDU 3. Migrate traffic to new link using GE3 (10G port) DU: 1922B-1122A_1 (Combine existing 2+0 Huawei with new 2+0 and create 4+0 EPLA) NE (1922B RTN02) 1. Transfer IF cable from RTN01 7-ISM8-1 to RTN02 4-ISM8-1 2. Transfer IF cable from RTN01 7-ISM8-2 to RTN02 4-ISM8-2 3. Create 4+0 for 7-ISM8 and 3-ISM8 4. Migrate 1922B traffic to new formed link 5. Decom RTN01 for re-deployment FE (1122A RTN10) 1. Add ISM8 card at slot 3 2. Transfer IF cable from RTN08 7-ISM8-1 to RTN10 3-ISM8-1 3. Transfer IF cable from RTN08 7-ISM8-2 to RTN10 3-ISM8-2 4. Create 4+0 for 7-ISM8 and 3-ISM8 5. Migrate 1922B traffic to new formed link/new CP port 6. Decom RTN08 for re-deployment | [7 empty] | GTSB | SQ202411140220-GTSB | GTSB | SQ202408080491-GTSB | 2025-11-25 | 2025-11-24 | Completed | 2024-11-13 | 2024-11-13 | 2024-11-13 | 2024-11-13 | laina@girobumi.com.mylaina@girobumi.com.my |  |  | 1.00 | Unassigned | Completed |  | 2024-11-13 | 2024-11-13 | 2024-11-13 | 2024-11-13 | laina@girobumi.com.mylaina@girobumi.com.my |  |  | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071019 |  | 2024-07-11 | 2024-07-22 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-22 | NAYOMI THAKSHILA6819000029 | Warehouse Team | MORRISON EXPRESS (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-13 | 2024-07-31 | 2024-07-13 | 2024-09-23 | ADEEL//ISLAM/6799000145 | GTSB TI | 2024-07-13 | 2024-07-31 | 2024-07-13 | 2024-09-23 | ADEEL//ISLAM/6799000145 | GTSB TI | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | SHUJAAT//ALI/6800000124 |  |  | 2024-07-13 | 2024-07-31 | 2024-07-13 | 2024-08-30 | ADEEL//ISLAM/6799000145 | 2024-07-13 | 2024-07-31 | 2024-07-13 | 2024-07-15 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | NG HONG JIE7018000036 | Logistic Team | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
7615A-7192A | Wisma Pang | DU00003936708 | Sabah | Sabah | 4.243713 | 117.885536 |  |  | WK02 | JAN 25 | RFS |  |  | 00. Integrated/RFS Done | 23G waveguide to replace | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1) 1xISM8 card 2) 1x23G 112MHz Sub A Lo FE: 1) 1xRTN910A 2) 1x23G 112MHz Sub A Hi | MW Hardware Upgrade | Existing link 7615A-7192A 1+0 56MHz (7615A RTN03-7192A RTN11) 1) To replace ISV3 at 7615A with ISM8 2) To install new IDU at 7192A 3) Replace existing ODU with 112MHz ODU 4) Upgrade link to 112MHz Impact site: 7615A NE (7615A RTN03) 1. Replace ISV3 at slot 1 with new ISM8 2. Replace ODU with new 112MHz ODU 3. Upgrade link to 112MHz FE (7192A new RTN) 1. Install new RTN910A (ops team to assign RTN number) 2. Transfer IF cable from RTN11 3-ISV3 to new RTN 7-ISM8-1 3. Replace ODU with new 112MHz ODU 4. Upgrade link to 112MHz 5. Migrate traffic to new link and created DCN | [7 empty] | NR services | SQ202501160053-NR Services | NR services | SQ202501140138-NR Services // SQ202504260199-NR Services | 2025-01-17 | 2025-01-15 | Completed | 2025-01-14 | 2025-01-14 | 2025-01-14 | 2025-01-14 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-14 | 2025-01-17 | 2025-01-14 | 2025-01-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-14 | 2025-01-17 | 2025-01-14 | 2025-01-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-15 | 2025-01-17 | 2025-01-15 | 2025-01-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24120635 |  | 2025-01-09 | 2025-01-09 | Completed | 2024-12-06 | 2025-01-09 | 2025-01-09 | 2025-01-09 | NUR/WAFA/MIJONG/6871000001 |  | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-01-09 | RAMLAN//BIN ROSLAN/6000002578 | NR Service TI | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-01-16 | RAMLAN//BIN ROSLAN/6000002578 | NR Service TI | 2025-01-10 | 2025-01-10 | 2025-01-10 | 2025-01-10 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-01-14 | RAMLAN//BIN ROSLAN/6000002578 | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-01-11 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | tseping//wang/6819000006 | Logistic Team | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
4967A-4685B | Karangan(Mxs) | DU00003936709 | Northern | Kedah | 5.423196 | 5.423196 | W49-52 | DEC 24 | W49-52 | DEC 24 |  |  |  | 00. Site Out/Drop | 15/8: Pending BoQ, TX SoW Details | TSS |  | 13G_4+0_28M_CA. NE_4967A 13G_DP_1.8m (MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub_A_Lo x1. FE_4685B 13G_DP_1.8m (MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub_A_Hi x1. | Cancel / Drop | Solution and TI completed follow TX Rollout 4967A. | [13 empty] | Ongoing | 2024-12-28 | 2024-12-28 | 2024-12-28 |  | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1278C-1070A | Perodua Serendah | DU00003936710 | Central | Selangor | 3.372967 | 101.582180 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 19/7: D1: Cutover done. Remote upgrade | AA | PAC |  | MW Remote Upgrade | MW Remote Upgrade 56Mhz to 112Mhz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2024-07-19 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
9425A-9441A | KUCHING DIGI CENTER | DU00003936711 | Sarawak | Sarawak | 1.554087 | 110.332175 |  | DEC 24 |  |  |  |  | ZTE | 00. Integrated/RFS Done | 22/10: Pending Site DO 20/9: Pending Site BoM. Req regional to verifty on materials availability | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_0.6/0.6M_SP_2x SB B | MW Swap | SWAP MW LINK 9425A-9441A WITH HUAWEI_23GHZ_1+0_56MHZ_0.6M NE: 1. SWAP existing SM IDU with HW RTN910A 2. Swap existing ODU with HW XMC-3_SB B. 3. Swap exisrting Antenna with 0.6m_SP. 4. Configure 23G_1+0_0.6_1024QAM 5. Dismantle esisting SM MW link FE: 1. SWAP existing SM IDU with HW RTN910A 2. Swap existing ODU with HW XMC-3_SB B. 3. Swap exisrting Antenna with 0.6m_SP. 4. Configure 23G_1+0_0.6_1024QAM 5. Dismantle esisting SM MW link . | [7 empty] | Magicell | SQ202411120055-Magicell | Trintel | SQ202412180567-Trintel // SQ202504260214-Trintel | 2024-12-13 | 2024-12-11 | Completed | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2024-11-01 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-04 | 2024-11-04 | 2024-11-04 | 2024-11-04 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-20 | 2024-11-22 | 2024-11-20 | 2024-11-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-11 | 2024-12-13 | 2024-12-11 | 2024-12-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24121715 |  | 2024-12-18 | 2025-01-04 | Completed | 2024-12-17 | 2024-12-18 | 2024-12-17 | 2025-01-04 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-16 | 2025-01-14 | 2025-01-07 | 2025-01-09 | LAW KIM CHANG7667000035 | Trintel TI | 2024-12-16 | 2025-01-14 | 2025-01-06 | 2025-01-31 | LAW KIM CHANG7667000035 | Trintel TI | 2025-01-08 | 2025-01-08 | 2025-01-08 | 2025-01-08 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-12-16 | 2025-01-14 | 2025-02-04 | 2025-02-04 | LAW KIM CHANG7667000035 | 2024-12-16 | 2025-01-14 | 2025-01-08 | 2025-01-08 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-04 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
K00211-K00148 | K010A_K00211OD_TANAHMERAH | DU00003936712 | Northern | Kedah | 6.023896 | 100.483220 | WK32 - WK35 | AUG 24 | WK32 - WK35 | AUG 24 |  |  |  | 00. Integrated/RFS Done | 12/9: Cutover done. Post-CO T/shooting WIP | TSS+TI | L1+ATP+PAC | 2 x SFP 1G 1 pair patch cord | MW IDU Patching | ETH port connection at Huawei IDU NT05810 Batumenunggul GE1 to PTN port To patch GE3 (optical) to new PTN port and transfer traffic ZTE K00791 CB_KG_GUAR_KEPAYANG to new PTN port Impacted sites: K00791 NE (K00211): 1) Remain existing FE (K00148): 1) Patch IDU NT05810 GE3 port (optical) to new PTN port (ops team to assign) 2) Reconfigure traffic ZTE K00791 CB_KG_GUAR_KEPAYANG on IDU to GE3 and PTN on new port | [7 empty] | GCI | SQ202409251048-GCI | GCI | SQ202409060591-GCI | 2024-11-29 | 2024-11-29 | Completed | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-09-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240821AR |  | 2024-08-22 | 2024-08-23 | Completed | 2024-08-21 | 2024-08-22 | 2024-08-21 | 2024-08-23 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-12 | 2024-09-30 | 2024-09-11 | 2024-10-19 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2024-09-12 | 2024-09-30 | 2024-09-11 | 2024-10-19 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-09-12 | 2024-09-30 | 2024-09-11 | 2024-09-12 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-06-08: 2024-09-12; 2025-06-08: 2024-09-30; 2025-06-08: 2024-09-11; 2025-06-13: 2024-09-12 |  |  | 2024-10-16 | 2024-11-16 | 2024-10-16 | 2024-10-16 | ASTI//GANIS PUTRIANI/6237001358
2637A-B00695 | Pt16 Sg Panjang | DU00003936713 | Central | Selangor | 3.718412 | 101.124040 |  |  |  | JAN 25 | Cancel / Drop | SOW Existing TX | ZTE | 00. Site Out/Drop | 13/1/2025 : SBC KJS - 76M 3 Legged Tower - NE site 2637A Pt16 Sg Panjang, EDOTCO (M) SDN BHD - TOWER 61M LAND - FE site B00695 B062A_B00695OD_PT13SGPJG 9/8: SOW done under 2637A_PostMOCN |  |  |  | Cancel / Drop | LINK DONE UNDER NIC 2637A_PostMOCN and 2637A_PostMOCN1 | [7 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY240730AG | 11/9: Req repeal DO due SOW cancel | 2024-07-31 |  | Ongoing | 2024-07-30 | 2024-07-31 | 2024-07-30 |  | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing
9699B-9258B | TK Materials | DU00003936714 | Sarawak | Sarawak | 2.282935 | 111.847260 | [6 empty] | ZTE | 00. Integrated/RFS Done | 24/10: D1: Cutover done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M from 9699B-9258B | MW Remote Upgrade | MW Remote Upgrade from 18G_56Mhz to 18G_128QAM_112Mhz NE: 1. Remote upgrade from 56Mhz to 128QAM_112Mhz. 2. Configure 18G_1+0_128QAM_112Mhz. FE: 1. Remote upgrade from 56Mhz to 128QAM_112Mhz. 2. Configure 18G_1+0_128QAM_112Mhz. | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-10-24 | 2024-10-24 | 2024-10-24 | 2024-10-24 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2024-11-28 | 2024-12-28 | 2024-11-28 | 2024-11-28 | ASTI//GANIS PUTRIANI/6237001358
4672C-4034A | Idaman Lavendar | DU00003936715 | Northern | Penang | 5.331271 | 100.272489 | [7 empty] | 00. Integrated/RFS Done | 18/7: D2: Cutover done 10/7: EB CRQ start 17/7 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1) 1x18G XMC3E Sub B Hi 2) 1xISM8 card 3) 1xRTN910A FE: 1) 1x18G XMC3E Sub B Lo 2) 1xISM8 card 3) 1xRTN910A | MW Hardware Upgrade | Existing link 4672C-4034A 2+0 (4672C RTN01-4034A RTN11) To upgrade 18G link to 112MHz Impact site: 4672C NE (4672C RTN01) 1. Swap IDU with RTN910A 2. Add ISM8 card slot 3 3. Swap existing 18G ODU with new XMC3E ODU 4. Transfer existing 18G link to 7-ISM8-1 5. Upgrade to 112MHz 6. Transfer existing 15G link to 3-ISM8-1 7. Create EPLA 2+0 NE (4034A RTN11) 1. Swap IDU with RTN910A 2. Add ISM8 card slot 3 3. Swap existing 18G ODU with new XMC3E ODU 4. Transfer existing 18G link to 7-ISM8-1 5. Upgrade to 112MHz 6. Transfer existing 15G link to 3-ISM8-1 7. Create EPLA 2+0 | [7 empty] | GCI | SQ202408220943-GCI | GCI | SQ202408080062-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2024-07-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071005 |  | 2024-07-11 | 2024-07-13 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-08-06 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-08-06 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-17 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-07-19 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-07-18 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
9737C_PL | kampung hulubeladin | DU00006593382 | Sarawak | Sarawak | 1.634970 | 111.209000 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Remote Software upgrade from 23G_1+0_56M to 23G_1+0_112M | Remote Software upgrade from 23G_1+0_56M to 23G_1+0_112M | Remote Software upgrade from 23G_1+0_56M to 23G_1+0_112M | XMC_3E | MAC | 23G | 0.3 | 0.3 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-02-04 | [15 empty] | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202602120121-GCI | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | CHEONG/SENG/WAH/7018000306
9188A_PL | Pusa(Celcom) | DU00006593383 | Sarawak | Sarawak | 1.626610 | 111.292255 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP x 2. Fiber patch cord x 1 pairs. | MW IDU Patching | Perform 10G patching between 9188A RTN04-9188A RTN03 to solve IDU-IDU bottleneck issue. NE_9188A 1. 10G patching between 9188A_RTN03_GE4 to 9188A_RTN04_GE3. 2. Disconnect existing ETH cable between 9188A_RTN04 to 9188A_RTN03 and disable unused port. Site Impacted : 9566C , 9737C , 9188A , 9463B | Perform 10G patching between 9188A RTN04-9188A RTN03 to solve IDU-IDU bottleneck issue NE_9188A 1. 10G patching between 9188A_RTN03_GE4 to 9188A_RTN04_GE3. 2. Disconnect existing ETH cable between 9188A_RTN04 to 9188A_RTN03 and disable unused port. Site Impacted : 9566C , 9737C , 9188A , 9463B | [6 empty] | NR Services | SQ202602250637-NR Services | NR Services | SQ202602160109-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26020433 |  | 2026-02-05 |  | Ongoing | 2026-02-04 | 2026-02-05 | 2026-02-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [13 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-02-04 | [15 empty] | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202602120121-GCI | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | CHEONG/SENG/WAH/7018000306
9566C_HU_1 | Baladdin (REL) | DU00006597648 | Sarawak | Sarawak | 1.631781 | 111.204366 | [9 empty] | TSS+AA+TI |  | 13G_4+0_28M NE_9566C 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub B_Hi x1. FE_9188A. 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub B_Hi x1. | MW Parallel Link | Install Parallel link 13G_4+0_28M and 13G-2+0_28M will be install under DU ID 9566C_HU_2. Combination of 13G_6+0_28M config. ***Refer DU ID 9566C_HU_2 for new RTN910A installation. Site Impacted : 9737C. NE_9566C 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross connect , CA and EPLA. 5.Enable GE1 , transfer existing ETH from 9566C_RTN01_GE2 to new RTN910A_GE1. 6.Traffic migrate to new parallel link. 7.No decomm existing MW. FE_9188A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 3.Install new XMC_5D , Sub B_Hi. 4.Enable GE3 , 10G Port Fiber Patching to existing 9188A_RTN03_GE6. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new parallel link. 7.No decomm existing MW. | Install Parallel link 13G_4+0_28M and 13G-2+0_28M will be install under DU ID 9566C_HU_2. Combination of 13G_6+0_28M config. ***Refer DU ID 9566C_HU_2 for new RTN910A installation. Site Impacted : 9737C. NE_9566C 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross connect , CA and EPLA. 5.Enable GE1 , transfer existing ETH from 9566C_RTN01_GE2 to new RTN910A_GE1. 6.Traffic migrate to new parallel link. 7.No decomm existing MW. | Install Parallel link 13G_4+0_28M and 13G-2+0_28M will be install under DU ID 9566C_HU_2. Combination of 13G_6+0_28M config. ***Refer DU ID 9566C_HU_2 for new RTN910A installation. Site Impacted : 9737C. FE_9188A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 3.Install new XMC_5D , Sub B_Hi. 4.Enable GE3 , 10G Port Fiber Patching to existing 9188A_RTN03_GE6. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new parallel link. 7.No decomm existing MW. | XMC_5D | MDD | 13G | 1.2 | 1.2 | Nr Services | SQ202603130186-NR Services | Magicell |  | 2026-03-13 | 2026-03-13 | Completed | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202602120121-GCI | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | CHEONG/SENG/WAH/7018000306
1497H_AD | 99Speedmart TMN CEMPAKA BANTING | DU00006597649 | Central | Selangor | 2.800328 | 101.493299 | [7 empty] | 05. Doable |  | TSS+TI | L1+ATP+PAC | 2XPATCH CORD | MW IDU Patching | Migrate 1497H to B00473 Tx route before: 1497H-NLOS-2094A-1130A Tx route after: 1497H-NLOS-B00473 PATCHING NLOS AT FE FROM xD 2094A TO xC B00473 |  | Migrate 1497H to B00473 Tx route before: 1497H-NLOS-2094A-1130A Tx route after: 1497H-NLOS-B00473 PATCHING NLOS AT FE FROM xD 2094A TO xC B00473 | [5 empty] | GCI | SQ202602270377-GTSB | GCI | SQ202602270373-GTSB |  |  | Ongoing | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26031071 |  | 2026-03-11 | 2026-03-14 | Completed | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-10 | 2026-04-17 | 2026-04-10 | 2026-04-10 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-04-10 | 2026-04-17 | 2026-04-10 | 2026-04-11 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-04-12 | 2026-04-12 | 2026-04-12 | 2026-04-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-12 | 2026-04-10 | 2026-04-17 | 2026-04-10 | 2026-04-11 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-06-08: 2026-04-10; 2025-06-08: 2026-04-17; 2025-06-08: 2026-04-10; 2025-06-13: 2026-04-10 | [7 empty] | GCI | SQ202602120113-GCI | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
9566C_HU_2 | Baladdin(REL) | DU00006597650 | Sarawak | Sarawak | 1.631781 | 111.204366 | [9 empty] | TSS+AA+TI |  | 13G_2+0_28M NE_9566C 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. FE_9188A. 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Install Parallel link 13G_2+0_28M and 13G-4+0_28M will be install under DU ID 9566C_HU_1. Combination of 13G_6+0_28M config. ***Refer DU ID 9566C_HU_1 for combination 13G_6+0_28M. Site Impacted : 9737C. NE_9566C 1.Install new 13G_DP_1.2M(MDD). 2.Install new new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decomm existing MW. FE_9188A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decomm existing MW. | Install Parallel link 13G_2+0_28M and 13G-4+0_28M will be install under DU ID 9566C_HU_1. Combination of 13G_6+0_28M config. ***Refer DU ID 9566C_HU_1 for combination 13G_6+0_28M. Site Impacted : 9737C. NE_9566C 1.Install new 13G_DP_1.2M(MDD). 2.Install new new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decomm existing MW. | Install Parallel link 13G_2+0_28M and 13G-4+0_28M will be install under DU ID 9566C_HU_1. Combination of 13G_6+0_28M config. ***Refer DU ID 9566C_HU_1 for combination 13G_6+0_28M. Site Impacted : 9737C. FE_9188A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decomm existing MW. | XMC_5D | MDD | 13G | 1.2 | 1.2 | Nr Services | SQ202603130186-NR Services | Magicell |  | 2026-03-13 | 2026-03-13 | Completed | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202602120121-GCI | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | CHEONG/SENG/WAH/7018000306
1203H_AD | 99 Speedmart KGSG LANG | DU00006597651 | Central | Selangor | 2.790280 | 101.510325 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | FE_2094A/B00473 1.New CAT6 cable with suitable length(IDU HW NLOS to Cisco) x1. 2.Request electrical SFP Module for Cisco Router x1. (NLOS only have electrical interface) | MW IDU Patching | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 1203H_AD & DU 1497H_AD(BOTH DU NEED TO PERFORM FIRST BEFORE PERFORM DU B00473_Decom3). 2ND - DU B00473_Decom3.**** Perform MW IDU(NLOS) Patching at FE_2094A/B00473. Site Impacted : 1203H. FE_2094A/B00473 1.Disconnect/remove cascading in between port GE05 or GE06 of existing ZTE MW Link 2094A-1130A, ZXMW 18G_56Mhz_2+0_512Q_860M and port 2-EG3-3(P&E) of existing 1203H-NLOS-2094A. 2.Request new electrical 1G port at PTN/Cisco(PTN ID 70001) from ZTE IPRAN Team. 3.Perform new patching port 2-EG3-3(P&E) and new electrical 1G port at PTN/Cisco(PTN ID 70001). 4.Request new xC Vlan DCN & Vlan Services for NLOS 1203H from ZTE IPRAN team. 5.Migrate NLOS 1203H traffic to new electrical 1G port at PTN/Cisco(PTN ID 70001). |  | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 1203H_AD & DU 1497H_AD(BOTH DU NEED TO PERFORM FIRST BEFORE PERFORM DU B00473_Decom3). 2ND - DU B00473_Decom3.**** Perform MW IDU(NLOS) Patching at FE_2094A/B00473. Site Impacted : 1203H. FE_2094A/B00473 1.Disconnect/remove cascading in between port GE05 or GE06 of existing ZTE MW Link 2094A-1130A, ZXMW 18G_56Mhz_2+0_512Q_860M and port 2-EG3-3(P&E) of existing 1203H-NLOS-2094A. 2.Request new electrical 1G port at PTN/Cisco(PTN ID 70001) from ZTE IPRAN Team. 3.Perform new patching port 2-EG3-3(P&E) and new electrical 1G port at PTN/Cisco(PTN ID 70001). 4.Request new xC Vlan DCN & Vlan Services for NLOS 1203H from ZTE IPRAN team. 5.Migrate NLOS 1203H traffic to new electrical 1G port at PTN/Cisco(PTN ID 70001). | [5 empty] | GTSB | SQ202602230036-GTSB | GTSB | SQ202602230033-GTSB |  |  | Ongoing | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-16 | 2026-04-23 | 2026-04-16 | 2026-04-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-16 | 2026-04-23 | 2026-04-16 | 2026-04-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022318 |  | 2026-02-24 | 2026-03-05 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-03-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-28 | 2026-03-31 | 2026-02-28 | 2026-03-06 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-02-28 | 2026-03-31 | 2026-02-28 | 2026-03-06 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-03-03 | 2026-02-28 | 2026-03-31 | 2026-02-28 | 2026-03-04 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-06-08: 2026-02-28; 2025-06-08: 2026-03-31; 2025-06-08: 2026-02-28; 2025-06-13: 2026-03-03 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202602120128-GTSB
4170A_AD | Puspakom MakMandin | DU00006608656 | Northern | Penang | 5.417139 | 100.389111 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cat6 Cable x1. | MW Re-engineering | 4170A currently has 2 TDC LL port. To perform load balancing as current LL utilization is Imbalance between these 2 ports. Kindly refer DU ID 4170A_AD_1 for 4170A_RTN02 Activity. Impacted Sites : 4170A , 4800C. NE_4170A 1) Patch 4170A RTN03 direct to TDC port #1 (Port details not available. To check at site). 2) Re-engineer for TDC port #1 to only carry traffic 4170A and 4800C. 3) Remove connection 4170A RTN03-RTN02 and disable unused port. 4) Create new DCN for 4170A RTN03. | 4170A currently has 2 TDC LL port. To perform load balancing as current LL utilization is Imbalance between these 2 ports. Kindly refer DU ID 4170A_AD_1 for 4170A_RTN02 Activity. Impacted Sites : 4170A , 4800C. NE_4170A 1) Patch 4170A RTN03 direct to TDC port #1 (Port details not available. To check at site). 2) Re-engineer for TDC port #1 to only carry traffic 4170A and 4800C. 3) Remove connection 4170A RTN03-RTN02 and disable unused port. 4) Create new DCN for 4170A RTN03. | [6 empty] | GCI | SQ202602230142-GCI | GCI | SQ202602230136-GCI | 2026-03-05 | 2026-03-04 | Completed | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022313 |  | 2026-02-24 | 2026-03-02 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-03-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-27 | 2026-03-03 | 2026-02-27 | 2026-03-02 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | GCI TI | 2026-02-27 | 2026-03-03 | 2026-02-27 | 2026-03-02 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | GCI TI | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-27 | 2026-02-27 | 2026-03-03 | 2026-02-27 | 2026-03-02 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | 2025-06-08: 2026-02-27; 2025-06-08: 2026-03-03; 2025-06-08: 2026-02-27; 2025-06-13: 2026-02-27 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602120114-GCI | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | CHEONG/SENG/WAH/7018000306
4170A_AD_1 | PuspakomMak Mandin | DU00006608657 | Northern | Penang | 5.417139 | 100.389111 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cat6 Cable x1. | MW Re-engineering | 4170A currently has 2 TDC LL port. To perform load balancing as current LL utilization is Imbalance between these 2 ports. Kindly refer DU ID 4170A_AD for 4170A_RTN03 Activity. Impacted site : 4042D , 4937C NE_4170A 1) Patch 4170A RTN02 direct to TDC port #2 (Port details not available. To check at site) 2) Re-engineer for TDC port #2 to only carry traffic 4042D and 4937C 3) Remove connection 4170A RTN02-RTN01 and disable unused port. 4) Create new DCN for 4170A RTN02 5) Dismantle IDU 4170A RTN01. | 4170A currently has 2 TDC LL port. To perform load balancing as current LL utilization is Imbalance between these 2 ports. Kindly refer DU ID 4170A_AD for 4170A_RTN03 Activity. Impacted site : 4042D , 4937C NE_4170A 1) Patch 4170A RTN02 direct to TDC port #2 (Port details not available. To check at site) 2) Re-engineer for TDC port #2 to only carry traffic 4042D and 4937C 3) Remove connection 4170A RTN02-RTN01 and disable unused port. 4) Create new DCN for 4170A RTN02 5) Dismantle IDU 4170A RTN01. | [6 empty] | GCI | SQ202602230142-GCI | GCI | SQ202602230136-GCI | 2026-03-05 | 2026-03-04 | Completed | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022314 |  | 2026-02-24 | 2026-03-02 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-03-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-27 | 2026-03-03 | 2026-02-27 | 2026-03-02 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | GCI TI | 2026-02-27 | 2026-03-03 | 2026-02-27 | 2026-03-02 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | GCI TI | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-27 | 2026-02-27 | 2026-03-03 | 2026-02-27 | 2026-03-02 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | 2025-06-08: 2026-02-27; 2025-06-08: 2026-03-03; 2025-06-08: 2026-02-27; 2025-06-13: 2026-02-27 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602120114-GCI | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | CHEONG/SENG/WAH/7018000306
B00007_HU | SPGPCKALAM | DU00005948168 | Central | Selangor | 3.245210 | 101.472190 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 4X ISM8 CARD 2X RTN910A 2X 13G 1.2M MDD ANTENNA 1x ODU 13G XMC5D SUB B HI 1X ODU 13G XMC5D SUB B LO 2X SFP 1G 10KM 1X PAIR PATCH CORD | MW Parallel Link | MW PARALLEL LINK B00007-B00545 WITH HUAWEI_13G4+0_1.2M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_B_WITH CA_5.6KM IMPACTED: 1965B TRANSFER BBU 1965B TRAFFIC TO THIS NEW LINK | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 AT SLOT 3 AND 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. PATCH AND TRANSFER BBU 1965B TRAFFIC TO THIS NEW LINK | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 AT SLOT 3 AND 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. PATCH AND TRANSFER BBU 1965B TRAFFIC TO THIS NEW LINK 6. PATCH TO NEW CP PORT | XMC3E | MAC | 18G | 1.2 | 1.2 | MTK | SQ202512170150-MTK | MTK | SQ202511070143-MTK // SQ202511190823-MTK | 2026-02-20 | 2026-02-20 | Completed | 2025-12-17 | 2026-02-20 | 2026-02-20 | 2026-02-20 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102821 |  | 2025-10-29 | 2025-10-30 | Completed | 2025-10-28 | 2025-10-29 | 2025-10-28 | 2025-10-30 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-28 | 2026-01-16 | 2026-01-16 | MOHD FADZILLAH BIN TARMIJI8225000017 | MTK TI | 2025-11-10 | 2025-11-28 | 2026-01-17 | 2026-01-17 | MOHD FADZILLAH BIN TARMIJI8225000017 | MTK TI | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-19 | 2025-11-10 | 2025-11-28 | 2026-01-19 | 2026-01-19 | MOHD FADZILLAH BIN TARMIJI8225000017 | 2025-06-08: 2025-11-10; 2025-06-08: 2025-11-28; 2025-06-08: 2025-11-19; 2025-06-13: 2025-11-19 |  |  | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202508150527-GCI | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | EZRIN TASNIM BIN ABDUL GANI6798000128
7512A_HU_2 | Morisem | DU00005948169 | Sabah | Sabah | 5.504748 | 118.395624 | [7 empty] | 01. Pending Planning |  | TSS+AA+TI |  | 13G_4+0_28M_512QAM_EPLA(Without CA) NE_7512A New 13G_1.8M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. FE_7585A New 13G_1.8M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x2. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. | MW Parallel Link | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202508150543-GTSB
3288B_HU | Taman Maju Jaya | DU00005948170 | Central | Selangor | 3.132236 | 101.746435 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC | NA | MW Remote Upgrade | Link existing 18G_1+0_56M Site Impacted : 3288B , 1320A. Perform Remote Software Upgrade to 18G_1+0_112M with 512QAM. | Site Impacted : 3288B , 1320A. NE3288B Perform Remote Software Upgrade to 18G_1+0_112M with 512QAM. | Site Impacted : 3288B , 1320A. FE_B00601 Perform Remote Software Upgrade to 18G_1+0_112M with 512QAM. | [5 empty] | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-23 | [15 empty] | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202508150527-GCI | 2025-08-17 | 2025-08-17 | 2025-08-17 | 2025-08-17 | CHEONG/SENG/WAH/7018000306
4136R_HU | Kg. Padang Ekor | DU00005948171 | Northern | Kedah | 5.481310 | 100.560691 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link existing 18G_2+0_28M Site Impacted : 4136R Perform Remote Software Upgrade to 18G_2+0_56M with 512QAM. | Link existing 18G_2+0_28M Site Impacted : 4136R Perform Remote Software Upgrade to 18G_2+0_56M with 512QAM. | [8 empty] | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-24 | [15 empty] | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-17 | 2025-08-17 | 2025-08-17 | 2025-08-17 | CHEONG/SENG/WAH/7018000306
B02793_HU | JLNBALAPANSEK13SA | DU00005948172 | Central | Selangor | 3.087658 | 101.547670 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_B02793 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. FE_B00549 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. | MW Swap | Link existing 18G_1+0_56M Swap existing link to 23G_2+0_112M Site Impacted : B02793. NE_B02793 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link. 6.Decom existing MW link CT10288. FE_B00549 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create new In band DCN 6.Traffic migrate to new MW link. 7.Decom existing MW link CT10288. | Link existing 18G_1+0_56M Swap existing link to 23G_2+0_112M Site Impacted : B02793. NE_B02793 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link. 6.Decom existing MW link CT10288. | Link existing 18G_1+0_56M Swap existing link to 23G_2+0_112M Site Impacted : B02793. FE_B00549 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create new In band DCN 6.Traffic migrate to new MW link. 7.Decom existing MW link CT10288. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202508200537-GTSB | GTSB | SQ202508200506-GTSB // SQ202508200516-GTSB | 2025-10-08 | 2025-10-07 | Completed | 2025-09-22 | 2025-10-06 | 2025-09-22 | 2025-09-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-10-06 | 2025-09-22 | 2025-09-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082546 |  | 2025-08-26 | 2025-09-13 | Completed | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-09-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-24 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-24 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-18 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-23 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-17 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202508150527-GCI | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | CHEONG/SENG/WAH/7018000306
4781B_HU | Felda Besout 4&6 | DU00005948173 | Northern | Perak | 3.778250 | 101.276388 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x IF Cable 2x Patch Cord | MW Re-engineering | -POINTING AND POI NEEDED FOR 4191R TO XC- MW REENGINEERING 4781B-4730A RTN05 SLOT 7-1 & 7-2 SHIFT IF CABLE TO 4781B-A00553 RTN01 SLOT 7-1 & 7-2 BRING TRAFFIC 4191R TO XD FE IDU PATCH TO NEW CP PORT AND DO PORT LAG 2G | 1. SHIFT IF CABLE 4781B-4730A RTN05 SLOT 7-1 & 7-2 TO 4781B-A00553 RTN01 SLOT 7-1 & 7-2 BRING TRAFFIC 4191R TO XD 2. POINTING AND POI NEEDED FOR 4191R TO XC 4781B-A00553 | 1. FE IDU A00553 PATCH TO NEW CP PORT AND DO PORT LAG 2G | [5 empty] | GCI | SQ202508200564-GCI | GCI | SQ202508200559-GCI | 2025-11-28 | 2025-11-27 | Completed | 2025-08-26 | 2025-08-27 | 2025-08-26 | 2025-08-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | 2025-09-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081975 |  | 2025-08-20 | 2025-08-22 | Completed | 2025-08-19 | 2025-08-20 | 2025-08-19 | 2025-08-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-09-08 | 2025-08-25 | 2025-08-26 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-08-25 | 2025-09-08 | 2025-08-25 | 2025-08-26 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-25 | 2025-08-25 | 2025-09-08 | 2025-08-25 | 2025-08-26 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-09-16: 2025-08-25; 2025-09-16: 2025-09-08; 2025-09-16: 2025-08-25; 2025-09-17: 2025-08-25 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | EZRIN TASNIM BIN ABDUL GANI6798000128
3199A_HU | Surau Ad-Dhuha Sec 8 | DU00005948174 | Central | Selangor | 3.178423 | 101.578225 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X ISM8 CARD 1X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3 SUB B HI 1X ODU 23G XMC3 SUB B LO | MW Swap | MW SWAP UPG 3199A-2997A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3_SUB_B_1.07KM IMPACTED: 3199A DISMANTLE EXISTING LINK EXCEPT FE IDU | 1. INSTALL NEW RTN910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512AM 5. DISMANTLE EXISTING LINK | 1. REPLACE EXISTING ISV3 CARD TO 1PCS ISM8 CARD AT SLOT 4 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512AM 5. DISMANTLE EXISTING LINK EXCEPT IDU | XMC3 | MAC | 23G | 0.6 | 0.6 | GCI | SQ202508200493-GCI | GCI | SQ202508200482-GCI // SQ202508200487-GCI | 2025-11-11 | 2025-11-10 | Completed | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082544 |  | 2025-08-26 | 2025-08-28 | Completed | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-08-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-11 | 2025-09-18 | 2025-09-10 | 2025-09-12 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-09-11 | 2025-09-18 | 2025-09-10 | 2025-09-18 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-12 | 2025-09-11 | 2025-09-18 | 2025-09-10 | 2025-09-18 | Ragunalan//A/L L.Krisnan6000006720 | 2025-09-11 | 2025-09-18 | 2025-09-10 | 2025-09-12 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202508150527-GCI | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
2991C_HU | MIRAMAR_HOTEL1 (REL) | DU00005948175 | Central | Kuala Lumpur | 3.137546 | 101.700847 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 2991C-1063B 23G_1+0_0.3M/0.3M_DP_56MHZ_512QAM TO 23G_1+0_0.3M/0.3M_DP_112MHZ_512QAM IMPACTED SITE: 2991C | MW REMOTE UPGRADE LINK 2991C-1063B 23G_1+0_0.3M/0.3M_DP_56MHZ_512QAM TO 23G_1+0_0.3M/0.3M_DP_112MHZ_512QAM IMPACTED SITE: 2991C | MW REMOTE UPGRADE LINK 2991C-1063B 23G_1+0_0.3M/0.3M_DP_56MHZ_512QAM TO 23G_1+0_0.3M/0.3M_DP_112MHZ_512QAM IMPACTED SITE: 2991C | XMC3E | MAC | 23G | 0.3 | 0.3 | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-25 | [15 empty] | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202508150527-GCI | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
4659D_HU | Hospital Kulim | DU00005948176 | Northern | Kedah | 5.391796 | 100.574044 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | WRONG DU ID. SHOULD BE UNDER 4695D_HU DUE TO NE IDENTIFIER 4626A/K00576-TMNARKED RDC - 4695D_KAMPUNG CHEROK KELUBI-7-ISM8-1(4695D-RTN01 (V-01)) | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202508150530-GCI | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
K00155_HU | BUKITKECHIL | DU00005948177 | Northern | Kedah | 5.623825 | 100.422036 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G 1.2M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap | MW SWAP UPGRADE K00155-K00333 WITH HUAWEI_18G_2+0_1.2M/1.2M_DP_112MHZ_256QAM_1556MBPS_XMC3E_SUB_A & B_4.5KM IMPACTED: K00155 | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. PATCH TO NEW CP PORT | XMC3E | MAC | 18G | 0.6 | 0.6 | MTK | SQ202509100076-MTK | MTK | SQ202509100072-MTK // SQ202509100074-MTK |  |  | Ongoing | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY251001B0 |  | 2025-10-03 | 2025-10-09 | Completed | 2025-10-02 | 2025-10-03 | 2025-10-01 | 2025-10-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-14 | 2026-02-26 | 2026-02-26 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2026-01-09 | 2026-01-14 | 2026-03-01 | 2026-03-01 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-15 | 2026-01-09 | 2026-01-14 | 2026-03-01 | 2026-03-01 | DZULFAIZAL//BIN MAULUF/8225000001 | 2026-01-09 | 2026-01-14 | 2026-02-27 | 2026-02-27 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | NG HONG JIE7018000036 | Logistic Team | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
7010C_HU | Log Pond | DU00005948178 | Sabah | Sabah | 4.280401 | 117.868913 |  |  |  |  | DT February |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M_512QAM_EPLA NE_7010C New 23G_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN02, NEID 9-43876). New XMC_3E, Sub B_Lo x2. FE_7677B New 23G_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 9-19306). New XMC_3E, Sub B_Hi x2. | MW Swap | Existing HW MW Link_7010C-7677B, 18G_1+0_110MHZ_512QAM. MW Swap to HW MW Link 7010C-7677B, 23G_2+0_110MHZ_512QAM_EPLA. Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7010C-7677B, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. Site Impacted : 7010C. NE_7010C 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43876) and reuse existing slot 07(port 1 & 2). 3.Install new XMC_3E, Sub B_Lo x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7010C via new HW MW Link 7010C-7677B, 23G_2+0_110MHZ_512QAM_EPLA. 6.Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7010C-7677B, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. FE_7677B 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-19306) and reuse existing slot 03(port 1 & 2). 3.Install new XMC_3E, Sub B_Hi x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7010C via existing port at IBeam/CP 7205A. 6.Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7010C-7677B, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. | Existing HW MW Link_7010C-7677B, 18G_1+0_110MHZ_512QAM. MW Swap to HW MW Link 7010C-7677B, 23G_2+0_110MHZ_512QAM_EPLA. Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7010C-7677B, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. Site Impacted : 7010C. NE_7010C 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43876) and reuse existing slot 07(port 1 & 2). 3.Install new XMC_3E, Sub B_Lo x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7010C via new HW MW Link 7010C-7677B, 23G_2+0_110MHZ_512QAM_EPLA. 6.Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7010C-7677B, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. | Existing HW MW Link_7010C-7677B, 18G_1+0_110MHZ_512QAM. MW Swap to HW MW Link 7010C-7677B, 23G_2+0_110MHZ_512QAM_EPLA. Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7010C-7677B, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. Site Impacted : 7010C. FE_7677B 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-19306) and reuse existing slot 03(port 1 & 2). 3.Install new XMC_3E, Sub B_Hi x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7010C via existing port at IBeam/CP 7205A. 6.Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7010C-7677B, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. | XMC_3E | MAC | 23G | 23G_0.6M(MAC)+OMT x1 | 23G_0.6M(MAC)+OMT x1 | Seri Pancar | SQ202602090132-Seri Pancar | GCI | SQ202604030210-GCI // SQ202604030211-GCI |  |  | Ongoing | 2026-02-04 | 2026-02-28 | 2026-02-05 | 2026-02-05 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-02-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031157 |  | 2026-03-12 | 2026-03-30 | Completed | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-30 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-04-30 | 2026-04-02 | 2026-04-06 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-04-02 | 2026-04-30 | 2026-04-02 | 2026-04-06 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-14 | 2026-04-02 | 2026-04-30 | 2026-04-02 | 2026-04-17 | RAI//JORDAN RICHARD RIBU/7018000190 | 2026-01-09: 2026-04-02; 2026-01-14: 2026-04-30; 2026-02-27: 2026-04-02; 2026-02-27: 2026-04-06 | [7 empty] | GTSB | SQ202508150543-GTSB
3986A_HU | Empire Damansara IB | DU00005948179 | Central | Selangor | 3.167639 | 101.612398 | [7 empty] | 02. Pending Access |  | TSS+AA+TI+Dismantle |  | 18G_2+0_112M. NE_3986A 18G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. FE_1391B 18G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. | MW Swap | Link existing 18G_1+0_56M , Remote Software Not Support (XMC_3 ODU). Swap existing link to 18G_2+0_112M. Site Impacted : 1587C , 3986A , 3303B , 1319B. NE_3986A 1.Install new 18G_DP_0.6M(MAC)+OMT 2.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Cretae service cross connect and EPLA. 5.All traffic migrate to new link with Port Enable GE1 for 1587C , Enable GE2 for 3986A and Enable GE3 for 3303B. 6.Decom existing MW. Ensure all traffic migrated before decom. FE_1391B 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Enable GE1 , Patching ETH cable to existing 1391B_RTN04_GE2. 6.Decom existing MW.Ensure all traffic migrated before decom. | Link existing 18G_1+0_56M , Remote Software Not Support (XMC_3 ODU). Swap existing link to 18G_2+0_112M. Site Impacted : 1587C , 3986A , 3303B , 1319B. NE_3986A 1.Install new 18G_DP_0.6M(MAC)+OMT 2.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Cretae service cross connect and EPLA. 5.All traffic migrate to new link with Port Enable GE1 for 1587C , Enable GE2 for 3986A and Enable GE3 for 3303B. 6.Decom existing MW. Ensure all traffic migrated before decom. | Link existing 18G_1+0_56M , Remote Software Not Support (XMC_3 ODU). Swap existing link to 18G_2+0_112M. Site Impacted : 1587C , 3986A , 3303B , 1319B. FE_1391B 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Enable GE1 , Patching ETH cable to existing 1391B_RTN04_GE2. 6.Decom existing MW.Ensure all traffic migrated before decom. | XMC_3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202508200554-Magicell | Magicell | SQ202508200545-Magicell // SQ202508200549-Magicell |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25082547 |  | 2025-08-26 | 2025-08-27 | Completed | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-08-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202508150527-GCI | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | CHEONG/SENG/WAH/7018000306
3025C_HU | Kg Telok Gong (REL) | DU00005948180 | Central | Selangor | 2.934969 | 101.373768 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M CA. NE_3025C 15G_DP_0.6M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Lo x1. FE_1082A 15G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Link existing 15G_2+0_28M Install parallel link 15G_4+0_28M CA. Site Impacted : 3025C. NE_3025C 1.Install new 15G_DP_0.6M(MDD). 2.Reuse existing 3025C_RTN01. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 3025C_RTN01. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA with existing MW link. 6.No link to be decom. FE_1082A 1.Install new 15G_DP_1.2M(MDD). 2.Reuse existing 1082A_RTN09. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 1082A_RTN09. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA with existing MW link. 6.No link to be decom. | Link existing 15G_2+0_28M Install parallel link 15G_4+0_28M CA. Site Impacted : 3025C. NE_3025C 1.Install new 15G_DP_0.6M(MDD). 2.Reuse existing 3025C_RTN01. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 3025C_RTN01. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA with existing MW link. 6.No link to be decom. | Link existing 15G_2+0_28M Install parallel link 15G_4+0_28M CA. Site Impacted : 3025C. FE_1082A 1.Install new 15G_DP_1.2M(MDD). 2.Reuse existing 1082A_RTN09. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 1082A_RTN09. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA with existing MW link. 6.No link to be decom. | XMC_5D | MDD | 15G | 0.6 | 1.2 | GCI | SQ202508200493-GCI | GCI | SQ202508200482-GCI // SQ202508200487-GCI | 2025-11-08 | 2025-11-07 | Completed | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-30 | 2025-10-01 | 2025-09-30 | 2025-09-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082184 |  | 2025-08-22 | 2025-08-25 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-17 | 2025-09-24 | 2025-09-17 | 2025-09-23 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-09-17 | 2025-09-24 | 2025-09-17 | 2025-09-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  | 2025-09-23 | 2025-09-17 | 2025-09-24 | 2025-09-17 | 2025-10-02 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2026-01-09: 2025-09-17; 2026-01-14: 2025-09-24; 2026-02-27: 2025-09-17; 2026-02-27: 2025-09-18 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202508150527-GCI | 2025-08-17 | 2025-08-17 | 2025-08-17 | 2025-08-17 | CHEONG/SENG/WAH/7018000306
7489B_HU_1 | Simp Kertam | DU00005955361 | Sabah | Perak | 5.430000 | 118.270400 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M_256QAM_EPLA - LINK 2 NE_7489B New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN01) under DU 7489B_HU. New XMC_5D Pro, Sub B_Lo x1. FE_7585A New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN02) under DU 7489B_HU. New XMC_5D Pro, Sub BB_Hi x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE FOR MOUNTING 1.2M ANTENNA DISH SIZE. 2.NEED TO PERFORM DU IN SEQUENCES - 1ST 7489B_HU(LINK 1) - 2ND 7489B_HU_1(LINK 2)**** Build new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2. Later, will combine new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1 and new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2 become HW MW Parallel Link 7489B-7585A, 15G_6+0_28M_256QAM_EPLA. Site Impacted : 7732B & 7493B. NE_7489B 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01) under DU 7489B_HU and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2. 4.Later, will combine new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1 and new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2 become HW MW Parallel Link 7489B-7585A, 15G_6+0_28M_256QAM_EPLA. FE_7585A 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02) under DU 7489B_HU and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2. 4.Later, will combine new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1 and new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2 become HW MW Parallel Link 7489B-7585A, 15G_6+0_28M_256QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE FOR MOUNTING 1.2M ANTENNA DISH SIZE. 2.NEED TO PERFORM DU IN SEQUENCES - 1ST 7489B_HU(LINK 1) - 2ND 7489B_HU_1(LINK 2)**** Build new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2. Later, will combine new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1 and new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2 become HW MW Parallel Link 7489B-7585A, 15G_6+0_28M_256QAM_EPLA. Site Impacted : 7732B & 7493B. NE_7489B 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01) under DU 7489B_HU and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2. 4.Later, will combine new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1 and new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2 become HW MW Parallel Link 7489B-7585A, 15G_6+0_28M_256QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE FOR MOUNTING 1.2M ANTENNA DISH SIZE. 2.NEED TO PERFORM DU IN SEQUENCES - 1ST 7489B_HU(LINK 1) - 2ND 7489B_HU_1(LINK 2)**** Build new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2. Later, will combine new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1 and new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2 become HW MW Parallel Link 7489B-7585A, 15G_6+0_28M_256QAM_EPLA. Site Impacted : 7732B & 7493B. FE_7585A 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02) under DU 7489B_HU and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2. 4.Later, will combine new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1 and new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2 become HW MW Parallel Link 7489B-7585A, 15G_6+0_28M_256QAM_EPLA. | XMC-5D Pro | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | Seri Pancar | SQ202602090132-Seri Pancar | GTSB | SQ202604100652-GTSB // SQ202604100653-GTSB |  |  | Ongoing | 2026-02-04 | 2026-02-28 | 2026-02-12 | 2026-02-12 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-06 | 2026-04-13 | 2026-04-06 | 2026-04-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031152 |  | 2026-03-12 | 2026-04-02 | Completed | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-04-02 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-07 | 2026-05-09 | 2026-04-07 |  | ABDULLAH//BIN NASIB/6000059295 | GTSB TI | [6 empty] | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-30 | 2026-04-07 | 2026-05-09 | 2026-04-07 |  | ABDULLAH//BIN NASIB/6000059295 | 2026-01-09: 2026-04-07; 2026-01-14: 2026-05-09; 2026-02-27: 2026-04-07; 2026-02-27: 2026-04-13 | [7 empty] | GTSB | SQ202508150543-GTSB | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | HSU//MYET CHAE/6799000011
1113A-1087A | Pulau Ketam | DU00003557053 | Central | Selangor | 3.018927 | 101.252870 | WK08 | FEB 25 | WK08 | FEB 25 | TI | LOS not clear | ZTE | 03. TSS Only | 20/2/2025 : Cancel proceed due to LOS block 19/2/2025 : Ground work assemble antena 6ft activity only 13/1/2025 : Digi OB - 45M 3 Legged Tower - NE site 1113A Pulau Ketam, Digi OB - 45M 4 Legged Tower - FE site 1087A Rantau Panjang | TSS |  | 13G_1.2m&1.8m_DP_2+0_28Mhz | MW Parallel Link | TSS ONLY PULAU KETAM LOS BLOCK ISSUE | [7 empty] | MTK | SQ202506100562-MTK | MTK | No PR required-Work at TSS only | 2025-06-21 | 2025-06-20 | Completed | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-20 | 2025-06-21 | 2025-06-20 | 2025-06-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-20 | 2025-06-21 | 2025-06-20 | 2025-06-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-20 | 2025-06-21 | 2025-06-20 | 2025-06-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240619AB |  | 2024-06-20 | 2024-07-18 | Completed | 2024-06-19 | 2024-06-20 | 2024-06-19 | 2024-07-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-17 | 2024-08-31 | 2024-08-17 |  | EDE//RICKYJOE BIN RAHMAT/7019000022 | Datasco TI | 2024-08-17 | 2024-08-31 | 2024-08-17 |  | EDE//RICKYJOE BIN RAHMAT/7019000022 | Datasco TI | 2024-03-27 | 2024-03-27 |  |  | Mohd wafifahmi10353358 |  |  | 2024-08-17 | 2024-08-31 | 2024-08-17 |  | EDE//RICKYJOE BIN RAHMAT/7019000022 | 2026-01-09: 2024-08-17; 2026-01-14: 2024-08-31; 2026-02-27: 2024-08-17 | [7 empty] | GCI | SQ202507080517-GCI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
S01754-7207A | S106A_S01754OD_TMNSEMPAUL2 | DU00004377360 | Sabah | Sabah | 4.463397 | 118.588153 |  |  | WK03 | JAN 25 | RFS |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 2+0 0.6m/0.6m XMC3E NE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 3) 1x18GHz 0.6m DP FE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 3) 1x18GHz 0.6m DP | MW Swap | Existing link 7064K-7207A-01_ZNIC To swap Existing 18G 1+0 112MHz to 18G 2+0 112MHz Impacted sites: S01754 Tx route before: S01754/S01754-S00501 Tx route after: S01754/S01754-7207A NE (S01754): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at new RTN01 3-ISM8 remarks: to reuse existing frequency channel for V 3) Migrate traffic to new link 4) Decom existing link FE (7207A): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at new RTN01 3-ISM8 remarks: to reuse existing frequency channel for V 3) Migrate traffic to new link. Use xD CTS LL. 4) Decom existing link | [7 empty] | AllStar | SQ202504210278-Allstar | AllStar | SQ202501210500-Allstar // SQ202504260190-Allstar | 2025-07-11 | 2025-07-09 | Completed | [8 empty] | Unassigned | Disabled |  | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-06 | 2025-05-09 | 2025-05-06 | 2025-05-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-09 | 2025-07-11 | 2025-07-09 | 2025-07-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25011375 |  | 2025-01-14 | 2025-01-15 | Completed | 2025-01-13 | 2025-01-14 | 2025-01-13 | 2025-01-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-22 | 2025-01-31 | 2025-01-22 | 2025-02-12 | ELVEN//LASIUS/8217000007 | Allstar TI | 2025-01-22 | 2025-01-31 | 2025-01-22 | 2025-02-28 | ELVEN//LASIUS/8217000007 | Allstar TI | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-01-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-20 | 2025-01-22 | 2025-01-31 | 2025-01-22 | 2025-03-12 | ELVEN//LASIUS/8217000007 | 2025-01-22 | 2025-01-31 | 2025-01-22 | 2025-02-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506050733-GTSB | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | HSU//MYET CHAE/6799000011
K00325-K00082 | K011A_K00325OD_CB_KGNAWA | DU00004377361 | Northern | Kedah | 6.116900 | 100.514100 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | SFP 1km and patch cord | MW IDU Patching | Remarks: Site Pokok Sena have 2 NE ID In xC NMS: K00082 In EPMS: K00352 Congestion at IDU-IDU connection from IDU Huawei NT05849 K00082 Pokoksena - K00325 Kgnawa GE1 to SM NT05499 GNE KgSgDurianPSena LAN4 To divert site K00899 to other port Impact site: K00899 Tx route: K00352-K00834 NE (K00325): 1) Remain existing FE (K00352): 1) Patch Huawei NT05849 GE4 (optical) to SM NT05499 LAN D (optical) 2) Divert K00899 service to new port | [7 empty] | GCI | SQ202504280464-GCI | GCI | SQ202504280751-GCI | 2025-09-27 | 2025-09-26 | Completed | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25012109 |  | 2025-01-22 | 2025-01-22 | Completed | 2025-01-21 | 2025-01-22 | 2025-01-21 | 2025-01-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | MOHD SHAHRAIN/BIN/MOHD SHKERY/6000002587 | GCI TI | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-07-06 | MOHD SHAHRAIN/BIN/MOHD SHKERY/6000002587 | GCI TI | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-20 | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-12-17 | MOHD SHAHRAIN/BIN/MOHD SHKERY/6000002587 | 2026-01-09: 2025-05-20; 2026-01-14: 2025-05-31; 2026-02-27: 2025-05-20; 2026-02-27: 2025-05-20 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
4180D-4410C | Lebuh Bandar U Utama | DU00004377362 | Northern | Perak | 4.353137 | 100.992147 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 2+0 0.6m/1.2m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 3) 1x18GHz 0.6m DP FE: 1) 1xISM8 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 3) 1x18GHz 0.6m DP | MW Swap | Existing link Huawei NT05811 (A01073-A00607) A01073 RAN off colocated with 4810D A00607 RAN off colocated with 4410C xC fiber/PTN at A00607 will be relocated to 4410C To swap Existing link Huawei 18GHz 1+0 with new Huawei link 18GHz 2+0 Impacted sites: 4180D Current Tx route: 4180D/-A01073-A00607 New Tx route: 4180D/4180D-4410C NE (4180D): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8. Channel V to reuse existing channel 3) Migrate traffic to new link remarks: BBU to use 10G port under DU 4180D (Tx Mini Project) 4) Decom existing link FE (4410C): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8. Channel V to reuse existing channel 3) Patch new IDU to xC PTN. Migrate traffic to new link remarks: To use 10G port under DU A00607 (Tx Mini Project) 4) Decom existing link | [7 empty] | GCI | SQ202503060145-GCI | GCI | SQ202503050483-GCI // SQ202504150095-GCI | 2025-11-28 | 2025-11-28 | Completed | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250220BR |  | 2025-02-21 | 2025-02-25 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-26 | 2025-03-08 | 2025-02-26 | 2025-03-03 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-26 | 2025-03-08 | 2025-02-26 | 2025-03-03 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-02-26 | 2025-03-08 | 2025-02-26 | 2025-03-10 | MOHD FAIZ BIN MD YUNUS6800000186 | 2026-01-09: 2025-02-26; 2026-01-14: 2025-03-08; 2026-02-27: 2025-02-26; 2026-02-27: 2025-02-28 |  |  | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358
Q02226_EB | Q124B_Q02226OD_TMNBANJARANSERAPI | DU00004416985 | Sarawak | Sarawak | 1.562020 | 110.224200 | [7 empty] | 06. Other Issue | 19/9/2025 : Plan to do MW IDU Relocation - Re-plan due to Cisco router down 17/9/2025 : Plan to do MW IDU Relocation - Cancel proceed 13/9/2025 : Plan to do MW IDU Relocation - Cancel proceed, team attend other site 11/9/2025 : Plan to do MW IDU Relocation - Cancel proceed due to stuck at site Q00032_EB 10/9/2025 : Plan to do MW IDU Relocation - Cancel proceed due to FE losscom 9/9/2025 : Plan to do MW IDU Relocation - cancel proceed due to shortage material | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC SM_AGS20 2+0 MW link SW03990 to xD Cabinet. - Patching xC SM_AGS20 link SW03990 to xD MW Link IDU 9458A POI Needed : No | [7 empty] | MTK | SQ202412230346-MTK | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2024-12-27 | 2024-12-23 | Completed | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-20 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-23 | 2024-12-27 | 2024-12-23 | 2024-12-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-23 | 2024-12-27 | 2024-12-23 | 2024-12-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-23 | 2024-12-27 | 2024-12-23 | 2024-12-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090876 |  | 2025-09-09 | 2025-09-09 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-09 | 2025-09-13 | 2025-09-09 | 2025-09-09 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-09-09 | 2025-09-13 |  |  | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | [7 empty] | 2025-09-09 | 2025-09-13 |  |  | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | 2026-01-09: 2025-09-09; 2026-01-14: 2025-09-13; 2026-02-27: 2025-09-09; 2026-02-27: 2025-09-09
4359B_EB | Klebang Ind RCC | DU00004416986 | Northern | Perak | 4.669093 | 101.119706 | [7 empty] | 06. Other Issue |  | TSS+TI |  |  | BBU Patching | At NE: Patching BBU to existing xD 2nd TDC LL 4359B POI Needed : No | [7 empty] | MTK | SQ202502120359-MTK | MTK | SQ202412180554-MTK | 2026-03-13 | 2026-03-12 | Completed | 2024-12-24 | 2024-12-24 | 2024-12-24 | 2024-12-24 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241217AG |  | 2024-12-18 |  | Ongoing | 2024-12-17 | 2024-12-18 | 2024-12-17 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [20 empty] | 2024-12-19 | 2024-12-31 | 2024-12-23 | 2024-12-23 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2026-01-09: 2024-12-19; 2026-01-14: 2024-12-31; 2026-02-27: 2024-12-23; 2026-02-27: 2024-12-23 | [7 empty] | GCI | SQ202507250716-GCI | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | CHEONG/SENG/WAH/7018000306
9009C_EB | Matang Malihah | DU00004416987 | Sarawak | Sarawak | 1.551796 | 110.241019 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 28/8/2025 : Cutover done 27/8/2025 : Cutover done, pending update EPMS | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | At FE: - Patching xD Huawei Mw link to MW IDU 9429A POI Needed : No | [7 empty] | Trintel | SQ202508290708-Trintel | Trintel | SQ202508250731-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-29 | 2025-09-11 | 2025-08-29 | 2025-09-11 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-25 | 2025-09-22 | 2025-09-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-26 | 2025-09-22 | 2025-09-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082699 |  | 2025-01-10 | 2025-01-11 | Completed | 2025-01-10 | 2025-01-10 | 2025-01-11 | 2025-01-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-27 | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-29 | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-28 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-09-01 | MATTHEW//ANAK ARON/6000043057 | 2026-01-09: 2025-08-20; 2026-01-14: 2025-08-20; 2026-02-27: 2025-08-20; 2026-02-27: 2025-08-27 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202509250704-GTSB | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | AB.RAHMAN//BIN MAT NOOH/6237001519
S01442_EB | S106A_S01442OD_T3_KGSGBUAYA | DU00004416988 | Sabah | Sabah | 4.469530 | 118.525280 |  |  |  | FEB 25 | In Plan | TX READINESS ISSUE |  | 06. Other Issue |  | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN910A 2+0 MW link SB02806 to xD Cabinet. - Patching xC HW_RTN910A link SB02806 to xD MW Link IDU 7627A POI Needed : Yes | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK | 2024-12-13 | 2024-12-10 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-10 | 2024-12-13 | 2024-12-10 | 2024-12-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241211CE |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2025-03-19 |  |  | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | 2025-02-25 | 2025-03-19 |  |  | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | [7 empty] | 2025-02-25 | 2025-03-19 |  |  | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | 2026-01-09: 2025-02-25; 2026-01-14: 2025-03-19
K00999_EB | PI PPR Paya Nahu | DU00004416989 | Northern | Kedah | 5.642076 | 100.512021 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC HW_NLOS MW link NT05721 to xD Cabinet. Maintain existing Route. POI Needed : No | [7 empty] | MTK | SQ202412130209-MTK | MTK | SQ202412170146-MTK // SQ202504260186-MTK // SQ202505150476-MTK | 2025-11-28 | 2025-11-27 | Completed | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-11 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24121612 |  | 2024-12-17 | 2024-12-17 | Completed | 2024-12-16 | 2024-12-17 | 2024-12-16 | 2024-12-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-13 | 2025-02-28 | 2025-02-14 | 2025-02-24 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-02-13 | 2025-02-28 | 2025-02-24 | 2025-02-24 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-02-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-02-13 | 2025-02-28 | 2025-03-07 | 2025-03-07 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2026-01-09: 2025-02-13; 2026-01-14: 2025-02-28; 2026-02-27: 2025-03-05; 2026-02-27: 2025-03-05 |  |  | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358 |  |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
B01918_EB | TNB SELAYANG | DU00004416990 | Central | Selangor | 3.253308 | 101.656107 |  | FEB 25 |  | FEB 25 | TI | EB decom/terminate | Celcom | 00. Site Out/Drop | 13/2/2025 : B01918 EB already decom/terminate 10/2/2025 : CELCOM AXIATA BERHAD - BOOM 6M - NE site B01918 TNB SELAYANG, EDOTCO (M) SDN BHD - TRIPOD 6M ROOFTOP - FE site B00263 B057B_B00263OD_TMNSLYGSEGAR | TSS |  |  | MW New Link / Reroute | . Reroute & build new MW link B01918-3434A with Huawei 23G_28MHz_1+0_0.6M_0.4KM . Dismantle Old Microwave link B01918-B00514 POI Needed : No | [7 empty] | MTK | SQ202412040242-MTK | MTK | No PR required-Work at TSS only | 2025-03-15 | 2025-03-14 | Completed | 2024-11-29 | 2024-12-07 | 2024-11-29 | 2024-12-02 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-12 | 2025-03-13 | 2025-03-12 | 2025-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-12 | 2025-03-13 | 2025-03-12 | 2025-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-14 | 2025-03-15 | 2025-03-14 | 2025-03-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24120321 |  | 2024-12-04 |  | Ongoing | 2024-12-03 | 2024-12-04 | 2024-12-03 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2024-12-09 | 2024-12-31 |  |  | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-12-09 | 2024-12-31 | 2024-12-17 |  | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | [7 empty] | 2024-12-09 | 2024-12-31 |  |  | RIDHUAN//BIN MANSOR/8225000011 | 2026-01-09: 2024-12-09; 2026-01-14: 2024-12-31 | [7 empty] | GTSB_AA | SQ202510300116-GTSB
9439A_EB | Kpg. Gita 2 MP | DU00004416991 | Sarawak | Sarawak | 1.562880 | 110.316190 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | BBU Patching | At NE: Patch 9439A BBU to xD IDIU 9439A POI Needed : No | [7 empty] | MTK | SQ202501160056-MTK | MTK | SQ202501160048-MTK // SQ202504260210-MTK | 2025-01-24 | 2025-01-20 | Completed | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-15 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-20 | 2025-01-24 | 2025-01-20 | 2025-01-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-20 | 2025-01-24 | 2025-01-20 | 2025-01-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-20 | 2025-01-24 | 2025-01-20 | 2025-01-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25011076 |  | 2025-01-10 | 2025-01-13 | Completed | 2025-01-10 | 2025-01-10 | 2025-01-11 | 2025-01-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-13 | 2025-01-31 | 2025-01-15 | 2025-01-15 | AZUWAN//BIN HAROM/8225000003 | MTK TI | 2025-01-14 | 2025-01-31 | 2025-01-14 | 2025-01-16 | AZUWAN//BIN HAROM/8225000003 | MTK TI | 2025-01-14 | 2025-01-15 | 2025-01-14 | 2025-01-15 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  | 2025-01-14 | 2025-01-13 | 2025-01-31 | 2025-01-17 | 2025-01-17 | AZUWAN//BIN HAROM/8225000003 | 2026-01-09: 2025-01-13; 2026-01-14: 2025-01-31; 2026-02-27: 2025-01-15; 2026-02-27: 2025-01-15 |  |  | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045
S01823_EB | PI KG SERUSOP | DU00004416992 | Sabah | Sabah | 6.245946 | 116.239331 |  |  |  |  | RFS |  |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC HW_NLOS MW link SB02860 to xD Cabinet. - Patching xC HW_NLOS MW link SB02860 to xD HW IDU 7365A POI Needed : Yes | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK // SQ202504260198-MTK | 2024-12-13 | 2024-12-06 | Completed | 2024-11-22 | 2024-11-29 | 2024-11-22 | 2024-11-29 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-02 | 2024-12-06 | 2024-12-02 | 2024-12-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-02 | 2024-12-06 | 2024-12-02 | 2024-12-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-06 | 2024-12-13 | 2024-12-06 | 2024-12-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241211CA |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-14 | 2024-12-14 | 2025-01-21 | 2025-01-21 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | 2025-01-07 | 2025-01-30 | 2025-01-21 | 2025-01-21 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-01-07 | 2025-01-30 | 2025-01-22 | 2025-01-22 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | 2026-01-09: 2025-01-07; 2026-01-14: 2025-01-30; 2026-02-27: 2025-01-07; 2026-02-27: 2025-01-07 |  |  | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
S00987_EB | S110C_S00987OD_T3_LADANGBELIAN | DU00004416993 | Sabah | Sabah | 4.636210 | 117.521750 |  |  |  | FEB 25 | In Plan | TX READINESS ISSUE |  | 06. Other Issue |  | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN910A 2+0 MW link SB02793 to xD Cabinet. - Patching xC HW_RTN910A 2+0 MW link SB02793 to xD HW IDU 7664B POI Needed : Yes | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK |  |  | Ongoing | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-04 | 2024-12-06 | 2024-12-04 | 2024-12-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-04 | 2024-12-06 | 2024-12-04 | 2024-12-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY241211CR |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-14 | 2024-12-14 |  |  |  | MTK TI
9337A_EB | Siol Kandis | DU00004416994 | Sarawak | Sarawak | 1.572357 | 110.360732 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 29/8/2025 : Site drop, existing already migrate from xC to xD 28/8/2025 : Plan to do BBU Patching - cancel due to not receive keys 0124: SOW changed. DO to be returned. No need to execute. | TSS+TI | L1+ATP+PAC |  | BBU Patching | At NE: Patch 9337A BBU to xD IDIU 9337A POI Needed : No | [7 empty] | Trintel | SQ202508140691-Trintel | Trintel | SQ202508140688-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-29 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250826A0 |  | 2025-01-10 | 2025-01-13 | Completed | 2025-01-10 | 2025-01-10 | 2025-01-11 | 2025-01-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-29 | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-09-02 | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-29 | SHAHARIN BIN RUSLAN6799000052 |  | 2025-08-29 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-09-02 | MATTHEW//ANAK ARON/6000043057 | 2026-01-09: 2025-08-20; 2026-01-14: 2025-08-20; 2026-02-27: 2025-08-20; 2026-02-27: 2025-08-29 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202509250704-GTSB | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | AB.RAHMAN//BIN MAT NOOH/6237001519
A00353_EB | CELCOM IPOH BRANCH | DU00004416995 | Northern | Perak | 4.598560 | 101.093960 | [7 empty] | 06. Other Issue |  | TSS |  |  | MW New Link / Reroute | . Reroute & build new MW link A00353-4546A with Huawei 23G_28MHz_1+0_0.3M_0.4KM . Patching New MW Link A00353-4546A to xC Cisco Router. . Dismantle Old Microwave link A00353-A00140 POI Needed : No | [7 empty] | MTK | SQ202412130209-MTK | MTK | SQ202412170146-MTK | 2026-01-28 | 2026-02-03 | Completed | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-11 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-02-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO | 2024-12-17 |  | Ongoing | 2024-12-16 | 2024-12-17 | 2024-12-16 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB_AA | SQ202510300144-GTSB
B01927_EB | B016M_B01927IB_OASIS_SQUARE | DU00004416996 | Central | Selangor | 3.113703 | 101.573205 | WK13 | APR 25 |  | APR 25 | TI | Pending PTW approval | ZTE | 06. Other Issue | 10/2/2025 : EDOTCO (M) - INBUILDING - NE site B01927 B016M_B01927IB_OASIS_SQUARE, Digi OB - 3M Boom - RT - FE site 3203A Oasis Ara Damansara | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | . Reroute & build new MW link B01927-3203A with Huawei 23G_28MHz_1+0_0.3M_0.2KM POI Needed : No | [7 empty] | MTK | SQ202504280387-MTK | MTK | SQ202511190715-MTK // SQ202511190823-MTK |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25020441 |  | 2025-02-05 | 2025-02-06 | Completed | 2025-02-04 | 2025-02-05 | 2025-02-04 | 2025-02-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB_AA | SQ202510300116-GTSB
S01052_EB | PI KGHAMPILAN | DU00004416997 | Sabah | Sabah | 4.659332 | 118.283258 |  |  |  | FEB 25 | RFS | DONE |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC HW_NLOS MW link SB02889 to xD Cabinet. - Patching xC HW_NLOS MW link SB02889 to xD HW IDU 7931A | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK // SQ202504260198-MTK | 2024-12-13 | 2024-12-10 | Completed | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-10 | 2024-12-13 | 2024-12-10 | 2024-12-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241211C6 |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-27 | 2025-03-08 | 2025-02-28 | 2025-02-28 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | 2025-02-27 | 2025-03-08 | 2025-02-28 | 2025-02-28 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-02-27 | 2025-02-27 | 2025-03-08 | 2025-04-09 | 2025-04-09 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | 2026-01-09: 2025-02-27; 2026-01-14: 2025-03-08; 2026-02-27: 2025-02-28; 2026-02-27: 2025-02-28 |  |  | 2025-04-23 | 2025-05-23 | 2025-04-23 | 2025-04-23 | MASDIANA//BINTI BEDIN/6801000016
Q02281_EB | SK_SG_BAGIAN | DU00004416998 | Sarawak | Sarawak | 2.848270 | 112.941120 | [7 empty] | 05. Doable |  | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN910A 4+0 MW link Q02281-Q00633 to xD Cabinet. - Patching xC HW_RTN910A MW link Q02281-Q00633 to xD IDU 9114A POI Needed : Yes | [7 empty] | MTK | SQ202412090540-MTK | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2024-11-29 | 2024-11-27 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-27 | 2024-11-29 | 2024-11-27 | 2024-11-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-27 | 2024-11-29 | 2024-11-27 | 2024-11-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-27 | 2024-11-29 | 2024-11-27 | 2024-11-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090877 |  | 2025-09-09 | 2025-10-20 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-10-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-13 | 2025-10-14 | 2025-10-13 | 2025-10-21 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-10-13 | 2025-10-14 | 2025-10-13 |  | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | [7 empty] | 2025-10-13 | 2025-10-14 | 2025-10-13 |  | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2026-01-09: 2025-10-13; 2026-01-14: 2025-10-14; 2026-02-27: 2025-10-13; 2026-02-27: 2025-10-21
S01435_EB | S110C_S01435OD_T3_KM10KALABAKANNABAWAN | DU00004416999 | Sabah | Sabah | 4.450983 | 117.398333 |  |  |  |  | Pending DO |  |  | 05. Doable |  | TSS+AA+TI+Dismantle |  | 13G_4+0_1.2/1.2_MDD_SB A 2x RTN910A 4xISM8 | MW New Link / Reroute | . Reroute & build new MW link S01435-7625A with Huawei 13G_28MHz_4+0_1.8M_9.1KM . Dismantle Old Microwave link S01435-S00227 POI Needed : Yes | Build new MW link S01435-7625A _13G_4+0_1.2/1.28MDD_XMC-5D_SB A. NE: 1.INstall new RTN910A. 2. Add new 2 ISM8 at slot 4 and 3 3. Install new 13G_XMC-5D_SB A. 4. Install antenna 13G_1.8MDD. 5.Configure 13G_4+0_1.8/1.8MDD_CA_800M 6. Dismantle mw link S01435-S00227. | Build new MW link S01435-7625A _13G_4+0_1.2/1.28MDD_XMC-5D_SB A. FE: 1. Install new RTN910A. 2.Install 2xISM8 at slot 3 and 4. 3. Install new 13G_XMC-5D_SB A. 4. Install antenna 13G_1.8MDD. 5.Configure 13G_4+0_1.8/1.8MDD_CA_800M 6. Dismantle mw link S01435-S00227. | [5 empty] | MTK | SQ202412090536-MTK | NR services | SQ202507290140-NR Services // SQ202507290144-NR Services | 2025-01-10 | 2025-01-06 | Completed | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071529 |  | 2025-07-16 | 2025-08-01 | Completed | 2025-07-15 | 2025-07-16 | 2025-07-15 | 2025-08-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB_AA | SQ202510300153-GTSB | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | HSU//MYET CHAE/6799000011
Q02372_EB | SEB SIBU REGIONAL OFFICE (SEB Sibu A) | DU00004417000 | Sarawak | Sarawak | 2.307952 | 111.862224 | [6 empty] | ZTE | 06. Other Issue |  | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | . Reroute & build new MW link Q02372-9368A with Huawei 15G_28MHz_1+0_0.6M,1.2M_4.5M . Dismantle Old Microwave link Q02372-Q00213 POI Needed : Yes | [7 empty] | MTK | SQ202412090540-MTK // SQ202412240471-MTK | MTK | SQ202501160048-MTK | 2025-01-10 | 2025-01-09 | Completed | 2024-11-22 | 2024-11-30 | 2024-11-25 | 2024-11-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-08 | 2025-01-09 | 2025-01-08 | 2025-01-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-09 | 2025-01-10 | 2025-01-09 | 2025-01-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-09 | 2025-01-10 | 2025-01-09 | 2025-01-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO | 2025-01-15 |  | Ongoing | 2025-01-14 | 2025-01-15 | 2025-01-14 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB_AA | SQ202510300154-GTSB
Q01940_EB | Q124F_Q01940OD_BORNEOSAMARIANGWATERPARK | DU00004417001 | Sarawak | Sarawak | 1.678099 | 110.309785 | [7 empty] | 00. Integrated/RFS Done | 10/9/2025 : Cutover done | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN910A 2+0 MW link SW03900 to xD Cabinet. - Patching xC HW_RTN910A link SW03900 to xD MW Link IDU 9483A POI Needed : No | [7 empty] | MTK | SQ202412230346-MTK | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2025-01-10 | 2025-01-06 | Completed | 2024-12-23 | 2024-12-23 | 2024-12-23 | 2024-12-23 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090878 |  | 2025-09-09 | 2025-09-10 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-10 | 2025-09-13 | 2025-09-10 | 2025-09-10 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-09-10 | 2025-09-13 | 2025-09-10 | 2025-09-20 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-10 | 2025-09-10 | 2025-09-13 | 2025-09-10 | 2025-09-20 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | 2026-01-09: 2025-09-10; 2026-01-14: 2025-09-13; 2026-02-27: 2025-09-10; 2026-02-27: 2025-09-10 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019
B02314_AD | RICOH Bukit Raja | DU00004417002 | Central | Selangor | 3.074543 | 101.458978 | WK16 | APR 25 | WK16 | APR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 18/4/2025 : Cutover done 10/2/2025 : CELCOM AXIATA BERHAD - INBUILDING - NE site B02314 RICOH Bukit Raja, STEALTH - 24M Lampole - FE site 1179B Bkt Raja Ind Park Apartment | TSS+TI+Dismantle | MRCF+PAC |  | MW Dismantle | MW DISMANTLE NE AND FE | MW DISMANTLE NE AND FE EXCEPT IDU | MW DISMANTLE NE AND FE EXCEPT IDU | [5 empty] | GTSB | SQ202504240787-GTSB | GTSB | SQ202504160582-GTSB // SQ202504160583-GTSB // SQ202504260131-GTSB | 2026-01-22 | 2026-01-21 | Completed | 2025-07-11 | 2025-07-25 | 2025-07-11 | 2025-07-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-11 | 2025-07-25 | 2025-07-11 | 2025-07-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-30 | 2025-07-31 | 2025-07-30 | 2025-07-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-22 | 2026-01-21 | 2026-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO | 2025-04-14 | 2025-10-27 | Completed | 2025-04-13 | 2025-04-14 | 2025-10-23 | 2025-10-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-17 | 2025-04-30 | 2025-04-17 | 2025-12-13 | PUWANESWARAN//A/L SUKUMARAN6000018484 | GTSB TI | 2025-04-17 | 2025-04-30 | 2025-04-17 | 2025-07-10 | PUWANESWARAN//A/L SUKUMARAN6000018484 | GTSB TI | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-04-17 | 2025-04-30 | 2025-04-17 | 2026-02-23 | PUWANESWARAN//A/L SUKUMARAN6000018484 | 2025-04-17 | 2025-04-30 | 2025-04-17 | 2025-04-18 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202509250626-GCI | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
7474A_EB | Kg Tumalasak | DU00004417003 | Sabah | Sabah | 4.935044 | 116.485385 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xD HW_RTN910A 3+0 MW link 7474A-7466A to xD Cabinet. - Patching xD HW_RTN910A 3+0 MW link 7474A-7466A to xC Swaped Link S01001-7465A | [7 empty] | MTK | SQ202412230337-MTK | NR services | SQ202510230962-NR Services // SQ202511030651-NR Services | 2026-04-21 | 2026-04-14 | Completed | 2024-12-19 | 2024-12-19 | 2024-12-19 | 2024-12-19 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-26 | 2024-12-27 | 2024-12-26 | 2024-12-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-26 | 2024-12-27 | 2024-12-26 | 2024-12-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-21 | 2026-04-14 | 2026-04-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100938 |  | 2025-10-10 | 2025-10-10 | Completed | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-17 | 2025-11-17 | 2025-10-17 | 2025-10-18 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-17 | 2025-11-17 | 2025-10-17 | 2025-10-18 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-14 | 2025-10-17 | 2025-11-17 | 2025-10-17 | 2025-11-14 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2026-01-09: 2025-10-17; 2026-01-14: 2025-11-17; 2026-02-27: 2025-10-17; 2026-02-27: 2025-10-17 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | MASDIANA//BINTI BEDIN/6801000016
Q01746_EB | Q140C_Q01746OD_LANANGIND2 | DU00004417004 | Sarawak | Sarawak | 2.239750 | 111.863300 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC SM_AGS20 1+0 MW link SW02809 to xD Cabinet. - Patching xC SM_AGS20 link SW02809 to xD MW Link IDU 9419B POI Needed : No | [7 empty] | MTK | SQ202412090540-MTK | MTK | SQ202504280825-MTK // SQ202504280851-MTK | 2024-11-29 | 2024-11-25 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032806 |  | 2025-03-29 | 2025-04-05 | Completed | 2025-03-28 | 2025-03-29 | 2025-03-28 | 2025-04-05 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-02 | 2025-05-31 | 2025-05-05 | 2025-05-07 | Muhammad izzuddin bin alias6000014049 | MTK TI | 2025-05-02 | 2025-05-31 | 2025-05-02 | 2025-05-07 | Muhammad izzuddin bin alias6000014049 | MTK TI | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-02 | 2025-05-31 | 2025-05-05 | 2025-05-05 | Muhammad izzuddin bin alias6000014049 | 2026-01-09: 2025-05-02; 2026-01-14: 2025-05-31; 2026-02-27: 2025-05-03; 2026-02-27: 2025-05-03 |  |  | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
S01619_EB | S098B_S01619OD_AUMKARAUMPALMESTATE | DU00004417005 | Sabah | Sabah | 4.867940 | 118.015200 |  |  |  | FEB 25 | In Plan | TX READINESS ISSUE |  | 06. Other Issue |  | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN905 2+0 MW link SB02980 to xD Cabinet. - Patching xD LL and BBU to newly Relocate xC HW_RTN905 POI Needed : No | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK | 2024-12-13 | 2024-12-06 | Completed | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-02 | 2024-12-06 | 2024-12-02 | 2024-12-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-02 | 2024-12-06 | 2024-12-02 | 2024-12-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-06 | 2024-12-13 | 2024-12-06 | 2024-12-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241211CP |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-14 | 2024-12-14 |  |  |  | MTK TI
Q00032_EB | Q124B_Q00032OD_TMSERAPI | DU00004417006 | Sarawak | Sarawak | 1.584458 | 110.193637 | [7 empty] | 00. Integrated/RFS Done | 17/9/2025 : Cutover done 11/9/2025 : Pending pointing due to waiting Vlan 10/9/2025 : Relocation done, pending patching 9/9/2025 : Plan to do MW IDU Relocation - cancel proceed due to shortage material | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN910A 2+0 MW link SW03969 to xD Cabinet. - Patching xC HW_RTN910A link SW03969 to xD MW Link IDU 9028B POI Needed : No | [7 empty] | MTK | SQ202412180531-MTK | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2024-12-20 | 2024-12-18 | Completed | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-12-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090879 |  | 2025-09-09 | 2025-09-10 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-10 | 2025-09-13 | 2025-09-10 | 2025-09-10 | MAMORA AGAM ANAK THOMAS7667000042 | Trintel TI | 2025-09-10 | 2025-09-13 | 2025-09-10 | 2025-09-20 | MAMORA AGAM ANAK THOMAS7667000042 | Trintel TI | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-17 | 2025-09-10 | 2025-09-13 | 2025-09-10 | 2025-09-24 | MAMORA AGAM ANAK THOMAS7667000042 | 2026-01-09: 2025-09-10; 2026-01-14: 2025-09-13; 2026-02-27: 2025-09-10; 2026-02-27: 2025-09-10 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019
S01001_EB | S099A_S01001OD_T3_KGMATIKU | DU00004417007 | Sabah | Sabah | 4.838370 | 116.499404 |  |  |  |  | Pending DO |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW New Link / Reroute | . Reroute & build new MW link S01001-7465A with Huawei 13G_28MHz_4+0_1.2M_6.6KM . Dismantle Old Microwave link S01001-S01002 POI Needed : Yes | [7 empty] | MTK | SQ202412230337-MTK | NR services | SQ202507300478-NR Services // SQ202507300483-NR Services | 2025-01-10 | 2025-01-06 | Completed | 2024-12-19 | 2024-12-19 | 2024-12-19 | 2024-12-19 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-31 | 2025-01-03 | 2024-12-31 | 2024-12-31 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-31 | 2025-01-03 | 2024-12-31 | 2024-12-31 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071528 |  | 2025-07-16 | 2025-07-28 | Completed | 2025-07-15 | 2025-07-16 | 2025-07-15 | 2025-07-28 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-27 | 2025-08-27 | 2025-07-27 | 2025-07-29 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-07-27 | 2025-08-27 | 2025-07-27 | 2025-08-25 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-30 | 2025-07-27 | 2025-08-27 | 2025-07-27 | 2025-08-23 | RALPH O'BRYAN HILARY7167000030 | 2025-07-27 | 2025-08-27 | 2025-07-27 | 2025-07-29 | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | tseping//wang/6819000006 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
9065R_EB | T3_0342 - KG LUNDU | DU00004417008 | Sarawak | Sarawak | 1.698610 | 110.076442 | [6 empty] | ZTE | 06. Other Issue | 23/9/2025 : Plan to do MW IDU Relocation - Hold due to losscom | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC SM_AGS20 1+0 MW link SW02698 to xD Cabinet. - Patching xD LL and BBU 9031B to xC IDU SW02698 POI Needed : Yes | [7 empty] | Trintel | SQ202509241037-Trintel | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2026-01-22 | 2026-01-15 | Completed | 2025-09-25 | 2025-11-06 | 2025-09-25 | 2025-11-06 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090880 |  | 2025-09-09 |  | Ongoing | 2025-09-08 | 2025-09-09 | 2025-09-08 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202511040438-GTSB
S01814_EB | PI KAMPUNG BUGAYA | DU00004417009 | Sabah | Sabah | 4.491900 | 118.560115 |  |  |  | FEB 25 | RFS | TI DONE |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC HW_NLOS MW link SB02824 to xD Cabinet. - Patching xC HW_NLOS MW link SB02824 to xD HW IDU 7627A POI Needed : Yes | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK // SQ202504260198-MTK | 2024-12-13 | 2024-12-12 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-27 | 2024-11-29 | 2024-11-27 | 2024-11-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-27 | 2024-11-29 | 2024-11-27 | 2024-11-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241211C8 |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2025-03-19 | 2025-02-25 | 2025-02-25 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | 2025-02-25 | 2025-03-19 | 2025-02-25 | 2025-02-26 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-25 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-02-25 | 2025-03-19 | 2025-04-09 | 2025-04-09 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | 2026-01-09: 2025-02-25; 2026-01-14: 2025-03-19; 2026-02-27: 2025-02-26; 2026-02-27: 2025-02-26 |  |  | 2025-04-23 | 2025-05-23 | 2025-04-23 | 2025-04-23 | MASDIANA//BINTI BEDIN/6801000016
S01828_EB | PI BATU PAYUNG | DU00004417010 | Sabah | Sabah | 4.224361 | 118.001083 |  |  |  | FEB 25 | In Plan | TX READINESS ISSUE |  | 06. Other Issue |  | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC HW_NLOS MW link SB02864 to xD Cabinet. - Patching xC HW_NLOS MW link SB02864 to xD HW IDU 7966A POI Needed : Yes | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK | 2024-12-20 | 2024-12-18 | Completed | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241211CC |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-15 | 2025-01-31 |  |  | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | 2025-01-15 | 2025-01-31 |  |  | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | [7 empty] | 2025-01-15 | 2025-01-31 |  |  | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | 2026-01-09: 2025-01-15; 2026-01-14: 2025-01-31; 2026-02-27: 2025-01-16; 2026-02-27: 2025-01-16
Q00177_EB | Q140C_Q00177OD_BKTLAN | DU00004417011 | Sarawak | Sarawak | 2.245511 | 111.798235 | [7 empty] | 05. Doable |  | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC SM_AGS20 2+0 MW link SW02977 to xD Cabinet. - Patching xC SM_AGS20 link SW02977 to xD MW Link IDU 9385B POI Needed : No | [7 empty] | MTK | SQ202412090540-MTK | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2024-11-29 | 2024-11-27 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-27 | 2024-11-29 | 2024-11-27 | 2024-11-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-27 | 2024-11-29 | 2024-11-27 | 2024-11-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-27 | 2024-11-29 | 2024-11-27 | 2024-11-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032804 |  | 2025-03-29 | 2025-04-05 | Completed | 2025-03-28 | 2025-03-29 | 2025-03-28 | 2025-04-05 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-29 | 2025-05-22 |  |  | Muhammad izzuddin bin alias6000014049 | MTK TI | 2025-04-29 | 2025-05-22 |  |  | Muhammad izzuddin bin alias6000014049 | MTK TI | [7 empty] | 2025-04-29 | 2025-05-22 |  |  | Muhammad izzuddin bin alias6000014049 | 2026-01-09: 2025-04-29; 2026-01-14: 2025-05-22
Q02082_EB | Q144A_Q02082OD_T3_JLNTATAUSANGAN | DU00004417012 | Sarawak | Sarawak | 2.853330 | 112.846389 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC SM_AGS20 1+0 MW link SW03226 to xD Cabinet. - Patching xC SM_AGS20 link SW03226 to xD IDU 9114A POI Needed : Yes | [7 empty] | MTK | SQ202412100100-MTK | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2024-12-13 | 2024-12-06 | Completed | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-05 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-04 | 2024-12-06 | 2024-12-04 | 2024-12-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-04 | 2024-12-06 | 2024-12-04 | 2024-12-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-06 | 2024-12-13 | 2024-12-06 | 2024-12-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090882 |  | 2025-09-09 | 2025-10-20 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-10-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-13 | 2025-10-14 | 2025-10-13 | 2025-10-21 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-10-13 | 2025-10-14 | 2025-10-13 | 2025-11-11 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-13 | 2025-11-15 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2026-01-09: 2025-10-13; 2026-01-14: 2025-10-14; 2026-02-27: 2025-10-13; 2026-02-27: 2025-10-21 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019
9042R_EB | T3_0334 - KG SRIKANDUNG | DU00004417013 | Sarawak | Sarawak | 1.642969 | 110.164219 | [6 empty] | ZTE | 06. Other Issue | 23/9/2025 : Plan to do MW IDU Relocation - Hold due to losscom and RSL-96 | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC SM_AGS20 1+0 MW link SW02670 to xD Cabinet. - Patching xD LL and BBU 9465A to xC IDU SW02670 POI Needed : Yes | [7 empty] | Trintel | SQ202509241037-Trintel | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2025-11-14 | 2025-11-07 | Completed | 2025-09-25 | 2025-11-06 | 2025-09-25 | 2025-11-06 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-24 | 2025-10-22 | 2025-10-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-14 | 2025-11-07 | 2025-11-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-14 | 2025-11-07 | 2025-11-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090883 |  | 2025-09-09 |  | Ongoing | 2025-09-08 | 2025-09-09 | 2025-09-08 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202511040438-GTSB
Q01838_EB | UOB KUCHING | DU00004417014 | Sarawak | Sarawak | 1.551458 | 110.372030 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN910 1+0 MW link SW02909 to xD Cabinet. - PatchxD LL and BBU 9454A to xC MW Link SW02909 POI Needed : Yes | [7 empty] | MTK | SQ202412130211-MTK | MTK | SQ202412170149-MTK // SQ202504260210-MTK // SQ202511050243-MTK | 2024-12-13 | 2024-12-12 | Completed | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-11 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2024-12-26 | 2024-12-31 | Completed | 2024-12-26 | 2024-12-26 | 2024-12-31 | 2024-12-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 | MOHD FADZILLAH BIN TARMIJI8225000017 |  | 2025-01-03 | 2025-01-20 | 2025-01-06 | 2025-01-07 | AZUWAN//BIN HAROM/8225000003 | MTK TI | 2025-01-07 | 2025-01-07 | 2025-01-07 | 2025-01-07 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-01-03 | 2025-01-20 | 2025-01-06 | 2025-01-10 | AZUWAN//BIN HAROM/8225000003 | 2026-01-09: 2025-01-03; 2026-01-14: 2025-01-20; 2026-02-27: 2025-01-05; 2026-02-27: 2025-01-05 |  |  | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045
Q01626_EB | QS50243_4_1-RHGEMAT | DU00004417015 | Sarawak | Sarawak | 3.134128 | 112.982640 | [6 empty] | ZTE | 05. Doable |  | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN905 2+0 MW link SW04040 to xD Cabinet. - Patching xC HW_RTN905 link SW04040 to xD MW Link IDU 9110A POI Needed : No | [7 empty] | MTK | SQ202412090540-MTK | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-27 | 2024-11-29 | 2024-11-27 | 2024-11-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-27 | 2024-11-29 | 2024-11-27 | 2024-11-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032807 |  | 2025-03-29 | 2025-04-05 | Completed | 2025-03-28 | 2025-03-29 | 2025-03-28 | 2025-04-05 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed
S01445_EB | KAMPUNG_PAKALANGAN | DU00004417016 | Sabah | Sabah | 4.375600 | 118.560100 |  |  |  | FEB 25 | In Plan | TX READINESS ISSUE |  | 06. Other Issue |  | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN950A 4+0 MW link SB02728 to xD Cabinet. - Patching xC HW_RTN950A link SB02728 to xD MW Link IDU 7626B POI Needed : Yes | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK | 2024-12-13 | 2024-12-10 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-10 | 2024-12-13 | 2024-12-10 | 2024-12-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241211CH |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-14 | 2024-12-14 |  |  |  | MTK TI
9471A_EB | Sri Matang | DU00004417017 | Sarawak | Sarawak | 1.559216 | 110.299697 |  |  |  | AUG 25 |  |  |  | 03. TSS Only | 22/8/2025 : Site drop, SOW change to LL upgrade 0124: SOW changed. DO to be returned. No need to execute. | TSS+TI |  |  | BBU Patching | At NE: Patch 9471A BBU to xD IDIU 9471A POI Needed : No | [7 empty] | MTK | SQ202501140162-MTK | Trintel | No PR required-Work at TSS only | 2025-01-24 | 2025-01-22 | Completed | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | MOHD FADZILLAH BIN TARMIJI8225000017 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-22 | 2025-01-24 | 2025-01-22 | 2025-01-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-22 | 2025-01-24 | 2025-01-22 | 2025-01-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-22 | 2025-01-24 | 2025-01-22 | 2025-01-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081455 |  | 2025-01-10 | 2025-01-13 | Completed | 2025-01-10 | 2025-01-10 | 2025-01-11 | 2025-01-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 |  | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-08-20 | 2025-08-20 | 2025-08-20 |  | MATTHEW//ANAK ARON/6000043057 | Trintel TI | [7 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  | MATTHEW//ANAK ARON/6000043057 | 2026-01-09: 2025-08-20; 2026-01-14: 2025-08-20; 2026-02-27: 2025-08-20
S00650_EB | KGTGKAPOR | DU00004417018 | Sabah | Sabah | 4.519887 | 118.533399 |  |  |  | FEB 25 | RFS | TI DONE |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN905 1+0 MW link SB02697 to xD Cabinet. - Patching xC HW_RTN905 link SB02697 to xD MW Link IDU 7627A POI Needed : No | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK // SQ202504260198-MTK | 2024-12-13 | 2024-12-10 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-10 | 2024-12-13 | 2024-12-10 | 2024-12-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241211CJ |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-14 | 2025-02-26 | 2025-02-26 | 2025-02-26 | AHMAD//SHAFIQ BIN ASPAR/6801000041 | MTK TI | 2025-02-26 | 2025-03-31 | 2025-02-26 | 2025-02-26 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-02-26 | 2025-02-26 | 2025-03-31 | 2025-02-26 | 2025-03-05 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | 2026-01-09: 2025-02-26; 2026-01-14: 2025-03-31; 2026-02-27: 2025-02-26; 2026-02-27: 2025-03-05 |  |  | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
Q01421_EB | Q140B_Q01421OD_RAMOJLNRANTAUPJGSBW | DU00004417019 | Sarawak | Sarawak | 2.386700 | 111.865700 | [7 empty] | 03. TSS Only | 4/9/2025 : Task done under DU Q01421-9375B | TSS+TI |  |  | MW IDU Relocation | Work overlapping with HU Q01421-9375B. Survey done, Drop for TI | [7 empty] | MTK | SQ202412090540-MTK | MTK | No PR required-Work at TSS only | 2025-01-10 | 2025-01-08 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-08 | 2025-01-10 | 2025-01-08 | 2025-01-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-08 | 2025-01-10 | 2025-01-08 | 2025-01-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-08 | 2025-01-10 | 2025-01-08 | 2025-01-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032803 |  | 2025-03-29 | 2025-04-05 | Completed | 2025-03-28 | 2025-03-29 | 2025-03-28 | 2025-04-05 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-05 | 2025-05-31 |  |  | Muhammad izzuddin bin alias6000014049 | MTK TI | 2025-05-05 | 2025-05-31 |  |  | Muhammad izzuddin bin alias6000014049 | MTK TI | [7 empty] | 2025-05-05 | 2025-05-31 |  |  | Muhammad izzuddin bin alias6000014049 | 2026-01-09: 2025-05-05; 2026-01-14: 2025-05-31
Q01381_EB | Q124B_Q01381OD_TMNKOMPODIM | DU00004417020 | Sarawak | Sarawak | 1.593636 | 110.274400 | [7 empty] | 00. Integrated/RFS Done | 19/9/2025 : Plan to do MW IDU Relocation - Re-plan due to FE site vandalism 17/9/2025 : Plan to do MW IDU Relocation - Cancel proceed 13/9/2025 : Plan to do MW IDU Relocation - Cancel proceed, team attend other site 11/9/2025 : Plan to do MW IDU Relocation - Cancel proceed due to stuck at site Q00032_EB 10/9/2025 : Plan to do MW IDU Relocation - Cancel proceed due to stuck at site Q00032_EB 9/9/2025 : Plan to do MW IDU Relocation - cancel proceed due to shortage material | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC SM_AGS20 1+0 MW link SW03010 to xD Cabinet. - Patching xC SM_AGS20 link SW03010 to xD MW Link IDU 9458A POI Needed : No | [7 empty] | MTK | SQ202412230346-MTK | Trintel | SQ202509241016-Trintel // SQ202509241029-Trintel | 2024-12-27 | 2024-12-23 | Completed | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-20 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-23 | 2024-12-27 | 2024-12-23 | 2024-12-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-23 | 2024-12-27 | 2024-12-23 | 2024-12-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-23 | 2024-12-27 | 2024-12-23 | 2024-12-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090884 |  | 2025-09-09 | 2025-09-09 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-09 | 2025-09-13 | 2025-09-09 | 2025-09-09 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-09-09 | 2025-09-13 | 2025-09-09 | 2025-11-06 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-09-09 | 2025-09-13 | 2025-09-09 | 2025-11-05 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | 2026-01-09: 2025-09-09; 2026-01-14: 2025-09-13; 2026-02-27: 2025-09-09; 2026-02-27: 2025-09-09 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019
9383B_EB | Taman Harmoni MP | DU00004417021 | Sarawak | Sarawak | 2.295080 | 111.822887 |  |  |  | AUG 25 |  |  |  | 00. Site Out/Drop | 20/8/2025 : Site drop due to duplicate with 9383B_PostMOCN. BBU already repatch back to xD LL | TSS+TI |  |  | BBU Patching | At NE: Patch 9383B BBU to xD IDU 9383B POI Needed : No | [7 empty] | Trintel | SQ202510290902-Trintel | Trintel | No PR required-Site drop/cancel | 2025-09-26 | 2025-09-26 | Completed | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-26 | 2025-09-23 | 2025-09-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-26 | 2025-09-23 | 2025-09-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081382 |  | 2025-08-14 | 2025-08-30 | Completed | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-30 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-19 | 2025-08-19 | 2025-08-19 |  | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | Trintel TI | 2025-08-19 | 2025-08-19 | 2025-08-19 |  | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | Trintel TI | [7 empty] | 2025-08-19 | 2025-08-19 | 2025-08-19 |  | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | 2026-01-09: 2025-08-19; 2026-01-14: 2025-08-19; 2026-02-27: 2025-08-19; 2026-02-27: 2025-08-20 | [7 empty] | GTSB | SQ202509250704-GTSB | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | AB.RAHMAN//BIN MAT NOOH/6237001519
9069B_EB | TM Matang Jaya | DU00004417022 | Sarawak | Sarawak | 1.582199 | 110.304100 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 10/9/2025 : Cutover done, pending declare 9/9/2025 : Plan to do BBU Patching - cancel proceed due to keys issue 27/8/2025 : Plan to do BBU Patching - cancel proceed due to stuck at site 9009C_EB | TSS+TI | L1+ATP+PAC |  | BBU Patching | At NE: Patch 9069B BBU to xD IDIU 9069B POI Needed : No | [7 empty] | Trintel | SQ202509241037-Trintel | Trintel | SQ202509110859-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-09-09 | 2025-09-10 | 2025-09-09 | 2025-09-10 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-17 | 2025-09-19 | 2025-09-17 | 2025-09-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-17 | 2025-09-19 | 2025-09-17 | 2025-09-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250826A1 |  | 2025-01-10 | 2025-01-13 | Completed | 2025-01-10 | 2025-01-10 | 2025-01-11 | 2025-01-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-09-10 | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-09-13 | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-09-18 | MATTHEW//ANAK ARON/6000043057 | 2026-01-09: 2025-08-25; 2026-01-14: 2025-08-25; 2026-02-27: 2025-08-25; 2026-02-27: 2025-09-10 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202509250704-GTSB | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | AB.RAHMAN//BIN MAT NOOH/6237001519
S01448_EB | PJ_NAGUS_ESTATE | DU00004417024 | Sabah | Sabah | 4.361230 | 118.392280 |  |  |  | FEB 25 | In Plan | TX READINESS ISSUE |  | 06. Other Issue |  | TSS+TI |  |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN910A 2+0 MW link SB02732 to xD Cabinet. - Patching xC HW_RTN910A link SB02732 to xD MW Link IDU 7627A POI Needed : Yes | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK | 2024-12-13 | 2024-12-11 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-29 | 2024-11-26 | 2024-11-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-29 | 2024-11-26 | 2024-11-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-11 | 2024-12-13 | 2024-12-11 | 2024-12-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241211CN |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-14 | 2024-12-14 |  |  |  | MTK TI
S01452_EB | S106A_S01452OD_T3_KGTAMPIKAPOR | DU00004417025 | Sabah | Sabah | 4.557730 | 118.470040 |  |  |  | FEB 25 | RFS | TI DONE |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN910A 2+0 MW link SB02732 to xD Cabinet. - Patching xC HW_RTN910A link SB02732 to xD MW Link IDU 7627A POI Needed : Yes | [7 empty] | MTK | SQ202412090536-MTK | MTK | SQ202412310404-MTK // SQ202504260198-MTK | 2024-12-13 | 2024-12-10 | Completed | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-10 | 2024-12-13 | 2024-12-10 | 2024-12-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241211CL |  | 2024-12-13 | 2024-12-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-14 | 2025-02-26 | 2025-02-26 | 2025-02-26 | AHMAD//SHAFIQ BIN ASPAR/6801000041 | MTK TI | 2025-02-26 | 2025-03-31 | 2025-02-26 | 2025-02-26 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | MTK TI | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-02-26 | 2025-02-26 | 2025-03-31 | 2025-02-26 | 2025-03-05 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | 2026-01-09: 2025-02-26; 2026-01-14: 2025-03-31; 2026-02-27: 2025-02-26; 2026-02-27: 2025-03-05 |  |  | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
Q01477_EB | Q124B_Q01477OD_SCRIVEREDGEKCH | DU00004417026 | Sarawak | Sarawak | 1.558380 | 110.324055 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_56M_1024QAM NE_Q01477 New 23G_0.6M(MAC)+OMT x1. New RTN910AF(RTN01). New XMC_3E, Sub A_Lo x1. FE_9441A New 23G_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01). New ISM8 x1. New XMC_3E, Sub A_Hi x1. | MW New Link / Reroute | **IMPORTANT NOTE: NEED TO PERFORM POI LAYER 2 FROM XD TO XC** Existing HW MW Link Q01477-Q00061, 18G_1+0_56MHZ_1024QAM. Install new HW MW Link Q01477-9441A, 23G_1+0_56MHZ_1024QAM. Later, decom existing HW MW Link Q01477-Q00061, 23G_1+0_56MHZ_1024QAM. Site Impacted : Q01477. NE_Q01477 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching EB Traffic to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic Q01477 via new HW MW Link Q01477-9441A, 23G_1+0_56MHZ_1024QAM. 8.Decom existing HW MW Link Q01477-Q00061, 18G_1+0_56MHZ_1024QAM. FE_9441A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01). 3.Insert new ISM8 into slot 03 of existing RTN910A(RTN01). 4.Install new XMC_3E, Sub A_Hi x1. Configure it. 5.Request new xD vlan dcn and vlan services. 6.Migrate traffic Q01477 via existing IBeam port at CP 9999A in which similar with existing traffics such as 9441A, 9425A & 9002M. 7.Decom existing HW MW Link Q01477-Q00061, 18G_1+0_56MHZ_1024QAM. | **IMPORTANT NOTE: NEED TO PERFORM POI LAYER 2 FROM XD TO XC** Existing HW MW Link Q01477-Q00061, 18G_1+0_56MHZ_1024QAM. Install new HW MW Link Q01477-9441A, 23G_1+0_56MHZ_1024QAM. Later, decom existing HW MW Link Q01477-Q00061, 18G_1+0_56MHZ_1024QAM. Site Impacted : Q01477. NE_Q01477 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching EB Traffic to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic Q01477 via new HW MW Link Q01477-9441A, 23G_1+0_56MHZ_1024QAM. 8.Decom existing HW MW Link Q01477-Q00061, 18G_1+0_56MHZ_1024QAM. | **IMPORTANT NOTE: NEED TO PERFORM POI LAYER 2 FROM XD TO XC** Existing HW MW Link Q01477-Q00061, 18G_1+0_56MHZ_1024QAM. Install new HW MW Link Q01477-9441A, 23G_1+0_56MHZ_1024QAM. Later, decom existing HW MW Link Q01477-Q00061, 18G_1+0_56MHZ_1024QAM. Site Impacted : Q01477. FE_9441A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01). 3.Insert new ISM8 into slot 03 of existing RTN910A(RTN01). 4.Install new XMC_3E, Sub A_Hi x1. Configure it. 5.Request new xD vlan dcn and vlan services. 6.Migrate traffic Q01477 via existing IBeam port at CP 9999A in which similar with existing traffics such as 9441A, 9425A & 9002M. 7.Decom existing HW MW Link Q01477-Q00061, 18G_1+0_56MHZ_1024QAM. | XMC_3E | MAC | 23G | 23G_0.6M(MAC) x1. | 23G_0.6M(MAC) x1. | MTK | SQ202502120369-MTK | Trintel | SQ202508070591-Trintel // SQ202508070599-Trintel | 2025-07-11 | 2025-07-07 | Completed | 2024-12-30 | 2024-12-30 | 2024-12-30 | 2024-12-30 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-30 | 2025-07-04 | 2025-06-30 | 2025-06-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-29 | 2025-07-04 | 2025-06-30 | 2025-06-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25101454 |  | 2025-10-15 | 2025-10-16 | Completed | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-20 | JERRY SONLEY SALI7667000071 | Trintel TI | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2026-03-10 | JERRY SONLEY SALI7667000071 | Trintel TI | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-25 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2026-03-26 | JERRY SONLEY SALI7667000071 | 2026-01-09: 2025-10-16; 2026-01-14: 2025-10-16; 2026-02-27: 2025-10-16; 2026-02-27: 2025-10-17 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507080651-GTSB | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | AB.RAHMAN//BIN MAT NOOH/6237001519
4597B_IPR | Desa Sri Iskandar RDC | DU00006055036 | Northern | Perak | 4.358610 | 100.937000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1. 1G SFP Module 40KM x1 2. Fiber Patch Cord ( LC - E2K ) x 2 pairs | IDU-IPRAN | Upgrade IDU Fiber 4597B-fiber-4734A from 1+0 to 2+0 LAG Impact sites: 4597B,4724D,4742D NE (4597B): 1) Install 1G SFP optical 40km at RTN01 GE6 2) Patch to second fiber core at ODF (refer port number in OPM report) 3) Create LAG FE (4734A): 1) Patch to second fiber core at ODF (refer port number in OPM report) 2) Create LAG | Upgrade IDU Fiber 4597B-fiber-4734A from 1+0 to 2+0 LAG Impact sites: 4597B,4724D,4742D NE (4597B): 1) Install 1G SFP optical 40km at RTN01 GE6 2) Patch to second fiber core at ODF (refer port number in OPM report) 3) Create LAG | Upgrade IDU Fiber 4597B-fiber-4734A from 1+0 to 2+0 LAG Impact sites: 4597B,4724D,4742D FE (4734A): 1) Patch to second fiber core at ODF (refer port number in OPM report) 2) Create LAG | [5 empty] | GCI | SQ202509300138-GCI | GCI | SQ202510090314-GCI | 2025-11-29 | 2025-11-28 | Completed | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100121 |  | 2025-10-02 | 2025-10-04 | Completed | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-04 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-16 | 2025-10-19 | 2025-10-16 | 2025-10-28 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-10-16 | 2025-10-19 | 2025-10-16 | 2025-12-05 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-05 | 2025-10-16 | 2025-10-19 | 2025-10-16 | 2025-12-05 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2026-01-09: 2025-10-16; 2026-01-14: 2025-10-19; 2026-02-27: 2025-10-16; 2026-02-27: 2025-12-05 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | CHEONG/SENG/WAH/7018000306
4008B_AD_1 | Farlim | DU00006092472 | Northern | Penang | 5.395875 | 100.289201 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_4008B New 23G_DP_0.3M(MAC)+OMT x1. New RTN910A(RTN01). New XMC_3E, Sub B_Lo x1. New CAT6 cable with suitable length x1. FE_4307C/P00580 New 23G_DP_0.3M(MAC)+OMT x1. New RTN910A(RTN01). New XMC_3E, Sub B_Hi x1. New Huawei Fiber SFP Module with suitable type x1.(Mandatory to check at site for patching IDU to PTN/Cisco) New Fiber Patch Cord with suitable type and length.(Required if existing patch cord from BBU 4307C to PTN/Cisco not suitable to use) New CAT6 cable with suitable length x1.(Required if existing BBU 4307C need to patching to IDU using electrical) | MW New Link / Reroute | Existing HW MW Link 4008B-4876B, 23G_1+0_56M_512QAM_450M. Install new HW MW Link 4008B-4307C, 23G_1+0_112M_512QAM_900M. Later, decom existing HW MW Link 4008B-4876B, 23G_1+0_56M_512QAM_450M. Site Impacted : 4008B & 4307C. NE_4008B 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub B_Lo x1. Configure it. 4.Build new HW MW Link 4008B-4307C, 23G_1+0_112M_512QAM_900M. 5.Enable port 8-EM6-1 of new RTN910A(RTN01). 6.Patching Traffic to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 7.Request new xC Vlan DCN & new Vlan services from ZTE IPRAN Team. 8.Migrate RAN Traffic to new MW Link 23G_1+0_112M_512QAM_900M. 9.Later, decom existing HW MW Link 4008B-4876B, 23G_1+0_56M_512QAM_450M. FE_4307C/P00580 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub B_Hi x1. Configure it. 4.Please verify at site whether existing BBU 4307C connected to PTN/Cisco at P00580 using Fiber or Electrical. If Fiber, please follow step below. 5.Enable port 8-EM6-1 of new RTN910A(RTN01). 6.Enable port 8-EM6-5 of new RTN910A(RTN01) and insert Fiber SFP Module with suitable type. 7.Disconnect existing Fiber patch cord at BBU 4307C and patching PTN/Cisco(existing port Gi 0/0/3) to port 8-EM6-5 of new RTN910A(RTN01). 8.Ensure BBU 4307C using electrical port and patching CAT6 cable from BBU 4307C to port 8-EM6-1 of new RTN910A(RTN01). 9.Request new xC Vlan DCN & new Vlan services for 4008B from ZTE IPRAN Team. 10.RAN 4307C already migrate to xC P00580 previously and no need to request Vlan services(just reuse). 11.Migrate RAN Traffic 4008B to xC PTN/Cisco. 12.Later, decom existing HW MW Link 4008B-4876B, 23G_1+0_56M_512QAM_450M. | Existing HW MW Link 4008B-4876B, 23G_1+0_56M_512QAM_450M. Install new HW MW Link 4008B-4307C, 23G_1+0_112M_512QAM_900M. Later, decom existing HW MW Link 4008B-4876B, 23G_1+0_56M_512QAM_450M. Site Impacted : 4008B & 4307C. NE_4008B 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub B_Lo x1. Configure it. 4.Build new HW MW Link 4008B-4307C, 23G_1+0_112M_512QAM_900M. 5.Enable port 8-EM6-1 of new RTN910A(RTN01). 6.Patching Traffic to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 7.Request new xC Vlan DCN & new Vlan services from ZTE IPRAN Team. 8.Migrate RAN Traffic to new MW Link 23G_1+0_112M_512QAM_900M. 9.Later, decom existing HW MW Link 4008B-4876B, 23G_1+0_56M_512QAM_450M. | Existing HW MW Link 4008B-4876B, 23G_1+0_56M_512QAM_450M. Install new HW MW Link 4008B-4307C, 23G_1+0_112M_512QAM_900M. Later, decom existing HW MW Link 4008B-4876B, 23G_1+0_56M_512QAM_450M. Site Impacted : 4008B & 4307C. NE_4008B 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub B_Lo x1. Configure it. 4.Build new HW MW Link 4008B-4307C, 23G_1+0_112M_512QAM_900M. 5.Enable port 8-EM6-1 of new RTN910A(RTN01). 6.Patching Traffic to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 7.Request new xC Vlan DCN & new Vlan services from ZTE IPRAN Team. 8.Migrate RAN Traffic to new MW Link 23G_1+0_112M_512QAM_900M. 9.Later, decom existing HW MW Link 4008B-4876B, 23G_1+0_56M_512QAM_450M. | XMC_3E | MAC | 23G | 23G_0.3M(MAC)+OMT x1 | 23G_0.3M(MAC)+OMT x1 | GTSB | SQ202509230219-GTSB // SQ202511110798-GTSB | GTSB | SQ202509230182-GTSB // SQ202509230199-GTSB | 2025-12-23 | 2025-12-16 | Completed | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-07 | 2025-11-14 | 2025-11-07 | 2025-11-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092695 |  | 2025-09-27 | 2025-09-30 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-13 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-13 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-03 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-13 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-01 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | NG HONG JIE7018000036 | Logistic Team | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202509260807-GTSB
7980B_IPR_1 | Pekan Nabalu | DU00006092473 | Sabah | Sabah | 6.036541 | 116.455593 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 1. RTN910A x1. 2.10G SFP Module x2. 3. ISM8 x2. 5. Fiber patch cord x 2 pairs | MW Hardware Upgrade | Site affected : 7766B , 7355B , 7343B , 7778B , 7980B , 7299R. NE_7980B_RTN01. 1.Hardware upgrade new RTN910A , due to existing 7980B_RTN01 not support 10G port.(RTN no provide by OPS team). 2.Install new 10G SFP Module at new RTN910A_GE3.Fiber Patch cord patching to 7980B_RTN02. 3.Install new 10G SFP Module at existing 7980B_RTN02_GE4.Fiber patch cord patching to new RTN910A 4.Existing LAN cable 7980B_RTN02_GE4 , change to GE5 (1G) interconnect to 7980A_RTN03_GE5(1G). 5.Install new RTN910A , 7_ISM8-1+0 to support 7778B child site. (RTN no provide by OPS team.). 6.Install new 3_ISM8-2+0 and 4_SIM8-2+0 into new RTN910A to support 7766B & 7355B child sites. 7.Disconnect existing LAN cable and disable unused interface ports. 8.Create cross connect and entire traffic migrate to new GE port and new RTN910A. 9.Decom existing IDU only. | Site affected : 7766B , 7355B , 7343B , 7778B , 7980B , 7299R. NE_7980B_RTN01. 1.Hardware upgrade new RTN910A , due to existing 7980B_RTN01 not support 10G port.(RTN no provide by OPS team). 2.Install new 10G SFP Module at new RTN910A_GE3.Fiber Patch cord patching to 7980B_RTN02. 3.Install new 10G SFP Module at existing 7980B_RTN02_GE4.Fiber patch cord patching to new RTN910A 4.Existing LAN cable 7980B_RTN02_GE4 , change to GE5 (1G) interconnect to 7980A_RTN03_GE5(1G). 5.Install new RTN910A , 7_ISM8-1+0 to support 7778B child site. (RTN no provide by OPS team.). 6.Install new 3_ISM8-2+0 and 4_SIM8-2+0 into new RTN910A to support 7766B & 7355B child sites. 7.Disconnect existing LAN cable and disable unused interface ports. 8.Create cross connect and entire traffic migrate to new GE port and new RTN910A. 9.Decom existing IDU only. | [6 empty] | NR services | SQ202511250897-NR Services | NR services | SQ202510150296-NR Services // SQ202510150302-NR Services | 2025-11-25 | 2025-11-25 | Completed | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100935 |  | 2025-10-10 | 2025-10-10 | Completed | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-20 | 2025-12-20 | 2025-11-20 | 2025-11-21 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-11-20 | 2025-12-20 | 2025-11-20 | 2025-11-21 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-21 | 2025-11-20 | 2025-12-20 | 2025-11-20 | 2025-11-25 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-11-20 | 2025-12-20 | 2025-11-20 | 2025-11-20 | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-11 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-16 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509260798-GCI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | CHEONG/SENG/WAH/7018000306
7461B_HU | Tung Hup Estate (Celcom) | DU00006092474 | Sabah | Sabah | 5.317995 | 117.866790 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_512Q_28Mhz_448Mbps 2/4: Required additioanal BOM for 1x RTN910 | MW Parallel Link | Install new link 13G_2+0_512Q_28Mhz_448Mbps to be parallel with existing link Existing link 13G_2+0 &15 G_2+0_28Mhz_800Mbps (EPLA) Config EPLA new link and existing link become 6+0 Impact site: 7491B, 7144K, 7727E, 7654E, 7655E, 7728E, 7765E, 7692E, 7645E, 7718E, 7760E, 7687E, , S02003 | NE: 1. Install new RTN910A 2. Install new 13G 1.2m XMC-3 ANTENNA 3. Install new 13G XMC-3 sb B 4. Configure link 13G 2+0 28MHZ 512QAM EPLA 5. Re-enginering existing link at RTN950 to new RTN910 6. Config EPLA existing link and new link become 6+0 | [FE: 1. Install ISM8 card at slot 4 at existing IDU RTN05 2. Install new 13G 1.2m XMC-3 ANTENNA 3. Install new 13G XMC-3 sb B 4. Configure link 13G 2+0 28MHZ 512QAM EPLA 5. Config EPLA existing link and new link become 6+0] | XMC-3 | XMC | 13G | 1.2m | 1.2m | Seri Pancar | SQ202602090132-Seri Pancar | GCI | SQ202604060638-GCI // SQ202604060639-GCI |  |  | Ongoing | 2026-02-04 | 2026-02-28 | 2026-02-12 | 2026-02-12 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031150 |  | 2026-03-12 | 2026-03-16 | Completed | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-30 | 2026-04-30 | 2026-03-30 | 2026-04-06 | GERALD GAWAN/ANAK/ENTALANG/6000028653 | GCI TI | 2026-03-30 | 2026-04-30 | 2026-03-30 | 2026-04-06 | GERALD GAWAN/ANAK/ENTALANG/6000028653 | GCI TI | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2026-03-30 | 2026-04-30 | 2026-03-30 | 2026-04-17 | GERALD GAWAN/ANAK/ENTALANG/6000028653 | 2025-09-30: 2026-03-30; 2025-09-30: 2026-04-30; 2025-09-30: 2026-03-30; 2025-10-01: 2026-03-31 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202509260812-GTSB | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q01134_AD | Q130A_Q01134OD_T3_SGBOK | DU00006106199 | Sarawak | Sarawak | 3.752900 | 114.134400 | [7 empty] | 03. Pending TSS | [13 empty] | Magicell | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100649-GTSB
2443A_AD | Ijok (CELCOM) | DU00006106200 | Central | Selangor | 3.296836 | 101.447680 | [7 empty] | 05. Doable |  |  |  | 4X ISM8 CARD 2X RTN910A 1X 13G 1.2M DP ANTENNA 2X 13G 1.8M MDD ANTENNA 1x ODU 13G XMC5D SUB A HI 1x ODU 13G XMC5D SUB A LO | Cancel / Drop | DONE UNDER MW EOS SWAP --FREQUENCY SCANNING NEEDED DUE TO 3 EXISTING PARALLEL LINK AT SITE-- MW SWAP UPGRADE LINK 2443A-1156A SM MW4 WITH HUAWEI_13G_4+0_1.2M/1.8M_DP_28MHZ_512QAM_794MBPS_XMC5D_SUB_A_WITH CA_10.1KM IMPACTED: 1089L, 1155A, 1774H, 1650H DISMANTLE EXISTING LINK SM MW4 V POLAR WILL CONFIGURE 512QAM H POLAR WILL CONFIGURE 128QAM | DONE UNDER MW EOS SWAP 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM 5. DISMANTLE EXISTING LINK SM MW4 | DONE UNDER MW EOS SWAP 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM 5. DISMANTLE EXISTING LINK SM MW4 6. PATCH EXISTING CHILD IDU TO NEW IDU | XMC5D | MDD | 13G | 1.2 | 1.8 | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25121674 |  | 2025-12-17 | 2026-01-14 | Completed | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2026-01-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202510100626-GCI | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01141_AD | Q130A_Q01141OD_T3_LONGTERAWAN | DU00006106201 | Sarawak | Sarawak | 3.983851 | 114.630894 | [7 empty] | 03. Pending TSS | [13 empty] | Magicell | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100649-GTSB
Q01825_AD | Q130A_Q01825OD_SOPTINBARAP1 | DU00006106202 | Sarawak | Sarawak | 4.160699 | 114.240202 | [7 empty] | 03. Pending TSS | [13 empty] | Magicell | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100649-GTSB
Q01138_AD | Q130A_Q01138OD_T3_KUALATUTOH | DU00006106203 | Sarawak | Sarawak | 4.023260 | 114.393080 | [7 empty] | 03. Pending TSS | [13 empty] | Magicell | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100649-GTSB
Q01144_AD | Q130A_Q01144OD_T3_SGSTAPANG | DU00006106204 | Sarawak | Sarawak | 4.125075 | 114.410740 | [7 empty] | 03. Pending TSS |  | TSS+AA+TI+Dismantle |  | 18G_2+0_55M_512QAM_EPLA NE_Q01144 New 18G_1.2M(MAC)+OMT x1. New RTN910AF(RTN02). New XMC_3E, Sub A_Lo x2. New CAT6 cable x1. FE_9202K New 18G_1.2M(MAC)+OMT x1. New RTN910AF(RTN02). New XMC_3E, Sub A_Hi x2. New CAT6 cable x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.EXISTING UPLINK HW MW LINK 9202K-9294A, 13G_2+0_28MHZ_2048QAM_EPLA NEED TO UPGRADE AS CURRENT CAPACITY ONLY 546MBPS.**** Existing HW MW Link_ID SW03756, Q01144-Q00365 13G or 15G_1+0_1024QAM. Install new HW MW Link Q01144-9202K, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link_ID SW03756, Q01144-Q00365 13G or 15G_1+0_1024QAM. Site Impacted : Q01144. NE_Q01144 1.Install new 18G_1.2M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01) x1. 3.Install new XMC_3E, Sub A_Lo x2. Configure it. 4.Build new HW MW Link Q01144-9202K, 18G_2+0_55MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910A(RTN01) and patching to existing BBU Q01144. Configure it. 6.Request new xD Vlan DCN and Vlan Services. 7.Migrate traffics Q01144 via new Q01144-9202K, 18G_2+0_55MHZ_512QAM_EPLA. 8.Later, decom existing HW MW Link_ID SW03756, Q01144-Q00365 13G or 15G_1+0_1024QAM. FE_9202K 1.Install new 18G_1.2M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02) x1. 3.Install new XMC_3E, Sub A_Hi x2. Configure it. 4.Build new HW MW Link Q01144-9202K, 18G_2+0_55MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910A(RTN02) and perform cascading to port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-24460). Configure it. 6.Request new xD Vlan DCN and Vlan Services. 7.Migrate traffics Q01144 via existing IBeam port at CP 9294A in which similar with existing traffics like 9202K & Q02312. 8.Later, decom existing HW MW Link_ID SW03756, Q01144-Q00365 13G or 15G_1+0_1024QAM. | ****IMPORTANT NOTE: 1.EXISTING UPLINK HW MW LINK 9202K-9294A, 13G_2+0_28MHZ_2048QAM_EPLA NEED TO UPGRADE AS CURRENT CAPACITY ONLY 546MBPS.**** Existing HW MW Link_ID SW03756, Q01144-Q00365 13G or 15G_1+0_1024QAM. Install new HW MW Link Q01144-9202K, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link_ID SW03756, Q01144-Q00365 13G or 15G_1+0_1024QAM. Site Impacted : Q01144. NE_Q01144 1.Install new 18G_1.2M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01) x1. 3.Install new XMC_3E, Sub A_Lo x2. Configure it. 4.Build new HW MW Link Q01144-9202K, 18G_2+0_55MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910A(RTN01) and patching to existing BBU Q01144. Configure it. 6.Request new xD Vlan DCN and Vlan Services. 7.Migrate traffics Q01144 via new Q01144-9202K, 18G_2+0_55MHZ_512QAM_EPLA. 8.Later, decom existing HW MW Link_ID SW03756, Q01144-Q00365 13G or 15G_1+0_1024QAM. | ****IMPORTANT NOTE: 1.EXISTING UPLINK HW MW LINK 9202K-9294A, 13G_2+0_28MHZ_2048QAM_EPLA NEED TO UPGRADE AS CURRENT CAPACITY ONLY 546MBPS.**** Existing HW MW Link_ID SW03756, Q01144-Q00365 13G or 15G_1+0_1024QAM. Install new HW MW Link Q01144-9202K, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link_ID SW03756, Q01144-Q00365 13G or 15G_1+0_1024QAM. Site Impacted : Q01144. FE_9202K 1.Install new 18G_1.2M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02) x1. 3.Install new XMC_3E, Sub A_Hi x2. Configure it. 4.Build new HW MW Link Q01144-9202K, 18G_2+0_55MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910A(RTN02) and perform cascading to port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-24460). Configure it. 6.Request new xD Vlan DCN and Vlan Services. 7.Migrate traffics Q01144 via existing IBeam port at CP 9294A in which similar with existing traffics like 9202K & Q02312. 8.Later, decom existing HW MW Link_ID SW03756, Q01144-Q00365 13G or 15G_1+0_1024QAM. | XMC_3E | MAC | 18G | 18G_1.2M(MAC)+OMT x1 | 18G_1.2M(MAC)+OMT x1 | Magicell | SQ202602040288-Magicell | NR Services | SQ202604150320-NR Services // SQ202604150329-NR Services | 2026-03-18 | 2026-03-17 | Completed | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-11 | 2026-02-18 | 2026-02-11 | 2026-02-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26032804 |  | 2026-03-29 | 2026-03-31 | Completed | 2026-03-28 | 2026-03-29 | 2026-03-28 | 2026-03-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-28 | 2026-05-02 | 2026-04-29 |  | DINESH SINGH CHEEMA7167000003 | NR Service TI | 2026-04-28 | 2026-05-02 | 2026-04-29 |  | DINESH SINGH CHEEMA7167000003 | NR Service TI | [7 empty] | 2026-04-28 | 2026-05-02 | 2026-04-29 |  | DINESH SINGH CHEEMA7167000003 | 2025-09-30: 2026-04-28; 2025-09-30: 2026-05-02; 2025-09-30: 2026-04-29; 2025-10-01: 2026-05-04 | [7 empty] | GTSB | SQ202510100649-GTSB
Q01130_AD | Q130A_Q01130OD_CB_LONGTERU | DU00006106205 | Sarawak | Sarawak | 3.863516 | 114.251697 | [7 empty] | 03. Pending TSS | [13 empty] | Magicell | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100649-GTSB
Q01136_AD | Q130A_Q01136OD_CB_SGPEKING | DU00006106206 | Sarawak | Sarawak | 3.908302 | 114.357971 | [7 empty] | 03. Pending TSS | [13 empty] | Magicell | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100649-GTSB
1146K_LOS | B060C_B01948OD_INDBDRALAMJAYA | DU00005682356 | Central | Selangor | 3.246100 | 101.445110 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_1146K/B01948. 23G_DP_0.6M(MAC)+OMT x1 RTN910A x1. XMC_3E , Sub A & B_HI x2. FE_2531A/B00045. 23G_DP_0.6M(MAC)+OMT x1 RTN910A x1. XMC_3E , Sub A & B_Lo x2.. | MW New Link / Reroute | Existing SM link 18G_1+0_56M Link reroute to FE 2531A/B00045 with 23G_2+0_112M. Site Impacted : 1146K/B01948. NE_1146K/B01948. 1.Install new 23G_DP_0.6M(MAC)+OMT 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_HI 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Decom existing SM link. FE_2531A/B00045. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create new In Band DCN 6.Traffic migrate to new link and new FE route. 7.Decom existing SM link. | Existing SM link 18G_1+0_56M Link reroute to FE 2531A/B00045 with 23G_2+0_112M. Site Impacted : 1146K/B01948. NE_1146K/B01948. 1.Install new 23G_DP_0.6M(MAC)+OMT 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_HI 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Decom existing SM link. | Existing SM link 18G_1+0_56M Link reroute to FE 2531A/B00045 with 23G_2+0_112M. Site Impacted : 1146K/B01948. FE_2531A/B00045. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create new In Band DCN 6.Traffic migrate to new link and new FE route. 7.Decom existing SM link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202506190612-GCI | GCI | SQ202507140707-GCI // SQ202507140714-GCI | 2025-11-12 | 2025-11-11 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-11 | 2025-11-12 | 2025-11-11 | 2025-11-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070217 |  | 2025-07-03 | 2025-07-04 | Completed | 2025-07-02 | 2025-07-03 | 2025-07-02 | 2025-07-04 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-21 | 2025-07-14 | 2025-07-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-14 | 2025-07-21 | 2025-07-14 | 2025-07-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-14 | 2025-07-14 | 2025-07-21 | 2025-07-14 | 2025-07-18 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-07-14 | 2025-07-21 | 2025-07-14 | 2025-07-14 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | NG HONG JIE7018000036 | Logistic Team | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160751-GCI | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | CHEONG/SENG/WAH/7018000306
1274H_LOS | 99 Speedmart JLN PEKAN BARU MERU | DU00005682357 | Central | Selangor | 3.064228 | 101.455670 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | New NLOS RTN510 equipment NE_1274H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_B00379 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH cable / LAN Cable. | MW New Link / Reroute | Link reroute to new FE B00379 with new NLOS RTN510 equipment due to LOS block. NE_1274H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. FE_B00379 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.ETH cable patching to B00379 New Port CISCO 71052-TM_BKTRAJA-ACC1. 6.Decom existing NLOS Radio | Link reroute to new FE B00379 with new NLOS RTN510 equipment due to LOS block. NE_1274H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. | Link reroute to new FE B00379 with new NLOS RTN510 equipment due to LOS block. FE_B00379 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.ETH cable patching to B00379 New Port CISCO 71052-TM_BKTRAJA-ACC1. 6.Decom existing NLOS Radio | RTN510 | Flat Panel | 5 | 0.3 | 0.3 | GTSB | SQ202506190617-GTSB | GTSB | SQ202506250183-GTSB // SQ202506250191-GTSB // SQ202507250413-GTSB | 2025-11-12 | 2025-11-11 | Completed | 2025-07-07 | 2025-07-21 | 2025-07-07 | 2025-07-07 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-07 | 2025-07-21 | 2025-07-07 | 2025-07-07 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-07 | 2025-07-08 | 2025-07-07 | 2025-07-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-11 | 2025-11-12 | 2025-11-11 | 2025-11-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070125 |  | 2025-07-02 | 2025-07-08 | Completed | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-08 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-08-18 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-07-21 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | NG HONG JIE7018000036 | Logistic Team | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160751-GCI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
B02805-B00634 | B061F_B02805OD_KGCHEMPEDAK_KUANG | DU00003969243 | Central | Selangor | 3.223143 | 101.532040 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 31/7: D1: Cutover done. Remote upgrade | AA | PAC | N/A | MW Remote Upgrade | Remote upgrade existing link 28MHz to 56MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
9686A-9121A | Kemena Industrial 2 | DU00003969244 | Sarawak | Sarawak | 3.151988 | 113.077047 |  |  | WK32-WK35 | AUG 24 |  |  | ZTE | 00. Integrated/RFS Done | 30/8: D3: Cutover done 26/8: MOS & Pre-installation WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz 0.6m SP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz 0.6m SP | MW Swap | Existing link SW02392 WE KemenaInd3 Swap existing SM 18G 1+0 56MHz to Huawei 18G 1+0 112MHz Impact sites: 9686A NE (9686A) 1. Install new RTN910A (ops team to assign RTN number) 2. Install new link at new RTN 7-ISM8-1 3. Cutover traffic to new link FE (9121A) 1. Install new RTN910A (ops team to assign RTN number) 2. Install new link at new RTN 7-ISM8-1 3. Patch new RTN GE1 to xC LL (use existing port) 4. Cutover traffic to new link and create new DCN | [7 empty] | Trintel | SQ202408220969-Trintel | Trintel | SQ202408220993-Trintel | 2024-08-30 | 2024-08-26 | Completed | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-08-07 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-08 | 2024-08-09 | 2024-08-08 | 2024-08-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-08 | 2024-08-09 | 2024-08-08 | 2024-08-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24081395 |  | 2024-08-14 | 2024-08-16 | Completed | 2024-08-13 | 2024-08-14 | 2024-08-13 | 2024-08-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-20 | 2024-09-20 | 2024-09-14 | 2024-09-14 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2024-08-20 | 2024-09-20 | 2024-08-20 | 2024-09-11 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-09-05 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-08-20 | 2024-09-20 | 2024-09-04 | 2024-09-04 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-08-20 | 2024-09-20 | 2024-08-20 | 2024-08-20 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-12-13 | 2025-01-13 | 2024-12-13 | 2024-12-13 | ASTI//GANIS PUTRIANI/6237001358
R00023_HU_2 | R001B_R00023OD_KUALAPERLIS | DU00006538445 | Northern | Perlis | 6.383942 | 100.152053 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M_512QAM_EPLA(Without CA) NE_R00023 New 15G_1.2M(MDD)+Dual Coupler x1. Re-use existing RTN910AF(RTN02, NEID 44-23958). New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN. FE_R00028/4323K New 15G_1.2M(MDD)+Dual Coupler x1. New RTN910AF(RTN04). New ISM8 x1. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x4 RUN. New SFP Module 1.25G/1G 1310nm 10Km x2.(For IDU Huawei & Cisco) New Optical Patchcord with suitable type and length x1. | MW Parallel Link | Build new HW MW Parallel R00023-R00028/4323K, 15G_4+0_28M_512QAM_EPLA(Without CA). Site Impacted : 4611C. NE_R00023 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Re-use existing RTN910AF(RTN02, NEID 44-23958) and insert x2 ISM8 into slot 03 and 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel R00023-R00028/4323K, 15G_4+0_28M_512QAM_EPLA(Without CA). 4.Disconnect/remove cascading in between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 44-23958) and port 8-EM6-1 of existing RTN910AF(RTN04, NEID 44-13960). 5.Request new xC Vlan DCN & Vlan Services. 6.Divert traffic 4611C ONLY to new HW MW Parallel R00023-R00028/4323K, 15G_4+0_28M_512QAM_EPLA(Without CA). FE_R00028/4323K 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN04). 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel R00023-R00028/4323K, 15G_4+0_28M_512QAM_EPLA(Without CA). 4.Request new xC Vlan DCN & Vlan Services. 5.Request new Optical port at PTN/Cisco Router from ZTE IPRAN Team. 6.Enable port 8-EM6-5 of new RTN910AF(RTN04). Insert SFP Module 1.25G/1G 1310nm 10Km. 7.Insert SFP Module 1.25G/1G 1310nm 10Km into new port at PTN/Cisco Router. 8.Patching suitable Optical patch cord between port 8-EM6-5 of new RTN910AF(RTN04) and new port at PTN/Cisco Router. 9.Divert traffic 4611C ONLY to new port at PTN/Cisco Router. | Build new HW MW Parallel R00023-R00028/4323K, 15G_4+0_28M_512QAM_EPLA(Without CA). Site Impacted : 4611C. NE_R00023 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Re-use existing RTN910AF(RTN02, NEID 44-23958) and insert x2 ISM8 into slot 03 and 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel R00023-R00028/4323K, 15G_4+0_28M_512QAM_EPLA(Without CA). 4.Disconnect/remove cascading in between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 44-23958) and port 8-EM6-1 of existing RTN910AF(RTN04, NEID 44-13960). 5.Request new xC Vlan DCN & Vlan Services. 6.Divert traffic 4611C ONLY to new HW MW Parallel R00023-R00028/4323K, 15G_4+0_28M_512QAM_EPLA(Without CA). | Build new HW MW Parallel R00023-R00028/4323K, 15G_4+0_28M_512QAM_EPLA(Without CA). Site Impacted : 4611C. FE_R00028/4323K 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN04). 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel R00023-R00028/4323K, 15G_4+0_28M_512QAM_EPLA(Without CA). 4.Request new xC Vlan DCN & Vlan Services. 5.Request new Optical port at PTN/Cisco Router from ZTE IPRAN Team. 6.Enable port 8-EM6-5 of new RTN910AF(RTN04). Insert SFP Module 1.25G/1G 1310nm 10Km. 7.Insert SFP Module 1.25G/1G 1310nm 10Km into new port at PTN/Cisco Router. 8.Patching suitable Optical patch cord between port 8-EM6-5 of new RTN910AF(RTN04) and new port at PTN/Cisco Router. 9.Divert traffic 4611C ONLY to new port at PTN/Cisco Router. | XMC-5D Pro | MDD | 15G | 15G_1.2M(MDD)+Dual Coupler x1 | 15G_1.2M(MDD)+Dual Coupler x1 | GTSB | SQ202601190558-GTSB | GTSB | SQ202601190542-GTSB // SQ202601190547-GTSB |  |  | Ongoing | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-16 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-12 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-21 | 2026-04-14 | 2026-04-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011901 |  | 2026-01-20 | 2026-01-30 | Completed | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-03 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-16 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-05 | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-03-04 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-07-20: 2026-01-31; 2025-07-20: 2026-02-28; 2025-07-20: 2026-01-31; 2025-07-21: 2026-02-03 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601210796-GTSB
B02495_HU | SURAUATTAQWABKTBERUNTUNG | DU00006088953 | Central | Selangor | 3.402610 | 101.601000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK B02495-B00135 WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB_B_1.73KM IMPACTED: B02495 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 6. PATCH TO NEW CP PORT | XMC3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202509300135-Magicell | Magicell | SQ202510090253-Magicell // SQ202510090295-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251001AU |  | 2025-10-03 | 2025-10-06 | Completed | 2025-10-02 | 2025-10-03 | 2025-10-01 | 2025-10-06 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-15 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-29 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-15 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-29 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-07-20: 2025-10-13; 2025-07-20: 2025-10-13; 2025-07-20: 2025-10-13; 2025-07-21: 2025-10-15 |  |  | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260791-GCI | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | EZRIN TASNIM BIN ABDUL GANI6798000128
4466A_HU_1 | Taman Rakyat RDD | DU00006088954 | Northern | Perak | 4.921788 | 100.724654 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_256Q_56Mhz_788Mbps NE: 1x ISM8 1x 0.6m MDD ant (18G) 1x ODU 18G_XMC-5D sb-A_Hi FE: 1x ISM8 1x 0.6m MDD ant (18G) 1x ODU 18G_XMC-5D sb-A_Lo | MW Parallel Link | Install new link 18G_2+0_256Q_56Mhz_788Mbps to be parallel with existing link Config EPLA new link and existing link Impact site: 4466A, 4424A, 4565D Existing link 18G_2+0_112Mhz | NE: 1. Install ISM8 card at slot 3 at existing IDU RTN03 2. Install new 18G 0.6m MDD ANTENNA 3. Install new 18G XMC-5D sb A 4. Configure link 18G 2+0 56MHZ 256QAM EPLA 5. Config EPLA existing link and new link become 4+0 | FE: 1. Install ISM8 card at slot 3 at existing IDU RTN05 2. Install new 18G 0.6m MDD ANTENNA 3. Install new 18G XMC-5D sb A 4. Configure link 18G 2+0 56MHZ 256QAM EPLA 5. Config EPLA existing link and new link become 4+0 | XMC_5D | MDD | 18G | 0.6m | 0.6m | MTK | SQ202512170175-MTK | MTK | SQ202511190833-MTK // SQ202511190838-MTK |  |  | Ongoing | 2025-12-17 | 2026-03-09 | 2026-03-09 | 2026-03-09 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-06 | 2026-04-13 | 2026-04-06 | 2026-04-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25111256 |  | 2025-12-13 | 2025-11-15 | Completed | 2025-11-12 | 2025-12-13 | 2025-11-12 | 2025-11-15 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-13 | 2026-02-28 | 2026-03-03 | 2026-03-03 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2026-02-13 | 2026-02-28 | 2026-03-04 | 2026-03-04 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | AKMAL//BIN RAZALI/6794000078 |  | 2025-11-27 | 2026-02-13 | 2026-02-28 | 2026-03-04 | 2026-03-04 | DZULFAIZAL//BIN MAULUF/8225000001 | 2025-07-20: 2026-02-13; 2025-07-20: 2026-02-28; 2025-07-20: 2026-02-13; 2025-07-21: 2026-02-13 |  |  | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202509260807-GTSB | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | AB.RAHMAN//BIN MAT NOOH/6237001519
7014L_HU | Kampung Baru Long Pond | DU00006088955 | Sabah | Sabah | 4.279380 | 117.864000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_256Q_112Mhz_778Mbps | MW Hardware Upgrade | Change ODU to get Bandwith 112Mhz (Config: 18G_1+0_256Q_112Mhz_778Mbps) Existing link 18G1+0_56Mhz_449Mbps Impact site: 7014L | NE: 1. Install new ODU support 112Mhz by change with existing ODU 2. Configure as per LB | FE: 1. Install new ODU support 112Mhz by change with existing ODU 2. Configure as per LB | XMC-3E | XMC | 18G | 0.6m | 0.6m | GTSB | SQ202512120263-GTSB | GTSB | SQ202512120255-GTSB // SQ202512120259-GTSB | 2026-01-14 | 2026-01-07 | Completed | 2025-12-16 | 2025-12-18 | 2025-12-16 | 2025-12-16 | PAVITRAN AL CHINNAKOLANDAY6799000150 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | PAVITRAN AL CHINNAKOLANDAY6799000150 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25120352 |  | 2025-12-04 | 2025-12-06 | Completed | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-06 | 2026-01-03 | 2025-12-06 | 2025-12-06 | MOHD JUSRIADI BIN KAMARING6799000129 | GTSB TI | 2025-12-06 | 2026-01-03 | 2025-12-06 | 2025-12-07 | MOHD JUSRIADI BIN KAMARING6799000129 | GTSB TI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-09 | 2025-12-06 | 2026-01-03 | 2025-12-06 | 2025-12-13 | MOHD JUSRIADI BIN KAMARING6799000129 | 2025-07-20: 2025-12-06; 2025-07-20: 2026-01-03; 2025-07-20: 2025-12-06; 2025-07-21: 2025-12-06 |  |  | 2025-12-24 | 2026-01-24 | 2025-12-24 | 2025-12-24 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202509260812-GTSB | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | AB.RAHMAN//BIN MAT NOOH/6237001519
7698B_HU | Taman LCN (REL) | DU00006088956 | Sabah | Sabah | 4.277138 | 117.902388 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_256Q_112Mhz_1556Mbps_MDD NE: 1x RTN910 1x ISM8 1x 0.6m XMC-5D ant (18G) 1x ODU 13G_XMC-5D sb-A_Lo FE: 1x ISM8 1x 0.6m XMC-5D ant (18G) 1x ODU 13G_XMC-5D sb-A_Lo | MW Parallel Link | Install link 18G_2+0_256Q_112Mhz-1556Mbps to be parallel with existing 18G 2+0 (sharing antenna). Impact site: 7698B, 7651C Reengineering 18G_2+0 link to 7196A from RTN01 to new RTN | NE: 1. Install New IDU 2. Install new 18G 0.6m MDD ANTENNA 3. Install new 18G XMC-5D sb A 4. Configure link 18G 2+0 112MHZ 256QAM 5. Install new ISM card at slot 3 6. Relocate link 18G 2+0 from RTN01 slot 3 port 1 and slot 4 port 1 TO new IDU slot 3 7. Config EPLA become 18G 4+0 (existing link +new link) | FE: 1. Install ISM8 at slot 4 2. Install new 18G 0.6m MDD ANTENNA 3. Install new 18G XMC-5D sb A 4. Configure link 18G 2+0 112MHZ 256QAM 5. Configure LAG 1G +1G IPRAN | XMC-5D | MDD | 18G | 0.6m | 0.6m | Seri Pancar | SQ202602090132-Seri Pancar | GTSB | SQ202602130249-GTSB // SQ202602130265-GTSB |  |  | Ongoing | 2026-02-04 | 2026-02-28 | 2026-02-05 | 2026-02-05 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-21 | 2026-04-14 | 2026-04-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26020458 |  | 2026-02-05 | 2026-02-14 | Completed | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-08 | 2026-02-28 | 2026-02-08 | 2026-02-14 | MOHD AIRELL SHAH6000044820 | GTSB TI | 2026-02-08 | 2026-02-28 | 2026-02-08 | 2026-02-14 | MOHD AIRELL SHAH6000044820 | GTSB TI | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-20 | 2026-02-08 | 2026-02-28 | 2026-02-08 | 2026-02-25 | MOHD AIRELL SHAH6000044820 | 2025-07-20: 2026-02-08; 2025-07-20: 2026-02-28; 2025-07-20: 2026-02-08; 2025-07-21: 2026-02-13 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202509260812-GTSB | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | AB.RAHMAN//BIN MAT NOOH/6237001519
S00331_HU | CB_TOMANGGONG | DU00006088957 | Sabah | Sabah | 5.388319 | 118.647892 | [7 empty] | 01. Pending Planning |  | TSS+AA+TI |  | 8G_4+0_28M_256QAM_EPLA NE_S00331 New 8G_2.4M(MS)+Hybrid Coupler x1. Re-use existing RTN950A(NEID 198-44453). New ISM8 x4. New XMC_3, Sub A_Hi x2. New XMC_3, Sub B_Hi x2. New IF cables with suitable length and type x4 RUN. FE_S00335 New 8G_2.4M(MS)+Hybrid Coupler x1. Re-use existing RTN950A(NEID 198-33383). New ISM8 x4. New XMC_3, Sub A_Lo x2. New XMC_3, Sub B_Hi x2. New IF cables with suitable length and type x4 RUN. | MW Parallel Link | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM FREQUENCY SCANNING FOR 8G IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.MANDATORY TO PERFORM TSS FOR ENSURE SPACING AT TOWER FOR MOUNTING NEW 2.4M ANTENNA DISH SIZE AVAILABLE AT NE & FE SITE.**** Existing HW MW Link_SB02901, S00331-S00335, 7G_4+0_28MHZ_256QAM_XPIC_EPLA. Build new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. Later, combine existing HW MW Link_SB02901, S00331-S00335, 7G_4+0_28MHZ_256QAM_XPIC_EPLA and new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. Become 7G&8G_8+0_28MHZ_256QAM_XPIC & EPLA. Site Impacted : S01603/7136K & 7482B. NE_S00331 1.Install new 8G_2.4M(MS)+Hybrid Coupler x1. 2.Re-use existing RTN950A(NEID 198-44453) and insert 2x new ISM8 into slot 04 & 06. Also swap existing ISM6 slot 03 & 05 with new 2x ISM8. 3.Install new XMC_3, Sub A_Hi x2 & Sub B_Hi x2. Build new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. 4.Lay new IF cables x4 RUN. 5.Later, combine existing HW MW Link_SB02901, S00331-S00335, 7G_4+0_28MHZ_256QAM_XPIC_EPLA and new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. Become 7G&8G_8+0_28MHZ_256QAM_XPIC & EPLA. FE_S00335 1.Install new 8G_2.4M(MS)+Hybrid Coupler x1. 2.Re-use existing RTN950A(NEID 198-33383) and insert 2x new ISM8 into slot 04 & 06. Also swap existing ISM6 slot 03 & 05 with new 2x ISM8. 3.Install new XMC_3, Sub A_Lo x2 & Sub B_Lo x2. Build new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. 4.Lay new IF cables x4 RUN. 5.Later, combine existing HW MW Link_SB02901, S00331-S00335, 7G_4+0_28MHZ_256QAM_XPIC_EPLA and new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. Become 7G&8G_8+0_28MHZ_256QAM_XPIC & EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM FREQUENCY SCANNING FOR 8G IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.MANDATORY TO PERFORM TSS FOR ENSURE SPACING AT TOWER FOR MOUNTING NEW 2.4M ANTENNA DISH SIZE AVAILABLE AT NE & FE SITE.**** Existing HW MW Link_SB02901, S00331-S00335, 7G_4+0_28MHZ_256QAM_XPIC_EPLA. Build new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. Later, combine existing HW MW Link_SB02901, S00331-S00335, 7G_4+0_28MHZ_256QAM_XPIC_EPLA and new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. Become 7G&8G_8+0_28MHZ_256QAM_XPIC & EPLA. Site Impacted : S01603/7136K & 7482B. NE_S00331 1.Install new 8G_2.4M(MS)+Hybrid Coupler x1. 2.Re-use existing RTN950A(NEID 198-44453) and insert 2x new ISM8 into slot 04 & 06. Also swap existing ISM6 slot 03 & 05 with new 2x ISM8. 3.Install new XMC_3, Sub A_Hi x2 & Sub B_Hi x2. Build new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. 4.Lay new IF cables x4 RUN. 5.Later, combine existing HW MW Link_SB02901, S00331-S00335, 7G_4+0_28MHZ_256QAM_XPIC_EPLA and new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. Become 7G&8G_8+0_28MHZ_256QAM_XPIC & EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM FREQUENCY SCANNING FOR 8G IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.MANDATORY TO PERFORM TSS FOR ENSURE SPACING AT TOWER FOR MOUNTING NEW 2.4M ANTENNA DISH SIZE AVAILABLE AT NE & FE SITE.**** Existing HW MW Link_SB02901, S00331-S00335, 7G_4+0_28MHZ_256QAM_XPIC_EPLA. Build new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. Later, combine existing HW MW Link_SB02901, S00331-S00335, 7G_4+0_28MHZ_256QAM_XPIC_EPLA and new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. Become 7G&8G_8+0_28MHZ_256QAM_XPIC & EPLA. Site Impacted : S01603/7136K & 7482B. FE_S00335 1.Install new 8G_2.4M(MS)+Hybrid Coupler x1. 2.Re-use existing RTN950A(NEID 198-33383) and insert 2x new ISM8 into slot 04 & 06. Also swap existing ISM6 slot 03 & 05 with new 2x ISM8. 3.Install new XMC_3, Sub A_Lo x2 & Sub B_Lo x2. Build new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. 4.Lay new IF cables x4 RUN. 5.Later, combine existing HW MW Link_SB02901, S00331-S00335, 7G_4+0_28MHZ_256QAM_XPIC_EPLA and new HW MW Parallel Link S00331-S00335, 8G_4+0_28MHZ_256QAM_EPLA. Become 7G&8G_8+0_28MHZ_256QAM_XPIC & EPLA. | XMC-3 | MS | 8G | 8G_2.4M(MS)+Hybrid Coupler x1 | 8G_2.4M(MS)+Hybrid Coupler x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202509260812-GTSB
4513B_HU | Bukit Kinding | DU00006088958 | Northern | Perak | 4.697220 | 101.151230 | [7 empty] | 05. Doable | 18/3/2026: Vandalized already recovered, able to proceed TI | TSS+AA+TI+Dismantle |  | 18G_2+0_110M_256QAM_EPLA NE_4513B New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01). New XMC_5D, Sub B_Lo x1. New CAT6 cable x1. FE_4346A New 18G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN04). New XMC_5D, Sub B_Hi x1. New CAT6 cable x2 for LAG. | MW Swap | Existing HW MW link 18G_2+0_55M_512QAM_EPLA. Swap existing link to new HW MW Link 18G_2+0_110M_256QAM_EPLA. Later, decom existing HW MW link 18G_2+0_55M_512QAM_EPLA.(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. Site Impacted : 4513B. NE_4513B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01). 3.Install new XMC_5D, Sub B_Lo x1. Build new HW MW Link 18G_2+0_110M_256QAM_EPLA. 4.Re-use existing Vlan DCN and Vlan services. 5.Migrate traffics via new HW MW Link 18G_2+0_110M_256QAM_EPLA. 6.Later, decom existing HW MW link 18G_2+0_55M_512QAM_EPLA.(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. FE_4346A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN04). 3.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Link 18G_2+0_110M_256QAM_EPLA. 4.Re-use existing Vlan DCN and Vlan services. 5.Enable port 8-EM6-2 of existing RTN910AF(RTN04). 6.Request new IBeam 1G port and patching with port 8-EM6-2 of existing RTN910AF(RTN04). 7.Perform LAG for both IDU port and both IBeam port. 8.Migrate traffics to 2x 1G port at IBeam. 9.Later, decom existing HW MW link 18G_2+0_55M_512QAM_EPLA.(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. | Existing HW MW link 18G_2+0_55M_512QAM_EPLA. Swap existing link to new HW MW Link 18G_2+0_110M_256QAM_EPLA. Later, decom existing HW MW link 18G_2+0_55M_512QAM_EPLA.(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. Site Impacted : 4513B. NE_4513B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01). 3.Install new XMC_5D, Sub B_Lo x1. Build new HW MW Link 18G_2+0_110M_256QAM_EPLA. 4.Re-use existing Vlan DCN and Vlan services. 5.Migrate traffics via new HW MW Link 18G_2+0_110M_256QAM_EPLA. 6.Later, decom existing HW MW link 18G_2+0_55M_512QAM_EPLA.(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. | Existing HW MW link 18G_2+0_55M_512QAM_EPLA. Swap existing link to new HW MW Link 18G_2+0_110M_256QAM_EPLA. Later, decom existing HW MW link 18G_2+0_55M_512QAM_EPLA.(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. Site Impacted : 4513B. FE_4346A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN04). 3.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Link 18G_2+0_110M_256QAM_EPLA. 4.Re-use existing Vlan DCN and Vlan services. 5.Enable port 8-EM6-2 of existing RTN910AF(RTN04). 6.Request new IBeam 1G port and patching with port 8-EM6-2 of existing RTN910AF(RTN04). 7.Perform LAG for both IDU port and both IBeam port. 8.Migrate traffics to 2x 1G port at IBeam. 9.Later, decom existing HW MW link 18G_2+0_55M_512QAM_EPLA.(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. | XMC_5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_1.2M(MDD) x1. | Magicell | SQ202510220709-Magicell | Magicell | SQ202510220690-Magicell // SQ202510220702-Magicell // SQ202511260115-Magicell | 2026-01-26 | 2026-01-21 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110579 |  | 2025-12-04 | 2025-11-10 | Completed | 2025-11-05 | 2025-12-04 | 2025-11-05 | 2025-11-10 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-11 | 2027-05-05 | 2026-05-11 |  | SITI SARAH BINTI SAADDIN7018000284 | Magicell TI | 2026-05-11 | 2027-05-05 | 2026-05-11 |  | SITI SARAH BINTI SAADDIN7018000284 | Magicell TI | [7 empty] | 2026-05-11 | 2027-05-05 | 2026-05-11 |  | SITI SARAH BINTI SAADDIN7018000284 | 2025-07-20: 2026-05-11; 2025-07-20: 2027-05-05; 2025-07-20: 2026-05-11 | [7 empty] | GTSB | SQ202509260807-GTSB | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
A01064_HU | T3_JERAMMENGKUANG | DU00006088959 | Northern | Perak | 4.065056 | 101.241114 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Swap existing to 13G_4+0_28M NE_A001064 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. ISM8 x2. FE_A00081. 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. ISM8 x2. | MW Swap | Existing SM Link 13G_2+0_28M Swap existing to 13G_4+0_28M Site Impacted : A001064. NE_A001064 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Hi. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 5.Cross connect , CA and EPLA. 6.Traffic migrate to new link. 7.Decom existing SM link. FE_4317A/A00081. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Lo. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 5.Create cross connect , CA and EPLA. 6.Traffic migrate to new link. 7.Decom existing SM link | Existing SM Link 13G_2+0_28M. Swap existing to 13G_4+0_28M. Site Impacted : A001064. NE_A001064 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Hi. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 5.Cross connect , CA and EPLA. 6.Traffic migrate to new link. 7.Decom existing SM link. | Existing SM Link 13G_2+0_28M. Swap existing to 13G_4+0_28M. Site Impacted : A001064. FE_A00081. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Lo. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 5.Create cross connect , CA and EPLA. 6.Traffic migrate to new link. 7.Decom existing SM link | XMC_5D | MDD | 13G | 1.2M | 1.2M | MTK | SQ202509300141-MTK | MTK | SQ202510230942-MTK // SQ202510230950-MTK |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25100116 |  | 2025-10-02 | 2025-10-17 | Completed | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-17 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-03-20 | 2026-02-24 | 2026-02-24 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2026-02-23 | 2026-03-20 | 2026-03-01 | 2026-03-01 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-30 | 2026-02-23 | 2026-03-20 | 2026-03-03 | 2026-03-03 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | 2026-02-23 | 2026-03-20 | 2026-02-23 | 2026-02-24 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | NG HONG JIE7018000036 | Logistic Team | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | CHEONG/SENG/WAH/7018000306
2061A_HU | Shah Alam Exit | DU00006088960 | Central | Selangor | 3.094486 | 101.556166 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3 SUB A HI 1X ODU 23G XMC3 SUB A LO 1x ODU 23G XMC3 SUB B HI 1X ODU 23G XMC3 SUB B LO | MW Swap | MW SWAP 2061A-1233B WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3_SUB_A & B_0.79KM IMPACTED: 2061A, 3621A DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU RTN910 SLOT 7 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU RTN910 SLOT 7 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 2G 6. DISMANTLE EXISTING LINK | XMC3 | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202509300135-Magicell | Magicell | SQ202510090253-Magicell // SQ202510090295-Magicell | 2025-12-10 | 2025-12-10 | Completed | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251001AS |  | 2025-10-07 | 2025-10-15 | Completed | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-15 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-15 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-15 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-08 | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-13 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-08 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260791-GCI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
4720D_HU | Taman Felcra Jaya | DU00006088961 | Northern | Perak | 4.128976 | 100.904823 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M NE_4720D 15G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. FE_4592B. 15G_DP_1.2M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Hi x2. | MW Parallel Link | Existing link 15G_2+0_28M Install parallel link 15G_2+0_28M for 4720D. Priority , to install new uplink for 4592B-A00458 (Refer DU ID 4592B_HU). Site Impacted : 4720D NE_4720D 1.Install new 15G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4720D_RTN01 ( ID : 13890). 3.Install new 3_ISM8-2+0 into existing 4720D_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No link to be decom. FE_4592B. 1.Install new 15G_DP_1.2M(MAC)+OMT. 2.Reuse existing 4592B_RTN01 ( ID : 23890). 3.Install new 3_ISM8-2+0 into existing 4592B_RTN01. 4.Install new XMC_3E , Sub A & B_Hi. 5.Disconnect Old ETH LAN cable from 4592B_RTN01_GE1 ( ID : 23890). 6.ETH LAN Cable patching from 4592B_RTN01_GE1 ( ID : 23890) to new parallel link RTN910A_GE1 (Refer 4592B_HU). 7.Create service cross connect and EPLA. 8.Traffic migrate to new parallel link. 9. No link to be decom | Existing link 15G_2+0_28M Install parallel link 15G_2+0_28M for 4720D. Priority , to install new uplink for 4592B-A00458 (Refer DU ID 4592B_HU). Site Impacted : 4720D NE_4720D 1.Install new 15G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4720D_RTN01 ( ID : 13890). 3.Install new 3_ISM8-2+0 into existing 4720D_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No link to be decom. | Existing link 15G_2+0_28M Install parallel link 15G_2+0_28M for 4720D. Priority , to install new uplink for 4592B-A00458 (Refer DU ID 4592B_HU). Site Impacted : 4720D FE_4592B. 1.Install new 15G_DP_1.2M(MAC)+OMT. 2.Reuse existing 4592B_RTN01 ( ID : 23890). 3.Install new 3_ISM8-2+0 into existing 4592B_RTN01. 4.Install new XMC_3E , Sub A & B_Hi. 5.Disconnect Old ETH LAN cable from 4592B_RTN01_GE1 ( ID : 23890). 6.ETH LAN Cable patching from 4592B_RTN01_GE1 ( ID : 23890) to new parallel link RTN910A_GE1 (Refer 4592B_HU). 7.Create service cross connect and EPLA. 8.Traffic migrate to new parallel link. 9. No link to be decom | XMC_3E | MAC | 15G | 0.6 | 1.2 | MTK | SQ202509300141-MTK | MTK | SQ202510150288-MTK // SQ202510150292-MTK | 2025-12-03 | 2025-12-02 | Completed | [8 empty] | Unassigned | Disabled |  | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-02 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251001AY |  | 2025-10-03 | 2025-10-09 | Completed | 2025-10-02 | 2025-10-03 | 2025-10-01 | 2025-10-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-13 | 2025-10-31 | 2026-01-12 | 2026-01-12 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-10-13 | 2025-10-31 | 2026-01-12 | 2026-01-12 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-15 | 2025-10-13 | 2025-10-31 | 2026-01-14 | 2026-01-14 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-10-07: 2025-10-13; 2025-10-07: 2025-10-31; 2025-10-07: 2025-11-25; 2025-10-08: 2025-11-25 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | CHEONG/SENG/WAH/7018000306
3853B_HU | Jalan PJS 2_1 | DU00006088962 | Central | Selangor | 3.079247 | 101.636727 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3 SUB A HI 1X ODU 23G XMC3 SUB A LO | MW Swap | MW SWAP 3853B-1243B WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3_SUB_A_0.96KM IMPACTED: 3853B DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 SLOT 7 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 SLOT 7 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | XMC3 | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202509300135-Magicell | Magicell | SQ202510090253-Magicell // SQ202510090295-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251001AQ |  | 2025-10-03 | 2025-10-06 | Completed | 2025-10-02 | 2025-10-03 | 2025-10-01 | 2025-10-06 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-13 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-18 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-13 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-18 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260791-GCI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
3185B_HU | pBTS Taman Bersatu LP | DU00006088963 | Central | Sabah | 5.902224 | 116.044421 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 23G_1+0_56M_512QAM_395M. MW Remote Upgrade to HW 23G_1+0_112M_512QAM_889M. Site Impacted : 3185B NE_3185B 1.Existing ODU XMC-3(support BW 112MHz) may remotely upgrade to BW 112MHz. FE_7273A 1.Existing ODU XMC-3(support BW 112MHz) may remotely upgrade to BW 112MHz. | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_112M_128QAM_676M. Site Impacted : 7308R & 7077K/S01749 NE_7308R 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_112M_128QAM_676M. Site Impacted : 7308R & 7077K/S01749 FE_7643A 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | XMC_3 | MAC | 23G | 23G_SP_0.6M(MAC) x1. | 23G_SP_0.6M(MAC) x1. | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-03 | [15 empty] | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202509260805-GTSB
4427B_HU | Spg Taiping RCD | DU00006088964 | Northern | Perak | 4.820556 | 100.702667 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 18G_2+0_55M_256QAM_790M. MW Remote Upgrade to HW 18G_2+0_110M_128QAM_1354M. Site Impacted : 4462A(Naming Temporary in NMS) & 4426D. NE_4462A(RTN910AF-RTN02) 1.Existing ODU XMC-3E may remotely upgrade to BW 110MHz & 128QAM. FE_4427B(RTN910AF-RTN03) 1.Existing ODU XMC-3E may remotely upgrade to BW 110MHz & 128QAM. | Link Existing HW 18G_2+0_55M_256QAM_790M. MW Remote Upgrade to HW 18G_2+0_110M_128QAM_1354M. Site Impacted : 4462A(Naming Temporary in NMS) & 4426D. NE_4462A(RTN910AF-RTN02) 1.Existing ODU XMC-3E may remotely upgrade to BW 110MHz & 128QAM. | Link Existing HW 18G_2+0_55M_256QAM_790M. MW Remote Upgrade to HW 18G_2+0_110M_128QAM_1354M. Site Impacted : 4462A(Naming Temporary in NMS) & 4426D. FE_4427B(RTN910AF-RTN03) 1.Existing ODU XMC-3E may remotely upgrade to BW 110MHz & 128QAM. | XMC-3 | MS | 18G | 18G_0.6M(MS) x1. | 18G_0.6M(MS) x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-05 | [15 empty] | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202509260807-GTSB
4272A_HU_1 | Permatang Bera 2 | DU00006088965 | Northern | Penang | 5.509877 | 100.384527 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_1+0_110M_256QAM NE_4272A New 18G_1.2M(MDD) x1. New RTN910AF(RTN16) x1. New XMC_5D, Sub A_Hi x1. New CAT6 cable x1. FE_4276A New 18G_1.2M(MDD) x1. New RTN910AF(RTN14) x1. New XMC_5D, Sub A_Lo x1. New CAT6 cable x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Build new HW MW Parallel Link 4272A-4276A, 18G_1+0_110MHZ_256QAM. Site Impacted : 4272A ONLY. NE_4272A 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN16). 3.Install new XMC_5D, Sub A_Hi x1. 4.Build new HW MW Parallel Link 4272A-4276A, 18G_1+0_110MHZ_256QAM. 5.Enable port 8-EM6-1 of new RTN910AF(RTN16). 6.Disconnect BBU 4272A from port 8-EG6-1 of existing RTN910F(RTN08). 7.Perform patching BBU 4272A to port 8-EM6-1 of new RTN910AF(RTN16). 8.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 9.Migrate traffic 4272A ONLY via new HW MW Parallel Link 4272A-4276A, 18G_1+0_110MHZ_256QAM. FE_4276A 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN16). 3.Install new XMC_5D, Sub A_Lo x1. 4.Build new HW MW Parallel Link 4272A-4276A, 18G_1+0_110MHZ_256QAM. 5.Enable port 8-EM6-1 of new RTN910AF(RTN14). 6.Request new IBeam port, new Vlan DCN and Vlan Services from ZTE IPRAN Team. 7.Migrate traffic 4272A ONLY via new IBeam port. | ****IMPORTANT NOTE: 1.PLEASE PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Build new HW MW Parallel Link 4272A-4276A, 18G_1+0_110MHZ_256QAM. Site Impacted : 4272A ONLY. NE_4272A 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN16). 3.Install new XMC_5D, Sub A_Hi x1. 4.Build new HW MW Parallel Link 4272A-4276A, 18G_1+0_110MHZ_256QAM. 5.Enable port 8-EM6-1 of new RTN910AF(RTN16). 6.Disconnect BBU 4272A from port 8-EG6-1 of existing RTN910F(RTN08). 7.Perform patching BBU 4272A to port 8-EM6-1 of new RTN910AF(RTN16). 8.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 9.Migrate traffic 4272A ONLY via new HW MW Parallel Link 4272A-4276A, 18G_1+0_110MHZ_256QAM. | ****IMPORTANT NOTE: 1.PLEASE PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Build new HW MW Parallel Link 4272A-4276A, 18G_1+0_110MHZ_256QAM. Site Impacted : 4272A ONLY. FE_4276A 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN16). 3.Install new XMC_5D, Sub A_Lo x1. 4.Build new HW MW Parallel Link 4272A-4276A, 18G_1+0_110MHZ_256QAM. 5.Enable port 8-EM6-1 of new RTN910AF(RTN14). 6.Request new IBeam port, new Vlan DCN and Vlan Services from ZTE IPRAN Team. 7.Migrate traffic 4272A ONLY via new IBeam port. | MDD | MDD | 18G | 18G_1.2M(MDD) x1. | 18G_1.2M(MDD) x1. | MTK | SQ202601280674-MTK | MTK | SQ202512300541-MTK // SQ202512300543-MTK |  |  | Ongoing | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-11 | 2026-02-18 | 2026-02-11 | 2026-02-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-27 | 2026-04-03 | 2026-03-27 | 2026-03-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25121308 |  | 2026-01-14 | 2025-12-16 | Completed | 2025-12-13 | 2026-01-14 | 2025-12-13 | 2025-12-16 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-31 | 2026-01-22 | 2026-01-22 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2026-01-22 | 2026-01-31 | 2026-01-28 | 2026-01-28 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-23 | 2026-01-22 | 2026-01-31 | 2026-01-28 | 2026-01-28 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-10-09: 2026-01-22; 2025-10-09: 2026-01-31; 2025-10-09: 2026-01-27; 2025-10-13: 2026-01-27 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202509260807-GTSB
4632B_HU | Lubuk Saga | DU00006088966 | Northern | Kedah | 5.560245 | 100.559285 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M NE_4632B. 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Hi x1. FE_4281A 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Lo x1. | MW Parallel Link | Existing link 15G_4+0_56M. Install a new parallel link 13G_4+0_28M Site Impacted : 4337C. NE_4632B. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.( RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Enable GE1 , ETH patching to existing 4632B_RTN01_GE2 ( ID : 12512). 6.Disconnect Old ETH LAN patching from 4632B_RTN01_GE2 to 4632B_RTN02_GE2 (ID : 30251). 7.Create service cross connect , CA and EPLA. 8.Traffic migrate to new parallel link. 9.No link to be decom. FE_4281A 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and New In band DCN. 6.Traffic migrate to new parallel link. 7.No link to be decom. | Existing link 15G_4+0_56M. Install a new parallel link 13G_4+0_28M Site Impacted : 4337C. NE_4632B. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.( RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Enable GE1 , ETH patching to existing 4632B_RTN01_GE2 ( ID : 12512). 6.Disconnect Old ETH LAN patching from 4632B_RTN01_GE2 to 4632B_RTN02_GE2 (ID : 30251). 7.Create service cross connect , CA and EPLA. 8.Traffic migrate to new parallel link. 9.No link to be decom. | Existing link 15G_4+0_56M. Install a new parallel link 13G_4+0_28M. Site Impacted : 4337C. FE_4281A 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and New In band DCN. 6.Traffic migrate to new parallel link. 7.No link to be decom. | XMC_5D | MDD | 13G | 1.2 | 1.2 | NWAVE | SQ202509300147-N-Wave | NWAVE | SQ202510090424-N-Wave // SQ202510090433-N-Wave | 2025-11-28 | 2025-11-27 | Completed | 2025-10-06 | 2025-11-06 | 2025-10-06 | 2025-10-07 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100113 |  | 2025-10-02 | 2025-10-04 | Completed | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-04 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-06 | 2025-11-06 | 2025-10-06 | 2025-10-16 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-10-06 | 2025-11-06 | 2025-10-06 | 2025-10-18 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-10 | 2025-10-06 | 2025-11-06 | 2025-10-06 | 2025-10-18 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | 2025-10-09: 2025-10-06; 2025-10-09: 2025-11-06; 2025-10-09: 2025-10-06; 2025-10-13: 2025-10-08 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | CHEONG/SENG/WAH/7018000306
1693B_HU | Puncak Alam Highway 2 (ZED) | DU00006088967 | Central | Selangor | 3.145270 | 101.474623 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 4X ISM8 CARD 2X RTN910A 2X 13G 1.2M MDD ANTENNA 1x ODU 13G XMC5D SUB B HI 1X ODU 13G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL 1693B-1612B WITH HUAWEI_13G_4+0_1.2M/1.2M_MDD_28MHZ_256QAM_800MBPS_XMC5D_SUB_B_WITH CA_7.9KM IMPACTED: 1693B NEW LINK CARRY BBU 1693B | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 AT SLOT 3 AND 4 2. INSTALL NEW 13G 0.6M DP ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM WITH CA 5. PATCH BBU 1693B TO NEW LINK | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 AT SLOT 3 AND 4 2. INSTALL NEW 13G 0.6M DP ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM WITH CA 5. PATCH TO NEWCP PORT | 5D | MDD | 13G | 1.2 | 1.2 | Magicell | SQ202509300135-Magicell | Magicell | SQ202510090253-Magicell // SQ202510090295-Magicell // SQ202605070082-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-29 | 2025-10-28 | 2025-10-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100110 |  | 2025-10-02 | 2025-10-06 | Completed | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-06 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-27 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-11-04 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-28 | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-11-04 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-10-09: 2025-10-26; 2025-10-09: 2025-10-26; 2025-10-09: 2025-10-26; 2025-10-13: 2025-10-29 |  |  | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260791-GCI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
3915C_HU | Institut Pendidikan Guru Kampus Pendidikan Teknik (IPGKPT) | DU00006088968 | Central | Sembilan | 2.728114 | 101.799150 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 18G_1+0_56M.Remote Software Upgrade from 56M to 112M. Realignment is required if RSL not meet. | Remote Software Upgrade to 112M. Realignment is required if RSL not meet. Site Impacted : 3915C | Remote Software Upgrade to 112M. Realignment is required if RSL not meet. Site Impacted : 3915C | [5 empty] | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-06 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509260791-GCI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | CHEONG/SENG/WAH/7018000306
3256A_HU | COUNTRYHOMES1 | DU00006088969 | Central | Selangor | 3.331739 | 101.535194 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 1X ISM8 CARD 1X RTN910A 1X 15G 0.6M DP ANTENNA 1X 15G 1.2M DP ANTENNA 1x ODU 15G XMC3 SUB A HI 1X ODU 15G XMC3 SUB A LO 1x ODU 15G XMC3 SUB B HI 1X ODU 15G XMC3 SUB B LO | MW Parallel Link | MW PARALLEL LINK 3256A-2476A WITH HUAWEI_15G_2+0_0.6M/1.2M_DP_28MHZ_512QAM_448MBPS_XMC3_SUB_A & B_5.5KM IMPACTED: 2746C NEW LINK CARRY 2746C TRAFFIC | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 15G 0.6M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. PATCH SM 2746C-3256A MW1 TO NEW LINK | 1. INSTALL NEW 1PCS ISM8 AT 2476A RTN05 SLOT 3 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. NEW LINK CARRY 2746C TRAFFIC | XMC3 | MAC | 15G | 0.6 | 1.2 | Magicell | SQ202510090302-Magicell | Magicell | SQ202510090253-Magicell // SQ202510090295-Magicell // SQ202605070082-Magicell | 2025-12-06 | 2025-12-10 | Completed | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100945 |  | 2025-10-12 | 2025-10-13 | Completed | 2025-10-11 | 2025-10-12 | 2025-10-09 | 2025-10-13 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-28 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-11-10 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-28 | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-11-10 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-10-09: 2025-10-26; 2025-10-09: 2025-10-26; 2025-10-09: 2025-10-26; 2025-10-13: 2025-10-28 |  |  | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260791-GCI | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | EZRIN TASNIM BIN ABDUL GANI6798000128
9697B_PL | Samalaju OM | DU00006101919 | Sarawak | Sarawak | 3.551770 | 113.333443 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9388B_HU | RhSemop | DU00006616503 | Sarawak | Sarawak | 2.418034 | 111.396973 | [9 empty] | TSS+AA+TI |  | 15G_4+0_28M_256QAM_EPLA(WO CA) NE_9388B New 15G_1.2M(MDD)+Dual Coupler x1. New RTN910AF(RTN08). New ISM8 x2. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x6 RUN.(x4 RUN for new ODU and x2 RUN for existing ODU) FE_9366A New 15G_1.2M(MDD)+Dual Coupler x1. New RTN910AF(RTN07). New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. | MW Parallel Link | Add new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). Perform Load Balancing. Site Impacted : 9028R. NE_9388B 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN08) and insert ISM8 x2 into slot 03 & slot 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new x4 RUN of IF cables from new 2x ODU 15G XMC_5D Pro, Sub A&B_Hi to new RTN910AF(RTN08) slot 03(ISM8 Port 1 & 2) and slot 04(ISM8 Port 1 & 2). 5.Decom existing IF cables from existing 2x ODU 13G XMC-3 23-ODU & 43-ODU to existing RTN910AF(RTN03, NEID 9-20443) slot 03(ISM8 Port 1 & 2). 6.Lay new x2 of IF cables from existing 2x ODU 13G XMC-3 23-ODU & 43-ODU to new RTN910AF(RTN08) slot 07(ISM8 Port 1 & 2). 7.Build new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). 8.Request new xD Vlan DCN and Vlan Services. 9.Migrate traffic 9028R ONLY via new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). FE_9366A 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN07) and insert ISM8 x2 into slot 03 & slot 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Lay new x4 RUN of IF cables from new 2x ODU 15G XMC_5D Pro, Sub A&B_Hi to new RTN910AF(RTN07) slot 03(ISM8 Port 1 & 2) and slot 04(ISM8 Port 1 & 2). 5.Build new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). 6.Request new 1G x1 of IBeam port from ZTE IPRAN Team. 7.Request new xD Vlan DCN and Vlan Services. 8.Migrate traffic 9028R ONLY via new 1G x1 of IBeam port. 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN08) and insert ISM8 x2 into slot 03 & slot 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new x4 RUN of IF cables from new 2x ODU 15G XMC_5D Pro, Sub A&B_Hi to new RTN910AF(RTN08) slot 03(ISM8 Port 1 & 2) and slot 04(ISM8 Port 1 & 2). 5.Decom existing IF cables from existing 2x ODU 13G XMC-3 23-ODU & 43-ODU to existing RTN910AF(RTN03, NEID 9-20443) slot 03(ISM8 Port 1 & 2). 6.Lay new x2 of IF cables from existing 2x ODU 13G XMC-3 23-ODU & 43-ODU to new RTN910AF(RTN08) slot 07(ISM8 Port 1 & 2). 7.Build new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). 8.Request new Vlan DCN and Vlan Services. 9.Migrate traffic 9028R via new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). | Add new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). Perform Load Balancing. Site Impacted : 9028R. NE_9388B 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN08) and insert ISM8 x2 into slot 03 & slot 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new x4 RUN of IF cables from new 2x ODU 15G XMC_5D Pro, Sub A&B_Hi to new RTN910AF(RTN08) slot 03(ISM8 Port 1 & 2) and slot 04(ISM8 Port 1 & 2). 5.Decom existing IF cables from existing 2x ODU 13G XMC-3 23-ODU & 43-ODU to existing RTN910AF(RTN03, NEID 9-20443) slot 03(ISM8 Port 1 & 2). 6.Lay new x2 of IF cables from existing 2x ODU 13G XMC-3 23-ODU & 43-ODU to new RTN910AF(RTN08) slot 07(ISM8 Port 1 & 2). 7.Build new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). 8.Request new xD Vlan DCN and Vlan Services. 9.Migrate traffic 9028R ONLY via new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). | Add new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). Perform Load Balancing. Site Impacted : 9028R. FE_9366A 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN07) and insert ISM8 x2 into slot 03 & slot 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Lay new x4 RUN of IF cables from new 2x ODU 15G XMC_5D Pro, Sub A&B_Hi to new RTN910AF(RTN07) slot 03(ISM8 Port 1 & 2) and slot 04(ISM8 Port 1 & 2). 5.Build new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). 6.Request new 1G x1 of IBeam port from ZTE IPRAN Team. 7.Request new xD Vlan DCN and Vlan Services. 8.Migrate traffic 9028R ONLY via new 1G x1 of IBeam port. 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN08) and insert ISM8 x2 into slot 03 & slot 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new x4 RUN of IF cables from new 2x ODU 15G XMC_5D Pro, Sub A&B_Hi to new RTN910AF(RTN08) slot 03(ISM8 Port 1 & 2) and slot 04(ISM8 Port 1 & 2). 5.Decom existing IF cables from existing 2x ODU 13G XMC-3 23-ODU & 43-ODU to existing RTN910AF(RTN03, NEID 9-20443) slot 03(ISM8 Port 1 & 2). 6.Lay new x2 of IF cables from existing 2x ODU 13G XMC-3 23-ODU & 43-ODU to new RTN910AF(RTN08) slot 07(ISM8 Port 1 & 2). 7.Build new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). 8.Request new Vlan DCN and Vlan Services. 9.Migrate traffic 9028R via new parallel Huawei MW Link 15G_4+0_28M_256QAM_EPLA(WO CA). | XMC_5D Pro | MDD | 15G | 15G_1.2M(MDD)+Dual Coupler x1 | 15G_1.2M(MDD)+Dual Coupler x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202602260653-GTSB
7213R_HU | Kg.Gelam-Gelam | DU00006616504 | Sabah | Sabah | 4.486020 | 118.657220 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI+Dismantle |  | 18G_2+0_110M_256QAM_EPLA NE_7213R New 18G_1.2M(MDD)x1. Re-use existing RTN910AF(RTN01, NEID 9_23324). New XMC_5D Pro, Sub B_Lo x1. FE_7649B New 18G_0.6M(MDD)x1. New RTN910AF(RTN01). New XMC_5D Pro, Sub B_Hi x1. New CAT6 cable x1. New SFP Module 1G 10Km 1310nm x2(IDU-IDU cascading). New Optical Patchcord with suitable type and length x1. | MW Swap | Existing HW MW Link 7213R-7649B, 18G_1+0_55MHZ_512QAM. MW Swap HW MW Link 7213R-7649B, 18G_2+0_110MHZ_256QAM_EPLA. Later, decom existing HW MW Link 7213R-7649B, 18G_1+0_55MHZ_512QAM. Anyway, do not decom RTN910AF(RTN01, NEID 9-23324) at 7213R and RTN910AF(RTN03, NEID 9-43519) at 7649B. Site Impacted : 7213R. NE_7213R. 1.Install new 18G_1.2M(MDD)x1. 2.Re-use existing RTN910AF(RTN01, NEID 9_23324). 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Build new HW MW Link 7213R-7649B, 18G_2+0_110MHZ_256QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffics 7213R via new HW MW Link 7213R-7649B, 18G_2+0_110MHZ_256QAM_EPLA. 7.Later, decom existing HW MW Link 7213R-7649B, 18G_1+0_55MHZ_512QAM. Anyway, do not decom RTN910AF(RTN01, NEID 9-23324) at 7213R and RTN910AF(RTN03, NEID 9-43519) at 7649B. FE_7649B. 1.Install new 18G_0.6M(MDD)x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Build new HW MW Link 7213R-7649B, 18G_2+0_110MHZ_256QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910AF(RTN01). 6.Insert Optical SFP Module 1G 10Km 1310nm into port 8-EM6-5 of existing RTN910AF(RTN03, NEID 9-43519). Enable and configure it. 7.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN01) and port 8-EM6-5 of existing RTN910AF(RTN03, NEID 9-43519). 8.Re-use existing xD Vlan DCN and Vlan Services. 9.Migrate traffics 7213R via existing port at IBeam(CP 7209A) similar to existing traffics such as 7649B, 7230C & 7801E. 10.Later, decom existing HW MW Link 7213R-7649B, 18G_1+0_55MHZ_512QAM. Anyway, do not decom RTN910AF(RTN01, NEID 9-23324) at 7213R and RTN910AF(RTN03, NEID 9-43519) at 7649B. | Existing HW MW Link 7213R-7649B, 18G_1+0_55MHZ_512QAM. MW Swap HW MW Link 7213R-7649B, 18G_2+0_110MHZ_256QAM_EPLA. Later, decom existing HW MW Link 7213R-7649B, 18G_1+0_55MHZ_512QAM. Anyway, do not decom RTN910AF(RTN01, NEID 9-23324) at 7213R and RTN910AF(RTN03, NEID 9-43519) at 7649B. Site Impacted : 7213R. NE_7213R. 1.Install new 18G_1.2M(MDD)x1. 2.Re-use existing RTN910AF(RTN01, NEID 9_23324). 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Build new HW MW Link 7213R-7649B, 18G_2+0_110MHZ_256QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffics 7213R via new HW MW Link 7213R-7649B, 18G_2+0_110MHZ_256QAM_EPLA. 7.Later, decom existing HW MW Link 7213R-7649B, 18G_1+0_55MHZ_512QAM. Anyway, do not decom RTN910AF(RTN01, NEID 9-23324) at 7213R and RTN910AF(RTN03, NEID 9-43519) at 7649B. | Existing HW MW Link 7213R-7649B, 18G_1+0_55MHZ_512QAM. MW Swap HW MW Link 7213R-7649B, 18G_2+0_110MHZ_256QAM_EPLA. Later, decom existing HW MW Link 7213R-7649B, 18G_1+0_55MHZ_512QAM. Anyway, do not decom RTN910AF(RTN01, NEID 9-23324) at 7213R and RTN910AF(RTN03, NEID 9-43519) at 7649B. Site Impacted : 7213R. FE_7649B. 1.Install new 18G_0.6M(MDD)x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Build new HW MW Link 7213R-7649B, 18G_2+0_110MHZ_256QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910AF(RTN01). 6.Insert Optical SFP Module 1G 10Km 1310nm into port 8-EM6-5 of existing RTN910AF(RTN03, NEID 9-43519). Enable and configure it. 7.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN01) and port 8-EM6-5 of existing RTN910AF(RTN03, NEID 9-43519). 8.Re-use existing xD Vlan DCN and Vlan Services. 9.Migrate traffics 7213R via existing port at IBeam(CP 7209A) similar to existing traffics such as 7649B, 7230C & 7801E. 10.Later, decom existing HW MW Link 7213R-7649B, 18G_1+0_55MHZ_512QAM. Anyway, do not decom RTN910AF(RTN01, NEID 9-23324) at 7213R and RTN910AF(RTN03, NEID 9-43519) at 7649B. | XMC_5D Pro | MDD | 18G | 18G_1.2M(MDD)x1 | 18G_0.6M(MDD)x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202602260632-GTSB
2802C_HU | KwsPerindustrian Sg Buloh (EB) | DU00006616505 | Central | Selangor | 3.184098 | 101.554570 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 2802C-2361A ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM_954MBPS IMPACTED SITE: 2802C | MW REMOTE UPGRADE LINK 2802C-2361A ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM_954MBPS IMPACTED SITE: 2802C | MW REMOTE UPGRADE LINK 2802C-2361A ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM_954MBPS IMPACTED SITE: 2802C | XMC3 | MAC | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602260549-GCI | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
4559D_AD | Sri SaujanaMacallum | DU00006722821 | Northern | Penang | 5.408275 | 100.334200 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | 23G_2+0_56M. NE_4559D. 23G_DP_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub A & B_Hi x1. FE_4039A. 23G_DP_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub A & B_Lo x1. | MW Parallel Link | Existing link 23G_1+0_112M Install parallel link 23G_2+0_56M. Site Impacted : 4559D. NE_4559D. 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 4559D_RTN01 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW link. FE_4039A. 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 4039A_RTN01 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW link. | Existing link 23G_1+0_112M Install parallel link 23G_2+0_56M. Site Impacted : 4559D. NE_4559D. 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 4559D_RTN01 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW link. | Existing link 23G_1+0_112M Install parallel link 23G_2+0_56M. Site Impacted : 4559D. FE_4039A. 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 4039A_RTN01 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202605050374-GCI | GCI | SQ202604230170-GCI // SQ202604230175-GCI // SQ202604280634-GCI |  |  | Ongoing | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041473 |  | 2026-04-15 | 2026-04-17 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-20 | 2026-04-30 | 2026-04-20 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-04-20 | 2026-04-30 | 2026-04-20 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-28 | 2026-04-20 | 2026-04-30 | 2026-04-20 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-10-09: 2026-04-20; 2025-10-09: 2026-04-30; 2025-10-09: 2026-04-20; 2025-10-13: 2026-04-21 | [7 empty] | GCI | SQ202604100697-GCI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | CHEONG/SENG/WAH/7018000306
1401B_AD | PUAS LestariPuchong (KJS) | DU00006722822 | Central | Selangor | 2.992849 | 101.658633 | [7 empty] | 01. Pending Planning |  | TSS+AA+TI |  | 23G_2+0_112M. NE_1401B 23G_DP_0.6M (MAC) x1. ISM8 x1. XMC_3E , Sub A & B_Lo x1. FE_1311B. 23G_DP_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub A & B_Hi x1. | MW Parallel Link | Existing link 18G_2+0_112M Install parallel link 23G_2+0_112M. Site Impacted : 1401B , 3904B , 1045C , 2649B , 1228H , 1673H NE_1401B 1.Install new 23G_DP_0.6M (MAC). 2.Reuse existing 1401B_RTN07 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new Parallel link. 7.No decom MW link. FE_1311B. 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 1311B_RTN03 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new Parallel link. 7.No decom MW link. | Existing link 18G_2+0_112M Install parallel link 23G_2+0_112M. Site Impacted : 1401B , 3904B , 1045C , 2649B , 1228H , 1673H NE_1401B 1.Install new 23G_DP_0.6M (MAC). 2.Reuse existing 1401B_RTN07 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new Parallel link. 7.No decom MW link. | Existing link 18G_2+0_112M Install parallel link 23G_2+0_112M. Site Impacted : 1401B , 3904B , 1045C , 2649B , 1228H , 1673H FE_1311B. 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 1311B_RTN03 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new Parallel link. 7.No decom MW link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050106 |  | 2026-05-04 | 2026-05-06 | Completed | 2026-05-01 | 2026-05-04 | 2026-05-04 | 2026-05-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202604100691-GCI | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | CHEONG/SENG/WAH/7018000306
4427D-4462A | Taman Simpang | DU00003318213 | Northern | Perak | 4.827601 | 100.709285 | WK05 | JAN 24 | WK08 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB BAND B HI FE: 1X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB BAND B LO | MW Swap | NE 1. REUSE EXISTING RTN01 7-ISM8-1 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXITING LINK EXCEPT IDU FE 1. REUSE EXISTING RTN01 7-ISM8-1 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXITING LINK EXCEPT IDU | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402200883-GCI | 2024-03-31 | 2024-03-27 | Completed | 2024-01-29 | 2024-01-30 | 2024-01-30 | 2024-01-30 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-11 | 2024-02-29 | 2024-02-11 | 2024-02-23 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020356 |  | 2024-02-06 | 2024-02-13 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-23 | 2024-02-29 | 2024-02-23 | 2024-02-26 | MAT//SAFAREED BIN MAT DESA/6800000177 | GCI TI | 2024-02-23 | 2024-02-29 | 2024-02-23 | 2024-02-25 | MAT//SAFAREED BIN MAT DESA/6800000177 | GCI TI | 2024-02-25 | 2024-02-25 | 2024-02-25 | 2024-02-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-23 | 2024-02-29 | 2024-02-23 | 2024-03-12 | MAT//SAFAREED BIN MAT DESA/6800000177 | 2024-02-23 | 2024-02-29 | 2024-02-23 | 2024-02-27 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
7309C-7936A | Madai Baturong | DU00003318214 | Sabah | Sabah | 4.740330 | 118.131430 | WK05 | JAN 24 | WK08 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_1.2,1.2 DP_28Mhz | MW Swap | [8 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202403220526-NR Services | 2024-02-09 | 2024-02-07 | Completed | 2024-01-25 | 2024-01-31 | 2024-01-28 | 2024-01-28 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-06 | 2024-02-09 | 2024-02-06 | 2024-02-06 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-09 | 2024-02-07 | 2024-02-07 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240219A2 |  | 2024-02-20 | 2024-02-20 | Completed | 2024-02-19 | 2024-02-20 | 2024-02-19 | 2024-02-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-02-21 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-02-24 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-05 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-02-27 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-02-23 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
4674C-4048A | Lorong Semarak Api | DU00003318215 | Northern | Penang | 5.385900 | 100.283400 |  |  | WK04 | JAN 24 | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC |  | MW Remote Upgrade | [8 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-01-22 | 2024-01-27 | 2024-01-23 | 2024-01-23 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
1152A-1154A | Sekinchan Town | DU00003318216 | Central | Selangor | 3.508017 | 101.101988 | WK05 | JAN 24 | WK08 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6m/0.6m_MDD_1+0_112Mhz_512Q(XMC5D sub B) | MW Swap | MW SWAP MW LINK 1152A-1154A WITH HUAWEI_18G_1+0_112MHZ_0.6M NE: 1. INSTALL NEW IDU RTN 910A 2. INSTALL NEW 18G 0.6M MDD DP ANTENNA 3. INSTALL NEW 18G 112MHZ XMC-5D ODU SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN 910A 2. INSTALL NEW 18G 0.6M MDD DP ANTENNA 3. INSTALL NEW 18G 112MHZ XMC-5D ODU SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK | [7 empty] | Nera | SQ202402140179-Nera | Nera | SQ202402190127-Nera | 2024-04-26 | 2024-04-29 | Completed | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | MOHD//KHALID IZHAR BIN SUBOH/7670000009 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-08 | 2024-02-08 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2024-03-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2024-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020141 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  |  | Assigned | Completed |  | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-20 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-20 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-22 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-20 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4969A-4968A | Sungai Kob | DU00003318217 | Northern | Kedah | 5.429180 | 100.644020 | WK04 | JAN 24 | WK32-WK35 | AUG 24 | TI | MOS TI In Plan | ZTE | 00. Integrated/RFS Done | 6/3/2024 : MW Parallel Link. Risk to proceed TI. Pending request PTW Celcom. EB CRQ rejected 0127 Pending TSSR submission from GCI | TSS+AA+TI | L1+ATP+PAC | NE: 1X RTN 910A 2X ISM8 CARD 1X 15G 1.2M MDD ANTENNA 1X 15G XMC-5D SUB BAND A LO FE: 1X RTN 910A 2X ISM8 CARD 1X 15G 1.2M MDD ANTENNA 1X 15G XMC-5D SUB BAND A HI | MW Parallel Link | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/1/3 NE 1. INSTALL NEW RTN 910A + 2 ISM8 CARDS 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 2+0 28MHZ 5. SHIFT EXISTING 15 2+0 IF CABLE AD CONFIGURATION FROM RTN01 7-ISM6 TO NEW RTN 910A 3-ISM8 6. SHIFT EXISTING 13 2+0 IF CABLE AD CONFIGURATION FROM RTN01 3-ISV3 & 4-ISV3 TO NEW RTN 910A 4-ISM8 7. EPLA NEW 15G 2+0 WITH EXISTING 15G 2+0 & 13G 2+0 8. DISMANTLE UNUSED EXISTING IDU FE 1. INSTALL NEW RTN 910A + 2 ISM8 CARDS 2. PATCH NEW RTN 910A TO NEW CP PORT 3. INSTALL NEW 15G 1.2M MDD ANTENNA 4. INSTALL NEW 15G XMC-5D SUB BAND B 5. CONFIGURE LINK 15G 2+0 28MHZ 6. SHIFT EXISTING 15 2+0 IF CABLE AD CONFIGURATION FROM RTN02 7-ISM6 TO NEW RTN 910A 3- ISM8 7. SHIFT EXISTING 13 2+0 IF CABLE AD CONFIGURATION FROM RTN02 3-ISV3 & 4-ISV3 TO NEW RTN 910A 4-ISM8 8. EPLA NEW 15G 2+0 WITH EXISTING 15G 2+0 & 13G 2+0 9. DISMANTLE UNUSED EXISTING IDU | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402220010-GCI // SQ202508140738-GCI | 2024-08-21 | 2024-11-28 | Completed | 2024-01-31 | 2024-01-31 | 2024-01-26 | 2024-01-26 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-11 | 2024-02-29 | 2024-02-11 | 2024-02-23 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020907 |  | 2024-02-10 | 2024-02-13 | Completed | 2024-02-09 | 2024-02-10 | 2024-02-09 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-06-20 | 2024-06-27 | 2024-06-20 | 2025-06-14 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-06-20 | 2024-09-30 | 2024-06-20 | 2025-07-06 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-06-20 | 2024-06-27 | 2024-06-20 | 2026-02-07 | ANWAR//BIN ABDUL RASID/6800000149 | 2025-10-09: 2024-06-20; 2025-10-09: 2024-06-27; 2025-10-09: 2024-06-20; 2025-10-13: 2025-05-16 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402
3002A-1099A | pBTS Pahang Pharmacy | DU00003318218 | Central | Selangor | 3.116031 | 101.447534 | WK07 | FEB 24 | WK11 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_0.6m&0.6m_SP_1+0_112MHz | MW Swap | DCN VLAN : 415, PORT NUMBER : GigabitEthernet0/3/1 MW SWAP Huawei 23G 1+0 112Mhz NE: 1- Install Swap Existing IDU 910A. 2- Install New 1+0 XMC-3 ODU. 3- Install New 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- Patch 3002A BBU to new link. 6- Dismantle existing SM Microwave Link FE: 1- Install New IDU 910A. 2- Install New 1+0 XMC-3 ODU. 3- Install New 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- To provide new port at PTN. Required DCN VLAN. 6- Dismantle existing SM Microwave Link | [7 empty] | Ascentrack | SQ202402190087-Ascentrack | Ascentrack | SQ202402270713-Ascentrack | 2024-09-27 | 2024-09-25 | Completed | 2024-02-02 | 2024-02-02 | 2024-02-15 | 2024-02-15 | Nor//Syamsyairi Bin Hashim/7539000044 |  | ASCENTRACK SDN. BHD. |  | Unassigned | Completed |  | 2024-02-17 | 2024-02-18 | 2024-02-17 | 2024-02-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-02-17 | 2024-02-18 | 2024-02-17 | 2024-02-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-09-25 | 2024-09-27 | 2024-09-25 | 2024-09-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021425 |  | 2024-02-15 | 2024-02-23 | Completed | 2024-02-14 | 2024-02-15 | 2024-02-14 | 2024-02-23 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-26 | 2024-02-29 | 2024-02-26 | 2024-05-29 | Nor//Syamsyairi Bin Hashim/7539000044 | Ascentrack TI | 2024-02-26 | 2024-02-29 | 2024-02-26 | 2024-04-30 | Nor//Syamsyairi Bin Hashim/7539000044 | Ascentrack TI | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-02-26 | 2024-02-29 | 2024-02-26 | 2024-09-24 | Nor//Syamsyairi Bin Hashim/7539000044 | 2024-02-26 | 2024-02-29 | 2024-02-26 | 2024-02-27 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7676B-7192A | TM Tawau | DU00003318219 | Sabah | Sabah | 4.253079 | 117.887907 | WK04 | JAN 24 | WK19 | MAY 24 | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | 9/5: D3: Cutover done 3/5: Pending EB CRQ approval | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_0.6,0.6SP_112Mhz | MW Swap | [8 empty] | Seri Pancar | SQ202402130369-Seri Pancar | GTSB | SQ202409120182-GTSB | 2024-09-20 | 2024-09-19 | Completed | 2024-01-27 | 2024-01-31 | 2024-01-26 | 2024-01-26 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-01-30 | 2024-01-31 | 2024-01-30 | 2024-01-30 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-30 | 2024-01-31 | 2024-01-23 | 2024-01-30 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240405B8 |  | 2024-04-06 | 2024-04-15 | Completed | 2024-04-05 | 2024-04-06 | 2024-04-05 | 2024-04-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-06 | 2024-05-31 | 2024-05-06 | 2024-05-08 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-05-06 | 2024-05-31 | 2024-05-06 | 2024-05-08 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-16 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2024-05-06 | 2024-05-31 | 2024-05-06 | 2024-05-13 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | 2024-05-06 | 2024-05-31 | 2024-05-06 | 2024-05-08 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-05-27 | tseping//wang/6819000006 | Logistic Team | 2024-07-26 | 2024-08-26 | 2024-07-26 | 2024-07-26 | ASTI//GANIS PUTRIANI/6237001358
4570C-4405A | Kg Cina Pasir Panjang | DU00003318220 | Northern | Perak | 4.195438 | 100.683499 | WK05 | JAN 24 | WK09 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1X RTN 910A 1X 23G 0.6M ANTENNA 1X 23G XMC-3 SUB BAND A LO FE: 1X RTN 910A 1X 23G 0.6M ANTENNA 1X 23G XMC-3 SUB BAND A HI | MW Swap | NE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M ANTENNA 3. INSTALL NEW 1+0 23G 112MHZ XMC-3 SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. DISMANTLE EXISTING SM LINK FE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M ANTENNA 3. INSTALL NEW 1+0 23G 112MHZ XMC-3 SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. DISMANTLE EXISTING SM LINK | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402200883-GCI | 2024-03-31 | 2024-03-27 | Completed | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-11 | 2024-02-29 | 2024-02-11 | 2024-02-23 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020908 |  | 2024-02-10 | 2024-02-13 | Completed | 2024-02-09 | 2024-02-10 | 2024-02-09 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-02-21 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-02-26 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-03-08 | ANWAR//BIN ABDUL RASID/6800000149 | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-03-04 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
1132C-1099A | Jalan Khamis | DU00003318222 | Central | Selangor | 3.130615 | 101.428167 | WK07 | FEB 24 | WK08 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI | L1+ATP+PAC | 18G_0.6/0.6 SP MDD_1+0_110MHZ_SUB A | MW Parallel Link | MW Parallel Huawei 18G 1+0 112Mhz 1132C-1099A to carry traffic of 1132C BBU only NE: 1) Install new RTN910A (RTN02) 2) Install new 18G 1+0 112MHz at RTN02 7-ISM8 3) Migrate 1132C BBU only to new link FE: 1) Install new RTN910A (ops team to assign new RTN number) 2) Install new 18G 1+0 112MHz at new RTN 7-ISM8 3) Migrate 1132C BBU only to new link 4) Patch new IDU to new CP port and establish new DCN | [7 empty] | Ascentrack | SQ202402190087-Ascentrack | Ascentrack | SQ202402270713-Ascentrack | 2024-03-01 | 2024-03-05 | Completed | 2024-02-06 | 2024-02-06 | 2024-02-15 | 2024-02-15 | Nor//Syamsyairi Bin Hashim/7539000044 |  | ASCENTRACK SDN. BHD. |  | Unassigned | Completed |  | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | Nor//Syamsyairi Bin Hashim/7539000044 |  | ASCENTRACK SDN. BHD. |  | Unassigned | Completed |  | 2024-02-20 | 2024-02-21 | 2024-02-20 | 2024-02-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-02-28 | 2024-03-01 | 2024-02-28 | 2024-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021017 |  | 2024-02-12 | 2024-02-16 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-02-16 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-17 | 2024-02-29 | 2024-02-17 | 2024-02-22 | MUHAMMAD NUR IZZUDDIN BIN MUHAMED MAZLAN7539000041 | Ascentrack TI | 2024-02-17 | 2024-02-29 | 2024-02-17 | 2024-02-21 | MUHAMMAD NUR IZZUDDIN BIN MUHAMED MAZLAN7539000041 | Ascentrack TI | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-17 | 2024-02-29 | 2024-02-17 | 2024-02-22 | MUHAMMAD NUR IZZUDDIN BIN MUHAMED MAZLAN7539000041 | 2025-10-09: 2024-02-17; 2025-10-09: 2024-02-29; 2025-10-09: 2024-02-17; 2025-10-13: 2024-02-17 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
9274B-9384A | Jalan Tekam | DU00003318223 | Sarawak | Sarawak | 2.286270 | 111.840739 | WK05 | JAN 24 | WK13 | MAR 24 | RFS | Pending plan | ZTE | 00. Integrated/RFS Done | 28/3: D2: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_0.6,0.6SP_112Mhz | MW Swap | [8 empty] | Trintel | SQ202402130359-Trintel | Datasco | SQ202404030681-Datasco | 2024-03-22 | 2024-03-23 | Completed | 2024-01-26 | 2024-01-27 | 2024-01-27 | 2024-01-29 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-23 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240314BF |  | 2024-03-15 | 2024-03-20 | Completed | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-26 | 2024-03-30 | 2024-03-26 | 2024-03-28 | Chiew Hua Kai7019000037 | Datasco TI | 2024-03-26 | 2024-03-30 | 2024-03-26 | 2024-04-13 | Chiew Hua Kai7019000037 | Datasco TI | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-26 | 2024-03-30 | 2024-04-24 | 2024-04-24 | Chiew Hua Kai7019000037 | 2024-03-26 | 2024-03-30 | 2024-03-29 | 2024-03-29 | 2024-04-28 | 2024-04-28 | 2024-04-28 | 2024-04-28 | CHONG QIEW LEK7018000038 | Logistic Team | 2024-07-30 | 2024-08-30 | 2024-07-30 | 2024-07-30 | ASTI//GANIS PUTRIANI/6237001358
4587D-4073B | General Hospital (REL) | DU00003318224 | Northern | Penang | 5.417801 | 100.310089 | WK04 | JAN 24 | WK08 | FEB 24 | RFS | Pending L1 | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6m&0.6m_DP_1+0_110MHz | MW Swap | NE 1- Install new ISM8 at exisitng RTN910A RTN01 Slot 3. 2- Swap existing XMC-3 ODU to new XMC-5D ODU. 3- Swap exsiting antenna to new 0.6m MDD antenna . 4- Configure link 1+0_900M_512QAM_110MHz. 5- Patch 4587D BBU to new link. FE 1- Install new ISM8 at exisitng RTN910A RTN01 Slot 3. 2- Swap existing XMC-3 ODU to new XMC-5D ODU. 3- Swap exsiting antenna to new 0.6m MDD antenna . 4- Configure link 1+0_900M_512QAM_110MHz. | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402160379-GCI // SQ202406260407-GCI | 2024-03-31 | 2024-03-27 | Completed | 2024-01-29 | 2024-01-29 | 2024-01-26 | 2024-01-26 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-09 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-11 | 2024-02-29 | 2024-02-11 | 2024-02-23 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020911 |  | 2024-02-10 | 2024-02-13 | Completed | 2024-02-09 | 2024-02-10 | 2024-02-09 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | 2024-02-27 | 2024-02-28 | 2024-02-21 | 2024-02-29 | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-27 | 2024-02-28 | 2024-03-18 | 2024-03-18 | MUHAMAD ARIFF BIN KHASIM6800000179 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-02-29 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
3103A-1103A | Tengku Kelana (REL) | DU00003318225 | Central | Selangor | 3.041157 | 101.447541 | WK05 | JAN 24 | WK11 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | D2: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_0.6m&0.6m_SP_1+0_112MHz | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/1/3 NE 1- Swap existing HW RTN950 to new RTN910A. 2- Swap existing HW XMC-2 ODU to new XMC-3 ODU. 3- Swap exsting HW 0.3m Antenna to new 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- Patch 3103A BBU to new link. FE 1- Swap existing HW RTN950 to new RTN910A. 2- Swap existing HW XMC-2 ODU to new XMC-3 ODU. 3- Swap exsting HW 0.3m Antenna to new 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- To provide new port at PTN. Required DCN VLAN. | [7 empty] | Nera | SQ202402140179-Nera | Nera | SQ202402270732-Nera | 2024-06-15 | 2024-06-14 | Completed | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | MOHD//KHALID IZHAR BIN SUBOH/7670000009 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-08 | 2024-02-08 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-03-05 | 2024-03-06 | 2024-03-05 | 2024-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-06-14 | 2024-06-15 | 2024-06-14 | 2024-06-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021433 |  | 2024-02-15 | 2024-03-18 | Completed | 2024-02-14 | 2024-02-15 | 2024-02-14 | 2024-03-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  |  | Assigned | Completed |  | 2024-03-14 | 2024-03-31 | 2024-03-18 | 2024-03-18 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-18 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-19 | AZIZAH//BINTI A.RAHMAN/7670000012 | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-16 | 2024-10-24 | 2024-10-24 | 2024-10-24 | 2024-10-24 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7318B-7634A | Taman Sinar Jaya 2 | DU00003318226 | Sabah | Sabah | 6.192519 | 116.209251 | WK02 | JAN 24 | WK14 | APR 24 | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | 4/4: D2: Cutover done 3/4: MOS & TI In Plan 4/4 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_0.6,1.2 SP_110Mhz | MW Swap | [8 empty] | Magicell | SQ202402130373-Magicell | NR services | SQ202404030679-NR Services | 2025-10-24 | 2025-10-29 | Completed | 2024-01-12 | 2024-01-12 | 2024-01-12 | 2024-01-13 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. |  | Unassigned | Completed |  | 2024-01-20 | 2024-01-20 | 2024-01-20 | 2024-01-24 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-22 | 2024-01-26 | 2024-01-24 | 2024-01-24 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-29 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24032847 |  | 2024-03-29 | 2024-03-30 | Completed | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-03-30 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-30 | 2024-04-06 | 2024-03-30 | 2024-04-03 | RONNEY//LOUIS LUSIN/7167000022 | NR Service TI | 2024-03-30 | 2024-04-06 | 2024-03-30 | 2024-04-03 | RONNEY//LOUIS LUSIN/7167000022 | NR Service TI | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-04-03 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2024-03-30 | 2024-04-06 | 2024-03-30 | 2024-04-05 | RONNEY//LOUIS LUSIN/7167000022 | 2024-03-30 | 2024-04-06 | 2024-03-30 | 2024-04-02 | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-04-29 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
1986A-1610B | Klang Utara(TMTouch) | DU00003318227 | Central | Selangor | 3.028889 | 101.371722 |  | MAY 24 | WK19 | MAY 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 24/5: D2: Cutover done 23/5: D2: Continue TI, Pending FE E CRQ approval 15/5: D1: TI NE done, FE Pending EB CRQ approval | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6m&0.6m_DP_1+0_110MHz | MW Swap | DCN VLAN : 416, PORT NUMBER : GigabitEthernet0/1/3 NE 1- Install Swap Existing IDU 910A. 2- Install New 1+0 XMC-5D ODU. 3- Install New 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- Patch 1986A BBU to new link. 6- Dismantle existing SM Microwave Link FE 1- Install New IDU 910A. 2- Install New 1+0 XMC-5D ODU. 3- Install New 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- To provide new port at PTN. Required DCN VLAN. 6- Dismantle existing SM Microwave Link | [7 empty] | Datasco | SQ202411140206-Datasco | Datasco | SQ202506110832-Datasco // SQ202506110835-Datasco |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24041713 |  | 2024-02-15 | 2024-03-18 | Completed | 2024-02-14 | 2024-02-15 | 2024-02-14 | 2024-03-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-31 | 2026-01-22 | 2026-01-22 | HERRY//BELLYJOE RUAB/7019000030 | Datasco TI | [6 empty] | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-08-30 | C.PRATHABAN///6798000081 | [7 empty] | 2024-05-07: 2025-11-30; 2024-05-07: 2025-11-30; 2024-05-07: 2025-11-30; 2024-05-07: 2025-11-30 | NG HONG JIE7018000036 | Logistic Team | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402 |  | Assign Subcon
2724A-1110A | Kebun Batu 7 | DU00003318228 | Central | Selangor | 2.972731 | 101.516488 | WK08 | FEB 24 | WK08 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6m&0.6m_DP_1+0_110MHz | MW Swap | DCN VLAN : 416, PORT NUMBER : GigabitEthernet0/2/20 NE 1- Install Swap Existing IDU 910A. 2- Install New 1+0 XMC-5D ODU. 3- Install New 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- Patch 2724A BBU to new link. 6- Dismantle existing SM Microwave Link FE 1- Install New IDU 910A. 2- Install New 1+0 XMC-5D ODU. 3- Install New 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- To provide new port at PTN. Required DCN VLAN. 6- Dismantle existing SM Microwave Link | [7 empty] | Allstar | SQ202402270775-Allstar | Allstar | SQ202402190097-Allstar // SQ202510070055-Allstar | 2024-06-26 | 2024-06-25 | Completed | 2024-02-19 | 2024-02-23 | 2024-02-19 | 2024-02-19 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-02-22 | 2024-02-22 | 2024-02-23 | 2024-02-23 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-05-24 | 2024-05-25 | 2024-05-24 | 2024-05-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-06-25 | 2024-06-26 | 2024-06-25 | 2024-06-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021010 |  | 2024-02-12 | 2024-02-15 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-02-15 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-19 | ISTIKHAR//AHMAD/6798000193 | Allstar TI | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-20 | ISTIKHAR//AHMAD/6798000193 | Allstar TI | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-03-05 | ISTIKHAR//AHMAD/6798000193 | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-19 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
2615A-7282A | pBTS Kg Getisan | DU00003318229 | Sabah | Sabah | 6.094324 | 116.122774 | WK04 | JAN 24 | WK10 | MAR 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6m&0.6m_DP_2+0_56MHz | MW Swap | [8 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202403220526-NR Services | 2024-02-09 | 2024-02-07 | Completed | 2024-01-21 | 2024-01-21 | 2024-01-21 | 2024-01-21 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-05 | 2024-02-09 | 2024-02-05 | 2024-02-05 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-05 | 2024-02-09 | 2024-02-05 | 2024-02-05 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-09 | 2024-02-07 | 2024-02-07 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24030472 |  | 2024-03-05 | 2024-03-05 | Completed | 2024-03-04 | 2024-03-05 | 2024-03-04 | 2024-03-05 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-07 | NEVILLE JUDE RONNIE7167000013 | NR Service TI | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-07 | NEVILLE JUDE RONNIE7167000013 | NR Service TI | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-08 | NEVILLE JUDE RONNIE7167000013 | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-06 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-03-19 | tseping//wang/6819000006 | Logistic Team | 2024-07-26 | 2024-08-26 | 2024-07-26 | 2024-07-26 | ASTI//GANIS PUTRIANI/6237001358
7005D-7064A | Taman Jutaya | DU00003318230 | Sabah | Sabah | 5.368897 | 116.182879 |  |  | WK03 | JAN 24 | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC |  | MW Remote Upgrade | [8 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-01-18 | 2024-01-18 | 2024-01-18 | 2024-01-18 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 | [17 empty] | 2024-07-26 | 2024-08-26 | 2024-07-26 | 2024-07-26 | ASTI//GANIS PUTRIANI/6237001358
1200B-1094A | Jln Besar | DU00003318231 | Central | Selangor | 3.140930 | 101.368380 |  | MAR 24 | WK14 | APR 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 6/5: Pending TX Ops declare CO done 3/5: Report site vandalism. Missing IDU Card 26/4: D3: Cutover done 25/4: D2: TI done, T/shooting RSL (raining). Continue 26/4 24/4: D1: TI WIP 23/4: Material collection from Ascentrack. MOS TI 24/4 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_0.6,0.6_110Mhz | MW Swap | NE 1- Install IDU 910A. 2- Install 1+0 ODU. 3- Swap 0.6m Antenna with new HW 0.6m Antenna. 4- Configure link 1+0_889M_512QAM FE 1- New IDU 910A. 2- Install 1+0 ODU 3- Swap 0.6m Antenna with new HW 1.2m Antenna. 4- Configure link 1+0_889M_512QAM. 5- To provide new port at PTN. Required DCN VLAN | [7 empty] | Datasco | SQ202407050112-Datasco | Datasco | SQ202411040292-Datasco // SQ202411180542-Datasco | 2024-04-25 | 2024-04-25 | Completed | 2024-04-25 | 2024-04-25 | 2024-04-25 | 2024-04-25 | Ezwan Bin Muhamad7019000134 |  | DATASCO SDN. BHD. |  | Unassigned | Completed | [9 empty] | Unassigned | Disabled | [9 empty] | Unassigned | Disabled | [9 empty] | Unassigned | Disabled |  |  | DOWMY24020126 |  | 2024-02-02 | 2024-03-16 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-03-16 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-23 | 2024-04-30 | 2024-04-23 | 2024-05-02 | Muhammad//Syarul Nizwa bin Mohd Nor/7019000049 | Datasco TI | 2024-04-23 | 2024-04-30 | 2024-04-23 |  | Muhammad//Syarul Nizwa bin Mohd Nor/7019000049 | Datasco TI | 2024-04-25 | 2024-04-26 | 2024-04-26 | 2024-04-26 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-04-23 | 2024-04-30 | 2024-04-23 |  | Muhammad//Syarul Nizwa bin Mohd Nor/7019000049 | 2024-04-23 | 2024-04-30 | 2024-04-23 | 2024-05-12 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | NG HONG JIE7018000036 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
3569B-1071A | Sg Rasau Toll Shoplot | DU00003318232 | Central | Selangor | 3.063792 | 101.488243 | WK07 | MAR 24 | WK14 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 23/10: Interim solution: To proceed with SW Upgrade activity 18/10: HU Cases still open 2/4: D2: Cutover done | TSS+AA+TI | L1+ATP+PAC | 15G_0.6/1.2_DP_4+0_28MHZ | MW Parallel Link | Change from [NE 1) Install new RTN910A (ops team to assign new RTN number) 2) Install new 15G 4+0 28MHz at new RTN 3-ISM8 and 4-ISM8 with CA 3) Migrate 3569B BBU only to new link FE] to [NE 1) Install new RTN910A (ops team to assign new RTN number) 2) Install new 15G 4+0 28MHz at new RTN 3-ISM8 and 4-ISM8 with CA 3) Migrate 3569B BBU only to new link FE 1) Install new RTN910A (ops team to assign new RTN number) 2) Install new 15G 4+0 28MHz at new RTN 3-ISM8 and 4-ISM8 with CA 3) Migrate 3569B BBU only to new link 4) Patch new IDU to new CP port and establish new DCN] | [7 empty] | Nera | SQ202402190091-Nera | Perwira | SQ202409120151-Perwira | 2024-12-04 | 2024-12-03 | Completed | 2024-02-07 | 2024-02-07 | 2024-02-14 | 2024-02-14 | MOHD//KHALID IZHAR BIN SUBOH/7670000009 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-05-17 | 2024-05-18 | 2024-05-17 | 2024-05-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-17 | 2024-05-18 | 2024-05-17 | 2024-05-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-12-03 | 2024-12-04 | 2024-12-03 | 2024-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021903 |  | 2024-02-20 | 2024-03-13 | Completed | 2024-02-19 | 2024-02-20 | 2024-02-19 | 2024-03-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-31 | 2024-04-06 | 2024-03-31 | 2024-04-04 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-31 | 2024-04-06 | 2024-03-31 | 2024-04-30 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-08 | C.PRATHABAN///6798000081 |  |  | 2024-03-31 | 2024-04-06 | 2024-03-31 | 2024-05-21 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-02-27: 2024-03-31; 2024-02-28: 2024-04-06; 2024-02-29: 2024-03-31; 2024-02-29: 2024-04-01 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
3778A-1157A | Jalan Tebuk Sri Makmur | DU00003318233 | Central | Selangor | 3.632969 | 101.042631 | WK06 | FEB 24 | WK12 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | D3: Cutover done. RSL rectification | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_0.6m&1.2m_DP_4+0_28MHz | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/13 NE 1- Install new IDU 910A. Install 2x ISM8 Modem. 2- Install new 2x XMC-5D ODU. 3- Install new 0.6m MDD Antenna. 4- Configure link 4+0_900M_512QAM with EPLA. 5- Dismantle existing SM Microwave Link 6- Patch 3778A BBU to new link FE 1- Install new IDU 910A. Install 2x ISM8 Modem. 2- Install new 2x XMC-5D ODU. 3- Install new 1.2m MDD Antenna. 4- Configure link 4+0_900M_512QAM with EPLA. 5- Dismantle existing SM Microwave Link 6- To provide new port at PTN. Required DCN VLAN. | [7 empty] | Nera | SQ202402140179-Nera | Nera | SQ202402270732-Nera | 2024-04-05 | 2024-04-05 | Completed | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-01 | MOHD//KHALID IZHAR BIN SUBOH/7670000009 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-05 | 2024-02-06 | 2024-02-08 | 2024-02-08 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-03-19 | 2024-03-20 | 2024-03-19 | 2024-03-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-04 | 2024-04-05 | 2024-04-04 | 2024-04-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24022215 |  | 2024-02-23 | 2024-03-05 | Completed | 2024-02-22 | 2024-02-23 | 2024-02-22 | 2024-03-05 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-11 | 2024-03-31 | 2024-03-11 | 2024-03-11 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-03-11 | 2024-03-31 | 2024-03-19 | 2024-03-19 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | C.PRATHABAN///6798000081 |  |  | 2024-03-11 | 2024-03-31 | 2024-03-11 | 2024-03-29 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | 2024-03-11 | 2024-03-31 | 2024-03-11 | 2024-03-19 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
9063C-9384B | Klinik Kesihatan Sibujaya | DU00003318234 | Sarawak | Sarawak | 2.245093 | 111.971578 | WK25 | JUN 24 |  |  |  | Pending DO | ZTE | 00. Integrated/RFS Done | 23/7: D4: Cutover done 19/7: D3: Continue TI 17/7: MOS & TI In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_0.6,0.6 SP_110Mhz | MW Swap | NE: 1- Install IDU 910A. 2- Install 1+0 ODU_SB A. 3- Swap 0.6m Antenna. 4- Configure link 1+0_889M_512QAM. FE: 1- Install IDU 910A. 2- Install 1+0 ODU_SB A. 3- Swap 0.6m Antenna. 4- Configure link 1+0_889M_512QAM. | [7 empty] | Trintel | SQ202402130359-Trintel | Datasco | SQ202408070476-Datasco | 2024-03-22 | 2024-03-19 | Completed | 2024-01-29 | 2024-01-30 | 2024-01-30 | 2024-01-31 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-05 | 2024-02-09 | 2024-02-05 | 2024-02-05 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-05 | 2024-02-09 | 2024-02-05 | 2024-02-05 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-19 | 2024-03-22 | 2024-03-19 | 2024-03-19 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24070808 |  | 2024-07-09 | 2024-07-16 | Completed | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-07-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-18 | 2024-07-31 | 2024-07-23 | 2024-07-23 | Chiew Hua Kai7019000037 | Datasco TI | 2024-07-18 | 2024-07-31 | 2024-07-22 | 2024-07-23 | Chiew Hua Kai7019000037 | Datasco TI | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-22 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-07-18 | 2024-07-31 | 2024-08-30 | 2024-08-30 | Chiew Hua Kai7019000037 | 2024-07-18 | 2024-07-31 | 2024-07-20 | 2024-07-20 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-08 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-09-26 | 2024-10-26 | 2024-09-26 | 2024-09-26 | ASTI//GANIS PUTRIANI/6237001358
9143B-9484A | Kg Tungku Housing Kuching | DU00003318235 | Sarawak | Sarawak | 1.576131 | 110.337595 | WK04 | JAN 24 | WK11 | MAR 24 | RFS | Pending L1 | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_0.6,0.6_112Mhz | MW Swap | [8 empty] | Trintel | SQ202402130359-Trintel | Datasco | SQ202403220509-Datasco | 2024-03-22 | 2024-03-19 | Completed | 2024-01-25 | 2024-01-26 | 2024-01-23 | 2024-01-23 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-06 | 2024-02-09 | 2024-02-06 | 2024-02-06 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-06 | 2024-02-09 | 2024-02-06 | 2024-02-06 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-19 | 2024-03-22 | 2024-03-19 | 2024-03-19 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24030699 |  | 2024-03-07 | 2024-03-08 | Completed | 2024-03-06 | 2024-03-07 | 2024-03-06 | 2024-03-08 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-12 | 2024-03-16 | 2024-03-12 | 2024-03-15 | Yeo//Kai Kee/7019000070 | Datasco TI | 2024-03-12 | 2024-03-16 | 2024-03-12 | 2024-03-15 | Yeo//Kai Kee/7019000070 | Datasco TI | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-12 | 2024-03-16 | 2024-03-12 | 2024-03-15 | Yeo//Kai Kee/7019000070 | 2024-03-12 | 2024-03-16 | 2024-03-12 | 2024-03-12 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-04-04 | CHONG QIEW LEK7018000038 | Logistic Team | 2024-07-30 | 2024-08-30 | 2024-07-30 | 2024-07-30 | ASTI//GANIS PUTRIANI/6237001358
2537A-1130A | Kg Kanchong Tengah | DU00003318236 | Central | Selangor | 2.747350 | 101.492730 | WK09 | MAR 24 | WK09 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_1.2,1.2 DP_28Mhz | MW Swap | NE 1- Install IDU 910A.Install 2x ISM8. 2- Install 2x XMC-5D ODU. 3- Swap 0.6m Antenna with new HW 1.2m Antenna. 4- Configure link 4+0_900M_512QAM with EPLA FE 1- New IDU 910A. 2- Install 2x XMC-5D ODU. 3- Swap 0.6m Antenna with new HW 1.2m Antenna. 4- Configure link 4+0_900M_512QAM with EPLA. 5- To provide new port at PTN. Required DCN VLAN | [7 empty] | Nera | SQ202403120266-Nera | Nera | SQ202402190127-Nera | 2024-04-05 | 2024-04-05 | Completed | 2024-02-26 | 2024-03-01 | 2024-02-29 | 2024-02-29 | MOHD//KHALID IZHAR BIN SUBOH/7670000009 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-19 | 2024-03-20 | 2024-03-19 | 2024-03-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-19 | 2024-03-20 | 2024-03-19 | 2024-03-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-04 | 2024-04-05 | 2024-04-04 | 2024-04-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020138 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  |  | Assigned | Completed |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-03-08 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-03-20 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4169B-4054A | Tmn cheeseman | DU00003318237 | Northern | Penang | 5.404485 | 100.303874 | WK09 | MAY 24 | WK20 | JUN 24 | TI | MOS TI In Plan | ZTE | 00. Integrated/RFS Done | 27/6: D3: Cutover done 21/6: D2: TI done, pending cutover due access limited. Pending EB CRQ approval 20/6: MOS & TI WIP, CO plan 21/6 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1X ISM8 CARD 1X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB BAND B LO FE: 1X ISM8 CARD 1X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB BAND B HI | MW Swap | NE 1. INSTALL NEW ISM8 CARD AT RTN02 SLOT 3 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 2+0 56MHZ 5. DISMANTLE EXISTING 2+0 28MHZ LINK FE 1. INSTALL NEW ISM8 CARD AT RTN02 SLOT 3 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 2+0 56MHZ 5. DISMANTLE EXISTING 2+0 28MHZ LINK | [7 empty] | GCI | SQ202409120132-GCI | GCI | SQ202402200883-GCI // SQ202409100506-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-02-26 | 2024-03-01 | 2024-07-05 | 2024-07-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-05 | 2024-07-05 | 2024-07-05 | 2024-07-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020357 |  | 2024-02-06 | 2024-02-13 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-06-20 | 2024-06-30 | 2024-06-19 | 2024-06-20 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-06-20 | 2024-06-30 | 2024-06-19 | 2024-06-20 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-27 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-06-20 | 2024-06-30 | 2024-06-19 | 2024-06-30 | SAFUAN//BIN YUSOFF/6800000178 | 2024-06-20 | 2024-06-30 | 2024-06-19 | 2024-06-20 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
1789A-1093A | Tmn Sri Berembang | DU00003318238 | Central | Selangor | 2.995661 | 101.399395 | WK06 | FEB 24 | WK11 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_0.6,0.6 DP_112Mhz | MW Swap | NE 1- Install IDU 910A. 2- Install 2+0 ODU 3- Swap 0.6m SM Antenna with new 0.6m HW Antenna. 4- Configure link 2+0_900M_512QAM 5. Dismantle existing link 1- New IDU 910A. 2- Install 2+0 ODU 3- Swap 0.6m SM Antenna with new 0.6m HW Antenna. 4- Configure link 12+0_900M_512QAM 5- To provide new port at PTN. Required DCN VLAN FE 6- Dismantle existing link | [7 empty] | Nera | SQ202402140179-Nera | Nera | SQ202402270732-Nera | 2024-05-01 | 2024-05-06 | Completed | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-01 | MOHD//KHALID IZHAR BIN SUBOH/7670000009 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-05 | 2024-02-06 | 2024-02-08 | 2024-02-08 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-03-05 | 2024-03-06 | 2024-03-05 | 2024-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-30 | 2024-05-01 | 2024-04-30 | 2024-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020320 |  | 2024-02-05 | 2024-03-04 | Completed | 2024-02-03 | 2024-02-05 | 2024-02-03 | 2024-03-04 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-09 | 2024-03-16 | 2024-03-12 | 2024-03-12 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | 2024-03-09 | 2024-03-16 | 2024-03-12 | 2024-03-12 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-09 | 2024-03-16 | 2024-03-20 | 2024-03-20 | AZIZAH//BINTI A.RAHMAN/7670000012 | 2024-03-09 | 2024-03-16 | 2024-03-09 | 2024-03-09 | 2025-01-17 | 2025-01-17 | 2025-01-17 | 2025-01-17 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
9102C-9345B | Kg Baru Bintulu | DU00003318239 | Sarawak | Sarawak | 3.163195 | 113.054836 | WK04 | JAN 24 | WK11 | MAR 24 | RFS | Pending compliance | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_0.6,0.6 DP_110Mhz | MW Swap | [8 empty] | NR Services | SQ202402130363-NR Services | YPTT | SQ202403220516-YPTT | 2024-03-22 | 2024-03-19 | Completed | 2024-01-24 | 2024-01-24 | 2024-01-26 | 2024-01-26 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-01 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-19 | 2024-03-22 | 2024-03-19 | 2024-03-19 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24030697 |  | 2024-03-07 | 2024-03-08 | Completed | 2024-03-06 | 2024-03-07 | 2024-03-06 | 2024-03-08 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-13 | 2024-03-29 | 2024-03-13 | 2024-03-18 | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2024-03-13 | 2024-03-29 | 2024-03-13 | 2024-03-18 | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-13 | 2024-03-29 | 2024-03-13 | 2024-03-20 | NORAZHARI BIN MOHAMAD SALIM6794000032 | 2024-03-13 | 2024-03-29 | 2024-03-13 | 2024-03-18 | 2024-06-14 | 2024-06-14 | 2024-06-14 | 2024-06-14 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-07-30 | 2024-08-30 | 2024-07-30 | 2024-07-30 | ASTI//GANIS PUTRIANI/6237001358
4100A-4090A | Jln Batu Maung | DU00003318240 | Northern | Penang | 5.278292 | 100.278922 | WK04 | JAN 24 | WK08 | FEB 24 | RFS | Pending compliance | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_0.6,0.6 DP_110Mhz | MW Swap | NE 1- Install IDU 910A. 2- Install 2+0 ODU and configure EPLA. 3- Swap 23G 0.6m Antenna with new 18G HW 0.6m Antenna. 4- Configure link 2+0_1600M_512QAM FE 1- New IDU 910A. 2- Install 2+0 ODU and configure EPLA. 3- Swap 23G 0.6m Antenna with new 18G HW 0.6m Antenna. 4- Configure link 2+0_1600M_512QAM. 5- To provide new port at PTN. Required DCN VLAN | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402160379-GCI // SQ202406260407-GCI | 2024-02-29 | 2024-02-23 | Completed | 2024-01-30 | 2024-01-30 | 2024-01-26 | 2024-01-26 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-01-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-26 | 2024-02-29 | 2024-02-01 | 2024-02-02 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-02-01 | 2024-02-29 | 2024-02-01 | 2024-02-23 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020358 |  | 2024-02-06 | 2024-02-13 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-20 | 2024-02-27 | 2024-02-20 | 2024-02-20 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-02-20 | 2024-06-30 | 2024-02-20 | 2024-08-27 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-20 | 2024-02-27 | 2024-02-20 | 2024-02-27 | HIMAN//BIN ADAM/6800000183 | 2024-02-20 | 2024-02-27 | 2024-02-20 | 2024-02-20 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
3716C-2067A | Jln Delima Parkland (REL) | DU00003318241 | Central | Selangor | 2.969737 | 101.452839 | WK13 | MAR 24 | WK13 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 27/3: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 0.6m/0.6m_SP_1+0_110Mhz_889Mbps | MW Swap | NE 1. INSTALL NEW IDU RTN 910A 2. INSTALL NEW 18G 0.6M MDD DP ANTENNA 3. INSTALL NEW 18G 110MHZ XMC-5D ODU SUB BAND B 4. CONFIGURE LINK 18G 1+0 110MHZ 5. DISMANTLE EXISTING LINK FE 1. INSTALL NEW IDU RTN 910A 2. INSTALL NEW 18G 0.6M MDD DP ANTENNA 3. INSTALL NEW 18G 110MHZ XMC-5D ODU SUB BAND B 4. CONFIGURE LINK 18G 1+0 110MHZ 5. DISMANTLE EXISTING LINK | [7 empty] | Perwira | SQ202407050123-Perwira | Perwira | SQ202409120151-Perwira | 2024-09-03 | 2024-09-02 | Completed | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | SAMANTHA LOOI SHU-YI6237001479 |  |  |  | Unassigned | Completed |  | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-07-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-07-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-09-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020137 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  |  | Assigned | Completed |  | 2024-03-26 | 2024-03-31 | 2024-03-26 | 2024-04-04 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-26 | 2024-03-31 | 2024-03-26 | 2024-04-04 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | C.PRATHABAN///6798000081 |  |  | 2024-03-26 | 2024-03-31 | 2024-03-26 | 2024-04-02 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-03-26 | 2024-03-31 | 2024-03-26 | 2024-03-27 | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | NG HONG JIE7018000036 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
4036C-4427B | Tmn Kaya | DU00003318242 | Northern | Perak | 4.812079 | 100.736045 | WK05 | JAN 24 | WK10 | MAR 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1X RTN 910A 1X 18G 1.2M MDD ANTENNA 1X 18G XMC-5D SUB BAND B LO FE: 1X RTN 910A 1X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB BAND B HI | MW Swap | NE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 2+0 56MHZ 5. DISMANTLE EXISTING SM 2+0 28MHZ LINK FE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 2+0 56MHZ 5. DISMANTLE EXISTING SM 2+0 28MHZ LINK | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402200883-GCI // SQ202406260407-GCI // SQ202409100506-GCI | 2024-02-29 | 2024-02-23 | Completed | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-11 | 2024-02-29 | 2024-02-11 | 2024-02-23 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Disabled |  |  | DOWMY24020359 |  | 2024-02-06 | 2024-02-13 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-27 | 2024-02-29 | 2024-11-15 | 2024-11-15 | MAT//SAFAREED BIN MAT DESA/6800000177 | GCI TI | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-03-05 | MAT//SAFAREED BIN MAT DESA/6800000177 | GCI TI | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-27 | 2024-02-29 | 2024-03-12 | 2024-03-12 | MAT//SAFAREED BIN MAT DESA/6800000177 | 2024-02-29: 2024-02-27; 2024-02-29: 2024-02-29; 2024-02-29: 2024-02-28; 2024-02-29: 2024-02-28 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
2558B-1372A | Tmn Jasa Sg Tua | DU00003318243 | Central | Selangor | 3.256398 | 101.674703 | WK06 | FEB 24 | WK11 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | D2: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_0.6m&0.6m_SP_1+0_112MHz | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/1/1 NE 1- Install swap existing SM IDU to New RTN910A. 2- Install swap existing SM ODU to New 1+0 XMC-3 ODU. 3- Install swap exsting SM Antenna to New 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- Patch 2558B BBU to new link. FE 1- Install swap existing SM IDU to New RTN910A. 2- Install swap existing SM ODU to New 1+0 XMC-3 ODU. 3- Install swap exsting SM Antenna to New 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- To provide new port at PTN. Required DCN VLAN. 6- Dismantle existing SM Microwave Link | [7 empty] | Nera | SQ202402140179-Nera | Nera | SQ202402270732-Nera | 2024-05-10 | 2024-05-06 | Completed | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-02 | MOHD//KHALID IZHAR BIN SUBOH/7670000009 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-08 | 2024-02-08 | 2024-02-08 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-03-05 | 2024-03-06 | 2024-03-05 | 2024-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-30 | 2024-05-10 | 2024-04-30 | 2024-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021432 |  | 2024-02-15 | 2024-03-05 | Completed | 2024-02-14 | 2024-02-15 | 2024-02-14 | 2024-03-05 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-14 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-19 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-19 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-15 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4400B-4404A | Kg Raja Hitam RDC | DU00003318244 | Northern | Perak | 4.342131 | 100.753000 | WK05 | JAN 24 | WK09 | MAR 24 | RFS | Pending TX OPS update EPMS | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1X RTN 910A 1X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB BAND B HI FE: 1X RTN 910A 1X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB BAND B LO | MW Swap | NE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 1+0 56MHZ 5. DISMANTLE EXISTING SM LINK FE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 1+0 56MHZ 5. DISMANTLE EXISTING SM LINK | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402200883-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-01-29 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-02-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020360 |  | 2024-02-06 | 2024-02-13 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-27 | 2024-02-29 | 2025-12-05 | 2025-12-05 | team7gcitechnicalteam7gcitechnical | GCI TI | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-02-29 | team7gcitechnicalteam7gcitechnical | GCI TI | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | SengKee Seow10241846 |  |  | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-03-03 | team7gcitechnicalteam7gcitechnical | 2024-02-27 | 2024-02-29 | 2024-02-28 | 2024-02-28 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
3026C-1083A | Kg Sg Sembilang (REL) | DU00003318245 | Central | Selangor | 3.196137 | 101.318834 | WK10 | MAR 24 | WK11 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6m&0.6m_DP_1+0_110MHz | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/21 NE 1- Install swap existing SM to New IDU 910A. 2- Install swap existing SM to New 1+0 XMC-5D ODU. 3- Install swap existing SM to New 0.6m MDD Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- Patch 3026C BBU to new link. FE 1- Install swap existing SM to New IDU 910A. 2- Install swap existing SM to New 1+0 XMC-5D ODU. 3- Install swap existing SM to New 0.6m MDD Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- To provide new port at PTN. Required DCN VLAN. | [7 empty] | Allstar | SQ202403120253-Allstar | Allstar | SQ202402190097-Allstar // SQ202510070055-Allstar | 2024-04-09 | 2024-04-16 | Completed | 2024-03-04 | 2024-03-08 | 2024-03-05 | 2024-03-05 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-04-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021011 |  | 2024-02-12 | 2024-02-15 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-02-15 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-05-29 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | Allstar TI | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-03-23 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | Allstar TI | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | C.PRATHABAN///6798000081 |  |  | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-06-19 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-03-13 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7001D-7646C | Bubul | DU00003318246 | Sabah | Sabah | 4.452671 | 118.607092 |  |  | WK04 | JAN 24 | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC |  | MW Remote Upgrade | [8 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-01-22 | 2024-01-27 | 2024-01-23 | 2024-01-23 | C.PRATHABAN///6798000081 | [17 empty] | 2024-07-26 | 2024-08-26 | 2024-07-26 | 2024-07-26 | ASTI//GANIS PUTRIANI/6237001358
7618A-7202A | Hot Spring Tawau | DU00003318247 | Sabah | Sabah | 4.297636 | 117.901816 | WK04 | JAN 24 | WK10 | MAR 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_1.2,0.6 SP_110Mhz | MW Parallel Link | [8 empty] | Seri Pancar | SQ202402130369-Seri Pancar | GTSB | SQ202403220520-GTSB | 2024-02-09 | 2024-02-05 | Completed | 2024-01-22 | 2024-01-31 | 2024-01-22 | 2024-01-22 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-01-25 | 2024-01-31 | 2024-01-25 | 2024-01-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-25 | 2024-01-31 | 2024-01-25 | 2024-01-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-05 | 2024-02-09 | 2024-02-05 | 2024-02-05 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24030471 |  | 2024-03-05 | 2024-03-05 | Completed | 2024-03-04 | 2024-03-05 | 2024-03-04 | 2024-03-05 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-07 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-07 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-13 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-07 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
4300D-4663A | Alor Mengkudu (REL) | DU00003318248 | Northern | Kedah | 6.095604 | 100.392712 | WK04 | JAN 24 | WK07 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1X ISM8 CARD 1X 23G 0.6M DP ANTENNA 1X 23G XMC-3 SUB BAND A LO 1X 23G XMC-3 SUB BAND B LO FE: 1X ISM8 CARD 1X 23G 0.6M DP ANTENNA 1X 23G XMC-3 SUB BAND A HI 1X 23G XMC-3 SUB BAND B HI | MW Swap | NE 1. INSTALL ISM8 CARD AT RTN01 SLOT 3 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 2+0 23G XMC-3 SUB BAND A & B 4. CONFIGURE LINK 23G 2+0 56MHZ 5. DISMANTLE EXISTING LINK FE 1. INSTALL ISM8 CARD AT RTN05 SLOT 3 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 2+0 23G XMC-3 SUB BAND A & B 4. CONFIGURE LINK 23G 2+0 56MHZ 5. DISMANTLE EXISTING LINK | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402200883-GCI // SQ202406260407-GCI // SQ202409100506-GCI | 2024-02-29 | 2024-02-23 | Completed | 2024-01-31 | 2024-01-31 | 2024-01-25 | 2024-01-25 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-28 | 2024-01-28 | 2024-01-28 | 2024-01-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-26 | 2024-02-29 | 2024-02-01 | 2024-02-02 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-02-01 | 2024-02-29 | 2024-02-01 | 2024-02-23 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020909 |  | 2024-02-10 | 2024-02-13 | Completed | 2024-02-09 | 2024-02-10 | 2024-02-09 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-21 | team41gcitechnicalteam41gcitechnical | GCI TI | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-02-21 | team41gcitechnicalteam41gcitechnical | GCI TI | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-02-20 | team41gcitechnicalteam41gcitechnical | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-02-16 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
1312C-1605B | Kg Lombong | DU00003318249 | Central | Selangor | 2.971737 | 101.552448 | WK07 | FEB 24 | WK08 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6/0.6_MDD_1+0_110MHZ | MW Swap | NE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK FE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK 6. REPATCH NEW RTN 910A TO CP PORT | [7 empty] | Ascentrack | SQ202402190087-Ascentrack | Ascentrack | SQ202402270713-Ascentrack | 2024-09-03 | 2024-09-02 | Completed | 2024-02-07 | 2024-02-07 | 2024-02-15 | 2024-02-15 | Nor//Syamsyairi Bin Hashim/7539000044 |  | ASCENTRACK SDN. BHD. |  | Unassigned | Completed |  | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | Nor//Syamsyairi Bin Hashim/7539000044 |  | ASCENTRACK SDN. BHD. |  | Unassigned | Completed |  | 2024-02-17 | 2024-02-18 | 2024-02-17 | 2024-02-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-09-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020125 |  | 2024-02-02 | 2024-02-16 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-16 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-02-22 | Nor//Syamsyairi Bin Hashim/7539000044 | Ascentrack TI | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-02-29 | Nor//Syamsyairi Bin Hashim/7539000044 | Ascentrack TI | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-03-09 | Nor//Syamsyairi Bin Hashim/7539000044 | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-02-22 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4506C-4966A | Silterra Malaysia Kulim | DU00003318250 | Northern | Kedah | 5.406612 | 100.591344 | WK16 | APR 24 | WK13 | APR 24 | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | 26/4: D3: Cutover done 25/4: D2: TI done, T/shooting RSL (raining). Continue 26/4 28/3: TI done, pending cutover (need SFP electrical) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1X RTN 910A 1X 23G 0.6M DP ANTENNA 1X 23G XMC-3 SUB BAND A LO 1X 23G XMC-3 SUB BAND B LO FE: 1X RTN 910A 1X 23G 1.2M DP ANTENNA 1X 23G XMC-3 SUB BAND A HI 1X 23G XMC-3 SUB BAND B HI | MW Swap | DCN VLAN : 418, PORT NUMBER : GigabitEthernet0/1/2 NE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 2+0 23G XMC-3 SUB BAND A & B 4. CONFIGURE LINK 23G 2+0 56MHZ 5. DISMANTLE EXISTING LINK FE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 1.2M DP ANTENNA 3. INSTALL NEW 2+0 23G XMC-3 SUB BAND A & B 4. CONFIGURE LINK 23G 2+0 56MHZ 5. PATCH NEW RTN 910A TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402200883-GCI // SQ202406260407-GCI | 2024-03-31 | 2024-03-27 | Completed | 2024-01-24 | 2024-01-24 | 2024-01-26 | 2024-01-26 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-11 | 2024-02-29 | 2024-02-11 | 2024-02-23 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020910 |  | 2024-02-10 | 2024-02-13 | Completed | 2024-02-09 | 2024-02-10 | 2024-02-09 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-04 | team41gcitechnicalteam41gcitechnical | GCI TI | 2024-03-01 | 2024-06-30 | 2024-03-01 | 2024-05-20 | team41gcitechnicalteam41gcitechnical | GCI TI | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-01 | 2024-03-31 | 2024-03-01 | 2024-06-05 | team41gcitechnicalteam41gcitechnical | 2024-03-01 | 2024-03-31 | 2024-03-01 | 2024-03-01 | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-06-06 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
3044C-1087A | Jalan Haji Othman Lama | DU00003351398 | Central | Selangor | 3.060370 | 101.402280 | WK09 | MAR 24 | WK09 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Re-use antenna, 23G 1+0 112MHz 890Mbps | MW Hardware Upgrade | NE: 1. ODU: Swap existing ODU XMC-3 Sub-band A to XMC-3 112MHz Sub-band A model 2. Antenna: Remain 3. IDU: Install new RTN910A, named RTN02 4. IF card: Built-in Slot 7 ISM8 5. IF cable: Disconnect from RTN Slot 7-1, re-connect to new RTN02 Slot 7-1 6. Configure: Bandwidth 112MHz 7. Re-patch BBU to the new RTN02 FE: 1. ODU: Swap existing ODU XMC-3 Sub-band A to XMC-3 112MHz Sub-band A model 2. Antenna: Remain 3. IDU: Install new RTN910A, named RTN11 4. IF card: Built-in Slot 7 ISM8 5. IF cable: Disconnect from RTN03 Slot 7-1, re-connect to new RTN11 Slot 7-1 6. Configure: Bandwidth 112MHz 7. Re-patch PFS fiber from RTN03 to the new RTN11 | [7 empty] | Ascentrack | SQ202404170271-Ascentrack | Ascentrack | SQ202403260147-Ascentrack // SQ202409100362-Ascentrack | 2024-12-04 | 2024-12-03 | Completed | 2024-02-26 | 2024-03-01 | 2024-04-01 | 2024-04-01 | Nor//Syamsyairi Bin Hashim/7539000044 |  | ASCENTRACK SDN. BHD. |  | Unassigned | Completed |  | 2024-03-11 | 2024-03-12 | 2024-03-04 | 2024-03-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-11 | 2024-03-12 | 2024-03-04 | 2024-03-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-12-03 | 2024-12-04 | 2024-12-03 | 2024-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022241 |  | 2024-02-23 | 2024-02-23 | Completed | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | Nor//Syamsyairi Bin Hashim/7539000044 |  | ASCENTRACK SDN. BHD. |  | Unassigned | Completed |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-05-29 | Nor//Syamsyairi Bin Hashim/7539000044 | Ascentrack TI | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-03-02 | Nor//Syamsyairi Bin Hashim/7539000044 | Ascentrack TI | 2024-03-02 | 2024-03-02 | 2024-03-02 | 2024-03-02 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-04-19 | Nor//Syamsyairi Bin Hashim/7539000044 | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-03-04 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7469A-7066A | Dangulad Tampak | DU00003351399 | Sabah | Sabah | 5.337072 | 116.166503 | WK11 | MAR 24 | WK16 | APR 24 | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1. ODU XMC-3 112MHz Sub-band B model x 2 2. ISM8 x 1 3. RTN910A x 1 | MW Hardware Upgrade | NE: Install: 1. Antenna: Existing 2. ODU: Swap existing XMC-3 Sub-band A to XMC-3 112MHz Sub-band B model x 1 3. IDU: Existing 4. IF card: Install new ISM8 x 1 at Slot 3 5. IF cable: Re-use existing IF cable 6. Configure: Link 7469A ->7066A 1+0 112MHz 889Mbps Dismantle/ Remain: 1. Dismantle old ODU FE: Install: 1. Antenna: Existing 2. ODU: Swap existing XMC-3 Sub-band A to XMC-3 112MHz Sub-band B model x 1 3. IDU: Install new RTN910A x 1, named RTN03 and patch to existing RTN02 4. IF card: New RTN910A Built-in Slot 7-1 5. IF cable: Re-use existing IF cable for the new ODU to Slot 7-1 6. Configure: Link 7469A ->7066A 1+0 112MHz 889Mbps 7. DCN IP and VLAN: Not required Dismantle/ Remain: 1. Dismantle old ODU | [7 empty] | Magicell | SQ202409100246-Magicell | Magicell | SQ202407020206-Magicell | 2024-03-29 | 2025-04-09 | Completed | 2024-03-11 | 2024-03-15 | 2024-03-22 | 2024-03-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. |  | Unassigned | Completed |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2025-04-09 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240220AT |  | 2024-11-20 | 2024-11-20 | Completed | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-20 | NUR/WAFA/MIJONG/6871000001 |  |  | 1.00 | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-01 | 2024-03-12 | JOREY//BIN BALANG/7018000180 | Magicell TI | 2024-03-04 | 2024-03-08 | 2024-03-12 | 2024-03-12 | JOREY//BIN BALANG/7018000180 | Magicell TI | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2024-03-01 | 2024-03-31 | 2024-03-01 | 2024-03-15 | JOREY//BIN BALANG/7018000180 | 2024-03-01 | 2024-03-31 | 2024-03-01 | 2024-03-02 | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 | tseping//wang/6819000006 | Logistic Team | 2024-11-30 | 2024-12-30 | 2024-11-30 | 2024-11-30 | ASTI//GANIS PUTRIANI/6237001358
7937A-7935A | Ladang Giram | DU00003351400 | Sabah | Sabah | 4.597600 | 118.190600 | WK04 | JAN 24 | WK09 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | 23/10: Interim solution: reconfigure link BW & Mod 3/9: Initial SOW not enough capacity | TSS+AA+TI | L1+ATP+PAC | 15G 4+0 28MHz 800Mbps | MW Parallel Link | NE: 1. Antenna: Install new 1.2m MDD model x 1 2. ODU: Install XMC-5D Sub-band A x 1 3. IDU: Install new RTN910A x 1, named RTN06 4. IF card: Install ISM8 card x 2 at Slot 3 and 4 5. IF cable: 2 pcs 6. Configure: CA 7. BBU re-patch to this new RTN06 FE: 1. Antenna: Install new 1.2m MDD x 1 2. ODU: Install XMC-5D Sub-band A x 1 3. IDU: Install new RTN910A x 1, named RTN07 and patch to existing RTN06 4. IF card: Install ISM8 card x 2 at Slot 3 and 4 5. IF cable: 2 pcs 6. Configure: CA | [7 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202403220526-NR Services | 2024-02-29 | 2024-02-29 | Completed | 2024-01-29 | 2024-01-29 | 2024-01-27 | 2024-01-27 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-01 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-01 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240219A3 |  | 2024-02-20 | 2024-02-20 | Completed | 2024-02-19 | 2024-02-20 | 2024-02-19 | 2024-02-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-02-21 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-02-27 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-27 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-21 | 2024-02-29 | 2024-02-21 | 2024-03-11 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2024-02-29: 2024-02-21; 2024-02-29: 2024-02-29; 2024-02-29: 2024-02-21; 2024-03-04: 2024-02-22 |  |  | 2024-07-26 | 2024-08-26 | 2024-07-26 | 2024-07-26 | ASTI//GANIS PUTRIANI/6237001358
3318A-1070A | pBTS Pahang Bulk Mover (M) | DU00003351401 | Central | Selangor | 3.357204 | 101.597800 |  |  | WK04 | JAN 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC | Set BW to 56MHz 256QAM | MW Remote Upgrade | Set BW to 56MHz 256QAM | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-01-22 | 2024-01-27 | 2024-01-23 | 2024-01-23 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
3452C_LOS | eMOS KLIA Eng Complex | DU00005887817 | Central | Selangor | 2.728738 | 101.723724 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G 0.3M SP ANTENNA 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK 3452C-1675K/B02215 WITH HUAWEI_18G_1+0_0.3M/0.3M_SP_112MHZ_512QAM_889MBPS_XMC3E_SUB_B_0.54KM IMPACTED: 3452C DISMANTLE EXISTING LINK 3452C-2043B | 1. INSTALL NEW RTN910A 2. INSTALL NEW 18G 0.3M SP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512AM 5. DISMANTLE EXISTING LINK 3452C-2043B | 1. INSTALL NEW RTN910A 2. INSTALL NEW 18G 0.3M SP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512AM 5. DISMANTLE EXISTING LINK 3452C-2043B | XMC3E | SP MAC | 18G | 0.3 | 0.3 | GTSB | SQ202507300472-GTSB | GTSB | SQ202508200506-GTSB // SQ202508200516-GTSB | 2025-08-26 | 2025-08-20 | Completed | 2025-08-12 | 2025-08-26 | 2025-08-12 | 2025-08-12 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-12 | 2025-08-26 | 2025-08-12 | 2025-08-12 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-12 | 2025-08-13 | 2025-08-12 | 2025-08-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250807A9 |  | 2025-08-09 | 2025-08-18 | Completed | 2025-08-08 | 2025-08-09 | 2025-08-08 | 2025-08-18 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-31 | 2025-08-18 | 2025-09-03 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-08-18 | 2025-08-31 | 2025-08-18 | 2025-09-04 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-19 | 2025-08-18 | 2025-08-31 | 2025-08-18 | 2025-09-08 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-08-18 | 2025-08-31 | 2025-08-18 | 2025-08-19 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202508150527-GCI | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
4260B_AD | KG NAWA | DU00005933946 | Northern | Kedah | 6.116903 | 100.514197 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Cancel / drop due to have LOS clear from 4700D - 4958A based on 4700D TSS Report. So no required via 4260B - 4261B. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202508150530-GCI | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-23 | CHEONG/SENG/WAH/7018000306
4700D_AD | Taman Akasia | DU00005933947 | Northern | Kedah | 6.162704 | 100.503099 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M. NE_4700D 18G_SP_0.6(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub B_Hi x1. FE_4958A 18G_SP_0.6(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub B Lo x1. | MW New Link / Reroute | Link existing 4700D - 4260B with configuration 15G_2+0_28M. New link / reroute to new FE 4958A with 18G_1+0_112M. (Refer DU ID 4958A_AD , DU Code : DU00005933948) Site Impacted : 4700D NE_4700D 1.Install new 18G_SP_0.6(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect. 5.Migrate traffic to new link and new FE routing. 6.Decom existing IDU , ODU and ANT. (4700D - 4260B). FE_4958A 1.Install new 18G_SP_0.6(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide bu OPS team). 3.Install new XMC_3E , Sub B Lo. 4.Create cross connect. 5.Migrate traffic to new link and new FE routing. 6.Decom existing ODU , 3_ISM8 and ANT.(4260B-4700D). | Link existing 4700D - 4260B with configuration 15G_2+0_28M. New link / reroute to new FE 4958A with 18G_1+0_112M. (Refer DU ID 4958A_AD , DU Code : DU00005933948) Site Impacted : 4700D NE_4700D 1.Install new 18G_SP_0.6(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0.( RTN no provide by OPS team). 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect. 5.Migrate traffic to new link and new FE routing. 6.Decom existing IDU , ODU and ANT. (4700D - 4260B). | Link existing 4700D - 4260B with configuration 15G_2+0_28M. New link / reroute to new FE 4958A with 18G_1+0_112M. (Refer DU ID 4958A_AD , DU Code : DU00005933948) Site Impacted : 4700D FE_4958A 1.Install new 18G_SP_0.6(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide bu OPS team). 3.Install new XMC_3E , Sub B Lo. 4.Create cross connect. 5.Migrate traffic to new link and new FE routing. 6.Decom existing ODU , 3_ISM8 and ANT.(4260B-4700D). | XMC_3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202508110937-GCI | GCI | SQ202508110929-GCI // SQ202508110934-GCI | 2025-12-04 | 2025-12-03 | Completed | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092283 |  | 2025-09-23 | 2025-09-24 | Completed | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-13 | 2025-10-18 | 2025-10-13 | 2025-10-24 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2025-10-13 | 2025-10-18 | 2025-10-13 | 2025-10-30 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-15 | 2025-10-13 | 2025-10-18 | 2025-10-13 | 2025-10-30 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | 2025-10-13 | 2025-10-18 | 2025-10-13 | 2025-10-14 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | NG HONG JIE7018000036 | Logistic Team | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | CHEONG/SENG/WAH/7018000306
4958A_AD | Pokok Sena Kedah(Celcom) | DU00005933948 | Northern | Kedah | 6.155636 | 100.519159 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 23G_1+0_112M NE_4958A 23G_SP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A_Lo x1. FE_4292B 23G_SP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A_Hi x1. | MW New Link / Reroute | New upstream link for 4958A-4292B.(Priority to install) New Link config with 23G_1+0_112M to support 4700D ( Refer DU ID 4700D_AD , DU Code : DU00005933947). NE_4958A 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new 3_ISM8-1+0 into new RTN910A. (Refer DU ID 4700D_AD). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic BBU_4700D thru new upstream link. 6.No link to be decom. FE_4292B 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Enable GE1 , ETH LAN patching to existing 4292B_RTN02_GE2. ( ID : 30372). 6.Traffic BBU_4700D thru new upstream link. 7.Create new In band DCN. 8.No link to be decom. | New upstream link for 4958A-4292B.(Priority to install) New Link config with 23G_1+0_112M to support 4700D ( Refer DU ID 4700D_AD , DU Code : DU00005933947). NE_4958A 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new 3_ISM8-1+0 into new RTN910A. (Refer DU ID 4700D_AD). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic BBU_4700D thru new upstream link. 6.No link to be decom. | New upstream link for 4958A-4292B. ( Priority to Install) New Link config with 23G_1+0_112M to support 4700D ( Refer DU ID 4700D_AD , DU Code : DU00005933947). FE_4292B 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Enable GE1 , ETH LAN patching to existing 4292B_RTN02_GE2. ( ID : 30372). 6.Traffic BBU_4700D thru new upstream link. 7.Create new Inband DCN. 8.No link to be decom. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202508110937-GCI | GCI | SQ202508110929-GCI // SQ202508110934-GCI | 2025-11-29 | 2025-11-28 | Completed | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092693 |  | 2025-09-27 | 2025-09-29 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-09 | 2025-10-13 | 2025-10-09 | 2025-10-12 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2025-10-09 | 2025-10-13 | 2025-10-09 | 2025-10-12 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-10 | 2025-10-09 | 2025-10-13 | 2025-10-09 | 2025-10-30 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | 2024-02-29: 2025-10-09; 2024-02-29: 2025-10-13; 2024-02-29: 2025-10-09; 2024-03-04: 2025-10-10 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | CHEONG/SENG/WAH/7018000306
4402D_LOS | Venture Elec | DU00006437004 | Northern | Penang | 5.298797 | 100.293001 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | TX Mini Project, 4402D-4331C, 23G 1+0, ODU XMC-3 56MHz Sub band B x 2, RTN910A x 2, A23D03MAC-3NX x 1, A23D03MAC-3NX x 1, Ant ht NE/FE: 18m/25m | MW New Link / Reroute | Install MW New Link 23G 0.3DP/0.3DP dish, ODU Sub band B | Install 23G 0.3DP dish, 1+0, NE TX high, ODU XMC-3 Sub band B x 1, IDU RTN910A x 1; IDU patching not required; Migration into new link: BBU 4402D | Install 23G 0.3DP dish, 1+0, FE TX low, ODU XMC-3 Sub band B x 1, IDU RTN910A x 1; IDU patching to iBEAM new port | XMC-3 | 18/25 | 23G | 0.3 | 0.3 | GCI | SQ202512240396-GCI | GCI | SQ202601150389-GCI // SQ202601150442-GCI | 2026-01-29 | 2026-02-03 | Completed | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-29 | 2026-01-22 | 2026-02-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122617 |  | 2026-01-31 | 2025-12-29 | Completed | 2025-12-26 | 2026-01-31 | 2025-12-26 | 2025-12-29 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-07 | 2026-01-10 | 2026-01-07 | 2026-01-16 | NAZARULISKANDAR//BIN YUSNI/6800000203 | GCI TI | 2026-01-07 | 2026-01-10 | 2026-01-07 | 2026-01-16 | NAZARULISKANDAR//BIN YUSNI/6800000203 | GCI TI | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-13 | 2026-01-07 | 2026-01-10 | 2026-01-07 | 2026-02-25 | NAZARULISKANDAR//BIN YUSNI/6800000203 | 2024-02-29: 2026-01-07; 2024-02-29: 2026-01-10; 2024-02-29: 2026-01-07; 2024-03-04: 2026-01-08 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512241144-GTSB | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | LIM//WEI CHONG/6798000110
4180D | Lebuh Bandar U Utama | DU00004377341 | Northern | Perak | 4.353137 | 100.992147 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP and patch cord | BBU Patching | Congestion at port IDU to BBU To upgrade to 10G Remarks: related to MW link upgrade DU 4180D-4410C (Tx Mini Project). Need to complete MW link upgrade before upgrade BBU interface to 10G Impact site: 4180D Tx route before: 4180D/4180D-4410C Tx route after: 4180D/4180D-4410C NE (4180D): 1) Install 10G SFP at IDU 2) Install 10G SFP at BBU 3) Migrate traffic to 10G port | [7 empty] | GCI | SQ202503190713-GCI | GCI | SQ202503050483-GCI | 2025-04-21 | 2025-04-21 | Completed | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-19 | 2025-04-19 | 2025-04-19 | 2025-04-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022152 |  | 2025-02-22 | 2025-02-25 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-02-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-27 | 2025-03-07 | 2025-02-27 | 2025-03-04 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-27 | 2025-03-07 | 2025-02-27 | 2025-03-12 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-02-27 | 2025-03-07 | 2025-02-27 | 2025-03-10 | MOHD FAIZ BIN MD YUNUS6800000186 | 2024-02-29: 2025-02-27; 2024-02-29: 2025-03-07; 2024-02-29: 2025-02-27; 2024-03-04: 2025-03-10 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402
K00119 | K009A_K00119OD_JKRKUALANERANG | DU00004377342 | Northern | Kedah | 6.251197 | 100.614711 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | SFP 1km and patch cord | IDU-IPRAN | Congestion at CP site from IDU NT05948 K00119 JKRKUALANERANG - K00780 KG KUBANG JULUK GE5 to PTN 60087-JKRKUALANERANG GE0/0/3 To divert site K00833 to other IDU/CP port Impact site: K00833 Tx route: K00119 NE (K00119): 1) Patch GE6 (optical) to new PTN port (ops team to assign new port) 2) Divert K00833 to new port | [7 empty] | CCSMY | SQ202504170473-CCS | CCSMY | SQ202503200262-CCS // SQ202504260175-CCS | 2025-07-19 | 2025-07-21 | Completed | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022147 |  | 2025-02-22 | 2025-02-25 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-02-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-16 | 2025-03-16 | 2025-03-16 | 2025-03-16 | CHEN TAK//EOH YANG/7021000004 |  | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-28 | ABDUL//HALIM MUKREEM BIN ABDUL LATIF/7021000062 | CCS TI | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-13 | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-05-04 | ABDUL//HALIM MUKREEM BIN ABDUL LATIF/7021000062 | 2024-02-29: 2025-03-19; 2024-02-29: 2025-03-31; 2024-02-29: 2025-03-19; 2024-03-04: 2025-07-11 |  |  | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507250716-GCI | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | CHEONG/SENG/WAH/7018000306
A00607 | A044A_A00607OD_UITMHOSTEL | DU00004377343 | Northern | Perak | 4.351600 | 100.954300 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP and patch cord | IDU-IPRAN | Congestion at CP site from IDU NT05811 GE1 to PTN 66101-UITMHOSTEL GE0/0/2 To upgrade to 10G port Remarks: related to MW link upgrade DU 4180D-4410C (Tx Mini Project). Need to complete MW link upgrade before upgrade interface to 10G Impact site: 4180D Tx route: A00607 NE (A00607): 1) Upgrade port IDU to PTN using 10G port | [7 empty] | GCI | SQ202503190713-GCI | GCI | SQ202503050483-GCI | 2025-11-29 | 2025-12-03 | Completed | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022154 |  | 2025-02-22 | 2025-02-24 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-02-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-27 | 2025-03-07 | 2025-02-27 | 2025-03-04 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-27 | 2025-03-07 | 2025-02-27 | 2025-03-04 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-02-27 | 2025-03-07 | 2025-02-27 | 2025-03-06 | MOHD FAIZ BIN MD YUNUS6800000186 | 2024-02-29: 2025-02-27; 2024-02-29: 2025-03-07; 2024-02-29: 2025-02-27; 2024-03-04: 2025-02-28 |  |  | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358
S01754 | S106A_S01754OD_TMNSEMPAUL2 | DU00004377344 | Sabah | Sabah | 4.463397 | 118.588153 |  |  | WK03 | JAN 25 | RFS |  |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP and patch cord | BBU Patching | Congestion at port 7064K/S01754 RTN01 GE1 to BBU To upgrade to 10G Remarks: Related to MW link upgrade (DU S01754-7207A Tx Mini Project). Need to complete MW link upgrade before upgrade BBU interface to 10G Impact site: S01754 Tx route before: S01754/S01754-S00501 Tx route after: S01754/S01754-7207A NE (S01754): 1) Install 10G SFP at RTN01 GE3 2) Install 10G SFP at BBU 3) Migrate traffic to 10G port | [7 empty] | AllStar | SQ202504210278-Allstar | AllStar | SQ202501210500-Allstar // SQ202504260190-Allstar |  |  | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25011376 |  | 2025-01-14 | 2025-01-15 | Completed | 2025-01-13 | 2025-01-14 | 2025-01-13 | 2025-01-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-18 | 2025-02-01 | 2025-01-18 | 2025-02-12 | CALVIN/RAY/BENEDICT/6798000250 | Allstar TI | 2025-01-18 | 2025-02-01 | 2025-01-18 | 2025-02-12 | CALVIN/RAY/BENEDICT/6798000250 | Allstar TI | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-01-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-20 | 2025-01-18 | 2025-02-01 | 2025-01-18 | 2025-02-18 | CALVIN/RAY/BENEDICT/6798000250 | 2024-02-29: 2025-01-18; 2024-02-29: 2025-02-01; 2024-02-29: 2025-01-18; 2024-03-04: 2025-02-14 |  |  | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
A00228 | A042A_A00228OD_CB_TMBTKURAU | DU00004377345 | Northern | Perak | 4.975600 | 100.796100 |  |  |  |  | 00. Integrated/RFS Done |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | SFP 1km and patch cord | IDU-IPRAN | Congestion at CP site from IDU A00228-TM BT KURAU-RTN01 GE1 to PTN 66015-TMBTKURAU GE0/0/3 To divert site 4584A to other IDU/CP port Impact site: 4584A Tx route: A00228 NE (A00288): 1) Patch GE5 (optical) to new PTN port (ops team to assign new port) 2) Divert 4584A to new port | [7 empty] | GCI | SQ202504280464-GCI | GCI | SQ202504280751-GCI | 2025-11-29 | 2025-11-28 | Completed | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25030662 |  | 2025-03-07 | 2025-03-11 | Completed | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-11 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-05-31 | 2025-05-28 | 2025-05-28 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2025-05-28 | 2025-06-28 | 2025-05-28 | 2025-05-28 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-28 | 2025-05-28 | 2025-06-28 | 2025-05-28 | 2025-05-29 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2024-02-29: 2025-05-28; 2024-02-29: 2025-06-28; 2024-02-29: 2025-05-28; 2024-03-04: 2025-05-28 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250716-GCI | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
4993A | Bandar Darul Aman(ZED) | DU00004377346 | Northern | Kedah | 6.236759 | 100.438022 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | SFP 1km and patch cord | IDU-IPRAN | Congestion at CP site from IDU 4993A/K00579-BDR DARUL AMAN-RTN01 GE1 to PTN 60178-BDRDARULAMAN GE0/0/1 To divert site 4751A to other IDU/CP port Impact site: 4751A Tx route: 4993A/K00579 NE (4993A/K00579): 1) Patch GE5 (optical) to new PTN port (ops team to assign new port) 2) Divert 4751A to new port | [7 empty] | CCSMY | SQ202503190701-CCS | CCSMY | SQ202503200262-CCS // SQ202504260175-CCS | 2025-11-29 | 2025-11-28 | Completed | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022148 |  | 2025-02-22 | 2025-02-25 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-02-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-03 | 2025-03-29 | 2025-03-07 | 2025-03-07 | ABDUL//HALIM MUKREEM BIN ABDUL LATIF/7021000062 | CCS TI | 2025-03-03 | 2025-03-29 | 2025-03-07 | 2025-03-07 | ABDUL//HALIM MUKREEM BIN ABDUL LATIF/7021000062 | CCS TI | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-07 | 2025-03-03 | 2025-03-29 | 2025-03-07 | 2025-03-07 | ABDUL//HALIM MUKREEM BIN ABDUL LATIF/7021000062 | 2024-02-29: 2025-03-03; 2024-02-29: 2025-03-29; 2024-02-29: 2025-03-06; 2024-03-04: 2025-03-06 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509250641-GCI | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
1405A_LOS | UNZA | DU00006681152 | Central | Selangor | 3.057398 | 101.596147 | [7 empty] | 01. Pending Planning |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_56M. NE_1405A 23G_DP_0.3M(MAC) x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. FE_2082A 23G_DP_0.3M(MAC) x1. ISM8 x1. XMC_3E , Sub A & B_Hi x2. | MW New Link / Reroute | Current link 1405A-1179A LOS Block with MW config 23G_1+0_112M (64QAM). Link reroute to new FE 2082A. Install new MW 23G_2+0_56M. Site Impacted : 1405A. NE_1405A 1.23G_DP_0.3M(MAC). 2.Install new RTN910A ,7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link (1405A-1179A). FE_2082A 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing 2082A_RTN02 , 3_ISM8-2+0. (ID : 34430). 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link (1179A-1405A). | Current link 1405A-1179A LOS Block with MW config 23G_1+0_112M (64QAM). Link reroute to new FE 2082A. Install new MW 23G_2+0_56M. Site Impacted : 1405A. NE_1405A 1.23G_DP_0.3M(MAC). 2.Install new RTN910A ,7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link (1405A-1179A). | Current link 1405A-1179A LOS Block with MW config 23G_1+0_112M (64QAM). Link reroute to new FE 2082A. Install new MW 23G_2+0_56M. Site Impacted : 1405A. FE_2082A 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing 2082A_RTN02 , 3_ISM8-2+0. (ID : 34430). 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link (1179A-1405A). | XMC_3E | MAC | 23G | 0.3 | 0.3 | GTSB | SQ202604060610-GTSB | GTSB | SQ202604290740-GTSB // SQ202604290749-GTSB |  |  | Ongoing | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-15 | 2026-04-29 | 2026-04-15 | 2026-04-15 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-04-16 | 2026-04-15 | 2026-04-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-04-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26041327 |  | 2026-04-14 | 2026-04-29 | Completed | 2026-04-13 | 2026-04-14 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-04-30 | 2026-04-23 | 2026-05-03 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2026-04-23 | 2026-04-30 | 2026-04-23 | 2026-05-03 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-28 | 2026-04-23 | 2026-04-30 | 2026-04-23 |  | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2026-04-23 | 2026-04-30 | 2026-04-23 | 2026-04-24 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | NG HONG JIE7018000036 | Logistic Team | [5 empty] | GCI | SQ202603270220-GCI | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | CHEONG/SENG/WAH/7018000306
Q00329_AD | Q130A_Q00329OD_LONGLAMA | DU00006681153 | Sarawak | Sarawak | 3.766964 | 114.407092 | [9 empty] | NA |  |  | MW Re-engineering | Remote configuration only. ETH Patching already in place from existing Q00329 RTN910A ( ID : 31763) to existing RTN910A ( ID : 13753). Transfer traffic Q01130 from existing PTN Q00329 30384-LONGLAMA to MW link SW03753 Q00329_LONG LAMA - Q00365_BKT DABEI | Remote configuration only. ETH Patching already in place from existing Q00329 RTN910A ( ID : 31763) to existing RTN910A ( ID : 13753). Transfer traffic Q01130 from existing PTN Q00329 30384-LONGLAMA to MW link SW03753 Q00329_LONG LAMA - Q00365_BKT DABEI | [12 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202603270348-GCI | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | CHEONG/SENG/WAH/7018000306
3410B_AD | Pangsapuri Teratai Kajang | DU00005375701 | Central | Selangor | 2.971197 | 101.821792 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_3+0_112M_512QAM LINK 1/ANT 1 NE_3410B New 18G_0.6M(MDD) x1. Reuse Existing RTN910A(RTN04) New ISM8 x1. New XMC_5D, Sub B_Lo x1. FE_2118B/B00562 New 18G_0.6M(MDD) x1. New RTN910A x1. New ISM8 x1. New XMC_5D, Sub B_Hi x1. New SFP Module 10G 1310nm 40Km x2(For IDU & PTN). New suitable quantity, length and type of Fiber Patch Cord. | MW New Link / Reroute | Existing HW Link 3410B(RTN04)-1048A(RTN03),18G_1+0_112MHz_512QAM. Existing HW Link 3410B(RTN01)-1048A(RTN02),23G_2+0_112MHz_512QAM_EPLA. New MW Link/Reroute, 3410B(RTN01)-2118B(RTN02)-18G_3+0_112M_512QAM_CA&EPLA. Later, once complete New MW Link/Reroute, 3410B(RTN01)-2118B(RTN02)-18G_3+0_112M_512QAM_CA&EPLA. May decom ODU & Antenna but do not decom RTN910A(RTN01) at 3410B of existing HW Link 3410B(RTN01)-1048A(RTN02),23G_2+0_112MHz_512QAM_EPLA. May decom RTN910A, ODU & Antenna of existing HW Link 3410B(RTN04)-1048A(RTN03),18G_1+0_112MHz_512QAM. Site Impacted : 3410B, 3408B, 3882B & 1666H. NE_3410B 1.Install new 18G_0.6M(MDD) x1. 2.Insert new ISM8 x1 into slot 03 of existing RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Enable port 8-EM6-2 of existing RTN910A(RTN02). Configure it. 5.Shifting existing BBU 3410B from port 8-EM6-1 of existing RTN910A(RTN04) to port 8-EM6-2 of existing RTN910A(RTN02). Configure it. 6.Request new xC Vlan services from ZTE IPRAN Team for all RAN(3410B, 3408B, 3882B & 1666H). 7.Migrate traffic to xC PTN,B00562. 8.Later, once On Air New MW Link/Reroute , 3410B(RTN01)-2118B(RTN02)-18G_3+0_112M_512QAM_CA&EPLA. May decom ODU & Antenna but do not decom RTN910A(RTN01) at 3410B of existing HW Link 3410B(RTN01)-1048A(RTN02),23G_2+0_112MHz_512QAM_EPLA. May decom RTN910A, ODU & Antenna of existing HW Link 3410B(RTN04)-1048A(RTN03),18G_1+0_112MHz_512QAM. FE_2118B/B00562 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN02). Configure it. 3.Insert 1x new ISM8 into slot 03 of new RTN910A(RTN02). Configure it. 4.Install new XMC_5D, Sub B_Hi. Configure it. 5.Insert SFP Module 10G 40Km into port 8-EM6-3 of new RTN910A(RTN02). Configure it. 6.Insert SFP Module 10G 40Km into port TenGigabitEthernet0/0/26 of existing xC PTN. Configure it. 7.Patching Fiber patch cord from port 8-EM6-3 of new RTN910A(RTN02) and port TenGigabitEthernet0/0/26(10G) of existing xC PTN B00562. 8.Later, once On Air New MW Link/Reroute , 3410B(RTN01)-2118B(RTN02)-18G_3+0_112M_512QAM_CA&EPLA. May decom ODU & Antenna but do not decom RTN910A(RTN01) at 3410B of existing HW Link 3410B(RTN01)-1048A(RTN02),23G_2+0_112MHz_512QAM_EPLA. May decom RTN910A, ODU & Antenna of existing HW Link 3410B(RTN04)-1048A(RTN03),18G_1+0_112MHz_512QAM. | Existing HW Link 3410B(RTN04)-1048A(RTN03),18G_1+0_112MHz_512QAM. Existing HW Link 3410B(RTN01)-1048A(RTN02),23G_2+0_112MHz_512QAM_EPLA. New MW Link/Reroute, 3410B(RTN01)-2118B(RTN02)-18G_3+0_112M_512QAM_CA&EPLA. Later, once complete New MW Link/Reroute, 3410B(RTN01)-2118B(RTN02)-18G_3+0_112M_512QAM_CA&EPLA. May decom ODU & Antenna but do not decom RTN910A(RTN01) at 3410B of existing HW Link 3410B(RTN01)-1048A(RTN02),23G_2+0_112MHz_512QAM_EPLA. May decom RTN910A, ODU & Antenna of existing HW Link 3410B(RTN04)-1048A(RTN03),18G_1+0_112MHz_512QAM. Site Impacted : 3410B, 3408B, 3882B & 1666H. NE_3410B 1.Install new 18G_0.6M(MDD) x1. 2.Insert new ISM8 x1 into slot 03 of existing RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Enable port 8-EM6-2 of existing RTN910A(RTN02). Configure it. 5.Shifting existing BBU 3410B from port 8-EM6-1 of existing RTN910A(RTN04) to port 8-EM6-2 of existing RTN910A(RTN02). Configure it. 6.Request new xC Vlan services from ZTE IPRAN Team for all RAN(3410B, 3408B, 3882B & 1666H). 7.Migrate traffic to xC PTN,B00562. 8.Later, once On Air New MW Link/Reroute , 3410B(RTN01)-2118B(RTN02)-18G_3+0_112M_512QAM_CA&EPLA. May decom ODU & Antenna but do not decom RTN910A(RTN01) at 3410B of existing HW Link 3410B(RTN01)-1048A(RTN02),23G_2+0_112MHz_512QAM_EPLA. May decom RTN910A, ODU & Antenna of existing HW Link 3410B(RTN04)-1048A(RTN03),18G_1+0_112MHz_512QAM. | Existing HW Link 3410B(RTN04)-1048A(RTN03),18G_1+0_112MHz_512QAM. Existing HW Link 3410B(RTN01)-1048A(RTN02),23G_2+0_112MHz_512QAM_EPLA. New MW Link/Reroute, 3410B(RTN01)-2118B(RTN02)-18G_3+0_112M_512QAM_CA&EPLA. Later, once complete New MW Link/Reroute, 3410B(RTN01)-2118B(RTN02)-18G_3+0_112M_512QAM_CA&EPLA. May decom ODU & Antenna but do not decom RTN910A(RTN01) at 3410B of existing HW Link 3410B(RTN01)-1048A(RTN02),23G_2+0_112MHz_512QAM_EPLA. May decom RTN910A, ODU & Antenna of existing HW Link 3410B(RTN04)-1048A(RTN03),18G_1+0_112MHz_512QAM. Site Impacted : 3410B, 3408B, 3882B & 1666H. FE_2118B/B00562 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN02). Configure it. 3.Insert 1x new ISM8 into slot 03 of new RTN910A(RTN02). Configure it. 4.Install new XMC_5D, Sub B_Hi. Configure it. 5.Insert SFP Module 10G 40Km into port 8-EM6-3 of new RTN910A(RTN02). Configure it. 6.Insert SFP Module 10G 40Km into port TenGigabitEthernet0/0/26 of existing xC PTN. Configure it. 7.Patching Fiber patch cord from port 8-EM6-3 of new RTN910A(RTN02) and port TenGigabitEthernet0/0/26(10G) of existing xC PTN B00562. 8.Later, once On Air New MW Link/Reroute , 3410B(RTN01)-2118B(RTN02)-18G_3+0_112M_512QAM_CA&EPLA. May decom ODU & Antenna but do not decom RTN910A(RTN01) at 3410B of existing HW Link 3410B(RTN01)-1048A(RTN02),23G_2+0_112MHz_512QAM_EPLA. May decom RTN910A, ODU & Antenna of existing HW Link 3410B(RTN04)-1048A(RTN03),18G_1+0_112MHz_512QAM. | XMC_5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_0.6M(MDD) x1. | GTSB | SQ202505080085-GTSB | GTSB | SQ202505150117-GTSB // SQ202505150118-GTSB | 2025-07-05 | 2025-07-03 | Completed | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-06-09 | 2025-05-26 | 2025-05-26 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051473 |  | 2025-05-15 | 2025-05-19 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-06-08 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-06-28 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-29 | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-07-09 | Aminuddin bin che azibA0563734967123169280 | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-05-20 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202505070162-GTSB
4989C-4247A | Gemilang Business Centre | DU00003489661 | Northern | Penang | 5.350240 | 100.439594 |  | MAY 24 |  | MAY 24 | RFS | Planning WIP | ZTE | 00. Integrated/RFS Done | 24/5: D2: Cutover done 23/5: MOS & TI In Plan, Pending EB CRQ approval 21/5: Collection done, MOS & TI In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1. 1x IDU 910A 2. 1+0 23G XMC3 ODU Subband B (for support 112Mhz) | MW Hardware Upgrade | NE: 1. Reuse existing IDU 910A. 2. Reuse existing Antenna. 3. Swap existing 1+0 ODU with new 23G 1+0 ODU (Sub B) for support 112Mhz. 4. Configure link 23G 1+0 112Mhz. FE: 1. Swap existing IDU 950 RTN 03 with new IDU 910A. Reengineering MW Link 4375C-4247A to new IDU 910A. 2. Reuse existing Antenna. 3. Swap existing 1+0 ODU with new 23G 1+0 ODU (Sub B) for support 112Mhz. 4. Configure link 23G 1+0 112Mhz. | [7 empty] | GCI | SQ202407010442-GCI | GCI | SQ202407020120-GCI | 2024-08-21 | 2024-11-26 | Completed | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24051903 |  | 2024-05-20 | 2024-05-21 | Completed | 2024-05-19 | 2024-05-20 | 2024-05-19 | 2024-05-21 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-23 | 2024-05-31 | 2024-05-22 | 2024-05-29 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-05-23 | 2024-05-31 | 2024-05-22 | 2024-05-29 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-05-23 | 2024-05-31 | 2024-05-22 | 2024-05-24 | team21gcitechnicalteam21gcitechnical | 2024-05-23 | 2024-05-31 | 2024-05-22 | 2024-05-23 | 2025-10-05 | 2025-10-05 | 2025-10-05 | 2025-10-05 | NG HONG JIE7018000036 | Logistic Team | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
9233B-9134A | RH HQ IB | DU00003489662 | Sarawak | Sarawak | 2.264567 | 111.843715 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | no more in MSP tracker_W22 and AVG Utili 27% | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | HSU//MYET CHAE/6799000011
3644B-1096A | Jalan Keretapi Lama | DU00003489663 | Central | Selangor | 3.135811 | 101.370456 |  | MAR 24 | WK14 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 3/4: D1: Cutover done 28/3: EB CRQ approved. Plan 3/4 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 112MHZ 0.6M/0.6M_256QAM SUB A | MW Hardware Upgrade | HARDWARE UPGRADE FROM 18G 1+0 56MHZ TO 18G 1+0 112MHZ 0.6M/0.6M_256QAM SUB A 3644B-1096A IMPACTED SITE: 1448H NLOS NE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 18G XMC3 112MHZ SUB A 3. REUSE EXISTING 18G 0.6M SP ANTENNA 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM FE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 18G XMC3 112MHZ SUB A 3. REUSE EXISTING 18G 0.6M SP ANTENNA 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. REPATCH TO EXISTING CP PORT | [7 empty] | Perwira | SQ202407050123-Perwira | Perwira | SQ202403120476-Perwira | 2024-08-17 | 2024-08-16 | Completed | 2024-04-03 | 2024-06-30 | 2024-04-03 | 2024-04-03 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | PERWIRA ENERGY SDN. BHD. |  | Assigned | Completed |  | 2024-07-16 | 2024-07-17 | 2024-07-16 | 2024-07-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-16 | 2024-07-17 | 2024-07-16 | 2024-07-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-16 | 2024-08-17 | 2024-08-16 | 2024-08-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240301BH |  | 2024-03-02 | 2024-03-13 | Completed | 2024-03-01 | 2024-03-02 | 2024-03-01 | 2024-03-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-03 | 2024-04-10 | 2024-04-04 | 2024-04-04 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-04-03 | 2024-04-10 | 2024-04-04 | 2024-04-04 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-04-03 | 2024-04-03 | 2024-04-04 | 2024-04-04 | KII//YEE TERNG/6800000113 |  |  | 2024-04-03 | 2024-04-10 | 2024-04-05 | 2024-04-05 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-04-03 | 2024-04-10 | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-06-30 |  |  | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
9714B-9157B | Samariang Batu | DU00003489664 | Sarawak | Sarawak | 1.603480 | 110.326098 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | remote upgrade - no material require |  |  |  | Cancel / Drop | MW Remote Upgrade Huawei 18GHz 1+0 110MHz NE: 1. Change Bandwidth from 18GHz_1+0_55MHz to 18GHz_1+0_110MHz (will use existing freq) 2. Please capture (screen shot) current metering (Tx Power, Rsl, etc) before proceed with this activity FE: 1. Change Bandwidth from 18GHz_1+0_55MHz to 18GHz_1+0_110MHz (will use existing freq) 2. Please capture (screen shot) current metering (Tx Power, Rsl, etc) before proceed with this activity | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | remote upgrade - no material require |  |  | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300154-GTSB
9687B-9470A | Rampangi 2 | DU00003489665 | Sarawak | Sarawak | 1.649638 | 110.333820 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB
Q00676-Q00254 | LDG SILAS | DU00003501229 | Sarawak | Sarawak | 3.070000 | 113.124900 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | HSU//MYET CHAE/6799000011
B02873-B00666 | JLNSGBUAYA2 | DU00003501230 | Central | Selangor | 3.376502 | 101.535928 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 26/7: D3: Cutover done. Post-CO Tshooting WIP 25/7: MOS & TI In Plan 24/7: BoM ready, Pending DO. Materials transfer from W00103 (MTK) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_0.6/0.6M MAC | MW Swap | MW Swap Huawei B02873-B00666_23G 1+0 112MHz NE: 1. Swap Existing HW IDU with new HW RTN910A 2. Swap Existing HW ODU with new HW XMC 3_ 23GHz_ODU (Sub A) 3. Swap Existing HW Antenna with New Huawei 23GHz 0.6m SP MAC 4. Configure link as 23GHz 1+0 112MHz_256QAM FE: 1. Swap Existing HW IDU with new HW RTN910A 2. Swap Existing HW ODU with new HW XMC 3_ 23GHz_ODU (Sub A) 3. Swap Existing HW Antenna with New Huawei 23GHz 0.6m SP MAC 4. Configure link as 23GHz 1+0 112MHz_256QAM | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202408080495-MTK | 2025-10-25 | 2025-10-27 | Completed | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-09 | 2024-09-10 | 2024-09-09 | 2024-09-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-09 | 2024-09-10 | 2024-09-09 | 2024-09-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Full site material DM from TX Rollout W00103 |  |  | Disabled | [8 empty] | Unassigned | Disabled |  | 2024-07-25 | 2024-07-31 | 2024-07-24 | 2024-08-01 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-07-25 | 2024-08-01 | 2024-07-24 | 2024-08-01 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | C.PRATHABAN///6798000081 |  |  | 2024-07-25 | 2024-07-31 | 2024-07-24 | 2024-08-01 | RIDHUAN//BIN MANSOR/8225000011 | 2024-07-25 | 2024-07-31 | 2024-07-24 | 2024-07-27 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 | NG HONG JIE7018000036 | Logistic Team | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
9004B-7647C | pBTS 7 Inn Hotel | DU00003501231 | Sarawak | Sarawak | 4.471912 | 118.609097 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | no more in MSP tracker_W22 and site down in NMS | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | HSU//MYET CHAE/6799000011
2027A-2133A | Kg Merbau Sempak (Asiaspace) | DU00003501232 | Central | Selangor | 3.219555 | 101.509100 |  | MAY 24 |  | JUN 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 29/7: Cutover done. Materials transfer from K00038 | TSS+AA+TI | L1+ATP+PAC | 18G 1+0 ODU XMC-3E Sub band A x 2, A18S06MAC-3NX x 1, A18S06MAC-3NX x 1, ISM8 x 2 | MW Parallel Link | NE: Install: 1. Antenna: Install new 18G 0.6m SP A18S06MAC-3NX x 1 2. ODU: Install XMC-3E 112MHz Sub-band A x 1 3. IDU: Existing 4. IF card: Install new ISM8 x 1 5. IF cable: Connect new IF cable x 1 from the new ODUs to IDU 6. Configure: combine with the existing 2+0 link become 3+0 ePLA Dismantle/ Remain: 1. Remain existing Huawei link (antenna, ODU, IDU, IF cables) to configure 3+0 ePLA FE: Install: 1. Antenna: Install new 18G 0.6m SP A18S06MAC-3NX x 1 2. ODU: Install XMC-3E 112MHz Sub-band A x 1 3. IDU: Existing 4. IF card: Install new ISM8 x 1 5. IF cable: Connect new IF cable x 1 from the new ODUs to IDU 6. Configure: combine with the existing 2+0 link become 3+0 ePLA Dismantle/ Remain: 1. Remain existing Huawei link (antenna, ODU, IDU, IF cables) to configure 3+0 ePLA | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202408080495-MTK | 2024-09-20 | 2024-09-19 | Completed | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-09-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-09-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-08-01 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | SHUJAAT//ALI/6800000124 |  |  | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-08-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-02-29: 2024-07-29; 2024-02-29: 2024-07-31; 2024-02-29: 2024-07-29; 2024-03-04: 2024-07-30 |  |  | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
S01445-S00468 | KAMPUNG PAKALANGAN | DU00003501233 | Sabah | Sabah | 4.375600 | 118.560100 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB
K00892-K00450 | TMN LEMBAH BUJANG | DU00003501234 | Northern | Kedah | 5.706229 | 100.436000 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Planning | Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | SWAP MW LINK K00892/4237K-K00450/4949B WITH HUAWEI_18G_2+0_112MHZ EXISTING MW CFG: SM_18GHZ_1+0_56MHZ. Already deployed. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4332C-4083B | Politeknik Seb. Prai (REL) | DU00003501235 | Northern | Penang | 5.369076 | 100.426153 |  |  |  | MAY 24 | RFS |  | ZTE | 00. Integrated/RFS Done | 15/5: D2: Cutover done 14/5: MOS & TI In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X ISM8 CARD 2X 18G 0.6M DP ANTENNA 2X 18G XMC-3E SUB B HI 2X 18G XMC-3E SUB B LO | MW Swap | SWAP MW LINK 4332C-4083B WITH HUAWEI_18G_2+0_112MHZ_0.6M_1.63KM EXISTING MW CFG: HW_23GHZ_1+0 IMPACTED SITES: 4332C NE: AT 4332C: 1. INSTALL NEW ISM8 CARD AT RTN01(44-13975) SLOT 3 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 2+0 18G XMC-3E SUB B 4. CONFIGIURE LINK 18G 2+0 112MHZ 5. DISMANTLE EXISTING LINK EXCEPT IDU FE: AT 4083B: 1. INSTALL NEW ISM8 CARD AT RTN03(44-23975) SLOT 3 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 2+0 18G XMC-3E SUB B 4. CONFIGIURE LINK 18G 2+0 112MHZ 5. DISMANTLE EXISTING LINK EXCEPT IDU | [7 empty] | GCI | SQ202411080263-GCI | GCI | SQ202407020120-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2024-08-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-08-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240503A0 |  | 2024-05-04 | 2024-05-09 | Completed | 2024-05-03 | 2024-05-04 | 2024-05-03 | 2024-05-09 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-14 | 2024-05-28 | 2024-05-14 | 2024-05-16 | team7gcitechnicalteam7gcitechnical | GCI TI | 2024-05-14 | 2024-05-28 | 2024-05-14 | 2024-05-16 | team7gcitechnicalteam7gcitechnical | GCI TI | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-05-14 | 2024-05-28 | 2024-05-14 | 2024-05-16 | team7gcitechnicalteam7gcitechnical | 2024-05-14 | 2024-05-28 | 2024-05-14 | 2024-05-15 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
4474A-1157A | Sg Besar | DU00003501236 | Central | Selangor | 3.657700 | 100.998150 |  |  |  |  | Cancel / Drop | WK09 Closed by MSP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop |  |  |  | Cancel / Drop | WK09 Closed by MSP | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4481A-A00860 | Lekir | DU00003501237 | Northern | Perak | 4.177801 | 100.652350 |  |  | WK13 | MAR 24 | RFS | Pending plan | ZTE | 00. Integrated/RFS Done | 26/3: Cutover done | TSS+AA+TI | L1+ATP+PAC | 2X RTN 910A 1X ISM8 CARD 2X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB A HI 1X 18G XMC-5D SUB A HI | MW New Link / Reroute | ADD NEW MW LINK 4481A-A00860 WITH HUAWEI_18GHZ_2+0_112MHZ_0.6M_2.67KM IMPACTED SITES: 4524D SERVICE VLAN: 4524D 4481A: 1. INSTALL NEW RTN 910A + 1 ISM8 CARD 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 5. SHIFT 4481A-4524D IF CABLE & CONFIGURATION FROM RTN02-4-ISM8-2 TO NEW RTN 910A A00860: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 5. PATCH NEW RTN TO CELCOM A00860 OB FIBER | [7 empty] | GCI | SQ202409120132-GCI | GCI | SQ202411040342-GCI | 2025-12-12 | 2025-12-14 | Completed | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | SAMANTHA LOOI SHU-YI6237001479 |  |  |  | Unassigned | Completed |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24031220 |  | 2024-03-13 | 2024-03-15 | Completed | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-15 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-16 | 2024-03-31 | 2024-03-16 | 2024-03-23 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-03-16 | 2024-06-30 | 2024-03-16 | 2024-09-13 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-08-08 | 2024-08-29 | 2024-08-08 | 2024-09-20 | ANWAR//BIN ABDUL RASID/6800000149 | 2024-02-29: 2024-03-16; 2024-02-29: 2024-03-31; 2024-02-29: 2024-03-16; 2024-03-04: 2024-03-18 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202512170724-GCI | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q02083-Q01115 | ULU SEGAN 2 | DU00003501238 | Sarawak | Sarawak | 3.111430 | 113.078770 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | HSU//MYET CHAE/6799000011
B01064-B00504 | BAGAN TERAP | DU00003501239 | Central | Selangor | 3.749130 | 101.061380 |  |  |  |  | Cancel / Drop | Close due to not in XC HU list | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Close due to not in XC HU list |  |  |  | Cancel / Drop | [8 empty] | Nera | No PR required-Site drop/cancel | Nera | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7726B-7196A | Surau Kurnia Jaya | DU00003501240 | Sabah | Sabah | 4.247603 | 117.940070 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | Pass to Huawei and verification found new link already installed | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | AB.RAHMAN//BIN MAT NOOH/6237001519
1007C-2435A | Green Valley Park | DU00003501241 | Central | Selangor | 3.290400 | 101.474800 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
N00047-N00118 | KM247SGGADUT | DU00003501242 | Southern | Sembilan | 2.625441 | 101.999649 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop |  |  |  | Cancel / Drop | Link to decom (Huawei NIC) | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
B02212-B00557 | JLN SEGENTING BANTING | DU00003501243 | Central | Selangor | 2.890200 | 101.466900 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 22/1/2024 : Cutover done 21/1/2025 : Installation complete, pending cutover 20/1/2025 : Cancel proceed due to not receive keys 19/1/2025 : EDOTCO (M) SDN BHD - MONOPOLE 45M LAND - NE site B02212 JLN SEGENTING BANTING, EDOTCO (M) SDN BHD - TOWER 45M LAND - FE site B00557 B058E_B00557OD_TLKPGARANG, EDOTCO (M) - 24M Lampole - Patching site 3294C Tlk Panglima Garang (REL) 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 23G 0.6M DP ANTENNA 1X 23G XMC-3E SUB B HI 1X 23G XMC-3E SUB B LO | MW New Link / Reroute | MW NEW LINK B02212-3294C WITH HUAWEI_23G_1+0_112MHZ_0.6M/0.6M_1024QAM_SUB B_954MBPS_1.3KM PATCHING FE IDU 3294C TO B00557 USE OB FIBER IMPACTED: B02212 DISMANTLE EXISTING LINK B02212-B00557 NE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM FE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. IDU PATCHING TO OB FIBER B00557 | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. IDU PATCHING TO OB FIBER B00557 | [5 empty] | Magicell | SQ202502050311-Magicell | Magicell | SQ202501270124-Magicell // SQ202504260146-Magicell | 2025-03-13 | 2025-03-11 | Completed | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-01-31 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-07 | 2025-02-08 | 2025-02-07 | 2025-02-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-11 | 2025-03-13 | 2025-03-11 | 2025-03-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25011490 |  | 2025-01-15 | 2025-02-07 | Completed | 2025-01-14 | 2025-01-15 | 2025-01-14 | 2025-02-07 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-20 | 2025-01-31 | 2025-02-07 | 2025-02-07 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-01-20 | 2025-01-31 | 2025-02-04 | 2025-02-07 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-22 | 2025-01-20 | 2025-01-31 | 2025-01-27 | 2025-01-27 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-01-20 | 2025-01-31 | 2025-01-22 | 2025-01-22 | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
2936C-1777B | Taman Bidara Selayang | DU00003501244 | Central | Selangor | 3.241986 | 101.644188 |  |  | WK16 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 5/4: Cutover done 4/4: D1: MOS & TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112MHZ_0.6M/0.6M_512QAM_SUB B | MW Swap | MW SWAP MW LINK 2936C-1777B WITH HUAWEI_18G_2+0_112MHZ_0.6M/0.6M_512QAM_SUB B NE: 1. REUSE EXISTING IDU RTN910 RTN01 SLOT 7 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK FE: 1. REUSE EXISTING IDU RTN910 RTN01 SLOT 7 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | MTK | SQ202404170286-MTK | MTK | SQ202409110359-MTK | 2024-06-07 | 2024-06-04 | Completed | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. |  | Unassigned | Completed |  | 2024-04-29 | 2024-04-30 | 2024-04-29 | 2024-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-29 | 2024-04-30 | 2024-04-29 | 2024-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-06-04 | 2024-06-07 | 2024-06-04 | 2024-06-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24040211 |  | 2024-04-03 | 2024-04-03 | Completed | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-04 | 2024-04-30 | 2024-04-04 | 2024-04-18 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-04-04 | 2024-04-30 | 2024-04-04 | 2024-04-23 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-04-05 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-04-04 | 2024-04-30 | 2024-04-04 | 2024-04-07 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-04-04 | 2024-04-30 | 2024-04-04 | 2024-04-05 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | NG HONG JIE7018000036 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
A00574-A00576 | POSRAYA_G9 | DU00003501245 | Northern | Perak | 4.572800 | 101.263800 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Planning | Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  | NA | Cancel / Drop | A00574-A00576 dismantle Celcom MW link. A00574 is colo site 4542B , TX Decom at A00574. New TX route 4542B - 4905B - A00564. Swap existing SM 13G_1+0_28M to HW 13G_4+0_28M follow the new TX route , it has implemented in TX rollout project. Current Utilization is 47% based on EMS , history performance instances unable to captured due to not enable in EMS. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4634D-4018B | Kelab Gelugor (REL) | DU00003501246 | Northern | Penang | 5.369328 | 100.309778 |  |  |  | JUN 24 | Planning | Planning WIP | ZTE | 00. Integrated/RFS Done | Remote Upgrade DONE | AA | PAC |  | MW Remote Upgrade | REMOTE UPGRADE FOR MW 4634D-4018B: CHANGE TO HUAWEI_18G_1+0_112MHZ. EXISTING MW CFG: HW_18G_1+0_56MHZ IMPACTED SITES: 4634D NE: CHANGE TO HUAWEI_18G_1+0_112MHZ. FE: CHANGE TO HUAWEI_18G_1+0_112MHZ. | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-06-24 | C.PRATHABAN///6798000081 | [17 empty] | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
9037C-9373B | Lorong Apollo Sungai Merah | DU00003501247 | Sarawak | Sarawak | 2.327628 | 111.847425 |  |  |  | JUN 25 |  | Pending TI | ZTE | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE FROM 18G_56MHz TO 112MHZ_256QAM_779MHZ | REMOTE UPGRADE FROM 18G_56MHz TO 112MHz_256QAM_779Mhz | REMOTE UPGRADE FROM 18G_56MHz TO 112MHz_256QAM_779Mhz | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-01 | [15 empty] | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB_AA | SQ202510300154-GTSB | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | HSU//MYET CHAE/6799000011
K00416-K00380 | BATUPUTIHHOTST | DU00003501248 | Northern | Kedah | 5.452100 | 100.633300 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Upgrade under NIC DU: K00416_PostMOCN & K00416_PostMOCN1 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2274A-2715B | Tmn Kajang Mulia | DU00003501249 | Central | Selangor | 2.998667 | 101.795775 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop |  |  |  | Cancel / Drop | NIC NOV 2024 PLAN. UPGRADE UNDER NIC. RPM NEED TO SPEED UP NIC TX UPGRADE DUE TO HU. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9979A-9458A | Taman Matang | DU00003501250 | Sarawak | Sarawak | 1.575161 | 110.280586 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | HSU//MYET CHAE/6799000011
9570B-9363B | Kampung Hulu Nyalau | DU00003501251 | Sarawak | Sarawak | 3.602191 | 113.426530 |  | FEB 25 |  | AUG 25 | Planning | Planning WIP | ZTE | 00. Integrated/RFS Done | 10/9/2025 : RSL not meet KPI due to blockage TNB cable 2605: Pending Subcon to proceed TI. 2/9: Pending Tx Solution for HU | TSS+AA+TI |  | Install new parallel link to config as 13G_4+0_28M. NE_9570B 1.Install new 13G_DP_1.2m(MDD) x1. 2.Install new 13G_XMC_5D, Sub_A_L0 x 1. 3.Install new ISM8 x2. FE_9363B 1.Install new 13G_ DP_1.8m(MDD) x1. 2.Install new 13G_XMC_5D , Sub_A_Hi x1. 3.Install new ISM8 x2. | MW Parallel Link | Existing 13G_1+0_28M_XPIC. Install new parallel link to config as 13G_4+0_28M_CA. Site Impacted : 9570B. NE_9570B 1.Install new 13G_DP_1.2m(MDD). 2.Reuse existing RTN910A, 9570B_RTN01. 3.Install new 13G_XMC_5D,Sub_A_L0. 4.Install new 3_ISM8-2+0 & 4_ISM8-2+0 into existing 9570B_RTN01. 5.Create EPLA with existing 1+0_XPIC and service cross connect. 6.No decom due to new parallel link. FE_9363B 1.Install new 13G_ DP_1.8m(MDD). 2.Reuse existing RTN910A, 9363B_RTN01. 3.Install new 13G_XMC_5D , Sub_A_Hi. 4.Install new 3_ISM8-2+0 & 4_ISM8-2+0 into existing 9363B_RTN01. 5.Create EPLA with existing 1+0_XPIC and service cross connect. 6.No decom due to new parallel link. | [7 empty] | Trintel | SQ202501270116-Trintel | Trintel | SQ202503240715-Trintel // SQ202503240717-Trintel // SQ202506170554-Trintel | 2025-02-07 | 2025-02-06 | Completed | 2025-01-24 | 2025-01-25 | 2025-01-24 | 2025-02-05 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-06 | 2025-02-07 | 2025-02-06 | 2025-02-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-06 | 2025-02-07 | 2025-02-06 | 2025-02-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-06 | 2025-02-07 | 2025-02-06 | 2025-02-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022689 |  | 2025-02-28 | 2025-03-14 | Completed | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-03-14 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-17 | 2025-04-17 | 2025-03-18 | 2025-03-18 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-03-17 | 2025-04-17 |  |  | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | [7 empty] | 2025-03-17 | 2025-04-17 |  |  | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-02-29: 2025-03-17; 2024-02-29: 2025-04-17; 2024-02-29: 2025-03-17; 2024-03-04: 2025-03-17 | [7 empty] | GCI | SQ202505190538-GCI | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | CHEONG/SENG/WAH/7018000306
9667C-9358A | Jalan Sibu Jaya (SJDH) | DU00003501252 | Sarawak | Sarawak | 2.244259 | 111.977303 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB
9080B-9382B | Fortune Commercial Centre | DU00003501253 | Sarawak | Sarawak | 2.292437 | 111.835562 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | no more in MSP tracker_W22 and AVG Utili 40% | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB
9257B-9145A | Permai Jaya | DU00003501254 | Sarawak | Sarawak | 2.306645 | 111.887436 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | no more in MSP tracker_W22_Changed Tx route in NMS | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | HSU//MYET CHAE/6799000011
Q01154-Q01155 | NG TADA | DU00003501255 | Sarawak | Sarawak | 2.084000 | 112.352900 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | HSU//MYET CHAE/6799000011
Q00236-Q00115 | KRUSEN | DU00003501256 | Sarawak | Sarawak | 1.049240 | 110.505160 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | HSU//MYET CHAE/6799000011
A01158-A00485 | RPA2 TJG RAMBUTAN | DU00003501257 | Northern | Perak | 4.662355 | 101.173000 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 2+0 112MHz 0.6m/1.2m DP NE: 1) 1xISM8 2) 1x23GHz XMC3 Sub A Lo 3) 1x23GHz XMC3 Sub B Lo 3) 1x23GHz 0.6m DP FE: 1) 1xISM8 2) 1x23GHz XMC3 Sub A Hi 3) 1x23GHz XMC3 Sub B Hi 3) 1x23GHz 0.6m DP | MW Swap | Existing link NT05718 (A01158-A00485) Swap existing HW 18G 1+0 112MHz to HW 23G 2+0 112MHz (18G no material) Impact sites: A01158 NE (A01158) 1. Install new ISM8 card at existing RTN slot 3 2. Install new link at existing RTN 3-ISM8 3. Cutover traffic to new link 4. Decom existing 18G link FE (A00485) 1. Install new ISM8 card at existing RTN slot 3 2. Install new link at existing RTN 3-ISM8 3. Cutover traffic to new link 4. Decom existing 18G link. | [7 empty] | CCSMY | SQ202408220933-CCS | CCSMY | SQ202504260061-CCS // SQ202504260064-CCS // SQ202504260175-CCS | 2024-11-26 | 2024-11-26 | Completed | 2024-08-04 | 2024-08-04 | 2024-08-04 | 2024-08-04 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041366 |  | 2025-04-14 | 2025-04-15 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-22 | 2025-04-30 | 2025-04-22 | 2025-05-07 | Saleem//Muhammed/7021000077 | CCS TI | 2025-04-22 | 2025-04-30 | 2025-04-22 | 2025-05-07 | Saleem//Muhammed/7021000077 | CCS TI | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-24 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-24 | 2025-04-22 | 2025-04-30 | 2025-04-22 | 2025-05-09 | Saleem//Muhammed/7021000077 | 2025-04-22 | 2025-04-30 | 2025-04-22 | 2025-04-23 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402
4924A-1799B | Malim Prima | DU00003501258 | Northern | Perak | 3.715331 | 101.530972 |  |  |  | JUL 24 | Planning | Planning WIP | ZTE | 00. Integrated/RFS Done | 30/7: Cutover done | TSS+AA+TI | L1+ATP+PAC | 4xISM8 card NE: 1) 2xISM8 FE: 1) 2xISM8 | MW Hardware Upgrade | Existing link 4924A-1799B 2+0 (4924A RTN01-1799B RTN02) Existing link using 2+0 XMC5D To convert to 4+0 CA Final config will be 4+0 Impact site: 4924A,4078K NE (4924A) 1. Add ISM8 at RTN01 slot 3 and 4 2. Transfer existing IF cable from 7-ISM8-1 to 3-ISM8-1 3. Transfer existing IF cable from 7-ISM8-2 to 4-ISM8-1 4. Configure CA and 4+0 EPLA FE (1799B) 1. Add ISM8 RTN02 slot 3 and 4 2. Transfer existing IF cable from 7-ISM8-1 to 3-ISM8-1 3. Transfer existing IF cable from 7-ISM8-2 to 4-ISM8-1 4. Configure CA and 4+0 EPLA | [7 empty] | CCSMY | SQ202408220933-CCS | CCSMY | SQ202408080059-CCS | 2025-12-16 | 2025-12-15 | Completed | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-06 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24072012 |  | 2024-07-22 | 2024-07-23 | Completed | 2024-07-21 | 2024-07-22 | 2024-07-21 | 2024-07-23 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | ABDUL//HALIM MUKREEM BIN ABDUL LATIF/7021000062 | CCS TI | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | ABDUL//HALIM MUKREEM BIN ABDUL LATIF/7021000062 | CCS TI | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2026-04-07 | ABDUL//HALIM MUKREEM BIN ABDUL LATIF/7021000062 | 2024-02-29: 2024-07-29; 2024-02-29: 2024-07-31; 2024-02-29: 2024-07-29; 2024-03-04: 2024-07-30 |  |  | 2024-10-16 | 2024-11-16 | 2024-10-16 | 2024-10-16 | ASTI//GANIS PUTRIANI/6237001358
4900B-4574A | Puncak Arabella | DU00003501259 | Eastern | Pahang | 4.463318 | 101.383419 |  | MAY 24 | WK18 | MAY 24 | RFS |  | ZTE | 00. Integrated/RFS Done | 2/5: D3: Cutover done 30/4: D2: Continue TI 29/4: MOS & TI WIP. Continue 30/4 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28MHZ_256QAM_1.2M/1.2M_512QAM_SUB A | MW Swap | MW SWAP MW LINK 4900B-4574A SM MW1 WITH HUAWEI_15G_4+0_28MHZ_1.2M/1.2M_256QAM_SUB A_WITH CA IMPACTED SITE: 4443B, 4102D, 4021C NE: 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND A 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND A 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | GCI | SQ202409100301-GCI | GCI | SQ202409100489-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24040483 |  | 2024-04-05 | 2024-04-17 | Completed | 2024-04-04 | 2024-04-05 | 2024-04-04 | 2024-04-17 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-29 | 2024-05-03 | 2024-04-29 | 2024-05-08 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2024-04-29 | 2024-05-03 | 2024-04-29 | 2024-05-20 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-04-29 | 2024-05-03 | 2024-04-29 | 2024-05-08 | MOHD SAIDI BIN ABD RAZAK6800000181 | 2024-04-29 | 2024-05-03 | 2024-04-29 | 2024-05-02 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-10 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-09-09 | 2024-10-09 | 2024-09-09 | 2024-09-09 | ASTI//GANIS PUTRIANI/6237001358
4673C-4042A | Pine Residence | DU00003501260 | Northern | Penang | 5.381510 | 100.275338 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Integrated/RFS Done | 10/9: D2: Cutover done 9/9: MOS & Pre-installation In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1) 1x18G XMC3E Sub A Lo 2) 1xISM8 card FE: 1) 1x18G XMC3E Sub A Hi 2) 1xISM8 card | MW Hardware Upgrade | To add ISM8 card and change ODU to support 112MHz Impact site: 4673C NE (4673C RTN01): 1) Add ISM8 card at slot 3 2) Transfer IF cable to 3-ISM8-1 3) Replace ODU with new XMC3E 4) Upgrade 112MHz FE (4042A RTN01): 1) Add ISM8 card at slot 3 2) Transfer IF cable to 3-ISM8-1 3) Replace ODU with new XMC3E 4) Upgrade 112MHz | [7 empty] | CCSMY | SQ202410010443-CCS | CCSMY | SQ202410010451-CCS | 2025-12-16 | 2025-12-15 | Completed | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24083046 |  | 2024-08-31 | 2024-09-03 | Completed | 2024-08-30 | 2024-08-31 | 2024-08-30 | 2024-09-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-09 | 2024-09-30 | 2024-09-09 | 2024-09-12 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2024-09-09 | 2024-09-30 | 2024-09-09 | 2024-09-12 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-09-09 | 2024-09-30 | 2024-09-09 | 2024-09-10 | Muhamad//rais bin mat isa/7021000043 | 2024-09-09 | 2024-09-30 | 2024-09-09 | 2024-09-10 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | NG HONG JIE7018000036 | Logistic Team | 2024-10-16 | 2024-11-16 | 2024-10-16 | 2024-10-16 | ASTI//GANIS PUTRIANI/6237001358
1423A-3801C | Sg.Buaya (Celcom) | DU00003501261 | Central | Selangor | 3.375520 | 101.520279 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop |  |  |  | Cancel / Drop | Upgrade done under NIC. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3784A-1965B | Pangsapuri Alam Perdana | DU00003501262 | Central | Selangor | 3.257219 | 101.449400 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop | TSS |  |  | Cancel / Drop | HU ON 8May - Utilization 52% | [7 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Ongoing | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4090D-4624B | Taman Seri Bayu Bedong | DU00003501263 | Northern | Kedah | 5.709412 | 100.544370 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | done under 2024 DU NIC 4090D_PostMOCN | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505070167-GTSB | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | AB.RAHMAN//BIN MAT NOOH/6237001519
S00777-S00133 | KAMPUNG KIRIMAN | DU00003501264 | Sabah | Sabah | 6.908000 | 117.088800 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB
9663C-9165A | Pekan Siburan (REL) | DU00003501265 | Sarawak | Sarawak | 1.364171 | 110.404120 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB
7667B-7642B | Bromas Camp Tawau | DU00003501266 | Sabah | Sabah | 4.628183 | 117.744956 |  |  |  |  | Drop | Pass to Huawei |  | 03. TSS Only | TSS only | TSS |  | 18GHz_1.2m/1.2m_MDD_1+0_110MHz_SB A | MW Swap | MW Swap Huawei 18G 1+0 1.2m &1.2m 110MHz NE: 1. Swap existing IDU with RTN910A. 3. Swap existing Antenna with HW 1.2m MDD. 4. Swap existing ODU with 18G XMC 5D (SB A). 5. Configure link as 18GHz 1+0 110MHz_CA. FE: 1. Swap existing IDU RTN 03 with RTN910A. 3. Swap existing Antenna with HW 1.2m MDD. 4. Swap existing ODU with 18G XMC 5D (SB A). 5. Configure link as 18GHz 1+0 110MHz_CA. | [7 empty] | GTSB | SQ202404030674-GTSB |  |  | 2025-10-24 | 2025-10-24 | Completed | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | PAVITRAN AL CHINNAKOLANDAY6799000150 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-04-04 | 2024-04-05 | 2024-04-04 | 2024-04-04 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-04 | 2024-04-05 | 2024-04-04 | 2024-04-04 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2025-10-17 | 2025-10-24 | 2025-10-24 | 2025-10-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7642B-7622A | Bromas SBC | DU00003501267 | Sabah | Sabah | 4.596586 | 117.741826 |  | MAR 24 |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | 1. 7642B-7622 7G - no 7G/8G Material | TSS |  | 7GHz_1.8m/1.8m_DP_2+0_28MHz | MW Swap | MW Swap Huawei 7G 1+0 1.8m&1.8m 28MHz to 7G 2+0 1.8M&1.8m 28MHz NE: 1. Reuse existing RTN910A RTN_04. 2. Swap new HW DP antenna 1.8m. 3. Install new ODU. 4. Install new ISM_8 at Slot 4 and shift existing link from ISV-3 at Slot 3 to ISM8. 5. Configure link as 7GHz 2+0 28MHz EPLA with existing 1+0. FE: 1. Reuse existing RTN950A RTN_08 2. Swap new HW DP antenna 1.8m. 3. Install new ODU. 4. Install new ISM_8 at Slot 5 and shift existing link from ISV-3 at Slot 3 to ISM8. 5. Configure link as 7GHz 2+0 28MHz EPLA with existing 1+0. | [7 empty] | GTSB | SQ202404030674-GTSB |  |  | 2024-11-15 | 2024-11-11 | Completed | 2024-04-02 | 2024-04-30 | 2024-04-02 | 2024-04-02 | PAVITRAN AL CHINNAKOLANDAY6799000150 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-02 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-02 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-11-11 | 2024-11-15 | 2024-11-11 | 2024-11-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | 7G - no 7G/8G Material |  |  | Not started | [8 empty] | Unassigned | Not started
3982B-1434B | Kuil Sri Purvaneshwari Amman | DU00003501268 | Central | Selangor | 3.061738 | 101.505086 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop |  |  |  | Cancel / Drop | Closed by MSP 13Apr | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9700B-9135A | Jalan Au Yoong Selatan | DU00003501269 | Sarawak | Sarawak | 2.312222 | 111.837500 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB
K00336-K00406 | KGPISANG | DU00003501270 | Northern | Kedah | 6.289000 | 100.647400 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Already divert to xD CP(4999A).Not proceed. Link close due to low utilization. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505070167-GTSB
K00917-K00416 | TMN MUTIARA_KARANGAN | DU00003501271 | Northern | Kedah | 5.436328 | 100.641035 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Planning | Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Need to drop for upgrade in Mini Project due to MW Link K00917-K00416(NT05426) already replaced by HW MW Link K00917/4246K-K00416/4202K. Capa 889Mbps and current utilization <60%. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4795A-4640A | Jalan Melor Sg Petani (REL) | DU00003501272 | Northern | Kedah | 5.668779 | 100.476799 |  | MAY 24 |  | JUN 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done | 17/7: D1: Cutover done 10/7: EB CRQ start 17/7 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB A HI 1X 18G XMC-5D SUB A LO | MW Swap | SWAP MW LINK 4795A-4640A WITH HUAWEI_18G_2+0_56MHZ_0.6M_2.87KM EXISTING MW CFG: HW_18GHZ_1+0_56MHZ_CH2 IMPACTED SITES: 4795A NE: AT 4795A: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB A 4. CONFIGURE LINK 18G 2+0 56MHZ 5. PATCH 4795A BBU TO NEW RTN 910A 6. DISMANTLE EXISTING LINK FE: AT 4640A: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB A 4. CONFIGURE LINK 18G 2+0 56MHZ 5. PATCH NEW RTN 910A TO NEW CP PORT 6. DISMANTLE EXISTING LINK EXCEPT IDU | [7 empty] | GCI | SQ202408220943-GCI | GCI | SQ202408080062-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-24 | 2024-07-24 | 2024-07-24 | 2024-07-24 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240619AQ |  | 2024-06-20 | 2024-06-27 | Completed | 2024-06-19 | 2024-06-20 | 2024-06-19 | 2024-06-27 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-07-18 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-07-18 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-17 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-07-18 | SAFUAN//BIN YUSOFF/6800000178 | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-07-17 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
7068C-7209A | Taman Sempul | DU00003501273 | Sabah | Sabah | 4.467922 | 118.591585 |  |  |  |  | Drop/Cancel | Cancel/Drop | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop |  |  |  | Cancel / Drop | Tx Upgrade Done under 7068C (NIC) | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4635D-4475B | Bdr Baru Teluk Intan | DU00003501274 | Northern | Perak | 4.026670 | 101.027000 |  | MAR 24 |  | MAR 24 | RFS | Pending L1 | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X RTN 910A 2X 18G 0.6M MDD ANTENNA 1X 18G 112MHZ XMC-5D SUB A HI 1X 18G 112MHZ XMC-5D SUB A HI | MW Swap | SWAP EXISTING 4635D-4475B MW WITH HUAWEI_18GHZ_1+0_112MHZ_0.6M_2.43KM EXISTING MW CFG: 18GHZ_1+0_56MHZ. IMPACTED SITES: 4635D 4635D: 1. REUSE EXISTING RTN01 7-ISM8 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G 112MHZ XMC-5D SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK EXCEPT IDU 4475B: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G 112MHZ XMC-5D SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 5. PATCH NEW RTN 910A TO NEW CP PORT 6. DISMANTLE EXISTING LINK EXCEPT IDU | [7 empty] | GCI | SQ202407010442-GCI | GCI | SQ202409100506-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-03-17 | 2024-03-17 | 2024-03-17 | 2024-03-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24030664 |  | 2024-03-07 | 2024-03-15 | Completed | 2024-03-06 | 2024-03-07 | 2024-03-06 | 2024-03-15 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-16 | 2024-03-31 | 2024-03-16 | 2024-03-23 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2024-03-16 | 2024-03-31 | 2024-03-16 | 2024-03-23 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-16 | 2024-03-31 | 2024-03-16 | 2024-03-29 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2024-03-16 | 2024-03-31 | 2024-03-16 | 2024-03-16 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
B00778-B01300 | PERODUA RAWANG | DU00003501275 | Central | Selangor | 3.364727 | 101.573286 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 24/1/2025 : Cutover done 23/1/2025 : FE installation complete, pending install NE site due to not receive keys without Maxis work permit 22/1/2025 : OSS don't want release keys. Need PTW Maxis for site B00778. 20/1/2025 : Cancel proceed due to not receive keys 19/1/2025 : MAXIS COMMUNICATION BERHAD - TOWER 76M LAND - NE site B00778 PERODUA RAWANG, EDOTCO (M) SDN BHD - TOWER 61M LAND - FE site B01300 SG CHOH 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112MHZ_0.3M/0.6M_DP_1024QAM_SUB A & B_1778MBPS | MW Parallel Link | MW PARALLEL LINK B00778-B01300 WITH HUAWEI_18G_2+0_112MHZ_0.3M/0.6M_DP_1024QAM_XMC-3E_SUB A & B_1778MBPS_2.52KM_EPLA WITH EXISTING LINK IMPACTED: B00778 DISMANTLE EXISTING LINK NE: 1. INSTALL NEW IDU RTN910 2. INSTALL 1 UNIT ISM8 CARD AT NEW IDU SLOT 3 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. INSTALL NEW 18G XMC-3E SUB BAND A & B AT SLOT 7 5. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 6. TRANSFER EXISTING LINK IF CABLE TO NEW IDU SLOT 3 7. CREATE EPLA WITH EXISTING LINK 2+0 FE: 1. INSTALL NEW IDU RTN910 2. INSTALL 1 UNIT ISM8 CARD AT NEW IDU SLOT 3 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. INSTALL NEW 18G XMC-3E SUB BAND A & B AT SLOT 7 5. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 6. TRANSFER EXISTING LINK IF CABLE TO NEW IDU SLOT 3 7. CREATE EPLA WITH EXISTING LINK 2+0 8. PATCH TO NEW CP PORT | 1. INSTALL NEW IDU RTN910 2. INSTALL 1 UNIT ISM8 CARD AT NEW IDU SLOT 3 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. INSTALL NEW 18G XMC-3E SUB BAND A & B AT SLOT 7 5. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 6. TRANSFER EXISTING LINK IF CABLE TO NEW IDU SLOT 3 7. CREATE EPLA WITH EXISTING LINK 2+0 | 1. INSTALL NEW IDU RTN910 2. INSTALL 1 UNIT ISM8 CARD AT NEW IDU SLOT 3 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. INSTALL NEW 18G XMC-3E SUB BAND A & B AT SLOT 7 5. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 6. TRANSFER EXISTING LINK IF CABLE TO NEW IDU SLOT 3 7. CREATE EPLA WITH EXISTING LINK 2+0 8. PATCH TO NEW CP PORT | [5 empty] | Magicell | SQ202502050311-Magicell | Magicell | SQ202501270124-Magicell // SQ202504260146-Magicell | 2025-03-13 | 2025-03-11 | Completed | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-01-31 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-07 | 2025-02-08 | 2025-02-07 | 2025-02-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-11 | 2025-03-13 | 2025-03-11 | 2025-03-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25011491 |  | 2025-01-15 | 2025-02-07 | Completed | 2025-01-14 | 2025-01-15 | 2025-01-14 | 2025-02-07 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-20 | 2025-01-31 | 2025-02-07 | 2025-02-07 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-01-20 | 2025-01-31 | 2025-02-04 | 2025-02-07 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2025-01-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-24 | 2025-01-20 | 2025-01-31 | 2025-01-24 | 2025-01-24 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-01-20 | 2025-01-31 | 2025-01-24 | 2025-01-24 | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
S00589-S01445 | PULAU MABUL | DU00003501276 | Sabah | Sabah | 4.244894 | 118.631061 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | Pass to Huawei as Gyn remark 12Jun'25 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | AB.RAHMAN//BIN MAT NOOH/6237001519
S01442-S00250 | KAMPUNG SUNGAI BUAYA | DU00003501277 | Sabah | Sabah | 4.469530 | 118.525280 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | HSU//MYET CHAE/6799000011
9009C-9429A | Matang Malihah | DU00003501278 | Sarawak | Sarawak | 1.551796 | 110.241019 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | no more in MSP tracker_W22 and AVG Utili 33.7% | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | HSU//MYET CHAE/6799000011
K00423-K00417 | NAMI | DU00003501279 | Northern | Kedah | 6.055600 | 100.762200 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Drop. Link not in HU tracker (WK52 2025) | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505070167-GTSB
N00306-N00162 | N00306_TMNDESAKASIA | DU00003501280 | Southern | Sembilan | 2.826460 | 101.777450 |  | MAY 24 |  | JUN 24 |  | Pending DO | ZTE | 00. Site Out/Drop | 14/10: DR done by Perwira 16/8. DRCDMY012202408010006 26/6: Link Drop. SOW done by MSP | NA |  | NE: 1x IDU 910A 1x ISM8 Card 2+0 15G ODU Subband A 2x waveguide and hybrid coupler (for V & H polar) FE: 1x IDU 910A 1x ISM8 Card 2+0 15G ODU Subband A 2x waveguide and hybrid coupler (for V & H polar) | MW Hardware Upgrade | NE: 1. Swap existing IDU with IDU 910A. Install 1x ISM8 Card. 2. Reuse existing 1.2m DP Antenna. Install waveguide & coupler for V and H polarization. 3. Reuse existing 15G 2+0 ODU. Install 15G 2+0 ODU (Subband A). 4. Configure link 15G 4+0 28Mhz. FE: 1. Swap existing IDU with IDU 910A. Install 1x ISM8 Card. 2. Reuse existing 1.2m DP Antenna. Install waveguide & coupler for V and H polarization. 3. Reuse existing 15G 2+0 ODU. Install 15G 2+0 ODU (Subband A). 4. Configure link 15G 4+0 28Mhz. | [7 empty] | Perwira | No PR required-Site drop/cancel | Perwira | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24060322 | 14/10: DR done by Perwira 16/8. DRCDMY012202408010006 | 2024-06-04 | 2024-06-22 | Completed | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-22 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed | [40 empty] | GTSB_AA | SQ202510300156-GTSB
1431B-1799A | Sek 13 Shah Alam Club | DU00003501281 | Central | Selangor | 3.074506 | 101.535295 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop |  |  |  | Cancel / Drop | Swap to Huaweidone under NIC. High utilization solved | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01190-Q00518 | SG ANTU | DU00003501282 | Sarawak | Sarawak | 1.922638 | 111.242606 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB | 2025-06-24 | 2025-06-24 | 2025-06-17 | 2025-06-24 | HSU//MYET CHAE/6799000011
A01110-A00287 | KG TERSUSUN TANAH HITAM | DU00003501283 | Northern | Perak | 4.725930 | 101.140300 |  | MAY 24 |  | JUN 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done | 10/7: D2: Cutover done 9/7: D1: Spill W27. TI done, Pending config & alignment - heavy rain. Continue 10/7 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Swap | SWAP MW LINK A01110-A00287 WITH HUAWEI_18G_1+0_112MHZ_0.6M_1.63KM EXISTING MW CFG: SM_18GHZ_1+0 IMPACTED SITES: A01110 NE: AT A01110: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. PATCH A01110 BBU TO NEW RTN 910A 6. DISMANTLE EXISTING LINK FE: AT A00287: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. PATCH NEW RTN 910A TO A00287 OB FIBER 6. DISMANTLE EXISTING LINK | [7 empty] | CCSMY | SQ202408300855-CCS | CCSMY | SQ202411120061-CCS | 2024-11-29 | 2024-11-29 | Completed | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2024-07-13 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2024-07-19 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240619AF |  | 2024-06-20 | 2024-06-26 | Completed | 2024-06-19 | 2024-06-20 | 2024-06-19 | 2024-06-26 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-07-10 | Usman MUMTAZ7021000053 | CCS TI | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-07-10 | Usman MUMTAZ7021000053 | CCS TI | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | C.PRATHABAN///6798000081 |  |  | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-08-17 | Usman MUMTAZ7021000053 | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-07-10 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
Q00169-Q00205 | PDRM SBW | DU00003501284 | Sarawak | Sarawak | 2.313470 | 111.831960 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | HSU//MYET CHAE/6799000011
B02505-B00641 | JLNSGPINANG_KLANG | DU00003501285 | Central | Selangor | 3.056756 | 101.429100 |  |  | WK32-WK35 | AUG 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 12/10: D3: Cutover done 9/10: Replan CO to 11/10 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_0.6/0.6 DP MAC | MW Swap | MW Swap Huawei B02505-B00641_18G 2+0 56MHz NE: 1. Swap Existing SM IDU with new HW RTN910A 2. Swap Existing SM ODU with new HW XMC 3_ 18GHz_ODU (Sub B) 3. Swap Existing SM Antenna with New Huawei 13GHz 0.6m DP MAC 4. Configure link as 18GHz 2+0 56MHz_512QAM FE: 1. Swap Existing SM IDU with new HW RTN910A 2. Swap Existing SM ODU with new HW XMC 3_ 18GHz_ODU (Sub B) 3. Swap Existing SM Antenna with New Huawei 13GHz 0.6m DP MAC 4. Configure link as 18GHz 2+0 56MHz_512QAM | [7 empty] | Allstar | SQ202411040252-Allstar | Allstar | SQ202409020176-Allstar // SQ202410290946-Allstar // SQ202510070055-Allstar | 2025-10-24 | 2025-10-27 | Completed | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2024-06-07 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-10 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24082307 |  | 2024-08-24 | 2024-09-03 | Completed | 2024-08-23 | 2024-08-24 | 2024-08-23 | 2024-09-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-07 | 2024-10-31 | 2024-10-07 | 2024-10-17 | AG//MOHD SHAFFIQ BIN AG SIDEK/6798000203 | Allstar TI | 2024-10-07 | 2024-10-31 | 2024-10-07 | 2024-11-20 | AG//MOHD SHAFFIQ BIN AG SIDEK/6798000203 | Allstar TI | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-10-08 | 2024-10-31 | 2024-10-08 | 2024-10-14 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | 2024-10-08 | 2024-10-31 | 2024-10-08 | 2024-10-12 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | NG HONG JIE7018000036 | Logistic Team | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
K00277-K00179 | BUKITAPING | DU00003501286 | Northern | Kedah | 5.132400 | 100.585700 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Planning | Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Existing SM MW Link 3+0)15G+18G) had sufficient capacity(~1500Mbps). Trigger Celcom NOC to check 3rd channel had RSL ~94dBm(suspect ODU problem). | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
B00027-B01841 | TMN_BKT_SUBANG 2 | DU00003501287 | Central | Selangor | 3.168800 | 101.517600 | WK07 | FEB 25 | WK07 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 15/2/2025 : Cutover done 14/2/2025 : Installation complete, alignment WIP 3/8: D2: Cutover done. Post-CO T/shooting WIP. RSL need to rectify due LOS critical (blocking by tree branches) 2/8: MOS & Pre-installation WIP 1/8/2024 : EDOTCO (M) SDN BHD - BOOM 3M ROOFTOP - NE site B00027 TMN_BKT_SUBANG 2, ASIASPACE SDN BHD - WATER TANK 24M LAND - FE site B01841 B061G_B01841OD_WTTMNBKTSUBANG, EDGEPOINT INFRA - 30M Monopole - Patching site 1365B Tmn Bukit Subang (REL) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112MHz_512QAM_0.6M/0.6M_SUB B_889MBPS | MW Swap | MW SWAP LINK W00027-B01841 WITH HUAWEI_23G_2+0_112MHz_512QAM_0.6M/0.6M_SUB B EPLA WITH EXISTING LINK NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. TRANSFER ODU FROM EXISTING LINK TO NEW LINK 6. DISMANTLE ANTENNA AND IDU FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. IDU PATCHING TO 1365B 6. TRANSFER ODU FROM EXISTING LINK TO NEW LINK 7. DISMANTLE EXISTING ANTENNA AND IDU | [7 empty] | Allstar | SQ202407050105-Allstar | GCI | SQ202504150088-GCI // SQ202510130790-GCI // SQ202510130807-GCI | 2024-08-03 | 2024-08-02 | Completed | 2024-05-21 | 2024-05-21 | 2024-05-24 | 2024-05-24 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-07-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-07-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-02 | 2024-08-03 | 2024-08-02 | 2024-08-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022478 |  | 2024-07-31 | 2024-08-02 | Completed | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-08-02 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-01 | 2024-08-31 | 2024-08-01 | 2024-09-12 | SAQIB//ZIA/6798000199 | Allstar TI | 2024-08-01 | 2024-08-31 | 2024-08-01 | 2024-09-12 | SAQIB//ZIA/6798000199 | Allstar TI | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-02-14 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-14 | 2025-02-14 | 2025-02-21 | 2025-02-13 | 2025-02-25 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2024-08-01 | 2024-08-31 | 2024-08-01 | 2024-08-02 | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-08-16 | NG HONG JIE7018000036 | Logistic Team | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
Q01867-Q00206 | RH JELINGAI | DU00003501288 | Sarawak | Sarawak | 2.141147 | 112.151825 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | HSU//MYET CHAE/6799000011
K00354-K00352 | BT14PKSENA | DU00003501289 | Northern | Kedah | 6.187100 | 100.544200 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Already MOCN. Current utilization under DU00002962665 is 25.5% Only. | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505070167-GTSB
Q01169-Q00906 | TG BEKAKAP | DU00003501290 | Sarawak | Sarawak | 2.317060 | 111.682868 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | HSU//MYET CHAE/6799000011
7014K-7643A | S109A_S01766OD_RAMOSPGTENGHILAN | DU00003501291 | Sabah | Sabah | 6.252498 | 116.333295 |  |  |  |  | Drop/Cancel | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | HSU//MYET CHAE/6799000011
Q01118-Q01117 | RH AKO | DU00003501292 | Sarawak | Sarawak | 3.187365 | 113.339502 |  |  |  |  | Doable |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M_512QAM_EPLA NE_Q01118 New 13G_2.4M(MS) x1. Re-use existing RTN910AF(NEID 183-35220). New ISM8 x1. New XMC_3, Sub A&B_Hi x2. FE_Q01117 New 13G_1.8M(MS) x1. Re-use existing RTN910AF(NEID 183-35218). New ISM8 x1. New XMC_3, Sub A&B_Lo x2. | MW Parallel Link | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(ENT LL SABAJU MILL OFFICE) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** Existing HW MW Link_SW03708, Q01118-Q01117, 8G_4+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link Q01118-Q01117, 8G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. Become 8G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. Site Impacted : Q01118, Q01810, 9259R, Q01812 & ENT LL SABAJU MILL OFFICE. NE_Q01118 1.Install new 13G_2.4M(MS) x1. 2.Re-use existing RTN910AF(NEID 183-35220) and insert ISM8 into slot 04. 3.Install new XMC_3, Sub A&B_Hi x2. Build new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link Q01118-Q01117, 8G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. Become 8G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. FE_Q01117 1.Install new 13G_1.8M(MS) x1. 2.Re-use existing RTN910AF(NEID 183-35218) and insert ISM8 into slot 04. 3.Install new XMC_3, Sub A&B_Lo x2. Build new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link Q01118-Q01117, 8G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. Become 8G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(ENT LL SABAJU MILL OFFICE) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** Existing HW MW Link_SW03708, Q01118-Q01117, 8G_4+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link Q01118-Q01117, 8G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. Become 8G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. Site Impacted : Q01118, Q01810, 9259R, Q01812 & ENT LL SABAJU MILL OFFICE. NE_Q01118 1.Install new 13G_2.4M(MS) x1. 2.Re-use existing RTN910AF(NEID 183-35220) and insert ISM8 into slot 04. 3.Install new XMC_3, Sub A&B_Hi x2. Build new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link Q01118-Q01117, 8G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. Become 8G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(ENT LL SABAJU MILL OFFICE) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** Existing HW MW Link_SW03708, Q01118-Q01117, 8G_4+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link Q01118-Q01117, 8G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. Become 8G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. Site Impacted : Q01118, Q01810, 9259R, Q01812 & ENT LL SABAJU MILL OFFICE. FE_Q01117 1.Install new 13G_1.8M(MS) x1. 2.Re-use existing RTN910AF(NEID 183-35218) and insert ISM8 into slot 04. 3.Install new XMC_3, Sub A&B_Lo x2. Build new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link Q01118-Q01117, 8G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link Q01118-Q01117, 13G_2+0_28MHZ_512QAM_EPLA. Become 8G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. | XMC-3 | MS | 13G | 13G_2.4M(MS) x1. | 13G_1.8M(MS) x1. | Trintel | SQ202511050248-Trintel | Trintel | SQ202601190587-Trintel // SQ202601190592-Trintel | 2025-11-07 | 2025-10-31 | Completed | 2025-09-16 | 2025-09-20 | 2025-09-16 | 2025-09-20 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-31 | 2025-11-07 | 2025-10-31 | 2025-10-31 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011443 |  | 2026-01-15 | 2026-01-15 | Completed | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | Fiona Wan Yen Chin7667000028 | Trintel TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-29 | Fiona Wan Yen Chin7667000028 | Trintel TI | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-30 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-02-27 | Fiona Wan Yen Chin7667000028 | 2024-02-29: 2026-01-22; 2024-02-29: 2026-01-22; 2024-02-29: 2026-01-22; 2024-03-04: 2026-01-22 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202506050662-GTSB | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | HSU//MYET CHAE/6799000011
A00966_HU | KGSGTUKANG_SIDIN | DU00005718504 | Northern | Perak | 4.058347 | 101.104858 | [7 empty] | 00. Integrated/RFS Done | 23/07: TI Started 24/07: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_A00966 New 23G_DP_1.2M(MS) x1. New RTN910A(RTN01). New XMC_3E, Sub A&B_Hi x2. New CAT6 Cable with suitable length x1. FE_4473B New 23G_DP_1.2M(MS) x1. New RTN910A(RTN01). New XMC_3E, Sub A&B_Lo x2. New Optical SFP Module 10G 1Km 1310nm x1. New Optical Patch Cord with suitable length x1. | MW New Link / Reroute | Existing SM MW Link_ID NT05337 A00966-A00172, 18G_1+1 HOT STANDBY_56M_2048QAM_471M. Install new HW MW Link A00966(RTN01)-4473B(RTN01), 23G_2+0_112M_256QAM_EPLA. Decom existing SM MW Link_ID NT05337 A00966-A00172, 18G_1+1 HOT STANDBY_56M_2048QAM_471M. Site Impacted : A00966 & A00332. NE_A00966 1.Install new 23G_DP_01.2M(MS) x1. 2.Install new RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Hi. Configure it. 4.Remain xC vlan services. 5.Enable port 8-EM6-1 of new RTN910A(RTN01). 6.Patching BBU to port 8-EM6-1 of existing RTN910A(RTN01). Configure it. 7.Migrate traffic to new link. 8.Decom existing SM MW Link_ID NT05337 A00966-A00172, 18G_1+1 HOT STANDBY_56M_2048QAM_471M. FE_4473B 1.Install new 23G_DP_01.2M(MS) x1. 2.Install new RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Lo. Configure it. 4.Remain xC vlan services and remain port Te0/0/26 at PTN/Cisco. 5.Enable port 8-EM6-3 of new RTN910A(RTN01) and insert 10G SFP Module into it. 6.Patching port 8-EM6-3 of new RTN910A(RTN01) and existing port Te0/0/26 of PTN/Cisco. Configure it. 7.Enable port 8-EM6-1 of new RTN910A(RTN01) and cascade with LAN 1 of existing SM MW Link ID_NT05370(A00332-A00966). 8.Migrate traffics A00966 & A00332 via new HW MW Link A00966(RTN01)-4473B(RTN01), 23G_2+0_112M_256QAM_EPLA. 9.Decom existing SM MW Link_ID NT05337 A00966-A00172, 18G_1+1 HOT STANDBY_56M_2048QAM_471M. | Existing SM MW Link_ID NT05337 A00966-A00172, 18G_1+1 HOT STANDBY_56M_2048QAM_471M. Install new HW MW Link A00966(RTN01)-4473B(RTN01), 23G_2+0_112M_256QAM_EPLA. Decom existing SM MW Link_ID NT05337 A00966-A00172, 18G_1+1 HOT STANDBY_56M_2048QAM_471M. Site Impacted : A00966 & A00332. NE_A00966 1.Install new 23G_DP_01.2M(MS) x1. 2.Install new RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Hi. Configure it. 4.Remain xC vlan services. 5.Enable port 8-EM6-1 of new RTN910A(RTN01). 6.Patching BBU to port 8-EM6-1 of existing RTN910A(RTN01). Configure it. 7.Migrate traffic to new link. 8.Decom existing SM MW Link_ID NT05337 A00966-A00172, 18G_1+1 HOT STANDBY_56M_2048QAM_471M. | Existing SM MW Link_ID NT05337 A00966-A00172, 18G_1+1 HOT STANDBY_56M_2048QAM_471M. Install new HW MW Link A00966(RTN01)-4473B(RTN01), 23G_2+0_112M_256QAM_EPLA. Decom existing SM MW Link_ID NT05337 A00966-A00172, 18G_1+1 HOT STANDBY_56M_2048QAM_471M. Site Impacted : A00966 & A00332. FE_4473B 1.Install new 23G_DP_01.2M(MS) x1. 2.Install new RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Lo. Configure it. 4.Remain xC vlan services and remain port Te0/0/26 at PTN/Cisco. 5.Enable port 8-EM6-3 of new RTN910A(RTN01) and insert 10G SFP Module into it. 6.Patching port 8-EM6-3 of new RTN910A(RTN01) and existing port Te0/0/26 of PTN/Cisco. Configure it. 7.Enable port 8-EM6-1 of new RTN910A(RTN01) and cascade with LAN 1 of existing SM MW Link ID_NT05370(A00332-A00966). 8.Migrate traffics A00966 & A00332 via new HW MW Link A00966(RTN01)-4473B(RTN01), 23G_2+0_112M_256QAM_EPLA. 9.Decom existing SM MW Link_ID NT05337 A00966-A00172, 18G_1+1 HOT STANDBY_56M_2048QAM_471M. | XMC_3E | MS | 23G | 23G_DP_1.2M(MS) x1 | 23G_DP_1.2M(MS) x1 | GCI | SQ202508060635-GCI | GCI | SQ202507230772-GCI // SQ202507230777-GCI // SQ202508140739-GCI | 2026-01-26 | 2026-01-21 | Completed | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-07 | 2025-08-14 | 2025-08-07 | 2025-08-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Manager | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071919 |  | 2025-07-20 | 2025-07-22 | Completed | 2025-07-19 | 2025-07-20 | 2025-07-19 | 2025-07-22 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-23 | 2025-08-06 | 2025-07-23 | 2025-08-04 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-07-23 | 2025-08-06 | 2025-07-23 | 2025-08-04 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | AKMAL//BIN RAZALI/6794000078 |  |  | 2025-07-23 | 2025-08-06 | 2025-07-23 | 2025-08-09 | MOHD SAIDI BIN ABD RAZAK6800000181 | 2025-07-23 | 2025-08-06 | 2025-07-23 | 2025-07-24 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | NG HONG JIE7018000036 | Logistic Team | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202507080632-GTSB
3181B6_HU | pBTS Masjid Kunak | DU00005718505 | Sabah | Sabah | 4.685404 | 118.250371 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_0.6/0.6_DP_SB A,B 2xISM8 2xSFP | MW Swap | MW SWAP 3181B-7931A WITH 18G_2+0_0.6/0.6_DP_128QAM_1352QAM NEED TO CONFIGURE 10G PORT AT FE | MW SWAP 3181B-7931A WITH 18G_2+0_0.6/0.6_DP_128QAM_1352QAM NE: 1. Reuse existing RTN910A and install ISM8 at slot 3 2. Swap existng ODU with XMC-3E_SB A,B. 3. Swap exisitng antenna with 0.6_DP. 4. Configure 18G_2+0_0.6_DP_128QAM_1352QAM_EPLA. | MW SWAP 3181B-7931A WITH 18G_2+0_0.6/0.6_DP_128QAM_1352QAM NE: 1. Reuse existing RTN950 and install ISM8 at Slot 3 2. Swap existng ODU with XMC-3E_SB A,B. 3. Swap exisitng antenna with 0.6_DP. 4. Configure 18G_2+0_0.6_DP_128QAM_1352QAM_EPLA. 10. Need to configure 10G port at 7931A. | XMC-3E_A,B |  | 18 | 0.6 | 0.6 | NR services | SQ202509300151-NR Services | NR services | SQ202509300159-NR Services // SQ202509300167-NR Services | 2025-11-24 | 2025-11-17 | Completed | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-25 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-24 | 2025-10-30 | 2025-10-27 | 2025-10-29 | Paula//Nina Anak Kuchop/7167000011 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-19 | 2025-11-12 | 2025-11-12 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-17 | 2025-11-24 | 2025-11-17 | 2025-11-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092412 |  | 2025-09-25 | 2025-09-26 | Completed | 2025-09-24 | 2025-09-25 | 2025-09-24 | 2025-09-26 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-25 | 2025-11-25 | 2025-10-25 | 2025-10-27 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-10-25 | 2025-11-25 | 2025-10-25 | 2025-10-27 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2025-10-25 | 2025-11-25 | 2025-10-25 | 2025-11-01 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-10-25 | 2025-11-25 | 2025-10-25 | 2025-10-27 | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | tseping//wang/6819000006 | Logistic Team | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507080638-GTSB | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | HSU//MYET CHAE/6799000011
4340D_HU | Masjid Taman Seruling | DU00005718506 | Northern | Kedah | 5.643709 | 100.513520 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M_EPLA NE_4340D New 18G_0.6M(MDD) x1. New ISM8 x1. New XMC_5D, Sub A_Hi x1. FE_4932A New 18G_1.2M(MDD) x1. New RTN910A(Naming RTN01) x1. New XMC_5D, Sub A_Lo x1. | MW Swap | Existing HW MW Link 18G_2+0_112M&56M_128QAM_EPLA + LAG at IBeam. Using 0.6m/0.6m antenna size. Swap existing HW MW Link with new HW MW Link 18G_2+0_112M_512QAM_EPLA + LAG at IBeam. Using 0.6m/1.2m antenna size. Later, decom existing HW MW Link 18G_2+0_112M&56M_128QAM_EPLA + LAG at IBeam. Site Impacted : 4340D & 4046L. NE_4340D 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN01). 3.Insert new ISM8 into slot 03 of existing RTN910A(RTN01). 4.Install new XMC_5D, Sub A_Hi x1. Configure it. 5.Re-use existing vlan services. 6.Migrate traffic to new link 18G_2+0_112M_512QAM_EPLA. Configure it. 7.Later, decom existing HW MW Link 18G_2+0_112M&56M_128QAM_EPLA. FE_4932A 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(also naming RTN01 as existing RTN910A). 3.Install new XMC_5D, Sub A_Lo x1. Configure it. 4.Create new In Band DCN. 5.Re-use existing vlan services and re-use existing 2x IBeam for LAG. 6.Enable 2x port(8-EM6-1 & 8-EM6-2) of new RTN910A(naming RTN01) for existing 2x IBeam port. Configure LAG. 7.Migrate traffic to new link 18G_2+0_112M_512QAM_EPLA. Configure it. 8.Later, decom existing HW MW Link 18G_2+0_112M&56M_128QAM_EPLA. | Existing HW MW Link 18G_2+0_112M&56M_128QAM_EPLA + LAG at IBeam. Using 0.6m/0.6m antenna size. Swap existing HW MW Link with new HW MW Link 18G_2+0_112M_512QAM_EPLA + LAG at IBeam. Using 0.6m/1.2m antenna size. Later, decom existing HW MW Link 18G_2+0_112M&56M_128QAM_EPLA + LAG at IBeam. Site Impacted : 4340D & 4046L. NE_4340D 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN01). 3.Insert new ISM8 into slot 03 of existing RTN910A(RTN01). 4.Install new XMC_5D, Sub A_Hi x1. Configure it. 5.Re-use existing vlan services. 6.Migrate traffic to new link 18G_2+0_112M_512QAM_EPLA. Configure it. 7.Later, decom existing HW MW Link 18G_2+0_112M&56M_128QAM_EPLA. | Existing HW MW Link 18G_2+0_112M&56M_128QAM_EPLA + LAG at IBeam. Using 0.6m/0.6m antenna size. Swap existing HW MW Link with new HW MW Link 18G_2+0_112M_512QAM_EPLA + LAG at IBeam. Using 0.6m/1.2m antenna size. Later, decom existing HW MW Link 18G_2+0_112M&56M_128QAM_EPLA + LAG at IBeam. Site Impacted : 4340D & 4046L. FE_4932A 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(also naming RTN01 as existing RTN910A). 3.Install new XMC_5D, Sub A_Lo x1. Configure it. 4.Create new In Band DCN. 5.Re-use existing vlan services and re-use existing 2x IBeam for LAG. 6.Enable 2x port(8-EM6-1 & 8-EM6-2) of new RTN910A(naming RTN01) for existing 2x IBeam port. Configure LAG. 7.Migrate traffic to new link 18G_2+0_112M_512QAM_EPLA. Configure it. 8.Later, decom existing HW MW Link 18G_2+0_112M&56M_128QAM_EPLA. | XMC_5D | MDD | 18G | New 18G_0.6M(MDD) | New 18G_1.2M(MDD) | Magicell | SQ202508200574-Magicell | Magicell | SQ202508270977-Magicell // SQ202508270985-Magicell | 2025-12-09 | 2025-12-02 | Completed | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082138 |  | 2025-08-22 | 2025-08-25 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-05 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | AKMAL//BIN RAZALI/6794000078 |  | 2025-09-29 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-13 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-06 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | NG HONG JIE7018000036 | Logistic Team | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202507080632-GTSB | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MAZELAN BIN RAMLI6798000096
9544A_HU | Rumah Datu Anduh | DU00005718507 | Sarawak | Sarawak | 3.640912 | 113.720359 | [6 empty] | ZTE | 05. Doable |  | TSS+AA+TI+Dismantle |  | 15G_2+0_1.2/1.2_MDD_512QAM 2xRTN910A 2xXMC-5D_SB A | MW Swap | MW SWAP EXISTING NEC 13G_1+0 WITH HW 15G_2+0_1.2/1.2_MDD_512QAM. CARRY 9544A. | MW SWAP EXISTING NEC 13G_1+0 WITH HW 15G_2+0_1.2/1.2_MDD_512QAM. NE: 1. Install new RTN910A. 2. Install new XMC_5D_SB A. 3. Install new antenna HW 15G_1.2MDD 4. Configure 15G_2+0_1.2/1.2_MDD_521QAM_450M_EPLA. 5. Carry 9544A traffic. | MW SWAP EXISTING NEC 13G_1+0 WITH HW 15G_2+0_1.2/1.2_MDD_512QAM. FE: 1. Install new RTN910A. 2. Install new XMC_5D_SB A. 3. Install new antenna HW 15G_1.2MDD 4. Configure 15G_2+0_1.2/1.2_MDD_521QAM_450M_EPLA. 5. Carry 9544A traffic. | XMC-5D_SB A |  | 15 | 1.2 | 1.2 | Magicell | SQ202509030212-Magicell | Magicell |  | 2025-11-17 | 2025-11-10 | Completed | 2025-09-03 | 2025-09-30 | 2025-09-29 | 2025-09-29 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-17 | 2025-10-14 | 2025-10-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26042502 |  | 2026-04-26 | 2026-04-26 | Completed | 2026-04-25 | 2026-04-26 | 2026-04-25 | 2026-04-26 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202507080651-GTSB | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | HSU//MYET CHAE/6799000011
4210C_HU | BBrown M Pasir (REL) | DU00005718508 | Northern | Penang | 5.313887 | 100.285694 | [7 empty] | 00. Integrated/RFS Done | 23/07: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1x ODU 18G XMC-3E SB_A HI 1x ODU 18G XMC-3E SB_A LO | MW Hardware Upgrade | Existing MW Link having RSL degradation. Team at site perform antenna re-alignment. Existing 18G_1+0_450Mbps_Util 100% Change ODU at NE and FE to get config 112Mhz | Existing MW Link having RSL degradation. Team at site perform antenna re-alignment. Change old ODU to new ODU support 112Mhz and change freq channel follow LB | Existing MW Link having RSL degradation. Team at site perform antenna re-alignment. Change old ODU to new ODU support 112Mhz and change freq channel follow LB | XMC-3E | MAC | 18G | 0.6m | 0.6m | GCI | SQ202507250118-GCI | GCI | SQ202507230772-GCI // SQ202507230777-GCI | 2025-08-13 | 2025-08-07 | Completed | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-29 | 2025-08-07 | 2025-07-29 | 2025-07-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071149 |  | 2025-07-12 | 2025-07-15 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-08-05 | 2025-07-22 | 2025-07-24 | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2025-07-22 | 2025-08-05 | 2025-07-22 | 2025-07-22 | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-22 | 2025-07-22 | 2025-08-05 | 2025-07-22 | 2025-07-28 | MUHAMAD ARIFF BIN KHASIM6800000179 | 2025-07-22 | 2025-08-05 | 2025-07-22 | 2025-07-22 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | NG HONG JIE7018000036 | Logistic Team | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202507080632-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q01831_HU | RHAGAN2 | DU00005718509 | Sarawak | Sarawak | 2.414660 | 112.175270 | [6 empty] | ZTE | 00. Site Out/Drop | 4/9/2025 : Task will do under NIC TX |  |  |  | Under NIC | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507080651-GTSB | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | HSU//MYET CHAE/6799000011
B00414_HU | KGENDAH | DU00005718510 | Central | Selangor | 2.729340 | 101.467690 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G 4+0 1.2M_1.2M MDD | MW New Link / Reroute | INSTALL NEW MW LINK B00414-1130A WITH HUAWEI_15G 4+0 28MHZ 1.2M_1.2M DP_5.3KM | MW LINK B00414-1130A WITH HUAWEI_15G 4+0 28MHZ 1.2M_1.2M DP NE: 1. Install new HW RTN910AF 2. Connect new IF cable x 2 from ODU to Slot 3-1, 3-2 3. Install new HW 1.2m MDD antenna 4. Install new XMC-5D ODU (SB A,B) 5. Configure link 15G_4+0_28MHz CA 6. Dismantle SM Link B00414-B00353 | MW LINK B00414-1130A WITH HUAWEI_15G 4+0 28MHZ 1.2M_1.2M DP FE: 1. Install new HW RTN910AF 2. Connect new IF cable x 2 from ODU to Slot 3-1, 3-2 3. Install new HW 1.2m MDD antenna 4. Install new XMC-5D ODU (SB A,B) 5. Configure link 15G_4+0_28MHz CA 6. Patch to iBeam. 7. Dismantle SM Link B00414-B00353 | [5 empty] | GCI | SQ202506300673-GCI | GCI | SQ202506300718-GCI // SQ202506300724-GCI | 2025-11-14 | 2025-11-07 | Completed | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-28 | 2025-08-06 | 2025-07-28 | 2025-07-28 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-14 | 2025-11-07 | 2025-11-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25063084 |  | 2025-07-06 | 2025-07-08 | Completed | 2025-07-05 | 2025-07-06 | 2025-07-05 | 2025-07-08 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-05 | 2025-07-12 | 2025-07-04 | 2025-07-08 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-05 | 2025-07-12 | 2025-07-04 | 2025-07-08 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-07 | 2025-07-05 | 2025-07-12 | 2025-07-04 | 2025-07-12 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-07-05 | 2025-07-12 | 2025-07-04 | 2025-07-05 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202507080560-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | LIM//WEI CHONG/6798000110
Q01710_HU | SKBRAYANG | DU00005718511 | Sarawak | Sarawak | 1.914402 | 111.409751 | [6 empty] | ZTE | 03. Pending TSS |  | TSS+AA+TI+Dismantle |  | 15G_4+0_28M_512QAM_CA NE_Q01710 New 15G_1.2M(MDD) x1. New RTN910AF(RTN01). New XMC_5D, Sub A_Lo x1. New ISM8 x1. New CAT6 cable x1. FE_Q00385 New 15G_1.2M(MDD) x1. New RTN910AF(RTN01). New XMC_5D, Sub A_Hi x1. New ISM8 x1. New CAT6 cable x1. | MW Swap | Existing SM MW link_ID SW02696 18G_1+0_28M_2048QAM. Swap existing link to new HW MW Link 15G_4+0_28M_512QAM_CA. Later, decom existing SM MW link_ID SW02696 18G_1+0_28M_2048QAM. Site Impacted : Q01710. NE_Q01710 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). Insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01) 3.Install new XMC_5D, Sub A_Lo x1. Build new HW MW Link 15G_4+0_28M_512QAM_CA. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching Traffic to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Re-use existing Vlan DCN and Vlan services. 7.Migrate traffic via new HW MW Link 15G_4+0_28M_512QAM_CA. 8.Later, decom existing SM MW link_ID SW02696 18G_1+0_28M_2048QAM. FE_Q00385 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). Insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01) 3.Install new XMC_5D, Sub A_Hi x1. Build new HW MW Link 15G_4+0_28M_512QAM_CA. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching Traffic to existing port(Gi0/0/2) at PTN/Cisco. Configure it. 6.Re-use existing Vlan DCN and Vlan services. 7.Later, decom existing SM MW link_ID SW02696 18G_1+0_28M_2048QAM. | Existing SM MW link_ID SW02696 18G_1+0_28M_2048QAM. Swap existing link to new HW MW Link 15G_4+0_28M_512QAM_CA. Later, decom existing SM MW link_ID SW02696 18G_1+0_28M_2048QAM. Site Impacted : Q01710. NE_Q01710 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). Insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01) 3.Install new XMC_5D, Sub A_Lo x1. Build new HW MW Link 15G_4+0_28M_512QAM_CA. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching Traffic to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Re-use existing Vlan DCN and Vlan services. 7.Migrate traffic via new HW MW Link 15G_4+0_28M_512QAM_CA. 8.Later, decom existing SM MW link_ID SW02696 18G_1+0_28M_2048QAM. | Existing SM MW link_ID SW02696 18G_1+0_28M_2048QAM. Swap existing link to new HW MW Link 15G_4+0_28M_512QAM_CA. Later, decom existing SM MW link_ID SW02696 18G_1+0_28M_2048QAM. Site Impacted : Q01710. FE_Q00385 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). Insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01) 3.Install new XMC_5D, Sub A_Hi x1. Build new HW MW Link 15G_4+0_28M_512QAM_CA. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching Traffic to existing port(Gi0/0/2) at PTN/Cisco. Configure it. 6.Re-use existing Vlan DCN and Vlan services. 7.Later, decom existing SM MW link_ID SW02696 18G_1+0_28M_2048QAM. | XMC-5D_SB A | MDD | 15G | 1.2 | 1.2 | Allstar | SQ202512120606-Allstar | Allstar | SQ202512120278-Allstar // SQ202512120283-Allstar |  |  | Ongoing | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25112456 |  | 2025-11-25 | 2025-11-28 | Completed | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-28 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-13 | 2025-12-19 | 2025-12-13 | 2025-12-13 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-12-13 | 2025-12-19 |  |  | TONI//ANAK KUMBONG/6798000163 | Allstar TI | [7 empty] | 2025-12-13 | 2025-12-19 |  |  | TONI//ANAK KUMBONG/6798000163 | 2025-09-23: 2025-12-13; 2025-09-23: 2025-12-19; 2025-09-23: 2025-12-13; 2025-10-06: 2025-12-13 | [7 empty] | GTSB | SQ202507080651-GTSB | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | HSU//MYET CHAE/6799000011
9024H_AD | Taiyo Yuden(Sarawak) Sdn Bhd | DU00006645357 | Sarawak | Sarawak | 1.527750 | 110.406270 | [9 empty] | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS RTN510 NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW Swap | Existing NLOS cambium faulty. To swap with Huawei NLOS equipment Site Impacted : 9024H. NE_9024H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new NLOS RTN510. 6.Decom existing Cambium radio (9024H-NLOS-9459A). FE_9459A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.Enable GE1 , ETH patching to existing 9459A_RTN01 ( ID : 20780). 6.Traffic migrate to new NLOS RTN510. 7.Decom existing Canbium Radio (9459A-NLOS-9024H). | Existing NLOS cambium faulty. To swap with Huawei NLOS equipment Site Impacted : 9024H. NE_9024H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new NLOS RTN510. 6.Decom existing Cambium radio (9024H-NLOS-9459A). | Existing NLOS cambium faulty. To swap with Huawei NLOS equipment. Site Impacted : 9024H. FE_9459A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.Enable GE1 , ETH patching to existing 9459A_RTN01 ( ID : 20780). 6.Traffic migrate to new NLOS RTN510. 7.Decom existing Canbium Radio (9459A-NLOS-9024H). | [7 empty] | Trintel | SQ202603260178-Trintel // SQ202603260183-Trintel |  |  | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030318 |  | 2026-03-04 | 2026-03-03 | Completed | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-03 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-03-05 | Chin Sun Lun7667000040 | Trintel TI | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-04-09 | Chin Sun Lun7667000040 | Trintel TI | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-02 | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-04-20 | Chin Sun Lun7667000040 | 2025-09-23: 2026-03-05; 2025-09-23: 2026-03-31; 2025-09-23: 2026-03-05; 2025-10-06: 2026-03-13 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202603170140-GCI | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | CHEONG/SENG/WAH/7018000306
4604A_AD | JBA KualaPerlis(Trunk) | DU00006645358 | Northern | Perlis | 6.396967 | 100.136690 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x PATCHCORD | BBU Patching | BBU Patch to fiber ODF port : (P1,P2) to 4601A Hotel Federal (P133,P134). | BBU Patch to fiber ODF port : (P1,P2) to 4601A Hotel Federal (P133,P134). | [6 empty] | GTSB | SQ202603040037-GTSB | GTSB | SQ202603030416-GTSB | 2026-04-15 | 2026-04-20 | Completed | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26030412 |  | 2026-03-05 | 2026-03-09 | Completed | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-04-17 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-04-17 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-13 | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-04-20 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-09-23: 2026-03-05; 2025-09-23: 2026-03-31; 2025-09-23: 2026-03-05; 2025-10-06: 2026-03-06 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202603170124-GCI | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
4601A_AD | HotelFederal Kangar | DU00006645359 | Northern | Perlis | 6.439091 | 100.197575 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x PATCHCORD | MW Re-engineering | Patch ODF port : (P133,P134) to IBEAM for site 4604A | Patch ODF port : (P133,P134) to IBEAM for site 4604A | [6 empty] | GTSB | SQ202603040037-GTSB | GTSB | SQ202603030416-GTSB |  |  | Ongoing | 2026-04-02 | 2026-04-02 | 2026-04-01 | 2026-04-01 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26030413 |  | 2026-03-05 | 2026-03-09 | Completed | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-04-07 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-04-07 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-13 | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-04-05 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-09-23: 2026-03-05; 2025-09-23: 2026-03-31; 2025-09-23: 2026-03-05; 2025-10-06: 2026-03-06 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202603170124-GCI | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
3104H_LOS | 99 Speedmart NS Broga | DU00005027529 | Central | Sembilan | 2.935750 | 101.911290 |  | FEB 25 |  | FEB 25 | TI | No LOS clear | ZTE | 00. Site Out/Drop | 13/2/2025 : Survey LOS done. No clear LOS 10/2/2025 : Digi OB - Small Cell - NE site 3104H 99 Speedmart NS Broga | TSS |  | NA | MW New Link / Reroute | Upon actual TSS LOS hunting , no LOS found , surrounding trees obstacle. | No LOS found from actual TSS LOS hunting. Proposed Fiber. | [6 empty] | MTK | SQ202502050329-MTK | MTK | No PR required-Work at TSS only | 2025-03-27 | 2025-03-27 | Completed | 2025-01-28 | 2025-01-28 | 2025-01-28 | 2025-01-28 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-12 | 2025-02-13 | 2025-02-12 | 2025-02-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-19 | 2025-02-20 | 2025-02-19 | 2025-02-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-26 | 2025-03-27 | 2025-03-26 | 2025-03-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300116-GTSB
4407D-4770A | Taman Kemboja | DU00005048645 | Northern | Kedah | 5.643399 | 100.557986 |  |  |  |  | Integrated/RFS Done |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_4407D 18G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Hi x1. FE_4470A 18G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Lo x1. | MW Swap | Existing link 18G_1+0_112M Swap existing to 18G_2+0_112M Site impacted : 4407D. NE_4407D 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no, provide by MSP team). 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link 18G_2+0_112M. 6.Decom existing IDU , ODU and Ant. FE_4470A 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4470A_RTN03. 3.Install 3_ISM8-2+0 into existing 4470A_RTN03. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new MW link 18G_2+0_112M. 7.Decom existing ODU and Ant. | Existing link 18G_1+0_112M Swap existing to 18G_2+0_112M Site impacted : 4407D. NE_4407D 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4407D_RTN01. 3.Install new 3_ISM8-2+0 into existing 4407D_RTN01. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new MW link 18G_2+0_112M. 7.Decom existing ODU and Ant. | Existing link 18G_1+0_112M Swap existing to 18G_2+0_112M Site impacted : 4407D. FE_4470A 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4470A_RTN03. 3.Install 3_ISM8-2+0 into existing 4470A_RTN03. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new MW link 18G_2+0_112M. 7.Decom existing ODU and Ant. | XMC_5D | MDD | 18G | 0.6 | 0.6 | GTSB | SQ202504170477-GTSB | GTSB | SQ202503200272-GTSB // SQ202503200273-GTSB // SQ202504260178-GTSB | 2025-10-25 | 2025-10-24 | Completed | 2025-03-20 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-09 | 2025-05-24 | 2025-05-09 | 2025-05-09 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25030310 |  | 2025-03-04 | 2025-03-04 | Completed | 2025-03-03 | 2025-03-04 | 2025-03-03 | 2025-03-04 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-10-13 | NOOR//HUSSAIN/6799000147 | GTSB TI | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-05-08 | NOOR//HUSSAIN/6799000147 | GTSB TI | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-07 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-12 | NOOR//HUSSAIN/6799000147 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509250641-GCI | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
1057A-2400A | Puspati (TM) | DU00005048646 | Central | Selangor | 2.908268 | 101.765780 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 27/2/2025 : Cutover done 26/2/2025 : FE installation complete, NE installation WIP 24/2/2025 : CELCOM (M) - Digi CSU - 30M 3-Legged Tower - NE site 1057A Puspati (TM), EDGEPOINT INFRA - 60M 3 Legged Tower - FE site 2400A KM290 NS H_way(AsiaSpace _ZED) | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 2X 18G 1.2M DP ANTENNA 2x ODU 18G XMC3E SUB B HI 2X ODU 18G XMC3E SUB B LO | MW Parallel Link | MW PARALLEL LINK 1057A-2400A WITH HUAWEI_18G_2+0_1.2M/1.2M_DP_112MHZ_128QAM_1352MBPS_XMC3E_SUB B_4.31KM EPLA WITH EXISTING LINK IMPACTED: 1057A, B02503, 1532H, 1834B, B02922 NE: 1. INSTALL NEW 1PCS ISM8 CARD AT SLOT 3 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 3. INSTALL NEW 18G 1.2M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM EPLA WITH EXISTING 2+0 FE: 1. INSTALL NEW 1PCS ISM8 CARD AT SLOT 3 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 3. INSTALL NEW 18G 1.2M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM EPLA WITH EXISTING 2+0 | 1. INSTALL NEW 1PCS ISM8 CARD AT SLOT 3 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 3. INSTALL NEW 18G 1.2M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM EPLA WITH EXISTING 2+0 | 1. INSTALL NEW 1PCS ISM8 CARD AT SLOT 3 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 3. INSTALL NEW 18G 1.2M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM EPLA WITH EXISTING 2+0 | XCM3E | DP | 18G | 1.2 | 1.2 | Magicell | SQ202503270787-Magicell | Magicell | SQ202502270723-Magicell // SQ202504260146-Magicell | 2025-10-08 | 2025-10-07 | Completed | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022403 |  | 2025-02-25 | 2025-02-25 | Completed | 2025-02-24 | 2025-02-25 | 2025-02-24 | 2025-02-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-28 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-28 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-27 | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-03-03 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | 2025-03-05: 2025-02-26; 2025-03-05: 2025-02-28; 2025-03-05: 2025-02-26; 2025-03-05: 2025-02-28 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
4293B | Pulau Tuba T`flow | DU00005048647 | Northern | Kedah | 6.239410 | 99.835420 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1x New CAT6 cable with suitable length | MW IDU Patching | 1.LOAD BALANCING TASK. 2.MW IDU PATCHING AT 4293B, TO RE-PATCH EXISTING IDU SM MW LINK 4293B-K00793/4164K FROM EXISTING IDU FOR HW MW LINK 4293B(RTN02)-4464A(RTN03), PORT 8-EM6-2 TO EXISTING IDU FOR HW MW LINK K00465/4163K(RTN01)-4464A(RTN11), PORT 8-EM6-2. 3.ENABLE PORT 8-EM6-2 OF K00465/4163K(RTN01) & DISABLE PORT PORT 8-EM6-2 OF 4293B(RTN02). 4.IMPACTED SITES: K00793/4164K & 4014D. | 1.LOAD BALANCING TASK. 2.MW IDU PATCHING AT 4293B, TO RE-PATCH EXISTING IDU SM MW LINK 4293B-K00793/4164K FROM EXISTING IDU FOR HW MW LINK 4293B(RTN02)-4464A(RTN03), PORT 8-EM6-2 TO EXISTING IDU FOR HW MW LINK K00465/4163K(RTN01)-4464A(RTN11), PORT 8-EM6-2. 3.ENABLE PORT 8-EM6-2 OF K00465/4163K(RTN01) & DISABLE PORT PORT 8-EM6-2 OF 4293B(RTN02). 4.IMPACTED SITES: K00793/4164K & 4014D. | [6 empty] | GCI | SQ202504280464-GCI | GCI | SQ202504260070-GCI | 2025-10-30 | 2025-10-29 | Completed | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-28 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-30 | 2025-10-29 | 2025-10-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041642 |  | 2025-04-17 | 2025-04-19 | Completed | 2025-04-16 | 2025-04-17 | 2025-04-16 | 2025-04-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-28 | 2025-05-03 | 2025-04-28 | 2025-04-28 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-04-28 | 2025-05-03 | 2025-04-28 | 2025-04-28 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-04-28 | 2025-05-03 | 2025-04-28 | 2025-05-04 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-03-05: 2025-04-28; 2025-03-05: 2025-05-03; 2025-03-05: 2025-04-28; 2025-03-05: 2025-05-06 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI
2732B-1039A | Tmn Cheras Perdana | DU00005048648 | Central | Selangor | 3.042971 | 101.769549 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 27/2/2025 : Cutover done 25/2/2025 : FE installation complete, pending install NE site due to owner deal on Thursday 09:30 24/2/2025 : Plan install NE and FE site - Cancel proceed due to keys issue 23/2/2025 : Digi OB - 3M Bipod - RT - NE site 2732B Tmn Cheras Perdana, Digi OB - 45M 4 Legged Tower - FE site 1039A Cheras Jaya 2202 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap | MW SWAP LINK SM MW1 2732B-1039A WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB A & B_2.32KM IMPACTED: 2732B, 1732H DISMANTLE EXISTING LINK NE: 1. INSTALL NEW RTN910A 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK SM FE: 1. INSTALL NEW RTN910A 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 5. DISMANTLE EXISTING LINK SM | 1. INSTALL NEW RTN910A 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK SM | 1. INSTALL NEW RTN910A 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK SM | XMC3E | DP | 18G | 0.6 | 0.6 | Magicell | SQ202503270787-Magicell | Magicell | SQ202502270723-Magicell // SQ202504260146-Magicell | 2025-04-25 | 2025-04-25 | Completed | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-25 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022118 |  | 2025-02-22 | 2025-02-22 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-02-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-02-28 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-02-28 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-27 | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-03-06 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-03-10 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358
7088Z_LOS | KgBalat | DU00005048649 | Sabah | Sabah | 5.306710 | 117.612640 |  |  |  |  | RFS | TI done | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G 4+0 2.4m/2.4m MS XMC3 sub A&B NE: 1) 1 x RTN910A 2) 1 x ISM8 cards 3) 2 x 13G XMC3 sub A Hi 4) 2 x 13G XMC3 sub B Hi 5) 1 x 13G 2.4m MS FE: 1) 1 x RTN910A 2) 1 x ISM8 cards 3) 2 x 13G XMC3 sub A Hi 4) 2 x 13G XMC3 sub B Hi 5) 1 x 13G 2.4m MS | MW New Link / Reroute | Existing MW link LOS block. Reroute to new FE NE (7088Z): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 3) Install new 4+0 link at 7-ISM8 and 3-ISM8 4) Patch existing RTN950A GE2 to new RTN GE2 5) Patch 7088Z BBU to new RTN GE1 6) Migrate traffic to new link 7) Decom old link FE (7498B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 3) Install new 4+0 link at 7-ISM8 and 3-ISM8 4) Patch new RTN GE1 to existing RTN02 GE2 5) Migrate traffic to new link. | NE (7088Z): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 3) Install new 4+0 link at 7-ISM8 and 3-ISM8 4) Patch existing RTN950A GE2 to new RTN GE2 5) Patch 7088Z BBU to new RTN GE1 6) Migrate traffic to new link 7) Decom old link | FE (7498B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 3) Install new 4+0 link at 7-ISM8 and 3-ISM8 4) Patch new RTN GE1 to existing RTN02 GE2 5) Migrate traffic to new link. | XMC3 | MS DP | 13GHz | 2.4m | 2.4m | NR services | SQ202502260432-NR Services | NR services | SQ202504210220-NR Services // SQ202504210225-NR Services // SQ202504260199-NR Services | 2025-07-11 | 2025-07-10 | Completed | 2025-02-19 | 2025-02-24 | 2025-02-21 | 2025-02-21 | MUHD//KHAIRUL NIZAM/7023000104 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-10 | 2025-07-11 | 2025-07-10 | 2025-07-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031647 |  | 2025-03-17 | 2025-03-24 | Completed | 2025-03-16 | 2025-03-17 | 2025-03-16 | 2025-03-24 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-10 | 2025-04-30 | 2025-04-10 | 2025-04-12 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-04-10 | 2025-04-30 | 2025-04-10 | 2025-04-14 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-18 | 2025-04-10 | 2025-04-30 | 2025-04-10 | 2025-04-25 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-03-05: 2025-04-10; 2025-03-05: 2025-04-30; 2025-03-05: 2025-04-10; 2025-03-05: 2025-04-11 |  |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016
7095Z-7756B | Tampasak | DU00005048650 | Sabah | Sabah | 5.287740 | 116.894430 |  |  |  |  | Drop/Cancel | Cancel/Drop | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Performance issue | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9195R-9162A | Kg. Giam Baru | DU00005048651 | Sarawak | Sarawak | 1.313872 | 110.273298 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1xISM8 card 1x18G XMC3E Sub A Hi 1x18G XMC3E Sub A Lo | MW Hardware Upgrade | Existing MW link Huawei 9195R-9162A-01_ZBAU 1) To upgrade capacity from 450Mbps to 889Mbps 2) To upgrade ODU from XMC3 to XMC3E for high Tx power 3) To install new ISM8 card at 9162A RTN01 slot 3 to avoid IDU-IDU bottleneck 4) To transfer 9162A BBU from RTN02 to RTN01 NE (9195R): 1) Replace ODU to XMC3E 2) Upgrade link to 112MHz FE (9162A): 1) Add ISM8 card at RTN01 slot 3 2) Transfer existing link to RTN01 3-ISM8-1 3) Replace ODU to XMC3E 4) Upgrade link to 112MHz 5) Transfer 9162A BBU from existing RTN02 GE2 to RTN01 GE2 6) Dismantle 9162A RTN02 | NE (9195R): 1) Replace ODU to XMC3E 2) Upgrade link to 112MHz | FE (9162A): 1) Add ISM8 card at RTN01 slot 3 2) Transfer existing link to RTN01 3-ISM8-1 3) Replace ODU to XMC3E 4) Upgrade link to 112MHz 5) Transfer 9162A BBU from existing RTN02 GE2 to RTN01 GE2 6) Dismantle 9162A RTN02 | XMC3E |  | 18G |  |  | Trintel | SQ202503060206-Trintel | Trintel | SQ202502270771-Trintel // SQ202504260214-Trintel | 2025-03-07 | 2025-03-03 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-02-27 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-03 | 2025-03-07 | 2025-03-03 | 2025-03-03 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-03 | 2025-03-07 | 2025-03-03 | 2025-03-03 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-03 | 2025-03-07 | 2025-03-03 | 2025-03-03 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021833 |  | 2025-02-19 | 2025-02-24 | Completed | 2025-02-18 | 2025-02-19 | 2025-02-18 | 2025-02-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2025-03-25 | 2025-02-27 | 2025-02-27 | ALVIN TAY KAI SENG7667000030 | Trintel TI | 2025-02-25 | 2025-03-25 | 2025-02-26 | 2025-02-27 | ALVIN TAY KAI SENG7667000030 | Trintel TI | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-02-26 | 2025-02-25 | 2025-03-25 | 2025-07-21 | 2025-07-21 | ALVIN TAY KAI SENG7667000030 | 2025-02-25 | 2025-03-25 | 2025-03-10 | 2025-03-10 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-04 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
4657A_LOS | Spg 4 Kangkong | DU00004679173 | Northern | Kedah | 6.024641 | 100.383913 | [7 empty] | 00. Integrated/RFS Done | 17/12: Fine tune & RSL rectification at FE site. Cutover done, RSL normalized 16/12: Urgent to raised up antenna level for better RSL | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NA | MW Swap | At 4973B . raise up the antenna height in order to get the LOS is clear. link config 3+0 ( 13G_1+0_28M & 15G_2+0_28M with EPLA). Antenna location to raise up for 13G_1+0_28M only. | [7 empty] | GCI | SQ202412180522-GCI | GCI | SQ202412180551-GCI // SQ202504150095-GCI |  |  | Ongoing | 2024-12-18 | 2024-12-18 | 2024-12-18 | 2024-12-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2024-12-31 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24121822 |  | 2024-12-19 | 2025-02-19 | Completed | 2024-12-18 | 2024-12-19 | 2024-12-18 | 2025-02-19 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-17 | 2024-12-31 | 2024-12-17 | 2024-12-22 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-12-17 | 2024-12-31 | 2024-12-17 | 2024-12-22 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-12-18 | 2024-12-18 | 2024-12-18 | 2024-12-18 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-12-17 | 2024-12-31 | 2024-12-17 | 2024-12-30 | SAFUAN//BIN YUSOFF/6800000178 | 2025-03-05: 2024-12-17; 2025-03-05: 2024-12-31; 2025-03-05: 2024-12-17; 2025-03-05: 2024-12-18 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300164-GCI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | CHEONG/SENG/WAH/7018000306
W01361_LOS | W066U_W01361OD_MIDVALLEYNORTH_JLNSYEDPUTRA | DU00004713669 | Central | Kuala Lumpur | 3.120292 | 101.676936 |  | DEC 24 |  | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 20/12/2024 : Cutover done 19/12/2024 : Plan enter site at night | TSS+TI+Dismantle | L1+ATP+PAC | IF Cable due to changed ant location to another Tower leg | MW Swap | Decom existing antenna , relocate the antenna location at different tower leg | Decom existing antenna , relocate the antenna location at different tower leg | [6 empty] | Magicell | SQ202412190502-Magicell | Magicell | SQ202412190331-Magicell // SQ202504260146-Magicell | 2025-05-20 | 2025-05-19 | Completed | 2025-02-25 | 2025-05-05 | 2025-05-05 | 2025-05-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-07 | 2025-05-08 | 2025-05-07 | 2025-05-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-19 | 2025-05-20 | 2025-05-19 | 2025-05-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020748 |  | 2025-02-08 | 2025-02-10 | Completed | 2025-02-07 | 2025-02-08 | 2025-02-07 | 2025-02-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-19 | 2025-12-01 | 2024-12-19 | 2025-02-03 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 |  | 2024-12-19 | 2025-12-01 | 2024-12-19 | 2025-02-27 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2024-12-20 | 2024-12-19 | 2025-12-01 | 2024-12-19 | 2025-01-03 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | 2025-03-05: 2024-12-19; 2025-03-05: 2025-12-01; 2025-03-05: 2024-12-19; 2025-03-05: 2024-12-20 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | CHEONG/SENG/WAH/7018000306
1225B_LOS | Surau Al-Hikmah | DU00004807607 | Central | Selangor | 3.181631 | 101.545492 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 22/1/2025 : Decom and L1 done 20/1/2025 : Cutover done 6/1/2025 : SBC KJS - 20M Lampole - NE site 1225B Surau Al-Hikmah, UMOBILE - 45M Monopole - FE site 1182B PUAS Sg Buloh (Umobile) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_1225B 18G_DP_0.6(MDD) x1. RTN910A x1. XMC_5D , Sub_A_Lo x1. FE_1182B 18G_DP_0.6(MDD) x1. RTN910A x1. XMC_5D , Sub_A_Hi x1. ETH cable x1. | MW New Link / Reroute | Link reroute to new FE 1182B due to LOS Block with config 18G_2+0_112M Site Impacted : 1225B , 1776H. NE_1225B 1.Install new 18G_DP_0.6(MDD) 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub_A_Lo. 4.Create service cross connect and enable EPLA. 5.Enable GE1 & GE2 , migrate traffic BBU_1225B to GE1 and Migrate traffic RTN510_02 to GE2 into new RTN910A. 6.Decom existing MW link 1225B_RTN01 to 1364B_RTN05. 7.Ensure traffic migration successful before decom existing MW equipment. FE_1182B 1.Install new 18G_DP_0.6(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub_A_Hi. 4.Create service cross connect and enable EPLA. 5.Enable GE1 , ETH cable patching to existing 1182B_RTN01 (GE2).Enable new In-band DCN. 6. Traffic 1225B and 1776H migrate to new FE route. 7.Decom existing MW link 1364B_RTN05 to 1225B_RTN01. 8.Ensure traffic migration successful before decom existing MW equipment. | Link reroute to new FE 1182B due to LOS Block with config 18G_2+0_112M Site Impacted : 1225B , 1776H. NE_1225B 1.Install new 18G_DP_0.6(MDD) 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub_A_Lo. 4.Create service cross connect and enable EPLA. 5.Enable GE1 & GE2 , migrate traffic BBU_1225B to GE1 and Migrate traffic RTN510_02 to GE2 into new RTN910A. 6.Decom existing MW link 1225B_RTN01 to 1364B_RTN05. 7.Ensure traffic migration successful before decom existing MW equipment. | Link reroute to new FE 1182B due to LOS Block with config 18G_2+0_112M Site Impacted : 1225B , 1776H. FE_1182B 1.Install new 18G_DP_0.6(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub_A_Hi. 4.Create service cross connect and enable EPLA. 5.Enable GE1 , ETH cable patching to existing 1182B_RTN01 (GE2).Enable new In-band DCN. 6. Traffic 1225B and 1776H migrate to new FE route. 7.Decom existing MW link 1364B_RTN05 to 1225B_RTN01. 8.Ensure traffic migration successful before decom existing MW equipment. | XMC_5D | MDD | 17810.000 18140.000 | 0.6M | 0.6M | GTSB | SQ202501140152-GTSB | GTSB | SQ202501030381-GTSB // SQ202504260131-GTSB | 2025-03-05 | 2025-02-10 | Completed | 2025-02-05 | 2025-03-05 | 2025-02-05 | 2025-02-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-05 | 2025-03-05 | 2025-02-05 | 2025-02-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-04 | 2025-02-05 | 2025-02-04 | 2025-02-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-07 | 2025-02-08 | 2025-02-07 | 2025-02-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250103AO |  | 2025-01-04 | 2025-02-27 | Completed | 2025-01-03 | 2025-01-04 | 2025-01-03 | 2025-02-27 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-19 | 2025-01-31 | 2025-01-19 | 2025-02-27 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-01-19 | 2025-01-31 | 2025-01-19 | 2025-02-27 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-01-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-20 | 2025-01-19 | 2025-01-31 | 2025-01-19 | 2025-01-22 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-01-19 | 2025-01-31 | 2025-01-19 | 2025-01-20 | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
4169H_LOS | 99 Speedmart PK BERCHAM | DU00004807608 | Northern | Perak | 4.632595 | 101.130251 | [7 empty] | 03. TSS Only |  | TSS |  | Proposed Fiber due to No LOS is available Found during actual TSS LOS survey. | MW New Link / Reroute | Proposed Fiber due to No LOS is available Found during actual TSS LOS survey. | [7 empty] | GCI | SQ202502180252-GCI | GCI | No PR required-Work at TSS only | 2026-03-14 | 2026-03-13 | Completed | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-12 | 2025-02-13 | 2025-02-12 | 2025-02-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010368 |  | 2025-01-04 |  | Ongoing | 2025-01-03 | 2025-01-04 | 2025-01-03 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2025-01-13 | 2025-01-31 | 2025-01-13 |  | team21gcitechnicalteam21gcitechnical | GCI TI | 2025-01-13 | 2025-01-31 | 2025-01-13 |  | team21gcitechnicalteam21gcitechnical | GCI TI | [7 empty] | 2025-01-13 | 2025-01-31 | 2025-01-13 |  | team21gcitechnicalteam21gcitechnical | 2025-03-05: 2025-01-13; 2025-03-05: 2025-01-31; 2025-03-05: 2025-01-13; 2025-03-05: 2025-01-13 | [7 empty] | GCI | SQ202505070152-GCI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | CHEONG/SENG/WAH/7018000306
1635H_LOS | 99 Speedmart KOTA WARISAN 1 | DU00004807609 | Central | Selangor | 2.824631 | 101.705908 | WK06 | FEB 25 | WK06 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 7/2/2025 : Cutover done 6/2/2025 : Cutover WIP 5/2/2025 : Plan install NE and FE site - MOS activity only 6/1/2025 : Digi OB - Small Cell - NE site 1635H 99 Speedmart KOTA WARISAN 1, EDOTCO (M) - 3M Boom - RT - FE site 3043C Warisan Megah | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | new NLOS equipment. NE_1635H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave. Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual. polarization/Separate Mount with bracket x1. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. FE_3043C 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. 6. ETH cable x1 | MW New Link / Reroute | Link reroute to new FE 3043C due to LOS block with config new NLOS equipment. Site Impacted : 1635H. NE_1635H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave. Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual. polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. 6. Traffic migrate to new FE with NLOS new equipment via existing MW link (1635H-NLOS-3043C-1489A-2549A). 7. Decom existing NLOS (1635H-NLOS-1489A), Ensure traffic migrate successful before proceed decom existing equipment. FE_3043C 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. 6. Traffic migrate to new FE with NLOS new equipment via existing MW link (1635H-NLOS-3043C-1489A-2549A) 7. ETH cable patching to existing 3043C_RTN01 (GE2). 8. Decom existing NLOS (1489A-NLOS-1635H) , Ensure traffic migrate successful before proceed decom existing equipment. | [7 empty] | Magicell | SQ202501140157-Magicell | Magicell | SQ202501030382-Magicell // SQ202504260146-Magicell | 2025-11-19 | 2025-11-12 | Completed | 2025-01-07 | 2025-01-07 | 2025-01-07 | 2025-01-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-19 | 2025-11-12 | 2025-11-12 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250103AE |  | 2025-01-04 | 2025-02-07 | Completed | 2025-01-03 | 2025-01-04 | 2025-01-03 | 2025-02-07 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-04 | 2025-02-28 | 2025-02-07 | 2025-02-07 | MUHAMMAD//HAZMAN BIN HASSAN/7018000218 | Magicell TI | 2025-02-04 | 2025-02-28 | 2025-02-04 | 2025-02-07 | MUHAMMAD//HAZMAN BIN HASSAN/7018000218 | Magicell TI | 2025-02-06 | 2025-02-06 | 2025-02-06 | 2025-02-06 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-06 | 2025-02-04 | 2025-02-28 | 2025-02-28 | 2025-04-12 | MUHAMMAD//HAZMAN BIN HASSAN/7018000218 | 2025-02-04 | 2025-02-28 | 2025-02-05 | 2025-02-05 | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300116-GTSB
7242A_LOS | Kolombong | DU00004807610 | Sabah | Sabah | 5.968090 | 116.107490 |  |  |  |  | Pending Access | Pending FE access(TA issue) | Digi | 00. Integrated/RFS Done | Pending FE access(TA issue) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_7242A 18G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. FE_7032A 18G_DP_0.6m(MAC)+OMT x1. 2.Install new RTN910A x1 XMC_3E , Sub A & B_Hi x2. | MW New Link / Reroute | Link reroute to new FE 7032A due to LOS block with config 18G_2+0_112M Site Impacted : 7242A NE_7242A 1.Install new 18G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA for 2+0. 5.Migrate traffic 7242A to new FE route. 6.Decom existing MW IDU , ODU and Ant (7242A_RTN01-7000A).Ensure traffic successful migrate before decom. FE_7032A 1.Install new 18G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA for 2+0. 5.Migrate traffic to new FE. 6.Enable new In-Band DCN. 7.Decom existing ODU and Ant (7000A_RTN01-7242A).Ensure traffic successful migrate before decom. | Link reroute to new FE 7032A due to LOS block with config 18G_2+0_112M Site Impacted : 7242A NE_7242A 1.Install new 18G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA for 2+0. 5.Migrate traffic 7242A to new FE route. 6.Decom existing MW IDU , ODU and Ant (7242A_RTN01-7000A).Ensure traffic successful migrate before decom. | Link reroute to new FE 7032A due to LOS block with config 18G_2+0_112M Site Impacted : 7242A FE_7032A 1.Install new 18G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA for 2+0. 5.Migrate traffic to new FE. 6.Enable new In-Band DCN. 7.Decom existing ODU and Ant (7000A_RTN01-7242A).Ensure traffic successful migrate before decom. | XMC_3E | MAC | 18G | 0.6 | 0.6 | NR services | SQ202502050337-NR Services | NR services | SQ202507190102-NR Services // SQ202507190103-NR Services | 2025-07-11 | 2025-07-07 | Completed | 2025-02-01 | 2025-02-01 | 2025-02-01 | 2025-02-09 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022858 |  | 2025-03-01 | 2025-03-03 | Completed | 2025-02-28 | 2025-03-01 | 2025-02-28 | 2025-03-03 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-03 | 2025-03-31 | 2025-03-03 | 2025-08-14 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-03-03 | 2025-03-31 | 2025-03-03 | 2025-08-21 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-13 | 2025-03-03 | 2025-03-31 | 2025-03-03 | 2025-08-23 | RALPH O'BRYAN HILARY7167000030 | 2025-03-03 | 2025-03-31 | 2025-03-03 | 2025-03-04 | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-10-21 | tseping//wang/6819000006 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507080638-GTSB | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | HSU//MYET CHAE/6799000011
7733B_LOS | Ladang Tas | DU00004807611 | Sabah | Sabah | 5.244283 | 118.276176 |  |  |  |  | RFS | TI done |  | 00. Integrated/RFS Done | MwAntenna HW-13G_1.2M_Dual Polarization_A13D12MDD-3NX | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M. NE_7733B 13G_DP_1.2m(MDD) x1. XMC_5D , Sub_A_Lo x1. RTN910A x1. ISM8 x2. FE_7487B 13G_DP_1.8m(MDD) x1. XMC_5D , Sub_A_Hi x1. RTN910A x1 ISM8 x2. | MW New Link / Reroute | Link reroute to new FE 7487B due to LOS block with config 13G_4+28M. Site Impacted : 7733B , 7095A , 7487B. NE_7733B 1.Install new 13G_DP_1.2m(MDD) 2.Install new XMC_5D , Sub_A_Lo. 3.Install new RTN910A. (RTN no provide by MSP team). 4.Install 3_ISM8-2+0 and 4_ISM8-2+0 config CA. 5.Create service cross connect , EPLA and CA configuration. 6.Enable GE 1 & GE2. 7.Migrate traffic BBU_7733B to GE1 and 7733B_RTN02 to GE2 for reroute to new FE. 8.Decom existing MW link (7733B_RTN01 to 7501A_RTN02). Ensure traffic migration successful before decom. FE_7487B 1.Install new 13G_DP_1.8m(MDD). 2.Install new XMC_5D , Sub_A_Hi. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install 3_ISM8-2+0 and 4_ISM8-2+0 config CA. 5.Create service cross connect , EPLA and CA. 6.Enable GE1 , ETH patching to existing 7487B_RTN02 (GE2). 7.Migrate traffic for 7733B & 7095A to new FE via Existing MW link.(7733B-7487B-7494B-7581A). 8.Decom existing MW link (7501A_RTN02 to 7733B_RTN01). Ensure traffic migration successful before decom. | [7 empty] | NR services | SQ202502260432-NR Services | NR services | SQ202504230258-NR Services // SQ202504230262-NR Services // SQ202504260199-NR Services | 2025-07-11 | 2025-07-07 | Completed | 2025-02-19 | 2025-02-24 | 2025-02-20 | 2025-02-20 | MUHD//KHAIRUL NIZAM/7023000104 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031648 |  | 2025-03-17 | 2025-04-15 | Completed | 2025-03-16 | 2025-03-17 | 2025-03-16 | 2025-04-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-21 | 2025-05-10 | 2025-04-21 | 2025-04-24 | WILFRED BALANG7167000026 | NR Service TI | 2025-04-21 | 2025-05-10 | 2025-04-21 | 2025-04-24 | WILFRED BALANG7167000026 | NR Service TI | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-22 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-04-21 | 2025-05-10 | 2025-04-21 | 2025-05-01 | WILFRED BALANG7167000026 | 2025-04-21 | 2025-05-10 | 2025-04-21 | 2025-04-22 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GCI_AA | SQ202510300170-GCI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | CHEONG/SENG/WAH/7018000306
Q01838_EB_1 | UOB KUCHING | DU00005521168 | Sarawak | Sarawak | 1.551458 | 110.372030 | [6 empty] | ZTE | 03. Pending TSS |  | TSS+AA+TI+Dismantle |  | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO | MW Swap | MW SWAP UPGRADE Q01838-9454A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB_A_0.41KM IMPACTED: Q01838 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING | XMC3E | MAC | 23G | 0.6 | 0.6 | Iezzpro | SQ202509090306-Iezzpro | Iezzpro | SQ202509090333-Iezzpro // SQ202509090359-Iezzpro |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505190538-GCI | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | EZRIN TASNIM BIN ABDUL GANI6798000128
2435A_HU | Batu Arang Junction (KJS) | DU00005523612 | Central | Selangor | 3.338015 | 101.479405 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 4X ISM8 CARD 2X RTN910 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1X ODU 15G XMC5D SUB B LO | MW Parallel Link | MWPARALLEL LINK 2435A-1423A WITH HUAWEI_15G_4+0_1.2M/1.2M_DP MDD_28MHZ_256QAM_800MBPS_XMC3_SUB_B_6.2KM PATCH FE 1423A TO TM LL XC B00666 IMPACTED: 2435A NEW LINK BRING BBU 2435A | 1. INSTALL NEW RTN910 AND 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M DP MDD ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA 5. PATCH BBU 2435A TO NEW LINK IDU | 1. INSTALL NEW RTN910 AND 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M DP MDD ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA 5. PATCH IDU TO XC B00666 TM LL | 5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202505240068-Magicell | Magicell | SQ202507190091-Magicell // SQ202507190092-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-12 | 2025-08-13 | 2025-08-12 | 2025-08-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061808 |  | 2025-06-19 | 2025-06-20 | Completed | 2025-06-18 | 2025-06-19 | 2025-06-18 | 2025-06-20 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-25 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-31 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-26 | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-31 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-03-05: 2025-07-17; 2025-03-05: 2025-07-17; 2025-03-05: 2025-07-17; 2025-03-05: 2025-07-26 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202505190510-GCI | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | EZRIN TASNIM BIN ABDUL GANI6798000128
4425A_HU_1 | Changkat Lobak RDD | DU00005565101 | Northern | Perak | 5.131190 | 100.627210 | [7 empty] | 00. Integrated/RFS Done | 26/05: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X RTN910A | MW Hardware Upgrade | MW Hardware Upgrade - at NE Site 4425A HW MW IDU 4425A-RTN02 Transfer MW Link to 4538D from 3-ISM8-1 4452A-RTN02 to New 7-ISM8-1 4452A-RTN03 NE 4452A-RTN02 1. Install New RTN910A Naming as RTN03 2. Transfer MW Link to 4538D from 3-ISM8-1 4452A-RTN02 to New 7-ISM8-1 4452A-RTN03 3. Configure the Transfering Link at the New 4425A-RTN03 4. Create Service 4538D at 4425A-RTN03 & Patch New Cable to New PTN Port xC A00064 - 4425A-RTN03 will be carry Traffic 4538D 5. Reconfigure Service 4146R at 4452A-RTN02 & Patch Existing Cable to Existing PTN Port xC A00064 - 4425A-RTN02 will be carry Traffic 4146R 6. Decom existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) - Current BBU already Patch to xC - No Traffic on Current Link FE 4773A 1. Decom existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) - Current BBU already Patch to xC - No Traffic on Current Link | MW Hardware Upgrade - at NE Site 4425A HW MW IDU 4425A-RTN02 Transfer MW Link to 4538D from 3-ISM8-1 4452A-RTN02 to New 7-ISM8-1 4452A-RTN03 NE 4452A-RTN02 1. Install New RTN910A Naming as RTN03 2. Transfer MW Link to 4538D from 3-ISM8-1 4452A-RTN02 to New 7-ISM8-1 4452A-RTN03 3. Configure the Transfering Link at the New 4425A-RTN03 4. Create Service 4538D at 4425A-RTN03 & Patch New Cable to New PTN Port xC A00064 - 4425A-RTN03 will be carry Traffic 4538D 5. Reconfigure Service 4146R at 4452A-RTN02 & Patch Existing Cable to Existing PTN Port xC A00064 - 4425A-RTN02 will be carry Traffic 4146R 6. Decom existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) - Current BBU already Patch to xC - No Traffic on Current Link | FE 4773A 1. Decom existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) - Current BBU already Patch to xC - No Traffic on Current Link | XMC3 |  | 18G | 0.6 | 0.6 | NWAVE | SQ202507160641-N-Wave | NWAVE | SQ202506260767-N-Wave // SQ202506260771-N-Wave // SQ202603170679-N-Wave // SQ202603170684-N-Wave | 2026-03-13 | 2026-03-12 | Completed | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061164 |  | 2025-06-12 | 2025-06-13 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | Khairul Azman Bin Din7160000001 |  | 2025-06-26 | 2025-06-30 | 2025-06-26 | 2025-07-21 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-06-26 | 2025-06-30 | 2025-06-26 | 2026-03-05 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2025-06-26 | 2025-06-30 | 2025-06-26 | 2025-06-26 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506050639-GCI | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
2772A-1084A | Jln Sg Keramat | DU00003341260 | Central | Selangor | 3.085230 | 101.408130 | WK11 | MAR 24 | WK13 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 26/3: Cutover done | TSS+AA+TI | L1+ATP+PAC | 23G 0.6m/0.6m DP 2+0 56Mhz | MW Parallel Link | DCN VLAN : 415, PORT NUMBER : GigabitEthernet0/2/26 NE 1- Install Huawei IDU 910A. 2- Install Huawei 2+0 ODU. 3- Install Huawei 0.6m Antenna DP. 4- Configure link 2+0_900M_512QAM. 5- Transfer node B 2772A to new MW Link FE 1- Install Huawei IDU 910A. 2- Install Huawei 2+0 ODU. 3- Install Huawei 0.6m Antenna DP. 4- Configure link 2+0_900M_512QAM. 5- Configure new DCN VLAN for monitoring. | [7 empty] | Nera | SQ202404020442-Nera | Nera | SQ202404020447-Nera | 2024-05-24 | 2024-05-23 | Completed | 2024-03-04 | 2024-03-08 | 2024-03-25 | 2024-03-26 | NUR//AFIQAH BINTI MOHD ROSDI/7670000015 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-30 | 2024-03-31 | 2024-03-30 | 2024-03-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-03 | 2024-04-04 | 2024-04-03 | 2024-04-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-05-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24022218 |  | 2024-03-16 | 2024-03-16 | Completed | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | NUR//AFIQAH BINTI MOHD ROSDI/7670000015 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-25 | 2024-03-31 | 2024-03-25 | 2024-03-25 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | 2024-03-25 | 2024-06-30 | 2024-03-25 | 2024-04-01 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | 2024-04-02 | 2024-04-04 | 2024-04-08 | 2024-04-08 | C.PRATHABAN///6798000081 |  |  | 2024-03-25 | 2024-03-31 | 2024-03-25 | 2024-04-05 | AZIZAH//BINTI A.RAHMAN/7670000012 | 2025-03-05: 2024-03-25; 2025-03-05: 2024-03-31; 2025-03-05: 2024-03-25; 2025-03-05: 2024-03-26 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
1937B-1349A | Kemuning Jln Tamborin (KJS) | DU00003341261 | Central | Selangor | 3.021154 | 101.544380 | WK10 | MAR 24 | WK10 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | D2: Cutover done | TSS+AA+TI | L1+ATP+PAC | 18G 0.6m/0.6m 2+0 DP 56Mhz | MW Swap | NE 1- Install 1x ISM8 Card at existing IDU 910A RTN01 at slot 3. Dismantle SM IDU AGS20 after installation. 2- Swap SM 1+0 ODU with Huawei 2+0 ODU. 3- Swap SM Antenna with new Huawei 0.6m Antenna MDD. 4- Configure link 2+0_800M_512QAM. FE 1- Swap SM IDU AGS20 with Huawei IDU 910A 2- Swap SM 1+0 ODU with Huawei 1+0 ODU. 3- Swap SM Antenna with new Huawei 0.6m Antenna MDD. 4- Configure link 2+0_800M_512QAM | [7 empty] | Allstar | SQ202403120253-Allstar | Allstar | SQ202402190097-Allstar // SQ202510070055-Allstar | 2024-05-03 | 2024-05-06 | Completed | 2024-02-26 | 2024-03-01 | 2024-03-01 | 2024-03-01 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-05 | 2024-03-05 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-30 | 2024-05-03 | 2024-04-30 | 2024-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021012 |  | 2024-02-12 | 2024-02-15 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-02-15 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-07 | 2024-03-31 | 2024-03-07 | 2024-05-08 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | Allstar TI | 2024-03-07 | 2024-06-30 | 2024-03-07 | 2024-03-22 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | Allstar TI | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-08 | 2024-03-31 | 2024-03-07 | 2024-04-22 | MUHAMMAD//AMIRUL FAIZ BIN RUZAIDI/6798000189 | 2025-03-05: 2024-03-08; 2025-03-05: 2024-03-31; 2025-03-05: 2024-03-07; 2025-03-05: 2024-06-20 |  |  | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
1887A-1253A | The Intermark Basement | DU00003341262 | Central | Kuala Lumpur | 3.161845 | 101.720012 |  | MAR 24 | WK32-WK35 | AUG 24 | Closed | Under NIC Project | ZTE | 00. Integrated/RFS Done | 3/8: SOW done under 1887A_Additional 15/5: CD update pending PRPO issue 8/4: Site co-located with 2909B. 1887A recorded as dismantle NE structure unsave for 1.2m antenna. Escalated to CD for rectification. NE need BM WP for cabling inside riser. | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_0.6m/1.2m_2+0_28Mhz | MW Swap | NE 1- Existing IDU 910A. Install 1x ISM8 Modem. 2- Swap SM 1+0 ODU with Huawei 2+0 ODU. 3- Swap SM Antenna with new Huawei 0.6m Antenna MDD. 4- Configure link 2+0_400M_512QAM with EPLA. 5- Dismantle SM IDU after installation. FE 1- New IDU 910A. 2- Swap SM 1+0 ODU with Huawei 2+0 ODU. 3- Swap SM Antenna with new Huawei 1.2m Antenna MDD. 4- Configure link 2+0_400M_512QAM with EPLA. 5- Reuse existing port at PTN. Required DCN VLAN. 6- Impact sites 1887A, 2909B, 3617A. | [7 empty] | Allstar | SQ202403180278-Allstar | Allstar | SQ202402190097-Allstar | 2024-04-30 | 2024-04-29 | Completed | 2024-03-01 | 2024-03-31 | 2024-03-12 | 2024-03-14 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-04-01 | 2024-04-30 | 2024-04-04 | 2024-04-04 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-04-17 | 2024-04-18 | 2024-04-17 | 2024-04-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2024-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020117 |  | 2024-02-02 | 2024-02-03 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-09-24 | ALI//HAMZA/6798000192 | Allstar TI | 2024-03-14 | 2024-09-30 | 2024-03-14 | 2024-11-19 | ALI//HAMZA/6798000192 | Allstar TI | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-08-15 | C.PRATHABAN///6798000081 |  |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-11-15 | ALI//HAMZA/6798000192 | 2025-03-05: 2024-03-14; 2025-03-05: 2024-03-31; 2025-03-05: 2024-03-14; 2025-03-05: 2024-03-14 |  |  | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
2982A-1361A | Kampung Subang | DU00005085639 | Central | Selangor | 3.159730 | 101.523940 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE LINK 2982A-1361A WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_1.44KM DISMANTLE EXISTING LINK 2982A-1412A IMPACTED: 2982A, 2364A | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. CASCADE EXISTING IDU 2982A RTN02 (CARRY 2364A) TO NEW IDU 6. PATCH BBU 2982A TO NEW IDU 7. DISMANTLE EXISTING LINK 2982A-1412A | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 7. DISMANTLE EXISTING LINK 2982A-1412A | XMC3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202505090486-GCI | GCI | SQ202505090491-GCI // SQ202505090501-GCI // SQ202506040497-GCI // SQ202506160499-GCI | 2025-07-02 | 2025-07-01 | Completed | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-04 | 2025-06-05 | 2025-06-04 | 2025-06-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051359 |  | 2025-05-14 | 2025-05-16 | Completed | 2025-05-13 | 2025-05-14 | 2025-05-13 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-21 | 2025-05-28 | 2025-05-20 | 2025-05-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-05-21 | 2025-05-28 | 2025-05-20 | 2025-05-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-23 | 2025-05-21 | 2025-05-28 | 2025-05-20 | 2025-05-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-05-21 | 2025-05-28 | 2025-05-20 | 2025-05-21 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505020429-GCI | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
1469H_LOS_1 | 99 Speedmart TELOK PANGLIMA GARANG 1 | DU00005085640 | Central | Selangor | 2.908612 | 101.466945 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 24/2/2025 : FE installation complete, pending install NE site 15/1/2025 : Cancel proceed due to TM PTW expired 6/1/2025 : Digi OB - Small Cell - NE site 1469H 99 Speedmart TELOK PANGLIMA GARANG 1, TELEKOM (M) - Tower - FE site 2719A TPG industry 8/11: Allstar drop TI work. To change subcon 30/8: Pending BoQ, TX SoW Details | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | Link reroute to new FE 3294C due to LOS block from previous FE. NE_1469H Nlos-OptiX RTN /PI-DC B10 /Power injector x1. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1 FE_3294C Nlos-OptiX RTN /PI-DC B10 /Power injector x1. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1 | MW New Link / Reroute | Link reroute to new FE 3294C due to LOS block from previous FE. NE_1469H 1.Install new NLOS equipment (Indoor & Outdoor). 2.Capture existing radio config and parameters. 3.Perform alignment direct towards new FE 3294C 4.Create service cross connect and migrate service to new NLOS link. FE_3294C 1.Install new NLOS equipment (Indoor & Outdoor). 2.Capture existing parameters before redeploying. 3.Alignment direct towards opposite site 1469H. 4.Patch ETH cable to existing IDU 5.Create new In-band DCN via new route. 6.Traffic migrate to new route via existing Link | [7 empty] | Magicell | SQ202503190673-Magicell | Magicell | SQ202502270723-Magicell // SQ202504260146-Magicell |  |  | Ongoing | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25040925 |  | 2025-04-10 | 2025-04-10 | Completed | 2025-04-09 | 2025-04-10 | 2025-04-09 | 2025-04-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-04-10 | MUHAMAD//SYAZWAN BIN KHIRRUL ANUAR/7018000168 | Magicell TI | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-04-18 | MUHAMAD//SYAZWAN BIN KHIRRUL ANUAR/7018000168 | Magicell TI | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-25 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-25 | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-03-13 | MUHAMAD//SYAZWAN BIN KHIRRUL ANUAR/7018000168 | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-03-10 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300116-GTSB
3354A-4770A_1 | pBTS SP Heights | DU00005132319 | Northern | Kedah | 5.630889 | 100.545155 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | link 23G_2+0_112M NE_3354A 23G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. FE_4479A. 23G_DP_1.2M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Hi x2. | MW Parallel Link | Existing link 23G_1+0_112M Install parallel link 23G_2+0_112M Site Impacted : 3354A. NE_3354A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 3354A_RTN01. 3.Install new 3_ISM8-2+0 into existing 3354A_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create cross connect and EPLA with new 23G_2+0 and existing 23G_1+0 link. 6.No decom existing MW link. FE_4479A. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4479A_RTN 14. 3.Install new 3_ISM8-2+0 into existing 4479A_RTN 14. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create cross connect and EPLA with new 23G_2+0 and eixsting 23G_1+0 link. 6.No decom existing MW link. | Existing link 23G_1+0_112M Install parallel link 23G_2+0_112M Site Impacted : 3354A. NE_3354A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 3354A_RTN01. 3.Install new 3_ISM8-2+0 into existing 3354A_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create cross connect and EPLA with new 23G_2+0 and existing 23G_1+0 link. 6.No decom existing MW link. | Existing link 23G_1+0_112M Install parallel link 23G_2+0_112M Site Impacted : 3354A. FE_4479A. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4479A_RTN 14. 3.Install new 3_ISM8-2+0 into existing 4479A_RTN 14. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create cross connect and EPLA with new 23G_2+0 and eixsting 23G_1+0 link. 6.No decom existing MW link. | XMC_3E | MAC | 23G | 0.6 | 1.2 | CCSMY | SQ202504170473-CCS | CCSMY | SQ202504210107-CCS // SQ202504210102-CCS // SQ202504260175-CCS | 2026-01-23 | 2026-01-23 | Completed | 2025-03-21 | 2025-04-21 | 2025-03-21 | 2025-03-21 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032111 |  | 2025-03-22 | 2025-03-22 | Completed | 2025-03-21 | 2025-03-22 | 2025-03-21 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-07 | 2025-04-30 | 2025-04-07 | 2025-04-18 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2025-04-07 | 2025-04-30 | 2025-04-07 | 2025-04-18 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-18 | 2025-04-07 | 2025-04-30 | 2025-04-07 | 2025-04-24 | MUHAMMAD//MUZAMMAL/7021000054 | 2025-03-05: 2025-04-07; 2025-03-05: 2025-04-30; 2025-03-05: 2025-04-07; 2025-03-05: 2025-04-07 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | CHEONG/SENG/WAH/7018000306
3104H_LOS_1 | 99 Speedmart NS Broga | DU00005132320 | Central | Sembilan | 2.935750 | 101.911290 | WK10 | MAR 25 | WK10 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 8/3/2025 : Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Install new NLOS NE_3104H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. FE_3064C_22 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Link reroute to new FE 3064C_22 due to LOS block with new NLOS equipment. Site Impacted : 3104H NE_3104H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. 6. Traffic migrate to new FE route with new NLOS equipment. FE_3064C_22 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. Traffic migrate to new FE with new NLOS equipment. 7. ETH cable patching to Fiber port from NLOS equipment. 8. Create New In-Band DCN. | [7 empty] | Magicell | SQ202503190673-Magicell | Magicell | SQ202503200170-Magicell // SQ202503200172-Magicell // SQ202504260146-Magicell |  |  | Ongoing | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25030518 |  | 2025-03-06 | 2025-03-27 | Completed | 2025-03-05 | 2025-03-06 | 2025-03-05 | 2025-03-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-08 | 2025-03-31 | 2025-03-27 | 2025-03-27 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-03-08 | 2025-03-31 | 2025-03-27 | 2025-03-27 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-03-08 | 2025-03-08 | 2025-03-08 | 2025-03-08 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-03-08 | 2025-03-31 | 2025-03-10 | 2025-03-10 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-03-08 | 2025-03-31 | 2025-03-10 | 2025-03-10 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-06 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300116-GTSB
4586A-4428B_3 | Tmn Berkat Taiping | DU00005132321 | Northern | Perak | 4.868210 | 100.687110 | [7 empty] | 00. Integrated/RFS Done | 05/07: DO Ready 18/07 : TI Started 22/07: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_4586A New 18G_1.2M(MS) x1. Re-used existing RTN910A. New XMC_3E, Sub A&B_Lo x2. FE_4428B/A00071 New 18G_1.2M(MS) x1. Re-used existing RTN910A. New XMC_3E, Sub A&B_Hi x2. | MW Swap | Existing HW MW Link 18G_1+0_112M_1024QAM. Swap existing HW MW Link with new HW MW Link 18G_2+0_112M_512QAM_EPLA. Later, decom existing HW MW Link 18G_1+0_112M_1024QAM for 18G ODU and 18G Antenna ONLY. Do not decom RTN910A at both sites(4586A & 4428B). Site Impacted : 4586A. NE_4586A 1.Install new 18G_1.2M(MS) x1. 2.Re-used existing RTN910A. 3.Install new XMC_3E, Sub A&B_Lo x2. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link new HW MW Link 18G_2+0_112M_512QAM_EPLA. Configure it. 6.Later, decom existing HW MW Link 18G_1+0_112M_1024QAM for 18G ODU and 18G Antenna ONLY. Do not decom RTN910A at both sites(4586A & 4428B). FE_4428B/A00071 1.Install new 18G_1.2M(MS) x1. 2.Re-used existing RTN910A. 3.Install new XMC_3E, Sub A&B_Hi x2. Configure it. 4.Re-use existing vlan services and existing port at Cisco/PTN. 5.Later, decom existing HW MW Link 18G_1+0_112M_1024QAM for 18G ODU and 18G Antenna ONLY. Do not decom RTN910A at both sites(4586A & 4428B). | Existing HW MW Link 18G_1+0_112M_1024QAM. Swap existing HW MW Link with new HW MW Link 18G_2+0_112M_512QAM_EPLA. Later, decom existing HW MW Link 18G_1+0_112M_1024QAM for 18G ODU and 18G Antenna ONLY. Do not decom RTN910A at both sites(4586A & 4428B). Site Impacted : 4586A. NE_4586A 1.Install new 18G_1.2M(MS) x1. 2.Re-used existing RTN910A. 3.Install new XMC_3E, Sub A&B_Lo x2. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link new HW MW Link 18G_2+0_112M_512QAM_EPLA. Configure it. 6.Later, decom existing HW MW Link 18G_1+0_112M_1024QAM for 18G ODU and 18G Antenna ONLY. Do not decom RTN910A at both sites(4586A & 4428B). | Existing HW MW Link 18G_1+0_112M_1024QAM. Swap existing HW MW Link with new HW MW Link 18G_2+0_112M_512QAM_EPLA. Later, decom existing HW MW Link 18G_1+0_112M_1024QAM for 18G ODU and 18G Antenna ONLY. Do not decom RTN910A at both sites(4586A & 4428B). Site Impacted : 4586A. FE_4428B/A00071 1.Install new 18G_1.2M(MS) x1. 2.Re-used existing RTN910A. 3.Install new XMC_3E, Sub A&B_Hi x2. Configure it. 4.Re-use existing vlan services and existing port at Cisco/PTN. 5.Later, decom existing HW MW Link 18G_1+0_112M_1024QAM for 18G ODU and 18G Antenna ONLY. Do not decom RTN910A at both sites(4586A & 4428B). | XMC_3E | MS | 18G | 18G_1.2M(MS) x1. | 18G_1.2M(MS) x1. | Magicell | SQ202507160595-Magicell | Magicell | SQ202507190097-Magicell // SQ202507190099-Magicell // SQ202511030393-Magicell | 2025-12-04 | 2025-11-27 | Completed | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-11-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070519 |  | 2025-07-07 | 2025-07-08 | Completed | 2025-07-05 | 2025-07-07 | 2025-07-05 | 2025-07-08 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-18 | 2026-07-26 | 2025-07-18 | 2025-07-31 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-07-18 | 2026-07-26 | 2025-07-18 | 2025-07-18 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-22 | 2025-07-18 | 2026-07-26 | 2025-07-18 | 2025-08-01 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-07-18 | 2026-07-26 | 2025-07-18 | 2025-08-02 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505070167-GTSB | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | MAZELAN BIN RAMLI6798000096
9333B_EB | Rh James | DU00005141468 | Sarawak | Sarawak | 2.740235 | 112.661791 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | [6 empty] | Trintel | SQ202504170489-Trintel | Allstar | SQ202504240801-Allstar // SQ202506170537-Allstar | 2025-04-17 | 2025-04-11 | Completed | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-09 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-10 | 2025-04-17 | 2025-04-10 | 2025-04-11 | CHRISTINE IVY ANAK GIRIN7667000067 | Trintel TI | TRINTEL (M) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041715 |  | 2025-04-18 | 2025-04-21 | Completed | 2025-04-17 | 2025-04-18 | 2025-04-17 | 2025-04-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-06 | 2025-05-12 | 2025-05-07 | 2025-05-14 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-05-06 | 2025-05-12 | 2025-05-08 | 2025-05-14 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-05-06 | 2025-05-12 | 2025-07-15 | 2025-07-15 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | 2025-03-05: 2025-05-06; 2025-03-05: 2025-05-12; 2025-03-05: 2025-05-06; 2025-03-05: 2025-05-06 |  |  | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-06-19 | IDA//NAJEEHA BINTI MAZLAN/7018000019
9419A_EB | Kg. Stinggang | DU00005141469 | Sarawak | Sarawak | 1.483147 | 110.029646 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | [6 empty] | Magicell | SQ202503270813-Magicell | Allstar | SQ202504230266-Allstar // SQ202504260202-Allstar | 2025-04-18 | 2025-04-14 | Completed | 2025-03-11 | 2025-03-31 | 2025-03-24 | 2025-03-24 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-14 | 2025-04-18 | 2025-04-14 | 2025-04-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-14 | 2025-04-18 | 2025-04-14 | 2025-04-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041713 |  | 2025-04-18 | 2025-04-21 | Completed | 2025-04-17 | 2025-04-18 | 2025-04-17 | 2025-04-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-21 | 2025-04-28 | 2025-04-21 | 2025-04-25 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-04-21 | 2025-04-28 | 2025-04-22 | 2025-04-26 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-21 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-04-21 | 2025-04-28 | 2025-05-04 | 2025-05-04 | BONG NEE NYEEbong.allstar@gmail.com | 2025-03-05: 2025-04-21; 2025-03-05: 2025-04-28; 2025-03-05: 2025-04-21; 2025-03-05: 2025-04-21 |  |  | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-06-19 | IDA//NAJEEHA BINTI MAZLAN/7018000019
9352B_EB | Rumah Mamat | DU00005141470 | Sarawak | Sarawak | 3.568356 | 113.643013 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | [6 empty] | Trintel | SQ202504170489-Trintel | Allstar | SQ202504240801-Allstar | 2025-04-11 | 2025-04-11 | Completed | 2025-04-04 | 2025-04-04 | 2025-04-04 | 2025-04-09 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041711 |  | 2025-04-18 | 2025-04-21 | Completed | 2025-04-17 | 2025-04-18 | 2025-04-17 | 2025-04-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-29 | 2025-05-05 | 2025-04-29 | 2025-05-02 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-04-29 | 2025-05-05 | 2025-04-29 | 2025-05-02 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-04-29 | 2025-05-05 | 2025-04-30 | 2025-04-30 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | 2025-03-05: 2025-04-29; 2025-03-05: 2025-05-05; 2025-03-05: 2025-04-29; 2025-03-05: 2025-04-29 |  |  | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
9378A_EB | Kemantan-Julau Junction | DU00005141471 | Sarawak | Sarawak | 2.066678 | 111.820211 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | [6 empty] | Trintel | SQ202504170489-Trintel | Allstar | SQ202504240801-Allstar | 2025-04-11 | 2025-04-11 | Completed | 2025-04-03 | 2025-04-03 | 2025-04-03 | 2025-04-09 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041716 |  | 2025-04-18 | 2025-04-21 | Completed | 2025-04-17 | 2025-04-18 | 2025-04-17 | 2025-04-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-05 | 2025-05-10 | 2025-05-02 | 2025-05-07 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-05-05 | 2025-05-10 | 2025-05-05 | 2025-05-07 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-05 | 2025-05-05 | 2025-05-10 | 2025-05-05 | 2025-07-15 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | 2025-03-05: 2025-05-05; 2025-03-05: 2025-05-10; 2025-03-05: 2025-05-05; 2025-03-05: 2025-05-05 |  |  | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-06-19 | IDA//NAJEEHA BINTI MAZLAN/7018000019
4591A-B01049 | Kg.Tebok Pulai | DU00005141472 | Northern | Selangor | 3.725100 | 100.972370 | WK10 | MAR 25 | WK10 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 7/3/2025 : Cutover done 6/3/2025 : Cutover WIP 5/3/2025 : Instalation complete only 60% due to shortage antenna boom bracket | TSS+AA+TI | L1+ATP+PAC | 18G 2+0 1.2m/1.2m XMC3E NE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 4) 1x18GHz 1.2m DP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 4) 1x18GHz 1.2m DP 5) 1G SFP and patch cord | MW New Link / Reroute | To build new link B00695-B01348-4591A-B01049 to offload traffic from congested MW link B00695-4475A Impact sites: 1771C,2637A Tx route before: 4591A/4591A-4475A Tx route after: 4591A/4591A-B01049 NE (4591A): 1) New RTN910A will be installed under DU B01348-4591A (Tx Mini Project) 2) Install new link at new RTN 7-ISM8 3) Migrate 1771C and 2637A traffic to new link FE (B01049): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8 3) Patch new IDU to xC PTN 71450-BT37_SEKENDI (ops team to assign port) 4) Migrate 1771C and 2637A traffic to new 4+0 link. Create new DCN | NE (4591A): 1) New RTN910A will be installed under DU B01348-4591A (Tx Mini Project) 2) Install new link at new RTN 7-ISM8 3) Migrate 1771C and 2637A traffic to new link | FE (B01049): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8 3) Patch new IDU to xC PTN 71450-BT37_SEKENDI (ops team to assign port) 4) Migrate 1771C and 2637A traffic to new 4+0 link. Create new DCN | XMC3E | MAC DP | 18G | 1.2m | 1.2m | GTSB | SQ202503060147-GTSB | GTSB | SQ202503200272-GTSB // SQ202503200273-GTSB // SQ202504260178-GTSB | 2025-12-09 | 2025-12-02 | Completed | 2025-03-05 | 2025-03-31 | 2025-03-05 | 2025-03-28 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Completed |  | 2025-04-10 | 2025-06-30 | 2025-04-04 | 2025-06-09 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022809 |  | 2025-03-01 | 2025-03-24 | Completed | 2025-02-28 | 2025-03-01 | 2025-02-28 | 2025-03-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-05 | 2025-03-31 | 2025-03-05 | 2025-03-24 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-03-05 | 2025-03-31 | 2025-03-05 | 2025-05-06 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-06 | 2025-03-05 | 2025-03-31 | 2025-03-05 | 2025-04-09 | Aminuddin bin che azibA0563734967123169280 | 2025-03-05: 2025-03-05; 2025-03-05: 2025-03-31; 2025-03-05: 2025-03-05; 2025-03-05: 2025-03-05 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507080632-GTSB
9347B_EB | Sg Asap | DU00005141474 | Sarawak | Sarawak | 3.058021 | 113.923633 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | [6 empty] | Magicell | SQ202503190735-Magicell | Allstar | SQ202504240801-Allstar | 2025-03-31 | 2025-03-24 | Completed | 2025-03-07 | 2025-03-31 | 2025-03-10 | 2025-03-10 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-24 | 2025-03-28 | 2025-03-24 | 2025-03-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-24 | 2025-03-28 | 2025-03-24 | 2025-03-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041709 |  | 2025-04-18 | 2025-04-21 | Completed | 2025-04-17 | 2025-04-18 | 2025-04-17 | 2025-04-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-30 | 2025-05-06 | 2025-05-02 | 2025-05-07 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-04-30 | 2025-05-06 | 2025-03-07 | 2025-05-09 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-07 | 2025-04-30 | 2025-05-06 | 2025-03-07 | 2025-07-15 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | 2025-03-05: 2025-04-30; 2025-03-05: 2025-05-06; 2025-03-05: 2025-03-07; 2025-03-05: 2025-05-09 |  |  | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-06-19 | IDA//NAJEEHA BINTI MAZLAN/7018000019
9506B_EB | Telok Melano | DU00005141475 | Sarawak | Sarawak | 2.004234 | 109.645417 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | [6 empty] | Magicell | SQ202503190735-Magicell | Allstar | SQ202504240801-Allstar // SQ202504260202-Allstar | 2025-04-18 | 2025-04-14 | Completed | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-19 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-14 | 2025-04-18 | 2025-04-14 | 2025-04-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-14 | 2025-04-18 | 2025-04-14 | 2025-04-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041714 |  | 2025-04-18 | 2025-04-21 | Completed | 2025-04-17 | 2025-04-18 | 2025-04-17 | 2025-04-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-23 | 2025-04-29 | 2025-04-21 | 2025-04-25 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-04-23 | 2025-04-29 | 2025-04-21 | 2025-04-25 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-04-23 | 2025-04-29 | 2025-04-23 | 2025-04-23 | BONG NEE NYEEbong.allstar@gmail.com | 2025-03-05: 2025-04-23; 2025-03-05: 2025-04-29; 2025-03-05: 2025-04-23; 2025-03-05: 2025-04-23 |  |  | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
9045B_EB | Kg Bokah USP | DU00005141476 | Sarawak | Sarawak | 1.494158 | 109.923300 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | [6 empty] | Magicell | SQ202503190735-Magicell | Allstar | SQ202504230266-Allstar // SQ202504260202-Allstar | 2025-04-18 | 2025-04-14 | Completed | 2025-03-11 | 2025-03-31 | 2025-03-18 | 2025-03-18 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-14 | 2025-04-18 | 2025-04-14 | 2025-04-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-14 | 2025-04-18 | 2025-04-14 | 2025-04-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041712 |  | 2025-04-18 | 2025-04-21 | Completed | 2025-04-17 | 2025-04-18 | 2025-04-17 | 2025-04-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-21 | 2025-04-28 | 2025-04-21 | 2025-04-25 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-04-21 | 2025-04-28 | 2025-04-22 | 2025-04-26 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-22 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-04-21 | 2025-04-28 | 2025-05-04 | 2025-05-04 | BONG NEE NYEEbong.allstar@gmail.com | 2025-03-05: 2025-04-21; 2025-03-05: 2025-04-28; 2025-03-05: 2025-04-23; 2025-03-05: 2025-04-23 |  |  | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
9641A_EB | Long Tuma | DU00005141477 | Sarawak | Sarawak | 4.809710 | 115.405409 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 3 x Cat6 cable | IPRAN Port Upgrade | Existing BBU patched to NEC IDU. To install new IDU for EB site as existing NEC IDU port faulty 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port 5) Patch NEC IDU to RTN GE4 port remarks: in case using electrical SFP to use GE5 port for EB site and GE6 port for NEC IDU 5) Create new DCN | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | [6 empty] | Trintel | SQ202510010674-Trintel | CCSMY | SQ202506190638-CCS // SQ202507030752-CCS |  |  | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250519AF |  | 2025-05-20 | 2025-06-14 | Completed | 2025-05-19 | 2025-05-20 | 2025-05-19 | 2025-06-14 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-17 | 2025-07-03 | 2025-06-19 | 2025-06-30 | Hermanwijaya bin suardi7021000085 | CCS TI | 2025-06-17 | 2025-07-03 | 2025-06-19 | 2025-07-06 | Hermanwijaya bin suardi7021000085 | CCS TI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-19 | 2025-06-17 | 2025-07-03 | 2025-06-19 | 2026-03-31 | Hermanwijaya bin suardi7021000085 | 2025-03-05: 2025-06-19; 2025-03-05: 2025-06-30; 2025-03-05: 2025-06-19; 2025-03-05: 2025-06-19 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 |  | Assign Subcon
9416A_EB | Kg Keranji | DU00005141478 | Sarawak | Sarawak | 1.714688 | 109.775784 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | Existing BBU patched direct to LL port. To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch BBU to RTN GE2 port 4) Patch EB site to RTN GE3 port remarks: in case using electrical SFP to use GE5 port for EB site 5) Create new DCN | [6 empty] | Magicell | SQ202503270813-Magicell | Allstar | SQ202504280811-Allstar | 2025-04-25 | 2025-04-21 | Completed | 2025-03-12 | 2025-03-31 | 2025-03-24 | 2025-03-24 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25042497 |  | 2025-04-25 | 2025-04-28 | Completed | 2025-04-24 | 2025-04-25 | 2025-04-24 | 2025-04-28 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-30 | 2025-05-06 | 2025-04-30 | 2025-05-02 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-04-30 | 2025-05-06 | 2025-04-30 | 2025-05-05 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-04-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-30 | 2025-04-30 | 2025-05-06 | 2025-05-04 | 2025-05-04 | KENISTON//ANAK SPANCER/6798000184 | 2025-03-05: 2025-04-30; 2025-03-05: 2025-05-06; 2025-03-05: 2025-04-30; 2025-03-05: 2025-04-30 |  |  | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-06-19 | IDA//NAJEEHA BINTI MAZLAN/7018000019
1882H_LOS | IWK Shah Alam | DU00005152648 | Central | Selangor | 3.036280 | 101.557720 |  |  |  |  | Cancel / Drop | No LOS available | ZTE | 00. Site Out/Drop | 13/3/2025 : Survey LOS done and found no LOS available. Request use LL by MSP | TSS |  |  | MW New Link / Reroute | NO LOS DURING SURVEY. PROPOSED FIBER. CANCEL DROP | [7 empty] | Magicell | SQ202503190673-Magicell | Magicell | No PR required-Work at TSS only | 2025-06-18 | 2025-06-18 | Completed | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-02 | 2025-04-02 | 2025-04-02 | 2025-04-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-11 | 2025-04-12 | 2025-04-11 | 2025-04-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-17 | 2025-06-18 | 2025-06-17 | 2025-06-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300116-GTSB
4695D_HU | kampung cherok kelubi | DU00006022003 | Northern | Kedah | 5.621190 | 100.465023 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO 2X PATCH CORD | MW Swap | MW SWAP UPGRADE 4695D-4626A WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_0.8KM IMPACTED: 4695D DISMANTLE EXISTING LINK PATCH TO OB FIBER K00576 AND DO PORT LAG 2G | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 2G AT K00576 OB FIBER 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | MTK | SQ202509230170-MTK | MTK | SQ202509230103-MTK // SQ202509230115-MTK | 2025-11-29 | 2025-11-28 | Completed | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | AMIRUL SYAHRINI BIN MOHD ZIN6000023342 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092316 |  | 2025-09-24 | 2025-09-29 | Completed | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-10-10 | 2025-10-02 | 2025-10-07 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-09-30 | 2025-10-10 | 2025-10-02 | 2025-11-26 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-02 | 2025-09-30 | 2025-10-10 | 2025-10-18 | 2025-11-24 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-09-30 | 2025-10-10 | 2025-10-18 | 2025-11-25 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | NG HONG JIE7018000036 | Logistic Team | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
4770A | Toklin (Trunk ) | DU00003268215 | Northern | Kedah | 5.630050 | 100.570910 | Cancel |  | Cancel |  |  |  | ZTE | 00. Integrated/RFS Done | 7/6: Cutover done | TSS+TI | L1+ATP+PAC | 2x Fiber 1G 1330nm 40km Module 2x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN port reengineering at IBeam 4770A for RTN21 NE (4770A) at IBeam: 1) 1G port at GE0/4/2. 2) Insert new Fiber SFP module 1G SFP SM 1330 40km at port GE0/4/2. NE (4770A) at new Huawei RTN 910A(RTN21: 1) Insert new Fiber SFP module 1G SFP SM 13300 40km at 8-EM6-5(Port 5). | [7 empty] | GCI | SQ202408300869-GCI | GCI | SQ202407020120-GCI | 2024-11-29 | 2024-11-29 | Completed | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2023-12-20 | 2023-12-20 | Completed | 2023-12-19 | 2023-12-20 | 2023-12-19 | 2023-12-20 | 罗尔伍6696000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2023-12-25 | 2023-12-29 |  |  | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2024-05-30 | 2024-09-30 | 2024-05-29 | 2024-08-14 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2024-06-07 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-05-30 | 2024-05-31 | 2024-05-29 | 2025-11-24 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | 2025-09-30: 2024-05-30; 2025-10-10: 2024-05-31; 2025-10-18: 2024-05-29; 2025-11-25: 2024-06-07 |  |  | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
7172D_HU | KaboganJunction (REL) | DU00006523390 | Sabah | Sabah | 4.441761 | 118.612117 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X IF CABLE (SUITABLE LENGTH) | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 7172D-7647C WITH FROM 18G_1+0_0.6M/0.6M_MDD_56MHZ_512QAM TO HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_256QAM_1556MBPS_XMC5D_SUB_A_LINK_2.91KM IMPACTED: 7172D | 1. REUSE EXISTING IDU 2. REUSE EXISTING 18G 0.6M MDD ANTENNA 3. ADD IF CABLE ODU HORIZONTAL POLAR TO SLOT 7-2 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM | 1. REUSE EXISTING IDU RTN910 2. REUSE EXISTING 18G 0.6M MDD ANTENNA 3. ADD IF CABLE ODU HORIZONTAL POLAR TO SLOT 3-2 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM | XMC5D | MDD | 18G | 0.6 | 0.6 | NR services | SQ202602250627-NR Services | NR services | SQ202602090118-NR Services // SQ202602090125-NR Services |  |  | Ongoing | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26012151 |  | 2026-01-22 | 2026-02-12 | Completed | 2026-01-21 | 2026-01-22 | 2026-01-21 | 2026-02-12 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-02-12 | RANA//WAQAS/6000006187 | NR Service TI | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-02-12 | RANA//WAQAS/6000006187 | NR Service TI | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-11 | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-03-18 | RANA//WAQAS/6000006187 | 2025-09-30: 2026-01-30; 2025-10-10: 2026-02-28; 2025-10-18: 2026-01-30; 2025-11-25: 2026-02-11 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202601210780-GCI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | EZRIN TASNIM BIN ABDUL GANI6798000128
S00769_HU | S097A_S00769OD_AUMKAROILMILL | DU00006523391 | Sabah | Sabah | 4.747936 | 117.868222 | [7 empty] | 04. Pending DO |  | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 2X RTN910A 1X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D PRO SUB A HI 1x ODU 15G XMC5D PRO SUB A LO | MW Swap | MW SWAP UPGRADE LINK S00769-S00770 WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_256QAM_800MBPS_XMC5D_SUB_A_WITH CA_LINK_4.82KM IMPACTED: S00769 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 AND 2 PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 AND 2 PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA 5. DISMANTLE EXISTING LINK | XMC5D | MDD | 15G | 0.6 | 1.2 | NR services | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601210780-GCI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
4051R_HU | KgBukit Sebelah | DU00006523392 | Northern | Kedah | 5.857600 | 100.889000 | [7 empty] | 04. Pending DO |  | TSS+AA+TI |  | 13G_2+0_28M. NE_4051R 13G_DP_1.2M(MDD) x1. ISM8 x1. XMC_5D , Sub B_Hi x1 FE_4990B 13G_DP_1.2M(MDD) x1. ISM8 x1. XMC_5D , Sub B_Lo x1. | MW Parallel Link | Existing link 15G_2+0_28M. Install parallel link 13G_2+0_28M. Site Impacted : 4051R , 4019P. NE_4051R 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4051R_RTN01. 3.Install new 3_ISM8-2+0 into existing 4051R_RTN01. 4.Create service cross connect and EPLA existng MW link. 5.Traffic migrate to new Parallel link. 6.No MW to decomm. FE_4990B 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4990B_RTN01. 3.Install new 4_ISM8-2+0 into existing 4990B_RTN01. 4.Transfer existing 3_ISM8-2+0 from 4990B_RTN02 to existing 4990B_RTN01_3_ISM8-2+0. 5.Create service cross connect and EPLA with existing MW link. 6.Traffic migrate to new Parallel link. 7.No MW decomm. | Existing link 15G_2+0_28M. Install parallel link 13G_2+0_28M. Site Impacted : 4051R , 4019P. NE_4051R 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4051R_RTN01. 3.Install new 3_ISM8-2+0 into existing 4051R_RTN01. 4.Create service cross connect and EPLA existng MW link. 5.Traffic migrate to new Parallel link. 6.No MW to decomm. | Existing link 15G_2+0_28M. Install parallel link 13G_2+0_28M. Site Impacted : 4051R , 4019P. FE_4990B 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4990B_RTN01. 3.Install new 4_ISM8-2+0 into existing 4990B_RTN01. 4.Transfer existing 3_ISM8-2+0 from 4990B_RTN02 to existing 4990B_RTN01_3_ISM8-2+0. 5.Create service cross connect and EPLA with existing MW link. 6.Traffic migrate to new Parallel link. 7.No MW decomm. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GTSB | SQ202601220776-GTSB | GTSB | SQ202601220771-GTSB // SQ202601220774-GTSB |  |  | Ongoing | 2026-01-31 | 2026-02-28 | 2026-01-31 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26012304 |  | 2026-01-24 | 2026-01-30 | Completed | 2026-01-23 | 2026-01-24 | 2026-01-23 | 2026-01-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-31 | 2026-02-28 | 2026-01-31 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-31 | 2026-02-28 | 2026-01-31 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | [7 empty] | 2026-01-31 | 2026-02-28 | 2026-01-31 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-09-30: 2026-01-31; 2025-10-10: 2026-02-28; 2025-10-18: 2026-01-31 | [7 empty] | GCI | SQ202601210776-GCI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | CHEONG/SENG/WAH/7018000306
4306R_HU | KGSG PETAI | DU00006523393 | Northern | Perak | 4.747857 | 100.719026 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M_512QAM_EPLA NE_4306R New 15G_0.6M(MS)+Coupler x1. Re-use existing RTN910AF(RTN01, NEID 44-13943). New ISM8 x1. New XMC_3, Sub A&B_Lo x2. New IF cables with suitable length and type x2 RUN. FE_A00559/4343B New 15G_1.2M(HS)+Coupler x1. Re-use existing RTN910AF(RTN02, NEID 44-23943). New ISM8 x1. New XMC_3, Sub A&B_Hi x2. New IF cables with suitable length and type x2 RUN. | MW Swap | Existing HW MW Link 4306R-A00559/4343B, 18G_1+0_55MHZ_256QAM_0.6/0.6. MW Swap HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. Later, decom existing HW MW Link 4306R-A00559/4343B, 18G_1+0_55MHZ_256QAM_0.6/0.6. Anyway, do not decom RTN910AF(RTN01, NEID 44-13943) and RTN910AF(RTN02, NEID 44-23943). Site Impacted : 4306R. NE_4306R. 1.Install new 15G_0.6M(MS)+Coupler x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-13943) and insert x1 new ISM8 into slot 03. 3.Install new XMC_3, Sub A&B_Lo x2. Configure it. 4.Build new HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. 5.Re-use existing xC Vlan DCN and Vlan Services. 6.Migrate traffic 4306R via new HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. 7.Later, decom existing HW MW Link 4306R-A00559/4343B, 18G_1+0_55MHZ_256QAM_0.6/0.6. Anyway, do not decom RTN910AF(RTN01, NEID 44-13943) and RTN910AF(RTN02, NEID 44-23943). FE_A00559/4343B. 1.Install new 15G_1.2M(HS)+Coupler x1. 2.Re-use existing RTN910AF(RTN02, NEID 44-23943) and insert x1 new ISM8 into slot 03. 3.Install new XMC_3, Sub A&B_Hi x2. Configure it. 4.Build new HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. 5.Re-use existing xC Vlan DCN and Vlan Services. 6.Re-use existing port at PTN/Cisco. 7.Migrate traffic 4306R via new HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. 8.Later, decom existing HW MW Link 4306R-A00559/4343B, 18G_1+0_55MHZ_256QAM_0.6/0.6. Anyway, do not decom RTN910AF(RTN01, NEID 44-13943) and RTN910AF(RTN02, NEID 44-23943). | Existing HW MW Link 4306R-A00559/4343B, 18G_1+0_55MHZ_256QAM_0.6/0.6. MW Swap HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. Later, decom existing HW MW Link 4306R-A00559/4343B, 18G_1+0_55MHZ_256QAM_0.6/0.6. Anyway, do not decom RTN910AF(RTN01, NEID 44-13943) and RTN910AF(RTN02, NEID 44-23943). Site Impacted : 4306R. NE_4306R. 1.Install new 15G_0.6M(MS)+Coupler x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-13943) and insert x1 new ISM8 into slot 03. 3.Install new XMC_3, Sub A&B_Lo x2. Configure it. 4.Build new HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. 5.Re-use existing xC Vlan DCN and Vlan Services. 6.Migrate traffic 4306R via new HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. 7.Later, decom existing HW MW Link 4306R-A00559/4343B, 18G_1+0_55MHZ_256QAM_0.6/0.6. Anyway, do not decom RTN910AF(RTN01, NEID 44-13943) and RTN910AF(RTN02, NEID 44-23943). | Existing HW MW Link 4306R-A00559/4343B, 18G_1+0_55MHZ_256QAM_0.6/0.6. MW Swap HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. Later, decom existing HW MW Link 4306R-A00559/4343B, 18G_1+0_55MHZ_256QAM_0.6/0.6. Anyway, do not decom RTN910AF(RTN01, NEID 44-13943) and RTN910AF(RTN02, NEID 44-23943). Site Impacted : 4306R. FE_A00559/4343B. 1.Install new 15G_1.2M(HS)+Coupler x1. 2.Re-use existing RTN910AF(RTN02, NEID 44-23943) and insert x1 new ISM8 into slot 03. 3.Install new XMC_3, Sub A&B_Hi x2. Configure it. 4.Build new HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. 5.Re-use existing xC Vlan DCN and Vlan Services. 6.Re-use existing port at PTN/Cisco. 7.Migrate traffic 4306R via new HW MW Link 4306R-A00559/4343B, 15G_4+0_28MHZ_512QAM_EPLA_0.6/1.2. 8.Later, decom existing HW MW Link 4306R-A00559/4343B, 18G_1+0_55MHZ_256QAM_0.6/0.6. Anyway, do not decom RTN910AF(RTN01, NEID 44-13943) and RTN910AF(RTN02, NEID 44-23943). | XMC_3 | MS & HS | 15G | 15G_0.6M(MS)+Coupler x1 | 15G_1.2M(HS)+Coupler x1 | GTSB | SQ202601220776-GTSB | GTSB | SQ202601220771-GTSB // SQ202601220774-GTSB // SQ202604200216-GTSB // SQ202604280656-GTSB |  |  | Ongoing | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-30 | 2026-04-04 | 2026-03-30 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26012218 |  | 2026-01-23 | 2026-01-30 | Completed | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-05 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-12 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-11 | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-11 | HAMZAH BIN ABDUL MUTALIF6799000301 | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-05 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601210796-GTSB
4261B_HU_1 | TUALANG | DU00006523394 | Northern | Kedah | 6.117703 | 100.476047 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_2+0_28M_1024QAM_EPLA NE_4261B New 13G_1.2M(MDD) x1. New RTN910AF(RTN06). New ISM8 x2. New XMC_5D Pro, Sub A_Hi x1. New IF cables with suitable length and type x5 RUN - x4 existing channels-shifting from RTN910A(RTN02, NEID 9-41426) to new RTN910AF(RTN06) and x1 for new channels). New CAT6 cable x1. FE_4678A New 13G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN05, NEID 9-12988). New ISM8 x1. New XMC_5D Pro, Sub A_Lo x1. New IF cables with suitable length and type x1 RUN. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing Huawei MW Link 4261B-4678A, 13G_4+0_28MHZ_2048QAM_EPLA. Build new parallel HW MW Link 4261B-4678A, 13G_2+0_28MHZ_1024QAM_EPLA. Later, combine existing Huawei MW Link 4261B-4678A, 13G_4+0_28MHZ_2048QAM_EPLA and new parallel HW MW Link 4261B-4678A, 13G_2+0_28MHZ_1024QAM_EPLA. Become 13G_6+0_28MHZ_2048QAM&1024QAM_EPLA. Site Impacted : 4261B. NE_4261B 1.Install 13G_1.2M(MDD) x1. 2.Install new RTN910A(RTN06) x1 and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Due to need to swap RTN910A(RTN02, NEID 9-41426) to new RTN910AF(RTN06). Therefore, if existing IF cables not sufficient length to terminate, require to lay new 4x RUN IF cable with suitable length and type together with new IF cable 1x RUN with suitable length and type for new parallel HW MW Link 4261B-4678A, 13G_2+0_28MHZ_1024QAM_EPLA. 5.Later, combine existing Huawei MW Link 4261B-4678A, 13G_4+0_28MHZ_2048QAM_EPLA and new parallel HW MW Link 4261B-4678A, 15G_2+0_28MHZ_1024QAM_EPLA. Become 13G_6+0_28MHZ_2048QAM&1024QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN06). 7.Perform patching between port 8-EG6-1 of new RTN910AF(RTN06) and existing BBU 4261B. 8.Re-use existing Vlan DCN and Vlan Services. 9.Migrate traffic 4261B via 13G_6+0_28MHZ_2048QAM&1024QAM_EPLA. FE_4678A 1.Install 13G_1.2M(MDD) x1. 2.Re-use RTN910AF(RTN05, NEID 9-12988) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Later, combine existing Huawei MW Link 4261B-4678A, 13G_4+0_28MHZ_2048QAM_EPLA and new parallel HW MW Link 4261B-4678A, 13G_2+0_28MHZ_1024QAM_EPLA. Become 13G_6+0_28MHZ_2048QAM&1024QAM_EPLA. 5.Re-use existing Vlan DCN and Vlan Services. 6.Migrate traffic 4261B via existing port of IBeam. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing Huawei MW Link 4261B-4678A, 13G_4+0_28MHZ_2048QAM_EPLA. Build new parallel HW MW Link 4261B-4678A, 13G_2+0_28MHZ_1024QAM_EPLA. Later, combine existing Huawei MW Link 4261B-4678A, 13G_4+0_28MHZ_2048QAM_EPLA and new parallel HW MW Link 4261B-4678A, 13G_2+0_28MHZ_1024QAM_EPLA. Become 13G_6+0_28MHZ_2048QAM&1024QAM_EPLA. Site Impacted : 4261B. NE_4261B 1.Install 13G_1.2M(MDD) x1. 2.Install new RTN910A(RTN06) x1 and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Due to need to swap RTN910A(RTN02, NEID 9-41426) to new RTN910AF(RTN06). Therefore, if existing IF cables not sufficient length to terminate, require to lay new 4x RUN IF cable with suitable length and type together with new IF cable 1x RUN with suitable length and type for new parallel HW MW Link 4261B-4678A, 13G_2+0_28MHZ_1024QAM_EPLA. 5.Later, combine existing Huawei MW Link 4261B-4678A, 13G_4+0_28MHZ_2048QAM_EPLA and new parallel HW MW Link 4261B-4678A, 15G_2+0_28MHZ_1024QAM_EPLA. Become 13G_6+0_28MHZ_2048QAM&1024QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN06). 7.Perform patching between port 8-EG6-1 of new RTN910AF(RTN06) and existing BBU 4261B. 8.Re-use existing Vlan DCN and Vlan Services. 9.Migrate traffic 4261B via 13G_6+0_28MHZ_2048QAM&1024QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing Huawei MW Link 4261B-4678A, 13G_4+0_28MHZ_2048QAM_EPLA. Build new parallel HW MW Link 4261B-4678A, 13G_2+0_28MHZ_1024QAM_EPLA. Later, combine existing Huawei MW Link 4261B-4678A, 13G_4+0_28MHZ_2048QAM_EPLA and new parallel HW MW Link 4261B-4678A, 13G_2+0_28MHZ_1024QAM_EPLA. Become 13G_6+0_28MHZ_2048QAM&1024QAM_EPLA. Site Impacted : 4261B. FE_4678A 1.Install 13G_1.2M(MDD) x1. 2.Re-use RTN910AF(RTN05, NEID 9-12988) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Later, combine existing Huawei MW Link 4261B-4678A, 13G_4+0_28MHZ_2048QAM_EPLA and new parallel HW MW Link 4261B-4678A, 13G_2+0_28MHZ_1024QAM_EPLA. Become 13G_6+0_28MHZ_2048QAM&1024QAM_EPLA. 5.Re-use existing Vlan DCN and Vlan Services. 6.Migrate traffic 4261B via existing port of IBeam. | XMC_5D Pro | MDD | 13G | 13G_1.2M(MDD) x1 | 13G_1.2M(MDD) x1 | GTSB | SQ202601220776-GTSB | GTSB | SQ202601220771-GTSB // SQ202601220774-GTSB |  |  | Ongoing | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-03-02 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-04-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26012216 |  | 2026-01-23 | 2026-01-30 | Completed | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-06 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-03-02 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-06 | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-03-09 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-09-30: 2026-01-31; 2025-10-10: 2026-02-28; 2025-10-18: 2026-01-31; 2025-11-25: 2026-02-06 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601210796-GTSB
7135D_HU | JalanKauran | DU00006523395 | Sabah | Sabah | 5.311997 | 116.130554 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M. NE_7135G 23G_SP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E_Sub A_Hi x1. FE_7065A 23G_SP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A_Lo x1. | MW Swap | Existing link 18G_1+0_56M. Hardware Not Support Remote Software Upgrade. Swap existing link to 18G_1+0_112M. Site Impacted : 7135D. NE_7135G 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E_Sub A_Hi. 4.Create service cross connect. 5.Traffic migrate to new link. 6.Decom existing MW link. FE_7065A 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Reuse existing 7065A_RTN01. 3.Install new 4_ISM8-1+0 into existing 7065A_RTN01. 4.Install new XMC_3E , Sub A_Lo. 5.Create service cross connect. 6.Traffic migrate to new link. 7.Decom existing MW link. | Existing link 18G_1+0_56M. Hardware Not Support Remote Software Upgrade. Swap existing link to 18G_1+0_112M. Site Impacted : 7135D. NE_7135G 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E_Sub A_Hi. 4.Create service cross connect. 5.Traffic migrate to new link. 6.Decom existing MW link. | Existing link 18G_1+0_56M. Hardware Not Support Remote Software Upgrade. Swap existing link to 18G_1+0_112M. Site Impacted : 7135D. FE_7065A 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Reuse existing 7065A_RTN01. 3.Install new 4_ISM8-1+0 into existing 7065A_RTN01. 4.Install new XMC_3E , Sub A_Lo. 5.Create service cross connect. 6.Traffic migrate to new link. 7.Decom existing MW link. | XMC_3E | MAC | 23G | 0.6 | 0. | NR services | SQ202604100662-NR Services | NR services | SQ202604030214-NR Services // SQ202604030216-NR Services |  |  | Ongoing | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022334 |  | 2026-02-24 | 2026-04-01 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-04-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-31 | 2026-04-30 | 2026-03-30 | 2026-04-01 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-03-31 | 2026-04-30 | 2026-03-30 | 2026-04-01 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-01 | 2026-03-31 | 2026-04-30 | 2026-03-30 | 2026-04-13 | RALPH O'BRYAN HILARY7167000030 | 2026-03-31 | 2026-04-30 | 2026-03-30 | 2026-03-31 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202601210780-GCI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | CHEONG/SENG/WAH/7018000306
1001L_PL | Sepintas | DU00006523396 | Central | Selangor | 3.787214 | 101.008918 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | Perform 23G_2+0_55MHZ_512QAM_EPLA NE_1001L Re-use existing 23G_DP_1.2M(MAC) x1. New 23G OMT x1(if not available at site) Re-use existing RTN910AF(RTN01, NEID 33-18052). New XMC_3, Sub B_Hi x1. FE_B00277 Re-use existing 23G_DP_0.3M(MAC) x1. New 23G OMT x1(if not available at site) Re-use existing RTN910AF(RTN03, NEID 33-28052). New XMC_3, Sub B_Lo x1. | MW Hardware Upgrade | Perform 23G_2+0_55MHZ_512QAM_EPLA. Site Impacted : 1001L. NE_1001L 1.Re-use existing 23G_DP_1.2M(MAC) x1 and add new OMT x1(if not available at site). 2.Install new XMC_3, Sub B_Hi x1. 3.Re-use existing RTN910AF(RTN01, NEID 33-18052) and use Slot 07 Port 2(for 2nd channel). 4.Build new HW MW Link 23G_2+0_55MHZ_512QAM_EPLA. 5.Re-use existing Vlan Services. 6.Migrate traffic 1001L into new HW MW Link 23G_2+0_55MHZ_512QAM_EPLA. FE_B00277 1.Re-use existing 23G_DP_1.2M(MAC) x1 and add new OMT x1(if not available at site). 2.Install new XMC_3, Sub B_Lo x1. 3.Re-use existing RTN910AF(RTN03, NEID 33-28052) and use Slot 07 Port 2(for 2nd channel). 4.Build new HW MW Link 23G_2+0_55MHZ_512QAM_EPLA. 5.Re-use existing Vlan Services. 6.Migrate traffic 1001L into existing port at PTN/Cisco Router. | Perform 23G_2+0_55MHZ_512QAM_EPLA. Site Impacted : 1001L. NE_1001L 1.Re-use existing 23G_DP_1.2M(MAC) x1 and add new OMT x1(if not available at site). 2.Install new XMC_3, Sub B_Hi x1. 3.Re-use existing RTN910AF(RTN01, NEID 33-18052) and use Slot 07 Port 2(for 2nd channel). 4.Build new HW MW Link 23G_2+0_55MHZ_512QAM_EPLA. 5.Re-use existing Vlan Services. 6.Migrate traffic 1001L into new HW MW Link 23G_2+0_55MHZ_512QAM_EPLA. | Perform 23G_2+0_55MHZ_512QAM_EPLA. Site Impacted : 1001L. FE_B00277 1.Re-use existing 23G_DP_1.2M(MAC) x1 and add new OMT x1(if not available at site). 2.Install new XMC_3, Sub B_Lo x1. 3.Re-use existing RTN910AF(RTN03, NEID 33-28052) and use Slot 07 Port 2(for 2nd channel). 4.Build new HW MW Link 23G_2+0_55MHZ_512QAM_EPLA. 5.Re-use existing Vlan Services. 6.Migrate traffic 1001L into existing port at PTN/Cisco Router. | XMC_3 | MAC | 23G | existing 23G_DP_1.2M(MAC) x1 | existing 23G_DP_0.3M(MAC) x1 | GTSB | SQ202602230036-GTSB | GTSB | SQ202602230027-GTSB // SQ202602230033-GTSB | 2026-05-11 | 2026-05-06 | Completed | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-27 | 2026-03-13 | 2026-03-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-04 | 2026-05-11 | 2026-05-04 | 2026-05-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022319 |  | 2026-02-24 | 2026-02-26 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-05 | NOR HAZILA//BINTI HAMIDON/6799000245 | GTSB TI | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-05 | NOR HAZILA//BINTI HAMIDON/6799000245 | GTSB TI | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | SITI HAFIZAH BINTI NOH6237001145 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-09 | NOR HAZILA//BINTI HAMIDON/6799000245 | 2025-09-30: 2026-03-03; 2025-10-10: 2026-03-31; 2025-10-18: 2026-03-03; 2025-11-25: 2026-03-03 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601210792-GTSB
7626B_HU | Kg.Kubang (Celcom) | DU00006523397 | Sabah | Sabah | 4.414070 | 118.522150 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI+Dismantle |  | 18G_2+0_110M_512QAM_EPLA NE_7626B New 18G_1.2M(MDD)x1. Re-use existing RTN910AF(RTN03, NEID 9-29273). New XMC_5D Pro, Sub A_Lo x1. New IF cables with suitable length and type x2 RUN. FE_7976A New 18G_1.2M(MDD)x1. Re-use existing RTN910AF(RTN02, NEID 9-18383). New ISM8 x1. New XMC_5D Pro, Sub A_Hi x1. New IF cables with suitable length and type x2 RUN. | MW Swap | Existing HW MW Link 7626B-7976A, 18G_1+0_110MHZ_512QAM. MW Swap HW MW Link 7626B-7976A, 18G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link 7626B-7976A, 18G_1+0_110MHZ_512QAM include decom existing RTN910AF(RTN03, NEID 9-29274) at 7976A. Anyway, do not decom existing RTN910AF(RTN03, NEID 9-29273) at 7626B. Site Impacted : 7626B. NE_7626B. 1.Install new 18G_1.2M(MDD)x1. 2.Re-use existing RTN910AF(RTN03, NEID 9-29273). 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN from new ODU/Antenna to existing RTN910AF(RTN03, NEID 9-29273) slot 07 Port 1 & 2. Configure it. 4.Build new HW MW Link 7626B-7976A, 18G_2+0_110MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffics 7626B via new HW MW Link 7626B-7976A, 18G_2+0_110MHZ_512QAM_EPLA. 7.Later, decom existing HW MW Link 7626B-7976A, 18G_1+0_110MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN03, NEID 9-29273) at 7626B. FE_7976A. 1.Install new 18G_1.2M(MDD)x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-18383) and insert new ISM8 x1 into slot 04 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN from new ODU/Antenna to existing RTN910AF(RTN02, NEID 9-18383) slot 04 Port 1 & 2. Configure it. 4.Build new HW MW Link 7626B-7976A, 18G_2+0_110MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Re-use existing IBeam port. 7.Migrate traffics 7626B via existing IBeam port. 8.Later, decom existing HW MW Link 7626B-7976A, 18G_1+0_110MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN03, NEID 9-29273) at 7626B. | Existing HW MW Link 7626B-7976A, 18G_1+0_110MHZ_512QAM. MW Swap HW MW Link 7626B-7976A, 18G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link 7626B-7976A, 18G_1+0_110MHZ_512QAM include decom existing RTN910AF(RTN03, NEID 9-29274) at 7976A. Anyway, do not decom existing RTN910AF(RTN03, NEID 9-29273) at 7626B. Site Impacted : 7626B. NE_7626B. 1.Install new 18G_1.2M(MDD)x1. 2.Re-use existing RTN910AF(RTN03, NEID 9-29273). 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN from new ODU/Antenna to existing RTN910AF(RTN03, NEID 9-29273) slot 07 Port 1 & 2. Configure it. 4.Build new HW MW Link 7626B-7976A, 18G_2+0_110MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffics 7626B via new HW MW Link 7626B-7976A, 18G_2+0_110MHZ_512QAM_EPLA. 7.Later, decom existing HW MW Link 7626B-7976A, 18G_1+0_110MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN03, NEID 9-29273) at 7626B. | Existing HW MW Link 7626B-7976A, 18G_1+0_110MHZ_512QAM. MW Swap HW MW Link 7626B-7976A, 18G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link 7626B-7976A, 18G_1+0_110MHZ_512QAM include decom existing RTN910AF(RTN03, NEID 9-29274) at 7976A. Anyway, do not decom existing RTN910AF(RTN03, NEID 9-29273) at 7626B. Site Impacted : 7626B. FE_7976A. 1.Install new 18G_1.2M(MDD)x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-18383) and insert new ISM8 x1 into slot 04 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN from new ODU/Antenna to existing RTN910AF(RTN02, NEID 9-18383) slot 04 Port 1 & 2. Configure it. 4.Build new HW MW Link 7626B-7976A, 18G_2+0_110MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Re-use existing IBeam port. 7.Migrate traffics 7626B via existing IBeam port. 8.Later, decom existing HW MW Link 7626B-7976A, 18G_1+0_110MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN03, NEID 9-29273) at 7626B. | XMC_5D Pro | MDD | 18G | 18G_1.2M(MDD)x1 | 18G_1.2M(MDD)x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601210802-GTSB
4584A_HU_1 | BatuKurau | DU00006523398 | Northern | Kedah | 4.983135 | 100.798053 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_4+0_112M_512QAM_CA NE_4584A New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN05, NEID 9-36257). New ISM8 x2. New XMC_5D Pro, Sub A_Lo x1. FE_A00228 New 18G_0.6M(MDD) x1. New RTN910AF(RTN03). New ISM8 x1. New XMC_5D Pro, Sub A_Hi x1. New SFP Module 10G with 10Km 1310nm x2 or equivalent(For IDU HW RTN910AF and Cisco Router). New Optical Patch Cord cable x1 with suitable type and length. | MW New Link / Reroute | Existing xD Huawei MW Link 4584A(RTN02, NEID 9-30087)-4422A(RTN03, NEID 9-30086), 13G_4+0_28MHZ_EPLA. Install new HW MW Link 4584A-A00228, 18G_4+0_112MHZ_512QAM_CA. Later, decom existing xD Huawei MW Link 4584A(RTN02, NEID 9-30087)-4422A(RTN03, NEID 9-30086), 13G_4+0_28MHZ_EPLA. Site Impacted : 4572B & 4079K. NE_4584A 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN05, NEID 9-36257) and insert 2x new ISM8 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Build new HW MW Link 4584A-A00228, 18G_4+0_112MHZ_512QAM_CA. 5.Request new xC vlan dcn and vlan services. 6.Disconnect/remove existing cascading between port 8-EM6-1 of existing RTN910AF(RTN04, NEID 9-23522) and port 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-30087). 7.Migrate traffics 4572B & 4079K via new HW Link 4584A-A00228, 18G_4+0_112MHZ_512QAM_CA. 8.Later, decom existing xD Huawei MW Link 4584A(RTN02, NEID 9-30087)-4422A(RTN03, NEID 9-30086), 13G_4+0_28MHZ_EPLA. FE_A00228 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN03) x1. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Build new HW MW Link 4584A-A00228, 18G_4+0_112MHZ_512QAM_CA. 5.Request new xC Vlan dcn and Vlan services. 6.Request new x1 10G port at PTN/Cisco Router from ZTE IPRAN Team and insert new SFP Module 10G with 10Km 1310nm or equivalent. Configure and enable it. 7.Insert new SFP Module 10G with 10Km 1310nm or equivalent into port 8-EM6-3 of new RTN910A(RTN03). Configure and enable it. 8.Perform patching in between new x1 10G port at PTN/Cisco Router and port 8-EM6-3 of new RTN910A(RTN03). 9.Migrate traffics 4572B & 4079K into new 10G port PTN/Cisco Router. 10.Later, decom existing xD Huawei MW Link 4584A(RTN02, NEID 9-30087)-4422A(RTN03, NEID 9-30086), 13G_4+0_28MHZ_EPLA. | Existing xD Huawei MW Link 4584A(RTN02, NEID 9-30087)-4422A(RTN03, NEID 9-30086), 13G_4+0_28MHZ_EPLA. Install new HW MW Link 4584A-A00228, 18G_4+0_112MHZ_512QAM_CA. Later, decom existing xD Huawei MW Link 4584A(RTN02, NEID 9-30087)-4422A(RTN03, NEID 9-30086), 13G_4+0_28MHZ_EPLA. Site Impacted : 4572B & 4079K. NE_4584A 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN05, NEID 9-36257) and insert 2x new ISM8 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Build new HW MW Link 4584A-A00228, 18G_4+0_112MHZ_512QAM_CA. 5.Request new xC vlan dcn and vlan services. 6.Disconnect/remove existing cascading between port 8-EM6-1 of existing RTN910AF(RTN04, NEID 9-23522) and port 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-30087). 7.Migrate traffics 4572B & 4079K via new HW Link 4584A-A00228, 18G_4+0_112MHZ_512QAM_CA. 8.Later, decom existing xD Huawei MW Link 4584A(RTN02, NEID 9-30087)-4422A(RTN03, NEID 9-30086), 13G_4+0_28MHZ_EPLA. | Existing xD Huawei MW Link 4584A(RTN02, NEID 9-30087)-4422A(RTN03, NEID 9-30086), 13G_4+0_28MHZ_EPLA. Install new HW MW Link 4584A-A00228, 18G_4+0_112MHZ_512QAM_CA. Later, decom existing xD Huawei MW Link 4584A(RTN02, NEID 9-30087)-4422A(RTN03, NEID 9-30086), 13G_4+0_28MHZ_EPLA. Site Impacted : 4572B & 4079K. FE_A00228 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN03) x1. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Build new HW MW Link 4584A-A00228, 18G_4+0_112MHZ_512QAM_CA. 5.Request new xC Vlan dcn and Vlan services. 6.Request new x1 10G port at PTN/Cisco Router from ZTE IPRAN Team and insert new SFP Module 10G with 10Km 1310nm or equivalent. Configure and enable it. 7.Insert new SFP Module 10G with 10Km 1310nm or equivalent into port 8-EM6-3 of new RTN910A(RTN03). Configure and enable it. 8.Perform patching in between new x1 10G port at PTN/Cisco Router and port 8-EM6-3 of new RTN910A(RTN03). 9.Migrate traffics 4572B & 4079K into new 10G port PTN/Cisco Router. 10.Later, decom existing xD Huawei MW Link 4584A(RTN02, NEID 9-30087)-4422A(RTN03, NEID 9-30086), 13G_4+0_28MHZ_EPLA. | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | GTSB | SQ202601220776-GTSB | GTSB | SQ202601220771-GTSB // SQ202601220774-GTSB |  |  | Ongoing | [8 empty] | Unassigned | Not started |  | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-11 | 2026-05-04 | 2026-05-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-04 | 2026-05-11 | 2026-05-04 | 2026-05-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26012212 |  | 2026-01-23 | 2026-02-07 | Completed | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-02-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-28 | 2026-02-23 | 2026-03-05 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2026-02-23 | 2026-02-28 | 2026-02-23 | 2026-03-05 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-02 | 2026-02-23 | 2026-02-28 | 2026-02-23 | 2026-03-18 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | 2025-09-30: 2026-02-23; 2025-10-10: 2026-02-28; 2025-10-18: 2026-02-23; 2025-11-25: 2026-02-25 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601210796-GTSB
1859A_IPR | Midvalleycas | DU00006523399 | Central | Kuala Lumpur | 3.116830 | 101.676760 | [7 empty] | 05. Doable |  | TSS+TI | L1+ATP+PAC | 10G SFP 10km x2 Fiber patch Cord x 1 pairs | BBU Patching | Change patching BBU to ATN from 1G to 10G port (ops team and swap room to assign ATN and BBU port) Impact site: 1859A Existing SFP at ATN: 40km Existing SFP at BBU: 10km Propose to use: 1) 2x10G SFP 10km 2) IBEAM port GE0/2/3 | Change patching BBU to ATN from 1G to 10G port (ops team and swap room to assign ATN and BBU port) Impact site: 1859A Existing SFP at ATN: 40km Existing SFP at BBU: 10km Propose to use: 1) 2x10G SFP 10km 2) IBEAM port GE0/2/3 | [6 empty] | GCI | SQ202601210056-GCI | GCI | SQ202601210050-GCI | 2026-04-02 | 2026-04-02 | Completed | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26012055 |  | 2026-02-21 | 2026-01-22 | Completed | 2026-01-20 | 2026-02-21 | 2026-01-20 | 2026-01-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-26 | 2026-04-01 | 2026-03-25 | 2026-03-26 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-03-26 | 2026-04-01 | 2026-03-25 | 2026-03-27 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-03-26 | 2026-04-01 | 2026-03-25 | 2026-03-27 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-09-30: 2026-03-26; 2025-10-10: 2026-04-01; 2025-10-18: 2026-03-25; 2025-11-25: 2026-03-26 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601210773-GCI | 2026-01-20 | 2026-01-27 | 2026-01-20 | 2026-01-20 | CHEONG/SENG/WAH/7018000306
K00260_IPR | K012A_K00260OD_DUSUNPENGAPIT | DU00006523400 | Northern | Kedah | 5.896200 | 100.669200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | FE_K00260 New CAT6 cable with suitable length x1. | MW IDU Patching | Perform MW IDU Patching at NE K00260. Site Impacted : 4639B & K01052. NE_K00260. 1.Enable electrical LAN port 2 of existing xC SM IDU AGS 20(IP 10.127.142.51). 2.Request new electrical port at PTN/Cisco Router from ZTE IPRAN team. 3.Request new xC Vlan Services from ZTE IPRAN Team. 4.Perform new patching between LAN port 2 of existing xC SM IDU AGS 20(IP 10.127.142.51) and new electrical port at PTN/Cisco Router. 5.Migrate traffics(load balancing/split) 4639B & K01052 ONLY to new port at PTN/Cisco Router. | Perform MW IDU Patching at NE K00260. Site Impacted : 4639B & K01052. NE_K00260. 1.Enable electrical LAN port 2 of existing xC SM IDU AGS 20(IP 10.127.142.51). 2.Request new electrical port at PTN/Cisco Router from ZTE IPRAN team. 3.Request new xC Vlan Services from ZTE IPRAN Team. 4.Perform new patching between LAN port 2 of existing xC SM IDU AGS 20(IP 10.127.142.51) and new electrical port at PTN/Cisco Router. 5.Migrate traffics(load balancing/split) 4639B & K01052 ONLY to new port at PTN/Cisco Router. | [6 empty] | GTSB | SQ202601190558-GTSB | GTSB | SQ202601190547-GTSB | 2026-04-02 | 2026-03-30 | Completed | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-17 | 2026-03-24 | 2026-03-17 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26012007 |  | 2026-01-21 | 2026-01-22 | Completed | 2026-01-20 | 2026-01-21 | 2026-01-20 | 2026-01-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-09 | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-11 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-09-30: 2026-01-31; 2025-10-10: 2026-02-28; 2025-10-18: 2026-01-31; 2025-11-25: 2026-02-06 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601210796-GTSB
7396A_HU | Bkt.Karakit | DU00006523401 | Sabah | Sabah | 7.119932 | 117.085104 | [7 empty] | 05. Doable |  | TSS+TI |  | ETN Cat 6 cable x1 | BBU Patching | Patching 7396A BBU to xC SM MW link 7GHz 4+0 , S00576 - S00133 (SB02487). | Patching 7396A BBU to xC SM MW link 7GHz 4+0 , S00576 - S00133 (SB02487). | [12 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601210780-GCI
7228B_LOS | Taman Andamas | DU00006547699 | Sabah | Sabah | 5.939510 | 116.095980 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+MRCF+PAC | 23G_1+0_112M. NE_7228B 23G_SP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub B_Lo x1. FE_7041A. 23G_SP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub B_Hi x1. | MW New Link / Reroute | Link reroute to new FE 7041A due to existing LOS Block. Install new link 23G_1+0_112M. Site Impacted : 7228B. NE_7228B 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Lo. 4.Create service cross connect. 5.Traffic migrate to new link and New FE routing. 6.Decom existing MW link. FE_7041A. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect. 5.Enable GE1 , ETH patching to existing 7041A_RTN01_GE1. 6.Traffic migrate to new link and New FE routing. 7.Decomm existing ODU and ANT only. | Link reroute to new FE 7041A due to existing LOS Block. Install new link 23G_1+0_112M. Site Impacted : 7228B. NE_7228B 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Lo. 4.Create service cross connect. 5.Traffic migrate to new link and New FE routing. 6.Decom existing MW link. | Link reroute to new FE 7041A due to existing LOS Block. Install new link 23G_1+0_112M. Site Impacted : 7228B. FE_7041A. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect. 5.Enable GE1 , ETH patching to existing 7041A_RTN01_GE1. 6.Traffic migrate to new link and New FE routing. 7.Decomm existing ODU and ANT only. | XMC_3E | MAC | 23G | 0.6 | 0.6 | NR services | SQ202603100206-NR Services | NR services | SQ202603030374-NR Services // SQ202603030376-NR Services |  |  | Ongoing | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26021226 |  | 2026-02-13 | 2026-03-10 | Completed | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-03-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-01 | 2026-04-01 | 2026-03-01 | 2026-03-10 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-03-01 | 2026-04-01 | 2026-03-01 | 2026-03-10 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-08 | 2026-03-01 | 2026-04-01 | 2026-03-01 | 2026-03-14 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2026-03-01 | 2026-04-01 | 2026-03-01 | 2026-03-02 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202602120118-GCI | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | CHEONG/SENG/WAH/7018000306
4947A_AD | Kota Kuala Muda | DU00006674885 | Northern | Kedah | 5.589331 | 100.373029 | [7 empty] | 05. Doable |  | TSS+TI | L1+ATP+PAC | NE_4947A New CAT6 cable x1.(Re-use existing or If required may use new) NE_4566C/P00117 New CAT6 cable x1.(Re-use existing or If required may use new) | BBU Patching | Perform reengineering at 4947A & 4566C(fallback). Site Impacted :4947A. NE_4947A 1.Currently, traffic 4947A backhauling via existing xD HW MW Link 4947A(RTN06, NEID 9-36222)-4272A(RTN12, NEID 9-36223), 15G_4+0_28MHZ_256QAM_XPIC_EPLA. 2.Disconnect/remove config/disable existing patching existing BBU 4947A from port 8-EM6-2 of RTN910AF(RTN06, NEID 9-36222). 2.Enable port 7-EM10-3 of RTN905(RTN01, NEID 190-45693) and perform patching from this port to existing BBU 4947A. 3.Re-use existing Vlan Services. 4.Migrate traffic 4947A back to existing xC HW MW Link 4947A(RTN01, NEID 190-45693)-4566C(RTN03, NEID 190-45695), 18G_2+0_112MHZ_2048QAM_EPLA. CURRENT FE_4272A/P00262 1.Remove config at RTN910AF(RTN12, NEID 9-36223). 2.Also, remove config at Cisco/PTN(PTN ID PTN 63278-PERMATANG_BERA2 GigabitEthernet0/0/9). 3.No need to go to 4272A/P00262. NEW FE_4566C/P00117 1.Enable port 7-EM10-5 of existing RTN905(RTN03, NEID 190-45695). 2.Enable port GE0/0/13 of PTN/Cisco PTN ID 63233-PMTGBENDAHARI. 3.Patching port 7-EM10-5 of existing RTN905(RTN03, NEID 190-45695) to port GE0/0/13 of PTN/Cisco PTN ID 63233-PMTGBENDAHARI. 4.Re-use existing Vlan Services. 5.Migrate traffic 4947A back to port GE0/0/13 of PTN/Cisco PTN ID 63233-PMTGBENDAHARI. | Perform reengineering at 4947A & 4566C(fallback). Site Impacted :4947A. NE_4947A 1.Currently, traffic 4947A backhauling via existing xD HW MW Link 4947A(RTN06, NEID 9-36222)-4272A(RTN12, NEID 9-36223), 15G_4+0_28MHZ_256QAM_XPIC_EPLA. 2.Disconnect/remove config/disable existing patching existing BBU 4947A from port 8-EM6-2 of RTN910AF(RTN06, NEID 9-36222). 2.Enable port 7-EM10-3 of RTN905(RTN01, NEID 190-45693) and perform patching from this port to existing BBU 4947A. 3.Re-use existing Vlan Services. 4.Migrate traffic 4947A back to existing xC HW MW Link 4947A(RTN01, NEID 190-45693)-4566C(RTN03, NEID 190-45695), 18G_2+0_112MHZ_2048QAM_EPLA. | Perform reengineering at 4947A & 4566C(fallback). Site Impacted :4947A. CURRENT FE_4272A/P00262 1.Remove config at RTN910AF(RTN12, NEID 9-36223). 2.Also, remove config at Cisco/PTN(PTN ID PTN 63278-PERMATANG_BERA2 GigabitEthernet0/0/9). 3.No need to go to 4272A/P00262. NEW FE_4566C/P00117 1.Enable port 7-EM10-5 of existing RTN905(RTN03, NEID 190-45695). 2.Enable port GE0/0/13 of PTN/Cisco PTN ID 63233-PMTGBENDAHARI. 3.Patching port 7-EM10-5 of existing RTN905(RTN03, NEID 190-45695) to port GE0/0/13 of PTN/Cisco PTN ID 63233-PMTGBENDAHARI. 4.Re-use existing Vlan Services. 5.Migrate traffic 4947A back to port GE0/0/13 of PTN/Cisco PTN ID 63233-PMTGBENDAHARI. | [5 empty] | GCI | SQ202603180478-GCI | GCI | SQ202603180473-GCI |  |  | Ongoing | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-30 | 2026-05-07 | 2026-04-30 | 2026-05-01 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26031714 |  | 2026-04-30 | 2026-04-20 | Completed | 2026-04-20 | 2026-04-30 | 2026-04-20 | 2026-04-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-16 | 2026-04-04 | 2026-03-16 | 2026-04-20 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-03-16 | 2026-04-04 | 2026-03-16 | 2026-04-20 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-18 | 2026-03-16 | 2026-04-04 | 2026-03-16 | 2026-04-20 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-09-30: 2026-03-16; 2025-10-10: 2026-04-04; 2025-10-18: 2026-03-16; 2025-11-25: 2026-03-16 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202603170130-GTSB
4372D_AD | East BKIP | DU00006687114 | Northern | Penang | 5.231869 | 100.459667 | [9 empty] | TSS+AA+TI |  | 15G_4+0_28M. NE_4372D. 15G_DP_0.6M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Hi x1. FE_4116B 15G_DP_0.6M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Lo x1. | MW Swap | Link reroute to new FE 4116B due to existing link LOS Block. Link Config 15G_4+0_28M. Site Impacted : 4372D , 4399E. NE_4372D. 1.Install new 15G_DP_0.6M(MDD). 2.Install new RTN910A , 3_ISM8-2+0 and 4_ISM8-2+0. 3.Install new 3_ISM8 & 4_ISM8. 4.Install new XMC_5D , Sub A_Hi. 5.Enable GE1 , 4372D_BBU 6.Enable GE2 , NLOS 4399E. 7.Create service cross connect , CA and EPLA. 8.Traffic migrate to new link and new FE routing. 9.Decom existing MW link. FE_4116B 1.Install new 15G_DP_0.6M(MDD). 2.Reuse existing 4116B_RTN04 (ID : 30283). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Migrate traffic to new link and new FE routing. 7.Decom existing MW link. | Link reroute to new FE 4116B due to existing link LOS Block. Link Config 15G_4+0_28M. Site Impacted : 4372D , 4399E. NE_4372D. 1.Install new 15G_DP_0.6M(MDD). 2.Install new RTN910A , 3_ISM8-2+0 and 4_ISM8-2+0. 3.Install new 3_ISM8 & 4_ISM8. 4.Install new XMC_5D , Sub A_Hi. 5.Enable GE1 , 4372D_BBU 6.Enable GE2 , NLOS 4399E. 7.Create service cross connect , CA and EPLA. 8.Traffic migrate to new link and new FE routing. 9.Decom existing MW link. | Link reroute to new FE 4116B due to existing link LOS Block. Link Config 15G_4+0_28M. Site Impacted : 4372D , 4399E. FE_4116B 1.Install new 15G_DP_0.6M(MDD). 2.Reuse existing 4116B_RTN04 (ID : 30283). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Migrate traffic to new link and new FE routing. 7.Decom existing MW link. | XMC_5D | MDD | 15G | 1.2 | 1.2 | GCI | SQ202604280648-GCI | GCI | SQ202605070533-GCI // SQ202605070538-GCI |  |  | Ongoing | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050104 |  | 2026-05-04 | 2026-05-05 | Completed | 2026-05-01 | 2026-05-04 | 2026-05-01 | 2026-05-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-07 | 2026-05-31 | 2026-05-07 |  | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2026-05-07 | 2026-05-31 | 2026-05-07 |  | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | [7 empty] | 2026-05-07 | 2026-05-31 | 2026-05-07 |  | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2025-09-30: 2026-05-07; 2025-10-10: 2026-05-31; 2025-10-18: 2026-05-07; 2025-11-25: 2026-05-07 | [7 empty] | GCI | SQ202603270331-GCI | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | CHEONG/SENG/WAH/7018000306
9030K_HU | Q118B_Q01114OD_SGSEMANOK | DU00005862742 | Sarawak | Sarawak | 3.099911 | 112.916100 | [6 empty] | ZTE | 06. Other Issue | 27/10 - NE done, FE site padlock faulty (TSS) | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M NE_9030K New ISM8 x1. FE_9025X New ISM8 x1. | MW Hardware Upgrade | Link Existing HW 15G_4+0_28M_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 15G_4+0_28M_512QAM_EPLA become HW 15G_6+0_28M_512QAM_CA. Site Impacted : 9030K, 9010K & 9008K. NE_9030K 1.Insert new ISM8 card into slot 04 of existing RTN910A(RTN01). 2.Shifting existing 1 of IF cable from existing ISM8 slot 03 Port 2 into new ISM8 slot 04 of Port 1. Configure it. 3.Configure HW 15G_6+0_28M_512QAM_CA for new channels( 2x Channels) and existing channels(4x Channels). Total new capacity will be 1344Mbps. FE_9025X 1.Insert new ISM8 card into slot 04 of existing RTN910A(RTN01). 2.Shifting existing 1 of IF cable from existing ISM8 slot 03 Port 2 into new ISM8 slot 04 of Port 1. Configure it. 3.Configure HW 15G_6+0_28M_512QAM_CA for new channels( 2x Channels) and existing channels(4x Channels). Total new capacity will be 1344Mbps. | Link Existing HW 15G_4+0_28M_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 15G_4+0_28M_512QAM_EPLA become HW 15G_6+0_28M_512QAM_CA. Site Impacted : 9030K, 9010K & 9008K. NE_9030K 1.Insert new ISM8 card into slot 04 of existing RTN910A(RTN01). 2.Shifting existing 1 of IF cable from existing ISM8 slot 03 Port 2 into new ISM8 slot 04 of Port 1. Configure it. 3.Configure HW 15G_6+0_28M_512QAM_CA for new channels( 2x Channels) and existing channels(4x Channels). Total new capacity will be 1344Mbps. | Link Existing HW 15G_4+0_28M_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 15G_4+0_28M_512QAM_EPLA become HW 15G_6+0_28M_512QAM_CA. Site Impacted : 9030K, 9010K & 9008K. FE_9025X 1.Insert new ISM8 card into slot 04 of existing RTN910A(RTN01). 2.Shifting existing 1 of IF cable from existing ISM8 slot 03 Port 2 into new ISM8 slot 04 of Port 1. Configure it. 3.Configure HW 15G_6+0_28M_512QAM_CA for new channels( 2x Channels) and existing channels(4x Channels). Total new capacity will be 1344Mbps. | XMC_5D | MDD | 15G | Reuse Existing 15G_1.2M(MDD) | Reuse Existing 15G_1.2M(MDD) | Magicell | SQ202509030212-Magicell | iEzzpro | SQ202603170061-Iezzpro // SQ202603170066-Iezzpro | 2026-01-28 | 2026-02-03 | Completed | 2025-09-03 | 2025-09-30 | 2025-12-01 | 2025-12-01 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-02-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102417 |  | 2025-10-25 | 2025-10-25 | Completed | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-17 | 2026-04-17 | 2026-03-17 | 2026-03-17 | Kevin//Tan/6000033214 | Iezzpro TI | 2026-03-17 | 2026-04-17 | 2026-03-17 | 2026-03-26 | Hairil Nizam//Maliki/6000033206 | Iezzpro TI | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-20 | 2026-03-17 | 2026-04-17 | 2026-03-17 | 2026-03-31 | Hairil Nizam//Maliki/6000033206 | 2025-09-30: 2026-03-17; 2025-10-10: 2026-04-17; 2025-10-18: 2026-03-17; 2025-11-25: 2026-03-17 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507250636-GTSB
7489B_HU | Simp. Kertam | DU00005862743 | Sabah | Sabah | 5.431111 | 118.270410 | [7 empty] | 08. Pending RFS |  | TSS+AA+TI |  | 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1 NE_7489B New 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. New RTN910AF(RTN01). New ISM8 x1. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type 4x RUN. New CAT6 cable x1. FE_7585A New 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. New RTN910AF(RTN02). New ISM8 x1. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type 4x RUN. New CAT6 cable x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE FOR MOUNTING 1.2M ANTENNA DISH SIZE. 2.NEED TO PERFORM DU IN SEQUENCES - 1ST 7489B_HU(LINK 1) - 2ND 7489B_HU_1(LINK 2)**** Build new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1. Later, will combine new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1 and new HW MW Parallel Link 7489B-7585A, 15G_2+0_28M_256QAM_EPLA - LINK 2 become HW MW Parallel Link 7489B-7585A, 15G_6+0_28M_256QAM_EPLA. Site Impacted : 7732B & 7493B. NE_7489B 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF(RTN01) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1. 4.Disable port 8-EM6-1 of existing RTN910AF(RTN07, NEID 9-43789). Check for confirm physical CAT6 cable cascading before disconnect. 5.Disable port 8-EM6-2 of existing RTN910AF(RTN06, NEID 9-43809). Check for confirm physical CAT6 cable cascading before disconnect. 6.Disconnect/remove existing cascading between port 8-EM6-1 of existing RTN910AF(RTN07, NEID 9-43789) and port 8-EM6-2 of existing RTN910AF(RTN06, NEID 9-43809). 7.Enable port 8-EM6-2 of new RTN910AF(RTN01). 8.Perform new cascading between port 8-EM6-2 of new RTN910AF(RTN01) and port 8-EM6-1 of existing RTN910AF(RTN07, NEID 9-43789). 9.Request new xD Vlan DCN and Vlan services. 10.Migrate traffics 7732B & 7493B via new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1. FE_7585A 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF(RTN02) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Request new 1G Electrical port at IBeam. 6.Request new xD Vlan DCN and Vlan services. 7.Migrate traffics 7732B & 7493B via new 1G Electrical port at IBeam. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE FOR MOUNTING 1.2M ANTENNA DISH SIZE. 2.NEED TO PERFORM DU IN SEQUENCES - 1ST 7489B_HU(LINK 1) - 2ND 7489B_HU_1(LINK 2)**** Build new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1. Site Impacted : 7732B & 7493B. NE_7489B 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF(RTN01) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1. 4.Disable port 8-EM6-1 of existing RTN910AF(RTN07, NEID 9-43789). Check for confirm physical CAT6 cable cascading before disconnect. 5.Disable port 8-EM6-2 of existing RTN910AF(RTN06, NEID 9-43809). Check for confirm physical CAT6 cable cascading before disconnect. 6.Disconnect/remove existing cascading between port 8-EM6-1 of existing RTN910AF(RTN07, NEID 9-43789) and port 8-EM6-2 of existing RTN910AF(RTN06, NEID 9-43809). 7.Enable port 8-EM6-2 of new RTN910AF(RTN01). 8.Perform new cascading between port 8-EM6-2 of new RTN910AF(RTN01) and port 8-EM6-1 of existing RTN910AF(RTN07, NEID 9-43789). 9.Request new xD Vlan DCN and Vlan services. 10.Migrate traffics 7732B & 7493B via new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE FOR MOUNTING 1.2M ANTENNA DISH SIZE. 2.NEED TO PERFORM DU IN SEQUENCES - 1ST 7489B_HU(LINK 1) - 2ND 7489B_HU_1(LINK 2)**** Build new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1. Site Impacted : 7732B & 7493B. FE_7585A 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF(RTN02) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel Link 7489B-7585A, 15G_4+0_28M_256QAM_EPLA(without CA) - LINK 1. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Request new 1G Electrical port at IBeam. 6.Request new xD Vlan DCN and Vlan services. 7.Migrate traffics 7732B & 7493B via new 1G Electrical port at IBeam. | XMC-5D Pro | MDD | 15G | 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. | 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. | NR services | SQ202605070552-NR Services | NR services | SQ202604290773-NR Services // SQ202604290787-NR Services |  |  | Ongoing | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25090205 |  | 2025-09-03 | 2025-09-03 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-03 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-05-29 | 2026-04-29 |  | MUHAMMAD ISMAIL BIN ADAM SHAH7167000034 | NR Service TI | 2026-04-29 | 2026-05-29 | 2026-04-29 |  | MUHAMMAD ISMAIL BIN ADAM SHAH7167000034 | NR Service TI | [7 empty] | 2026-04-29 | 2026-05-29 | 2026-04-29 |  | MUHAMMAD ISMAIL BIN ADAM SHAH7167000034 | 2025-09-30: 2026-04-29; 2025-10-10: 2026-05-29; 2025-10-18: 2026-04-29; 2025-11-25: 2026-04-29 | [7 empty] | GTSB | SQ202507250629-GTSB
9127B_HU | Samalaju-Tokuyama | DU00005862744 | Sarawak | Sarawak | 3.539772 | 113.314212 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M_256QAM NE_9127B New 18G_0.6M(MDD) x1. New RTN910A x1. New XMC_5D, Sub B_Lo x1. FE_9363B New 18G_0.6M(MDD) x1. New RTN910A x1. New XMC_5D, Sub B_Hi x1. New CAT6 cable x1. | MW New Link / Reroute | Build MW New Link/Reroute ,HW MW Link 9127B-9363B 18G_1+0_112MHz_256QAM. Later, may decom existing HW MW Link 9127B-9363B/Q00704 18G_1+0_55MHZ_512QAM. May decom IDU, ODU & Antenna at 9127B but do not decom IDU at 9363B, ONLY decom ODU & Antenna. This is due to IDU already shared with other traffic(9834B). Site Impacted : 9127B. NE_9127B 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_5D, Sub B_Lo x1. Configure HW MW Link 18G_1+0_112M_256QAM. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN02). Configure it. 6.Request new xD Vlan DCN and Vlan Services. 7.Migrate traffics to new link. 8.Later, may decom(IDU, ODU & Antenna) existing HW MW Link 9127B-9363B/Q00704 18G_1+0_55MHZ_512QAM. FE_9363B 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN09) x1. 3.Install new XMC_5D, Sub B_Hi x1. Configure HW MW Link 18G_1+0_112M_256QAM. 4.Enable port 8-EM6-1 of new RTN910A(RTN09). 5.Request new xD Vlan DCN, Vlan Services and new IBeam port. 6.Patching port 8-EM6-1 of new RTN910A(RTN09) to new IBeam port. Configure it. 7.Migrate traffics to new IBeam port. 8.Later, may decom(ODU & Antenna ONLY) existing HW MW Link 9127B-9363B/Q00704 18G_1+0_55MHZ_512QAM. Anyway do not decom existing IDU due to IDU already shared with existing traffic 9834B. | Build MW New Link/Reroute ,HW MW Link 9127B-9363B 18G_1+0_112MHz_256QAM. Later, may decom existing HW MW Link 9127B-9363B/Q00704 18G_1+0_55MHZ_512QAM. May decom IDU, ODU & Antenna at 9127B but do not decom IDU at 9363B, ONLY decom ODU & Antenna. This is due to IDU already shared with other traffic(9834B). Site Impacted : 9127B. NE_9127B 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_5D, Sub B_Lo x1. Configure HW MW Link 18G_1+0_112M_256QAM. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN02). Configure it. 6.Request new xD Vlan DCN and Vlan Services. 7.Migrate traffics to new link. 8.Later, may decom(IDU, ODU & Antenna) existing HW MW Link 9127B-9363B/Q00704 18G_1+0_55MHZ_512QAM. | Build MW New Link/Reroute ,HW MW Link 9127B-9363B 18G_1+0_112MHz_256QAM. Later, may decom existing HW MW Link 9127B-9363B/Q00704 18G_1+0_55MHZ_512QAM. May decom IDU, ODU & Antenna at 9127B but do not decom IDU at 9363B, ONLY decom ODU & Antenna. This is due to IDU already shared with other traffic(9834B). Site Impacted : 9127B. FE_9363B 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN09) x1. 3.Install new XMC_5D, Sub B_Hi x1. Configure HW MW Link 18G_1+0_112M_256QAM. 4.Enable port 8-EM6-1 of new RTN910A(RTN09). 5.Request new xD Vlan DCN, Vlan Services and new IBeam port. 6.Patching port 8-EM6-1 of new RTN910A(RTN09) to new IBeam port. Configure it. 7.Migrate traffics to new IBeam port. 8.Later, may decom(ODU & Antenna ONLY) existing HW MW Link 9127B-9363B/Q00704 18G_1+0_55MHZ_512QAM. Anyway do not decom existing IDU due to IDU already shared with existing traffic 9834B. | XMC-5D_SB B | MDD | 18 | 0.6 | 0.6 | Trintel | SQ202509040637-Trintel | Trintel | SQ202509040608-Trintel // SQ202509040617-Trintel | 2025-09-17 | 2025-09-17 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-09 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-10 | 2025-09-12 | 2025-09-10 | 2025-09-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-10 | 2025-09-12 | 2025-09-10 | 2025-09-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102415 |  | 2025-10-25 | 2025-11-06 | Completed | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-11-06 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-10 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-13 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-13 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-22 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2025-09-30: 2025-11-08; 2025-10-10: 2025-11-15; 2025-10-18: 2025-11-08; 2025-11-25: 2025-11-10 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507250636-GTSB | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | HSU//MYET CHAE/6799000011
1164C_HU | Taman Bukit Subang | DU00005862745 | Central | Selangor | 3.172230 | 101.514445 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 1164C-1365B 23G_1+0_0.6M/0.6M_SP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_SP_112MHZ_1024QAM IMPACTED SITE: 1164C, 2777B | MW REMOTE UPGRADE LINK 1164C-1365B 23G_1+0_0.6M/0.6M_SP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_SP_112MHZ_1024QAM IMPACTED SITE: 1164C, 2777B | MW REMOTE UPGRADE LINK 1164C-1365B 23G_1+0_0.6M/0.6M_SP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_SP_112MHZ_1024QAM IMPACTED SITE: 1164C, 2777B | XMC3 | MAC | 23G | 0.6 | 0.6 | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-25 | [15 empty] | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507250548-GCI | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
4393A_HU | Tg Piandang RDD | DU00005862746 | Northern | Perak | 5.066460 | 100.382480 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M NE_4393A 13G_DP_1.8M(MDD) x1. ISM8 x2. XMC_5D , Sub B_Lo x1 FE_4141R 13G_DP_1.8M(MDD). x1. ISM8 x2. XMC_5D , Sub B_Hi x1. ETH LAN Cable x2. | MW Swap | Existing link 13G_4+0_28M (4393A - 4396A) Link reroute to FE 4141R with swap existing link to 13G_6+0_28M. Create 2nd DU ID for 2nd ant and upgrade uplink to new parallel link 18G_2+0. Link Config 13G_4+0_28M (CA) with refer DU ID 4393A_HU_1 (DU Code : DU00005895482) to EPLA with 13G_2+0_28M (NCA) for complete 13G_6+0_28M full configuration. TSS for FE reroute to 4141R is required. Install Uplink 4141R-4396A is priority. Site Impacted : 4393A NE_4393A 1.Install new 13G_DP_1.8M(MDD) x1. 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub B_Lo for ant 1 with CA. 4.Create service cross connect , CA and EPLA to become 13G_6+0_28M. 5.Enable GE1 , migrate BBU_4393A traffic to new link and new FE routing. 6.Decom existing ODU , ANT and IDU.(4393A-4396A/A00216). FE_4141R 1.Install new 13G_DP_1.8M(MDD). x1. 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A.(RTN no provide by OPS team). 3.Install new XMC_5D , Sub B_Hi for ant 1 with CA. 4.Create service cross connect , CA and EPLA to become 13G_6+0_28M. 5.Enable GE1 , ETH patching to existing 4141R_RTN02_GE1 (ID : 13787). 6.Traffic migrate to new link and new FE route. 7.Decom existing IDU , ODU and ANT.(4396A/A00216-4393A). | Existing link 13G_4+0_28M (4393A - 4396A). Link reroute to FE 4141R with swap existing link to 13G_6+0_28M. Create 2nd DU ID for 2nd ant (4393A_HU_1) and upgrade uplink to new parallel link 18G_2+0 (4141R_AD). Link Config 13G_4+0_28M (CA) with refer DU ID 4393A_HU_1 (DU Code : DU00005895482) EPLA with 13G_2+0_28M (NCA) to complete 13G_6+0_28M full configuration. TSS for FE reroute to 4141R is required. Install Uplink 4141R-4396A is priority. Site Impacted : 4393A. NE_4393A 1.Install new 13G_DP_1.8M(MDD) x1. 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub B_Lo for ant 1 with CA. 4.Create service cross connect , CA and EPLA to become 13G_6+0_28M. 5.Enable GE1 , migrate BBU_4393A traffic to new link and new FE routing. 6.Decom existing ODU , ANT and IDU.(4393A-4396A/A00216). | Existing link 13G_4+0_28M (4393A - 4396A). Link reroute to FE 4141R with swap existing link to 13G_6+0_28M. Create 2nd DU ID for 2nd ant (4383A_HU_1) and upgrade uplink to new parallel link 18G_2+0 (4141R_AD). Link Config 13G_4+0_28M(CA) with refer DU ID 4393A_HU_1 (DU Code : DU00005895482) EPLA with 13G_2+0_28M (NCA) to complete 13G_6+0_28M full configuration. TSS for FE reroute to 4141R is required. Install Uplink 4141R-4396A is priority. Site Impacted : 4393A FE_4141R 1.Install new 13G_DP_1.8M(MDD). x1. 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A.(RTN no provide by OPS team). 3.Install new XMC_5D , Sub B_Hi for ant 1 with CA. 4.Create service cross connect , CA and EPLA to become 13G_6+0_28M. 5.Enable GE1 , ETH patching to existing 4141R_RTN02_GE1 (ID : 13787). 6.Traffic migrate to new link and new FE route. 7.Decom existing IDU , ODU and ANT.(4396A/A00216-4393A). | XMC_5D | MDD | 13G | 1.8 | 1.8 | GCI | SQ202511110794-GCI | GCI | SQ202508270947-GCI // SQ202508270956-GCI | 2025-11-13 | 2025-11-13 | Completed | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250821AH |  | 2025-08-22 | 2025-08-23 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-09-08 | 2025-08-25 | 2025-08-30 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-08-25 | 2025-09-08 | 2025-08-25 | 2025-08-30 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-15 | 2025-08-25 | 2025-09-08 | 2025-08-25 | 2026-03-31 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-09-30: 2025-08-25; 2025-10-10: 2025-09-08; 2025-10-18: 2025-08-25 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507250560-GCI | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | CHEONG/SENG/WAH/7018000306
4177K_HU | MERBOK | DU00005862747 | Northern | Kedah | 5.710797 | 100.415296 | [7 empty] | 00. Integrated/RFS Done | 26/8: got bee hive | TSS+AA+TI | L1+ATP+PAC | 2X 15G 1.2M MS ANTENNA 2x ODU 15G XMC3 SUB B HI 2X ODU 15G XMC3 SUB B LO | MW Parallel Link | MW PARALLEL UPGRADE 4177K/K00017-K00109 WITH HUAWEI_15G_2+0_1.2M/1.2M_DP_28MHZ_512QAM_448MBPS_XMC3_SUB_B_6.95KM IMPACTED: K00836,K00837 | 1. REUSE EXISTING RTN910 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM AT SLOT 7 5. EPLA NEW LINK WITH EXISTING 13G 4+0 | 1. REUSE EXISTING RTN910 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM AT SLOT 7 5. EPLA NEW LINK WITH EXISTING 13G 4+0 | XMC3 | MAC | 15G | 1.2 | 1.2 | GCI | SQ202507310866-GCI | GCI | SQ202507310847-GCI // SQ202507310853-GCI | 2025-09-18 | 2025-09-19 | Completed | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-24 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081277 |  | 2025-08-16 | 2025-08-14 | Completed | 2025-08-15 | 2025-08-16 | 2025-08-12 | 2025-08-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-24 | 2025-09-07 | 2025-08-24 | 2025-09-17 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2025-08-24 | 2025-09-07 | 2025-08-24 | 2025-09-12 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-08-24 | 2025-09-07 | 2025-08-24 | 2025-10-28 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | 2025-09-30: 2025-08-24; 2025-10-10: 2025-09-07; 2025-10-18: 2025-08-24; 2025-11-25: 2025-10-27 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507250560-GCI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
3186B7_EVT | PBTS JELAJAH KARNIVAL KPDN | DU00005862748 | Sabah | Sabah | 5.990940 | 116.686610 | [13 empty] | Planning and integration support only for event site 3186B7 Tx route: 3186B7-S00140 1) New port at S00140 PTN 20066-TANAHMERAHRANAU 2) New DCN IP S00140 RTN03 3) New DCN VLAN S00140 RTN03 4) New NE ID FE IDU S00140 RTN03 5) New NE ID NE IDU 3186B7 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
7341B_HU | Indarason (Celcom) | DU00005862749 | Sabah | Sabah | 6.792560 | 116.661423 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M_512QAM_CA NE_7341B New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 9-43867) and re-use existing ISM8 slot 03. New ISM8 x1.(for slot 04) New XMC_5D, Sub B_Lo x1. FE_7019A New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 9-43866) and re-use existing ISM8 slot 03. New ISM8 x1.(for slot 04) New XMC_5D, Sub B_Hi x1. | MW Swap | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Existing HW MW Link 7341B-7019A, 13G&15G_3+0_28MHZ_512QAM_EPLA. Swap existing HW MW Link 15G_1+0_28MHZ_512QAM with new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. Later, combine existing HW MW Link 7341B-7019A, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Decom Antenna 15G and ODU 15G under existing HW MW Link 15G_1+0_28MHZ_512QAM. Anyway, do not decom existing RTN910AF at NE & FE. Site Impacted : 7034B. NE_7341B 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43867) and re-use existing ISM8 slot 03. 3.Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN02, NEID 9-43867). 4.Install new XMC_5D, Sub A_Lo x2. Build new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. 5.Perform cascading between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-43867) and port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-36093). 6.Re-use existing xD vlan dcn and vlan services. 7.Migrate traffics 7034B via new HW MW Link 13G&15G_6+0_28MHZ_512QAM_EPLA. 8.Later, combine existing HW MW Link 7341B-7019A, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. 9.Decom Antenna 15G and ODU 15G under existing HW MW Link 15G_1+0_28MHZ_512QAM. FE_7019A 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43866) and re-use existing ISM8 slot 03. 3.Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN02, NEID 9-43866). 4.Install new XMC_5D, Sub A_Hi x2. Build new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. 5.Re-use existing xD vlan dcn and vlan services. 6.Migrate traffics 7034B via existing port of IBeam at CP(7000A). 7.Later, combine existing HW MW Link 7341B-7019A, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. 8.Decom Antenna 15G and ODU 15G under existing HW MW Link 15G_1+0_28MHZ_512QAM. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Existing HW MW Link 7341B-7019A, 13G&15G_3+0_28MHZ_512QAM_EPLA. Swap existing HW MW Link 15G_1+0_28MHZ_512QAM with new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. Later, combine existing HW MW Link 7341B-7019A, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Decom Antenna 15G and ODU 15G under existing HW MW Link 15G_1+0_28MHZ_512QAM. Anyway, do not decom existing RTN910AF at NE & FE. Site Impacted : 7034B. NE_7341B 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43867) and re-use existing ISM8 slot 03. 3.Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN02, NEID 9-43867). 4.Install new XMC_5D, Sub A_Lo x2. Build new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. 5.Perform cascading between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-43867) and port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-36093). 6.Re-use existing xD vlan dcn and vlan services. 7.Migrate traffics 7034B via new HW MW Link 13G&15G_6+0_28MHZ_512QAM_EPLA. 8.Later, combine existing HW MW Link 7341B-7019A, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. 9.Decom Antenna 15G and ODU 15G under existing HW MW Link 15G_1+0_28MHZ_512QAM. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Existing HW MW Link 7341B-7019A, 13G&15G_3+0_28MHZ_512QAM_EPLA. Swap existing HW MW Link 15G_1+0_28MHZ_512QAM with new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. Later, combine existing HW MW Link 7341B-7019A, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Decom Antenna 15G and ODU 15G under existing HW MW Link 15G_1+0_28MHZ_512QAM. Anyway, do not decom existing RTN910AF at NE & FE. Site Impacted : 7034B. FE_7019A 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43866) and re-use existing ISM8 slot 03. 3.Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN02, NEID 9-43866). 4.Install new XMC_5D, Sub A_Hi x2. Build new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. 5.Re-use existing xD vlan dcn and vlan services. 6.Migrate traffics 7034B via existing port of IBeam at CP(7000A). 7.Later, combine existing HW MW Link 7341B-7019A, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7341B-7019A, 15G_4+0_28MHZ_512QAM_CA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. 8.Decom Antenna 15G and ODU 15G under existing HW MW Link 15G_1+0_28MHZ_512QAM. | XMC-5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | NR services | SQ202604100662-NR Services | NR services | SQ202604060625-NR Services // SQ202604060627-NR Services |  |  | Ongoing | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031154 |  | 2026-03-12 | 2026-03-18 | Completed | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-18 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-06 | 2026-05-06 | 2026-04-06 | 2026-04-07 | RANA//WAQAS/6000006187 | NR Service TI | 2026-04-06 | 2026-05-06 | 2026-04-06 | 2026-04-21 | RANA//WAQAS/6000006187 | NR Service TI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-09 | 2026-04-06 | 2026-05-06 | 2026-04-06 | 2026-04-21 | RANA//WAQAS/6000006187 | 2026-04-06 | 2026-05-06 | 2026-04-06 | 2026-04-07 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | [5 empty] | GTSB | SQ202507250629-GTSB
7365B_HU_3 | Richard Lind Tower SBC | DU00005862750 | Sabah | Sabah | 5.341290 | 118.482297 | [7 empty] | 03. Pending TSS |  | TSS+AA+TI |  |  | MW Parallel Link | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507250629-GTSB
B02608_HU | B058C_B02608OD_LBHKEBUNNENASBDRPUTERAKLG | DU00005862751 | Central | Selangor | 2.989890 | 101.495350 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 1X 23G 0.6M DP ANTENNA 1X 23G 1.2M SP ANTENNA 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP 1247C/B02608-B01344 WITH HUAWEI_23G_1+0_0.6M/1.2M_DP_112MHZ_1024QAM_954MBPS_XMC3E_SUB_B_2.03KM DISMANTLE EXISTING LINK IMPACTED: 1247C | 1. INSTALL NEW RTN9101 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN9101 2. INSTALL NEW 23G 1.2M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK 6. PATCH TO NEW CP PORT | XMC3E | MAC | 23G | 0.6 | 1.2 | GCI | SQ202507250103-GCI | GCI | SQ202507250397-GCI // SQ202507250407-GCI // SQ202511060402-GCI | 2025-11-15 | 2025-11-07 | Completed | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-07 | 2025-11-15 | 2025-11-07 | 2025-11-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072982 | WIP A23D06MAC-3NX x 2 | 2025-07-30 | 2025-07-31 | Completed | 2025-07-29 | 2025-07-30 | 2025-07-29 | 2025-07-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-12 | 2025-08-19 | 2025-08-11 | 2025-08-12 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-08-12 | 2025-08-19 | 2025-08-11 | 2025-08-19 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-12 | 2025-08-12 | 2025-08-19 | 2025-08-11 | 2025-08-19 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-08-12 | 2025-08-19 | 2025-08-11 | 2025-08-12 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507250548-GCI | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
9001C_HU | Permyjaya Technology Park (Emart Tudan) | DU00005862752 | Sarawak | Sarawak | 4.482421 | 114.039414 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_9001C New 23G_DP_0.6M(MAC)+OMT x1. New RTN910A(RTN01). New XMC_3E, Sub A_Lo x1. FE_9546A New 23G_DP_0.6M(MAC)+OMT x1. New RTN910A(RTN03). New XMC_3E, Sub A_Hi x1. New CAT6 1x. | MW Swap | Existing NEC MW Link 9001C-9546A-01, 23G_1+0_56MHZ_440M. Install new HW MW Link 9001C-9546A, 23G_1+0_112MHZ_512QAM. Later, decom existing NEC MW Link 9001C-9546A-01, 23G_1+0_56MHZ_440M. Site Impacted : 9001C. NE_9001C 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Re-use existing vlan dcn and vlan services. 7.Migrate traffic 9001C via new HW MW Link 9001C-9546A, 23G_1+0_112MHZ_512QAM. 8.Decom existing NEC MW Link 9001C-9546A-01, 23G_1+0_56MHZ_440M. FE_9546A 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN03) x1. 3.Install new 1x XMC_3E, Sub A_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN03). 5.Patching port 8-EM6-1 of new RTN910A(RTN02) to existing port at IBeam. Configure it. 6.Re-use existing vlan dcn and vlan services. 7.Decom existing NEC MW Link 9001C-9546A-01, 23G_1+0_56MHZ_440M. | Existing NEC MW Link 9001C-9546A-01, 23G_1+0_56MHZ_440M. Install new HW MW Link 9001C-9546A, 23G_1+0_112MHZ_512QAM. Later, decom existing NEC MW Link 9001C-9546A-01, 23G_1+0_56MHZ_440M. Site Impacted : 9001C. NE_9001C 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Re-use existing vlan dcn and vlan services. 7.Migrate traffic 9001C via new HW MW Link 9001C-9546A, 23G_1+0_112MHZ_512QAM. 8.Decom existing NEC MW Link 9001C-9546A-01, 23G_1+0_56MHZ_440M. | Existing NEC MW Link 9001C-9546A-01, 23G_1+0_56MHZ_440M. Install new HW MW Link 9001C-9546A, 23G_1+0_112MHZ_512QAM. Later, decom existing NEC MW Link 9001C-9546A-01, 23G_1+0_56MHZ_440M. Site Impacted : 9001C. FE_9546A 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN03) x1. 3.Install new 1x XMC_3E, Sub A_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN03). 5.Patching port 8-EM6-1 of new RTN910A(RTN02) to existing port at IBeam. Configure it. 6.Re-use existing vlan dcn and vlan services. 7.Decom existing NEC MW Link 9001C-9546A-01, 23G_1+0_56MHZ_440M. | XMC_3E | MAC | 23G | 23G_DP_0.6M(MAC)+OMT x1. | 23G_DP_0.6M(MAC)+OMT x1. | Magicell | SQ202509030212-Magicell | iEzzpro | SQ202512030588-Iezzpro // SQ202512030594-Iezzpro | 2025-11-17 | 2025-11-10 | Completed | 2025-09-03 | 2025-09-30 | 2025-09-08 | 2025-09-08 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-03 | 2025-10-31 | 2025-10-03 | 2025-10-31 | AZRI//BIN ABDULLAH/6799000073 | Design and Material Team | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111880 |  | 2025-11-19 | 2025-11-20 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-12-09 | Kevin//Tan/6000033214 | Iezzpro TI | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-12-09 | Kevin//Tan/6000033214 | Iezzpro TI | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-12-08 | Kevin//Tan/6000033214 | 2025-09-30: 2025-11-22; 2025-10-10: 2025-11-29; 2025-10-18: 2025-11-22; 2025-11-25: 2025-11-27 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507250636-GTSB
B01690_HU | B065B_B01690OD_T3_KGHULUTAMU | DU00005862753 | Central | Selangor | 3.463920 | 101.694720 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 2X RTN910A 1X 13G 1.2M DP ANTENNA 1X 13G 1.8M DP ANTENNA 2x ODU 13G XMC3 SUB A HI 2X ODU 13G XMC3 SUB A LO 2x ODU 13G XMC3 SUB B HI 2X ODU 13G XMC3 SUB B LO | MW Swap | MW SWAP B01690-C00007 WITH HUAWEI_13G_4+0_1.2M/1.8M_DP MS_28MHZ_256QAM_800MBPS_XMC3_SUB_A & B_WITH CA_10.5KM DISMANTLE EXISTING LINK (REUSE FREQ CHANNEL 1) IMPACTED: B01690 | 1. INSTALL NEW RTN910 AND 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.2M DP ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM WITH CA 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 AND 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M DP ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM WITH CA 5. DISMANTLE EXISTING LINK 6. PATCH TO NEW CP PORT | XMC3 | MS | 13G | 1.2 | 1.8 | GTSB | SQ202508290656-GTSB | GTSB | SQ202508290719-GTSB // SQ202508290722-GTSB | 2025-11-25 | 2025-11-24 | Completed | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-10-28 | 2025-10-29 | 2025-10-28 | 2025-10-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250724AL |  | 2025-07-25 | 2025-08-27 | Completed | 2025-07-24 | 2025-07-25 | 2025-07-24 | 2025-08-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-26 | 2025-09-30 | 2025-09-26 | 2025-12-13 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-09-26 | 2025-09-30 | 2025-09-26 | 2025-12-22 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-15 | 2025-09-26 | 2025-09-30 | 2025-09-26 | 2026-01-23 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-09-26 | 2025-09-30 | 2025-09-26 | 2025-12-02 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250548-GCI | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
4704D_HU | Kampung Telok Wang Besar | DU00005862754 | Northern | Kedah | 5.616478 | 100.430790 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M with MDD type. NE_4704D. 18G_SP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Hi x1.. FE_4941A. 18G_SP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Lo x1.. | MW Swap | Existing link 18G_1+0_56M. Not Support For Remote Upgrade. Swap existing link to 18G_1+0_112M with MDD type. Site Impacted : 4704D. NE_4704D. 1.Install new 18G_SP_0.6M(MDD). 2.Reuse existing 4704D_RTN01 (ID : 27626). 3.Install new 3_ISM8-1+0 into existing 4704D_RTN01 (ID:27626). 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and cofig with 112M. 6.Traffic migrate with new link configuration 18G_1+0_112M. 7.Decom Existing ODU and ANT. FE_4941A. 1.Install new 18G_SP_0.6M(MDD). 2.Reuse existing 4941A_RTN01 (ID : 27627). 3.Install new 3_ISM8-1+0 into existing 4914A_RTN01 (ID : 27627). 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and config with 112M. 6.Traffic migrate with new link configuration 18G_1+0_112M. 7.Decom existing ODU and ANT. | Existing link 18G_1+0_56M. Not Support For Remote Upgrade. Swap existing link to 18G_1+0_112M with MDD type. Site Impacted : 4704D. NE_4704D. 1.Install new 18G_SP_0.6M(MDD). 2.Reuse existing 4704D_RTN01 (ID : 27626). 3.Install new 3_ISM8-1+0 into existing 4704D_RTN01 (ID:27626). 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and cofig with 112M. 6.Traffic migrate with new link configuration 18G_1+0_112M. 7.Decom Existing ODU and ANT. | Existing link 18G_1+0_56M. Not Support For Remote Upgrade. Swap existing link to 18G_1+0_112M with MDD type. Site Impacted : 4704D. FE_4941A. 1.Install new 18G_SP_0.6M(MDD). 2.Reuse existing 4941A_RTN01 (ID : 27627). 3.Install new 3_ISM8-1+0 into existing 4914A_RTN01 (ID : 27627). 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and config with 112M. 6.Traffic migrate with new link configuration 18G_1+0_112M. 7.Decom existing ODU and ANT. | XMC_5D | MDD | 18G | 0.6 | 0.6 | GCI | SQ202507310866-GCI | GCI | SQ202507310847-GCI // SQ202507310853-GCI | 2025-11-29 | 2025-11-28 | Completed | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081269 |  | 2025-08-16 | 2025-08-14 | Completed | 2025-08-15 | 2025-08-16 | 2025-08-12 | 2025-08-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-21 | 2025-09-04 | 2025-08-21 | 2025-08-21 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-08-21 | 2025-09-04 | 2025-08-21 | 2025-08-30 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-21 | 2025-08-21 | 2025-09-04 | 2025-08-21 | 2025-09-02 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-08-21 | 2025-09-04 | 2025-08-21 | 2025-08-29 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507250560-GCI | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | CHEONG/SENG/WAH/7018000306
Q00089_HU | Q124A_Q00089OD_BINAMAS | DU00005862755 | Sarawak | Sarawak | 1.553910 | 110.360310 | [6 empty] | ZTE | 03. Pending TSS |  | TSS |  | 15G_4+0_1.2/1.2_MDD_SB A 2XRTN910A 4XISM8 | MW Swap | 03 Mar 2026: TSS only. Upgrade/Swap not required as child site Q01028 will reroute MW SWAP Q00089-Q00085 WITH 15G_4+0_1.2/1.2 MDD_XMC-5D_SB A. DISMANTLE SM LINK | MW SWAP Q00089-Q00085 WITH 15G_4+0_1.2/1.2 MDD_XMC-5D_SB A. NE: 1. Swap SM IDU with RTN910A. 2. Install new 2xISM8 at slot 3 and 4. 3. Swap exisitng ODU with XMC-5D_SB A. 4. Swap exisitng antenna with 15G_1.2MDD. 5. Configure 15G_4+0_1.2/1.2_MDD_CA. 6. Dismantle SM link. | MW SWAP Q00089-Q00085 WITH 15G_4+0_1.2/1.2 MDD_XMC-5D_SB A. FE: 1. Swap SM IDU with RTN910A. 2. Install new 2xISM8 at slot 3 and 4. 3. Swap exisitng ODU with XMC-5D_SB A. 4. Swap exisitng antenna with 15G_1.2MDD. 5. Configure 15G_4+0_1.2/1.2_MDD_CA. 6. Dismantle SM link. | XMC-5D SB A |  | 15 | 1.2 | 1.2 | Magicell | SQ202509030212-Magicell |  |  |  |  | Not started | 2025-09-03 | 2025-09-30 | [6 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | DO Canceled (More than 30 days) | 2025-08-26 |  | Ongoing | 2025-08-25 | 2025-08-26 | 2025-08-25 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202507250636-GTSB | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | HSU//MYET CHAE/6799000011
1480C_HU | JALAN KEBUN | DU00005862756 | Central | Selangor | 2.961670 | 101.530162 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 1X ISM8 CARD 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Hardware Upgrade | MW HARDWARE UPGRADE 1480C-1605B WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM_954MBPS_XMC3E_SUB_B_1.38KM IMPACTED: 1480C | 1. REUSE EXISTING RTN910 2. REUSE EXISTING 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING ODU | 1. INSTALL NEW 1PCS ISM8 AT RTN11 1605B SLOT 3 2. REUSE EXISTING 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. SHIFT IF CABLE FROM EXISTING IDU RTN07 TO RTN11 5. CONFIGURE LINK 18G 1+0 112MHZ 1024QAM 6. PATCH RTN11 TO NEW CP PORT AND DO PORT LAG 2G 7. DISMANTLE EXISTING ODU AND IDU RTN07 | XMC3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202507250103-GCI | GCI | SQ202507250397-GCI // SQ202507250407-GCI | 2025-08-15 | 2025-08-14 | Completed | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-14 | 2025-08-15 | 2025-08-14 | 2025-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250724AM |  | 2025-07-25 | 2025-08-05 | Completed | 2025-07-24 | 2025-07-25 | 2025-07-24 | 2025-08-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-05 | 2025-08-12 | 2025-08-05 | 2025-08-05 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-08-05 | 2025-08-12 | 2025-08-05 | 2025-08-06 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-06 | 2025-08-05 | 2025-08-12 | 2025-08-05 | 2025-08-12 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-08-05 | 2025-08-12 | 2025-08-05 | 2025-08-05 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | NG HONG JIE7018000036 | Logistic Team | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507250548-GCI | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
A00537_HU | A043B_A00537OD_TLKRUBIAH | DU00005862757 | Northern | Perak | 4.167979 | 100.629754 |  |  |  |  | 6/2: pending access BM(hardcore access) |  |  | 02. Pending Access | 9/9: hardcore access issue | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 2X RTN910A 2X 13G 1.8M MDD ANTENNA 1x ODU 13G XMC5D SUB B HI 1X ODU 13G XMC5D SUB B LO | MW Swap | MW SWAP UPGRADE 4389A/A00537-A00268 WITH HUAWEI_13G_4+0_1.8M/1.8M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_B_WITH CA_11KM IMPACTED: 4389A | 1. INSTALL NEW RTN910 AND 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING | 1. INSTALL NEW RTN910 AND 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING 6. PATCH TO NEW CP PORT | 5D | MDD | 13G | 1.8 | 1.8 | GCI | SQ202507310866-GCI | GCI | SQ202507310847-GCI // SQ202507310853-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25082303 |  | 2025-08-24 | 2025-08-28 | Completed | 2025-08-23 | 2025-08-24 | 2025-08-23 | 2025-08-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202507250560-GCI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
1113A_LOS | Pulau Ketam | DU00005653089 | Central | Selangor | 3.018927 | 101.252875 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | New link install 13G_4+0_28M. . NE_1113A 13G_DP_1.2M(MS) x1 RTN910A x1 ISM8 x2 XMC_3E , Sub A & B_Lo x2 FE_1082A 13G_DP_1.2M(MS) x1. RTN910A x1. ISM8 x2. XMC_3E , Sub A & B_Hi x2. | MW New Link / Reroute | Link Reroute to new FE 1082A due to existing link LOS issue. New link install 13G_4+0_28M Site Impacted : 1113A , 1024K NE_1113A 1.Install new 13G_DP_1.2M(MS) + Waveguide + Coupler. 2.Install new RTN910A.(RTN no provide by GOP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.ETH Cable cascade to existing 1113A_RTN02. 6.Create service cross connect and EPLA. 7.BBU 1113A migrate to new MW link and new FE route. 8.Decom existing MW (1113A - 1087A). FE_1082A 1.Install new 13G_DP_1.2M(MS) + Waveguide + Coupler. 2.Install new RTN910A.(RTN no provide by GOP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Create new In Band DCN. 7.Traffci migrate to new MW link and new FE route. 8.Decom existing MW link (1087A - 1113A). | Link Reroute to new FE 1082A due to existing link LOS issue. New link install 13G_4+0_28M Site Impcated : 1113A , 1024K NE_1113A 1.Install new 13G_DP_1.2M(MS) + Waveguide + Coupler. 2.Install new RTN910A.(RTN no provide by GOP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.ETH Cable cascade to existing 1113A_RTN02. 6.Create service cross connect and EPLA. 7.BBU 1113A migrate to new MW link and new FE route. 8.Decom existing MW (1113A - 1087A). | Link Reroute to new FE 1082A due to existing link LOS issue. New link install 13G_4+0_28M Site Impcated : 1113A , 1024K FE_1082A 1.Install new 13G_DP_1.2M(MS) + Waveguide + Coupler. 2.Install new RTN910A.(RTN no provide by GOP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Create new In Band DCN. 7.Traffci migrate to new MW link and new FE route. 8.Decom existing MW link (1087A - 1113A). | XMC_3E | MS | 13G | 1.2 | 1.2 | MTK | SQ202507080847-MTK | MTK | SQ202507100553-MTK // SQ202507100557-MTK // SQ202507300767-MTK | 2025-08-21 | 2025-08-20 | Completed | 2025-06-19 | 2025-07-08 | 2025-06-19 | 2025-07-08 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-10 | 2025-07-11 | 2025-07-10 | 2025-07-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-04 | 2025-08-05 | 2025-08-04 | 2025-08-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062433 |  | 2025-06-25 | 2025-06-25 | Completed | 2025-06-24 | 2025-06-25 | 2025-06-24 | 2025-06-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-09 | 2025-07-30 | 2025-07-10 | 2025-07-10 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-07-09 | 2025-08-11 | 2025-07-09 | 2025-08-11 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-14 | 2025-07-09 | 2025-07-30 | 2025-08-12 | 2025-08-12 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-07-09 | 2025-07-30 | 2025-08-19 | 2025-08-19 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | NG HONG JIE7018000036 | Logistic Team | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506050638-GCI | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
3166B-1087A | pBTS MFE Formwork (EB) | DU00003906113 | Central | Selangor | 3.054388 | 101.382480 |  |  |  | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 14/8: Cutover done. NMS issue, T/shooting WIP by CD 7/8: DO ready, Collection in plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1) 1x18G XMC3E Sub B Lo FE: 1) 1x18G XMC3E Sub B Hi 2) 1xRTN910A | MW Hardware Upgrade | Existing link in NMS 1087A-3166B_ZNIC 1+0 56MHz (3166B RTN01-1087A RTN04) To replace existing ODU with new XMC3E ODU (to use high tx power) To install new IDU at FE/CP site Impact site: 3166B5 NE (3166B RTN01) 1. Swap ODU to XMC3E 2. Upgrade link to 112MHz FE (1087A) 1. Install new IDU (ops team to assign IDU number) 2. Transfer IF cable from RTN04 3-ISM8-1 to new RTN 7-ISM8-1 3. Swap ODU to XMC3E 4, Upgrade to 112MHz 5. Patch new IDU to new CP port. Migrate traffic and create new DCN | [7 empty] | Allstar | SQ202408220872-Allstar | Allstar | SQ202408140500-Allstar // SQ202510070055-Allstar | 2024-10-02 | 2024-10-01 | Completed | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-07 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-21 | 2024-09-22 | 2024-09-21 | 2024-09-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2024-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240806A9 |  | 2024-08-07 | 2024-08-09 | Completed | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-08-09 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-14 | 2024-08-31 | 2024-08-14 | 2024-11-19 | ALI//HAMZA/6798000192 | Allstar TI | 2024-08-14 | 2024-08-31 | 2024-08-14 | 2024-09-23 | ALI//HAMZA/6798000192 | Allstar TI | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-08-15 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-08-14 | 2024-08-31 | 2024-08-14 | 2024-08-15 | ALI//HAMZA/6798000192 | 2024-08-14 | 2024-08-31 | 2024-08-14 | 2024-08-14 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-06 | NG HONG JIE7018000036 | Logistic Team | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358
4012D-4118C | ISTANA BUKIT MALUT (CELCOM) | DU00003906114 | Northern | Kedah | 6.313284 | 99.784546 |  |  | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 11/9: Langkawi Island sites, pending collection & MOS due weather permitting issue | AA | PAC |  | MW Remote Upgrade | Upgrade existing link SM NT05094 from 18GHz 1+0 56MHz to 512QAM to 2048QAM Modulation , due to 112M not support from actual configuration. Impacted site: 4012D | [7 empty] | CCSMY | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Ongoing | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2024-08-11 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | Cancel DO req by Hady | 2024-08-07 |  | Ongoing | 2024-08-06 | 2024-08-07 | 2024-08-06 |  | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [13 empty] | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-03-24 | [15 empty] | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045
4399A-4391A | Titi Serong RCC | DU00003906115 | Northern | Perak | 5.099611 | 100.456417 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | DU00004180975 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01812_AD | Q118B_Q01812OD_SABAJUMILL | DU00006593386 | Sarawak | Sarawak | 3.198936 | 113.508614 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cat 6 cable x1. | MW IDU Patching | Offload Q01812 to SM link SW03330 Q01117-Q00254 MW1 to ease up congestion on Huawei link 9031K/Q01117_RH RANGGA - 9057X / Q00254_BKT NYABAU Site Impacted : Q01812 , Q03058 CPE Sabaju Mill. 1) Patch SM IDU SW03935 Q01118-Q01812 MW1 to SM IDU SW03330 Q01117-Q00254 MW1 2) Existing Q01117_RTN01_GE2 ETH Patching to 9031K_RTN04_GE2. |  | Offload Q01812 to SM link SW03330 Q01117-Q00254 MW1 to ease up congestion on Huawei link 9031K/Q01117_RH RANGGA - 9057X / Q00254_BKT NYABAU Site Impacted : Q01812 , Q03058 CPE Sabaju Mill. 1) Patch SM IDU SW03935 Q01118-Q01812 MW1 to SM IDU SW03330 Q01117-Q00254 MW1 2) Existing Q01117_RTN01_GE2 ETH Patching to 9031K_RTN04_GE2. | [5 empty] | Trintel | SQ202602230149-Trintel | Trintel | SQ202602160111-Trintel | 2026-03-04 | 2026-03-04 | Completed | 2026-02-14 | 2026-02-28 | 2026-02-14 | 2026-02-19 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26021239 |  | 2026-02-13 | 2026-02-14 | Completed | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-14 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-14 | 2026-02-28 | 2026-02-14 | 2026-02-19 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2026-02-14 | 2026-02-28 | 2026-02-14 | 2026-02-19 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2026-02-14 | 2026-02-14 | 2026-02-14 | 2026-02-14 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-14 | 2026-02-14 | 2026-02-28 | 2026-02-14 | 2026-02-21 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2025-09-30: 2026-02-14; 2025-10-10: 2026-02-28; 2025-10-18: 2026-02-14; 2025-11-25: 2026-02-14 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202602120121-GCI | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | CHEONG/SENG/WAH/7018000306
8408E_EB | Blue Archipelago Berhad | DU00006593387 | Eastern | Terengganu | 5.572640 | 102.805980 | [9 empty] | TSS+AA+TI+Dismantle |  | ZTE 15G_1+0_0.6/0.6__sub A | MW Swap | Existing mw is unknown - team please check actual on site - existing link will be decom Install new ZTE MW 15G_1+0_0.6/0.6m to swap with existing mw | 1. Install new IDU NR9150 2. Install new 15G 0.6m DP ant 3. Install new ODU 15G SRU2D sub A_Lo 4. Config link 15G 1+0 28Mhz 512Qam 5. Dismantle existing link | 1. Install new IDU NR9150 2. Install new 15G 0.6m DP ant 3. Install new ODU 15G SRU2D sub A_Hi 4. Config link 15G 1+0 28Mhz 512Qam 5. Dismantle existing link 6. Connect IDU to DU uplink T00038 | SRU2D | 30 | 15G | 0.6 | 0.6 | GTSB | SQ202602160081-GTSB | GTSB | No PR required-TI done under OE Link | 2026-03-17 | 2026-03-10 | Completed | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-27 | 2026-03-06 | 2026-02-27 | 2026-02-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26042830 |  | 2026-04-29 | 2026-05-05 | Completed | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-06 | 2026-05-31 | 2026-05-06 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-05-06 | 2026-05-31 | 2026-05-06 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | [7 empty] | 2026-05-06 | 2026-05-31 | 2026-05-06 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-09-30: 2026-05-06; 2025-10-10: 2026-05-31; 2025-10-18: 2026-05-06; 2025-11-25: 2026-05-07 | [7 empty] | GTSB | SQ202602120145-GTSB | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | AB.RAHMAN//BIN MAT NOOH/6237001519
4621B_AD | Jeniang | DU00006599522 | Northern | Kedah | 5.813417 | 100.631991 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cat 6 Cable x1. | BBU Patching | Patch 4621B BBU to existing IBEAM 4621B-MAC-001 Jeniang | Patch 4621B BBU to existing IBEAM 4621B-MAC-001 Jeniang | [6 empty] | GCI | SQ202602230142-GCI | GCI | SQ202602230136-GCI | 2026-03-13 | 2026-03-12 | Completed | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022315 |  | 2026-02-24 | 2026-03-02 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-03-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-28 | 2026-02-24 | 2026-03-02 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-02-24 | 2026-02-28 | 2026-02-24 | 2026-03-02 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | SHIV KUMAR6800000084 |  | 2026-03-03 | 2026-02-24 | 2026-02-28 | 2026-02-24 | 2026-03-02 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-09-30: 2026-02-24; 2025-10-10: 2026-02-28; 2025-10-18: 2026-02-24; 2025-11-25: 2026-02-25 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602120114-GCI | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | CHEONG/SENG/WAH/7018000306
3440B8_LOS | pBTS Angkasa Apartment (C) | DU00006599523 | Sabah | Sabah | 6.027447 | 116.140470 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 1X 18G 0.6M MAC ANTENNA 1x ODU 18G XMC3E SUB B HI 1x ODU 18G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK REROUTE 3440B8-S00824/7008K WITH HUAWEI_18G_1+0_0.6M/0.6M_MAC_112MHZ_512QAM_889MBPS_XMC3E_SUB_B_LINK_2.08KM IMPACTED: 3440B8 DISMANTLE EXISTING LINK 3440B8-7152B | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MAC ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 3440B8-7152B | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 128QAM WITH CA 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK 3440B8-7152B | XMC3E | MAC | 18G | 0.6 | 0.6 | YPTT |  | YPTT | SQ202604100665-YPTT // SQ202604100672-YPTT |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26033126 |  | 2026-04-01 | 2026-04-09 | Completed | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | DOMINIC DAVIES6794000049 | YPTT TI | 2026-04-08 | 2026-04-08 | 2026-04-08 |  | DIUSLIN//JUPILIN/6794000056 | YPTT TI | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-15 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  | DIUSLIN//JUPILIN/6794000056 | 2025-09-30: 2026-04-08; 2025-10-10: 2026-04-08; 2025-10-18: 2026-04-08; 2025-11-25: 2026-04-08 | [7 empty] | GCI | SQ202602260576-GCI | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | EZRIN TASNIM BIN ABDUL GANI6798000128
9202R_AD | Kg. MentongBaing | DU00006599524 | Sarawak | Sarawak | 1.008790 | 110.626876 | [9 empty] | TSS+TI |  | FE_9256A/Q00635 New CAT6 cable x1. | MW IDU Patching | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(9100E) BEFORE PERFORM MIGRATION/REROUTING TO XC PTN/CISCO ROUTER AT Q00635. 2.MANDATORY TO PERFORM DU(9202R_AD, 9020R_PostMOCN, 9021R_PostMOCN & Q01246) IN SIMULTANEOUSLY OR SEQUENCES IN THE SAME DAY IN ORDER TO AVOID LONG OUTAGE OCCUR AS ALL TRAFFICS(9202R, 9100E, 9020R, 9327K & 9021R) CONNECTED TO SINGLE SACOFA LL (9256A-LL-9999A) BEFORE DECOM EXISTING LL SACOFA(9256A-LL-9999A) & DECOM EXISTING HW MW LINK 9257A(RTN02, NEID 9-20646)- 9256A(RTN03, NEID 9-20645).**** Site Impacted: 9202R, 9100E, 9020R, 9327K & 9021R. FE_9256A/Q00635 1.Request new 1G port(Electrical) of PTN/Cisco Router from ZTE IPRAN Team. 2.Request new xC Vlan DCN and Vlan Services. 3.Disconnect or remove Tejas(Sacofa LL) from port 8-EM6-1 of existing RTN910AF(RTN04, NEID 9-22196). 4.Disconnect or remove cascading from port 8-EM6-2 of existing RTN910AF(RTN04, NEID 9-22196) and NEC IDU. Disable port 8-EM6-2. 5.Perform patching in between port 8-EM6-1 of existing RTN910AF(RTN04, NEID 9-22196) and new 1G port(Electrical) of PTN/Cisco Router. 6.Migrate traffics 9202R & 9100E ONLY to xC PTN/Cisco at Q00635. |  | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(9100E) BEFORE PERFORM MIGRATION/REROUTING TO XC PTN/CISCO ROUTER AT Q00635. 2.MANDATORY TO PERFORM DU(9202R_AD, 9020R_PostMOCN, 9021R_PostMOCN & Q01246) IN SIMULTANEOUSLY OR SEQUENCES IN THE SAME DAY IN ORDER TO AVOID LONG OUTAGE OCCUR AS ALL TRAFFICS(9202R, 9100E, 9020R, 9327K & 9021R) CONNECTED TO SINGLE SACOFA LL (9256A-LL-9999A) BEFORE DECOM EXISTING LL SACOFA(9256A-LL-9999A) & DECOM EXISTING HW MW LINK 9257A(RTN02, NEID 9-20646)- 9256A(RTN03, NEID 9-20645).**** Site Impacted: 9202R, 9100E, 9020R, 9327K & 9021R. FE_9256A/Q00635 1.Request new 1G port(Electrical) of PTN/Cisco Router from ZTE IPRAN Team. 2.Request new xC Vlan DCN and Vlan Services. 3.Disconnect or remove Tejas(Sacofa LL) from port 8-EM6-1 of existing RTN910AF(RTN04, NEID 9-22196). 4.Disconnect or remove cascading from port 8-EM6-2 of existing RTN910AF(RTN04, NEID 9-22196) and NEC IDU. Disable port 8-EM6-2. 5.Perform patching in between port 8-EM6-1 of existing RTN910AF(RTN04, NEID 9-22196) and new 1G port(Electrical) of PTN/Cisco Router. 6.Migrate traffics 9202R & 9100E ONLY to xC PTN/Cisco at Q00635. | [5 empty] | Allstar | SQ202603180484-Allstar | Allstar | SQ202603180480-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030631 |  | 2026-03-07 | 2026-03-31 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-26 | 2026-04-01 | 2026-03-31 | 2026-03-31 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-03-26 | 2026-04-01 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | [7 empty] | 2026-03-26 | 2026-04-01 |  |  | ROYSTON//AHHOLE/6000038561 | 2025-09-30: 2026-03-26; 2025-10-10: 2026-04-01; 2025-10-18: 2026-03-26; 2025-11-25: 2026-03-26 | [7 empty] | GTSB | SQ202602120283-GTSB
Q00268_IPR | Q132A_Q00268OD_CB_TT844 | DU00006599525 | Sarawak | Sarawak | 3.609036 | 113.685310 | [9 empty] | TSS+TI |  | NE_Q00268 New CAT6 cable with suitable length x1. | MW IDU Patching | Perform MW IDU Patching at NE Q00268. Site Impacted : Q00757. NE_Q00268. 1.Disconnect/remove cascading between port LAN 1 of existing SM IDU AGS 20(IP ADDRESS 10.127.143.107) of existing SM MW Link_ID SW03805 and port 8-EM6-1 of existing RTN910AF(NEID 82-34962) of existing HW MW Link Q00268_TT844 - 9073K/Q00509_MYYBTUTRUNK. 2.Disable port 8-EM6-1 of existing RTN910AF(NEID 82-34962) of existing HW MW Link Q00268_TT844 - 9073K/Q00509_MYYBTUTRUNK. 3.Request new 1G electrical port at PTN/Cisco Router(Q00268 - PTN ID 30157) from ZTE IPRAN team. 4.Request new xC Vlan DCN and Vlan Services. 5.Perform new patching between port LAN 1 of existing SM IDU AGS 20(IP ADDRESS 10.127.143.107) of existing SM MW Link_ID SW03805 and new 1G electrical port at PTN/Cisco Router(Q00268 - PTN ID 30157). 6.Migrate traffics Q00757 to new 1G electrical port at PTN/Cisco Router(Q00268 - PTN ID 30157). | Perform MW IDU Patching at NE Q00268. Site Impacted : Q00757. NE_Q00268. 1.Disconnect/remove cascading between port LAN 1 of existing SM IDU AGS 20(IP ADDRESS 10.127.143.107) of existing SM MW Link_ID SW03805 and port 8-EM6-1 of existing RTN910AF(NEID 82-34962) of existing HW MW Link Q00268_TT844 - 9073K/Q00509_MYYBTUTRUNK. 2.Disable port 8-EM6-1 of existing RTN910AF(NEID 82-34962) of existing HW MW Link Q00268_TT844 - 9073K/Q00509_MYYBTUTRUNK. 3.Request new 1G electrical port at PTN/Cisco Router(Q00268 - PTN ID 30157) from ZTE IPRAN team. 4.Request new xC Vlan DCN and Vlan Services. 5.Perform new patching between port LAN 1 of existing SM IDU AGS 20(IP ADDRESS 10.127.143.107) of existing SM MW Link_ID SW03805 and new 1G electrical port at PTN/Cisco Router(Q00268 - PTN ID 30157). 6.Migrate traffics Q00757 to new 1G electrical port at PTN/Cisco Router(Q00268 - PTN ID 30157). | [6 empty] | Trintel |  | Trintel |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26020921 |  | 2026-02-10 |  | Ongoing | 2026-02-09 | 2026-02-10 | 2026-02-09 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202602120283-GTSB
7434B_HU | LabukBay | DU00006601873 | Sabah | Sabah | 5.933678 | 117.797720 | [7 empty] | 03. Pending TSS |  | TSS+AA+TI |  | 4X ISM8 CARD 2X RTN910A 2X 13G 1.8M DP ANTENNA 2x ODU 13G XMC3 SUB A HI 2x ODU 13G XMC3 SUB A LO 2x ODU 13G XMC3 SUB B HI 2x ODU 13G XMC3 SUB B LO | MW Parallel Link | MW PARALLEL LINK 7434B-7147A WITH HUAWEI_13G_4+0_1.8M/1.8M_DP_28MHZ_256QAM_800MBPS_XMC3_SUB_A & B_WITH CA_LINK_14.15KM IMPACTED: 7434B NEW LINK WILL CARRY 7420B-7434B | 1. INSTALL NEW IDU RTN910 AND 2PCS IDU ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M DP ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM 5. PATCH IDU 7420B-7434B TO NEW LINK 6. REPATCH 7216Z-7434B TO 7434B RTN02 | 1. INSTALL NEW IDU RTN910 AND 2PCS IDU ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M DP ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM 5. PATCH NEW IDU TO 7147A RTN02 | XMC3 | MAC | 13G | 1.8 | 1.8 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202602120118-GCI
Q01009_HU | T3KGMENTU | DU00006601874 | Sarawak | Sarawak | 0.930750 | 110.584000 | [9 empty] | TSS+AA+TI |  | 15G_4+0_28M_512QAM_CA NE_9205P/Q01009 New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 17-18038). New ISM8 x1. New XMC_5D Pro, Sub B_Hi x1. New IF cables with suitable length and type x2 RUN. FE_9153R/Q00642 New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 17-28038). New ISM8 x1. New XMC_5D Pro, Sub B_Lo x1. New IF cables with suitable length and type x2 RUN. | MW Parallel Link | Existing HW MW Link 9205P/Q01009-9153R/Q00642, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. Later, combine existing HW MW Link 9205P/Q01009-9153R/Q00642, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. Become 15G_6+0_28MHZ_512QAM&1024QAM_EPLA. Site Impacted : 9205P/Q01009. NE_9205P/Q01009 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 17-18038) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. 4.Shifting existing IF cable at ISM8 slot 03 Port 1 to ISM8 slot 07 Port 2. 5.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Hi x1 to existing RTN910AF(RTN02, NEID 17-18038) ISM8 slot 03(Port 1) and slot 04(Port 1). 6.Build new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. 7.Re-use existing Vlan DCN & Vlan Services. 8.Migrate 9205P/Q01009 into new HW MW Link 15G_6+0_28MHZ_512QAM&1024QAM_EPLA. 9.Later, combine existing HW MW Link 9205P/Q01009-9153R/Q00642, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. Become 15G_6+0_28MHZ_512QAM&1024QAM_EPLA. FE_9153R/Q00642 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 17-28038) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub B_Lo x1. 4.Shifting existing IF cable at ISM8 slot 03 Port 1 to ISM8 slot 07 Port 2. 5.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Hi x1 to existing RTN910AF(RTN02, NEID 17-28038) ISM8 slot 03(Port 1) and slot 04(Port 1). 6.Build new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. 7.Re-use existing Vlan DCN & Vlan Services. 8.Migrate 9205P/Q01009 into existing PTN/Cisco Router port at Q00794. 9.Later, combine existing HW MW Link 9205P/Q01009-9153R/Q00642, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. Become 15G_6+0_28MHZ_512QAM&1024QAM_EPLA. | Existing HW MW Link 9205P/Q01009-9153R/Q00642, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. Later, combine existing HW MW Link 9205P/Q01009-9153R/Q00642, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. Become 15G_6+0_28MHZ_512QAM&1024QAM_EPLA. Site Impacted : 9205P/Q01009. NE_9205P/Q01009 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 17-18038) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. 4.Shifting existing IF cable at ISM8 slot 03 Port 1 to ISM8 slot 07 Port 2. 5.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Hi x1 to existing RTN910AF(RTN02, NEID 17-18038) ISM8 slot 03(Port 1) and slot 04(Port 1). 6.Build new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. 7.Re-use existing Vlan DCN & Vlan Services. 8.Migrate 9205P/Q01009 into new HW MW Link 15G_6+0_28MHZ_512QAM&1024QAM_EPLA. 9.Later, combine existing HW MW Link 9205P/Q01009-9153R/Q00642, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. Become 15G_6+0_28MHZ_512QAM&1024QAM_EPLA. | Existing HW MW Link 9205P/Q01009-9153R/Q00642, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. Later, combine existing HW MW Link 9205P/Q01009-9153R/Q00642, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. Become 15G_6+0_28MHZ_512QAM&1024QAM_EPLA. Site Impacted : 9205P/Q01009. FE_9153R/Q00642 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 17-28038) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub B_Lo x1. 4.Shifting existing IF cable at ISM8 slot 03 Port 1 to ISM8 slot 07 Port 2. 5.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Hi x1 to existing RTN910AF(RTN02, NEID 17-28038) ISM8 slot 03(Port 1) and slot 04(Port 1). 6.Build new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. 7.Re-use existing Vlan DCN & Vlan Services. 8.Migrate 9205P/Q01009 into existing PTN/Cisco Router port at Q00794. 9.Later, combine existing HW MW Link 9205P/Q01009-9153R/Q00642, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 9205P/Q01009-9153R/Q00642, 15G_4+0_28MHZ_1024QAM_CA. Become 15G_6+0_28MHZ_512QAM&1024QAM_EPLA. | XMC-5D Pro | MDD | 15G | 15G_1.2M(MDD) x1 | 15G_1.2M(MDD) x1 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050641 |  | 2026-05-07 |  | Ongoing | 2026-05-06 | 2026-05-07 | 2026-05-06 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202602120283-GTSB
1220D_HU | Simpang PuncakAlam (REL) | DU00006601875 | Central | Selangor | 3.247838 | 101.469325 | [7 empty] | 04. BOM / Material Issue | 18/3/2026: FE can only install 0.6m antenna | TSS+AA+TI | L1+ATP+PAC | 18G_1+0_112M NE_1220D 18G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D Pro Sub A_Lo x1. FE_2069B. 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D Pro Sub A x1. | MW Parallel Link | Existing link 15G_4+0_28M Install parallel link 18G_1+0_112M. Site Impacted : 1220D , 1434H. NE_1220D 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_5D Sub A_Lo. 5.Enable GE1 , ETH Patching 1220D_BBU , carry 1220D. 6.Enable GE2 , ETH Patching NLOS (RNT510) , carry 1434H. 7.Create service cross connect and EPLA. 8.All traffic migrate to new parallel link. 9.No decomm existing MW. FE_2069B. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_5D Sub A_Hi. 4.Enable GE1 , ETH patching to existing 2069B_RTN01_GE2. 5.Create service cross connect and EPLA. 6.All traffic migrate to new parallel link. 7.No Decomm existing MW. | Existing link 15G_4+0_28M Install parallel link 18G_1+0_112M. Site Impacted : 1220D , 1434H. NE_1220D 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_5D Sub A_Lo. 5.Enable GE1 , ETH Patching 1220D_BBU , carry 1220D. 6.Enable GE2 , ETH Patching NLOS (RNT510) , carry 1434H. 7.Create service cross connect and EPLA. 8.All traffic migrate to new parallel link. 9.No decomm existing MW. | Existing link 15G_4+0_28M Install parallel link 18G_1+0_112M. Site Impacted : 1220D , 1434H. FE_2069B. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_5D Sub A_Hi. 4.Enable GE1 , ETH patching to existing 2069B_RTN01_GE2. 5.Create service cross connect and EPLA. 6.All traffic migrate to new parallel link. 7.No Decomm existing MW. | XMC_5D | MDD | 18G | 1.2 | 0.6 | GTSB | SQ202602230036-GTSB | GTSB | SQ202602230027-GTSB // SQ202602230033-GTSB // SQ202604200140-GTSB | 2026-03-13 | 2026-03-12 | Completed | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26033104 |  | 2026-04-01 | 2026-04-02 | Completed | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-09 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-09 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-03 | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-20 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | 2025-09-30: 2026-04-01; 2025-10-10: 2026-04-30; 2025-10-18: 2026-04-01; 2025-11-25: 2026-04-03 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602120113-GCI | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | CHEONG/SENG/WAH/7018000306
1794B_LOS | Shoplot Tmn Melawati 2 | DU00005249936 | Central | Selangor | 3.221839 | 101.740786 |  | APR 25 |  | APR 25 | DO | Doable, just waiting material | ZTE | 00. Site Out/Drop | 24/3/2025 : Digi OB - 3M Boom - RT - NE site 1794B Shoplot Tmn Melawati 2, Digi OB - 3M Bipod - RT - FE site 1288A JBA Wangsa maju | TSS |  | 23G_2+0_112M NE_1794B 23G_DP_0.6M(MDD) x1. RTN901A x1. XMC_5D , Sub A_Hi x1. FE_1288A. 23G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. | MW Swap | Existing SM link 18G_1+1_28M. Swap existing link to 23G_2+0_112M and install antenna at height location due to LOS Block. Site Impacted : 1479E. NE_1794B 1.Install 23G_DP_0.6M(MDD) at height location. 2.Install new RTN901A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching to existing 1794B_RTN01 (GE2). 6.Traffic 1479E_BBU via the new link 23G_2+0_112M. 7.Decomm existing SM link. FE_1288A. 1.Install 23G_DP_0.6M(MDD) at height location. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.Decomm existing SM link. | Existing SM link 18G_1+1_28M. Swap existing link to 23G_2+0_112M and install antenna at height location due to LOS Block. Site Impacted : 1479E. NE_1794B 1.Install 23G_DP_0.6M(MDD) at height location. 2.Install new RTN901A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching to existing 1794B_RTN01 (GE2). 6.Traffic 1479E_BBU via the new link 23G_2+0_112M. 7.Decomm existing SM link. | Existing SM link 18G_1+1_28M. Swap existing link to 23G_2+0_112M and install antenna at height location due to LOS Block. Site Impacted : 1479E. FE_1288A. 1.Install 23G_DP_0.6M(MDD) at height location. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.Decomm existing SM link. | XMC_5D | MDD | 23G | 0.6 | 0.6 | Magicell | SQ202504170467-Magicell // SQ202505160538-Magicell | Magicell | No PR required-Work at TSS only | 2025-08-21 | 2025-08-20 | Completed | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-04-30 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-15 | 2025-08-16 | 2025-08-15 | 2025-08-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI_AA | SQ202510300160-GCI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | CHEONG/SENG/WAH/7018000306
4627C_HU | Masjid Batu Kg Pertama | DU00005277726 | Northern | Penang | 5.390040 | 100.417535 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Task completed under 4627C_LOS due to LOS Block | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q02349_AD | RUMAH NABAU RUMAH ENTILI | DU00005284033 | Sarawak | Sarawak | 2.560743 | 111.818920 | [6 empty] | ZTE | 03. Pending TSS |  | TSS+AA+TI+Dismantle |  | 15G_2+0_28M NE_Q02349 13G_DP_1.2M(MAC) x1. RTN910 x1. XMC_3 , Sub B_Hi x2. FE_Q01171 13G_DP_1.2M(MAC) x1. RTN910 x1. XMC_3 , Sub B_Lo x2. | MW New Link / Reroute | Install New Microwave Link 15G_2+0_28M with EPLA Site Impacted : Q02349 NE_Q02349 1.Install new 15G_DP_1.2M(MAC) 2.Install New RTN910A 3.Install new 2+0 XMC_3 , Sub B_Hi Propose FE_Q001171 1.Install new 15G_DP_1.2M(MAC) 2.Install new RTN910A 3.Install new 2+0 XMC_3 , Sub B_Lo 4.Enable GE1 , ETH cable patching to exiting New FE Port SW03521 Q01171 KgRassau - Q00661 SgKut | NE Q02349 1. Install New 15G DP 1.2M MAC 2. Install New RTN910A 3. Install New 2+0 XMC3 Sub B Hi | FE_Q001171 1.Install new 15G_DP_1.2M(MAC) 2.Install new RTN910A 3.Install new 2+0 XMC_3 , Sub B_Lo 4.Enable GE1 , ETH cable patching to exiting New FE Port SW03521 Q01171 KgRassau - Q00661 SgKut | XMC3 | MAC | 15G | 1.2m | 1.2m | Magicell | SQ202509180716-Magicell |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25032808 |  | 2025-03-29 | 2025-04-05 | Completed | 2025-03-28 | 2025-03-29 | 2025-03-28 | 2025-04-05 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202507190089-GTSB | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | HSU//MYET CHAE/6799000011
3887C_HU | Central i-City Shopping Centre IB | DU00005289651 | Central | Selangor | 3.062279 | 101.481925 |  |  |  | JUN 25 |  |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X ISM8 CARD 2X 23G 0.6M MAC ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK 3887C-1620B WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_1.3KM IMPACTED: 3887C DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW ISM8 AT EXISTING RTN910 SLOT 3 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202505020369-GTSB | GTSB | SQ202504240805-GTSB // SQ202504240806-GTSB | 2025-11-25 | 2025-11-24 | Completed | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-28 | 2025-07-14 | 2025-07-14 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052164 |  | 2025-05-22 | 2025-05-27 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-15 | 2025-06-30 | 2025-06-15 | 2025-06-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-06-15 | 2025-06-30 | 2025-06-15 | 2025-06-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-06-30 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-30 | 2025-06-15 | 2025-06-30 | 2025-06-15 | 2025-07-05 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-06-15 | 2025-06-30 | 2025-06-15 | 2025-07-07 | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
7461A_HU | Nabawan RT (REL) | DU00005289652 | Sabah | Sabah | 5.041634 | 116.425916 |  |  |  |  | LOS blocked | 1.MwODU-ODU XMC-5D_15G_Subband B(H/L) x 2pc 2.MwAntenna HW-15G_1.2M_Dual Polarization_A15D12MDD-3NX x 2pc | ZTE | 03. TSS Only | Non-doable | TSS |  | 15G 4+0 1.2m/1.2m MDD XMC5D sub B NE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 15G XMC5D sub B Lo 4) 1 x 15G 1.2m MDD FE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 15G XMC5D sub B Hi 4) 1 x 15G 1.2m MDD 5) 1G SFP and patch cord | MW Parallel Link | 22 Nov 2025: TSS only due to 7461A-7476A LOS block. To reroute 7461A-7443A under DU 7461A_HU_1 To install parallel 4+0 CA to carry 7461A traffic only To use optical port at FE site due to no electrical port available NE (7461A): 1) Install new RTN910A 2) Install new ISM8 card at new IDU slot 3 and 4 3) Install new 4+0 CA link at 3-ISM8 and 4-ISM8 4) Migrate 7461A traffic to new link FE (7476A): 1) Install new RTN910A 2) Install new ISM8 card at new IDU slot 3 and 4 3) Install new 4+0 CA link at 3-ISM8 and 4-ISM8 4) Patch new IDU GE5 to RTN01 GE6 (use optical) 5) Migrate 7461A traffic to new link | NE (7461A): 1) Install new RTN910A 2) Install new ISM8 card at new IDU slot 3 and 4 3) Install new 4+0 CA link at 3-ISM8 and 4-ISM8 4) Migrate 7461A traffic to new link | FE (7476A): 1) Install new RTN910A 2) Install new ISM8 card at new IDU slot 3 and 4 3) Install new 4+0 CA link at 3-ISM8 and 4-ISM8 4) Patch new IDU GE5 to RTN01 GE6 (use optical) 5) Migrate 7461A traffic to new link | XMC5D | MDD | 15G | 1.2m | 1.2m | Seri Pancar | SQ202506180105-Seri Pancar | NR services | No PR required-Work at TSS only | 2025-07-31 | 2025-07-10 | Completed | 2025-06-16 | 2025-07-31 | 2025-06-17 | 2025-06-17 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-10 | 2025-07-11 | 2025-07-10 | 2025-07-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Full site DR Request on 2026/2/27 | 2025-11-03 | 2025-11-04 | Completed | 2025-11-02 | 2025-11-03 | 2025-11-02 | 2025-11-04 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-07 | 2025-12-08 | 2025-11-06 | 2025-11-07 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-11-07 | 2025-12-08 | 2025-11-06 |  | RALPH O'BRYAN HILARY7167000030 | NR Service TI | [7 empty] | 2025-11-07 | 2025-12-08 | 2025-11-06 |  | RALPH O'BRYAN HILARY7167000030 | 2025-09-30: 2025-11-07; 2025-10-10: 2025-12-08; 2025-10-18: 2025-11-06; 2025-11-25: 2025-11-07 | [7 empty] | GTSB | SQ202507080638-GTSB | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | AB.RAHMAN//BIN MAT NOOH/6237001519
9495A_HU | Kg Sira | DU00005289653 | Sarawak | Sarawak | 1.198210 | 110.411910 | [6 empty] | ZTE | 00. Integrated/RFS Done | 1/10/2025 : Installation complete, pending cutover 29/9/2025 : Pending alignment and cutover 27/9/2025 : Installation WIP 26/9/2025 : Installation WIP | TSS+AA+TI | L1+ATP+PAC | 15G 4+0 1.2m/1.2m MDD XMC5D sub A NE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 15G XMC5D sub A Lo 4) 1 x 15G 1.2m MDD FE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 15G XMC5D sub A Hi 4) 1 x 15G 1.2m MDD 5) 1G SFP and patch cord | MW Parallel Link | To install parallel 4+0 CA and EPLA with existing 2+0 to create 6+0 EPLA NE: To add ISM8 card to existing 9495A RTN01 FE: To Install new IDU, patch to existing RTN01 using optical port and transfer existing 2+0 link to new IDU NE (9495A): 1) Install new RTN910A 2) Install new ISM8 card at RTN01 slot 3 and 4 3) Install new 4+0 CA link at 3-ISM8 and 4-ISM8 4) Transfer existing 2+0 link from RTN01 7-ISM8 to new IDU 7-ISM8 5) Create 6+0 EPLA FE (9163A): 1) Install new RTN910A 2) Install new ISM8 card at new IDU slot 3 and 4 3) Install new 4+0 CA link at 3-ISM8 and 4-ISM8 4) Transfer existing 2+0 link from RTN02 7-ISM8 to new IDU 7-ISM8 5) Create 6+0 EPLA 6) Patch new IDU GE1 to RTN01 GE1 7) Migrate 9495A,9201R traffic to new link | NE (9495A): 1) Install new RTN910A 2) Install new ISM8 card at RTN01 slot 3 and 4 3) Install new 4+0 CA link at 3-ISM8 and 4-ISM8 4) Transfer existing 2+0 link from RTN01 7-ISM8 to new IDU 7-ISM8 5) Create 6+0 EPLA | FE (9163A): 1) Install new RTN910A 2) Install new ISM8 card at new IDU slot 3 and 4 3) Install new 4+0 CA link at 3-ISM8 and 4-ISM8 4) Transfer existing 2+0 link from RTN02 7-ISM8 to new IDU 7-ISM8 5) Create 6+0 EPLA 6) Patch new IDU GE5 to RTN01 GE5 (use optical) 7) Migrate 9495A,9201R traffic to new link | XMC5D | MDD | 15G | 1.2m | 1.2m | Allstar | SQ202506160462-Allstar | Allstar | SQ202509040262-Allstar // SQ202509040270-Allstar | 2025-10-31 | 2025-10-28 | Completed | 2025-05-20 | 2025-05-20 | 2025-06-13 | 2025-06-13 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-30 | 2025-08-01 | 2025-07-30 | 2025-07-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-30 | 2025-08-01 | 2025-07-30 | 2025-07-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082415 |  | 2025-08-25 | 2025-09-26 | Completed | 2025-08-24 | 2025-08-25 | 2025-08-24 | 2025-09-26 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-26 | 2025-10-02 | 2025-10-17 | 2025-10-17 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-09-26 | 2025-10-02 | 2025-10-13 | 2025-10-17 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-02 | 2025-09-26 | 2025-10-02 | 2025-10-07 | 2025-10-17 | BONG NEE NYEEbong.allstar@gmail.com | 2025-09-30: 2025-09-26; 2025-10-10: 2025-10-02; 2025-10-18: 2025-09-26; 2025-11-25: 2025-09-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB_AA | SQ202510300154-GTSB
7063D_HU | TAMAN SABANA (REL) | DU00005289654 | Sabah | Sabah | 5.374421 | 116.156334 |  |  |  |  | RFS | 29/05: TI done, pending RFS declare | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1) 1x18GHz XMC3E Sub A Hi FE: 1) 1x18GHz XMC3E Sub A Lo | MW Hardware Upgrade | Replace existing ODU with new XMC3E ODU for 112MHz upgrade NE (7063D RTN01): 1) Replace 7-ISM8-1 ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade and change frequency channel FE (7068A RTN05): 1) Replace 7-ISM8-1 ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade and change frequency channel | NE (7063D RTN01): 1) Replace 7-ISM8-1 ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade and change frequency channel | FE (7068A RTN05): 1) Replace 7-ISM8-1 ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade and change frequency channel | XMC3E |  | 18G |  |  | YPTT | SQ202504210299-YPTT | NR services | SQ202506030434-NR Services // SQ202506030440-NR Services | 2025-04-30 | 2025-04-25 | Completed | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | DOMINIC DAVIES6794000049 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-24 | 2025-04-25 | 2025-04-24 | 2025-04-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-24 | 2025-04-25 | 2025-04-24 | 2025-04-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-25 | 2025-04-30 | 2025-04-25 | 2025-04-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051624 |  | 2025-05-17 | 2025-05-19 | Completed | 2025-05-16 | 2025-05-17 | 2025-05-16 | 2025-05-19 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-06-03 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-06-03 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-03 | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-06-10 | RALPH O'BRYAN HILARY7167000030 | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
9967A-9197B | City Hotel Sibu Market | DU00003451161 | Sarawak | Sarawak | 2.287778 | 111.827028 | WK19 | MAY 24 |  |  | Drop | Pass to Huawei | ZTE | 03. TSS Only |  | TSS |  | 23GHz_0.6m/0.6m_MS_1+0_112MHz | MW Swap | DCN VLAN : 411, PORT NUMBER : GigabitEthernet0/5/0 | [7 empty] | Trintel | SQ202403220491-Trintel |  |  | 2024-04-05 | 2024-04-02 | Completed | 2024-03-04 | 2024-03-05 | 2024-03-04 | 2024-03-05 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-04-02 | 2024-04-05 | 2024-04-02 | 2024-04-02 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-02 | 2024-04-05 | 2024-04-02 | 2024-04-02 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-02 | 2024-04-05 | 2024-04-02 | 2024-04-02 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9046Z-9156A | T3E_0309_Kampung Sekai | DU00003451162 | Sarawak | Sarawak | 2.823103 | 112.195100 | WK19 | MAY 24 |  |  | Drop | Pass to Huawei |  | 03. TSS Only |  | TSS |  | 13GHz_1.8m/1.8m_DP_2+0_28MHz | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/16 | [7 empty] | Trintel | SQ202409100111-Trintel |  |  | 2024-06-28 | 2024-06-24 | Completed | 2024-03-23 | 2024-05-03 | 2024-03-23 | 2024-05-03 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-29 | 2024-03-31 | 2024-03-29 | 2024-03-29 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-29 | 2024-03-31 | 2024-03-29 | 2024-03-29 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-06-24 | 2024-06-28 | 2024-06-24 | 2024-06-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7506B-7570A | Kg. Sg Monyet | DU00003451163 | Sabah | Sabah | 5.859055 | 117.774982 | WK08 | FEB 24 | WK14 | APR 24 | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | 3/4: Cutover done 2/4: D1: TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13GHz_1.2m/1.2m_MDD_4+0_28MHz | MW Swap | [8 empty] | NR Services | SQ202402210496-NR Services | NR services | SQ202404030679-NR Services | 2024-02-29 | 2024-02-29 | Completed | 2024-02-18 | 2024-02-20 | 2024-02-18 | 2024-02-20 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-25 | 2024-02-29 | 2024-02-25 | 2024-02-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-25 | 2024-02-29 | 2024-02-25 | 2024-02-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24032846 |  | 2024-03-29 | 2024-04-01 | Completed | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-04-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-04-04 | RONNEY//LOUIS LUSIN/7167000022 |  | 2024-04-05 | 2024-04-05 | 2024-04-04 | 2026-01-18 | RONNEY//LOUIS LUSIN/7167000022 |  | 2024-04-03 | 2024-04-03 | 2024-04-04 | 2024-04-04 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2026-01-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2026-01-18 | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-04-29 | tseping//wang/6819000006 | Logistic Team | 2024-09-25 | 2024-10-25 | 2024-09-25 | 2024-09-25 | ASTI//GANIS PUTRIANI/6237001358
7072C-7282B | University Apartment 2 | DU00003451164 | Sabah | Sabah | 6.045711 | 116.147123 |  |  | WK07 | FEB 24 | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | Cutover done | AA | PAC |  | MW Remote Upgrade | [8 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-02-17 | 2024-02-17 | 2024-02-17 | 2024-02-17 | MURUGAVALE PRESHANTHAN6237001235 | [17 empty] | 2024-07-26 | 2024-08-26 | 2024-07-26 | 2024-07-26 | ASTI//GANIS PUTRIANI/6237001358
7893A-7064A | Taman Jaya Keningau | DU00003451165 | Sabah | Sabah | 5.346119 | 116.169298 | WK19 | MAY 24 | WK23 | MAY 24 | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | 17/5: D3: Cutover done 16/5: D2: TI WIP 15/5: D1: MOS & TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/1.2m_MDD_1+0_110MHz | MW Swap | [8 empty] | Seri Pancar | SQ202409030650-Seri Pancar // SQ202409120134-Seri Pancar | Magicell | SQ202409120165-Magicell | 2024-03-15 | 2024-03-14 | Completed | 2024-02-22 | 2024-02-23 | 2024-02-22 | 2024-02-22 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2024-03-11 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2024-03-11 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-14 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24051333 |  | 2024-05-14 | 2024-05-14 | Completed | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-15 | 2024-05-31 | 2024-05-14 | 2024-05-18 | RAYINALE BIN LISIAS7018000087 | Magicell TI | 2024-05-15 | 2024-05-31 | 2024-05-14 | 2024-05-18 | RAYINALE BIN LISIAS7018000087 | Magicell TI | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-16 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2024-05-15 | 2024-05-31 | 2024-05-14 | 2024-05-20 | RAYINALE BIN LISIAS7018000087 | 2024-05-15 | 2024-05-31 | 2024-05-14 | 2024-05-16 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | tseping//wang/6819000006 | Logistic Team | 2024-07-26 | 2024-08-26 | 2024-07-26 | 2024-07-26 | ASTI//GANIS PUTRIANI/6237001358
7105B-7042A | Telipok 2 | DU00003451166 | Sabah | Sabah | 6.107162 | 116.210931 | WK08 | FEB 24 | WK21 | MAY 24 | RFS |  | ZTE | 00. Integrated/RFS Done | 27/5: D2: Cutover done 24/5: MOS & TI In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_2+0_110MHz | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/5 | [7 empty] | Seri Pancar | SQ202409030650-Seri Pancar // SQ202409120134-Seri Pancar | NR services | SQ202407020282-NR Services | 2024-02-29 | 2024-02-27 | Completed | 2024-02-21 | 2024-02-22 | 2024-02-21 | 2024-02-21 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-25 | 2024-02-29 | 2024-02-25 | 2024-02-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-25 | 2024-02-29 | 2024-02-25 | 2024-02-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-02-27 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24052121 |  | 2024-05-22 | 2024-05-21 | Completed | 2024-05-21 | 2024-05-22 | 2024-05-21 | 2024-05-21 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-24 | 2024-05-31 | 2024-05-24 | 2024-05-27 | NEVILLE JUDE RONNIE7167000013 | NR Service TI | 2024-05-24 | 2024-05-31 | 2024-05-24 | 2024-05-27 | NEVILLE JUDE RONNIE7167000013 | NR Service TI | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-05-27 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-05-24 | 2024-05-31 | 2024-05-24 | 2024-05-28 | NEVILLE JUDE RONNIE7167000013 | 2024-05-24 | 2024-05-31 | 2024-05-24 | 2024-05-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
1220D_HU_2 | SimpangPuncak Alam (REL) | DU00006825201 | Central | Selangor | 3.247838 | 101.469325 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4599D_AD | Pala PlaceApartment (REL) | DU00006825202 | Northern | Penang | 5.459099 | 100.219287 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4706B_AD | KAMDAR SeriManjung | DU00006825203 | Northern | Perak | 4.205511 | 100.674890 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9252Z_HU_1 | Simpang KgTanjung Limbang | DU00006825204 | Sarawak | Sarawak | 4.618440 | 114.888070 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7376K2_EVT | PESTA KAAMATAN2026 PAITAN DISTRICT LEVEL | DU00006825205 | Sabah | Sabah | 6.054020 | 117.340580 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1220D_HU_1 | Simpang PuncakAlam (REL) | DU00006825206 | Central | Selangor | 3.247838 | 101.469325 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
B01348-4591A | B062B_B01348OD_T3_PT7SGPJG | DU00004576726 | Central | Selangor | 3.708610 | 101.026610 | WK10 | MAR 25 | WK10 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 7/3/2025 : Cutover done 28/2/2025 : Installation complete, pending cutover due to waiting link 4591A-B01049 reroute 27/2/2025 : NE installation complete, pending install FE site due to raining day 21/1/2025 : EDOTCO (M) SDN BHD - TOWER 61M LAND - NE site B01348 B062B_B01348OD_T3_PT7SGPJG, Digi OB - 45M 4 Legged Tower - FE site 4591A Kg.Tebok Pulai | TSS+AA+TI | L1+ATP+PAC | 15G 4+0 1.2m/1.2m MS XMC3 sub A/B with coupler NE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 2 x 15G XMC3 sub A Lo 4) 2 x 15G XMC3 sub B Lo 5) 2 x 15G coupler 6) 2 x 15G waveguide 7) 1 x 15G 1.2m MS 8) 4 run IF cable FE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 2 x 15G XMC3 sub A Hi 4) 2 x 15G XMC3 sub B Hi 5) 2 x 15G coupler 6) 2 x 15G waveguide 7) 1 x 15G 1.2m MS 8) 4 run IF cable | MW Parallel Link | To build new 4+0 link B00695-B01348-4591A-B01049 to offload traffic from congested MW link B00695-4475A Impact sites: 1771C,2637A Tx route before: B01348/B01348-B00298 Tx route after: B01348-4591A-B01049 NE (B01348): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Cascade new RTN GE1 to new RTN GE1 installed under DU B00695-B01348 5) Migrate 1771C and 2637A traffic to new 4+0 link FE (4591A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) New uplink 4591A-B01049 to be installed under DU 4591A-B01049 (Tx Mini Project) 5) Migrate 1771C and 2637A traffic to new route. | [7 empty] | GTSB | SQ202504170454-GTSB | GTSB | SQ202503200152-GTSB // SQ202503200154-GTSB // SQ202504260131-GTSB | 2025-05-01 | 2025-04-30 | Completed | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-04-10 | 2025-04-24 | 2025-04-10 | 2025-04-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-15 | 2025-04-16 | 2025-04-15 | 2025-04-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-30 | 2025-05-01 | 2025-04-30 | 2025-04-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022003 |  | 2025-02-21 | 2025-02-26 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-26 | 2025-03-31 | 2025-02-26 | 2025-03-24 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-02-26 | 2025-03-31 | 2025-02-26 | 2025-03-24 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-13 | 2025-02-26 | 2025-03-31 | 2025-02-26 | 2025-03-24 | Aminuddin bin che azibA0563734967123169280 | 2025-05-28: 2025-02-26; 2025-05-28: 2025-03-31; 2025-05-28: 2025-02-26; 2025-05-28: 2025-03-07 |  |  | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202504140801-GCI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | EZRIN TASNIM BIN ABDUL GANI6798000128
B00695-B01348 | B062A_B00695OD_PT13SGPJG | DU00004576727 | Central | Selangor | 3.726250 | 101.078970 | WK10 | MAR 25 | WK10 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 7/3/2025 : Cutover done 28/2/2025 : Installation complete, pending cutover due to waiting link 4591A-B01049 reroute 27/2/2025 : FE installation complete, pending install NE site 21/1/2025 : EDOTCO (M) SDN BHD - TOWER 61M LAND - NE site B00695 B062A_B00695OD_PT13SGPJG, EDOTCO (M) SDN BHD - TOWER 61M LAND - FE site B01348 B062B_B01348OD_T3_PT7SGPJG | TSS+AA+TI | L1+ATP+PAC | 15G 4+0 1.2m/1.2m MS XMC3 sub A/B with coupler NE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 2 x 15G XMC3 sub A Hi 4) 2 x 15G XMC3 sub B Hi 5) 2 x 15G coupler 6) 2 x 15G waveguide 7) 1 x 15G 1.2m MS 8) 4 run IF cable FE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 2 x 15G XMC3 sub A Lo 4) 2 x 15G XMC3 sub B Lo 5) 2 x 15G coupler 6) 2 x 15G waveguide 7) 1 x 15G 1.2m MS 8) 4 run IF cable | MW New Link / Reroute | To build new 4+0 link B00695-B01348-4591A-B01049 to offload traffic from congested MW link B00695-4475A Impact sites: 1771C,2637A Tx route before: B00695/B00695-4475A Tx route after: B00695/B00695-B01348-4591A-B01049 NE (B00695): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Transfer IF cable for link to 1771C from RTN01 4-ISM8 to new RTN 7-ISM8 5) Cascade RTN02 GE1 to new RTN GE1 6) Migrate 1771C and 2637A traffic to new 4+0 link FE (B01348): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Cascade new RTN GE1 to new RTN GE1 installed under DU B01348-4591A 5) Migrate 1771C and 2637A traffic to new 4+0 link | [7 empty] | GTSB | SQ202504170454-GTSB | GTSB | SQ202503200152-GTSB // SQ202503200154-GTSB // SQ202504260131-GTSB | 2025-06-18 | 2025-06-30 | Completed | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-04-10 | 2025-04-24 | 2025-04-10 | 2025-04-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-17 | 2025-06-18 | 2025-06-17 | 2025-06-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022017 |  | 2025-02-21 | 2025-02-26 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-26 | 2025-03-31 | 2025-02-26 | 2025-03-24 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-02-26 | 2025-03-31 | 2025-02-26 | 2025-03-24 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-02-26 | 2025-03-31 | 2025-02-26 | 2025-03-24 | Aminuddin bin che azibA0563734967123169280 | 2025-05-28: 2025-02-26; 2025-05-28: 2025-03-31; 2025-05-28: 2025-02-26; 2025-05-28: 2025-02-28 |  |  | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358
2527A-1156A | Fruit Valley | DU00004576728 | Central | Selangor | 3.387330 | 101.450699 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 21/1/2025 : Cutover done 20/1/2025 : SBC KJS - 76M 3 Legged Tower - NE site 2527A Fruit Valley, Digi OB - 60M 4 Legged Tower - FE site 1156A Btg. Berjuntai | TSS+AA+TI | L1+ATP+PAC | 4xISM8 card | MW Hardware Upgrade | Existing link 2527A-1156A 15G 2+0 using ODU XMC5D To install new ISM8 card at NE and FE IDU To enable CA and re-config the link as 4+0 CA Impact site: 2527A,B01179 NE (2527A RTN01) 1. Add ISM8 slot 3 and 4 2. Transfer IF cable for ODU V to 3-ISM8-1 3. Transfer IF cable for ODU H to 4-ISM8-1 4. Configure 4+0 CA NE (1156A RTN04) 1. Add ISM8 slot 3 and 4 2. Transfer IF cable for ODU V to 3-ISM8-1 3. Transfer IF cable for ODU H to 4-ISM8-1 4. Configure 4+0 CA | [7 empty] | GTSB | SQ202501210409-GTSB | GTSB | SQ202412310378-GTSB // SQ202504260131-GTSB | 2025-03-03 | 2025-02-24 | Completed | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-01-31 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-17 | 2025-03-03 | 2025-02-17 | 2025-02-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | TSSR Approved by CD. | DOWMY24121823 |  | 2024-12-19 | 2025-02-27 | Completed | 2024-12-18 | 2024-12-19 | 2024-12-18 | 2025-02-27 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-02-27 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-03-14 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-03-24 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-05-28: 2025-01-20; 2025-05-28: 2025-01-31; 2025-05-28: 2025-01-20; 2025-05-28: 2025-01-21 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
1987A_LOS | Tmn Bayu Perdana | DU00004654573 | Central | Selangor | 3.019085 | 101.432379 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_1987A 18G_0.6m(MDD) x1. RTN910A x1. XMC_5D-2+0 , Sub A_Lo x1. FE_3532A 18G_0.6m(MDD) x1. RTN910A x1. XMC_5D-2+0 , Sub A_Hi x1. | MW New Link / Reroute | Link Reroute to New FE 3532A due to LOS Block Site Impacted : 1987A , 1376H , 1104A and 1603B. NE_1987A 1.Install new 18G_0.6m(MDD) 2.Install new RTN910A ,7_ISM8-2+0 3.Install new XMC_5D-2+0 , Sub A_Lo 4.Create EPLA and service cross connect. 5.Migrate service to new FE route with new config. 6.Decom existing MW (1987A-1090A). FE_3532A 1.Install new 18G_0.6m(MDD). 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_5D-2+0 , Sub A_Hi. 4.Create EPLA and service cross connect. 5.Create new in band DCN. 6.Migrate service to new FE route with new config. 7.Decom existing MW (1090A-1987A). | [7 empty] | YPTT | SQ202412180491-YPTT | YPTT | SQ202412310399-YPTT // // SQ202504260171-YPTT |  |  | Ongoing | 2025-03-11 | 2025-03-31 | 2025-03-11 | 2025-03-11 | MOHD//SHAHREEZAN BIN RAZALI/6794000119 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24121928 |  | 2024-12-20 |  | Ongoing | 2024-12-19 | 2024-12-20 | 2024-12-19 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2024-12-27 | 2025-12-31 | 2024-12-27 |  | JOSEF/BIN/ABSARI/6794000120 | YPTT TI | 2024-12-27 | 2025-12-31 | 2024-12-27 | 2025-06-05 | JOSEF/BIN/ABSARI/6794000120 | YPTT TI | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-12-27 | 2025-12-31 | 2024-12-27 | 2025-01-03 | JOSEF/BIN/ABSARI/6794000120 | 2024-12-27 | 2025-12-31 | 2024-12-27 | 2024-12-27 | 2025-01-07 | 2025-01-07 | 2025-01-07 | 2025-01-07 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202509250653-GTSB | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | AB.RAHMAN//BIN MAT NOOH/6237001519
S00567_LOS | S104A_S00567OD_CB_KGSAGINDAIBARU | DU00006661045 | Sabah | Sabah | 5.847055 | 116.815754 | [21 empty] | Seri Pancar | SQ202603170104-Seri Pancar |  |  |  |  | Ongoing | 2026-03-15 | 2026-03-31 | 2026-03-16 | 2026-03-17 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202603170137-GTSB
2684A20_LOS | pBTSKg Matupang | DU00006661046 | Sabah | Sabah | 5.793952 | 116.818765 | [21 empty] | Seri Pancar | SQ202603170104-Seri Pancar |  |  |  |  | Ongoing | 2026-03-15 | 2026-03-31 | 2026-03-16 | 2026-03-17 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-03-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202603170137-GTSB
K00323_HU | K006A_K00323OD_KGIMAM | DU00006661047 | Northern | Kedah | 6.335325 | 100.377027 | [7 empty] | 05. Doable | 29/4: MRCF update for K01060_HU. Originally this site no decom 20/4: Pending L1 | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M_512QAM_EPLA NE_K00323/4192K New 13G_1.2M(MDD) x1. New RTN910AF. New ISM8 x1. New XMC_5D Pro, Sub A_Hi x1. New IF cables with suitable length and type x2 RUN. FE_4183K/K00116 New 13G_1.2M(MDD) x1. New RTN910AF. New ISM8 x1. New XMC_5D Pro, Sub A_Lo x1. New IF cables with suitable length and type x2 RUN. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link K00323/4192K-4183K/K00116, 15G_4+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link K00323/4192K-4183K/K00116, 15G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM&2048QAM_EPLA. Site Impacted : 4192K/K00323 & K01060. NE_K00323/4192K 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub A_Hi x1 to existing RTN910AF(NEID 183-29983) ISM8 slot 03(Port 1 & 2). 5.Build new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Later, combine existing HW MW Link K00323/4192K-4183K/K00116, 15G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. Become 13g&15G_6+0_28MHZ_512QAM&2048QAM_EPLA. 8.Migrate traffics 4192K/K00323 & K01060 into new HW MW Link 13G&15G_6+0_28MHZ_512QAM&2048QAM_EPLA. FE_4183K/K00116 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub A_Hi x1 to existing RTN910AF(NEID 183-29989) ISM8 slot 03(Port 1 & 2). 5.Build new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Later, combine existing HW MW Link K00323/4192K-4183K/K00116, 15G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM&2048QAM_EPLA. 8.Migrate traffics 4192K/K00323 & K01060 into into existing PTN/Cisco Router port. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link K00323/4192K-4183K/K00116, 15G_4+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link K00323/4192K-4183K/K00116, 15G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM&2048QAM_EPLA. Site Impacted : 4192K/K00323 & K01060. NE_K00323/4192K 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub A_Hi x1 to existing RTN910AF(NEID 183-29983) ISM8 slot 03(Port 1 & 2). 5.Build new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Later, combine existing HW MW Link K00323/4192K-4183K/K00116, 15G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. Become 13g&15G_6+0_28MHZ_512QAM&2048QAM_EPLA. 8.Migrate traffics 4192K/K00323 & K01060 into new HW MW Link 13G&15G_6+0_28MHZ_512QAM&2048QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link K00323/4192K-4183K/K00116, 15G_4+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link K00323/4192K-4183K/K00116, 15G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM&2048QAM_EPLA. Site Impacted : 4192K/K00323 & K01060. FE_4183K/K00116 1.Install new 13G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 183-29989) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub A_Hi x1 to existing RTN910AF(NEID 183-29989) ISM8 slot 03(Port 1 & 2). 5.Build new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Later, combine existing HW MW Link K00323/4192K-4183K/K00116, 15G_4+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link K00323/4192K-4183K/K00116, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM&2048QAM_EPLA. 8.Migrate traffics 4192K/K00323 & K01060 into into existing PTN/Cisco Router port. | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD) x1 | 13G_1.2M(MDD) x1 | GCI | SQ202603180478-GCI | GCI | SQ202603180471-GCI // SQ202603180473-GCI |  |  | Ongoing | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031333 |  | 2026-03-14 | 2026-03-26 | Completed | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-06 | 2026-04-30 | 2026-04-06 | 2026-04-25 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-04-06 | 2026-04-30 | 2026-04-06 | 2026-04-25 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-13 | 2026-04-06 | 2026-04-30 | 2026-04-06 | 2026-04-25 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | 2026-04-06 | 2026-04-30 | 2026-04-06 | 2026-04-07 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | NG HONG JIE7018000036 | Logistic Team | [5 empty] | GTSB | SQ202603170130-GTSB
9007D_HU | Taman SepakatJaya | DU00006661048 | Sarawak | Sarawak | 1.593894 | 110.415441 | [9 empty] | TSS+AA+TI |  |  | MW Parallel Link | Existing link 15G_2+0_28M Install parallel link 23G_1+0_56M Site Impacted : 9007D. NE_9007D 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 9007D_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A_Hi. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No decomm MW link. FE_9145B 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 9145B_RTN02 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A_Lo. 5.Create service cross connect and EPA with existing MW link. 6.Traffic migrate to new parallel link. 7.No decomm MW link. | Existing link 15G_2+0_28M Install parallel link 23G_1+0_56M Site Impacted : 9007D. NE_9007D 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 9007D_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A_Hi. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No decomm MW link. | Existing link 15G_2+0_28M Install parallel link 23G_1+0_56M Site Impacted : 9007D. FE_9145B 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 9145B_RTN02 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A_Lo. 5.Create service cross connect and EPA with existing MW link. 6.Traffic migrate to new parallel link. 7.No decomm MW link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202603170140-GCI | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | CHEONG/SENG/WAH/7018000306
K01060_HU | JEN1_0001V_K01060_Kg.Kubang Chenok | DU00006661049 | Northern | Kedah | 6.372703 | 100.363999 | [7 empty] | 05. Doable | 29/4: Material returned but MRCF update at K00323_HU. Wrong DU update. To amend by GCI 20/4: Pending L1 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M_512QAM_EPLA(Without CA) NE_K01060/4044P New 13G_1.2M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. FE_K00323/4192K New 13G_1.2M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x2. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. | MW Swap | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 15G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link K01060-Q00323/4192K, 15G_2+0_28MHZ_512QAM_EPLA. Swap existing with new HW MW Link K01060-Q00323/4192K, 13G_4+0_28MHZ_512QAM_EPLA. Later, decom existing HW MW Link K01060-Q00323/4192K, 15G_2+0_28MHZ_512QAM_EPLA. Site Impacted : K01060/4044P. NE_K01060/4044P 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN01) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Lay new IF cables from new XMC_5D Pro to new RTN910AF(RTN01) into slot 03(Port 1 & 2) & slot 04(Port 1 & 2). 4.Build new HW MW Link K01060-Q00323/4192K, 13G_4+0_28MHZ_512QAM_EPLA. 5.Re-use existing xC Vlan DCN & Vlan Services. 6.Migrate traffic K01060/4044P to new HW MW Link K01060-Q00323/4192K, 13G_4+0_28MHZ_512QAM_EPLA. 7.Later, decom existing HW MW Link K01060-Q00323/4192K, 15G_2+0_28MHZ_512QAM_EPLA. FE_K00323/4192K 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN01) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Lay new IF cables from new XMC_5D Pro to new RTN910AF(RTN01) into slot 03(Port 1 & 2) & slot 04(Port 1 & 2). 4.Build new HW MW Link K01060-Q00323/4192K, 13G_4+0_28MHZ_512QAM_EPLA. 5.Enable 8-EM6-1 of new RTN910AF(RTN01) and patching to port 8-EM6-5 of existing RTN910AF(NEID 183-29983). 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic K01060/4044P to existing port at PTN/Cisco. 8.Later, decom existing HW MW Link K01060-Q00323/4192K, 15G_2+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 15G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link K01060-Q00323/4192K, 15G_2+0_28MHZ_512QAM_EPLA. Swap existing with new HW MW Link K01060-Q00323/4192K, 13G_4+0_28MHZ_512QAM_EPLA. Later, decom existing HW MW Link K01060-Q00323/4192K, 15G_2+0_28MHZ_512QAM_EPLA. Site Impacted : K01060/4044P. NE_K01060/4044P 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN01) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Lay new IF cables from new XMC_5D Pro to new RTN910AF(RTN01) into slot 03(Port 1 & 2) & slot 04(Port 1 & 2). 4.Build new HW MW Link K01060-Q00323/4192K, 13G_4+0_28MHZ_512QAM_EPLA. 5.Re-use existing xC Vlan DCN & Vlan Services. 6.Migrate traffic K01060/4044P to new HW MW Link K01060-Q00323/4192K, 13G_4+0_28MHZ_512QAM_EPLA. 7.Later, decom existing HW MW Link K01060-Q00323/4192K, 15G_2+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 15G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link K01060-Q00323/4192K, 15G_2+0_28MHZ_512QAM_EPLA. Swap existing with new HW MW Link K01060-Q00323/4192K, 13G_4+0_28MHZ_512QAM_EPLA. Later, decom existing HW MW Link K01060-Q00323/4192K, 15G_2+0_28MHZ_512QAM_EPLA. Site Impacted : K01060/4044P. FE_K00323/4192K 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN01) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Lay new IF cables from new XMC_5D Pro to new RTN910AF(RTN01) into slot 03(Port 1 & 2) & slot 04(Port 1 & 2). 4.Build new HW MW Link K01060-Q00323/4192K, 13G_4+0_28MHZ_512QAM_EPLA. 5.Enable 8-EM6-1 of new RTN910AF(RTN01) and patching to port 8-EM6-5 of existing RTN910AF(NEID 183-29983). 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic K01060/4044P to existing port at PTN/Cisco. 8.Later, decom existing HW MW Link K01060-Q00323/4192K, 15G_2+0_28MHZ_512QAM_EPLA. | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD) x1 | 13G_1.2M(MDD) x1 | GCI | SQ202603180478-GCI | GCI | SQ202603180471-GCI // SQ202603180473-GCI |  |  | Ongoing | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031334 |  | 2026-03-14 | 2026-03-26 | Completed | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-06 | 2026-04-30 | 2026-04-06 | 2026-05-03 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-04-06 | 2026-04-30 | 2026-04-06 | 2026-05-03 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-13 | 2026-04-06 | 2026-04-30 | 2026-04-06 | 2026-05-03 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | 2025-05-28: 2026-04-06; 2025-05-28: 2026-04-30; 2025-05-28: 2026-04-06; 2025-05-28: 2026-04-08 | [7 empty] | GTSB | SQ202603170130-GTSB
K00389_HU | K005C_K00389OD_SPG3PASIR | DU00006661050 | Northern | Kedah | 5.716000 | 100.379500 | [7 empty] | 05. Doable |  | TSS+AA+TI |  | 4X ISM8 CARD 2X RTN910A 1X 13G 1.2M MDD ANTENNA 1X 13G 1.8M MDD ANTENNA 1x ODU 13G XMC5D SUB A HI 1x ODU 13G XMC5D SUB A LO | MW New Link / Reroute | MW NEW LINK K00389-4779A WITH HUAWEI_13G_4+0_1.2M/1.8M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_A_WITH CA_LINK_10.62KM IMPACTED: 4630K PATCH NEW LINK TO LL K00109 PATCH IDU 4434K RTN03 TO NEW LINK IDU NEW LINK CARRY TRAFFIC 4630K RTN01-4434K RTN03 | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. PATCH IDU 4434K RTN03 TO NEW LINK IDU | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO NEW LL PORT 6. NEW LINK CARRY TRAFFIC 4630K RTN01-4434K RTN03] to [1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO NEW LL PORT 6. NEW LINK CARRY TRAFFIC 4630K RTN01-4434K RTN03 | XMC5D | MDD | 13G | 1.2 | 1.8 | GCI | SQ202603180478-GCI | GCI | SQ202603180471-GCI // SQ202603180473-GCI |  |  | Ongoing | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031076 |  | 2026-03-11 | 2026-04-07 | Completed | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-04-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-30 | 2026-04-14 |  | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-04-14 | 2026-04-30 | 2026-04-14 |  | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | [7 empty] | 2026-04-14 | 2026-04-30 | 2026-04-14 |  | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | 2025-05-28: 2026-04-14; 2025-05-28: 2026-04-30; 2025-05-28: 2026-04-14; 2025-05-28: 2026-04-14 | [7 empty] | GCI | SQ202603170124-GCI | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | EZRIN TASNIM BIN ABDUL GANI6798000128
2382A_AD | Taman Manjalara | DU00006661051 | Central | Kuala Lumpur | 3.193061 | 101.629078 | [7 empty] | 04. Pending DO |  | TSS+TI |  | Fiber patch cord x 1 pairs | BBU Patching | NE_2382A BBU patching to access port : 0/0/3 | NE_2382A BBU patching to access port : 0/0/3 | [6 empty] | MTK | SQ202603180465-MTK | MTK | SQ202603180462-MTK |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202603170116-GCI | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | CHEONG/SENG/WAH/7018000306
7355C_AD | Pulau Mataking | DU00006666097 | Sabah | Sabah | 4.579300 | 118.948700 | [7 empty] | 05. TI WIP |  | TSS+AA+TI+Dismantle |  | 13G_3(1+1)_28M_512QAM_EPLA_SD NE_7355C New 13G_1.2M(MDD) x2(x1 Main & x1 Diversity). New RTN910AF(RTN02). New ISM8 x2. New XMC_5D Pro, Sub A_Lo x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. FE_7044K/S00974 New 13G_1.2M(MDD) x2(x1 Main & x1 Diversity). New RTN910AF(RTN02). New ISM8 x2. New XMC_5D Pro, Sub A_Hi x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.IF NO FREQUENCY SCANNING PERFORM, SUGGEST TO BRING TOGETHER SUB BAND B DUE TO LOGISTIC ISSUE**** Existing HW MW Link 7355C-7625B, 7G_1+0_28MHZ_4096QAM. Build new HW MW Link 7355C-7044K/S00974, 13G_3(1+1)_28M_512QAM_EPLA_SD. Later, decom existing HW MW Link 7355C-7625B, 7G_1+0_28MHZ_4096QAM. Site Impacted : 7355C. NE_7355C 1.New 13G_1.2M(MDD) x2(x1 Main & x1 Diversity). 2.Install new RTN910AF(RTN02) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Lo x2. -Install ODU Sub Band A(CH1) Lo to Main Antenna(Vertical&Horizontal). -Install ODU Sub Band A(CH1) Lo to Diversity Antenna(Vertical&Horizontal). -Lay 1st IF cable from ODU CH1 Lo of Main Antenna(Vertical) to ISM8 slot 03 Port 1. -Lay 2nd IF cable from ODU CH3 Lo of Main Antenna(Horizontal) to ISM8 slot 07 Port 1. -Lay 3rd IF cable from ODU CH1 Lo of Diversity Antenna(Vertical) to ISM8 slot 04 Port 1. -Lay 4th IF cable from ODU CH3 Lo of Diversity Antenna(Horizontal) to ISM8 slot 07 Port 2. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Patching existing BBU to port 8-EM6-1 of new RTN910AF(RTN02). 6.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 7.Migrate traffics 7355C into new HW MW Link 7355C-7044K/S00974, 13G_3(1+1)_28M_512QAM_EPLA_SD. 8.Later, decom existing HW MW Link 7355C-7625B, 7G_1+0_28MHZ_4096QAM. FE_7044K/S00974 1.New 13G_1.2M(MDD) x2(x1 Main & x1 Diversity). 2.Install new RTN910AF(RTN02) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Hi x2. -Install ODU Sub Band A(CH1) Hi to Main Antenna(Vertical&Horizontal). -Install ODU Sub Band A(CH1) Hi to Diversity Antenna(Vertical&Horizontal). -Lay 1st IF cable from ODU CH1 Hi of Main Antenna(Vertical) to ISM8 slot 03 Port 1. -Lay 2nd IF cable from ODU CH3 Hi of Main Antenna(Horizontal) to ISM8 slot 07 Port 1. -Lay 3rd IF cable from ODU CH1 Hi of Diversity Antenna(Vertical) to ISM8 slot 04 Port 1. -Lay 4th IF cable from ODU CH3 Hi of Diversity Antenna(Horizontal) to ISM8 slot 07 Port 2. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Enable port 17-SLF2EM6-3 of existing RTN950A(RTN01, NEID 9-23028). 6.Perform cascading in between port 8-EM6-1 of new RTN910AF(RTN02) and port 17-SLF2EM6-3 of existing RTN950A(RTN01, NEID 9-23028). 7.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 8.Migrate traffics 7355C into same port at IBeam(CP 7205A) similar to existing traffics such as 7044K/S00974 and etc. 9.Later, decom existing HW MW Link 7355C-7625B, 7G_1+0_28MHZ_4096QAM. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.IF NO FREQUENCY SCANNING PERFORM, SUGGEST TO BRING TOGETHER SUB BAND B DUE TO LOGISTIC ISSUE**** Existing HW MW Link 7355C-7625B, 7G_1+0_28MHZ_4096QAM. Build new HW MW Link 7355C-7044K/S00974, 13G_3(1+1)_28M_512QAM_EPLA_SD. Later, decom existing HW MW Link 7355C-7625B, 7G_1+0_28MHZ_4096QAM. Site Impacted : 7355C. NE_7355C 1.New 13G_1.2M(MDD) x2(x1 Main & x1 Diversity). 2.Install new RTN910AF(RTN02) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Lo x2. -Install ODU Sub Band A(CH1) Lo to Main Antenna(Vertical&Horizontal). -Install ODU Sub Band A(CH1) Lo to Diversity Antenna(Vertical&Horizontal). -Lay 1st IF cable from ODU CH1 Lo of Main Antenna(Vertical) to ISM8 slot 03 Port 1. -Lay 2nd IF cable from ODU CH3 Lo of Main Antenna(Horizontal) to ISM8 slot 07 Port 1. -Lay 3rd IF cable from ODU CH1 Lo of Diversity Antenna(Vertical) to ISM8 slot 04 Port 1. -Lay 4th IF cable from ODU CH3 Lo of Diversity Antenna(Horizontal) to ISM8 slot 07 Port 2. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Patching existing BBU to port 8-EM6-1 of new RTN910AF(RTN02). 6.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 7.Migrate traffics 7355C into new HW MW Link 7355C-7044K/S00974, 13G_3(1+1)_28M_512QAM_EPLA_SD. 8.Later, decom existing HW MW Link 7355C-7625B, 7G_1+0_28MHZ_4096QAM. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.IF NO FREQUENCY SCANNING PERFORM, SUGGEST TO BRING TOGETHER SUB BAND B DUE TO LOGISTIC ISSUE**** Existing HW MW Link 7355C-7625B, 7G_1+0_28MHZ_4096QAM. Build new HW MW Link 7355C-7044K/S00974, 13G_3(1+1)_28M_512QAM_EPLA_SD. Later, decom existing HW MW Link 7355C-7625B, 7G_1+0_28MHZ_4096QAM. Site Impacted : 7355C. FE_7044K/S00974 1.New 13G_1.2M(MDD) x2(x1 Main & x1 Diversity). 2.Install new RTN910AF(RTN02) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Hi x2. -Install ODU Sub Band A(CH1) Hi to Main Antenna(Vertical&Horizontal). -Install ODU Sub Band A(CH1) Hi to Diversity Antenna(Vertical&Horizontal). -Lay 1st IF cable from ODU CH1 Hi of Main Antenna(Vertical) to ISM8 slot 03 Port 1. -Lay 2nd IF cable from ODU CH3 Hi of Main Antenna(Horizontal) to ISM8 slot 07 Port 1. -Lay 3rd IF cable from ODU CH1 Hi of Diversity Antenna(Vertical) to ISM8 slot 04 Port 1. -Lay 4th IF cable from ODU CH3 Hi of Diversity Antenna(Horizontal) to ISM8 slot 07 Port 2. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Enable port 17-SLF2EM6-3 of existing RTN950A(RTN01, NEID 9-23028). 6.Perform cascading in between port 8-EM6-1 of new RTN910AF(RTN02) and port 17-SLF2EM6-3 of existing RTN950A(RTN01, NEID 9-23028). 7.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 8.Migrate traffics 7355C into same port at IBeam(CP 7205A) similar to existing traffics such as 7044K/S00974 and etc. 9.Later, decom existing HW MW Link 7355C-7625B, 7G_1+0_28MHZ_4096QAM. | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD) x2(x1 Main & x1 Diversity) | 13G_1.2M(MDD) x2(x1 Main & x1 Diversity) | GCI | SQ202604030213-GCI | GCI | SQ202603170090-GCI // SQ202603170093-GCI |  |  | Ongoing | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031137 |  | 2026-04-04 | 2026-03-15 | Completed | 2026-03-15 | 2026-04-04 | 2026-03-15 | 2026-03-15 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-15 | 2026-04-04 | 2026-03-15 | 2026-03-27 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-03-15 | 2026-04-04 | 2026-03-15 |  | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | [7 empty] | 2026-03-15 | 2026-04-04 | 2026-03-15 |  | RAI//JORDAN RICHARD RIBU/7018000190 | 2025-05-28: 2026-03-15; 2025-05-28: 2026-04-04; 2025-05-28: 2026-03-15; 2025-05-28: 2026-03-17 | [7 empty] | GTSB | SQ202603170137-GTSB
2984A_HU | MEX HW KM22.9 | DU00006004404 | Central | Selangor | 2.964073 | 101.655771 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_2984A 23G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Hi x2. FE_1313B 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. | MW New Link / Reroute | Install new link 2984A-1313B to support 1865B & 2984A. (Refer DU ID 1865B_HU). Site Impacted : 1865B , 2984A. TSS Survey for 2984A - 1313B is required. NE_2984A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 2984A_RTN02 ( ID : 34215). 3.Install new 4_ISM8-2+0 into existing 2984A_RTN02. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.No link to be decom. FE_1313B 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A . 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create new In band DCN. 6.No link to be decom. | Install new link 2984A-1313B to support 1865B & 2984A. (Refer DU ID 1865B_HU). Site Impacted : 1865B , 2984A. TSS Survey for 2984A - 1313B is required. NE_2984A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 2984A_RTN02 ( ID : 34215). 3.Install new 4_ISM8-2+0 into existing 2984A_RTN02. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.No link to be decom. | Install new link 2984A-1313B to support 1865B & 2984A. (Refer DU ID 1865B_HU). Site Impacted : 1865B , 2984A. TSS Survey for 2984A - 1313B is required. FE_1313B 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A . 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create new In band DCN. 6.No link to be decom. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202509030923-GTSB | GTSB | SQ202509030913-GTSB // SQ202509030917-GTSB | 2026-01-14 | 2026-01-13 | Completed | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | KANNAN A/L RAMACHANDRAN6799000115 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-24 | 2026-01-07 | 2025-12-24 | 2025-12-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092537 |  | 2025-09-26 | 2025-09-30 | Completed | 2025-09-25 | 2025-09-26 | 2025-09-25 | 2025-09-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-12-13 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2026-01-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-13 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2026-01-26 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2026-01-26 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | NG HONG JIE7018000036 | Logistic Team | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509041074-GCI | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | CHEONG/SENG/WAH/7018000306
1225H_LOS | 99 Speedmart KL TMN SERI SENTOSA | DU00006010683 | Central | Kuala Lumpur | 3.072790 | 101.651667 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | 1225H reroute to new FE 3726A due to LOS Block. Site Impacted : 1225H. NE_1225H. 1.Install new RTN510 with relocate Boom location. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (1225H-1357B). FE_3726A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5. ETH patching to existing 3726A_RTN02_GE1 ( ID : 42877). 6.Traffic migrate to new route FE site with new NLOS. 7.Decom existing NLOS Radio (1357B - 1225H). | 1225H reroute to new FE 3726A due to LOS Block. Site Impacted : 1225H. NE_1225H. 1.Install new RTN510 with relocate Boom location. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (1225H-1357B). | 1225H reroute to new FE 3726A due to LOS Block. Site Impacted : 1225H. FE_3726A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5. ETH patching to existing 3726A_RTN02_GE1 ( ID : 42877). 6.Traffic migrate to new route FE site with new NLOS. 7.Decom existing NLOS Radio (1357B - 1225H). | [5 empty] | Magicell | SQ202509240830-Magicell | Magicell | SQ202510230920-Magicell // SQ202510230933-Magicell | 2025-11-12 | 2025-11-11 | Completed | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-11 | 2025-11-12 | 2025-11-11 | 2025-11-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100755 |  | 2025-10-08 | 2025-10-09 | Completed | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-21 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-21 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-12 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-12-05 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-10 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202510100626-GCI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | CHEONG/SENG/WAH/7018000306
7475B_HU | Kg Hamparan Badai | DU00006409252 | Sabah | Sabah | 5.366780 | 119.194140 | [7 empty] | 05. Doable |  | TSS+AA+TI |  | 13G_2+0_28M_512QAM_EPLA NE_7475B New 13G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-43940). New ISM8 x1. New XMC_5D Pro, Sub A_Hi x1. New IF cables with suitable length x2 RUN. FE_7623B New 13G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-43939). New ISM8 x1. New XMC_5D Pro, Sub A_Lo x1. New IF cables with suitable length x2 RUN. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL.**** Existing HW MW Link 7475B-7623B, 13G_4+0_28MHZ_512QAM_EPLA Build new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7475B-7623B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7475B. NE_7475B 1.Install new 13G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-43940) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. Build new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Later, combine existing HW MW Link 7475B-7623B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. FE_7623B 1.Install new 13G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-43939) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. Build new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Later, combine existing HW MW Link 7475B-7623B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL.**** Existing HW MW Link 7475B-7623B, 13G_4+0_28MHZ_512QAM_EPLA Build new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7475B-7623B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7475B. NE_7475B 1.Install new 13G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-43940) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. Build new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Later, combine existing HW MW Link 7475B-7623B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL.**** Existing HW MW Link 7475B-7623B, 13G_4+0_28MHZ_512QAM_EPLA Build new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7475B-7623B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7475B. FE_7623B 1.Install new 13G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-43939) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. Build new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Later, combine existing HW MW Link 7475B-7623B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7475B-7623B, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD) x1. | 13G_1.2M(MDD) x1. | Seri Pancar |  | GCI | SQ202604200224-GCI // SQ202604200228-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040845 |  | 2026-04-09 | 2026-04-13 | Completed | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-03 | 2026-05-31 | 2026-05-05 | 2026-05-05 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | [33 empty] | GTSB | SQ202512180098-GTSB
7146D_AD | Gunosukod | DU00006409253 | Sabah | Sabah | 5.905948 | 116.084917 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 18G_1+0_55M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_256QAM_778M. Site Impacted : 7146D. NE_7146D 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). FE_7267A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). | Link Existing HW 18G_1+0_55M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_256QAM_778M. Site Impacted : 7146D. NE_7146D 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). | Link Existing HW 18G_1+0_55M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_256QAM_778M. Site Impacted : 7146D. FE_7267A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). |  |  | 18G | [8 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-16 | [15 empty] | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202512180098-GTSB
7299R_AD | Sk Giok (Kg Giok) | DU00006409254 | Sabah | Sabah | 6.014750 | 116.446970 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 18G_1+0_55M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_256QAM_778M. Site Impacted : 7299R. NE_7299R 1.Existing ODU XMC-5D(equipped 112MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). FE_7980B 1.Existing ODU XMC-5D(equipped 112MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). | Link Existing HW 18G_1+0_55M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_256QAM_778M. Site Impacted : 7299R. NE_7299R 1.Existing ODU XMC-5D(equipped 112MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). | Link Existing HW 18G_1+0_55M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_256QAM_778M. Site Impacted : 7299R. FE_7980B 1.Existing ODU XMC-5D(equipped 112MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). |  |  | 18G | [8 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-16 | [15 empty] | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202512180098-GTSB
2636B_HU | Jln Abdul Manan | DU00006409255 | Central | Selangor | 3.105617 | 101.388933 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X ISM8 CARD 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB B HI 1x ODU 18G XMC5D SUB B LO | MW Swap | MW SWAP LINK 2636B-1096A WITH HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_256QAM_1556MBPS_XMC5D_SUB_B_2.76KM IMPACTED: 2636B | 1. INSTALL NEW 1PCS ISM8 CARD AT SLOT 3 EXISTING IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW 1PCS ISM8 CARD AT SLOT 3 EXISTING IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 2G 6. DISMANTLE EXISTING LINK | XMC5D | MDD | 18G | 0.6 | 0.6 | GTSB | SQ202601130167-GTSB | GTSB | SQ202601130155-GTSB // SQ202601130159-GTSB | 2026-03-13 | 2026-03-12 | Completed | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123095 |  | 2025-12-31 | 2026-01-10 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-12 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-14 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-13 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-19 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-13 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170715-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
4691D_HU | Taman Ria Mesra 2 | DU00006409256 | Northern | Kedah | 5.806604 | 100.537064 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1x ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK 4691D-K00874 WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_256QAM_1556MBPS_XMC3E_SUB_A & B_LINK_1.11KM IMPACTED: 4691D DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING 6. PATCH 10G SFP AT EXISTING IDU | XMC3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202601210141-GCI | GCI | SQ202601210098-GCI // SQ202601210138-GCI // SQ202603270199-GCI | 2026-01-29 | 2026-01-29 | Completed | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011449 |  | 2026-01-15 | 2026-01-19 | Completed | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-27 | 2026-01-21 | 2026-01-28 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-01-21 | 2026-01-27 | 2026-01-21 | 2026-01-28 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-22 | 2026-01-21 | 2026-01-27 | 2026-01-21 | 2026-01-28 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | 2026-01-21 | 2026-01-27 | 2026-01-21 | 2026-01-22 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | NG HONG JIE7018000036 | Logistic Team | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170724-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
7025R_AD | Kg Ranggu | DU00006409257 | Sabah | Sabah | 4.309705 | 118.001056 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Ad-hoc remote upgrade 56 to 112MHz | Ad-hoc remote upgrade 56 to 112MHz | Ad-hoc remote upgrade 56 to 112MHz | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-16 | [15 empty] | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512170731-GCI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
2715C_AD | Desa Jenjarom | DU00006409258 | Central | Selangor | 2.874419 | 101.486898 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M with 512QAM. | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M with 512QAM. | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M with 512QAM. | [5 empty] | In-House |  | In-House |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-07 | [15 empty] | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170715-GCI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | CHEONG/SENG/WAH/7018000306
3462B_HU | Genting RSC 9 IB | DU00006409259 | Central | Pahang | 3.426760 | 101.791135 | [7 empty] | 02. Pending Access |  | TSS+AA+TI |  | 18G_1+0_110M_512QAM NE_3462B New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 9-27052). New ISM8 x1. New XMC_5D Pro, Sub B_Lo x1. FE_1016A New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN07, NEID 9-27051). New ISM8 x1. New XMC_5D Pro, Sub B_hI x1. | MW Parallel Link | Existing HW MW Link 3462B-1016A, 23G_1+0_112MHZ_512QAM. Build new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. Later, combine existing HW MW Link 3462B-1016A, 23G_1+0_112MHZ_512QAM and new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. Become 23G&18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : 3462B & 3462C. NE_3462B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-27052) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. 4.Later, combine existing HW MW Link 3462B-1016A, 23G_1+0_112MHZ_512QAM and new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. Become 23G&18G_2+0_110MHZ_512QAM_EPLA. FE_1016A 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN07, NEID 9-27051) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. 4.Later, combine existing HW MW Link 3462B-1016A, 23G_1+0_112MHZ_512QAM and new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. Become 23G&18G_2+0_110MHZ_512QAM_EPLA. | Existing HW MW Link 3462B-1016A, 23G_1+0_112MHZ_512QAM. Build new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. Later, combine existing HW MW Link 3462B-1016A, 23G_1+0_112MHZ_512QAM and new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. Become 23G&18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : 3462B & 3462C. NE_3462B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-27052) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. 4.Later, combine existing HW MW Link 3462B-1016A, 23G_1+0_112MHZ_512QAM and new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. Become 23G&18G_2+0_110MHZ_512QAM_EPLA. | Existing HW MW Link 3462B-1016A, 23G_1+0_112MHZ_512QAM. Build new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. Later, combine existing HW MW Link 3462B-1016A, 23G_1+0_112MHZ_512QAM and new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. Become 23G&18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : 3462B & 3462C. FE_1016A 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN07, NEID 9-27051) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. 4.Later, combine existing HW MW Link 3462B-1016A, 23G_1+0_112MHZ_512QAM and new HW MW Parallel Link 3462B-1016A, 18G_1+0_110MHZ_512QAM. Become 23G&18G_2+0_110MHZ_512QAM_EPLA. | XMC-5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | MTK | SQ202601210097-MTK | MTK | SQ202601210072-MTK // SQ202601210080-MTK |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25123096 |  | 2025-12-31 | 2026-01-22 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202512180092-GTSB
S01630_HU | S089A_S01630OD_CB_IJMMEMAHAT | DU00006409260 | Sabah | Sabah | 6.473136 | 117.518136 | [7 empty] | 05. Doable |  | TSS+AA+TI |  | 13G_2+0_28M. NE_S01630. 13G_DP_2.4M(MS)+OMT+ Waveguide x1 XMC_3E , Sub A & B_Lo x1. FE_7398A. 13G_DP_2.4M(MS)+OMT + Waveguide x1. XMC_3E , Sub A & B_Hi x1. | MW Parallel Link | Existing link 13G_2+0_28M Install parallel link 13G_2+0_28M. ** TSS Survey is required to confirm space enough to install 2.4M antenna , especially at FE 7398A** Site Impacted : 7220K / S01630. NE_S01630. 1.Install new 13G_DP_2.4M(MS)+OMT+ Waveguide 2.Reuse existing 7220K / S01630_RTN01 , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA with existing MW link. 5.Traffic migrate to new parallel link. 6.No decom MW link. FE_7398A. 1.Install new 13G_DP_2.4M(MS)+OMT+ Waveguide 2.Reuse existing 7398A_RTN08 , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA with existing MW link. 5.Traffuc migrate to new parallel link. 6.No decom MW link. | Existing link 13G_2+0_28M Install parallel link 13G_2+0_28M. ** TSS Survey is required to confirm space enough to install 2.4M antenna , especially at FE 7398A** Site Impacted : 7220K / S01630. NE_S01630. 1.Install new 13G_DP_2.4M(MS)+OMT+ Waveguide 2.Reuse existing 7220K / S01630_RTN01 , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA with existing MW link. 5.Traffic migrate to new parallel link. 6.No decom MW link. | Existing link 13G_2+0_28M Install parallel link 13G_2+0_28M. ** TSS Survey is required to confirm space enough to install 2.4M antenna , especially at FE 7398A** Site Impacted : 7220K / S01630. FE_7398A. 1.Install new 13G_DP_2.4M(MS)+OMT+ Waveguide 2.Reuse existing 7398A_RTN08 , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA with existing MW link. 5.Traffuc migrate to new parallel link. 6.No decom MW link. | XMC_3E | MS | 13G | 2.4 | 2.4 |  |  | YPTT | SQ202603130167-YPTT // SQ202603130174-YPTT |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26011441 |  | 2026-01-15 | 2026-02-05 | Completed | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-02-05 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202512170731-GCI | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | CHEONG/SENG/WAH/7018000306
7140D_AD | Kampung Muhibah | DU00006409261 | Sabah | Sabah | 6.920223 | 116.842147 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 23G_1+0_55M_512QAM_450M. MW Remote Upgrade to HW 23G_1+0_110M_256QAM_778M. Site Impacted : 7140D. NE_7140D 1.Existing ODU XMC-3(equipped 110MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). FE_7013A 1.Existing ODU XMC-3(equipped 110MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). | Link Existing HW 23G_1+0_55M_512QAM_450M. MW Remote Upgrade to HW 23G_1+0_110M_256QAM_778M. Site Impacted : 7140D. NE_7140D 1.Existing ODU XMC-3(equipped 110MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). | Link Existing HW 23G_1+0_55M_512QAM_450M. MW Remote Upgrade to HW 23G_1+0_110M_256QAM_778M. Site Impacted : 7140D. FE_7013A 1.Existing ODU XMC-3(equipped 110MHz) may remotely upgrade from 55MHz to BW 110MHz(256QAM). |  |  | 23G | [8 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-16 | [15 empty] | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202512180098-GTSB
7024D_AD | Lahad Datu Oil Mill | DU00006409262 | Sabah | Sabah | 5.025050 | 118.347930 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Remote Software Upgrade from 23G_1+0_56M to 23G_1+0_112M with 512QAM. | Remote Software Upgrade from 23G_1+0_56M to 23G_1+0_112M with 512QAM. | Remote Software Upgrade from 23G_1+0_56M to 23G_1+0_112M with 512QAM. | [11 empty] | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-09 | [15 empty] | 2025-12-24 | 2026-01-24 | 2025-12-24 | 2025-12-24 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512170731-GCI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | CHEONG/SENG/WAH/7018000306
1059L_HU | Tmn Jaya Utama | DU00006409263 | Central | Selangor | 2.908990 | 101.474746 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 23G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 23G_1+0_112M_512QAM_889M. Site Impacted : 1059L. NE_1059L 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(512QAM). FE_2720A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(512QAM). | Link Existing HW 23G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 23G_1+0_112M_512QAM_889M. Site Impacted : 1059L. NE_1059L 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(512QAM). | Link Existing HW 23G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 23G_1+0_112M_512QAM_889M. Site Impacted : 1059L. FE_2720A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(512QAM). |  |  | 23G |  |  | In-House |  | In-House |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-13 | [15 empty] | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512180092-GTSB
S01003_AD | S099A_S01003OD_CB_VRT3PAGALUNGAN | DU00006450728 | Sabah | Sabah | 4.498800 | 116.424900 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 10G SFP_40KM_1550nm x2 Fiber Patch Cord x 1 pairs | BBU Patching | BBU_S01003 Patching direct to DDF Port 13 & 14. (10G SFP_40KM_1550nm) | BBU_S01003 Patching direct to DDF Port 13 & 14. (10G SFP_40KM_1550nm). Site Impacted : S01003. | [6 empty] | GCI | SQ202512300551-GCI | GCI | SQ202512300548-GCI | 2026-01-07 | 2026-01-06 | Completed | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-05 | 2026-01-06 | 2026-01-05 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2026-01-11 | 2026-01-11 | Completed | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-01-11 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-03-03 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-09 | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-03-03 | RAI//JORDAN RICHARD RIBU/7018000190 | 2025-11-05: 2026-01-02; 2025-11-05: 2026-01-31; 2025-11-05: 2026-01-02; 2025-11-10: 2026-03-02 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
S00704_AD | S099A_S00704OD_CB_SAPULUTTOWN | DU00006450729 | Sabah | Sabah | 4.714368 | 116.479685 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP_40KM_1550nm x2. Fiber patch cord x 1 pairs Fiber-LC-FC 15m x 2 pcs. | MW Re-engineering | Patching fiber patch cord from ODF port 13 &14 to PTN ( PTN 20206-SAPULUT_TOWN optical). (10G SFP_40KM_1550nm) Site Impacted : S01003 , S01004. | Patching fiber patch cord from ODF port 13 &14 to PTN ( PTN 20206-SAPULUT_TOWN optical). (10G SFP_40KM_1550nm) Site Impacted : S01003 , S01004. | [6 empty] | GCI | SQ202512300551-GCI | GCI | SQ202512300548-GCI | 2026-01-15 | 2026-01-14 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122230 |  | 2025-12-23 | 2026-02-12 | Completed | 2025-12-22 | 2025-12-23 | 2025-12-22 | 2026-02-12 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-02-12 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-02-12 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-16 | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-03-03 | RAI//JORDAN RICHARD RIBU/7018000190 | 2025-11-05: 2026-01-02; 2025-11-05: 2026-01-31; 2025-11-05: 2026-01-02; 2025-11-10: 2026-01-02 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
S01004_AD_1 | S099A_S01004OD_T3_KGSALUNG | DU00006450730 | Sabah | Sabah | 4.585720 | 116.451280 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | RTN910A x1. 10G SFP_40KM_1550nm x4. Fiber Patch Cord x 2 pairs. ETH cat 6 cable x1 | MW IDU Patching | Install New RTN910A ( RTN no provide by OPS team). Enable GE1 , BBU_S01044 ETH LAN patching to RTN910A_GE1.(ETH cat 6 cable). (Refer to DU ID S01004_AD). Enable GE5 , Patching fiber patch cord to ODF port 13 & 14.(10G SFP_40KM_1550nm). Enable GE6 , Patching fiber patch cord to ODF port 1 & 2.(10G SFP_40KM_1550nm). Create New Inband DCN via PTN 20206-SAPUT_TOWN. Site Impacted : S01003 , S01004. | Install New RTN910A ( RTN no provide by OPS team). Enable GE1 , BBU_S01044 ETH LAN patching to RTN910A_GE1.(ETH cat 6 cable). (Refer to DU ID S01004_AD). Enable GE5 , SFP fiber patch cord to ODF port 13 & 14.(10G SFP_40KM_1550nm). Enable GE6 , SFP fiber patch cord to ODF port 1 & 2.(10G SFP_40KM_1550nm). Create New Inband DCN via PTN 20206-SAPUT_TOWN. Site Impacted : S01003 , S01004. | [6 empty] | GCI | SQ202512300551-GCI | GCI | SQ202512300548-GCI | 2026-02-23 | 2026-02-23 | Completed | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122231 |  | 2025-12-23 | 2026-03-04 | Completed | 2025-12-22 | 2025-12-23 | 2025-12-22 | 2026-03-04 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-03-04 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-03-04 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-16 | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-03-04 | RAI//JORDAN RICHARD RIBU/7018000190 | 2025-11-05: 2026-01-02; 2025-11-05: 2026-01-31; 2025-11-05: 2026-01-02; 2025-11-10: 2026-03-03 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
S01004_AD | S099A_S01004OD_T3_KGSALUNG | DU00006450731 | Sabah | Sabah | 4.585720 | 116.451280 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | BOQ refer to DU ID S01004_AD_1 | BBU Patching | 1. BBU_S01004 ETH cable direct patching to new RTN910A_GE1. New RTN910A (Refer to DU ID S01004_AD_1). Site Impacted : S01004 | 1. BBU_S01004 ETH cable direct patching to new RTN910A_GE1. New RTN910A (Refer to DU ID S01004_AD_1). Site Impacted : S01004 | [6 empty] | GCI | SQ202512300551-GCI | GCI | SQ202512300548-GCI | 2026-01-07 | 2026-01-06 | Completed | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2026-01-11 | 2026-01-11 | Completed | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-01-11 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-01-02 | 2026-01-31 | 2026-01-02 | 2026-03-28 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-09 | 2026-04-14 | 2026-04-30 | 2026-04-14 | 2026-04-15 | STANNIE//AVILA RASAM/6800000192 | 2025-11-05: 2026-01-02; 2025-11-05: 2026-01-31; 2025-11-05: 2026-01-02; 2025-11-10: 2026-03-03 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
4655B_HU_1 | KolejKediaman Bkt Kachi(Maxis) | DU00006461290 | Northern | Kedah | 6.440940 | 100.531000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module x2. Fiber patch cord x1 pairs. | BBU Patching | NE_4655B 4655B_BBU patching to use 10G port. Enable GE3 , 4655B_BBU transfer from GE1 to GE3 , 10GE port. Disable unused GE port at 4655B_RTN01. Cross connect new GE3 , 10G port. | NE_4655B 4655B_BBU patching to use 10G port. Enable GE3 , 4655B_BBU transfer from GE1 to GE3 , 10GE port. Disable unused GE port at 4655B_RTN01. Cross connect new GE3 , 10G port. | [6 empty] | GTSB | SQ202512300376-GTSB | GTSB | SQ202512300366-GTSB | 2026-02-04 | 2026-02-05 | Completed | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-25 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-01-28 | 2026-01-27 | 2026-01-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122721 |  | 2026-01-31 | 2025-12-31 | Completed | 2025-12-27 | 2026-01-31 | 2025-12-27 | 2025-12-31 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-16 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-17 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-03 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-22 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2025-11-05: 2026-01-14; 2025-11-05: 2026-01-14; 2025-11-05: 2026-01-14; 2025-11-10: 2026-01-15 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512241124-GCI | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | CHEONG/SENG/WAH/7018000306
7018L_HU_1 | DelimaVillage | DU00006461291 | Sabah | Sabah | 6.036131 | 116.135143 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M_512QAM_EPLA NE_7018L New 23G_DP_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 9-23460). New XMC_3E, Sub A&B_Hi x2. FE_7286A New 23G_DP_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 9-29216). New ISM8 x1. New XMC_3E, Sub A&B_Lo x2. | MW Swap | Existing HW MW Link_7018L-7286A, 23G_1+0_112MHZ_512QAM_889M. MW Swap to new HW MW Link 7018L-7286A, 23G_2+0_112MHZ_512QAM_1778M. Later, decom Antenna, ODU and RTN910AF(RTN02, NEID 9-23461) ONLY of 7018L-7286A, 23G_1+0_112MHZ_512QAM_889M. Anyway, do not decom RTN910AF(RTN01, NEID 9-23460). Site Impacted : 7018L. NE_7018L 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-23460). 3.Install new XMC_3E, Sub A&B_Hi x2. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 7018L via new HW MW Link 7018L-7286A, 23G_2+0_112MHZ_512QAM_1778M. 6.Later, decom Antenna, ODU and RTN910AF(RTN02, NEID 9-23461) ONLY of 7018L-7286A, 23G_1+0_112MHZ_512QAM_889M. Anyway, do not decom RTN910AF(RTN01, NEID 9-23460). FE_7286A 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-29216). Insert new ISM8 into slot 03. 3.Install new XMC_3E, Sub A&B_Lo x2. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 7018L via existing port of IBeam. 6.Later, decom Antenna, ODU and RTN910AF(RTN02, NEID 9-23461) ONLY of 7018L-7286A, 23G_1+0_112MHZ_512QAM_889M. Anyway, do not decom RTN910AF(RTN01, NEID 9-23460). | Existing HW MW Link_7018L-7286A, 23G_1+0_112MHZ_512QAM_889M. MW Swap to new HW MW Link 7018L-7286A, 23G_2+0_112MHZ_512QAM_1778M. Later, decom Antenna, ODU and RTN910AF(RTN02, NEID 9-23461) ONLY of 7018L-7286A, 23G_1+0_112MHZ_512QAM_889M. Anyway, do not decom RTN910AF(RTN01, NEID 9-23460). Site Impacted : 7018L. NE_7018L 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-23460). 3.Install new XMC_3E, Sub A&B_Hi x2. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 7018L via new HW MW Link 7018L-7286A, 23G_2+0_112MHZ_512QAM_1778M. 6.Later, decom Antenna, ODU and RTN910AF(RTN02, NEID 9-23461) ONLY of 7018L-7286A, 23G_1+0_112MHZ_512QAM_889M. Anyway, do not decom RTN910AF(RTN01, NEID 9-23460). | Existing HW MW Link_7018L-7286A, 23G_1+0_112MHZ_512QAM_889M. MW Swap to new HW MW Link 7018L-7286A, 23G_2+0_112MHZ_512QAM_1778M. Later, decom Antenna, ODU and RTN910AF(RTN02, NEID 9-23461) ONLY of 7018L-7286A, 23G_1+0_112MHZ_512QAM_889M. Anyway, do not decom RTN910AF(RTN01, NEID 9-23460). Site Impacted : 7018L. FE_7286A 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-29216). Insert new ISM8 into slot 03. 3.Install new XMC_3E, Sub A&B_Lo x2. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 7018L via existing port of IBeam. 6.Later, decom Antenna, ODU and RTN910AF(RTN02, NEID 9-23461) ONLY of 7018L-7286A, 23G_1+0_112MHZ_512QAM_889M. Anyway, do not decom RTN910AF(RTN01, NEID 9-23460). | XMC_3E | MAC | 23G | 23G_DP_0.6M(MAC)+OMT x1 | 23G_DP_0.6M(MAC)+OMT x1 | NR services | SQ202602250627-NR Services | NR services | SQ202604200353-NR Services // SQ202604200358-NR Services |  |  | Ongoing | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022337 |  | 2026-02-24 | 2026-04-16 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-04-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-04-16 | RANA//WAQAS/6000006187 | NR Service TI | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-04-25 | RANA//WAQAS/6000006187 | NR Service TI | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-20 | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-04-25 | RANA//WAQAS/6000006187 | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-04-15 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | [5 empty] | GTSB | SQ202512241147-GTSB
7647B_HU_1 | SMKBum Bum SBC | DU00006461292 | Sabah | Sabah | 4.448181 | 118.691654 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_7647B New ISM8 x1. IF cable with suitable length and type x1 RUN. New CAT6 cable x1. | MW Re-engineering | ****IMPORTANT NOTE: 1.PLEASE CHECK AND ENSURE BBU/RAN 7647B WHETHER STILL BACKHAULING TO XC(TX ROUTE 7647B/S00395-S00520). IF YES, PLEASE DIVERT BBU/RAN 7647B TO NEW TX ROUTE 7647B-7000D-7209A. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7647B_HU. 2ND - DU 7647B_HU_1.**** Reengineering at 7647B to reduce IDU-IDU cascade to avoid Eth port bottleneck. Site Impacted : 7647B, 7625B, 7355C, 7215R & 7127H. NE_7647B 1.Insert ISM8 x1 into slot 03 of existing RTN910AF(RTN03, NEID 9-23320). Configure it. 2.Shifting existing IF cable from slot 07 Port 1 of existing RTN910AF(RTN02, NEID 153-27680) to slot 03 Port 1 of existing RTN910AF(RTN03, NEID 9-23320). Configure it. 3.Disconnect/remove existing cascade in between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23320) and port 8-EM6-2 of existing RTN910AF(RTN02, NEID 153-27680). 4.Disconnect/remove existing cascade in between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 153-27680) and port 6-EM6T-1 of existing RTN950(RTN01, NEID 9-18474). 5.Disconnect/remove existing cascade in between port of existing NLOS Cambium(7127H) and port 6-EM6T-2 of existing RTN950(RTN01, NEID 9-18474). 6.Perform new cascading between port of existing NLOS Cambium(7127H) and port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23320). 7.Decom existing RTN950(RTN01, NEID 9-18474) and existing RTN910AF(RTN02, NEID 153-27680). Later, return to warehouse. | ****IMPORTANT NOTE: 1.PLEASE CHECK AND ENSURE BBU/RAN 7647B WHETHER STILL BACKHAULING TO XC(TX ROUTE 7647B/S00395-S00520). IF YES, PLEASE DIVERT BBU/RAN 7647B TO NEW TX ROUTE 7647B-7000D-7209A. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7647B_HU. 2ND - DU 7647B_HU_1.**** Reengineering at 7647B to reduce IDU-IDU cascade to avoid Eth port bottleneck. Site Impacted : 7647B, 7625B, 7355C, 7215R & 7127H. NE_7647B 1.Insert ISM8 x1 into slot 03 of existing RTN910AF(RTN03, NEID 9-23320). Configure it. 2.Shifting existing IF cable from slot 07 Port 1 of existing RTN910AF(RTN02, NEID 153-27680) to slot 03 Port 1 of existing RTN910AF(RTN03, NEID 9-23320). Configure it. 3.Disconnect/remove existing cascade in between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23320) and port 8-EM6-2 of existing RTN910AF(RTN02, NEID 153-27680). 4.Disconnect/remove existing cascade in between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 153-27680) and port 6-EM6T-1 of existing RTN950(RTN01, NEID 9-18474). 5.Disconnect/remove existing cascade in between port of existing NLOS Cambium(7127H) and port 6-EM6T-2 of existing RTN950(RTN01, NEID 9-18474). 6.Perform new cascading between port of existing NLOS Cambium(7127H) and port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23320). 7.Decom existing RTN950(RTN01, NEID 9-18474) and existing RTN910AF(RTN02, NEID 153-27680). Later, return to warehouse. | [6 empty] | NR services | SQ202603030384-NR Services | NR services | SQ202602160089-NR Services |  |  | Ongoing | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26021229 |  | 2026-02-13 | 2026-02-26 | Completed | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-26 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-16 | 2026-03-16 | 2026-02-15 | 2026-02-26 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-16 | 2026-03-16 | 2026-02-15 | 2026-02-26 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-26 | 2026-02-16 | 2026-03-16 | 2026-02-15 | 2026-02-27 | RALPH O'BRYAN HILARY7167000030 | 2026-02-16 | 2026-03-16 | 2026-02-15 | 2026-02-25 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202512241147-GTSB
4677B_HU | Tanah Merah(CLM) | DU00006461293 | Northern | Kedah | 6.023870 | 100.483210 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M. 1.18G_DP_1.2M(MDD) x1. 2.XMC_5D , Sub A_Hi x1. FE_4992A 1. 18G_DP_1.2M(MDD) x1. 2. XMC_5D , Sub A_Lo x1. | MW Swap | Existing link 18G_1+0_112M with XMC_3E. Swap existing link to 18G_2+0_112M due to material received XMC_5D ODU at site. NE_4677B 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 4677B_RTN04 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link. 6.Decomm existing Ant & XMC_3E. FE_4992A. 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 4992A_RTN08 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link. 6.Decomm existing Ant and XMC_3E. | Existing link 18G_1+0_112M with XMC_3E. Swap existing link to 18G_2+0_112M due to material received XMC_5D ODU at site. NE_4677B 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 4677B_RTN04 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link. 6.Decomm existing Ant & XMC_3E. | Existing link 18G_1+0_112M with XMC_3E. Swap existing link to 18G_2+0_112M due to material received XMC_5D ODU at site. FE_4992A. 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 4992A_RTN08 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link. 6.Decomm existing Ant and XMC_3E. | [5 empty] | GTSB | SQ202512300376-GTSB | GTSB | SQ202512300360-GTSB // SQ202512300366-GTSB // SQ202601150530-GTSB // SQ202601150542-GTSB | 2026-01-20 | 2026-01-21 | Completed | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-16 | 2026-01-17 | 2026-01-16 | 2026-01-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123002 |  | 2025-12-31 | 2026-01-12 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-13 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-14 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-14 | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-22 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-11-05: 2026-01-12; 2025-11-05: 2026-01-31; 2025-11-05: 2026-01-12; 2025-11-10: 2026-01-13 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512241124-GCI | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | CHEONG/SENG/WAH/7018000306
4655B_HU | KolejKediaman Bkt Kachi(Maxis) | DU00006461294 | Northern | Kedah | 6.440940 | 100.531000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | NE_4655B. 18G_SP_1.2M(MAC) x1. XMC_3E , Sub A_Lo x1. FE_4991A. 18G_SP_0.6M(MAC) x1. XMC_3E , Sub A_Hi x1. ETH LAN cable x1. | MW Parallel Link | Existing link 18G_1+0_112M MW upgrade with EPLA existing link. MW link configuration 18G_1+0_112M. Site Impacted : 4655B. NE_4655B. 1.Install new 18G_SP_1.2M(MAC). 2.Reuse existing 4655B_RTN01 , 3_ISM8-2+0 , port 2. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No decom MW link. FE_4991A. 1.Install new 18G_SP_0.6M(MAC). 2.Reuse existing 4991A_RTN05 , 3_ISM8-2+0 , port 2. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and EPLA with existing link. 5.Enable GE2 , create physical LAG to Fiber Ibeam port. 6.Traffic migrate to new parallel link. 7.No decom MW link. | Existing link 18G_1+0_112M MW upgrade with EPLA existing link. MW link configuration 18G_1+0_112M. Site Impacted : 4655B. NE_4655B. 1.Install new 18G_SP_1.2M(MAC). 2.Reuse existing 4655B_RTN01 , 3_ISM8-2+0 , port 2. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No decom MW link. | Existing link 18G_1+0_112M MW upgrade with EPLA existing link. MW link configuration 18G_1+0_112M. Site Impacted : 4655B. FE_4991A. 1.Install new 18G_SP_0.6M(MAC). 2.Reuse existing 4991A_RTN05 , 3_ISM8-2+0 , port 2. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and EPLA with existing link. 5.Enable GE2 , create physical LAG to Fiber Ibeam port. 6.Traffic migrate to new parallel link. 7.No decom MW link. | XMC_3E | MAC | 18G | 1.2 | 0.6 | GTSB | SQ202512300376-GTSB | GTSB | SQ202512300360-GTSB // SQ202512300366-GTSB | 2026-03-05 | 2026-03-04 | Completed | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-22 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Completed |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122720 |  | 2026-01-31 | 2025-12-31 | Completed | 2025-12-27 | 2026-01-31 | 2025-12-27 | 2025-12-31 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-17 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-17 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-16 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-21 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2025-11-05: 2026-01-14; 2025-11-05: 2026-01-14; 2025-11-05: 2026-01-14; 2025-11-10: 2026-01-16 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512241124-GCI | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | CHEONG/SENG/WAH/7018000306
Q01771_HU | Q118B_Q01771OD_TMNEVERGREENBTU | DU00006461295 | Sarawak | Sarawak | 3.183093 | 113.067847 | [9 empty] | TSS+AA+TI |  | NE_Q01771 18G_SP_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub B_Lo x1. FE_9106A 18G_SP_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub B_Hi x1. | MW Swap | Existing link 18G_1+0_56M. Proceed with SWAP due to KPI not meeting to existing config. Swap existing link 18G_1+0_112M. Site Impacted : Q01771. NE_Q01771 1.Install new 18G_SP_0.6M(MAC). 2.Reuse existing 9121K_RTN01. 3.Install new 3_ISM8-1+0 into existing 9121K_RTN01. 4.Install new XMC_3E , Sub B_Lo. 5.Traffic migrate to new link. 6.Decom existing ODU and ANT. FE_9106A 1.Install new 18G_SP_0.6M(MAC). 2.Reuse existing 9106A_RTN08. 3.Install new 3_ISM8-1+0 into existing 9106A_RTN08. 4.Install new XMC_3E , Sub B_Hi. 5.Traffic migrate to new link. 6.Decom existing ODU and ANT. | Existing link 18G_1+0_56M. Proceed with SWAP due to KPI not meeting to existing config. Swap existing link 18G_1+0_112M. Site Impacted : Q01771. NE_Q01771 1.Install new 18G_SP_0.6M(MAC). 2.Reuse existing 9121K_RTN01. 3.Install new 3_ISM8-1+0 into existing 9121K_RTN01. 4.Install new XMC_3E , Sub B_Lo. 5.Traffic migrate to new link. 6.Decom existing ODU and ANT. | Existing link 18G_1+0_56M. Proceed with SWAP due to KPI not meeting to existing config. Swap existing link 18G_1+0_112M. Site Impacted : Q01771. FE_9106A 1.Install new 18G_SP_0.6M(MAC). 2.Reuse existing 9106A_RTN08. 3.Install new 3_ISM8-1+0 into existing 9106A_RTN08. 4.Install new XMC_3E , Sub B_Hi. 5.Traffic migrate to new link. 6.Decom existing ODU and ANT. | XMC_3E | MAC | 18G | 0.6 | 1.2 | Magicell | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241133-GCI | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | CHEONG/SENG/WAH/7018000306
4427K_HU | K010A_K00337OD_BKTPATONG | DU00006461296 | Northern | Kedah | 6.036520 | 100.530930 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 2X 18G 1.2M MDD ANTENNA 1x ODU 18G XMC5D SUB B HI 1x ODU 18G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL LINK 4427K-4677B WITH HUAWEI_18G_1+0_1.2M/1.2M_MDD_112MHZ_256QAM_778MBPS_XMC5D_SUB_B_LINK_5.5KM IMPACTED: 4427K, 4676B, 4974B | 1. INSTALL NEW ISM8 AT EXISTING IDU SLOT 3 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM EPLA WITH EXISTING 18G 1+0 TO BECOME 2+0 | 1. INSTALL NEW ISM8 AT EXISTING IDU SLOT 4 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM EPLA WITH EXISTING 18G 1+0 TO BECOME 2+0 | XMC5D | MDD | 18G | 1.2 | 1.2 | GTSB | SQ202512300376-GTSB | GTSB | SQ202512300360-GTSB // SQ202512300366-GTSB | 2026-01-15 | 2026-01-15 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123003 |  | 2025-12-31 | 2025-12-31 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2025-12-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-31 | 2026-01-09 | 2026-01-09 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-09 | 2026-01-31 | 2026-01-09 | 2026-01-15 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-15 | 2026-01-09 | 2026-01-31 | 2026-01-09 | 2026-01-22 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-11-05: 2026-01-09; 2025-11-05: 2026-01-31; 2025-11-05: 2026-01-09; 2025-11-10: 2026-01-12 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512241124-GCI | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
7647B_HU | SMKBum Bum SBC | DU00006461297 | Sabah | Sabah | 4.448181 | 118.691654 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M_512QAM_EPLA(Without CA) NE_7647B New 15G_1.2M(MDD)+Dual Coupler x1. Re-use existing RTN910AF(RTN04, NEID 153-46349). New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. FE_7000D New 15G_0.6M(MDD)+Dual Coupler x1. New RTN910AF(RTN03). New ISM8 x2. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x2 RUN.(for existing HW MW Link 13G_2+0_28M_512QAM_EPLA shifting IF cable from slot 07 Port 1 & 2 of existing RTN910AF(RTN02, NEID 174-39259) to slot 07 Port 1 & 2 of new RTN910AF(RTN03). New IF cables with suitable length and type x4 RUN.(for new parallel HW MW Link 15G_4+0_28M_512QAM_EPLA(Without CA)). New SFP Module 10G with 10Km 1310nm x2 or equivalent(For cascading between port 8-EM6-3 of RTN02, NEID 174-39259 and port 8-EM6-3 of new RTN910AF(RTN03). New Optical Patch Cord cable x1 with suitable type and length. | MW Parallel Link | ****IMPORTANT NOTE: 1.PLEASE CHECK AND ENSURE BBU/RAN 7647B WHETHER STILL BACKHAULING TO XC(TX ROUTE 7647B/S00395-S00520). IF YES, PLEASE DIVERT BBU/RAN 7647B TO NEW TX ROUTE 7647B-7000D-7209A. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7647B_HU. 2ND - DU 7647B_HU_1.**** Existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA. Build new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). Later, combine existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). Become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA. Site Impacted : 7647B, 7625B, 7355C, 7215R & 7127H. NE_7647B 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Re-use existing RTN910AF(RTN04, NEID 153-46349) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Build new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). 5.Later, combine existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). Become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA. 6.Re-use existing xD Vlan DCN and Vlan Services. 7.Migrate traffics 7647B, 7625B, 7355C, 7215R & 7127H via 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA. FE_7000D 1.Install 15G_0.6M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN03) and insert insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Shifting existing IF cable from slot 07 Port 1 & 2 of existing RTN910AF(RTN02, NEID 174-39259) to slot 07 Port 1 & 2 of new RTN910AF(RTN03). 5.If short, lay new IF cable x1 RUN from existing ODU of existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA to slot 07 Port 1 & 2 of new RTN910AF(RTN03). 6.Build new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA) using slot 03 & 04 of new RTN910AF(RTN03). 7.Later, combine existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). Become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA. 8.Re-use existing xD Vlan DCN and Vlan Services. 9.Enable port 8-EM6-3 of existing RTN910AF(RTN02, NEID 174-39259) and insert new SFP Module 10G with 10Km 1310nm x1. 10.Enable port 8-EM6-3 of new RTN910AF(RTN03) and insert new SFP Module 10G with 10Km 1310nm x1. 11.Perform cascading between port 8-EM6-3 of existing RTN910AF(RTN02, NEID 174-39259) and port 8-EM6-3 of new RTN910AF(RTN03). 12.Migrate traffics 7647B, 7625B, 7355C, 7215R & 7127H via existing port of IBeam at CP 7209A. | ****IMPORTANT NOTE: 1.PLEASE CHECK AND ENSURE BBU/RAN 7647B WHETHER STILL BACKHAULING TO XC(TX ROUTE 7647B/S00395-S00520). IF YES, PLEASE DIVERT BBU/RAN 7647B TO NEW TX ROUTE 7647B-7000D-7209A. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7647B_HU. 2ND - DU 7647B_HU_1.**** Existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA. Build new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). Later, combine existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). Become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA. Site Impacted : 7647B, 7625B, 7355C, 7215R & 7127H. NE_7647B 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Re-use existing RTN910AF(RTN04, NEID 153-46349) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Build new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). 5.Later, combine existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). Become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA. 6.Re-use existing xD Vlan DCN and Vlan Services. 7.Migrate traffics 7647B, 7625B, 7355C, 7215R & 7127H via 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA. | ****IMPORTANT NOTE: 1.PLEASE CHECK AND ENSURE BBU/RAN 7647B WHETHER STILL BACKHAULING TO XC(TX ROUTE 7647B/S00395-S00520). IF YES, PLEASE DIVERT BBU/RAN 7647B TO NEW TX ROUTE 7647B-7000D-7209A. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7647B_HU. 2ND - DU 7647B_HU_1.**** Existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA. Build new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). Later, combine existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). Become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA. Site Impacted : 7647B, 7625B, 7355C, 7215R & 7127H. FE_7000D 1.Install 15G_0.6M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN03) and insert insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Shifting existing IF cable from slot 07 Port 1 & 2 of existing RTN910AF(RTN02, NEID 174-39259) to slot 07 Port 1 & 2 of new RTN910AF(RTN03). 5.If short, lay new IF cable x1 RUN from existing ODU of existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA to slot 07 Port 1 & 2 of new RTN910AF(RTN03). 6.Build new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA) using slot 03 & 04 of new RTN910AF(RTN03). 7.Later, combine existing Huawei MW Link 7647B-7000D, 13G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link 7647B-7000D, 15G_4+0_28MHZ_256QAM_EPLA(wo CA). Become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA. 8.Re-use existing xD Vlan DCN and Vlan Services. 9.Enable port 8-EM6-3 of existing RTN910AF(RTN02, NEID 174-39259) and insert new SFP Module 10G with 10Km 1310nm x1. 10.Enable port 8-EM6-3 of new RTN910AF(RTN03) and insert new SFP Module 10G with 10Km 1310nm x1. 11.Perform cascading between port 8-EM6-3 of existing RTN910AF(RTN02, NEID 174-39259) and port 8-EM6-3 of new RTN910AF(RTN03). 12.Migrate traffics 7647B, 7625B, 7355C, 7215R & 7127H via existing port of IBeam at CP 7209A. | XMC_5D Pro | MDD | 15G | 15G_1.2M(MDD)+Dual Coupler x1 | 15G_0.6M(MDD)+Dual Coupler x1 | NR services | SQ202603030384-NR Services | NR services | SQ202602160087-NR Services // SQ202602160089-NR Services |  |  | Ongoing | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26021228 |  | 2026-02-13 | 2026-02-26 | Completed | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-26 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-16 | 2026-03-16 | 2026-02-15 | 2026-02-26 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-16 | 2026-03-16 | 2026-02-15 | 2026-02-26 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-26 | 2026-02-16 | 2026-03-16 | 2026-02-15 | 2026-03-04 | RALPH O'BRYAN HILARY7167000030 | 2025-11-05: 2026-02-16; 2025-11-05: 2026-03-16; 2025-11-05: 2026-02-15; 2025-11-10: 2026-02-25 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202512241147-GTSB
4191R_HU | LadangSungei Erong | DU00006461298 | Northern | Perak | 3.807830 | 101.220660 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 1X RTN910A 2X 13G 1.2M MDD ANTENNA 1x ODU 13G XMC5D SUB B HI 1x ODU 13G XMC5D SUB B LO | MW Swap | MW SWAP LINK 4191R-4781B WITH HUAWEI_13G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_889MBPS_XMC5D_SUB_B_WITH CA_7.00KM IMPACTED: 4191R DISMANTLE EXISTING LINK | 1. INSTALL NEW 2PCS ISM8 CARD AT SLOT 3&4 EXISTING IDU RTN910 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 112MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK EXCEPT IDU | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 AT SLOT 3&4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 112MHZ 512QAM WITH CA 5. PATCH NEW IDU TO EXISTING IDU 4781B-4256K 6. DISMANTLE EXISTING LINK | XMC5D | MDD | 13G | 1.2 | 1.2 | GTSB | SQ202512300376-GTSB | GTSB | SQ202512300360-GTSB // SQ202512300366-GTSB | 2026-02-04 | 2026-02-05 | Completed | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-23 | 2026-01-24 | 2026-01-23 | 2026-01-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122719 |  | 2026-01-31 | 2025-12-31 | Completed | 2025-12-27 | 2026-01-31 | 2025-12-27 | 2025-12-31 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-31 | 2026-01-09 | 2026-01-09 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-09 | 2026-01-31 | 2026-01-09 | 2026-01-11 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-01-09 | 2026-01-31 | 2026-01-09 | 2026-01-19 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2025-11-05: 2026-01-09; 2025-11-05: 2026-01-31; 2025-11-05: 2026-01-09; 2025-11-10: 2026-01-11 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512241124-GCI | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
6182R_HU | Taman Albury | DU00006461299 | Southern | Sembilan | 2.878820 | 101.914880 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB B HI 1x ODU 18G XMC5D SUB B LO | MW Swap | MW SWAP LINK 6182R-2362B WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC5D_SUB_B_LINK_2.22KM IMPACTED: 6182R DISMANTLE EXISTING LINK EXCEPT IDU | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK EXCEPT IDU | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK EXCEPT IDU | XMC5D | MDD | 18G | 0.6 | 0.6 | GTSB | SQ202512300434-GTSB | GTSB | SQ202512300406-GTSB // SQ202512300424-GTSB | 2026-02-21 | 2026-02-20 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-20 | 2026-02-21 | 2026-02-20 | 2026-02-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123004 |  | 2025-12-31 | 2025-12-31 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2025-12-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-12 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-12 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-14 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-02-25 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-08 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | NG HONG JIE7018000036 | Logistic Team | [5 empty] | GCI | SQ202512241136-GCI | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
7017D_HU | Lapasan Village | DU00006461300 | Sabah | Sabah | 6.109860 | 116.165850 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 23G_1+0_56M Remote Software Upgrade to 23G_1+0_112M Site Impacted : 7017D | Existing link 23G_1+0_56M Remote Software Upgrade to 23G_1+0_112M Site Impacted : 7017D | Existing link 23G_1+0_56M Remote Software Upgrade to 23G_1+0_112M Site Impacted : 7017D | XMC_3E | MAC | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 | [17 empty] | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512241128-GCI | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | CHEONG/SENG/WAH/7018000306
4991A_IPR_1 | UUM | DU00006461301 | Northern | Kedah | 6.457932 | 100.499451 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x PATCHCORD | MW IDU Patching | LAG for IDU at CP port (related to DU 4655B_HU) | LAG for IDU at CP port (related to DU 4655B_HU) | [6 empty] | GCI | SQ202601280647-GCI | GCI | SQ202601080374-GCI | 2026-01-24 | 2026-01-23 | Completed | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-23 | 2026-01-24 | 2026-01-23 | 2026-01-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123090 |  | 2025-12-31 | 2026-01-02 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-21 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-21 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-21 | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-24 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2026-01-07: 2026-01-21; 2026-01-07: 2026-01-28; 2026-01-07: 2026-01-21; 2026-01-08: 2026-01-21 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512241124-GCI | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
4565D_HU | Kg Changkat Larah | DU00006461302 | Northern | Kedah | 4.935150 | 100.724000 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M with 512QAM | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M with 512QAM | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M with 512QAM | XMC_3 | XMC | 18G | 0.6 | 0.6 | In-House |  | In-House |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-07 | [15 empty] | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512241124-GCI | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | CHEONG/SENG/WAH/7018000306
4739D_HU | Kenari 3a | DU00006461303 | Northern | Kedah | 5.364930 | 100.572720 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M with 512QAM. | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M with 512QAM. | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M with 512QAM. | [5 empty] | In-House |  | In-House |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-07 | [15 empty] | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512241124-GCI | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | CHEONG/SENG/WAH/7018000306
4697D_HU | Taman Bandar Permata | DU00006461304 | Northern | Kedah | 5.452390 | 100.533270 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X 18G 0.6M MDD ANTENNA 1X 18G 1.2M MDD ANTENNA 1x ODU 18G XMC5D SUB A HI 1x ODU 18G XMC5D SUB A LO | MW Swap | MW SWAP LINK 4697D-4683A WITH HUAWEI_18G_2+0_0.6M/1.2M_DP_112MHZ_512QAM_1778MBPS_XMC5D_SUB_A_LINK_3.68KM IMPACTED: 4697D PATCH FE TO NEW CP PORT AND DO PORT LAG 2G DISMANTLE EXISTING LINK EXCEPT IDU | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK EXCEPT IDU | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 2G 6. DISMANTLE EXISTING LINK EXCEPT IDU | XMC5D | MDD | 18G | 0.6 | 1.2 | GTSB | SQ202512300376-GTSB | GTSB | SQ202512300360-GTSB // SQ202512300366-GTSB | 2026-01-21 | 2026-01-21 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123005 |  | 2025-12-31 | 2025-12-31 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2025-12-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-13 | AG KU NURULIKHSAN//BIN PG ANAPI/6799000310 | GTSB TI | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-15 | AG KU NURULIKHSAN//BIN PG ANAPI/6799000310 | GTSB TI | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-14 | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-23 | AG KU NURULIKHSAN//BIN PG ANAPI/6799000310 | 2026-01-07: 2026-01-12; 2026-01-07: 2026-01-31; 2026-01-07: 2026-01-12; 2026-01-08: 2026-01-14 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512241124-GCI | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
7018L_HU_2 | DelimaVillage | DU00006461305 | Sabah | Sabah | 6.036131 | 116.135143 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 7018L NE_7018L New SFP Module 10G with 10Km 1310nm or equivalent as per ZTE IPRAN advise on the length required x1(For ZTE RAN). New Optical Patch Cord cable x1 with suitable type and length. | BBU Patching | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 7018L. Site Impacted :7018L. NE_7018L 1.Insert new suitable SFP Module 10G into new port 10G RAN. Enable it. 2.Patching new Optical Patch Cord cable to port 10G RAN and suitable port of ODF(obtain advise from ZTE IPRAN Team). | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 7018L. Site Impacted :7018L. NE_7018L 1.Insert new suitable SFP Module 10G into new port 10G RAN. Enable it. 2.Patching new Optical Patch Cord cable to port 10G RAN and suitable port of ODF(obtain advise from ZTE IPRAN Team). | [6 empty] | NR services | SQ202601220792-NR Services | NR services | SQ202601220785-NR Services |  |  | Ongoing | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26011633 |  | 2026-01-17 | 2026-01-20 | Completed | 2026-01-16 | 2026-01-17 | 2026-01-16 | 2026-01-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-01-30 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-01-30 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-30 | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-02-11 | LEONARD//EDUAN/6000038538 | 2026-01-07: 2026-01-30; 2026-01-07: 2026-02-28; 2026-01-07: 2026-01-30; 2026-01-08: 2026-01-30 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202512241147-GTSB
7040A_HU | TamanHartamas | DU00006461306 | Sabah | Sabah | 6.103197 | 116.204337 | [7 empty] | 05. TI WIP |  | TSS+AA+TI+Dismantle |  | 18G_2+0_55M_512QAM_EPLA NE_7040A New 18G_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 9-43398). New XMC_3, Sub B_Hi x1. FE_7544B New 18G_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 9-43415). New XMC_3, Sub B_Lo x1. | MW Swap | Existing HW MW Link_7040A-7544B, 15G&18G_3+0_28MHZ&55MHZ_512QAM_EPLA. MW Swap existing HW MW Link_7040A-7544B, 15G_2+0_28MHZ_512QAM_EPLA to new HW MW Link 7040A-7544B, 18G_2+0_55MHZ_512QAM. Later, decom existing HW MW Link_7040A-7544B, 15G_2+0_28MHZ_512QAM_EPLA and perform EPLA between existing 7040A-7544B, 18G_1+0_55MHZ_512QAM and new HW MW Link 7040A-7544B, 18G_2+0_55MHZ_512QAM_EPLA. Become new HW MW Link 7040A-7544B, 18G_3+0_55MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-43398) and RTN910AF(RTN01, NEID 9-43415). Site Impacted : 7040A. NE_7040A. 1.Install new 0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-43398). 3.Re-use existing ISM8 slot 07 Port 1&2 of existing RTN910AF(RTN01, NEID 9-43398). 4.Install new XMC_3, Sub B_Hi x1. Lay new IF cables x1 with suitable length and type from new XMC_3, Sub B_Hi x1 to existing ISM8 slot 07 Port 1&2 of existing RTN910AF(RTN01, NEID 9-43398). Configure it. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffic 7040A via new HW MW Link 7040A-7544B, 18G_3+0_55MHZ_512QAM_EPLA. 7.Later, decom existing HW MW Link_7040A-7544B, 15G_2+0_28MHZ_512QAM_EPLA and perform EPLA between existing 7040A-7544B, 18G_1+0_55MHZ_512QAM and new HW MW Link 7040A-7544B, 18G_2+0_55MHZ_512QAM_EPLA. Become new HW MW Link 7040A-7544B, 18G_3+0_55MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-43398) and RTN910AF(RTN01, NEID 9-43415). FE_4399A 1.Install new 0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-43415). 3.Re-use existing ISM8 slot 03 Port 1&2 of existing RTN910AF(RTN01, NEID 9-43415). 4.Install new XMC_3, Sub B_Lo x1. Lay new IF cables x1 with suitable length and type from new XMC_3, Sub B_Lo x1 to existing ISM8 slot 03 Port 1&2 of existing RTN910AF(RTN01, NEID 9-43415). Configure it. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffic 7040A via existing port of IBeam at CP 7000A. 7.Later, decom existing HW MW Link_7040A-7544B, 15G_2+0_28MHZ_512QAM_EPLA and perform EPLA between existing 7040A-7544B, 18G_1+0_55MHZ_512QAM and new HW MW Link 7040A-7544B, 18G_2+0_55MHZ_512QAM_EPLA. Become new HW MW Link 7040A-7544B, 18G_3+0_55MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-43398) and RTN910AF(RTN01, NEID 9-43415). | Existing HW MW Link_7040A-7544B, 15G&18G_3+0_28MHZ&55MHZ_512QAM_EPLA. MW Swap existing HW MW Link_7040A-7544B, 15G_2+0_28MHZ_512QAM_EPLA to new HW MW Link 7040A-7544B, 18G_2+0_55MHZ_512QAM. Later, decom existing HW MW Link_7040A-7544B, 15G_2+0_28MHZ_512QAM_EPLA and perform EPLA between existing 7040A-7544B, 18G_1+0_55MHZ_512QAM and new HW MW Link 7040A-7544B, 18G_2+0_55MHZ_512QAM_EPLA. Become new HW MW Link 7040A-7544B, 18G_3+0_55MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-43398) and RTN910AF(RTN01, NEID 9-43415). Site Impacted : 7040A. NE_7040A. 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-43398). 3.Re-use existing ISM8 slot 07 Port 1&2 of existing RTN910AF(RTN01, NEID 9-43398). 4.Install new XMC_3, Sub B_Hi x1. Lay new IF cables x1 with suitable length and type from new XMC_3, Sub B_Hi x1 to existing ISM8 slot 07 Port 1&2 of existing RTN910AF(RTN01, NEID 9-43398). Configure it. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffic 7040A via new HW MW Link 7040A-7544B, 18G_3+0_55MHZ_512QAM_EPLA. 7.Later, decom existing HW MW Link_7040A-7544B, 15G_2+0_28MHZ_512QAM_EPLA and perform EPLA between existing 7040A-7544B, 18G_1+0_55MHZ_512QAM and new HW MW Link 7040A-7544B, 18G_2+0_55MHZ_512QAM_EPLA. Become new HW MW Link 7040A-7544B, 18G_3+0_55MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-43398) and RTN910AF(RTN01, NEID 9-43415). | Existing HW MW Link_7040A-7544B, 15G&18G_3+0_28MHZ&55MHZ_512QAM_EPLA. MW Swap existing HW MW Link_7040A-7544B, 15G_2+0_28MHZ_512QAM_EPLA to new HW MW Link 7040A-7544B, 18G_2+0_55MHZ_512QAM. Later, decom existing HW MW Link_7040A-7544B, 15G_2+0_28MHZ_512QAM_EPLA and perform EPLA between existing 7040A-7544B, 18G_1+0_55MHZ_512QAM and new HW MW Link 7040A-7544B, 18G_2+0_55MHZ_512QAM_EPLA. Become new HW MW Link 7040A-7544B, 18G_3+0_55MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-43398) and RTN910AF(RTN01, NEID 9-43415). Site Impacted : 7040A. FE_4399A 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-43415). 3.Re-use existing ISM8 slot 03 Port 1&2 of existing RTN910AF(RTN01, NEID 9-43415). 4.Install new XMC_3, Sub B_Lo x1. Lay new IF cables x1 with suitable length and type from new XMC_3, Sub B_Lo x1 to existing ISM8 slot 03 Port 1&2 of existing RTN910AF(RTN01, NEID 9-43415). Configure it. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffic 7040A via existing port of IBeam at CP 7000A. 7.Later, decom existing HW MW Link_7040A-7544B, 15G_2+0_28MHZ_512QAM_EPLA and perform EPLA between existing 7040A-7544B, 18G_1+0_55MHZ_512QAM and new HW MW Link 7040A-7544B, 18G_2+0_55MHZ_512QAM_EPLA. Become new HW MW Link 7040A-7544B, 18G_3+0_55MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-43398) and RTN910AF(RTN01, NEID 9-43415). | XMC_3 | MAC | 18G | 18G_0.6M(MAC)+OMT x1 | 18G_0.6M(MAC)+OMT x1 | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022335 |  | 2026-02-24 |  | Ongoing | 2026-02-23 | 2026-02-24 | 2026-02-23 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-20 | 2026-05-20 | 2026-04-20 |  | RANA//WAQAS/6000006187 | NR Service TI | 2026-04-20 | 2026-05-20 | 2026-04-20 |  | RANA//WAQAS/6000006187 | NR Service TI | [7 empty] | 2026-04-20 | 2026-05-20 | 2026-04-20 |  | RANA//WAQAS/6000006187 | 2026-01-07: 2026-04-20; 2026-01-07: 2026-05-20; 2026-01-07: 2026-04-20; 2026-01-08: 2026-04-21 | [7 empty] | GTSB | SQ202512241147-GTSB
9646B_HU | KG BATU DANAU LIMBANG | DU00006461307 | Sarawak | Sarawak | 4.653250 | 114.842690 | [9 empty] | TSS+AA+TI |  | 13G_2+0_28M NE_9646B 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D_Sub A_Lo x1. ETH cat 6 x1. FE_9288A. 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. | MW Parallel Link | Existing link 13G_2+0_28M Install parallel link 13G_2+0_28M to become 13G_6+0_28M with EPLA 13G_4+0_28M under DU ID 9646B_HU_1 ( DU Code : DU00006514800). Site Impacted ; 9288R , 9287R , 9252Z , BBU E/// , SW03633. NE_9646B 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D_Sub A_Lo 4.Enable GE1 , transfer ETH from existing 9646B_RTN02_GE1 to New 9646B_RTN910A_GE1. 5.Disable unused GE port. 6.Create Service cross connect and EPLA. 7.Traffic migrate to new 13G_6+0_28M link. 8.No MW Decomm. FE_9288A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Enable GE1 , ETH patching to existing 9228A_RTN01_GE1. 5.Create service cross connect and EPLA. 6.Traffic migrate to new 13G_6+0_28M link. 7.No MW Decomm. | Existing link 13G_2+0_28M Install parallel link 13G_2+0_28M to become 13G_6+0_28M with EPLA 13G_4+0_28M under DU ID 9646B_HU_1 ( DU Code : DU00006514800). Site Impacted ; 9288R , 9287R , 9252Z , BBU E/// , SW03633. NE_9646B 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D_Sub A_Lo 4.Enable GE1 , transfer ETH from existing 9646B_RTN02_GE1 to New 9646B_RTN910A_GE1. 5.Disable unused GE port. 6.Create Service cross connect and EPLA. 7.Traffic migrate to new 13G_6+0_28M link. 8.No MW Decomm. | Existing link 13G_2+0_28M Install parallel link 13G_2+0_28M to become 13G_6+0_28M with EPLA 13G_4+0_28M under DU ID 9646B_HU_1 ( DU Code : DU00006514800). Site Impacted ; 9288R , 9287R , 9252Z , BBU E/// , SW03633. FE_9288A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Enable GE1 , ETH patching to existing 9228A_RTN01_GE1. 5.Create service cross connect and EPLA. 6.Traffic migrate to new 13G_6+0_28M link. 7.No MW Decomm. | XMC_5D | MDD | 13G | 1.2 | 1.2 | Trintel | SQ202601300958-Trintel |  |  |  |  | Ongoing | 2026-01-16 | 2026-01-31 | 2026-01-16 | 2026-01-29 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | JERRY SONLEY SALI7667000071 | Trintel TI | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | JERRY SONLEY SALI7667000071 | Trintel TI | [7 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | JERRY SONLEY SALI7667000071 | 2026-01-07: 2026-01-15; 2026-01-07: 2026-01-15; 2026-01-07: 2026-01-15 | [7 empty] | GCI | SQ202512241133-GCI | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | CHEONG/SENG/WAH/7018000306
7143B_HU | Jln Kg Tg Aru | DU00006461308 | Sabah | Sabah | 5.957190 | 116.051940 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI |  | 23G_1+0_112M NE_7143B 23G_SP_0.6M(MAC) x1. XMC_3E , Sub B_Lo x1. FE_7037A. 23G_SP_0.6M(MAC) x1. XMC_3E , Sub B_Hi x1. | MW Parallel Link | Existing link 23G_1+0_112M Install Parallel link 23G_1+0_112M Site Impacted : 7143B NE_7143B 1.Install new 23G_SP_0.6M(MAC). 2.Reuse existing 7143B_RTN03 , 7_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub B_Lo. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6. No MW decomm. FE_7037A. 1.Install new 23G_SP_0.6M(MAC). 2.Reuse existing 7037A_RTN10 , 7_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW Decomm. | Existing link 23G_1+0_112M Install Parallel link 23G_1+0_112M Site Impacted : 7143B NE_7143B 1.Install new 23G_SP_0.6M(MAC). 2.Reuse existing 7143B_RTN03 , 7_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub B_Lo. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6. No MW decomm. | Existing link 23G_1+0_112M Install Parallel link 23G_1+0_112M Site Impacted : 7143B FE_7037A. 1.Install new 23G_SP_0.6M(MAC). 2.Reuse existing 7037A_RTN10 , 7_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW Decomm. | XMC_3E | MAC | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | CHEONG/SENG/WAH/7018000306
1169D_HU | TmnJuta | DU00006461309 | Central | Selangor | 3.571028 | 101.655768 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_55M_512QAM_EPLA NE_1169D New 18G_DP_0.6M(MAC) x1. Re-use existing RTN910AF(RTN01, NEID 9-35803). New XMC_3E , Sub A_Lo x2. FE_1150A New 18G_DP_1.2M(MAC) x1. Re-use existing RTN910AF(RTN01, NEID 9-42957). New ISM8 x1. New XMC_3E , Sub A_Hi x2. | MW Swap | ****IMPORTANT NOTE: 1.ALREADY TRIGGER ZTE RAVIN IN ORDER TO TRIGGER GOP VIA EMAIL FOR CHECKING EXISTING HW MW LINK 1169D-1150A PERFORMANCE ISSUE IN WHICH HAD RSL DEGRADED UNTIL -90DBM. 2.PLEASE ENSURE LINK PERFORMANCE BACK TO NORMAL BEFORE CAN IMPLEMENTING DU 1169D_HU**** Existing HW MW Link_1169D-1150A, 18G_1+0_55MHZ_256QAM_395M. MW Swap to new HW MW Link 1169D-1150A, 18G_2+0_55MHZ_512QAM_EPLA_900M. Later, decom Antenna, ODU and RTN910AF(RTN03, NEID 9-35804) ONLY of HW MW Link_1169D-1150A, 18G_1+0_55MHZ_256QAM_395M. Anyway, do not decom RTN910AF(RTN01, NEID 9-35803). Site Impacted : 1169D. NE_1169D 1.Install new 18G_DP_0.6M(MAC) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-35803). 3.Install new XMC_3E , Sub A_Lo x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 1169D via new HW MW Link 1169D-1150A, 18G_2+0_55MHZ_512QAM_EPLA_900M. 6.Later, decom Antenna, ODU and RTN910AF(RTN03, NEID 9-35804) ONLY of HW MW Link_1169D-1150A, 18G_1+0_55MHZ_256QAM_395M. Anyway, do not decom RTN910AF(RTN01, NEID 9-35803). FE_1150A 1.Install new 18G_DP_1.2M(MAC) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-42957). Insert new ISM8 into slot 03. 3.Install new XMC_3E , Sub A_Hi x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 1169D via existing port at IBeam(CP 1146A). 6.Later, decom Antenna, ODU and RTN910AF(RTN03, NEID 9-35804) ONLY of HW MW Link_1169D-1150A, 18G_1+0_55MHZ_256QAM_395M. Anyway, do not decom RTN910AF(RTN01, NEID 9-35803). | ****IMPORTANT NOTE: 1.ALREADY TRIGGER ZTE RAVIN IN ORDER TO TRIGGER GOP VIA EMAIL FOR CHECKING EXISTING HW MW LINK 1169D-1150A PERFORMANCE ISSUE IN WHICH HAD RSL DEGRADED UNTIL -90DBM. 2.PLEASE ENSURE LINK PERFORMANCE BACK TO NORMAL BEFORE CAN IMPLEMENTING DU 1169D_HU**** Existing HW MW Link_1169D-1150A, 18G_1+0_55MHZ_256QAM_395M. MW Swap to new HW MW Link 1169D-1150A, 18G_2+0_55MHZ_512QAM_EPLA_900M. Later, decom Antenna, ODU and RTN910AF(RTN03, NEID 9-35804) ONLY of HW MW Link_1169D-1150A, 18G_1+0_55MHZ_256QAM_395M. Anyway, do not decom RTN910AF(RTN01, NEID 9-35803). Site Impacted : 1169D. NE_1169D 1.Install new 18G_DP_0.6M(MAC) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-35803). 3.Install new XMC_3E , Sub A_Lo x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 1169D via new HW MW Link 1169D-1150A, 18G_2+0_55MHZ_512QAM_EPLA_900M. 6.Later, decom Antenna, ODU and RTN910AF(RTN03, NEID 9-35804) ONLY of HW MW Link_1169D-1150A, 18G_1+0_55MHZ_256QAM_395M. Anyway, do not decom RTN910AF(RTN01, NEID 9-35803). | ****IMPORTANT NOTE: 1.ALREADY TRIGGER ZTE RAVIN IN ORDER TO TRIGGER GOP VIA EMAIL FOR CHECKING EXISTING HW MW LINK 1169D-1150A PERFORMANCE ISSUE IN WHICH HAD RSL DEGRADED UNTIL -90DBM. 2.PLEASE ENSURE LINK PERFORMANCE BACK TO NORMAL BEFORE CAN IMPLEMENTING DU 1169D_HU**** Existing HW MW Link_1169D-1150A, 18G_1+0_55MHZ_256QAM_395M. MW Swap to new HW MW Link 1169D-1150A, 18G_2+0_55MHZ_512QAM_EPLA_900M. Later, decom Antenna, ODU and RTN910AF(RTN03, NEID 9-35804) ONLY of HW MW Link_1169D-1150A, 18G_1+0_55MHZ_256QAM_395M. Anyway, do not decom RTN910AF(RTN01, NEID 9-35803). Site Impacted : 1169D. FE_1150A 1.Install new 18G_DP_1.2M(MAC) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-42957). Insert new ISM8 into slot 03. 3.Install new XMC_3E , Sub A_Hi x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 1169D via existing port at IBeam(CP 1146A). 6.Later, decom Antenna, ODU and RTN910AF(RTN03, NEID 9-35804) ONLY of HW MW Link_1169D-1150A, 18G_1+0_55MHZ_256QAM_395M. Anyway, do not decom RTN910AF(RTN01, NEID 9-35803). | XMC_3E | MAC | 18G | 18G_DP_0.6M(MAC) x1. | 18G_DP_1.2M(MAC) x1. | GCI | SQ202602230131-GCI | GCI | SQ202601080364-GCI // SQ202601080370-GCI |  |  | Ongoing | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-30 | 2026-04-06 | 2026-03-30 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123091 |  | 2025-12-31 | 2025-12-31 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2025-12-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-17 | 2026-02-09 | 2026-02-10 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-02-10 | 2026-02-17 | 2026-02-09 | 2026-02-20 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-16 | 2026-02-10 | 2026-02-17 | 2026-02-09 | 2026-02-20 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2026-02-10 | 2026-02-17 | 2026-02-09 | 2026-02-12 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512241142-GTSB
7489B | Simp. Kertam | DU00005010613 | Sabah | Sabah | 5.430000 | 118.270400 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP and patch cord | MW IDU Patching | 7489B RTN06-RTN09 congested. To replace with 10G port NE (7489B): 1) Existing connection: RTN06 GE1 to RTN09 GE2 2) Change to: RTN06 GE4 to RTN09 GE4 (10G) | NE (7489B): 1) Existing connection: RTN06 GE1 to RTN09 GE2 2) Change to: RTN06 GE4 to RTN09 GE4 (10G) | [6 empty] | NR services | SQ202502260432-NR Services | NR services | SQ202504080124-NR Services // SQ202504260199-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-02-19 | 2025-02-24 | 2025-02-22 | 2025-02-22 | MUHD//KHAIRUL NIZAM/7023000104 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-02-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-02-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250220BY |  | 2025-02-21 | 2025-02-24 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-24 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-04 | 2025-03-22 | 2025-03-04 | 2025-03-05 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-03-04 | 2025-03-22 | 2025-03-04 | 2025-03-05 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  | 2025-03-05 | 2025-03-04 | 2025-03-22 | 2025-03-04 | 2025-03-06 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | 2026-01-07: 2025-03-04; 2026-01-07: 2025-03-22; 2026-01-07: 2025-03-04; 2026-01-08: 2025-03-05 |  |  | 2025-03-24 | 2025-04-24 | 2025-03-24 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
4958A-4292B | Pokok Sena Kedah(Celcom) | DU00005036758 | Northern | Kedah | 6.155636 | 100.519159 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 23G_2+0_112M NE_4958A 23G_DP_0.6M(MAC)+OMT x1. XMC_3E , Sub A & B_Hi x2. ISM8 x1. FE_4292B 23G_DP_0.6M(MAC)+OMT x1. XMC_3E , Sub A & B_Lo x2. ISM8 x1. | MW Parallel Link | Existing link 23G_1+0_112M Install parallel link 23G_2+0_112M Site Impacted : 4958A , 4701D. NE_4958A 1.Install new 23G_DP_0.6M(MAC)+OMT 2.Install XMC_3E , Sub A & B_Hi. 3.Install 3_ISM8 into existing 4958A_RTN 11. 4.Reuse existing 4958A_RTN11. 5.Create service cross connect and EPLA. 6.No decom existing MW link. FE_4292B 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install XMC_3E , Sub A & B_Lo. 3.Install 3_ISM8 into existing 4292B_RTN02. 4.Reuse existing 4292B_RTN02. 5.Create service cross connect and EPLA. 6.No decom existing MW link. | Existing link 23G_1+0_112M Install parallel link 23G_2+0_112M Site Impacted : 4958A , 4701D. NE_4958A 1.Install new 23G_DP_0.6M(MAC)+OMT 2.Install XMC_3E , Sub A & B_Hi. 3.Install 3_ISM8 into existing 4958A_RTN 11. 4.Reuse existing 4958A_RTN11. 5.Create service cross connect and EPLA. 6.No decom existing MW link. | Existing link 23G_1+0_112M Install parallel link 23G_2+0_112M Site Impacted : 4958A , 4701D. FE_4292B 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install XMC_3E , Sub A & B_Lo. 3.Install 3_ISM8 into existing 4292B_RTN02. 4.Reuse existing 4292B_RTN02. 5.Create service cross connect and EPLA. 6.No decom existing MW link. | XMC_3E | MAC | 22736.000 23408.000 | 0.6m | 0.6m | GCI | SQ202503190713-GCI | GCI | SQ202503200266-GCI // SQ202503200268-GCI // SQ202504150095-GCI | 2026-01-20 | 2026-01-19 | Completed | 2025-03-16 | 2025-03-16 | 2025-03-16 | 2025-03-16 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022659 |  | 2025-02-27 | 2025-03-15 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-03-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-05 | 2025-03-31 | 2025-03-05 | 2025-03-15 | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2025-03-05 | 2025-03-31 | 2025-03-05 | 2025-03-24 | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-14 | 2025-03-05 | 2025-03-31 | 2025-03-05 | 2025-03-22 | MUHAMAD ARIFF BIN KHASIM6800000179 | 2026-01-07: 2025-03-05; 2026-01-07: 2025-03-31; 2026-01-07: 2025-03-05; 2026-01-08: 2025-03-24 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | CHEONG/SENG/WAH/7018000306
3295A2 | pBTS Jalan Kemboja Sbk Bernam | DU00005036759 | Central | Selangor | 3.787696 | 101.008307 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 18/2/2025 : Cutover done 17/2/2025 : Cutover WIP 15/2/205 : Plan install NE and FE site - Cancel proceed due to team stuck at site 4583B | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X IDU RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO | MW New Link / Reroute | MW REROUTE 3295A2-4585B WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB A_1.77KM FE IDU PATCHING TO XC B00277 OB FIBER IMPACTED: 3295A2 DISMANTLE EXISTING LINK 3295A2-4473A NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 3295A2-4473A FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. PATCH NEW IDU TO XC B00277 OB FIBER 6. DISMANTLE EXISTING LINK 3295A2-4473A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 3295A2-4473A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. PATCH NEW IDU TO XC B00277 OB FIBER 6. DISMANTLE EXISTING LINK 3295A2-4473A | XMC3E | DP | 23G | 0.6 | 0.6 | GCI | SQ202502260369-GCI | GCI | SQ202502180507-GCI // SQ202504150088-GCI | 2026-01-06 | 2026-01-05 | Completed | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-05 | 2025-03-06 | 2025-03-05 | 2025-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-05 | 2026-01-06 | 2026-01-05 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020831 |  | 2025-02-10 | 2025-02-10 | Completed | 2025-02-08 | 2025-02-10 | 2025-02-08 | 2025-02-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-03-05 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-03-05 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-18 | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-03-11 | MOHD FAIZ BIN MD YUNUS6800000186 | 2026-01-07: 2025-02-12; 2026-01-07: 2025-02-28; 2026-01-07: 2025-02-12; 2026-01-08: 2025-03-05 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
4583B_LOS | Kg Parit Baru | DU00005036760 | Northern | Selangor | 3.811880 | 100.845811 | WK07 | FEB 25 | WK07 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 15/2/2025 : Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X IDU RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO | MW New Link / Reroute | MW REROUTE 4583B-1612C/B00175 WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_128QAM_676MBPS_XMC3E_SUB A_2.83KM IDU PATCHING FE 1612C TO B00175 LL IDU PATCHING NE LINK 2796C-4583B TO NEW IDU 4583B-1612C/B00175 (NEW CP POINTING FOR CHILDSITE) IMPACTED: 4583B, 2796C DISMANTLE EXISTING LINK 4583B-4473A NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 128QAM 5. IDU PATCHING FOR CHILDSITE 2796C-4583B TO NEW IDU 4583B-1612C/B00175 6. DISMANTLE EXISTING LINK 4583B-4473A FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 128QAM 5. PATCH IDU TO XC B00175 LL 6. DISMANTLE EXISTING LINK 4583B-4473A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 128QAM 5. IDU PATCHING FOR CHILDSITE 2796C-4583B TO NEW IDU 4583B-1612C/B00175 6. DISMANTLE EXISTING LINK 4583B-4473A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 128QAM 5. PATCH IDU TO XC B00175 LL 6. DISMANTLE EXISTING LINK 4583B-4473A | XMC3E | DP | 18G | 0.6 | 0.6 | GCI | SQ202502180252-GCI | GCI | SQ202502180528-GCI // SQ202504150095-GCI // SQ202508140738-GCI | 2025-11-11 | 2025-11-13 | Completed | 2025-02-10 | 2025-02-10 | 2025-02-10 | 2025-02-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-12 | 2025-02-12 | 2025-02-12 | 2025-02-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020826 |  | 2025-02-10 | 2025-02-10 | Completed | 2025-02-08 | 2025-02-10 | 2025-02-08 | 2025-02-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-11 | 2025-02-28 | 2025-02-11 | 2025-03-05 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-11 | 2025-02-28 | 2025-02-11 | 2025-03-05 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-15 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-02-11 | 2025-02-28 | 2025-02-11 | 2025-03-11 | MOHD FAIZ BIN MD YUNUS6800000186 | 2025-02-11 | 2025-02-28 | 2025-02-11 | 2025-03-05 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | NG HONG JIE7018000036 | Logistic Team | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358
3373A | pBTS Jalan Menteri ( C ) | DU00005036761 | Central | Selangor | 3.757048 | 100.985110 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 19/2/2025 : Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X IDU RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO | MW New Link / Reroute | MW REROUTE 3373A-B02823 WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB A_0.70KM IMPACTED: 3373A DISMANTLE EXISTING LINK 3373A-4473A NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 3373A-4473A FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 3373A-4473A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 3373A-4473A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 3373A-4473A | XMC3E | DP | 23G | 0.6 | 0.6 | GCI | SQ202502260369-GCI | GCI | SQ202502180507-GCI // SQ202504150088-GCI // SQ202508140736-GCI | 2025-03-21 | 2025-03-20 | Completed | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-02-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-05 | 2025-03-06 | 2025-03-05 | 2025-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020829 |  | 2025-02-10 | 2025-02-10 | Completed | 2025-02-08 | 2025-02-10 | 2025-02-08 | 2025-02-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-14 | 2025-02-28 | 2025-02-14 | 2025-03-05 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-14 | 2025-02-28 | 2025-02-14 | 2025-03-05 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-02-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-14 | 2025-02-14 | 2025-02-28 | 2025-02-14 | 2025-03-11 | MOHD FAIZ BIN MD YUNUS6800000186 | 2026-01-07: 2025-02-14; 2026-01-07: 2025-02-28; 2026-01-07: 2025-02-14; 2026-01-08: 2025-03-05 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
4576A_LOS_1 | Bukit Pagar Tapah | DU00005036762 | Northern | Perak | 4.186050 | 101.254110 | [7 empty] | 00. Integrated/RFS Done | 29/04: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_4576A 18G_0.6m(MDD) x1. RTN910A,7_ISM8-2+0 x1. XMC_5D-2+0 , Sub_B_H x1i. FE_A00076 18G_0.6m(MDD) x1. RTN910A,7_ISM8-2+0 x1 XMC_5D-2+0 , Sub_B_Lo x1. | MW New Link / Reroute | Link Reroute to new FE A00076 due to LOS block. 18G_2+0_112M Site Impacted: 4576A. NE_4576A 1.Install new 18G_0.6m(MDD). 2.Install new RTN910A,7_ISM8-2+0(RTN no provide by MSP). 3.Install new XMC_5D-2+0 , Sub_B_Hi. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new FE route with new MW link. 6.Decom existing MW link (4576A-4442A) FE_A00076 1.Install new 18G_0.6m(MDD). 2.Install new RTN910A,7_ISM8-2+0(RTN no provide by MSP team). 3.Install new XMC_5D-2+0 , Sub_B_Lo. 4.Enable EPLA and service cross connect. 5.Migrate tarffic to new FE route with new MW link. 6.Create New In Band DCN. 7.Decom existing MW link (4442A-4576A). | Link Reroute to new FE A00076 due to LOS block. 18G_2+0_112M Site Impacted: 4576A. NE_4576A 1.Install new 18G_0.6m(MDD). 2.Install new RTN910A,7_ISM8-2+0(RTN no provide by MSP). 3.Install new XMC_5D-2+0 , Sub_B_Hi. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new FE route with new MW link. 6.Decom existing MW link (4576A-4442A) | Link Reroute to new FE A00076 due to LOS block. 18G_2+0_112M Site Impacted: 4576A. FE_A00076 1.Install new 18G_0.6m(MDD). 2.Install new RTN910A,7_ISM8-2+0(RTN no provide by MSP team). 3.Install new XMC_5D-2+0 , Sub_B_Lo. 4.Enable EPLA and service cross connect. 5.Migrate tarffic to new FE route with new MW link. 6.Create New In Band DCN. 7.Decom existing MW link (4442A-4576A). | XMC_5D | MDD | 18G | 0.6 | 0.6 | GCI | SQ202503190713-GCI | GCI | SQ202504260066-GCI // SQ202504260070-GCI // SQ202505150106-GCI | 2025-11-19 | 2025-11-18 | Completed | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-24 | 2025-07-23 | 2025-07-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25042224 |  | 2025-04-23 | 2025-04-24 | Completed | 2025-04-22 | 2025-04-23 | 2025-04-22 | 2025-04-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-25 | 2025-04-30 | 2025-04-25 | 2025-05-24 | team21gcitechnicalteam21gcitechnical | GCI TI | 2025-04-25 | 2025-04-30 | 2025-04-25 | 2025-07-06 | team21gcitechnicalteam21gcitechnical | GCI TI | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-29 | 2025-04-25 | 2025-04-30 | 2025-04-25 | 2025-12-17 | team21gcitechnicalteam21gcitechnical | 2026-01-07: 2025-04-25; 2026-01-07: 2025-04-30; 2026-01-07: 2025-04-25; 2026-01-08: 2025-04-25 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | CHEONG/SENG/WAH/7018000306
8037Z-4448B | Brook_T3_0269_RAN SHARING | DU00005036763 | Northern | Kelantan | 4.675209 | 101.495277 | [7 empty] | 03. TSS Only | 23/07: Commercial issue, End of July Settle (FE Blue Valley) | TSS |  | 13G_4+0_28M_CA NE_8037Z 13G_DP_1.8M(MDD) x1. XMC_5D , Sub B_Lo x1. ISM8 x2. FE_4448B 3G_DP_1.2M(MDD) x1. XMC_5D , Sub B_Hi x1. ISM8 x2 RTN910A x1 | MW New Link / Reroute | 8037Z to existing FE , no LOS available. and No LOS during TSS survey. Proposed Fiber. | 8037Z to existing FE , no LOS available. and No LOS during TSS survey. Proposed Fiber. | 8037Z to existing FE , no LOS available. and No LOS during TSS survey. Proposed Fiber. | XMC_5D | MDD | 13G | 1.8M | 1.2M | Magicell | SQ202504240474-Magicell // SQ202510010077-Magicell // SQ202511040094-Magicell | Magicell | No PR required-Work at TSS only |  |  | Ongoing | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-05-28 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-03 | 2026-04-04 | 2026-04-03 | 2026-04-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25032207 |  | 2025-03-23 | 2025-03-25 | Completed | 2025-03-22 | 2025-03-23 | 2025-03-22 | 2025-03-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-04-23 | 2025-04-23 | 2025-04-23 |  | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | [7 empty] | 2025-04-23 | 2025-04-23 | 2025-04-23 |  | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2026-01-07: 2025-04-23; 2026-01-07: 2025-04-23; 2026-01-07: 2025-04-23 | [7 empty] | GCI | SQ202505190519-GCI | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | CHEONG/SENG/WAH/7018000306
4607C-4574A | Kg Raja New Township | DU00005036764 | Northern | Pahang | 4.558429 | 101.414746 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+PAC | 15G_4+0_28M NE_4607C 15G_DP_0.6M(MDD) x2. XMC_5D , Sub A & B_Hi x2. ISM8 x2. FE_4574A 15G_DP_1.2M(MDD) x2. XMC_5D , Sub A & B_Lo x2. ISM8 x2. | MW Parallel Link | Existing link 15G_2+0_28M. Install new parallel link 15G_4+0_28M Site Impacted : 4607C , 4161D. NE_4607C 1.Install new 15G_DP_2 x 0.6M(MDD). 2.Reuse existing 4607C_RTN 3.Install new XMC_5D , Sub A & B_Hi for respective ant. 4.Install new 3_ISM8-2+0 & 4_ISM8-2+0. 5.Create service cross connect and EPLA. 6.No decom existing Huawei MW link . 7.Need to decom the existing SM link from the previous NIC as part of the TX rollout project. (4607C-4574A MW1) FE_4574A 1.Install new 15G_DP_2 x 1.2M(MDD). 2.Reuse existing 4574A_RTN 3.Install new XMC_5D , Sub A & B_Lo for respective ant. 4.Install new 3_ISM8-2+0 & 4_ISM8-2+0. 5.Create service cross connect and EPLA. 6.No decom existing Huawei MW link. 7.Need to decom the existing SM link from the previous NIC as part of the TX rollout project.(4574A-4607C MW1). | Existing link 15G_2+0_28M. Install new parallel link 15G_4+0_28M Site Impacted : 4607C , 4161D. NE_4607C 1.Install new 15G_DP_2 x 0.6M(MDD). 2.Reuse existing 4607C_RTN 3.Install new XMC_5D , Sub A & B_Hi for respective ant. 4.Install new 3_ISM8-2+0 & 4_ISM8-2+0. 5.Create service cross connect and EPLA. 6.No decom existing MW link. 7.Need to decom the existing SM link from the previous NIC as part of the TX rollout project.(4607C-4574A MW1). | Existing link 15G_2+0_28M. Install new parallel link 15G_4+0_28M Site Impacted : 4607C , 4161D. FE_4574A 1.Install new 15G_DP_2 x 1.2M(MDD). 2.Reuse existing 4574A_RTN 3.Install new XMC_5D , Sub A & B_Lo for respective ant. 4.Install new 3_ISM8-2+0 & 4_ISM8-2+0. 5.Create service cross connect and EPLA. 6.No decom existing MW link. .7Need to decom the existing SM link from the previous NIC as part of the TX rollout project.(4574A-4607C MW1). | XMC_5D | MDD | 15G | 0.6M x2 | 1.2M x2 | Magicell | SQ202503270808-Magicell | Magicell | SQ202503200275-Magicell // SQ202503200278-Magicell // SQ202504260184-Magicell // SQ202511030393-Magicell | 2025-08-19 | 2025-08-18 | Completed | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-19 | 2025-08-18 | 2025-08-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022668 |  | 2025-02-27 | 2025-03-13 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-03-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-06 | 2025-03-31 | 2025-03-06 | 2025-03-13 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-03-06 | 2025-03-31 | 2025-03-06 | 2025-03-13 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-07 | 2025-03-06 | 2025-03-31 | 2025-03-06 | 2025-03-10 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2026-01-07: 2025-03-06; 2026-01-07: 2025-03-31; 2026-01-07: 2025-03-06; 2026-01-08: 2025-03-07 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402
4189R | Kg Seri Perkasa | DU00005036765 | Northern | Perak | 3.808220 | 101.016110 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X IDU RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK 4189R-4585B WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB B_3.10KM IDU PATCHING AT FE 4585B TO XC B00277 OB FIBER IMPACTED: 4189R DISMANTLE EXISTING LINK 4189R-4473A NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 4189R-4473A FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. PATCH NEW IDU TO XC B00277 OB FIBER 6. 4585B BBU PATCHING TO XC OB FIBER B00277 7. DISMANTLE EXISTING LINK 4189R-4473A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 4189R-4473A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. PATCH NEW IDU TO XC B00277 OB FIBER 6. 4585B BBU PATCHING TO XC OB FIBER B00277 7. DISMANTLE EXISTING LINK 4189R-4473A | XMC3E | DP | 18G | 0.6 | 0.6 | GCI | SQ202502260417-GCI | GCI | SQ202502180528-GCI // SQ202504150095-GCI // SQ202508140738-GCI | 2025-11-27 | 2025-11-26 | Completed | 2025-02-07 | 2025-02-18 | 2025-02-18 | 2025-02-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021328 |  | 2025-02-14 | 2025-02-15 | Completed | 2025-02-13 | 2025-02-14 | 2025-02-13 | 2025-02-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-16 | 2025-02-28 | 2025-02-16 | 2025-03-05 | team41gcitechnicalteam41gcitechnical | GCI TI | 2025-02-16 | 2025-02-28 | 2025-02-16 | 2025-03-05 | team41gcitechnicalteam41gcitechnical | GCI TI | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-18 | 2025-02-16 | 2025-02-28 | 2025-02-16 | 2025-03-20 | MOHD FAIZ BIN MD YUNUS6800000186 | 2025-02-16 | 2025-02-28 | 2025-02-16 | 2025-03-05 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | NG HONG JIE7018000036 | Logistic Team | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300164-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
4992C-4063A | Jln Bayan Lepas | DU00005036766 | Northern | Penang | 5.296240 | 100.261921 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_4992C 23G_DP_0.6(MAC)+OMT x1. XMC_3E , Sub A & B_Hi x2. ISM8 x1. FE_4063A 23G_DP_0.6M(MAC)+OMT x1. XMC_3E , Sub A & B_Lo x2. ISM8 x1. | MW Swap | Existing link 23G_1+0_112M Swap existing link to 23G_2+0_112M ( Existing Space Constraint Issue). Site Impacted : 4992C , 4026L. NE_4992C 1.Install new 23G_DP_0.6(MAC)+OMT 2.Install XMC_3E , Sub A & B_Hi. 3.Install 3_ISM8-2+0 into existing 4992C_RTN01. 4.Reuse existing 4992C_RTN01. 5.Create service cross connect and EPLA. 6.Decom existing ODU and ANT. FE_4063A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install XMC_3E , Sub A & B_Lo. 3.Install 3_ISM8-2+0 into existing 4063A_RTN01. 4.Reuse existing 4063A_RTN01. 5.Create service cross connect and EPLA. 6.Decom existing ODU and ANT. | Existing link 23G_1+0_112M Swap existing link to 23G_2+0_112M (Existing Space Constraint Issue). Site Impacted : 4992C , 4026L. NE_4992C 1.Install new 23G_DP_0.6(MAC)+OMT 2.Install XMC_3E , Sub A & B_Hi. 3.Install 3_ISM8-2+0 into existing 4992C_RTN01. 4.Reuse existing 4992C_RTN01. 5.Create service cross connect and EPLA. 6.Decom existing ODU and ANT. | Existing link 23G_1+0_112M Swap existing link to 23G_2+0_112M (Existing Space Constraint Issue). Site Impacted : 4992C , 4026L. FE_4063A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install XMC_3E , Sub A & B_Lo. 3.Install 3_ISM8-2+0 into existing 4063A_RTN01. 4.Reuse existing 4063A_RTN01. 5.Create service cross connect and EPLA. 6.Decom existing ODU and ANT. | [5 empty] | GCI | SQ202504170476-GCI | GCI | SQ202504230248-GCI // SQ202504230250-GCI // SQ202504240699-GCI // SQ202505150106-GCI | 2025-09-27 | 2025-09-26 | Completed | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022664 |  | 2025-02-27 | 2025-03-20 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-03-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-21 | 2025-03-31 | 2025-03-21 | 2025-04-09 | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2025-03-21 | 2025-03-31 | 2025-03-21 | 2025-04-15 | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-03-25 | 2025-03-21 | 2025-03-31 | 2025-03-21 | 2025-04-19 | MUHAMAD ARIFF BIN KHASIM6800000179 | 2025-03-21 | 2025-03-31 | 2025-03-21 | 2025-04-11 | 2025-10-05 | 2025-10-05 | 2025-10-05 | 2025-10-05 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI
9640A-9283A | Sundar | DU00005038778 | Sarawak | Sarawak | 4.886000 | 115.209400 |  |  |  | AUG 25 |  |  | ZTE | 03. Pending TSS |  | TSS+AA+TI |  | 7G 2+0 28MHz 1.8m/1.8m XMC3, Sub J&L NE: 1) 1xISM8 card 2) 1x7GHz ODU XMC3 Sub J Lo 3) 1x7GHz ODU XMC3 Sub L Lo 4) 1x7GHz 1.8m DP FE: 1) 1xISM8 card 2) 1x7GHz ODU XMC3 Sub J Hi 3) 1x7GHz ODU XMC3 Sub L Hi 4) 1x7GHz 1.8m DP | MW Parallel Link | Install new parallel 2+0 link and EPLA with existing 3+0 link to create 5+0 link Impact sites: 9640A,9590C,9025Z,9256Z,9254Z Tx route: 9640A-9283A NE (9640A RTN02): 1) Install new ISM8 card at existing RTN02 slot 4 2) Install new link at 4-ISM8 3) Configure 5+0 EPLA FE (9283A RTN01): 1) Install new ISM8 card at existing RTN01 slot 4 2) Install new link at 4-ISM8 3) Configure 5+0 EPLA | NE (9640A RTN02): 1) Install new ISM8 card at existing RTN02 slot 4 2) Install new link at 4-ISM8 3) Configure 5+0 EPLA | FE (9283A RTN01): 1) Install new ISM8 card at existing RTN01 slot 4 2) Install new link at 4-ISM8 3) Configure 5+0 EPLA | XMC3 | DP | 7G | 1.8m | 1.8m | Trintel | SQ202511260578-Trintel | Trintel | SQ202509090366-Trintel // SQ202509090378-Trintel | 2026-01-28 | 2026-02-03 | Completed | 2025-10-25 | 2025-10-27 | 2025-10-25 | 2025-10-27 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-25 | 2025-10-27 | 2025-10-25 | 2025-10-27 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-02-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO | 2025-09-09 |  | Ongoing | 2025-09-08 | 2025-09-09 | 2025-09-08 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB_AA | SQ202510300154-GTSB
7061C-7450B | Sandakan Square | DU00005038779 | Sabah | Sabah | 5.868025 | 118.115544 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 2+0 0.6m/0.6m XMC3E NE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 4) 1x18GHz 0.6m DP FE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 4) 1x18GHz 0.6m DP | MW Swap | Swap existing 1+0 to 2+0 link NE (7061C RTN01): 1) Add new ISM8 card at existing RTN01 slot 4 2) Install new link at 4-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 7061C to new 2+0 link 5) Dismantle existing link FE (7450B RTN01): 1) Add new ISM8 card at existing RTN01 slot 4 2) Install new link at 4-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 7061C to new 2+0 link 5) Dismantle existing link | NE (7061C RTN01): 1) Add new ISM8 card at existing RTN01 slot 4 2) Install new link at 4-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 7061C to new 2+0 link 5) Dismantle existing link | FE (7450B RTN01): 1) Add new ISM8 card at existing RTN01 slot 4 2) Install new link at 4-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 7061C to new 2+0 link 5) Dismantle existing link | XMC3E | MAC DP | 18G | 0.6m | 0.6m | NR services | SQ202502180265-NR Services | NR services | SQ202504080097-NR Services // SQ202504080100-NR Services // SQ202504260199-NR Services | 2025-07-11 | 2025-07-07 | Completed | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-02-14 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021403 |  | 2025-02-15 | 2025-02-17 | Completed | 2025-02-14 | 2025-02-15 | 2025-02-14 | 2025-02-17 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-02-24 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-02-24 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-03-05 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-03-05 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016
9140B-9321A | Politeknik Matang 3G Den | DU00005038780 | Sarawak | Sarawak | 1.631060 | 110.190418 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 2+0 112MHz 0.6m/0.6m XMC3 NE: 1) 1xISM8 2) 1x23GHz XMC3E Sub A Hi 3) 1x23GHz XMC3E Sub B Hi 4) 1x23GHz 0.6m DP FE: 1) 1xISM8 2) 1x23GHz XMC3E Sub A Lo 3) 1x23GHz XMC3E Sub B Lo 4) 1x23GHz 0.6m DP | MW Swap | Swap existing 1+0 to 2+0 link NE (9140B RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9140B to new 2+0 link 5) Dismantle existing link FE (9321A RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9140B to new 2+0 link 5) Dismantle existing link | NE (9140B RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9140B to new 2+0 link 5) Dismantle existing link | FE (9321A RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 9140B to new 2+0 link 5) Dismantle existing link | XMC3 | MAC DP | 23G | 0.6m | 0.6m | Allstar | SQ202503060197-Allstar | Allstar | SQ202503050492-Allstar // SQ202504260202-Allstar | 2025-07-11 | 2025-07-07 | Completed | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-06-30 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022169 |  | 2025-02-22 | 2025-02-22 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-02-22 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-24 | 2025-03-02 | 2025-02-24 | 2025-02-27 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-02-24 | 2025-03-02 | 2025-02-24 | 2025-02-28 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-03-26 | 2025-02-24 | 2025-03-02 | 2025-03-04 | 2025-03-04 | BONG NEE NYEEbong.allstar@gmail.com | 2025-02-24 | 2025-03-02 | 2025-03-04 | 2025-03-04 | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507080651-GTSB | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | AB.RAHMAN//BIN MAT NOOH/6237001519
S00965-7165A | S093G_S00965OD_UITMADMINHILL | DU00005038781 | Sabah | Sabah | 6.066116 | 116.139886 |  |  |  |  | RFS | DONE | ZTE | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Perform remote upgrade 56MHz to 112MHz | NE (S00965): Perform remote upgrade 56MHz to 112MHz | FE (7165A): Perform remote upgrade 56MHz to 112MHz | [5 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
7000D-7209A | Kampung Simunul | DU00005038782 | Sabah | Sabah | 4.469602 | 118.619610 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | DO ready | TSS+AA+TI | L1+ATP+PAC | 18G 2+0 112MHz 0.6m/0.6m XMC3E NE: 1) 1xISM8 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 4) 1x18GHz 0.6m DP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 4) 1x18GHz 0.6m DP 5) 1x extra cat6 cable | MW Parallel Link | To add parallel link 7000D-7209A and perform load balancing. Traffic from 7000D RTN02 will use new link To perform LAG for IDU to IBEAM connection at 7209A NE (7000D RTN02): 1) Add ISM8 card at RTN02 slot 3 2) Install new link at 3-ISM8 3) Remove connection RTN02-RTN01 4) Migrate traffic 7127H,7215R,7625B,7355C to new link FE (7209A): 1) Install new RTN910A (ops team to assign number) 2) Install new link 7-ISM8 3) Patch GE1 and GE2 to CP port. Create LAG. migrate traffic and create DCN | NE (7000D RTN02): 1) Add ISM8 card at RTN02 slot 3 2) Install new link at 3-ISM8 3) Remove connection RTN02-RTN01 4) Migrate traffic 7127H,7215R,7625B,7355C to new link | FE (7209A): 1) Install new RTN910A (ops team to assign number) 2) Install new link 7-ISM8 3) Patch GE1 and GE2 to CP port. Create LAG. migrate traffic and create DCN | XMC3E | MAC DP | 18G | 0.6m | 0.6m | NR services | SQ202502260432-NR Services | NR services | SQ202504080110-NR Services // SQ202504080124-NR Services // SQ202504260199-NR Services | 2025-09-04 | 2025-09-04 | Completed | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-25 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-04 | 2025-03-07 | 2025-03-04 | 2025-03-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-04 | 2025-03-07 | 2025-03-04 | 2025-03-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021588 |  | 2025-02-16 | 2025-02-18 | Completed | 2025-02-15 | 2025-02-16 | 2025-02-15 | 2025-02-18 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-23 | 2025-02-28 | 2025-02-23 | 2025-03-06 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-02-23 | 2025-02-28 | 2025-02-23 | 2025-03-06 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  | 2025-03-06 | 2025-02-23 | 2025-02-28 | 2025-02-23 | 2025-03-17 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | 2025-02-24: 2025-02-23; 2025-03-02: 2025-02-28; 2025-03-04: 2025-02-23; 2025-03-04: 2025-03-10 |  |  | 2025-04-23 | 2025-05-23 | 2025-04-23 | 2025-04-23 | MASDIANA//BINTI BEDIN/6801000016
1427H_LOS | 99 Speedmart Tmn Perindustrian Puchong | DU00005051992 | Central | Selangor | 2.997850 | 101.612470 | WK12 | MAR 25 | WK12 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 21/3/2025 : Cutover done 20/3/2025 : FE installation complete, pending install NE site 19/3/2025 : Plan install NE and FE site - CRQ approved, cancel proceed spillover tomorrow 18/3/2025 : Digi OB - Small Cell - NE site 1427H 99 Speedmart Tmn Perindustrian Puchong, Digi OB - 3M Boom - RT - FE site 3655C Puchong Utama 8 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS RTN510 NE_1427H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. FE_3655C 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. | MW New Link / Reroute | Existing TX Route 1427H/1427H-NLOS-2168A-1213A Cambium link reroute to new FE 3655C due to LOS block. Existing cambium equipment Swap existing cambium equipment to NLOS RTN510. Site Impacted : 1427H. NE_1427H 1.Install new NLOS equipment (Indoor & Outdoor). 2.capture existing radio config and parameters. 3.Perform alignment direct towrads new FE 3655C. 4.Create service cross connect. 5.Migrate service to new NLOS link and New TX route (1427H-3655C-1372B). 6.Decom existing Cambium Link.Ensure traffic migrate completely before decom. FE_3655C 1.Install new NLOS equipment (Indoor & Outdoor). 2.Capture existing radio config and parameters. 3.Perform alignment direct twords 1427H. 4.Create service cross connect. 5.Enable GE port , ETH patching to existing 3655C_RTN01 (GE2). 6.Traffic migrate to new NLOS link and new TX route (1427H-3655C-1372B). 7.Decom existing cambium link.Ensure traffic migrate completely before decom. | Existing TX Route 1427H/1427H-NLOS-2168A-1213A Cambium link reroute to new FE 3655C due to LOS block. Existing cambium equipment Swap existing cambium equipment to NLOS RTN510. Site Impacted : 1427H. NE_1427H 1.Install new NLOS equipment (Indoor & Outdoor). 2.capture existing radio config and parameters. 3.Perform alignment direct towrads new FE 3655C. 4.Create service cross connect. 5.Migrate service to new NLOS link and New TX route (1427H-3655C-1372B). 6.Decom existing Cambium Link.Ensure traffic migrate completely before decom. | Existing TX Route 1427H/1427H-NLOS-2168A-1213A Cambium link reroute to new FE 3655C due to LOS block. Existing cambium equipment Swap existing cambium equipment to NLOS RTN510. Site Impacted : 1427H. FE_3655C 1.Install new NLOS equipment (Indoor & Outdoor). 2.Capture existing radio config and parameters. 3.Perform alignment direct twords 1427H. 4.Create service cross connect. 5.Enable GE port , ETH patching to existing 3655C_RTN01 (GE2). 6.Traffic migrate to new NLOS link and new TX route (1427H-3655C-1372B). 7.Decom existing cambium link.Ensure traffic migrate completely before decom. | [5 empty] | Magicell | SQ202503190673-Magicell | Magicell | SQ202503240702-Magicell // SQ202503240705-Magicell // SQ202504260146-Magicell | 2025-07-04 | 2025-07-04 | Completed | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-06-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031379 |  | 2025-03-14 | 2025-03-27 | Completed | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-27 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-27 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-21 | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-24 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-20 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202507080517-GCI | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
4476B_IPR | Lekir | DU00005996130 | Northern | Perak | 4.139380 | 100.724660 | [7 empty] | 00. Integrated/RFS Done | 8/9: Plan 12/9 | TSS+TI | L1+ATP+PAC | ETH LAN Cable x1 | IDU-IPRAN | Perform LAG at CP site for IDU 4476B-LEKIR-RTN05 to 4476B-MAC-001 Lekir 1) Patch 4476B-LEKIR-RTN05 GE2 to new CP port 2) Create LAG 3) Impact sites: 4027C | Perform LAG at CP site for IDU 4476B-LEKIR-RTN05 to 4476B-MAC-001 Lekir 1) Patch 4476B-LEKIR-RTN05 GE2 to new CP port 2) Create LAG 3) Impact sites: 4027C | [6 empty] | GTSB | SQ202508270907-GTSB | GTSB | SQ202508270967-GTSB | 2025-11-19 | 2025-11-20 | Completed | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082724 |  | 2025-08-28 | 2025-09-18 | Completed | 2025-08-27 | 2025-08-28 | 2025-08-27 | 2025-09-18 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-18 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-18 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-16 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2025-02-24: 2025-09-11; 2025-03-02: 2025-09-11; 2025-03-04: 2025-09-11; 2025-03-04: 2025-09-11 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509041075-GCI | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | CHEONG/SENG/WAH/7018000306
Q01137_AD | Q130A_Q01137OD_CB_PEGRAHENTERI | DU00006018817 | Sarawak | Sarawak | 3.664580 | 114.274520 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [8 empty] | Magicell | No PR required-Site drop/cancel |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q00486_AD | Q130A_Q00486OD_LAPOK | DU00006018818 | Sarawak | Sarawak | 3.706780 | 114.199730 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [8 empty] | Magicell | No PR required-Site drop/cancel |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01135_AD | Q130A_Q01135OD_CB_LOAGANBUNUT | DU00006018819 | Sarawak | Sarawak | 3.746660 | 114.239730 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [8 empty] | Magicell | No PR required-Site drop/cancel |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q02042_AD | Q130A_Q02042OD_T3_RHSERING | DU00006018820 | Sarawak | Sarawak | 3.822810 | 114.328510 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [8 empty] | Magicell | No PR required-Site drop/cancel |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01139_AD | Q130A_Q01139OD_T3_LONGPANAI | DU00006018821 | Sarawak | Sarawak | 3.949700 | 114.539200 | [7 empty] | 01. Pending Planning |  | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | [8 empty] | Magicell | SQ202509180716-Magicell |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100649-GTSB
3058C6-7230A | pBTS Suang Parai Village Housing (KM) | DU00004020679 | Sabah | Sabah | 6.038823 | 116.139549 |  |  |  | FEB 25 | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | DO ready | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 2+0 XMC3E 0.6m/0.6m DP NE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 4) 1x18GHz 0.6m DP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 4) 1x18GHz 0.6m DP 5) 1xcat6 cable | MW Swap | Existing link Huawei 3058C-7230A-01 (3058C RTN01 - 7230A RTN01) Swap existing 23G 1+0 with new 18G 2+0 Create LAG at CP port Impact sites: 3058C NE (3058C) 1. Install new ISM8 card at RTN01 slot 4 2. Install new link at RTN01 4-ISM8 3. Cutover traffic to new link FE (7230A) 1. Install new RTN910A (ops team to assign RTN number) 2. Install new link at new RTN 7-ISM8 3. Patch GE1 and GE2 new RTN to 2xnew CP port and create LAG 4. Cutover traffic to new link and create DCN | [7 empty] | YPTT | SQ202411120054-YPTT | NR services | SQ202502270741-NR Services // SQ202504260199-NR Services | 2025-07-11 | 2025-07-07 | Completed | 2024-11-06 | 2024-11-06 | 2024-11-06 | 2024-11-06 | DOMINIC DAVIES6794000049 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-07 | 2024-11-08 | 2024-11-07 | 2024-11-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-07 | 2024-11-08 | 2024-11-07 | 2024-11-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010776 |  | 2025-01-09 | 2025-01-15 | Completed | 2025-01-08 | 2025-01-09 | 2025-01-08 | 2025-01-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-23 | 2025-02-28 | 2025-02-23 | 2025-02-25 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-02-23 | 2025-02-28 | 2025-02-23 | 2025-02-25 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-25 | 2025-02-23 | 2025-02-28 | 2025-02-23 | 2025-02-27 | RALPH O'BRYAN HILARY7167000030 | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-02-26 | 2025-03-11 | 2025-03-11 | 2025-03-11 | 2025-03-11 | tseping//wang/6819000006 | Logistic Team | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
4573D-4685A | Surau Ittihad Taman Selasih Fasa 6 | DU00004020680 | Northern | Kedah | 5.380930 | 100.529520 |  |  |  | AUG 24 |  |  |  | 00. Integrated/RFS Done | 15/8: MOS & Pre-Installation WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: N/A FE: 1 x ISM8 card | MW Hardware Upgrade | 4685A fiber ready. To migrate child site (4573D) to fiber Impacted site: 4573D Current tx route: 4573D-4685A-4966A New tx route: 4573D-4685A-fiber-4966A NE (4573D): 1) Remain existing FE (4685A): 1) Install new ISM8 card at RTN01 slot 3 2) Transfer link RTN03 7-ISM8-1 to RTN01 3-ISM8-1 3) Migrate 4573D traffic to 4685A-fiber-4966A 4) RTN03 can be dismantle for re-deployment | [7 empty] | CCSMY | SQ202409251047-CCS | CCSMY | SQ202408220986-CCS | 2026-01-20 | 2026-01-19 | Completed | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-24 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240806AD |  | 2024-08-07 | 2024-08-15 | Completed | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-08-15 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-15 | 2024-08-31 | 2024-08-14 | 2024-08-15 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2024-08-15 | 2024-08-31 | 2024-08-14 | 2025-04-18 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-08-15 | 2024-08-31 | 2024-08-14 | 2026-04-08 | Arif//Afif Bin Mohd Zabidi/7021000041 | 2024-08-15 | 2024-08-31 | 2024-08-14 | 2024-08-20 | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | NG HONG JIE7018000036 | Logistic Team | 2024-10-16 | 2024-11-16 | 2024-10-16 | 2024-10-16 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300164-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
K00051_HU_1 | K013A_K00051OD_CB_TITIBAKONG | DU00006493366 | Northern | Kedah | 5.810423 | 100.378713 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_55M_512QAM_856 NE_4392K/K00051 New ISM8 x1. Re-use existing IF from slot 07 Port 2 to slot 03 Port 1. FE_K00825 New ISM8 x1. Re-use existing IF from slot 07 Port 2 to slot 03 Port 1. | MW Hardware Upgrade | Existing HW MW Link HW 18G_2+0_55M_512QAM_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 18G_2+0_55M_512QAM and later configure new HW 18G_4+0_55M_512QAM_CA. Site Impacted : 4392K/K00051 NE_4392K/K00051 1.Insert new ISM8 card into slot 03 of existing RTN910AF(RTN01, NEID 44-13940). 2.Shifting existing IF cable from slot 07 Port 2 to slot 03 Port 1 of existing RTN910AF(RTN01, NEID 44-13940). 3.Configure existing HW 18G_2+0_55M_512QAM_EPLA to new HW 18G_4+0_55M_512QAM_CA. FE_K00825 1.Insert new ISM8 card into slot 03 of existing RTN910AF(RTN01, NEID 44-23940). 2.Shifting existing IF cable from slot 07 Port 2 to slot 03 Port 1 of existing RTN910AF(RTN01, NEID 44-23940). 3.Configure existing HW 18G_2+0_55M_512QAM_EPLA to new HW 18G_4+0_55M_512QAM_CA. | Existing HW MW Link HW 18G_2+0_55M_512QAM_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 18G_2+0_55M_512QAM and later configure new HW 18G_4+0_55M_512QAM_CA. Site Impacted : 4392K/K00051 NE_4392K/K00051 1.Insert new ISM8 card into slot 03 of existing RTN910AF(RTN01, NEID 44-13940). 2.Shifting existing IF cable from slot 07 Port 2 to slot 03 Port 1 of existing RTN910AF(RTN01, NEID 44-13940). 3.Configure existing HW 18G_2+0_55M_512QAM_EPLA to new HW 18G_4+0_55M_512QAM_CA. | Existing HW MW Link HW 18G_2+0_55M_512QAM_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 18G_2+0_55M_512QAM and later configure new HW 18G_4+0_55M_512QAM_CA. Site Impacted : 4392K/K00051 FE_K00825 1.Insert new ISM8 card into slot 03 of existing RTN910AF(RTN01, NEID 44-23940). 2.Shifting existing IF cable from slot 07 Port 2 to slot 03 Port 1 of existing RTN910AF(RTN01, NEID 44-23940). 3.Configure existing HW 18G_2+0_55M_512QAM_EPLA to new HW 18G_4+0_55M_512QAM_CA. |  |  | 18G |  |  | GCI | SQ202601210141-GCI | GCI | SQ202601210098-GCI // SQ202601210138-GCI | 2026-03-17 | 2026-03-10 | Completed | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011448 |  | 2026-01-15 | 2026-01-15 | Completed | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-28 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-28 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-23 | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-28 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | 2025-02-24: 2026-01-22; 2025-03-02: 2026-01-27; 2025-03-04: 2026-01-22; 2025-03-04: 2026-01-23 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601070337-GTSB
4689D_HU_1 | Klebang RiaShoplot | DU00006493367 | Northern | Perak | 4.684521 | 101.108180 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | Perform 15G_4+0_28MHZ_512QAM_CA NE_4689D New ISM8 x1. Lay new IF cable with suitable type and length x1 RUN. FE_4346A New ISM8 x1. Lay new IF cable with suitable type and length x1 RUN. | MW Hardware Upgrade | Perform new HW MW Link, 15G_4+0_28MHZ_512QAM_CA. Site Impacted : 4689D. NE_4689D 1.Re-use exsiting RTN910AF(RTN01, NEID 9-24434) insert ISM8 into slot 04. 2.Lay new IF cable from 2nd port of ODU to new ISM8 slot 04 Port 1. Configure 4689D-4346A, 15G_4+0_28MHZ_512QAM_CA. 3.Re-use existing Vlan DCN and Vlan Services. 4.Migrate traffic 4689D via new HW MW Link, 15G_4+0_28MHZ_512QAM_CA. FE_4346A 1.Re-use exsiting RTN910AF(RTN10, NEID 9-24435) insert ISM8 into slot 04. 2.Lay new IF cable from 2nd port of ODU to new ISM8 slot 04 Port 1. Configure 4689D-4346A, 15G_4+0_28MHZ_512QAM_CA. 3.Re-use existing Vlan DCN and Vlan Services. 4.Migrate traffic 4689D via existing IBeam port. | Perform new HW MW Link, 15G_4+0_28MHZ_512QAM_CA. Site Impacted : 4689D. NE_4689D 1.Re-use exsiting RTN910AF(RTN01, NEID 9-24434) insert ISM8 into slot 04. 2.Lay new IF cable from 2nd port of ODU to new ISM8 slot 04 Port 1. Configure 4689D-4346A, 15G_4+0_28MHZ_512QAM_CA. 3.Re-use existing Vlan DCN and Vlan Services. 4.Migrate traffic 4689D via new HW MW Link, 15G_4+0_28MHZ_512QAM_CA. | Perform new HW MW Link, 15G_4+0_28MHZ_512QAM_CA. Site Impacted : 4689D. FE_4346A 1.Re-use exsiting RTN910AF(RTN10, NEID 9-24435) insert ISM8 into slot 04. 2.Lay new IF cable from 2nd port of ODU to new ISM8 slot 04 Port 1. Configure 4689D-4346A, 15G_4+0_28MHZ_512QAM_CA. 3.Re-use existing Vlan DCN and Vlan Services. 4.Migrate traffic 4689D via existing IBeam port. | XMC-5D Pro | MDD | 15G | 15G_0.6M(MDD) x1 | 15G_0.6M(MDD) x1 | GTSB | SQ202601150547-GTSB | GTSB | SQ202601150530-GTSB // SQ202601150542-GTSB |  |  | Ongoing | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-03 | 2026-04-10 | 2026-04-03 | 2026-04-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26012905 |  | 2026-01-30 | 2026-02-07 | Completed | 2026-01-29 | 2026-01-30 | 2026-01-29 | 2026-02-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-09 | 2026-02-28 | 2026-02-08 | 2026-02-24 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-02-09 | 2026-02-28 | 2026-02-08 | 2026-02-24 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-23 | 2026-02-09 | 2026-02-28 | 2026-02-08 | 2026-03-05 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-02-24: 2026-02-09; 2025-03-02: 2026-02-28; 2025-03-04: 2026-02-08; 2025-03-04: 2026-02-09 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601070337-GTSB
4529D_HU_1 | FeldaTeloi Timur | DU00006493368 | Northern | Kedah | 5.712500 | 100.676700 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M NE_4529D 13G_DP_1.2M(MDD) x1. XMC_5D , Sub A_Hi x1. FE_4623B. 13G_DP_1.2M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Lo x1. | MW Parallel Link | Existing link 15G_2+0_28M Install parallel link 13G_2+0_28M Site Impacted : 4529D NE_4529D 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4529D_RTN01 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW decom. FE_4623B. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4623B_RTN05 , 3_ISM8-2+0. 3.Install new 3_ISM8_2+0 into existing 4623B_RTN05. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLS with existing link. 6.Traffic migrate to new parallel link. 7.No MW decom. | Existing link 15G_2+0_28M Install parallel link 13G_2+0_28M Site Impacted : 4529D NE_4529D 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4529D_RTN01 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW decom. | Existing link 15G_2+0_28M Install parallel link 13G_2+0_28M Site Impacted : 4529D FE_4623B. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4623B_RTN05 , 3_ISM8-2+0. 3.Install new 3_ISM8_2+0 into existing 4623B_RTN05. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLS with existing link. 6.Traffic migrate to new parallel link. 7.No MW decom. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202601210141-GCI | GCI | SQ202601210098-GCI // SQ202601210138-GCI | 2026-02-04 | 2026-02-05 | Completed | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-28 | 2026-01-29 | 2026-01-28 | 2026-01-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010732 |  | 2026-01-08 | 2026-01-09 | Completed | 2026-01-07 | 2026-01-08 | 2026-01-07 | 2026-01-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-25 | 2026-01-19 | 2026-01-20 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-01-19 | 2026-01-25 | 2026-01-19 | 2026-01-21 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-20 | 2026-01-19 | 2026-01-25 | 2026-01-19 | 2026-02-06 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-02-24: 2026-01-19; 2025-03-02: 2026-01-25; 2025-03-04: 2026-01-19; 2025-03-04: 2026-01-20 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601070319-GCI | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | CHEONG/SENG/WAH/7018000306
B00774-B00542 | W066BB_B00774OD_TMNEMAS | DU00003911402 | Central | Selangor | 3.077614 | 101.764009 |  |  |  |  | Cancel / Drop | Close due to not in XC HU list | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Close due to not in XC HU list |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S00196-S00194 | S105B_S00196OD_TMNUNUYAN | DU00003911403 | Sabah | Sabah | 5.879710 | 118.052510 |  |  |  |  | Drop/Cancel |  |  | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Link has been reroute under NIC | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3293A-3310C | pBTS Setia Damai Migrant | DU00003911404 | Central | Selangor | 3.093065 | 101.463617 |  |  |  | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 15/8: D1: Cutover done | TSS+AA+TI | L1+ATP+PAC | FE: 1) 1xISM8 card | MW Hardware Upgrade | To perform reengineering at FE site 3310C to solve GE port congestion issue. Impact site: 3292A2, 3310C NE (3293A): 1) Remain existing FE (3310C): 1) Install new ISM8 card at RTN01 slot 3 2) Transfer IF cable from RTN02 7-ISM8-1 to RTN01 3-ISM8-1 3) Transfer BBU from RTN02 GE1 to RTN01 GE1 4) Re-configure service | [7 empty] | Allstar | SQ202408220872-Allstar | Allstar | SQ202408140500-Allstar | 2024-09-20 | 2024-09-19 | Completed | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-15 | 2024-08-16 | 2024-08-15 | 2024-08-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-22 | 2024-08-21 | 2024-08-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24080774 |  | 2024-08-08 | 2024-08-09 | Completed | 2024-08-07 | 2024-08-08 | 2024-08-07 | 2024-08-09 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-15 | 2024-08-31 | 2024-08-14 | 2024-11-19 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | Allstar TI | 2024-08-15 | 2024-08-31 | 2024-08-14 | 2024-09-23 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | Allstar TI | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-08-15 | SHUJAAT//ALI/6800000124 |  |  | 2024-08-15 | 2024-08-31 | 2024-08-14 | 2024-08-16 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | 2025-02-24: 2024-08-15; 2025-03-02: 2024-08-31; 2025-03-04: 2024-08-14; 2025-03-04: 2024-09-10 |  |  | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358
1819H_AD | Blok 2 Jalan 2 Kg Tasek Tambahan | DU00005794264 | Central | Selangor | 3.127502 | 101.771886 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | RTN 510_NLOS Radio NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_2108B 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | 1819H reroute to new FE 2163A due to existing FE 3240A to be decomm. Site Impacted : 1819H. NE_1819H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (1819H-3240A). FE_2163A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and reroute to new FE.. 5.Traffic migrate to new route FE site and with new NLOS equipment. 6.ETH cable patching to existing 2163A_RTN01_GE1. 7.Decom existing NLOS Radio (3240A - 1819H). | 1819H reroute to new FE 2163A due to existing FE 3240A to be decomm. Site Impacted : 1819H. NE_1819H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (1819H-3240A). | 1819H reroute to new FE 2163A due to existing FE 3240A to be decomm. Site Impacted : 1819H. FE_2163B. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new FE route. 5.Traffic migrate to new route FE site and with new NLOS equipment. 6.ETH cable patching to existing 2163A_RTN01_GE1. 7.Decom existing NLOS Radio (3240A - 1819H). | [5 empty] | GTSB | SQ202507220774-GTSB | GTSB | SQ202507220783-GTSB // SQ202507220789-GTSB | 2026-02-25 | 2026-02-25 | Completed | 2025-08-05 | 2025-08-19 | 2025-08-05 | 2025-08-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-05 | 2025-08-19 | 2025-08-05 | 2025-08-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-06 | 2025-08-07 | 2025-08-06 | 2025-08-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072108 |  | 2025-07-23 | 2025-07-23 | Completed | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-23 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-25 | PUWANESWARAN//A/L SUKUMARAN6000018484 | GTSB TI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-31 | PUWANESWARAN//A/L SUKUMARAN6000018484 | GTSB TI | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-31 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-31 | PUWANESWARAN//A/L SUKUMARAN6000018484 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-25 | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | NG HONG JIE7018000036 | Logistic Team | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507080517-GCI | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | CHEONG/SENG/WAH/7018000306
9042Z_LOS_1 | RumahLambai_RumahMinda_LadangMapai | DU00005794265 | Sarawak | Sarawak | 2.113270 | 112.284130 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 29/9/2025 : Cutover done, pending declare 27/9/2025 : Pending cutover due to pending Vlan 20/9/2025 : Plan to do MW New Link / Reroute - Re-plan due to CRQ not yet approved | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M_256QAM_CA NE_9042Z New 13G_1.2M(MDD) x1. New RTN910AF x1. New ISM8 x1. New XMC_5, Sub B_Lo x1. FE_Q01152 New 13G_1.2M(MDD) x1. New RTN910AF x1. New ISM8 x1. New XMC_5, Sub B_Hi x1. New Optical SFP Module HW 1.25G 10Km 1310nm x2. New Optical Patch Cord cable with suitable type and length x1. | MW New Link / Reroute | Existing HW MW Link_9042Z-9354A, 13G_3+0_28MHZ_256QAM&512QAM_EPLA. Reroute to new MW Link HW MW Link 9042Z-Q01152, 13G_4+0_28MHZ_256QAM_CA. Later, decom existing HW MW Link_9042Z-9354A, 13G_3+0_28MHZ_256QAM&512QAM_EPLA. Also, do not decom down link MW Link 9042Z-9043Z. Site Impacted : 9042Z & 9043Z. NE_9042Z 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01). 4.Install new XMC_5, Sub B_Lo x1. Configure it. 5.Request new xC Vlan DCN and Vlan services from ZTE IPRAN Team. 6.Migrate traffic 9042Z & 9043Z via new HW MW Link 9042Z-Q01152, 13G_4+0_28MHZ_256QAM_CA. 7.Later, decom existing HW MW Link_9042Z-9354A, 13G_3+0_28MHZ_256QAM&512QAM_EPLA. FE_Q01152 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF and insert new ISM8 x1 into slot 03 of new RTN910AF. 3.Install new XMC_5, Sub B_Hi x1. Configure it. 4.Request new xC Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Enable port 8-EM6-1 of new RTN910AF and insert Optical SFP Module 1.25G 10Km 1310nm. 6.Enable port 8-EM6-5 of existing RTN910AF of HW MW Link_SW03578 Q01152-Q00206(NEID 40892) and insert Optical SFP Module 1.25G 10Km 1310nm. 7.Cascading port 8-EM6-1 of new RTN910AF and port 8-EM6-5 of existing RTN910AF of HW MW Link_SW03578 Q01152-Q00206(NEID 40892). Configure it. 8.Migrate traffics 9042Z & 9043Z via existing port at PTN/Cisco at Q00206 in which similar to existing child sites such as Q01152, Q01155 & Q01154. 9.Later, decom existing HW MW Link_9042Z-9354A, 13G_3+0_28MHZ_256QAM&512QAM_EPLA. | Existing HW MW Link_9042Z-9354A, 13G_3+0_28MHZ_256QAM&512QAM_EPLA. Reroute to new MW Link HW MW Link 9042Z-Q01152, 13G_4+0_28MHZ_256QAM_CA. Later, decom existing HW MW Link_9042Z-9354A, 13G_3+0_28MHZ_256QAM&512QAM_EPLA. Also, do not decom down link MW Link 9042Z-9043Z. Site Impacted : 9042Z & 9043Z. NE_9042Z 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01). 4.Install new XMC_5, Sub B_Lo x1. Configure it. 5.Request new xC Vlan DCN and Vlan services from ZTE IPRAN Team. 6.Migrate traffic 9042Z & 9043Z via new HW MW Link 9042Z-Q01152, 13G_4+0_28MHZ_256QAM_CA. 7.Later, decom existing HW MW Link_9042Z-9354A, 13G_3+0_28MHZ_256QAM&512QAM_EPLA. | Existing HW MW Link_9042Z-9354A, 13G_3+0_28MHZ_256QAM&512QAM_EPLA. Reroute to new MW Link HW MW Link 9042Z-Q01152, 13G_4+0_28MHZ_256QAM_CA. Later, decom existing HW MW Link_9042Z-9354A, 13G_3+0_28MHZ_256QAM&512QAM_EPLA. Also, do not decom down link MW Link 9042Z-9043Z. Site Impacted : 9042Z & 9043Z. FE_Q01152 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF and insert new ISM8 x1 into slot 03 of new RTN910AF. 3.Install new XMC_5, Sub B_Hi x1. Configure it. 4.Request new xC Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Enable port 8-EM6-1 of new RTN910AF and insert Optical SFP Module 1.25G 10Km 1310nm. 6.Enable port 8-EM6-5 of existing RTN910AF of HW MW Link_SW03578 Q01152-Q00206(NEID 40892) and insert Optical SFP Module 1.25G 10Km 1310nm. 7.Cascading port 8-EM6-1 of new RTN910AF and port 8-EM6-5 of existing RTN910AF of HW MW Link_SW03578 Q01152-Q00206(NEID 40892). Configure it. 8.Migrate traffics 9042Z & 9043Z via existing port at PTN/Cisco at Q00206 in which similar to existing child sites such as Q01152, Q01155 & Q01154. 9.Later, decom existing HW MW Link_9042Z-9354A, 13G_3+0_28MHZ_256QAM&512QAM_EPLA | XMC-5D_SB B | MDD | 13G | 1.2 | 1.2 | MTK | SQ202507180636-MTK | Iezzpro | SQ202509090333-Iezzpro // SQ202509090359-Iezzpro | 2025-08-01 | 2025-07-30 | Completed | 2025-07-17 | 2025-07-18 | 2025-07-17 | [5 empty] | Unassigned | Disabled |  | 2025-07-22 | 2025-07-25 | 2025-07-22 | 2025-07-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-25 | 2025-07-22 | 2025-07-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-30 | 2025-08-01 | 2025-07-30 | 2025-07-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081346 |  | 2025-08-14 | 2025-09-02 | Completed | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-09-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-09-30 | 2025-09-21 | 2025-09-21 | Kevin//Tan/6000033214 | Iezzpro TI | 2025-09-19 | 2025-09-30 | 2025-10-13 | 2025-10-13 | Kevin//Tan/6000033214 | Iezzpro TI | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-02 | 2025-09-19 | 2025-09-30 | 2025-10-13 | 2025-10-13 | Kevin//Tan/6000033214 | 2025-07-24: 2025-09-19; 2025-07-24: 2025-09-30; 2025-07-24: 2025-09-29; 2025-07-25: 2025-09-29 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507080651-GTSB | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | HSU//MYET CHAE/6799000011
1524C_LOS | Eco Ardence_4 | DU00005794266 | Central | Selangor | 3.092962 | 101.473765 | [7 empty] | 03. TSS Only | 10/7/25:site decomm wip | TSS |  |  | MW New Link / Reroute | Team to proceed with TSS survey as site is being dismantled. | Team to proceed with TSS survey as site is being dismantled. | [6 empty] | GTSB | SQ202507160578-GTSB | GTSB | No PR required-Work at TSS only | 2025-08-21 | 2025-08-20 | Completed | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-12 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-18 | 2025-08-04 | 2025-08-04 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-06 | 2025-08-07 | 2025-08-06 | 2025-08-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202507080517-GCI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | CHEONG/SENG/WAH/7018000306
4611C_AD | Kuala Perlis Town | DU00006260179 | Northern | Perlis | 6.398600 | 100.132800 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB A HI 1x ODU 18G XMC5D SUB A LO | MW New Link / Reroute | MW NEW LINK/REROUTE LINK 4611C-R00023 WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC5D_SUB_B_2.53KM IMPACTED: 4611C DISMANTLE EXISTING LINK 4611C-4604A | 1. INSTALL NEW IDU RTN 910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 4611C-4604A | 1. INSTALL NEW IDU RTN 910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 4611C-4604A | XMC5D | MDD | 18G | 0.6 | 0.6 | Magicell | SQ202511270710-Magicell // SQ20260429056-Magicell | Magicell | SQ202511260111-Magicell // SQ202511260115-Magicell | 2025-12-05 | 2025-12-04 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-04 | 2025-12-05 | 2025-12-04 | 2025-12-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251117A0 |  | 2025-12-13 | 2025-11-20 | Completed | 2025-11-18 | 2025-12-13 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-01 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-08 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-28 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511130557-GCI | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
9701B_AD | Surau Darul Aman Miri | DU00006260180 | Sarawak | Sarawak | 4.492203 | 114.032800 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_56M_256QAM_EPLA NE_9701B New 23G_DP_0.3M(MAC)+OMT x1. Re-use existing RTN910AF(RTN02). New XMC_3, Sub B_Lo x2. FE_9529A New 23G_DP_0.3M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01). New XMC_3, Sub B_Hi x2. | MW New Link / Reroute | Existing HW MW Link 9701B-9579A, 23G_2+0_56M_512QAM_EPLA. Install new reroute HW MW Link 9701B-9529A, 23G_2+0_56M_256QAM_EPLA. Later, decom existing HW MW Link 9701B-9579A, 23G_2+0_56M_512QAM_EPLA. Site Impacted : 9701B. NE_9701B 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN02). 3.Install new XMC_3, Sub B_Lo x1. Configure it. 4.Lay new IF cable 2x and terminate at built in ISM8 port 1 & 2 of existing RTN910AF(RTN02). 5.Build new HW MW Link 9701B-9529A, 23G_2+0_56M_256QAM_EPLA. 6.Request new xD Vlan DCN & new Vlan services from ZTE IPRAN Team. 7.Migrate RAN Traffic to new HW MW Link 9701B-9529A, 23G_2+0_56M_256QAM_EPLA. 8.Later, decom existing HW MW Link 9701B-9579A, 23G_2+0_56M_512QAM_EPLA. FE_9529A 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01). 3.Install new XMC_3, Sub B_Hi x2. Configure it. 4.Lay new IF cable 2x and terminate at built in ISM8 port 1 & 2 of existing RTN910AF(RTN01). 5.Request new xD Vlan DCN & new Vlan services from ZTE IPRAN Team. 6.Migrate RAN Traffic to same port at IBeam(CP 9074A) similar to RAN 9529A. 7.Later, decom existing HW MW Link 9701B-9579A, 23G_2+0_56M_512QAM_EPLA. | Existing HW MW Link 9701B-9579A, 23G_2+0_56M_512QAM_EPLA. Install new reroute HW MW Link 9701B-9529A, 23G_2+0_56M_256QAM_EPLA. Later, decom existing HW MW Link 9701B-9579A, 23G_2+0_56M_512QAM_EPLA. Site Impacted : 9701B. NE_9701B 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN02). 3.Install new XMC_3, Sub B_Lo x1. Configure it. 4.Lay new IF cable 2x and terminate at built in ISM8 port 1 & 2 of existing RTN910AF(RTN02). 5.Build new HW MW Link 9701B-9529A, 23G_2+0_56M_256QAM_EPLA. 6.Request new xD Vlan DCN & new Vlan services from ZTE IPRAN Team. 7.Migrate RAN Traffic to new HW MW Link 9701B-9529A, 23G_2+0_56M_256QAM_EPLA. 8.Later, decom existing HW MW Link 9701B-9579A, 23G_2+0_56M_512QAM_EPLA. | Existing HW MW Link 9701B-9579A, 23G_2+0_56M_512QAM_EPLA. Install new reroute HW MW Link 9701B-9529A, 23G_2+0_56M_256QAM_EPLA. Later, decom existing HW MW Link 9701B-9579A, 23G_2+0_56M_512QAM_EPLA. Site Impacted : 9701B. FE_9529A 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01). 3.Install new XMC_3, Sub B_Hi x2. Configure it. 4.Lay new IF cable 2x and terminate at built in ISM8 port 1 & 2 of existing RTN910AF(RTN01). 5.Request new xD Vlan DCN & new Vlan services from ZTE IPRAN Team. 6.Migrate RAN Traffic to same port at IBeam(CP 9074A) similar to RAN 9529A. 7.Later, decom existing HW MW Link 9701B-9579A, 23G_2+0_56M_512QAM_EPLA. | XMC_3 | MAC | 23G | 23G_0.3M(MAC)+OMT x1 | 23G_0.3M(MAC)+OMT x1 | Magicell | SQ202511070147-Magicell | Trintel | SQ202511170542-Trintel // SQ202511170549-Trintel | 2025-11-17 | 2025-11-10 | Completed | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-05 | 2025-11-12 | 2025-11-05 | 2025-11-05 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111174 |  | 2025-11-12 | 2025-11-13 | Completed | 2025-11-11 | 2025-11-12 | 2025-11-11 | 2025-11-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-14 | JERRY SONLEY SALI7667000071 | Trintel TI | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-20 | JERRY SONLEY SALI7667000071 | Trintel TI | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-21 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-12-18 | JERRY SONLEY SALI7667000071 | 2025-11-25: 2025-11-12; 2025-11-25: 2025-11-12; 2025-11-25: 2025-11-12; 2025-11-28: 2025-11-14 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511050424-GTSB
7328H6_EVT | DEWAN DATUK SRI PENGLIMA HJ.MOHD. DUN BANIR (DEWAN PA’MUSA BEAUFORT) | DU00006260181 | Sabah | Sabah | 5.344640 | 115.746680 | [13 empty] | Planning and integration support only for event site 7328H6 DEWAN DATUK SRI PENGLIMA HJ.MOHD. DUN BANIR (DEWAN PA’MUSA BEAUFORT) Tx route: 7328H6/7328H6-7001A-LL-7000A 1) Share port with 7001A at 7000A 2) New NE ID FE IDU 7001A RTN03 3) New NE ID NE IDU 7328H6 RTN01 4) At FE site 7001A patch RTN03 GE1 to existing RTN01 GE1 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
R00095_AD | R001B_R00095OD_IKBN_KUALA_PERLIS | DU00006260182 | Northern | Perlis | 6.397994 | 100.143876 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 2X RTN910A 2X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB A HI 1x ODU 15G XMC5D SUB A LO | MW New Link / Reroute | MW NEW LINK/REROUTE LINK R00025-4729A WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_512QAM_848MBPS_XMC5D_WITH CA_SUB_A_6.90KM IMPACTED: R00025 DISMANTLE EXISTING LINK R00095-R00010 | 1. INSTALL NEW IDU RTN 910 AND 2PCS ISM8 SLOT 3&4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 16G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK R00095-R00010 | 1. INSTALL NEW IDU RTN 910 AND 2PCS ISM8 SLOT 3&4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 16G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK R00095-R00010 | XMC5D | MDD | 13G | 0.6 | 1.2 | Magicell | SQ202511270710-Magicell // SQ20260429056-Magicell | Magicell | SQ202511260111-Magicell // SQ202511260115-Magicell // SQ202512120136-Magicell | 2025-11-29 | 2025-12-03 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251117A3 |  | 2025-12-13 | 2025-11-20 | Completed | 2025-11-18 | 2025-12-13 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-29 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-01 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-10 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511130557-GCI | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
3393A_HU | Putra-Cyber2 | DU00006260183 | Central | Selangor | 2.856590 | 101.690610 | [7 empty] | 03. TSS Only |  | TSS |  |  | MW New Link / Reroute | TSS ONLY. HU DONE UNDER 1869B_HU_1 MW NEW LINK 3393A-3092A WITH HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_512QAM_1778MBPS_XMC5D_SUB_A_LINK_2.05KM REVERSE THE LINK FROM EXISTING 3393A-1869B TO 1869B-3393A IMPACTED: 3251C, 3393A, 2736C NEW LINK CARRY 3251C, 3393A, 2736C TRAFFIC FE PATCH TO FIBER | [7 empty] | Magicell | SQ202511260105-Magicell | Magicell | No PR required-Work at TSS only |  |  | Ongoing | 2025-11-21 | 2025-11-22 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25111253 |  | 2025-12-13 | 2025-11-18 | Completed | 2025-11-12 | 2025-12-13 | 2025-11-12 | 2025-11-18 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202511040420-GCI | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
4135H_AD | ZV Specialised | DU00006260184 | Northern | Perlis | 6.401290 | 100.135499 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS RTN501 NE. 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE. 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | UPLINK DU 4608B_AD NEED TO REROUTE FIRST. NLOS link reroute to new FE 4608B due to LOS Block NLOS RTN510 Site Impacted : 4135H. 4135H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new FE route site. 6.Decom existing NLOS radio (4135H-NLOS-4604A) FE_4608B 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create Service cross connect. 5.GE port , patching the ETH cable to existing 6.Traffic migarte to new FE. 7.Decom existing NLOS Radio (4135H-NLOS-4604A) | 4135H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new FE route site. 6.Decom existing NLOS radio (4135H-NLOS-4604A) | FE_4608B 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create Service cross connect. 5.GE port , patching the ETH cable to existing 6.Traffic migarte to new FE. 7.Decom existing NLOS Radio (4135H-NLOS-4604A) | [5 empty] | Magicell | SQ202511270710-Magicell // SQ20260429056-Magicell | GTSB | SQ202601190057-GTSB // SQ202601190059-GTSB | 2025-12-04 | 2025-12-03 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111801 |  | 2025-12-13 | 2025-11-20 | Completed | 2025-11-18 | 2025-12-13 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2026-01-08 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-13 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2026-01-16 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2026-01-07 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511130557-GCI | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
4302B_AD_2 | CKTJONG | DU00006158634 | Northern | Perak | 3.983534 | 101.124790 | [9 empty] | TSS+TI |  |  | MW Dismantle | ****IMPORTANT NOTE: PLEASE ENSURE DU 4302B_AD AND DU 4445A_AD IMPLEMENT FIRST. IF NOT, IT WILL IMPACT OUTAGE TO RAN TRAFFICS 4302B & 4445A. Site Impacted : 4302B & 4445A(If DU 4302B_AD & DU 4445A_AD not implement at first stage) NE_4302B & FE_4445A. 1.Decom existing xD HW MW Link 4302B-4445A(13G&15G_6+0_28MHZ_512QAM_1344. | ****IMPORTANT NOTE: PLEASE ENSURE DU 4302B_AD AND DU 4445A_AD IMPLEMENT FIRST. IF NOT, IT WILL IMPACT OUTAGE TO RAN TRAFFICS 4302B & 4445A. Site Impacted : 4302B & 4445A(If DU 4302B_AD & DU 4445A_AD not implement at first stage) NE_4302B & FE_4445A. 1.Decom existing xD HW MW Link 4302B-4445A(13G&15G_6+0_28MHZ_512QAM_1344. | ****IMPORTANT NOTE: PLEASE ENSURE DU 4302B_AD AND DU 4445A_AD IMPLEMENT FIRST. IF NOT, IT WILL IMPACT OUTAGE TO RAN TRAFFICS 4302B & 4445A. Site Impacted : 4302B & 4445A(If DU 4302B_AD & DU 4445A_AD not implement at first stage) NE_4302B & FE_4445A. 1.Decom existing xD HW MW Link 4302B-4445A(13G&15G_6+0_28MHZ_512QAM_1344. | [5 empty] | GTSB | SQ202604060636-GTSB | GTSB | SQ202604060630-GTSB // SQ202604060633-GTSB // SQ202604280656-GTSB |  |  | Ongoing | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [7 empty] | 2026-04-17 | 2026-04-30 | 2026-04-17 |  | AIMAN HAKIM//BIN AZHARI/6799000313 | GTSB TI | [7 empty] | 2026-04-17 | 2026-04-30 | 2026-04-17 |  | AIMAN HAKIM//BIN AZHARI/6799000313 | 2025-11-25: 2026-04-17; 2025-11-25: 2026-04-30; 2025-11-25: 2026-04-17; 2026-01-07: 2026-04-17 | [7 empty] | GTSB | SQ202510100642-GTSB
4302B_AD | CKTJONG | DU00006158635 | Northern | Perak | 3.983534 | 101.124790 | [7 empty] | 06. Other Issue |  | TSS+TI | L1+ATP+PAC | BBU Patching at NE(4302B). NE_4302B/A00079 New SFP Module 1G with 10Km 1310nm x2(For ZTE RAN & HW IDU). New Optical Patch Cord cable x1 with suitable type and length. | BBU Patching | ****IMPORTANT NOTE: 1.PLEASE ENSURE DU 4302B_AD PERFORM FIRST BEFORE PERFORM DU 4445A_AD. 2.EXISTING XC HW MW LINK NT06016, A00079-A0012 HAVING RSL DEGRADATION FOR ALL CHANNEL. ALREADY TRIGGER GOP VIA EMAIL BY RAVIN AND STILL AWAITING ACTION FROM GOP. SUSPECT LOS PARTIALLY BLOCKED OR ANTENNA MISALIGNMENT. 3.EXISTING XC HW MW Link_ID NT06016, A00079-A00128 NEED TO CHANGE TX SOW FROM DECOM TO EXISTING TX. 4.AT A00128 NEED TO REMAIN OB FIBER(66031-TELUKINTAN-AGGB01).**** Diverting xD Traffic to existing xC HW MW Link_ID NT06016, A00079-A00128. Site Impacted : 4302B. NE_4302B/A00079 1.Disable port 8-EM6-1 of RTN01(NEID 30486) of existing HW MW Link(4302B-4445A). 2.Enable port 8-EM6-5 of existing HW MW Link_ID NT06016, A00079-A00128. 3.Insert Optical SFP Module 1G 10Km 1310nm into RAN/BBU 4302B and into port 8-EM6-5 RTN910AF(NEID 34727). 4.Perform patching in between RAN/BBU 4302B and into port 8-EM6-5 RTN910AF(NEID 34727) 5.Request new xC Vlan Services. 6.Migrate traffic 4302B via existing HW MW Link_ID NT06016, A00079-A00128. FE_A00128 1.Request new port at PTN/Cisco from ZTE IPRAN Team. 2.Migrate traffic 4302B into new 1G at PTN/Cisco. | ****IMPORTANT NOTE: 1.PLEASE ENSURE DU 4302B_AD PERFORM FIRST BEFORE PERFORM DU 4445A_AD. 2.EXISTING XC HW MW LINK NT06016, A00079-A0012 HAVING RSL DEGRADATION FOR ALL CHANNEL. ALREADY TRIGGER GOP VIA EMAIL BY RAVIN AND STILL AWAITING ACTION FROM GOP. SUSPECT LOS PARTIALLY BLOCKED OR ANTENNA MISALIGNMENT. 3.EXISTING XC HW MW Link_ID NT06016, A00079-A00128 NEED TO CHANGE TX SOW FROM DECOM TO EXISTING TX. 4.AT A00128 NEED TO REMAIN OB FIBER(66031-TELUKINTAN-AGGB01).**** Diverting xD Traffic to existing xC HW MW Link_ID NT06016, A00079-A00128. Site Impacted : 4302B. NE_4302B/A00079 1.Disable port 8-EM6-1 of RTN01(NEID 30486) of existing HW MW Link(4302B-4445A). 2.Enable port 8-EM6-5 of existing HW MW Link_ID NT06016, A00079-A00128. 3.Insert Optical SFP Module 1G 10Km 1310nm into RAN/BBU 4302B and into port 8-EM6-5 RTN910AF(NEID 34727). 4.Perform patching in between RAN/BBU 4302B and into port 8-EM6-5 RTN910AF(NEID 34727) 5.Request new xC Vlan Services. 6.Migrate traffic 4302B via existing HW MW Link_ID NT06016, A00079-A00128. | ****IMPORTANT NOTE: 1.PLEASE ENSURE DU 4302B_AD PERFORM FIRST BEFORE PERFORM DU 4445A_AD. 2.EXISTING XC HW MW LINK NT06016, A00079-A0012 HAVING RSL DEGRADATION FOR ALL CHANNEL. ALREADY TRIGGER GOP VIA EMAIL BY RAVIN AND STILL AWAITING ACTION FROM GOP. SUSPECT LOS PARTIALLY BLOCKED OR ANTENNA MISALIGNMENT. 3.EXISTING XC HW MW Link_ID NT06016, A00079-A00128 NEED TO CHANGE TX SOW FROM DECOM TO EXISTING TX. 4.AT A00128 NEED TO REMAIN OB FIBER(66031-TELUKINTAN-AGGB01).**** Diverting xD Traffic to existing xC HW MW Link_ID NT06016, A00079-A00128. Site Impacted : 4302B. FE_A00128 1.Request new port at PTN/Cisco from ZTE IPRAN Team. 2.Migrate traffic 4302B into new 1G at PTN/Cisco. | [5 empty] | GTSB | SQ202512160971-GTSB | GTSB | SQ202512240260-GTSB |  |  | Ongoing | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-30 | 2026-05-07 | 2026-04-30 | 2026-05-01 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251118AO |  | 2025-11-19 | 2025-11-20 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-07 | 2026-04-30 | 2026-04-07 | 2026-04-09 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-04-07 | 2026-04-30 | 2026-04-07 | 2026-04-09 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-07 | 2026-04-30 | 2026-04-07 | 2026-04-20 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-11-25: 2026-04-07; 2025-11-25: 2026-04-30; 2025-11-25: 2026-04-07; 2026-01-07: 2026-04-08 | [7 empty] | GTSB | SQ202510100642-GTSB
4302B_AD_1 | CKTJONG | DU00006158636 | Northern | Perak | 3.983534 | 101.124790 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [8 empty] | GTSB |  | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100642-GTSB
9355B | Kidurong Ind (Celcom) | DU00004586676 | Sarawak | Sarawak | 3.247877 | 113.094521 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | To perform IDU patching at NE site 9355B from xD IDU to xC PTN for Q01293 xC BBU BW sharing Impacted site: Q01293 (xC BBU) Current Tx route: Q01293-Q00286-Q00254 New Tx route: Q01293/9764B-9355B/Q00252 REMARKS: PHYSICAL PATCHING TO BE CARRIED OUT BY OSS TEAM. ZTE TEAM TO PROVIDE REMOTE SUPPORT FOR PORT AND SERVICE CONFIGURATION ONLY NE (9355B): 1) Perform patching from 9355B RTN01 GE5 (optical) to xC PTN (PTN ID 30145 KIDURONGIND) - ops team to assign port 2) Perform service configuration. Recommend to reconfigure service using QinQ to avoid broadcast storm - ops team to assign SVLAN | [9 empty] | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB_AA | SQ202510300154-GTSB | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q01293 | Q118B_Q01293OD_KIDURONGIND2 | DU00004586677 | Sarawak | Sarawak | 3.261171 | 113.089564 | [7 empty] | 00. Site Out/Drop |  | AA |  |  | MW Remote Upgrade | To perform BBU patching for xC BBU Q01293 to xD MW link 9764B-9355B Current Tx route: Q01293-Q00286-Q00254 New Tx route: Q01293/9764B-9355B/Q00252 REMARKS: PHYSICAL PATCHING TO BE CARRIED OUT BY OSS TEAM. ZTE TEAM TO PROVIDE REMOTE SUPPORT FOR PORT AND SERVICE CONFIGURATION ONLY 1) Patch xC BBU Q01293 to 9764B RTN01 GE2 2) Perform service configuration on existing MW link 9764B-9355B | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300154-GTSB
1087B_LOS | Jinjang Utara 2 | DU00004586693 | Central | Kuala Lumpur | 3.219550 | 101.656680 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 9/12: TSS in plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_1087B 18G_0.6m(MDD) x1. RTN910A x1. XMC_5D-2+0 , sub A_Lo x1. FE_2086B 18G_0.6m(MDD) x1. RTN910A x1. XMC_5D-2+0 , Sub A_Hi x1. | MW New Link / Reroute | Link Reroute to new FE 1098B due to LOS Block. Site Impacted : 1087B , 2338A NE_1087B 1.Install new 18G_0.6m(MDD). 2.Install new RTN910A.(RTN no provide by MSP team). 3.Install new XMC_5D-2+0 , sub A_Lo 4.Enable EPLA and Service cross connect. 5.Traffic migrate to new FE route (1087B & 2338A). 6. Patch GE1 to BBU 1087B and GE2 cascade to RTN02 (which carry 2338A) 7.Decom existing mw Parallel link (1087B-1002A).Ensure no traffic before decom.1087B (RTN01 & RTN02) , 1002A (RTN03 & RTN06). FE_1098B 1.Install new 18G_0.6m(MDD). 2.Install new RTN910A.(RTN no provide bt MSP team). 3.Install new XMC_5D-2+0 , Sub A_Hi. 4.Enable EPLA and service cross connect. 5.Enable GE1 port , patching ETH cable to existing 1098B_RTN03 (GE2). 6.Traffic migrate to new FE route (1087B & 2338A). 7.Create new IN band DCN 8.Decom existing mw parallel link (1002A-1087B).Ensure no traffic before decom.1087B (RTN01 & RTN02) , 1002A (RTN03 & RTN06). | [7 empty] | YPTT | SQ202412180491-YPTT | YPTT | SQ202412180543-YPTT // SQ202504260171-YPTT |  |  | Ongoing | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | MOHD//SHAHREEZAN BIN RAZALI/6794000119 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24121401 |  | 2024-12-16 |  | Ongoing | 2024-12-14 | 2024-12-16 | 2024-12-14 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2024-12-21 | 2024-12-31 | 2024-12-21 |  | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2024-12-21 | 2024-12-31 | 2024-12-21 |  | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2024-12-23 | 2024-12-23 | 2024-12-23 | 2024-12-23 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-12-21 | 2024-12-31 | 2024-12-21 | 2024-12-26 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | 2024-12-21 | 2024-12-31 | 2024-12-21 | 2024-12-21 | 2025-01-07 | 2025-01-07 | 2025-01-07 | 2025-01-07 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
4686A_LOS | Relau | DU00004621708 | Northern | Perak | 5.226203 | 100.549009 | [6 empty] | ZTE | 00. Integrated/RFS Done | 11/12: Raised up antenna at NE & RSL as per LB 10/12: Trigger by xD LOS blocked | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NA | MW Swap | Solution 1: Raise up / Relocate ant height at 4239A in order obtained the clear LOS towards the 4686A and towards the 4773A. | [7 empty] | GCI | SQ202412120234-GCI | GCI | SQ202412120232-GCI // SQ202504150095-GCI | 2025-08-21 | 2025-08-20 | Completed | 2025-01-08 | 2025-01-08 | 2025-01-08 | 2025-01-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24121212 |  | 2024-12-13 | 2024-12-30 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2024-12-30 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-11 | 2024-12-31 | 2024-12-11 | 2024-12-30 | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2024-12-11 | 2024-12-31 | 2024-12-11 | 2024-12-30 | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-01-13 | 2024-12-11 | 2024-12-31 | 2024-12-11 | 2025-01-08 | MUHAMAD ARIFF BIN KHASIM6800000179 | 2025-11-25: 2024-12-11; 2025-11-25: 2024-12-31; 2025-11-25: 2024-12-11; 2026-01-07: 2024-12-12 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
3695A_AD | Jade Hill | DU00005988869 | Central | Selangor | 2.994500 | 101.759280 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G 1.2M DP ANTENNA 1x ODU 18G XMC5D SUB B HI 1X ODU 18G XMC5D SUB B LO | MW New Link / Reroute | MW NEW LINK 3695A-1037A WITH HUAWEI_18G_1+0_1.2M/1.2M_DP_112MHZ_256QAM_778MBPS_XMC3E_SUB_B_4.2KM IMPACTED: 3695A DISMANTLE EXISTING LINK 3695A-2270A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK 3695A-2270A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK 3695A-2270A | XMC3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202508250724-Magicell | Magicell | SQ202510010659-Magicell // SQ202510010661-Magicell // SQ202511240180-Magicell // SQ202511260101-Magicell | 2025-10-10 | 2025-10-09 | Completed | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092649 |  | 2025-10-01 | 2025-11-21 | Completed | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-11-21 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-11-21 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-12-15 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-07 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-12-13 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-11-21 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | NG HONG JIE7018000036 | Logistic Team | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509041074-GCI | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
4508A_LOS | Eng Hock Hin Furni RDC | DU00004395060 | Northern | Perak | 4.617141 | 101.108905 | [7 empty] | 03. TSS Only | 15/11: NE PTN ready. Not proceed with MW solution. TSS only done | TSS |  | 23G_2+0_112M NE_4508A. 23G_DP_0.6m(MAC)+OMT x1. XMC_3E-2+0 , Sub_A&B_Hi x2. FE_4340B 23G_DP_0.6m(MAC)+OMT x1. XMC_3E-2+0 , Sub_A&B_Lo x2. RTN910A x1. | MW New Link / Reroute | Existing link 18G_2+0_56M Link reroute to new FE 4340B with config 23G_2+0_112M due to LOS Block. Site Impacted: 4340B NE_4508A. 1.Install a new 23G_DP_0.6m(MAC)+OMT. 2.Install XMC_3E-2+0 , Sub_A&B_Hi 3.Reuse existing 4340B_RTN01. 4.Install 3_ISM8-2+0 into existing RTN4340B_RTN01 5.Enable EPLA & service cross connect. 6.Traffci migrate to new FE 4340B. 7.Decom existing Ant & ODU (4508A-4546A) FE_4340B 1.Install a new 23G_DP_0.6m(MAC)+OMT. 2.Install XMC_3E-2+0 , Sub_A&B_Lo. 3.Install new RTN910A, 7_ISM8-2+0. 4.Enable EPLA & service cross connect. 5.Create new In band DCN. 6.Decom existing Ant & ODU (4546A-4508A) | [7 empty] | CCSMY |  | CCSMY | No PR required-Work at TSS only |  |  | Ongoing | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24111159 |  | 2024-11-12 |  | Ongoing | 2024-11-11 | 2024-11-12 | 2024-11-11 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202507080524-GCI | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | CHEONG/SENG/WAH/7018000306
3174B2_LOS | pBTS Precint 11 | DU00004416920 | Central | Selangor | 2.963824 | 101.662050 |  |  |  |  | TSS Only | No available LOS | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. CD plan to relocate RAN to near by site or install LL | TSS |  | IF Cable | MW Swap | ----TSS only due to no other clear LOS---- The ant at FE 2057A needs to be raise in order to ensure a clear line of sight to the NE site. | [7 empty] | Magicell | SQ202501140157-Magicell | Magicell | No PR required-Work at TSS only | 2025-12-23 | 2025-12-16 | Completed | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2025-01-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2025-01-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-11-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
3310C-3293A_1 | Desa Alam Seksyen U12 Shah Alam | DU00004416921 | Central | Selangor | 3.079016 | 101.482358 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_3293A New 18G_0.6M(MAC)+OMT x1. Re-use existing RTN910A(RTN01) x1. New XMC_3E, Sub A_Hi x1. FE_3310C New 18G_0.6M(MAC)+OMT x1. Re-use existing RTN910A(RTN01) x1. New XMC_3E, Sub A_Lo x1. | MW Swap | Existing HW MW Link 23G_1+0_112M_128QAM_676M. Swap existing HW MW Link with new HW MW Link 18G_2+0_112M_256QAM_EPLA. Later, decom ONLY 23G ODU and 23G Antenna for existing HW MW Link 23G_1+0_112M_128QAM_676M at both NE(3293A) & FE(3310C) and do not decom existing RTN910A. Site Impacted : 3293A. NE_3293A 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A_Hi x1. Configure it. 4.Migrate traffic to new link new HW MW Link 18G_2+0_112M_256QAM_EPLA. Configure it. 5.Later, decom ONLY 23G ODU and 23G Antenna for existing HW MW Link 23G_1+0_112M_128QAM_676M at both NE(3293A) & FE(3310C) and do not decom existing RTN910A(RTN01). FE_3310C 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A_Hi x1. Configure it. 4.Re-use existing vlan services and existing port at IBeam. 5.Migrate traffic to new link new HW MW Link 18G_2+0_112M_256QAM_EPLA. Configure it. 6.Later, decom ONLY 23G ODU and 23G Antenna for existing HW MW Link 23G_1+0_112M_128QAM_676M at both NE(3293A) & FE(3310C) and do not decom existing RTN910A(RTN01). | Existing HW MW Link 23G_1+0_112M_128QAM_676M. Swap existing HW MW Link with new HW MW Link 18G_2+0_112M_256QAM_EPLA. Later, decom ONLY 23G ODU and 23G Antenna for existing HW MW Link 23G_1+0_112M_128QAM_676M at both NE(3293A) & FE(3310C) and do not decom existing RTN910A. Site Impacted : 3293A. NE_3293A 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A_Hi x1. Configure it. 4.Migrate traffic to new link new HW MW Link 18G_2+0_112M_256QAM_EPLA. Configure it. 5.Later, decom ONLY 23G ODU and 23G Antenna for existing HW MW Link 23G_1+0_112M_128QAM_676M at both NE(3293A) & FE(3310C) and do not decom existing RTN910A(RTN01). | Existing HW MW Link 23G_1+0_112M_128QAM_676M. Swap existing HW MW Link with new HW MW Link 18G_2+0_112M_256QAM_EPLA. Later, decom ONLY 23G ODU and 23G Antenna for existing HW MW Link 23G_1+0_112M_128QAM_676M at both NE(3293A) & FE(3310C) and do not decom existing RTN910A. Site Impacted : 3293A. FE_3310C 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A_Hi x1. Configure it. 4.Re-use existing vlan services and existing port at IBeam. 5.Migrate traffic to new link new HW MW Link 18G_2+0_112M_256QAM_EPLA. Configure it. 6.Later, decom ONLY 23G ODU and 23G Antenna for existing HW MW Link 23G_1+0_112M_128QAM_676M at both NE(3293A) & FE(3310C) and do not decom existing RTN910A(RTN01). | XMC_3E | MAC | 18G | 18G_0.6M(MAC)+OMT x1. | 18G_0.6M(MAC)+OMT x1. | GCI | SQ202506190612-GCI | GCI | SQ202506190647-GCI // SQ202506190656-GCI | 2025-08-13 | 2025-08-07 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-29 | 2025-08-07 | 2025-07-29 | 2025-07-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070401 |  | 2025-07-06 | 2025-07-07 | Completed | 2025-07-05 | 2025-07-06 | 2025-07-05 | 2025-07-07 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-15 | 2025-07-22 | 2025-07-14 | 2025-07-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-15 | 2025-07-22 | 2025-07-14 | 2025-07-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | SITI HAFIZAH BINTI NOH6237001145 |  |  | 2025-07-15 | 2025-07-22 | 2025-07-14 | 2025-07-19 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-07-15 | 2025-07-22 | 2025-07-14 | 2025-07-15 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202505280699-GTSB
1663C-1337B | Apartment Suria | DU00004416922 | Central | Selangor | 3.192266 | 101.584740 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 21/1/2025 : Cutover done 13/1/2025 : NIP GLOBAL LOGISTICS - 24M Lampole - NE site 1663C Apartment Suria, EDGEPOINT INFRA - 60M 4 Legged Tower - FE site 1337B Sungai Buloh R&R(AsiaSpace) | TSS+AA+TI | L1+ATP+PAC | FE: 1) 1xRTN910A 2) SFP 1km and patch cords | MW Hardware Upgrade | To perform reengineering at FE site 1337B to solve GE port congestion at 1337B RTN-02 GE5 Impact site: 1663C Tx route: 1663C-1337B NE (1663C): 1) Remain existing FE (1337B/B00775): 1) Install new RTN910A (ops team to assign RTN number) 2) Transfer IF cable from RTN02 7-ISM8-2 to new RTN 7-ISM8-1 3) Patch new RTN GE5 (optical) to new xC PTN port (ops to assign) 4) Transfer 1663C traffic to new port 5) Reconfigure DCN | [7 empty] | GTSB | SQ202501210409-GTSB | GTSB | SQ202412310378-GTSB // SQ202504260131-GTSB | 2025-03-06 | 2025-03-03 | Completed | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-02-27 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-20 | 2025-03-06 | 2025-02-20 | 2025-02-20 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-03 | 2025-03-04 | 2025-03-03 | 2025-03-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24122307 |  | 2024-12-24 | 2025-02-27 | Completed | 2024-12-23 | 2024-12-24 | 2025-02-27 | 2025-02-27 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-02-27 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-02-27 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-03-10 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2025-10-01: 2025-01-20; 2025-10-01: 2025-01-31; 2025-10-01: 2025-01-20; 2025-11-21: 2025-01-21 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
4330D-4990B | Ulu Leggong | DU00004416923 | Northern | Kedah | 5.801977 | 100.915960 | W49-52 | DEC 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X RTN 910A 1X ISM8 CARD 2X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Swap | SWAP MW LINK 4330D-4990B WITH HUAWEI_18G_1+0_56MHZ_0.6M_2.39KM EXISTING MW CFG: HW_15GHZ_1+0_28MHZ IMPACTED SITES: 4656C NE (4330D): 1. INSTALL NEW ISM8 CARD AT RTN01(9-12042) SLOT 3 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 56MHZ 5. DISMANTLE EXISTING LINK EXCEPT IDU FE (4990B): 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 56MHZ 5. CASCADE NEW RTN 910A TO RTN02(9-41725) 5. DISMANTLE EXISTING LINK | [7 empty] | CCSMY | SQ202504210258-CCS | CCSMY | SQ202503200258-CCS // SQ202503200262-CCS // SQ202504260175-CCS | 2025-12-03 | 2025-11-26 | Completed | 2025-03-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-12-03 | 2025-11-26 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25030663 |  | 2025-03-07 | 2025-03-16 | Completed | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-11 | 2025-03-31 | 2025-03-16 | 2025-03-16 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2025-03-11 | 2025-03-31 | 2025-03-16 | 2025-03-16 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-13 | 2025-03-11 | 2025-03-31 | 2025-05-13 | 2025-05-13 | MUHAMMAD//MUZAMMAL/7021000054 | 2025-03-11 | 2025-03-31 | 2025-03-12 | 2025-03-12 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-20 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB
3364C_LOS | Kuaters Guru Seksyen 24 Shah Alam (REL) | DU00006119073 | Central | Selangor | 3.041528 | 101.517578 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+PAC | 18G_2+0_112M. NE_3364C. 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. FE_1795A. 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW New Link / Reroute | Reroute the existing link 18G_2+0_112M due to LOS block by preposed new FE 1795A via TSS Survey. New Link Config with 18G_2+0_112M. Site Impacted : 3364C , 1758H. NE_3364C. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Lo. 4.Create cross connect and EPLA. 5.Enable GE1 , ETH patching BBU_3364C. 6.Enable GE2 , ETH patching to existing NLOS_RTN905 , carry 1758H. 7.All traffic migrate to new link and new FE routing. 8.Decom existing MW link. FE_1795A. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Hi. 4.Create cross connect and EPLA. 5.Create new Inband DCN. 6.Enable GE1 , ETH patching to existing 1795A_RTN01_GE5 (ID : 24961). 7.Traffic migrate to new link and new FE routing. 8.Decom existing MW link. | Reroute the existing link 18G_2+0_112M due to LOS block by preposed new FE 1795A via TSS Survey. New Link Config with 18G_2+0_112M. Site Impacted : 3364C , 1758H. NE_3364C. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Lo. 4.Create cross connect and EPLA. 5.Enable GE1 , ETH patching BBU_3364C. 6.Enable GE2 , ETH patching to existing NLOS_RTN905 , carry 1758H. 7.All traffic migrate to new link and new FE routing. 8.Decom existing MW link. | Reroute the existing link 18G_2+0_112M due to LOS block by preposed new FE 1795A via TSS Survey. New Link Config with 18G_2+0_112M. Site Impacted : 3364C , 1758H. FE_1795A. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Hi. 4.Create cross connect and EPLA. 5.Create new Inband DCN. 6.Enable GE1 , ETH patching to existing 1795A_RTN01_GE5 (ID : 24961). 7.Traffic migrate to new link and new FE routing. 8.Decom existing MW link. | XMC_5D | MDD | 18G | 0.6 | 0.6 | GCI | SQ202509260740-GCI | MTK | SQ202510240588-MTK // SQ202510240598-MTK // SQ202511210031-MTK | 2025-11-26 | 2025-11-25 | Completed | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-29 | 2025-10-28 | 2025-10-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102163 |  | 2025-10-23 | 2025-10-25 | Completed | 2025-10-22 | 2025-10-23 | 2025-10-21 | 2025-10-25 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-05 | 2025-11-21 | 2025-11-06 | 2025-11-06 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-11-05 | 2025-11-21 | 2025-12-20 | 2025-12-20 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | AKMAL//BIN RAZALI/6794000078 |  | 2025-11-10 | 2025-11-05 | 2025-11-21 | 2025-12-26 | 2025-12-26 | RIDHUAN//BIN MANSOR/8225000011 | 2025-10-01: 2025-11-05; 2025-10-01: 2025-11-21; 2025-10-01: 2025-11-06; 2025-11-21: 2025-11-06 |  |  | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260791-GCI | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | CHEONG/SENG/WAH/7018000306
9829B_AD | Rh. Sagring | DU00006235138 | Sarawak | Sarawak | 2.216700 | 111.994000 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_128QAM_676M. Site Impacted : 9829B. NE_9829B 1.Existing ODU XMC-3 may remotely upgrade to BW 110MHz(128QAM). FE_9357A 1.Existing ODU XMC-3 may remotely upgrade to BW 110MHz(128QAM). | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_128QAM_676M. Site Impacted : 9829B. NE_9829B 1.Existing ODU XMC-3 may remotely upgrade to BW 110MHz(128QAM). | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_128QAM_676M. Site Impacted : 9829B. FE_9357A 1.Existing ODU XMC-3 may remotely upgrade to BW 110MHz(128QAM). | XMC-3 | MAC | 18G | 18G_SP_0.6M(MAC)x1. | 18G_SP_0.6M(MAC)x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-12 | [15 empty] | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202510300425-GTSB
1331H_LOS | 99 Speedmart BDR COUNTRY HOMES 1 | DU00006368154 | Central | Selangor | 3.325166 | 101.525066 | [7 empty] | 06. Other Issue | [13 empty] | YPTT | SQ202603180467-YPTT | YPTT |  |  |  | Ongoing | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-04 | 2026-05-11 | 2026-05-04 | 2026-05-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112644 |  | 2025-12-27 |  | Ongoing | 2025-11-27 | 2025-12-27 | 2025-11-27 |  | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202511280921-GTSB
Q01423_AD | ​Q116A_Q01423OD_MN_UMABALOILIKO | DU00006343213 | Sarawak | Sarawak | 3.072900 | 113.961500 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | FE_9347B/Q00742 New CAT6 cable with suitable length x1. | MW IDU Patching | ****IMPORTANT NOTE: 1.9347B LL UPGRADE EXPECTED TO BE COMPLETE ON 23RD OF DECEMBER, 2025.**** Perform MW IDU Patching at FE 9347B/Q00742. Site Impacted : Q01423. FE_9347B/Q00742 1.Disconnect/remove existing xC Cisco/PTN Q00742 from port 8-EM6-2 of existing xC RTN910AF(NEID 82-13644) of HW MW Link_ID SW03644 Q01423-Q00742 15G_4+0_28MHZ_2048QAM_EPLA_1092M. 2.Enable port 8-EM6-4 of existing xD RTN910AF(RTN01, NEID 9-35501). 3.Perform new patching port 8-EM6-2 of existing RTN910AF(NEID 82-13644) and port 8-EM6-4 of existing xD RTN910AF(RTN01, NEID 9-35501). 4.Request new xD Vlan DCN & Vlan Services for Q01423 from ZTE IPRAN team. 5.Migrate Q01423 traffic to existing IBeam port at CP(9106A) in which similar to traffics such as 9347B. |  | ****IMPORTANT NOTE: 1.9347B LL UPGRADE EXPECTED TO BE COMPLETE ON 23RD OF DECEMBER, 2025.**** Perform MW IDU Patching at FE 9347B/Q00742. Site Impacted : Q01423. FE_9347B/Q00742 1.Disconnect/remove existing xC Cisco/PTN Q00742 from port 8-EM6-2 of existing xC RTN910AF(NEID 82-13644) of HW MW Link_ID SW03644 Q01423-Q00742 15G_4+0_28MHZ_2048QAM_EPLA_1092M. 2.Enable port 8-EM6-4 of existing xD RTN910AF(RTN01, NEID 9-35501). 3.Perform new patching port 8-EM6-2 of existing RTN910AF(NEID 82-13644) and port 8-EM6-4 of existing xD RTN910AF(RTN01, NEID 9-35501). 4.Request new xD Vlan DCN & Vlan Services for Q01423 from ZTE IPRAN team. 5.Migrate Q01423 traffic to existing IBeam port at CP(9106A) in which similar to traffics such as 9347B. | [5 empty] | Trintel | SQ202601210184-Trintel | Trintel | SQ202601210180-Trintel |  |  | Ongoing | 2026-01-27 | 2026-01-31 | 2026-01-27 | 2026-01-27 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26011506 |  | 2026-01-16 | 2026-01-28 | Completed | 2026-01-15 | 2026-01-16 | 2026-01-15 | 2026-01-28 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-03-04 | AINA MARINI//ATON/6794000115 | Trintel TI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-03-04 | AINA MARINI//ATON/6794000115 | Trintel TI | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-27 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-03-02 | AINA MARINI//ATON/6794000115 | 2025-10-01: 2026-01-26; 2025-10-01: 2026-01-26; 2025-10-01: 2026-01-26; 2025-11-21: 2026-01-27 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202511280943-GTSB
Q00780_AD | ​Q116A_Q00780OD_SGASAP2 | DU00006343214 | Sarawak | Sarawak | 3.084300 | 113.919300 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_110M_512QAM_EPLA NE_Q00780 New 18G_1.2M(MS) x1. Re-use existing RTN910AF(NEID 82-23613). New ISM8 x1. New XMC_3E, Sub A_Hi x2. FE_9347B New 18G_1.2M(MS) x1. Re-use existing RTN910AF(NEID 9-35501). New ISM8 x1. New XMC_3E, Sub A_Lo x2. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(ENT SOP SEPAKAU MILL) & DO NOT PROCEED REROUTING/DIVERTING IF CRQ NOT OBTAIN YET.**** Reroute to new HW MW Link Q00780-9347B, 18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : Q00780, Q01424, Q01808/9124K & ENT SOP SEPAKAU MILL. NE_Q00780 1.Install new 18G_1.2M(MS) x1. 2.Re-use existing RTN910AF(NEID 82-23613). Insert new ISM8 x1 into slot 04. 3.Install new XMC_3E, Sub A_Hi x2. Configure it. 4.Disconnect port of existing RTN910AF(NEID 82-23613) that connect to existing PTN/Cisco Router. Disable the port. 5.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 6.Migrate traffic Q00780, Q01424, Q01808/9124K & ENT SOP SEPAKAU MILL via new HW MW Link Q00780-9347B, 18G_2+0_110MHZ_512QAM_EPLA. FE_9347B 1.Install new 18G_1.2M(MS) x1. 2.Re-use existing RTN910AF(NEID 9-35501). Insert new ISM8 x1 into slot 03. 3.Install new XMC_3E, Sub A_Lo x2. Configure it. 4.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Migrate traffic Q00780, Q01424, Q01808/9124K & ENT SOP SEPAKAU MILL via existing port of IBeam at CP(9106A) in which port similar to site 9347B. | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(ENT SOP SEPAKAU MILL) & DO NOT PROCEED REROUTING/DIVERTING IF CRQ NOT OBTAIN YET.**** Reroute to new HW MW Link Q00780-9347B, 18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : Q00780, Q01424, Q01808/9124K & ENT SOP SEPAKAU MILL. NE_Q00780 1.Install new 18G_1.2M(MS) x1. 2.Re-use existing RTN910AF(NEID 82-23613). Insert new ISM8 x1 into slot 04. 3.Install new XMC_3E, Sub A_Hi x2. Configure it. 4.Disconnect port of existing RTN910AF(NEID 82-23613) that connect to existing PTN/Cisco Router. Disable the port. 5.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 6.Migrate traffic Q00780, Q01424, Q01808/9124K & ENT SOP SEPAKAU MILL via new HW MW Link Q00780-9347B, 18G_2+0_110MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(ENT SOP SEPAKAU MILL) & DO NOT PROCEED REROUTING/DIVERTING IF CRQ NOT OBTAIN YET.**** Reroute to new HW MW Link Q00780-9347B, 18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : Q00780, Q01424, Q01808/9124K & ENT SOP SEPAKAU MILL. FE_9347B 1.Install new 18G_1.2M(MS) x1. 2.Re-use existing RTN910AF(NEID 9-35501). Insert new ISM8 x1 into slot 03. 3.Install new XMC_3E, Sub A_Lo x2. Configure it. 4.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Migrate traffic Q00780, Q01424, Q01808/9124K & ENT SOP SEPAKAU MILL via existing port of IBeam at CP(9106A) in which port similar to site 9347B. | XMC_3E | MS | 18G | 18G_1.2M(MS) x1. | 18G_1.2M(MS) x1. | Trintel | SQ202601300958-Trintel | Redtone | SQ202603060643-Redtone // SQ202603060646-Redtone | 2026-03-20 | 2026-03-17 | Completed | 2026-01-27 | 2026-01-31 | 2026-01-27 | 2026-01-27 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-13 | 2026-02-20 | 2026-02-13 | 2026-02-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-03 | 2026-03-10 | 2026-03-03 | 2026-03-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-20 | 2026-03-13 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022122 |  | 2026-02-22 |  | Ongoing | 2026-02-21 | 2026-02-22 | 2026-02-21 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-02-24 | 2026-03-10 |  |  |  | REDTONE TI | [6 empty] | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-04 | 2026-02-24 | 2026-03-10 |  |  | ANDREW BIN JUHAN6000068232 | 2025-10-01: 2026-02-24; 2025-10-01: 2026-03-10; 2025-10-01: 2026-02-26; 2025-11-21: 2026-02-26 | [7 empty] | GTSB | SQ202511280943-GTSB
7310B-7677B | Kg Pisang | DU00004999268 | Sabah | Sabah | 4.280240 | 117.878290 |  |  |  |  | RFS | DONE | ZTE | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 1 x RTN910A 1 x ISM8 card 10G SFP and patch cord | MW Hardware Upgrade | 7677B RTN02-RTN01 GE port congestion To swap RTN01 from RTN950A to RTN910A and use 10G port Tx route: 7677B-LL-7205A Impact sites: 7010C,7310B NE (7310B): 1) Remain existing FE (7677B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install ISM8 card at new RTN slot 3 3) Transfer link from RTN01 1-ISM8-1 to new RTN 7-ISM8-1 4) Transfer link from RTN01 3-ISM8-1 to new RTN 3-ISM8-1 5) Patch new RTN GE4 to RTN02 GE4 (10G port) 6) Decom RTN01 (RTN950A) | NE (7310B): 1) Remain existing | FE (7677B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install ISM8 card at new RTN slot 3 3) Transfer link from RTN01 1-ISM8-1 to new RTN 7-ISM8-1 4) Transfer link from RTN01 3-ISM8-1 to new RTN 3-ISM8-1 5) Patch new RTN GE4 to RTN02 GE4 (10G port) 6) Decom RTN01 (RTN950A) | [5 empty] | NR services | SQ202502120362-NR Services | NR services | SQ202502270741-NR Services // SQ202504260199-NR Services | 2025-06-27 | 2025-06-25 | Completed | 2025-02-11 | 2025-02-11 | 2025-02-11 | 2025-02-11 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-10 | 2025-02-14 | 2025-02-10 | 2025-02-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-10 | 2025-02-14 | 2025-02-10 | 2025-02-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021401 |  | 2025-02-15 | 2025-02-15 | Completed | 2025-02-14 | 2025-02-15 | 2025-02-14 | 2025-02-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-21 | 2025-03-15 | 2025-02-21 | 2025-02-22 | RAMLAN//BIN ROSLAN/6000002578 | NR Service TI | 2025-02-21 | 2025-03-15 | 2025-02-21 | 2025-02-22 | RAMLAN//BIN ROSLAN/6000002578 | NR Service TI | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-02-23 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-23 | 2025-02-21 | 2025-03-15 | 2025-02-21 | 2025-03-03 | RAMLAN//BIN ROSLAN/6000002578 | 2025-02-21 | 2025-03-15 | 2025-02-21 | 2025-02-22 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | tseping//wang/6819000006 | Logistic Team | 2025-04-23 | 2025-05-23 | 2025-04-23 | 2025-04-23 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
Q01081_HU | Q133A_Q01081OD_LDGKURAYA | DU00006813230 | Sarawak | Sarawak | 2.872840 | 112.451594 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01427_HU | Q123A_Q01427OD_MN_PELAJAU | DU00006813231 | Sarawak | Sarawak | 1.968010 | 112.921910 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
C01482_HU | JEN1_0521Va_C01482_KuatersKerajaan Sungai Burung | DU00006813232 | Northern | Pahang | 4.493829 | 101.395113 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7012L_HU | KampungBulu Silou | DU00006813233 | Sabah | Sabah | 5.351369 | 116.134000 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
C01483_HU | JEN1_0522V_C01483_FlatLembah Jasar | DU00006813234 | Northern | Pahang | 4.473328 | 101.371159 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3068A_HU | CYBERJAYA ELITEP3.8 (REL) | DU00006813235 | Central | Selangor | 2.938410 | 101.627100 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9181X_HU_1 | Q118B_Q00469OD_BT39BTU | DU00006813236 | Sarawak | Sarawak | 3.406580 | 113.493971 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7461A_HU_2 | NabawanRT (REL) | DU00006813237 | Sabah | Sabah | 5.041634 | 116.425916 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7757B_HU | Tongkabira | DU00006813238 | Sabah | Sabah | 5.490600 | 116.992600 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7085L_HU | TamanSulaiman Jaya | DU00006813239 | Sabah | Sabah | 6.214620 | 116.216135 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4782D_HU_1 | KampungPadang Kunyit | DU00006813240 | Northern | Kedah | 6.178331 | 100.437750 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2476A_HU_3 | SgSerai (Maxis) | DU00006813241 | Central | Selangor | 3.284510 | 101.549880 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1299B-1737A | Jln Temerloh2 | DU00004306481 | Central | Kuala Lumpur | 3.171363 | 101.709718 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 24/10: D1: Cutover done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 1299B (RTN02)-1737A (RTN06) 2+0 56MHz To upgrade to 2+0 112MHz Impacted sites: 1313A,W01588,3714A Tx route: 1299B-1737A NE (1299B): 1) Change BW and Tx power to new 112MHz FE (1737A): 1) Change BW and Tx power to new 112MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
7323C-7958A | KGPOPOK | DU00004306482 | Sabah | Sabah | 6.519114 | 116.795600 | [7 empty] | 00. Integrated/RFS Done | 25/10: Cutover done. RSL different 5dbm 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 7323C-7958A-01_ZBAU To upgrade to 1+0 112MHz Impacted sites: 7323C Tx route: 7323C-7958A NE (7323C): 1) Change BW, channel and Tx power to new 112MHz FE (7958A): 1) Change BW, channel and Tx power to new 112MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-11 | 2024-11-11 | 2024-11-11 | 2024-11-11 | SHUJAAT//ALI/6800000124 | [17 empty] | 2024-11-30 | 2024-12-30 | 2024-11-30 | 2024-11-30 | ASTI//GANIS PUTRIANI/6237001358
2362B-1851B | Daching Ilir | DU00004306483 | Central | Selangor | 2.887050 | 101.896670 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 24/10: D1: Cutover done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 2362B-1851B-03-HNIC_Project 1+0 link using MODU To enable CA and create 2+0 CA link Impacted sites: 2362B,2361B Tx route: 2362B-1851B NE (2362B): 1) Set IF conflux and enable CA 2) Configure 2nd link 3) Create EPLA 2+0 CA FE (1851B): 1) Set IF conflux and enable CA 2) Configure 2nd link 3) Create EPLA 2+0 CA | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
S01647-7289A | S101A_S01647OD_KGKITANGANSUGUD | DU00004306484 | Sabah | Sabah | 5.856406 | 116.101079 | [7 empty] | 00. Integrated/RFS Done | 24/10: D1: Cutover done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 7145K-7289A_01_ZNIC To upgrade to 112MHz Impacted sites: S01647 Tx route: S01647/S01647-7289A-LL-7000A NE (S01647): 1) Change BW and channel to new 112MHz FE (7289A): 1) Change BW and channel to new 112MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-11 | 2024-11-11 | 2024-11-11 | 2024-11-11 | SHUJAAT//ALI/6800000124 | [17 empty] | 2024-11-30 | 2024-12-30 | 2024-11-30 | 2024-11-30 | ASTI//GANIS PUTRIANI/6237001358
2321A_LOS | Sek 3 BBB | DU00004322641 | Central | Selangor | 2.946754 | 101.780623 |  |  |  |  | Cancel / Drop | Done under DU 2321A TX NIC | ZTE | 00. Site Out/Drop | 18/10: Done by ZTE under TX NIC 2321A (Swap Activity) |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3469C_LOS | pBTS Taman Indah Jaya | DU00004322642 | Central | Selangor | 3.073260 | 101.630591 |  |  |  |  | Cancel / Drop | Done under TX NIC 3469C_Additional | ZTE | 00. Site Out/Drop | Cancel / drop. Solution done under TX NIC 3469C_Additional |  |  | 18G_2+0_112M NE_3469C 18G_DP_0.6m(MDD) x1. RTN910A x1. XMC_5D-2+0 , Sub_A_Hi x1. FE_1196A 18G_DP_0.6m(MDD) x1. RTN910A x1. XMC_5D-2+0 , Sub A_Lo x1. | Cancel / Drop | Link reroute to new FE 1196A with 18G_2+0_112M due to LOS block. NE_3469C 1.Install 18G_DP_0.6m(MDD). 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_5D-2+0 , Sub_A_Hi. 4.Create EPLA and service cross connect. 5.Migrate traffic to new link. 6.Decom existing MW link. FE_1196A 1.Install 18G_DP_0.6m(MDD). 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_5D-2+0 , Sub A_Lo. 4.Create new In Band DCN. 5.Create EPLA and service cross connect. 6.Migrate traffic to new link. 7.Decom existing MW link. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300116-GTSB
P00007-4291C | P032A_P00007OD_BTBATUKAWAN | DU00004330968 | Northern | Penang | 5.269259 | 100.415540 | [7 empty] | 00. Integrated/RFS Done | 16/11: MW Remote upgrade done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Upgrade existing link from 18GHz 1+0 56MHz to 112MHz Impacted site: P00007 NE (P00007): 1) Upgrade link to 112MHz FE (4291C): 1) Upgrade link to 112MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
4164D-4597A | Gereja Methodist Tamil Teluk Intan | DU00004330969 | Northern | Perak | 4.022310 | 101.021147 | [7 empty] | 00. Integrated/RFS Done | 27/11: Cutover done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Upgrade existing link from 18GHz 1+0 28MHz to 56MHz Impacted site: 4164D NE (4164D RTN01): 1) Upgrade link to 56MHz FE (4597A RTN01): 1) Upgrade link to 56MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
1395A_AD | Semaipadu | DU00005881339 | Central | Selangor | 3.105020 | 101.600082 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | 24Jul-Site award to Huawei for the reroute. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2395A_AD | Jln SS 2_4a | DU00005881340 | Central | Selangor | 3.111503 | 101.611310 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | 24Jul-Site award to Huawei for the reroute. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4329H_LOS | 99 Speedmart PG Tmn Seri Juru | DU00006224982 | Northern | Penang | 5.311370 | 100.442140 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+PAC | NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | NLOS Link reroute to new FE 4241 due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 4329H. NE_4329H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (4329H-NLOS-4150C). FE_4241A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new Inband DCN. 5.Traffic migrate to new route FE and with new NLOS radio. 6.ETH cable patching to CP Fiber port. 7.Decom existing NLOS Radio (4150C-NLOS-4329H). | NLOS Link reroute to new FE 4241 due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 4329H. NE_4329H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (4329H-NLOS-4150C). | NLOS Link reroute to new FE 4241 due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 4329H. FE_4241A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new Inband DCN. 5.Traffic migrate to new route FE and with new NLOS radio. 6.ETH cable patching to CP Fiber port. 7.Decom existing NLOS Radio (4150C-NLOS-4329H). | [5 empty] | NWAVE | SQ202510300101-N-Wave | NWAVE | SQ202601130210-N-Wave // SQ202601130214-N-Wave | 2026-03-14 | 2026-03-13 | Completed | 2025-11-13 | 2025-12-13 | 2025-11-13 | 2025-11-13 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251121AQ |  | 2025-12-20 | 2025-12-01 | Completed | 2025-11-21 | 2025-12-20 | 2025-11-28 | 2025-12-01 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-10 | 2026-01-10 | 2025-12-10 | 2025-12-10 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-12-10 | 2026-01-10 | 2025-12-10 | 2026-01-02 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-14 | 2025-12-10 | 2026-01-10 | 2025-12-10 | 2026-01-27 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | 2025-12-10 | 2026-01-10 | 2025-12-10 | 2025-12-31 | 2026-01-18 | 2026-01-18 | 2026-01-18 | 2026-01-18 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510300396-GCI | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | CHEONG/SENG/WAH/7018000306
Q01548_AD_1 | Q126A_Q01548OD_MN_LUBAITENGAH | DU00006231398 | Sarawak | Sarawak | 4.633570 | 114.926390 | [9 empty] | TSS+TI |  | New CAT6 cable with suitable length x1. | BBU Patching | Perform re-engineering by doing POI Layer 2 for xC site **Important Note: 1. Re-engineering for xC site(Ericsson BBU) in which patching and divert to xD Host and perform POI Layer 2 to xC Host.** Site Impacted: Q01548. NE_Q01548 1.Enable port 8-EM6-1 for existing RTN910AF(RTN01) of existing HW MW Link Q01548-9252Z. 2.Patching Ericsson BBU/RAN(Q01548) to port 8-EM6-1 for existing RTN910AF(RTN01) of existing HW MW Link Q01548-9252Z. 3.ZTE IPRAN Team need to perform POI in between xD Host(CP 9284A) and suitable xC Host via internet cloud. | Perform re-engineering by doing POI Layer 2 for xC site **Important Note: 1. Re-engineering for xC site(Ericsson BBU) in which patching and divert to xD Host and perform POI Layer 2 to xC Host.** Site Impacted: Q01548. NE_Q01548 1.Enable port 8-EM6-1 for existing RTN910AF(RTN01) of existing HW MW Link Q01548-9252Z. 2.Patching Ericsson BBU/RAN(Q01548) to port 8-EM6-1 for existing RTN910AF(RTN01) of existing HW MW Link Q01548-9252Z. 3.ZTE IPRAN Team need to perform POI in between xD Host(CP 9284A) and suitable xC Host via internet cloud. | [8 empty] | YPTT | SQ202511190861-YPTT |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25110142 |  | 2025-11-02 | 2025-11-03 | Completed | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-03 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | [7 empty] | 2025-11-05 | 2025-11-06 | 2025-11-05 | 2026-03-16 | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | 2025-10-01: 2025-11-05; 2025-10-01: 2025-11-06; 2025-10-01: 2025-11-05; 2025-11-21: 2025-11-05 | [7 empty] | GTSB | SQ202510300425-GTSB
7443A_HU_1 | Nabawan | DU00006281174 | Sabah | Sabah | 5.042950 | 116.429456 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_110M_256QAM_EPLA(LINK 1) NE_7443A New 18G_1.2M(MDD) x1. New RTN910AF(RTN04) x1. New XMC_5D, Sub B_Lo x1. FE_7476A New 18G_1.2M(MDD) x1. Re-use existing RTN950A(RTN01). New ISM8 x1. New XMC_5D, Sub B_Hi x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILD SITES. 3.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Build new HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1) Site Impacted : 2788B18, 7339C, 7443A, 7476A, 7461A, 7063C & 7198R(Due to SW Version Upgrade from R21 to R23). NE_7443A 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04). 3.Install new XMC_5D, Sub B_Lo x1. Build new HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1). 4.Proceed to perform DU 7461A_HU_1. 5.Once DU 7461A_HU_1 completed. DU 7443A_HU_1 in which HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1) will backhauling traffics 7461A & 7063C. FE_7476A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN950A(RTN01-NEID 19182). Need to upgrade SW Version from R21 to R23. 3.Impacted all traffic(approx 10~15 minutes) under RTN950A(RTN01-NEID 19182). 4.Insert new ISM8 x1 into slot 01. 5.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1). 6.Proceed to perform DU 7461A_HU_1. 7.Once DU 7461A_HU_1 completed. DU 7443A_HU_1 in which HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1) will backhauling traffics 7461A & 7063C. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILDS. 3.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Build new HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1). Site Impacted : 2788B18, 7339C, 7443A, 7476A, 7461A, 7063C & 7198R(Due to SW Version Upgrade from R21 to R23). NE_7443A 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04). 3.Install new XMC_5D, Sub B_Lo x1. Build new HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1). 4.Proceed to perform DU 7461A_HU_1. 5.Once DU 7461A_HU_1 completed. DU 7443A_HU_1 in which HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1) will backhauling traffics 7461A & 7063C. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILDS. 3.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Build new HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1). Site Impacted : 2788B18, 7339C, 7443A, 7476A, 7461A, 7063C & 7198R(Due to SW Version Upgrade from R21 to R23). FE_7476A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN950A(RTN01-NEID 19182). Need to upgrade SW Version from R21 to R23. 3.Impacted all traffic(approx 10~15 minutes) under RTN950A(RTN01-NEID 19182). 4.Insert new ISM8 x1 into slot 01. 5.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1). 6.Proceed to perform DU 7461A_HU_1. 7.Once DU 7461A_HU_1 completed. DU 7443A_HU_1 in which HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1) will backhauling traffics 7461A & 7063C. | XMC-5D | MDD | 18G | 18G_1.2M(MDD) x1. | 18G_1.2M(MDD) x1. | NR services | SQ202602250627-NR Services | NR services | SQ202602130272-NR Services // SQ202602130278-NR Services |  |  | Ongoing | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26020319 |  | 2026-02-04 | 2026-02-11 | Completed | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-11 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-03-10 | 2026-02-10 | 2026-02-11 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-10 | 2026-03-10 | 2026-02-10 | 2026-02-11 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-12 | 2026-02-10 | 2026-03-10 | 2026-02-10 | 2026-02-23 | RALPH O'BRYAN HILARY7167000030 | 2025-10-01: 2026-02-10; 2025-10-01: 2026-03-10; 2025-10-01: 2026-02-10; 2025-11-21: 2026-02-10 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511180736-GTSB
7487B_HU_1 | Kg Gaban | DU00006281175 | Sabah | Sabah | 5.319390 | 118.239430 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M. NE_7487B 13G_DP_1.2M(MDD) x1. XMC_5D , Sub A_Hi x1. FE_7494B 13G_DP_1.2(MDD) x1. XMC_5D , Sub A_Lo x1. | MW Parallel Link | Existing link 13G_4+0_28M_Sub B. Install Parallel link 13G_2+0_28M. Site Impacted : 7733B , 7694E (7657E , 7767E and 7730E RAN yet to integrate). NE_7487B 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 7487B_RTN02 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW link to Decom. FE_7494B 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 7494B_RTN03 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW link to Decom. | Existing link 13G_4+0_28M_Sub B. Install Parallel link 13G_2+0_28M. Site Impacted : 7733B , 7694E (7657E , 7767E and 7730E RAN yet to integrate). NE_7487B 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 7487B_RTN02 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW link to Decom. | Existing link 13G_4+0_28M_Sub B. Install Parallel link 13G_2+0_28M. Site Impacted : 7733B , 7694E (7657E , 7767E and 7730E RAN yet to integrate). FE_7494B 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 7494B_RTN03 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW link to Decom. | XMC_3E | MDD | 13G | 1.2 | 1.2 | Seri Pancar | SQ202602090132-Seri Pancar | GTSB | SQ202603130143-GTSB // SQ202603130149-GTSB |  |  | Ongoing | 2026-02-04 | 2026-02-28 | 2026-02-12 | 2026-02-12 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-05 | 2026-05-06 | 2026-05-05 | 2026-05-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-05 | 2026-05-06 | 2026-05-05 | 2026-05-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030333 |  | 2026-03-04 | 2026-03-05 | Completed | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-05 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-11 | 2026-03-31 | 2026-03-11 | 2026-04-03 | ABDULLAH//BIN NASIB/6000059295 | GTSB TI | 2026-03-11 | 2026-03-31 | 2026-03-11 | 2026-04-03 | ABDULLAH//BIN NASIB/6000059295 | GTSB TI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-13 | 2026-03-11 | 2026-03-31 | 2026-03-11 | 2026-04-20 | ABDULLAH//BIN NASIB/6000059295 | 2025-10-01: 2026-03-11; 2025-10-01: 2026-03-31; 2025-10-01: 2026-03-11; 2025-11-21: 2026-03-29 | [7 empty] | GCI | SQ202512170731-GCI | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | CHEONG/SENG/WAH/7018000306
7512A_HU_3 | Morisem | DU00006281176 | Sabah | Sabah | 5.504748 | 118.395624 | [7 empty] | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
K01107_HU | K009A_K01107OD_Kg_Sungai Khap_Thai | DU00006281177 | Northern | Kedah | 6.054434 | 100.742181 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_55M_512QAM_EPLA NE_4056P/K01107 New 18G_1.2M(MDD) x1. New RTN910AF(RTN02). New XMC_5D Pro, Sub B_Lo x1. New CAT6 cable x1. FE_4020Z/K00628 New 18G_0.6M(MDD) x1. New RTN910AF(RTN02). New XMC_5D Pro, Sub B_Hi x1. New CAT6 cable x1. | MW Swap | Existing HW MW Link 4056P/K01107-4020Z/K00628, 18G_1+0_55MHZ_512QAM. MW Swap to new HW MW Link 4056P/K01107-4020Z/K00628, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link 4056P/K01107-4020Z/K00628, 18G_1+0_55MHZ_512QAM. Site Impacted : 4056P/K01107. NE_4056P/K01107 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Patching existing BBU to port 8-EM6-1 of new RTN910AF(RTN02). 6.May re-use existing xC Vlan DCN and Vlan Services. 7.Migrate traffic 4056P/K01107 via new HW MW Link 4056P/K01107-4020Z/K00628, 18G_2+0_55MHZ_512QAM_EPLA. 8.Later, decom existing HW MW Link 4056P/K01107-4020Z/K00628, 18G_1+0_55MHZ_512QAM. FE_4020Z/K00628 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_5D Pro, Sub B_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Patching port 8-EM6-1 of new RTN910AF(RTN02) to port LAN 2 of existing SM Link ID_NT05643 K00628-K00626 MW1. 6.May re-use existing xC vlan dcn and vlan services. 7.Migrate traffic 4056P/K01107 via existing port Gi0/0/3 of PTN/Cisco at K00260. 8.Later, decom existing HW MW Link 4056P/K01107-4020Z/K00628, 18G_1+0_55MHZ_512QAM. | Existing HW MW Link 4056P/K01107-4020Z/K00628, 18G_1+0_55MHZ_512QAM. MW Swap to new HW MW Link 4056P/K01107-4020Z/K00628, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link 4056P/K01107-4020Z/K00628, 18G_1+0_55MHZ_512QAM. Site Impacted : 4056P/K01107. NE_4056P/K01107 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Patching existing BBU to port 8-EM6-1 of new RTN910AF(RTN02). 6.May re-use existing xC Vlan DCN and Vlan Services. 7.Migrate traffic 4056P/K01107 via new HW MW Link 4056P/K01107-4020Z/K00628, 18G_2+0_55MHZ_512QAM_EPLA. 8.Later, decom existing HW MW Link 4056P/K01107-4020Z/K00628, 18G_1+0_55MHZ_512QAM. | Existing HW MW Link 4056P/K01107-4020Z/K00628, 18G_1+0_55MHZ_512QAM. MW Swap to new HW MW Link 4056P/K01107-4020Z/K00628, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link 4056P/K01107-4020Z/K00628, 18G_1+0_55MHZ_512QAM. Site Impacted : 4056P/K01107. FE_4020Z/K00628 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_5D Pro, Sub B_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Patching port 8-EM6-1 of new RTN910AF(RTN02) to port LAN 2 of existing SM Link ID_NT05643 K00628-K00626 MW1. 6.May re-use existing xC vlan dcn and vlan services. 7.Migrate traffic 4056P/K01107 via existing port Gi0/0/3 of PTN/Cisco at K00260. 8.Later, decom existing HW MW Link 4056P/K01107-4020Z/K00628, 18G_1+0_55MHZ_512QAM. | XMC_5D Pro | MDD | 18G | 18G_1.2M(MDD) x1. | 18G_0.6M(MDD) x1. | GTSB | SQ202601130151-GTSB | GTSB | SQ202601130143-GTSB // SQ202601130146-GTSB // SQ202604200216-GTSB // SQ202604280656-GTSB |  |  | Ongoing | 2026-01-15 | 2026-01-31 | 2026-01-15 | 2026-01-22 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Completed |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-10 | 2026-03-03 | 2026-03-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123097 |  | 2025-12-31 | 2026-01-10 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-15 | 2026-01-31 | 2026-01-15 | 2026-01-16 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-01-15 | 2026-01-31 | 2026-01-15 | 2026-01-17 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-16 | 2026-01-15 | 2026-01-31 | 2026-01-15 | 2026-01-21 | HAMZAH BIN ABDUL MUTALIF6799000301 | 2025-10-01: 2026-01-15; 2025-10-01: 2026-01-31; 2025-10-01: 2026-01-15; 2025-11-21: 2026-01-16 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512180096-GTSB
7586A_HU_1 | Kg. Suan Lamba | DU00006281178 | Sabah | Sabah | 5.646599 | 118.128209 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M_512QAM_EPLA NE_7586A New 15G_1.2M(MDD) x1. Re-use existing RTN950A(RTN02, NEID 9-23423). New ISM8 x1. New XMC_5D Pro, Sub B_Lo x1. FE_7421B New 15G_1.2M(MDD) x1. Re-use existing RTN950A(RTN06, NEID 9-23424). New ISM8 x1. New XMC_5D Pro, Sub B_Hi x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 15G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL.**** Existing HW MW Link 7586A-7421B, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7586A-7421B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7586A & 7747B. NE_7586A 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-23423) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7586A-7421B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. FE_7421B 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN06, NEID 9-23424) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7586A-7421B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 15G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL.**** Existing HW MW Link 7586A-7421B, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7586A-7421B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7586A & 7747B. NE_7586A 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-23423) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7586A-7421B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 15G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL.**** Existing HW MW Link 7586A-7421B, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7586A-7421B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7586A & 7747B. FE_7421B 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN06, NEID 9-23424) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7586A-7421B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7586A-7421B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. | XMC-5D Pro | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | NR services | SQ202603170086-NR Services | NR services | SQ202604280667-NR Services // SQ202604280671-NR Services |  |  | Ongoing | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26021232 |  | 2026-02-13 | 2026-03-15 | Completed | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-03-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-04-03 | 2026-03-03 | 2026-03-15 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-03-03 | 2026-04-03 | 2026-03-03 | 2026-04-02 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-11 | 2026-03-03 | 2026-04-03 | 2026-03-03 | 2026-04-02 | IBRAHIM//BIN SAHABU/7167000007 | 2025-10-01: 2026-03-03; 2025-10-01: 2026-04-03; 2025-10-01: 2026-03-03; 2025-11-21: 2026-04-02 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511180736-GTSB
7328H7_EVT | DEWAN SERBAGUNA SIPITANG (PRN) | DU00006281179 | Sabah | Sabah | 5.079680 | 115.549970 | [13 empty] | Planning and integration support only for event site 7328H7 DEWAN SERBAGUNA SIPITANG (PRN) Tx route: 7328H7/7328H7-7388A-7212A-LL-7000A 1) Share port with 7388A at 7000A 2) New NE ID FE IDU 7388A RTN03 3) New NE ID NE IDU 7328H7 RTN01 4) At FE site 7388A - Install new RTN03 - Transfer BBU patching from RTN01 GE1 to RTN03 GE1 - Patch RTN03 GE2 to RTN01 GE1 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01657-Q00315 | DESAPAHABANAN2 | DU00004048395 | Sarawak | Sarawak | 4.785768 | 114.997851 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | No more HU and 4+0_1092M_max utili 25% only | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | HSU//MYET CHAE/6799000011
Q01018-Q00023 | KGTEBELU | DU00004048396 | Sarawak | Sarawak | 1.547111 | 110.858210 | [7 empty] | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
K00911-4751A | BDR DARULAMAN IND | DU00004048397 | Northern | Kedah | 6.243741 | 100.427783 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 28/9: Cutover done 27/9: MOS & Pre-installation in plan 23/8: Revise DU from K00911-K00026 to K00911-4751A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 1+0 0.6m/0.6m XMC3 NE: 1) 1xRTN910A 2) 1x23GHz XMC3E Sub B Lo 3) 1x23GHz 0.6m SP FE: 1) 1xISM8 card 2) 1x23GHz XMC3E Sub B Hi 3) 1x23GHz 0.6m SP | MW New Link / Reroute | Existing link RTN NT05444 Swap existing 18G 1+0 56MHz with new link/route 23G 1+0 112MHz Existing Tx route: K00911-K00026 New Tx route: K00911-4751A-4993A/K00579 Impact sites: K00911 NE (K00911) 1. Install new RTN910A (ops team to assign RTN number) 2. Install new link at new RTN 7-ISM8-1 3. Migrate K00911 traffic to new link FE (4751A) 1. Install new ISM8 card at RTN01 slot 3 2. Install new link at RTN01 3-ISM8-1 3. Migrate K00911 traffic to new link | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202410280596-GCI | 2024-11-29 | 2024-11-29 | Completed | 2024-10-31 | 2024-10-31 | 2024-10-31 | 2024-10-31 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24083050 |  | 2024-08-31 | 2025-02-19 | Completed | 2024-08-30 | 2024-08-31 | 2024-08-30 | 2025-02-19 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-27 | 2024-10-04 | 2024-09-27 | 2025-02-19 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | GCI TI | 2024-09-27 | 2024-10-04 | 2024-09-27 | 2024-12-04 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | GCI TI | 2024-10-14 | 2024-10-14 | 2024-10-14 | 2024-10-14 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-09-27 | 2024-10-04 | 2024-09-27 | 2025-05-06 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | 2024-09-27 | 2024-10-04 | 2024-09-27 | 2025-02-26 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | NG HONG JIE7018000036 | Logistic Team | 2024-11-12 | 2024-12-12 | 2024-11-12 | 2024-11-12 | ASTI//GANIS PUTRIANI/6237001358
B01593-B01963 | MENTARICOURTPJ | DU00004048398 | Central | Selangor | 3.082310 | 101.609121 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 24/10: Post-CO & L1 rectification 23/10: Cutover done. 22/10: D2: TI done, Alignment WIP. Possible to CO subject to access by BM | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub B Hi 3) 1x18GHz 0.6m SP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub B Hi 3) 1x18GHz 0.6m SP | MW Swap | Existing link RTN CT08874 Swap existing 18G 1+0 56MHz with new 18G 1+0 112MHz Impact sites: B01593 NE (B01593) 1. Install new RTN910A (ops team to assign RTN number) 2. Install new link at new RTN 7-ISM8-1 (reuse existing link frequency channel) 3. Migrate B01593 traffic to new link FE (B01963) 1. Install new RTN910A (ops team to assign RTN number) 2. Install new link at new RTN 7-ISM8-1 (reuse existing link frequency channel) 3. Patch RTN to CP port (ops team to assign). Migrate B01593 traffic to new link 4. Configure new DCN | [7 empty] | Magicell | SQ202409251042-Magicell | Magicell | SQ202410100842-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2024-10-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-15 | 2025-08-16 | 2025-08-15 | 2025-08-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24100386 |  | 2024-11-22 | 2024-12-02 | Completed | 2024-10-22 | 2024-11-22 | 2024-10-03 | 2024-12-02 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-22 | 2024-11-22 | 2024-12-02 | 2024-12-02 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2024-10-22 | 2024-11-22 | 2024-12-02 | 2024-12-02 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2024-10-24 | 2024-10-24 | 2024-10-24 | 2024-10-24 | SHUJAAT//ALI/6800000124 |  |  | 2024-10-22 | 2024-11-22 | 2024-11-05 | 2024-11-05 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | 2024-10-22 | 2024-11-22 | 2024-11-12 | 2024-11-12 | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2024-12-04 | NG HONG JIE7018000036 | Logistic Team | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
4764A-4863B | Lubok Peringgi | DU00004048399 | Northern | Kedah | 6.136378 | 100.356945 |  | AUG 24 |  | AUG 24 |  |  |  | 00. Integrated/RFS Done | 10/9: D3: Cutover done. Post-CO T/shooting WIP - RSL deviation 3dbm 28/8: D2: Continue TI. CO In Plan 27/8: MOS & Pre-installation WIP | TSS+AA+TI | L1+ATP+PAC | NE: 1) IF cable 2) 1xISM8 card 3) 1x18G XMC3E sub B Hi FE: 1) IF cable 2) 1xISM8 card 3) 1x18G XMC3E sub B Lo | MW Hardware Upgrade | Existing link 4764A-4863B 1+0 56MHz (4764A RTN01-4863B RTN03) Installed antenna was DP To add 2nd ODU to H port and configure as 2+0 Impact site: 4764A NE (4764A RTN01) 1. Install new ODU at antenna H port 2. Install new link at RTN01 7-ISM8-2 3. Configure EPLA 2+0 FE (4863B RTN03) 1. Install new ODU at antenna H port 2. Install new link at RTN03 3-ISM8-2 3. Configure EPLA 2+0 | [7 empty] | CCSMY | SQ202409251047-CCS | CCSMY | SQ202409060588-CCS | 2024-11-29 | 2024-11-29 | Completed | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-11 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24081489 |  | 2024-08-15 | 2024-08-17 | Completed | 2024-08-14 | 2024-08-15 | 2024-08-14 | 2024-08-17 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-27 | 2024-08-31 | 2024-08-27 | 2024-09-03 | Usman MUMTAZ7021000053 | CCS TI | 2024-08-27 | 2024-08-31 | 2024-08-27 | 2025-07-06 | Usman MUMTAZ7021000053 | CCS TI | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-08-30 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-08-27 | 2024-08-31 | 2026-04-07 | 2026-04-07 | Usman MUMTAZ7021000053 | 2025-10-01: 2024-08-27; 2025-10-01: 2024-08-31; 2025-10-01: 2024-08-30; 2025-11-21: 2024-08-30 |  |  | 2024-10-16 | 2024-11-16 | 2024-10-16 | 2024-10-16 | ASTI//GANIS PUTRIANI/6237001358
Q01248-Q00290 | LDG PALM HEAD | DU00003403042 | Sarawak | Sarawak | 3.394480 | 113.284409 | WK11 | MAR 24 | WK06 | FEB 24 | TI | Pending compliance | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 8GHz_0.6m/1.2m_SP_2+0_29.65MHz | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/29 | [7 empty] | YPTT | SQ202411140427-YPTT | YPTT | SQ202407020308-YPTT |  |  | Ongoing | 2024-03-11 | 2024-03-15 | 2025-10-29 | 2025-10-29 | JORDAN CHIN ZHEN WOON6794000058 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24012965 |  | 2024-08-30 | 2024-01-30 | Completed | 2024-08-29 | 2024-08-30 | 2024-01-30 | 2024-01-30 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-05-05 | 2024-05-05 | 2024-05-05 | 2024-05-05 | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2024-02-07 | 2024-06-30 | 2024-02-07 | 2024-06-28 | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-07 | C.PRATHABAN///6798000081 |  |  | 2024-02-07 | 2024-02-23 | 2024-02-07 | 2026-04-01 | NORAZHARI BIN MOHAMAD SALIM6794000032 | 2024-02-07 | 2024-02-23 | 2024-02-07 | 2024-04-01 | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045
9029C-9318A | Kampung Mendang Laut | DU00004388529 | Sarawak | Sarawak | 1.450759 | 110.391471 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_9029C 23G_DP_0.6m(MAC)+OMT x1. XMC_3E-2+0 , Sub_A&B_Lo x2. FE_9318A 23G_DP_0.6m(MAC)+OMT x1. XMC_3E-2+0,Sub_A&B_Hi x2. | MW Swap | Existing link 18G_1+0_112M_SP_0.6/0.6 Swap existing link to 23G_2+0_112M. Site Impacted:9029C,9422B. NE_9029C 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new XMC_3E-2+0 , Sub_A&B_Lo. 3.Reuse existing 9029C_RTN01 , 3_ISM8-2+0 configure it as 2+0. 4.Enable EPLA and service cross connect. 5.Decom existing ODU and Ant. FE_9318A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new XMC_3E-2+0,Sub_A&B_Hi. 3.Reuse existing 9318A_RTN04,7_ISM8-2+0 configure it as 2+0. 4.Enable EPLA and service cross connect. 5.Enable GE port and configure Physical LAG. 6.Remain existing In-Band DCN. 7.Decom existing ODU and Ant. | [7 empty] | Allstar | SQ202502260439-Allstar | Allstar | SQ202502270769-Allstar // SQ202504260202-Allstar | 2025-04-25 | 2025-04-21 | Completed | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250120AK |  | 2025-01-21 | 2025-02-04 | Completed | 2025-01-20 | 2025-01-21 | 2025-01-20 | 2025-02-04 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-05 | 2025-02-11 | 2025-02-18 | 2025-02-18 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-02-05 | 2025-02-11 | 2025-02-11 | 2025-02-20 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-13 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-02-05 | 2025-02-11 | 2025-02-22 | 2025-02-22 | BONG NEE NYEEbong.allstar@gmail.com | 2025-02-05 | 2025-02-11 | 2025-02-22 | 2025-02-22 | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-25 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
4470A_HU | Beruas(Maxis) | DU00004388530 | Northern | Kedah | 4.498551 | 100.782910 | [7 empty] | 00. Integrated/RFS Done | 25/6 : CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_4470A 23G_DP_0.6M(MAC)+OMT x1. 23G_XMC_3E , Sub A & B_Lo x2. RTN910A x1 FE_4024K/A00126. 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. | MW New Link / Reroute | Existing link 13G_2+0_28M.(4470A - 4490A) Link reroute to new FE 4024K/A00126 to support the 4711B child site. FE reroute due to 2.4M antenna size. Site Impacted: 4711B. NE_4470A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install 23G_XMC_3E , Sub A & B_Lo. 3.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 4.Traffic migrate to new link 23G_2+0_112M. 5.Enable GE1 , existing ETH cable at 4470A_RTN03 transfer to GE1 new RTN910A. 6.Existing 3_ISM8_(4711B_V & H) at 4470A_RTN01 transfer to Slot 3 new RTN910A. 7.Create service cross connect & EPLA for entire service. 8.Decom existing MW link (4470A_RTN01 to 4490A_RTN01). Ensure entire traffic migrate to new link before decom. FE_4024K/A00126. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect & EPLA. 5.Create new In Band DCN. 6.Enable GE 1 , ETH cable pathching the Cisco Fiber port Gi0/2/6. (66054-BERUAS-ACC1). 7.Decom existing MW link (4490A_RTN01 to 4470A_RTN01).Ensure entire traffic migrate to new link before decom. | Existing link 13G_2+0_28M.(4470A - 4490A) Link reroute to new FE 4024K/A00126 to support the 4711B child site. FE reroute due to 2.4M antenna size. Site Impacted: 4711B. NE_4470A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install 23G_XMC_3E , Sub A & B_Lo. 3.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 4.Traffic migrate to new link 23G_2+0_112M. 5.Enable GE1 , existing ETH cable at 4470A_RTN03 transfer to GE1 new RTN910A. 6.Existing 3_ISM8_(4711B_V & H) at 4470A_RTN01 transfer to Slot 3 new RTN910A. 7.Create service cross connect & EPLA for entire service. 8.Decom existing MW link (4470A_RTN01 to 4490A_RTN01).Ensure entire traffic migrate to new link before decom. | Existing link 13G_2+0_28M.(4470A - 4490A) Link reroute to new FE 4024K/A00126 to support the 4711B child site. FE reroute due to 2.4M antenna size. Site Impacted: 4711B. FE_4024K/A00126. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect & EPLA. 5.Create new In Band DCN. 6.Enable GE 1 , ETH cable pathching the Cisco Fiber port Gi0/2/6. (66054-BERUAS-ACC1). 7.Decom existing MW link (4490A_RTN01 to 4470A_RTN01).Ensure entire traffic migrate to new link before decom. | XMC_3E | MAC | 12765.000 12877.000 12821.000 12933.000 | 0.6 | 0.6 | CCSMY | SQ202504280454-CCS | GCI | SQ202506160513-GCI // SQ202506160540-GCI // SQ202508140739-GCI | 2025-11-27 | 2025-11-26 | Completed | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-24 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061161 |  | 2025-06-12 | 2025-06-13 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-06-24 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-07-06 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-07-16 | ANAS FIKRI ADHA BIN RAZMI6000009598 | 2025-02-05: 2025-06-14; 2025-02-11: 2025-06-28; 2025-02-22: 2025-06-14; 2025-02-22: 2025-06-14 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | CHEONG/SENG/WAH/7018000306
3814A-1124A | Masjid At-Taqwa Banting (REL) | DU00004388531 | Central | Selangor | 2.810811 | 101.492446 |  |  | W49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 6/12: D3: Cutover done 4/12: D2: TI NE done, pending access FE. Plan 6/12 (EB CRQ approval window) 11/11: Uplink for TX MINI 3815A-3814A | TSS+AA+TI | L1+ATP+PAC | New parallel link 23G_2+0_112M. NE_3814A 23G_DP_0.6m(MAC)+OMT x1. ISM8-2+0 x1 XMC_3E-2+0 ,Sub A&B_Lo x2. FE_1124A 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1 XMC_3E-2+0,Sub A&B_Hi x2. | MW Parallel Link | For 3814A , prioritize uplink 3814A-1124A. 3814A-1124A. Existing link 23G_1+0_112M.SP_0.6/0.6m. Establish new parallel link 23G_2+0_112M. Site Impacted: 3814A,3815A. NE_3814A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new 3_ISM8-2+0 into new RTN910A. 3.Install new XMC_3E-2+0 ,Sub A&B_Lo 4.Enable EPLA and service cross connect. 5.No decom is required. FE_1124A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0 3.Install new XMC_3E-2+0,Sub A&B_Hi. 4.Enable EPLA and service cross connect. 5.Create New In-Band DCN. | [7 empty] | YPTT | SQ202411280087-YPTT | YPTT | SQ202411250784-YPTT // SQ202504260171-YPTT | 2025-05-28 | 2025-05-27 | Completed | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-15 | 2025-05-16 | 2025-05-15 | 2025-05-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-27 | 2025-05-28 | 2025-05-27 | 2025-05-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112280 |  | 2024-11-23 | 2024-12-30 | Completed | 2024-11-22 | 2024-11-23 | 2024-11-22 | 2024-12-30 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-06 | 2025-01-05 | 2024-12-06 | 2024-12-30 | MD//ERWAN BIN ROHMAN/6794000008 | YPTT TI | 2024-12-06 | 2025-01-05 | 2024-12-06 | 2024-12-25 | MD//ERWAN BIN ROHMAN/6794000008 | YPTT TI | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-12-06 | 2025-01-05 | 2024-12-06 | 2024-12-26 | MD//ERWAN BIN ROHMAN/6794000008 | 2025-02-05: 2024-12-03; 2025-02-11: 2025-01-03; 2025-02-22: 2024-12-03; 2025-02-22: 2024-12-03 |  |  | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI
3815A-3814A | Jln Delima | DU00004388532 | Central | Selangor | 2.818071 | 101.496808 |  |  | W49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 7/12: Cutover done 4/12: D2: TI done, continue alignment & CO 6/12 (EB CRQ approved) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW Swap | Existing link 15G_1+0_28M. Swap existing link to 23G_2+0_112M. Site Impacted:3815A,3814A. NE_3815A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Reuse existing 3815A_RTN01,7_ISM8-2+0 config it as 2+0.(RTN no provide by MSP team). 3.Install new XMC_3E-2+0 , Sub A&B_Hi. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new link 23G_2+0_112M. 6.Decom existing 15G ODU and Ant. For 3814A , prioritize uplink 3814A-1124A. FE_3814A. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0 config it as 2+0.(RTN no provide by MSP team). 3.Install new XMC_3E-2+0 , Sub A&B_Lo. 4.Enable EPLA and service cross connect. 5.Decom existing 15G ODU , Ant and 3_ISV3. | [7 empty] | YPTT | SQ202411280087-YPTT | YPTT | SQ202411250784-YPTT // SQ202504260171-YPTT | 2025-08-30 | 2025-09-03 | Completed | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-29 | 2025-08-30 | 2025-08-29 | 2025-09-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112279 |  | 2024-11-23 | 2024-12-30 | Completed | 2024-11-22 | 2024-11-23 | 2024-11-22 | 2024-12-30 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-03 | 2025-01-03 | 2024-12-03 | 2024-12-30 | MD//ERWAN BIN ROHMAN/6794000008 | YPTT TI | 2024-12-03 | 2025-01-03 | 2024-12-03 | 2024-12-23 | MD//ERWAN BIN ROHMAN/6794000008 | YPTT TI | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-12-03 | 2025-01-03 | 2024-12-03 | 2024-12-24 | MD//ERWAN BIN ROHMAN/6794000008 | 2024-12-03 | 2025-01-03 | 2024-12-03 | 2024-12-04 | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-20 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202509250626-GCI
4660B-4991A | Kolej Bank Muamalat | DU00004388533 | Northern | Kedah | 6.479375 | 100.509930 | W49-52 | DEC 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 3/12: D2: Cutover done 2/12: MOS & TI WIP. Continue 3/12 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_4660B. 23G_DP_0.6m(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. FE_4991A. 23G_DP_0.6m(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Hi x2. | MW Swap | Existing link 23G_1+0_112M. Swap existing link to 23G_2+0_112M. Site Impacted:4660B. NE_4660B. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Reuse existing 4660B_RTN01. 3.Install new 3_ISM8-2+0 into existing 4660B_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Enable EPLA & service cross connect. 6.Migrate traffic to new link. 7.Decom existing Ant and ODU. FE_4991A. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Reuse existing 4991A_RTN02. 3.Install new 3_ISM8-2+0 into existing 4991A-RTN02. 4.Install new XMC_3E , Sub A & B_Hi. 5.Enable EPLA & service cross connect. 6.Migrate traffic to new link. 7.Decom existing Ant and ODU. | [7 empty] | CCSMY | SQ202501140160-CCS | CCSMY | SQ202411260109-CCS // SQ202504260175-CCS | 2025-08-15 | 2025-08-14 | Completed | 2025-01-12 | 2025-01-12 | 2025-01-12 | 2025-01-12 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-14 | 2025-08-15 | 2025-08-14 | 2025-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241125A7 |  | 2024-11-26 | 2024-12-05 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2024-12-05 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-02 | 2024-12-20 | 2024-12-02 | 2024-12-05 | HASHIM//BIN AHMAD ZAIDI/7021000032 | CCS TI | 2024-12-02 | 2024-12-20 | 2024-12-02 | 2024-12-05 | HASHIM//BIN AHMAD ZAIDI/7021000032 | CCS TI | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-12-02 | 2024-12-20 | 2024-12-02 | 2024-12-14 | HASHIM//BIN AHMAD ZAIDI/7021000032 | 2024-12-02 | 2024-12-20 | 2024-12-02 | 2024-12-05 | 2024-12-19 | 2024-12-19 | 2024-12-19 | 2024-12-19 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202508150516-GCI | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | EZRIN TASNIM BIN ABDUL GANI6798000128
4306A-4733A | Changkat Tin RCC | DU00004395047 | Northern | Perak | 4.287200 | 101.046700 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | DU00003819264 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7649B-7209A | Seafest Hotel | DU00004395048 | Sabah | Sabah | 4.478526 | 118.617523 |  |  |  |  | RFS | TI done | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G 2+0 0.6m/0.6m XMC3E NE: 1) 1xISM8 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 3) 1x18GHz 0.6m DP FE: 1) 1xISM8 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 3) 1x18GHz 0.6m DP | MW Parallel Link | MW HW 7649b-7209A-01-HNIC_Project) congested To install parallel link and create EPLA 3+0 Impact site: 7649B,7360A,7230C,7801E Tx route: 7649B-7209A NE (7649B): 1) Add ISM8 card at 7649B RTN03 slot 4 2) Install new link at RTN03 4-ISM8 3) Create 3+0 EPLA FE (7209A): 1) Add ISM8 card at 7209A RTN10 slot 4 2) Install new link at RTN10 4-ISM8 3) Create 3+0 EPLA | [7 empty] | NR services | SQ202504080153-NR Services | NR services | SQ202504210220-NR Services // SQ202504210225-NR Services // SQ202504260199-NR Services | 2025-09-04 | 2025-09-04 | Completed | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-17 | 2025-04-24 | 2025-04-21 | 2025-04-21 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032150 |  | 2025-03-22 | 2025-04-09 | Completed | 2025-03-21 | 2025-03-22 | 2025-03-21 | 2025-04-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-14 | 2025-05-10 | 2025-04-14 | 2025-04-15 | WILFRED BALANG7167000026 | NR Service TI | 2025-04-14 | 2025-05-10 | 2025-04-14 | 2025-04-15 | WILFRED BALANG7167000026 | NR Service TI | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-04-17 | 2025-04-14 | 2025-05-10 | 2025-04-14 | 2025-04-21 | WILFRED BALANG7167000026 | 2025-02-05: 2025-04-14; 2025-02-11: 2025-05-10; 2025-02-22: 2025-04-14; 2025-02-22: 2025-04-16 |  |  | 2025-05-29 | 2025-06-29 | 2025-05-29 | 2025-05-29 | MASDIANA//BINTI BEDIN/6801000016
7209A_1 | Bubul Road Semporna (Maxis) | DU00004395049 | Sabah | Sabah | 4.477580 | 118.606350 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | DO ready | TSS+TI | L1+ATP+PAC | 1xCat6 cable SFP 1km and patch cord | IDU-IPRAN | Expecting 7209A BUBUL ROAD SEMPORNA RTN10 GE1 to CP will congested after MW link 7649B-7209A upgraded. To perform patching to CP port and create 3+0 LAG NE (7209A RTN10): 1) Patch GE2 to new CP port (electrical) 2) Patch GE5 to new CP port (optical) 3) Create 3+0 LAG | [7 empty] | NR services | SQ202502120362-NR Services | NR services | SQ202504080100-NR Services // SQ202504260199-NR Services | 2025-06-27 | 2025-06-25 | Completed | 2025-02-11 | 2025-02-11 | 2025-02-11 | 2025-02-11 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021402 |  | 2025-02-15 | 2025-02-15 | Completed | 2025-02-14 | 2025-02-15 | 2025-02-14 | 2025-02-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-21 | 2025-03-08 | 2025-02-21 | 2025-02-28 | RAMLAN//BIN ROSLAN/6000002578 | NR Service TI | 2025-02-21 | 2025-03-08 | 2025-02-21 | 2025-02-28 | RAMLAN//BIN ROSLAN/6000002578 | NR Service TI | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-02-21 | 2025-03-08 | 2025-02-21 | 2025-03-05 | RAMLAN//BIN ROSLAN/6000002578 | 2025-02-05: 2025-02-21; 2025-02-11: 2025-03-08; 2025-02-22: 2025-02-21; 2025-02-22: 2025-02-28 |  |  | 2025-03-24 | 2025-04-24 | 2025-03-24 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507080638-GTSB | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q01421-9375B | Q140B_Q01421OD_RAMOJLNRANTAUPJGSBW | DU00004395050 | Sarawak | Sarawak | 2.386700 | 111.865700 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz 1.2m SP FE: 1) 1xISM8 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz 0.6m SP | MW Swap | Existing link SM SW02367 (Q01421-Q00585) To swap Existing link SM 13GHz 1+0 with new Huawei link 18GHz 1+0 112MHz Impacted sites: Q01421 Current Tx route: Q01421-Q00585 New Tx route: Q01421-9375B-LL-9368A NE (Q01421): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link FE (9375B/Q00585): 1) Add new ISM8 card at 9375B-RANTAU PANJANG-RTN01 slot 3 2) Install new link at RTN01 3-ISM8-1 3) Migrate Q01421 traffic to new link. 4) Decom existing link | [7 empty] | Datasco | SQ202502120366-Datasco | NR Services | SQ202505190439-NR Services // SQ202505190447-NR Services | 2025-04-25 | 2025-04-21 | Completed | 2025-02-08 | 2025-02-08 | 2025-03-03 | 2025-03-03 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-17 | 2025-03-21 | 2025-03-17 | 2025-03-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-16 | 2025-04-18 | 2025-04-16 | 2025-04-16 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250508AF |  | 2025-05-09 | 2025-05-13 | Completed | 2025-05-08 | 2025-05-09 | 2025-05-08 | 2025-05-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-15 | 2025-05-20 | 2025-05-15 | 2025-06-14 | DINESH SINGH CHEEMA7167000003 | NR Service TI | 2025-05-15 | 2025-05-20 | 2025-05-15 | 2025-06-28 | DINESH SINGH CHEEMA7167000003 | NR Service TI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-13 | 2025-05-15 | 2025-05-20 | 2025-05-15 | 2025-07-05 | DINESH SINGH CHEEMA7167000003 | 2025-02-05: 2025-05-15; 2025-02-11: 2025-05-20; 2025-02-22: 2025-05-15; 2025-02-22: 2025-05-19 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402
9411A_EB | Tmn Sri Wangi | DU00004395051 | Sarawak | Sarawak | 1.577998 | 110.314859 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 21/8/2025 : Cutover done | TSS+TI | L1+ATP+PAC |  | BBU Patching | At NE: Patch 9411A BBU to xD IDIU 9411A POI Needed : No | [7 empty] | Trintel | SQ202509241037-Trintel | Trintel | SQ202509110859-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-22 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-26 | 2025-09-22 | 2025-09-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-26 | 2025-09-22 | 2025-09-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081456 |  | 2025-01-10 | 2025-01-13 | Completed | 2025-01-10 | 2025-01-10 | 2025-01-11 | 2025-01-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-21 | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-21 | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-21 | MATTHEW//ANAK ARON/6000043057 | 2025-02-05: 2025-08-20; 2025-02-11: 2025-08-20; 2025-02-22: 2025-08-20; 2025-02-22: 2025-08-21 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202509250704-GTSB | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q00254 | Q118B_Q00254OD_BKTNYABAU | DU00004395052 | Sarawak | Sarawak | 3.217583 | 113.080630 |  | DEC 24 |  |  |  |  | ZTE | 00. Integrated/RFS Done | 6/12: Cutover done 4/12: MOS & TI WIP. Need CD to configure new SR-PTN Port | TSS+TI | L1+ATP+PAC | SFP 1km and patch cord | IDU-IPRAN | IDU HW SW03685 (Q00650-Q00254) at Q00254 port congested. This IDU cascaded to Q00254-BKT NYABAU-RTN05 then to PTN port 0/3/0/9 causing congestion. To establish new connection from IDU SW03685 direct to PTN and offload NIC sites Q01590,Q02083,9569B to new port. Impact site: Q01590,Q02083,9569B Tx route: Q00254 NE (Q00254): 1) Patch GE4 (optical) to new PTN port (ops team to assign new port) 2) Divert Q01590,Q02083,9569B to new port | [7 empty] | Datasco | SQ202412040275-Datasco | Datasco | SQ202411260106-Datasco // SQ202504260205-Datasco | 2025-10-31 | 2025-10-28 | Completed | 2024-12-06 | 2024-12-06 | 2024-12-09 | 2024-12-09 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241120A1 |  | 2024-11-21 | 2024-12-02 | Completed | 2024-11-20 | 2024-11-21 | 2024-11-20 | 2024-12-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-04 | 2024-12-31 | 2024-12-20 | 2024-12-20 | Wong Ching Chai7019000072 | Datasco TI | 2024-12-04 | 2024-12-31 | 2024-12-12 | 2024-12-19 | Wong Ching Chai7019000072 | Datasco TI | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-09 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-12-04 | 2024-12-31 | 2024-12-13 | 2024-12-13 | Wong Ching Chai7019000072 | 2025-02-05: 2024-12-04; 2025-02-11: 2024-12-31; 2025-02-22: 2024-12-05; 2025-02-22: 2024-12-05 |  |  | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202510300425-GTSB
9569B-9113A | Kampung Pandan | DU00004395053 | Sarawak | Sarawak | 3.123610 | 113.059110 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done | 2605: Pending Subcon to proceed TI | TSS+AA+TI | L1+ATP+PAC | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1xISM8 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz 0.6m SP 4) SFP and patchcord FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz 0.6m SP 4) SFP and patchcord | MW Parallel Link | MW SM SW03210 (Q01115-Q00650) congested To install parallel link and offload child site Q01590 to this new link Impact site: Q01590 Tx route: Q01115-Q00650-Q00254 NE (9569B/Q01115): 1) Add ISM8 card at Q01115-ULUSEGAN-RTN02 slot 3 2) Install new link at RTN02 3-ISM8-1 18G 1+0 0.6m/0.6m XMC3E 3) Remove cascade RTN02 to SM IDU SW03210 4) Migrate traffic Q01590 to new link FE (9113A/Q00650): 1) Install new RTN910A (ops team to provide RTN number) 2) Install new link at new RTN 7-ISM8-1 18G 1+0 0.6m/0.6m XMC3E 3) Patch new RTN GE5 (optical) to IDU SW03685 GE3 (optical) 4) Migrate traffic Q01590 to new link | [7 empty] | Trintel | SQ202501270116-Trintel | Allstar | SQ202506120261-Allstar // SQ202506120262-Allstar | 2025-05-09 | 2025-04-29 | Completed | 2025-01-25 | 2025-01-27 | 2025-01-25 | 2025-02-24 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-29 | 2025-05-09 | 2025-04-29 | 2025-04-29 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-29 | 2025-05-09 | 2025-04-29 | 2025-04-29 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-29 | 2025-05-09 | 2025-04-29 | 2025-04-29 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052094 |  | 2025-05-25 | 2025-06-13 | Completed | 2025-05-24 | 2025-05-25 | 2025-05-24 | 2025-06-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-26 | 2025-06-01 | 2025-06-12 | 2025-06-13 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-05-26 | 2025-06-01 | 2025-06-10 | 2025-06-20 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-10 | 2025-05-26 | 2025-06-01 | 2025-07-01 | 2025-07-01 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | 2025-02-05: 2025-05-26; 2025-02-11: 2025-06-01; 2025-02-22: 2025-06-16; 2025-02-22: 2025-06-16 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402
Q00488-Q00367 | Q132A_Q00488OD_BORNEOTROPICAL | DU00004422476 | Sarawak | Sarawak | 4.180403 | 113.998665 |  |  |  | AUG 25 |  |  | ZTE | 03. TSS Only | 5/8/2025 : Huawei already done swap MW 1/8/2025 : Only MOS activity 2605: Doable. Pending material DT. | TSS+AA+TI+Dismantle |  | 13G_2+0_1.8M/1.2M_MDD_28HZ_256QAM SUB B | MW Swap | MW Swap SW00937 EOS Equipment with new Huawei EQ NE: 1. Swap IDU with new 910A IDU. 2. Swap ODU with 2+0 XMC5D (Sub B) 3. Swap Antenna with new 1.8m MDD Antenna. 4. Configure link 2+0 256QAM 28Mhz FE: 1. Swap IDU with new 910A IDU. 2. Swap ODU with 2+0 XMC5D (Sub B) 3. Swap Antenna with new 1.2m MDD Antenna. 4. Configure link 2+0 256QAM 28Mhz |  |  | XMC-5D |  | 13G | 1.8 | 1.2 | Allstar | SQ202503190729-Allstar | NR Services | No PR required-Work at TSS only | 2025-04-25 | 2025-04-21 | Completed | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-04-16 | 2025-04-18 | 2025-04-16 | 2025-04-16 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-16 | 2025-04-18 | 2025-04-16 | 2025-04-16 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071140 |  | 2025-07-12 | 2025-07-31 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-21 | 2025-07-25 | 2025-09-03 | 2025-09-03 | system | NR Service TI | [13 empty] | 2025-07-21 | 2025-07-25 |  |  |  | 2025-02-05: 2025-07-21; 2025-02-11: 2025-07-25 | [7 empty] | GTSB_AA | SQ202510300154-GTSB | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | HSU//MYET CHAE/6799000011
4618C_LOS | Lagenda Heights RT | DU00004422477 | Northern | Kedah | 5.662886 | 100.502810 |  |  | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 10/12: D2: Cutover done 29/11: TSS & LOS hunting concurrent TI | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M due to LOS Block. NE_4618C 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E-2+0 , Sub_A & B_Hi x2. FE_K00307 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E-2+0 , Sub A & B_Lo x2. | MW New Link / Reroute | Link reroute to new FE 4956C with 23G_2+0_112M due to LOS Block. NE_4618C 1.Install 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E-2+0 , Sub_A & B_Hi. 4.Create EPLA and service cross connect. 5.Traffic migrate to new link with new FE site. 6.Decom existing MW link. (4618C-4640A) FE_4956C 1.Install 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_3E-2+0 , Sub A & B_Lo. 4.Create EPLA and service cross connect. 5.Enable GE1 , ETH cable patching to existing 4956C_RTN01 (GE2). 6.Traffic migrate to new FE link via existing MW (4956C-4637A). 7.Decom existing MW link. (4640A-4618C) | [7 empty] | GCI | SQ202505200530-GCI | GCI | SQ202411260115-GCI // SQ202504150095-GCI // SQ202508140739-GCI | 2025-08-21 | 2025-08-20 | Completed | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-12-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-17 | 2024-12-17 | 2024-12-17 | 2024-12-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112586 |  | 2024-11-26 | 2024-12-09 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2024-12-09 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-09 | 2024-12-31 | 2024-12-09 | 2024-12-09 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-12-09 | 2024-12-31 | 2024-12-09 | 2024-12-10 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-12-09 | 2024-12-31 | 2024-12-09 | 2024-12-14 | SAFUAN//BIN YUSOFF/6800000178 | 2024-12-09 | 2024-12-31 | 2024-12-09 | 2024-12-13 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | NG HONG JIE7018000036 | Logistic Team | 2024-12-19 | 2025-01-19 | 2024-12-19 | 2024-12-19 | ASTI//GANIS PUTRIANI/6237001358 |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
9846A_IPR | Boulevard Kuching IB | DU00006053160 | Sarawak | Sarawak | 1.509492 | 110.336072 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9846A 10G PORT 9846A/9846A-LL-9999A Install 1 10G SFP Optical at SACOFA Port ETH 1-3-3 Install 1 10G SFP Optical at HW 9846A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port ETH 1-3-3 to HW 9846A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All Sites: 9846A, 9287B | 9846A 10G PORT 9846A/9846A-LL-9999A Install 1 10G SFP Optical at SACOFA Port ETH 1-3-3 Install 1 10G SFP Optical at HW 9846A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port ETH 1-3-3 to HW 9846A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All Sites: 9846A, 9287B | N/A | [5 empty] | Allstar | SQ202509241008-Allstar | Allstar | SQ202509241003-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250922B9 |  | 2025-09-23 | 2025-09-24 | Completed | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-03 | 2025-10-09 | 2025-10-04 | 2025-10-04 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-03 | 2025-10-09 | 2025-10-13 | 2025-10-13 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-04 | 2025-10-03 | 2025-10-09 | 2025-10-11 | 2025-10-11 | ROYSTON//ANAK RAMSY/6798000228 | 2025-02-05: 2025-10-03; 2025-02-11: 2025-10-09; 2025-02-22: 2025-10-09; 2025-02-22: 2025-10-09 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260801-GCI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
9126A_IPR | Rumah Dingon | DU00006053161 | Sarawak | Sarawak | 2.840046 | 112.781703 | [7 empty] | 00. Integrated/RFS Done | 8/10/2025 - received xfp from sacofa pic. Subcon to replan enter 29/9/2025 : Plan to do IDU-IPRAN - Hold due to losscom | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9126A 10G PORT 9126A/9126A-LL-9106A Install 1 10G SFP Optical at SACOFA Port ETH 1-2-1 Install 1 10G SFP Optical at HW 9126A RTN01 8-EM6-4(PORT-4) Patching Optical Patch Cord SACOFA Port ETH 1-2-1 to HW 9126A RTN01 8-EM6-4(PORT-4) Reconfigure Traffic for All Sites: 9126A, 9386B, 9044Z, 9340K | 9126A 10G PORT 9126A/9126A-LL-9106A Install 1 10G SFP Optical at SACOFA Port ETH 1-3-3 Install 1 10G SFP Optical at HW 9126A RTN01 8-EM6-4(PORT-4) Patching Optical Patch Cord SACOFA Port ETH 1-3-3 to HW 9126A RTN01 8-EM6-4(PORT-4) Reconfigure Traffic for All Sites: 9126A, 9386B, 9044Z, 9340K | N/A | [5 empty] | Allstar | SQ202509241008-Allstar | Allstar | SQ202509241003-Allstar // SQ202512170142-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250922BA |  | 2025-09-23 | 2025-09-23 | Completed | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-23 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-29 | 2025-10-05 | 2025-09-29 | 2025-09-29 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-29 | 2025-10-05 | 2025-11-12 | 2025-11-12 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-22 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-22 | 2025-09-29 | 2025-10-05 | 2025-11-15 | 2025-11-15 | ROYSTON//AHHOLE/6000038561 | 2025-02-05: 2025-09-29; 2025-02-11: 2025-10-05; 2025-02-22: 2025-09-29; 2025-02-22: 2025-09-29 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202509260801-GCI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
9162A_IPR | Kg. Karu | DU00006053162 | Sarawak | Sarawak | 1.292583 | 110.277007 | [7 empty] | 00. Integrated/RFS Done | 24/9/2025 : Plan to do IDU-IPRAN - Re-plan due to SFP module shortage | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9162A 10G PORT 9162A/9162A-LL-9999A Install 1 10G SFP Optical at SACOFA Port ETH 1-1-3 Install 1 10G SFP Optical at HW 9162A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port ETH 1-1-3 to HW 9162A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All Sites: 9162A, 9194R, 9195R, 9188R | 9162A 10G PORT 9162A/9162A-LL-9999A Install 1 10G SFP Optical at SACOFA Port ETH 1-1-3 Install 1 10G SFP Optical at HW 9162A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port ETH 1-1-3 to HW 9162A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All Sites: 9162A, 9194R, 9195R, 9188R | N/A | [5 empty] | Allstar | SQ202509241008-Allstar | Allstar | SQ202509241003-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250922BB |  | 2025-09-23 | 2025-09-24 | Completed | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-09-24 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-24 | 2025-10-01 | 2025-10-13 | 2025-10-13 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-03 | 2025-09-24 | 2025-10-01 | 2025-10-13 | 2025-10-13 | ROYSTON//ANAK RAMSY/6798000228 | 2025-02-05: 2025-09-24; 2025-02-11: 2025-10-01; 2025-02-22: 2025-09-24; 2025-02-22: 2025-09-24 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260801-GCI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
9086A_IPR | Kuala Baram | DU00006053163 | Sarawak | Sarawak | 4.556653 | 114.008880 | [7 empty] | 00. Integrated/RFS Done | 19/9/2025 : Cutover done | TSS+TI | L1+ATP+PAC |  | IDU-IPRAN | Site affected : 9086A , 9830B , 9011B3 , 3359A5. NE_9086A 1.Install new 10G SFP module at existing 9086A_RTN01_GE3. (ID : 29600). 2.Install new 10G SFP module at new Sacofa Port 10GE 1-3-15. 3.Install new 3_ISM8-1+0 into existing 9086A_RTN01 (ID: 29600), and transfer the 2x IF cables from 9086A_RTN02 (ID: 24129) to 9086A_RTN01 to carry traffic for the 9011B3. 4.Install new 4_ISM8-1+0 into existing 9086A_RTN01 (ID : 29600), and transfer the IF cable from 9086A_RTN03 (ID : 24160) to 9086A_RTN01 to carry traffic for the 3359A5. 5.Patching Fiber patch cord from 10G 9086A_RTN01_GE3 to 10G new Sacofa port 10GE 1-3-15. 6.Disconnect ETH cable at Old Sacofa Ports , old Interconnect IDU LAN cable and disable unused port. 7.Create service cross connect and migrate entire traffic to new Sacofa port 10GE 1-3-15. | Site affected : 9086A , 9830B , 9011B3 , 3359A5. NE_9086A 1.Install new 10G SFP module at existing 9086A_RTN01_GE3. (ID : 29600). 2.Install new 10G SFP module at new Sacofa Port 10GE 1-3-15. 3.Install new 3_ISM8-1+0 into existing 9086A_RTN01 (ID: 29600), and transfer the 2x IF cables from 9086A_RTN02 (ID: 24129) to 9086A_RTN01 to carry traffic for the 9011B3. 4.Install new 4_ISM8-1+0 into existing 9086A_RTN01 (ID : 29600), and transfer the IF cable from 9086A_RTN03 (ID : 24160) to 9086A_RTN01 to carry traffic for the 3359A5. 5.Patching Fiber patch cord from 10G 9086A_RTN01_GE3 to 10G new Sacofa port 10GE 1-3-15. 6.Disconnect ETH cable at Old Sacofa Ports , old Interconnect IDU LAN cable and disable unused port. 7.Create service cross connect and migrate entire traffic to new Sacofa port 10GE 1-3-15. | [6 empty] | Allstar | SQ202509241008-Allstar | Allstar | SQ202509241003-Allstar // SQ202512170142-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250922BC |  | 2025-09-23 | 2025-09-23 | Completed | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-23 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-09-26 | 2025-10-17 | 2025-10-17 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-19 | 2025-09-26 | 2025-10-17 | 2025-10-17 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-19 | 2025-09-19 | 2025-09-26 | 2025-10-05 | 2025-10-17 | ROYSTON//AHHOLE/6000038561 | 2025-02-05: 2025-09-19; 2025-02-11: 2025-09-26; 2025-02-22: 2025-09-19; 2025-02-22: 2025-09-19 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260801-GCI | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | CHEONG/SENG/WAH/7018000306
9452A_IPR | Gold Jade MP | DU00006053164 | Sarawak | Sarawak | 1.545330 | 110.331190 | [7 empty] | 00. Integrated/RFS Done | 19/9/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 10G SFP Module x 2. Fiber Patch Cord x 1 pairs. | IDU-IPRAN | Site affected 9452A , 9044C. NE_9452A 1.Install new 10G SFP module at existing 9452A_RTN01_GE3 (ID : 20251). 2.Install new 10G SFP module at new Sacofa Port 10GE 1-4-2 3.Patching Fiber patch cord from 9452A_RTN01_GE3 to new Sacofa port 10GE 1-4-2. 4.Disconnect existing LAN cable from Old Sacofa port and disable unused port. 5.Create service cross connect and all traffic migrate to new Sacofa port 10GE 1-4-2. | Site affected 9452A , 9044C. NE_9452A 1.Install new 10G SFP module at existing 9452A_RTN01_GE3 (ID : 20251). 2.Install new 10G SFP module at new Sacofa Port 10GE 1-4-2 3.Patching Fiber patch cord from 9452A_RTN01_GE3 to new sacofa port 10GE 1-4-2. 4.Disconnect existing LAN cable from Old Sacofa port and disable unused port. 5.Create service cross connect and all traffic migrate to new sacofa port 10GE 1-4-2. | [6 empty] | Allstar | SQ202509241008-Allstar | Allstar | SQ202509241003-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250922BD |  | 2025-09-23 | 2025-09-24 | Completed | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-09-25 | 2025-10-17 | 2025-10-17 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-19 | 2025-09-25 | 2025-10-17 | 2025-10-17 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-19 | 2025-09-19 | 2025-09-25 | 2025-10-05 | 2025-10-17 | ROYSTON//ANAK RAMSY/6798000228 | 2025-02-05: 2025-09-19; 2025-02-11: 2025-09-25; 2025-02-22: 2025-09-19; 2025-02-22: 2025-09-19 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260801-GCI | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | CHEONG/SENG/WAH/7018000306
Q02233_HU | Rumah Lambor | DU00006053165 | Sarawak | Sarawak | 4.260840 | 114.073790 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_55M_512QAM_EPLA NE_Q02233 New 18G_1.2M(MDD) x1. New RTN910AF(RTN01). New XMC_5D Pro, Sub A_Hi x1. New CAT6 cable x1. FE_Q00592 New 18G_1.2M(MDD) x1. New RTN910AF(RTN01). New XMC_5D Pro, Sub A_Lo x1. New SFP Module 1.25G/1G 1310nm 10Km x1.(For IDU Huawei) New Optical Patchcord with suitable type and length x1. | MW Swap | Existing SM MW Link_ID SW04228 Q02233-Q00592 MW1, 13G_1+0_28MHZ_1024QAM_223M. MW Swap to new HW MW Link Q02233-Q00592, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom Existing SM MW Link_ID SW04228 Q02233-Q00592 MW1, 13G_1+0_28MHZ_1024QAM_223M. Site Impacted : Q02233 & Q02239. NE_Q02233 1.Install new 18G_1.2M(MDD) x1. 2.New RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Enable port 8-EM6-1 and perform patching to existing BBU. 5.Enable port 8-EM6-2 and perform cascading to LAN 1 of existing IDU SM AGS20(IP Adr: 10.127.212.229). 6.Request new xC Vlan DCN. 7.Migrate traffics Q02233 & Q02239 via new HW MW Link Q02233-Q00592, 18G_2+0_55MHZ_512QAM_EPLA. 8.Later, decom Existing SM MW Link_ID SW04228 Q02233-Q00592 MW1, 13G_1+0_28MHZ_1024QAM_223M. FE_Q00592 1.Install new 18G_1.2M(MDD) x1. 2.New RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-5 of new RTN910AF(RTN01) and insert suitable SFP Module 1.25G/1G 1310nm 10Km. 5.Perform cascading between port 8-EM6-5 of new RTN910AF(RTN01) and LAN 5 of existing IDU SM AGS20(IP Adr: 10.127.212.226). 6.Request new xC Vlan DCN. 7.Migrate traffics Q02233 & Q02239 via existing port at PTN/Cisco Router. 8.Later, decom Existing SM MW Link_ID SW04228 Q02233-Q00592 MW1, 13G_1+0_28MHZ_1024QAM_223M. | Existing SM MW Link_ID SW04228 Q02233-Q00592 MW1, 13G_1+0_28MHZ_1024QAM_223M. MW Swap to new HW MW Link Q02233-Q00592, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom Existing SM MW Link_ID SW04228 Q02233-Q00592 MW1, 13G_1+0_28MHZ_1024QAM_223M. Site Impacted : Q02233 & Q02239. NE_Q02233 1.Install new 18G_1.2M(MDD) x1. 2.New RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Enable port 8-EM6-1 and perform patching to existing BBU. 5.Enable port 8-EM6-2 and perform cascading to LAN 1 of existing IDU SM AGS20(IP Adr: 10.127.212.229). 6.Request new xC Vlan DCN. 7.Migrate traffics Q02233 & Q02239 via new HW MW Link Q02233-Q00592, 18G_2+0_55MHZ_512QAM_EPLA. 8.Later, decom Existing SM MW Link_ID SW04228 Q02233-Q00592 MW1, 13G_1+0_28MHZ_1024QAM_223M. | Existing SM MW Link_ID SW04228 Q02233-Q00592 MW1, 13G_1+0_28MHZ_1024QAM_223M. MW Swap to new HW MW Link Q02233-Q00592, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom Existing SM MW Link_ID SW04228 Q02233-Q00592 MW1, 13G_1+0_28MHZ_1024QAM_223M. Site Impacted : Q02233 & Q02239. FE_Q00592 1.Install new 18G_1.2M(MDD) x1. 2.New RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-5 of new RTN910AF(RTN01) and insert suitable SFP Module 1.25G/1G 1310nm 10Km. 5.Perform cascading between port 8-EM6-5 of new RTN910AF(RTN01) and LAN 5 of existing IDU SM AGS20(IP Adr: 10.127.212.226). 6.Request new xC Vlan DCN. 7.Migrate traffics Q02233 & Q02239 via existing port at PTN/Cisco Router. 8.Later, decom Existing SM MW Link_ID SW04228 Q02233-Q00592 MW1, 13G_1+0_28MHZ_1024QAM_223M. | XMC_5D Pro | MDD | 18G | 18G_1.2M(MDD) x1 | 18G_1.2M(MDD) x1 | Magicell | SQ202601210174-Magicell | Magicell | SQ202604150290-Magicell // SQ202604150306-Magicell |  |  | Ongoing | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26032420 |  | 2026-03-25 | 2026-03-25 | Completed | 2026-03-24 | 2026-03-25 | 2026-03-24 | 2026-03-25 | JOEJI NATAN BIN JAINOL7018000182 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-11 | 2026-04-30 | 2026-04-11 | 2026-04-22 | NURUL NABILAH BINTI ABDUL MUTALIP6000068098 | Magicell TI | 2026-04-11 | 2026-04-30 | 2026-04-11 | 2026-04-13 | MAGICELL SDN BHDWB80039548 | Magicell TI | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-14 | 2026-04-10 | 2026-04-30 | 2026-04-10 | 2026-04-22 | JOEJI NATAN BIN JAINOL7018000182 | 2025-02-05: 2026-04-10; 2025-02-11: 2026-04-30; 2025-02-22: 2026-04-10; 2025-02-22: 2026-04-13 | [7 empty] | GTSB | SQ202509260816-GTSB
9038A_IPR | Ayer Manis | DU00006053166 | Sarawak | Sarawak | 1.188799 | 110.564757 | [7 empty] | 00. Integrated/RFS Done | 24/9/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 10G SFP Module x2. ISM8 x 1. Fiber patch Cord x 1 pairs. | IDU-IPRAN | Site affected : 9038A , 9245A , 9585C. NE_9038A 1.Install new 10G SFP module at existing 9038A_RTN01_GE3 (ID : 20411). 2.Install new 10G SFP module at new Sacofa Port ETH 1-2-1. 3.Install new 3_ISM8-1+0 into existing 9038A_RTN01 (ID: 20411), and transfer the IF cable from 9038A_RTN02 (ID: 24448) to 9038A_RTN01 to carry traffic for the 9245A. 4.Patching Fiber patch cord from 10G 9038A_RTN01_GE3 to new 10G SFP Module Sacofa Port ETH 1-2-1. 5.Disconnect ETH cable at old Sacofa Ports , old Interconnect IDU LAN cable , disable unused port and put proper port labelling. 6.Create service cross connect and migrate entire traffic to new sacofa port ETH 1-2-1. | Site affected : 9038A , 9245A , 9585C. NE_9038A 1.Install new 10G SFP module at existing 9038A_RTN01_GE3 (ID : 20411). 2.Install new 10G SFP module at new Sacofa Port ETH 1-2-1. 3.Install new 3_ISM8-1+0 into existing 9038A_RTN01 (ID: 20411), and transfer the IF cable from 9038A_RTN02 (ID: 24448) to 9038A_RTN01 to carry traffic for the 9245A. 4.Patching Fiber patch cord from 10G 9038A_RTN01_GE3 to new 10G SFP Module Sacofa Port ETH 1-2-1. 5.Disconnect ETH cable at old Sacofa Ports , old Interconnect IDU LAN cable , disable unused port and put proper port labelling. 6.Create service cross connect and migrate entire traffic to new sacofa port ETH 1-2-1. | [6 empty] | Allstar | SQ202509241008-Allstar | Allstar | SQ202509241003-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250922BE |  | 2025-09-23 | 2025-09-24 | Completed | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-09-24 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-24 | 2025-10-01 | 2025-10-13 | 2025-10-13 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-24 | 2025-09-24 | 2025-10-01 | 2025-10-11 | 2025-10-11 | ROYSTON//ANAK RAMSY/6798000228 | 2025-02-05: 2025-09-24; 2025-02-11: 2025-10-01; 2025-02-22: 2025-09-24; 2025-02-22: 2025-09-24 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509260801-GCI | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | CHEONG/SENG/WAH/7018000306
4635A_HU_2 | Kuala Kertil | DU00006088511 | Northern | Kedah | 5.606915 | 100.651200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M NE_4635A. 13G_DP_1.2M(MDD) x1. XMC_5D , Sub A_Lo x1. FE_4946A. 13G_DP_1.2M(MDD) x1. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing link 13G_2+0_28M (4635A_RTN07-4946A_RTN08). Install new parallel link with 13G_2+0_28M , EPLA with existing 13G_2+0_28M. Site Impacted : 4536D , 4057R. NE_4635A. 1.Install new 13G_DP_1.2M(DD). 2.Reuse existing 4635A_RTN07 ( ID : 30289). 3.Install new 3_ISM8-2+0 into existing 4635A_RTN07. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA to become 13G_4+0_28M. 6.Traffic migrate to new parallel link. 7.No link to be decom. FE_4946A. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4946A_RTN08 (ID : 30290). 3.Install new 3_ISM8-2+0 into existing 4946A_RTN08. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA to become 13G_4+0_28M. 6.Traffic migrate to new parallel link. 7.No link to be decom. | Existing link 13G_2+0_28M (4635A_RTN07-4946A_RTN08). Install new parallel link with 13G_2+0_28M , EPLA with existing 13G_2+0_28M. Site Impacted : 4536D , 4057R. NE_4635A. 1.Install new 13G_DP_1.2M(DD). 2.Reuse existing 4635A_RTN07 ( ID : 30289). 3.Install new 3_ISM8-2+0 into existing 4635A_RTN07. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA to become 13G_4+0_28M. 6.Traffic migrate to new parallel link. 7.No link to be decom. | Existing link 13G_2+0_28M (4635A_RTN07-4946A_RTN08). Install new parallel link with 13G_2+0_28M , EPLA with existing 13G_2+0_28M. Site Impacted : 4536D , 4057R. FE_4946A. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4946A_RTN08 (ID : 30290). 3.Install new 3_ISM8-2+0 into existing 4946A_RTN08. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA to become 13G_4+0_28M. 6.Traffic migrate to new parallel link. 7.No link to be decom. | XMC_5D | MDD | 13G | 1.2 | 1.2 | NWAVE | SQ202509260779-N-Wave | NWAVE | SQ202509260770-N-Wave // SQ202509260774-N-Wave | 2025-11-29 | 2025-11-28 | Completed | 2025-09-30 | 2025-10-30 | 2025-09-30 | 2025-09-30 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092678 |  | 2025-09-27 | 2025-09-29 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-10-30 | 2025-09-30 | 2025-10-01 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-09-30 | 2025-10-30 | 2025-09-30 | 2025-10-03 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-03 | 2025-09-30 | 2025-10-30 | 2025-09-30 | 2025-10-08 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2025-02-05: 2025-09-30; 2025-02-11: 2025-10-30; 2025-02-22: 2025-09-30; 2025-02-22: 2025-10-01 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | CHEONG/SENG/WAH/7018000306
4635A_HU_3 | Kuala Kertil | DU00006088512 | Northern | Kedah | 5.606915 | 100.651200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x2. | MW IDU Patching | Site Impacted : 4536D , 4057R. 1. Existing 4635A_RTN03_GE2 ( ID : 41924) , ETH patching to 4635A_RTN07_GE1 ( ID : 30289). 2. Disconnect the existing ETH LAN cable and disable unused port. 3. Create service cross connect and entire traffic migrate to existing MW link at 4946A_RTN08 ( ID : 30290). After parallel link 13G_2+0_28M installed ( Refer DU ID 4635A_HU_2). | NE_4635A 1. Existing 4635A_RTN03_GE2 ( ID : 41924) , ETH patching to 4635A_RTN07_GE1 ( ID : 30289). 2. Disconnect the existing ETH LAN cable and disable unused port. 3. Create service cross connect and entire traffic migrate to existing MW link at 4946A_RTN08 ( ID : 30290). After parallel link 13G_2+0_28M installed ( Refer DU ID 4635A_HU_2). | [6 empty] | NWAVE | SQ202509260779-N-Wave | NWAVE | SQ202509260774-N-Wave | 2025-12-10 | 2025-12-10 | Completed | 2025-09-30 | 2025-10-30 | 2025-09-30 | 2025-09-30 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092679 |  | 2025-09-27 | 2025-09-29 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-01 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-03 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-03 | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-08 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2025-02-05: 2025-10-01; 2025-02-11: 2025-11-01; 2025-02-22: 2025-10-01; 2025-02-22: 2025-10-01 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | CHEONG/SENG/WAH/7018000306
9284A_IPR | Bukit Mas | DU00006106223 | Sarawak | Sarawak | 4.741124 | 115.008812 | [7 empty] | 00. Integrated/RFS Done | 9/10 Pending Planner update EPMS (TX Route and SOW) | TSS+TI | L1+ATP+PAC | 1. ETH LAN Cable x1. | IDU-IPRAN | Perform LAG at CP site for IDU 9284A BUKIT MAS_RTN05 to 9284A-MAC-001 Bukit Mas Impact sites: 9055C,9285A, 9643B. 1) Patch 9284A BUKIT MAS_RTN05 GE2 to new CP port 2) Create LAG | Perform LAG at CP site for IDU 9284A BUKIT MAS_RTN05 to 9284A-MAC-001 Bukit Mas Impact sites: 9055C,9285A, 9643B. 1) Patch 9284A BUKIT MAS_RTN05 GE2 to new CP port 2) Create LAG | [6 empty] | YPTT | SQ202512190118-YPTT | YPTT | SQ202511110829-YPTT | 2025-12-06 | 2025-12-10 | Completed | 2025-11-06 | 2025-11-13 | 2025-11-07 | 2025-11-07 | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110315 |  | 2025-11-04 | 2025-11-24 | Completed | 2025-11-03 | 2025-11-04 | 2025-11-03 | 2025-11-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-19 | 2025-11-20 | 2025-11-19 | 2025-11-24 | JORDAN CHIN ZHEN WOON6794000058 | YPTT TI | 2025-11-25 | 2025-11-25 | 2025-11-06 | 2025-11-06 | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-07 | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-07 | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | 2025-02-05: 2025-11-07; 2025-02-11: 2025-11-08; 2025-02-22: 2025-11-07; 2025-02-22: 2025-11-07 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202510300402-GCI | 2025-10-17 | 2025-10-18 | 2025-10-17 | 2025-10-17 | CHEONG/SENG/WAH/7018000306
Q01380_EB_1 | Q124E_Q01380OD_KGPAYAMEBI | DU00006108237 | Sarawak | Sarawak | 1.407980 | 110.280120 | [9 empty] | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | At FE: - Patching xC SM_ALC+2E link SW03011to xD MW Link IDU 9414A POI Needed : Yes. BBU still E/// | [7 empty] | Allstar | SQ202603180484-Allstar | Allstar | SQ202603180480-Allstar |  |  | Ongoing | 2026-04-22 | 2026-04-27 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030632 |  | 2026-03-07 | 2026-03-31 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-25 | 2026-03-31 | 2026-03-31 | 2026-03-31 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-03-25 | 2026-03-31 | 2026-03-31 | 2026-03-31 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-03-25 | 2026-03-31 | 2026-04-01 | 2026-04-01 | ROYSTON//AHHOLE/6000038561 | 2025-02-05: 2026-03-25; 2025-02-11: 2026-03-31; 2025-02-22: 2026-03-25; 2025-02-22: 2026-03-25 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402
4963B_HU | Ulu | DU00005826245 | Northern | Kedah | 5.444775 | 100.726855 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x 1. | MW IDU Patching | Existing HW link 13G_4+0_28M. 3rd priority , to reroute traffic upon uplink installation completed. Uplink refer to DU ID 4982B_HU (DU Code : DU00005244032) and K00416_HU (DU Code : DU00005832682) Site Impacted : 4963B. FE_4982B 1. ETH LAN Cable Patching from 4982B_RTN03 ( ID : 27994) to new IDU 4982B_RTN910A ,by transfer existing ETH cable from 4982B_RTN03_GE1 (ID : 27994) to New 4982B_RTN910A_GE1. 2.New RTN910A no provide by Ops team/GOP team. 3.New link to be install refer under DU ID 4982B_HU ( DU Code : DU00005244032) & new parallel link refer under DU ID K00416_HU (DU Code : DU00005832682). |  | FE_4982B 1. ETH LAN Cable Patching from 4982B_RTN03 ( ID : 27994) to new IDU 4982B_RTN910A. By transfer existing ETH cable from 4982B_RTN02_GE1 to New 4982B_RTN910A_GE1. | [5 empty] | GTSB | SQ202508040494-GTSB | GTSB | SQ202508040522-GTSB | 2026-01-22 | 2026-01-22 | Completed | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071916 |  | 2025-07-20 | 2025-08-26 | Completed | 2025-07-19 | 2025-07-20 | 2025-07-19 | 2025-08-26 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-26 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-26 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-26 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-02-05: 2025-08-23; 2025-02-11: 2025-08-23; 2025-02-22: 2025-08-23; 2025-02-22: 2025-08-25 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507190085-GCI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | CHEONG/SENG/WAH/7018000306
S01051_EB | S01051_PI MASILAU | DU00005853606 | Sabah | Sabah | 6.012783 | 116.597233 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | need to patch IDU to use xD LL. Need to do POI |  | need to patch IDU to use xD LL. Need to do POI | [5 empty] | NR services | SQ202509300151-NR Services | NR services | SQ202509090323-NR Services | 2025-11-24 | 2025-11-17 | Completed | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-17 | 2025-11-24 | 2025-11-17 | 2025-11-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090208 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-07 | 2025-10-07 | 2025-09-07 | 2025-09-23 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-09-07 | 2025-10-07 | 2025-09-07 | 2025-10-06 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-09-07 | 2025-10-07 | 2025-09-07 | 2025-10-05 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-02-05: 2025-09-07; 2025-02-11: 2025-10-07; 2025-02-22: 2025-09-07; 2025-02-22: 2025-09-23 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507250629-GTSB | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | HSU//MYET CHAE/6799000011
7649B_HU | Seafest Hotel | DU00005870094 | Sabah | Sabah | 4.478526 | 118.617523 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M_512QAM_EPLA NE_7649B New 23G_DP_0.6M(MAC)+OMT x1. New RTN910AF(RTN01). New ISM8 x1. New XMC_3E, Sub B_Lo x2. New CAT6 cables 2x2. FE_7209A New 23G_DP_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN10). New XMC_3E, Sub B_Hi x2. | MW Swap | ****IMPORTANT NOTE: 1.ENSURE SPACING AVAILABLE TO MOUNT NEW ANTENNA 0.6M/1.2M AT NE & FE. 2.NEED TO APPLY CRQ AS CHILD SITE IS EB 7801E. 3.NEED TO IMPLEMENT SIMULTANEOUSLY DU 7649B_HU & DU 7649B_HU_1 BY SAME TEAM/SUB CON. 4.LATER REFER DU 7649B_HU_1 FOR TX SOW**** Existing HW MW link 18G_1+0_112M(1st HW MW Parallel Link). Swap existing link to new HW MW Link 23G_2+0_112M_EPLA. Later, decom existing 18G ODU & Antenna ONLY of existing HW MW link 18G_1+0_112M. Do not decom RTN910AF at NE & FE. Site Impacted : 7649B, 7230C, 7801E, 7360A & 7213R. NE_7649B 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub B_Lo x2. Build new HW MW Link 23G_2+0_112M_EPLA. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01). 5.Shifting BBU 7649A from port 8-EM6-1 of existing RTN910AF(RTN03) to port 8-EM6-1 of new RTN910AF(RTN01). 6.Enable port 8-EM6-2 of new RTN910AF(RTN01). 7.Cascading port 8-EM6-2 of new RTN910AF(RTN01) to port 8-EM6-1 of existing RTN910AF(RTN03). 8.Proceed with 2nd DU 7649B_HU_1 & refer TX SOW. 9.Later, decom existing 18G ODU & Antenna ONLY of existing HW MW link 18G_1+0_112M. Do not decom RTN910AF at NE & FE. FE_7209A 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Reuse existing RTN910AF(RTN10). 3.Install new XMC_3E, Sub B_Lo x2. 4.Reuse existing ISM8 Slot 07 Port 1 & 2. Build new HW MW Link 23G_2+0_112M_EPLA. 5.Reuse existing Vlan DCN & Vlan Services. 6.Re-use existing xD existing 3x IBeam port. 7.Proceed with 2nd DU 7649B_HU_1 & refer TX SOW. 8.Later, decom existing 18G ODU & Antenna ONLY of existing HW MW link 18G_1+0_112M. Do not decom RTN910AF at NE & FE. | ****IMPORTANT NOTE: 1.ENSURE SPACING AVAILABLE TO MOUNT NEW ANTENNA 0.6M/1.2M AT NE & FE. 2.NEED TO APPLY CRQ AS CHILD SITE IS EB 7801E. 3.NEED TO IMPLEMENT SIMULTANEOUSLY DU 7649B_HU & DU 7649B_HU_1 BY SAME TEAM/SUB CON. 4.LATER REFER DU 7649B_HU_1 FOR TX SOW**** Existing HW MW link 18G_1+0_112M(1st HW MW Parallel Link).. Swap existing link to new HW MW Link 23G_2+0_112M_EPLA. Later, decom existing 18G ODU & Antenna ONLY of existing HW MW link 18G_1+0_112M. Do not decom RTN910AF at NE & FE. Site Impacted : 7649B, 7230C, 7801E, 7360A & 7213R. NE_7649B 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub B_Lo x2. Build new HW MW Link 23G_2+0_112M_EPLA. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01). 5.Shifting BBU 7649A from port 8-EM6-1 of existing RTN910AF(RTN03) to port 8-EM6-1 of new RTN910AF(RTN01). 6.Enable port 8-EM6-2 of new RTN910AF(RTN01). 7.Cascading port 8-EM6-2 of new RTN910AF(RTN01) to port 8-EM6-1 of existing RTN910AF(RTN03). 8.Proceed with 2nd DU 7649B_HU_1 & refer TX SOW. 9.Later, decom existing 18G ODU & Antenna ONLY of existing HW MW link 18G_1+0_112M. Do not decom RTN910AF at NE & FE. | ****IMPORTANT NOTE: 1.ENSURE SPACING AVAILABLE TO MOUNT NEW ANTENNA 0.6M/1.2M AT NE & FE. 2.NEED TO APPLY CRQ AS CHILD SITE IS EB 7801E. 3.NEED TO IMPLEMENT SIMULTANEOUSLY DU 7649B_HU & DU 7649B_HU_1 BY SAME TEAM/SUB CON. 4.LATER REFER DU 7649B_HU_1 FOR TX SOW**** Existing HW MW link 18G_1+0_112M(1st HW MW Parallel Link).. Swap existing link to new HW MW Link 23G_2+0_112M_EPLA. Later, decom existing 18G ODU & Antenna ONLY of existing HW MW link 18G_1+0_112M. Do not decom RTN910AF at NE & FE. Site Impacted : 7649B, 7230C, 7801E, 7360A & 7213R. FE_7209A 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Reuse existing RTN910AF(RTN10). 3.Install new XMC_3E, Sub B_Lo x2. 4.Reuse existing ISM8 Slot 07 Port 1 & 2. Build new HW MW Link 23G_2+0_112M_EPLA. 5.Reuse existing Vlan DCN & Vlan Services. 6.Re-use existing xD existing 3x IBeam port. 7.Proceed with 2nd DU 7649B_HU_1 & refer TX SOW. 8.Later, decom existing 18G ODU & Antenna ONLY of existing HW MW link 18G_1+0_112M. Do not decom RTN910AF at NE & FE. | XMC_3E | MAC | 23G | 23G_0.6M(MAC)+OMT x1. | 23G_0.6M(MAC)+OMT x1. | Seri Pancar | SQ202602090132-Seri Pancar | NR services | SQ202602270361-NR Services // SQ202602270364-NR Services |  |  | Ongoing | 2026-02-04 | 2026-02-28 | 2026-02-06 | 2026-02-06 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-16 | 2026-03-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26021414 |  | 2026-02-15 | 2026-02-16 | Completed | 2026-02-14 | 2026-02-15 | 2026-02-14 | 2026-02-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-27 | 2026-03-21 | 2026-02-27 | 2026-02-27 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-27 | 2026-03-21 | 2026-02-27 | 2026-02-28 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-03-01 | 2026-02-27 | 2026-03-21 | 2026-02-27 | 2026-03-09 | RALPH O'BRYAN HILARY7167000030 | 2026-02-27 | 2026-03-21 | 2026-02-27 | 2026-02-28 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507250629-GTSB
9566C_HU | Baladdin (REL) | DU00005870095 | Sarawak | Sarawak | 1.631781 | 111.204366 | [6 empty] | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Last mile site, already existing 6+0 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507250636-GTSB | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | HSU//MYET CHAE/6799000011
9038B_HU | Simunjan 2 | DU00005870096 | Sarawak | Sarawak | 1.383822 | 110.760558 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_0.6/0.6_DP_MAC 2xISM8 4xXMC-3_SB A,B | MW Swap | MW SWAP 9038B-9056A WITH 23G_2+0_0.6/0.6_128QAM_EPLA | MW SWAP 9038B-9056A WITH 23G_2+0_0.6/0.6_128QAM_EPLA NE: 1. Reuse existing RTN910A_RTN02 2. Install new ISM8 at slot 3. 3. Swap exisitng ODU with XMC-3_SB A,B. 4. Swap existing antenna with 23G_0.6m 5. Configure 23G_2+0_0.6/0.6_MAC_EPLA | MW SWAP 9038B-9056A WITH 23G_2+0_0.6/0.6_128QAM_EPLA FE: 1. Reuse existing RTN910A_RTN02 2. Install new ISM8 at slot 3. 3. Swap exisitng ODU with XMC-3_SB A,B. 4. Swap existing antenna with 23G_0.6m 5. Configure 23G_2+0_0.6/0.6_MAC_EPLA | XMC-3 SB A,B |  | 23 | 0.6 | 0.6 | Magicell | SQ202509030212-Magicell | GTSB | SQ202509040325-GTSB // SQ202509040348-GTSB | 2025-11-28 | 2025-11-22 | Completed | 2025-09-03 | 2025-09-30 | 2025-10-31 | 2025-10-31 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-19 | 2025-11-12 | 2025-11-12 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-21 | 2025-11-28 | 2025-11-21 | 2025-11-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082515 |  | 2025-08-26 | 2025-09-25 | Completed | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-09-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-06 | 2025-11-30 | 2025-11-06 | 2025-11-08 | JAKLY CLAMEN//JONLEY/6000055922 | GTSB TI | 2025-11-06 | 2025-11-30 | 2025-11-06 | 2025-12-09 | JAKLY CLAMEN//JONLEY/6000055922 | GTSB TI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-08 | 2025-11-06 | 2025-11-30 | 2025-11-06 | 2025-12-09 | JAKLY CLAMEN//JONLEY/6000055922 | 2025-02-05: 2025-11-06; 2025-02-11: 2025-11-30; 2025-02-22: 2025-11-06; 2025-02-22: 2025-11-07 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507250636-GTSB | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | HSU//MYET CHAE/6799000011
4537D_HU_1 | Kg Teluk Jamat | DU00005870097 | Northern | Kedah | 6.135998 | 100.453076 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M. NE_4537D 15G_DP_1.2M(MDD) x1. ISM8 x1. XMC_5D , Sub B Hi x1. FE_4678A. 15G_DP_1.2M(MDD) x1. ISM8 x1. XMC_5D , Sub B Lo x1. | MW Parallel Link | Existing link 15G_2+0_28M Install parallel link 15G_2+0_28M. Site Impacted : 4537D. NE_4537D 1.Install 15G_DP_1.2M(MDD). 2.Reuse existing 4537D_RTN01 (ID : 36125). 3.Install new 3_ISM8-2+0 into existing 4537D_RTN01 (ID : 36125). 4.Install new XMC_5D , Sub B Hi. 5.Create service cross connect & EPLA new and existing link. 6.No link to be decom. FE_4678A. 1.Install 15G_DP_1.2M(MDD). 2.Reuse existing 4678A_RTN22 (ID : 36126). 3.Install new 3_ISM8-2+0 into existing 4678A_RTN22 (ID: 36126). 4.Install new XMC_5D , Sub B Lo. 5.Create service cross connect & EPLA new and existing link. 6.No link to be decom. | Existing link 15G_2+0_28M Install parallel link 15G_2+0_28M. Site Impacted : 4537D. NE_4537D 1.Install 15G_DP_1.2M(MDD). 2.Reuse existing 4537D_RTN01 (ID : 36125). 3.Install new 3_ISM8-2+0 into existing 4537D_RTN01 (ID : 36125). 4.Install new XMC_5D , Sub B Hi. 5.Create service cross connect & EPLA new and existing link. 6.No link to be decom. | Existing link 15G_2+0_28M Install parallel link 15G_2+0_28M. Site Impacted : 4537D. FE_4678A. 1.Install 15G_DP_1.2M(MDD). 2.Reuse existing 4678A_RTN22 (ID : 36126). 3.Install new 3_ISM8-2+0 into existing 4678A_RTN22 (ID: 36126). 4.Install new XMC_5D , Sub B Lo. 5.Create service cross connect & EPLA new and existing link. 6.No link to be decom. | XMC_5D | MDD | 15G | 1.2M | 1.2M | Magicell | SQ202508060640-Magicell | Magicell | SQ202508060644-Magicell // SQ202508060648-Magicell | 2025-11-29 | 2025-12-03 | Completed | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-03 | 2025-09-04 | 2025-09-03 | 2025-09-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082134 |  | 2025-08-22 | 2025-08-25 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-05 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | AKMAL//BIN RAZALI/6794000078 |  | 2025-09-25 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-13 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-02-05: 2025-09-23; 2025-02-11: 2025-09-23; 2025-02-22: 2025-09-23; 2025-02-22: 2025-10-06 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507250560-GCI | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | CHEONG/SENG/WAH/7018000306
4261B_HU | TUALANG | DU00005870098 | Northern | Kedah | 6.117703 | 100.476047 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | DU ID 4261B_HU is 100% HU due to the impact on two child sites : 4049R & 4700D. The plan is to perform load balancing by install a new link / reroute child site 4700D. Refer to the following DU ID for the new link / reroute : 1. 4700D_AD ( DU Code : DU00005933947). 2. 4958A_AD ( DU Code : DU00005933948). 3. 4260B_AD (Cancel / Drop ). | DU ID 4261B_HU is 100% HU due to the impact on two child sites : 4049R & 4700D. The plan is to perform load balancing by install a new link / reroute child site 4700D. Refer to the following DU ID for the new link / reroute 1. 4700D_AD ( DU Code : DU00005933947). 2. 4958A_AD ( DU Code : DU00005933948). 3. 4260B_AD (Cancel / Drop ). | DU ID 4261B_HU is 100% HU due to the impact on two child sites : 4049R & 4700D. The plan is to perform load balancing by install a new link / reroute child site 4700D. Refer to the following DU ID for the new link / reroute 1. 4700D_AD ( DU Code : DU00005933947). 2. 4958A_AD ( DU Code : DU00005933948). 3. 4260B_AD (Cancel / Drop ). | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202507250560-GCI | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | CHEONG/SENG/WAH/7018000306
9972A_HU | Taman Tunku 2 | DU00005870099 | Sarawak | Sarawak | 4.310596 | 113.993255 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE FROM 256QAM_112MHZ TO 512QAM_112MHZ_889MBPS | MW REMOTE UPGRADE FROM 256QAM_112MHZ TO 512QAM_112MHZ_889MBPS NE: Reuse equipment. Remote software upgrade from 256QAM to 23G_1+0_512QAM_889M | MW REMOTE UPGRADE FROM 256QAM_112MHZ TO 512QAM_112MHZ_889MBPS FE: Reuse equipment. Remote software upgrade from 256QAM to 23G_1+0_512QAM_889M | [7 empty] | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507250636-GTSB | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | HSU//MYET CHAE/6799000011
4403B_HU_1 | Simpang Dua Manjung-100Q4 | DU00005870100 | Northern | Perak | 4.200910 | 100.723720 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_4403B New 18G_1.2M(MDD) x1. Reuse existing RTN910A(RTN01). New XMC_5D, Sub A_Hi x1. New IF cable for 2nd channel(Horizontal) with suitable length. FE_4300B New 18G_0.6M(MDD) x1. Reuse existing RTN910A(RTN01). New XMC_5D, Sub A_Lo x1. New IF cable for 2nd channel(Horizontal) with suitable length. | MW Swap | Link Existing HW 18G_1+0_112M_512QAM. Swap existing link to new HW 18G_2+0_112M_512QAM_EPLA. Site Impacted : 4403B. NE_4403B 1.Install new 18G_1.2M(MDD). 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_5D , Sub A_Hi. Configure new HW 18G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and migrate RAN traffic to new MW link. 5.Later, decom existing HW 18G_1+0_112M_512QAM but decom existing ODU 18G and existing antenna 18G(1.2m-SP) ONLY. Do not decom RTN910A(RTN01). FE_4300B 1.Install new 18G_0.6M(MDD). 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_5D , Sub A_Lo. Configure new HW 18G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and existing port at IBeam. 5.Later, decom existing HW 18G_1+0_112M_512QAM but decom existing ODU 18G and existing antenna 18G(0.6m-SP) ONLY. Do not decom RTN910A(RTN01). | Link Existing HW 18G_1+0_112M_512QAM. Swap existing link to new HW 18G_2+0_112M_512QAM_EPLA. Site Impacted : 4403B. NE_4403B 1.Install new 18G_1.2M(MDD). 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_5D , Sub A_Hi. Configure new HW 18G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and migrate RAN traffic to new MW link. 5.Later, decom existing HW 18G_1+0_112M_512QAM but decom existing ODU 18G and existing antenna 18G(1.2m-SP) ONLY. Do not decom RTN910A(RTN01). | Link Existing HW 18G_1+0_112M_512QAM. Swap existing link to new HW 18G_2+0_112M_512QAM_EPLA. Site Impacted : 4403B. FE_4300B 1.Install new 18G_0.6M(MDD). 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_5D , Sub A_Lo. Configure new HW 18G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and existing port at IBeam. 5.Later, decom existing HW 18G_1+0_112M_512QAM but decom existing ODU 18G and existing antenna 18G(0.6m-SP) ONLY. Do not decom RTN910A(RTN01). | XMC_5D | D) x1. MDD | 18G | 18G_1.2M(MDD) x1. | 18G_0.6M(MDD) x1. | MTK | SQ202509300141-MTK | MTK | SQ202510150288-MTK // SQ202510150292-MTK | 2026-01-28 | 2026-02-03 | Completed | 2025-10-10 | 2025-10-24 | 2025-10-10 | 2025-10-29 | AMIRUL SYAHRINI BIN MOHD ZIN6000023342 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-30 | 2025-11-06 | 2025-10-30 | 2025-10-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-02-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251001B2 |  | 2025-10-03 | 2025-10-09 | Completed | 2025-10-02 | 2025-10-03 | 2025-10-01 | 2025-10-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-10 | 2025-10-24 | 2025-10-10 | 2025-10-15 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-10-10 | 2025-10-24 | 2025-10-10 | 2025-11-26 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-11 | 2025-10-10 | 2025-10-24 | 2025-10-18 | 2025-11-24 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-02-05: 2025-10-10; 2025-02-11: 2025-10-24; 2025-02-22: 2025-10-18; 2025-02-22: 2025-11-25 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202507250622-GTSB
7512A_HU_1 | Morisem | DU00005870101 | Sabah | Sabah | 5.504748 | 118.395624 |  |  |  |  | No space for Parallel Link |  |  | 03. Pending TSS |  | TSS+AA+TI |  | 13G_4+0_28M_256QAM_CA NE_7512A New 13G_1.2M(MDD) x1. New RTN910A(RTN15). New ISM8 x1. New XMC_5D Pro, Sub A_Lo x1. New IF cables with suitable length x2 RUN. FE_7585A New 13G_1.2M(MDD) x1. New RTN910A(RTN15). New ISM8 x1. New XMC_5D Pro, Sub A_Hi x1. New IF cables with suitable length x2 RUN. New Fiber SFP Module 1G 10Km 1310nm x2.(at IDU and IBeam) New Fiber patch cord with suitable type and length x1pair. | MW Parallel Link | **IMPORTANT NOTE:** 1. Mandatory to perform physical Frequency Scanning for 13G & 15G. Priority 13G if "NO" channel available then proceed for 15G. 2. Once free channel available(must be 4 Channels available) for 13G or 15G(if 13G channel not available), later mandatory to perform TSS especially to find available spacing for mounting 1x1.2m per site. 3. PM need to trigger CD/GOP for CRQ and obtain approval first before perform load balancing task as many child sites(EB) will impacted. Build new HW MW Link 7512A(RTN15)-7585A(RTN02), 13G_4+0_28MHZ_256QAM_772M_CA. Site Impacted : 7743E, 7703E, 7629E, 7704E, 7630E,7670E, 7749E & 7676E. NE_7512A 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910A(RTN15) x1 and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Enable port 8-EM6-1 of new RTN910AF(RTN15). 6.Disconnect cascading at RTN08 at 7512A for port 8-EM6-1(to RTN04) and port 8-EM6-2(to RTN10) and disable both port. 7.Immediate perform re-cascading between port 8-EM6-1(at RTN04) and port 8-EM6-2(at RTN10). To avoid losscomm and outage for existing sites 7749E & 7676E. 8.Enable port 8-EM6-1 of existing RTN910A(RTN08). 9.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN15) and port 8-EM6-1 of existing RTN910A(RTN08). 10.Re-use existing Vlan services for EB sites 7743E, 7703E, 7629E, 7704E, 7630E &7670E. 11.Migrate traffic for EB sites 7743E, 7703E, 7629E, 7704E, 7630E &7670E to new IBeam port(request from ZTE IPRAN team) via new HW MW Link 7512A(RTN15)-7585A(RTN02), 13G_4+0_28MHZ_256QAM_772M_CA. FE_7585A 1.Install new 13G_1.2M(MDD) x1 2.Install new RTN910A(RTN02) x1 and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Enable port 8-EM6-5 of new RTN910AF(RTN02) and insert Fiber SFP Module 1G 10Km 1310nm. 6.Request new IBeam port from ZTE IPRAN team and insert Fiber SFP Module 1G 10Km 1310nm. 7.Patching Fiber patch cord between port 8-EM6-4 of new RTN910AF(RTN02) and new IBeam port. 8.Re-use existing Vlan services for EB sites 7743E, 7703E, 7629E, 7704E, 7630E &7670E. 9.Migrate traffic for EB sites 7743E, 7703E, 7629E, 7704E, 7630E &7670E to new IBeam port(request from ZTE IPRAN team). | **IMPORTANT NOTE:** 1. Mandatory to perform physical Frequency Scanning for 13G & 15G. Priority 13G if "NO" channel available then proceed for 15G. 2. Once free channel available(must be 4 Channels available) for 13G or 15G(if 13G channel not available), later mandatory to perform TSS especially to find available spacing for mounting 1x1.2m per site. 3. PM need to trigger CD/GOP for CRQ and obtain approval first before perform load balancing task as many child sites(EB) will impacted. Build new HW MW Link 7512A(RTN15)-7585A(RTN02), 13G_4+0_28MHZ_256QAM_772M_CA. Site Impacted : 7743E, 7703E, 7629E, 7704E, 7630E,7670E, 7749E & 7676E. NE_7512A 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910A(RTN15) x1 and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Enable port 8-EM6-1 of new RTN910AF(RTN15). 6.Disconnect cascading at RTN08 at 7512A for port 8-EM6-1(to RTN04) and port 8-EM6-2(to RTN10) and disable both port. 7.Immediate perform re-cascading between port 8-EM6-1(at RTN04) and port 8-EM6-2(at RTN10). To avoid losscomm and outage for existing sites 7749E & 7676E. 8.Enable port 8-EM6-1 of existing RTN910A(RTN08). 9.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN15) and port 8-EM6-1 of existing RTN910A(RTN08). 10.Re-use existing Vlan services for EB sites 7743E, 7703E, 7629E, 7704E, 7630E &7670E. 11.Migrate traffic for EB sites 7743E, 7703E, 7629E, 7704E, 7630E &7670E to new IBeam port(request from ZTE IPRAN team) via new HW MW Link 7512A(RTN15)-7585A(RTN02), 13G_4+0_28MHZ_256QAM_772M_CA. | **IMPORTANT NOTE:** 1. Mandatory to perform physical Frequency Scanning for 13G & 15G. Priority 13G if "NO" channel available then proceed for 15G. 2. Once free channel available(must be 4 Channels available) for 13G or 15G(if 13G channel not available), later mandatory to perform TSS especially to find available spacing for mounting 1x1.2m per site. 3. PM need to trigger CD/GOP for CRQ and obtain approval first before perform load balancing task as many child sites(EB) will impacted. Build new HW MW Link 7512A(RTN15)-7585A(RTN02), 13G_4+0_28MHZ_256QAM_772M_CA. Site Impacted : 7743E, 7703E, 7629E, 7704E, 7630E,7670E, 7749E & 7676E. FE_7585A 1.Install new 13G_1.2M(MDD) x1 2.Install new RTN910A(RTN02) x1 and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Enable port 8-EM6-5 of new RTN910AF(RTN02) and insert Fiber SFP Module 1G 10Km 1310nm. 6.Request new IBeam port from ZTE IPRAN team and insert Fiber SFP Module 1G 10Km 1310nm. 7.Patching Fiber patch cord between port 8-EM6-4 of new RTN910AF(RTN02) and new IBeam port. 8.Re-use existing Vlan services for EB sites 7743E, 7703E, 7629E, 7704E, 7630E &7670E. 9.Migrate traffic for EB sites 7743E, 7703E, 7629E, 7704E, 7630E &7670E to new IBeam port(request from ZTE IPRAN team). | XMC_5D Pro | MDD | 13G | 13G_1.2M(MDD) x1 | 13G_1.2M(MDD) x1 | Seri Pancar | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507250629-GTSB
1446H_LOS | 99 Speedmart BDR PUTERA | DU00005870102 | Central | Selangor | 2.996470 | 101.490852 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS Radio NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH LAN Cable x1. FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH LAN Cable x1. | MW New Link / Reroute | Cambium link reroute to new FE 1014K/B00363 due to existing FE being LOS Block. Swap to NLOS with new FE routing 1014K/B00363. Site Impacted : 1446H NE_1446H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing Cambium radio (1446H-NLOS-3659B). FE_1410K/B00363. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new Inband DCN. 5.Traffic migrate to new route FE and with new NLOS. 6.ETH cable patching to Cisco PTN new Port Gi 0/0/22 (70632-TMJLNKEBUN-ACC1).. 7.Decom existing Cambium Radio (3659B-NLOS-1446H). | Cambium link reroute to new FE 1014K/B00363 due to existing FE being LOS Block. Swap to NLOS with new FE routing 1014K/B00363. Site Impacted : 1446H NE_1446H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing Cambium radio (1446H-NLOS-3659B). | Cambium link reroute to new FE 1014K/B00363 due to existing FE being LOS Block. Swap to NLOS with new FE routing 1014K/B00363. Site Impacted : 1446H FE_1410K/B00363. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new Inband DCN. 5.Traffic migrate to new route FE and with new NLOS. 6.ETH cable patching to Cisco PTN new Port Gi 0/0/22 (70632-TMJLNKEBUN-ACC1).. 7.Decom existing Cambium Radio (3659B-NLOS-1446H). | [5 empty] | GTSB | SQ202507230726-GTSB | GTSB | SQ202508200506-GTSB // SQ202508200516-GTSB | 2025-08-27 | 2025-08-20 | Completed | 2025-08-13 | 2025-08-27 | 2025-08-13 | 2025-08-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-27 | 2025-08-13 | 2025-08-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081209 |  | 2025-08-16 | 2025-08-20 | Completed | 2025-08-15 | 2025-08-16 | 2025-08-15 | 2025-08-20 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-06 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-10-29 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-06 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-10-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-02-05: 2025-09-03; 2025-02-11: 2025-09-03; 2025-02-22: 2025-09-03; 2025-02-22: 2025-09-04 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507250548-GCI | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | CHEONG/SENG/WAH/7018000306
K00119_IPR_1 | K009A_K00119OD_JKRKUALANERANG | DU00005871000 | Northern | Kedah | 6.251197 | 100.614711 | [7 empty] | 00. Integrated/RFS Done | 24/07: DO done | TSS+TI | L1+ATP+PAC | 1X LAN Cable | MW IDU Patching | Split traffic at NT05603 K00119-K00334 MW1 LAN6 to PTN 60087-JKRKUALANERANG-ACC1.celcom.com.my/GigabitEthernet0/0/2 Patch IDU SM NT05603 K00119-K00334 MW1 new port to new PTN 60087-JKRKUALANERANG port and transfer traffic from sites below: 1) K00807 T3_KAMPUNG_LUBUK_RAMBAI | Split traffic at NT05603 K00119-K00334 MW1 LAN6 to PTN 60087-JKRKUALANERANG-ACC1.celcom.com.my/GigabitEthernet0/0/2 Patch IDU SM NT05603 K00119-K00334 MW1 new port to new PTN 60087-JKRKUALANERANG port and transfer traffic from sites below: 1) K00807 T3_KAMPUNG_LUBUK_RAMBAI | N/A | [5 empty] | CCSMY | SQ202512170154-CCS | CCSMY | SQ202507290113-CCS |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25072402 |  | 2025-07-25 | 2025-07-30 | Completed | 2025-07-24 | 2025-07-25 | 2025-07-24 | 2025-07-30 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-14 | 2025-08-31 | 2025-08-14 | 2025-09-18 | CHEN TAK//EOH YANG/7021000004 | CCS TI | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | CHEN TAK//EOH YANG/7021000004 | CCS TI | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | AKMAL//BIN RAZALI/6794000078 |  | 2025-11-20 | 2025-08-14 | 2025-08-31 | 2025-08-14 | 2025-10-05 | CHEN TAK//EOH YANG/7021000004 | 2025-02-05: 2025-08-14; 2025-02-11: 2025-08-31; 2025-02-22: 2025-08-14; 2025-02-22: 2025-08-14 |  |  | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507250560-GCI | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
7440B_IPR | Pin Besar SBC | DU00005871001 | Sabah | Sabah | 5.355435 | 117.932900 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | ETH LAN Cable x 1 | IDU-IPRAN | Perform LAG at CP site for IDU 7440B PIN BESAR SBC RTN05 to 7440B-MAC-001 NE_7740B_RTN05 (ID : 43905) 1) Patch RTN05 GE2 to new CP port 2) Create LAG 3) Impact sites: 7654E,7655E,7645E,7687E,7692E,7461B,7491B,S01624 remarks: child sites involving EB sites | NE_7740B_RTN05 (ID : 43905) 1) Patch RTN05 GE2 to new CP port 2) Create LAG 3) Impact sites: 7654E,7655E,7645E,7687E,7692E,7461B,7491B,S01624 | [6 empty] | NR services | SQ202509300151-NR Services | NR services | SQ202509090323-NR Services | 2025-11-11 | 2025-11-10 | Completed | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-03 | 2025-10-04 | 2025-10-03 | 2025-10-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-03 | 2025-10-04 | 2025-10-03 | 2025-10-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090206 |  | 2025-09-03 | 2025-09-03 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-03 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-28 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-10-02 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-06 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-06 | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-10-09 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-02-05: 2025-09-26; 2025-02-11: 2025-10-26; 2025-02-22: 2025-09-26; 2025-02-22: 2025-09-27 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507250599-GCI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | CHEONG/SENG/WAH/7018000306
9199A_IPR | Kabong Bazaar | DU00005871002 | Sarawak | Sarawak | 1.803335 | 111.116450 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 29/8/2025 : Cutover done 26/8/2025 : Plan to do BBU Patching - cancel proceed | TSS+AA+TI | L1+ATP+PAC |  | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) Impact site: 9199A | [7 empty] | NR Services | SQ202508040512-NR Services | NR Services | SQ202508040535-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25080515 |  | 2025-08-06 | 2025-08-14 | Completed | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-14 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-17 | 2025-09-18 | 2025-09-17 | 2025-09-17 | MAN BIN HARUN7167000009 | NR Service TI | 2025-09-10 | 2025-09-15 | 2025-09-10 |  |  |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-29 | [15 empty] | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507250636-GTSB | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | HSU//MYET CHAE/6799000011
2684A20_EVT | PBTS KG.MATUPANG | DU00005882668 | Sabah | Sabah | 5.793560 | 116.820122 | [13 empty] | Planning and integration support only for event site 2684A20 Tx route: 2684A20/2684A20-S00567-S00383-S00566 1) Share port at 20196-NALAPAK-ACC1 GigabitEthernet0/0/1 2) New NE ID NE IDU 2684A20 RTN01 3) New NE ID FE IDU 7115R/S00567 RTN02 4) At far end S00567 patch new IDU [7115R/S00567 RTN02] GE1 to existing IDU [7115R/S00567_KG SAGINDAI BARU - 7119R/S00383_KG NABUTAN] GE2 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
4622B_HU | SikTown | DU00006643861 | Northern | Kedah | 5.820505 | 100.742662 | [7 empty] | 05. Doable |  | TSS+TI | L1+ATP+PAC | ETH Cat 6 Cable x1. | MW IDU Patching | Patch IDU 4622B-RTN04 (xD) to 4622B_SIK TOWN-4439K/K00420_SIK RTM (xC) Migrate sites 4124R,4125R to new route. Site Impacted : 4124R , 4125R. NE_4622B 1. ETH Patching from 4622B_RTN04_GE1 ( ID : 30070) to 4622B_RTN01_GE 2 ( ID : 13843). Tx route before: 4124R-4622B-4623B 4125R-4622B-4623B Tx route after: 4124R-4622B-K00420 4125R-4622B-K00420 | Patch IDU 4622B-RTN04 (xD) to 4622B_SIK TOWN-4439K/K00420_SIK RTM (xC) Migrate sites 4124R,4125R to new route. Site Impacted : 4124R , 4125R. NE_4622B 1. ETH Patching from 4622B_RTN04_GE1 ( ID : 30070) to 4622B_RTN01_GE 2 ( ID : 13843). Tx route before: 4124R-4622B-4623B 4125R-4622B-4623B Tx route after: 4124R-4622B-K00420 4125R-4622B-K00420 | [6 empty] | GCI | SQ202603130699-GCI | GCI | SQ202603130696-GCI |  |  | Ongoing | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031073 |  | 2026-04-30 | 2026-04-20 | Completed | 2026-04-20 | 2026-04-30 | 2026-04-20 | 2026-04-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-20 | 2026-04-30 | 2026-04-20 | 2026-04-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2026-04-20 | 2026-04-30 | 2026-04-20 | 2026-04-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-09 | 2026-04-07 | 2026-04-30 | 2026-04-07 | 2026-04-20 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-02-05: 2026-04-07; 2025-02-11: 2026-04-30; 2025-02-22: 2026-04-07; 2025-02-22: 2026-04-07 | [7 empty] | GCI | SQ202603170124-GCI | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | CHEONG/SENG/WAH/7018000306
2684A20_HU | pBTSKg Matupang | DU00006643862 | Sabah | Sabah | 5.793952 | 116.818765 | [7 empty] | 03. Pending TSS |  | TSS+AA+TI+Dismantle |  | 18G_2+0_110M_128QAM_EPLA NE_2684A20 New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 16-17131). New XMC_5D Pro, Sub A_Lo x1. New ISM8 x1. New IF cables with suitable length and type x2 RUN. FE_S00567 New 18G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 16-27131). New XMC_5D Pro, Sub A_Hi x1. New ISM8 x1. New IF cables with suitable length and type x2 RUN. | MW Swap | ****IMPORTANT NOTE: 1.NEED TO UPGRADE UPLINK HW MW LINK 7119R/S00383-S00566, 18G_1+0_110MHZ_2048QAM_1047M. CURRENT MAX UTILIZATION ~65%. 2.NEED TO UPGRADE UPLINK HW MW LINK 7128P/S00567-7119R/S00383, 15G_2+0_28MHZ_1024QAM_488M. CURRENT MAX UTILIZATION ~100%. Existing HW MW Link 2684A20-S00567, 18G_1+0_55MHZ_128QAM. Swap existing with HW MW Link 2684A20-S00567, 18G_2+0_110MHZ_128QAM_EPLA. Later, may decom ODU and Antenna ONLY for existing HW MW Link 2684A20-S00567, 18G_1+0_55MHZ_128QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 16-17131) at NE and existing RTN910AF(RTN02, NEID 16-27131) at FE. Site Impacted : 2684A20. NE_2684A20 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 16-17131) and insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN01, NEID 16-17131) ISM8 slot 03 Port 1 & 2 . Build new HW MW Link 18G_2+0_110MHZ_128QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Migrate traffic 2684A20 to new HW MW Link 18G_2+0_110MHZ_128QAM_EPLA. 6.Later, may decom ODU and Antenna ONLY for existing HW MW Link 2684A20-S00567, 18G_1+0_55MHZ_128QAM. Anyway, do not decom RTN910AF(RTN01, NEID 16-17131) at NE and existing RTN910AF(RTN02, NEID 16-27131) at FE. FE_S00567 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 16-27131) and insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN02, NEID 16-27131) ISM8 slot 03 Port 1 & 2 . Build new HW MW Link 18G_2+0_110MHZ_128QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Migrate traffic 2684A20 to existing port at PTN/Cisco S00566. 6.Later, may decom ODU and Antenna ONLY for existing HW MW Link 2684A20-S00567, 18G_1+0_55MHZ_128QAM. Anyway, do not decom RTN910AF(RTN01, NEID 16-17131) at NE and existing RTN910AF(RTN02, NEID 16-27131) at FE. | Existing HW MW Link 2684A20-S00567, 18G_1+0_55MHZ_128QAM. Swap existing with HW MW Link 2684A20-S00567, 18G_2+0_110MHZ_128QAM_EPLA. Later, may decom ODU and Antenna ONLY for existing HW MW Link 2684A20-S00567, 18G_1+0_55MHZ_128QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 16-17131) at NE and existing RTN910AF(RTN02, NEID 16-27131) at FE. Site Impacted : 2684A20. NE_2684A20 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 16-17131) and insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN01, NEID 16-17131) ISM8 slot 03 Port 1 & 2 . Build new HW MW Link 18G_2+0_110MHZ_128QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Migrate traffic 2684A20 to new HW MW Link 18G_2+0_110MHZ_128QAM_EPLA. 6.Later, may decom ODU and Antenna ONLY for existing HW MW Link 2684A20-S00567, 18G_1+0_55MHZ_128QAM. Anyway, do not decom RTN910AF(RTN01, NEID 16-17131) at NE and existing RTN910AF(RTN02, NEID 16-27131) at FE. | Existing HW MW Link 2684A20-S00567, 18G_1+0_55MHZ_128QAM. Swap existing with HW MW Link 2684A20-S00567, 18G_2+0_110MHZ_128QAM_EPLA. Later, may decom ODU and Antenna ONLY for existing HW MW Link 2684A20-S00567, 18G_1+0_55MHZ_128QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 16-17131) at NE and existing RTN910AF(RTN02, NEID 16-27131) at FE. Site Impacted : 2684A20. FE_S00567 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 16-27131) and insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN02, NEID 16-27131) ISM8 slot 03 Port 1 & 2 . Build new HW MW Link 18G_2+0_110MHZ_128QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Migrate traffic 2684A20 to existing port at PTN/Cisco S00566. 6.Later, may decom ODU and Antenna ONLY for existing HW MW Link 2684A20-S00567, 18G_1+0_55MHZ_128QAM. Anyway, do not decom RTN910AF(RTN01, NEID 16-17131) at NE and existing RTN910AF(RTN02, NEID 16-27131) at FE. | XMC-5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_1.2M(MDD) x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202603170137-GTSB
Q01209_AD | Q129A_Q01209OD_CB_KGSELEMAS | DU00006643863 | Sarawak | Sarawak | 2.233069 | 111.645273 | [9 empty] | TSS+TI |  | 2XPATCHCORD | BBU Patching | BBU Patch to fiber ODF Core port : C1,C2 to Point B Q00906 KG LEBAAN (Core port C1,C2 to port Cisco PTN) | BBU Patch to fiber ODF Core port : C1,C2 to Point B Q00906 KG LEBAAN (Core port C1,C2 to port Cisco PTN) | [6 empty] | Iezzpro | SQ202603180489-Iezzpro | Iezzpro | SQ202603180487-Iezzpro |  |  | Ongoing | 2026-04-26 | 2026-04-27 | 2026-04-26 | 2026-04-27 | Kevin//Tan/6000033214 |  | IEZZPRO INCORPORATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-26 | 2026-04-30 | 2026-04-27 | 2026-04-27 | Kevin//Tan/6000033214 |  | IEZZPRO INCORPORATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26031805 |  | 2026-03-19 | 2026-03-26 | Completed | 2026-03-18 | 2026-03-19 | 2026-03-18 | 2026-03-26 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-26 | 2026-04-26 | 2026-03-25 | 2026-03-26 | Hairil Nizam//Maliki/6000033206 | Iezzpro TI | 2026-03-26 | 2026-04-26 | 2026-03-25 | 2026-05-08 | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | [7 empty] | 2026-03-26 | 2026-04-26 | 2026-03-25 |  | MOHAMAD TARMIZI//ISWANDI/6000060946 | 2025-02-05: 2026-03-26; 2025-02-11: 2026-04-26; 2025-02-22: 2026-03-25; 2025-02-22: 2026-03-26 | [7 empty] | GCI | SQ202603170140-GCI | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
7189A_PORT | Simpangan | DU00006731068 | Sabah | Sabah | 5.185603 | 115.974140 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7189A RTN01-RTN02 10G 10G PORT IDU RTN01-RTN02 1. INSTALL 1 10G SFP OPTICAL AT HW 7189A RTN01 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7189A RTN02 8-EM6-3 3. PATCHING PATCH CORD 7189A RTN01 8-EM6-3 TO HW 7189A RTN02 8-EM6-2 4. RECONFIGURE TRAFFIC IMPACTED SITE: 7189A, 7227K, 7328C, 7179R, 7166R, 7173R | 7189A RTN01-RTN02 10G 10G PORT IDU RTN01-RTN02 1. INSTALL 1 10G SFP OPTICAL AT HW 7189A RTN01 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7189A RTN02 8-EM6-3 3. PATCHING PATCH CORD 7189A RTN01 8-EM6-3 TO HW 7189A RTN02 8-EM6-2 4. RECONFIGURE TRAFFIC IMPACTED SITE: 7189A, 7227K, 7328C, 7179R, 7166R, 7173R | [6 empty] | NR services |  | NR services | SQ202604230198-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041472 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-05-10 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-05-10 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-05-10 | LEONARD//EDUAN/6000038538 | 2025-02-05: 2026-04-15; 2025-02-11: 2026-05-15; 2025-02-22: 2026-04-15; 2025-02-22: 2026-05-07 | [7 empty] | GCI | SQ202604150440-GCI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
4698D_HU | SerojaParkhomes | DU00006643865 | Northern | Kedah | 5.695319 | 100.522000 | [7 empty] | 05. Doable |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M NE_4698D 15G_DP_0.6M(MS) + Waveguide x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. FE_4628B 15G_DP_0.6M(MS) + Waveguide x1. ISM8 x1. XMC_3E , Sub A & B_Hi x2. | MW Parallel Link | Existing link 13G_2+0_28M Install parallel link for 15G_2+0_28M Site Impacted : 4698D NE_4698D 1.Install new 15G_DP_0.6M(MS)+Waveguide. 2.Reuse existing 4698D_RTN01 , 3_IMS8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No decomm MW link. FE_4628B 1.Install new 15G_DP_0.6M(MS)+Waveguide. 2.Reuse existing 4628B_RTN02 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No decomm MW link. | Existing link 13G_2+0_28M Install parallel link for 15G_2+0_28M Site Impacted : 4698D NE_4698D 1.Install new 15G_DP_0.6M(MS)+Waveguide. 2.Reuse existing 4698D_RTN01 , 3_IMS8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No decomm MW link. | Existing link 13G_2+0_28M Install parallel link for 15G_2+0_28M Site Impacted : 4698D FE_4628B 1.Install new 15G_DP_0.6M(MS)+Waveguide. 2.Reuse existing 4628B_RTN02 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A_Hi. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No decomm MW link. | XMC_3E | MS | 15G | 0.6M | 0.6 | GCI | SQ202603130699-GCI | GCI | SQ202603130693-GCI // SQ202603130696-GCI // SQ202604070590-GCI | 2026-04-15 | 2026-04-14 | Completed | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-10 | 2026-04-10 | 2026-04-09 | 2026-04-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26031075 |  | 2026-04-30 | 2026-04-20 | Completed | 2026-04-20 | 2026-04-30 | 2026-04-20 | 2026-04-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-04-30 | 2026-04-02 | 2026-04-20 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-04-02 | 2026-04-30 | 2026-04-02 | 2026-04-20 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-03 | 2026-04-02 | 2026-04-30 | 2026-04-02 | 2026-04-20 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2025-02-05: 2026-04-02; 2025-02-11: 2026-04-30; 2025-02-22: 2026-04-02; 2025-02-22: 2026-04-02 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202603170124-GCI | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | CHEONG/SENG/WAH/7018000306
4622B_HU_1 | Sik Town | DU00006643866 | Northern | Kedah | 5.820505 | 100.742662 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x PATCHCORD | BBU Patching | Patch 4622B to TM LL Tx route before: 4622B-K00420 Tx route after: 4622B-LL-4000A | Patch 4622B to TM LL Tx route before: 4622B-K00420 Tx route after: 4622B-LL-4000A | [6 empty] | GCI | SQ202603060620-GCI | GCI | SQ202603060618-GCI |  |  | Ongoing | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040126 |  | 2026-04-30 | 2026-04-20 | Completed | 2026-04-20 | 2026-04-30 | 2026-04-20 | 2026-04-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-20 | 2026-04-30 | 2026-04-20 | 2026-04-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2026-04-20 | 2026-04-30 | 2026-04-20 | 2026-04-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-07 | 2026-04-30 | 2026-04-07 | 2026-04-20 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-02-05: 2026-04-07; 2025-02-11: 2026-04-30; 2025-02-22: 2026-04-07; 2025-02-22: 2026-04-07 | [7 empty] | GCI | SQ202603170124-GCI | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
3951B9_EVT | PBTS TAMANBAYVIEW HEIGHTS | DU00006643867 | Sabah | Sabah | 5.976190 | 116.097566 | [13 empty] | 3951B9_EVT PBTS TAMAN BAYVIEW HEIGHTS Tx route: 33951B9/33951B9-7223A-LL-7000A 1) Share port with 7223A at 7000A LL 2) New NE ID NE IDU 33951B9 RTN01 3) New NE ID FE IDU 7223A RTN02 4) FE IDU SET VLAN NMS 437 5) FE CASCADE RTN01 GE1 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [42 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | CHEONG/SENG/WAH/7018000306
9014L_HU | JalanKemuyang | DU00006643868 | Sarawak | Sarawak | 2.345155 | 111.961550 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 9014L-9182B ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS IMPACTED SITE: 9014L | MW REMOTE UPGRADE LINK 9014L-9182B ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS IMPACTED SITE: 9014L | MW REMOTE UPGRADE LINK 9014L-9182B ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS IMPACTED SITE: 9014L | XMC3 | MAC | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202603170140-GCI | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
9833B_AD | KpgLebaan | DU00006643869 | Sarawak | Sarawak | 2.274200 | 111.667100 | [9 empty] | TSS+TI | L1+ATP+PAC | 2XPATCHCORD | BBU Patching | 9833B Kpg Lebaan : BBU Patch to Cisco PTN | 9833B Kpg Lebaan : BBU Patch to Cisco PTN | [6 empty] | Iezzpro | SQ202603180489-Iezzpro | Iezzpro | SQ202603180487-Iezzpro |  |  | Ongoing | 2026-04-20 | 2026-04-24 | 2026-04-20 | 2026-04-20 | Kevin//Tan/6000033214 |  | IEZZPRO INCORPORATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-27 | Kevin//Tan/6000033214 |  | IEZZPRO INCORPORATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26031803 |  | 2026-03-19 | 2026-03-25 | Completed | 2026-03-18 | 2026-03-19 | 2026-03-18 | 2026-03-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-26 | 2026-04-26 | 2026-03-25 | 2026-04-01 | Hairil Nizam//Maliki/6000033206 | Iezzpro TI | 2026-03-26 | 2026-04-26 | 2026-03-25 | 2026-04-06 | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2026-03-26 | 2026-04-26 | 2026-03-25 | 2026-04-20 | MOHAMAD TARMIZI//ISWANDI/6000060946 | 2025-02-05: 2026-03-26; 2025-02-11: 2026-04-26; 2025-02-22: 2026-03-25; 2025-02-22: 2026-03-26 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202603170140-GCI | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00782_HU_1 | Q126A_Q00782OD_CB_KGMERITAM | DU00006643870 | Sarawak | Sarawak | 4.729430 | 114.869910 | [9 empty] | TSS+AA+TI |  | 13G_4+0_28M_512QAM_EPLA NE_Q00782 New 13G_1.8M(MS)+Hybrid Coupler x1. Re-use existing RTN910AF(NEID 82-42760). New ISM8 x2. New XMC_3, Sub A&B_Lo x4. New 13G Flexi WG x2. New IF cables with suitable length and type x4 RUN. FE_9291P/Q00328 New 13G_1.8M(MS)+Hybrid Coupler x1. Re-use existing RTN910AF(NEID 82-42757). New ISM8 x2. New XMC_3, Sub A&B_Hi x4. New 13G Flexi WG x2. New IF cables with suitable length and type x4 RUN. | MW Parallel Link | Existing Huawei MW Link 7G_2+0_28MHZ_2048QAM_EPLA_484M. Add new parallel Huawei MW Link 13G_4+0_28MHZ_512QAM_EPLA_856M. Later, combine existing Huawei MW Link 7G_2+0_28MHZ_2048QAM_EPLA_484M and new parallel Huawei MW Link 13G_4+0_28MHZ_512QAM_EPLA_856M. Become new Huawei MW Link 7G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. Site Impacted : Q00782. NE_Q00782 1.Install 13G_1.8M(MS)+Hybrid Coupler x1. 2.Re-use existing RTN910AF(NEID 82-42760) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_3, Sub A&B_Lo x4. Configure it. 4.Lay new x4 RUN of IF cables from new 4x ODU XMC_3, Sub A&B_Lo to existing RTN910AF(NEID 82-42760) ISM8 slot 03(Port 1&2) and ISM8 slot 04(Port 1&2). 5.Re-use existing Vlan DCN and Vlan Services. 6.Backhaul traffic Q00782 via new 7G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. FE_9291P/Q00328 1.Install 13G_1.8M(MS)+Hybrid Coupler x1. 2.Re-use existing RTN910AF(NEID 82-42757) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_3, Sub A&B_Hi x4. Configure it. 4.Lay new x4 RUN of IF cables from new 4x ODU XMC_3, Sub A&B_Hi to existing RTN910AF(NEID 82-42757) ISM8 slot 03(Port 1&2) and ISM8 slot 04(Port 1&2). 5.Re-use existing Vlan DCN and Vlan Services. 6.Backhaul traffic Q00782 via existing port of IBeam. | Existing Huawei MW Link 7G_2+0_28MHZ_2048QAM_EPLA_484M. Add new parallel Huawei MW Link 13G_4+0_28MHZ_512QAM_EPLA_856M. Later, combine existing Huawei MW Link 7G_2+0_28MHZ_2048QAM_EPLA_484M and new parallel Huawei MW Link 13G_4+0_28MHZ_512QAM_EPLA_856M. Become new Huawei MW Link 7G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. Site Impacted : Q00782. NE_Q00782 1.Install 13G_1.8M(MS)+Hybrid Coupler x1. 2.Re-use existing RTN910AF(NEID 82-42760) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_3, Sub A&B_Lo x4. Configure it. 4.Lay new x4 RUN of IF cables from new 4x ODU XMC_3, Sub A&B_Lo to existing RTN910AF(NEID 82-42760) ISM8 slot 03(Port 1&2) and ISM8 slot 04(Port 1&2). 5.Re-use existing Vlan DCN and Vlan Services. 6.Backhaul traffic Q00782 via new 7G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. | Existing Huawei MW Link 7G_2+0_28MHZ_2048QAM_EPLA_484M. Add new parallel Huawei MW Link 13G_4+0_28MHZ_512QAM_EPLA_856M. Later, combine existing Huawei MW Link 7G_2+0_28MHZ_2048QAM_EPLA_484M and new parallel Huawei MW Link 13G_4+0_28MHZ_512QAM_EPLA_856M. Become new Huawei MW Link 7G&13G_6+0_28MHZ_2048QAM&512QAM_EPLA. Site Impacted : Q00782. FE_9291P/Q00328 1.Install 13G_1.8M(MS)+Hybrid Coupler x1. 2.Re-use existing RTN910AF(NEID 82-42757) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_3, Sub A&B_Hi x4. Configure it. 4.Lay new x4 RUN of IF cables from new 4x ODU XMC_3, Sub A&B_Hi to existing RTN910AF(NEID 82-42757) ISM8 slot 03(Port 1&2) and ISM8 slot 04(Port 1&2). 5.Re-use existing Vlan DCN and Vlan Services. 6.Backhaul traffic Q00782 via existing port of IBeam. | XMC_3 | MS | 13G | 13G_1.8M(MS)+Hybrid Coupler x1. | 13G_1.8M(MS)+Hybrid Coupler x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202603170145-GTSB
S01363_Additional | RS50262_9_0_KGSRIMENANTI | DU00006643871 | Sabah | Sabah | 4.983340 | 115.530800 | [7 empty] | 05. Doable |  | TSS+AA+TI+Dismantle |  | 18G_2+0_55M_512QAM_EPLA NE_7297K/S01363 New 18G_0.6M_DP_(MAC)+OMT x1. New RTN910AF(RTN01). New XMC_3, Sub A_Lo x2. New CAT6 cable x1. FE_7697A New 18G_0.6M_DP_(MAC)+OMT x1. New RTN910AF(RTN01). New XMC_3, Sub A_Hi x2. New CAT6 cable x1. | MW New Link / Reroute | Existing HW MW Link_ID SB02766, S01363-S00556 18G_1+0_112MHz_1024QAM. Install new HW MW Link S01363-7697A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link_ID SB02766, S01363-S00556 18G_1+0_112MHz_1024QAM. Site Impacted : S01363. NE_S01363 1.Install new 18G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01) x1. 3.Install new XMC_3, Sub A_Lo x2. Configure it. 4.Build new HW MW Link S01363-7697A, 18G_2+0_55MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910A(RTN01) and patching to existing BBU S01363. Configure it. 6.Request new xD Vlan DCN and Vlan Services. 7.Migrate traffics S01363 via new HW MW Link S01363-7697A, 18G_2+0_55MHZ_512QAM_EPLA. 8.Later, decom existing HW MW Link_ID SB02766, S01363-S00556 18G_1+0_112MHz_1024QAM. FE_7697A 1.Install new 18G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01) x1. 3.Install new XMC_3, Sub A_Hi x2. Configure it. 4.Build new HW MW Link S01363-7697A, 18G_2+0_55MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910A(RTN01) and enable port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-43507). 6.Perform cascading in between port 8-EM6-1 of new RTN910A(RTN01) to port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-43507). Configure it. 7.Request new xD Vlan DCN and Vlan Services. 8.Migrate traffics QS01363 via existing IBeam port at CP 7690A in which similar with existing traffics like 7697A. 9.Later, decom existing HW MW Link_ID SB02766, S01363-S00556 18G_1+0_112MHz_1024QAM. | Existing HW MW Link_ID SB02766, S01363-S00556 18G_1+0_112MHz_1024QAM. Install new HW MW Link S01363-7697A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link_ID SB02766, S01363-S00556 18G_1+0_112MHz_1024QAM. Site Impacted : S01363. NE_S01363 1.Install new 18G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01) x1. 3.Install new XMC_3, Sub A_Lo x2. Configure it. 4.Build new HW MW Link S01363-7697A, 18G_2+0_55MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910A(RTN01) and patching to existing BBU S01363. Configure it. 6.Request new xD Vlan DCN and Vlan Services. 7.Migrate traffics S01363 via new HW MW Link S01363-7697A, 18G_2+0_55MHZ_512QAM_EPLA. 8.Later, decom existing HW MW Link_ID SB02766, S01363-S00556 18G_1+0_112MHz_1024QAM. | Existing HW MW Link_ID SB02766, S01363-S00556 18G_1+0_112MHz_1024QAM. Install new HW MW Link S01363-7697A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link_ID SB02766, S01363-S00556 18G_1+0_112MHz_1024QAM. Site Impacted : S01363. FE_7697A 1.Install new 18G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01) x1. 3.Install new XMC_3, Sub A_Hi x2. Configure it. 4.Build new HW MW Link S01363-7697A, 18G_2+0_55MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910A(RTN01) and enable port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-43507). 6.Perform cascading in between port 8-EM6-1 of new RTN910A(RTN01) to port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-43507). Configure it. 7.Request new xD Vlan DCN and Vlan Services. 8.Migrate traffics QS01363 via existing IBeam port at CP 7690A in which similar with existing traffics like 7697A. 9.Later, decom existing HW MW Link_ID SB02766, S01363-S00556 18G_1+0_112MHz_1024QAM. | XMC-3 | MAC | 18G | 18G_0.6M_DP_(MAC)+OMT x1 | 18G_0.6M_DP_(MAC)+OMT x1 | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042872 |  | 2026-04-30 |  | Ongoing | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-08 | 2026-05-31 | 2026-05-08 |  | RANA//WAQAS/6000006187 | NR Service TI | 2026-05-08 | 2026-05-31 | 2026-05-08 |  | RANA//WAQAS/6000006187 | NR Service TI | [7 empty] | 2026-05-08 | 2026-05-31 | 2026-05-08 |  | RANA//WAQAS/6000006187 | 2025-02-05: 2026-05-08; 2025-02-11: 2026-05-31; 2025-02-22: 2026-05-08; 2025-02-22: 2026-05-09
4578C_LOS | Taman Sg Bakap | DU00005658044 | Northern | Penang | 5.237069 | 100.497144 | [7 empty] | 03. TSS Only | SOW Need to change to from MW SWAP to MW New Link Reroute | TSS |  |  | MW New Link / Reroute | Conduct TSS Survey to identify FE candidates with clear LOS. New SOW addendum to be included for 4578C_HU (DU Code: DU00005244067) and 4578C_HU_1 (DU Code: DU00005509291). | Perform TSS LOS Survey only. | [6 empty] | NWAVE | SQ202507300527-N-Wave | NWAVE | No PR required-Work at TSS only |  |  | Ongoing | 2025-07-21 | 2025-07-21 | 2025-06-19 | 2025-06-19 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2025-07-10 | 2025-07-10 | 2025-07-10 | [36 empty] | GCI | SQ202507190085-GCI | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | CHEONG/SENG/WAH/7018000306
3762A-2436A | Jalan Seroja 1 Batang Kali | DU00003710851 | Central | Selangor | 3.417360 | 101.580880 |  |  |  | AUG 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 12/8: Cutover done 29/7: Need new IDU for patching follow SOW & effected site is 3762A-2436A | TSS+TI | L1+ATP+PAC | 1x IDU 910A | MW IDU Patching | MW IDU Patching at FE. Migrate MW Link 3762A-2436A-1 to new xC PTN B00308. Install 1x IDU 910A at B00308. Reengineering MW Link 3762A-2436A-1 to the new IDU. To propose new port at xC PTN B00308. Impact site: 3762A,1665H,2689C | [7 empty] | Datasco | SQ202411140206-Datasco | Datasco | SQ202408140506-Datasco | 2025-03-07 | 2025-03-11 | Completed | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240527A6 |  | 2024-05-28 | 2024-07-11 | Completed | 2024-05-27 | 2024-05-28 | 2024-05-27 | 2024-07-11 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-07-26 | 2024-07-31 | 2024-07-26 |  | TAN//SWEE LOON/7019000028 | Datasco TI | 2024-07-26 | 2024-07-31 | 2024-07-26 |  | TAN//SWEE LOON/7019000028 | Datasco TI | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-08-09 | SHUJAAT//ALI/6800000124 |  |  | 2024-07-26 | 2024-07-31 | 2024-07-26 | 2025-01-23 | TAN//SWEE LOON/7019000028 | 2025-02-05: 2024-07-26; 2025-02-11: 2024-07-31; 2025-02-22: 2024-07-26; 2025-02-22: 2024-07-29 |  |  | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
4401D_LOS | SDM Specialty Chemicals 2 | DU00005576884 | Northern | Kedah | 5.788825 | 100.490701 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_4401D 23G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Hi x2. FE_4998B 23G_DP_0.6M(MAC)+OMT x1. ISM8 x1 XMC_3E , Sub A & B_Lo x2. | MW New Link / Reroute | Link reroute to new FE K00381 due to LOS Block. 23G_2+0_112M. Site Impacted : 4401D. NE_4401D 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4401D_RTN01. 3.Install new 3_ISM8-2+0 into existing 4401D_RTN01. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 23G_2+0_112M & New FE route. 7.Decom existing ANT and ODU.(4401D - 4998B) FE_K00381 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing K00381_RTN910A ( ID : 23776). 3.Install new 3_ISM8-2+0 into existing K00381_RTN910A (ID : 23776). 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 23G_2+0_112M and new FE route.. 7.Decom existing ODU , ANT and RTN_02. (4998B - 4401D) | Link reroute to new FE K00381 due to LOS Block. 23G_2+0_112M. Site Impacted : 4401D. NE_4401D 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4401D_RTN01. 3.Install new 3_ISM8-2+0 into existing 4401D_RTN01. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 23G_2+0_112M & New FE route. 7.Decom existing ANT and ODU.(4401D - 4998B) | Link reroute to new FE K00381 due to LOS Block. 23G_2+0_112M. Site Impacted : 4401D. FE_K00381 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing K00381_RTN910A ( ID : 23776). 3.Install new 3_ISM8-2+0 into existing K00381_RTN910A (ID : 23776). 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 23G_2+0_112M and new FE route.. 7.Decom existing ODU , ANT and RTN_02. (4998B - 4401D) | XMC_3E | MAC | 23G | 0.6 | 0.6 | NWAVE | SQ202505280561-N-Wave | NWAVE | SQ202505260236-N-Wave // SQ202505260283-N-Wave // SQ202506050572-N-Wave | 2026-01-06 | 2026-01-06 | Completed | 2025-05-28 | 2025-05-31 | 2025-05-28 | 2025-07-15 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-05-31 | 2025-09-30 | 2025-09-30 | Khairul Azman Bin Din7160000001 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Disabled | 2025-05-28 | 2025-05-31 | 2025-05-28 |  | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. |  | Assigned | Disabled |  | 2025-05-28 | 2025-05-31 | 2025-05-28 | 2025-07-10 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-07-15 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2026-02-27 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-10-25 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | NG HONG JIE7018000036 | Logistic Team | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050639-GCI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | CHEONG/SENG/WAH/7018000306
B01583_LOS | JLNSATELITUPM | DU00004203366 | Central | Selangor | 2.988990 | 101.719290 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 8/11: D2: Cutover done. Post-CO T/S ongoing 7/11: MOS & Pre-installation in progress 30/10: LOS hunting WIP. Existing link blocked. RSL -93dbm | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_B01583 23G_DP_0.6m(MAC) x1. ISM8 x1. 23G_XMC_3E , Sub_A & B_Lo x2. FE_B00697. 23_DP_0.6m(MAC) x1. RTN 910A x1. 23G_XMC_3E , Sub_A& B_Hi x2. | MW Swap | Existing SM link 23G_1+0_56M. (Loss Comm). Swap existing link to 23G_2+0_112M due to existing ant location low caused LOS blocking. Site Impacted: B00697,B01583,B02796/1716K. NE_B01583 1.Install new 23G_DP_0.6m(MAC). 2.Reuse existing B01583_RTN01 , 3_ISM8-2+0. 3.Install 3_ISM8-2+0 into existing B01583_RTN01. 4.Install 23G_XMC_3E , Sub_A & B_Lo. 5.Create service cross connect and EPLA. 6.Migrate traffic to new link 23G_2+0_112M. (B01583 & B02796/1716K). 6.Decom existing SM link. FE_B00697. 1.Install new 23_DP_0.6m(MAC) at location Tower leg with LOS is clear. 2.Install new RTN 910A,7_ISM8-2+0. 3.Install 23G_XMC_3E , Sub_A& B_Hi. 4.Create Inband DCN and EPLA 5.Create service cross connect and migrate traffic.(B01583 & B02796/1716K). 6.Enable GE port and ETH cable patching to PTN_Fiber. 7.Decom existing SM link. | [7 empty] | YPTT | SQ202411280565-YPTT | YPTT | SQ202411120060-YPTT // SQ202504260171-YPTT |  |  | Ongoing | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24110401 |  | 2024-11-05 | 2024-11-05 | Completed | 2024-11-04 | 2024-11-05 | 2024-11-04 | 2024-11-05 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-07 | 2024-11-07 | 2024-11-07 | 2024-12-30 | AKMAL//BIN RAZALI/6794000078 | YPTT TI | 2024-11-07 | 2024-11-07 | 2024-11-07 |  | AKMAL//BIN RAZALI/6794000078 | YPTT TI | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-11-07 | 2024-11-07 | 2024-11-07 | 2025-04-07 | AKMAL//BIN RAZALI/6794000078 | 2024-11-07 | 2024-11-07 | 2024-11-07 | 2024-11-11 | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2025-01-24 | NG HONG JIE7018000036 | Logistic Team | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202509250653-GTSB | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | AB.RAHMAN//BIN MAT NOOH/6237001519
B02885_LOS | MUTIARA VILLE_CYBERJAYA | DU00004203367 | Central | Selangor | 2.923395 | 101.634626 |  |  |  |  | Cancel / Drop | Done under TX NIC 1695C_Additional | ZTE | 00. Site Out/Drop | 25/9: Done by ZTE under TX NIC 1695C_Additional (Swap Activity) |  |  |  | Cancel / Drop | 1. Decom existing FE antenna & relocate to new boom in the same site. 2. Alignment for LOS adjusted link | [7 empty] | MTK | No PR required-Site drop/cancel |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2024-09-18 | 2024-09-30 | 2024-09-18 |  | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-09-18 | 2024-09-30 | 2024-09-18 |  | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | [7 empty] | 2024-09-18 | 2024-09-30 | 2024-09-18 |  | RIDHUAN//BIN MANSOR/8225000011 | 2024-11-07: 2024-09-18; 2024-11-07: 2024-09-30; 2024-11-07: 2024-09-18; 2024-11-11: 2024-09-18 | [7 empty] | GTSB_AA | SQ202510300116-GTSB
W01225_LOS | LAMPOLE_JLN_DATO_ONN | DU00004203368 | Central | Kuala Lumpur | 3.158424 | 101.690547 |  |  |  |  | TI | Proposed LL | ZTE | 00. Site Out/Drop | 16/1/2025 : All candidate no LOS 20/9: Pending Tx Solution for HU | TSS |  | NA | MW New Link / Reroute | Proposed Fiber , No LOS via actual TSS survey. | [7 empty] | Datasco | SQ202502120378-Datasco |  |  | 2026-01-20 | 2026-01-21 | Completed | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2024-10-28 | Mohammad//Azamril Nasil Bin Ahmad Jamaludin/7019000039 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-07 | 2025-01-06 | 2025-01-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-12 | 2025-02-13 | 2025-02-12 | 2025-02-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300116-GTSB
W01461_LOS | JLNSTONOR_KL | DU00004203369 | Central | Kuala Lumpur | 3.150624 | 101.717090 |  | FEB 25 |  | FEB 25 | Cancel / Drop | Site has been decom | ZTE | 00. Site Out/Drop | 13/2/2025 : No need proceed. Site W01461 has been decom 10/2/2025 : KONSORTIUM INFRASTRUKTUR W.P. SDN BHD - LAMP POLE 18M LAND - NE site W01461 JLNSTONOR_KL, XAIR NETWORK - 24M Lampole - FE site 3888A Jalan Conlay 20/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | SITE ALREADY DECOM | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  |  | 2024-11-26 |  | Ongoing | 2024-11-25 | 2024-11-26 | 2024-11-25 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [6 empty] | GCI TI
B01925_LOS | IJOKINDUSTRI | DU00004203370 | Central | Selangor | 3.273800 | 101.452330 |  |  |  |  | Cancel / Drop | Done under DU B01925 TX NIC | ZTE | 00. Site Out/Drop | 23/9: Done by ZTE under TX NIC B01925 (Swap Activity) |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
B02580_LOS | JLNTK5_44_TMNKINRARA | DU00004203371 | Central | Selangor | 3.061880 | 101.634794 | WK02 | JAN 25 | WK02 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 8/1/2025 : Cutover done 7/1/2025 : Installation complete, pending cutover due to raining day 6/1/2025 : NE installation complete, pending install FE due to not receive keys 5/1/2025 : EDOTCO (M) SDN BHD - BOOM 6M ROOFTOP - NE site B02580 JLNTK5_44_TMNKINRARA, Digi OB - Tower - FE site 1196A JBA Puchong 20/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Link Reroute to new FE 1196A due to LOS block. NE_B02580 23G_DP_0.6m(MAC)+OMT x1. XMC_3E-2+0 , Sub A & B_Lo. RTN910A x1. FE_1196A. 23G_DP_0.6m(MAC)+OMT x1. XMC_3E-2+0 , Sub A & B_Hi x2. RTN910A x1. | MW New Link / Reroute | Link Reroute to new FE 1196A due to LOS block. NE_B02580 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new XMC_3E-2+0. 3.Install new RTN910A,7_ISM8-2+0. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new route FE. 6.Decom existing MW link. FE_1196A. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new XMC_3E-2+0. 3.Install new RTN910A,7_ISM8-2+0. 4.Create new In Band DCN. 5.Enable EPLA and service cross connect. 6.Migrate traffic to new link. 7.Decom existing MW link. | [7 empty] | Magicell | SQ202501030386-Magicell | Magicell | SQ202411250781-Magicell // SQ202504260146-Magicell | 2025-03-01 | 2025-02-28 | Completed | 2024-12-26 | 2024-12-26 | 2024-12-26 | 2024-12-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-26 | 2024-12-26 | 2024-12-26 | 2024-12-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-02-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-28 | 2025-03-01 | 2025-02-28 | 2025-02-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112526 |  | 2024-11-26 | 2025-02-07 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2025-02-07 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-06 | 2025-01-31 | 2025-02-07 | 2025-02-07 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-01-06 | 2025-01-31 | 2025-02-04 | 2025-02-07 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-01-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-11 | 2025-01-06 | 2025-01-31 | 2025-01-28 | 2025-01-28 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-01-06 | 2025-01-31 | 2025-01-24 | 2025-01-24 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
1034B_LOS | Tmn Len Seng Cheras | DU00004199952 | Central | Kuala Lumpur | 3.070022 | 101.749426 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 19/2/2025 : Cutover done 14/2/2025 : Only survey activity 14/1/2025 : Digi OB - 6M RT - Wall Mounted Pole - NE site 1034B Tmn Len Seng Cheras, UMOBILE - In-Building System - FE site 3219B Cheras Sentral IB 22/10: Pending Site DO 27/9: LOS hunting NE done, pending BM approval FE for full TSS & proceed TI. 2/10: Target RFS by 12/10 23/9: LOS hunting plan 25/9 - access issue | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Link re-route to new FE 3219B and swap existing NLOS to MW with config 23G_1+0_112M. Site Impacted:1034B. NE_1034B 1.Install new 23G_0.6m(MAC) x1. 2.Install new XMC_3C-1+0 ODU, Sub_A_Lo x1. 3.Install new RTN910A x1. FE_3219B 1.Install new 23G_0.6m(MAC) x1. 2.Install new XMC_3C-1+0 ODU, Sub_A_Hi x1. 3.ISM8 x1. | MW New Link / Reroute | Existing TX route 1034B-NLOS-1273B-3446A-1465A Link re-route to new FE 3219B and swap existing NLOS to MW with config 23G_1+0_112M. For 3219B , priority upstream link 3219B-2448A Site Impacted:1034B. NE_1034B 1.Install new 23G_0.6m(MAC). 2.Install new XMC_3C-1+0 ODU, SUb_A_Lo. 3.Install new RTN910A, 7_ISM8-1+0. 4.Migrate service to new link. 5.Decom existing NLOS equipment. FE_3219B 1.Install new 23G_0.6m(MAC). 2.Install new XMC_3C-1+0 ODU, Sub_A_Hi. 3.Install new RTN910A, 7_ISM8-1+0. 4.Traffic reroute to new CP site via MW (3219B-2448A). 5.Decom existing NLOS equipment. | [7 empty] | Magicell | SQ202503190673-Magicell | Magicell | SQ202504210080-Magicell // SQ202504210088-Magicell // SQ202504260146-Magicell | 2025-11-11 | 2025-11-10 | Completed | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-03-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010781 |  | 2025-01-08 | 2025-01-08 | Completed | 2025-01-07 | 2025-01-08 | 2025-01-07 | 2025-01-08 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-14 | 2025-02-28 | 2025-02-19 | 2025-02-20 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-02-14 | 2025-02-28 | 2025-02-14 | 2025-02-27 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-02-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-19 | 2025-02-14 | 2025-02-28 | 2025-03-13 | 2025-03-13 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-02-14 | 2025-02-28 | 2025-03-10 | 2025-03-10 | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358
7063A | Guang Ji Temple | DU00004222644 | Sabah | Sabah | 5.319757 | 116.173867 | [7 empty] | 00. Integrated/RFS Done | 29/11: Integration in plan 7/10: Cutover done. Post-CO T/S WIP | TSS+TI | L1+ATP+PAC |  | BBU Patching | Patching from 1G port to 10G port (10G Ge0/2/2) | [7 empty] | NR Services | SQ202410280486-NR Services | NR services | SQ202410100848-NR Services | 2024-11-08 | 2024-11-05 | Completed | 2024-10-14 | 2024-10-14 | 2024-10-14 | 2024-10-14 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-15 | 2024-10-18 | 2024-10-15 | 2024-10-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-15 | 2024-10-18 | 2024-10-15 | 2024-10-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-05 | 2024-11-08 | 2024-11-05 | 2024-11-05 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24100241 |  | 2024-10-03 | 2024-10-03 | Completed | 2024-10-02 | 2024-10-03 | 2024-10-02 | 2024-10-03 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-26 | MARTO FERDANEND BIN MOTIAS7167000021 |  | 2024-10-27 | 2024-10-27 | 2024-10-26 |  | MARTO FERDANEND BIN MOTIAS7167000021 |  | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-10-14 | 2024-10-31 | 2024-10-14 | 2024-10-14 | MARTO FERDANEND BIN MOTIAS7167000021 | 2024-11-07: 2025-06-13; 2024-11-07: 2025-07-13; 2024-11-07: 2025-06-13 |  |  | 2024-11-30 | 2024-12-30 | 2024-11-30 | 2024-11-30 | ASTI//GANIS PUTRIANI/6237001358
3104H_AD | 99 Speedmart NS Broga | DU00005721941 | Central | Sembilan | 2.935750 | 101.911290 | [7 empty] | 00. Integrated/RFS Done | 25/6: CO done. | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Install new NLOS NE_3104H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. FE_2408A 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Link reroute to original FE 2408A as per email from ZTE and CD with new NLOS equipment. Site Impacted : 3104H NE_3104H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. 6. Traffic migrate to original route with new NLOS equipment. 7. Decom existing NLOS equipment 3104H - 3064H. FE_2408A 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. Traffic migrate to original FE with new NLOS equipment. 7. ETH cable patching to existing 2408A_RTN01_GE2 port from NLOS equipment. 8. Decom existing NLOS equipment 3064C - 3104H. | Link reroute to original FE 2408A as per email from ZTE and CD with new NLOS equipment. Site Impacted : 3104H NE_3104H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. 6. Traffic migrate to original route with new NLOS equipment. 7. Decom existing NLOS equipment 3104H - 3064H. | Link reroute to original FE 2408A as per email from ZTE and CD with new NLOS equipment. Site Impacted : 3104H FE_2408A 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. Traffic migrate to original FE with new NLOS equipment. 7. ETH cable patching to existing 2408A_RTN01 GE2 port from NLOS equipment. 8. Decom existing NLOS equipment 3064C - 3104H. | [5 empty] | Magicell | SQ202506190624-Magicell | Magicell | SQ202506250196-Magicell // SQ202506250205-Magicell | 2026-02-25 | 2026-02-25 | Completed | 2025-06-26 | 2025-06-26 | 2025-06-25 | 2025-06-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-03 | 2025-07-02 | 2025-07-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061963 |  | 2025-06-23 | 2025-07-18 | Completed | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-07-18 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-07-18 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-07-18 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-25 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-07-18 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-30 | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | NG HONG JIE7018000036 | Logistic Team | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507080517-GCI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | CHEONG/SENG/WAH/7018000306
9359B_IPR | Sg Asap 3 | DU00006624716 | Sarawak | Sarawak | 3.116570 | 113.933430 | [9 empty] | TSS+TI |  | Fiber Patch Cord x1 pairs 10G SFP x 2. | BBU Patching | BBU Patching To 9359B_LL Port info : ETH 10-PEX-1 | BBU Patching To 9359B_LL Port info : ETH 10-PEX-1 | [6 empty] | Allstar | SQ202603180484-Allstar | Allstar | SQ202603180480-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030633 |  | 2026-03-07 | 2026-03-31 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-09 | 2026-04-15 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-04-09 | 2026-04-15 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | [7 empty] | 2026-04-09 | 2026-04-15 |  |  | ROYSTON//AHHOLE/6000038561 | 2025-06-23: 2026-04-09; 2025-06-23: 2026-04-15 | [7 empty] | GCI | SQ202602260597-GCI | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | CHEONG/SENG/WAH/7018000306
9014A_IPR | SarawakTurf Club | DU00006624717 | Sarawak | Sarawak | 1.454319 | 110.328299 | [9 empty] | TSS+TI | L1+ATP+PAC | NE_9014A New suitable SFP Module 10G 1310nm x1(for IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW IDU Patching | Perform upgrade 1G(Electrical) to 10G(Optical) port. Site Impacted: 9014A & 9199R. NE_9014A 1.Disable port 8-EM6-1(1G Electrical) of existing RTN910AF(RTN01, NEID 9-24273). 2.Disconnect/remove existing CAT6 cable port 8-EM6-1(1G Electrical) of existing RTN910AF(RTN01, NEID 9-24273) to existing port 1G(Electrical) of Sacofa LL. 3.Insert suitable new Optical SFP Module 10G 1310nm x1 into port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-24273). Enable and configure it. 4.Patching Optical patch cord in between port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-24273) and new Sacofa LL 10G port(ETH 1-1-3). 5.Request new xD Vlan DCN & Vlan Services. 6.Migrate Traffics 9014A & 9199R into new Sacofa LL 10G port(ETH 1-1-3). | Perform upgrade 1G(Electrical) to 10G(Optical) port. Site Impacted: 9014A & 9199R. NE_9014A 1.Disable port 8-EM6-1(1G Electrical) of existing RTN910AF(RTN01, NEID 9-24273). 2.Disconnect/remove existing CAT6 cable port 8-EM6-1(1G Electrical) of existing RTN910AF(RTN01, NEID 9-24273) to existing port 1G(Electrical) of Sacofa LL. 3.Insert suitable new Optical SFP Module 10G 1310nm x1 into port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-24273). Enable and configure it. 4.Patching Optical patch cord in between port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-24273) and new Sacofa LL 10G port(ETH 1-1-3). 5.Request new xD Vlan DCN & Vlan Services. 6.Migrate Traffics 9014A & 9199R into new Sacofa LL 10G port(ETH 1-1-3). | [6 empty] | Allstar | SQ202603180484-Allstar | Allstar | SQ202603180480-Allstar |  |  | Ongoing | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030634 |  | 2026-03-07 | 2026-03-31 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-03-31 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-03-17 | 2026-03-24 | 2026-03-17 | 2026-04-08 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-31 | 2026-03-17 | 2026-03-24 | 2026-04-07 | 2026-04-07 | ROYSTON//AHHOLE/6000038561 | 2025-06-23: 2026-03-17; 2025-06-23: 2026-03-24; 2025-06-23: 2026-03-17; 2025-06-30: 2026-03-17 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202602260653-GTSB
3004A10_EVT | PBTS SMAN TOHPUAN HAJJAH RAHMAH | DU00006624718 | Sabah | Sabah | 5.793496 | 116.006378 | [13 empty] | Planning and integration support only for event site 3004A10_EVT PBTS SMAN TOH PUAN HAJJAH RAHMAH Tx route: 3004A10/3004A10-7404B-LL-7000A 1) Share port with 7404B at 7000A 2) New NE ID NE IDU 3004A10 RTN01 3) New NE ID FE IDU 7404B RTN01 4) New DCN IP 7404B RTN01 5) New DCN VLAN 7404B RTN01 6) At far end (7404B): - Install new IDU (7404B RTN01) - Patch BBU to 7404B RTN01 GE2 - Patch 7404B RTN01 GE1 to existing CTS port | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4857B_IPR_1 | BandarWawasan | DU00006632042 | Northern | Kedah | 6.291780 | 100.418000 | [7 empty] | 05. Doable |  | TSS+TI | L1+ATP+PAC | NE_K00214 New CAT6 cable x1. | MW IDU Patching | Perform new 1G(Electrical) port patching in between SM IDU and PTN?Cisco. Site Impacted: K00323. NE_K00214 1.Request new port 1G(Electrical) at existing PTN/Cisco 60033-BDRWAWASAN-ACC1 from ZTE IPRAN Team. 2.Enable port LAN 4(Electrical) at existing SM IDU AGS 20(IP Address 10.127.219.99) of existing SM MW Link_ID, NT05913 K00214-K00116 MW1. 3.Perform patching in between port LAN 4(Electrical) at existing SM IDU AGS 20(IP Address 10.127.219.99) of existing SM MW Link_ID, NT05913 K00214-K00116 MW1 and new port 1G(Electrical) at existing PTN/Cisco 60033-BDRWAWASAN-ACC1. 4.Cross check whether existing Vlan Services for traffic K00323 can be re-use if divert to new port 1G(Electrical) at existing PTN/Cisco 60033-BDRWAWASAN-ACC1. If NOT, need to request xC Vlan Services for traffic K00323 from ZTE IPRAN Team. 5.Migrate traffic K00323 into new new port 1G(Electrical) at existing PTN/Cisco 60033-BDRWAWASAN-ACC1. | Perform new 1G(Electrical) port patching in between SM IDU and PTN?Cisco. Site Impacted: K00323. NE_K00214 1.Request new port 1G(Electrical) at existing PTN/Cisco 60033-BDRWAWASAN-ACC1 from ZTE IPRAN Team. 2.Enable port LAN 4(Electrical) at existing SM IDU AGS 20(IP Address 10.127.219.99) of existing SM MW Link_ID, NT05913 K00214-K00116 MW1. 3.Perform patching in between port LAN 4(Electrical) at existing SM IDU AGS 20(IP Address 10.127.219.99) of existing SM MW Link_ID, NT05913 K00214-K00116 MW1 and new port 1G(Electrical) at existing PTN/Cisco 60033-BDRWAWASAN-ACC1. 4.Cross check whether existing Vlan Services for traffic K00323 can be re-use if divert to new port 1G(Electrical) at existing PTN/Cisco 60033-BDRWAWASAN-ACC1. If NOT, need to request xC Vlan Services for traffic K00323 from ZTE IPRAN Team. 5.Migrate traffic K00323 into new new port 1G(Electrical) at existing PTN/Cisco 60033-BDRWAWASAN-ACC1. | [6 empty] | GCI | SQ202604150154-GCI | GCI | SQ202604100648-GCI |  |  | Ongoing | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-30 | 2026-05-07 | 2026-04-30 | 2026-05-01 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26031084 |  | 2026-03-11 | 2026-03-14 | Completed | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-08 | 2026-04-30 | 2026-04-08 | 2026-04-09 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-04-08 | 2026-04-30 | 2026-04-08 | 2026-04-09 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-09 | 2026-04-08 | 2026-04-30 | 2026-04-08 | 2026-04-09 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-06-23: 2026-04-08; 2025-06-23: 2026-04-30; 2025-06-23: 2026-04-08; 2025-06-30: 2026-04-08 | [7 empty] | GTSB | SQ202602260616-GTSB
Q00313_IPR_1 | Q125A_Q00313OD_CB_BKTTIONG | DU00006632043 | Sarawak | Sarawak | 4.881264 | 115.395869 | [9 empty] | TSS+TI | L1+ATP+PAC | NE_Q00313 New SFP Module 10G 10Km 1310nm x1(IDU Huawei) & SFP Module 10G x1(PTN/Cisco). New Optical Patchcord with suitable type and length x1. | MW IDU Patching | Perform upgrade for existing HW IDU & PTN/Cisco Router 1G to 10G and patching. Site Impacted: Q00362, Q01546, Q00652, Q00604/9167R, 9335K(E/// BBU), Q01377(E/// BBU) & Q00932(E/// BBU). NE_Q00313 1.Disable port 17-SLF2EM6-1(1G Electrical) & port 17-SLF2EM6-3(1G Optical)of existing RTN950A(NEID 82-13619). 2.Disable port GE0/0/1(1G Optical) & GE0/0/3(1G Electrical) of existing 30108-BKTTIONG-ACC1. 3.Disconnect/remove existing patching of CAT6 cable and Optical patch cord cable from existing RTN950A(NEID 82-13619) to existing PTN/Cisco 30108-BKTTIONG-ACC1. 4.Insert new SFP Module 10G 1310nm 10Km x1 and enable port 17-SLF2EM6-5(10G Optical) of existing RTN950A(NEID 82-13619).Configure it. 5.Request new port 10G at existing PTN/Cisco 30108-BKTTIONG-ACC1 from ZTE IPRAN Team. 6.Insert new suitable SFP Module 10G into new port 10G at existing PTN/Cisco 30108-BKTTIONG-ACC1. Configure it 7.Patching port 17-SLF2EM6-5(10G Optical) of existing RTN950A(NEID 82-13619) to new port 10G at existing PTN/Cisco 30108-BKTTIONG-ACC1. 8.Please cross check with ZTE IPRAN team whether existing xC Vlan DCN & Vlan Services can be re-use. If NO request new xC Vlan DCN & Vlan Services. 9.Migrate Traffics Q00362, Q01546, Q00652, Q00604/9167R, 9335K(E/// BBU), Q01377(E/// BBU) & Q00932(E/// BBU will backhaul into new IBeam port 10G at existing PTN/Cisco 30108. | Perform upgrade for existing HW IDU & PTN/Cisco Router 1G to 10G and patching. Site Impacted: Q00362, Q01546, Q00652, Q00604/9167R, 9335K(E/// BBU), Q01377(E/// BBU) & Q00932(E/// BBU). NE_Q00313 1.Disable port 17-SLF2EM6-1(1G Electrical) & port 17-SLF2EM6-3(1G Optical)of existing RTN950A(NEID 82-13619). 2.Disable port GE0/0/1(1G Optical) & GE0/0/3(1G Electrical) of existing 30108-BKTTIONG-ACC1. 3.Disconnect/remove existing patching of CAT6 cable and Optical patch cord cable from existing RTN950A(NEID 82-13619) to existing PTN/Cisco 30108-BKTTIONG-ACC1. 4.Insert new SFP Module 10G 1310nm 10Km x1 and enable port 17-SLF2EM6-5(10G Optical) of existing RTN950A(NEID 82-13619).Configure it. 5.Request new port 10G at existing PTN/Cisco 30108-BKTTIONG-ACC1 from ZTE IPRAN Team. 6.Insert new suitable SFP Module 10G into new port 10G at existing PTN/Cisco 30108-BKTTIONG-ACC1. Configure it 7.Patching port 17-SLF2EM6-5(10G Optical) of existing RTN950A(NEID 82-13619) to new port 10G at existing PTN/Cisco 30108-BKTTIONG-ACC1. 8.Please cross check with ZTE IPRAN team whether existing xC Vlan DCN & Vlan Services can be re-use. If NO request new xC Vlan DCN & Vlan Services. 9.Migrate Traffics Q00362, Q01546, Q00652, Q00604/9167R, 9335K(E/// BBU), Q01377(E/// BBU) & Q00932(E/// BBU will backhaul into new IBeam port 10G at existing PTN/Cisco 30108. | [6 empty] | Allstar | SQ202603180484-Allstar | Allstar | SQ202603180480-Allstar |  |  | Ongoing | 2026-04-29 | 2026-05-05 | 2026-04-29 | 2026-04-29 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-05-05 | 2026-04-29 | 2026-04-29 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030635 |  | 2026-03-07 | 2026-03-31 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-15 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-04-15 | 2026-04-21 | 2026-04-22 | 2026-04-22 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-16 | 2026-04-15 | 2026-04-21 | 2026-04-22 | 2026-04-22 | ROYSTON//AHHOLE/6000038561 | 2025-06-23: 2026-04-15; 2025-06-23: 2026-04-21; 2025-06-23: 2026-04-15; 2025-06-30: 2026-04-15 | [7 empty] | GTSB | SQ202602260653-GTSB
B02014_IPR | B061F_B02014OD_SERIPRISTANA | DU00006632044 | Central | Selangor | 3.210790 | 101.473110 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | Fiber Patch Cord x 1 Pairs | MW IDU Patching | Upgrade patching from IDU to PTN 1G to 10G. Impacted site: 1220D , 1434H , 3447C. Existing: Huawei B02014-SERI PR ISTANA-RTN01 GE5 to 71415-SRI_PRISTANA/GigabitEthernet0/0/3 Integration team to assign new 10G port at IDU and PTN during migration | Upgrade patching from IDU to PTN 1G to 10G. Impacted site: 1220D , 1434H , 3447C. Existing: Huawei B02014-SERI PR ISTANA-RTN01 GE5 to 71415-SRI_PRISTANA/GigabitEthernet0/0/3 Integration team to assign new 10G port at IDU and PTN during migration | [6 empty] | GTSB | SQ202603030399-GTSB | GTSB | SQ202603030392-GTSB |  |  | Ongoing | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-27 | 2026-03-13 | 2026-03-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26030414 |  | 2026-03-05 | 2026-03-09 | Completed | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-07 | 2026-03-31 | 2026-03-07 | 2026-03-11 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-03-07 | 2026-03-31 | 2026-03-07 | 2026-03-12 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-03-07 | 2026-03-31 | 2026-03-07 | 2026-03-10 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-06-23: 2026-03-07; 2025-06-23: 2026-03-31; 2025-06-23: 2026-03-07; 2025-06-30: 2026-03-09 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602260549-GCI | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | CHEONG/SENG/WAH/7018000306
7105B_IPR | Telipok 2 | DU00006632045 | Sabah | Sabah | 6.107310 | 116.210850 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X PATCHCORD | MW IDU Patching | Perform LAG at CP site for IDU 7042A-TELIPOK-RTN03 to 7042A-MAC-001 Telipok 1) Patch IDU 7042A RTN03 GE2 to new CP port 2) Create LAG 3) Impact sites: 7105B |  | Perform LAG at CP site for IDU 7042A-TELIPOK-RTN03 to 7042A-MAC-001 Telipok 1) Patch IDU 7042A RTN03 GE2 to new CP port 2) Create LAG 3) Impact sites: 7105B | [5 empty] | NR services |  | NR services | SQ202604230198-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041466 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-04-28 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-04-28 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-04-26 | 2026-04-26 | 2026-04-26 | 2026-04-26 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-04-28 | LEONARD//EDUAN/6000038538 | 2025-06-23: 2026-04-15; 2025-06-23: 2026-05-15; 2025-06-23: 2026-04-15; 2025-06-30: 2026-04-23 | [7 empty] | GCI | SQ202602260576-GCI | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
9420A_IPR | Bau (Celcom) | DU00006645469 | Sarawak | Sarawak | 1.428731 | 110.132714 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x 10G SFP 1KM 2X PATCHCORD | MW IDU Patching | 9420A 10G PORT 9420A/9420A-LL-9999A INSTALL 1 10G SFP OPTICAL AT LL PORT (PENDING PORT INFO) INSTALL 1 10G SFP OPTICAL AT HW 9420A RTN01 8-EM6-3(PORT-3) PATCHING OPTICAL PATCH CORD LL PORT ETH (PENDING PORT INFO) to HW 9338B RTN01 8-EM6-3(PORT-3) RECONFIGURE TRAFFIC FOR ALL SITES: 9338B, 9936A, 9580B | 9420A 10G PORT 9420A/9420A-LL-9999A INSTALL 1 10G SFP OPTICAL AT LL PORT (PENDING PORT INFO) INSTALL 1 10G SFP OPTICAL AT HW 9420A RTN01 8-EM6-3(PORT-3) PATCHING OPTICAL PATCH CORD LL PORT ETH (PENDING PORT INFO) to HW 9338B RTN01 8-EM6-3(PORT-3) RECONFIGURE TRAFFIC FOR ALL SITES: 9338B, 9936A, 9580B | [6 empty] | Allstar | SQ202603180484-Allstar | Allstar | SQ202603180480-Allstar |  |  | Ongoing | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030636 |  | 2026-03-07 | 2026-03-31 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-19 | 2026-04-16 | 2026-04-16 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-03-13 | 2026-03-19 | 2026-04-16 | 2026-04-16 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-16 | 2026-03-13 | 2026-03-19 | 2026-04-20 | 2026-04-20 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-06-23: 2026-03-13; 2025-06-23: 2026-03-19; 2025-06-23: 2026-03-13; 2025-06-30: 2026-03-13 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202603170140-GCI | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01190_HU | Q136A_Q01190OD_T3_SGANTU | DU00005651410 | Sarawak | Sarawak | 1.922638 | 111.242606 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | HSU//MYET CHAE/6799000011
S01442_HU | S106A_S01442OD_T3_KGSGBUAYA | DU00005651411 | Sabah | Sabah | 4.469530 | 118.525280 | [7 empty] | 00. Integrated/RFS Done | 17/7: No material issue, plan RFS WK30 | TSS+AA+TI | L1+ATP+PAC | 2xISM8 | MW Hardware Upgrade | MW HARDWARE UPGRADE S01442-S00250 FROM 18G_2+0 TO 18G_4+0 | MW HARDWARE UPGRADE S01442-S00250 FROM 18G_2+0 TO 18G_4+0 NE: 1. Reuse RTN910A. 2. Install new ISM8 at Slot 3. 3. Reuse exisitng XMC-5D_ SB A. 4. Reuse exisitng antenna. 5. Configure 18G_4+0_112QAM_2704M_EPLA. | MW HARDWARE UPGRADE S01442-S00250 FROM 18G_2+0 TO 18G_4+0 FE: 1. Reuse RTN910A. 2. Install new ISM8 at Slot 3. 3. Reuse exisitng XMC-5D_ SB A. 4. Reuse exisitng antenna. 5. Configure 18G_4+0_112QAM_2704M_EPLA. | [5 empty] | NR services | SQ202508270926-NR Services | NR services | SQ202508200592-NR Services // SQ202508200595-NR Services | 2025-09-17 | 2025-09-17 | Completed | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071934 |  | 2025-07-24 | 2025-08-26 | Completed | 2025-07-23 | 2025-07-24 | 2025-07-23 | 2025-08-26 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-08-26 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-08-26 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-22 | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-08-26 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-23: 2025-08-18; 2025-06-23: 2025-09-18; 2025-06-23: 2025-08-18; 2025-06-30: 2025-08-22 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506050649-GTSB | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | HSU//MYET CHAE/6799000011
Q00228_HU | Q123A_Q00228OD_TMKAPITTV | DU00005651412 | Sarawak | Sarawak | 2.013463 | 112.934075 | [6 empty] | ZTE | 01. Pending Planning | 6/24/2025 1. NE Identifier refer to HW Link Q00521-Q00228(Link_ID SW03452) 7G_4+0_XPIC_256QAM_EPLA. 2. Utilization per week(31-07-2025 ~ 06-08-2025) for MAX 68.4%. 3. Need to amend visio topo. Tx route changed. 4. Need to check performance for another 2 consecutive weeks. Current utilization is 58%. 5. Need to perform TSS for new antenna dish 2.4m location availability. 6. Due to link distance ~41Km, 7G channel seem difficult to obtained free channel. Therefore, need to perform physical Freq Scanning in order to check free channel availability. | [18 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050662-GTSB
4262B_HU | TIKAM BATU - TRUNK ROAD | DU00005651413 | Northern | Kedah | 5.586833 | 100.399111 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M NE_4262B New 18G_0.6M(MDD) x1. New RTN910A x1. New XMC_5D, Sub B_Lo x1. FE_4947A New 18G_0.6M(MDD) x1. New RTN910A x1. New XMC_5D, Sub B_Hi x1. New CAT6 Cable with suitable length x1. | MW Swap | Existing HW MW Link 18G_1+0_56M_512QAM_422M. Swap existing HW MW Link with new HW MW Link 18G_1+0_112M_256QAM. Later, decom existing HW MW Link 18G_1+0_56M_512QAM_422M. Site Impacted : 4262B. NE_4262B 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A. 3.Install new XMC_5D, Sub B_Lo x1. Configure it. 4.Configure DCN Inband. 5.Re-use existing vlan services. 6.Migrate traffic to new link 18G_1+0_112M_256QAM. Configure it. 7.Later, decom existing HW MW Link 18G_1+0_56M_512QAM_422M. FE_4947A 1.Install New 18G_0.6M(MDD) x1. 2.Install new RTN910A. 3.Install new XMC_5D, Sub B_Hi x1. Configure it. 4.Configure DCN Inband. 5.Re-use existing vlan services and existing IBeam port at CP/PTN P00117. 6.Migrate traffic to new link 18G_1+0_112M_256QAM. Configure it. 7.Later, decom existing HW MW Link 18G_1+0_56M_512QAM_422M. | Existing HW MW Link 18G_1+0_56M_512QAM_422M. Swap existing HW MW Link with new HW MW Link 18G_1+0_112M_256QAM. Later, decom existing HW MW Link 18G_1+0_56M_512QAM_422M. Site Impacted : 4262B. NE_4262B 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A. 3.Install new XMC_5D, Sub B_Lo x1. Configure it. 4.Configure DCN Inband. 5.Re-use existing vlan services. 6.Migrate traffic to new link 18G_1+0_112M_256QAM. Configure it. 7.Later, decom existing HW MW Link 18G_1+0_56M_512QAM_422M. | Existing HW MW Link 18G_1+0_56M_512QAM_422M. Swap existing HW MW Link with new HW MW Link 18G_1+0_112M_256QAM. Later, decom existing HW MW Link 18G_1+0_56M_512QAM_422M. Site Impacted : 4262B. FE_4947A 1.Install New 18G_0.6M(MDD) x1. 2.Install new RTN910A. 3.Install new XMC_5D, Sub B_Hi x1. Configure it. 4.Configure DCN Inband. 5.Re-use existing vlan services and existing IBeam port at CP/PTN P00117. 6.Migrate traffic to new link 18G_1+0_112M_256QAM. Configure it. 7.Later, decom existing HW MW Link 18G_1+0_56M_512QAM_422M. | XMC_5D | MDD | 18G | New 18G_0.6M(MDD) x1. | New 18G_0.6M(MDD) x1. | Magicell | SQ202508200574-Magicell | Magicell | SQ202510010665-Magicell // SQ202510010666-Magicell | 2025-12-03 | 2025-11-26 | Completed | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-21 | 2025-08-28 | 2025-08-21 | 2025-08-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-12-03 | 2025-11-26 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092447 |  | 2025-09-30 | 2025-10-15 | Completed | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-02 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-13 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-06 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | NG HONG JIE7018000036 | Logistic Team | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB
9031K_HU | CB_RHRANGGA | DU00005651414 | Sarawak | Sarawak | 3.089222 | 113.211667 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 7G_2+0_1.8/1.8_DP XMC-3_ SB I/J 2xRTN910A. | MW Parallel Link | MW PARALLEL LINK 9031K-Q00254 WITH 7G_2+0_1.8/1.8_DP_XMC-3 SB I/J. CARRY TRAFFIC ONLY 9031K. PLEASE ARRANGE EXTRA SB FOR INTERFERANCE INCASE . | MW PARALLEL LINK 9031K-Q00254 WITH 7G_2+0_1.8/1.8_DP_XMC-3 SB I/J. NE: 1. Install new RTN910A. 2. Install new XMC-3_SB I and J. 3. Install new antenna 7G_1.8m_DP. 4. Configure 7G_2+0_1.8m_DP_EPLA. 5. Carry traffic only 9031K. | MW PARALLEL LINK 9031K-Q00254 WITH 7G_2+0_1.8/1.8_DP_XMC-3 SB I/J. FE: 1. Install new RTN910A. 2. Install new XMC-3_SB I and J. 3. Install new antenna 7G_1.8m_DP. 4. Configure 7G_2+0_1.8m_DP_EPLA. 5. Carry traffic only 9031K. | XMC-3 | MS | 7G | 1.8 | 1.8 | Magicell | SQ202509030212-Magicell | iEzzpro | SQ202511190855-Iezzpro // SQ202511190857-Iezzpro | 2025-11-17 | 2025-11-10 | Completed | 2025-09-03 | 2025-09-30 | 2025-09-29 | 2025-09-29 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111192 |  | 2025-11-12 | 2025-11-14 | Completed | 2025-11-11 | 2025-11-12 | 2025-11-11 | 2025-11-14 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-25 | 2026-03-30 | 2026-03-30 | Kevin//Tan/6000033214 | Iezzpro TI | 2025-11-18 | 2025-11-25 | 2026-03-30 | 2026-04-01 | Kevin//Tan/6000033214 | Iezzpro TI | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-09 | 2025-11-18 | 2025-11-25 | 2026-04-06 | 2026-04-06 | Kevin//Tan/6000033214 | 2025-09-30: 2025-11-18; 2025-09-30: 2025-11-25; 2025-09-30: 2025-11-20; 2025-10-06: 2025-11-20 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202506050662-GTSB | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | HSU//MYET CHAE/6799000011
4717B_HU | Bagan Bharu | DU00005651415 | Northern | Perak | 5.133780 | 100.754800 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M_EPLA NE_4717B New 18G_1.2M(MAC)+OMT x1. Re-use existing RTN910A x1. New XMC_3, Sub B_Hi x1. FE_4057Z/A00797 New 18G_1.2M(MAC)+OMT x1. Re-use existing RTN910A x1. New XMC_3, Sub B_Lo x1. | MW Swap | Existing HW MW Link 15G_2+0_28M_256QAM_400M. Swap existing HW MW Link with new HW MW Link 18G_2+0_56M_512QAM_EPLA. Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_256QAM_400M and do not decom RTN910A. Site Impacted : 4717B. NE_4717B 1.Install New 18G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Hi x1. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link 18G_2+0_56M_512QAM_EPLA. Configure it. 6.Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_256QAM_400M and do not decom RTN910A. FE_4057Z/A00797 1.Install New 18G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Lo x1. Configure it. 4.Re-use existing vlan services and existing IBeam port at CP/PTN A00797. 5.Migrate traffic to new link 18G_2+0_56M_512QAM_EPLA. Configure it. 6.Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_256QAM_400M and do not decom RTN910A. | Existing HW MW Link 15G_2+0_28M_256QAM_400M. Swap existing HW MW Link with new HW MW Link 18G_2+0_56M_512QAM_EPLA. Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_256QAM_400M and do not decom RTN910A. Site Impacted : 4717B. NE_4717B 1.Install New 18G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Hi x1. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link 18G_2+0_56M_512QAM_EPLA. Configure it. 6.Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_256QAM_400M and do not decom RTN910A. | Existing HW MW Link 15G_2+0_28M_256QAM_400M. Swap existing HW MW Link with new HW MW Link 18G_2+0_56M_512QAM_EPLA. Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_256QAM_400M and do not decom RTN910A. Site Impacted : 4717B. FE_4057Z/A00797 1.Install New 18G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Lo x1. Configure it. 4.Re-use existing vlan services and existing IBeam port at CP/PTN A00797. 5.Migrate traffic to new link 18G_2+0_56M_512QAM_EPLA. Configure it. 6.Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_256QAM_400M and do not decom RTN910A. | XMC_3 | MAC | 18G | New 18G_1.2M(MAC)+OMT | New 18G_1.2M(MAC)+OMT | MTK | SQ202512170175-MTK | MTK | SQ202510230942-MTK // SQ202510230950-MTK | 2025-12-24 | 2025-12-17 | Completed | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251001B6 |  | 2025-10-03 | 2025-10-09 | Completed | 2025-10-02 | 2025-10-03 | 2025-10-01 | 2025-10-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-10-15 | 2025-10-31 | 2026-01-28 | 2026-01-28 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | AKMAL//BIN RAZALI/6794000078 |  | 2025-11-10 | 2025-10-15 | 2025-10-31 | 2026-03-24 | 2026-03-24 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-10-15 | 2025-10-31 | 2025-12-09 | 2025-12-09 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB
A00859_HU | A043B_A00859OD_T3_TLKBATIK2 | DU00005651416 | Northern | Perak | 4.197900 | 100.605200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M_EPLA NE_A00859 New 18G_0.6M(MDD) x1. New RTN910A(RTN01). New XMC_5D, Sub A_Lo x1. FE_4387B/A00301 New 18G_1.2M(MDD) x1. New RTN910A(RTN01). New XMC_5D, Sub A_Hi x1. New CAT6 cable x1. | MW Swap | Existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. Install new HW MW Link A00859(RTN01)-4387B(RTN01), 18G_2+0_56MHZ_512QAM_EPLA. Later, decom existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. Site Impacted : A00859. NE_A00859 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Migrate traffic A00859 via new HW MW Link A00859(RTN01)-4387B(RTN01), 18G_2+0_56MHZ_512QAM_EPLA. 9.Decom existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. FE_4387B/A00301 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port Gi0/0/2 at PTN/Cisco A00331. In which use previously by existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Decom existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. | Existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. Install new HW MW Link A00859(RTN01)-4387B(RTN01), 18G_2+0_56MHZ_512QAM_EPLA. Later, decom existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. Site Impacted : A00859. NE_A00859 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Migrate traffic A00859 via new HW MW Link A00859(RTN01)-4387B(RTN01), 18G_2+0_56MHZ_512QAM_EPLA. 9.Decom existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. | Existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. Install new HW MW Link A00859(RTN01)-4387B(RTN01), 18G_2+0_56MHZ_512QAM_EPLA. Later, decom existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. Site Impacted : A00859. FE_4387B/A00301 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port Gi0/0/2 at PTN/Cisco A00331. In which use previously by existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Decom existing SM MW Link ID_NT05656 A00859-A00301, 18G_1+0_28MHZ_2048QAM_233M. | XMC_5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_1.2M(MDD) x1. | MTK | SQ202510090411-MTK | MTK | SQ202510070044-MTK // SQ202510070047-MTK // SQ202511260482-MTK | 2026-01-22 | 2026-01-15 | Completed | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-09 | AMIRUL SYAHRINI BIN MOHD ZIN6000023342 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-30 | 2025-11-06 | 2025-10-30 | 2025-10-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092654 |  | 2025-09-27 | 2025-09-29 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-06 | 2025-10-24 | 2025-10-06 | 2025-10-06 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-10-06 | 2025-10-24 | 2025-10-08 | 2025-11-26 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-08 | 2025-10-06 | 2025-10-24 | 2025-10-18 | 2025-11-24 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-10-06 | 2025-10-24 | 2025-10-18 | 2025-11-25 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | NG HONG JIE7018000036 | Logistic Team | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | MAZELAN BIN RAMLI6798000096
Q02009_HU | Q120A_Q02009OD_T3_KGTEBAANBESAR | DU00005651417 | Sarawak | Sarawak | 2.492940 | 111.521130 |  |  |  | AUG 25 |  |  |  | 05. Doable |  | TSS+AA+TI | L1+ATP+PAC | 2xISM8 | MW Hardware Upgrade | MW HARDWARE UPGRADE Q02009-Q00618 FROM 13G_2+0 TO 13G_4+0_CA | MW HARDWARE UPGRADE Q02009-Q00618 FROM 13G_2+0 TO 13G_4+0 NE: 1. Reuse exisiting RTN910A. 2.Install ISM 8 at Slot 3. 3. Reuse exisitng ODU XMC_5D_SB A. 4. Reuse existing antenna. 5. Configure 13G_4+0_CA_800M. | MW HARDWARE UPGRADE Q02009-Q00618 FROM 13G_2+0 TO 13G_4+0 FE: 1. Reuse exisiting RTN910A. 2.Install ISM 8 at Slot 3. 3. Reuse exisitng ODU XMC_5D_SB A. 4. Reuse existing antenna. 5. Configure 13G_4+0_CA_800M. | [5 empty] | Trintel | SQ202507300505-Trintel | Trintel | SQ202508070591-Trintel // SQ202508070599-Trintel | 2025-11-17 | 2025-11-10 | Completed | 2025-07-25 | 2025-07-28 | 2025-07-25 | 2025-07-28 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110141 |  | 2025-11-02 | 2025-11-04 | Completed | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-04 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-08 | AINA MARINI//ATON/6794000115 | Trintel TI | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2026-01-19 | AINA MARINI//ATON/6794000115 | Trintel TI | 2026-04-12 | 2026-04-12 | 2026-04-12 | 2026-04-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-12 | 2025-11-03 | 2025-11-03 | 2025-11-03 |  | AINA MARINI//ATON/6794000115 | 2025-10-15: 2025-11-03; 2025-10-31: 2025-11-03; 2025-12-09: 2025-11-03; 2025-12-09: 2025-11-27 | [7 empty] | GTSB | SQ202506050662-GTSB | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-06-30 | HSU//MYET CHAE/6799000011
1042K_HU | B058A_B02266OD_LORONGABDMANANMERU | DU00005651418 | Central | Selangor | 3.112700 | 101.430620 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 23G_1+0_56M_512QAM. MW Remote Upgrade to HW 23G_1+0_112M_256QAM. Site Impacted : 1042K/B02266. NE_1042K/B02266 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz. FE_1099A 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz. | Link Existing HW 23G_1+0_56M_512QAM. MW Remote Upgrade to HW 23G_1+0_112M_256QAM. Site Impacted : 1042K/B02266. NE_1042K/B02266 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz. | Link Existing HW 23G_1+0_56M_512QAM. MW Remote Upgrade to HW 23G_1+0_112M_256QAM. Site Impacted : 1042K/B02266. FE_1099A 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz. | XMC-3 | MAC | 23G | 23G_0.6M(MAC) x1. | 23G_0.6M(MAC) x1. |  |  | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-07 | [15 empty] | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506050643-GTSB
4020Z_HU | KGSGKAP | DU00005651419 | Northern | Kedah | 6.059490 | 100.739810 | [7 empty] | 00. Integrated/RFS Done | 18/07 : CO Done | AA | PAC |  | MW Remote Upgrade | Link Existing HW 18G_1+0_28M_512QAM_196M. MW Remote Upgrade to HW 18G_1+0_56M_512QAM_395M. Site Impacted : 4056P NE_4056P 1.Existing ODU XMC-2 may remotely upgrade to BW 56MHz ONLY. FE_4020Z 1.Existing ODU XMC-2 may remotely upgrade to BW 56MHz ONLY. | Link Existing HW 18G_1+0_28M_512QAM_196M. MW Remote Upgrade to HW 18G_1+0_56M_512QAM_395M. Site Impacted : 4056P NE_4056P 1.Existing ODU XMC-2 may remotely upgrade to BW 56MHz ONLY. | Link Existing HW 18G_1+0_28M_512QAM_196M. MW Remote Upgrade to HW 18G_1+0_56M_512QAM_395M. Site Impacted : 4056P FE_4020Z 1.Existing ODU XMC-2 may remotely upgrade to BW 56MHz ONLY. | XMC_2 | MAC | 18G | 18G_SP_0.6M(MAC) x1. | 18G_SP_1.2M(MAC) x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-07-18 | [15 empty] | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | MAZELAN BIN RAMLI6798000096
S00335_HU | S098A_S00335OD_CB_KEMBARASAKTI | DU00005651420 | Sabah | Sabah | 5.329400 | 119.055800 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050649-GTSB | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q01724_HU | Q132A_Q01724OD_CB_RHKUPANG | DU00005651421 | Sarawak | Sarawak | 3.858017 | 113.934059 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2x RTN910A 2x ISM8 2X 1.8M MDD ANTENNA (13G) 1x ODU 13G XMC-5D SB A_HI 1x ODU 13G XMC-5D SB A_LO | MW Swap | Install 13G_2+0_256Qam_28Mhz_400Mbps to be swap with existing SM link Config EPLA for new link Impact site: Q01724, Q01725 Dismantle existing SM link | NE: 1. Install new IDU RTN910A 2. Install new 13G 1.8m MDD ANTENNA 3. Install new 13G XMC-5D sb A 4. Configure link 13G 2+0 28MHZ 256QAM EPLA 5. Dismantle existing SM link | FE: 1. Install new IDU RTN910A 2. Install new 13G 1.8m MDD ANTENNA 3. Install new 13G XMC-5D sb A 4. Configure link 13G 2+0 28MHZ 256QAM EPLA 5. Dismantle existing SM link | XMC-5D | MDD | 13G | 1.8m | 1.8m | Allstar | SQ202508070530-Allstar | Redtone | SQ202604150336-Redtone // SQ202604150349-Redtone | 2025-12-23 | 2025-12-16 | Completed | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-10 | 2025-12-03 | 2025-12-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-10 | 2025-12-03 | 2025-12-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022125 |  | 2026-02-22 | 2026-02-24 | Completed | 2026-02-21 | 2026-02-22 | 2026-02-21 | 2026-02-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | Roy//Lee/6000056316 |  | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-26 | Roy//Lee/6000056316 |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-03-02 | 2026-03-16 | 2026-03-02 | 2026-03-24 | ANDREW BIN JUHAN6000068232 | 2025-10-15: 2026-03-19; 2025-10-31: 2026-03-26; 2025-12-09: 2026-03-19; 2025-12-09: 2026-03-26 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202506050662-GTSB | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | AB.RAHMAN//BIN MAT NOOH/6237001519
P00155_HU | P033B_P00155OD_PRAIINDAREA4 | DU00005651422 | Northern | Penang | 5.348917 | 100.414433 | [7 empty] | 00. Integrated/RFS Done | 29/07: Access FE ACM Prai | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2x IDU RTN910A 2X 0.6m MAC_SP ANTENNA (18G) 1x ODU 18G XMC-3E SB_A HI 1x ODU 18G XMC-3E SB_A LO 1x SFP and Patch Cord | MW Swap | Install new link P00155-4088D with HW_18G_1+0_112Mhz_512QAM_889Mbps_0.6m/0.6m_SP_XMC-3E_SUB A_1.42KM Patching IDU to Cisco Celcom P00158 at FE Required new port 1G at Cisco Router Celcom Impact site: P00155 Dismantle existing link (SM): 18G_1+0 | NE: 1. Install new IDU RTN910A 2. Install new 18G 0.6m SP Antenna 3. Install new 18G XMC-3E sb A 4. Configure link 18G 1+0_ 112Mhz_512QAM 5. Decom existing link P00155-P00158 (SM) | FE: 1. Install new IDU RTN910A 2. Install new 18G 0.6m SP Antenna 3. Install new 18G XMC-3E sb A 4. Configure link 18G 1+0_ 112Mhz_512QAM 5. Patching IDU to Cisco Router Celcom P00158 6. Decom existing link P00155-P00158 (SM) | XMC-3E | MAC | 18G | 0.6m | 0.6m | GTSB | SQ202507110773-GTSB | GTSB | SQ202507110777-GTSB // SQ202507110781-GTSB // SQ202510030332-GTSB | 2026-03-17 | 2026-03-10 | Completed | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071551 |  | 2025-07-17 | 2025-08-18 | Completed | 2025-07-16 | 2025-07-17 | 2025-07-16 | 2025-08-18 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-22 | 2025-08-31 | 2025-08-22 | 2025-08-23 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-08-22 | 2025-08-31 | 2025-08-22 | 2025-12-13 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-22 | 2025-08-22 | 2025-08-31 | 2025-08-22 | 2026-01-22 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-08-22 | 2025-08-31 | 2025-08-22 | 2025-08-22 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | AB.RAHMAN//BIN MAT NOOH/6237001519
4803D_HU | Jalan Paboi (REL) | DU00005651423 | Northern | Penang | 5.258593 | 100.469374 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M NE_4803D New 18G_0.6M(MDD) x1. Re-use existing RTN910A(RTN01) New XMC_5D, Sub A_Hi x1. FE_4116B/P00172 New 18G_0.6M(MDD) x1. Re-use existing RTN910A(RTN01) New XMC_5D, Sub A_Lo x1. | MW Swap | Existing HW MW Link 18G_1+0_56M_512QAM. Swap existing HW MW Link with new HW MW Link 18G_1+0_112M_256QAM. Later, decom existing 18G ODU & existing 18G Antenna ONLY of existing HW MW Link 18G_1+0_56M_512QAM. Anyway, do not decom existing RTN910A at 4803D & 4116B/P00172. Site Impacted : 4803D. NE_4803D 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new XMC_5D, Sub A_Hi x1. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link 18G_1+0_112M_256QAM. Configure it. 6.Later, decom existing 18G ODU & existing 18G Antenna ONLY of existing HW MW Link 18G_1+0_56M_512QAM. Anyway, do not decom existing RTN910A at 4803D & 4116B. FE_4116B/P00172 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new XMC_5D, Sub A_Lo x1. Configure it. 4.Re-use existing vlan services and re-use existing PTN/Cisco port. 5.Migrate traffic to new link 18G_1+0_112M_256QAM. Configure it. 6.Later, decom existing 18G ODU & existing 18G Antenna ONLY of existing HW MW Link 18G_1+0_56M_512QAM. Anyway, do not decom existing RTN910A at 4803D & 4116B. | Existing HW MW Link 18G_1+0_56M_512QAM. Swap existing HW MW Link with new HW MW Link 18G_1+0_112M_256QAM. Later, decom existing 18G ODU & existing 18G Antenna ONLY of existing HW MW Link 18G_1+0_56M_512QAM. Anyway, do not decom existing RTN910A at 4803D & 4116B/P00172. Site Impacted : 4803D. NE_4803D 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new XMC_5D, Sub A_Hi x1. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link 18G_1+0_112M_256QAM. Configure it. 6.Later, decom existing 18G ODU & existing 18G Antenna ONLY of existing HW MW Link 18G_1+0_56M_512QAM. Anyway, do not decom existing RTN910A at 4803D & 4116B. | Existing HW MW Link 18G_1+0_56M_512QAM. Swap existing HW MW Link with new HW MW Link 18G_1+0_112M_256QAM. Later, decom existing 18G ODU & existing 18G Antenna ONLY of existing HW MW Link 18G_1+0_56M_512QAM. Anyway, do not decom existing RTN910A at 4803D & 4116B/P00172. Site Impacted : 4803D. FE_4116B/P00172 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new XMC_5D, Sub A_Lo x1. Configure it. 4.Re-use existing vlan services and re-use existing PTN/Cisco port. 5.Migrate traffic to new link 18G_1+0_112M_256QAM. Configure it. 6.Later, decom existing 18G ODU & existing 18G Antenna ONLY of existing HW MW Link 18G_1+0_56M_512QAM. Anyway, do not decom existing RTN910A at 4803D & 4116B. | XMC_5D | MDD | 18G | New 18G_0.6M(MDD) | New 18G_0.6M(MDD) | Magicell | SQ202508200574-Magicell | Magicell | SQ202510010665-Magicell // SQ202510010666-Magicell // SQ202511110809-Magicell | 2025-12-03 | 2025-11-26 | Completed | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-21 | 2025-08-28 | 2025-08-21 | 2025-08-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-12-03 | 2025-11-26 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092448 |  | 2025-09-30 | 2025-10-15 | Completed | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-03 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-13 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-06 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | NG HONG JIE7018000036 | Logistic Team | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | MAZELAN BIN RAMLI6798000096
C01461_HU | KG SALANG | DU00005651424 | Eastern | Pahang | 4.140320 | 102.016430 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_C01461 New 23G_SP_1.2M(MAC) x1. New RTN910A(RTN01). New XMC_3E, Sub A_Lo x1. FE_C01096 New 23G_SP_1.2M(MAC) x1. New RTN910A(RTN01). New XMC_3E, Sub A_Hi x1. New CAT6 cable x1. | MW Swap | Existing HW MW Link C01461-C01096, 15G_1+0_28MHZ_1024QAM_219M. Install new HW MW Link C01461(RTN01)-C01096(RTN02), 23G_1+0_112MHZ_512QAM. Later, decom existing MW Link C01461-C01096, 15G_1+0_28MHZ_1024QAM_219M. Site Impacted : C01461. NE_C01461 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Migrate traffic C01461 via new HW MW Link C01461(RTN01)-C01096(RTN01), 23G_1+0_112MHZ_512QAM. 9.Decom existing HW MW Link C01461-C01096, 15G_1+0_28MHZ_1024QAM_219M. FE_C01096 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new 1x XMC_3E, Sub A_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching port 8-EM6-1 of new RTN910A(RTN02) to port 8-EM6-2 of existing RTN910A, uplink HW MW Link_ET04617, C01096-C00127. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Decom existing HW MW Link C01461-C01096, 15G_1+0_28MHZ_1024QAM_219M. | Existing HW MW Link C01461-C01096, 15G_1+0_28MHZ_1024QAM_219M. Install new HW MW Link C01461(RTN01)-C01096(RTN02), 23G_1+0_112MHZ_512QAM. Later, decom existing MW Link C01461-C01096, 15G_1+0_28MHZ_1024QAM_219M. Site Impacted : C01461. NE_C01461 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Migrate traffic C01461 via new HW MW Link C01461(RTN01)-C01096(RTN01), 23G_1+0_112MHZ_512QAM. 9.Decom existing HW MW Link C01461-C01096, 15G_1+0_28MHZ_1024QAM_219M. | Existing HW MW Link C01461-C01096, 15G_1+0_28MHZ_1024QAM_219M. Install new HW MW Link C01461(RTN01)-C01096(RTN02), 23G_1+0_112MHZ_512QAM. Later, decom existing MW Link C01461-C01096, 15G_1+0_28MHZ_1024QAM_219M. Site Impacted : C01461. FE_C01096 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new 1x XMC_3E, Sub A_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching port 8-EM6-1 of new RTN910A(RTN02) to port 8-EM6-2 of existing RTN910A, uplink HW MW Link_ET04617, C01096-C00127. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Decom existing HW MW Link C01461-C01096, 15G_1+0_28MHZ_1024QAM_219M. | XMC_3E | MAC | 23G | New 23G_SP_1.2M(MAC) x1. | New 23G_SP_1.2M(MAC) x1. | GCI | SQ202507030684-GCI | GCI | SQ202507030671-GCI // SQ202507030675-GCI // SQ202508140737-GCI | 2025-08-13 | 2025-08-07 | Completed | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-08-06 | 2025-07-31 | 2025-07-31 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070403 |  | 2025-07-06 | 2025-07-07 | Completed | 2025-07-05 | 2025-07-06 | 2025-07-05 | 2025-07-07 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-07-29 | 2025-07-21 | 2025-07-22 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-22 | 2025-07-29 | 2025-07-21 | 2025-07-29 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | AKMAL//BIN RAZALI/6794000078 |  |  | 2025-07-22 | 2025-07-29 | 2025-07-21 | 2025-07-29 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-07-22 | 2025-07-29 | 2025-07-21 | 2025-07-22 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202506050644-GTSB
4459B_HU | Kg Bakar Bata | DU00005651425 | Northern | Perak | 4.385900 | 100.789200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M NE_4459B New 18G_1.2M(MAC)+OMT x1. Re-use existing RTN910A x1. New XMC_3, Sub B_Lo x1. FE_4325A/A00460 New 18G_1.2M(MAC)+OMT x1. Re-use existing RTN910A x1. New XMC_3, Sub B_Hi x1. | MW Swap | Existing HW MW Link 15G_2+0_28M_512QAM_448M. Swap existing HW MW Link with new HW MW Link 18G_1+0_112M_512QAM. Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_512QAM_448M and do not decom RTN910A. Site Impacted : 4459B. NE_4459B 1.Install New 18G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Lo x1. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link 18G_1+0_112M_512QAM. Configure it. 6.Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_512QAM_448M and do not decom RTN910A. FE_4325A/A00460 1.Install New 18G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Hi x1. Configure it. 4.Re-use existing vlan services and existing IBeam port at CP/PTN A00460. 5.Migrate traffic to new link 18G_1+0_112M_512QAM. Configure it. 6.Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_512QAM_448M and do not decom RTN910A. | Existing HW MW Link 15G_2+0_28M_512QAM_448M. Swap existing HW MW Link with new HW MW Link 18G_1+0_112M_512QAM. Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_512QAM_448M and do not decom RTN910A. Site Impacted : 4459B. NE_4459B 1.Install New 18G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Lo x1. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link 18G_1+0_112M_512QAM. Configure it. 6.Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_512QAM_448M and do not decom RTN910A. | Existing HW MW Link 15G_2+0_28M_512QAM_448M. Swap existing HW MW Link with new HW MW Link 18G_1+0_112M_512QAM. Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_512QAM_448M and do not decom RTN910A. Site Impacted : 4459B. FE_4325A/A00460 1.Install New 18G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Hi x1. Configure it. 4.Re-use existing vlan services and existing IBeam port at CP/PTN A00460. 5.Migrate traffic to new link 18G_1+0_112M_512QAM. Configure it. 6.Later, decom 15G ODU & 15G antenna ONLY of existing HW MW Link 15G_2+0_28M_512QAM_448M and do not decom RTN910A. | XMC_3 | MAC | 18G | New 18G_1.2M(MAC)+OMT | New 18G_1.2M(MAC)+OMT | Magicell | SQ202508200574-Magicell | Magicell | SQ202510010665-Magicell // SQ202510010666-Magicell | 2025-12-03 | 2025-11-26 | Completed | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-12-03 | 2025-11-26 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092723 |  | 2025-09-30 | 2025-11-21 | Completed | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-11-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-11-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-11-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-03 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-26 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-06 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | NG HONG JIE7018000036 | Logistic Team | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB
1149K_HU | B061F_B02239OD_JLNSETIAKUANG | DU00005651426 | Central | Selangor | 3.237799 | 101.536759 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_56M NE_B02239 New 23G_1.2M(MS) x1. Re-use existing RTN910A x1. New XMC_3, Sub A_Lo x2. FE_B00258 New 23G_1.2M(MS) x1. Re-use existing RTN910A x1. New XMC_3, Sub A_Hi x2. | MW Swap | Existing HW MW Link 15G_2+0_28M_512QAM_EPLA. Swap existing HW MW Link with new HW MW Link 23G_2+0_56M_512QAM_EPLA. Later, decom existing 15G ODU and 15G antenna ONLY of HW MW Link 15G_2+0_28M_512QAM_EPLA. Do not decom RTN910A at both NE(B02239) and at FE(B00258). Site Impacted : B02239. NE_B02239 1.Install new 23G_1.2M(MS) x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Lo x2. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link new HW MW Link 23G_2+0_56M_512QAM_EPLA. Configure it. 6.Later, decom existing 15G ODU and 15G antenna ONLY of HW MW Link 15G_2+0_28M_512QAM_EPLA. 7.Do not decom RTN910A at both NE(B02239) and at FE(B00258). FE_B00258 1.Install new 23G_1.2M(MS) x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Lo x2. Configure it. 4.Re-use existing vlan services and existing port at IBeam. 5.Later, decom existing 15G ODU and 15G antenna ONLY of HW MW Link 15G_2+0_28M_512QAM_EPLA. 6.Do not decom RTN910A at both NE(B02239) and at FE(B00258). | Existing HW MW Link 15G_2+0_28M_512QAM_EPLA. Swap existing HW MW Link with new HW MW Link 23G_2+0_56M_512QAM_EPLA. Later, decom existing 15G ODU and 15G antenna ONLY of HW MW Link 15G_2+0_28M_512QAM_EPLA. Do not decom RTN910A at both NE(B02239) and at FE(B00258). Site Impacted : B02239. NE_B02239 1.Install new 23G_1.2M(MS) x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Lo x2. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link new HW MW Link 23G_2+0_56M_512QAM_EPLA. Configure it. 6.Later, decom existing 15G ODU and 15G antenna ONLY of HW MW Link 15G_2+0_28M_512QAM_EPLA. 7.Do not decom RTN910A at both NE(B02239) and at FE(B00258). | Existing HW MW Link 15G_2+0_28M_512QAM_EPLA. Swap existing HW MW Link with new HW MW Link 23G_2+0_56M_512QAM_EPLA. Later, decom existing 15G ODU and 15G antenna ONLY of HW MW Link 15G_2+0_28M_512QAM_EPLA. Do not decom RTN910A at both NE(B02239) and at FE(B00258). Site Impacted : B02239. FE_B00258 1.Install new 23G_1.2M(MS) x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub A_Lo x2. Configure it. 4.Re-use existing vlan services and existing port at IBeam. 5.Later, decom existing 15G ODU and 15G antenna ONLY of HW MW Link 15G_2+0_28M_512QAM_EPLA. 6.Do not decom RTN910A at both NE(B02239) and at FE(B00258). | XMC-3 | MS | 23G | 23G_1.2M(MS) x1. | 23G_1.2M(MS) x1. | Magicell | SQ202506190624-Magicell | Magicell | SQ202508070545-Magicell // SQ202508070551-Magicell | 2025-08-06 | 2025-07-28 | Completed | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-28 | 2025-08-06 | 2025-07-28 | 2025-07-28 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061962 |  | 2025-06-20 | 2025-06-23 | Completed | 2025-06-19 | 2025-06-20 | 2025-06-19 | 2025-06-23 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-30 | 2026-06-11 | 2025-06-30 | 2025-07-18 | MOHD//SAFRI BIN ARIF/7018000166 |  | 2025-06-30 | 2026-06-11 | 2025-06-30 | 2025-07-18 | MOHD//SAFRI BIN ARIF/7018000166 |  | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-02 | 2025-06-30 | 2026-06-11 | 2025-06-30 | 2025-07-17 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-06-30 | 2026-06-11 | 2025-06-30 | 2025-07-01 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202506050643-GTSB
8067C_HU | Bandar Putra Kemaman | DU00005651427 | Eastern | Terengganu | 4.193558 | 103.412600 | [7 empty] | 00. Site Out/Drop | 19/6: Dropped from GOP list under BO/NOC |  |  |  | Cancel / Drop | Under BO/NOC | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050644-GTSB | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | AB.RAHMAN//BIN MAT NOOH/6237001519
K00923_HU | K007A_K00923OD_WT_TMN_LAGENDA_PSERAI | DU00005651428 | Northern | Kedah | 5.500467 | 100.539430 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_K00923 New 23G_DP_0.3M(MAC)+OMT x1. New RTN910A(RTN01). New XMC_3E, Sub B_Lo x1. FE_P00114 New 23G_SP_1.2M(MAC) x1. New RTN910A(RTN01). New XMC_3E, Sub B_Hi x1. | MW Swap | Existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M. Install new HW MW Link K00923(RTN01)-P00114(RTN01), 23G_1+0_112MHZ_512QAM_889M. Later, decom existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M. Site Impacted : K00923/4614C. NE_K00923/4614C 1.Install new 23G_DP_0.3M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Migrate traffic K00923 via new HW MW Link K00923(RTN01)-P00114(RTN01), 23G_1+0_112MHZ_512QAM_889M. 9.Later, decom existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M. FE_P00114 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub A_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port of PTN/Cisco(Gi0/0/1) 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Later, decom existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M. | Existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M Install new HW MW Link K00923(RTN01)-P00114(RTN01), 23G_1+0_112MHZ_512QAM_889M. Later, decom existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M. Site Impacted : K00923/4614C. NE_K00923/4614C 1.Install new 23G_DP_0.3M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Migrate traffic K00923 via new HW MW Link K00923(RTN01)-P00114(RTN01), 23G_1+0_112MHZ_512QAM_889M. 9.Later, decom existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M. FE_P00114 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub A_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port of PTN/Cisco(Gi0/0/1) 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Later, decom existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M. | Existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M Install new HW MW Link K00923(RTN01)-P00114(RTN01), 23G_1+0_112MHZ_512QAM_889M. Later, decom existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M. Site Impacted : K00923/4614C. FE_P00114 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub A_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port of PTN/Cisco(Gi0/0/1) 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Later, decom existing SM MW Link_ID NT05421(K00923-P00114), 18G_1+0_56MHZ_1024QAM_471M. | XMC_3E | MAC | 23G | 23G_DP_0.3M(MAC)+OMT x1. | 23G_SP_1.2M(MAC) x1. | Magicell | SQ202511270710-Magicell | Magicell | SQ202511260111-Magicell // SQ202511260115-Magicell | 2025-12-09 | 2025-12-02 | Completed | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-11-25 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071144 |  | 2025-07-12 | 2025-07-16 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-10 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-24 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-10 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | MAZELAN BIN RAMLI6798000096
S00177_HU | S091A_S00177OD_SIMEDARBY | DU00005651429 | Sabah | Sabah | 5.640047 | 118.178880 | [7 empty] | 07. Solution Changed |  |  |  |  | Under NIC | existing 7G and Decom link Wait to MOCN 7505B (30/6/2025 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050649-GTSB | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | HSU//MYET CHAE/6799000011
2586B_HU | Jalan Zuhrah | DU00005651430 | Central | Selangor | 3.163709 | 101.541608 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_56M NE_2586B New 23G_0.3M(MAC)+OMT x1. New RTN910A x1. New XMC_3, Sub A_Hi x2. FE_1364A New 23G_0.3M(MAC)+OMT x1. New RTN910A x1. New XMC_3, Sub A_Lo x2. | MW Swap | Existing HW MW Link 23G_1+0_56M_512QAM. Swap existing HW MW Link with new HW MW Link 23G_2+0_56M_512QAM_EPLA. Later, decom existing HW MW Link 23G_1+0_56M_512QAM. **Team at site need to confirm LOS clearances for existing HW MW Link HW MW Link 23G_1+0_56M_512QAM as RSL degraded -40 ~ -43dBm, worry on partial LOS Block happened. If YES, do not to perform MW Swap** Site Impacted : 2586B. NE_2586B 1.Install new 23G_0.3M(MAC) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_3, Sub A_Hi x2. Configure it. 4.Configure DCN Inband. 5.Re-use existing vlan services. 6.Enable port 8-EM6-1 of new RTN910A(RTN02) and patching to BBU 2586B. 7.Migrate traffic to new link new HW MW Link 23G_2+0_56M_512QAM_EPLA. Configure it. 8.Later, decom existing HW MW Link 23G_1+0_56M_512QAM. FE_1364A 1.Install new 23G_0.3M(MAC) x1. 2.Install new RTN910A(RTN03) x1. 3.Install new XMC_3, Sub A_Lo x2. Configure it. 4.Configure DCN Inband. 5.Enable port 8-EM6-1 and port 8-EM6-2 of new RTN910A(RTN03) and perform cascading to existing RTN910A(RTN01) port 8-EM6-1 and to existing RTN910A(RTN05) port 8-EM6-1. 6.Re-use existing vlan services and existing port at IBeam. 7.Later, decom existing HW MW Link 23G_1+0_56M_512QAM. Remain IDU due to share with other child | Existing HW MW Link 23G_1+0_56M_512QAM. Swap existing HW MW Link with new HW MW Link 23G_2+0_56M_512QAM_EPLA. Later, decom existing HW MW Link 23G_1+0_56M_512QAM. **Team at site need to confirm LOS clearances for existing HW MW Link HW MW Link 23G_1+0_56M_512QAM as RSL degraded -40 ~ -43dBm, worry on partial LOS Block happened. If YES, do not to perform MW Swap** Site Impacted : 2586B. NE_2586B 1.Install new 23G_0.3M(MAC) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_3, Sub A_Hi x2. Configure it. 4.Configure DCN Inband. 5.Re-use existing vlan services. 6.Enable port 8-EM6-1 of new RTN910A(RTN02) and patching to BBU 2586B. 7.Migrate traffic to new link new HW MW Link 23G_2+0_56M_512QAM_EPLA. Configure it. 8.Later, decom existing HW MW Link 23G_1+0_56M_512QAM. | Existing HW MW Link 23G_1+0_56M_512QAM. Swap existing HW MW Link with new HW MW Link 23G_2+0_56M_512QAM_EPLA. Later, decom existing HW MW Link 23G_1+0_56M_512QAM. **Team at site need to confirm LOS clearances for existing HW MW Link HW MW Link 23G_1+0_56M_512QAM as RSL degraded -40 ~ -43dBm, worry on partial LOS Block happened. If YES, do not to perform MW Swap** Site Impacted : 2586B. FE_1364A 1.Install new 23G_0.3M(MAC) x1. 2.Install new RTN910A(RTN03) x1. 3.Install new XMC_3, Sub A_Lo x2. Configure it. 4.Configure DCN Inband. 5.Enable port 8-EM6-1 and port 8-EM6-2 of new RTN910A(RTN03) and perform cascading to existing RTN910A(RTN01) port 8-EM6-1 and to existing RTN910A(RTN05) port 8-EM6-1. 6.Re-use existing vlan services and existing port at IBeam. 7.Later, decom existing HW MW Link 23G_1+0_56M_512QAM. Remain IDU due to share with other child | XMC-3 | MAC | 23G | 23G_0.3M(MAC)+OMT x1. | 23G_0.3M(MAC)+OMT x1. | Magicell | SQ202506190624-Magicell | Magicell | SQ202508070545-Magicell // SQ202508070551-Magicell | 2025-07-18 | 2025-07-14 | Completed | 2025-06-24 | 2025-06-24 | 2025-06-25 | 2025-06-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-11 | 2025-07-18 | 2025-07-11 | 2025-07-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061961 |  | 2025-06-23 | 2025-07-17 | Completed | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-07-17 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-22 | 2026-06-18 | 2025-06-23 | 2025-07-17 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-06-22 | 2026-06-18 | 2025-06-23 | 2025-07-17 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-26 | 2025-06-22 | 2026-06-18 | 2025-06-23 | 2025-07-17 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-06-22 | 2026-06-18 | 2025-06-23 | 2025-06-26 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202506050643-GTSB
N00346_HU | KG LONDAH | DU00005651431 | Southern | Sembilan | 2.630150 | 102.585801 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2x IDU RTN910A 2X 1.2M MDD ANTENNA (15G) 1x ODU 15G XMC-5D SB_A HI 1x ODU 15G XMC-5D SB_A LO | MW Swap | MW SWAP LINK N00346-N00109 WITH HUAWEI_15G_2+0_28MHZ_512QAM_448Mbps_1.2M/1.2M_MDD_XMC-5D_SUB A_5.24KM IMPACTED: N00346 DISMANTLE EXISTING LINK (SM) | NE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND A 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. DISMANTLE EXISTING LINK (SM) | FE: 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND A 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. CONNECT IDU TO CISCO ROUTER FOLLOW EXISTING CONNECTION 6. DISMANTLE EXISTING LINK (SM) | XMC-5D | MDD | 15G | 1.2m | 1.2m | GCI | SQ202506260797-GCI | GCI | SQ202506260788-GCI // SQ202506260793-GCI | 2025-08-13 | 2025-08-07 | Completed | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-28 | 2025-08-06 | 2025-07-28 | 2025-07-28 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062625 |  | 2025-06-27 | 2025-07-02 | Completed | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-07-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-10 | 2025-07-17 | 2025-07-10 | 2025-07-10 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-10 | 2025-07-17 | 2025-07-10 | 2025-07-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-11 | 2025-07-10 | 2025-07-17 | 2025-07-10 | 2025-07-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-07-10 | 2025-07-17 | 2025-07-10 | 2025-07-10 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202506050664-GTSB | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q02313_HU | SG RAIT | DU00005651432 | Sarawak | Sarawak | 4.245760 | 113.948730 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_Q02313 New 23G_SP_1.2M(MAC) x1. New RTN910A(RTN01). New XMC_3E, Sub B_Hi x1. FE_9507A/Q01733 New 23G_SP_1.2M(MAC) x1. New RTN910A(RTN01). New XMC_3E, Sub B_Lo x1. New CAT6 cable x1 with suitable length.(Patching from xD Cabinet to xC Cabinet) | MW New Link / Reroute | Existing SM MW Link_ID SW04230(Q02313-Q00578), 18G_1+0_28MHZ_512QAM_200M. Install new HW MW Link Q02313(RTN01)-9507A(RTN03), 23G_1+0_112MHZ_512QAM_889M. Later, decom existing SM MW Link_ID SW04230(Q02313-Q00578), 18G_1+0_28MHZ_512QAM_200M. Site Impacted : Q02313. NE_Q02313 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new xD vlan DCN and vlan services. 7.Migrate traffic Q02313 via new HW MW Link Q02313(RTN01)-9507A(RTN03), 23G_1+0_112MHZ_512QAM_889M. 8.Later, decom existing SM MW Link_ID SW04230(Q02313-Q00578), 18G_1+0_28MHZ_512QAM_200M. FE_9507A/Q01733 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN03) x1. 3.Install new 1x XMC_3E, Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN03). 5.Perform patching between port 8-EM6-1 of new RTN910A(RTN03) and new port of PTN/Cisco at Q01733. 6.Request new xC vlan DCN and vlan services. 7.Migrate traffic Q02313 to new port of PTN/Cisco at Q01733. 8.Later, decom existing SM MW Link_ID SW04230(Q02313-Q00578), 18G_1+0_28MHZ_512QAM_200M. | Existing SM MW Link_ID SW04230(Q02313-Q00578), 18G_1+0_28MHZ_512QAM_200M. Install new HW MW Link Q02313(RTN01)-9507A(RTN03), 23G_1+0_112MHZ_512QAM_889M. Later, decom existing SM MW Link_ID SW04230(Q02313-Q00578), 18G_1+0_28MHZ_512QAM_200M. Site Impacted : Q02313. NE_Q02313 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new xD vlan DCN and vlan services. 7.Migrate traffic Q02313 via new HW MW Link Q02313(RTN01)-9507A(RTN03), 23G_1+0_112MHZ_512QAM_889M. 8.Later, decom existing SM MW Link_ID SW04230(Q02313-Q00578), 18G_1+0_28MHZ_512QAM_200M. | Existing SM MW Link_ID SW04230(Q02313-Q00578), 18G_1+0_28MHZ_512QAM_200M. Install new HW MW Link Q02313(RTN01)-9507A(RTN03), 23G_1+0_112MHZ_512QAM_889M. Later, decom existing SM MW Link_ID SW04230(Q02313-Q00578), 18G_1+0_28MHZ_512QAM_200M. Site Impacted : Q02313. FE_9507A/Q01733 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN03) x1. 3.Install new 1x XMC_3E, Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN03). 5.Perform patching between port 8-EM6-1 of new RTN910A(RTN03) and new port of PTN/Cisco at Q01733. 6.Request new xC vlan DCN and vlan services. 7.Migrate traffic Q02313 to new port of PTN/Cisco at Q01733. 8.Later, decom existing SM MW Link_ID SW04230(Q02313-Q00578), 18G_1+0_28MHZ_512QAM_200M. | XMC_3E | MAC | 23G | 23G_SP_1.2M(MAC) x1. | 23G_SP_1.2M(MAC) x1. | Magicell | SQ202509030212-Magicell | Allstar | SQ202508070557-Allstar // SQ202508070574-Allstar | 2025-11-17 | 2025-11-10 | Completed | 2025-09-03 | 2025-09-30 | 2025-09-11 | 2025-09-11 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-07 | 2025-10-10 | 2025-10-07 | 2025-10-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080796 |  | 2025-08-08 | 2025-08-27 | Completed | 2025-08-07 | 2025-08-08 | 2025-08-07 | 2025-08-27 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-25 | 2025-10-31 | 2025-10-25 | 2025-10-25 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-10-25 | 2025-10-31 | 2025-11-13 | 2025-11-13 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-07 | 2025-10-25 | 2025-10-31 | 2025-11-15 | 2025-11-15 | TONI//ANAK KUMBONG/6798000163 | 2025-10-25 | 2025-10-31 | 2025-10-25 | 2025-10-25 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-27 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202506050662-GTSB | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | MAZELAN BIN RAMLI6798000096
Q02033_HU | Q118B_Q02033OD_T3_COASTALHIGHWAYPLANTATIONCAMP3 | DU00005651433 | Sarawak | Sarawak | 3.461900 | 113.385940 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2xISM8 | MW Hardware Upgrade | MW HARDWARE UPGRADE Q02033-Q00704 (SW03831) FROM 13G_2+0 TO 13G_4+0_CA_256QAM | MW HARDWARE UPGRADE Q02033-Q00704 (SW03831) FROM 13G_2+0 TO 13G_4+0_CA NE: 1. Reuse exisitng RTN910A. 2. Install new 1xISM 8 at slot 3. 3. Reuse exisitng XMC-5D_SB A. 4. Reuse exisitng antenna. 5. Configure 13G_4+0_CA_256QAM | MW HARDWARE UPGRADE Q02033-Q00704 (SW03831) FROM 13G_2+0 TO 13G_4+0_CA FE: 1. Reuse exisitng RTN910A. 2. Install new 1xISM 8 at slot 3. 3. Reuse exisitng XMC-5D_SB A. 4. Reuse exisitng antenna. 5. Configure 13G_4+0_CA_256QAM | [5 empty] | Trintel | SQ202509040637-Trintel | Trintel | SQ202508070591-Trintel // SQ202508070599-Trintel |  |  | Ongoing | 2025-11-10 | 2025-11-11 | 2025-11-11 | 2025-11-11 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25110582 |  | 2025-11-06 | 2025-11-06 | Completed | 2025-11-05 | 2025-11-06 | 2025-11-05 | 2025-11-06 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-12-03 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-12-04 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-19 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-12-06 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2025-11-04: 2025-11-08; 2025-11-04: 2025-11-08; 2025-11-04: 2025-11-08; 2025-11-10: 2025-11-08 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202506050662-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | HSU//MYET CHAE/6799000011
B02043_HU | B058E_B02043OD_MN_BUSUTBARU | DU00005651434 | Central | Selangor | 2.917270 | 101.584896 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1.2 DP 2+0 | MW New Link / Reroute | INSTALL NEW MW LINK B02043-2728C WITH HUAWEI_18G_2+0_56MHZ_0.6m/0.6m MDD_5KM | MW LINK B02043-2728C WITH HUAWEI_18G_2+0_56MHZ_0.6M/0.6M MDD NE:1. Install new HW RTN910A.2. Connect new IF cable x 2 from ODU to Slot 7-1, 7-23. Install new HW 0.6m DP antenna.4. Install new XMC-5D PRO ODU (SB A)5. Configure link 18G_2+0_56MHz 6. DISMANTLE CELCOM SM MW LINK B02043-B01441 | MW LINK B02043-2728C WITH HUAWEI_18G_2+0_56MHZ_0.6M/0.6M MDD FE:1. Install new HW RTN910A.2. Connect new IF cable x 2 from ODU to Slot 7-1, 7-23. Install new HW 0.6m MDD antenna.4. Install new XMC-5D PRO ODU (SB A)5. Configure link 18G_2+0_56MHz6. Patch to existing IDU. 6. DISMANTLE CELCOM SM MW LINK B02043-B01441 | XMC-5D PRO | MDD | 18G | 0.6 | 0.6 | Magicell | SQ202506190624-Magicell | Magicell | SQ202508070545-Magicell // SQ202508070551-Magicell | 2025-10-31 | 2025-10-24 | Completed | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | NUR FATIHAH BINTI AYOB7018000236 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | NUR FATIHAH BINTI AYOB7018000236 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-16 | 2025-07-18 | 2025-07-16 | 2025-07-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-24 | 2025-10-31 | 2025-10-24 | 2025-10-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070703 |  | 2025-07-09 | 2025-07-08 | Completed | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-08 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-21 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-21 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-10 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-21 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-10 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | NG HONG JIE7018000036 | Logistic Team | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506050643-GTSB | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | LIM//WEI CHONG/6798000110
4676B_HU | SgTiang Kedah | DU00005651435 | Northern | Kedah | 5.989090 | 100.596594 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | SFP and Pacth cord | BBU Patching | Patching BBU 4676B from RTN950 RTN02 to RTN910A RTN02 (at NE only) | Patching BBU 4676B from RTN950 RTN02 to RTN910A RTN02 | [6 empty] | Magicell | SQ202511260138-Magicell | Magicell | SQ202511030393-Magicell | 2025-12-23 | 2025-12-16 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | AHMAD RASHIDI BIN SAFRI7018000135 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-05 | 2025-12-12 | 2025-12-05 | 2025-12-05 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071146 |  | 2025-07-12 | 2025-07-16 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-21 | MHD FARID/BIN/NGADININ ADININ/6000054868 | Magicell TI | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-27 | MHD FARID/BIN/NGADININ ADININ/6000054868 | Magicell TI | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | AKMAL//BIN RAZALI/6794000078 |  | 2025-11-27 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-27 | MHD FARID/BIN/NGADININ ADININ/6000054868 | 2025-07-07: 2025-10-30; 2025-07-07: 2025-10-30; 2025-07-07: 2025-10-30; 2025-07-10: 2025-11-27 |  |  | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | AB.RAHMAN//BIN MAT NOOH/6237001519
K00051_HU | K013A_K00051OD_CB_TITIBAKONG | DU00005651436 | Northern | Kedah | 5.810423 | 100.378713 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M_EPLA NE_K00051 New 18G_1.2M(MDD) x1. New RTN910A(RTN01). New XMC_5D, Sub B_Hi x1. FE_K00825 New 18G_1.2M(MDD) x1. New RTN910A(RTN01). New XMC_5D, Sub B_Lo x1. New CAT6 cable x1. | MW Swap | Existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. Install new HW MW Link K00051(RTN01)-K00825(RTN01), 18G_2+0_56MHZ_512QAM_EPLA. Later, decom existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. Site Impacted : K00051. NE_K00051 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Migrate traffic K00051 via new HW MW Link K00051(RTN01)-K00825(RTN01), 18G_2+0_56MHZ_512QAM_EPLA. 9.Decom existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. FE_K00825 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port Gi0/0/1 at PTN/Cisco K00825. In which use previously by existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Decom existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. | Existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. Install new HW MW Link K00051(RTN01)-K00825(RTN01), 18G_2+0_56MHZ_512QAM_EPLA. Later, decom existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. Site Impacted : K00051. NE_K00051 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Migrate traffic k00051 via new HW MW Link K00051(RTN01)-K00825(RTN01), 18G_2+0_56MHZ_512QAM_EPLA. 9.Decom existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. | Existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. Install new HW MW Link K00051(RTN01)-K00825(RTN01), 18G_2+0_56MHZ_512QAM_EPLA. Later, decom existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. Site Impacted : K00051. FE_K00825 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing port Gi0/0/1 at PTN/Cisco K00825. In which use previously by existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. Configure it. 6.Create new In Band DCN. 7.Re-use existing xC vlan services. 8.Decom existing SM MW Link ID_NT05794 K00051-K00825, 13G_2+0_28MHZ_2048QAM_LAG_466M. | XMC_5D | MDD | 18G | 18G_1.2M(MDD) x1. | 18G_1.2M(MDD) x1. | MTK | SQ202512170175-MTK | MTK | SQ202510230942-MTK // SQ202510230950-MTK |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY251001B4 |  | 2025-10-03 | 2025-10-09 | Completed | 2025-10-02 | 2025-10-03 | 2025-10-01 | 2025-10-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-15 | 2026-03-03 | 2026-03-03 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2026-01-09 | 2026-01-15 | 2026-03-05 | 2026-03-05 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | AKMAL//BIN RAZALI/6794000078 |  | 2025-11-01 | 2026-01-09 | 2026-01-15 | 2026-03-05 | 2026-03-05 | DZULFAIZAL//BIN MAULUF/8225000001 | 2026-01-09 | 2026-01-15 | 2026-01-23 | 2026-01-23 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | MAZELAN BIN RAMLI6798000096
3067C_AD | Putrajaya Hospital IB | DU00005666504 | Central | Putrajaya | 2.929200 | 101.674400 | [7 empty] | 02. Pending Access | 23/6: Special site request from CD, task will delivery by Chai HF (iMacro) | TSS+TI |  | 1x RTN01 | IDU-IPRAN | 1. Install IDU RTN 910A. 2. Reengineering 3067C to new IDU RTN 910A. | [7 empty] | Datasco | SQ202507020634-Datasco | Datasco | SQ202507020642-Datasco | 2025-11-28 | 2025-11-22 | Completed | 2025-06-23 | 2025-07-23 | 2025-06-23 | 2025-06-23 | MOHAMAD//ZULFAKAAR BIN SHAMSUDIN/7019000075 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | ATIQAH//BINTI ABDUL MURAD/7019000113 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-08-06 | 2025-07-31 | 2025-07-31 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-21 | 2025-11-28 | 2025-11-21 | 2025-11-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061039 |  | 2025-06-11 | 2025-06-12 | Completed | 2025-06-10 | 2025-06-11 | 2025-06-10 | 2025-06-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202507080560-GTSB
K00059_LOS | K013A_K00059OD_CB_TMGUNUNGJERAI | DU00005666505 | Northern | Kedah | 5.786440 | 100.433400 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | TSS Survey Done Under DU ID K00059 , DU CODE DU00002880859 | TSS Survey Done Under DU ID K00059 , DU CODE DU00002880859 | [12 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2161A-1798B | MASJID ZAKARIA | DU00004715256 | Central | Selangor | 3.251120 | 101.723702 | WK04 | JAN 24 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 21/1/2025 : Cutover done 20/1/2025 : Cancel proceed due to skylift issue parking 13/1/2025 : STEALTH - 24M Lampole - NE site 2161A MASJID ZAKARIA, Digi OB - 3M Bipod - RT - FE site 1798B Gombak Utara | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2 x RTN910A 1 x 23G XMC3 sub B Lo 1 x 23G XMC3 sub B Hi | MW Hardware Upgrade | To swap IDU at NE and FE from RTN950 to RTN910A To swap ODU at NE and FE from XMC2 to XMC3 Upgrade link to 112MHz Impact site: 2161A Tx route: 2161A-1798B-1007A NE (2161A) 1. Swap existing RTN950 to RTN910A 2. Transfer IF cable to 7-ISM8-1 3. Swap XMC2 ODU to XMC3 ODU and Configure 112MHz 4. Migrate 2161A to new link NE (1798B) 1. Swap existing RTN950 to RTN910A 2. Transfer ISV3 from RTN02 slot 1 and 2 (link 1798B-1007A) to RTN910A slot 3 and 4 3. Transfer existing 2+0 link 1798B-1007A to RTN910A slot 3 and 4 ISV3 4. Transfer existing link 2161A-1798B to 7-ISM8-1 5. Swap XMC2 ODU to XMC3 ODU and Configure 112MHz | [7 empty] | GCI | SQ202501140147-GCI | GCI | SQ202501140131-GCI // SQ202504150088-GCI | 2025-02-24 | 2025-02-24 | Completed | 2025-01-02 | 2025-01-22 | 2025-01-22 | 2025-01-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | TSSR Approved by CD. | DOWMY25010845 |  | 2025-01-09 | 2025-01-08 | Completed | 2025-01-08 | 2025-01-09 | 2025-01-08 | 2025-01-08 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-21 | 2025-01-28 | 2025-01-20 | 2025-01-20 | SYEDMOHAMAD//FARISAIMAN/6800000274 | GCI TI | 2025-01-21 | 2025-01-28 | 2025-01-20 | 2025-02-05 | SYEDMOHAMAD//FARISAIMAN/6800000274 | GCI TI | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-21 | 2025-01-21 | 2025-01-28 | 2025-01-20 | 2025-02-03 | SYEDMOHAMAD//FARISAIMAN/6800000274 | 2025-01-21 | 2025-01-28 | 2025-01-20 | 2025-01-21 | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
9054A | Asa Jaya(SACOFA) | DU00004872438 | Sarawak | Sarawak | 1.544498 | 110.611708 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | Cat6 cable | BBU Patching | 1) Patch 9054A BBU to IDU 9054A RTN01 GE2 2) Migrate 9054A to xD network |  |  | N/A | N/A | N/A | N/A | N/A | Magicell | SQ202501210444-Magicell | Magicell | SQ202501090069-Magicell // SQ202504260208-Magicell | 2025-02-21 | 2025-02-21 | Completed | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-01-20 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2025-01-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2025-01-03 | 2025-01-08 | Completed | 2025-01-03 | 2025-01-03 | 2025-01-08 | 2025-01-08 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-08 | 2025-01-15 | 2025-01-08 | 2025-01-09 | WATSON ANAK MAMBA7018000213 | Magicell TI | 2025-01-08 | 2025-01-15 | 2025-01-08 | 2025-01-09 | WATSON ANAK MAMBA7018000213 | Magicell TI | 2025-01-08 | 2025-01-08 | 2025-01-08 | 2025-01-08 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-08 | 2025-01-10 | WATSON ANAK MAMBA7018000213 | 2026-01-09: 2025-01-08; 2026-01-15: 2025-01-15; 2026-01-23: 2025-01-08; 2026-01-23: 2025-01-08 |  |  | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045
9240B-9372B | Permai timur | DU00004904422 | Sarawak | Sarawak | 2.306580 | 111.896872 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 1+0 112MHz 0.6m/0.6m XMC3 NE: 1) 1xRTN910A 2) 1x23GHz XMC3 Sub A Lo 3) 1x23GHz 0.6m SP FE: 1) 1xISM8 card 2) 1x23GHz XMC3 Sub A Hi 3) 1x23GHz 0.6m SP | MW Swap | Existing link Huawei NEC link congested. To swap Existing link NEC 23GHz 1+0 56MHz with new Huawei link 23GHz 1+0 112MHz Impacted sites: 9240B Current Tx route: 9240B-9372B-LL-9368A New Tx route: 9240B-9372B-LL-9368A NE (9240B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link FE (9372B): 1) Install new ISM8 card at 9372B RTN01 slot 3 2) Install new link at RTN01 3-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | NE (9240B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | FE (9372B): 1) Install new ISM8 card at 9372B RTN01 slot 3 2) Install new link at RTN01 3-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | XMC3 | MAC SP | 23G | 0.6m | 0.6m | MTK | SQ202502050339-MTK | Trintel | SQ202503050499-Trintel // SQ202504260214-Trintel | 2025-02-14 | 2025-02-11 | Completed | 2025-02-04 | 2025-02-04 | 2025-02-04 | 2025-02-04 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-11 | 2025-02-14 | 2025-02-11 | 2025-02-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-11 | 2025-02-14 | 2025-02-11 | 2025-02-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-11 | 2025-02-14 | 2025-02-11 | 2025-02-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022477 |  | 2025-02-25 | 2025-02-25 | Completed | 2025-02-24 | 2025-02-25 | 2025-02-24 | 2025-02-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2025-03-25 | 2025-03-04 | 2025-03-05 | CHRISTINE IVY ANAK GIRIN7667000067 | Trintel TI | 2025-02-25 | 2025-03-25 | 2025-03-04 | 2025-03-06 | CHRISTINE IVY ANAK GIRIN7667000067 | Trintel TI | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-03-05 | 2025-02-25 | 2025-03-25 | 2025-03-06 | 2025-03-06 | CHRISTINE IVY ANAK GIRIN7667000067 | 2025-02-25 | 2025-03-25 | 2025-03-04 | 2025-03-04 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
1949H_AD | MKH AVENUE | DU00005984520 | Central | Selangor | 2.992524 | 101.792079 | [7 empty] | 03. TSS Only | 24/11: Bulding owner not allow to install on rooftop. To emain NLOS untill further notice 17/10: Reactivate. MW link will swap NLOS (NLOS temporary to bring up site) 22/8: Take over by iMacro team-Qhalid, PO will raise under iMacro. | TSS |  |  | MW Swap | TSS ONLY 24/11: Bulding owner not allow to install on rooftop. To remain NLOS untill further notice MW SWAP LINK 1949H-2274A WITH HUAWEI_23G_1+0_0.3M/0.6M_DP_112MHZ_1024QAM_954MBPS_XMC3E_SUB_B_LINK_0.79KM IMPACTED: 1949H DISMANTLE EXISTING 1949H-2274A NLOS | [7 empty] | Magicell | SQ202510300097-Magicell | Magicell | No PR required-Work at TSS only | 2025-12-06 | 2025-12-10 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111001 |  | 2025-12-11 | 2025-11-18 | Completed | 2025-11-10 | 2025-12-11 | 2025-11-10 | 2025-11-18 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202509041074-GCI | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | EZRIN TASNIM BIN ABDUL GANI6798000128
9251A_EB | Krusen | DU00005500438 | Sarawak | Sarawak | 1.049240 | 110.505160 |  |  |  | AUG 25 |  |  |  | 06. Other Issue | 29/8/2025 : Plan to do IDU-IPRAN - cancel proceed due to Sacofa need PO to open port | TSS+TI |  | 1x 910A RTN | IDU-IPRAN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | [6 empty] | Magicell | SQ202505240074-Magicell | Allstar | SQ202505280659-Allstar | 2025-07-11 | 2025-07-07 | Completed | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | JAAFAR//BIN MOKHTAR/7018000111 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-19 | 2025-06-20 | 2025-06-19 | 2025-06-19 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250520AU |  | 2025-05-21 | 2025-05-22 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-22 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-22 | 2025-05-28 | 2025-05-29 | 2025-07-18 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-05-22 | 2025-05-28 | 2025-06-03 | 2025-07-18 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | [7 empty] | 2025-05-22 | 2025-05-28 | 2025-07-15 | 2025-07-21 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2026-01-09: 2025-05-22; 2026-01-15: 2025-05-28; 2026-01-23: 2025-05-22; 2026-01-23: 2025-05-22 | [7 empty] | GTSB | SQ202507080651-GTSB | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | AB.RAHMAN//BIN MAT NOOH/6237001519
9349B_EB | Woodman Plantation Bintulu | DU00005500439 | Sarawak | Sarawak | 3.010731 | 112.916334 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1x 910A RTN | IDU-IPRAN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | [6 empty] | Allstar | SQ202506120265-Allstar | Allstar | SQ202507190105-Allstar | 2025-10-31 | 2025-10-28 | Completed | 2025-05-22 | 2025-05-22 | 2025-06-10 | 2025-06-10 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-04 | 2025-07-02 | 2025-07-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-04 | 2025-07-02 | 2025-07-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070749 |  | 2025-07-08 | 2025-07-15 | Completed | 2025-07-07 | 2025-07-08 | 2025-07-07 | 2025-07-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-26 | 2025-08-01 | 2025-07-30 | 2025-07-30 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-26 | 2025-08-01 | 2025-07-30 | 2025-07-30 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-26 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-07-26 | 2025-08-01 | 2025-07-31 | 2025-07-31 | TONI//ANAK KUMBONG/6798000163 | 2026-01-09: 2025-07-26; 2026-01-15: 2025-08-01; 2026-01-23: 2025-07-26; 2026-01-23: 2025-07-26 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507080651-GTSB | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | AB.RAHMAN//BIN MAT NOOH/6237001519
2957C_LOS | Wisma Standard Chartered (EB) | DU00005500440 | Central | Kuala Lumpur | 3.054570 | 101.704306 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Link reroute to new FE 1727K/W00238 due to existing link LOS Block. Site Impacted : 2957C. NE_2957C 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site via existing MW SM link CT09424 (1727K/W00238-B00491). 6.Decom existing NLOS radio (2957C-NLOS-1023B).Ensure traffic migrate successful before proceed decom existing equipment. FE_1727K/W00238 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Enable GE port , ETH patching to existing SM link_CT09424. 6.Traffic migrate to new NLOS link and new TX route. 7.Decom existing NLOS radio (2957C-NLOS-1023B).Ensure traffic migrate successful before proceed decom existing equipment. | Link reroute to new FE 1727K/W00238 due to existing link LOS Block. Site Impacted : 2957C. NE_2957C 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site via existing MW SM link CT09424 (1727K/W00238-B00491). 6.Decom existing NLOS radio (2957C-NLOS-1023B).Ensure traffic migrate successful before proceed decom existing equipment. | Link reroute to new FE 1727K/W00238 due to existing link LOS Block. Site Impacted : 2957C. FE_1727K/W00238. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Enable GE port , ETH patching to existing SM link_CT09424. 6.Traffic migrate to new NLOS link and new TX route. 7.Decom existing NLOS radio (2957C-NLOS-1023B).Ensure traffic migrate successful before proceed decom existing equipment. | [5 empty] | Magicell | SQ202505300133-Magicell | Magicell | SQ202505260216-Magicell // SQ202505260226-Magicell | 2025-08-01 | 2025-08-05 | Completed | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-31 | 2025-08-01 | 2025-07-31 | 2025-08-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052154 |  | 2025-05-22 | 2025-05-23 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-06-25 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-06-25 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-11 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-06-25 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-27 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050638-GCI | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | CHEONG/SENG/WAH/7018000306
9712A_EB | Bkt Dabei (Celcom) | DU00005500441 | Sarawak | Sarawak | 4.190690 | 114.439520 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 23/9/2025 : Cutover done 22/9/2025 : Plan to do IDU-IPRAN - Re-plan due to stuck at site 9294A_IPR 10/9/2025 : CD ask hold until get Sacofa port info (Access road issue) | TSS+TI | L1+ATP+PAC | 1x 910A RTN | IDU-IPRAN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | [6 empty] | Allstar | SQ202509300153-Allstar | Allstar | SQ202509300155-Allstar // SQ202512170142-Allstar |  |  | Ongoing | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080521 |  | 2025-08-06 | 2025-08-14 | Completed | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-14 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-23 | 2025-09-29 | 2025-09-23 | 2025-09-23 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-23 | 2025-09-29 | 2025-12-15 | 2025-12-15 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-23 | 2025-09-23 | 2025-09-29 | 2025-12-16 | 2025-12-16 | ROYSTON//AHHOLE/6000038561 | 2025-05-25: 2025-09-23; 2025-05-25: 2025-09-29; 2025-05-25: 2025-09-23; 2025-05-27: 2025-09-23 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202604030185-GCI
3546A43_EVT | MBTS KARNIVAL IMAT PEKAN SOOK 2005 € | DU00006161036 | Sabah | Sabah | 5.144830 | 116.303938 | [13 empty] | Planning and integration support only for event site 3546A43 MBTS KARNIVAL IMAT PEKAN SOOK 2005 (E) Tx route: 3546A43-7442A 1) New port at IBEAM 7442A-MAC-001 Sook 2) New DCN IP 7442A RTN07 3) New DCN VLAN 7442A RTN07 4) New NE ID FE IDU 7442A RTN07 5) New NE ID NE IDU 3546A43 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128

## drop_down (hidden)
MOHD SYARIFFUL ANUAR//BIN AG BESAR/6000028224 | GerardAnthonyYabyabinGerardAnthonyYabyabin | NurulSyafiqah//Hamdan/6799000273 | ShafiraSalamShafiraSalam | NurainFatinNatasya//MohdOthlah/6799000270 | Tian Weihua10338888 | MOHAMMAD AIZAAN//BIN ABIDIN/6000028221 | ARIF//SAFWAN BIN SALLEH/6237001151 | RohizamRohizam | SITI HAFIZAH BINTI NOH6237001145 | WAN//MOHD ZHARIF BIN WAN SAPIANSORI/7018000199 | Zamudin Abd MauludZamudin | NurulAtiqah//MuhammadDamrah/6799000269 | ROHNI//DANIL/6000028216 | LIEW/KAI/WEN/6000028215 | ALISTER/ANAK/COLIN/6000028217 | HELIEZER//ATING/7018000197 | MUHAMMAD ANWAR/BIN/HAIRUDDIN/6000006442 | AWG//MUHD ZULKARNAIN ZUKRY BIN AWG SEPERI/7018000195 | ERICKSON//AK EDWARD/7018000192 | ADMON/ANAK/NYISENG/6000028210 | RAI//JORDAN RICHARD RIBU/7018000190 | BAGRI//SURUGAU/6000028212 | WB80034986 | REXCY RAYMOND7018000191 | MUHAMMAD IMRAN//MUHAMMAD RAMZAN/6000029541 | ///6237001158 | RaymondNgRaymondNg | ainfatinainfatin28@gmail.com | GWEE//KAH KIAT/7018000189 | WAN//FAIZUL AMRI BIN ABDULLAH/7018000187 | ROYSTEND//MARTIN/7018000188 | Hu Lihua10029645 | AZLISHAM//HALM/6799000254 | JISRON//ALBORT/6799000253 | Rong Hongbin10208390 | RAMIZAH BINTI ZAINON ABIDIN6000014055 | WB80037085 | Liu/Bin7023000003 | Lu/Ruisen7023000004 | DESMOND/DICKY/ANAK KINSI/6000028209 | ZARLES//BIN YAHAYA/7023000005 | KrishnaKumarKrishnaKumar | VALARIE VENICESSIA//ETED/6000038052 | Muhammad izzuddin bin alias6000014049 | NUR ANIS NAJWA BINTI//MOHD OTHLAH/6799000287 | MUHAMMAD USMAN//LIAQAT ALI/6799000286 | MohdMokhtarSaadMohdMokhtarSaad | SALMAN LAIQ//KHURSHID AHMAD/6799000289 | SABIR ALI//AHMAD YAR/6799000280 | LAU LEE LING7023000010 | MOHD FAZLI BIN ABDUL JALI7023000011 | MOHD//KHAIRUZ SHARIL BIN ALEKSIN/7023000012 | RUSSELL L UMBUL7023000013 | ELVIN KOAY//JING LIN/6799000284 | JHONAIDY TAHIR7023000014 | STEVE//SCHMEICHEL SAUL/7023000015 | WAQAS//MAJEED KHAN/6799000282 | sahzrin_datascosahzrin_datasco | JEFFRONY//BIN JAMAUN/7023000016 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | LAWRENCE BIN RUBIN7023000006 | MURUGAN//SOCKALINGAM/6799000277 | Wang/Zhongfei7023000007 | MuhammadAmirulAshraf//MohdNazri/6799000276 | GEORGE MICHALE BIN TUIS7023000008 | RICHIE//RICH TUIS/7023000009 | KUMANAN AL//MOGAN/6799000279 | MD ALI HASAN//SARDAR/6799000278 | WYREN//KOK SHAU CHIAN/7023000020 | LEEVISTER//BIN YUSOP/7023000021 | KENNY CELVIN BIN YUSAK7023000022 | RUDDY TUIS @ YUIS7023000023 | RYAN//RICHARD RIBU/7023000024 | LARRY//BIN LILING/7023000025 | ERICKSON YUNUS6000009986 | MUHAMMAD//AMIRUL ASYRAAF BIN MOHD HAZLAIDI/7023000026 | MUHAMMAD//HARITH HAIKAL BIN JAMALUDDEN/7018000163 | MUHAMMAD//ALIF HAIQAL BIN ABDUL MUTALIB/7018000164 | ABDUL RAHMAN BIN DOLHAN7018000161 | RamziBinMatRamziBinMat | ZUL//QADDIM BIN HAMDAN/7018000162 | AZIS//BIN AMIR HAMZAH/7018000160 | AHMAD//SHAFIQ BIN ASPAR/8225000019 | SONLEE//BERNABAS/7018000158 | MUHAMMAD HAFIZUL/BIN/MAT RUDIN/8225000018 | CHESTER//KRIS SUIMIN/7018000159 | MOHD FADZILLAH BIN TARMIJI8225000017 | SHAFFRY//BIN MOHAMAD ZAILANI/7018000156 | MUHAMMAD//FAUZAN BIN MOHD SYAM/6800000139 | MOHAMAD RAZIF BIN ZAINON ABIDIN8225000016 | DELL//PIERO SAUL/7018000157 | AHMAD//ADHAM BIN SULAIMAN/6800000138 | rightandtruejrrightandtruejr | AZRI//BIN HAROM/8225000015 | PUTRA//SYAFFIRUL DANIEL BIN ROSLI/7018000154 | MOHD//GHADAFI BIN ISMAIL/8225000014 | DAMIEN OH BOON PAR7018000155 | ZaidiRazabZaidiRazab | CHEE KIEN VUN7023000017 | Ling/Tao6800000135 | RIFINUS BIN TUIS @ YUIS7023000018 | HONG//HAI SAN/6800000134 | NOR//AMIRUL SYAFIQ BIN ROSE HAIZI/7023000019 | KUNNASILAN A/L PANNIRSELVEM6800000137 | REZDUAN//KASIM/6800000133 | RASYIDI BIN ZAKARIA6800000132 | BRYAN//CLARENCE BEDE CHARLES/7023000032 | MARJON//BIN KUNTAU/7023000036 | Willter JustineWillter_Justine | MOHD//SUFRI BIN AZHAR/8225000013 | MOSES//LENJAU VINSIEN/7018000152 | ShaileshYadavShaileshYadav | MOHAMMED//NORHISHAM BIN HUSSIN/8225000012 | RECKY//BIN AYONG/7018000153 | RIDHUAN//BIN MANSOR/8225000011 | DAMIAN//KURT ANAK ALFRED JAI/7018000150 | ShahrulnizamBAbdullahShahrulnizamBAbdullah | CAROLANIUS//BIN PANAI/8225000010 | MARGAIN//THOMAS/7018000151 | Noraslina Abu HasanNoraslina | HilzanBinPieeHilzanBinPiee | GAN//BO/6237000274 | MUHAMMAD//FAIRUS BIN CHE YUSUF/7018000149 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | OCK BERHADWB80035013 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MUSTAFA//BIN NASRI/7018000147 | MOHAMAD//NOOR BIN YANI/7018000148 | NURUL//AMIN/7018000145 | AHMAD//HAFIDZ AINUDDIN BIN AZMAN/6800000128 | Ismaariff Ismail8225000005 | MOHAMAD AMIRUL SYAFIQ BIN ROSLI7018000146 | ///6800000127 | Wan Khairri Anuar/Bin/Wan Muhammad Anuar/6237001118 | NUR//KHABIR RUSYDI BIN KHALID/8225000004 | FAIZ BIN KADIR7018000143 | AZUWAN//BIN HAROM/8225000003 | SHAMSUL//FARID AMIZAN BIN RAFAII/7018000144 | MOHD//ALFIAN BIN MAZLAN/7023000028 | MD//ABU SAEID/7023000029 | ALI RAZA AKBAR ALI6799000298 | MOHAMMAD SAIFULL BIN ARZAMAN6000038009 | Muhamad//Asraf Bin Mohd Nor/6800000125 | MUHAMMAD//KHAIRANI/7599000024 | MADILLAZMI/BIN/JUMAT/7599000025 | HASLINA/BINTI/HANIPAH/7599000026 | Mohd//Nurhishammudin Bin Abdullah/7599000020 | ULLAH//EHSAN/7023000042 | MOHD IRZAN IZHAR BIN FLORENTIUS7023000043 | JEPIUS//LOWIN/7023000045 | NANDRE//TAN NANLIPOK/7023000046 | FREDDENAN//LANGUB NETANEL/7023000047 | BOBBITO DONGKONG7023000048 | ABDUL//HAKIM BIN MUJI/7023000049 | AHMAD//DANIAL BIN HAPHAS/7018000185 | MUHAMMAD//AIMAN AFIQ BIN MUHAMMAD SUKRI/7018000183 | SHUKOR//BIN BASRI/7018000184 | LESLIE BARA NATANEL7018000181 | JOEJI NATAN BIN JAINOL7018000182 | YUSRI//ONDIRI/7023000040 | Zhu Tiancai10130404 | MOHD//FIKRI HIDAYAT BIN ALEKSIN/7023000041 | JOREY//BIN BALANG/7018000180 | YuliusDannyKrisantoYuliusDannyKrisanto | YONATAN YARIS6000067800 | LEE//JING WEN/6237001565 | SHARIDAH SHARUDINs.sharidah | YONG//YEE YIU/7018000178 | MUHAMMAD//DANIEL SHAH BIN DZULKIFLI/7018000179 | MUHAMMAD//FATHURRAIHAN BIN ZAIDOL ADZHA/7018000176 | AFZARHUSHAIRI//BIN WAN PANI/6800000119 | ASVENY//A/P MANOHAR/7018000177 | MOHD ZUL HISYAM BIN MOHAMAD7599000017 | STEVE//LEONEAL BIN SAZALI/7023000039 | ABDULLAH MUHSIN BIN AMINUDDIN6800000112 | MohidiJaanMohidiJaan | LIM//SOON KIAT/6800000115 | SYAHRULNIZAM//BIN MAAROP/7599000013 | NUR//AMIRAH FARHANA BINTI MOHAMAD BAKRI/6800000110 | BROND//STANILEY EDIK/7023000053 | NUR//FAEZAH BINTI JOHARI/7599000010 | DERFIT//WEN DERIN/7023000054 | Asmadi bin IsmailCelcom_asmadi | PILIPUS//BIN BERNABAS/7023000055 | Ahmad//Farizuan bin Mustafar/7599000012 | KIFAPOLO//BIN ARIBULAN/7023000056 | PITRA//ISRAM BIN SULAIMAN/7023000057 | LAJAREI//BIN LOWIN/7023000058 | JASNIN//BIN SALASNAIN/7023000059 | ALEX///7018000174 | ZUL//ARIZAL BIN MOHAMMAD ALI/7018000175 | LING//KUOK WEI/7018000172 | CHONG LI CHING7018000173 | HARIZAL//BIN MOHD TAMRIN/7018000170 | LARRY//JUANIS/7023000050 | ASYRAF//BIN MOHAMAD/7018000171 | JEIRY BIN KIBIN7023000051 | WELSON//BIN MOJULING/7023000052 | ///6237001576 | ALBERT//GOH CHIN SIANG/7018000169 | DamonOngDamonOng | cheekit//ngei/6237001574 | MUHAMMAD//SHAFIQ/7018000167 | MUHAMAD//SYAZWAN BIN KHIRRUL ANUAR/7018000168 | MOHAMMAD//SAIFUDDIN BIN MOHD NASIR/7018000165 | MOHD//SAFRI BIN ARIF/7018000166 | NURZAIRAH//BINTI ABDUL RAHIM/7599000006 | SHAHIRA//SULAIMAN/7599000007 | MUHAMMAD//SYAHIN ALIF BIN SAPARI/7599000008 | MOHD//AZUDIN BIN ABDUL MAJID/7599000009 | AZWIN//DAMIA BINTI ABDUL HALIM/6800000103 | KHAIRUL//BARRI BIN CHE AMAT/6800000100 | WB80036304 | MOHD//DANIAL BIN MOHD ROZAI/7599000005 | LATCHUMI//GANTAN A/L THANGAMANI/6800000182 | MOHD SAIDI BIN ABD RAZAK6800000181 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | HIMAN//BIN ADAM/6800000183 | QAMARUL NIZAM//RAMAN/6000008699 | MUHAMMAD//NA'IF BIN MOKHTAR/6800000180 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | UMI NOR PADZILAH BINTI PAUZI7018000120 | MARZUKI//BIN ABDULLAH/6000042135 | KALFIN//BIN BERNABAS/7667000077 | RAZLEE//BIN AB RAHIM/7018000116 | AWANG SARIFF BIN AWANG SAILIN7667000078 | MICK//CRUZE MARTIANUS/7018000117 | AGRAHIM//BIN A SAILIN/7667000079 | NG//SHU WEI/7018000114 | AHMED//FAWWAZ HADI BIN AHMED MAHIR/7018000115 | JuvonoJamingonJuvonoJamingon | LIANG WAH CHEONG7018000112 | MUHAMMAD//AMIRUL SYAFIQ BIN HIDZIR/7018000113 | MOHD//KHARI NIZAM BIN MOHD ADAM/7018000110 | Mohd Reduan JaiminReduan_Edotco | JAAFAR//BIN MOKHTAR/7018000111 | MUHAMAD ARIFF BIN KHASIM6800000179 | SAFUAN//BIN YUSOFF/6800000178 | Azami bin Samanazami | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | MOHAMMAD//MANAF BIN MOHAMMED/6800000175 | AHMAD//IRFAN BIN KAMARUDDIN/6800000174 | MUHAMMAD//ZIKRI BIN YUSNIZAL/7018000118 | MAT//SAFAREED BIN MAT DESA/6800000177 | WEE KIAN YEE7018000119 | JESINTHIRAN//NAIR A/L MAHAY INDRAN/6800000176 | MUHAMMAD HAEQEAL BIN RAMLEE6800000171 | MUHAMMAD//AZMAN BIN ZAKARIA/6800000173 | MUHAMMAD//NAJMUDDIN BIN ABD GHAFAR/6800000172 | Chua Teck Eechua@ascentrack.my | WARDINA PATOJAH BINTI HANIFAH6000030158 | TAN AH TOONG//TAN KEE SHAO/6000043476 | NURUL//AZIATUL NADIA BINTI ABDULLAH/7018000105 | NUR//HUSNA BINTI MOHD HAFIZ/7018000106 | AMIRAH//IZZATI BINTI AZMI/7018000103 | NOR//FATEHAH BINTI NOR SHAHID/7018000104 | OSMAN//BIN JAFFAR/7018000101 | FAUZAN BIN IDRIS7018000102 | JEFFRYDIN//BIN MAMAT/7018000100 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | AINA//NABILA BT MOHD IZAT/7018000107 | LOGA NATHAN/AL/RAVI CHANDRAN/6800000166 | AHMAD//ISMAIL ZAKI BIN AHMAD LUTFI/7018000108 | Mohamad//Farizul Hakimi Bin Che Ismail/6800000162 | THOMAS LINGGANG ANAK SUJANG6800000161 | Roy//Lee/6000056316 | MUHAMMAD//FARIS BIN MAZLAN/8225000002 | MUHAMMAD//AKIF ASWAWI BIN MOHD AMRIZAL/7018000141 | DZULFAIZAL//BIN MAULUF/8225000001 | feilin06352@163.comfeilin06352@163.com | MOHD FAIRUS GANESH ABDULLAH7667000060 | KELVIN HE10337974 | JULIUS//ANAK GANA/7667000061 | DHURGISH//KUMAR A/L UMANATHAN/7018000140 | NASARUDIN//BIN NASIR/7667000062 | ANISA//BINTI BOLI/7667000063 | TIHAANAKDOM//BIDUM/7667000064 | SABERI//BIN UMAR/7667000065 | MOHAMMAD//ALIF BIN ABDULLAH/7667000055 | ZUHAIRI//BIN MUHAMMAD/7018000138 | MUHAMMAD//NORSAZLI BIN ABDULLAH/6799000208 | MUHAMMAD//FAIRDAUS BIN RAMLI/7667000056 | MUHAMAD//AIDIL BIN JAMALUDIN/7018000139 | MUHAMMAD//NOR NAZREEN SAFRIZ BIN MARSIH/6799000207 | Mohammad//Nurhadi Bin Delakim/7667000057 | AHMAD//LUQMAN HAKIM BIN MOHD YAHYA/7018000136 | HENSON//ANAK SALLEH/7667000058 | MOHAMAD//ZIN BIN HARONA/7018000137 | MOHAMMAD//SYAFIQ BIN RITHAUDDIN/6799000205 | GIBSON WALTER KERRY7667000059 | AHMAD RASHIDI BIN SAFRI7018000135 | Ammaraffandi binkhairolanuar10337966 | MUHAMMAD//FADZRIN AIMAN BIN KAMARUDIN/7018000132 | MUHAMMAD//FIRDAUS BIN RAFEE/7018000133 | MUHAMMAD//SALEHIN BIN HALIT/6799000209 | NOR HELMI BIN ISMAIL6799000200 | Rejoilin/Edith/John/6000056320 | PUWANESWARAN//A/L SUKUMARAN6000018484 | NUR HAZIRAH/BINTI/AHMAD AZLAN/6800000158 | MUHAMMAD KHAIRUL NAZMIN/BIN/YAAKOB/6800000153 | ASIF//HUSSAIN/6799000203 | MUHAMMAD//ASRI BIN JAMAL/6800000155 | ZULKIFLI//BIN HASSAN/6799000202 | ZAIRI//MOHD/6000056322 | Siti Rohainisiti.rohani@southpac.com.my | Lily//Gabon/6000056323 | WB80039867 | AZARUL//NIZAM BIN RAZALI/6800000151 | Allstar_ConradAllstar_Conrad | KHAIRUL//AZUAR BIN ZAKARIA/6800000150 | Hairil Nizam//Maliki/6000033206 | AMINUDIN//BIN ABDUL RAZAK/7018000130 | ALBERT//TAY KAI WEN/7667000070 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | JERRY SONLEY SALI7667000071 | MAXWELL BIN YUNUS7667000072 | MOHD ISRI BIN ABD HUSSIN7667000073 | CHAN DAO LIANGRyanChan21 | MOHD HELMI BIN MOHD//JAMARI/7667000066 | MOHAMAD//FARHAN BIN HAIRI/7018000127 | CHRISTINE IVY ANAK GIRIN7667000067 | MUHAMMAD//AMIRUL HAKIM BIN KAMARUDIN/7018000128 | Gilbert Anak Juban7667000068 | HASIF//AFIF BIN ROSLI/7018000125 | MohdHafizMohdHafiz | MOHAMAD AZROL BIN ABDUL RAZAK7018000126 | AFDHALUDDIN//BIN ASRARUDDIN/7018000123 | MUHAMMAD//FARIS FARHAN BIN MOHAMAD NIZAM/7018000124 | ANWAR//BIN ABDUL RASID/6800000149 | FRENDDY//YACOB/7018000121 | JUDSON//OWEN JAMES/7018000122 | WILKITSON//ANAK SUMOI/6000033212 | MUJAHID//ADIL BIN MD KAMAL/6800000148 | Kevin//Tan/6000033214 | Mohd//Rayme Bin Mohamad/6000033213 | Jupri bin jasnijupri@yptt.com.my | SITI NATRAH BINTI NASIRUN6800000142 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | SOHAIL//NASIR/7018000129 | MOHD FARKHAN BIN MOHAMAD FAIZALfarhanzico96@gmail.com | QHALID//BIN HASHIM/6798000020 | Chin Sun Lun7667000040 | WB80041928 | SITI//NURASHIKIN FARAHAIN BINTI MOHAMAD DAUD/7667000041 | MOHD NAJHAN BIN MOHD YASSIN6000011429 | MAMORA AGAM ANAK THOMAS7667000042 | MOHD. AZIZUL BIN ALLIH7667000043 | ABANG//SYARIFUDDIN SYAFIQ BIN ABANG AZEMI/7667000033 | Marzuki bin Muhammadscrapperskys@gmail.com | MUHAMAD//MU'IZZUDDIN BIN MOHAMED/7667000034 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | LAW KIM CHANG7667000035 | MUHAMMAD//AMIN BIN MOHAMAD BESRI/6799000228 | IKHWAN SYAFIQ BIN ROSLI6798000018 | FELIX//SABANG ANAK BALLAI/7667000036 | NUR//ADAM ZULHAYAT BIN KAMARADIN/6799000227 | FERINO ANAK JAGAM7667000037 | DEXTER//BIN JUNGHOI/7667000038 | WB80041707 | CHARIS//LORIN JUSTIN/7667000039 | FAZAL ABBAS6799000222 | MOHAMAD//FATIHI BIN WAHAB/6799000221 | MUHAMMAD//AZAHAN BIN PUAD/6799000220 | ARBAB//ALI/6799000226 | JayHanSawJayHanSaw | Siew Wen JingWenJing22 | Azuani//Mohd/6000056729 | WB80042003 | ccledlian@gmail.comccledlian@gmail.com | WB80035560 | ANAS FIKRI ADHA BIN RAZMI6000009598 | NOURHAFISZUDDIN BIN IBRAHIMhafiszuddin | MOHD NORMAZLI BIN DELAHAK7667000050 | MOHAMMAD//HAMIRUL AZWAN BIN ULUI SILEK @ MOHD HANAFI/7667000051 | MOHD//FIRDAUS BIN KEPELI/7667000052 | YUSTIN YUSOF6000006085 | Leong Wee Kee10174935 | Hasbullah Bin Abdul Majidhasbullaham | WILSON//SARAN ANAK SUNGGOH/7667000053 | MITCHELL L. UMBUL6000006086 | MUHAMMAD HAFIZUL AKMAL BIN MOHAMMAD HANAFI7667000054 | DANNY SINGKUN6000006087 | Syahharon//Bin Ibrahim/7667000044 | MOHD//KHAIRUL AZHAN BIN HUSSIN/6799000219 | RONNIECAL//ANAK JOHNNY NAGAT/7667000045 | USMAN//KHALID/6799000218 | Wen Haozhou10137474 | Abg. Azrie Amiruddin Bin Abang Ali7667000046 | Mohamad//shahrulnizam bin mili/7667000047 | MUHAMMAD AMIRUL BIN MOHD NOOR6799000216 | TIMOTHY//RUDI/7667000048 | BADOL//BIN AHLI/7667000049 | MuhamadAwaludinMuhamadAwaludin | AZRIEN//BIN AMRAN/6799000211 | MUHAMMAD//NAJAHA NAJMI BIN SALLEH/6799000210 | TALHA//MUHAMMAD/6799000214 | JAMIL//CHOMPOT/6000056731 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | KhairilAnuarKhairilAnuar | How Pin Guanehowpin | ytyee@yahoo.comYeeYT22 | NAZRUL//AAMIR SYAH BIN DANI/7667000020 | KELLY//LIAW ALIAS/7667000021 | MAXWELL//JAWA ANAK UTED/7667000011 | ApalarajuApalaraju | ADELINA//JACY INJAN ANAK JACKSON/7667000012 | ALEXANDER SIGAR BALANG7667000013 | An/Yingrui6237001166 | Willis Jock Anak Kenny7667000014 | IMRAN//ALI/6799000249 | RAHMAT//HIDAYAT BIN BUJANG/7667000016 | REEMY//RALPHALL ANAK ULIS/7667000017 | PATRIK WEI ANAK EDUIN7667000018 | SHAHRUL//EIZLANHAN BIN DOLHAN/7667000019 | ARNOLDLIE//BIN YUSLI @ YUSALI/6799000244 | ABBASI//WAQAR/6799000243 | John Micheal Anak Jaomjohn.micheal.anak.jaom | ADNAN//MUHAMMAD/6799000242 | UWAIS AL QARNI BIN HISHAMUDIN6799000241 | JEYAKALISVARAN//SEMBUGANATHAN/6000010562 | MUHAMMAD//NASRUL ASRAF BIN MOHD RAPI/6800000197 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | NUR//FARHANAH BINTI HASSAN/6799000246 | NOR HAZILA//BINTI HAMIDON/6799000245 | BONG NEE NYEEbong.allstar@gmail.com | GWK87mpNC738s/eRciZE0nrIsFJdTlvzM1BSvUUd6Rk=team8gcitechnical | STANNIE//AVILA RASAM/6800000192 | Mohammad Hafizzi Ului//Bin Mohammad Hanafi/6000053238 | ZHARIF//FARIZAN BINABDUL HAMID/6800000194 | MUHAMMAD//KHAIRULANWAR BIN KARIM/6799000240 | NOOR//AZRAAI BIN SALEHUDDIN HAQE/6800000191 | ALVIN TAY KAI SENG7667000030 | ZAINAL//AZMAN BIN OMAR BAKHI/7667000031 | Roslan Bin KilingRoslan_Edotco | NICHOLAS UNCHAT ANAK BAKI7667000032 | ShukriShukri | ALBANUS//BIN PHILLIP/7667000022 | Mohamad//Aiman Ahsraf Bin Rosli/7667000023 | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | LOO CHU KAY6798000007 | DARREAL//JOSHUA ANAK SELIN/7667000025 | MOHAMAD//AMIRUDDIN FAHIM BIN EMRAN/6799000238 | DAVESSON//ANAK BARANDAH/7667000026 | FEILEXSTER//DE'LEON ANAK FRED/7667000027 | Fiona Wan Yen Chin7667000028 | SUKKRIE//BIN LILI/7667000029 | FAIZ//RASOOL/6799000233 | Ramganesh//Naidu A/L M Gunesakaran/6800000189 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | AMIR//HAMZAH BIN AB RAHMAN/6799000231 | MOHD FAIZ BIN MD YUNUS6800000186 | MOHD//NAZREEN BIN FIRDAUS/6799000237 | MUHAMMAD//AMIRUL ABIDIN BIN MUHAMMAD ALIM/6798000009 | MUHAMAD//ASYRAF MUNAWWAR BIN MOHD HUSSIN/6800000185 | AZRUL//HISYAM BIN KAMARUDIN/6800000188 | SHOAIB//AKTHAR/6799000235 | MOHD//RIZUAN BIN OSMAN/6799000234 | CHEREL//ANTIHING/6000035318 | Muhammad Ridzuan Abdullahmridzuanabdullah | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | FARDI BARU SUZANDI6000068248 | DOUGLAS GEORGE MOJUNTIN6000021148 | AZAMAN BIN ASMARAH6000002402 | ANDREW BIN JUHAN6000068232 | Armizi Bin Awang Ismail6000021147 | MIKE MICRON DOLIK6000068237 | Wang Huiling00332387 | MUHAMMAD/ASGHAR/MUHAMMAD ASHRAF/6000056258 | khoocw@allstarengineering.netkhoocw@allstarengineering.net | MOHAMAD AMIN//BIN MOHAMMAD DAIAN/6000037526 | NorSyalizaNorSyaliza | ANDREW JOK6000021121 | LU CHONG MUI6000021119 | GREGORY//ANAK USEN/6000021116 | Shamil/Amry/Mohamad Sukri/6000059305 | RONALD GARRY//ANAK ZIKIR/6000035357 | KIMBERLY//ANAK WANG/6000036201 | MUHAMAD FARIDZUAN/BIN/JAINURI/6000037530 | ELBY//HILLTON ANAK DAUT/6000036200 | MuhamadIzzatMuhamadIzzat | RolandAugustineRolandAugustine | MohdFaisalAnangMohdFaisalAnang | SumitraSThavarajahSumitraSThavarajah | Wu Bo10096828 | LEEROY QUIRINUS6000070995 | NurulhidayatiNurulhidayati | Asyraf bin AnahAsyraf21 | NikAshrafNikNikAshraf | AlHelmiAffendiAlHelmiAffendi | ZURAINI AIDA BINTI MOHAMAAida22 | MohdFaizalPadirMohdFaizalPadir | JUIN//MAJUNGGING/6000002414 | AnandKumarAnandKumar | Jeremy S chinechijer | angahmeal@gmail.comangahmeal@gmail.com | VICKY FREDOLIN//MOJUNTING/6000002404 | DANIEL CHAI PUAM SOONG6000037963 | RASHIDI/BIN/DARASIK/6000002405 | KrishnaMaruthaiKrishnaMaruthai | Hu Juan00025358 | Geveothy//Anak Goen/6000047777 | IELIYANARUS SHAHTZNAS//MOHMAD NASIR/6000046447 | KAMALRUL ARIFFIN BIN SATAR6000065188 | AMIRUL SYAHRINI BIN MOHD ZIN6000023342 | Noryusliza binti RoselyYusliza22 | ZulkepliZulkepli | mohd_nazmie@allstarengineering.netmohd_nazmie@allstarengineering.net | KENNEDY//ERIC KUINTIN/7023000064 | SABAI ANAK IMONG6000022084 | JitenderJitender | MOHD//HASANNI BIN MOHD KAMARUDIN/7023000067 | ZULQARNAIN//BIN MUHAMMAD/7023000069 | ABDUL//MUNIB BIN PUTAN/7023000060 | ERICMAN//BIN EDWARD/7023000061 | MAZRUN//BIN HARUN/7023000062 | Chen Shi10313064 | FRANCEYUKIA//BIN FURUT/7023000063 | AdrianChenjoyAdrianChenjoy | team21gcitechnicalteam21gcitechnical | MuhammadAmsyarMuhammadAmsyar | TAN//HEOW SANG/6237000338 | Yang Youming10048310 | Melvin Anak Ericmelvinnino3030@gmail.com | Khairulazuar000Khairulazuar000 | RICKTON BIN ZAKARIA @ KUROP7023000075 | Wan/Min7023000076 | AZMI BIN RAHIMazmirahim | ABDUL//RAZALI BIN KURUS/7023000070 | MUHAMMAD//RAID SALIM BIN SOLUNGIN/7023000071 | Ng Hui San00085438 | SHAFIE/BIN/MADSA/7023000087 | AHMAD BIN DIN6000031812 | MOHD NAZWAN BIN ABDUL SALLEH7023000089 | ASRIN BIN MOHD NASIPA0721673507634405376 | Sharidahsharidah | STEPHEN//LASUNG BESAR/7023000081 | RONALDO JASNEH7023000082 | PrahladSinghYadavPrahladSinghYadav | NoorAzaharNoorAzahar | CHAI//SONG YU/6237000310 | GERALD ANGGIT ANAK GENAM6000015771 | Nur Azlyn binti Mohd RosmanAzlyn | Cai/Dongming7023000098 | Ali//Arshad/6000003311 | DARIEL//BIN ABGAR/7023000099 | DATU MOHD//FADZLI BIN DATU BASRUN/7023000090 | MAXWELL MAJUMBA7023000091 | JERAMY//BIN YUSUP/7023000093 | LEO//BIN SIMON/7023000094 | MAD YASHIN BIN HUSSIN6000062542 | SHAHRIN//BIN SHAHLI/7023000096 | FIRDAUS//BIN TAJALDIN/6237000322 | Zheng Wei10049651 | ZEESHAN IQBAL//MUHAMMAD IQBAL/6000003306 | MAGICELL SDN BHDWB80039548 | Jeremy//Nyandang Anak Julian/6000061643 | HAIRUL ISMADI//BIN DIN/6000045165 | JessicaBartholomewUjahJessicaBartholomewUjah | LEE CHUN HUNG6237000773 | Mohamad Said Mat HassanSaid_Edotco | SufianSahuri BinAhmad10321952 | Lei Zhenpeng10173285 | GERALD GAWAN/ANAK/ENTALANG/6000028653 | MIMIE MELISA/BINTI/JUMAT/6000028656 | Kashif Ali//Syed Riaz Hussain Bukhari/6000004222 | JOCEAU UPAI RUGU6000028658 | Yvonne Chan Yi Wenyvonne@datasco.com | FIRDAUS HANAFI//BIN MOHD ZAIN/6000050502 | AHMAD FAKHRUL MUKMININ/BIN/ROSLAN/6000004227 | HAFIZ AMEER HAMZA//MUHAMMAD NAWAZ/6000028652 | AFIFAH BINTI MOHD ROFIDZAN6237001630 | Ma Qiong00270053 | ABDUL SAID BIN JANI6000018853 | MOHD SHAHRIN BIN ALI6237000307 | MOHAMAD/KHAIRUL/IQBAL/6000034049 | AliAkaramAliAkaram | Denilson//Ison/6000028647 | CL90008700 | MOHAMAD ZULFAHMI/BIN/MOHAMAD IZHAM/6000034050 | NUR//ARINA BINTI ISMAIL NASIRUDDIN/6237000750 | Mohd Fauzi Bin Hamdanfauzihamdan | JUDIH//LAJIUM/6000057179 | YAP//FEI LEONG/6237001604 | FABIAN NGUI THAI FUNG6237001607 | GABRIEL TAI JUN-SHENG6237001608 | MUHAMMAD NUR'AZIM HASIF BIN MOHD SAPIAN6000068296 | MuhdRazifRidzwanMuhdRazifRidzwan | laina@girobumi.com.mylaina@girobumi.com.my | KONG CHUNG ANG6237001613 | WB80032733 | EDDIE THOMAS SU7023000100 | ARFINAH//BINTI DARMANSYAH/7023000101 | YONG ZI WEI7023000102 | PAVITRAN AL CHINNAKOLANDAY6799000150 | MUHD//KHAIRUL NIZAM/7023000104 | ABD.SYAHIMAN BIN ABD.RASIDsyahiman | HIJRIN//NUR EFFA BINTI ABRAHIN/6800000219 | LESTER BIN DOINIS6237001265 | JUTI//ANAK RICHARD/6800000216 | DANISH//ASHRAF BIN DAWANA/6800000218 | HUANG//YI/6800000217 | AHMAD//FAIZ BIN SUPIYAN/6800000212 | ADEEL//ISLAM/6799000145 | WB80036223 | NORMAHADI//BIN MOHD NOR/6800000211 | MUHAMMAD//USMAN/6799000144 | MOHAMAD FAROUK SHAHANA BIN SARUDIN6800000214 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | EDWIN PAUL A/L WILLIAMS6799000148 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | NOOR//HUSSAIN/6799000147 | MUHAMMAD//HUSNIAN/6799000146 | MUHAMMAD AZLAN/BIN/MAT NOR/6794000121 | MUHD//AZMER BIN ARIPIN/6799000141 | WB80035444 | AMIRUL//HAZIZIE BIN HAMDAN/6799000140 | JOSEF/BIN/ABSARI/6794000120 | MHD FARID/BIN/NGADININ ADININ/6000054868 | AHMAD FAIQ/BIN/MOHD AZHAR/6000003292 | MOHAMMAD//FARISAL BIN MOHAMMAD/6800000209 | SALEEM//MUHAMMAD ZAHID/6800000208 | SIVANANTHAN//A/L MAHANDRAN/6800000205 | HASLINDA//BINTI JOJONG/6800000207 | NAEEM//ABBAS/6800000206 | MUHAMMAD IRFAN BIN SAHARRIZA6800000201 | MUHAMMAD RIDHZUAN BIN MUHAMMAD NAIM6799000134 | NORAZLINDA/BINTI/ZAKARIA/6794000118 | MUHAMMAD//SHAFIZ BIN LOKMAN/6800000200 | MUHAMMAD//ABDUL HADI BIN ZAINUDDIN/6799000133 | MOHD//SHAHREEZAN BIN RAZALI/6794000119 | WanIzibdinWanIzibdin | MOHD NAZRI BIN BALNAMA7023000107 | NAZARULISKANDAR//BIN YUSNI/6800000203 | MOHD//FARIS BIN ABDULLAH/6799000132 | Khairul Azman Bin Din7160000001 | MUHAMMAD//AIMAN NUR HAKIM BIN MOHD TAMIZI/6800000202 | BadrulHishamBadrulHisham | BILAL//MUHAMMAD/6799000137 | AINA MARINI//ATON/6794000115 | SAFRAZ//AHMED/6799000136 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | MUHAMMAD ZUHDI/BIN/ABAS/6794000117 | MUHAMMAD//IDHAM BIN MOHAMMAD HISHAM/6799000170 | Muhd Nor Rahimi//Zainal Abidin/6000003268 | MD//ARIFUL ISLAM/6799000174 | che.mohdrafi92che_mohdrafi92 | DAMANHURI BIN A RAZAKearadam | DINIE SYAHMI BIN NORZAMRI6799000171 | MD. FOYSAL AHAMMED6000062039 | AhmadTarmiziAhmadTarmizi | DENASA/DORIK/ANAK DAENG/6000042430 | WATSON JIMBAU//BUNSIE/6000019611 | IBNUHANEEF FATTAH/BIN/SUHAIRI/6000045933 | MAC//IVAN MARCOS/6799000164 | BernardWongBernardWong | NAVIN//A/L RAVUNATHAN/6799000168 | IFTIKHAR//AHMAD/6799000163 | Muhammad Hanif/Bin/Ruslan/6000005454 | MUHAMMAD//SALEEM/6799000162 | AHMAD//ALIF HAKIM BIN MOHAMED/6799000161 | Muhamad Nur AlAmin/Bin/Mohamad Nuri/6000005456 | FARIDHOH NAJIHAH BINTI FAIRUL NIZAM6000005453 | ABDIL HATTAB/BIN/SUHAIDI/6000043772 | Liu Kangkang10030760 | MUHAMAD SYAMIR AMIN/BIN/MD PAUZI/6000019606 | ROSLEY//BIN SADAH/6000044613 | ARMANSA//BIN AMIN YUSUF/6799000156 | RANA//IMRAN HUSSAIN/6799000153 | Nashrul Amzzar BasriEBASNAS | Wang Qianming10167836 | SHAMSON//BIN BALANG/6799000158 | FAUZUL//AMEEN BIN MOHAMED SUHIB/6799000157 | MICHAEL//DAWAN ANAK NICODEMUS KUJAT/6799000192 | MOHAMAD IZZAT FARHAN BIN MOHAMAD RADZI6799000191 | SHUKOR//BIN BASRI/6799000190 | JAYVEN//JOINIS/8366000018 | JACKSON//ANAK ELLY/6799000196 | ALIAMAD//BIN BAGOL/6799000195 | RAINGGO//BALAYAS/8366000016 | TONY//ANAK KADAM/6799000194 | RODNEY MOJUTI8366000017 | DEEVAN//RAJ A/L CHANDRASEGARAN/6799000193 | SITI SARAH BINTI SAADDIN7018000284 | MUHAMMADDANIELHAIKAL/BIN/RUSLI/7018000285 | LAW/WENG/KIT/7018000282 | FAHDA ANATI BINTI AHMAD AMIR7018000283 | HOSMANE//BASAVARAJ DHANANJAYA/6237000383 | THEE CHOOI MUN6237001223 | ABDULLAH//BIN NASIB/6000059295 | MUAMMAR/BIN/YANI/7018000277 | SURYADI/BIN/HASHIM/7018000278 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | FIRDAUS/BIN/HAMID/7018000275 | Azam/Azri/Roslan/7018000276 | KANES A/L BALAKRISHNAN6237001226 | ZULKANAIN//BIN MOHAMAD/6000041998 | FEADLEE BIN MOJUNTING8366000026 | MOHD SUFIAN/BIN/MOHAMAD/6800000255 | NADEEM//HASSAN/6799000187 | JUMADE BIN AMIR8366000024 | KARIKAALAN//A/L MUNIANDY/6799000186 | ARYON JASNE JASLY8366000021 | MUHAMMAD//FIRDAUS BIN ABDULLAH/6799000181 | MOHAMAD//ISZUAN BIN ISMAIL/6799000180 | MUHAMAD AKIF BIN HARWIS8366000009 | MOHD FIKRY BIN KAMAL8366000007 | ASHOKAN//A/L SUPRAMANIAM/6799000185 | SYLVERINUS//AHMUI MINIK/8366000008 | MOHD//AMIR BIN SAMSI/6799000184 | LEVROL BIN LISAD8366000005 | MOHAMAD//HASZUAN BIN ABDUL HASSAN/6799000183 | NUR AFIKAH BINTI YAPDI8366000006 | HAZNOR//BIN RAMLAN/6799000182 | MUHAMMAD/ARIFNURAZIM/IZANZUL/7018000271 | MUHAMMADFAUZAN/BIN/RIDZUAN/7018000272 | BRYANTINEZ/ANAK/BUNAWAN/7018000270 | Khairyzuliqwan//Hazemi/6000060267 | Masdee//Mattius/6000060265 | MURUGAVALE PRESHANTHAN6237001235 | HELLERRY//SALIUM/7018000266 | RONALDINHO//BARU NETANEL/7018000267 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | MOHD//SHAHRUL HAFIZI BIN ANUAR/7018000264 | MOKADDES//ALI/7018000265 | JOEMIN//BIN JIMMY/8366000014 | STEVE BIN ONGKAS6799000178 | RODLEY//MOJUTI/8366000015 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | MOHD ASMADI BIN MOHD ASRI6799000177 | AZHAR//BIN YUSOF/8366000012 | SUHELMI//BIN SULAIMAN/6799000176 | DAVIDNES//BIN DAMUS/8366000013 | MOHAMMAD//HAFIZ BIN ABDUL JAMEL/6799000175 | JIMMY//LEMUKU/8366000010 | CASECASANDRA//MAISOS/8366000011 | MUHAMMAD SYAFIQ AIMAN BIN ZAINAL ABIDIN6800000240 | MOHAMAD RUSYAIDI AZRI BIN MOHAMAD AFLAH6800000243 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 | MEHARBAN//ZEESHAN/6799000179 | MUZAMMIL IQBAL MUHAMMAD ARIF6794000112 | NOR AMIRUL SYAFIQ BIN ROSE HAIZI6000015290 | Liu Bin10002687 | A. Visnu VaradaA.VisnuVarada | AhmadShamsulAhmadShamsul | MUHAMMAD//NUR FALAQ BIN ROZAIN/6800000238 | MohdNizamNarawiMohdNizamNarawi | MUHAMMAD//NIZAMUDDIN BIN ZAINOL ABIDIN/6800000237 | MOHAMAD AMIRUL BIN AMINUDDIN7018000297 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | MUHAMMAD//IRSYAAD ILAHIE AL- HAFIZ BIN NOR AZAHAR/6800000239 | Jairal Teo Jichuin8366000003 | MUHAMMAD//FAIZ HAFIZ BIN MOHAMAD NOOR/6800000234 | KHAIRUL AZWAN/BIN/GHAZALI/6794000107 | JEFRIZIN BIN MORUNDANG8366000004 | JUPASTIN JUPIN6794000108 | AMIRUDIN8366000001 | MOHAMMAD//NAZER IKWAN BIN SALLEH/6800000236 | MOHAMMAD RIZAL/BIN/JONEH/6794000109 | BONNEY BIN MASIONG8366000002 | MUHAMMAD AMIRUL IDHAM BIN MUHAMMAD REDZUAN6800000235 | elvinlasung08elvinlasung08 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | NORDIN/BIN/MAT REJAB/6794000106 | MUHAMMAD ZARUL NAQUIB BIN HAIROL AZMAN6794000100 | ALIF//AZIZI BIN CHE ABDUL AZID/6794000102 | RAJA NUR AIMAN/BIN/RAJA HARRUN/7018000295 | AHAMADSHUKRI/BIN/HASHIM/7018000293 | noramirulnoramirul | MUHAMMAD FIRDAUS HAFIZI/BIN/ZURYADI/7018000294 | MUHAMADKHAIRULHISYAM/BIN/MUHAMADISHAK/7018000291 | RENDDEY/LEE/ROSLEE/7018000292 | MOHAMADFIKRI/BIN/MOHDAKHIR/7018000290 | TONNY JOINIStonny7174 | NUSAIBAH/BINTI/AHMADADIB/7018000288 | MUHAMADAIMAN/BIN/ABRAZAK/7018000289 | ALNIZAM BIN HUSSIN6800000226 | MUHAMMADHAMIRULHAMIZANJUSRI/BIN/ABDULRAHMAN/7018000286 | dudezariel82@gmail.comdudezariel82@gmail.com | MOHAMADNORIMAN/BIN/OTHMAN/7018000287 | MOHD ARIFF BIN MD ISA6800000228 | MOHAMMED//FADZLIN BIN RAZALI/6800000223 | MUHAMMAD//KHAIRULDINIE BIN AYUB/6800000222 | MOHD//HAIZAMUDDIN BIN IBRAHIM/6799000198 | MUHAMAD//SHAZRIL SHAZWAN BIN SAMSUDIN/6800000224 | Chan Yi WenYvonneChan22 | NOOR BAIZURA/BINTI/MD ADAM/6800000221 | MOHAMAD AZIZAN BIN BUJANG6000051341 | jiajye chooi10265696 | SapriSerinSapriSerin | MOHAMMAD NABIL SHABUDIN BIN JASMIN6000064288 | RIDZAUDDIN//BIN HAMZAH/7018000237 | MUHAMMAD//HAZIQ BIN HALIMI/7018000238 | Chai Choon GuanVernonChai | NUR FATIHAH BINTI AYOB7018000236 | OSCAR EEPUN RAFAI7018000234 | DAYANG NORFAZILAH BINTI YASNI6000032210 | AHMAD TAQIUDDIN/BIN/AHMAD SARIMIN/6000030032 | Zulkarnaen Iswandy AbdullahOnsite_zulkarnain | ZAPFRIE ANAK TARINI6800000298 | Gunasegaran Kovintan10229590 | KHILAFI/BIN/HASAN/6800000290 | SYAIFUL/BAKHTIAR BIN/REBIN/6000044686 | FADZLI/OTHMAN BIN/MOHAMAD SUKOR/6000044687 | YUGENDRAN A/L TAMILSELVANyugendran | RAZALI//BIN ABDUL HALIM/7018000224 | SYRIL//ALFIJI BIN SUHININ/6798000106 | JasmizalAzizanJasmizalAzizan | NOOR//IBRAHIM BIN MD SOOD/6798000100 | MUHAMMAD ALIF AFIFI BIN ZAFRI7018000220 | mhdzaha85mhdzaha85 | MUHAMMAD BADRUL AMIN/BIN/AHMAD ZAHARI/6800000285 | CHANG XIN YI6800000286 | MUHAMMAD NOOR AZZAM//ABU BAKAR/6800000281 | MUHAMMAD NORHAFIQ//BIN SUHAIMI/6800000280 | HUSSAIN//MUSTANSAR/6800000283 | MOHAMMAD NASRUN//BIN AZMI/6800000282 | ROYSTON//ZAIMI/6000032228 | MOHD//SHAHEZAN BIN SISA/7018000262 | Chai Hongfeng10332162 | MOHAMMAD AMIR RAZDIMAN7018000263 | Wang Bin10208645 | MUHAMMAD//ASHARI BIN WAN MAT/7018000260 | MUHAMMAD//ASIF/7018000261 | Zaimi Mukhtar Bin Muhamadzaimi@southpac.com.my | RAHMAT//BIN SALEH/7018000259 | GUNALAN//A/L GUNASEGARAN/7018000257 | LALTU///7018000258 | MUHAMMAD//FIRDAUS BIN NASRI/7018000255 | JAGATHISEN//A/L UNNY KRISHNAN/7018000256 | MOHAMAD//HAFIQ RAZMER BIN ROSMAN/7018000253 | MUHAMMAD ADIL6800000278 | KENNY//CARLSON ANAK PETER/6000058860 | MUHAMMAD//MUBEEN/6800000279 | SYEDMOHAMAD//FARISAIMAN/6800000274 | mlwong08@gmail.commlwong08@gmail.com | TAN JIA LER6000009419 | Khairul Azman Bin Din6000076278 | MOHD BADRIZ BIN NANANGA0516221395011710976 | SHAMSUL/BIN/UJUT/8366000029 | NOOR AZLIN/BINTI/TEH KAMARUDDIN/6000034898 | YOGANAND AL//TDASS/6000016170 | Jedi Susanto Ehak Lewar8366000027 | ErnoZanErnoZan | AMRU//ARIFFIN BIN AHMAD/7018000251 | NOVEENRAAJ//A/L SUBRAMANIAM/7018000252 | MUHD//YAZID BIN SHUIB/7018000250 | low chunyip10332155 | YASMIZA//BINTI MD YASSIN/7018000248 | KARTIK A/L SUBRAMANIAM7018000246 | SHAHIN///7018000245 | KINNICK/JUVIE JR/KALIP/8366000034 | MUHAMMAD USAMAH/BIN/ISMAIL/8366000032 | REYSEEDO//SIGAN ANAK LATI/6000035750 | CEASERIUS CHRIS SUIMIN8366000033 | LEE SHENG YONG6000055344 | Sharidah SharudinCelcom_sharidah | SUREIN RAAJ A/L THIYAGARAJAN6799000109 | ///6799000107 | YASIR//ABBAS/6799000106 | NIMAL//SHANTHA PASKUWAL MOHOTTIGE/6799000101 | WB80042032 | KHAIRUL AMRI//BIN ABDUL RAHMAN/6000052262 | MOHAMAD AALIMY//BIN AASERI/6000050083 | HENRY/ANAK/WAT/6000050085 | GOBI KRISHNAN AL YALEPPE YELLAPPAN6799000103 | MOHAMAD FISHOL//BIN ABDULLAH/6000050087 | AINNUR//SHAHIDAH BINTI MOHD SOEB/6798000153 | Kamarul Azmir Bin Kamaruddinkamarulazmir | MOHAMAD//NASRUN BIN ARIFFIN/6799000130 | jerrymrg@gmail.comjerrymrg@gmail.com | ZULEFFENDY/BIN/BAHARUDIN/6000007266 | RUDY ANAK WELIS6000007268 | Li Wei10180260 | Wu Shuya00116343 | WATSON ANAK MAMBA7018000213 | MOHD JUSRIADI BIN KAMARING6799000129 | KHAIRUL//AZRIL BIN ABDULLAH/7018000214 | PUWANESWARAN//A/L SUKUMARAN/7018000211 | ROKHINI//AP BASKARAN/6798000111 | MOHAMAD BIN KIPLI7018000212 | LIM//WEI CHONG/6798000110 | FAHRURRADZI HELMY BIN SUHAIZAD6799000123 | MOHAMAD NASYWAN/BIN/HJ MOHAMAD MASHUD/6799000122 | JIMMY//GANAN/6799000120 | Awang Izzuddin AzraeiAwangizzuddin | MUHAMMAD//HAZIQ BIN MOHD NOOR/6799000127 | KHOO CHIA WEI6798000118 | MUHAMMAD//SHAHIFUL BIN YUNUS/7018000217 | MUHAMMAD//HAZMAN BIN HASSAN/7018000218 | NORZALI//BIN JOHARI/6799000124 | Wincywincy@datasco.com | AyunieAyunie | ROZAILI BIN SABELI @ RABIAN6000076232 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | MUHAMMED//NUR QUYUM AL-HAKIM BIN RAHMAT/7018000205 | AHMAD//AL HADI BIN KARIMUN/6799000119 | FANCESOXWAU//BIN YANGAN/7018000202 | ALI//ATIF/6799000118 | EZRIN TASNIM BIN ABDUL GANI6798000128 | ALI//NAZAR/6237001298 | AHMAD//FAIZ AIMAN BIN MOHAMAD/7018000203 | SARAN//KUMAR A/L SASIKUMAR6799000117 | MOHD//RIZSHAM BIN MOHD RUSLAN/7018000200 | MOHD NOR ARIFFIN BIN YAHYAA0669548229546844160 | WB80041943 | MohdHasrafMdRouseMohdHasrafMdRouse | BARANEEDARAN//A/L SELVADASS SEBASTIN/6799000111 | NASRIAFIFI//BIN RAMALE/7018000209 | KANNAN A/L RAMACHANDRAN6799000115 | AhmadFirdausHakimAhmadFirdausHakim | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | BishmanA/LParapakaran///6799000113 | FANILA//ALOYSIUS/6000062819 | Zamri B AdenanZamri1973 | AHMAD REZUAN/BIN/HASHIM/6000062817 | AMRAN BIN AHMADamran_ahmad | HERIYANTO/BIN/LAGAN/7539000080 | MUHAMMAD HAFFIZUDDIN HAIKAL/BIN/AZLAN/7539000081 | HENGKEY/BIN/JEM/7539000083 | MUHAMMAD HAKEEM BIN RUZMAN6000014739 | SUZANA/BINTI/MAD JUSOH/7539000078 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | MOHAMAD AFIQ BIN MD DAUD6798000057 | Hasmadi Abd RahimHasmadi_Edotco | SHARIF MUSHAIK//ZULFIKAR/6000010382 | Amir hamzah B. Mohamad RamleeOnsite_amir | Nuraqira Fidianti Binti HQira22 | Aidaaida@datasco.com | TohSooJinTohSooJin | Amerul5243.datascoAmerul5243.datasco | NUR//FARAH ADLIN BINTI NOR AZMAN/6798000072 | MohdSapianSujakMohdSapianSujak | MELVIN//ANAK ERIC/7667000010 | MOHAMMAD FIRDAUS//HAFIZI/6000010370 | PEK//WEI LIANG/7667000001 | KHO//CHUNG PING/7667000002 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | WONG//KIONG MING/7667000004 | MOHD//FIRDAUS BIN MOHAMAD LOTFI/7539000062 | AZRUL FIKRAM BIN MOHD THANI6237000863 | LAU//HOCK KWANG/7667000005 | Soh//Kok Teng/7539000063 | PAUL BIN KINJOD7667000006 | MUHAMMAD//ISMA HARITH BIN KAMARUDIN/7667000008 | THOMAS//ANAK GEMA/7667000009 | Zhang Chuntao10069782 | SITI NORHAFIQA BINTI AZMI6798000041 | Chai Jie//Liu/6000047689 | MUHAMMAD ASHMAWI/BIN/HAMDAN/8992000001 | LYEANA NUR AIN BINTI ABU KASSIMlyeana@yptt.com.my | Chiew KokChen10352132 | Chan/Chun/Kit/8992000005 | EOH YANG CHEN TAKeohyang@qingnitech.com | MUHAMMAD AMIR AQMAR/BIN/NARZURAIDI/8992000004 | MOHD FAIZAL/BIN/UNDING/8992000003 | MUNISWARANE/A/L/KRISHNAN/8992000002 | HASSAN ALI6000078398 | Muhammad Nurafik Bin Ahmad6000070457 | JelsiJassJelsiJass | WB80041436 | NazariNazari | MUHAMMAD ARIEFF AIMAN/BIN/MOHD AZMI/8992000008 | MOHAMED REEZA BIN MOHAMED8992000007 | WAFA//BINTI MOHD HASLAN/6798000054 | AZIZUL//ANEH/6000048548 | MUHAMMAD FARIHAN/BIN/YAACOB/8992000006 | team44gcitechnicalteam44gcitechnical | AZamaniAZamani | SHIRLYN//TING CHEAU MUN/6798000048 | JohnMichaelJohnMichael | POO//CHEE HOE/6798000047 | AHMAD FAKHRUL HAZIQ BIN ROSZLAN6798000046 | SitiHamidahSitiHamidah | NurhannahJamaludinNurhannahJamaludin | MOHAMMAD RAZMI//BIN DAMDERAH/6000028944 | MatYatimMatYatim | team41gcitechnicalteam41gcitechnical | MOHD JAWAWI//ARIFIN/6000004974 | HamzahBinAhmadJoharHamzahBinAhmadJohar | Shafiq Iqmal Bin Shaarani6000008098 | Muhammad//Aniq Qusairi Bin Md Yusri/7539000033 | Muhamad//Samsuria bin Abdul Daim/7539000034 | Mohd//Fariq Bin Samsuddin/7539000035 | Roland Interlas6000008096 | MUHAMMAD//FITRI BIN SAFRIMAN/7539000036 | Saifuddin//bin Sulaiman/7539000030 | MOHD RIDZUAN BIN MOHAMED NAWI6798000099 | Zulkifli//bin Sulaiman/7539000031 | Muhammad Zulhelmi/Bin/Muhammad Asri/6000008092 | AMIR//SALIHIN BIN ABDULLAH/7539000032 | azman.ahmad@yptt.com.myazman.ahmad@yptt.com.my | KU//MUHHAMAD AIMAN BIN KU HAMDI/7539000038 | AZAFUDDIN//BIN MOHAMAD/7539000039 | EHORNSON BIN PARASINEHORNSON | NUR AZMAN BIN AHMAD6000066371 | Hinjecklee//Bin Soimin/7539000024 | ELLYANI//BINTI IDRUS/7539000025 | FARHAN HAKIM BIN ABD WAHAB6000070866 | HAIRIZAT//BIN MOHD ISA/7539000020 | Lee Yoke Seang7539000021 | PRAVIN NAIR//AL MAHAY INDRAN/6000058750 | Shah//Hakimi Hassan/7539000026 | Dinie//Syahmi Bin Norzamri/7539000027 | MOHD SYAHREDZA BIN SAPARI7539000028 | MOHD//RADUAN BIN HANAFI/7539000029 | ABDUL LATIF//ARSHAD/6000026740 | MUNIANDI A/L AYAHOO6000022382 | MUHAMMAD//IZZAT BIN BADRUDDIN/6798000084 | NURUL//AMIRAH/7539000060 | saadalkhir.sholahsaadalkhir.sholah | NURUL//ASHIKIN BINTI MOHAMMAD SHAH/7539000061 | NoorMohamedNoorMohamed | MOHAMED AMINULLAH BIN NORDIN AHMAD6000071749 | Abdullah Bin Siromasirom | FATIN//NOR NASYSUHA BINTI BERHUNIDIN/6798000078 | MOHD//FARHAN BIN CHAMIRON/7539000053 | ong chiajye10307162 | NOR AFIQ/BIN/NORDDIN/6000037844 | Yee//Choon Kiat/7539000059 | Guo Yasong10343220 | LimSweeBengLimSweeBeng | WB80039955 | BENNIE FRANTI6000037848 | FaridahOmarFaridahOmar | MAZELAN BIN RAMLI6798000096 | JohnmanGonzagaJohnmanGonzaga | LONG//TIEN TUCK/6798000095 | Feng Xijie10355208 | Ong Chee Sern10099189 | Mohd Amir Hafiz bin Othmanleafermaho@gmail.com | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | SirusAnakSirusAnak | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | Nor//Syamsyairi Bin Hashim/7539000044 | MUHAMMAD//HAKIEM SAHARUDIN B MOHD AB AZIZ/7539000045 | Mohd//Faddeli Bin Mohd Nor/7539000046 | AMIRUL SHAFIQ AQMAL BIN KAMARUL AZRI7539000047 | MUHAMMAD//ZAKI BIN HARON/7539000040 | RenCatikaRenCatika | RifinusKadoRifinusKado | MUHAMMAD NUR IZZUDDIN BIN MUHAMED MAZLAN7539000041 | MUHAMMAD AMINUDDIN BIN ABIDIN6798000088 | HASRUL LIZAM BIN MISROHasrulLizam | YAP AH MOOI7539000042 | Sazly//Bin Miskom/7539000043 | SUHENRAJ A/L PALANIAPPAN6000070886 | NorazuraNorazura | Learns//Walter/6000028503 | MOHAMAD ZAKIMI AKMAR BIN MOHD ZALAHUDIN6000003203 | Shukri NurdinEncemboy | WB80042073 | NorHazidaHamdanNorHazidaHamdan | MOHD//TAUFIQ BIN AK SANI/6237001301 | OLEKSANDR PROKOPCHUK6237000453 | PETRUS BIN SAKAI6237000455 | Mohd Zaaba Bin BaharudinMohdzaaba | RoslanMohamedRoslanMohamed | Fatihah Anis Mohd AluiFatihah | Muhammad Syahrilmsyahrilsaad | Ragunalan//A/L L.Krisnan6000006720 | ChokJC_Chok | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | MOHD RAFIZAN//BIN ABDUL HAMID/6000049459 | ahmad nasir bin sebawians2025 | MUHAMMAD SAHLAN//BIN BAHARUDDIN/6000040639 | Tan Kai Yang10196236 | HANDRICK MAGREENhandrick92 | Liu/Feilin6799000099 | AnvarulHaqueAnvarulHaque | KYAW THURA HTOON6000005840 | yutamnil89@gmail.comyutamnil89@gmail.com | MOHD//FUAD BIN MOHD ZANIN/7539000011 | SOMU//A/L VISVENADEN/7539000012 | LOW//CHUN WAI/7539000013 | PARANEETHARAN//A/L ARUMUGAM/7539000010 | RAZALI//BIN TAHA/7539000019 | NasTamimiNasTamimi | macxmapahin@gmail.commacxmapahin@gmail.com | MUHAMAD HAZIQ/BIN/HASSAN/7539000015 | SAJROKI//BIN SAJURI/7539000016 | MOHD//HAIRUL ZAHRIN BIN IBRAHIM/7539000017 | GabraielVictorGabraielVictor | DARMAWAN BIN BAMBANG6000005850 | romariodaymolromario_daymol | CHUA TECK EE7539000001 | WONG//MAN LEONG/7539000002 | Zhang Huimin00328154 | LiawBingShenVincentLiaw | WAN NURMISWARI BIN WAN ISMAIL6000014316 | RAVINKUMAR//A/L ANBALAGAN/7539000008 | RAJA//LOGESWARAN A/L RAMANATHAN/7539000009 | Sulaiman_MohamedSulaiman_CelcomDigi | MOHAMMAD//NAJIB BIN AHMAD FUAD/7539000004 | Siti//Nor Shafika Binti Mat Nazri/7539000005 | Mohd Norhalif Bin HusinHalif | MUHAMMAD ASHMAWI BIN HAMDAN7539000006 | NG//MING KWAN/6000038345 | Muhammad Afiq Bin Mat Jalil7539000007 | LASRIN/BIN/MIRURUK/6000027213 | RAYMOND TIM PELIMUN6000027212 | Halim bin Bohari6000069011 | YUN//CHENG TAO/6000005422 | SYAHREZAM//BIN ZAKARIA/6237000892 | NICHOLAS JIMBAU ANAK BEELA0669549501787873280 | Trintel (M) Sdn BhdWB80041310 | SANKARSON//BHATTACHARYA/6237000899 | MUHAMMAD SABHI RAJAIE B MD SUKERIA0579455208717598720 | Faiz Aththayyib bin Mohd Shaheziomha | MohdFaizalBMMohdFaizalBM | ABD RAZAK//BIN MD REJAB/6000060670 | MOHD LUTHFI/BIN/JUSLI/6000039611 | DOUGLAS/ANAK/COLIN/6000039613 | NorAzzahraNorAzzahra | AbdulAfiqinAbdulAfiqin | Thanniya A/P Annandarajahthanniya | NURAQIRA HASSIMnuraqira.datasco@gmail.com | ANDY//ANAK DARI/6237001720 | SUP10001836 | MOHD ALIFF BIN MOHD BASHAH6237001727 | GEM//L JIMENO/6237000879 | KENNEDY//MEDIK/6000035265 | PadmanathanPadmanathan | RAZDIMAN/BIN/MASRI/6000050404 | WB80036974 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | MUHAMMAD FAKRIE AMIR BIN MOHAMAD NOOR6000015203 | Karthikeyan Rehilmmq | Chan Wei Yee6000015205 | MOHAMMAD ADDAD//BIN AZEMAN/6237001736 | ZARIF KHAIZURAN//BIN ZAMZURI/6000006738 | RafizaMohdRedhuanRafizaMohdRedhuan | KHAIRUL-//MIEZZAN NAZZARUDIN/6794000011 | OBADIAH/THOMPSON/ANAK THOMAS/6000028467 | DENNISUS//BIN MATIUS/6794000012 | ZULAKMAR HAZWAN BIN ZULKHEFLIzulakmar.digi | MUHAMMAD//NAZIRUL HAKIMI BIN DILMI/6794000014 | MUHAMAD//FARIS BIN MOHMAD ARIFIN/6799000031 | AZMAN//BIN AHMAD/6794000010 | Qi/Xiuxian6237001392 | MOHD AMIRUL AZWA BIN EDY WALOYOAA92 | FREDDY CELVIN//DAIZ JHOSEPH/6000043613 | RIZAL//FA'IZ BIN RAMLI/6799000024 | MD//ERWAN BIN ROHMAN/6794000008 | MOHD//HAFIZOL BIN ABDUL WAHAB/6794000009 | CHOW KAH KIN6799000022 | Ning Fengshan10108301 | AMRIN//BADALLUMIN/6000030310 | Tang/Pujie6794000004 | NIU/CHAO6794000005 | MohamadTarmiziMohamadTarmizi | JahganathanThamotheranJahganathanThamotheran | MOHD//AMIRHAFIS BIN OTHMAN/6794000007 | Frederic larinisERLAFRE | MUHAMMAD SYAFIQ/HAKIMI BIN/AMIRONZI/6000030311 | CHIA//YIE LOON/6237001397 | HSU//MYET CHAE/6799000011 | BadrulHisyamBadrulHisyam | DANIAL ZAKWAN BIN MAT SAAT6794000033 | MUHAMMAD//SYAZANIE BIN EIDROSE/6794000034 | AMIRUL//AZRI BIN IBRAHIM/6794000035 | SHAHARIN BIN RUSLAN6799000052 | NUR//HAFIZAT BIN ZAKARIYA/6794000030 | Nurul Nizam//Bin Mohamad Sulong/6000053448 | KamilSharulhizamBinAhmadKifliKamilSharulhizamBinAhmadKifli | MOHD//REZUWAN BIN KASSIM/6794000031 | LIM//WEI SIONG/6799000050 | NORAZHARI BIN MOHAMAD SALIM6794000032 | Quinting Sungesunqui | Li/Xiangshi7666000002 | NURAQILAH//BINTI AZMAN/6237001371 | WB80041744 | ABDUL FAIZAL DUMILANAU/BIN/HASSAN/6800000315 | SURESH KUMAR BANGALORE SHANMUGAM6237001369 | ABDUL//AZIZ BIN MD SAAD/6794000026 | NURUL//MIRZA IZZATI BINTI MOHD RAFI/6794000027 | LEE//TZE LEONG/6794000028 | AMIRUL//ASRAF BIN MOHD KASIM/6794000029 | MUHAMMAD//HANIS FARHAN BIN BAKRI/6794000022 | ECO PURNOMO BIN BAMBANG6794000023 | MOHAMAD TARMIZI BIN MOHAMAD MUSTAFA6794000024 | JUPRI BIN JASNI6794000025 | Hou Wenhao10324007 | MOHAMAD//FIRDAUS BIN MOHD SHAHARUDDIN/6794000020 | MUHAMMAD//ASYRAFF BIN ZAITON/6794000021 | MohdHaizalMohdHaizal | MUHAMMAD HAZWAN/BIN/KAMARUDIN/6800000308 | Wang/Zhiguo6800000303 | MOHAMMAD//NORHISYAM BIN KERNI/6794000019 | HASRUL//LIZAM BIN MISRO/6794000015 | NAZERI//BIN KERNI/6794000016 | RISON//BIN ONGIKAL/6794000017 | ASFA//BATRISYIA BINTI CHE JUHAN/6799000036 | MOHD//AZHAR HANAFI BIN SAMSUL/6794000018 | MOHD/ROSLI/RAMLI/ROSLI8217000046 | HADYNATA BIN HARUN7167000010 | Paula//Nina Anak Kuchop/7167000011 | MUHAMMAD MUSLIM//BIN RAZALI/8217000044 | MOHMAD RUSOL//BIN ISHAK/8217000045 | Abang//Alfian Bin Abang Zainudin/7167000015 | Abdul//Malik Abdul Latip/7167000012 | AZRI//BIN ABDULLAH/6799000073 | NEVILLE JUDE RONNIE7167000013 | WongSoonHoWongSoonHo | NURAINESURAYA/BINTI/HISAM/6000049369 | team9gcitechnicalteam9gcitechnical | JocelynIsabelleJocelynIsabelle | IBRAHIM//BIN SAHABU/7167000007 | ROLANDO ABIA6000017373 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | ROSHAH IZWAN HAFFIZ BIN ROSMAN7167000005 | CHOW//YUEN KEAT/7167000006 | SPENCER CEDRIC YUSAK6000017370 | JOHANSSON MELAI BIN SAPINAR6000017376 | MAN BIN HARUN7167000009 | Ahmad Syafiq Fahmi//Bin Abdul Gapar/8217000035 | Liew//You Chiang/8217000033 | MOHD AMIRUL AMBRI//BIN ABD HAMID/8217000039 | DINESH SINGH CHEEMA7167000003 | DATU//AZRUN BIN DATU HARUN/7167000004 | Ally//Alistair Gerald/7167000001 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NAZIHAH//BINTI AMIRUDDIN/6799000061 | Nur Syazwani//Binti Saliman/6000049377 | DANNY EBIT ESOH6000017368 | Li Tuanxi10208190 | Tan Chor Boon10349353 | AZMIL COZY SWAN//BIN JINAL/8217000042 | MOHAMMED SAEED//ESHAQ/8217000043 | Mohd Faiz Syazwan//Faisol/6000038245 | NURUL NABILAH BINTI MOHD NASIR6799000092 | CLEMENT//YII MING KIAT/6799000091 | MOHD FAIRUS BIN YAACOB6237001326 | ng xinhwan00349041 | HarizDiaurahmanHarizDiaurahman | Liu Qixing10030436 | AbuYazidCheLahAbuYazidCheLah | NICKHOLAS JEEWELL KERAYAN PENIAS6000018202 | MUHAMMAD//SYAFFIQ BIN ABDUL MALEK/6799000082 | MuhammadNazminMuhammadNazmin | SITI//HAJAR BINTI HAMZAH/6799000086 | Norhaliza KiprawiNorhaliza | Roslan Bin Mohamed @ Ahmadroslanmo | MOHD/NIZAM/BIN JIFFERI/6000042755 | MOHD RAFIQ REDZA BIN RAKAWI6000059181 | PILIN//BIN JAMAJI/6000041428 | HIFZHAN//BIN HAYOM/6237001335 | Hafiss Ishakehumhis | ABDULLAH//BIN MOHD ARSATH/8217000002 | EVELYN PUYANG RUBIN6794000099 | Jumady Bin Baharuddin6000056538 | Ahmad//Salehudin/8217000003 | MohamadFaiz/Bin/AhmadJohari/7167000052 | ZAINOLKHAIREE//MOHD NASSIR/8217000001 | Murugan//A/L Velusamy/8217000006 | FATIN//AMALINA BINTI AB PATAH/6794000095 | ELVEN//LASIUS/8217000007 | MOHAMMAD//YUSRI AZIZAN BIN MUSTAPAH/6794000096 | RICK//JASON A/L DAVID/8217000004 | NORHAFIZAH//BINTI ZAHARI/6794000097 | TAJA//KALANG/8217000005 | JAUNAIDY BIN ENGKOH6000064160 | Peter Dick GimpuhutPeterDG | MOHAMAD SYAZUWAN BIN EIDROSE6000064161 | ABDUL//WAFIY BIN ABDUL HAMID/6794000092 | Zulkarnain MustaphaZulkarnain_Edotco | Noorhusna//Nabilah Binti Zainal/8217000009 | SURINDER SINGH//AL JOGA SINGH/7167000050 | MUHAMMAD KHAIRUNNAS//BIN NALLATHAMBY/7167000051 | HARRISON//PALUNG/6000044550 | TanSihSinTanSihSin | KhairulZawaniKhairulZawani | MD//FAIRUZ NGARIP/6798000215 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | asraf.datascoasraf.datasco | MOHAMMAD IQBAL BIN JAAFAR6798000211 | MOHAMMAD RAIMI BIN DAM @ DERAH6000011632 | ABD RASHID BIN OSMAN6000078333 | TAMOOR IFTIKHAR6000078334 | MUHAMMAD IKRAM BIN ALIAS6000078335 | Stevefandy//Gilbert/6798000219 | MohdNizarAbdulRaniMohdNizarAbdulRani | AbdulHannaanAbdulHannaan | USMAN//LIAQAT/7167000043 | MUHAMMAD ROBBIL AKRIZAN//BIN SHAARI/7167000044 | DAVID//THOMAS/6794000089 | WESLEY/JUSPHER/TAHIR/7167000041 | MOHAMAD SUBRI/BIN/MOHD ROSLI/7167000042 | MUHAMMAD AMIRUL ASYRAF//BIN MOHD LAZIM/7167000047 | DUBLIN UKOM ANAK CHENDOM6794000084 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | Mohd Fitri//bin Abdul Rahman/7167000046 | HASLAN BIN HARUN6794000087 | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | NOR//ALIYA NISA BINTI ANUAR/6794000081 | RAMACHANDRAN//A/L SUBRAMANIAM/6794000082 | MUHAMMAD/DOSUKEY/BIN JOHARI/7167000040 | 王志国wangzhiguo@gcidesign.com | MOHD HAQIMY BIN NIBONG6000064157 | JORDAN CHEW DING JIAN6798000221 | mrtaufiq07mrtaufiq07 | PAUL MIKI ANAK DIGUN7167000038 | Blue Beyond10055749 | BIVOON/ALEXZANDER/DIGUN/7167000039 | ChenHui Lim00347231 | ROYSTON//ANAK RAMSY/6798000228 | Zakaria//Bin Jamaluddin/8217000024 | KAMARUL AZMAN//BIN MUKHTAR/7167000032 | Jaidi//Tati/8217000025 | CHEW//KAH KEAT/7167000033 | SYAKIRIN/BIN/MANSOR/SYAKIRIN/8217000022 | RALPH O'BRYAN HILARY7167000030 | MOHD KHAIRUL HAZHEEM/BIN/MOHD RAHIMIE/6000036948 | RUZAINI/BIN/MUPANGAT/RUZAINI/8217000023 | ALEXROTKEEY BIN MATHIUS7167000031 | SHAHRIZAN BIN MOHD ZAINI7167000036 | MIKE ADDISON/ANAK/COLIN/6000036946 | Jaywell//Anak Erie/8217000029 | AMIR/BIN/ROSSAIFUDDIN/7167000037 | Majdi//bin Mahat/8217000026 | MUHAMMAD ISMAIL BIN ADAM SHAH7167000034 | Mohd Shahrizan Bin Kusairi6000076163 | Edwerd//George/8217000027 | RIZAN//RAHMAT/7167000035 | DENNIS/ANAK/SAMI/6000036945 | MuhammadWafiMuhammadWafi | Abdul Rauf Bin Junaidi6000076161 | FaizBinBaharudinFaizBinBaharudin | ShamsulMazliShamsulMazli | AHMAD//FAIZ AIMAN BIN MOHAMAD/6000031264 | STEFLEND//KAYA BIN BESAR/7167000027 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | Firman//Bin Mohamad/8217000031 | AIN HIDAYAHhidayah@girobumi.com.my | Idris//Bin Asim/8217000032 | Qutni//Bin Harun/8217000030 | DOMINNIC//ANAK AHHOLE/8217000013 | MARTO FERDANEND BIN MOTIAS7167000021 | ROBSON//ANAK OSCER/8217000014 | RONNEY//LOUIS LUSIN/7167000022 | AHMAD//NAZIRUL BIN AHMAD ABIR/8217000011 | MUHAMMAD//HAZIQ AQEEL BIN MOHAMAD RADZI/8217000012 | Royson//Anak Stephen/7167000020 | KAVINES///8217000017 | MOHAMMAD//NOOR AZLIZAN BIN RACKSASA @ JAMIL/7167000025 | IQBALIKRAM/BIN/ALADDIN/IQBAL/8217000018 | WILFRED BALANG7167000026 | LUKE//ANGGAI ANAK MIGAT/8217000015 | Suhatman//Bin Bambang Margono/7167000023 | NANTA//KUMAR A/L GANESAN/8217000016 | MOHD//KHALID IZHAR BIN SUBOH/7670000009 | AZREN//AZHAZEHAN BIN AZMAN/7167000024 | MOHAMMAD FAIZ BIN AHMAD6000068531 | MOHDFAIZAL/BIN/ABDULLAHKHAIRULCHIL/FAIZAL/8217000019 | AG//MOHD SHAFFIQ BIN AG SIDEK/6798000203 | RUBUN//A/L THIYAHARAJAN/7670000010 | MOHD FAHMI BIN DAHLAN6798000202 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | ALIF//ILYASA BIN RUSLI/6798000204 | MICHEAL//BICKSON ANAK BANING/6798000201 | MOUREEN//BINTI SIPIN/6798000200 | Wong//Yit Siang @ Fatrick/7167000018 | Edward//Vijay A/L Clement David/7167000019 | RICKY/ANAK/JACK/6000033453 | NUR//AFIQAH BINTI MOHD ROSDI/7670000015 | LARRY//@IGNATIUS BIN LOLIN @SIGI/7167000016 | KAMAZUL//SYAIRAH BINTI KAMARULZAMAN/7670000016 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | MOHDFAIS/BIN/MOHDZUKHI/FAIZ/8217000020 | FREDDY//BIN JUSTIN/7670000013 | MUHAMMAD//HELMI ARIF BIN ARIF/6798000207 | MOHDFAISAL/BIN/MOHDSHARIFF/FAISAL/8217000021 | Awg//Yazid Bin Awang Samsudin/7670000014 | RAHMAD//HIDAYAT BIN LAMRI/6798000206 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | AZIZAH//BINTI A.RAHMAN/7670000012 | MUHAMMAD//IKRAM BIN AZMAN/6798000208 | PHILIP//BIN SUNGKIT/6794000055 | Nazaruddin//Bin Hamzah/6000055646 | VuiChungThienVuiChungThien | DIUSLIN//JUPILIN/6794000056 | DENILSON JUSLIN6794000057 | JORDAN CHIN ZHEN WOON6794000058 | MUHAMMAD//DZAKIRIN HILMI BIN DILMI/6794000052 | JOENNY//BIN GEORGE/6794000053 | FREDRICK TUAH ANAK EDMUND6794000054 | MOHAMAD/ARIF/SILI/6798000263 | Mohamad Wazir Bin Mohd TarmiziA0607607069848809495 | MACX//MAPAHIN/6794000050 | Mohd//Rashiman Bin Mohd Rasid/8268000018 | MOHD//ROSMAN BIN MAT ALI/8268000015 | KHAIRUL//FIKRI IKHWAN BIN MOHD JUSLIN/8268000022 | PHILIPS//VHURAJKUMAR A/L TAMAL SALAVAN/8268000020 | RAYMUND//BIN EDONG/8268000021 | KUGEEN/AL/SUKUMARAN/7018000311 | MOHAMMAD//MAARUF/6000021467 | VISHNUTHARAN//A/L GOVINDASAMY/6794000048 | DOMINIC DAVIES6794000049 | TANG/CHUNG/SIONG/7018000317 | MohammadNurSyafiqMohammadNurSyafiq | NUR//SYAFIQAH BINTI MASTORI/6794000044 | LAU/LEE/HAW/6000031206 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | Zafri ZainalZafri_Edotco | HASMADI//BIN HUSIN/6794000046 | HEZRON//MAPAHIN/6794000047 | Nur Athirah//Binti Shamson/6000055639 | NIKSON//BIN SINAL/6794000041 | JAISON//MOJITOL/6794000042 | MUHAMMAD//ALIFF AFFENDI BIN ADDY SHAM/6794000043 | MOHAMMAD//YAAKUB/6000041492 | SUHAILA//BINTI LANIN/8268000008 | ERIC/SIMON/DAMIT/6000021463 | ASNIAH//BINTI LANAGA/8268000009 | SAUFI//AFFENDY BIN BASRI/8268000006 | Gordon Bryan Robert6000021461 | HAMSAH//BENNU/8268000007 | ABD//KAMELL BIN ABDUL LATIP/8268000004 | MOHAMAD//SALLEHUDIN BIN HASSAN/8268000005 | Team2gcitechnicalTeam2gcitechnical | ABDUL ATIQ BIN KHALID8268000013 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | NIK//AJIJAN @ NIK MOHD AZIZAN BIN HJ.OMAR/8268000014 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Ou Linjun10192118 | SUZAIN//BIN MUSLEE/8268000011 | udandny@gmail.comudandny@gmail.com | ERMAN//SHAH BIN YUSOP/8268000012 | NUR FATIMAH AZZAHRA/BINTI/HAMZAH/7018000302 | FATIN//HAFIZAH BINTI RAMLIN/8268000010 | Shen Jiaqi10288670 | MUHAMMAD SYAKIR/BIN/AHMAD FAUZI/7018000307 | MUHAMMAD//HADIF BIN RIDZUAN/6794000037 | FAHRUZI/BIN/DAHALAN/7018000308 | PARTHIBAN//SACHITHANANDAN/6794000038 | Roger Augustine//Anak Laga/6000055640 | CHEONG/SENG/WAH/7018000306 | MUHAMMAD//HAKIM BIN ZAMAN HURI/6794000077 | AKMAL//BIN RAZALI/6794000078 | MUHAMMAD//SYAMIL HANIFF BIN AB RASHID/6794000079 | WAN//MOHD AZRI BIN WAN MUDA/6794000073 | ALIF//IQMAL BIN CHE ABDUL AZID/6794000074 | ShahrulnizamShahrulnizam | FARIZUL//SHAFIQ BIN ABD WAHAB/6794000070 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 | He Zhiyong10078413 | Hao Wenjie10077566 | WERN JUN//NG/6798000240 | MOHD//SHAHRIL BIN RAMLY/6794000072 | SAFARUDDIN BIN MUT8268000002 | Naseer Ahmad//Muhammad Mansha/7021000102 | MAHENDRAN A/L MUNIANDY7018000336 | NoraziraNorazira | BOSLEY ANAK JUKEN8268000003 | Tahir Hussain Muhammad Arif7021000101 | BadrulNohBadrulNoh | MOHD NIDZA IRFAN/BIN/MOKHTAR/7018000334 | MAIDIN//BIN TANJILUL/8268000001 | MOHAMMAD ADDAD BIN AZEMAN6798000232 | MOHD DZUL AFFENDY/BIN/CHE DAN/7021000105 | ELWIN OMUKUL6000001832 | BADRUL HISHAM BIN ABDUL RAUB6799000003 | HU SWEE FONG6794000066 | KEEGAN//A/L A.K ANTHONY SAMY/6794000067 | YAP//WEI LOON/6794000068 | MUHAMMAD RIDHUAN BIN ROSTAM6794000069 | CHE//SHARIZEN BIN CHE GHANI/6794000062 | SHAFIKA ANASTASIA ANAK PAENG6794000063 | shahzam89shahzam89 | WAN/MUHAMMAD HAZIQ/BIN WAN SAPERI/6000055659 | CATHRYN LEIGH ANAK ALISTER AUSTRALIA6794000065 | CALVIN/RAY/BENEDICT/6798000250 | MOHAMMAD FIKRI/BIN/ABDUL RAZAK/7021000108 | WATSON SUMBANG CHANDONG6794000060 | AZHAR TARMIMI BIN ABDULLAH6794000061 | MOHAMAD HAZEEM/BIN/MOHAMAD OMAR/7021000112 | MATHEW/JAMES/LO WUN SING/6798000248 | ADAM/BIN/ABDUL HADI/7021000116 | WERN JUN//NG/6798000242 | MOHAMMAD ADDAD//BIN AZEMAN/6798000245 | MOK ZEE JIAN7018000320 | MOHD//AMIR BIN SAMSI/6798000244 | IMRAN ALI MUHAMMAD YAQOOB6000069817 | SHAHRUL IZAMshahrulizam@southpac.com.my | LEONARD JEE6794000059 | RAZALI/BIN/RAMLI/7018000328 | THINAGAREN A/L SUBRAMANIAM6000076588 | IBRAHIM BIN ABU BAKAR6000019123 | Norsyahriani Binti Ibrahim OoiSyahriani | MuhammadAmeerMuhammadAmeer | ROLAND JONG FOH CHOI6000068481 | KENISTON//ANAK SPANCER/6798000184 | AUSTIN//CHIONG CHUNG YAU/6798000183 | Mohd wafifahmi10353358 | MOHD//SAUFE BIN MOHAMAD/6798000180 | STEWARD//ANAK KINO/6798000182 | FAIZ/FATHULLAH BIN/OBAIDILLAH/6000050719 | BETARMOKE//ANAK COSIT/6798000181 | DAROS//BIN KIMORI/6798000177 | MUHAMAD AZIZI/BIN/SAJURI/6798000176 | ZULKIFLI//BIN SULAIMAN/6798000179 | MOHAMMAD//FAIZAL BIN AHMAD/6237000975 | Liang Zijin10170235 | MuhammadFakharulHilmeMuhammadFakharulHilme | NOR//HAFIZ BIN SAMSUDDIN/6798000178 | Mohd Zawawi Bin//Ab Rahman/6237000977 | Muhammad Nur Ahza Bin Ibrahim7019000166 | ABDUL//HALIM BIN ZULKIFLI/6798000197 | JURINA ANAK LOIS6000069320 | Murthy//Muniandy/7022000005 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | Monayem//Hossain/7022000003 | ISTIKHAR//AHMAD/6798000193 | team23gcitechnicalteam23gcitechnical | ALI//HAMZA/6798000192 | QuahJunhanQuahJunhan | MUHAMMAD//NIZAM BIN SIJAOL KHAN/6798000188 | MOHAMMAD//FIKHRI ADHA BIN SAYUTI/6798000187 | MUHAMMAD//AMIRUL FAIZ BIN RUZAIDI/6798000189 | SUP10001423 | Muhamad Zuhdi Bin Hamid6000044050 | Nor' Aizuddin Bin Mohd DaudNorAizuddinBinMohdDaud_YPTT | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | SYED//MUIZ BIN RAHAMADDULLA/6798000161 | Jedi//Susanto Ehak Lewar/6798000164 | John Buda//Anak Munan/6000009248 | TONI//ANAK KUMBONG/6798000163 | Zhong Jian10114556 | KHAIRUL//HAZIQ BIN ABDUL AZIZ/6798000159 | AZMIR//KHAN BIN HASAIN/6798000158 | asb01teamasb01team | KUM//POOI YEE/6798000154 | ARIF//BIN ZAKARIA/6798000157 | 罗尔伍6696000002 | Li Jie10163918 | MohammadHafifiMohammadHafifi | NAVIN KUMAR A/L RAJENDRAN6000067160 | AlexNguAlexNgu | Deyroy//Dylan Dolorian/6798000173 | Fazrin//Azry Bin Afrizal/6798000172 | MUHAMMAD//DINIE BIN YAHYA/6798000175 | MOHD//NAZMIE BIN MAHMUD/6798000174 | AhmadFaizulAhmadFaizul | Muhammad//Nabil Bin Zulkifli/6798000171 | Izat//Bin Roslee/6798000170 | Mohd//Faiz Bin Amdan/6798000169 | WAN ABDULLAH SA'ID BIN WAN NAZRI6798000166 | SHAHROL BAHTIAR BIN SAAD6000020026 | Amirul//Izham Bin Mat Hashim/6798000168 | Muhammad//Fikresya Bin Nadzrol/6798000167 | Lee PeiLeng00196239 | LUNSING//PAUNSIN BIN MOGIRONG/6000059548 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | Su Hongbing10066376 | FREDDY//ISHAK/6000035518 | Darwisley//Bin Buing/7019000130 | Girobumi Technologies SDN BHDWB80037456 | JAMESON//LOH/6000035517 | tseping//wang/6819000006 | MohdYusriBinYusoffMohdYusriBinYusoff | Muhammad//Shahbaz/7019000128 | ATEEQ//BIN AZAIRI/7019000129 | ANISYAHIDA//BINTI ABDUL HALIM/7670000006 | leslie.wie95leslie_wie95 | MOHD//IQMADATUL IKHLAS BIN ZAIDEL/7670000007 | FLORIAN//BIN ENJOL/7019000125 | VINDELLY//MICHAEL/6000035524 | NIKOL BIN PELIN7019000126 | AZDZAZUL//TARQI BIN ABU BAKAR/7670000005 | DD ROWEKAH ROGER7019000127 | Jabariah//Binti Jamar/7670000002 | YASHINNI//A/P MOHAN/7670000003 | xiangjun//chan/6819000001 | MOHD//AZAN HILME BIN HAMZAH/7019000122 | MOHAMAD//AZIZAN BIN BUJANG/7670000001 | ONG//THIAM ENG/7019000123 | team7gcitechnicalteam7gcitechnical | Nuraqira//Fidianti Binti Hassim/7019000141 | MOHAMAD TARMIZI//ISWANDI/6000060946 | Liu Zaiming10047646 | MUHAMMAD HASSAN//LIAQAT ALI/6000046665 | khamirul azizul//riduan/6000046666 | ChuaKhaiSiangChuaKhaiSiang | Intan//Azura Binti Hafiz Ahmad/7019000139 | Sasulhilmy_ShaariSasulhilmy_Edotco | Mohd//Azlan Bin Ahmad/7019000138 | Mazlin//Bin Parantis/7019000132 | roziezie5927roziezie5927 | Ezwan Bin Muhamad7019000134 | MUHAMMAD AIMAN SYAKIR BIN AZMAN7019000150 | AHMAD AIDIL ADHAM/BIN/HAMILI/7019000151 | DANISH AMIRUL ASYRAF/BIN/ISMAIL/7019000152 | ABID ALI//AHMAD ALI/6000046671 | SitiJarianahSitiJarianah | HERMANWIJAYA BIN SUARDIHermanwijayaBinSuardi_CCS | Mohd Sapianmohd.sapian.bin.sujak | nubailiamaluddinnubailiamaluddin@gcidesign.com.my | SAQIB//ZIA/6798000199 | JULIAT//DAY ANAK JONIE/6798000198 | RANDY//GA/6000035545 | Karam//Illahi/7019000148 | YEHEZKIEL/AJENG/GEOFFREY/6000035543 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 | TANG//WEI SEE/7019000142 | KamarolHishamKamarolHisham | YEAP CHUN LEONG7247000004 | RajaMohdAfiq/Bin/RajaIsmail/7019000144 | SAFDAR//TALIB HUSSAIN/7019000145 | ELVIN NABIL ANAK SUYUNG7019000160 | MOHD AZMIL/BIN/MOHD ARIFFIN/7019000161 | wmaliki@girobumi.com.mywmaliki@girobumi.com.my | MohammadNazrulBinKamaMohammadNazrulBinKama | varunvarungupta | MazhaniffAbuMazhaniffAbu | DAVID//THOMAS/7019000157 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | Kennedy William/Bin/Wilfred/7019000154 | MOHAMAD DANISH ABBASY/BIN/ABU BAKAR/6000031195 | Saddi Abbas//Muhammad Inayat/7019000156 | Muhammad Fakhran/Bin/Khalid/6000005746 | Badrulsyam AliasBadrulsyam | Saw Jay HanJay_saw | MohdNazrulMohdNazrul | MAZRILHISHAM//BIN MANSOR/6000047144 | NurFarhanaNurFarhana | SYCHIN//TAN/6819000040 | jamaludin abdullahjamaludin | WILYSTENLEY WENTON SAMUIL6000015559 | Kaimeng Chan10132374 | JIMMY//LAU EWE KIAT/6237001427 | AHMAD AZRIMI//AMIR/6000037348 | RABITHO/ARTIANTHO/ARIBULAN/6000037346 | MOHD ADHAR//OTHMAN/6000005737 | MOHAMAD HAFIZUL ARESARD BIN SABIN6000071244 | JINOL MAGIKOL6000071245 | KimHaur Yong10156325 | Woo Szeshing10342639 | Yau Fei Lee10132379 | NUR//AFIQAH AQILAH BINTI ABU KASSIM/6237001440 | MEOR ZAIM AFHAM BIN OSMAN6237000585 | Mohamadwazir97Mohamadwazir97 | ArmiziArmizi | LIM//AI NI/6819000037 | chung//chingxun/6819000035 | Frazialifraziali@southpac.com.my | NAYOMI THAKSHILA6819000029 | TAI/YUN/WEN/6000027992 | Mohd/Fauzi/Bin Nasir/6000049345 | MUHAMMAD NOR FAIZZAM/BIN/MISPAN/6000036032 | SYAHIRAH AQILA/BINTI/AZIZ JAAPAR/6000036033 | SYLVESTER//MILLER/6000035186 | RAIHANA NUR AIN/BINTI/ABDUL RAZAK/6000036030 | NURFIKA//BINTI IBRAHIM/6237001402 | MOHAMAD//NASRUN BIN ARIFFIN/6000005719 | ZAFRAN AMMAR/BIN/KHAIROL/6000035189 | Arvin/Slan/Jemain/6000035188 | Muhamad/Halman/Ahmad/6000047174 | MOHD//KHUSAIRI/6000005733 | JACKSON//BIN MAKANSIM/6000027984 | Mustapana//Yahya/6000047170 | TOMMY//DAVID/6000027987 | WB80030755 | NURUL NABILAH BINTI ABDUL MUTALIP6000068098 | Arfendy//Panggiran/6000028836 | FRANKLIN/DING/SUKONG/6000027989 | CLEMSON//BIN ASAN/6000027988 | SyahrirAbdulWahidSyahrir | JackreyJackrey92 | Hartinihartini@southpac.com.my | Zhao Wei10256261 | team20gcitechnicalteam20gcitechnical | Sofiah Nazli binti Zakariasofiah_nazli | Aminuddin bin che azibA0563734967123169280 | Zhang/Tao6000064904 | NUR AZIEMAH BINTI AHMAD6000006639 | MOHD SHAHRUL NIZAM//BIN MOHD DALIL/6000052952 | Roystonroy_23Roystonroy_23 | PIRAVIN//AL JAGATHISEN/6000050774 | MOHAMMAD NORSHAHRIL//BIN ASRI/6000052954 | sabalkeruinsabalkeruin | willterjustine.datascowillterjustine.datasco | SYLVESTER JULUS6000068068 | MohamadSyafiq//Safaai/6237000995 | EMANWARE ANAK SEMAN6000074739 | MOHD IZZAT FAUZI BIN MUHAMMADE RAPITAR6237000996 | Shi Qingqi10015236 | h.nawaz18188@gmail.comh.nawaz18188@gmail.com | WEELIEM/BIN/ABDUL GHANI/6000015563 | Abrar Hussain Imdad Hussain6000079176 | BRAD SHEEN TOKIS6000015562 | GREGORY BORIGA DUIS6000003046 | Lee Kee MingKMlee7618 | Mohamad AdhamAdham | MUHAMMAD AKRAM//BIN KHAZANI/6000005225 | MOHD FAIDZAL BIN MOHD NOOR7018000086 | RAYINALE BIN LISIAS7018000087 | SIRAJ MUNIR//MOHD HASSAN/6000005220 | ANSARUDDIN//BIN SEMAIL/7018000084 | Aldrin Bin//Badaruddin/6000005221 | MUHAMMAD//AMIRUL IZZUAN BIN ZAHARI/7018000085 | AHMAD//ASHRAF BIN MOHAMAD/7018000082 | JHONES LEE JULIUS7018000080 | MUHAMMAD//TAUFIQ ZULHAIQAL BIN ALI/7021000045 | MUHAMMAD//NOMAN ALI/7021000044 | STEVENSON UDAN//FRANCIS/6000041796 | MOHD//YASIR BIN YAHYA/7018000079 | MOHD AIRELL SHAH6000044820 | NUR NABIHAH SHUHADA BINTI SEMAN OTHMAN7018000077 | MUHAMAD IZUAN SHAFIQ BIN NORAZMAN6000015039 | Muhammad//said/7021000048 | MUHAMAD//NASIHIN BIN MAHDI/7018000078 | MAZLAN//TUGIMAN/6000014181 | Muhamad//rais bin mat isa/7021000043 | ABD MATIN//BIN ABD MAJID/6000014185 | TAMILSELVAN//A/L SUPRAMANIAM/7021000042 | Arif//Afif Bin Mohd Zabidi/7021000041 | MUHAMMAD FAIRULLAZZI BIN MAROZON6000014187 | Mohd//Faizal Bin Awaludin/7021000040 | NOR ALIYA NISA BINTI ANUAR6000075563 | Wei Dan10131687 | NurHanisNurHanis | MUHAMMAD//AZIM BIN AZWAN/7018000075 | NASRUN BIN RUHENNasrun22 | LOW//CHENG TAH/7018000076 | LimJunQuanLimJunQuan | MOHD//ASRUL AZWAN BIN OTHMAN/7018000073 | MUHAMAD//RIDZUAN BIN ABDUL KARIM/7018000074 | MOHAMMAD IQBAL KHAN/BIN/AKHTAR KHAN/6000044841 | MohdNizamMohdNizam | TAY CHOON KAI7018000072 | MOHAMAD//HELMI BIN OTHMAN/6237001041 | MUHAMMAD//ALIFF BIN MOHD AZUAN/7021000056 | BONNYPACE/ERIC/ABIA/6000043501 | AZREY ANAZ//BIN AZLAN/6000042654 | MUHAMAD//SAHRIN BIN SUFIAN/7021000055 | Hafizi Sabtuhafizisabtu | Iqmalludin//Bin Rosmadi/6000042659 | YUSRAN//BIN DAN/7021000059 | MohdNorHishamMohdNorHisham | MUHAMMAD//MUZAMMAL/7021000054 | Usman MUMTAZ7021000053 | skyrigerskyriger | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | MUNIANDY//A/L AZIMULAM/7021000051 | ahmadsaudin99ahmadsaudin99 | Ravinderanathanelograv | Nazri HashimNazri_Edotco | ROZAIMIE/BIN/REBIN/6000004351 | MOHD//HANIFF BIN IBRAHIM/7021000025 | RAJESWARAN KASINATHAN6237001487 | MOHAMAD//NAJIB/7021000024 | ALFEZY//AKIN/6000044847 | Md//Zamri bin Hasim/7021000023 | AHMAD//FARIZ BIN PI RAMLI/6237001485 | Muhammad//Nor Afiq Bin Hazman/7021000022 | MOHD//SUFIAN BIN SULAIMAN/6237001486 | ABDUL//RAHMAN BIN KASWARI/7021000029 | AHMAD//AZSRAFF RIDZUWAN HASRA WARIDI/7021000028 | ERMA//KU ZALI BIN MOHAD NOR/7021000027 | ZAINAL//FITRI BIN OTHMAN/7018000099 | MOHAMMAD//FAZRIL BIIN AZRUL SEBESTIAN/7021000026 | SaifulIrwanSaifulIrwan | MOHD//SHAHIDAN BIN MOHAMAD/7021000021 | Clarence//Anak Datu/7018000090 | GERARD ANTHONY REYES YABYABIN6801000086 | MUHAMMAD//HAIKAL/6000005218 | lim meiyen00339561 | NG CHANG TYNGng.changtyng@yptt.com.my | DanielTanLeongYuanDanielTanLeongYuan | JUZAIMI//BIN MOHD ZAINUDIN/7018000097 | SAZRIN//RIZMAN BIN JEFERY/7018000098 | LORANES//BIN RUBIN/7018000096 | Ricky//Thomas/7018000093 | Elvist//Tayson Siling/7018000094 | ZHANG DONG6000003031 | Malvin//Menggong anak Robert/7018000092 | SyahnizamSyahnizam | NOOR//SHAHREN BIN ABDUL SAMAD/7021000036 | Mohd//romzi bin nasir/7021000035 | Deven/Bin/Sinteh/6000043524 | MOHD//FAIZAL BIN MUKHTAR/7021000034 | Vun Koh An @ Felix6000043523 | MOHD//FADZRI BIN SUFIAN/7021000033 | Muhammad//Fariz Bin Fadzil/7021000039 | AZMEER//AZHAR/7021000038 | ELEX//ANAK LANOI/7018000088 | Ahmad//Ridzuan Bin Mohd Tajudin/7021000037 | Nelson//Lah Laing lah/7018000089 | Nickhole/Bin/Toion/6000043526 | HASHIM//BIN AHMAD ZAIDI/7021000032 | Raymond//Anak Bajan/7021000031 | ZaidiYusranZaidiYusran | Atiqah bt Abdul MuradAtiqah91 | JAKLY CLAMEN//JONLEY/6000055922 | MUHAMMAD ROHAZIMI BIN RAHIMI7018000039 | MUHAMAD ASYRAF BIN ISMAIL6237001463 | CHONG QIEW LEK7018000038 | WONG JING MUN6237001469 | steveSteveBinOngkas | NG HONG JIE7018000036 | MOHAMMAD//HAZIQ BIN MOHAMMAD SAUGI/7018000033 | MUHAMMAD//AWAIS/7021000082 | SAFDAR//HUSSAIN TALIB/7021000081 | MUHAMMAD//FAIZ BIN ROSMAN/7021000080 | JONI ANAK ASIN6000075526 | MHD FAKHRON NASIRIE BIN MUSTAFFA6000075524 | Hermanwijaya bin suardi7021000085 | MUHAMMAD FIKRI HUSAIMI BIN MEHAT6800000011 | DICKSON JUTTY ANAK WATT7018000031 | thagarajah//kuppusamy/7018000032 | LOO ZHI YEE6237001482 | LEE SUAT FEN7018000028 | Lei Yu10166721 | Shao Lijuan00303173 | AEZZIE ALFEERA DAYANA/BINTI/MOHD AZUAN/6000042611 | LeeKokKeenLeeKokKeen | Muhammad Adnan//Muhammad Ramzan/7021000099 | LOH//CHEAN HONG/7018000027 | SHEIKH ABDUL HADY BIN SHEIKH AB HAMID7018000024 | OMAR HAMZAH BIN IKMAL HISHAM6800000007 | YAP//SIEW THENG/6237001478 | SAMANTHA LOOI SHU-YI6237001479 | MOHD//FIRDAUS BIN IDRIS/7021000098 | Ren Yitao10177253 | HABIBULAKBAR/BIN/ALHAIDIL/7021000097 | haiderali121412haiderali_121412 | Anto Dalan @ Titusantodalan@gmail.com | Nur Hazwani Binti KastianNURHAZWANIKASTIAN | BalamuruganBalamurugan | HAIL MAN//BIN MUSTAFA/6000009600 | VALENTINE/ANAK/DUNCAN/6000059070 | MOHAMAD//SAMSI BIN MOHAMAD SATER/7018000060 | ABDUL//RAZAK BIN MOHAMAD RADI/6237001451 | Lai QingHui10094188 | Malai Pmozhushou80045983 | NURUL//ERNA SHAFIQAH BINTI KHAIRI ANUAR/7021000069 | IGNATIUS/JUSIN/ANAK LADING/6000059075 | GONDAL TAHIR KHALID7021000068 | AZMAN//BIN MOHD SALLEH/7021000067 | Yang Meng00343609 | Tan/Jian6000064898 | KHAIRUL//AMIR BIN AHMAD KHALIL/7018000058 | IMRAN//JAVED/7021000061 | TAIB//MUHAMMAD/7021000060 | MD. SARUAR MIA6000015052 | ABDUL//HALIM MUKREEM BIN ABDUL LATIF/7021000062 | ZAIM ZHARFAN BIN HOSSEN6000076873 | NURSUHAIMIE//BIN RIAMAT/6000029209 | MOHD ASYRAF/BIN/KARIM/6000037290 | BORNLUCK CHONG TIANLER7018000051 | Chan Yuan10156904 | HARIS MUSHTAQ7018000050 | MUHAMAD AIMAN AIDINI//BIN HALIM/6000041794 | MAZLAN BIN ABDUL RAHMAN6237001454 | Umar//Daraz/7021000078 | Saleem//Muhammed/7021000077 | MohdNoorKeefleeMohdNoorKeeflee | MA HIN MUN7018000045 | NIK//MOHD AZWAN BIN NIK LI/7021000070 | MOHD//AMIRUL HISYAM BIN ALIAS/7021000075 | Arihand Mazupatri//HamadEta/7684000005 | LEE JAU SHING6800000061 | MOHD TARMIZI//MOHD YUSUF/7684000006 | AMIRUL/AKMAL/NOR ISHAM/7684000007 | KAMARUL/HAFIZ/ABDUL AZIZ/7684000008 | TOH//SUK WEI/6800000062 | MOHD HASHRUL/MUBIN/ZULKIFLI/7684000009 | GeorgeKutGeorgeKut | SONY//ANDRIANA BIN HJ FUAD/6801000035 | NUR NABILAH/HUSNA BINTI/MOHD ZAIN/6000011503 | ShahrulAzmanShahrulAzman | SyarianshahSyarianshah | MOHD NIZAM//JAMAUDDIN/6000045755 | NUR AQILAH//BINTI ZAINAL/6799000309 | WONG//MEE YAN/6799000308 | Hu Bin10014886 | eejatskyline.cubecomeejatskyline.cubecom | ERVIN CHRISTOPHER//AL ALFANSO/6799000302 | HAMZAH BIN ABDUL MUTALIF6799000301 | AMMAR ALTAF//SHEIKH ALTAF/6799000300 | TAN KEAT HAN6801000026 | Mohd Akhir SulaimanAkhir_Edotco | MohdRadhiMohdRadhi | HANAFI//BIN HARUN/7684000001 | Mohd/Hafizzan/Hanapi/7684000002 | MOHD SHAHRIL BIN HISSAMmshahril76 | Nur Atira/Syafiqah/Mohd Ali/7684000003 | NURUL//NADIA BINTI ABDULLAH/6800000045 | Mohd Shahrun/Erni/Sharif/7684000004 | Hadi Mazrol bin Siduphadimazrol@gmail.com | MASDIANA//BINTI BEDIN/6801000016 | Li Xu10207558 | MOHAMAD SYAFIQ BIN SAFA AI7018000017 | NGEI//CHEE KIT/7018000015 | USMAN MUMTAZ MUMTAZ HUSSAIN6799000327 | Noryusliza//Binti Rosely/7019000106 | MAZWAN BIN MAZLAN7019000107 | CHIN KOOI THIAN7018000014 | MOHD//SUHAIMI BIN GHAZALI/7019000108 | Nasrun Bin Ruhen7019000109 | MOHD//EDI JASRI BIN ABDUL NASIR/7019000102 | AHMAD//FAIZAL BIN MOHD SHAH/7019000103 | USHANANTHANI A/P RAJENDRAN6799000320 | RIDHWAN//HAFIZ BIN MAT SONG/7019000104 | SIEW//WEN JING/7019000105 | LEE WEI HANG6800000037 | SUE JING REN6800000032 | Shahid//Nadeem/7019000100 | HILMAN ROHIMAT AHMAD6800000034 | MAHADIR//BIN MOHD ZAIN/7019000101 | MUHAMMAD FAIZ//BIN MOHD ROSDI/6799000317 | GEORGE CHAN//TECK PENG/6799000316 | MOHD//ZUL FEQAR BIN MUDRY/7019000117 | ELDERO//PAN HWA KHIONG/6800000028 | ARIF//FADLIN BOK BIN MOHD FAZIL BOK/7019000119 | MUHAMMAD USMAN//ZAFAR IQBAL/6799000319 | ATIQAH//BINTI ABDUL MURAD/7019000113 | AG KU NURULIKHSAN//BIN PG ANAPI/6799000310 | Aminah//Binti Abdullah/7019000114 | ZURAINI//AIDA BINTI MOHAMAD KAMAR/7019000115 | Mustaffa Muammar Bin Mustaffa MaarofMus89 | MOHAMAD//ADIB BIN KASIRON/7019000116 | LAURENCE IOSSNUARIE//ANAK JUNA/6000035511 | MOHAMAD AMIRUL ASRAF BIN ABD MANAH6799000314 | MOHD//SYAHRUL BIN JAAFAR/7019000110 | AIMAN HAKIM//BIN AZHARI/6799000313 | NUR//HAFIZAH BINTI ABD RAHINE/7019000111 | ANWAR//BIN ABDUL RASID/6799000312 | Muhammad//Zulfahmi Bin Jasni/7019000112 | MOHD//BADRIZ BIN NANANG/6799000311 | WAN//AMINAH SYAIRAH BINTI MHD NOR/6801000077 | MUHAMMAD//AFIQ BIN SIDEK/6801000076 | GordonBryanRobertGordonBryanRobert | NUR//AMYRUL ASRAFF BIN SAZALI/6801000075 | MUHAMMAD//FAUZAN BIN FISAL/6801000078 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | Durairajan/AL/Chinakarpan/6000006194 | Lin Pei00033372 | Nadeem//hassan/6000006190 | Mohammad Helmi//Bin Mohd Nor/6000006192 | MUHAMMAD SYAFIQ BIN AHMAD SUHAIMI7021000007 | Wang/Longfei7021000006 | CHEONG//MUN HONG/7021000005 | CHEN TAK//EOH YANG/7021000004 | AGONG ANAK SAM SUN6000077308 | OCHRAN//MARTUA YULIANTO/6801000084 | ALASSERIM//JASMIN BIN ABDUL JALIL TAK/6800000098 | NUR//SYAHIRAH AFIQAH BINTI FARIDUL QAHAR/6800000094 | MUHAMMAD//HAZIM BIN AZLISHAM/6801000064 | KOK XIAO QING6800000096 | Lim Hoi Yenhoiyen | MUHAMMAD//ANIS FARHAN BIN ANUAR/6801000063 | CHOO VOON WAI6800000095 | MOHD FAIZ BIN ABU BAKAR6800000092 | NOR ASSHIKIN/BINTI/MOHAMAD RADZI/6000062298 | Mohd//Rizal/7021000012 | MOHD//AZIZI BIN ZAKARIA/7021000011 | Mohammad Hasrul Bin Mohd Fadhil7021000018 | RIFDI//DANIAL ZULQARNAIN BIN ROSLI/7021000017 | BahaZurkaflyBahaZurkafly | MOHAMAD AZIZUL BIN ZAKARIA7021000015 | MUHAMMAD//AZIM BIN AZWAN/6000018176 | Ren Catika RengitRen93 | TAN//CHAU SIEAN/6801000073 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 | Suraj Kumar MishraS8574 | TAN HUI SHAN6801000072 | MOHAMAD//SHUKRI BIN PILUS/6800000086 | GARY ROBSON ROBERTgary.robson | RONALD SHAN A/L AMBUROSE6800000089 | SabrieMahriSabrieMahri | DOUGLAS//DUNGGAU ANAK WATT/6801000055 | MOHD//FADZIL BIN ABD RASHID/6800000085 | SHIV KUMAR6800000084 | MAS//AZNOR BIN AHMAT/6801000059 | Siti NorzaihanZaihan | MUHAMMAD//HAIKAL BIN SHAMSUDDIN/6801000058 | NUR//AYRIMIRA BINTI AHMAD ARIFIN/6800000081 | Siti Hamidah sitihamidahericsson | MUHAMMAD NAJIB BIN RAMLI6000011524 | Yan Li00130407 | M//Paramanathan A/L Mariappan/6237001055 | MUHAMMAD DANIAL//CHE MAT/6000024836 | NUR//SYAHIRAH BINTI ABU MAZLAN/6801000062 | MUHAMMAD//HANIF BIN MOHD FADZALI/6801000061 | NIZAR//KUSYRINA BINTI NGADI/6800000075 | AZHAN//AFIFI BIN S AFFENDI/6801000060 | MOHD//SHAHREEZAN BIN RAZALI/6801000044 | TAN TECK JINN6800000072 | HARRIS//FAUZIAN MOHD DAHLAN/7460000002 | AHMAD//SHAFIQ BIN ASPAR/6801000041 | AffendiAbuBakarAffendiAbuBakar | Mohammad Hamierul Asraf/bin/Arfian/6000031106 | RANA//WAQAS/6000006187 | Konli//Bernabas/6000043571 | Fadzilah Bin Hamdan//Haris/6237001065 | Mohd Ahzam ModinOnsite_ahzam | MELVIN KWAN YII SYN6000051182 | MUHAMAD//ASRUL BIN SHAHZALAN/6801000051 | YUE//JUN HONG/7020000004 | Mohd//Azlan Bin Yusuff/7020000003 | NOOR//SYAKIRAH BINTI RUSLAN HADI/6800000066 | AzmanIbrahimAzmanIbrahim | Png//Chee Hau/7019000050 | CHRISTOPER//YUSUF PANGIRAN/7019000051 | Rojer Anak Rexsa7019000052 | ELHAM BIN ARSHADA0633988845995327488 | MUHAMMAD FAKHRUL DAWANI BIN ABDUL NIKAH6000051920 | MUHAMMAD AIMAN HAIQAL//BIN MUHAMMAD ZAMRI/6000051924 | ///6871000037 | Jacqueline//Kong Yie Hue/6871000040 | Azreena///7019000048 | Muhammad//Syarul Nizwa bin Mohd Nor/7019000049 | Jiclyn//Binti Furut @ Furet/7019000062 | Farddy//Ongkirik/7019000063 | Muhammad//Aizat Bin Sanudin/7019000064 | MOHD//SHAHLAN AFZAN BIN ABDUL RASHID/6000061715 | Zhou Jing00097725 | Dong Xiaoyue00337714 | Sariff Roslin Sh AmeerilSariffRoslin | ALLEXSTER//SINTI/7019000059 | Wong Ching Chai7019000072 | Steward//Labo/7019000073 | Fong//Shyh Yung/7019000074 | MOHAMAD//ZULFAKAAR BIN SHAMSUDIN/7019000075 | Yeo//Kai Kee/7019000070 | MC//GIRAZOR BIN ANAS/7019000071 | Muhammad Faiq Bin Aidan6000022582 | MOHD AMEEN BIN DIMITY6000023428 | Anto//Dalan @ Titus/7019000069 | Wang/Jinwu6214001761 | NURULHUDA//BINTI SHAHARUL NIZAM/7019000067 | Jong Kianwee10342572 | FRANKIE ERWAN BIAH7019000068 | Usman//Khan/7019000083 | Sthepenius//Kahung/7019000084 | Huang Kaiyun10341263 | MAXMILLER//PACHELLES/7019000080 | Nelson//Bin Banson/7019000081 | Mohd//Danial Haikal Bin Ahmad/7019000082 | ABDUL RAHMAN BIN ALI SADARI6000023416 | Yong Hong Chyecd_hcyong | LEE YEN NING6000037657 | AkramBinAhmadAkramBinAhmad | Sazrin//Bin Ishak/7019000076 | SANDRE//SHYRON SAMI/7019000077 | JEFREY//BIN SABDANI/7019000078 | Biriyan//Bin Dayaman/7019000079 | RIZZUAN//BIN YUNHENDRI/7238000001 | Ng Xin Zhangngxinzhang | Muhammad//Norfikri Bin Ramlee/7238000003 | RIO//RINALDI BIN YUNDARI/7238000002 | Nur Shahera//Md Ali/7238000005 | Ahmad//Kamal Ikhwan Bin Mohd Ariffin/7238000004 | SANJAY DASedaasns | NORSHAMSUDIN//BIN DAUD/7019000007 | YEK/PIK/NGUK/6871000002 | AbdillahHasbieAbdillahHasbie | Rexcky Anak Gerunsin7019000009 | NUR/WAFA/MIJONG/6871000001 | Jong ah lim6000013215 | Png//Teng Hock/7019000004 | SARAH BINTI DOLAH7019000005 | Chan Dao Liang7019000006 | GALVIN//FRANCIS/6000033224 | kandasamyeanrakv | Hng Chee Yung10343000 | AMIRUL AFIF BIN MANSOR6000002563 | MUHAMMAD NOMAN ALI DILSHAD KHAN6000002564 | MARTIN ALBERT/BIN/SAMBALAI/6000002561 | Ahmad Ikhsan bin Zainuddin7019000020 | JASTIN//BALAYAS/6000002565 | Mohamad//Budi Bin Lukman/6801000100 | WEIGUO//DAN/6871000007 | TYNG ERN//SLEW/6871000006 | LI/CHENG6871000005 | MUHAMMAD NABIL ADAM BIN NORIKHWAN ZAINI6000067466 | MOHD BADRUL HISSHAM//MOHD ZANIN/6000002560 | Mohd//Hafiz Bin Mat Rani/7019000018 | Aaron//anak Meta/7019000019 | MOHD FIRDAUS BIN JAMALUDDIN6000006918 | NORFAHMI//BIN MOKHTAR/7019000015 | Albert Atau//Chau Soong Guan/7019000016 | JUNAIDI/BIN/SIMAN/6000002558 | Sarah DolahSarahDolah2 | NUR FARAH DIANA//ABDUL RAHIM/6000002559 | Mohamad//Asraf Mohd Nor/7019000011 | CHAN YI WEN7019000012 | HERRY//BELLYJOE RUAB/7019000030 | WB80030579 | LASTER NATANEL7019000031 | KENNETH//JONG/6000026987 | RajvinpalSinghRajvinpalSingh | RELDOF MARINUS6000067012 | STEPHANIE APRIL6000014517 | MOHAMAD NAZRIL FATHI BIN MAZLAN6000067014 | Mohamad Adib bin KasironAdib22 | MUHAMMAD//DANIEL PUTRA BIN MAZLAN/7019000029 | MUHAMMAD AMIN SYAZANI BIN AZHAR6000011498 | yap//hweebwen/6871000023 | MOHAMAD//FADZIL AIDIL BIN ROSDI/7019000025 | Ankesh Kumar KushwahaEKNAUKM | FAIZ//AZIB BIN ABDUL KHALIL/7019000026 | TeeYoungHwangTeeYoungHwang | RIDZUAN//BIN YUSOFF/7019000027 | TAN//SWEE LOON/7019000028 | Rimi Anak Asson7019000021 | EDE//RICKYJOE BIN RAHMAT/7019000022 | ASROY//BIN ANTIN/6000059872 | YUTAM///7019000023 | MohamadHanafiMohamadHanafi | MohamadSazalyMohamadSazaly | NABIL//AIMAN BIN NADZEMI/7019000024 | Mohammad Amirul ShafiqAmerul95 | MOHAMMAD//FAIZ BIN ABDUL RAHIM/7019000040 | HengFookLiangHengFookLiang | VANN//DONALD DAMUS/7019000041 | MATTHEW//ANAK ARON/6000043057 | TANG WEI SEEWincy22 | Wu/Fangliang6871000034 | Artin//Arzezee Bin Bagus/7019000036 | Chiew Hua Kai7019000037 | Piong Choon Tein00126789 | Andy//Wilson anak Oscer/7019000038 | AHMAD//BIN RAMLEE/6000059866 | Mohammad//Azamril Nasil Bin Ahmad Jamaludin/7019000039 | DEFVID//HENRRI MAIR/7019000032 | EDDY//ADHA BIN CHE NASIR/7019000033 | TeckChingKiingTeckChingKiing | ROMARIO//DAYMOL/7019000034 | Jee//Yi Heng/7019000035 | WB80041708 | TAUHEED//MUHAMAD RIZAL/6000051524 | AMBROSE/SEMAU/HENRY/6000028745 | JAINAL//ABIDIN BIN AKMAD/6000061325 | MUHAMMAD TARIQ//MUHAMMAD HANIF/6000063501 | safetygirobumi@yahoo.comsafetygirobumi@yahoo.com | MOHD FITRI BIN HASANmohdfitri | Chin Sau Jiet6000063978 | NG XIN NI6237001561 | Wang Yan00097321 | ROYSTON//AHHOLE/6000038561 | maykean//choong/6237001552 | alex//ong/6237001558 | MUHAMAD FAQRUL ISSRAQ BIN MOHD SHARIRfaqrul.1205 | Li Xigang10132021 | ANUAR BIN BASRI6000002574 | AJIZAM BIN MOHD NASIB6000002575 | TOMMY/BIN/GUBIN/6000002573 | RAMLAN//BIN ROSLAN/6000002578 | SEAN EMMANUEL//MARJON/6000002579 | WilsonPanelWilsonPanel | VOON HAO LE6000063527 | DHIRREN DAS/AL/SIVADASS/6000048379 | KohWoonChiehKohWoonChieh | Leeling.ftii@gmail.comLeeling.ftii@gmail.com | NorhalizaBteKiprawiNorhalizaBteKiprawi | Christopher/Calvin/Anak Kimet/6000059039 | MohdNazimMohdNazim | Basri Bin Si Bakar6000006926 | MOHAMMAD FIRDAUS/BIN/CHE KOB/6000002585 | Muhammad ZulfahmiFahmi22 | ZANETTI/BAKOM/ANAK RICKY/6000051532 | Kristina//Abul Hamid/6000051533 | MUHAMMAD NAUFAL AZHAD/BIN/ANUWAR/6000002584 | Sedeni//Othman/6000051534 | Nur/Azny/Azman/6000051535 | TENGIYAN//GALONG/6000051536 | MOHD SHAHRAIN/BIN/MOHD SHKERY/6000002587 | SundararajuSundararaju | KHAIRILAZHAR/BIN/ZAKARIA/6000002588 | MUHAMMAD//AZRUL BIN AMIR/6000049238 | MUHAMMAD AFIF HAIKAL/BIN/MOHAMAD NAZIR/6000002582 | SUZI//BINTI HUSSIN/6237000683 | RayAmosMojolouRayAmosMojolou | WB81119222 | MOHAMED AIMAN BIN ISMAIL6000071139 | NORDIN//BIN AHMAD/7019000094 | ROYLIEO//KONTIAM/7019000095 | ALIUDIN//BIN BAGOL/7019000096 | Muhammad//Asghar/7019000097 | RodiaAkmaRodiaAkma | Yonatan//Bin Balang/7019000090 | Mohd.//Khairulanam/7019000091 | NUR//ADRIANA DARWISYAH Binti Isarlizam/7019000092 | Fred//Johanes Benedict/7019000093 | Mohamad Fairuz Bin Muhamad Manawaryfairuzm | ROMARIO//NYIPA/6000035488 | ZAPRI//BIN MOHAMMAD/7019000088 | CHRISTOPHER//BIN BARU/6000035003 | JIKLON//BIN HASAN/7019000089 | md shabreeshabrees | ClarenceAngWaiLoonClarenceAngWaiLoon | Ali Akaram Bin Gulam Nabihasina | MUHAMMAD AKMAL BIN ISMAIL6000008700 | Mazwan MAzlanMazwan22 | ABDUL//QAYYUM BIN BUSMAN/6000026591 | WAN MUHAMAD ISMAIL BIN WAN DERAMAN6237001513 | ESTER ONG XIANG LIN6000071558 | Suriyahsuriyah@allstarengineering.net | WanSulaimanWanSulaiman | Muhammad//Kamran/7019000099 | AB.RAHMAN//BIN MAT NOOH/6237001519 | Chen Yuanyu10051419 | LEONARD//EDUAN/6000038538 | AbuKassimAbuKassim | Peng Zhiyang10120477 | WB80031348 | AhmadAizatAhmadAizat | ShafiemoShafiemo | VONG//SHAN CHA/6237000641 | MUHAMMAD ZARIS AIMAN BIN MOHD ZABIDY6000075933 | AMIRUL HAZREEN BIN MOHD HAZMAMA0789423369654345728
TX - L1 | NIC SSO Approval - 1st level - Northern | Testing - design | Skylift - NIC Congest Upg - IM Approval -Northern | temporary1 | NIC SSO Approval - 2nd level - Northern | OSS Central - Mohd Akhir Bin Sulaiman | Digi ATP Approval - CR With Equipment | Skylift - 2023 TX Rollout - IM Approval - Central | Skylift - 2023 CD BAU - RPM - Central | FAC Explaination_DCM Approval | Skylift - 2023 CD BAU - IM Approval - Central | Skylift - CD consolidation - IM Approval -Northern | Digi FF Northern | TSSR Hand Over to ZTE - Approver | OSS Central - Kamil Sharulhizam Bin Ahmad Kifli | OSS Central - Sasuhilmy Bin Shaari | Trintel TI | Audit Team | NIC SSO Approval - 1st level - Central | HR - Northern | TL - Logistic | Skylift - 2023 CD BAU - PR - Southern | HR - Platform | OSS Central - Hasmadi Bin Abdul Rahim | Digi FF Doc | SSV SSO Regional Approval - Sarawak | OSS Northern - Mohd Akhir Bin Sulaiman | OSS Northern - Mohamad Said Bin Mat Hassan | NWAVE TI | Datasco RF | Develop Report | Skylift - 2023 CD BAU - IM Approval -Southern | Datasco TI | RF Customer | NIC SSO Approval - 1st level - Sarawak | NIC SSO Approval - 2nd level - Sabah | Special Request | HQ Spot Check | NIC SSO Approval - 2nd level - Central | Site BOM import function | Allstar TI | RAN integration -Big Outsource | RPM Sarawak | Sign in sign out - HQ | Sign in sign out - Shi Qing Qi/ Hu Li Hua | Sign in sign out - Sabah - WengHaoZhou | Design and Material Manager | Sign in sign out - Wang Feng | Rollout Manager | Sign in sign out - Northern - Chiew | Quality Manager | Satellite TI | Perwira TI | Subcontractor PM Complaince Training Group | TX TSSR Customer Approval | Customer Quality Team | yangmeng | REDTONE TI | SSO Headquarter Approval | NR Service RF | MTK TI | DNB Project sign in sign out | OSS Northern - Hamzah bin Ahmad Johar | TSSR Decomm Workflow - TX | HR - Sarawak | OSS Sabah - Mohd Reduan Jaimin | Customer Project Team | TL - Core Network | TL - Technical Network Quality | TL - Outsourcing | TL - HQ and Others | Outsource Team | Solusi TI | PMM Team | PERNEC TI | Customer | B-BAND TI | ETSS Review Team_Design | Warehouse Team | PMO HR | Digi FF Eastern | Skylift - NIC Congest Upg - IM Approval - Central | Customer SA Team | Trintel RF | CCS TI | NIC FAC Cluster | ETSS Review Team_MW | OSS Sarawak - Gary Robson Robert | Workload - Tx Rollout | temporary | SSV Approval email notify | SSO Approval email notify | Sign in sign out - Sarawak - WengHaoZhou | Operation and Maintenance | SouthPac TI | Magicell RF | UCE RF | Ennova TI | OSS Sabah - Azami | NIC SSO Approval email notify | Sign in sign out - Central (Zhang Chuntao） | Sign in sign out - Northern -WangFeng | EPMS Team | Contract Management Team | Engineering Solution | DU Field | Rental Team Sarawak - Tiger Team | TL - Planning | Iezzpro TI | Digi FF Central | TSSR Decomm Workflow - RAN | TSSR Customer Review | Resource Management - BB | Resource Management - LYFLQH | Check Sign in sign out record | Transmission Team | RAN Integration Team | Core Network Team | Digi FF Eastern - CR With Equipment | RAN Team | Skylift - 2023 CD BAU - IM Approval - Sarawak | Digi FF Southern - CR With Equipment | Skylift - TX Mini Project - IM Approval - Sarawak | Digi FF Sarawak - CR With Equipment | Skylift - CD consolidation - RPM - Sarawak | Skylift - 2023 CD BAU - RPM - Sarawak | Skylift - 2023 TX Rollout - RPM - Sarawak | Skylift - 2023 CD BAU - RPM - Northern | Skylift - 2023 TX Rollout - RPM - Northern | Skylift - CD consolidation - IM Approval - Sabah | Logistic Team | Skylift - NIC Congest Upg - IM Approval - Sabah | RF Team | SA Team | Skylift - CD consolidation - RPM - Sabah | Skylift - TX Mini Project - RPM - Sabah | Tx Project | Rollout Team | Customer RF | OSS Sabah - Mohd Ahzam Bin Modin | OSS Sabah - Gary Robson Robert | OSS Central - Hamzah Bin Ahmad Johar | O and M Team -Big Outsource | Digi FF Sabah - CR With Equipment | TX -Big Outsource | OSS Central - Nazri Bin Hashim | Technical Manager | Digi FF Northern - CR With Equipment | Digi FF Central - CR With Equipment | TL - Repair Center | TL - Integration Room | TL - Design and Material | HR - Sabah | HR - Central | Skylift - TX - IM or RPM- Eastern | executive project manager group | Project Management Manager Group | Project Permission Administrator Group | Skylift - TX - PR Approval - Eastern | RPM Sabah | Project Document Management Manager Group | GTSB TI | Seri Pancar TI | Rental Team Central - Tiger Team | Customer TX Team | GCI TI | Skylift - PR Approval - Northern | YPTT TI | Allstar RF | Design and Material Team | Skylift - PR Approval - Sabah | test | Quality Team | GTSB RF | ETSS Review Team_RF | RPM Northern | RPM Central | Magicell TI | Document for OSS | Morrison | OSS Sarawak - Amir Hamzah | Skylift - TX Mini Project - RPM - Central | Skylift - PD Approval - Boss Lai | Skylift - NIC Congest Upg - RPM- Northern | Technical Director | Skylift - CD consolidation - IM Approval - Central | RF Planning Team | Supply Chain Manager | Outsource Manager | Subcontractor Compliance Training Inquiry | Doc Team | Skylift - TX Mini Project - IM Approval - Central | Skylift - CD consolidation - RPM - Central | OSS Sarawak - Zulkarnain Iswandy | OSS Sarawak - Mohd Syahnizam Garip | Futong TI | Sign in sign out - Chan Kai Meng | Skylift - 2023 CD BAU - RPM - Southern | Digi FF Sabah | SSV SSO Regional Approval - Sabah | Rental Team Sabah - Tiger Team | Rental Team Northern - Tiger Team | RF Planning Manager | OSS Sabah - Roslan Bin Kiling | Finance Team | TSSR - Site Folder | Acceptance Certificate | Starlink Speedtest Report Approved | Digi FF Southern | Digi FF Sarawak | Ascentrack TI | AsBuildDrawing - Design and TX reviewer | OSS Central - Mohd Nazim Bin Nawi | Subcontractor for settlement | Issue and Risk | Skylift - 2023 TX Rollout - IM Approval - Sarawak | Sign in sign out - Lim Wei Siong | Skylift - NIC Congest Upg - RPM- Sarawak | Skylift - 2023 TX Rollout - IM Approval - Sabah | HXCY | Skylift - NIC Congest Upg - IM Approval - Sarawak | Sign in sign out - Chooi Jia Jye | Skylift - CD consolidation - RPM - Northern | Skylift - 2023 CD BAU - IM Approval - Sabah | Implementation Plan Import Functions | Skylift - 2023 CD BAU - IM Approval -Northern | Skylift - 2023 TX Rollout - IM Approval -Northern | Skylift - 2023 TX Rollout - RPM - Central | Sign in sign out - Boss Lai | Sign in sign out - Central - Chiew | FAC Explaination_PD Approval | TSSR RF Second level Approval | Sign in sign out - Repair Center | Doc | TL - PMO | TL - O and M | TL - Commercial and Documentation | AsBuildDrawing - TX reviewer | TL - Technical RF | TL - Technical RAN | Skylift - NIC Congest Upg - RPM - Central | TL - SA | TL - Quality and Safety | OSS Southern - Hamzah bin Ahmad Johar | Skylift - PR Approval - Sarawak | TL - TX Project | Skylift - PR Approval - Central | GCI RF | DO Review Group | FAC Explaination_Resource | NR Service TI | NIC SSO Approval - 2nd level - Sarawak | YPTT RF | Nera TI | Project Cost Management Group | CCS RF | Futong RF | Customer RF Doc | NIC SSO Approval - 1st level - Sabah | OM and SPMS Team | Admin Team | Network Quality Team | OSS Northern - Zulkarnain Bin Mustapha | Skylift - 2023 CD BAU - RPM - Sabah | Resource Management - NFS | Skylift - 2023 TX Rollout - RPM - Sabah | Skylift - TX Mini Project - IM Approval - Sabah | Skylift - NIC Congest Upg - RPM- Sabah | East Field TI | Skylift - CD consolidation - IM Approval - Sarawak | Itech ZTE | Skylift - TX Mini Project - RPM - Sarawak | Resource Management - HR | Respontrade RF | OSS Northern - Nazri Bin Hashim | OSS Northern - Zafri Bin Zainal | Skylift - TX Mini Project - IM Approval -Northern | Skylift - TX Mini Project - RPM - Northern
New Starlink | MW Swap | MW New Link / Reroute | Under NIC | MW Dismantle | Existing TX | MW IDU Patching | MW Parallel Link | MW IDU Relocation | MW Re-engineering | IPRAN Port Upgrade | MW Remote Upgrade | MW Hardware Upgrade | BBU Patching | Cancel / Drop | IDU-IPRAN
PAC | L1+ATP+MRCF+PAC | L1+ATP+PAC | NA | MRCF+PAC
MAY 25 | DEC 24 | DEC 25 | APR 24 | OCT 24 | JAN 25 | MAY 24 | NOV 24 | AUG 24 | JUN 25 | AUG 25 | FEB 25 | APR 25 | OCT 25 | MAR 24 | JUL 25 | JUL 24 | JUN 24 | NOV 25 | MAR 25 | SEP 25 | JAN 24 | FEB 24 | SEP 24
GCI | GTSB | GCI_AA | GTSB_AA
DEC 24 | OCT 24 | JUN 24 | AUG 24 | AUG 25 | MAY 25 | SEP 25 | APR 25 | NOV 24 | JAN 24 | JUL 25 | NOV 25 | DEC 25 | JUL 24 | JAN 25 | SEP 24 | MAR 25 | FEB 24 | APR 24 | JUN 25 | MAR 24 | OCT 25 | MAY 24 | FEB 25
Digi | ZTE | Celcom
03. TSS Only | 07. Solution Changed | 08. Pending RFS | 04. BOM / Material Issue | 04. Pending CR Approval | 04. Pending DO | 05. Doable | 05. TI Together with RAN | 05. TI WIP | 06. HSSE Issue | 06. Resource Issue | 00. Integrated/RFS Done | 00. Site Out/Drop | 01. Pending Planning | 02. Pending Access | 02. Pending EB CRQ | 02. Pending PTW Approval | 02. Pending TP Approval by Site Owner | 03. Pending TSS | 03. Pending TSSR Approval | 02. Pending TP Submission by Site Owner | 06. Other Issue | 03. Pending TSSR Submission | 06. Pending mCME(CD)
TSS+AA+TI+Dismantle | AA | TSS+AA | NA | TSS+AA+TI | TSS+TI | TSS | TSS+TI+Dismantle