## data
site¦fix00012¦4188808420049567786¦2477626672974883536 | site¦fix00015 | du¦du_code | site¦region_name | site¦fix00008 | site¦fix00013 | site¦fix00010 | docata¦ZDCSZ640306 | docata¦ZDCSZ00843884 | docata¦ZDCSZ640230 | docata¦ZDCSZ00843885 | docata¦ZDCSZ0673674 | docata¦ZDCSZ00836966 | docata¦ZDCSZ640228 | docata¦ZDCSZ00885806 | docata¦ZDCSZ640229 | docata¦ZDCSZ0656912 | docata¦ZDCSZ0669212 | docata¦ZDCSZ00815531 | docata¦ZDCSZ00815532 | docata¦ZDCSZ642123 | docata¦ZDCSZ00969593 | docata¦ZDCSZ00969594 | docata¦ZDCSZ00969581 | docata¦ZDCSZ00969580 | docata¦ZDCSZ00969576 | docata¦ZDCSZ00969578 | docata¦ZDCSZ00969579 | docata¦ZDCSZ0657770 | docata¦ZDCSZ641766 | docata¦ZDCSZ0657771 | docata¦ZDCSZ641765 | WP10400¦plan_end_date | WP10400¦actual_end_date | WP10400¦status | WP10400¦AC0000111560¦plan_start_date | WP10400¦AC0000111560¦plan_end_date | WP10400¦AC0000111560¦actual_start_date | WP10400¦AC0000111560¦actual_end_date | WP10400¦AC0000111560¦responsible_user | WP10400¦AC0000111560¦responsible_team | WP10400¦AC0000111560¦supplier_no | WP10400¦AC0000111560¦comp_percent | WP10400¦AC0000111560¦assign_flag | WP10400¦AC0000111560¦status | WP10400¦AC0000111560¦remark | WP10400¦AC0000111561¦plan_start_date | WP10400¦AC0000111561¦plan_end_date | WP10400¦AC0000111561¦actual_start_date | WP10400¦AC0000111561¦actual_end_date | WP10400¦AC0000111561¦responsible_user | WP10400¦AC0000111561¦responsible_team | WP10400¦AC0000111561¦supplier_no | WP10400¦AC0000111561¦comp_percent | WP10400¦AC0000111561¦assign_flag | WP10400¦AC0000111561¦status | WP10400¦AC0000111561¦remark | WP10400¦AC0000111563¦plan_start_date | WP10400¦AC0000111563¦plan_end_date | WP10400¦AC0000111563¦actual_start_date | WP10400¦AC0000111563¦actual_end_date | WP10400¦AC0000111563¦responsible_user | WP10400¦AC0000111563¦responsible_team | WP10400¦AC0000111563¦supplier_no | WP10400¦AC0000111563¦comp_percent | WP10400¦AC0000111563¦assign_flag | WP10400¦AC0000111563¦status | WP10400¦AC0000111563¦remark | WP10400¦AC0000111564¦plan_start_date | WP10400¦AC0000111564¦plan_end_date | WP10400¦AC0000111564¦actual_start_date | WP10400¦AC0000111564¦actual_end_date | WP10400¦AC0000111564¦responsible_user | WP10400¦AC0000111564¦responsible_team | WP10400¦AC0000111564¦supplier_no | WP10400¦AC0000111564¦comp_percent | WP10400¦AC0000111564¦assign_flag | WP10400¦AC0000111564¦status | WP10400¦AC0000111564¦doc_delivery_status | WP10400¦AC0000111564¦remark | docata¦ZDCSZ640254 | docata¦ZDCSZ640255 | WP11000¦plan_end_date | WP11000¦actual_end_date | WP11000¦status | WP11000¦AC0000111565¦plan_start_date | WP11000¦AC0000111565¦plan_end_date | WP11000¦AC0000111565¦actual_start_date | WP11000¦AC0000111565¦actual_end_date | WP11000¦AC0000111565¦responsible_user | WP11000¦AC0000111565¦responsible_team | WP11000¦AC0000111565¦supplier_no | WP11000¦AC0000111565¦comp_percent | WP11000¦AC0000111565¦assign_flag | WP11000¦AC0000111565¦status | WP11000¦AC0000111565¦remark | WP10500¦AC0000111566¦plan_start_date | WP10500¦AC0000111566¦plan_end_date | WP10500¦AC0000111566¦actual_start_date | WP10500¦AC0000111566¦actual_end_date | WP10500¦AC0000111566¦responsible_user | WP10500¦AC0000111566¦responsible_team | WP11100¦AC0000111567¦plan_start_date | WP11100¦AC0000111567¦plan_end_date | WP11100¦AC0000111567¦actual_start_date | WP11100¦AC0000111567¦actual_end_date | WP11100¦AC0000111567¦responsible_user | WP11100¦AC0000111567¦responsible_team | WP11400¦AC0000111569¦plan_start_date | WP11400¦AC0000111569¦plan_end_date | WP11400¦AC0000111569¦actual_start_date | WP11400¦AC0000111569¦actual_end_date | WP11400¦AC0000111569¦responsible_user | WP11400¦AC0000111569¦responsible_team | docata¦ZDCSZ00885808 | WPC000011222¦AC0000111592¦plan_start_date | WPC000011222¦AC0000111592¦plan_end_date | WPC000011222¦AC0000111592¦actual_start_date | WPC000011222¦AC0000111592¦actual_end_date | WPC000011222¦AC0000111592¦responsible_user | WPC000011222¦AC0000111594¦plan_start_date | WPC000011222¦AC0000111594¦plan_end_date | WPC000011222¦AC0000111594¦actual_start_date | WPC000011222¦AC0000111594¦actual_end_date | WP11200¦AC0000111568¦plan_start_date | WP11200¦AC0000111568¦plan_end_date | WP11200¦AC0000111568¦actual_start_date | WP11200¦AC0000111568¦actual_end_date | WP11200¦AC0000111568¦responsible_user | WP11200¦AC0000111568¦responsible_team | WP12000¦AC0000111579¦plan_start_date | WP12000¦AC0000111579¦plan_end_date | WP12000¦AC0000111579¦actual_start_date | WP12000¦AC0000111579¦actual_end_date | WP12000¦AC0000111579¦responsible_user | docata¦ZDCSZ01027586 | docata¦ZDCSZ01027605 | WPC000013914¦AC0000157841¦plan_start_date | WPC000013914¦AC0000157841¦plan_end_date | WPC000013914¦AC0000157841¦actual_start_date | WPC000013914¦AC0000157841¦actual_end_date | WPC000013914¦AC0000157841¦responsible_user
Site Basic Info | Site Basic Info | Du | Site Basic Info | Site Basic Info | Site Basic Info | Site Basic Info | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | TX Solution | Network Planning | Network Planning | Network Planning | Network Planning | Network Planning | Network Planning | Network Planning | Installation | Installation | Installation | Installation | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Installation | Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Material On Site | Material On Site | Material On Site | Material On Site | Material On Site | Material On Site | Telecom Installation | Telecom Installation | Telecom Installation | Telecom Installation | Telecom Installation | Telecom Installation | Software Commissioning | Software Commissioning | Software Commissioning | Software Commissioning | Software Commissioning | Software Commissioning | Installation | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Hardware Dismantling | Hardware Dismantling | Hardware Dismantling | Hardware Dismantling | Hardware Dismantling | Hardware Dismantling | (Preliminary/Provisional) Acceptance Certification | (Preliminary/Provisional) Acceptance Certification | (Preliminary/Provisional) Acceptance Certification | (Preliminary/Provisional) Acceptance Certification | (Preliminary/Provisional) Acceptance Certification | Network Planning | Network Planning | TX Planning | TX Planning | TX Planning | TX Planning | TX Planning
Site Basic Info | Site Basic Info | Du | Site Basic Info | Site Basic Info | Site Basic Info | Site Basic Info | Wireless RAN | Microwave | Wireless RAN | Microwave | Wireless RAN | Wireless RAN | Wireless RAN | Microwave | Wireless RAN | Wireless RAN | Wireless RAN | Microwave | Microwave | TX SOW Details | Microwave | Microwave | Microwave | Microwave | Microwave | Microwave | Microwave | Wireless RAN | Wireless RAN | Wireless RAN | Wireless RAN | Survey&Design | Survey&Design | Survey&Design | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | Wireless RAN | Wireless RAN | Ready For Installation | Ready For Installation | Ready For Installation | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material On Site | Material On Site | Material On Site | Material On Site | Material On Site | Material On Site | Equipment Installation | Equipment Installation | Equipment Installation | Equipment Installation | Equipment Installation | Equipment Installation | TX Integrated | TX Integrated | TX Integrated | TX Integrated | TX Integrated | TX Integrated | Microwave | L1 Approved | L1 Approved | L1 Approved | L1 Approved | L1 Approved | EHS Check | EHS Check | EHS Check | EHS Check | MRCF | MRCF | MRCF | MRCF | MRCF | MRCF | PAC Approved | PAC Approved | PAC Approved | PAC Approved | PAC Approved | Microwave | Microwave | TX Planning | TX Planning | TX Planning | TX Planning | TX Planning
customer site code | customer site name | du code | region | Province/State | Latitude (North Plus South Minus) | Longitude (East Plus West Minus) | Plan Week - TSS | Plan Month - TSS | Plan Week - TI | Plan Month - TI | Issue Tagging | Issue Tagging Details | Current issue Owner | TX Current Issue Status Tagging | Current issue Remarks | TX Upgrade Scope | Wireless RAN TX Acceptance Scope | BOQ Configuration | Tx SOW | TX SOW Details | NE SOW Details | FE SOW Details | MW Config ODU Type | MW Config Antenna Type | MW Config MW Frequency | MW Config Antenna Size NE | MW Config Antenna Size FE | SubCon - TSS Team | Subcon PR - TSS | SubCon - TI Team | Subcon PR - TI | planned end time | actual end time | status | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | responsible company | complete percent | assign status | activity status | remark | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | responsible company | complete percent | assign status | activity status | remark | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | responsible company | complete percent | assign status | activity status | remark | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | responsible company | complete percent | assign status | activity status | doc delivery status | remark | DO Number | DO Remark | planned end time | actual end time | status | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | responsible company | complete percent | assign status | activity status | remark | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | TX Cutover Date | planned start time | planned end time | actual start time | actual end time | responsible person | planned start time | planned end time | actual start time | actual end time | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | planned start time | planned end time | actual start time | actual end time | responsible person | Subcon - Planning | Subcon PR - Planning | planned start time | planned end time | actual start time | actual end time | responsible person
4008B_AD | Farlim | DU00005252305 | Northern | Penang | 5.395875 | 100.289201 | [7 empty] | 03. TSS Only | 8/9: TSS only, request change DU. 21/8: TSS done, Pending MSP/GOP for FE confirmation. 23/07: TSS Done, Pending SOW 24/07: DO Done | TSS |  | 23G_2+0_56M NE_4008B New 23G_DP_1.2M(MS) x1. Re-use exsiting RTN910A(RTN01). New XMC_3E, Sub A&B_Lo x2. FE_P00062 New 23G_DP_1.2M(MS) x1. New RTN910A(RTN01). New XMC_3E, Sub A&B_Hi x2. New CAT6 Cable with suitable length x1. | MW New Link / Reroute | Existing HW MW Link 23G_1+0_56M_512QAM_450M. Install new HW MW Link 23G_2+0_56M_512QAM_900M_EPLA. Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. Site Impacted : 4008B. NE_4008B 1.Install new 23G_DP_1.2M(MS) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Lo. Configure it. 4.Build new HW MW Link 23G_2+0_56M_512QAM_900M_EPLA. 5.Request new xC Vlan DCN & new Vlan services from ZTE IPRAN Team. 6.Migrate RAN Traffic to new MW Link 23G_2+0_56M_512QAM_900M_EPLA. 7.Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. FE_P00062 1.Install new 23G_DP_1.2M(MS) x1. 2.Install new RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Enable new electrical 1G port at PTN/Cisco. Request from ZTE IPRAN Team. 6.Patching port 8-EM6-1 of new RTN910A(RTN01) and new electrical 1G port at PTN/Cisco. 7.Migrate RAN Traffic via xC PTN/Cisco. 8.Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. | Existing HW MW Link 23G_1+0_56M_512QAM_450M. Install new HW MW Link 23G_2+0_56M_512QAM_900M_EPLA. Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. Site Impacted : 4008B. NE_4008B 1.Install new 23G_DP_1.2M(MS) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Lo. Configure it. 4.Build new HW MW Link 23G_2+0_56M_512QAM_900M_EPLA. 5.Request new xC Vlan DCN & new Vlan services from ZTE IPRAN Team. 6.Migrate RAN Traffic to new MW Link 23G_2+0_56M_512QAM_900M_EPLA. 7.Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. | Existing HW MW Link 23G_1+0_56M_512QAM_450M. Install new HW MW Link 23G_2+0_56M_512QAM_900M_EPLA. Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. Site Impacted : 4008B. FE_P00062 1.Install new 23G_DP_1.2M(MS) x1. 2.Install new RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Enable new electrical 1G port at PTN/Cisco. Request from ZTE IPRAN Team. 6.Patching port 8-EM6-1 of new RTN910A(RTN01) and new electrical 1G port at PTN/Cisco. 7.Migrate RAN Traffic via xC PTN/Cisco. 8.Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. | XMC_3E | MS | 23G | 23G_DP_1.2M(MS) x1 | 23G_DP_1.2M(MS) x1 | GTSB | SQ202506180613-GTSB | GTSB | No PR required-Work at TSS only | 2025-09-29 | 2025-09-23 | Completed | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-29 | 2025-09-22 | 2025-09-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072403 |  | 2025-07-25 | 2025-08-09 | Completed | 2025-07-24 | 2025-07-25 | 2025-07-24 | 2025-08-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-19 | 2025-08-31 | 2025-08-19 | 2025-10-13 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2025-08-19 | 2025-08-31 | 2025-08-19 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | [7 empty] | 2025-08-19 | 2025-08-31 | 2025-08-19 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2025-08-19 | 2025-08-31 | 2025-08-19 | [12 empty] | GTSB | SQ202505070167-GTSB | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | HSU//MYET CHAE/6799000011
A01073_AD | BDR_UNI_LAKEVILLE | DU00005283921 | Northern | Perak | 4.353192 | 100.992190 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | IF cable | MW Swap | MW SWAP A01073-A00607 WITH 18G_2+0_0.6/1.2_DP XMC-3E SB A,B. DISMANTLE AND REINSTALL AT NEW ANTENNA PLACE. MODULATION ISSUE IN CURRENT EXISITING LINK_RUNNING QPSK ONLY. | MW SWAP A01073-A00607 WITH 18G_2+0_0.6/1.2_DP XMC-3E SB A,B. NE: 1. Reuse and re install exisitng 18G_0.6m at new place. 2. Reuse existing XMC-3E SB A,B. 3. Reuse exusting RTN910A. 4. Configure 18G_2+0_0.6/1.2_5 | MW SWAP A01073-A00607 WITH 18G_2+0_0.6/1.2_DP XMC-3E SB A,B. FE: 1. Reuse exisitng 18G_1.2m. 2. Reuse existing XMC-3E SB A,B. 3. Reuse exusting RTN910A. 4. Configure 18G_2+0_0.6/1.2_512QAM_EPLA. | [5 empty] | GCI | SQ202506180103-GCI | GCI | SQ202506160540-GCI | 2026-01-28 | 2026-01-30 | Completed | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-20 | 2025-08-13 | 2025-08-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250911AU |  | 2025-09-12 | 2025-09-22 | Completed | 2025-09-11 | 2025-09-12 | 2025-09-11 | 2025-09-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [7 empty] | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-07-06 | Mohamad Wazir Bin Mohd TarmiziA0607607069848809495 | GCI TI | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-09-08 | Mohamad Wazir Bin Mohd TarmiziA0607607069848809495 | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-09-08 | [6 empty] | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505070167-GTSB | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | HSU//MYET CHAE/6799000011
3870C_HU | Hospital Serdang | DU00005283922 | Central | Selangor | 2.976600 | 101.719910 |  | APR 25 |  | JUN 25 | DO | Pending PTW approval | ZTE | 00. Integrated/RFS Done | 21/4/2025 : UMOBILE - In-Building System - NE site 3870C Hospital Serdang, Digi OB - 60M 3 Legged Tower - FE site 1822B Mardi(ZED) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK 3870C-1822B WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_1.74KM IMPACTED: 3870C DISMANTLE EXISTING LIN | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202505020369-GTSB | GTSB | SQ202504240805-GTSB // SQ202504240806-GTSB | 2025-11-25 | 2025-11-24 | Completed | 2025-07-24 | 2025-08-07 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-24 | 2025-08-07 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052161 |  | 2025-05-22 | 2025-05-27 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-10 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-10 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-09 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-16 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-08 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300160-GCI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | EZRIN TASNIM BIN ABDUL GANI6798000128
7585A_HU | Sukau | DU00005283923 | Sabah | Sabah | 5.520207 | 118.270310 |  |  |  |  | Drop/Cancel |  |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506160769-GTSB
1258H_LOS | 99 Speedmart TMN DESA PERMAI | DU00005283924 | Central | Selangor | 3.147874 | 101.438043 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS RTN501 NE. 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE. 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | NLOS link reroute to new FE 1475C due to LOS Block NLOS RTN510 Site Impacted : 1258H. NE_1258H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new FE route site. 6.Decom existing NLOS radio (1258H-NLOS-3926B). FE_1475C 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create Service cross connect. 5.GE port , patching the ETH cable to existing 1475C_RTN01(GE2)_(ID: 34550). 6.Traffic migarte to new FE. 7.Decom existing NLOS Radio (3926B-NLOS-1258H). | NLOS link reroute to new FE 1475C due to LOS Block NLOS RTN510 Site Impacted : 1258H. NE_1258H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new FE route site. 6.Decom existing NLOS radio (1258H-NLOS-3926B). | NLOS link reroute to new FE 1475C due to LOS Block NLOS RTN510 Site Impacted : 1258H. NE_1258H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new FE route site. 6.Decom existing NLOS radio (1258H-NLOS-3926B). | [5 empty] | GTSB | SQ202505280173-GTSB | GTSB | SQ202505280180-GTSB // SQ202505280186-GTSB | 2025-07-05 | 2025-07-03 | Completed | 2025-06-11 | 2025-06-25 | 2025-06-11 | 2025-06-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-09 | 2025-06-23 | 2025-06-09 | 2025-06-09 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052744 |  | 2025-05-28 | 2025-05-31 | Completed | 2025-05-27 | 2025-05-28 | 2025-05-27 | 2025-05-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-03 | 2025-06-30 | 2025-06-03 | 2025-06-11 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2025-06-03 | 2025-06-30 | 2025-06-03 | 2025-06-11 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-10 | 2025-06-03 | 2025-06-30 | 2025-06-03 | 2025-06-23 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | 2025-06-03 | 2025-06-30 | 2025-06-03 | 2025-06-04 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505070146-GCI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | CHEONG/SENG/WAH/7018000306
9029C_HU | Kampung Mendang Laut | DU00005283925 | Sarawak | Sarawak | 1.450759 | 110.391510 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Utilization drop | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7468A_PL | Taman Anika | DU00005496004 | Sabah | Sabah | 5.350235 | 116.154505 | [5 empty] | DONE |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 112MHz 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub B Lo 3) 1x18GHz 0.6m SP FE: 1) 1x18GHz XMC3E Sub B Hi 2) 1x18GHz 0.6m SP | MW Swap | Swap existing SM to Huawei link Use existing IDU and ISM8 card at FE site NE (7468A): 1) Install new RTN910A 2) Install new link at 7-ISM8-1 3) Migrate traffic to new link 4) Dismantle existing link FE (7448A): 1) Install new link at existing 7448A RTN01 7-ISM8-1 2) Migrate traffic to new link 3) Remove connection to SM IDU 4) Dismantle existing link | NE (7468A): 1) Install new RTN910A 2) Install new link at 7-ISM8-1 3) Migrate traffic to new link 4) Dismantle existing link | FE (7448A): 1) Install new link at existing 7448A RTN01 7-ISM8-1 2) Migrate traffic to new link 3) Remove connection to SM IDU 4) Dismantle existing link | XMC3E | MAC SP | 18G | 0.6m | 0.6m | Seri Pancar | SQ202506180105-Seri Pancar | NR services | SQ202509300159-NR Services // SQ202509300167-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-06-16 | 2025-07-31 | 2025-06-17 | 2025-06-17 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250923AM |  | 2025-09-24 | 2025-09-26 | Completed | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-26 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-02 | 2025-11-02 | 2025-10-02 | 2025-10-09 | WILFRED BALANG7167000026 | NR Service TI | 2025-10-02 | 2025-11-02 | 2025-10-02 | 2025-10-09 | WILFRED BALANG7167000026 | NR Service TI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-07 | 2025-10-02 | 2025-11-02 | 2025-10-02 | 2025-10-13 | WILFRED BALANG7167000026 | 2025-10-02 | 2025-11-02 | 2025-10-02 | 2025-10-06 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507080638-GTSB | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | HSU//MYET CHAE/6799000011
4729A_HU | KgSg Dua | DU00006791303 | Northern | Perlis | 6.340151 | 100.166681 | [9 empty] | TSS+AA+TI |  | 18G_4+0_110M_512QAM_3556M NE_4729A New ISM8 x1. New IF cable x1 RUN with suitable type and length. New SFP Module 10G 10Km 1310nm x2(ZTE BBU x1 & IDU Huawei x1). New Optical Patchcord with suitable type and length x1. FE_4614A New ISM8 x1. New IF cable x1 RUN with suitable type and length. | MW Hardware Upgrade | Existing HW MW Link HW 18G_2+0_110M_512QAM_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 18G_2+0_110M_512QAM_EPLA and later configure new HW 18G_4+0_110M_512QAM_CA. Site Impacted : 4729A & R00095. NE_4729A 1.Insert SFP Module 10G 10Km 1310nm or equivalent into ZTE RAN(BBU) and port 8-EM6-3 ofexisting RTN910AF(RTN01, NEID 44-13700). Enable and config. 2.Insert new ISM8 x1 into slot 03 of existing RTN910AF(RTN01, NEID 44-13700). 3.Lay new IF cable x1 RUN. 4.Configure existing HW 18G_2+0_110M_512QAM_EPLA to new HW 18G_4+0_110M_512QAM_CA. FE_4614A 1.Insert new ISM8 x1 into slot 03 of existing RTN910AF(RTN01, NEID 44-23700). 2.Lay new IF cable x1 RUN. 3.Configure existing HW 18G_2+0_110M_512QAM_EPLA to new HW 18G_4+0_110M_512QAM_CA. | Existing HW MW Link HW 18G_2+0_110M_512QAM_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 18G_2+0_110M_512QAM_EPLA and later configure new HW 18G_4+0_110M_512QAM_CA. Site Impacted : 4729A & R00095. NE_4729A 1.Insert SFP Module 10G 10Km 1310nm or equivalent into ZTE RAN(BBU) and port 8-EM6-3 ofexisting RTN910AF(RTN01, NEID 44-13700). Enable and config. 2.Insert new ISM8 x1 into slot 03 of existing RTN910AF(RTN01, NEID 44-13700). 3.Lay new IF cable x1 RUN. 4.Configure existing HW 18G_2+0_110M_512QAM_EPLA to new HW 18G_4+0_110M_512QAM_CA. | Existing HW MW Link HW 18G_2+0_110M_512QAM_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 18G_2+0_110M_512QAM_EPLA and later configure new HW 18G_4+0_110M_512QAM_CA. Site Impacted : 4729A & R00095. FE_4614A 1.Insert new ISM8 x1 into slot 03 of existing RTN910AF(RTN01, NEID 44-23700). 2.Lay new IF cable x1 RUN. 3.Configure existing HW 18G_2+0_110M_512QAM_EPLA to new HW 18G_4+0_110M_512QAM_CA. |  |  | 18G |  |  | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070545-GTSB // SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050521 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing
K00828_HU | K010A_K00828OD_KGKBGKUAR | DU00006791304 | Northern | Kedah | 5.960110 | 100.466758 | [9 empty] | TSS+AA+TI+Dismantle |  | 18G_2+0_110M_512QAM_EPLA NE_K00828 New 18G_1.2M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 44-23963). New ISM8 x1. New XMC_3E , Sub A&B_Hi x2. New IF cables 2x RUN with suitable type and length. FE_K00148 New 18G_1.2M(MAC)+OMT x1. New RTN910AF. New XMC_3E , Sub A&B_Lo x2. New ISM8 x1. New IF cables 2x RUN with suitable type and length. New CAT6 cable x2. | MW Swap | Existing SM MW Link_ID NT04965, K00828-K00148 MW1 18G_1+0_110MHZ_512QAM_799M. MW Swap to new HW MW Link K00828-K00148, 18G_2+0_110MHZ_512QAM_EPLA_1778M. Later, decom existing SM MW Link_ID NT04965, K00828-K00148 MW1 18G_1+0_110MHZ_512QAM_799M. Site Impacted : K00828 & K01033. NE_K00828 1.Install new 18G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-23963). Insert new ISM8 x1 into slot 04. 3.Install new XMC_3E , Sub A&B_Hi x2. Configure it. 4.Lay new IF cables from XMC_3E , Sub A&B to existing RTN910AF(RTN01, NEID 44-23963) slot 04 Port 1 & 2. 5.Request new xC Vlan DCN and and re-use existing xC Vlan Services. 6.Enable port 8-EM6-1 and patching to existing BBU(K00828). 7.Migrate traffics K00828 & K01033 via new HW MW Link K00828-K00148, 18G_2+0_110MHZ_512QAM_EPLA_1778M. 8.Later, decom existing SM MW Link_ID NT04965, K00828-K00148 MW1 18G_1+0_110MHZ_512QAM_799M. FE_K00148 1.Install new 18G_1.2M(MAC)+OMT x1. 2.Install new RTN910AF and insert new ISM8 x1 into slot 04. 3.Install new XMC_3E , Sub A&B_Lo x2. Configure it. 4.Lay new IF cables from XMC_3E , Sub A&B to new RTN910AF slot 04 Port 1 & 2. 5.Request new xC Vlan DCN and and re-use existing xC Vlan Services. 6.Re-use existing 1G port(Electrical) at PTN/Cisco and request new 2nd 1G port(Electrical) at PTN/Cisco from ZTE IPRAN Team. 7.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF. 8.Perform LAG 1G x2 for port 8-EM6-1 and 8-EM6-2 of new RTN910AF and existing 1G port(Electrical) & new 2nd 1G port(Electrical) at PTN/Cisco. 9.Migrate traffics K00828 & K01033 into 2x 1G of existing PTN/Cisco. 10.Later, decom existing SM MW Link_ID NT04965, K00828-K00148 MW1 18G_1+0_110MHZ_512QAM_799M. | Existing SM MW Link_ID NT04965, K00828-K00148 MW1 18G_1+0_110MHZ_512QAM_799M. MW Swap to new HW MW Link K00828-K00148, 18G_2+0_110MHZ_512QAM_EPLA_1778M. Later, decom existing SM MW Link_ID NT04965, K00828-K00148 MW1 18G_1+0_110MHZ_512QAM_799M. Site Impacted : K00828 & K01033. NE_K00828 1.Install new 18G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-23963). Insert new ISM8 x1 into slot 04. 3.Install new XMC_3E , Sub A&B_Hi x2. Configure it. 4.Lay new IF cables from XMC_3E , Sub A&B to existing RTN910AF(RTN01, NEID 44-23963) slot 04 Port 1 & 2. 5.Request new xC Vlan DCN and and re-use existing xC Vlan Services. 6.Enable port 8-EM6-1 and patching to existing BBU(K00828). 7.Migrate traffics K00828 & K01033 via new HW MW Link K00828-K00148, 18G_2+0_110MHZ_512QAM_EPLA_1778M. 8.Later, decom existing SM MW Link_ID NT04965, K00828-K00148 MW1 18G_1+0_110MHZ_512QAM_799M. | Existing SM MW Link_ID NT04965, K00828-K00148 MW1 18G_1+0_110MHZ_512QAM_799M. MW Swap to new HW MW Link K00828-K00148, 18G_2+0_110MHZ_512QAM_EPLA_1778M. Later, decom existing SM MW Link_ID NT04965, K00828-K00148 MW1 18G_1+0_110MHZ_512QAM_799M. Site Impacted : K00828 & K01033. FE_K00148 1.Install new 18G_1.2M(MAC)+OMT x1. 2.Install new RTN910AF and insert new ISM8 x1 into slot 04. 3.Install new XMC_3E , Sub A&B_Lo x2. Configure it. 4.Lay new IF cables from XMC_3E , Sub A&B to new RTN910AF slot 04 Port 1 & 2. 5.Request new xC Vlan DCN and and re-use existing xC Vlan Services. 6.Re-use existing 1G port(Electrical) at PTN/Cisco and request new 2nd 1G port(Electrical) at PTN/Cisco from ZTE IPRAN Team. 7.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF. 8.Perform LAG 1G x2 for port 8-EM6-1 and 8-EM6-2 of new RTN910AF and existing 1G port(Electrical) & new 2nd 1G port(Electrical) at PTN/Cisco. 9.Migrate traffics K00828 & K01033 into 2x 1G of existing PTN/Cisco. 10.Later, decom existing SM MW Link_ID NT04965, K00828-K00148 MW1 18G_1+0_110MHZ_512QAM_799M. | XMC_3E | MAC | 18G | 18G_1.2M(MAC)+OMT x1 | 18G_1.2M(MAC)+OMT x1 | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070545-GTSB // SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
K00822_HU | K007A_K00822OD_DESA_AMANKARANGAN | DU00006791305 | Northern | Kedah | 5.500960 | 100.623633 | [9 empty] | TSS+AA+TI+Dismantle |  | 18G_2+0_112Mhz_256Mhz 2x ODU 18G SRU3D sub B Pair 2xMDD2 2x IF cable | MW Hardware Upgrade | Upgrade existing link become 18G_2+0_112Mhz_256Mhz Existing ZTE link 18G_1+0_112Mhz_256QAM_700Mbps Site Impacted : 4482K/K00822 NE: 1. Change ODU to SRU3D 2. Install MD2 card 3. Config link 18G 2+0 112Mhz 256Qam FE: 1. Change ODU to SRU3D 2. Install MD2 card 3. Config link 18G 2+0 112Mhz 256Qam | NE: 1. Change ODU to SRU3D 2. Install MD2 card 3. Config link 18G 2+0 112Mhz 256Qam | FE: 1. Change ODU to SRU3D 2. Install MD2 card 3. Config link 18G 2+0 112Mhz 256Qam | SRU3D | ZTE | 18G | 0.6m | 0.6m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202605080164-GTSB | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | AB.RAHMAN//BIN MAT NOOH/6237001519
4260E_HU | POWERCHOICE (EB) | DU00006791306 | Northern | Penang | 5.299764 | 100.449075 | [9 empty] | AA |  |  | MW Remote Upgrade | Existing HW link 18G_1+0_56M Software upgrade from 56M to 112M | Existing HW link 18G_1+0_56M Software upgrade from 56M to 112M | Existing HW link 18G_1+0_56M Software upgrade from 56M to 112M | XMC | MAC | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [42 empty] | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | CHEONG/SENG/WAH/7018000306
4710B_HU | BatuHampar RDD | DU00006791307 | Northern | Perak | 4.523489 | 100.712408 | [9 empty] | TSS+AA+TI |  | ZTE 15G_4+0_CA_28Mhz 2xMD2 card | MW Hardware Upgrade | Upgarde existing ZTE mw 15_2+0 become 4+0 CA ( ZXMW 15G_28Mhz_4+0_CA_512QAM_812Mbps)_6.9km Site Impacted : 4710B NE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM FE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM | NE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM | FE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM | SRU3D | ZTE | 15G | 1.2m | 1.2m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202605080164-GTSB | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | AB.RAHMAN//BIN MAT NOOH/6237001519
9663C_AD | PekanSiburan | DU00006791308 | Sarawak | Sarawak | 1.364075 | 110.404100 | [9 empty] | TSS+TI+Dismantle |  | 1X IDU RTN910 1X IF CABLE (SUITABLE LENGTH) | MW Hardware Upgrade | MW HARDWARE UPGRADE TO CHANGE ROUTE FROM XD LINK 9663C-9165A TO XC LINK 9663C-Q00042 INSTALL 1PCS IDU AT FE Q00042 AND IF CABLE FROM EXISTING ODU LINK 9663C-9165A TO XC PATCHING NEW IDU TO XC SACOFA LL BRING ALSO TRAFFIC CHILDSITE 9743C | REUSE EXISTING XD 9663C-9165A MW | 1. INSTALL NEW IDU RTN910A AT Q00042 2. REUSE EXISTING 23G 0.6M ANTENNA 3. REUSE EXISTING ODU 23G MAC 112MHZ SUB A 4. LAY NEW IF CABLE FROM EXISTING LINK 9663C-9165A TO NEW IDU AT Q00042 4. RECONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. PATCH NEW IDU TO XC SACOFA LL 6. DISMANTLE FE XD IDU | XMC3 | MAC | 23G | 0.3 | 0.6 | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26043007 |  | 2026-05-01 |  | Ongoing | 2026-04-30 | 2026-05-01 | 2026-04-30 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | [7 empty] | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | 2025-07-07: 2026-04-30; 2025-07-07: 2027-05-06; 2025-07-07: 2026-04-30; 2025-07-08: 2026-04-30 | [9 empty] | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
B02725_HU | BB1_SEK33SHLM2 | DU00006791309 | Central | Selangor | 3.017640 | 101.553930 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9166A_AD | BandarBaru Siburan | DU00006791310 | Sarawak | Sarawak | 1.341722 | 110.405830 | [9 empty] | TSS+AA+TI+Dismantle |  | RTN910A x1 IF cable x1 | MW Hardware Upgrade | MW Hardware Upgrade at Q00042. **Q00042 paired with 9165A. Site Impacted : 9166A. NE_9166A. 1.Reuse existing MW IDU , ODU and attenna. 2.Config with 23G_1+0_112M (Existing) 3.Traffic migrate to new FE routing. FE_Q00042 1.Install new RTN910A 2.Reuse existing 23G_0.6M antenna. 3.Reuse existing ODU 23G. 4.Lay new IF cable from existing ODU to new RTN910A. 5.Patch the new IDU to Sacofa LL. 6.Create New Inband DCN. 7.Dismantle existing IDU. | MW Hardware Upgrade at Q00042. **Q00042 paired with 9165A. Site Impacted : 9166A. NE_9166A. 1.Reuse existing MW IDU , ODU and attenna. 2.Config with 23G_1+0_112M (Existing) 3.Traffic migrate to new FE routing. | MW Hardware Upgrade at Q00042. **Q00042 paired with 9165A. Site Impacted : 9166A. FE_Q00042 1.Install new RTN910A 2.Reuse existing 23G_0.6M antenna. 3.Reuse existing ODU 23G. 4.Lay new IF cable from existing ODU to new RTN910A. 5.Patch the new IDU to Sacofa LL. 6.Create New Inband DCN & config with 23G_1+0_112M. 7.Create service cross connect n traffic migrate to new FE routing. 8.Dismantle existing IDU. | XMC | HAC | 23G | 0.6 | 0.6 | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26043005 |  | 2026-05-01 |  | Ongoing | 2026-04-30 | 2026-05-01 | 2026-04-30 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | [7 empty] | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | 2025-07-07: 2026-04-30; 2025-07-07: 2027-05-06; 2025-07-07: 2026-04-30; 2025-07-08: 2026-04-30 | [9 empty] | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | CHEONG/SENG/WAH/7018000306
9252Z_HU | SimpangKg Tanjung Limbang | DU00006791311 | Sarawak | Sarawak | 4.618440 | 114.888070 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1963B_HU | KgKuantan(Smart) | DU00006791312 | Central | Selangor | 3.360121 | 101.297123 | [9 empty] | TSS+AA+TI |  | ZTE 15G_4+0_CA_28Mhz 2xMD2 card | MW Hardware Upgrade | Upgarde existing ZTE mw 15_2+0 become 4+0 CA ( ZXMW 15G_28Mhz_4+0_CA_512QAM_812Mbps)_6.9km Site Impacted : 4710B NE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM FE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM | NE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM | FE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM | SRU3D | ZTE | 15G | 1.2m | 1.2m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202605080161-GTSB | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | AB.RAHMAN//BIN MAT NOOH/6237001519
1106L_HU | JlnTaming Kiri 6 | DU00006791313 | Central | Selangor | 3.024428 | 101.745267 | [9 empty] | TSS+AA+TI+Dismantle |  | 1X 23G 0.3M DP ANTENNA 1X 23G 1.2M MS ANTENNA 1x ODU 23G XMC3 SUB A HI 1x ODU 23G XMC3 SUB A LO 1x ODU 23G XMC3 SUB B HI 1x ODU 23G XMC3 SUB B LO | MW Swap | MW SWAP LINK 1106L-1039A WITH HUAWEI_23G_2+0_0.3M/1.2M_DP_112MHZ_256QAM_1556MBPS_XMC3_SUB_A & B_LINK_1.51KM DISMANTLE EXISTING LINK EXCEPT IDU IMPACTED: 1106L | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK EXCEPT IDU | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 23G 1.2M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 2G 6. DISMANTLE EXISTING LINK EXCEPT IDU | XMC3 | MAC | 23G | 0.3 | 1.2 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050712 |  | 2026-05-08 |  | Ongoing | 2026-05-07 | 2026-05-08 | 2026-05-07 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [42 empty] | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
7762E_HU | IOIPLANTATIONS SYARIMO 7 | DU00006791314 | Sabah | Sabah | 5.296583 | 117.702164 | [9 empty] | TSS+AA+TI |  | 13G_2+0_28M. NE_7762E 13G_DP_1.2M(MAC) x1. XMC_3E , Sub A & B_Hi x2. ISM8 x1. FE_7088Z 13G_DP_1.2M(MAC) x1. XMC_3E , Sub A & B_Lo x1. ISM8 x1. | MW Parallel Link | Existing MW link 15G_1+0_28M. Install parallel link 13G_2+0_28M. Site Impacted : 7762E , 7689E. NE_7762E 1.Install new 13G_DP_1.2M(MAC). 2.Reuse existing RTN910A , 3_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Install new 3_ISM8-2+0. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom existing MW link. FE_7088Z 1.Install new 13G_DP_1.2M(MAC). 2.Reuse existing RTN910A , 3_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Install new 3_ISM8-2+0. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom existing MW link. | Existing MW link 15G_1+0_28M. Install parallel link 13G_2+0_28M. Site Impacted : 7762E , 7689E. NE_7762E 1.Install new 13G_DP_1.2M(MAC). 2.Reuse existing RTN910A , 3_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Install new 3_ISM8-2+0. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom existing MW link. | Existing MW link 15G_1+0_28M. Install parallel link 13G_2+0_28M. Site Impacted : 7762E , 7689E. FE_7088Z 1.Install new 13G_DP_1.2M(MAC). 2.Reuse existing RTN910A , 3_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Install new 3_ISM8-2+0. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom existing MW link. | XMC_3E | MAC | 15G | 1.2 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [42 empty] | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | CHEONG/SENG/WAH/7018000306
9101C_AD | TamanDuranda Emas | DU00006791315 | Sarawak | Sarawak | 1.345949 | 110.411428 | [9 empty] | TSS+AA+TI+Dismantle |  | RTN910A x1 IF Cable x1 | MW Hardware Upgrade | MW Hardware Upgrade at Q00042. **Q00042 paired with 9165A. Site Impacted : 9101C. NE_9101C. 1.Reuse existing MW IDU , ODU and attenna. 2.Config with 23G_1+0_112M (Existing) 3.Traffic migrate to new FE routing. FE_Q00042 1.Install new RTN910A 2.Reuse existing 23G_0.6M antenna. 3.Reuse existing ODU 23G. 4.Lay new IF cable from existing ODU to new RTN910A. 5.Patch the new IDU to Sacofa LL. 6.Create New Inband DCN. 7.Dismantle existing IDU. | MW Hardware Upgrade at Q00042. **Q00042 paired with 9165A. Site Impacted : 9101C. NE_9101C. 1.Reuse existing MW IDU , ODU and attenna. 2.Config with 23G_1+0_112M (Existing) 3.Traffic migrate to new FE routing. | MW Hardware Upgrade at Q00042. **Q00042 paired with 9165A. Site Impacted : 9101C. FE_Q00042 1.Install new RTN910A 2.Reuse existing 23G_0.6M antenna. 3.Reuse existing ODU 23G. 4.Lay new IF cable from existing ODU to new RTN910A. 5.Patch the new IDU to Sacofa LL. 6.Create New Inband DCN. 7.Dismantle existing IDU. | XMC | HAC | 23G | 0.6 | 0.6 | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26043003 |  | 2026-05-01 |  | Ongoing | 2026-04-30 | 2026-05-01 | 2026-04-30 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | [7 empty] | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | 2025-07-07: 2026-04-30; 2025-07-07: 2027-05-06; 2025-07-07: 2026-04-30; 2025-07-08: 2026-04-30 | [9 empty] | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | CHEONG/SENG/WAH/7018000306
9005B9_AD | pBTS KampungSiburan | DU00006791316 | Sarawak | Sarawak | 1.355480 | 110.399310 | [9 empty] | TSS+TI+Dismantle |  | 1X IDU RTN910 1X IF CABLE (SUITABLE LENGTH) | MW Hardware Upgrade | MW HARDWARE UPGRADE TO CHANGE ROUTE FROM XD LINK 9005B9-9165A TO XC LINK 9005B9-Q00042 INSTALL 1PCS IDU AT FE Q00042 AND IF CABLE FROM EXISTING ODU LINK 9005B9-9165A TO XC PATCHING NEW IDU TO XC SACOFA LL | REUSE EXISTING XD 9005B9-9165A MW | 1. INSTALL NEW IDU RTN910A AT Q00042 2. REUSE EXISTING 23G 0.6M ANTENNA 3. REUSE EXISTING ODU 23G MAC 112MHZ SUB B 4. LAY NEW IF CABLE FROM EXISTING LINK 9005B9-9165A TO NEW IDU AT Q00042 4. RECONFIGURE LINK 23G 1+0 112MHZ 256QAM 5. PATCH NEW IDU TO XC SACOFA LL 6. DISMANTLE FE XD IDU | XMC3 | MAC | 23G | 0.6 | 0.6 | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26043001 |  | 2026-05-01 |  | Ongoing | 2026-04-30 | 2026-05-01 | 2026-04-30 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | [7 empty] | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | 2025-07-07: 2026-04-30; 2025-07-07: 2027-05-06; 2025-07-07: 2026-04-30; 2025-07-08: 2026-04-30 | [9 empty] | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
B00280_HU | B060B_B00280OD_KGPERMATANG | DU00006791317 | Central | Selangor | 3.371990 | 101.241970 | [9 empty] | TSS+AA+TI |  | ZTE 15G_4+0_CA_28Mhz 2xMD2 card | MW Hardware Upgrade | Upgarde existing ZTE mw 15_2+0 become 4+0 CA ( ZXMW 15G_28Mhz_4+0_CA_512QAM_812Mbps)_6.9km Site Impacted : 4710B NE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM FE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM | NE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM | FE: 1. Install MD2 card 2. Re-connect 2nd IF cable to MD2 3. Config link 15G 4+0_CA_ 28Mhz 512QAM | SRU3D | ZTE | 15G | 1.2m | 1.2m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202605080161-GTSB | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | AB.RAHMAN//BIN MAT NOOH/6237001519
9199R_HU | Kg.Kuap (Jalan Kuap) | DU00006791318 | Sarawak | Sarawak | 1.414011 | 110.354039 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4333C_HU | PenangBridge Tol (REL) | DU00006791319 | Northern | Penang | 5.354060 | 100.392140 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1156D_HU | Tmn SuraiSelayang | DU00006791320 | Central | Selangor | 3.243468 | 101.676741 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1007D_HU | KgBaru Sentosa (REL) | DU00006791321 | Central | Selangor | 3.504037 | 101.094831 | [9 empty] | TSS+AA+TI+Dismantle |  | 18G_2+0_110M_256QAM_EPLA NE_1007D New 18G_0.6M(MDD) x1. New RTN910AF(RTN01). New XMC_5D , Sub B_Lo x1. New IF cables 2x RUN with suitable type and length. New CAT6 cable x1. FE_1154A New 18G_0.6M(MDD) x1. New RTN910AF(RTN01). New XMC_5D , Sub B_Hi x1. New IF cables 2x RUN with suitable type and length. New CAT6 cable x1. | MW Swap | Existing HW MW Link 1007D-1154A, 18G_1+0_56MHZ_512QAML_422M. MW Swap to new HW MW Link 1007D-1154A, 18G_2+0_110MHZ_256QAM_EPLA_1556M. Later, decom existing HW MW Link 1007D-1154A, 18G_1+0_56MHZ_512QAML_422M. Site Impacted : 1007D. NE_1007D 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D , Sub B_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01). 5.Patching port 8-EM6-1 of new RTN910AF(RTN01) to existing BBU(1007D). 6.Re-use existing xD Vlan DCN and Vlan Services. 7.Migrate traffic 1007D via new HW MW Link 1007D-1154A, 18G_2+0_110MHZ_256QAM_EPLA_1556M. 8.Later, decom existing HW MW Link 1007D-1154A, 18G_1+0_56MHZ_512QAML_422M. FE_1154A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D , Sub B_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01). 5.Patching port 8-EM6-1 of new RTN910AF(RTN01) to existing IBeam port. 6.Re-use existing xD Vlan DCN and Vlan Services. 7.Migrate traffic 1007D into existing IBeam port. 8.Later, decom existing HW MW Link 1007D-1154A, 18G_1+0_56MHZ_512QAML_422M. | Existing HW MW Link 1007D-1154A, 18G_1+0_56MHZ_512QAML_422M. MW Swap to new HW MW Link 1007D-1154A, 18G_2+0_110MHZ_256QAM_EPLA_1556M. Later, decom existing HW MW Link 1007D-1154A, 18G_1+0_56MHZ_512QAML_422M. Site Impacted : 1007D. NE_1007D 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D , Sub B_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01). 5.Patching port 8-EM6-1 of new RTN910AF(RTN01) to existing BBU(1007D). 6.Re-use existing xD Vlan DCN and Vlan Services. 7.Migrate traffic 1007D via new HW MW Link 1007D-1154A, 18G_2+0_110MHZ_256QAM_EPLA_1556M. 8.Later, decom existing HW MW Link 1007D-1154A, 18G_1+0_56MHZ_512QAML_422M. | Existing HW MW Link 1007D-1154A, 18G_1+0_56MHZ_512QAML_422M. MW Swap to new HW MW Link 1007D-1154A, 18G_2+0_110MHZ_256QAM_EPLA_1556M. Later, decom existing HW MW Link 1007D-1154A, 18G_1+0_56MHZ_512QAML_422M. Site Impacted : 1007D. FE_1154A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D , Sub B_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01). 5.Patching port 8-EM6-1 of new RTN910AF(RTN01) to existing IBeam port. 6.Re-use existing xD Vlan DCN and Vlan Services. 7.Migrate traffic 1007D into existing IBeam port. 8.Later, decom existing HW MW Link 1007D-1154A, 18G_1+0_56MHZ_512QAML_422M. | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1502C_HU | SyabasSetia Ecohill | DU00006791322 | Central | Selangor | 2.923522 | 101.841570 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9743C_AD | LorongTengah Siburan | DU00006791323 | Sarawak | Sarawak | 1.357361 | 110.405641 | [9 empty] | TSS+AA+TI |  | ETH Cat 6 cable x 1 | MW New Link / Reroute | Existing link 9743C change FE routing due to site burned. Site Impacted : 9743C. NE_9743C 1. Reuse existing MW equipment ( IDU , ODU and ant). 2. remain MW config 15G_2+0_28M. FE_9663C 1. Reuse existing 9663C_RTN02 to RTN910A (Refer DU ID 9663C_AD). | Existing link 9743C change FE routing due to site burned. Site Impacted : 9743C. NE_9743C 1. Reuse existing MW equipment ( IDU , ODU and ant). 2. remain MW config 15G_2+0_28M. | Existing link 9743C change FE routing due to site burned. Site Impacted : 9743C. FE_9663C 1. Reuse existing 9663C_RTN02 to RTN910A (Refer DU ID 9663C_AD). | XMC | MAC | 15G | 0.6 | 0.6 | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | [7 empty] | 2026-04-30 | 2027-05-06 |  |  | BONG NEE NYEEbong.allstar@gmail.com | 2025-07-07: 2026-04-30; 2025-07-07: 2027-05-06; 2025-07-07: 2026-04-30; 2025-07-08: 2026-04-30 | [9 empty] | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | CHEONG/SENG/WAH/7018000306
2736C_HU | ATenang Sinar Fasa (REL) | DU00006791324 | Central | Selangor | 2.841528 | 101.707125 | [9 empty] | TSS+AA+TI+Dismantle |  | Perform MW Hardware Upgrade 18G_1+0_110MHZ_256QAM. NE_2736C Re-use existing 18G_SP_0.6M(MAC) x1. Re-use existing RTN910AF(RTN01, NEID 9-35838). New XMC_3E, Sub B_Hi x1. New IF cable with suitable length and type x1 RUN. FE_1869B Re-use existing 18G_SP_0.6M(MAC) x1. Re-use existing RTN910AF(RTN03, NEID 9-35839). New XMC_3E, Sub B_Lo x1. New IF cable with suitable length and type x1 RUN. | MW Hardware Upgrade | Perform MW Hardware Upgrade 18G_1+0_110MHZ_256QAM. Site Impacted : 2736C. NE_2736C 1.Re-use existing 18G_SP_0.6M(MAC) x1. 2.Decom existing ODU XMC-3 and replace with new XMC_3E, Sub B_Hi x1. 3.Lay new IF cable with suitable length and type 1x RUN(If Required). 4.Re-use existing RTN910AF(RTN01, NEID 9-35838). 5.Build new HW MW Link 18G_1+0_110MHZ_256QAM. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic 2736C into new HW MW Link 18G_1+0_110MHZ_256QAM. FE_1869B 1.Re-use existing 18G_SP_0.6M(MAC) x1. 2.Decom existing ODU XMC-3 and replace with new XMC_3E, Sub B_Lo x1. 3.Lay new IF cable with suitable length and type 1x RUN(If Required). 4.Re-use existing RTN910AF(RTN03, NEID 9-35839). 5.Build new HW MW Link 18G_1+0_110MHZ_512QAM. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic 2736C into existing port of PTN/Cisco at CP(B00246). | Perform MW Hardware Upgrade 18G_1+0_110MHZ_256QAM. Site Impacted : 2736C. NE_2736C 1.Re-use existing 18G_SP_0.6M(MAC) x1. 2.Decom existing ODU XMC-3 and replace with new XMC_3E, Sub B_Hi x1. 3.Lay new IF cable with suitable length and type 1x RUN(If Required). 4.Re-use existing RTN910AF(RTN01, NEID 9-35838). 5.Build new HW MW Link 18G_1+0_110MHZ_256QAM. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic 2736C into new HW MW Link 18G_1+0_110MHZ_256QAM. | Perform MW Hardware Upgrade 18G_1+0_110MHZ_256QAM. Site Impacted : 2736C. FE_1869B 1.Re-use existing 18G_SP_0.6M(MAC) x1. 2.Decom existing ODU XMC-3 and replace with new XMC_3E, Sub B_Lo x1. 3.Lay new IF cable with suitable length and type 1x RUN(If Required). 4.Re-use existing RTN910AF(RTN03, NEID 9-35839). 5.Build new HW MW Link 18G_1+0_110MHZ_512QAM. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic 2736C into existing port of PTN/Cisco at CP(B00246). | XMC_3E | MAC | 18G | Re-use existing 18G_SP_0.6M(MAC) x1 | Re-use existing 18G_SP_0.6M(MAC) | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050502 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing
9000L-Q00288 | Bandaria Park | DU00003480871 | Sarawak | Sarawak | 3.127020 | 110.282704 | WK16 | APR 24 |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  | TSS |  | NE: 1x 0.6m DP Antenna 1x ISM8 Card 15G 2+0 ODU (Sub A & Sub B) Coupler for V&H FE: 1x 1.2m DP Antenna 1x ISM8 Card 15G 2+0 ODU (Sub A & Sub B) Coupler for V&H | MW Swap | Site found using SP Antenna. Required MW Swap Upgrade from 15G 2+0 to 15G 4+0. NE 1- Existing IDU 910A. Install 1x ISM8 Card. 2- Existing 2+0 ODU. Install 15G 2+0 for Vertical and Horizontal (Sub A & Sub B). 3- Swap 0.6m SP Antenna with 0.6m DP Antenna. Install coupler for Vertical and Horizontal polar. 4- Configure link 4+0_800M_512QAM with EPLA. FE 1- Existing IDU 910A. Install 1x ISM8 Card. 2- Existing 2+0 ODU. Install 15G 2+0 for Vertical and Horizontal (Sub A & Sub B). 3- Swap 1.2m SP Antenna with 1.2m DP Antenna. Install coupler for Vertical and Horizontal polar. 4- Configure link 4+0_800M_512QAM with EPLA. | [7 empty] | Datasco | SQ202403220440-Datasco | Datasco | No PR required-Work at TSS only | 2024-06-30 | 2024-07-19 | Completed | 2024-03-11 | 2024-03-15 | 2024-03-13 | 2024-03-13 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. |  | Unassigned | Completed |  | 2024-03-26 | 2024-03-29 | 2024-03-26 | 2024-03-26 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-26 | 2024-03-29 | 2024-03-26 | 2024-03-26 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-26 | 2024-06-30 | 2024-03-26 | 2024-07-19 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [7 empty] | 2024-05-27 | 2024-05-31
1083A | Bt 15 Jln Kapar | DU00003489670 | Central | Selangor | 3.168433 | 101.318472 |  | MAR 24 |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  | At FE CP(1083A) 1) 1xsuitable Fiber 10G SFP SM 1550nm Module. 2) 1xsuitable Fiber Patch Cord cable required. At NE IM(1094A) 1) 1xsuitable Fiber 10G SFP SM 1550nm Module. 2) 1xsuitable Fiber Patch Cord cable required. 3) Request 1XNew RTN910AF. 4) 2xCAT6 cables. | Cancel / Drop | (1083A) at IBeam (CP site): 1) New 10G port at IBeam already share by IPRAN Team 2) Insert new Fiber SFP module 10G SFP SM 1550nm at port GE0/2/3. 3) Lay new suitable Fiber patch cord cable to new 10G port GE0/2/3. NE (1094A) at new Huawei RTN 910AF(RTN01) as a switch: 1) Insert new Fiber SFP module 10G SFP SM 1550nm at 8-EM6-3(Port 3). 2) Lay new suitable Fiber patch cord cable to 8-EM6-3(Port 3) from ODF. 3) Shifting existing OB Fiber patch cord from existing SM AGS -20 IDU(existing MW Link 1094A-1200B MW1) LAN 5 to new HW RTN910AF(RTN01) 8-EM6-3(Port 3). 4) Recascading RAN BBU 1094A from existing SM AGS -20 IDU(perhaps LAN 2) to new HW RTN910AF(RTN01) 8-EM6-1(Port 1). 5) Recascading existing SM AGS -20 IDU(existing MW Link 1094A-1200B MW1 with IP 10.7.253.135) to new HW RTN910AF(RTN01) 8-EM6-2(Port 2). Other Info: 1) New vlan services required for sites(1094A & 1200B). 2) New IP and vlan DCN required for RTN01(RTN910AF). | [7 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | No SFP 10G and patch cord E2K 15m |  |  | Not started | [8 empty] | Unassigned | Not started
7042A | Telipok | DU00003489671 | Sabah | Sabah | 6.116350 | 116.207130 |  | MAR 24 | WK12 | MAR 24 | RFS | TI WIP | ZTE | 00. Integrated/RFS Done | D2: Cutover done | TSS+TI | L1+ATP+PAC | At NE IBeam(7042A) 1) 1xsuitable "Electrical" 1G SFP Module. 2) 1xsuitable length of CAT6 cable required. At NE RTN04(7042A) 1) 1xsuitable "Electrical" 1G SFP Module. 2) Request 1XNew RTN910AF. | IDU-IPRAN | Adding 1G IPRAN port at IBeam 7042A. NE (7042A) at IBeam(CP site): 1) New 1G port at IBeam already share by IPRAN Team(Nazril). 2) Insert new "Electrical" SFP module 1G SFP at port GE0/2/2. 3) Lay new suitable CAT6 cable to new 1G port GE0/2/2 from RTN02(new RT910AF) 8-EM6-1(Port 1). 4) Configure it. NE (7042A) at new Huawei New RTN 910AF(RTN02): 1) Insert new "Electrical" SFP module 1G SFP SM at 8-EM6-1(Port 1). 2) Lay new CAT6 cable from RTN02(new RT910AF) 8-EM6-1(Port 1) to IBeam new 1G port GE0/2/2. 3) Shifting existing IF cable from exsiting RTN03(RTN 910A) for existing MW Link 7042A-7315B ISM6 slot 7 Port 1 to new RTN02(RTN 910AF) ISM8 slot 7 Port 1. Other Info: 1) New vlan services required for site(7315B). 2) New IP and vlan DCN required for RTN02(RTN910AF). | [7 empty] | NR Services | SQ202504210288-NR Services | NR services | SQ202411120063-NR Services |  |  | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24040801 |  | 2024-04-18 | 2024-04-19 | Completed | 2024-04-17 | 2024-04-18 | 2024-04-17 | 2024-04-19 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-20 | 2024-03-31 | 2024-03-20 | 2024-05-10 | MURES//BIN SAKAI/6800000004 | GCI TI | 2024-03-20 | 2024-06-30 | 2024-03-20 | 2024-05-10 | MURES//BIN SAKAI/6800000004 | GCI TI | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-20 | 2024-03-31 | 2024-03-20 | 2024-06-15 | MURES//BIN SAKAI/6800000004 | 2025-07-07: 2024-03-20; 2025-07-07: 2024-03-31; 2025-07-07: 2024-03-20; 2025-07-08: 2024-03-21 |  |  | 2024-11-30 | 2024-12-30 | 2024-11-30 | 2024-11-30 | ASTI//GANIS PUTRIANI/6237001358
1367A | WorldWideBusiness | DU00003489672 | Central | Selangor | 3.071544 | 101.541113 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP | TSS |  |  | Cancel / Drop | WK17: 1367A-MAC-001 Worldwide Business/GigabitEthernet0/2/13 Utilization reduced <70% | [13 empty] | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 |  | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7221A | Kinarut | DU00003489673 | Sabah | Sabah | 5.822128 | 116.044786 |  | MAR 24 |  | MAR 24 | RFS | Pending plan | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+TI | L1+ATP+PAC | At NE IBeam(7221A) 1) 1xsuitable "Electrical" 1G SFP Module. 2) 1xsuitable length of CAT6 cable required. At NE RTN04(7221A) 1) 1xsuitable "Electrical" 1G SFP Module. 2) Request 1XNew RTN910AF. | IDU-IPRAN | Adding 1G IPRAN port at IBeam 7221A. NE (7221A) at IBeam(CP site): 1) New 1G port at IBeam already share by IPRAN Team(Nazril). 2) Insert new "Electrical" SFP module 1G SFP at port GE0/2/8. 3) Lay new suitable CAT6 cable to new 1G port GE0/2/8 from RTN04(new RT910AF) 8-EM6-1(Port 1). 4) Configure it. NE (7221A) at new Huawei New RTN 910AF(RTN04): 1) Insert new "Electrical" SFP module 1G SFP SM at 8-EM6-1(Port 1). 2) Lay new CAT6 cable from RTN04(new RT910AF) 8-EM6-1(Port 1) to IBeam new 1G port GE0/2/8. 3) Shifting existing IF cable from exsiting RTN01(RTN 910AF) for existing MW Link 7221A-7961B ISM8 slot 7 Port 1 to new RTN04(RTN 910AF) ISM8 slot 7 Port 1. Other Info: 1) New vlan services required for site(7961B). 2) New IP and vlan DCN required for RTN04(RTN910AF). | [7 empty] | NR services | SQ202504210288-NR Services | NR services | SQ202411120063-NR Services |  |  | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24040802 |  | 2024-04-18 | 2024-04-19 | Completed | 2024-04-17 | 2024-04-18 | 2024-04-17 | 2024-04-19 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-19 | 2024-03-31 | 2024-03-19 | 2024-05-10 | MURES//BIN SAKAI/6800000004 | GCI TI | 2024-03-19 | 2024-06-30 | 2024-03-19 | 2024-05-10 | MURES//BIN SAKAI/6800000004 | GCI TI | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-19 | 2024-03-31 | 2024-03-19 | 2024-06-13 | MURES//BIN SAKAI/6800000004 | 2025-07-07: 2024-03-19; 2025-07-07: 2024-03-31; 2025-07-07: 2024-03-19; 2025-07-08: 2024-03-19 |  |  | 2024-11-30 | 2024-12-30 | 2024-11-30 | 2024-11-30 | ASTI//GANIS PUTRIANI/6237001358
1851B | Rinching Tengah (KJS) | DU00003489674 | Central | Selangor | 2.914596 | 101.856837 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  | 2x 1xnew suitable Fiber 10G SFP SM 1550 40km Module 2x Fiber Patch Cord cable | Cancel / Drop | 10G IPRAN port upgrade at IBeam 1851B and RTN13 at 1851B. FE (1851B) at IBeam: 1) Insert new Fiber SFP module 10G SF at new 10G port GE (to be advised). 2) Re-patching existing Fiber patch cord cable to new 10G port (to be advised). NE (1851B) at Huawei IDU 910A RTN13: 1) Insert new Fiber SFP module 10G SFP SM 1550 40km at 8-EM6-3(Port 3). 2) Re-patching existing Fiber patch cord cable to 8-EM6-3(Port 3). Impact sites: 1514C,1133B,1750C,1539H,3357A_12 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1156A | Btg. Berjuntai | DU00003489675 | Central | Selangor | 3.378158 | 101.407100 |  | MAR 24 |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  | At NE IBeam(1156A) 1) 1xsuitable Fiber 10G SFP SM 1550nm Module. 2) 1xsuitable Fiber Patch Cord cable required. At NE RTN06(1156A) 1) 1xsuitable Fiber 10G SFP SM 1550nm Module. 2) 1xsuitable Fiber Patch Cord cable required. 3) Request 1XNew RTN910AF. | Cancel / Drop | 10G IPRAN port upgrade at IBeam 1156A. NE (1156A) at IBeam(CP site): 1) New 10G port at IBeam already share by IPRAN Team(Nazril). 2) Insert new Fiber SFP module 10G SFP SM 1550nm at port GE0/2/9. 3) Lay new suitable Fiber patch cord cable to new 10G port GE0/2/9. 4) Configure it. NE (1154A) at new Huawei New RTN 910AF(RTN06): 1) Insert new Fiber SFP module 10G SFP SM 1550nm at 8-EM6-3(Port 3). 2) Lay new suitable Fiber patch cord cable to 8-EM6-3(Port 3) from ODF. 3) Shifting existing IF cable from exsiting RTN02(RTN 910AF) for exsiting MW Link 1156A-1610C ISM8 slot 4 Port 1 to new RTN06(RTN 910AF) ISM8 slot 7 Port 1. Other Info: 1) New vlan services required for site(1610C). 2) New IP and vlan DCN required for RTN06(RTN910AF). | [7 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | No SFP 10G and patch cord E2K 15m |  |  | Not started | [8 empty] | Unassigned | Not started
2827A-1342A | SHT Tunnel | DU00003607863 | Central | Selangor | 3.063338 | 101.555800 |  | MAY 24 |  | JUL 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 6/8: Continue T/shooting. Reverse H/L subband done. Need new LB 5/8: Change antenna done. Detect link interference 31/7: CD complaint antenna oversize at NE. 25/7: Cutover done. Post-CO T/shooting WIP 3/7: TI WIP, delay due raining. EB CRQ expired | TSS+AA+TI | L1+ATP+PAC | 18G_1+0_1.2M/1.2M_DP_112MHZ_512QAM SUB B | MW Parallel Link | MW PARALLEL LINK 2827A-1342A 18G_1+0_0.6M/1.2M_DP_112MHZ_512QAM SUB B TO CARRY TRAFFIC OF CHILD 3314B IMPACTED SITE: 3314B NE: 1) INSTALL NEW ISM8 AT EXISTING RTN02 SLOT 3 2) INSTALL NEW 18G 1+0 112MHZ AT EXISTING RTN02 3-ISM8 3) INSTALL NEW ANTENNA 18G 0.6M AND ODU SUBBAND B 4) MIGRATE 3314B TRAFFIC NEW LINK FE: 1) INSTALL NEW RTN910A (OPS TEAM TO ASSIGN NEW RTN NUMBER) 2) INSTALL NEW 18G 1+0 112MHZ AT NEW RTN 7-ISM8 3) INSTALL NEW ANTENNA 18G 1.2M AND ODU SUBBAND B 4) MIGRATE 3314B TRAFFIC NEW LINK 5) PATCH NEW IDU TO NEW CP PORT AND ESTABLISH NEW DCN | [7 empty] | Allstar | SQ202409110347-Allstar | Allstar | SQ202408080487-Allstar | 2024-08-23 | 2024-08-22 | Completed | 2024-07-03 | 2024-07-03 | 2024-07-02 | 2024-07-03 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-04 | 2024-07-05 | 2024-07-04 | 2024-07-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-17 | 2024-07-18 | 2024-07-17 | 2024-07-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240619AC |  | 2024-06-20 | 2024-06-21 | Completed | 2024-06-19 | 2024-06-20 | 2024-06-19 | 2024-06-21 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-09-12 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | Allstar TI | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-09-23 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | Allstar TI | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-09-20 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | 2025-07-07: 2024-07-02; 2025-07-07: 2024-07-28; 2025-07-07: 2024-07-02; 2025-07-08: 2024-07-02 |  |  | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
B00241-B00910 | BUKIT TAMPOI | DU00003607864 | Central | Selangor | 2.859400 | 101.670800 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Link existing 18G_1+0_56M. Alarm Loss Comm due to link dismantle. Relocate to 1665K/B01953-B00910.Link Config 23G_1+0_56M , one Ult performance < 70%. | Link existing 18G_1+0_56M. Alarm Loss Comm due to link dismantle. Relocate to 1665K/B01953-B00910.Link Config 23G_1+0_56M , one Ult performance < 70%. | Link existing 18G_1+0_56M. Alarm Loss Comm due to link dismantle. Relocate to 1665K/B01953-B00910.Link Config 23G_1+0_56M , one Ult performance < 70%. | [5 empty] | MTK | No PR required-Site drop/cancel | MTK | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7010C-7677B | Log Pond | DU00003607865 | Sabah | Sabah | 4.280401 | 117.868900 |  |  |  |  | Drop/Cancel | Pass to Huawei |  | 03. TSS Only | Pass to Huawei | TSS |  |  | MW Hardware Upgrade | MW Hardware upgrade 7010C-7667B HWi 18G 1+0 0.6m&0.6m 55MHz to 18G 1+0 0.6m&0.6m 110MHz NE: 1. Reuse existing RTN910A . 2. Change to XMC-3E ODU 18G_110MHz. 3. Configure link as 18GHz_1+0_110MHz. FE: 1. Install new IDU RTN910A . 2. Change to XMC-3E ODU 18G_110MHz. 3. Configure link as 18GHz_1+0_110MHz. | [7 empty] | NR services | SQ202502120362-NR Services |  |  | 2025-07-11 | 2025-07-07 | Completed | 2025-02-09 | 2025-02-09 | 2025-02-09 | 2025-02-09 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-11 | 2025-02-14 | 2025-02-11 | 2025-02-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-11 | 2025-02-14 | 2025-02-11 | 2025-02-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Full Site DR |  |  | Not started | [8 empty] | Unassigned | Not started |  | 2025-01-20 | 2025-02-15 | 2025-01-20 |  | RAMLAN//BIN ROSLAN/6000002578 | NR Service TI | 2025-01-20 | 2025-02-15 | 2025-01-20 |  | RAMLAN//BIN ROSLAN/6000002578 | NR Service TI | [7 empty] | 2025-01-20 | 2025-02-15 | 2025-01-20 |  | RAMLAN//BIN ROSLAN/6000002578 | 2025-07-07: 2025-01-20; 2025-07-07: 2025-02-15; 2025-07-07: 2025-01-20; 2025-07-08: 2025-01-20
Q01840-Q00233 | KG MELAYU BARU KAPIT | DU00003607866 | Sarawak | Sarawak | 2.008130 | 112.915300 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | 4/9/2025 : Task will do under NIC TX |  |  |  | Under NIC | link upgrded to 450Mhz and will decom under NIC | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050655-GTSB | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | HSU//MYET CHAE/6799000011
B01791-B00686 | PKFZ PORT KLANG | DU00003607867 | Central | Selangor | 2.905800 | 101.301300 |  |  |  |  | Cancel / Drop | Remove from HU list | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed due to already remove from HU list |  |  |  | Cancel / Drop | [8 empty] | Nera | No PR required-Site drop/cancel | Nera | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
N00405-B00550 | N00405_KM277PLHEAVEN | DU00003607868 | Southern | Sembilan | 2.790300 | 101.806900 |  |  | WK32-WK35 | AUG 24 |  |  |  | 03. TSS Only | 2/9: Site decom. Not proceed | TSS |  | 15G_2+0_512QAM_28MHZ_1.2M/1.2M_SUB A & B | MW Swap | MW SWAP LINK N00405-B00550 WITH HUAWEI_15G_2+0_512QAM_28MHZ_1.2M/1.2M_SUB A & B NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW 15G XMC-3 SUB BAND B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW 15G XMC-3 SUB BAND B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | Nera |  | CCSMY | No PR required-Work at TSS only |  |  | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY240527A9 |  | 2024-05-28 | 2024-05-31 | Completed | 2024-05-27 | 2024-05-28 | 2024-05-31 | 2024-05-31 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  |  | Assigned | Completed |  | 2024-05-31 | 2024-05-31 | 2024-05-31 | 2024-05-31 | RUBUN//A/L THIYAHARAJAN/7670000010 |  | 2024-06-01 | 2024-09-30 |  |  | RUBUN//A/L THIYAHARAJAN/7670000010 | Nera TI | [7 empty] | 2024-06-01 | 2024-06-30 | 2024-06-01 |  | RUBUN//A/L THIYAHARAJAN/7670000010 | 2025-07-07: 2024-06-01; 2025-07-07: 2024-06-30; 2025-07-07: 2024-06-01 | [7 empty] | GCI_AA | SQ202510300179-GCI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01372-Q00314 | KG GAYA | DU00003607869 | Sarawak | Sarawak | 4.842517 | 115.405500 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050655-GTSB | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | HSU//MYET CHAE/6799000011
4168A-4000A | SbJaya (TMTouch MSC) | DU00003607870 | Northern | Penang | 5.402417 | 100.393800 |  | MAY 24 |  | MAY 24 |  | Pending DO |  | 00. Site Out/Drop |  |  |  | 2X RTN 910A 1X 18G 0.6M MDD ANTENNA 1X 18G 1.2M MDD ANTENNA 1X 18G XMC-5D SUB A HI 1X 18G XMC-5D SUB A LO | Cancel / Drop | All traffic already divert to xC host | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3688C-3256A | Jalan Desa 1 | DU00003607871 | Central | Selangor | 3.322746 | 101.530000 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 29/11: Cutover done 14/11: Pending FE PTW approval (Edotco) - AC-839744 4/11: NE site pending Edgepoint approval, FE Pending PTW Edotco approval 23/10: Cannot proceed with Interim solution: SW Upgrade activity on existing link due ODU not supported | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1) 1x23GHz XMC3 112MHz Sub A Hi 2) 1xISM8 card FE: 1) 1x23GHz XMC3 112MHz Sub A Lo 2) 1xISM8 card | MW Hardware Upgrade | Perform hardware upgrade 1+0 56MHz to 1+0 112MHz for 3688C RTN01-3256A RTN02 1) Replace ODU with XMC3 112MHz 2) Use ISM8 card at NE and FE Impact site: 3688C NE (3688C RTN01): 1) Add ISM8 card at RTN01 slot 3 2) Replace ODU with new 112MHz ODU 3) Configure link with 112MHz FE (3256A RTN02): 1) Replace ISV3 card at RTN02 slot 4 with new ISM8 card 2) Replace ODU with new 112MHz ODU 3) Configure link with 112MHz | [7 empty] | Allstar | SQ202410280461-Allstar | Allstar | SQ202410100840-Allstar // SQ202504260124-Allstar // SQ202510070055-Allstar | 2024-11-06 | 2024-11-05 | Completed | 2024-10-14 | 2024-10-15 | 2024-10-15 | 2024-10-15 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-23 | 2024-10-24 | 2024-10-23 | 2024-10-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-05 | 2024-11-06 | 2024-11-05 | 2024-11-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-05 | 2024-11-06 | 2024-11-05 | 2024-11-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24090942 |  | 2024-09-10 | 2024-09-12 | Completed | 2024-09-09 | 2024-09-10 | 2024-09-09 | 2024-09-12 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-01 | 2024-12-31 | 2024-12-10 | 2024-12-10 | ALIF//ILYASA BIN RUSLI/6798000204 | Allstar TI | 2024-11-30 | 2025-11-30 | 2024-11-30 | 2024-11-30 | ALI//HAMZA/6798000192 | Allstar TI | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2024-12-04 | SHUJAAT//ALI/6800000124 |  |  | 2024-11-30 | 2025-11-30 | 2024-11-30 | 2024-12-20 | ALI//HAMZA/6798000192 | 2024-11-30 | 2025-11-30 | 2024-11-30 | 2024-11-30 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
3588C-2436A | Surau Taman Widuri | DU00003607872 | Central | Selangor | 3.431589 | 101.591600 |  |  |  | JUN 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 5/7: D1: Cutover done 1/7: FE Pending Edotco PTW approval. AC-806033 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 110MHz 0.6m/0.6m | MW Hardware Upgrade | MW Hardware upgrade 3588C-2436A HWi18G 1+0 0.6m&0.6m 55MHz to 18G 1+0 0.6m&0.6m 110MHz NE: 1. Reuse existing RTN910A . 2. Change to XMC-3E ODU 18G_110MHz_SB B. 3.Reuse existing Antenna. 4. Configure link as 18GHz_1+0_110MHz_889M FE: 1.Reuse existing IDU RTN910A . 2. Change to XMC-3E ODU 18G_110MHz_SB B. 3. Reuse existing Antenna. 4. Configure link as 18GHz_1+0_110MHz. | [7 empty] | Allstar | SQ202407050105-Allstar | Allstar | SQ202409110341-Allstar | 2024-07-18 | 2024-07-17 | Completed | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-27 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-17 | 2024-07-18 | 2024-07-17 | 2024-07-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240527A4 |  | 2024-05-28 | 2024-05-29 | Completed | 2024-05-27 | 2024-05-28 | 2024-05-27 | 2024-05-29 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-07-04 | 2024-07-31 | 2024-07-04 | 2024-09-19 | RAHMAD//HIDAYAT BIN LAMRI/6798000206 | Allstar TI | 2024-07-04 | 2024-07-31 | 2024-07-04 | 2024-09-23 | RAHMAD//HIDAYAT BIN LAMRI/6798000206 | Allstar TI | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-07-04 | 2024-07-31 | 2024-07-04 | 2024-07-19 | RAHMAD//HIDAYAT BIN LAMRI/6798000206 | 2024-07-04 | 2024-07-31 | 2024-07-04 | 2024-07-05 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-06 | NG HONG JIE7018000036 | Logistic Team | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
9121K-9062X | Q118B_Q01771OD_TMNEVERGREENBTU | DU00003607873 | Sarawak | Sarawak | 3.183093 | 113.067800 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Under observation |  |  | 18G_2+0_0.6/1.2_DP_110Mhz_XMC_3E_SB A,B | Cancel / Drop | MW SWAP 9121K- 9106A FROM 18G_1+0 TO 18G_2+0_0.6/1.2_DP_110MHz Need 10G port at FE | MW SWAP 9121K- 9106A FROM 18G_1+0 TO 18G_2+0_0.6/1.2_DP_110MHz NE: 1. Reuse exisitng RTM910A. 2. Swap exisitng ODU with XMC-3E_SB A,B. 3. Swap exisitng antenna with 0.6m_DP. 4. Configure 18G_2+0_0.6/1.2_DP_110Mhz_256QAM. | MW SWAP 9121K- 9106A FROM 18G_1+0 TO 18G_2+0_0.6/1.2_DP_110MHz FE: 1. Reuse exisitng RTM910A. 2. Swap exisitng ODU with XMC-3E_SB A,B. 3. Swap exisitng antenna with 0.6m_DP. 4. Configure 18G_2+0_0.6/1.2_DP_110Mhz_256QAM. 5. Need to use 10G port. | XMC-3E_SB A,B |  | 18 | 0.6 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050655-GTSB | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | HSU//MYET CHAE/6799000011
Y00041-A00006 | EMOS UPSI MAIN CAMPUS | DU00003874295 | Northern | Perak | 3.685603 | 101.523188 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
B00007-B00545 | B060C_B00007OD_SPGPCKALAM | DU00003874296 | Central | Selangor | 3.245210 | 101.472190 |  |  |  | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 23/8: Cutover done 19/8: Pending EB CRQ approval. Plan 22/8 - 24/8 | TSS+TI | L1+ATP+PAC | FE: 1) 2 x SFP 1G 10km 2) 1 pair patch cord | MW IDU Patching | Congestion at CP site B00545 from IDU CT11021 GE1 to PTN To divert site 1965B to other IDU/CP port. Impact site: 1965B NE (B00007): 1) Remain existing FE (B00545): 1) Patch GE4 (optical) to new PTN port (ops team to assign new port) 2) Divert 1965B to new port | [7 empty] | MTK | SQ202408300801-MTK | MTK | SQ202408140523-MTK | 2024-10-15 | 2024-10-14 | Completed | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-20 | 2024-09-21 | 2024-09-20 | 2024-09-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-20 | 2024-09-21 | 2024-09-20 | 2024-09-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-14 | 2024-10-15 | 2024-10-14 | 2024-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24080770 |  | 2024-08-08 | 2024-08-12 | Completed | 2024-08-07 | 2024-08-08 | 2024-08-07 | 2024-08-12 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-23 | 2024-08-31 | 2024-08-22 | 2024-08-26 | MOHD FADZILLAH BIN TARMIJI8225000017 | MTK TI | 2024-08-23 | 2024-08-31 | 2024-08-22 | 2024-08-26 | MOHD FADZILLAH BIN TARMIJI8225000017 | MTK TI | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | SHUJAAT//ALI/6800000124 |  |  | 2024-08-23 | 2024-08-31 | 2024-08-22 | 2024-08-25 | MOHD FADZILLAH BIN TARMIJI8225000017 | 2025-07-07: 2024-08-23; 2025-07-07: 2024-08-31; 2025-07-07: 2024-08-24; 2025-07-08: 2024-08-24 |  |  | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
K00575-P00117 | K005A_K00575OD_CB_KOTAKUALAMUDA_RDC | DU00003874298 | Northern | Kedah | 5.589310 | 100.373110 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Drop | (11/10): DU no proceeding, work done at TX Rollout P00117_PostMOCN |  | 03. TSS Only | 8/10: SOW done under P00117_PostMOCN | TSS |  | FE: 1) 2 x SFP 1G 10km 2) 1 pair patch cord | MW IDU Patching | Congestion at CP site P00117 from IDU NT05931 GE5 to PTN To divert site 4947A to other IDU/CP port. Impact site: 4947A NE (K00575): 1) Remain existing FE (P00117): 1) Patch GE6 (optical) to new PTN port (ops team to assign new port) 2) Divert 4947A to new port | [7 empty] | GCI | SQ202511050134-GCI |  |  | 2024-11-29 | 2024-11-29 | Completed | 2024-10-09 | 2024-10-09 | 2024-10-09 |  | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Disabled |  | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24083048 |  | 2024-08-31 | 2024-12-21 | Completed | 2024-08-30 | 2024-08-31 | 2024-08-30 | 2024-12-21 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-08 | 2024-10-31 | 2024-10-08 | 2024-10-15 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2024-10-08 | 2024-10-31 | 2024-10-08 | 2024-10-15 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | [7 empty] | 2024-10-08 | 2024-10-31 | 2024-10-08 | 2024-10-08 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-07-07: 2024-10-08; 2025-07-07: 2024-10-31; 2025-07-07: 2024-10-08; 2025-07-08: 2024-10-09
2673B-3256A | Jalan Desa Ria | DU00003874299 | Central | Selangor | 3.326174 | 101.541378 |  |  | WK32-WK35 | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 14/8: D2: Cutover done 13/8: MOS & Pre-installation WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 2+0 112MHz 0.6m/0.6m DP NE: 1) 1xRTN910A 2) 1x23GHz XMC3 Sub A Hi 3) 1x23GHz XMC3 Sub B Hi FE: 1) 1xRTN910A 2) 1x23GHz XMC3 Sub A Lo 3) 1x23GHz XMC3 Sub B Lo | MW Swap | Existing link 2673B-3256A 1+0 112MHz (2673B RTN01-3256A RTN03) To swap with 2+0 112MHz Impact site: 2673B NE (2673B) 1. Install new RTN910A (ops team to assign RTN number) 2. Swap SP antenna with DP antenna 3. Install new link 2+0 link at new RTN 7-ISM8 4. Reuse existing link channel for V polarization FE (3256A) 1. Swap existing RTN03 with new RTN910A to use CSHRF board 2. Transfer ISM8 card from slot 3 & 4 to new IDU 3. Swap SP antenna with DP antenna 4. Install new link 2+0 link at RTN01 7-ISM8 5. Reuse existing link channel for V polarization | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202408140523-MTK | 2024-09-28 | 2024-09-27 | Completed | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-08-16 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-21 | 2024-09-22 | 2024-09-21 | 2024-09-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-21 | 2024-09-22 | 2024-09-21 | 2024-09-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-27 | 2024-09-28 | 2024-09-27 | 2024-09-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO req by Hady | 2024-07-31 | 2024-08-01 | Completed | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-08-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-12 | 2024-08-31 | 2024-08-12 | 2024-08-19 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-08-12 | 2024-08-31 | 2024-08-12 | 2024-08-16 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | SHUJAAT//ALI/6800000124 |  |  | 2024-08-12 | 2024-08-31 | 2024-08-12 | 2024-08-15 | RIDHUAN//BIN MANSOR/8225000011 | 2024-08-12 | 2024-08-31 | 2024-08-12 | 2024-08-13 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 | NG HONG JIE7018000036 | Logistic Team | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
3211B-1605B | SKVE KM 112 (REL) | DU00003874300 | Central | Selangor | 2.928453 | 101.546713 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 23/7: D3: Cutover done 22/7: D2: TI done, CO in plan 19/7: D1: MOS & TI In Plan | TSS+AA+TI | L1+ATP+PAC | 15G 2+0 1.2m/1.2m DP NE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Hi 3) 1x15GHz XMC3 Sub B Hi 4) 1x15GHz 1.2m DP FE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Lo 3) 1x15GHz XMC3 Sub B Lo 4) 1x15GHz 1.2m DP | MW Parallel Link | Existing link 3211B-1605B 2+0 (3211B RTN01-1605B RTN02) Add parallel 2+0 Final config will be 4+0 Impact site: 3211B,1639H NE (3211B RTN01) 1. Add ISM8 at RTN02 slot 3 2. Install new 2+0 link at RTN01 3-ISM8 3. Create 4+0 EPLA FE (1605B RTN02) 1. Add ISM8 at RTN02 slot 3 2. Install new 2+0 link at RTN02 3-ISM8 3. Create 4+0 EPLA | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202408080495-MTK | 2024-09-20 | 2024-09-19 | Completed | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-08 | 2024-08-09 | 2024-08-08 | 2024-08-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-08 | 2024-08-09 | 2024-08-08 | 2024-08-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071012 |  | 2024-07-11 | 2024-07-12 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-12 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-19 | 2024-07-31 | 2024-07-19 | 2024-08-01 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-07-19 | 2024-08-01 | 2024-07-19 | 2024-08-01 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-07-24 | 2024-07-24 | 2024-07-24 | 2024-07-24 | SHUJAAT//ALI/6800000124 |  |  | 2024-07-19 | 2024-07-31 | 2024-07-19 | 2024-07-25 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-07-07: 2024-07-19; 2025-07-07: 2024-07-31; 2025-07-07: 2024-07-19; 2025-07-08: 2024-07-29 |  |  | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
3435B-1622B | pBTS Taman Sentosa Kapar (C ) | DU00003874301 | Central | Selangor | 3.132984 | 101.380310 |  |  | WK32-WK35 | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 6/8: D2: Cutover done. Post-CO T/shooting WIP 5/8: MOS & Pre-installation WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 2+0 112MHz 0.6m/0.6m DP NE: 1) 1xISM8 card 2) 1x23GHz XMC3 Sub A Lo 3) 1x23GHz XMC3 Sub B Lo FE: 1) 1xISM8 card 2) 1x23GHz XMC3 Sub A Hi 3) 1x23GHz XMC3 Sub B Hi | MW Swap | Existing link 3435B-1622B 1+0 112MHz (3435B_12 RTN01-1622B RTN01) To swap with 2+0 112MHz Impact site: 3435B NE (3435B) 1. Add ISM8 at RTN01 slot 3 2. Swap SP antenna with DP antenna 3. Install new link 2+0 link at RTN01 3-ISM8 4. Reuse existing link channel for V polarization FE (1622B) 1. Add ISM8 at RTN01 slot 3 2. Swap SP antenna with DP antenna 3. Install new link 2+0 link at RTN01 3-ISM8 4. Reuse existing link channel for V polarization | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202408140523-MTK | 2024-09-20 | 2024-09-19 | Completed | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-06 | 2024-09-07 | 2024-09-06 | 2024-09-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-06 | 2024-09-07 | 2024-09-06 | 2024-09-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240730AE |  | 2024-07-31 | 2024-08-01 | Completed | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-08-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-05 | 2024-08-31 | 2024-08-05 | 2024-08-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-08-05 | 2024-08-31 | 2024-08-05 | 2024-08-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-08-09 | SHUJAAT//ALI/6800000124 |  |  | 2024-08-05 | 2024-08-31 | 2024-08-05 | 2024-08-09 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-08-05 | 2024-08-31 | 2024-08-05 | 2024-08-05 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 | NG HONG JIE7018000036 | Logistic Team | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
3230B-1605B | Bandar Rimbayu | DU00003874302 | Central | Selangor | 2.940750 | 101.545111 | WK03 | JAN 25 | WK03 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 18/1/2025 : Cutover done 13/1/2025 : MAXIS - 30M Monopole - NE site 3230B Bandar Rimbayu, Digi OB - 45M 3 Legged Tower - FE site 1605B Kemuning Green Ville (Kota Kem 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_3230B 18G_DP_0.6m(MDD) x1. XMC_5D-2+0 , Sub_A_Hi x1. ISM8 x1. FE_1605B 18G_DP_1.2m(MDD) x1. XMC_5D-2+0, Sub_A_Lo x1. RTN910A x1. | MW Swap | Swap existing to 18G_2+0_112M Site impacted : 1603C,1185C,3230B NE_3230B 1.Install new 18G_DP_0.6m(MDD). 2.Install new XMC_5D-2+0 , Sub_A_Hi. 3.Reuse existing 3230B_RTN01. 4.Instal new 3_ISM8-2+0 into existing 3230B_RTN01. 5.Enable GE1 for patching BBU , EPLA and service cross connect. 6.Migrate traffic to new link (1603C,1185C). 7.Decom existing SM link. FE_1605B 1.Install new 18G_DP_1.2m(MDD). 2.Install new XMC_5D-2+0, Sub_A_Lo. 3.Install RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 4.Create Inband DCN and Enable GE1 connect to Ibeam. 5.Enable EPLA and service cross connect. 6.decom existing SM link. | Swap existing to 18G_2+0_112M Site impacted : 1603C,1185C,3230B NE_3230B 1.Install new 18G_DP_0.6m(MDD). 2.Install new XMC_5D-2+0 , Sub_A_Hi. 3.Reuse existing 3230B_RTN01. 4.Instal new 3_ISM8-2+0 into existing 3230B_RTN01. 5.Enable GE1 for patching BBU , EPLA and service cross connect. 6.Migrate traffic to new link (1603C,1185C). 7.Decom existing SM link. | Swap existing to 18G_2+0_112M Site impacted : 1603C,1185C,3230B FE_1605B 1.Install new 18G_DP_1.2m(MDD). 2.Install new XMC_5D-2+0, Sub_A_Lo. 3.Install RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 4.Create Inband DCN and Enable GE1 connect to Ibeam. 5.Enable EPLA and service cross connect. 6.decom existing SM link. | [5 empty] | GCI | SQ202503270731-GCI | GCI | SQ202501210455-GCI // SQ202504150088-GCI | 2025-03-05 | 2025-03-04 | Completed | 2025-01-18 | 2025-01-18 | 2025-01-31 | 2025-01-31 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-04 | 2025-03-05 | 2025-03-04 | 2025-03-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010846 |  | 2025-01-09 | 2025-01-08 | Completed | 2025-01-08 | 2025-01-09 | 2025-01-08 | 2025-01-08 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-18 | 2025-01-25 | 2025-01-17 | 2025-02-05 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-01-18 | 2025-01-25 | 2025-01-17 | 2025-02-05 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-01-19 | 2025-01-19 | 2025-01-19 | 2025-01-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-01-19 | 2025-01-18 | 2025-01-25 | 2025-01-17 | 2025-01-27 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-01-18 | 2025-01-25 | 2025-01-17 | 2025-01-18 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | CHEONG/SENG/WAH/7018000306
4457C-4939C | Pekan Gurney | DU00003874303 | Northern | Perak | 4.224830 | 100.738505 |  | JUL 24 | [5 empty] | 00. Integrated/RFS Done | 26/7: D2: Cutover done. Post-CO T/shooting WIP 25/7: MOS & TI In Plan | TSS+AA+TI | L1+ATP+PAC | 18G 1+0 1.2m/1.2m XMC3E NE: 1) 1x18GHz XMC3E Sub B Lo 2) 1x18GHz 1.2m SP FE: 1) 1x18GHz XMC3E Sub B Hi 2) 1x18GHz 1.2m SP 3) 1xCat6 cable | MW Parallel Link | Existing link 4457C-4939C 4+0 (4457C RTN01-4939C RTN02) Add parallel link 1+0 112MHz to existing 4+0 link Patch 2nd port at 4939C RTN02 to CP port and create LAG Final config will be 5+0 Impact sites: 4412D NE (4457C) 1. Install new link at RTN01 7-ISM8-1 2. Create EPLA 5+0 FE (4939C) 1. Install new link at RTN02 7-ISM8-1 2. Create EPLA 5+0 3. Patch GE2 to new IBEAM port 4. Create LAG | [7 empty] | GCI | SQ202408220943-GCI | GCI | SQ202408080062-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24072008 |  | 2024-07-22 | 2024-07-23 | Completed | 2024-07-21 | 2024-07-22 | 2024-07-21 | 2024-07-23 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-25 | 2024-07-31 | 2024-07-24 | 2024-08-06 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2024-07-25 | 2024-07-31 | 2024-07-24 | 2024-09-23 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-07-25 | 2024-07-31 | 2024-07-24 | 2024-08-05 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | 2025-07-07: 2024-07-25; 2025-07-07: 2024-07-31; 2025-07-07: 2024-07-24; 2025-07-08: 2024-07-25 |  |  | 2024-09-09 | 2024-10-09 | 2024-09-09 | 2024-09-09 | ASTI//GANIS PUTRIANI/6237001358
2038B-1082A | North Klang Industrial (Celcom) | DU00003874304 | Central | Selangor | 3.007073 | 101.374473 | WK09 | APR 25 | WK12 | APR 25 | TI | RSL -42 due to FE antenna install a bit low (Space constrain) | ZTE | 00. Integrated/RFS Done | 14/4/2025 : RSL not yet done due to need move up antenna or re-route 28/2/2025 : Installation complete, alignment WIP 27/2/2025 : Plan install NE and FE site - CRQ approved, cancel proceed due to team not receive keys 10/2/2025 : CELCOM (M) - 50M Tower - NE site 2038B North Klang Industrial (Celcom), Digi OB - 45M 3 Legged Tower - FE site 1082A West Port Lot 5692 23/9: Pending Site BoM | TSS+AA+TI | L1+ATP+PAC | Parallel link 15G_4+0_28M_CA with existing 13G_2+0 56MHz. NE_2038B 1. 15G_DP 1.2m ant. 2. ISM8 x2. 3. XMC_5D , Sub A_Lo x 1. FE_1082A 1. 15G_DP 1.2m ant. 2. RTN910AF x 1 (IDU) 3. ISM8 x 2. 4. XMC_5D , Sub A_Hi x 1. | MW Parallel Link | Existing link 13G_2+0_28Mhz. Parallel link 15G_4+0_28M_CA with existing 13G_2+0 56MHz with EPLA. Site Impacted: 2038B. NE_2038B 1.Install new 15G_DP 1.2m ant. 2.Install new 3_ISM8 & 4_ISM8 on existing RTN to configure 4+0 CA. 3.Install 2xXMC_5D , Sub A ODU for respective V&H channels. 4.Apply EPLA FE_1082A_RTN_08 1.Install new 15G_DP 1.2m ant. 2.Install new RTN910AF. 3.Install new 3_ISM8 & 4_ISM8 to configure 4+0 CA. 4.Install 2xXMC_5D , Sub A ODU for respective V&H channels. 5.Transfer existing 13G_2+0 IF cable to new 7_ISM8-1&2. 6.Apply EPLA 7.Remove existing 3_ISV3 & 4_ISV3 boards at RTN_08. | [7 empty] | Datasco | SQ202411140206-Datasco | Datasco | SQ202411150529-Datasco // SQ202504260127-Datasco |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25022019 | 15G 1.2/1.2 MDD 4+0 Sub A. wip 15G 1.2 MDD antenna ⏸️ | 2025-02-21 | 2025-02-25 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-03-10 | Muhammad//Shahbaz/7019000128 | Datasco TI | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2026-03-18 | Muhammad//Shahbaz/7019000128 | Datasco TI | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | MUHAMMAD AIMAN SYAKIR BIN AZMAN7019000150 | Datasco TI |  | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2026-03-18 | Muhammad//Shahbaz/7019000128 | 2025-07-07: 2025-02-26; 2025-07-07: 2025-02-26; 2025-07-07: 2025-02-26; 2025-07-08: 2025-02-28 |  |  | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
9279A-9236A | TM Jalan Glumbia | DU00003874305 | Sarawak | Sarawak | 1.232613 | 111.462348 |  |  | WK32-WK35 | AUG 24 |  |  |  | 03. TSS Only |  | TSS |  | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz 0.6m SP FE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz 0.6m SP | MW Swap | Existing link NEC 9279A_GLB-9236A_HLR-01 Swap existing NEC 28MHz with Huawei 112MHz. Reuse same channel Impact sites: 9279A NE (9279A) 1. Install new RTN910A 2. Install new link at RTN01 7-ISM8 (to reuse existing NEC channel) 3. Cutover traffic to new link FE (9236A) 1. Add ISM8 card RTN01 slot 3 2. Install new link at RTN01 3-ISM8-1 3. Cutover traffic to new link 4. Reconfigure DCN for NEC root NE at IDU 9236A_SAQ-9264A_HHT-01 and patch to RTN01 GE1 | [13 empty] | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [7 empty] | 2025-03-11 | 2025-03-11 | 2025-07-21 | 2025-07-21 | Shahid//Nadeem/7019000100 | Datasco TI | [7 empty] | 2025-03-11 | 2025-03-11 | 2025-07-21 | 2025-07-21 | Wong Ching Chai7019000072 | 2025-07-07: 2024-09-03; 2025-07-07: 2024-09-30; 2025-07-07: 2025-03-10; 2025-07-08: 2025-03-10
P00712-P00606 | P032A_P00712OD_CRESCENTIA_PARK | DU00003874306 | Northern | Penang | 5.261111 | 100.421667 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 21/11: CO in plan 20/11: D2: Link ready, pending BBU swap 19/11: MOS & TI In plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Swap existing link to 18G_2+0_112Mhz. NE_P00712. 1.Install new 18G_DP_0.6m x1. 2.Install new RTN910A x1. 3.Install new XMC_5D. Sub_B_Lo x1. FE_P00606. 1.Install new 18G_DP_0.6m x1. 2.Install new RTN910A x1. 3.Install new XMC_5D. Sub_B_Hi x1. | MW Swap | Existing link 18G_1+0_56Mhz.No license support 112M. Swap existing SM link to 18G_2+0_112Mhz. Site Impacted:P00712 & P00606. NE_P00712. 1.Install new 18G_DP_0.6m. 2.Install new RTN910A, 7-ISM8-2+0. 3.Install new XMC_5D-2+0, Sub_B_Lo. 4.Config 112M_2+0. 5.Decom existing SM link. FE_P00606. 1.Install new 18G_DP_0.6m. 2.Install new RTN910A, 7-ISM8-2+0. 3.Install new XMC_5D-2+0, Sub_B_Hi. 4.Config 112M_2+0. 5.Enable GE port 1 connect Fiber Cisco. 6.Create new In-Band DCN and service cross connect. 7.Decom existing SM link. | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202411150562-GCI // SQ202504150095-GCI | 2024-11-29 | 2024-11-29 | Completed | 2024-11-19 | 2024-11-19 | 2024-11-21 | 2024-11-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24110812 |  | 2024-11-09 | 2024-11-18 | Completed | 2024-11-08 | 2024-11-09 | 2024-11-08 | 2024-11-18 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-19 | 2024-11-30 | 2024-11-19 | 2024-11-21 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-11-19 | 2024-11-30 | 2024-11-19 | 2024-11-21 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-11-19 | 2024-11-30 | 2024-11-19 | 2024-11-23 | SAFUAN//BIN YUSOFF/6800000178 | 2024-11-19 | 2024-11-30 | 2024-11-19 | 2024-11-22 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
A00088-A00134 | A042A_A00088OD_SGBAYOR | DU00003874307 | Northern | Perak | 5.249910 | 100.780110 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Integrated/RFS Done |  |  | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU | TSS+AA+TI | L1+ATP+PAC | Install Parallel link 13G_6+0_28M NE_4791B/A00088. 13G_DP_1.2M(MDD) x2. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Lo & Sub B_Lo x2. FE_A00134. 13G_DP_1.2M(MDD) x2. RTN910A x1. 3ISM8 x2. XMC_5D , Sub A_Hi & Sub B_Hi x2. | MW Parallel Link | Existing link 13G_4+0_XPIC Install Parallel link 13G_6+0_28M Site Impacted : 4719B/A00088 , A01154. NE_4791B/A00088 1.Install new 2 x 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7-ISM8-2+0. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Lo & Sub B_Lo for ant 1 and ant 2 respectively. 5.Create service cross connect and EPLA for 6+0 link. 6.Enable GE1 , traffic 4791B/A00088_BBU migrate to new parallel link 6+0. 7.No decom existing MW link due to support A01154. FE_A00134. 1.Install new 2 x 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Hi & Sub B_Hi for ant 1 and ant 2 respectively. 5.Create service cross connect and EPLA for 6+0 link. 6.Create new In Band DCN. 7.Enable GE1 , ETH patching to Fiber PTN (Gi0/2/5). 8.No decom existing MW link due to support A01154. | Existing link 13G_4+0_XPIC Install Parallel link 13G_6+0_28M Site Impacted : 4719B/A00088 , A01154. NE_4791B/A00088 1.Install new 2 x 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7-ISM8-2+0. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Lo & Sub B_Lo for ant 1 and ant 2 respectively. 5.Create service cross connect and EPLA for 6+0 link. 6.Enable GE1 , traffic 4791B/A00088_BBU migrate to new parallel link 6+0. 7.No decom existing MW link due to support A01154. | Existing link 13G_4+0_XPIC Install Parallel link 13G_6+0_28M Site Impacted : 4719B/A00088 , A01154. FE_A00134. 1.Install new 2 x 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Hi & Sub B_Hi for ant 1 and ant 2 respectively. 5.Create service cross connect and EPLA for 6+0 link. 6.Create new In Band DCN. 7.Enable GE1 , ETH patching to Fiber PTN (Gi0/2/5). 8.No decom existing MW link due to support A01154. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GTSB | SQ202504210272-GTSB | GTSB | SQ202503200272-GTSB // SQ202503200273-GTSB // SQ202504260178-GTSB // SQ202505140375-GTSB | 2025-12-04 | 2025-12-03 | Completed | 2025-06-19 | 2025-07-03 | 2025-06-19 | 2025-06-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-09 | 2025-05-24 | 2025-05-09 | 2025-05-09 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022662 |  | 2025-02-27 | 2025-03-07 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-03-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-10-13 | KUNNASILAN A/L PANNIRSELVEM6800000137 | GTSB TI | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-06-13 | KUNNASILAN A/L PANNIRSELVEM6800000137 | GTSB TI | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-14 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-14 | KUNNASILAN A/L PANNIRSELVEM6800000137 | 2025-07-07: 2025-03-05; 2025-07-07: 2025-03-05; 2025-07-07: 2025-03-05; 2025-07-08: 2025-03-06 |  |  | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | CHEONG/SENG/WAH/7018000306
A01179-A00834 | eMOS SRI GANDA OIL MILL | DU00003874308 | Northern | Perak | 3.913389 | 101.199110 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | ( A01179 same link with Y00029 , link ID NT06178=NT05113) Follow TX Rollout Solution Y00029-A00834-A00553 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
B01017-W00320 | CASAVISTA CONDO | DU00003874309 | Central | Selangor | 3.138510 | 101.665110 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Cancel / Drop | Link already decom | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed due to link already decom 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S00468-S01442 | S106A_S00468OD_CB_TAGASAN | DU00003874310 | Sabah | Sabah | 4.414137 | 118.522111 |  |  |  |  | Pending TSS | MwAntenna HW-15G_1.2M_Dual Polarization_A15D12MDD-3NX | ZTE | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU | TSS+AA+TI | L1+ATP+PAC | 15G 4+0 1.2m/1.2m MDD XMC5D sub B NE: 1) 2 x ISM8 cards 2) 1 x 15G XMC5D sub B Hi 3) 1 x 15G 1.2m MDD FE: 1) 2 x ISM8 cards 2) 1 x 15G XMC5D sub B Lo 3) 1 x 15G 1.2m MDD | MW Parallel Link | MW link SB03008 8+0 congest. To install parallel 4+0 CA and create 2+0 link NE (S00468): 1) Install new ISM8 card at existing RTN950A SB03008 S00468 TAGASAN slot 1 and 2 2) Install new 4+0 CA link at 1-ISM8 and 2-ISM8 3) Create 12+0 EPLA+ FE (S01442): 1) Install new ISM8 card at existing RTN950A SB03008 S01442 KG SUNGAI BUAYA slot 1 and 2 2) Install new 4+0 CA link at 1-ISM8 and 2-ISM8 3) Create 12+0 EPLA+ | NE (S00468): 1) Install new ISM8 card at existing RTN950A SB03008 S00468 TAGASAN slot 1 and 2 2) Install new 4+0 CA link at 1-ISM8 and 2-ISM8 3) Create 12+0 EPLA+ | FE (S01442): 1) Install new ISM8 card at existing RTN950A SB03008 S01442 KG SUNGAI BUAYA slot 1 and 2 2) Install new 4+0 CA link at 1-ISM8 and 2-ISM8 3) Create 12+0 EPLA+ | XMC5D | MDD | 15G | 1.2m | 1.2m | NR services | SQ202502260432-NR Services | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services |  |  | Ongoing | 2025-02-26 | 2025-03-04 | 2025-09-28 | 2025-09-28 | MUHD//KHAIRUL NIZAM/7023000104 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25090211 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-25 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-26 | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-10-09 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2025-07-07: 2025-09-19; 2025-07-07: 2025-10-19; 2025-07-07: 2025-09-19; 2025-07-08: 2025-09-19 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016
Q01402-Q00250 | Q118B_Q01402OD_TMNPERTANIAN | DU00003874311 | Sarawak | Sarawak | 3.213240 | 113.150890 | [7 empty] | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
B01106-B00621 | KGSGMERAP | DU00003874312 | Central | Selangor | 2.905110 | 101.724710 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Cancel / Drop | Site has been decom | ZTE | 00. Site Out/Drop | 30/10: OSS update site already dismantle. Not proceed swap 30/10: DO released, pending collection |  |  | Swap existing link to 18G_1+0_112Mhz due to existing link software upgrade not supported. NE 1.Install new SP18G_0.6m x1. 2.Install new RTN910A x1. 3.Install new XMC_3E_1+0, Sub A_Lo x1. FE 1.Install new SP18G_0.6m x1. 2.Install new RTN910A x1. 3.Install new XMC_3E_1+0, Sub_A_Hi x1. | Cancel / Drop | Existing link 18G_1+0_56Mhz. Swap existing 18G_1+0_56Mhz to 18G_1+0_112M due to existing link license not supported. Site Impacted:B01106/B02842 , B00621. NE 1.Install new SP 18G_0.6m. 2.Install new RTN910A, 7-ISM8-1+0. 3.Install new XMC_3E_1+0, Sub ( A)_Lo 4.Config 112M_1+0. 5.Migrate traffic to new link. 6.Decom existing SM link. FE 1.Install new SP18G_0.6m. 2.Install new RTN910A, 7-ISM8-1+0. 3.Install new XMC_3E_1+0,Sub (A)_Hi 4.Config 112M_1+0. 5.Enable GE port 1 connect Fiber_Cisco. 6.Create new In-Band DCN and service cross connect. 7.Decom existing SM link. | [7 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24103027 |  | 2024-10-31 |  | Ongoing | 2024-10-30 | 2024-10-31 | 2024-10-30 |  | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing
Q01788_HU | KG MERANEK | DU00003874313 | Sarawak | Sarawak | 1.443650 | 110.460410 |  | FEB 25 | [5 empty] | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU | TSS |  |  | MW Swap | MW SWAP Q01709-Q00930 WITH 23G_1+0_0.6/0.6_SP_SB A NE: 1. Swap SM IDU with RTN910A. 2. Swap exisitng SM ODU with XMC-3_SB A. 3. Swap existng antenna with 0.6m HW antenna. 4. Configure 23G_1+0_0.6/0.6_SP 5. Dismantle SM link. FE: 1. Swap SM IDU with RTN910A. 2. Swap exisitng SM ODU with XMC-3_SB A. 3. Swap existng antenna with 0.6m HW antenna. 4. Configure 23G_1+0_0.6/0.6_SP 5. Dismantle SM link. | [7 empty] | Trintel | SQ202503190741-Trintel |  |  | 2025-03-14 | 2025-03-12 | Completed | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-12 | 2025-03-14 | 2025-03-12 | 2025-03-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-12 | 2025-03-14 | 2025-03-12 | 2025-03-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-12 | 2025-03-14 | 2025-03-12 | 2025-03-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506160770-GTSB | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | HSU//MYET CHAE/6799000011
4261B-4678A | TUALANG | DU00003898370 | Northern | Kedah | 6.117703 | 100.476047 |  |  |  | JUL 24 |  |  |  | 00. Integrated/RFS Done | 17/7: D3: Cutover done 16/7: D2: TI WIP 15/7: D1: MOS & TI In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G 2+0 1.2m/1.2m DP NE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Hi 3) 1x15GHz XMC3 Sub B Hi 4) 1x15GHz 1.2m DP FE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Lo 3) 1x15GHz XMC3 Sub B Lo 4) 1x15GHz 1.2m DP | MW Swap | Existing link 4261B-4678A 3+0 (4261B RTN03-4678A RTN14) EPLA 15G 2+0 and 15G 1+0. Swap existing 15G 1+0 (4261B-4678A-01) to 15G 2+0 Final config will be 4+0 Impact sites: 4261B,4260B,4979B,4049R NE (4261B) 1. Replace ISV3 at 4261B RTN03 slot 3 with ISM8 card 2. Swap 15G SP with 15G DP 3. Reuse existing channel for V 4. New channel for H 5. Create 4+0 EPLA FE (4678A) 1. Replace ISV3 at 4678A RTN14 slot 3 with ISM8 card 2. Swap 15G SP with 15G DP 3. Reuse existing channel for V 4. New channel for H 5. Create 4+0 EPLA | [7 empty] | GCI | SQ202408220943-GCI | GCI | SQ202408080062-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2024-07-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-23 | 2024-07-23 | 2024-07-23 | 2024-07-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071003 |  | 2024-07-11 | 2024-07-13 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-15 | 2024-07-31 | 2024-07-15 | 2024-08-08 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-07-15 | 2024-07-31 | 2024-07-15 | 2024-08-08 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-17 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-07-15 | 2024-07-31 | 2024-07-15 | 2024-07-19 | HIMAN//BIN ADAM/6800000183 | 2024-07-15 | 2024-07-31 | 2024-07-15 | 2024-07-17 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | NG HONG JIE7018000036 | Logistic Team | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507080524-GCI | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | CHEONG/SENG/WAH/7018000306
7937A-7935A_1 | Ladang Giram | DU00003898371 | Sabah | Sabah | 4.597610 | 118.190610 |  |  | WK32-WK35 | AUG 24 |  |  |  | 00. Integrated/RFS Done | 7/11: Cutover done. Post-CO T/S ongoing 6/11: MOS & Pre-installation in progress | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | N/A | MW Hardware Upgrade | Existing link 7937A-7935A 2+0 (7937A RTN03-7935A RTN05) Existing link 7937A-7935A 4+0 CA (7937A RTN06-7935A RTN07) To combine both links in 1 IDU and create EPLA 6+0 Impact site: 7691B, 7937A NE (7937A) 1. Transfer IF cable from RTN03 2-ISM8-1 to RTN06 7-ISM8-1 2. Transfer IF cable from RTN03 2-ISM8-2 to RTN06 7-ISM8-2 3. Create 6+0 EPLA 4. Remain BBU 7937A at RTN06 GE1 5. Patch RTN02 GE1 to RTN06 GE2 6. RTN03 will not carry any traffic. Can decom (if required) FE (7935A) 1. Transfer IF cable from RTN05 4-ISM8-1 to RTN07 7-ISM8-1 2. Transfer IF cable from RTN05 4-ISM8-2 to RTN07 7-ISM8-2 3. Create 6+0 EPLA 4. Remove IDU cascade RTN07-RTN06 5. Patch RTN07 GE1 to CP port GE 0/2/27 6. Migrate 7937A from GE0/2/26 to GE0/2/27 7. Reconfigure DCN from RTN05 to RTN07 8. RTN05 will not carry any traffic. Can decom (if required) | [7 empty] | NR services | SQ202411140353-NR Services | NR services | SQ202411120063-NR Services // SQ202504260199-NR Services | 2025-01-05 | 2025-01-05 | Completed | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-05 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-08 | 2024-11-15 | 2024-11-08 | 2024-11-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-08 | 2024-11-15 | 2024-11-08 | 2024-11-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-20 | 2024-11-22 | 2024-11-20 | 2024-11-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241024AI |  | 2024-10-25 | 2024-11-01 | Completed | 2024-10-24 | 2024-10-25 | 2024-10-24 | 2024-11-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-06 | 2024-11-30 | 2024-11-06 | 2024-11-08 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-11-06 | 2024-11-30 | 2024-11-06 | 2024-11-23 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | SYRIL//ALFIJI BIN SUHININ/6798000106 |  |  | 2024-11-06 | 2024-11-30 | 2024-11-06 | 2024-11-21 | RALPH O'BRYAN HILARY7167000030 | 2024-11-06 | 2024-11-30 | 2024-11-06 | 2024-11-09 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | tseping//wang/6819000006 | Logistic Team | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
4265B-4770A | Bandar Putri Jaya 2 | DU00003898372 | Northern | Kedah | 5.607045 | 100.528034 |  |  |  | JUL 24 |  |  |  | 00. Integrated/RFS Done | 15/7: D1: Cutover done 10/7: DO ready, collection in plan | TSS+AA+TI | L1+ATP+PAC | 15G 2+0 0.6m/1.2m DP NE: 1) 1xRTN910A 2) 1xISM8 card 2) 1x15GHz XMC3 Sub A Lo 3) 1x15GHz XMC3 Sub B Lo 4) 1x15GHz 0.6m DP FE: 1) 1xRTN910A 2) 1xISM8 card 2) 1x15GHz XMC3 Sub A Lo 3) 1x15GHz XMC3 Sub B Lo 4) 1x15GHz 0.6m DP | MW Parallel Link | Existing link 4265B-4770A 2+0 (4265B RTN02-4770A RTN12) Swap IDU to use CSHRF Add parallel 2+0 Final config will be 4+0 Impact site: 4265B NE (4265B) 1. Swap RTN02 with new RTN910AF 2. Add ISM8 at RTN02 slot 3 3. Transfer existing 2+0 link to RTN02 7-ISM8 4. Install new 2+0 link at RTN02 3-ISM8 5. Create 4+0 EPLA FE 1. Swap RTN12 with new RTN910AF 2. Add ISM8 at RTN12 slot 3 3. Transfer existing 2+0 link to RTN12 7-ISM8 4. Install new 2+0 link at RTN12 3-ISM8 5. Create 4+0 EPLA | [7 empty] | GCI | SQ202408220943-GCI | GCI | SQ202408080062-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071004 |  | 2024-07-11 | 2024-07-13 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-15 | 2024-07-30 | 2024-07-15 | 2024-07-16 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-07-15 | 2024-07-30 | 2024-07-15 | 2024-07-16 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-07-15 | 2024-07-30 | 2024-07-15 | 2024-07-16 | SAFUAN//BIN YUSOFF/6800000178 | 2025-07-07: 2024-07-15; 2025-07-07: 2024-07-30; 2025-07-07: 2024-07-15; 2025-07-08: 2024-07-15 |  |  | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
1162A-1153A | Kg Baru Tiram Buruk | DU00003898373 | Central | Selangor | 3.426790 | 101.242702 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 17/7: D4: Cutover done 16/7: D3: TI done, alignment WIP 13/7: D1: MOS & TI In Plan | TSS+AA+TI | L1+ATP+PAC | 15G 2+0 1.2m/1.2m DP NE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Lo 3) 1x15GHz XMC3 Sub B Lo 4) 1x15GHz 1.2m DP FE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Hi 3) 1x15GHz XMC3 Sub B Hi 4) 1x15GHz 1.2m DP | MW Parallel Link | Existing link 1162A-1153A 4+0 (1162A RTN01-1153A RTN07) Add parallel 2+0 Final config will be 6+0 Impact site: 1162A NE (1162A) 1. Add ISM8 at RTN01 slot 4 2. Install parallel 2+0 link 3. Create 6+0 EPLA FE (1153A) 1. Add ISM8 at RTN07 slot 4 2. Install parallel 2+0 link 3. Create 6+0 EPLA | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202408080495-MTK | 2024-09-20 | 2024-09-19 | Completed | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-08 | 2024-08-09 | 2024-08-08 | 2024-08-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-08 | 2024-08-09 | 2024-08-08 | 2024-08-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24071011 |  | 2024-07-11 | 2024-07-12 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-12 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-13 | 2024-07-31 | 2024-07-13 | 2024-08-01 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-07-13 | 2024-08-01 | 2024-07-13 | 2024-08-01 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-17 | SHUJAAT//ALI/6800000124 |  |  | 2024-07-13 | 2024-07-31 | 2024-07-13 | 2024-07-18 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-07-07: 2024-07-13; 2025-07-07: 2024-07-31; 2025-07-07: 2024-07-13; 2025-07-08: 2024-07-19 |  |  | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
9262A_IPR | SESCO Serian | DU00006468238 | Sarawak | Sarawak | 1.171995 | 110.566047 | [9 empty] | TSS+TI |  | IPRAN port upgrade to 10G at 9262A. NE_9262A New SFP Module 10G with 10Km 1310nm or equivalent as per ZTE IPRAN advise on the length required x1(For ZTE RAN). New Optical Patch Cord cable x1 with suitable type and length. | BBU Patching | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 9262A. Site Impacted : 9262A. NE_9262A 1.Insert new suitable SFP Module 10G into port 10G RAN. Enable it. 2.Patching new Optical Patch Cord cable to port 10G RAN and Sacofa eqpt. 3.Request new xD Vlan Services. | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 9262A. Site Impacted : 9262A. NE_9262A 1.Insert new suitable SFP Module 10G into port 10G RAN. Enable it. 2.Patching new Optical Patch Cord cable to port 10G RAN and Sacofa eqpt. 3.Request new xD Vlan Services. | [6 empty] | Trintel | SQ202601210184-Trintel | Trintel | SQ202601160550-Trintel |  |  | Ongoing | 2026-01-16 | 2026-01-31 | 2026-01-16 | 2026-01-20 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26011211 |  | 2026-01-13 | 2026-01-16 | Completed | 2026-01-12 | 2026-01-13 | 2026-01-12 | 2026-01-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-23 | ALVIN TAY KAI SENG7667000030 | Trintel TI | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | ALVIN TAY KAI SENG7667000030 | Trintel TI | [7 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | ALVIN TAY KAI SENG7667000030 | 2025-07-07: 2026-01-15; 2025-07-07: 2026-01-15; 2025-07-07: 2026-01-15; 2025-07-08: 2026-01-17 | [7 empty] | GTSB | SQ202601070342-GTSB
7286A_AD | Alam Mesra | DU00006468239 | Sabah | Sabah | 6.033280 | 116.130648 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x1. | BBU Patching | BBU Patching to 7286A_RTN01_GE6 ( ID : 29216). Site Impacted : 7286A , 7018L , 7085B. NE_7286A 1.Transfer 7286A_BBU from 7286A_RTN02_GE2 to 7286A_RTN01_GE6. 2.Create cross connect. 3.Disable unused GE port. | BBU Patching to 7286A_RTN01_GE6 ( ID : 29216). Site Impacted : 7286A , 7018L , 7085B. NE_7286A 1.Transfer 7286A_BBU from 7286A_RTN02_GE2 to 7286A_RTN01_GE6. 2.Create cross connect. 3.Disable unused GE port. | [6 empty] | NR services | SQ202601220792-NR Services | NR services | SQ202601220785-NR Services | 2026-02-03 | 2026-02-04 | Completed | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011632 |  | 2026-01-17 | 2026-01-20 | Completed | 2026-01-16 | 2026-01-17 | 2026-01-16 | 2026-01-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-01-30 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-01-30 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-30 | 2026-01-30 | 2026-02-28 | 2026-01-30 | 2026-02-10 | LEONARD//EDUAN/6000038538 | 2025-07-07: 2026-01-30; 2025-07-07: 2026-02-28; 2025-07-07: 2026-01-30; 2025-07-08: 2026-01-30 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512241128-GCI | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-26 | CHEONG/SENG/WAH/7018000306
S01974_AD | KAMPUNG SINAR BARU SANDAKAN | DU00006468240 | Sabah | Sabah | 5.937350 | 117.953670 | [7 empty] | 01. Pending Planning |  | TSS+AA+TI+Dismantle |  | 18G_1+0_112M. NE_S01974 18G_1+0_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub B_Hi x1. FE_7455B 18G_1+0_1.2M(MAC) x1. RTN910A x1. XMC_3E , Sub B_Lo x1. 10G SFP Module x2. Fiber patch cord x 1 pairs. | MW New Link / Reroute | Existing link 18G_1+0_112M reroute to new FE 7455B due to exiting fiber site (S00171) will be decom. (7455B pair site with S00662). New link config 18G_1+0_112M. Site Impacted : S01974. NE_S01974 1.Install new 18G_1+0_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect. 5.Migrate traffic to new link. 6.Decom existing MW link. FE_7455B 1.Install new 18G_1+0_1.2M(MAC). 2.Reuse existing 7455B_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0 4.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect & transfer to 10 Port. 6.Migrate traffic to new link. 7.Decom existing MW link. | Existing link 18G_1+0_112M reroute to new FE 7455B due to exiting fiber site (S00171) will be decom. (7455B pair site with S00662). New link config 18G_1+0_112M. Site Impacted : S01974. NE_S01974 1.Install new 18G_1+0_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect. 5.Migrate traffic to new link. 6.Decom existing MW link. | Existing link 18G_1+0_112M reroute to new FE 7455B due to exiting fiber site (S00171) will be decom. (7455B pair site with S00662). New link config 18G_1+0_112M. Site Impacted : S01974. FE_7455B 1.Install new 18G_1+0_1.2M(MAC). 2.Reuse existing 7455B_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0 4.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect & transfer to 10 Port. 6.Migrate traffic to new link. 7.Decom existing MW link. | XMC_3E | MAC | 18G | 0.6 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202603270343-GCI | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | CHEONG/SENG/WAH/7018000306
9158A_IPR | SarikeiHospital(SACOFA) | DU00006468241 | Sarawak | Sarawak | 2.131453 | 111.485124 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9158A. NE_9158A New SFP Module 10G with 10Km 1310nm or equivalent as per ZTE IPRAN advise on the length required x1(For ZTE RAN). New Optical Patch Cord cable x1 with suitable type and length. | BBU Patching | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 9158A. Site Impacted : 9158A. NE_9158A 1.Insert new suitable SFP Module 10G into port 10G RAN. Enable it. 2.Patching new Optical Patch Cord cable to port 10G RAN and Sacofa eqpt. 3.Request new xD Vlan Services. | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 9158A. Site Impacted : 9158A. NE_9158A 1.Insert new suitable SFP Module 10G into port 10G RAN. Enable it. 2.Patching new Optical Patch Cord cable to port 10G RAN and Sacofa eqpt. 3.Request new xD Vlan Services. | [6 empty] | Trintel | SQ202601150583-Trintel | Trintel | SQ202601150579-Trintel | 2026-01-31 | 2026-01-30 | Completed | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-14 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011212 |  | 2026-01-13 | 2026-01-16 | Completed | 2026-01-12 | 2026-01-13 | 2026-01-12 | 2026-01-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-26 | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | Trintel TI | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-26 | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | Trintel TI | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-26 | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | 2025-07-07: 2026-01-13; 2025-07-07: 2026-01-13; 2025-07-07: 2026-01-13; 2025-07-08: 2026-01-14 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202601070342-GTSB
9515A_IPR | PasarLutong MP | DU00006468242 | Sarawak | Sarawak | 4.467380 | 114.008570 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP x 2 Fiber Patch Cord x 1 Pair | IDU-IPRAN | NE_9515A_RTN01 1.Install new 10G SFP Module at new sacofa port 10G_ETH 1-2-25 2.Install new 10G SFP Module at 9515A_RTN01_GE3. 3.Patching Fiber patch cord 10G from 9515A_RTN01_GE3 to new sacofa port 10G_ETH 1-2-25. 4.Disconnect existing ETH cable at old Sacofa Ports and disable unused port at RTN and put proper port labelling. 5.Create service cross connect and migrate entire traffic to new sacofa 10G port ETH 1-2-25. 6.Reconfigure the DCN to new port. Site Affected 9515A , 9115K/Q01743 , 9703B , 9161X/Q01279_no traffic. | NE_9515A_RTN01 1.Install new 10G SFP Module at new sacofa port 10G_ETH 1-2-25 2.Install new 10G SFP Module at 9515A_RTN01_GE3. 3.Patching Fiber patch cord 10G from 9515A_RTN01_GE3 to new sacofa port 10G_ETH 1-2-25. 4.Disconnect existing ETH cable at old Sacofa Ports and disable unused port at RTN and put proper port labelling. 5.Create service cross connect and migrate entire traffic to new sacofa 10G port ETH 1-2-25. 6.Reconfigure DCN to new port. Site Affected 9515A , 9115K/Q01743 , 9703B , 9161X/Q01279_no traffic. | [6 empty] | Trintel | SQ202601210184-Trintel | Trintel | SQ202601210180-Trintel | 2026-01-28 | 2026-01-27 | Completed | [8 empty] | Unassigned | Disabled |  | 2026-01-27 | 2026-01-28 | 2026-01-27 | 2026-01-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-01-28 | 2026-01-27 | 2026-01-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-01-28 | 2026-01-27 | 2026-01-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011213 |  | 2026-01-13 | 2026-01-16 | Completed | 2026-01-12 | 2026-01-13 | 2026-01-12 | 2026-01-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-26 | 2026-01-31 | 2026-01-26 | 2026-01-26 | Fiona Wan Yen Chin7667000028 | Trintel TI | 2026-01-26 | 2026-01-31 | 2026-01-26 | 2026-01-26 | Fiona Wan Yen Chin7667000028 | Trintel TI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-26 | 2026-01-26 | 2026-01-31 | 2026-01-26 | 2026-01-26 | Fiona Wan Yen Chin7667000028 | 2025-07-07: 2026-01-26; 2025-07-07: 2026-01-31; 2025-07-07: 2026-01-26; 2025-07-08: 2026-01-26 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202601070323-GCI | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | CHEONG/SENG/WAH/7018000306
K01057_AD | KGSGKECIK | DU00006468243 | Northern | Kedah | 6.417100 | 100.490000 | [7 empty] | 06. Other Issue | 13/3: Pending MOCN | TSS+TI |  | ETH Cat 6 Cable x 1 | MW IDU Patching | FE_K00122/4995A. 1.IDU Patching to 4995A Fiber Ibeam Port ( Port Assign By Ops Team) 2. IBeam 4995A-MAC-001 |  | FE_K00122/4995A. 1.IDU Patching to 4995A Fiber Ibeam Port_4995A-MAC-001. ( Port Assign By Ops Team) | [5 empty] | GTSB | SQ202602230050-GTSB | GTSB | SQ202602230045-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022316 |  | 2026-02-24 | 2026-02-26 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-26 | 2026-02-28 | 2026-02-25 |  | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2026-02-26 | 2026-02-28 | 2026-02-25 |  | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | [7 empty] | 2026-02-26 | 2026-02-28 | 2026-02-25 |  | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2025-07-07: 2026-02-26; 2025-07-07: 2026-02-28; 2025-07-07: 2026-02-25; 2025-07-08: 2026-02-27 | [7 empty] | GCI | SQ202601070319-GCI | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-21 | CHEONG/SENG/WAH/7018000306
S01812_EB | PI KAMPUNG WONOD | DU00006468244 | Sabah | Sabah | 5.659200 | 117.070900 | [7 empty] | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
B02294_AD | B061H_B02294OD_KM18_FEDERAL_HWY | DU00005827295 | Central | Selangor | 3.082188 | 101.578908 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_B02994 23G_DP_0.6M(MAC) + OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. FE_2456A 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. | MW New Link / Reroute | B02294 reroute due to EOS equipment. Site Impacted : B02294 NE_B02994 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new TX route. 6.Decom existing SM link (CT09263). FE_2456A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create new In band DCN. 6.Enable GE1 , ETH cable patching to existing 2456A_RTN02 (ID : 26304) GE2. 7.Traffic migrate to new link and new TX route. 8.Decom existing SM link(CT09263). | B02294 reroute due to EOS equipment. Site Impacted : B02294 NE_B02994 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new TX route. 6.Decom existing SM link (CT09263). | B02294 reroute due to EOS equipment. Site Impacted : B02294 FE_2456A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create new In band DCN. 6.Enable GE1 , ETH cable patching to existing 2456A_RTN02 (ID : 26304) GE2. 7.Traffic migrate to new link and new TX route. 8.Decom existing SM link(CT09263). | [5 empty] | GTSB | SQ202507150625-GTSB | GTSB | SQ202507150631-GTSB // SQ202507150635-GTSB |  |  | Ongoing | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-04 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071553 |  | 2025-07-17 | 2025-07-22 | Completed | 2025-07-16 | 2025-07-17 | 2025-07-16 | 2025-07-22 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-29 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-12-22 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-31 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2026-01-29 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-29 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507190083-GCI | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | CHEONG/SENG/WAH/7018000306
K00416_HU | BATUPUTIHHOTST | DU00005832682 | Northern | Kedah | 5.452100 | 100.633300 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M NE_K00416 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. ISM8 x2. FE_4968A. 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. ISM8 x2. | MW Parallel Link | Install new parallel link 15G_4+0_28M to support child site 4963B. Refer DU ID 4963B_HU (DU Code : DU code : DU00005826245). First priority to install uplink to CP. Site Impacted : 4963B. NE_K00416 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by GOP team). 3.Install new XMC_5D , Sub A_Hi. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , interconnect ETH cable between new RTN910A ( new RTN910A under link K00416-4982A). 7.No decom link. FE_4968A. 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.( RTN no provide by GOP team). 3.Install new XMC_5D , Sub A_Hi. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , CA and EPLA. 6.Create new In band DCN. 7.No decom link. | Install new parallel link 15G_4+0_28M to support child site 4963B. Refer DU ID 4963B_HU (DU Code : DU code : DU00005826245). First priority to install uplink to CP. Site Impacted : 4963B. NE_K00416 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by GOP team). 3.Install new XMC_5D , Sub A_Hi. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , interconnect ETH cable between new RTN910A ( new RTN910A under link K00416-4982A). 7.No decom link. | Install new parallel link 15G_4+0_28M to support child site 4963B. Refer DU ID 4963B_HU (DU Code : DU code : DU00005826245). First priority to install uplink to CP. Site Impacted : 4963B. FE_4968A. 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.( RTN no provide by GOP team). 3.Install new XMC_5D , Sub A_Hi. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , CA and EPLA. 6.Create new In band DCN. 7.No decom link. | XMC_5D | MDD | 15G | 1.2 | 1.2 | GTSB | SQ202508040494-GTSB | GTSB | SQ202507290123-GTSB // SQ202507290125-GTSB | 2025-11-28 | 2025-11-27 | Completed | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071917 |  | 2025-07-20 | 2025-08-09 | Completed | 2025-07-19 | 2025-07-20 | 2025-07-19 | 2025-08-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-31 | 2025-08-18 | 2025-08-23 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-08-18 | 2025-08-31 | 2025-08-18 | 2025-09-03 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-21 | 2025-08-18 | 2025-08-31 | 2025-08-18 | 2025-09-02 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-07-28: 2025-08-18; 2025-07-28: 2025-08-31; 2025-07-28: 2025-08-18; 2025-07-29: 2025-08-23 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507190085-GCI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | CHEONG/SENG/WAH/7018000306
1872A_LOS | Carrefour Subang Jaya | DU00005842626 | Central | Selangor | 3.082928 | 101.588009 | [7 empty] | 00. Integrated/RFS Done | 22/8:Already done LOS survey bro, once material collection done, will plan for installation,Plan Next week | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK REROUTE 1872A-3757B WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3_SUB_B_0.56KM IMPaACTED: 1872A DISMANTLE EXISTING LINK 1872A-1195A | 1. INSTALL NEW RTN910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512AM 5. DISMANTLE EXISTING LINK 1872A-1195A | 1. INSTALL NEW RTN910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512AM 5. DISMANTLE EXISTING LINK 1872A-1195A | XMC | MAC | 23G | 0.6 | 0.6 | GCI | SQ202507160574-GCI | GCI | SQ202508270936-GCI // SQ202508270942-GCI | 2025-11-11 | 2025-11-10 | Completed | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-09-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | 2025-09-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082143 | No 23G_1+0_0.6/0.6 | 2025-08-22 | 2025-08-22 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-03 | 2025-09-10 | 2025-09-02 | 2025-09-04 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-09-03 | 2025-09-10 | 2025-09-02 | 2025-09-09 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-04 | 2025-09-03 | 2025-09-10 | 2025-09-02 | 2025-09-10 | Ragunalan//A/L L.Krisnan6000006720 | 2025-09-03 | 2025-09-10 | 2025-09-02 | 2025-09-05 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507250548-GCI | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
3174B2_LOS_1 | pBTS Precint 11 | DU00005842627 | Central | Selangor | 2.963824 | 101.662050 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M. NE_3174B_2 23G_SP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A_Lo x1. FE_2039A 23G_SP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A_Hi x1. | MW New Link / Reroute | MW link reroute to new FE 2039A due to existing link being LOS Block. Link configuration with 23G_1+0_112M. Site Impacted : 3174B_2. NE_3174B_2 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. (RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic migrate to new link and New FE routing. 6.Decom existing IDU , ODU and ANT. FE_2039A 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and traffic migrate to new FE routing and new link. 5.Enable GE1 , ETH patching to existing 2039A_RTN01_GE2 (ID : 11079). 6.Traffic migrate to new FE routing and new link. 7.Decom existing ODU , ANT. Maintain 2057A_RTN02 ( ID : 42038) to serve for child site 1575B | MW link reroute to new FE 2039A due to existing link being LOS Block. Link configuration with 23G_1+0_112M. Site Impacted : 3174B_2. NE_3174B_2 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. (RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic migrate to new link and New FE routing. 6.Decom existing IDU , ODU and ANT. | MW link reroute to new FE 2039A due to existing link being LOS Block. Link configuration with 23G_1+0_112M. Site Impacted : 3174B_2. FE_2039A 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and traffic migrate to new FE routing and new link. 5.Enable GE1 , ETH patching to existing 2039A_RTN01_GE2 (ID : 11079). 6.Traffic migrate to new FE routing and new link. 7.Decom existing ODU , ANT. 7.Decom existing ODU , ANT. Maintain 2057A_RTN02 ( ID : 42038) to serve for child site 1575B | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202507160574-GCI | GCI | SQ202508270936-GCI // SQ202508270942-GCI | 2025-11-11 | 2025-11-10 | Completed | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-11 | 2025-09-12 | 2025-09-11 | 2025-09-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082186 | No 23G_1+0_0.6/0.6 | 2025-08-22 | 2025-08-25 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-05 | 2025-09-12 | 2025-09-04 | 2025-09-05 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-09-05 | 2025-09-12 | 2025-09-04 | 2025-09-09 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-10 | 2025-09-05 | 2025-09-12 | 2025-09-04 | 2025-09-19 | Ragunalan//A/L L.Krisnan6000006720 | 2025-09-05 | 2025-09-12 | 2025-09-04 | 2025-09-05 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | NG HONG JIE7018000036 | Logistic Team | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507250548-GCI | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | CHEONG/SENG/WAH/7018000306
1906B_POC | Jln Sg Tekali | DU00004271738 | Central | Selangor | 3.106247 | 101.870543 |  |  |  |  | Closed | Under MW POC | ZTE | 00. Integrated/RFS Done | Move to CelcomDigi MW POC | NA | NA |  | Cancel / Drop | [8 empty] | GTSB | No PR required-Under MW POC | GTSB | No PR required-Under MW POC |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2025-01-14 | RONALD SHAN A/L AMBUROSE6800000089
4667B | Kolej Insaniah | DU00005038770 | Northern | Kedah | 6.144085 | 100.358995 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Re-patching BBu at 4667B from xC OB Fiber K00580 to existing MW link 4667B-4469A. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4874A | Finisar Indoor | DU00005038771 | Northern | Perak | 4.674734 | 101.122959 |  |  |  |  | TI IN PLAN | ZTE |  | 02. Pending TP Approval by Site Owner |  | TSS+AA+TI+Dismantle |  | 15G_2+0_28M_CA NE_4874A New 15G_0.6M(MDD) x1. New RTN910A x1. XMC_5D, Sub A_Hi x1. CAT6 cable x1. FE_4496A New 15G_1.2M(MDD) x1. New RTN910A x1. XMC_5D, Sub A_Lo x1. CAT6 cable x1. | MW Swap | Existing SM MW Link 15G_1+0_28M. Swap existing link to new HW 15G_2+0_28M_256QAM_CA. Site Impacted : 4874A. NE_4874A 1.Install new 15G_0.6M(MDD). 2.Install new 1xRTN910A(RTN01). 3.Install new 1x XMC_5D , Sub A_Hi. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Configure DCN Inband and reuse existing Vlan services. 7.Decom existing SM MW Link 15G_1+0_28M. FE_4496A 1.Install new 15G_1.2M(MDD). 2.Install new 1xRTN910A(RTN07). 3.Install new 1x XMC_5D , Sub A_Lo. 4.Enable port 8-EM6-1 of new RTN910A(RTN07). 5.Patching port 8-EM6-1 of new RTN910A(RTN07) to existing port at IBeam . Configure it. 6.Configure DCN Inband and reuse existing Vlan services. 7.Decom existing SM MW Link 15G_1+0_28M. | Existing SM MW Link 15G_1+0_28M. Swap existing link to new HW 15G_2+0_28M_256QAM_CA. Site Impacted : 4874A. NE_4874A 1.Install new 15G_0.6M(MDD). 2.Install new 1xRTN910A(RTN01). 3.Install new 1x XMC_5D , Sub A_Hi. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Configure DCN Inband and reuse existing Vlan services. 7.Decom existing SM MW Link 15G_1+0_28M. | Existing SM MW Link 15G_1+0_28M. Swap existing link to new HW 15G_2+0_28M_256QAM_CA. Site Impacted : 4874A. FE_4496A 1.Install new 15G_1.2M(MDD). 2.Install new 1xRTN910A(RTN07). 3.Install new 1x XMC_5D , Sub A_Lo. 4.Enable port 8-EM6-1 of new RTN910A(RTN07). 5.Patching port 8-EM6-1 of new RTN910A(RTN07) to existing port at IBeam . Configure it. | XMC_5D | MDD | 15G | 15G_0.6M(MDD) | 15G_1.2M(MDD) | NWAVE | SQ202507180759-N-Wave | NWAVE | SQ202508250303-N-Wave // SQ202508250310-N-Wave |  |  | Ongoing | 2025-07-17 | 2025-07-21 | 2025-07-21 | 2025-07-21 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2026-03-04 | 2026-03-04 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-17 | 2026-04-24 | 2026-04-17 | 2026-04-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250320A8 |  | 2025-03-21 | 2025-04-08 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-04-08 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202603170130-GTSB
4590A | NS KM201 NB(MAXIS) | DU00005038772 | Northern | Perak | 4.941552 | 100.671721 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Upgrade plan under NIC DU 4590A DU00002953823 | [13 empty] | Ongoing | 2025-04-23 | 2025-04-23 | 2025-04-23 |  | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Ongoing |  | 2025-04-23 | 2025-04-23 |  |  | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4406D | Puncak Surya | DU00005038773 | Northern | Kedah | 5.627960 | 100.558454 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_4406D New 23G_SP_0.6M(MAC)+OMT x1. New XMC_3E, Sub B_Hi x1. FE_4770A New 23G_SP_1.2M(MAC)+OMT x1. New XMC_3E, Sub B_Lo x1. | MW Swap | Link Existing HW 23G_1+0_56M Swap existing link to new HW 23G_1+0_112M Site Impacted : 4406D NE_4406D 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_3E , Sub B_Hi and terminate new IF/RG8 cable to existing RTN910(RTN01) at slot 07 of ISM8 port 01. 4.Configure DCN Inband. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). FE_4770A 1.Install new 23G_SP_1.2M(MAC)+OMT. 2.Reuse existing RTN910A(RTN17). 3.Install new 1x XMC_3E , Sub B_Lo and terminate new IF/RG8 cable to existing RTN910(RTN17) at slot 07 of ISM8 port 01. 4.Configure DCN Inband. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). 7.Reuse existing port at IBeam. | Link Existing HW 23G_1+0_56M Swap existing link to new HW 23G_1+0_112M Site Impacted : 4406D NE_4406D 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_3E , Sub B_Hi and terminate new IF/RG8 cable to existing RTN910(RTN01) at slot 07 of ISM8 port 01. 4.Configure DCN Inband. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). | Link Existing HW 23G_1+0_56M Swap existing link to new HW 23G_1+0_112M Site Impacted : 4406D FE_4770A 1.Install new 23G_SP_1.2M(MAC)+OMT. 2.Reuse existing RTN910A(RTN17). 3.Install new 1x XMC_3E , Sub B_Lo and terminate new IF/RG8 cable to existing RTN910(RTN17) at slot 07 of ISM8 port 01. 4.Configure DCN Inband. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). 7.Reuse existing port at IBeam. | XMC_3E | MAC | 23G | 23G_SP_0.6M(MAC)+OMT x1. | 23G_SP_1.2M(MAC)+OMT x1. | GCI | SQ202504170476-GCI | GCI | SQ202503280474-GCI // SQ202503280484-GCI // SQ202504150095-GCI // SQ202508140738-GCI | 2025-10-28 | 2025-10-28 | Completed | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022168 |  | 2025-02-22 | 2025-02-25 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-02-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-10 | 2025-03-31 | 2025-03-10 | 2025-04-07 | team7gcitechnicalteam7gcitechnical | GCI TI | 2025-03-10 | 2025-03-31 | 2025-03-10 | 2025-04-09 | team7gcitechnicalteam7gcitechnical | GCI TI | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-25 | 2025-03-10 | 2025-03-31 | 2025-03-10 | 2025-04-07 | team7gcitechnicalteam7gcitechnical | 2025-03-10 | 2025-03-31 | 2025-03-10 | 2025-03-13 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI
4083B | UITM Mara | DU00005038774 | Northern | Penang | 5.383600 | 100.423470 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M_EPLA NE_4083B 18G_DP_1.2M(MAC)+OMT x1. ISM8x1 XMC_3E, Sub A & B_Lo x2. FE_4171A 18G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E, Sub A & B_Hi x2. | MW Swap | Link Existing 18G_1+0_112M_PLA Swap existing link to 18G_2+0_112M_PLA (Due to Old Version IDU) Site Impacted : 4229D & 4627C NE_4083B 1.Install new 18G_DP_1.2M(MAC)+OMT. 2.Insert new 1xISM8 into slot 4 of RTN02. 3.Install XMC_3E , Sub A & B_Lo. 4.Migrate traffic to new link. 5.Decom existing MW link (ODU & Ant). FE_4171A 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Insert new 1xISM8 into slot 3 of RTN02. 3.Install XMC_3E , Sub A & B_Hi. 4.Migrate traffic to new link. 5.Decom existing MW link (ODU & Ant). 6.Request new port at IBeam from ZTE IPRAN and enable 8-EM6-2 of RTN02 and patching it using new 1xCAT6. 7.Perform LAG for existing port and new port at IBeam and at RTN02. | Link Existing 18G_1+0_112M_PLA Swap existing link to 18G_2+0_112M_PLA (Due to Old Version IDU) Site Impacted : 4229D & 4627C NE_4083B 1.Install new 18G_DP_1.2M(MAC)+OMT. 2.Insert new 1xISM8 into slot 4 of RTN02. 3.Install XMC_3E , Sub A & B_Lo. 4.Migrate traffic to new link. 5.Decom existing MW link (ODU & Ant). | Link Existing 18G_1+0_112M_PLA Swap existing link to 18G_2+0_112M_PLA (Due to OLD Version IDU) Site Impacted : 4229D & 4627C FE_4171A 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Insert new 1xISM8 into slot 3 of RTN02. 3.Install XMC_3E , Sub A & B_Hi. 4.Migrate traffic to new link. 5.Decom existing MW link (ODU & Ant). 6.Request new port at IBeam from ZTE IPRAN and enable 8-EM6-2 of RTN02 and patching it using new 1xCAT6. 7.Perform LAG for existing port and new port at IBeam and at RTN02. | XMC_3 | MAC | 18G | 18G_DP_1.2M(MAC)+OMT x1. | 18G_DP_0.6M(MAC)+OMT x1. | CCSMY | SQ202503190701-CCS | CCSMY | SQ202503200258-CCS // SQ202503200262-CCS // SQ202504260175-CCS | 2025-10-30 | 2025-10-29 | Completed | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-30 | 2025-10-29 | 2025-10-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022655 |  | 2025-02-27 | 2025-03-07 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-03-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-04 | 2025-03-31 | 2025-03-07 | 2025-03-07 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2025-03-04 | 2025-03-31 | 2025-03-07 | 2025-03-07 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-07 | 2025-03-04 | 2025-03-31 | 2025-03-10 | 2025-03-10 | Muhamad//rais bin mat isa/7021000043 | 2025-03-04 | 2025-03-31 | 2025-03-08 | 2025-03-08 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | EZRIN TASNIM BIN ABDUL GANI6798000128
4977B | Tobiar | DU00005038775 | Northern | Kedah | 6.067966 | 100.507302 | [7 empty] | 00. Integrated/RFS Done | 17/04: CO Done | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M_EPLA NE_4977B New 15G_DP_1.2M(MAC)+OMT x1. New 2xISM8 New XMC_3, Sub A & B_Lo x2. New suitable length of IF/RG8 cables for new 2+0. FE_4678A New 15G_DP_1.2M(MAC)+OMT x1. New 2xISM8 New XMC_3, Sub A & B_Hi x2. New suitable length of IF/RG8 cables for new 2+0. | MW Parallel Link | Link Existing HW 13G&15G_3+0_28M_EPLA. Build new MW Parallel Link HW 15G_2+0_28M_128QAM and configure EPLA with existing HW 13G&15G_3+0_28M_EPLA. Later, configuration will be 13G&15G_5+0_28M_512QAM(Existing)+128QAM(New)_EPLA. Site Impacted : 4676B & 4674B. Important Note: Need to configure new MW Parallel Link HW 15G_2+0_28M with 128QAM due to in order to meet KPI especially Availability % on Horizontal polarization. 13G channels seem fully use/utilize at FE site(4678A), thus not suggest to use for new MW Parallel Link. NE_4977B 1.Install new New 15G_DP_1.2M(MAC)+OMT x1. 2.Install new 2x XMC_3 , Sub A & B_Lo and lay new IF/RG8 cables, configure and terminate it. 3.Reuse existing RTN910A(RTN04). 4.Plug out existing 2x IF/RG8 cables from ISV3 slot 03 & 04 of RTN910A(RTN04) in which connected to 2x 13G ODU and existing 1x 13G antenna. 5.Remove existing ISV3 card at slot 03 & 04 and insert new 2xISM8 into slot 03 & 04. 6.Plug in back existing 2x IF/RG8 cables into ISM8 slot 03 at port 1 & 2 and plug in new 2x IF/RG8 cables into ISM8 slot 04 at port 1 & 2. 7.Please do not touch IF/RG8 cable connected to existing ISM8 slot 07 port 1 of RTN910A(RTN04) in which connected to existing 1x 15G ODU and existing 1x 15G antenna. 8.Build new MW Parallel Link HW 15G_2+0_28M_128QAM and configure EPLA with existing HW 13G&15G_3+0_28M_512QAM. 9.Later, new configuration will be 13G&15G_5+0_28M_512QAM(Existing)+128QAM(New)_EPLA. 10.Ensure existing RTN910A(RTN04) 8-EM6-2 still connected to existing RTN910A(RTN03) 8-EM6-1. Do not touch it if not required. FE_4678A 1.Install new New 15G_DP_1.2M(MAC)+OMT x1. 2.Install new 2x XMC_3 , Sub A & B_Hi and lay new IF/RG8 cables, configure and terminate it. 3.Reuse existing RTN910A(RTN16). 4.Plug out existing 2x IF/RG8 cables from ISV3 slot 03 & 04 of RTN910A(RTN16) in which connected to 2x 13G ODU and existing 1x 13G antenna. 5.Remove existing ISV3 card at slot 03 & 04 and insert new 2xISM8 into slot 03 & 04. 6.Plug in back existing 2x IF/RG8 cables into ISM8 slot 03 at port 1 & 2 and plug in new 2x IF/RG8 cables into ISM8 slot 04 at port 1 & 2. 7.Please do not touch IF/RG8 cable connected to existing ISM8 slot 07 port 1 of RTN910A(RTN16) in which connected to existing 1x 15G ODU and existing 1x 15G antenna. 8.Build new MW Parallel Link HW 15G_2+0_28M_128QAM and configure EPLA with existing HW 13G&15G_3+0_28M_512QAM. 9.Later, new configuration will be 13G&15G_5+0_28M_512QAM(Existing)+128QAM(New)_EPLA. 10.Ensure existing RTN910A(RTN16) 8-EM6-5 still connected to existing IBeam port. Do not touch it if not required. | Link Existing HW 13G&15G_3+0_28M_EPLA. Build new MW Parallel Link HW 15G_2+0_28M_128QAM and configure EPLA with existing HW 13G&15G_3+0_28M_EPLA. Later, configuration will be 13G&15G_5+0_28M_512QAM(Existing)+128QAM(New)_EPLA. Site Impacted : 4676B & 4674B. Important Note: Need to configure new MW Parallel Link HW 15G_2+0_28M with 128QAM due to in order to meet KPI especially Availability % on Horizontal polarization. 13G channels seem fully use/utilize at FE site(4678A), thus not suggest to use for new MW Parallel Link. NE_4977B 1.Install new New 15G_DP_1.2M(MAC)+OMT x1. 2.Install new 2x XMC_3 , Sub A & B_Lo and lay new IF/RG8 cables, configure and terminate it. 3.Reuse existing RTN910A(RTN04). 4.Plug out existing 2x IF/RG8 cables from ISV3 slot 03 & 04 of RTN910A(RTN04) in which connected to 2x 13G ODU and existing 1x 13G antenna. 5.Remove existing ISV3 card at slot 03 & 04 and insert new 2xISM8 into slot 03 & 04. 6.Plug in back existing 2x IF/RG8 cables into ISM8 slot 03 at port 1 & 2 and plug in new 2x IF/RG8 cables into ISM8 slot 04 at port 1 & 2. 7.Please do not touch IF/RG8 cable connected to existing ISM8 slot 07 port 1 of RTN910A(RTN04) in which connected to existing 1x 15G ODU and existing 1x 15G antenna. 8.Build new MW Parallel Link HW 15G_2+0_28M_128QAM and configure EPLA with existing HW 13G&15G_3+0_28M_512QAM. 9.Later, new configuration will be 13G&15G_5+0_28M_512QAM(Existing)+128QAM(New)_EPLA. 10.Ensure existing RTN910A(RTN04) 8-EM6-2 still connected to existing RTN910A(RTN03) 8-EM6-1. Do not touch it if not required. | Link Existing HW 13G&15G_3+0_28M_EPLA. Build new MW Parallel Link HW 15G_2+0_28M_128QAM and configure EPLA with existing HW 13G&15G_3+0_28M_EPLA. Later, configuration will be 13G&15G_5+0_28M_512QAM(Existing)+128QAM(New)_EPLA. Site Impacted : 4676B & 4674B. Important Note: Need to configure new MW Parallel Link HW 15G_2+0_28M with 128QAM due to in order to meet KPI especially Availability % on Horizontal polarization. 13G channels seem fully use/utilize at FE site(4678A), thus not suggest to use for new MW Parallel Link. FE_4678A 1.Install new New 15G_DP_1.2M(MAC)+OMT x1. 2.Install new 2x XMC_3 , Sub A & B_Hi and lay new IF/RG8 cables, configure and terminate it. 3.Reuse existing RTN910A(RTN16). 4.Plug out existing 2x IF/RG8 cables from ISV3 slot 03 & 04 of RTN910A(RTN16) in which connected to 2x 13G ODU and existing 1x 13G antenna. 5.Remove existing ISV3 card at slot 03 & 04 and insert new 2xISM8 into slot 03 & 04. 6.Plug in back existing 2x IF/RG8 cables into ISM8 slot 03 at port 1 & 2 and plug in new 2x IF/RG8 cables into ISM8 slot 04 at port 1 & 2. 7.Please do not touch IF/RG8 cable connected to existing ISM8 slot 07 port 1 of RTN910A(RTN16) in which connected to existing 1x 15G ODU and existing 1x 15G antenna. 8.Build new MW Parallel Link HW 15G_2+0_28M_128QAM and configure EPLA with existing HW 13G&15G_3+0_28M_512QAM. 9.Later, new configuration will be 13G&15G_5+0_28M_512QAM(Existing)+128QAM(New)_EPLA. 10.Ensure existing RTN910A(RTN16) 8-EM6-5 still connected to existing IBeam port. Do not touch it if not required. | XMC_3 | MAC | 15G | New 15G_DP_1.2M(MAC)+OMT x1. | New 15G_DP_1.2M(MAC)+OMT x1. | CCSMY | SQ202503190701-CCS | CCSMY | SQ202504210107-CCS // SQ202504210102-CCS // SQ202504260175-CCS |  |  | Ongoing | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25041370 |  | 2025-04-14 | 2025-04-16 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-16 | 2025-04-30 | 2025-04-16 | 2025-04-18 | IMRAN//JAVED/7021000061 | CCS TI | 2025-04-16 | 2025-04-30 | 2025-04-16 | 2025-04-18 | IMRAN//JAVED/7021000061 | CCS TI | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-17 | 2025-04-16 | 2025-04-30 | 2025-04-16 | 2025-05-13 | IMRAN//JAVED/7021000061 | 2025-07-28: 2025-04-16; 2025-07-28: 2025-04-30; 2025-07-28: 2025-04-16; 2025-07-29: 2025-04-16 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509250641-GCI | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | CHEONG/SENG/WAH/7018000306
4982B | Selarong Panjang | DU00005038776 | Northern | Kedah | 5.404690 | 100.686915 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M. NE_4982B 15G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Lo x1. FE_4954B 15G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub_Hi x1. | MW New Link / Reroute | Existing link 13G_2+0_28M Link reroute to new FE 4954B with 15G_4+0_28M. Site Impacted : 4963B NE_4982B 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A (RTN no provide by GOP team). 3.Install new 4_ISM8-2+0 and 3_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new link and new FE route. 7.Enable GE 1 , ETH patching to existing 4954B_RTN01 (ID : 41441). 8.Enable GE 2 , ETH patching to existing 4982B_RTN03 (ID : 27994). 9.Decom existing MW link (4982B_RTN02 - 4986A_RTN04).Ensure traffic migrated before decom. FE_4954B 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by GOP team). 3.Install new 4_ISM8-2+0 and 3_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Enable GE 1 , ETH patching to existing 4954B_RTN01 ( ID : 41441). 7.Traffic migrate to new link and new FE route. 8.Decom existing MW link (4986A_RTN04 - 4982B_RTN02).Ensure traffic migrated before decom. | Existing link 13G_2+0_28M Link reroute to new FE 4954B with 15G_4+0_28M. Site Impacted : 4963B NE_4982B 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A (RTN no provide by GOP team). 3.Install new 4_ISM8-2+0 and 3_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new link and new FE route. 7.Enable GE 1 , ETH patching to existing 4954B_RTN01 (ID : 41441). 8.Enable GE 2 , ETH patching to existing 4982B_RTN03 (ID : 27994). 9.Decom existing MW link (4982B_RTN02 - 4986A_RTN04).Ensure traffic migrated before decom. | Existing link 13G_2+0_28M Link reroute to new FE 4954B with 15G_4+0_28M. Site Impacted : 4963B FE_4954B 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by GOP team). 3.Install new 4_ISM8-2+0 and 3_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Enable GE 1 , ETH patching to existing 4954B_RTN01 ( ID : 41441). 7.Traffic migrate to new link and new FE route. 8.Decom existing MW link (4986A_RTN04 - 4982B_RTN02).Ensure traffic migrated before decom. | XMC_5D | MDD | 15G | 1.2 | 1.2 | GCI | SQ202504210266-GCI | GCI | SQ202506120237-GCI // SQ202506120246-GCI | 2025-12-05 | 2025-12-04 | Completed | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-04 | 2025-12-05 | 2025-12-04 | 2025-12-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052640 |  | 2025-05-27 | 2025-05-31 | Completed | 2025-05-26 | 2025-05-27 | 2025-05-26 | 2025-05-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2025-06-24 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2025-06-24 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-18 | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2026-04-02 | ANAS FIKRI ADHA BIN RAZMI6000009598 | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2025-06-13 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505190519-GCI | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | CHEONG/SENG/WAH/7018000306
4116B | Sg Bakap 2 Monopole (Celcom) | DU00005038777 | Northern | Penang | 5.237550 | 100.487780 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1x New CAT6 cable with suitable length | MW IDU Patching | MW IDU Patching need to perform by diverting traffic 4803D from exiting HW MW Link 4116B(RTN04)-4188A(RTN16) to xC PTN P00172. 4116B is Pair Colo with P00172. Site Impacted : 4803D NE_4116B 1.Disable port 8-EM6-1 OF RTN04. 2.Remove cascading between RTN01(port 8-EM6-1) and RTN04(port 8-EM6-1). 3.Patching new 1x CAT6 cable from RTN01(port 8-EM6-1) to xC PTN P00172. Get info port of xC PTN P00172 from ZTE IPRAN. 4.Configure DCN Inband for RTN01 and new VLAN services for 4803D thru xC Host. 5.Migrate 4803D traffic to new CP/PTN. Be aware BBU 4118B already backhauling and MOCN to xC PTN P00172 in Y2023. 6.Decom existing HW MW link 4116B(RTN04)-4188A(RTN16) will be perform by ZTE Decom Team. | MW IDU Patching need to perform by diverting traffic 4803D from exiting HW MW Link 4116B(RTN04)-4188A(RTN16) to xC PTN P00172. 4116B is Pair Colo with P00172. Site Impacted : 4803D NE_4116B 1.Disable port 8-EM6-1 OF RTN04. 2.Remove cascading between RTN01(port 8-EM6-1) and RTN04(port 8-EM6-1). 3.Patching new 1x CAT6 cable from RTN01(port 8-EM6-1) to xC PTN P00172. Get info port of xC PTN P00172 from ZTE IPRAN. 4.Configure DCN Inband for RTN01 and new VLAN services for 4803D thru xC Host. 5.Migrate 4803D traffic to new CP/PTN. Be aware BBU 4118B already backhauling and MOCN to xC PTN P00172 in Y2023. 6.Decom existing HW MW link 4116B(RTN04)-4188A(RTN16) will be perform by ZTE Decom Team. | - | - | - | - | - | - | GCI | SQ202504170476-GCI | GCI | SQ202503280484-GCI | 2025-10-25 | 2025-10-24 | Completed | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022156 |  | 2025-02-22 | 2025-02-24 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-02-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2025-04-09 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | GCI TI | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2025-04-09 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | GCI TI | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2025-04-12 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | 2025-07-28: 2025-03-24; 2025-07-28: 2025-03-31; 2025-07-28: 2025-03-24; 2025-07-29: 2025-03-28 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI
1434H_LOS | 99 Speedmart BDR SERI COALFIELDS | DU00005051446 | Central | Selangor | 3.246650 | 101.474810 | [7 empty] | 05. TI WIP |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | New NLOS RTN510 NE_1434H Nlos-OptiX RTN /PI-DC B10 /Power injector. x1 Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1 Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1 Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. ETH Cable / LAN Cable x1. FE_1220D Nlos-OptiX RTN /PI-DC B10 /Power injector x1 Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1 Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1 Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1 Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. ETH Cable / LAN Cable x1. | MW New Link / Reroute | Existing Cambium NLOS PTP 670. Swap to HW NLOS RTN510. **IMPORTANT NOTE: 1. STILL AWAITING SUITABLE CANDIDATE FE FOR 1220D IN WHICH PLAN TO USE MW LINK. 2. DO NOT MIGRATE UNTIL UPLINK MW LINK READY. 3. PLEASE ENSURE NEW HW MW LINK 3447C(RTN02)-1220D(RTN03) READY FIRST AS CASCADING REQUIRE FROM NLOS IDU TO RTN910A.** Later, decom existing Cambium NLOS PTP 670. Site Impacted : 1434H. NE_1434H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Request new vlan dcn and capture existing NLOS parameters and create service cross connect. 5.Enable port 2-EG3-3(P&E) and patching to Customer Box. 6.Traffic migrate to new FE route site. 7.Later, decom existing Cambium NLOS PTP 670.(1434H-NLOS-1965B). FE_1220D 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Request new vlan dcn and capture existing NLOS parameters and create service cross connect. 5.Enable port 2-EG3-3(P&E) of NLOS RTN510. 6.Enable port 8-EM6-2 of RTN910A(RTN03) of new HW MW Link 3447C(RTN02)-1220D(RTN03). 7.Cascading between port 2-EG3-3(P&E) of NLOS RTN510 and port 8-EM6-2 of new RTN910A(RTN03). 8.Traffic migrate to new FE route site. 9.Later, decom existing Cambium NLOS 5G.(1434H-NLOS-1965B). | Existing Cambium NLOS PTP 670. Swap to HW NLOS RTN510. **IMPORTANT NOTE: 1. STILL AWAITING SUITABLE CANDIDATE FE FOR 1220D IN WHICH PLAN TO USE MW LINK. 2. DO NOT MIGRATE UNTIL UPLINK MW LINK READY. 3. PLEASE ENSURE NEW HW MW LINK 3447C(RTN02)-1220D(RTN03) READY FIRST AS CASCADING REQUIRE FROM NLOS IDU TO RTN910A.** Later, decom existing Cambium NLOS PTP 670. Site Impacted : 1434H. NE_1434H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Request new vlan dcn and capture existing NLOS parameters and create service cross connect. 5.Enable port 2-EG3-3(P&E) and patching to Customer Box. 6.Traffic migrate to new FE route site. 7.Later, decom existing Cambium NLOS PTP 670.(1434H-NLOS-1965B). | Existing Cambium NLOS PTP 670. Swap to HW NLOS RTN510. **IMPORTANT NOTE: 1. STILL AWAITING SUITABLE CANDIDATE FE FOR 1220D IN WHICH PLAN TO USE MW LINK. 2. DO NOT MIGRATE UNTIL UPLINK MW LINK READY. 3. PLEASE ENSURE NEW HW MW LINK 3447C(RTN02)-1220D(RTN03) READY FIRST AS CASCADING REQUIRE FROM NLOS IDU TO RTN910A.** Later, decom existing Cambium NLOS PTP 670. Site Impacted : 1434H. FE_1220D 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Request new vlan dcn and capture existing NLOS parameters and create service cross connect. 5.Enable port 2-EG3-3(P&E) of NLOS RTN510. 6.Enable port 8-EM6-2 of RTN910A(RTN03) of new HW MW Link 3447C(RTN02)-1220D(RTN03). 7.Cascading between port 2-EG3-3(P&E) of NLOS RTN510 and port 8-EM6-2 of new RTN910A(RTN03). 8.Traffic migrate to new FE route site. 9.Later, decom existing Cambium NLOS 5G.(1434H-NLOS-1965B). |  | AS6D03SSNF | 5G | 0.3M | 0.3M | Magicell | SQ202506300654-Magicell | Magicell | SQ202507190091-Magicell // SQ202507190092-Magicell | 2026-01-29 | 2026-01-30 | Completed | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-07-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-29 | 2026-01-05 | 2025-12-29 | 2025-12-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-29 | 2026-01-22 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070936 |  | 2025-07-13 | 2025-07-14 | Completed | 2025-07-12 | 2025-07-13 | 2025-07-12 | 2025-07-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2026-01-29 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2026-04-21 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-06 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2026-04-21 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2026-04-07 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505280699-GTSB
3784A_LOS | Pangsapuri Alam Perdana | DU00005051447 | Central | Selangor | 3.257219 | 101.449410 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M_512QAM NE_3784A New 18G_0.6M(MDD) x1. New RTN910A(RTN02). New XMC_5D, Sub B_Lo x1. New CAT6 Cable with suitable length x2. FE_2531A New 18G_0.6M(MDD) x1. New RTN910A x1. New XMC_5D, Sub B_Hi x1. New CAT6 Cable with suitable length x1. | MW New Link / Reroute | Existing HW MW Link 3784A(RTN01)-1965B(RTN01), 18G_1+0_56M_512QAM. Install new HW MW Link 3784A(RTN02)-2531A(RTN06), 18G_2+0_56M_512QAM_EPLA. Later decom existing HW MW Link 3784A(RTN01)-1965B(RTN01), 18G_1+0_56M_512QAM. Site Impacted: 3784A & 1396E(EB Site need to obtain approval from GOP/CD for migration). NE_3784A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN02). 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Request new xD vlan DCN & services from ZTE IPRAN Team. Configure it. 5.Enable port 8-EM6-1 of new RTN910A(RTN02). 6.Shifting BBU from port 8-EM6-1 of existing RTN910A(RTN01) and repatching BBU at port 8-EM6-1 of new RTN910A(RTN02). Configure it. 7.Migrate traffic 3784A & 1396E to new HW MW Link 3784A(RTN02)-2531A(RTN06), 18G_2+0_56M_512QAM_EPLA. 8.Later decom existing HW MW Link 3784A(RTN01)-1965B(RTN01), 18G_1+0_56M_512QAM. FE_2531A 1.Install new 18G_0.6M(MDD) x1. 2.Install new 1xRTN910A(RTN06). Configure it. 3.Install new 1x XMC_5D, Sub A_Hi. Configure it. 4.Request new xD vlan DCN and services and new port of IBeam from ZTE IPRAN Team. 5.Enable port 8-EM6-1 of new RTN910A(RTN06). 6.Patching port 8-EM6-1 of new RTN910A(RTN06) and new port of IBeam. Configure it. 7.Migrate traffic 3784A & 1396E to the new port(GE0/1/5) at IBeam. 8.Later decom existing HW MW Link 3784A(RTN01)-1965B(RTN01), 18G_1+0_56M_512QAM. | Existing HW MW Link 3784A(RTN01)-1965B(RTN01), 18G_1+0_56M_512QAM. Install new HW MW Link 3784A(RTN02)-2531A(RTN06), 18G_2+0_56M_512QAM_EPLA. Later decom existing HW MW Link 3784A(RTN01)-1965B(RTN01), 18G_1+0_56M_512QAM. Site Impacted: 3784A & 1396E(EB Site need to obtain approval from GOP/CD for migration). NE_3784A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN02). 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Request new xD vlan DCN & services from ZTE IPRAN Team. Configure it. 5.Enable port 8-EM6-1 of new RTN910A(RTN02). 6.Shifting BBU from port 8-EM6-1 of existing RTN910A(RTN01) and repatching BBU at port 8-EM6-1 of new RTN910A(RTN02). Configure it. 7.Migrate traffic 3784A & 1396E to new HW MW Link 3784A(RTN02)-2531A(RTN06), 18G_2+0_56M_512QAM_EPLA. 8.Later decom existing HW MW Link 3784A(RTN01)-1965B(RTN01), 18G_1+0_56M_512QAM. | Existing HW MW Link 3784A(RTN01)-1965B(RTN01), 18G_1+0_56M_512QAM. Install new HW MW Link 3784A(RTN02)-2531A(RTN06), 18G_2+0_56M_512QAM_EPLA. Later decom existing HW MW Link 3784A(RTN01)-1965B(RTN01), 18G_1+0_56M_512QAM. Site Impacted: 3784A & 1396E(EB Site need to obtain approval from GOP/CD for migration). FE_2531A 1.Install new 18G_0.6M(MDD) x1. 2.Install new 1xRTN910A(RTN06). Configure it. 3.Install new 1x XMC_5D, Sub A_Hi. Configure it. 4.Request new xD vlan DCN and services and new port of IBeam from ZTE IPRAN Team. 5.Enable port 8-EM6-1 of new RTN910A(RTN06). 6.Patching port 8-EM6-1 of new RTN910A(RTN06) and new port of IBeam. Configure it. 7.Migrate traffic 3784A & 1396E to the new port(GE0/1/5) at IBeam. 8.Later decom existing HW MW Link 3784A(RTN01)-1965B(RTN01), 18G_1+0_56M_512QAM. | XMC-5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_0.6M(MDD) x1. | Magicell | SQ202506300654-Magicell | Magicell | SQ202507160752-Magicell // SQ202507160764-Magicell | 2026-01-29 | 2026-01-30 | Completed | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-07-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-29 | 2026-01-22 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070939 |  | 2025-07-13 | 2025-07-14 | Completed | 2025-07-12 | 2025-07-13 | 2025-07-12 | 2025-07-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-12-24 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-12-24 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-12-14 | 2025-12-14 | 2025-12-14 | 2025-12-14 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-14 | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-12-24 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-12-13 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505280699-GTSB
2721C_LOS | Taman Alam Perdana | DU00005051448 | Central | Selangor | 3.256342 | 101.456710 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE_2721C New 23G_0.6M(MS) x1. Re-used RTN910A(RTN01). New XMC_3, Sub A_Lo x2. FE_2531A New 23G_1.2M(MS) x1. New RTN910A x1. New XMC_3, Sub A_Hi x2. New CAT6 Cable with suitable length x1. | MW New Link / Reroute | Existing HW MW Link 2721C(RTN01)-1965B(RTN06), 18G_1+0_56M_512QAM. Install new HW MW Link 2721C(RTN01)-2531A(RTN05), 23G_2+0_56M_512QAM_EPLA. Decom existing HW MW Link 2721C(RTN01)-1965B(RTN06), 18G_1+0_56M_512QAM. But do not decom existing RTN910A(RTN01) at 2721C. Site Impacted : 2721C. NE_2721C 1.Install new 23G_0.6M(MS) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new 2x XMC_3, Sub A_Lo. Configure it. 4.Request new xD vlan DCN & services from ZTE IPRAN Team. 5.Migrate traffic to new link. 6.Decom existing HW MW Link 2721C(RTN01)-1965B(RTN06), 18G_1+0_56M_512QAM. But do not decom existing RTN910A(RTN01) at 2721C. FE_2531A 1.Install new 23G_1.2M(MS) x1. 2.Install new 1xRTN910A(RTN05). Configure it. 3.Install new 2x XMC_3, Sub A_Hi. Configure it. 4.Create new In Band DCN. 5.Request new xD vlan DCN and services and new port of IBeam from ZTE IPRAN Team. 6.Enable port 8-EM6-1 of new RTN910A(RTN05). 7.Patching port 8-EM6-1 of new RTN910A(RTN05) and new port of IBeam. Configure it. 8.Migrate traffic 2721C to the new port at IBeam. 9.Decom existing HW MW Link 2721C(RTN01)-1965B(RTN06), 18G_1+0_56M_512QAM. But do not decom existing RTN910A(RTN01) at 2721C. | Existing HW MW Link 2721C(RTN01)-1965B(RTN06), 18G_1+0_56M_512QAM. Install new HW MW Link 2721C(RTN01)-2531A(RTN05), 23G_2+0_56M_512QAM_EPLA. Decom existing HW MW Link 2721C(RTN01)-1965B(RTN06), 18G_1+0_56M_512QAM. But do not decom existing RTN910A(RTN01) at 2721C. Site Impacted : 2721C. NE_2721C 1.Install new 23G_0.6M(MS) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new 2x XMC_3, Sub A_Lo. Configure it. 4.Request new xD vlan DCN & services from ZTE IPRAN Team. 5.Migrate traffic to new link. 6.Decom existing HW MW Link 2721C(RTN01)-1965B(RTN06), 18G_1+0_56M_512QAM. But do not decom existing RTN910A(RTN01) at 2721C. | Existing HW MW Link 2721C(RTN01)-1965B(RTN06), 18G_1+0_56M_512QAM. Install new HW MW Link 2721C(RTN01)-2531A(RTN05), 23G_2+0_56M_512QAM_EPLA. Decom existing HW MW Link 2721C(RTN01)-1965B(RTN06), 18G_1+0_56M_512QAM. But do not decom existing RTN910A(RTN01) at 2721C. Site Impacted : 2721C. FE_2531A 1.Install new 23G_1.2M(MS) x1. 2.Install new 1xRTN910A(RTN05). Configure it. 3.Install new 2x XMC_3, Sub A_Hi. Configure it. 4.Create new In Band DCN. 5.Request new xD vlan DCN and services and new port of IBeam from ZTE IPRAN Team. 6.Enable port 8-EM6-1 of new RTN910A(RTN05). 7.Patching port 8-EM6-1 of new RTN910A(RTN05) and new port of IBeam. Configure it. 8.Migrate traffic 2721C to the new port at IBeam. 9.Decom existing HW MW Link 2721C(RTN01)-1965B(RTN06), 18G_1+0_56M_512QAM. But do not decom existing RTN910A(RTN01) at 2721C. | XMC-3 | MS | 23G | 23G_0.6M(MS) x1. | 23G_1.2M(MS) x1. | Magicell | SQ202506250168-Magicell | Magicell | SQ202507080896-Magicell // SQ202507080906-Magicell // SQ202507250427-Magicell | 2025-07-05 | 2025-07-04 | Completed | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061604 |  | 2025-07-03 | 2026-01-29 | Completed | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2026-01-29 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | MOHD//SAFRI BIN ARIF/7018000166 |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | MOHD//SAFRI BIN ARIF/7018000166 |  | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-07 | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2026-02-24 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-07-16: 2025-07-03; 2025-07-16: 2025-07-03; 2025-07-16: 2025-07-03; 2025-12-13: 2025-07-05 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505280699-GTSB
1965B_LOS | Simpang Punchak Alam (KJS) | DU00005051449 | Central | Selangor | 3.245301 | 101.472110 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Need to create new DU LOS for 1220D(Relo for 1965B). | [7 empty] | Magicell | No PR required-Site drop/cancel | Magicell | No PR required-Site drop/cancel |  |  | Ongoing | 2025-06-23 | 2025-06-23 | 2025-06-23 | [5 empty] | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
B02823-B00504 | JLNPADANG_SBKBERNAM | DU00005051450 | Central | Selangor | 3.762580 | 100.988010 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 19/2/2025 : Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X IDU RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP B02823-B00504 WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB A & B_1.37KM IMPACTED: B02823, 3373A DISMANTLE EXISTING LINK NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND PATCH 10G SFP AT PTN 7. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND PATCH 10G SFP AT PTN 7. DISMANTLE EXISTING LINK | XMC3E | DP | 23G | 0.6 | 0.6 | GCI | SQ202502260369-GCI | GCI | SQ202502270715-GCI // SQ202504150088-GCI | 2025-04-26 | 2025-04-25 | Completed | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-02-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-22 | 2025-04-23 | 2025-04-22 | 2025-04-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-25 | 2025-04-26 | 2025-04-25 | 2025-04-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021347 |  | 2025-02-14 | 2025-02-17 | Completed | 2025-02-13 | 2025-02-14 | 2025-02-13 | 2025-02-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-19 | 2025-02-26 | 2025-02-18 | 2025-02-19 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-19 | 2025-02-26 | 2025-02-18 | 2025-02-21 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-02-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-19 | 2025-02-19 | 2025-02-26 | 2025-02-18 | 2025-02-24 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-02-19 | 2025-02-26 | 2025-02-18 | 2025-02-19 | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | NG HONG JIE7018000036 | Logistic Team | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
1396E_LOS | Foresight Industries Puncak Alam | DU00005051451 | Central | Selangor | 3.247320 | 101.448310 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Existing TX | REUSE EXISTING TX. | [7 empty] | Magicell | No PR required-Site drop/cancel | Magicell | No PR required-Site drop/cancel |  |  | Ongoing | 2025-06-23 | 2025-06-23 | 2025-06-23 | [5 empty] | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
3447C_LOS | Eco Grandeur | DU00005051452 | Central | Selangor | 3.226230 | 101.457110 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_56M NE_3447C New 23G_DP_0.6M(MAC)+OMT x1. New RTN910A(RTN01). New XMC_3, Sub B_Lo x2. FE_1220D New 23G_DP_1.2M(MS) x1. New 23G FlexiWG x2. New RTN910A x1. New XMC_3, Sub B_Hi x2. New CAT6 Cable with suitable length x1. | MW New Link / Reroute | Existing HW MW Link 3447C-1965B, 23G_1+0_56M_512QAM. Install new HW MW Link 3447C(RTN02)-1220D(RTN03), 23G_2+0_56M_512QAM_EPLA. **IMPORTANT NOTE: 1. STILL AWAITING SUITABLE CANDIDATE FE FOR 1220D IN WHICH PLAN TO USE MW LINK. 2. DO NOT MIGRATE UNTIL UPLINK MW LINK READY.** Later, decom existing HW MW Link 3447C-1965B, 23G_1+0_56M_512QAM. Site Impacted : 3447C. NE_3447C 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN02). 3.Install new 2x XMC_3, Sub B_Lo. Configure HW MW Link 23G_2+0_56M_512QAM_EPLA. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN02). Configure it. 6.Create new In Band DCN. 7.Request new vlan services. 8.Decom existing HW MW Link 3447C-1965B, 23G_1+0_56M_512QAM. FE_1220D 1.Install new 23G_1.2M(MS) x1. 2.Install new 1xRTN910A(RTN03). Configure it. 3.Install new 2x XMC_3, Sub A_Hi. Configure HW MW Link 23G_2+0_56M_512QAM_EPLA. 4.Enable port 8-EM6-1 of new RTN910A(RTN03). 5.Cascading between port 8-EM6-1 of new RTN910A(RTN03) and new HW MW Uplink 1220D-???.(Not decide yet FE for 1220D) 6.Create new In Band DCN. 7.Request new vlan services. 8.Decom existing HW MW Link 3447C-1965B, 23G_1+0_56M_512QAM. | Existing HW MW Link 3447C-1965B, 23G_1+0_56M_512QAM. Install new HW MW Link 3447C(RTN02)-1220D(RTN03), 23G_2+0_56M_512QAM_EPLA. **IMPORTANT NOTE: 1. STILL AWAITING SUITABLE CANDIDATE FE FOR 1220D IN WHICH PLAN TO USE MW LINK. 2. DO NOT MIGRATE UNTIL UPLINK MW LINK READY.** Later, decom existing HW MW Link 3447C-1965B, 23G_1+0_56M_512QAM. Site Impacted : 3447C. NE_3447C 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN02). 3.Install new 2x XMC_3, Sub B_Lo. Configure HW MW Link 23G_2+0_56M_512QAM_EPLA. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN02). Configure it. 6.Create new In Band DCN. 7.Request new vlan services. 8.Decom existing HW MW Link 3447C-1965B, 23G_1+0_56M_512QAM. | Existing HW MW Link 3447C-1965B, 23G_1+0_56M_512QAM. Install new HW MW Link 3447C(RTN02)-1220D(RTN03), 23G_2+0_56M_512QAM_EPLA. **IMPORTANT NOTE: 1. STILL AWAITING SUITABLE CANDIDATE FE FOR 1220D IN WHICH PLAN TO USE MW LINK. 2. DO NOT MIGRATE UNTIL UPLINK MW LINK READY.** Later, decom existing HW MW Link 3447C-1965B, 23G_1+0_56M_512QAM. Site Impacted : 3447C. FE_1220D 1.Install new 23G_1.2M(MS) x1. 2.Install new 1xRTN910A(RTN03). Configure it. 3.Install new 2x XMC_3, Sub A_Hi. Configure HW MW Link 23G_2+0_56M_512QAM_EPLA. 4.Enable port 8-EM6-1 of new RTN910A(RTN03). 5.Cascading between port 8-EM6-1 of new RTN910A(RTN03) and new HW MW Uplink 1220D-???.(Not decide yet FE for 1220D) 6.Create new In Band DCN. 7.Request new vlan services. 8.Decom existing HW MW Link 3447C-1965B, 23G_1+0_56M_512QAM. | XMC_3 | MAC & MS | 23G | 23G_DP_0.6M(MAC)+OMT x1. | 23G_DP_1.2M(MS) x1. | Magicell | SQ202506300654-Magicell | Magicell | SQ202507250421-Magicell // SQ202507250427-Magicell | 2026-01-14 | 2026-01-07 | Completed | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-07-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-31 | 2026-01-07 | 2025-12-31 | 2025-12-31 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070935 |  | 2025-07-13 | 2025-07-14 | Completed | 2025-07-12 | 2025-07-13 | 2025-07-12 | 2025-07-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2026-01-29 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2026-04-01 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-07 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2026-03-31 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2026-03-17 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505280699-GTSB
2958C_HU | Kg Labohan Dagang | DU00006624199 | Central | Selangor | 2.800938 | 101.614812 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC |  | MW Hardware Upgrade | To change Tx route of 2958C to free up MW link 3774A-1236A To install new ISM8 card at FE IDU and change operating mode to IS8 To perform channel BW upgrade from 56MHz to 112MHz Tx route current: 2958C-3774A-1236A Tx route after: 2958C-3774A/B00198-B00269 1) Install new ISM8 card at IDU 3774A/B00198 LBHNDAGANG-RTN01 slot 3 2) Transfer link 2958C-3774A to new ISM8 card 3) Upgrade IS mode and channel BW to 112MHz 4) Migrate 2958C to new route Impact site: 2958C |  | To change Tx route of 2958C to free up MW link 3774A-1236A To install new ISM8 card at FE IDU and change operating mode to IS8 To perform channel BW upgrade from 56MHz to 112MHz Tx route current: 2958C-3774A-1236A Tx route after: 2958C-3774A/B00198-B00269 1) Install new ISM8 card at IDU 3774A/B00198 LBHNDAGANG-RTN01 slot 3 2) Transfer link 2958C-3774A to new ISM8 card 3) Upgrade IS mode and channel BW to 112MHz 4) Migrate 2958C to new route Impact site: 2958C | XMC3 | MAC | 18G | 0.6 | 0.6 | GCI | SQ202603130690-GCI | GCI | SQ202603130687-GCI // SQ202603130689-GCI |  |  | Ongoing | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26030614 |  | 2026-03-07 | 2026-03-10 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-25 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-12 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602260549-GCI | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
2510A_LOS | Northpoint Midvalley IB (Celcom) | DU00006624200 | Central | Kuala Lumpur | 3.120278 | 101.677700 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW New Link / Reroute | MW NEW LINK REROUTE 2510A-1243A WITH HUAWEI_18G_1+0_0.6M/0.6M_MDD_112MHZ_512QAM_889MBPS_XMC5D_SUB_B_LINK_1.19KM IMPACTED: 2510A DISMANTLE EXISTING LINK 2510A-3107B | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 2510A-3107B | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 2510A-3107B | XMC5D | MDD | 18G | 0.6 | 0.6 | GTSB | SQ202602250451-GTSB | GTSB | SQ202603060043-GTSB // SQ202603060047-GTSB | 2026-04-15 | 2026-04-08 | Completed | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-01 | 2026-04-15 | 2026-04-01 | 2026-04-01 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022765 |  | 2026-02-28 | 2026-03-05 | Completed | 2026-02-27 | 2026-02-28 | 2026-02-27 | 2026-03-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-09 | 2026-03-31 | 2026-03-09 | 2026-03-11 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2026-03-09 | 2026-03-31 | 2026-03-09 | 2026-03-18 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-11 | 2026-03-09 | 2026-03-31 | 2026-03-09 | 2026-03-24 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2026-03-09 | 2026-03-31 | 2026-03-09 | 2026-03-11 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602260549-GCI | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
7637A_AD | Tomher Industrial | DU00006624201 | Sabah | Sabah | 6.085390 | 116.197080 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module x2. Fiber patch cord x 1 pairs. | BBU Patching | Change patching BBU to IDU 7637A RTN02 from 1G to 10G port | Change patching BBU to IDU 7637A RTN02 from 1G to 10G port | [6 empty] | NR services | SQ202603060636-NR Services | NR services | SQ202604280671-NR Services |  |  | Ongoing | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022632 |  | 2026-02-27 | 2026-03-05 | Completed | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-03-05 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | LEONARD//EDUAN/6000038538 | 2025-07-16: 2026-03-05; 2025-07-16: 2026-04-05; 2025-07-16: 2026-03-05; 2025-12-13: 2026-03-05 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202602260576-GCI | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | CHEONG/SENG/WAH/7018000306
7702A_IPR | Bongawan | DU00006624202 | Sabah | Sabah | 5.535128 | 115.848781 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | Perform BBU patching from 1G to 10G port at 7702A. NE_7702A New SFP Module 10G with 1Km 1310nm x2(For BBU & IBeam). New Optical Patch Cord cable x1 with suitable type and length. | BBU Patching | Change patching BBU to ATN from 1G to 10G port (ops team and swap room to assign ATN and BBU port) Site Impacted :7702A. NE_7702A 1.Insert new suitable SFP Module 10G 1Km 1310nm into new port 10G RAN. Enable it. 2.Request new 10G port(suggest use GE0/2/2) at HW IBeam from ZTE IPRAN team and insert SFP Module 10G 1Km 1310nm. 3.Patching Optical patch cord between new port 10G RAN and new 10G port at HW IBeam. | Change patching BBU to ATN from 1G to 10G port (ops team and swap room to assign ATN and BBU port) Site Impacted :7702A. NE_7702A 1.Insert new suitable SFP Module 10G 1Km 1310nm into new port 10G RAN. Enable it. 2.Request new 10G port(suggest use GE0/2/2) at HW IBeam from ZTE IPRAN team and insert SFP Module 10G 1Km 1310nm. 3.Patching Optical patch cord between new port 10G RAN and new 10G port at HW IBeam. | [6 empty] | NR services | SQ202603060636-NR Services | NR services | SQ202603030376-NR Services | 2026-04-21 | 2026-04-14 | Completed | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-07 | 2026-04-14 | 2026-04-07 | 2026-04-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-21 | 2026-04-14 | 2026-04-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022633 |  | 2026-02-27 | 2026-03-02 | Completed | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-03-02 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-01 | 2026-04-01 | 2026-03-01 | 2026-03-02 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-03-01 | 2026-04-01 | 2026-03-01 | 2026-03-02 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-03-01 | 2026-04-01 | 2026-03-01 | 2026-03-04 | LEONARD//EDUAN/6000038538 | 2025-07-16: 2026-03-01; 2025-07-16: 2026-04-01; 2025-07-16: 2026-03-01; 2025-12-13: 2026-03-02 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202602260632-GTSB
9695A_AD | Desa Bahagia | DU00006652895 | Sarawak | Sarawak | 4.427108 | 114.047965 | [9 empty] | TSS+AA+TI |  | 1x ODU 18G XMC3E SUB B HI 1x ODU 18G XMC3E SUB B LO 2x 10G 1KM SFP IF CABLE SUITABLE LENGTH | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 9695A-9536A WITH FROM 18G_1+0_0.6M/0.6M_DP_112MHZ_128QAM TO HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_256QAM_1556MBPS_XMC3E_SUB_A & B_LINK_3.22KM PATCH EXISTING IDU 9536A RTN03 TO 9536A RTN01 USING 10G PORT IDU TO IDU IMPACTED: 9695A | 1. REUSE EXISTING IDU RTN910 2. REUSE EXISTING 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM | 1. REUSE EXISTING IDU RTN910 2. REUSE EXISTING 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. PATCH EXISTING IDU 9536A RTN03 TO 9536A RTN01 USING SFP 10G PORT IDU TO IDU | XMC3E | MAC | 18G | 0.6 | 0.6 | Redtone | SQ202604150357-Redtone | Redtone | SQ202604150336-Redtone // SQ202604150349-Redtone |  |  | Ongoing | 2026-04-13 | 2026-05-04 | 2026-04-13 | [5 empty] | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040614 |  | 2026-04-07 | 2026-04-10 | Completed | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-13 | 2026-04-30 | 2026-04-13 | 2026-04-14 | ALEXANDER SIGAR BALANG7667000013 | REDTONE TI | 2026-04-13 | 2026-04-30 | 2026-04-13 |  | ALEXANDER SIGAR BALANG7667000013 | REDTONE TI | [7 empty] | 2026-04-13 | 2026-05-04 | 2026-04-13 |  | ALEXANDER SIGAR BALANG7667000013 | 2025-07-16: 2026-04-13; 2025-07-16: 2026-05-04; 2025-07-16: 2026-04-13; 2025-12-13: 2026-04-14 | [7 empty] | GCI | SQ202603170140-GCI | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | EZRIN TASNIM BIN ABDUL GANI6798000128
9313A_AD_1 | Tapah(SACOFA) | DU00006652896 | Sarawak | Sarawak | 1.299740 | 110.406710 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | MW Re-engineering at 9313A. NE_9313A New CAT6 cable x1. | BBU Patching | BBU Patching at 9313A. Site Impacted :9313A. NE_9313A 1.Disconnect/remove/disable existing patching BBU 9313A from port 8-EM6-1 of RTN910AF(RTN04, NEID 9-24964). 2.Enable port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-20539). 3.Perform patching existing BBU 9313A toport 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-20539). 4.Re-use existing Vlan Services. | BBU Patching at 9313A. Site Impacted :9313A. NE_9313A 1.Disconnect/remove/disable existing patching BBU 9313A from port 8-EM6-1 of RTN910AF(RTN04, NEID 9-24964). 2.Enable port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-20539). 3.Perform patching existing BBU 9313A toport 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-20539). 4.Re-use existing Vlan Services. | [6 empty] | Allstar | SQ202603180484-Allstar | Allstar | SQ202603170098-Allstar |  |  | Ongoing | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030625 |  | 2026-03-07 | 2026-03-16 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-19 | 2026-03-16 | 2026-03-16 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-03-13 | 2026-03-19 | 2026-03-16 | 2026-03-16 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-17 | 2026-03-13 | 2026-03-19 | 2026-03-16 | 2026-03-16 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-07-16: 2026-03-13; 2025-07-16: 2026-03-19; 2025-07-16: 2026-03-14; 2025-12-13: 2026-03-14 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202603170145-GTSB
9786B_AD | Kg.Pabahanan | DU00006652897 | Sarawak | Sarawak | 4.775465 | 115.000322 | [9 empty] | TSS+AA+TI |  | 18G_1+0_56M. NE_9786B 18G_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub B_Lo x1. FE_9284A. 18G_1+0_1.2M(MAC) x1. ISM8 x1. XMC_3E , Sub B_Hi x1. | MW Parallel Link | Existing link 15G1+0_28M Install parallel link 18G_1+0_56M. Site Impacted : 9786B. NE_9786B 1.Install new 18G_0.6M(MAC). 2.Reuse existing 9786B_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No decomm existing MW. FE_9284A. 1.Install new 18G_1+0_1.2M(MAC). 2.Reuse existing 9284A_RTN11 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub B_Hi. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No decomm MW link. | Existing link 15G1+0_28M Install parallel link 18G_1+0_56M. Site Impacted : 9786B. NE_9786B 1.Install new 18G_0.6M(MAC). 2.Reuse existing 9786B_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No decomm existing MW. | Existing link 15G1+0_28M Install parallel link 18G_1+0_56M. Site Impacted : 9786B. FE_9284A. 1.Install new 18G_1+0_1.2M(MAC). 2.Reuse existing 9284A_RTN11 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub B_Hi. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No decomm MW link. | XMC_3E | MAC | 18G | 0.6 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041807 |  | 2026-04-19 | 2026-04-18 | Completed | 2026-04-18 | 2026-04-19 | 2026-04-18 | 2026-04-18 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202603170140-GCI | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | CHEONG/SENG/WAH/7018000306
9313A_AD | Tapah (SACOFA) | DU00006652898 | Sarawak | Sarawak | 1.299740 | 110.406710 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New SFP Module 10G 1310nm 1.4Km x2. New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Perform re-engineering by doing re-arrangement IDU-IDU cascading. Site Impacted: 9200R, 9164A, 9190R, 9192R & 9352K. NE_9313A 1.Insert new SFP Module 10G 1310nm 1.4Km x1 into port 8-EM6-3 of existing RTN910AF(RTN02, NEID 9-20681). Enable it. 2.Insert new SFP Module 10G 1310nm 1.4Km x1 into port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20539). Enable it. 3.Perform cascading between port 8-EM6-3 of existing RTN910AF(RTN02, NEID 9-20681) and port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20539). 4.Disconnect/remove/disable existing 1G(electrical) cascading in between port port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-20539) and port 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-24030). 5.Re-use existing Vlan DCN & Vlan Services. | Perform re-engineering by doing re-arrangement IDU-IDU cascading. Site Impacted: 9200R, 9164A, 9190R, 9192R & 9352K. NE_9313A 1.Insert new SFP Module 10G 1310nm 1.4Km x1 into port 8-EM6-3 of existing RTN910AF(RTN02, NEID 9-20681). Enable it. 2.Insert new SFP Module 10G 1310nm 1.4Km x1 into port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20539). Enable it. 3.Perform cascading between port 8-EM6-3 of existing RTN910AF(RTN02, NEID 9-20681) and port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20539). 4.Disconnect/remove/disable existing 1G(electrical) cascading in between port port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-20539) and port 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-24030). 5.Re-use existing Vlan DCN & Vlan Services. | [6 empty] | Allstar | SQ202603180484-Allstar | Allstar | SQ202603180480-Allstar |  |  | Ongoing | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030627 |  | 2026-03-07 | 2026-03-19 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-19 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-19 | 2026-03-19 | 2026-03-19 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-03-13 | 2026-03-19 | 2026-03-19 | 2026-03-19 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-17 | 2026-03-13 | 2026-03-19 | 2026-03-24 | 2026-03-24 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-07-16: 2026-03-13; 2025-07-16: 2026-03-19; 2025-07-16: 2026-03-14; 2025-12-13: 2026-03-14 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202603170145-GTSB
3265B_AD | Atria Shopping Mall Damansara | DU00006271565 | Central | Selangor | 3.127150 | 101.616560 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M NE_3265B. 18G_SP_0.3(MAC) x1. RTN910A x1. XMC_3E , sub B_Lo x1. FE_2389A. 18G_SP_0.3(MAC). RTN910A x1 XMC_3E , Sub B_Hi x1. | MW New Link / Reroute | Reroute the existing link to new FE due to 1211A will be dismantle. New link config with 18G_1+0_112M to new FE 2389A routing. Site Impacted : 3265B. NE_3265B. 1.Install new 18G_1+0_0.3(MAC). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new XMC_3E , sub B_Lo. 4.Create service cross connect. 5.Traffic migrate to new FE routing. 6.Decom existing MW link. FE_2389A. 1.Install new 18G_1+0_0.3(MAC). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect. 5.Enable GE1 , ETH patching to existing 2389A_RTN02. 6.Traffic migrate to new FE routing. 7.Decom existing MW link. ** Based on feedback from team the FE 1211A site facing an access issue. Resulting , existing equipment unable to decom indefinitely** | Reroute the existing link to new FE due to 1211A will be dismantle. New link config with 18G_1+0_112M to new FE 2389A routing. Site Impacted : 3265B. NE_3265B. 1.Install new 18G_1+0_0.3(MAC). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new XMC_3E , sub B_Lo. 4.Create service cross connect. 5.Traffic migrate to new FE routing. 6.Decom existing MW link. | Reroute the existing link to new FE due to 1211A will be dismantle. New link config with 18G_1+0_112M to new FE 2389A routing. Site Impacted : 3265B. FE_2389A. 1.Install new 18G_1+0_0.3(MAC). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect. 5.Enable GE1 , ETH patching to existing 2389A_RTN02. 6.Traffic migrate to new FE routing. 7.Decom existing MW link. | XMC_3E | MAC | 18G | 0.3 | 0.3 | Magicell | SQ202511190556-Magicell // SQ202604290559-Magicell | Magicell | SQ202511070103-Magicell // SQ202511070132-Magicell | 2026-02-20 | 2026-02-25 | Completed | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-19 | 2026-02-20 | 2026-02-19 | 2026-02-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110342 |  | 2025-12-04 | 2025-11-04 | Completed | 2025-11-04 | 2025-12-04 | 2025-11-03 | 2025-11-04 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-10 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-21 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-10 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-20 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-11 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202511040420-GCI | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | CHEONG/SENG/WAH/7018000306
1560H_AD | Jalan Ss 21_39 | DU00006271566 | Central | Selangor | 3.135078 | 101.621474 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Northbound site already rerouted | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1917H_AD | SS2 Murni | DU00006271567 | Central | Selangor | 3.119964 | 101.622366 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_28M NE_1917H 15G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Lo x1. FE_2913A. 18G_DP_0.6M(MDD) x1. RTN910A x1 XMC_5D , Sub B_Hi x1. | MW New Link / Reroute | Reroute the existing NLOS to new FE due to 1211A will be dismantle . New link config with 15G_2+0_28M to new FE 1210A routing. Site Urgent , plan 15G MW. Site Impacted : 1917A collocate 3017M . NE_1917H 1.Install new 15G_DP_0.6M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub B_Lo. 4.Create service cross connect. 5.Traffic migrate to new link and new FE routing. 6.Decom existing NLOS (1917H-1211A). FE_2913A. 1.Install new 15G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM82+0. 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.Traffic migrate to new link and new FE routing. 7.Decom existing NLOS (1211A-1917HA). ** Based on feedback from team the FE 1211A site facing an access issue. Resulting , existing equipment unable to decom indefinitely** | Reroute the existing NLOS to new FE due to 1211A will be dismantle . New link config with 15G_2+0_28M to new FE 1210A routing. Site Urgent , plan 15G MW. Site Impacted : 1917A collocate 3017M . NE_1917H 1.Install new 15G_DP_0.6M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub B_Lo. 4.Create service cross connect. 5.Traffic migrate to new link and new FE routing. 6.Decom existing NLOS (1917H-1211A). | Reroute the existing NLOS to new FE due to 1211A will be dismantle . New link config with 15G_2+0_28M to new FE 1210A routing. Site Urgent , plan 15G MW. Site Impacted : 1917A collocate 3017M . FE_2913A. 1.Install new 15G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM82+0. 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.Traffic migrate to new link and new FE routing. 7.Decom existing NLOS (1211A-1917HA). | XMC_5D | MDD | 15G | 0.6 | 0.6 | Magicell | SQ202511270694-Magicell | Magicell | SQ202511070103-Magicell // SQ202511070132-Magicell // SQ202511240180-Magicell | 2025-12-05 | 2025-12-10 | Completed | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-04 | 2025-12-05 | 2025-12-04 | 2025-12-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110358 |  | 2025-12-04 | 2025-11-05 | Completed | 2025-11-04 | 2025-12-04 | 2025-11-03 | 2025-11-05 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-13 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-21 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | AKMAL//BIN RAZALI/6794000078 |  | 2025-11-13 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-20 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-13 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202511040420-GCI | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | CHEONG/SENG/WAH/7018000306
1552H_AD | 99 Speedmart Damansara Jaya | DU00006271568 | Central | Selangor | 3.126415 | 101.615203 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Northbound site already rerouted | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1210A_AD | SS 2 | DU00006271569 | Central | Selangor | 3.118944 | 101.620255 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_1210A 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Hi x1. FE_2913A. 18G_DP_0.6M(MDD) x1. RTN910A x1. 10G SFP Module x2. Fiber patch core x 1 pairs XMC_5D , Sub B_Lo x1. | MW New Link / Reroute | Reroute the existing link 18G_2+0_112M due to FE will be dismantle. New link config with 18G_2+0_112M with new FE routing. Impacted site : 1320H , 1210A , 3005M , campus site wifi , 2109B , 2079B. ** Transfer all config from CP 1211A MAC_001 , GE_0/2/21 and GE_0/2/22 to New CP port (New port will be assign by OPS team)" NE_1210A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross conect and EPLA. 5.Enable GE1 , ETH patching to existing 1210A_RTN01 ( ID: 26682). 6.Traffic migarte to new link and new FE routing. 7.Decom existing link (1210A-1211A). FE_2913A. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new XMC_5D , Sub B_Lo. 4.Create service cross connect EPLA. 5.Create new Inband DCN and patching to Fiber 10G port. 6.Traffic migrate to new link and new FE routing. 7.Decom existing link (1211A-1210A). ** Based on feedback from team the FE 1211A site facing an access issue. Resulting , existing equipment unable to decom indefinitely** | Reroute the existing link 18G_2+0_112M due to FE will be dismantle. New link config with 18G_2+0_112M with new FE routing. Impacted site : 1320H , 1210A , 3005M , campus site wifi , 2109B , 2079B. ** Transfer all config from CP 1211A MAC_001 , GE_0/2/21 and GE_0/2/22 to New CP port (New port will be assign by OPS team)" NE_1210A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross conect and EPLA. 5.Enable GE1 , ETH patching to existing 1210A_RTN01 ( ID: 26682). 6.Traffic migarte to new link and new FE routing. 7.Decom existing link (1210A-1211A). | Reroute the existing link 18G_2+0_112M due to FE will be dismantle. New link config with 18G_2+0_112M with new FE routing. Impacted site : 1320H , 1210A , 3005M , campus site wifi , 2109B , 2079B. ** Transfer all config from CP 1211A MAC_001 , GE_0/2/21 and GE_0/2/22 to New CP port (New port will be assign by OPS team)" FE_2913A. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new XMC_5D , Sub B_Lo. 4.Create service cross connect EPLA. 5.Create new Inband DCN and patching to Fiber 10G port. 6.Traffic migrate to new link and new FE routing. 7.Decom existing link (1211A-1210A). | XMC_5D | MDD | 18G | 0.6 | 0.6 | Magicell | SQ202511270694-Magicell | Magicell | SQ202511070103-Magicell // SQ202511070132-Magicell // SQ202511240180-Magicell // SQ202512120102-Magicell |  |  | Ongoing | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25110362 |  | 2025-12-04 | 2025-11-04 | Completed | 2025-11-04 | 2025-12-04 | 2025-11-03 | 2025-11-04 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-21 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-21 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-14 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-20 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-05 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202511040420-GCI | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | CHEONG/SENG/WAH/7018000306
2152A_AD | SS22 (REL) | DU00006271570 | Central | Selangor | 3.128567 | 101.616896 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M NE_2152A 15G_DP_0.6M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D_Sub A_Lo x1. FE_2029A 15G_DP_0.6M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D_Sub A_Hi x1. | MW New Link / Reroute | Reroute to new FE due to 1211A will be dismantle. New link configuration with 15G_4+0_28M to new FE 2029A.Site Urgent , plan install 15G MW. Site Impacted : 2152A , 1552H , 1560H. NE_2152A 1.Install new 15G_DP_0.6M(MDD). 2.Install new RTN910A (RTN no provide by OPS team). 3.Install 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Install new XMC_5D_Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , ETH patching to existing 2152A_RTN03. 7.Traffic migrate to new link and new FE routing. 8.No decom due to original RTN direct connect to Fiber. FE_2029A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A (RTN no provide by OPS team). 3.Install 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Install new XMC_5D_Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Enable GE 1 , ETH patching to existing 2029A_RTN01. 7.Traffic migrate to new link and new FE routing. 8.No decom due to original RTN direct connect to Fiber. ** Based on feedback from team the FE 1211A site facing an access issue. Resulting , existing equipment unable to decom indefinitely** | Reroute to new FE due to 1211A will be dismantle. New link configuration with 15G_4+0_28M to new FE 2029A. Site Urgent , plan install 15G MW. Site Impacted : 2152A , 1552H , 1560H. NE_2152A 1.Install new 15G_DP_0.6M(MDD). 2.Install new RTN910A (RTN no provide by OPS team). 3.Install 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Install new XMC_5D_Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , ETH patching to existing 2152A_RTN03. 7.Traffic migrate to new link and new FE routing. 8.No decom due to original RTN direct connect to Fiber. | Reroute to new FE due to 1211A will be dismantle. New link configuration with 15G_4+0_28M to new FE 2029A. Site Urgent , plan install 15G MW. Site Impacted : 2152A , 1552H , 1560H. FE_2029A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A (RTN no provide by OPS team). 3.Install 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Install new XMC_5D_Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Enable GE 1 , ETH patching to existing 2029A_RTN01. 7.Traffic migrate to new link and new FE routing. 8.No decom due to original RTN direct connect to Fiber. | XMC_5D | MDD | 15G | 0.6 | 0.6 | Magicell | SQ202511190556-Magicell // SQ202604290559-Magicell | Magicell | SQ202511070103-Magicell // SQ202511070132-Magicell | 2025-12-06 | 2025-12-10 | Completed | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110356 |  | 2025-12-04 | 2025-11-04 | Completed | 2025-11-04 | 2025-12-04 | 2025-11-03 | 2025-11-04 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-10 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-21 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | AKMAL//BIN RAZALI/6794000078 |  | 2025-11-11 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-20 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-11-03: 2025-11-04; 2025-11-03: 2025-11-04; 2025-11-03: 2025-11-04; 2025-11-05: 2025-11-11 |  |  | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202511040420-GCI | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | CHEONG/SENG/WAH/7018000306
1220B_AD | PJU3 Payphone | DU00006271571 | Central | Selangor | 3.144476 | 101.598513 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | BBU Patching | Patch 1220B BBU to xC PTN B02219 due to existing CP 1211A having power issue | Patch 1220B BBU to xC PTN B02219 due to existing CP 1211A having power issue | N/A | [5 empty] | Magicell | SQ202512030572-Magicell | Magicell | SQ202511270687-Magicell | 2025-12-06 | 2025-12-10 | Completed | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251118AI |  | 2025-11-19 | 2025-11-20 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-25 | 2026-11-11 | 2025-11-25 | 2025-11-25 | RAZALI//BIN ABDUL HALIM/7018000224 | Magicell TI | 2025-11-25 | 2026-11-11 | 2025-11-25 | 2025-11-25 | RAZALI//BIN ABDUL HALIM/7018000224 | Magicell TI | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 | Tx Project | 2025-10-31 | 2025-11-25 | 2026-11-11 | 2025-11-25 | 2025-11-25 | RAZALI//BIN ABDUL HALIM/7018000224 | 2025-11-03: 2025-11-25; 2025-11-03: 2026-11-11; 2025-11-03: 2025-11-25; 2025-11-05: 2025-11-25 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511040420-GCI | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
1302H_AD | 99 Speedmart PJ SS 2 (1) | DU00006271572 | Central | Selangor | 3.117012 | 101.621343 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Northbound site already rerouted | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1390A_AD | Paramount Garden | DU00006271573 | Central | Selangor | 3.109956 | 101.626299 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_1390A 18G_DP_0.6M(MDD) x1. RTN910A x1 XMC_5D , Sub A_Hi x1. FE_1301B. 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. | MW New Link / Reroute | Reroute the existing link 18G_2+0_112M due to FE 1211A will be dismantle. New link config with 18G_2+0_112M to new FE 1301B routing. Site Impacted : 1390A , 3343A. NE_1390A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching to existing 1390A_RTN01. 6.Traffic migrate to new link and new FE routing. 7.Decom existing link (1390A-1211A). FE_1363B. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Create new Inband DCN. 6.Traffic migrate to new link and new FE routing. 7.Decom existing link (1211A-1390A). ** Based on feedback from team the FE 1211A site facing an access issue. Resulting , existing equipment unable to decom indefinitely** | Reroute the existing link 18G_2+0_112M due to FE 1211A will be dismantle. New link config with 18G_2+0_112M to new FE 1301B routing. Site Impacted : 1390A , 3343A. NE_1390A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching to existing 1390A_RTN01. 6.Traffic migrate to new link and new FE routing. 7.Decom existing link (1390A-1211A). | Reroute the existing link 18G_2+0_112M due to FE 1211A will be dismantle. New link config with 18G_2+0_112M to new FE 1301B routing. Site Impacted : 1390A , 3343A. FE_1363B. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Create new Inband DCN. 6.Traffic migrate to new link and new FE routing. 7.Decom existing link (1211A-1390A). | XMC_5D | MDD | 18G | 0.6 | 0.6 | Magicell | SQ202511070138-Magicell // SQ202604290559-Magicell | Magicell | SQ202511070103-Magicell // SQ202511070132-Magicell // SQ202511240180-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | NUR FATIHAH BINTI AYOB7018000236 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110360 |  | 2025-12-04 | 2025-11-04 | Completed | 2025-11-04 | 2025-12-04 | 2025-11-04 | 2025-11-04 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-13 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-13 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-06 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-13 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-05 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202511040420-GCI | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | CHEONG/SENG/WAH/7018000306
2611A13_AD | pBTS Hartalega Backyard | DU00006271574 | Central | Selangor | 2.811828 | 101.681311 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | PBTS site already relocated | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4616C_HU_1 | Masjid Puteri Jaya | DU00005438519 | Northern | Kedah | 5.611820 | 100.551270 |  |  |  |  | TI IN PLAN | ZTE |  | 00. Integrated/RFS Done | 23/05: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE_4616C New RTN910A x1. | MW Hardware Upgrade | Link Existing HW 15G&18G_3+0_28M&56M_EPLA. Swap/replaced existing RTN910A(RTN01) to new RTN910AF(RTN02). Site Impacted : 4616C. NE_4616C 1.Replaced existing RTN910A(RTN01) to RTN910AF(RTN02). Powerup and configure it. 2.Install new 1x RTN910A(RTN02) and swap existing RTN910A(RTN01). 3.Shifting existing 1x ISM8 from existing RTN910A(RTN01) and insert to new RTN910A(RTN02) on slot 03. Configure it. 4.Shifting existing 2x IF cables from existing RTN910A(RTN01) slot 03(Port 01 & 02) to new RTN910A(RTN02) on slot 07(Port 01 & 02). Configure it. 5.Shifting existing 1x IF cables from existing RTN910A(RTN01) slot 04(Port 01) to new RTN910A(RTN02) on slot 03(Port 01). Configure it. 6.Configure all channels using IS mode8. 7.Enable port 8-EM6-1 of new RTN910A(RTN02) and patching to BBU 4616C. Ensure all 3 channels working well and RAN traffic 4616C UP. 8.Return RTN910A(RTN01) to warehouse. | Link Existing HW 15G&18G_3+0_28M&56M_EPLA. Swap/replaced existing RTN910A(RTN01) to new RTN910AF(RTN02). Site Impacted : 4616C. NE_4616C 1.Replaced existing RTN910A(RTN01) to RTN910AF(RTN02). Powerup and configure it. 2.Shifting existing 1x ISM8 from existing RTN910A(RTN01) slot 03 to new RTN910A(RTN02) slot 03. Configure it. 3.Install new 1x RTN910A(RTN02) and swap existing RTN910A(RTN01). 4.Shifting existing 1x ISM8 from existing RTN910A(RTN01) and insert to new RTN910A(RTN02) on slot 03. Configure it. 5.Shifting existing 2x IF cables from existing RTN910A(RTN01) slot 03(Port 01 & 02) to new RTN910A(RTN02) on slot 07(Port 01 & 02). Configure it. 6.Shifting existing 1x IF cables from existing RTN910A(RTN01) slot 04(Port 01) to new RTN910A(RTN02) on slot 03(Port 01). Configure it. 7.Configure all channels using IS mode8. 8.Enable port 8-EM6-1 of new RTN910A(RTN02) and patching to BBU 4616C. Ensure all 3 channels working well and RAN traffic 4616C UP. 9.Return RTN910A(RTN01) to warehouse. | [6 empty] | CCSMY | SQ202505240069-CCS | CCSMY | SQ202505240083-CCS // SQ202505240084-CCS | 2025-09-04 | 2025-08-28 | Completed | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-09-02 | 2025-08-26 | 2025-08-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-28 | 2025-09-04 | 2025-08-28 | 2025-08-28 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050930 |  | 2025-05-10 | 2025-05-14 | Completed | 2025-05-09 | 2025-05-10 | 2025-05-09 | 2025-05-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-22 | 2025-05-31 | 2025-05-22 | 2025-06-04 | Saleem//Muhammed/7021000077 | CCS TI | 2025-05-22 | 2025-05-31 | 2025-05-22 | 2025-06-30 | Saleem//Muhammed/7021000077 | CCS TI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-22 | 2025-05-31 | 2025-05-22 | 2025-07-12 | Saleem//Muhammed/7021000077 | 2025-11-03: 2025-05-22; 2025-11-03: 2025-05-31; 2025-11-03: 2025-05-22; 2025-11-05: 2025-05-23 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB_AA | SQ202510300144-GTSB
4635A_HU | Kuala Kertil | DU00005184526 | Northern | Kedah | 5.606915 | 100.651210 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M. NE_4635A 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. FE_4410K. 18G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing 18G_2+0_112M. Install new parallel for 18G_2+0_112M. Load Balancing for 4410K - 4986A HU issue. Site Impacted : 4635A , 4622C. NE_4635A 1.Install 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Enable GE1 , BBU_4635A traffic migrate to new parallel link 18G_2+0_112M. 6.No decom existing MW link. FE_4410K. 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching to RTN910A_RTN07_GE1. 6.No decom existing MW link. | Existing 18G_2+0_112M. Install new parallel for 18G_2+0_112M. Site Impacted : 4635A , 4622C. NE_4635A 1.Install 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Enable GE1 , BBU_4635A traffic migrate to new parallel link 18G_2+0_112M. 6.No decom existing MW link. | Existing 18G_2+0_112M. Install new parallel for 18G_2+0_112M. Site Impacted : 4635A , 4622C. FE_4410K. 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching to new RTN910A_RTN07_GE1. 6.No decom existing MW link. | XMC_5D | MDD | 18G | 0.6 | 1.2 | CCSMY | SQ202504280454-CCS | NWAVE | SQ202510010668-N-Wave // SQ202510010669-N-Wave | 2025-11-28 | 2025-11-28 | Completed | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-24 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092656 |  | 2025-09-27 | 2025-09-29 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-01 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-09 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-08 | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-14 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2025-11-03: 2025-10-01; 2025-11-03: 2025-11-01; 2025-11-03: 2025-10-01; 2025-11-05: 2025-10-01 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | CHEONG/SENG/WAH/7018000306
9257R_AD | SamalajuTownship | DU00006678169 | Sarawak | Sarawak | 3.540140 | 113.298800 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041808 |  | 2026-04-19 | 2026-04-18 | Completed | 2026-04-18 | 2026-04-19 | 2026-04-18 | 2026-04-18 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202603270348-GCI
2065E_AD | MovenpickHotel & Convention Centre (eB) | DU00006678170 | Central | Selangor | 2.789394 | 101.677944 | [7 empty] | 01. Pending Planning |  | TSS+TI |  | Fiber Patch Cord x 1 Pair SFP Module x1. | BBU Patching | Migrate 2065E to TM LL Site Impacted : 2065E 1.BBU_2065E dierect patching to TM LL with Fiber Patch cord. 2.Access port UNI 1. ** Dismantle MW link , pls refer DU ID 2065E_Decomm. | Migrate 2065E to TM LL Site Impacted : 2065E 1.BBU_2065E dierect patching to TM LL with Fiber Patch cord. 2.Access port UNI 1. | [6 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26033097 |  | 2026-03-31 |  | Ongoing | 2026-03-30 | 2026-03-31 | 2026-03-30 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202603270220-GCI | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | CHEONG/SENG/WAH/7018000306
9256A_IPR | Kerait | DU00006678171 | Sarawak | Sarawak | 1.040275 | 110.677665 | [9 empty] | TSS+TI |  | NE_9256A New suitable SFP Module 10G 1310nm x1(for IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW IDU Patching | ****IMPORTANT NOTE: 1.OPS TEAM NEED TO ENSURE DU FOR 9202R_AD, 9020R_PostMOCN, 9021R_PostMOCN & Q01246 NOT DOING YET BEFORE IMPLEMENT THIS DU AS THOSE DU MENTION HAD DIFFERENT SOLUTION. 2.PLEASE APPLY CRQ FOR EB(9100E) FIRST AS PHYSICALLY STILL USE SAME LL 9256A-LL-9999A BUT DIFFERENT PORT AT IBEAM GE0/9/9 COMPARED TO TRAFFIC 9020R,9021R, 9202R & 9256R CURRENTLY USED PORT AT IBEAM GE0/9/4.**** Perform upgrade 1G(Electrical) to 10G(Optical) port. Site Impacted: 9021R, 9256A, 9202R, 9257A & 9100E. NE_9256A 1.Enable port 8-EM6-3(10G Optical) of existing RTN910AF(RTN01, NEID 9-20433). 2.Insert suitable new Optical SFP Module 10G 1310nm x1 into port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-20433). Enable and configure it. 3.Patching Optical patch cord in between port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-20433) and new Sacofa LL 10G port(ETH 1-4-5). 4.Request new xD Vlan DCN & Vlan Services. 5.Migrate Traffics 9021R, 9256A, 9202R, 9257A & 9100E into new Sacofa LL 10G port(ETH 1-4-5). Be aware as currently 9100E using port GE0/9/9 at IBeam compared to other traffics like 9021R, 9256A, 9202R, 9257A using port GE0/9/4 at IBeam. | ****IMPORTANT NOTE: 1.OPS TEAM NEED TO ENSURE DU FOR 9202R_AD, 9020R_PostMOCN, 9021R_PostMOCN & Q01246 NOT DOING YET BEFORE IMPLEMENT THIS DU AS THOSE DU MENTION HAD DIFFERENT SOLUTION. 2.PLEASE APPLY CRQ FOR EB(9100E) FIRST AS PHYSICALLY STILL USE SAME LL 9256A-LL-9999A BUT DIFFERENT PORT AT IBEAM GE0/9/9 COMPARED TO TRAFFIC 9020R,9021R, 9202R & 9256R CURRENTLY USED PORT AT IBEAM GE0/9/4.**** Perform upgrade 1G(Electrical) to 10G(Optical) port. Site Impacted: 9021R, 9256A, 9202R, 9257A & 9100E. NE_9256A 1.Enable port 8-EM6-3(10G Optical) of existing RTN910AF(RTN01, NEID 9-20433). 2.Insert suitable new Optical SFP Module 10G 1310nm x1 into port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-20433). Enable and configure it. 3.Patching Optical patch cord in between port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-20433) and new Sacofa LL 10G port(ETH 1-4-5). 4.Request new xD Vlan DCN & Vlan Services. 5.Migrate Traffics 9021R, 9256A, 9202R, 9257A & 9100E into new Sacofa LL 10G port(ETH 1-4-5). Be aware as currently 9100E using port GE0/9/9 at IBeam compared to other traffics like 9021R, 9256A, 9202R, 9257A using port GE0/9/4 at IBeam. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042803 |  | 2026-04-29 |  | Ongoing | 2026-04-28 | 2026-04-29 | 2026-04-28 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202603270476-GTSB
9997A_IPR | Samalaju EcoPark | DU00006678172 | Sarawak | Sarawak | 3.566822 | 113.384940 | [9 empty] | TSS+TI |  | Perform BBU patching from 1G to 10G port at 9997A. (BBU to Sacofa LL) NE_9997A New suitable SFP Module 10G with 1Km 1310nm x1(For BBU). New Optical Patch Cord cable x1 with suitable type and length. | BBU Patching | Change patching BBU to Sacofa LL from 1G to 10G port (Sacofa Ready. Pending customer integration) Site Impacted :9997A. NE_9997A 1.Insert new suitable SFP Module 10G 1Km 1310nm into new port 10G RAN. Enable it. 2.Sacofa Ready and port provided by GOP is ETH 1-2-3. 3.Patching Optical patch cord between new port 10G RAN and new 10G port at Sacofa. | Change patching BBU to Sacofa LL from 1G to 10G port (Sacofa Ready. Pending customer integration) Site Impacted :9997A. NE_9997A 1.Insert new suitable SFP Module 10G 1Km 1310nm into new port 10G RAN. Enable it. 2.Sacofa Ready and port provided by GOP is ETH 1-2-3. 3.Patching Optical patch cord between new port 10G RAN and new 10G port at Sacofa. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042804 |  | 2026-04-29 |  | Ongoing | 2026-04-28 | 2026-04-29 | 2026-04-28 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202603270476-GTSB
8080A_HU | KgPerpat | DU00006678173 | Eastern | Pahang | 2.788789 | 103.461880 | [7 empty] | 05. Doable |  | AA | PAC | 23G_1+0_112Mhz_0.6/0.6_833Mbps | MW Remote Upgrade | Remotely upgrade from 56 to 112 Mhz |  |  | SRU2D | 23G | 23G | 0.6 | 0.6 | GTSB |  | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042172 | Release fixing clip for MW EOS due to cannot cross project | 2026-04-22 |  | Ongoing | 2026-04-21 | 2026-04-22 | 2026-04-21 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [13 empty] | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GTSB | SQ202603270463-GTSB | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | AB.RAHMAN//BIN MAT NOOH/6237001519
9157B_IPR | KgSamariang | DU00006678174 | Sarawak | Sarawak | 1.598337 | 110.331421 | [9 empty] | TSS+TI |  | 2X 10G 1KM SFP | IPRAN Port Upgrade | 9157B 10G PORT 9157B/9157B-LL-9999A INSTALL 1 10G SFP OPTICAL AT LL PORT (PENDING PORT INFO) INSTALL 1 10G SFP OPTICAL AT HW 9157B RTN01 8-EM6-3(PORT-3) PATCHING OPTICAL PATCH CORD LL PORT ETH (PENDING PORT INFO) to HW 9157B RTN01 8-EM6-3(PORT-3) RECONFIGURE TRAFFIC FOR ALL SITES: 9157B, 9714B | [7 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042805 |  | 2026-04-29 |  | Ongoing | 2026-04-28 | 2026-04-29 | 2026-04-28 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202603270348-GCI | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
W01428_HU | W066BB_W01428OD_KM10_JLNCHERAS_JBTANPERHILITAN | DU00006678175 | Central | Kuala Lumpur | 3.084740 | 101.744860 | [7 empty] | 01. Pending Planning |  | AA | PAC | N/A | MW Remote Upgrade | MW Remote upgrade from 23G_1+0_56M to 23G_1+0_112M_512QAM NE W01428 config to 112M with Modulation 512QAM FE W00677 config to 112M with Modulation 512QAM | NE W01428 config to 112M with Modulation 512QAM | FE W00677 config to 112M with Modulation 512QAM | SRU2D | MA06U18 | 23G | 0.6 | 0.6 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042170 | Release fixing clip for MW EOS due to cannot cross project | 2026-04-22 | 2026-04-23 | Completed | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [13 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GTSB | SQ202603270457-GTSB | 2026-03-29 | 2026-03-29 | 2026-03-29 | 2026-03-29 | LIM//WEI CHONG/6798000110
7008L_HU | KAMPUNGBONGAWAN (REL) | DU00006678176 | Sabah | Sabah | 5.538258 | 115.862074 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 7008L-7702A ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS IMPACTED SITE: 7008L | MW REMOTE UPGRADE LINK 7008L-7702A ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS IMPACTED SITE: 7008L | MW REMOTE UPGRADE LINK 7008L-7702A ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS IMPACTED SITE: 7008L | XMC3 | MAC | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-21 | [20 empty] | GCI | SQ202603270343-GCI | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
9419B_IPR | UpperLanang Industrial MP | DU00006678177 | Sarawak | Sarawak | 2.241580 | 111.858440 | [9 empty] | TSS+TI |  | 2X 10G 1KM SFP | IPRAN Port Upgrade | 9419B 10G PORT 9419B/9419B-LL-9368A INSTALL 1 10G SFP OPTICAL AT LL PORT (PENDING PORT INFO) INSTALL 1 10G SFP OPTICAL AT HW 9419B RTN01 8-EM6-3(PORT-3) PATCHING OPTICAL PATCH CORD LL PORT ETH (PENDING PORT INFO) to HW 9419B RTN01 8-EM6-3(PORT-3) RECONFIGURE TRAFFIC FOR ALL SITES: 9419B, 9033C | [7 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042806 |  | 2026-04-29 |  | Ongoing | 2026-04-28 | 2026-04-29 | 2026-04-28 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202603270348-GCI | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01370_HU | Q125A_Q01370OD_LAWASAIRPORT | DU00006678178 | Sarawak | Sarawak | 4.851599 | 115.406102 | [9 empty] | TSS+AA+TI |  | Install new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. NE_9331K/Q01370 New 15G_0.6(MDD)+Dual Coupler x1. Re-use existing RTN910AF(RTN01, NEID 9-38895). New XMC_5D Pro, Sub A_Lo x2. New ISM8 x2. New IF cables with suitable length and type x4 RUN. FE_9641A New 15G_1.2M(MDD)+Dual Coupler x1. Re-use existing RTN910AF(RTN03, NEID 9-38896). New XMC_5D Pro, Sub A_Hi x2. New ISM8 x2. New IF cables with suitable length and type x4 RUN. | MW Parallel Link | ****IMPORTANT NOTE: 1. TO CHECK SPACING TO MOUNT NEW ANTENNA AT NE(0.6M) & FE(1.2M) AND TOWER LOADING CONDITION IF MOUNT 2ND ANTENNA 0.6M AT NE(MONOPOLE 16M).**** Existing HW MW Link 9331K/Q01370-9641A, 15G_2+0_28MHZ_1024QAM_EPLA. Install new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. Later, combine existing HW MW Link 9331K/Q01370-9641A, 15G_2+0_28MHZ_1024QAM_EPLA and new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. Become new HW MW Link 9331K/Q01370-9641A, 15G_6+0_28MHZ_256QAM&1024QAM_EPLA. Site Impacted : 9331K/Q01370. NE_9331K/Q01370 1.Install new 15G_DP_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN01, NEID 9-38895) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Lo x2. 4.Lay new IF cables with suitable length and type x4 RUN at slot 03(Port 1 & 2) and slot 04(Port 1 & 2). 5.Build new HW MW Parallel Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. 6.Re-use existing Vlan DCN and Vlan Services. 7.Later, combine existing HW MW Link 9331K/Q01370-9641A, 15G_2+0_28MHZ_1024QAM_EPLA and new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. Become new HW MW Link 9331K/Q01370-9641A, 15G_6+0_28MHZ_256QAM&1024QAM_EPLA. 8.Migrate traffic 9331K/Q01370 into new HW MW Link 9331K/Q01370-9641A, 15G_6+0_28MHZ_256QAM&1024QAM_EPLA. FE_9641A 1.Install new 15G_DP_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN03, NEID 9-38896) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Hi x2. 4.Lay new IF cables with suitable length and type x4 RUN at slot 03(Port 1 & 2) and slot 04(Port 1 & 2). 5.Build new HW MW Parallel Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. 6.Re-use existing Vlan DCN and Vlan Services. 7.Later, combine existing HW MW Link 9331K/Q01370-9641A, 15G_2+0_28MHZ_1024QAM_EPLA and new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. Become new HW MW Link 9331K/Q01370-9641A, 15G_6+0_28MHZ_256QAM&1024QAM_EPLA. 8.Migrate traffic 9331K/Q01370 into existing port at IBeam(CP 9074A). | ****IMPORTANT NOTE: 1. TO CHECK SPACING TO MOUNT NEW ANTENNA AT NE(0.6M) & FE(1.2M) AND TOWER LOADING CONDITION IF MOUNT 2ND ANTENNA 0.6M AT NE(MONOPOLE 16M).**** Existing HW MW Link 9331K/Q01370-9641A, 15G_2+0_28MHZ_1024QAM_EPLA. Install new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. Later, combine existing HW MW Link 9331K/Q01370-9641A, 15G_2+0_28MHZ_1024QAM_EPLA and new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. Become new HW MW Link 9331K/Q01370-9641A, 15G_6+0_28MHZ_256QAM&1024QAM_EPLA. Site Impacted : 9331K/Q01370. NE_9331K/Q01370 1.Install new 15G_DP_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN01, NEID 9-38895) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Lo x2. 4.Lay new IF cables with suitable length and type x4 RUN at slot 03(Port 1 & 2) and slot 04(Port 1 & 2). 5.Build new HW MW Parallel Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. 6.Re-use existing Vlan DCN and Vlan Services. 7.Later, combine existing HW MW Link 9331K/Q01370-9641A, 15G_2+0_28MHZ_1024QAM_EPLA and new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. Become new HW MW Link 9331K/Q01370-9641A, 15G_6+0_28MHZ_256QAM&1024QAM_EPLA. 8.Migrate traffic 9331K/Q01370 into new HW MW Link 9331K/Q01370-9641A, 15G_6+0_28MHZ_256QAM&1024QAM_EPLA. | ****IMPORTANT NOTE: 1. TO CHECK SPACING TO MOUNT NEW ANTENNA AT NE(0.6M) & FE(1.2M) AND TOWER LOADING CONDITION IF MOUNT 2ND ANTENNA 0.6M AT NE(MONOPOLE 16M).**** Existing HW MW Link 9331K/Q01370-9641A, 15G_2+0_28MHZ_1024QAM_EPLA. Install new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. Later, combine existing HW MW Link 9331K/Q01370-9641A, 15G_2+0_28MHZ_1024QAM_EPLA and new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. Become new HW MW Link 9331K/Q01370-9641A, 15G_6+0_28MHZ_256QAM&1024QAM_EPLA. Site Impacted : 9331K/Q01370. FE_9641A 1.Install new 15G_DP_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN03, NEID 9-38896) and insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Hi x2. 4.Lay new IF cables with suitable length and type x4 RUN at slot 03(Port 1 & 2) and slot 04(Port 1 & 2). 5.Build new HW MW Parallel Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. 6.Re-use existing Vlan DCN and Vlan Services. 7.Later, combine existing HW MW Link 9331K/Q01370-9641A, 15G_2+0_28MHZ_1024QAM_EPLA and new parallel HW MW Link 9331K/Q01370-9641A, 15G_4+0_28MHZ_256QAM_EPLA. Become new HW MW Link 9331K/Q01370-9641A, 15G_6+0_28MHZ_256QAM&1024QAM_EPLA. 8.Migrate traffic 9331K/Q01370 into existing port at IBeam(CP 9074A). | XMC-5D Pro | MDD | 15G | 15G_0.6M(MDD)+Dual Coupler x1 | 15G_1.2M(MDD)+Dual Coupler x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041809 |  | 2026-04-19 | 2026-04-18 | Completed | 2026-04-18 | 2026-04-19 | 2026-04-18 | 2026-04-18 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202603270476-GTSB
7885A_AD | PekanBaru Kinabatangan | DU00006678179 | Sabah | Sabah | 5.569822 | 117.848138 | [7 empty] | 05. Doable |  | TSS+AA+TI+Dismantle |  | 23G_2+0_112M_512QAM_EPLA. NE_7885A New 23G_SP_1.2M(MAC)+Hybrid Coupler x1. New RTN910AF(RTN01). New IF cables with suitable length and type x2 RUN. New XMC_3E, Sub A&B_Lo x2. New CAT6 cable x1. FE_S00601 New 23G_SP_1.2M(MAC)+Hybrid Coupler x1. New RTN910AF(RTN01). New IF cables with suitable length and type x2 RUN. New XMC_3E, Sub A&B_Lo x2. New CAT6 cable x2. | MW New Link / Reroute | Existing HW MW Link 7885A-7961A, 13G_2+0_28MHZ_512QAM_448M and HW MW Link 7885A-7961A, 15G_2+0_28MHZ_512QAM_448M. Install new MW Link/Reroute HW MW Link 7885A-S00601, 23G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link : 1.7885A-7961A, 13G_2+0_28MHZ_512QAM_448M. 2.7885A-7961A, 15G_2+0_28MHZ_512QAM_448M. Site Impacted : 7885A. NE_7885A 1.Install new 23G_SP_1.2M(MAC)+Hybrid Coupler x1. 2.Install new RTN910AF(RTN01) x1. 3.Install XMC_3E, Sub A&B_Lo x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 Port 1 and 2. 5.Build new MW Link/Reroute HW MW Link 7885A-S00601, 23G_2+0_110MHZ_512QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN01). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN01) to existing BBU(7885A) 8.Request new xC Vlan DCN and Vlan Services. 9.Migrate traffic 7885A via new MW Link/Reroute HW MW Link 7885A-S00601, 23G_2+0_110MHZ_512QAM_EPLA. 10.Later, decom existing HW MW Link : 7885A-7961A, 13G_2+0_28MHZ_512QAM_448M. 7885A-7961A, 15G_2+0_28MHZ_512QAM_448M. FE_S00601 1.Install new 23G_SP_1.2M(MAC)+Hybrid Coupler x1. 2.Install new RTN910AF(RTN01) x1. 3.Install XMC_3E, Sub A&B_Hi x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 Port 1 and 2. 5.Build new MW Link/Reroute HW MW Link 7885A-S00601, 23G_2+0_110MHZ_512QAM_EPLA. 6.Enable port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN01). 7.Request new 2x 1G(Electrical) port at PTN/Cisco from ZTE IPRAN team. 8.Perform patching and config LAG in between port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN01) and new 2x 1G(Electrical) port at PTN/Cisco. 9.Request new xC Vlan DCN and Vlan Services. 10.Migrate traffic 7885A via new LAG 2x 1G(Electrical) port at PTN/Cisco. 11.Later, decom existing HW MW Link : 7885A-7961A, 13G_2+0_28MHZ_512QAM_448M. 7885A-7961A, 15G_2+0_28MHZ_512QAM_448M. | Existing HW MW Link 7885A-7961A, 13G_2+0_28MHZ_512QAM_448M and HW MW Link 7885A-7961A, 15G_2+0_28MHZ_512QAM_448M. Install new MW Link/Reroute HW MW Link 7885A-S00601, 23G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link : 1.7885A-7961A, 13G_2+0_28MHZ_512QAM_448M. 2.7885A-7961A, 15G_2+0_28MHZ_512QAM_448M. Site Impacted : 7885A. NE_7885A 1.Install new 23G_SP_1.2M(MAC)+Hybrid Coupler x1. 2.Install new RTN910AF(RTN01) x1. 3.Install XMC_3E, Sub A&B_Lo x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 Port 1 and 2. 5.Build new MW Link/Reroute HW MW Link 7885A-S00601, 23G_2+0_110MHZ_512QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN01). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN01) to existing BBU(7885A) 8.Request new xC Vlan DCN and Vlan Services. 9.Migrate traffic 7885A via new MW Link/Reroute HW MW Link 7885A-S00601, 23G_2+0_110MHZ_512QAM_EPLA. 10.Later, decom existing HW MW Link : 7885A-7961A, 13G_2+0_28MHZ_512QAM_448M. 7885A-7961A, 15G_2+0_28MHZ_512QAM_448M. | Existing HW MW Link 7885A-7961A, 13G_2+0_28MHZ_512QAM_448M and HW MW Link 7885A-7961A, 15G_2+0_28MHZ_512QAM_448M. Install new MW Link/Reroute HW MW Link 7885A-S00601, 23G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link : 1.7885A-7961A, 13G_2+0_28MHZ_512QAM_448M. 2.7885A-7961A, 15G_2+0_28MHZ_512QAM_448M. Site Impacted : 7885A. FE_S00601 1.Install new 23G_SP_1.2M(MAC)+Hybrid Coupler x1. 2.Install new RTN910AF(RTN01) x1. 3.Install XMC_3E, Sub A&B_Hi x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 Port 1 and 2. 5.Build new MW Link/Reroute HW MW Link 7885A-S00601, 23G_2+0_110MHZ_512QAM_EPLA. 6.Enable port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN01). 7.Request new 2x 1G(Electrical) port at PTN/Cisco from ZTE IPRAN team. 8.Perform patching and config LAG in between port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN01) and new 2x 1G(Electrical) port at PTN/Cisco. 9.Request new xC Vlan DCN and Vlan Services. 10.Migrate traffic 7885A via new LAG 2x 1G(Electrical) port at PTN/Cisco. 11.Later, decom existing HW MW Link : 7885A-7961A, 13G_2+0_28MHZ_512QAM_448M. 7885A-7961A, 15G_2+0_28MHZ_512QAM_448M. | XMC-3E | MAC | 23G | 23G_SP_1.2M(MAC)+Hybrid Coupler x1 | 23G_SP_1.2M(MAC)+Hybrid Coupler x1 | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042750 |  | 2026-04-28 | 2026-04-29 | Completed | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-29 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-09 | 2026-06-09 | 2026-05-09 | 2026-05-09 | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-05-09 | 2026-06-09 | 2026-05-09 |  | MIKE MICRON DOLIK6000068237 | NR Service TI | [7 empty] | 2026-05-09 | 2026-06-09 | 2026-05-09 |  | MIKE MICRON DOLIK6000068237 | 2025-11-03: 2026-05-09; 2025-11-03: 2026-06-09; 2025-11-03: 2026-05-09; 2025-11-05: 2026-05-09 | [7 empty] | GTSB | SQ202603270472-GTSB
3613B_HU | AEOND Kayangan Outdoor | DU00006678180 | Central | Selangor | 3.076624 | 101.549114 | [7 empty] | 04. Pending DO |  | TSS+AA+TI | L1+ATP+PAC | 23G_2+0_112M. NE_3613B. 23G_DP_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub A & B_Hi x2. FE_1367A. 23G_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. | MW Parallel Link | Existing link 23G_2+0_56M Install parallel link 23G_2+0_112M. Site Impacted : 3613B_IBC , 3236B. NE_3613B. 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 3613B_RTN01 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.No decomm existing MW link. FE_1367A. 1.Install new 23G_0.6M(MAC). 2.Reuse existing 1367A_RTN04 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.No decomm existing MW link. | Existing link 23G_2+0_56M Install parallel link 23G_2+0_112M. Site Impacted : 3613B_IBC , 3236B. NE_3613B. 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 3613B_RTN01 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.No decomm existing MW link. | Existing link 23G_2+0_56M Install parallel link 23G_2+0_112M. Site Impacted : 3613B_IBC , 3236B. FE_1367A. 1.Install new 23G_0.6M(MAC). 2.Reuse existing 1367A_RTN04 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.No decomm existing MW link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202604150090-GCI | GCI | SQ202604100643-GCI // SQ202604100645-GCI |  |  | Ongoing | 2026-04-12 | 2026-04-12 | 2026-04-12 | 2026-04-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26032655 |  | 2026-03-27 | 2026-04-07 | Completed | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-04-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-07 | 2026-04-14 | 2026-04-06 | 2026-04-07 | LEEROY QUIRINUS6000070995 | GCI TI | 2026-04-07 | 2026-04-14 | 2026-04-06 | 2026-05-05 | LEEROY QUIRINUS6000070995 | GCI TI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-09 | 2026-04-07 | 2026-04-14 | 2026-04-06 | 2026-05-05 | LEEROY QUIRINUS6000070995 | 2025-11-03: 2026-04-07; 2025-11-03: 2026-04-14; 2025-11-03: 2026-04-06; 2025-11-05: 2026-04-07 | [7 empty] | GCI | SQ202603270220-GCI | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | CHEONG/SENG/WAH/7018000306
1679H_LOS | 99 SpeedmartHulu Bernam | DU00006678181 | Central | Selangor | 3.674005 | 101.520821 | [7 empty] | 01. Pending Planning |  | TSS |  |  | MW New Link / Reroute | TSS ONLY ALL LOS OPTION BLOCKED. STRUCTURE LOW FE candidate; 1061A❌ 1062A❌ 2582A❌ 3820A❌ 4073K❌ | [7 empty] | GTSB | SQ202604060610-GTSB | GTSB | No PR required-Work at TSS only |  |  | Ongoing | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-06 | 2026-04-20 | 2026-04-06 | 2026-04-06 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202603270220-GCI | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
2432A_HU | Kundang (KJS) | DU00006678182 | Central | Selangor | 3.290591 | 101.522942 | [7 empty] | 01. Pending Planning |  | TSS+AA+TI | L1+ATP+PAC | 23G_1+0_112M. NE_2432A 23G_SP_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub A_Lo x1. FE_1422A. 23G_SP_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub A_Hi x1. | MW Parallel Link | Existing link 18G_1+0_112M Install parallel link 18G_1+0_112M. Site Impacted : 1147K , 1125D. NE_2432A 1.Install new 23G_SP_0.6M(MAC). 2.Reuse existing 2432A_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A_Lo. 5.Create service cross connect and EPLA with eixsting MW link. 6.No decomm MW Link. FE_1422A. 1.Install new 23G_SP_0.6M(MAC). 2.Reuse existing 1422A_RTN02 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A_Hi. 5.Create service cross connect and EPLA with existing MW link. 6.No decomm MW link. | Existing link 18G_1+0_112M Install parallel link 18G_1+0_112M. Site Impacted : 1147K , 1125D. NE_2432A 1.Install new 23G_SP_0.6M(MAC). 2.Reuse existing 2432A_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A_Lo. 5.Create service cross connect and EPLA with eixsting MW link. 6.No decomm MW Link. | Existing link 18G_1+0_112M Install parallel link 18G_1+0_112M. Site Impacted : 1147K , 1125D. FE_1422A. 1.Install new 23G_SP_0.6M(MAC). 2.Reuse existing 1422A_RTN02 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_3E , Sub A_Hi. 5.Create service cross connect and EPLA with existing MW link. 6.No decomm MW link. | XMC_3E | MAC | 18G | 0.6 | 0.6 | GTSB | SQ202604060610-GTSB | GTSB | SQ202604060602-GTSB // SQ202604060606-GTSB |  |  | Ongoing | 2026-04-23 | 2026-05-07 | 2026-04-23 | 2026-04-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-05-07 | 2026-04-23 | 2026-04-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-04-24 | 2026-04-23 | 2026-04-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26032517 |  | 2026-03-26 | 2026-03-30 | Completed | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-30 | 2026-03-31 | 2026-03-30 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-03-30 | 2026-03-31 | 2026-03-30 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-07 | 2026-03-30 | 2026-03-31 | 2026-03-30 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2025-11-03: 2026-03-30; 2025-11-03: 2026-03-31; 2025-11-03: 2026-03-30; 2025-11-05: 2026-04-16 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202603270220-GCI | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | CHEONG/SENG/WAH/7018000306
1172L_AD | LOJIIWK_SIERAMASUTAMA(REL) | DU00006678183 | Central | Selangor | 3.203125 | 101.588100 | [7 empty] | 01. Pending Planning |  | AA | PAC |  | MW Remote Upgrade | MW Remote Software upgrade from 23G_1+0_56M to 23G_1+0_112M_512QAM NE 1172L config to 112M with Modulation 512QAM FE 1049B config to 112M with Modulation 512QAM |  |  | XMC3 | MAC | 23G | 0.6 | 0.6 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202603270457-GTSB | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | LIM//WEI CHONG/6798000110
1372H_AD | 99Speedmart USJ Avenue | DU00006678184 | Central | Selangor | 3.062151 | 101.567669 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI+Dismantle |  | ETH Cat 6 cable x1 | MW IDU Patching | Migrate traffic at FE to xC Backhaul. Tx Route Before : 1372H-NLOS-2603B-2021B. Tx Route After : 1372H-NLOS-2603B/B00395. ** Refer 2603B_DECOM to decom the existing MW link after migrate traffic at FE to xC backhual. Site Impacted : 1372H. FE_2603B 1. Existing NLOS radio patching to B00395. 2.Create New Inband DCN. |  | Migrate traffic at FE to xC Backhaul. Tx Route Before : 1372H-NLOS-2603B-2021B. Tx Route After : 1372H-NLOS-2603B/B00395. ** Refer 2603B_DECOM to decom the existing MW link after migrate traffic at FE to xC backhual. Site Impacted : 1372H. FE_2603B 1. Existing NLOS radio patching to B00395. 2.Create New Inband DCN. | [5 empty] | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050311 |  | 2026-05-04 |  | Ongoing | 2026-05-03 | 2026-05-04 | 2026-05-03 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202603270220-GCI | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | CHEONG/SENG/WAH/7018000306
7326R_HU | Sk Pahu Hibaan | DU00006678185 | Sabah | Sabah | 5.951176 | 116.544560 | [7 empty] | 05. Doable |  | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 2X RTN910A 1X 15G 0.6M DP ANTENNA 1X 15G 1.2M DP ANTENNA | MW Swap | MW SWAP LINK 7326R-7021A WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_256QAM_800MBPS_XMC5D_SUB_B_WITH CA_LINK_4.81KM DISMANTLE EXISTING LINK IMPACTED: 7326R | 1. INSTALL NEW RTN910 AND 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 AND 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA 5. DISMANTLE EXISTING LINK | XMC5D | MDD | 15G | 0.6 | 1.2 | NR services |  | NR services | SQ202605070549-NR Services // SQ202605070551-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041470 |  | 2026-04-15 | 2026-04-30 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-30 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-20 | 2026-05-20 | 2026-04-20 |  | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-04-20 | 2026-05-20 | 2026-04-20 |  | MIKE MICRON DOLIK6000068237 | NR Service TI | [7 empty] | 2026-04-20 | 2026-05-20 | 2026-04-20 |  | MIKE MICRON DOLIK6000068237 | 2025-11-03: 2026-04-20; 2025-11-03: 2026-05-20; 2025-11-03: 2026-04-20 | [7 empty] | GCI | SQ202603270343-GCI | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
9386B_HU | Balingian | DU00006678186 | Sarawak | Sarawak | 2.929831 | 112.542775 | [9 empty] | TSS+AA+TI |  | 7G_4+0_28M_512QAM_EPLA NE_9386B New A7WD24MS-3NX+Hybrid Coupler x1. New RTN910AF x1. New ISM8 x2. New XMC_3, Sub I,J,K&L_Hi x4. New IF cables with suitable length and type 4x RUN. FE_9126A New A7WD18MS-3NX+Coupler x1. New RTN910AF x1. New ISM8 x2. New XMC_3, Sub I,J,K&L_Lo x4. New IF cables with suitable length and type 4x RUN. New CAT6 cable x1. | MW Parallel Link | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202603270476-GTSB
9130B_AD | Samalaju-Port | DU00006678187 | Sarawak | Sarawak | 3.584828 | 113.345808 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202603270348-GCI
3292B_LOS | Caltex SalakSouth | DU00006731093 | Central | Kuala Lumpur | 3.082900 | 101.695736 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X ISM8 CARD 1X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3 SUB B HI 1x ODU 23G XMC3 SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE 3292B-1035D WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM_954MBPS_XMC3_SUB_B_LINK_0.34KM DISMANTLE EXISTING LINK 3292B-1720A IMPACTED: 3292B | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK 3292B-1720A | 1. INSTALL NEW 1PCS ISM8 CARD AT EXISTING IDU 1035D RTN01 SLOT 3 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK 3292B-1720A | XMC3 | MAC | 23G | 0.6 | 0.6 | GCI | SQ202604280451-GCI | GCI | SQ202604280454-GCI // SQ202604280620-GCI |  |  | Ongoing | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042152 |  | 2026-04-22 | 2026-04-22 | Completed | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-05-06 | 2026-04-28 |  | LEEROY QUIRINUS6000070995 | GCI TI | 2026-04-29 | 2026-05-06 | 2026-04-28 |  | LEEROY QUIRINUS6000070995 | GCI TI | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-02 | 2026-04-29 | 2026-05-06 | 2026-04-28 |  | LEEROY QUIRINUS6000070995 | 2025-11-03: 2026-04-29; 2025-11-03: 2026-05-06; 2025-11-03: 2026-04-28; 2025-11-05: 2026-04-29 | [7 empty] | GCI | SQ202604150406-GCI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | EZRIN TASNIM BIN ABDUL GANI6798000128
1401H_AD | 99 SpeedmartBDR SG CHANDONG | DU00006739259 | Central | Selangor | 2.978477 | 101.348508 | [9 empty] | TSS |  |  | MW New Link / Reroute | CLAIM TSSR ONLY LOS OPTION ALL BLOCK. CONFIRM BY GOP | CLAIM TSSR ONLY LOS OPTION ALL BLOCK. CONFIRM BY GOP | CLAIM TSSR ONLY LOS OPTION ALL BLOCK. CONFIRM BY GOP | [5 empty] | GTSB | SQ202604290755-GTSB | MTK | No PR required-Work at TSS only |  |  | Ongoing | 2026-05-01 | 2026-05-15 | 2026-05-01 | 2026-05-01 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-01 | 2026-05-15 | 2026-05-01 | 2026-05-01 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042037 |  | 2026-04-21 | 2026-04-23 | Completed | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202604150406-GCI | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
2918A_AD | Plaza Tol JlnDuta | DU00006739260 | Central | Kuala Lumpur | 3.176640 | 101.655000 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_56M NE 1.23G_DP_0.6(MAC) x1. 2.23G_XMC_3E_A&B_HI x2 3.RTN910A x1 FE 1.23G_DP_0.6(MAC) x1. 2.23G_XMC_3E_A&B_HI x2 3.RTN910A x1 | MW New Link / Reroute | Link reroute to new FE 2380A/W00884 due to existing FE 1114B will be decom. Link config 23G_2+0_56M Site Impacted : 2918A NE_2918A. 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and New FE routing. 6.Decom existing MW link 2918A-1114B. FE_2380A/W00884. 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create new Inband DCN. 6.Traffic migrate to new link and New FE routing. 7.Decom existing MW link 1114B-2918A. | Link reroute to new FE 2380A/W00884 due to existing FE 1114B will be decom. Link config 23G_2+0_56M Site Impacted : 2918A NE_2918A. 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and New FE routing. 6.Decom existing MW link 2918A-1114B. | Link reroute to new FE 2380A/W00884 due to existing FE 1114B will be decom. Link config 23G_2+0_56M Site Impacted : 2918A FE_2380A/W00884. 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create new Inband DCN. 6.Traffic migrate to new link and New FE routing. 7.Decom existing MW link 1114B-2918A. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202604290735-GCI | GCI | SQ202604200105-GCI // SQ202604200124-GCI |  |  | Ongoing | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-04-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-04-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26041307 |  | 2026-04-14 | 2026-04-17 | Completed | 2026-04-13 | 2026-04-14 | 2026-04-17 | 2026-04-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-04-22 | 2026-04-14 | 2026-04-21 | MUHAMMAD ADIL6800000278 | GCI TI | 2026-04-15 | 2026-04-22 | 2026-04-14 | 2026-04-21 | MUHAMMAD ADIL6800000278 | GCI TI | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-17 | 2026-04-15 | 2026-04-22 | 2026-04-14 | 2026-04-21 | MUHAMMAD ADIL6800000278 | 2026-04-15 | 2026-04-22 | 2026-04-14 | 2026-04-15 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | [5 empty] | GCI | SQ202604150406-GCI | 2026-04-12 | 2026-04-12 | 2026-04-12 | 2026-04-12 | CHEONG/SENG/WAH/7018000306
Q01905-9139B | IPG BT LINTANG | DU00004197825 | Sarawak | Sarawak | 1.529910 | 110.351810 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done | 20/9: Pending Site BoM. Req regional to verifty on materials availability | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 1+0 112MHz 0.6m/0.6m XMC3 NE: 1) 1xRTN910A 2) 1x23GHz XMC3 Sub B Hi 3) 1x18GHz 0.6m SP FE: 1) 1xISM8 card 2) 1x23GHz XMC3E Sub B Lo 3) 1x23GHz 0.6m SP | MW New Link / Reroute | SARAWAK SW03094 Q01905 IPG BT LINTANG TO Q00567 BORMILL - MW EOS + Reroute due to LOS block identified during survey. Tx route before: Q01905-Q00567 Tx route after: Q01905-9139B-9029A-LL-9999A Impacted site: Q01905 NE (Q01905): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Cutover traffic to new link 4) Decom old link FE (9139B RTN01): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at new RTN 3-ISM8-1 3) Cutover traffic to new link | NE (Q01905): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Cutover traffic to new link 4) Decom old link | FE (9139B RTN01): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at new RTN 3-ISM8-1 3) Cutover traffic to new link | XMC3 | MAC SP | 23G | 0.6m | 0.6m | Allstar | SQ202411140401-Allstar // SQ202501080102-Allstar | Allstar | SQ202507080934-Allstar // SQ202507080939-Allstar | 2025-02-04 | 2025-02-04 | Completed | 2025-02-04 | 2025-02-04 | 2025-02-04 | 2025-02-04 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-01-20 | 2025-01-24 | 2025-01-20 | 2025-01-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-01-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-20 | 2025-01-24 | 2025-01-20 | 2025-01-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070365 |  | 2025-07-04 | 2025-07-07 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-07 | 2025-07-13 | 2025-07-07 | 2025-07-07 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-07-07 | 2025-07-13 | 2025-07-07 | 2025-07-21 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-17 | 2025-07-07 | 2025-07-13 | 2025-07-23 | 2025-07-23 | BONG NEE NYEEbong.allstar@gmail.com | 2025-07-07 | 2025-07-13 | 2025-07-07 | 2025-07-07 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-07 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507080651-GTSB | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | HSU//MYET CHAE/6799000011
S01405-7407A | RS50303_4_1-KGTAMUDARAT | DU00004199094 | Sabah | Sabah | 6.262662 | 116.450325 |  |  |  |  | RFS |  |  | 00. Integrated/RFS Done | 18/12: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G 0.6m/1.2m DP 2+0_SB B,B | MW New Link / Reroute | MW NEW LINK S01405-7407A WITH 15G_2+0_0.6/1.2_DP_SB A,B NE: 1. Install new RTN910A 2. Install new XMC-3_SB B,B. 3. Install new antenna 13G_0.6_DP 4. Configure 13G_2+0_0.6_1024QAM 5. Dismantle S01405-S00461 MW link. FE: 1. Install new RTN910A 2. Install new XMC-3_SB B,B. 3. Install new antenna 13G_1.2_DP 4. Configure 13G_2+0_1.2_1024QAM 5. Dismantle S01405-S00461 MW link. | [7 empty] | NR Services | SQ202504210288-NR Services | NR services | SQ202412170152-NR Services // SQ202504260199-NR Services | 2026-01-12 | 2026-01-12 | Completed | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-17 | 2025-10-14 | 2025-10-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-17 | 2025-10-14 | 2025-10-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-17 | 2025-10-14 | 2025-10-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24120630 |  | 2024-12-11 | 2024-12-14 | Completed | 2024-12-10 | 2024-12-11 | 2024-12-10 | 2024-12-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-15 | 2024-12-30 | 2024-12-15 | 2024-12-18 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-12-15 | 2024-12-30 | 2024-12-15 | 2024-12-18 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-12-18 | 2024-12-18 | 2024-12-18 | 2024-12-18 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-12-15 | 2024-12-30 | 2024-12-15 | 2024-12-19 | RALPH O'BRYAN HILARY7167000030 | 2025-11-03: 2024-12-15; 2025-11-03: 2024-12-30; 2025-11-03: 2024-12-15; 2025-11-05: 2024-12-16 |  |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202510300419-GTSB
S00590-S00140 | S104A_S00590OD_CB_BKTKIMANDAU | DU00004199095 | Sabah | Sabah | 6.066810 | 116.821110 |  |  |  |  | Pending Material | MwAntenna HW-13G_1.8M_Dual Polarization_A13D18MDD x2pc | ZTE | 06. Other Issue | Non-doable | TSS+AA+TI |  | 13G_2+0_1.2/1.2M_MDD_SB B | MW Parallel Link | Parallel MW LINK S00590-S00140 WITH HUAWEI_13G_2+0_1.2/1.2M_MDD_SB B_16.67KM NE: 1. Install new HW RTN910A. 2. Install newODU XMC-5D_SB B 3. Swap SM antenna with 1.2M_MDD. 4. Configure 13G_2+0_1.2m_EPLA FE: 1. Install new HW RTN910A. 2. Install newODU XMC-5D_SB B 3. Swap SM antenna with 1.2M_MDD. 4. Configure 13G_2+0_1.2m_EPLA | [7 empty] | NR services | SQ202504080161-NR Services |  |  |  |  | Ongoing | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | [7 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300153-GTSB
7536A-7487A | Kolej Matrikulasi Labuan | DU00004199096 | Sabah | Sabah | 5.357742 | 115.225868 |  |  |  |  | DONE UNDER NIC | DONE under NIC |  | 07. Solution Changed | Proceed HU Upgrade under Tx Mini due site MOCN 2025 >TI DONE under NIC |  |  | 18G_0.6m/0.6m_MDD_1+0_110Mhz_256Q | Cancel / Drop | 05/06/25: Cancel/drop. Link already upgraded under Tx rollout DU 7536A DU00002884772. Current utilization ~30% SWAP MW LINK 7536A-7487A WITH: HUAWEI_18GHZ_2+0_112MHZ_0.6m NE: 1. Reuse existing IDU RTN 02. 2. Reuse existing ISM-8 card and configure 2+0 EPLA with existing link at Slot 7. 3. Swap existing ODU with XMC-5D ODU (SB B) 4. Swap existing Antenna with 0.6m 18G MDD. 5. Configure 18GHz_2+0_0.6m_110MHz_256QAM FE: 1. Reuse existing IDU RTN 02. 2. Swap existing ISV3 with new ISM-8 at Slot 4 and configure 2+0 EPLA with existing link. 3. Swap existing ODU with XMC-5D ODU (SB B) 4. Swap existing Antenna with 0.6m 18G MDD. 5. Configure 18GHz_2+0_0.6m_110MHz_256QAM | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7037B-7399A | Kg Bintasan | DU00004199097 | Sabah | Sabah | 6.584330 | 116.709470 |  |  |  | JUN 25 | TI WIP | Alignment WIP(-36dBm) | Digi | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G 1.2M/1.2M 4+0 MDD | MW Swap | SWAP MW LINK 7037B-7399A WITH HUAWEI_15G_4+0_110MHZ_1.2M NE: 1. Swap existing IDU with HW RTN910A. 2. Swap existing ODU with HW XMC-5D 15G ( SB A). 3. Swap existing Antenna with 15G 1.2m MDD. 4. Configure 15G_4+0_512QAM_800M. FE: 1. Swap existing IDU with HW RTN910A. 2. Swap existing ODU with HW XMC-5D 15G ( SB A). 3. Swap existing Antenna with 15G 1.2m MDD. 4. Configure 15G_4+0_512QAM_800M. | [7 empty] | NR Services | SQ202510230970-NR Services | NR services | SQ202412310408-NR Services | 2026-01-12 | 2026-01-12 | Completed | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-17 | 2025-10-14 | 2025-10-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-17 | 2025-10-14 | 2025-10-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-17 | 2025-10-14 | 2025-10-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24120629 |  | 2024-12-11 | 2024-12-14 | Completed | 2024-12-10 | 2024-12-11 | 2024-12-10 | 2024-12-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-19 | 2024-12-23 | 2024-12-18 | 2025-08-21 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-04-17 | 2025-04-30 | 2025-04-17 | 2025-08-21 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-21 | 2025-04-17 | 2025-04-30 | 2025-04-17 | 2025-09-10 | RALPH O'BRYAN HILARY7167000030 | 2025-11-03: 2024-12-19; 2025-11-03: 2024-12-23; 2025-11-03: 2024-12-18; 2025-11-05: 2025-04-28 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
7180D7_EVT | LBTS_HARI MALAYSIA 2025 | DU00006038967 | Sabah | Sabah | 5.980872 | 116.076981 | [13 empty] | Planning and integration support only for event site 7180D7 LBTS_HARI MALAYSIA 2025 Tx route: 7180D7-7036A 1) New port IBEAM at 7036A-MAC-001 Pos Malaysia 2) New DCN IP 7036A RTN04 3) New DCN VLAN 7036A RTN04 4) New NE ID FE IDU 7036A RTN04 5) New NE ID NE IDU 7180D7 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
4994A_HU_1 | Kodiang | DU00006038968 | Northern | Kedah | 6.392275 | 100.311142 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Install new RTN910A for Hardware Upgrade. NE_4994A RTN910A x1 FE_4606B RTN910A x1. | MW Hardware Upgrade | Hardware upgrade IDU to new version due to existing not support for IS8 Mode. Install new RTN910A for Hardware Upgrade. ( Refer to DU ID 4994A_HU). Site Impacted 4994A. NE_4994A 1.Install new RTN910A.(RTN no provide by OPS team). 2.Transfer existing 2 x ISM8 into new RTN910A , 3_ISM8-2+0 and 4_ISM8-2+0. (Refer DU ID 4994A_HU). 3.Transfer existing IF cable 2+0 (1_ISV3 & 2_ISV3) to new RTN910A , 7_ISM8-2+0. 4.Configure link to 15G_6+0_28M. 5.Decom existing 1_ISV3 and 2_ISV3. FE_4606B 1.Install new RTN910A.(RTN no provide by OPS team). 2.Transfer existing 2x ISM8 into new RTN910A , 3_ISM8-2+0 and 4_ISM8-2+0. (Refer DU ID 4994A_HU). 3.Transfer existing IF cable 2+0 (1_ISV3 & 2_ISV3) to new RTN910A , 7_ISM8_2+0. 4.Configure link to 15G_6+0_28M. 5.New Inband DCN 6.Decom existing 1_ISV3 and 2_ISV3. | Hardware upgrade IDU to new version due to existing not support for IS8 Mode. Install new RTN910A for Hardware Upgrade. Site Impacted 4994A. NE_4994A 1.Install new RTN910A.(RTN no provide by OPS team). 2.Transfer existing 2 x ISM8 into new RTN910A , 3_ISM8-2+0 and 4_ISM8-2+0. (Refer DU ID 4994A_HU). 3.Transfer existing IF cable 2+0 (1_ISV3 & 2_ISV3) to new RTN910A , 7_ISM8-2+0. 4.Configure link to 15G_6+0_28M. 5.Decom existing 1_ISV3 and 2_ISV3. | Hardware upgrade IDU to new version due to existing not support for IS8 Mode. Install new RTN910A for Hardware Upgrade. Site Impacted 4994A. FE_4606B 1.Install new RTN910A.(RTN no provide by OPS team). 2.Transfer existing 2x ISM8 into new RTN910A , 3_ISM8-2+0 and 4_ISM8-2+0. (Refer DU ID 4994A_HU). 3.Transfer existing IF cable 2+0 (1_ISV3 & 2_ISV3) to new RTN910A , 7_ISM8_2+0. 4.Configure link to 15G_6+0_28M. 5.New Inband DCN 6.Decom existing 1_ISV3 and 2_ISV3. | [5 empty] | NWAVE | SQ202509300147-N-Wave | NWAVE | SQ202510090424-N-Wave // SQ202510090433-N-Wave | 2025-11-28 | 2025-11-27 | Completed | 2025-10-08 | 2025-11-08 | 2025-10-08 | 2025-10-09 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100127 |  | 2025-10-02 | 2025-10-04 | Completed | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-04 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-08 | 2025-11-08 | 2025-10-08 | 2025-10-09 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-10-08 | 2025-11-08 | 2025-10-08 | 2025-10-09 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-09 | 2025-10-08 | 2025-11-08 | 2025-10-08 | 2025-10-23 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2025-10-08 | 2025-11-08 | 2025-10-08 | 2025-10-08 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | NG HONG JIE7018000036 | Logistic Team | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | CHEONG/SENG/WAH/7018000306
4731A-4414A | Trolak (Trunk) | DU00004766392 | Northern | Perak | 3.924760 | 101.329880 | [7 empty] | 00. Integrated/RFS Done | 05/02 : CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Hardware upgrade NE RTN910A x1 ISM8 x 2. FE RTN910A x1. ISM8 x 2. | MW Hardware Upgrade | Hardware upgrade from legacy IDU and ISV3 board to New RTN910A and ISM8 board with latest software Version for TX Rollout_4731A NE_4731A_RTN05. 1. Install new RTN910A , 7_ISM8-2+0. 2. Install 3_ISM8-2+0 and 4_ISM8-2+0. 3. Configure to 15G_6+0 and EPLA. 4. Migrate existing traffic to New RTN910A. 5. Decom existing 4731A_RTN05 and ISV3 boards. 6. Ensure all traffic migrate successful before decom. FE_4414A_RTN05. 1. Install new RTN910A , 7_ISM8-2+0. 2. Install new 3_ISM8-2+0 and 4_ISM8-2+0. 3. Configure to 15G_6+0 and EPLA. 4. Migrate existing traffic to new RTN910A. 5. Decom existing 4414A_RTN05 and ISV3 boards. 6. Ensure all traffic migrate successful before decom. | [7 empty] | CCSMY | SQ202504210258-CCS | CCSMY | SQ202412310401-CCS // SQ202504260175-CCS | 2025-12-17 | 2025-12-16 | Completed | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24122417 |  | 2024-12-25 | 2025-02-26 | Completed | 2024-12-24 | 2024-12-25 | 2024-12-24 | 2025-02-26 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-17 | 2025-01-31 | 2025-02-25 | 2025-02-26 | MUHAMAD//SAHRIN BIN SUFIAN/7021000055 | CCS TI | 2025-01-17 | 2025-01-31 | 2025-02-25 | 2025-04-30 | MUHAMAD//SAHRIN BIN SUFIAN/7021000055 | CCS TI | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-05 | 2025-01-17 | 2025-01-31 | 2025-05-09 | 2025-05-09 | MUHAMAD//SAHRIN BIN SUFIAN/7021000055 | 2025-01-17 | 2025-01-31 | 2025-05-15 | 2025-05-15 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050701-GCI | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | EZRIN TASNIM BIN ABDUL GANI6798000128
4149R_LOS | Kg. Sumatera | DU00004840313 | Northern | Perak | 5.222240 | 100.751510 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M_CA. NE_4149R 13G_DP_1.2M(MDD) x1. XMC_5D , Sub A_Hi RTN 910A x1. ISM8 x2. FE_4988B 13G_DP_1.2M(MDD) x1. XMC_5D , Sub A_Lo x1. RTN910A x1. ISM8 x2. | MW New Link / Reroute | Link reroute to new FE 4988B due to LOS block with config 13G_4+0_28M_CA. Site Impacted : 4149R NE_4149R 1.Install new 13G_DP_1.2M(MDD). 2.Install new XMC_5D-4+0 with CA. 3.Install new RTN 910A.(RTN no provide by MSP team). 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , EPLA and CA config. 6.Traffic 4149R migrate to new FE route with 13G_4+0_28M_CA link. 7.Decom existing MW link IDU , Ant and ODU (4149R_RTN01 to 4718B_RTN02).Ensure traffic migrate successful before decomm. FE_4718B 1.Install new 13G_DP_1.2M(MDD). 2.Install new XMC_5D-4+0 with CA. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , EPLA and CA config. 6.Enable GE1 , ETH cable patching to existing 4718B_RTN01(GE2). 7.Traffic migrate to new FE via existing HW link (4149R-4718B-4952B). 8.Decom existing MW link IDU , Ant and ODU (4718B_RTN02-4149R).Ensure traffic migrate successful before decomm. | [7 empty] | GCI | SQ202504170476-GCI | GCI | SQ202504210115-GCI // SQ202504210118-GCI // SQ202505150106-GCI // SQ202508140738-GCI | 2025-08-05 | 2025-08-05 | Completed | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-04 | 2025-08-05 | 2025-08-04 | 2025-08-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25012206 |  | 2025-01-23 | 2025-02-13 | Completed | 2025-01-22 | 2025-01-23 | 2025-01-22 | 2025-02-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-27 | 2025-03-08 | 2025-02-27 | 2025-04-08 | team21gcitechnicalteam21gcitechnical | GCI TI | 2025-02-27 | 2025-03-08 | 2025-02-27 | 2025-04-19 | team21gcitechnicalteam21gcitechnical | GCI TI | 2025-04-03 | 2025-04-03 | 2025-04-03 | 2025-04-03 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-02-27 | 2025-03-08 | 2025-02-27 | 2025-04-30 | team21gcitechnicalteam21gcitechnical | 2025-02-27 | 2025-03-08 | 2025-02-27 | 2025-03-10 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | CHEONG/SENG/WAH/7018000306
9010A-9999A | Yeo Hong Chuan | DU00004904977 | Sarawak | Sarawak | 1.558222 | 110.347250 |  |  |  |  | Under observation | Under observation | ZTE | 06. Other Issue | 10/9/2025 : Pending survey, need to confirm RAN plan to decom Under observation | TSS+AA+TI+Dismantle |  | 15G_4+0_1.2/1.2_MDD_XMC-5D_SB A 2xRTN910A | MW Swap | MW SWAP 9010A-9999A WITH 15G_4+0_1.2/1.2_MDD_XMC-5D_SB A DISMANTLE SM LINK | MW SWAP 9010A-9999A WITH 15G_4+0_1.2/1.2_MDD_XMC-5D_SB A NE: 1. Install new RTN910A. 2. Install new XMC-5D_SB A. 3. Install new antenna 15G_1.2MDD. 4. Configure 15G_4+0_1.2MDD_256QAM_CA. 5. Dismantle SM link. | MW SWAP 9010A-9999A WITH 15G_4+0_1.2/1.2_MDD_XMC-5D_SB A FE: 1. Install new RTN910A. 2. Install new XMC-5D_SB A. 3. Install new antenna 15G_1.2MDD. 4. Configure 15G_4+0_1.2MDD_256QAM_CA. 5. Dismantle SM link. | [5 empty] | Magicell |  | YPTT |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | DO Canceled (More than 30 days) | 2025-08-26 |  | Ongoing | 2025-08-25 | 2025-08-26 | 2025-08-25 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202506050655-GTSB | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | HSU//MYET CHAE/6799000011
4586A-4428B | Tmn Berkat Taiping | DU00004174587 | Northern | Perak | 4.868210 | 100.687110 |  |  | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 2/12: D2: Cutover done. Post-CO T/S ongoing 28/11: TI done, pending CO. Request SFP Cisco/Edotco WP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz 0.6m SP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz 0.6m SP | MW Swap | Existing link SM NT04576 18GHz 1+0 56MHz To swap Existing link 18GHz 1+0 56MHz with new Huawei link 18GHz 1+0 112MHz Impacted sites: 4586A NE (4586A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link FE (4428B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Patch new RTN to new xC PTN port (ops team to assign new port) 4) Migrate traffic to new link. Create new DCN 5) Decom existing link | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202411150562-GCI // SQ202504150095-GCI | 2025-12-17 | 2025-12-16 | Completed | 2024-11-30 | 2024-11-30 | 2024-12-02 | 2024-12-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2024-12-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112588 |  | 2024-11-26 | 2024-12-03 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2024-12-03 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-28 | 2024-12-07 | 2024-11-28 | 2024-12-03 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2024-11-28 | 2024-12-07 | 2024-11-28 | 2024-12-03 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-11-28 | 2024-12-07 | 2024-11-28 | 2024-12-07 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2024-11-28 | 2024-12-07 | 2024-11-28 | 2024-11-28 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
2705C-2771B | Bandar Tasik Puteri 5 | DU00004174588 | Central | Selangor | 3.277440 | 101.487490 |  | APR 25 |  | APR 25 | TI | Plan use scaffolding | ZTE | 00. Site Out/Drop | 10/2/2025 : Access road issue blocking by construction, suggest use scaffolding 10/2/2025 : BANGKIT SETIA - 30M Lampole - NE site 2705C Bandar Tasik Puteri 5, EDGEPOINT INFRA - Tower - FE site 2771B LATAR HW Puncak Alam 14/10: Pending Site DO |  |  | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1x18GHz XMC3E Sub B Hi 2) 1x18GHz 0.6m SP FE: 1) 1x18GHz XMC3E Sub B Lo 2) 1x18GHz 0.6m SP | Cancel / Drop | 07 Jan 2026: Cancel/drop. Site having access/road/scaffolding issue. Link not in HU list anymore Existing link 2705C 3-ISM8 -2771B 3-ISM8 15G 2+0 Existing link 2705C 7-ISM8-1 -2771B 7-ISM8-1 15G 1+0 To swap Existing link 15GHz 1+0 with new Huawei link 18GHz 1+0 56MHz Impacted sites: 2705C NE (2705C): 1) Swap existing 15G SP antenna with new 18G SP antenna 2) Install new link at RTN01 7-ISM8-1 3) Decom existing link FE (2771B): 1) Swap existing 15G SP antenna with new 18G SP antenna 2) Install new link at RTN01 7-ISM8-1 3) Decom existing link | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24112069 | 18G_0.6/1.2_1+0_SUB A. WIP P.dismantle 18G 0.6 & 1.2⏸️ | 2024-11-21 |  | Ongoing | 2024-11-20 | 2024-11-21 | 2024-11-20 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2024-12-03 | 2024-12-10 | 2024-12-03 |  | SYEDMOHAMAD//FARISAIMAN/6800000274 | GCI TI | 2024-12-03 | 2024-12-10 | 2024-12-03 |  | SYEDMOHAMAD//FARISAIMAN/6800000274 | GCI TI | [7 empty] | 2024-12-03 | 2024-12-10 | 2024-12-03 |  | SYEDMOHAMAD//FARISAIMAN/6800000274 | 2025-01-17: 2024-12-03; 2025-01-31: 2024-12-10; 2025-05-15: 2024-12-03
9067H_LOS | Mukah New Airport | DU00006560891 | Sarawak | Sarawak | 2.887940 | 112.043140 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB A HI 1x ODU 18G XMC5D SUB A LO | MW New Link / Reroute | MW NEW LINK REROUTE 9067H-9376A WITH HUAWEI_18G_1+0_0.6M/0.6M_MDD_112MHZ_512QAM_889MBPS_XMC5D_SUB_A_LINK_2.74KM IMPACTED: 9067H PATCH TO XC Q00190 LL DISMANTLE EXISTING LINK NLOS | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK NLOS | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. PATCH IDU TO xC Q00190 LL 6. DISMANTLE EXISTING LINK NLOS | XMC5D | MDD | 18G | 0.6 | 0.6 | NR Services | SQ202602130286-NR Services | YPTT | SQ202604100684-YPTT // SQ202604100687-YPTT | 2026-03-13 | 2026-03-12 | Completed | 2026-02-11 | 2026-02-13 | 2026-02-11 | 2026-02-16 | MAN BIN HARUN7167000009 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26031806 |  | 2026-03-19 | 2026-03-25 | Completed | 2026-03-18 | 2026-03-19 | 2026-03-18 | 2026-03-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-28 | 2026-04-10 | 2026-03-28 |  | MUHAMMAD//NAZIRUL HAKIMI BIN DILMI/6794000014 | YPTT TI | 2026-03-28 | 2026-04-10 | 2026-03-28 |  | MUHAMMAD//NAZIRUL HAKIMI BIN DILMI/6794000014 | YPTT TI | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-06 | 2026-03-28 | 2026-04-10 | 2026-03-28 |  | MUHAMMAD//NAZIRUL HAKIMI BIN DILMI/6794000014 | 2025-01-17: 2026-02-05; 2025-01-31: 2026-02-12; 2025-05-15: 2026-02-05; 2025-05-15: 2026-02-11 | [7 empty] | GCI | SQ202602120121-GCI | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | EZRIN TASNIM BIN ABDUL GANI6798000128
9159A | Dalat(SACOFA) | DU00004954316 | Sarawak | Sarawak | 2.743414 | 111.943760 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1xCat6 cable | IDU-IPRAN | Create LAG at 9159A RTN02 IDU to CP port to solve CP port congestion Impact sites: 9407B, 9560B, Q01041 To perform patching to CP port and create 2+0 LAG NE (9159A): 1) Patch 9159A RTN02 GE2 to new CP port (9159A-MAC-001 GigabitEthernet 0/2/21) 2) Create 2+0 LAG | NE (9159A): 1) Patch 9159A RTN02 GE2 to new CP port (9159A-MAC-001 GigabitEthernet 0/2/21) 2) Create 2+0 LAG | [6 empty] | YPTT | SQ202504210316-YPTT | YPTT | SQ202502060436-YPTT // SQ202504260215-YPTT | 2025-09-17 | 2025-09-17 | Completed | 2025-02-04 | 2025-02-11 | 2025-02-04 | 2025-02-05 | JORDAN CHIN ZHEN WOON6794000058 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-10 | 2025-09-12 | 2025-09-10 | 2025-09-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-10 | 2025-09-12 | 2025-09-10 | 2025-09-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2025-02-05 | 2025-02-28 | 2025-02-05 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | 2025-02-05 | 2025-02-28 | 2025-02-05 | 2025-02-06 | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-02-04 | 2025-02-14 | 2025-02-23 | 2025-07-25 | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | 2025-01-17: 2025-07-09; 2025-01-31: 2025-08-01; 2025-05-15: 2025-02-05 |  |  | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202510100649-GTSB
3501C_LOS | KL Baptist Church Desa Park City (REL) | DU00004180988 | Central | Kuala Lumpur | 3.182292 | 101.627064 | WK06 | FEB 25 | WK06 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 5/2/2025 : Cutover done 17/1/2025 : Digi OB - 3M Boom - RT - NE site 3501C KL Baptist Church Desa Park City (REL), Edotco Site Catalog/Exchange - MONOPOLE 36M LAND - FE site W00261 W066B_W00261OD_CMX7 2/10: Pending Site BoM | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M. NE_3501C 18G_SP_0.6m (MAC)+OMT x1. RTN910A x1. XMC_3E_1+0 , Sub B_Hi x1. FE_2145A 18G_SP 0.6m (MAC)+OMT x1. ISM8 x1 XMC_3E_1+0 , Sub B_Lo x1. | MW New Link / Reroute | Existing 18G_1+0_56M Link reroute to new FE 2145A with config 18G_1+0_112M. Site Impacted: 3501C,3102A NE_3501C 1.Install new SP 0.6m. 2.Install new RTN910AF , 7_ISM8-1+0 (RTN no provide by MSP team). 3.Install new XMC_3E_1+0. 4.Create service cross connect. 5.Migrate traffic to new route FE 2145A. 6.Decom existing MW link 3501C-2019B. FE_2145A 1.Install new SP 0.6m. 2.Reuse existing 2145A_RTN03. 3.Install new 3_ISM8 into existing 2145A_RTN03. 4.Install new XMC_3E_1+0 , Sub B_Lo. 5.Create service cross connect and EPLA with existing MW link. 6.Decom existing MW link 2019B-3501C. | Existing 18G_1+0_56M Link reroute to new FE 2145A with config 18G_1+0_112M. Site Impacted: 3501C,3102A NE_3501C 1.Install new SP 0.6m. 2.Install new RTN910AF , 7_ISM8-1+0 (RTN no provide by MSP team). 3.Install new XMC_3E_1+0. 4.Create service cross connect. 5.Migrate traffic to new route FE 2145A. 6.Decom existing MW link 3501C-2019B. | Existing 18G_1+0_56M Link reroute to new FE 2145A with config 18G_1+0_112M. Site Impacted: 3501C,3102A FE_2145A 1.Install new SP 0.6m. 2.Reuse existing 2145A_RTN03. 3.Install new 3_ISM8 into existing 2145A_RTN03. 4.Install new XMC_3E_1+0 , Sub B_Lo. 5.Create service cross connect and EPLA with existing MW link. 6.Decom existing MW link 2019B-3501C. | [5 empty] | MTK | SQ202505080617-MTK | MTK | SQ202504260152-MTK // SQ202505190309-MTK // SQ202505190329-MTK | 2025-02-14 | 2025-02-14 | Completed | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-10 | 2025-01-11 | 2025-01-10 | 2025-01-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-12 | 2025-02-13 | 2025-02-12 | 2025-02-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-13 | 2025-02-14 | 2025-02-13 | 2025-02-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25013103 |  | 2024-10-09 | 2024-10-11 | Completed | 2024-10-08 | 2024-10-09 | 2024-10-08 | 2024-10-11 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-04 | 2025-02-19 | 2025-02-05 | 2025-02-05 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-02-04 | 2025-02-19 | 2025-02-05 | 2025-02-05 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-05 | 2025-02-04 | 2025-02-19 | 2025-03-17 | 2025-03-17 | RIDHUAN//BIN MANSOR/8225000011 | 2025-02-04 | 2025-02-19 | 2025-02-05 | 2025-02-05 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
1340B_LOS | OUG Kesas (Lamp pole) | DU00004180989 | Central | Kuala Lumpur | 3.064515 | 101.670579 |  |  |  |  | Cancel / Drop | Done under TX NIC 1340B_Additional | ZTE | 00. Site Out/Drop | 25/9: Solution done under TX NIC 1340B_Additional. 1340B patching to W00214 use MW link W00214-W00089 | TSS |  | 23G_2+0_112M NE_1340B 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. FE_2232A. 23G_DP_0.6m(MAC)+OMT x1. XMC_3E, Sub A & B_Lo x2. RTN910A x1. ISM8 x1. | MW New Link / Reroute | Link reroute to new FE 2232A with 23G_2+0_112M due to LOS Block. NE_1340B 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0 3.Install new XMC_3E , Sub A & B_Hi 4.Enable EPLA & Service cross connect. 5.Traffic migrate to new route and new link. 6.Decom existing MW link. FE_2232A. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install XMC_3E, Sub A & B_Lo. 3.Reuse existing 2232A_RTN01. 4.Install 3_ISM8-2+0 into existing 2232A_RTN01 5.Enable EPLA and Service cross connect. 6.Traffic migrate to new FE via existing MW link to 1458A. 7.Decom existing MW link. | [7 empty] | Datasco | No PR required-Site drop/cancel |  |  |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300116-GTSB
3612B_LOS | Taman Subang Mas | DU00004180991 | Central | Selangor | 3.055013 | 101.558879 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 24/1/2025 : Decom and L1 done 23/1/2025 : Cutover done 22/1/2025 : Cutover WIP 21/1/2025 : Relocate antenna done, alignment WIP 20/1/2025 : Cancel proceed due to TM PTW pending approval 18/1/2025 : Alignment still issue due to cross electrical tower, need to antenna on top of tower 17/1/2025 : Installation complete, pending alignment 16/1/2025 : NE installation complete, pending install FE site due to beehive issue 15/1/2025 : NE installation complete, pending install FE site 6/1/2024 : Digi OB - 6M Tripod - RT - NE site 3612B Taman Subang Mas, Digi OB - Enterprise driven site - FE site 1486E Nippon Paint DR Shah Alam 20/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Link reroute with config 23G_2+0_112M due to LOS block. NE_3612B 23G_0.6m(MAC)+OMT x1. RTN910A x1. XCM_3-2+0 , Sub_A & B_Lo x2. FE_2603B/B00395 23G_0.6m(MAC)+OMT x1. RTN910A x1 XMC_3-2+0, Sub_A & B_Hi x2. | MW New Link / Reroute | Link reroute to new FE 1486E with config 23G_2+0_112M due to LOS block. Site Impacted : 3612B , 1486E , 2603B/B00395. NE_3612B 1.Install 23G_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XCM_3-2+0 , Sub_A & B_Lo. 4.Enable EPLA and service cross connect. 5.Traffic migrate to new link direct towards new FE. 6.Decom existing MW link.(3612B-2021B) FE_2603B/B00395 1.Install 23G_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3-2+0, Sub_A & B_Hi. 4.Create new In Band DCN. 5.Enable GE Port patching to ODF Fiber port and existing BBU patch to RTN910A. 6.Enable EPLA and service cross connect. 7.Traffic migrate to new link direct towrads new FE. 8.Decom existing MW link.(2021B-3612B) | [7 empty] | GCI | SQ202505150496-GCI | GCI | SQ202501030055-GCI // SQ202504150088-GCI | 2025-06-18 | 2025-06-18 | Completed | 2024-09-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-01-31 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-12 | 2025-02-13 | 2025-02-12 | 2025-02-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-17 | 2025-06-18 | 2025-06-17 | 2025-06-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24103035 |  | 2024-10-31 | 2024-11-30 | Completed | 2024-10-30 | 2024-10-31 | 2024-10-30 | 2024-11-30 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-15 | 2025-01-22 | 2025-01-15 | 2025-01-15 | MUHAMMAD NORHAFIQ//BIN SUHAIMI/6800000280 | GCI TI | 2025-01-15 | 2025-01-22 | 2025-01-15 | 2025-01-27 | MUHAMMAD NORHAFIQ//BIN SUHAIMI/6800000280 | GCI TI | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-23 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-23 | 2025-01-15 | 2025-01-22 | 2025-01-15 | 2025-01-24 | MUHAMMAD NORHAFIQ//BIN SUHAIMI/6800000280 | 2025-01-15 | 2025-01-22 | 2025-01-15 | 2025-01-18 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
B02664_LOS | SIERRA10_PUCHONG | DU00004180992 | Central | Selangor | 2.964018 | 101.658610 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 26/11: D2: Cutover done. Post-CO T/S ongoing | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Link reroute to new FE 1313B with config 18G_1+0_112M due to LOS block. NE_B02664 1.Install new 18G_SP_0.6m ant 1. 2.Install 18G_XMC_3E ODU , Sub_B_Lo x1. 3.Install new RTN910A x1 FE_1313B 1.Install new 18G_SP_0.6m ant x1. 2.Install 18G_XMC_3E ODU , Sub_B_Hi. 3.Install new RTN910A x1. | MW New Link / Reroute | Existing link 18G_1+0_56M(B02664-B01551-B00818) Link reroute to new FE 1313B with config 18G_1+0_112M due to LOS block. Site Impacted: B02664. NE_B02664 1.Install new 18G_SP_0.6m ant. 2.Install 18G_XMC_3E ODU and config 112M. 3.Install new RTN910A ,7_ISM8-1+0. 4.Service cross connect to new FE site. 5.Decom existing SM link (B02664-B01551). FE_1313B 1.Install new 18G_SP_0.6m ant. 2.Install 18G_XMC_3E ODU and config 112M. 3.Install new RTN910A, 7_ISM8-1+0. 4.Create new In-band and service cross connect to new FE site. 5.Decom existing SM link (B02664-B01551). | [7 empty] | Datasco | SQ202411140206-Datasco | Magicell | SQ202411150549-Magicell | 2024-12-28 | 2024-12-30 | Completed | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-09-13 | MOHAMAD//ZULFAKAAR BIN SHAMSUDIN/7019000075 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-15 | 2024-11-15 | 2024-11-15 | 2024-11-15 | MOHAMAD//ZULFAKAAR BIN SHAMSUDIN/7019000075 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-20 | 2024-11-21 | 2024-11-20 | 2024-11-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-12-27 | 2024-12-28 | 2024-12-27 | 2024-12-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24103011 |  | 2024-10-31 | 2024-11-15 | Completed | 2024-10-30 | 2024-10-31 | 2024-10-30 | 2024-11-15 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-25 | 2024-12-07 | 2024-11-25 | 2025-02-07 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2024-11-25 | 2024-12-07 | 2024-11-25 | 2025-02-07 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-11-25 | 2024-12-07 | 2024-11-25 | 2024-12-02 | MOHD//SAFRI BIN ARIF/7018000166 | 2024-11-25 | 2024-12-07 | 2024-11-25 | 2024-11-26 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
1415H_AD | 99 Speedmart JLN CHERAS | DU00004180993 | Central | Kuala Lumpur | 3.129380 | 101.720215 | [6 empty] | ZTE | 03. TSS Only | 28/3: As per requested by MSP, site need to proceed and bring up the link. 3/1/2025 : No need proceed. Site drop 30/8: Pending BoQ, TX SoW Details | TSS |  | New NLOS RTN510 equipment NE_1415H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_W00201 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH cable / LAN Cable. | MW New Link / Reroute | Link reroute to new FE W00201 with new NLOS RTN510 equipment due to LOS block. NE_1415H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. FE_W00201 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.ETH cable patching to existing Fiber_Ibeam. 6.Decom existing NLOS Radio | [7 empty] | Datasco | SQ202411250752-Datasco | YPTT | No PR required-Work at TSS only |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25010390 |  | 2025-01-04 |  | Ongoing | 2025-01-03 | 2025-01-04 | 2025-01-03 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [7 empty] | 2025-01-07 | [32 empty] | GTSB_AA | SQ202510300116-GTSB
3695A_LOS | Jade Hill | DU00004180994 | Central | Selangor | 2.994510 | 101.759280 | WK02 | JAN 25 | WK02 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 9/1/2025 : Cutover done 8/1/2025 : Cancel proceed due to material issue and pending CRQ approval 6/1/2025 : Digi OB - 3M Bipod - RT - NE site 3695A Jade Hill, Digi OB - 45M 3 Legged Tower - FE site 3639C Eaton International School - Jade Hill 20/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_3695A. 23G_SP_0.6m(MAC) x1. XMC_3E , Sub A_Lo x1. RTN910A x1. FE_3639C 23G_SP_0.6m(MAC) x1. XMC_3E , Sub A_Hi x1. RTN910A x1. | MW New Link / Reroute | Link reoute to new FE 3639C with 23G_1+0_112M due to LOS block. NE_3695A. Site impacted: 3695A 1.Install 23G_SP_0.6m(MAC). 2.Install XMC_3E , Sub A_Lo. 3.Install new RTN910A , 7_ISM8-1+0. 4.Enable EPLA & service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing MW link. FE_2270A 1.Install 23G_SP_0.6m(MAC). 2.Install XMC_3E , Sub A_Hi. 3.Install new RTN910A , 7_ISM8-1+0. 4.Enable EPLA & service cross connect. 5.Enable GE port , patching to existing 2270A_RTN01(GE2). 6.Traffic migrate to new link 23G_1+0_112M and via existing MW link to 1037A (3695A-2270A-1059A-1037A). 7.Decom existing MW link. | [7 empty] | Magicell | SQ202504150442-Magicell | Magicell | SQ202411250781-Magicell // SQ202504260146-Magicell |  |  | Ongoing | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-23 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24112525 |  | 2024-11-26 | 2025-02-07 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2025-02-07 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-09 | 2025-01-18 | 2025-02-07 | 2025-02-07 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-01-09 | 2025-01-18 | 2025-02-04 | 2025-02-07 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-09 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-01-09 | 2025-01-18 | 2025-02-03 | 2025-02-03 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-01-09 | 2025-01-18 | 2025-01-09 | 2025-01-09 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202509250626-GCI
2349A_LOS | SS 22a LP | DU00004180995 | Central | Selangor | 3.128820 | 101.611326 |  |  |  |  | Cancel / Drop | Done under NIC DU 2349A | ZTE | 00. Site Out/Drop | 25/11: Solution done under TX NIC 2349A | TSS |  | 23G_2+0_112M NE_2349A 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1 XMC_3E , Sub A& B_Lo x2. FE_1197A. 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1 XMC_3E , Sub A& B_Hi x2. | MW New Link / Reroute | Link reroute to new FE 1197A with 23G_2+0_112M due to LOS block. 23G_2+0_112M Site Impacted : 2349A NE_2349A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Enable EPLA and service cross connect. 5.Traffic migrate to new route and new link. 6.Decom existing MW link. FE_1197A. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Enable EPLA & Service cross connect. 5.Create new In Band DCN 6.Traffic migrate to new route and new link. 7.Decom existing MW link. | Link reroute to new FE 1197A with 23G_2+0_112M due to LOS block. 23G_2+0_112M Site Impacted : 2349A NE_2349A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Enable EPLA and service cross connect. 5.Traffic migrate to new route and new link. 6.Decom existing MW link. | Link reroute to new FE 1197A with 23G_2+0_112M due to LOS block. 23G_2+0_112M Site Impacted : 2349A FE_1197A. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Enable EPLA & Service cross connect. 5.Create new In Band DCN 6.Traffic migrate to new route and new link. 7.Decom existing MW link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | Datasco | No PR required-Site drop/cancel | YPTT | No PR required-Site drop/cancel |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24112530 |  | 2024-11-26 |  | Ongoing | 2024-11-25 | 2024-11-26 | 2024-11-25 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing
1420B_LOS | PUAS BK5 (KJS) | DU00004180996 | Central | Selangor | 3.035910 | 101.650810 |  |  |  |  | Cancel / Drop | Done under DU 1420B TX NIC | ZTE | 00. Site Out/Drop | 17/9: Solution done under TX NIC 1420B (Reroute Link Activity) | TSS |  |  | MW New Link / Reroute | [8 empty] | Datasco | SQ202411060152-Datasco |  |  | 2025-06-05 | 2025-06-04 | Completed | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-27 | 2025-05-28 | 2025-05-27 | 2025-05-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-27 | 2025-05-28 | 2025-05-27 | 2025-05-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-04 | 2025-06-05 | 2025-06-04 | 2025-06-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
1140H_LOS | ONE LUCKY PHONE SHOP ENTERPRISE | DU00004185451 | Central | Selangor | 3.012124 | 101.599898 | WK03 | JAN 25 | WK03 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 18/1/2025 : Cutover done 17/1/2025 : Cutover WIP 16/1/2025 : FE installation complete, pending install NE 14/1/2025 : Digi OB - Small Cell - NE site 1140H ONE LUCKY PHONE SHOP ENTERPRISE, SBC KJS - 24M Lampole - FE site 3625C Flat Puchong Permai 9/3/23: NE already dismantle | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Install new NLOS NE_1140H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. FE_3625C 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Raise up ant location at 3633C in order to get the NLOS clear LOS. With Install new NLOS equipment. | Raise up ant location at 3633C in order to get the NLOS clear LOS. Install new NLOS equipment. | Raise up ant location at 3633C in order to get the NLOS clear LOS. | [5 empty] | YPTT | SQ202501210421-YPTT | YPTT | SQ202501210491-YPTT // SQ202504220106-YPTT // SQ202504260171-YPTT |  |  | Ongoing | 2025-01-16 | 2025-01-31 | 2025-01-16 | 2025-01-18 | MD//ERWAN BIN ROHMAN/6794000008 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. |  | Unassigned | Completed | [8 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25011063 |  | 2025-01-11 | 2025-01-18 | Completed | 2025-01-10 | 2025-01-11 | 2025-01-10 | 2025-01-18 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-16 | 2025-01-31 | 2025-01-16 | 2025-01-18 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2025-01-16 | 2025-01-31 | 2025-01-16 | 2025-01-18 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2025-01-17 | 2025-01-17 | 2025-01-17 | 2025-01-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-17 | 2025-01-16 | 2025-01-31 | 2025-01-16 | 2025-01-24 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | 2025-01-16 | 2025-01-31 | 2025-01-16 | 2025-01-17 | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2025-01-24 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300116-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
1535H_LOS | 99 Speedmart Eco Majestic | DU00004185452 | Central | Selangor | 2.909295 | 101.851227 | WK15 | APR 25 | WK15 | APR 25 | TI | RSL stuck -60 | ZTE | 00. Site Out/Drop | 11/4/2025 : Alignment WIP 7/2/2025 : Digi OB - Small Cell - NE site 1535H 99 Speedmart Eco Majestic, SBC KJS - 24M Lampole - FE site 3239B Bandar Tasik Kesuma 18/12: D3: Continue TI & plan for CO 13/12: D2: TI done, RSL rectification 10/12: D1: TI WIP. Continue 12/12 | TSS |  | Link reroute to 1535H - 3239B due to LOS block NE_1535H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. x1 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. FE_3239B 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. 6. ETH Cable / LAN Cable x1. | MW New Link / Reroute | Existing route 1535H - 1851B (NLOS) Link reroute to 1535H - 3239B due to LOS block. NE_1535H. 1. Install new NLOS equipment (Indoor & Outdoor). 2.Capture existing radio config and parameters. 3.Perform alignment direct towards new FE 3239B. 4.Create service cross connect and migrate service to new NLOS link. FE_3239B. 1. Install new NLOS equipment (Indoor & Outdoor). 2.Capture existing radio config and parameters. 3. Perform alignment direct towards 1535H. 4. Enable GE port patching to existing MW IDU 3239B_RTN01 (GE2). 5. Create service connect and traffic route to new FE 3239B. | [7 empty] | Allstar | SQ202411260589-Allstar | YPTT | SQ202412030129-YPTT | 2024-11-20 | 2024-11-19 | Completed | 2024-09-27 | 2024-09-30 | 2024-09-27 | 2024-10-24 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2024-10-28 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-28 | 2024-10-30 | 2024-10-28 | 2024-10-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-19 | 2024-11-20 | 2024-11-19 | 2024-11-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24101024 |  | 2024-10-11 | 2024-11-01 | Completed | 2024-10-10 | 2024-10-11 | 2024-10-10 | 2024-11-01 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-09 | 2024-12-31 | 2024-12-09 | 2024-12-30 | AKMAL//BIN RAZALI/6794000078 | YPTT TI | 2024-12-09 | 2024-12-31 | 2024-12-09 |  | AKMAL//BIN RAZALI/6794000078 | YPTT TI | [7 empty] | 2024-12-09 | 2024-12-31 | 2024-12-09 |  | AKMAL//BIN RAZALI/6794000078 | 2024-12-09 | 2024-12-31 | 2024-12-09 | 2024-12-10 | 2025-01-10 | 2025-01-10 | 2025-01-10 | 2025-01-10 | NG HONG JIE7018000036 | Logistic Team
1694C_LOS | Masreca 19 | DU00004185453 | Central | Selangor | 2.900130 | 101.630060 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 21/11: Proceed dismantle antenna at B02147 & to re-install at 1240A 24/10: Planner change FE. SOW to be completed under TX NIC 1694C 22/10: F/up with xC Syahril on the port config - still pending 10/10: D1: TI done but pending alignment. Pending PTN port infor (FE is CRAN Edotco sites) Materials DM from TX NIC 1694C DOWMY240919F1 Magicell | TSS+AA+TI | L1+ATP+PAC | 23G_1+0_112M. NE_1694C 23G SP_0.6m x1. XMC_3E_1+0 , Sub_A_Hi x1. RTN910AF x1 FE_1240A. 23G SP_0.6m x1. XMC_3E_1+0 , Sub_A_Lo x1. RTN910AF x1. | MW New Link / Reroute | Existing SM link 23G_1+0_56M_256QAM Perform link reroute to new FE B02417 with config 23G_1+0_112M. New Parallel will be introduce for the 1240A-1122A. Site Impacted: 1694C NE_1694C 1. Install new 23G SP_0.6m. 2. Install new XMC_3E_1+0 , Sub_A_Hi. 3. Install new RTN910AF , 7-ISM8-1+0.(RTN no provide by MSP team). 4. Migrate traffic to new route FE 1240A. FE_B02417. 1.Install new 23G SP_0.6m. 2.Install new XMC_3E_1+0 , Sub_A_Lo. 3.Install new RTN910AF , 7-ISM8_1+0 (RTN no provide by MSP team). 4.Enable GE1 interconnect ETH cable to existing 1240A_RTN03 (GE3). 5.Traffic migrate via existing link 1240A_RTN03 - 1122A_RTN06. | [7 empty] | MTK | SQ202411270598-MTK | Magicell | SQ202411060164-Magicell // SQ202504260146-Magicell | 2025-07-02 | 2025-07-01 | Completed | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-09-13 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-25 | 2024-11-27 | 2024-11-25 | 2024-11-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2024-10-09 | 2024-10-31 | 2024-10-09 | 2024-12-12 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2024-10-09 | 2024-10-31 | 2024-10-09 | 2024-12-16 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2024-11-22 | 2024-10-09 | 2024-10-31 | 2024-10-09 | 2024-12-05 | MOHD//SAFRI BIN ARIF/7018000166 | 2024-10-09 | 2024-10-31 | 2024-10-09 | 2024-11-21 | 2024-12-12 | 2024-12-12 |  |  | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
1247H_LOS | 99 Speedmart BDR KINRARA 1 | DU00004185454 | Central | Selangor | 3.055149 | 101.649923 |  |  |  |  | TSS Only | No available LOS | ZTE | 00. Site Out/Drop | 28/2/2025 : Done survey by Allstar. No LOS available 30/8: Pending BoQ, TX SoW Details | TSS |  | Proposed Fiber due to No LOS is available Found during actual TSS LOS survey. | MW New Link / Reroute | Proposed Fiber due to No LOS is available Found during actual TSS LOS survey. | [7 empty] | Allstar | SQ202509040797-Allstar | Allstar | No PR required-Site drop/cancel | 2025-07-02 | 2025-07-01 | Completed | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | WAN ABDULLAH SA'ID BIN WAN NAZRI6798000166 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-23 | 2024-10-24 | 2024-10-23 | 2024-10-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202506160751-GCI | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | EZRIN TASNIM BIN ABDUL GANI6798000128
3634C_LOS | Permai Prima | DU00004185455 | Central | Selangor | 3.124576 | 101.784007 |  |  |  |  | Cancel / Drop | Done under DU 3634C TX NIC | ZTE | 00. Site Out/Drop | 15/8: Done by ZTE under TX NIC 3634C (Parallel Link Activity) |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4227H_LOS | 99 Speedmart PK Menglembu Impiana | DU00004185456 | Northern | Perak | 4.556493 | 101.052090 |  |  |  | JAN 25 | TI | Doable | ZTE | 00. Integrated/RFS Done | 6/1/2025 : Digi OB - Small Cell - NE site 4227H 99 Speedmart PK Menglembu Impiana, Digi OB - 45M 3 Legged Tower - FE site 4548A Menglembu Timur RDD 30/8: Pending BoQ, TX SoW Details | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | New NLOS RTN510 equipment NE_4227H. 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable NE_4065C 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH cable / LAN Cable. | MW New Link / Reroute | Link reroute to new FE 4065C with New NLOS equipment due to LOS block NE_4227H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. FE_4065C 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.ETH cable patching to existing 4065C_RTN01 (GE2). 6.Traffic migrate to TX route 4227H-NLOS-4065C-4560A. 6.Decom existing NLOS Radio | Link reroute to new FE 4065C with New NLOS equipment due to LOS block. NE_4227H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. | Link reroute to new FE 4065C with New NLOS equipment due to LOS block FE_4065C 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.ETH cable patching to existing 4065C_RTN01 (GE2). 6.Traffic migrate to TX route 4227H-NLOS-4065C-4560A. 6.Decom existing NLOS Radio | [5 empty] | GCI | SQ202502120339-GCI | GCI | SQ202502180528-GCI // SQ202504150095-GCI | 2025-11-17 | 2025-11-10 | Completed | 2024-12-24 | 2025-02-12 | 2025-02-12 | 2025-02-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010377 |  | 2025-01-04 | 2025-02-19 | Completed | 2025-01-03 | 2025-01-04 | 2025-01-03 | 2025-02-19 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-02-19 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | GCI TI | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-02-19 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | GCI TI | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-13 | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-03-02 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | 2025-01-17: 2025-02-12; 2025-01-31: 2025-02-28; 2025-05-15: 2025-02-12; 2025-05-15: 2025-03-02 |  |  | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300144-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
W01373_LOS | W066G_W01373OD_JALANCENGALSELATAN_SETAPAK | DU00004185457 | Central | Kuala Lumpur | 3.203753 | 101.712117 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 14/11: Link ready, pending CO. Plan 14/11 13/11: MOS & TI In plan 6/11: To proceed MOS & TI use materials from TX NIC W01373 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_56M NE_W01373. 23G_SP_0.6m(MAC) x1. RTN910A x1. XMC_3E, Sub_B_Hi x1. FE_W01016 23G_SP_0.6m(MAC) x1. Install new RTN910A x1. XMC_3E,SUb_B_Lo x1. | MW New Link / Reroute | Existing SM link 23G_1+0_56M Link reroute to new FE W01016 with config 23G_1+0_112M due to LOS block. Site Impacted: W01373 NE_W01373. 1.Install new 23G_SP_0.6m(MAC). 2.Install new RTN910A, 7_ISM8-1+0. 3.Install new XMC_3E, Sub_B_Hi 4.Create service cross connect and migrate traffic to new FE. 5.Decom existing SM link. FE_W01016 1.Install new 23G_SP_0.6m(MAC). 2.Install new RTN910A,7_ISM8-1+0. 3.Install new XMC_3E,SUb_B_Lo. 4.Create service cross connect and migrate traffic to new FE. 5.Create In Band DCN. 6.Decom existing SM link. | [7 empty] | Datasco | SQ202411140206-Datasco | Datasco | SQ202411150529-Datasco // SQ202504260127-Datasco |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | use material DM from TX NIC W01373 | 2024-11-12 | 2025-03-10 | Completed | 2024-11-11 | 2024-11-12 | 2024-11-11 | 2025-03-10 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2025-03-10 | MAHADIR//BIN MOHD ZAIN/7019000101 | Datasco TI | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2025-03-10 | MAHADIR//BIN MOHD ZAIN/7019000101 | Datasco TI | 2024-12-02 | 2024-12-03 | 2024-12-02 | 2024-12-03 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-12-10 | MAHADIR//BIN MOHD ZAIN/7019000101 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-13 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
3247B_LOS | Jln Tmn Melati (REL) | DU00004185458 | Central | Kuala Lumpur | 3.191656 | 101.705820 |  |  | W49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 8/11: Allstar drop TI work. To change subcon 20/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_3247B. 18G_DP_0.6m(MAC) x1. XMC_3E-2+0, Sub_A_Hi x1. FE_W01271. 18G_DP_0.6m(MAC) x1. RTN910A x1. XMC_3E-2+0 , Sub_A_Lo x1. | MW New Link / Reroute | Existing link 18G_2+0_112M Link reroute to new FE W01271 with config 18G_2+0_112M due to LOS Block. Site Impacted: 3247B,1137C. NE_3247B. 1.Install new 18G_DP_0.6m(MAC). 2.Reuse existing 3247B_RTN02 , 7_ISM8-2+0. 3.Install new XMC_3E-2+0, Sub_A_Hi. 4.Create EPLA and service connect direct towards new FE W01271. 5.Remain cascade ETH cable between RTN03 and RTN02 for child site 1137C via this new route. 6.Migrate service to new route. Confirm and verify with NOC for the traffic status before decom. 7.Decom existing Ant & ODU. FE_W01271. 1.Install new 18G_DP_0.6m(MAC). 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E-2+0 , Sub_A_Lo. 4.Enable EPLA and service cross connect. 5.Create new In Band DCN. 6.Verify and confirm with NOC for the traffic status before decom. 7.Decom existing MW link at 1288A (1288A-3247B). | [7 empty] | Allstar | SQ202411260589-Allstar | GTSB | SQ202411250768-GTSB // SQ202504260131-GTSB | 2025-03-21 | 2025-03-20 | Completed | 2024-09-30 | 2024-10-04 | 2024-09-30 | 2024-10-10 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-21 | 2024-10-21 | 2024-10-21 | 2024-10-21 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-17 | 2025-03-18 | 2025-03-17 | 2025-03-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112276 | 18G_0.6/0.6_DP_2+0_SUB A & B. wip 18G 0.6 MAC⏸️ | 2024-11-23 | 2024-12-29 | Completed | 2024-11-22 | 2024-11-23 | 2024-11-22 | 2024-12-29 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-26 | 2025-01-31 | 2024-12-26 | 2024-12-29 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2024-12-26 | 2025-01-31 | 2024-12-26 | 2024-12-29 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2024-12-27 | 2024-12-27 | 2024-12-27 | 2024-12-27 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-12-26 | 2025-01-31 | 2024-12-26 | 2025-01-03 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2024-12-26 | 2025-01-31 | 2024-12-26 | 2024-12-27 | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2025-01-24 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
2442A_LOS | AU1 Setiawangsa | DU00004185459 | Central | Selangor | 3.177054 | 101.737491 |  |  |  |  | Cancel / Drop | Done under TX NIC 2242A | ZTE | 00. Site Out/Drop | 10/7: Done by ZTE under TX NIC 2442A (Swap Activity) | TSS |  | Link reroute to new FE 2088A with config 18_2+0_112M NE_2442A 1.Install new DP_0.6m ant x1. 2.Install new XMC_3E x2. 3.Install new OMT coupler x1. 4.Install new RTN910A x1. FE_2088A 1.Install new DP_0.6m ant x1. 2.Install new XMC_3E x2. 3.Install new OMT coupler fx1. 4.Install new RTN910A x1. | MW New Link / Reroute | Existing link 18G_1+0_112M Link reroute to new FE 2088A with config 18_2+0_112M NE_2442A 1.Install new DP_0.6m ant. 2.Install new XMC_3E_2+0. 3.Install new OMT coupler for 2+0 config. 4.Install new RTN910A , 7_ISM8-2+0. (RTN Naming provide by MSP team). 5.Migarte traffic to new FE route 2088A-1271A(CP). 6.Decom existing link. FE_2088A 1.Install new DP_0.6m ant. 2.Install new XMC_3E_2+0. 3.Install new OMT coupler for 2+0 config. 4.Install new RTN910A, 7_ISM8-2+0.(RTN Naming provide by MSP team). 5.Enable GE port 1 interconnect to EM6_3 on existing RTN_02. 6.New traffic re-route to 2442A-2088A-1271A. 7.Decom existing link. New parallel link for northbound is required. Upon 2442A reroute to new 1271A CP. 2088A-1271A Parallel link. | [7 empty] | MTK | SQ202411270598-MTK | GCI | No PR required-Work at TSS only | 2024-11-20 | 2024-11-19 | Completed | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-09-13 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-22 | 2024-10-24 | 2024-10-22 | 2024-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-19 | 2024-11-20 | 2024-11-19 | 2024-11-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1783A_LOS | Tmn Bkt Sentosa | DU00004185460 | Central | Selangor | 2.995913 | 101.476404 |  |  | W49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 2/10: Pending Site DO | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M. NE_1783A DP 0.6m x1.(MAC)+OMT x1 RTN910A x1. XMC_3E x2 , Sub (A & B_Hi) x2. FE_B00644 DP 0.6m x1.(MAC)+OMT x1. RTN910A x1. XMC_3E x2 , Sub (A & B_Lo) x2. | MW New Link / Reroute | Existing 18G_1+0_112M Reroute existing link to new FE B00644 with 18G_2+0_112M. NE_1783A 1.Install new DP 0.6m. 2.Install new RTN910A , 7-SIM8-2+0. (RTN naming provide by MSP team). 3.Install new XMC_3E-2+0. 4.Install OMT coupler for 2+0 config. 5.Migrate traffic to new route and new RTN910. 6.Decom existing MW link (1783A-2646B). FE_B00644 1.Install new DP 0.6m 2.Install new RTN910A, 7_ISM*-2+0. (RTN Naming provide by MSP team). 3.Install new XMC_3E-2+0. 4.Install OMT Coupler. 5.Create new In-Band DCN and service cross connect. 6.Enable GE port to connect PTN. 7. Decom existing MW link (2646B-1783A). | [7 empty] | MTK | SQ202411270598-MTK | GTSB | SQ202412310265-GTSB // SQ202504260131-GTSB | 2025-07-02 | 2025-07-01 | Completed | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-16 | 2024-10-17 | 2024-10-16 | 2024-10-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Manager | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-24 | 2024-10-25 | 2024-10-24 | 2024-10-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112564 | 18G_0.6/1.2_DP_2+0_SUB A & B. wip 18G 0.6 MAC & 1.2 MAC⏸️ | 2024-11-26 | 2024-12-29 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2024-12-29 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-26 | 2025-01-31 | 2024-12-26 | 2024-12-29 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2024-12-26 | 2025-01-31 | 2024-12-26 | 2024-12-29 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2024-12-28 | 2024-12-28 | 2024-12-28 | 2024-12-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-12-26 | 2025-01-31 | 2024-12-26 | 2024-12-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2024-12-26 | 2025-01-31 | 2024-12-26 | 2024-12-27 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
1170C_LOS | KFC I-City | DU00004185461 | Central | Selangor | 3.064661 | 101.483274 |  |  | W49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 30/8: Pending BoQ, TX SoW Details | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_1170C 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. FE_2041A. 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. | MW Parallel Link | Link Reroute to new FE B01402 with 23G_2+0_112M due to LOS block. NE_1170C 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Enable EPLA and service cross connect. 5.Traffic migrate to new route and new link. 6.Decom existing MW link. FE_B01402. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Enable EPLA & Service cross connect. 5.Create new In Band DCN 6.Traffic migrate to new route and new link. 7.Decom existing MW link. | [7 empty] | GTSB | SQ202411260594-GTSB | GTSB | SQ202411250768-GTSB // SQ202504260131-GTSB | 2025-02-08 | 2025-02-10 | Completed | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2024-12-31 | laina@girobumi.com.mylaina@girobumi.com.my |  |  | 1.00 | Unassigned | Completed |  | 2024-12-31 | 2025-01-31 | 2024-12-31 | 2025-01-07 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-01-07 | 2025-01-08 | 2025-01-07 | 2025-01-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-07 | 2025-02-08 | 2025-02-07 | 2025-02-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112523 |  | 2024-11-26 | 2024-12-29 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2024-12-29 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-22 | 2024-12-31 | 2024-12-22 | 2024-12-29 | NIK MOHD HAIRIE//ZAKARIA/6799000281 |  | 2024-12-22 | 2024-12-31 | 2024-12-22 | 2024-12-29 | NIK MOHD HAIRIE//ZAKARIA/6799000281 |  | 2024-12-27 | 2024-12-27 | 2024-12-27 | 2024-12-27 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-12-22 | 2024-12-31 | 2024-12-22 | 2025-03-06 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2024-12-22 | 2024-12-31 | 2024-12-22 | 2024-12-23 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
1399H_LOS | 99 Speedmart KG PENDAMAR | DU00004185462 | Central | Selangor | 2.979160 | 101.430350 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop 20/9: Pending Tx Solution for HU | TSS |  | Proposed Fiber due to All FE no LOS via TSS Survey | MW New Link / Reroute | Proposed Fiber due to All FE no LOS via TSS survey | [7 empty] | Allstar | SQ202411260589-Allstar | Allstar | No PR required-Site drop/cancel | 2024-12-27 | 2024-12-26 | Completed | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-01 | 2024-10-31 | 2024-10-10 | 2024-10-10 | WAN ABDULLAH SA'ID BIN WAN NAZRI6798000166 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-26 | 2024-12-27 | 2024-12-26 | 2024-12-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-12-26 | 2024-12-27 | 2024-12-26 | 2024-12-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1770A_LOS | Tmn Rinching | DU00004185463 | Central | Selangor | 2.929752 | 101.851631 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | Link ready. 3rd leg parallel link protection 14/11: Continue NE & plan CO 15/11 9/11: TI FE done, pending NE. Pending EB CRQ approval 8/11: MOS & Pre-installation in progress | TSS+AA+TI | L1+ATP+PAC | Links reroute to new FE 2843C with 23G_2+0_112M config. NE_1770A 1.Install new 23G_DP_0.6m (MAC) X1 2.Install new RTN910A x1. 3.Install new 23G_XMC-3 , Sub_(A & B_Lo) x2. 4.Install OMT coupler for 2+0 config x1. FE_2843C 1.Install new 23G_DP_0.3m (MAC) x1. 2.Install new 23G_XMC-3, Sub_(A & B_Hi) x2. 3.Install OMT coupler for 2+0 config x1. 4.Install ISM8 x1. | MW New Link / Reroute | Links reroute to new FE 2843C with 23G_2+0_112M config due to LOS block and it serve for 3rd leg protection with 1G cap requirement. NE_1770A 1.Install new 23G_DP_0.6m (MAC). 2.Install new RTN910A,7_ISM8-2+0. (RTN no provide by MSP team). 3.Install new 23G_XMC-3_2+0 ODU, Sub_ (A & B_Lo). 4.Install OMT coupler for 2+0 config. 5.Create EPLA and service cross connect. 6.Traffic carry via MW route to new CP at 1851B. For 2843C , prioritize install the northbound parallel link (2843C-1851B) before making intermediate link connection. FE_2843C 1.Install new 23G_DP_0.3m.(MAC) 2.Reuse existing RTN 910A, install 3_ISM8-2+0 (Parallel link RTN910A). 3.Install new 23G_XMC-3_2+0 ODU, Sub_ (A & B_Hi). 4.Install OMT coupler for 2+0 config. 5.Create EPLA and service cross connect. 6.Traffic carry via MW route to new CP at 1851B. Create new DU ID 2843C-1851B | [7 empty] | MTK | SQ202411270598-MTK | GCI | SQ202411150539-GCI // SQ202509020092-GCI | 2024-11-20 | 2024-11-19 | Completed | 2024-10-07 | 2024-10-07 | 2024-10-07 | 2024-10-07 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-15 | 2024-10-16 | 2024-10-15 | 2024-10-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-15 | 2024-10-16 | 2024-10-15 | 2024-10-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-19 | 2024-11-20 | 2024-11-19 | 2024-11-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Manager | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24103010 |  | 2024-10-31 | 2024-11-05 | Completed | 2024-10-30 | 2024-10-31 | 2024-10-30 | 2024-11-05 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-08 | 2024-11-15 | 2024-11-07 | 2024-11-08 | HUSSAIN//MUSTANSAR/6800000283 | GCI TI | 2024-11-08 | 2024-11-15 | 2024-11-07 | 2024-12-06 | HUSSAIN//MUSTANSAR/6800000283 | GCI TI | 2024-11-15 | 2024-11-15 | 2024-11-15 | 2024-11-15 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-11-08 | 2024-11-15 | 2024-11-07 | 2024-11-15 | HUSSAIN//MUSTANSAR/6800000283 | 2024-11-12: 2024-11-08; 2024-11-12: 2024-11-15; 2024-11-12: 2024-11-07; 2024-11-13: 2024-11-08 |  |  | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
2656B_LOS | Jln Meranti Permai | DU00004185464 | Central | Selangor | 2.969993 | 101.604195 | WK04 | JAN 25 | WK04 | JAN 25 | Cancel / Drop | Cancel proceed, no LOS | ZTE | 00. Site Out/Drop | 22/1/2025 : Only survey activity due to FE option LOS block 21/1/2025 : Cancel proceed spillover tomorrow 16/1/2025 : Digi OB - 3M Bipod - RT - NE site 2656B Jln Meranti Permai, CELCOM (M) - Tower - FE site 2049B Taman Mas Sepang(Celcom), CELCOM AXIATA BERHAD - TOWER 30M LAND - Patching site B01048 B061L_B01048OD_TMNMASSEPANG 12/9: Done by ZTE under TX NIC 2656B (Swap Activity) | TSS |  |  | MW New Link / Reroute | NO LOS. CANCEL DROP |  |  | XMC_3E | DP | 18G | 0.6M | 0.6M | Allstar | SQ202411260589-Allstar | Magicell | No PR required-Work at TSS only | 2025-07-02 | 2025-07-01 | Completed | 2024-09-10 | 2024-09-16 | 2024-09-10 | 2024-09-26 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | WAN ABDULLAH SA'ID BIN WAN NAZRI6798000166 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-08 | 2024-10-09 | 2024-10-08 | 2024-10-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25011645 |  | 2025-01-17 | 2025-01-20 | Completed | 2025-01-16 | 2025-01-17 | 2025-01-16 | 2025-01-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-21 | 2025-01-31 |  |  | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-01-21 | 2025-01-31 |  |  | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | [7 empty] | 2025-01-21 | 2025-01-31 |  |  | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2024-11-12: 2025-01-21; 2024-11-12: 2025-01-31 | [7 empty] | GCI_AA | SQ202510300160-GCI | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | CHEONG/SENG/WAH/7018000306
2653B_LOS | Jalan Nusa Putra 1_2g | DU00004185465 | Central | Selangor | 2.933536 | 101.614261 |  |  |  |  | Cancel / Drop | Done under TX NIC 2653B_Additional | ZTE | 00. Site Out/Drop | 14/11: Solution done under TX NIC 2653B_Additional |  |  | 23G_2+0_112M NE_2653B 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1 XMC_3E , Sub A & B_Hi x2. FE_2239A. 23G_DP_0.6m(MAC)+OMT x1. XMC_3E, Sub A & B_Lo x2. RTN910A x1. | Cancel / Drop | Link reroute to new FE 2239A with 23G_2+0_112M due to LOS Block. NE_2653B 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0 3.Install new XMC_3E , Sub A & B_Hi 4.Enable EPLA & Service cross connect. 5.Traffic migrate to new route and new link. 6.Decom existing MW link. FE_2239A. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install XMC_3E, Sub A & B_Lo. 3.Install new RTN910A,7_ISM8-2+0. 4.Enable EPLA and Service cross connect. 5.Traffic migrate to new route and new link. 6.Create In band DCN. 7.Decom existing MW link. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3751B_LOS | Madrasah Al-Islah | DU00004185466 | Central | Kuala Lumpur | 3.180839 | 101.694936 |  | JAN 25 | WK02 | JAN 25 | TI | No LOS available | ZTE | 00. Site Out/Drop | 14/1/2025 : Site no LOS available and skylift also no parking. Proposed to install LL 6/1/2024 : SKYLINE TECHNOLOGY - 18M DBKL Lampole - NE site 3751B Madrasah Al-Islah, VOLKSBAHN TECHNOLOGIES - MONOPOLE 30M LAND - FE site W01334 W066E_W01334OD_LRT_SENTUL 26/9: LOS hunting WIP. Skylift D1. Parking skylift issue - main road blocked | TSS |  |  | MW New Link / Reroute | DROPPED DUE TO NO LOS. ALREADY SEND LOS REPORT TO PROPOSE FIBER. | [7 empty] | MTK | SQ202411270598-MTK | MTK | No PR required-Work at TSS only | 2025-02-15 | 2025-02-14 | Completed | 2025-01-10 | 2025-01-13 | 2025-01-13 | 2025-01-13 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-21 | 2025-01-22 | 2025-01-21 | 2025-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-01-28 | 2025-01-29 | 2025-01-28 | 2025-01-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-14 | 2025-02-15 | 2025-02-14 | 2025-02-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO | 2025-01-04 |  | Ongoing | 2025-01-03 | 2025-01-04 | 2025-01-03 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2024-09-26 | 2024-09-30 | 2024-09-25 |  | MUHAMMAD HAFIZUL/BIN/MAT RUDIN/8225000018 | MTK TI | 2024-09-26 | 2024-09-30 |  |  | MUHAMMAD HAFIZUL/BIN/MAT RUDIN/8225000018 | MTK TI | [7 empty] | 2024-09-26 | 2024-09-30 | 2024-09-25 |  | MUHAMMAD HAFIZUL/BIN/MAT RUDIN/8225000018 | 2024-11-12: 2024-09-26; 2024-11-12: 2024-09-30; 2024-11-12: 2024-09-25
2690A_LOS | IMU Bukit Jalil | DU00004185467 | Central | Kuala Lumpur | 3.060694 | 101.687889 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 8/11: Cutover done. Post-CO T/S ongoing 7/11: Link ready, pending cutover due TX NIC W01420 WIP 6/11: Change ODU to XMC3E done. Need to revise LB. Req CR for cut tree 4/11: D2: TI done, RSL -41dbm. To change ODU XMC3E for high TX Power, plan CO 6/11 Materials DM from TX NIC 2690A DOWMY240718EZ Magicell | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Link reroute to new FE W01420 with config 18G_1+0_112M. NE_2690A. 1. Install new 23G_0.6m x1. 2. Install RTN910A x1. 3. Install XMC_3E ODU , Sub_B_Lo x1. FE_W01420. 1. Install new 23G_0.6m x1. 2. Install RTN910A x1. 3. Install XMC_3E ODU , Sub_B_Hi x1. | MW New Link / Reroute | Existing link 23G_1+0_56M Link reroute to new FE W01420 with config 18G_1+0_112M. Site Impacted : 2690A , W01420 , W00818 , W00389. NE_2690A 1. Install new 23G_0.6m. 2. Install RTN910A. 3. Install XMC_3E ODU , Sub_B_Lo. 4. Alignment direct towards to W01420. 5. Migrate traffic to new FE. 6.Decom existing SM link (2690A-1255A). FE_W01420 1. Install new 23G_0.6m 2. Install RTN910A. 3. Install XMC_3E ODU , Sub_B_Hi. 4. Alignment direct towards to 2690A. 5. Enable GE port 1 connect ETH cable to existing SIAE IDU LAN 3 port.(CT10236 MESRARIA2) 6. Create In-band DCN and service cross connect. 7. Traffic drop at W00389 CP via existing MW route MW01420-W00818-W00389. | [7 empty] | MTK | SQ202409230199-MTK // SQ202410290950-MTK | Magicell | SQ202411120059-Magicell // SQ202504260146-Magicell | 2024-11-28 | 2024-11-27 | Completed | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-07 | 2024-10-08 | 2024-10-07 | 2024-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-15 | 2024-10-16 | 2024-10-15 | 2024-10-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-27 | 2024-11-28 | 2024-11-27 | 2024-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24102377 |  | 2024-10-24 | 2024-10-26 | Completed | 2024-10-23 | 2024-10-24 | 2024-10-23 | 2024-10-26 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-23 | 2024-10-31 | 2024-10-23 | 2024-11-19 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2024-10-23 | 2024-10-31 | 2024-10-23 | 2024-11-19 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-10-23 | 2024-10-31 | 2024-10-23 | 2024-11-11 | MOHD//SAFRI BIN ARIF/7018000166 | 2024-10-23 | 2024-10-31 | 2024-10-23 | 2024-11-07 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | NG HONG JIE7018000036 | Logistic Team | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358
1469H_LOS | 99 Speedmart TELOK PANGLIMA GARANG 1 | DU00004185468 | Central | Selangor | 2.908612 | 101.466945 | WK07 | FEB 25 | WK07 | FEB 25 | Cancel / Drop | Use DU 1469H_LOS_1 | ZTE | 03. TSS Only | 15/1/2025 : Cancel proceed due to TM PTW expired 6/1/2025 : Digi OB - Small Cell - NE site 1469H 99 Speedmart TELOK PANGLIMA GARANG 1, TELEKOM (M) - Tower - FE site 2719A TPG industry 8/11: Allstar drop TI work. To change subcon 30/8: Pending BoQ, TX SoW Details | TSS |  | Link reroute to new FE 2719A due to LOS block from previous FE. NE_1469H Nlos-OptiX RTN /PI-DC B10 /Power injector x1. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1 FE_2719A Nlos-OptiX RTN /PI-DC B10 /Power injector x1. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1 | MW New Link / Reroute | Link reroute to new FE 2719A due to LOS block from previous FE. NE_1469H 1.Install new NLOS equipment (Indoor & Outdoor). 2.Capture existing radio config and parameters. 3.Perform alignment direct towards new FE 2719A. 4.Create service cross connect and migrate service to new NLOS link. FE_2719A 1.Install new NLOS equipment (Indoor & Outdoor). 2.Capture existing parameters before redeploying. 3.Alignment direct towards opposite site 1469H. 4.Patch ETH cable to existing SM IDU (2719A-1126A). 5.Create new In-band DCN via new route. 6.Traffic migrate to new route via existing SM MW link (2719A-1126A). | [7 empty] | Allstar | SQ202409260132-Allstar | Magicell | No PR required-Work at TSS only | 2025-07-02 | 2025-07-01 | Completed | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-11-07 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-13 | 2024-11-30 | 2024-11-13 | 2024-11-13 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-26 | 2025-03-27 | 2025-03-26 | 2025-03-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24110664 | no stock Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material⏸️ | 2024-11-07 | 2024-11-28 | Completed | 2024-11-06 | 2024-11-07 | 2024-11-06 | 2024-11-28 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-11-29 |  |  |  | YPTT TI
2677C_LOS | Tmn Kemuning Banting | DU00004185469 | Central | Selangor | 2.804130 | 101.498810 |  |  | W49-52 | DEC 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 3/12: D1: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Links reroute to new FE B02058 with config 18G_1+0_112M due to LOS Block. NE_2677C 1.Reuse existing 18G_SP_0.6m ant x1. 2.Reuse existing RTN910A x1. 3.Reuse XMC_3, Sub B_Hi x1. FE_B02058 1.Install new 18G_SP_0.6m ant x1. 2.Install new RTN910A x1. 3.Install new XMC_3, Sub_B_Lo x1. | MW New Link / Reroute | Existing link config 18G_1+0_112M. Link reroute to new FE B02058 with config 18G_1+0_112M due to LOS Block. NE_2677C 1.Reuse existing 18G_SP_0.6m ant 2.Reuse existing RTN910A ,7_ISM8-1+0. 3.Reuse XMC_3 ODU , Sub B_Hi 4.Alignment direct towards new FE B02058. 5.Traffic migrate direct to new FE B02058 CP site. FE_B02058 1.Install new 18G_SP_0.6m ant. 2.Install new RTN910A,7_ISM8-1+0. 3.Install new XMC_3-1+0 , Sub_B_Lo 4.Alignment direct towards FE 2677C. 5.Create new In-Band DCN. 6.Enable GE port and service cross connect. 7.Patching ETH to Fiber_Cisco. 8.Decom existing ant and XMC_3 ODU at 1130A (1130A-2677C). | [7 empty] | MTK | SQ202411270598-MTK | GCI | SQ202411150539-GCI // SQ202504150088-GCI // SQ202509020092-GCI | 2024-11-13 | 2024-11-12 | Completed | 2024-10-07 | 2024-10-07 | 2024-10-07 | 2024-10-07 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-15 | 2024-10-16 | 2024-10-15 | 2024-10-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-15 | 2024-10-16 | 2024-10-15 | 2024-10-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-12 | 2024-11-13 | 2024-11-12 | 2024-11-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112277 |  | 2024-11-23 | 2024-12-15 | Completed | 2024-11-22 | 2024-11-23 | 2024-11-22 | 2024-12-15 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-03 | 2024-12-10 | 2024-12-03 | 2024-12-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2024-12-03 | 2024-12-10 | 2024-12-03 | 2024-12-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2024-12-04 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-12-03 | 2024-12-10 | 2024-12-03 | 2024-12-11 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2024-12-03 | 2024-12-10 | 2024-12-03 | 2024-12-03 | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
1336C_LOS | Taman Naga Emas | DU00004185470 | Central | Kuala Lumpur | 3.077123 | 101.696812 |  |  |  |  | Cancel / Drop | Done under DU 1336C TX NIC | ZTE | 00. Site Out/Drop | 16/7: Done by ZTE under TX NIC 1336C (Reroute Link Activity) |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2736A_LOS | Tmn Bukit Desa | DU00004185471 | Central | Kuala Lumpur | 3.110540 | 101.685530 |  |  |  |  | RFS | Pending L1 | ZTE | 00. Integrated/RFS Done | 14/11: Cutover done 13/11: Link ready, pending CO 12/11: MOS & Pre-installation in plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Link reroute to new FE W00097 due to LOS block NE_2736A 1.Install 23G_SP_0.6m (MAC) x1. 2.Install RTN910A x1. 3.Install XMC_3, Sub_A_Lo x1. FE_W00097 1.Install 23G_SP_0.6m(MAC) x1. 2.Install RTN910A x1. 3.Install XMC_3, Sub_A_Hi x1. | MW New Link / Reroute | Exsiting link 23G_1+0_56M Link reroute to new FE W00097 due to LOS block Site Impacted : 2736A,1735A. NE_2736A 1.Install 23G_SP_0.6m (MAC). 2.Install RTN910A, 7_ISM8-1+0.(RTN no provide by MSP team). 3.Install XMC_3, Sub_A_Lo. 4.Create service cross connect. 5.Migrate traffic to new link. 6.Decom existing SM link. FE_W00097 1.Install 23G_SP_0.6m(MAC). 2.Install RTN910A, 7_ISM8-1+0.(RTN no provide by MSP team). 3.Install XMC_3, Sub_A_Hi. 5.Create In-Band DCN and service cross connect. 6.Enable GE port connect to Ibeam port. 7.Decom existing SM link. | [7 empty] | MTK | SQ202411270598-MTK | GCI | SQ202411150539-GCI // SQ202504150088-GCI // SQ202509020092-GCI | 2024-11-28 | 2024-11-27 | Completed | 2024-10-16 | 2024-10-16 | 2024-10-16 | 2024-10-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-17 | 2024-10-18 | 2024-10-17 | 2024-10-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-22 | 2024-10-23 | 2024-10-22 | 2024-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-27 | 2024-11-28 | 2024-11-27 | 2024-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24102542 |  | 2024-10-26 | 2024-11-05 | Completed | 2024-10-25 | 2024-10-26 | 2024-10-25 | 2024-11-05 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-12 | 2024-11-19 | 2024-11-11 | 2024-11-12 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2024-11-12 | 2024-11-19 | 2024-11-11 | 2025-01-05 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-11-12 | 2024-11-19 | 2024-11-11 | 2025-02-05 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2024-11-12 | 2024-11-19 | 2024-11-11 | 2024-11-12 | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
3770B_LOS | Jalan Yaakob Latif | DU00004185472 | Central | Kuala Lumpur | 3.108145 | 101.727818 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 28/10: Cutover done 22/10: TI FE done, pending relocate antenna and configure NE due no site cabinet key (with lock bar). Link install at W00416 (xC PTN) 18/10: Materials DM from TX NIC 3770B YPTT | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Link reroute to new FE W00416 with config 18G_1+0_112M. Site Impacted: 3770B. NE_3770B 1.Install 18G_0.6m(MDD) x1. 2.Install new RTN910A x1. 3.Install XMC_5D ODU_1+0 , Sub_A_Lo x1. FE_W00416. 1.Install 18G_0.6m(MDD) x1. 2.Install new RTN910A x1. 3.Install XMC_5D ODU_1+0 , Sub_A_Hi x1. | MW New Link / Reroute | Link reroute to new FE W00416 with config 18G_1+0_112M. Site Impacted: 3770B. NE_3770B 1.Install 18G_0.6m(MDD). 2.Install new RTN910A. 3.Install XMC_5D ODU_1+0 , Sub_A_Lo. 4.Config 112M_1+0 and service cross connect. 5.Migrate traffic to new link. 6.Decom existing MW link. FE_W00416. 1.Install 18G_0.6m(MDD). 2.Install new RTN910A. 3.Install XMC_5D ODU_1+0 , Sub_A_Hi. 4.Config 112M_1+0 and service cross connect. 5.Create new In-band DCN. 6.Enable GE port patching ETH to PTN_Fiber. 7.Traffic route to new CP at W00416. 8.Decom existing MW link. | [7 empty] | Allstar | SQ202411260589-Allstar | YPTT | SQ202411120060-YPTT | 2025-07-09 | 2025-07-09 | Completed | 2024-10-02 | 2024-10-31 | 2024-10-02 | 2024-10-08 | WAN ABDULLAH SA'ID BIN WAN NAZRI6798000166 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-01 | 2024-10-18 | 2024-10-18 | 2024-10-18 | WAN ABDULLAH SA'ID BIN WAN NAZRI6798000166 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | DM materials from TX NIC 3770B |  |  | Not started | [8 empty] | Unassigned | Not started |  | 2024-10-28 | 2024-11-09 | 2024-10-28 |  | NORDIN/BIN/MAT REJAB/6794000106 | YPTT TI | 2024-10-28 | 2024-11-09 | 2024-10-28 |  | NORDIN/BIN/MAT REJAB/6794000106 | YPTT TI | 2024-10-29 | 2024-10-29 | 2024-10-29 | 2024-10-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-10-28 | 2024-11-09 | 2024-10-28 | 2025-01-16 | NORDIN/BIN/MAT REJAB/6794000106 | 2024-11-12: 2024-10-28; 2024-11-12: 2024-11-09; 2024-11-12: 2024-10-28; 2024-11-13: 2024-12-17 |  |  | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202509250626-GCI | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
2205A_LOS | Al-ikhwan Keramat | DU00004185473 | Central | Kuala Lumpur | 3.167859 | 101.724258 |  |  |  |  | Cancel / Drop | Done under TX NIC 2205A | ZTE | 00. Site Out/Drop | 6/8: Done by ZTE under TX NIC 2205A (Reroute Link Activity) |  |  | NA | Cancel / Drop | Link reroute to new FE 1266A follow NIC reroute new FE solution. | [7 empty] | MTK | No PR required-Site drop/cancel | MTK | No PR required-Site drop/cancel |  |  | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300116-GTSB
3564C_LOS | Jasmin Apartment LP | DU00004185474 | Central | Kuala Lumpur | 3.196260 | 101.728469 |  |  | W49-52 | DEC 24 | RFS | RFS done | ZTE | 00. Integrated/RFS Done | 5/12: D2: Cutover done 4/12: D1: TI done, pending alignment. Continue 5/12 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Link reroute to new FE 1435A with config 23G_1+0_112M due to LOS Block. 1435A the minor CME to extend the arm bracket 2m is required. NE_3564C 1.Install new 23G_SP_0.6m(MAC) x1. 2.Install new RTN910A x1. 3.Install new 23G_XMC-3, Sub A_Lo x1. FE_1435A.(Minor CME to extend the arm bracket 2m is required). 1.Install new 23G_SP_0.6m(MAC) x1. 2.Install new ISM8 x1. 3.Install new 23G_XMC-3,Sub A_Hi x1. | MW New Link / Reroute | Link reroute to new FE 1435A with config 23G_1+0_112M due to LOS Block. 1435A the minor CME to extend the arm bracket 2m is required. NE_3564C 1.Install new 23G_SP_0.6m(MAC). 2.Install new RTN910A,7_ISM8-1+0.(RTN no provide by MSP team). 3.Install new 23G_XMC-3, Sub A_Lo. 4.Migrate traffic to new link. 5.Decom existing link. FE_1435A.(Minor CME to extend the arm bracket 2m is required). 1.Install new 23G_SP_0.6m(MAC). 2.Install new 23G_XMC-3,Sub A_Hi. 3.Install new 3_ISM8-1+0 into existing RTN02. 4.Enable EPLA and service cross connect via existing MW link direct towards CP at 1737A. 5.Decom existing MW link. | [7 empty] | Allstar | SQ202411120051-Allstar | Allstar | SQ202411150526-Allstar // SQ202504260124-Allstar | 2024-10-31 | 2024-10-23 | Completed | 2024-09-30 | 2024-10-04 | 2024-09-30 | 2024-10-10 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-01 | 2024-10-31 | 2024-10-16 | 2024-10-16 | WAN ABDULLAH SA'ID BIN WAN NAZRI6798000166 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-23 | 2024-10-24 | 2024-10-23 | 2024-10-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-23 | 2024-10-25 | 2024-10-23 | 2024-10-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24102221 |  | 2024-10-23 | 2024-11-01 | Completed | 2024-10-22 | 2024-10-23 | 2024-10-22 | 2024-11-01 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-01 | 2024-12-31 | 2024-12-03 | 2025-03-21 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | Allstar TI | 2024-12-01 | 2024-12-31 | 2024-12-03 | 2025-03-21 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | Allstar TI | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-12-01 | 2024-12-31 | 2024-12-03 | 2024-12-24 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | 2024-12-01 | 2024-12-31 | 2024-12-03 | 2024-12-04 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | CHEONG/SENG/WAH/7018000306
1370B_LOS | Seksyen 6B Bdr. Kinrara | DU00004185475 | Central | Kuala Lumpur | 3.045497 | 101.664862 |  |  |  |  | Cancel / Drop | Done under DU 1370B TX NIC | ZTE | 00. Integrated/RFS Done | 16/8: Done by ZTE under TX NIC 1370B (Swap Activity) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_1370B 23G_SP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A_Lo x1. FE_3292C 23G_SP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A_Hi x1 | MW New Link / Reroute | Link reroute with 23G_1+0_112M configuration to new FE 3292C due to existing link being fully blocking by building. Site Impacted 1370B. NE_1370B 1.Install new 23G_SP_0.6M(MAC)+OMT 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by Ops Team). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and traffic migrate to new link + new FE routing. 5.Decom existing MW link (1370B-3666A). FE_3292C 1.Install new 223G_SP_0.6M(MAC)+OMT. 2.Reuse existing 3292C_RTN02( ID : 34196). 3.Install new 4_ISM8-1+0 into existing 3292C_RTN02 (ID : 34196). 4.Install new XMC_3E , Sub A_Hi. 5.Create service cross connect and EPLA to existing upstream link. 6.Traffic migrate to new link and NE FE routing. 7.Decom existing MW link (3666A-1370B). | Link reroute with 23G_1+0_112M configuration to new FE 3292C due to existing link being fully blocking by building. Site Impacted 1370B. NE_1370B 1.Install new 23G_SP_0.6M(MAC)+OMT 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by Ops Team). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and traffic migrate to new link + new FE routing. 5.Decom existing MW link (1370B-3666A). | Link reroute with 23G_1+0_112M configuration to new FE 3292C due to existing link being fully blocking by building. Site Impacted 1370B. FE_3292C 1.Install new 223G_SP_0.6M(MAC)+OMT. 2.Reuse existing 3292C_RTN02( ID : 34196). 3.Install new 4_ISM8-1+0 into existing 3292C_RTN02 (ID : 34196). 4.Install new XMC_3E , Sub A_Hi. 5.Create service cross connect and EPLA to existing upstream link. 6.Traffic migrate to new link and NE FE routing. 7.Decom existing MW link (3666A-1370B). | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202507090481-GCI | GCI | SQ202509020086-GCI // SQ202509020092-GCI | 2025-08-21 | 2025-08-20 | Completed | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-14 | 2025-08-15 | 2025-08-14 | 2025-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082145 | No 23G_1+0_0.6/0.6 | 2025-08-22 | 2025-08-22 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-28 | 2025-09-04 | 2025-08-28 | 2025-09-03 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-08-28 | 2025-09-04 | 2025-08-28 | 2025-09-04 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-28 | 2025-08-28 | 2025-09-04 | 2025-08-28 | 2025-09-04 | Ragunalan//A/L L.Krisnan6000006720 | 2025-08-02 | 2025-08-09 | 2025-08-02 | 2025-08-02 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507080517-GCI | 2025-08-03 | 2025-08-03 | 2025-08-03 | 2025-08-03 | CHEONG/SENG/WAH/7018000306
2950A_LOS | Persiaran Batu Nilam | DU00004185476 | Central | Selangor | 3.000404 | 101.431902 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 19/11: D2: Cutover done. Post-CO T/S ongoing 18/11: D1: TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Perform link reroute to new FE 2777C with config 15G_4+0_512M CA.. NE_2950A 1.New 15G_DP 0.6m antenna x1. 2.New RTN910AF x1. 3.ISM8 x2. 4.15G_XMC_5D with CA x1. FE_2777C 1.New 15G_DP 0.6m antenna x1. 2.New RTN910AF x1. 3.ISM8 x2. 4.15G_XMC_5D with CA x1. | MW New Link / Reroute | Existing 13G_2+0_28M. Perform link reroute to new FE 2777C with config 15G_4+0_512M CA. Site Impacted: 2950A Site status : Post MOCN. NE_2950A 1.Install new 15G_DP 0.6m antenna. 2.Install new RTN910AF. 3_ISM8-2+0 & 4_ISM8-2+0 with EPLA (RTN naming provide by MSP team). 3.Install new 15G_XMC_5D_4+0 ODU with CA. 4.Config freq TX & RX for respective V & H channels. 5.Alignment direct towards new FE 2777C. 6.Migrate service link to new FE. 7.Decom existing MW link. FE_2777C 1.Install new 15G_DP 0.6m antenna. 2.Install new RTN910AF, 3_ISM8-2+0 & 4_ISM8-2+0 with EPLA. (RTN naming provide by MSP team). 3.Install new 15G_XMC_5D_4+0 ODU with CA. 4.Config freq TX & RX for respective V & H channels. 5.Alignment direct towards 2905A. 6.Create new In-Band DCN & service cross connect. 7.Decom existing MW link. | [7 empty] | MTK | SQ202411270598-MTK | GCI | SQ202411150539-GCI // SQ202509020092-GCI | 2024-11-13 | 2024-11-12 | Completed | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-22 | 2024-10-24 | 2024-10-22 | 2024-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-22 | 2024-10-24 | 2024-10-22 | 2024-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-12 | 2024-11-13 | 2024-11-12 | 2024-11-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24102543 |  | 2024-10-26 | 2024-11-05 | Completed | 2024-10-25 | 2024-10-26 | 2024-10-25 | 2024-11-05 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-18 | 2024-11-25 | 2024-11-18 | 2024-12-06 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2024-11-18 | 2024-11-25 | 2024-11-18 | 2024-12-06 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-19 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-11-18 | 2024-11-25 | 2024-11-18 | 2024-11-29 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2024-11-18 | 2024-11-25 | 2024-11-18 | 2024-11-18 | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
W00103_LOS | W066O_W00103OD_EMERALD | DU00004185477 | Central | Kuala Lumpur | 3.143610 | 101.707610 | WK02 | JAN 25 | WK02 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 10/1/2025 : Cutover done 9/1/2025 : Installation complete, pending cutover due to access limit 8/1/2025 : NE installation complete, pending install FE site due to receive wrong keys 6/1/2025 : EDOTCO (M) SDN BHD - TRIPOD 6M LAND - NE site W00103 W066O_W00103OD_EMERALD, Digi OB - 3M Boom - RT - FE site 1063B BERJAYA TIME SQUARE 30/8: Pending BoQ, TX SoW Details | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M 23G_DP_0.6m(MAC)+OMT x1. XMC_3E , Sub A & B_Hi x2. RTN910A x1. FE_1063B 23G_DP_0.6m(MAC)+OMT x1. XMC_3E , Sub A & B_Lo x2. ISM8 x1. | MW Swap | Existing SM link 23G_2+0_56M. Link reroute to new FE 1063B with 23G_2+0_112M due to LOS block. Site Impacted: W00103. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install XMC_3E , Sub A & B_Hi. 3.Install new RTN910A,7_ISM8-2+0.(RTN no provide by MSP team). 4.Create EPLA and service cross connect. 5.Migrate traffic to new route with new MW link. 6.Decom existing SM link. FE_1063B 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install XMC_3E , Sub A & B_Lo. 3.Reuse existing 1063B_RTN07. 4.Install 3_ISM8 into existing 1063B_RTN07. 5.Create EPLA and service cross connect. 6.Migrate traffic to new route with new MW link. 7.Decom existing SM link. | [7 empty] | Datasco | SQ202411270566-Datasco | GTSB | SQ202412310378-GTSB // SQ202504260131-GTSB | 2025-11-25 | 2025-11-24 | Completed | 2024-09-20 | 2024-11-20 | 2024-11-20 | 2024-11-20 | MOHAMAD//ZULFAKAAR BIN SHAMSUDIN/7019000075 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-20 | MOHAMAD//ZULFAKAAR BIN SHAMSUDIN/7019000075 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24122640 |  | 2024-12-27 | 2025-01-02 | Completed | 2024-12-26 | 2024-12-27 | 2025-01-01 | 2025-01-02 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-07 | 2025-01-31 | 2025-02-27 | 2025-02-27 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-01-07 | 2025-01-31 | 2025-02-27 | 2025-02-27 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-01-10 | 2025-01-10 | 2025-01-10 | 2025-01-10 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-01-07 | 2025-01-31 | 2025-01-10 | 2025-01-10 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-01-07 | 2025-01-31 | 2025-01-08 | 2025-01-08 | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2025-01-24 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
3733A_LOS | Masjid Bandar Bukit Puchong 2 | DU00004185478 | Central | Selangor | 2.980385 | 101.621569 |  |  |  |  | Cancel / Drop | Under TX NIC | ZTE | 00. Site Out/Drop | 12/9: Done by ZTE under TX NIC 3733A (Swap Activity) | TSS |  | Follow existing TX route, no reroute, Realignment, RSL stable within -30dbm to -35dbm with AM enable. History performance data from 25-Sept-3-Oct) , No alrm. | MW New Link / Reroute | Follow existing TX route, no reroute required. Realignment, RSL stable within -30dbm to -35dbm with AM enable. History performance data from 25-Sept-3-Oct) , No alrm. | [7 empty] | Allstar | SQ202411260589-Allstar |  |  | 2024-11-20 | 2024-11-19 | Completed | 2024-09-10 | 2024-09-16 | 2024-09-10 | 2024-09-26 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-07 | 2024-10-08 | 2024-10-07 | 2024-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-23 | 2024-10-24 | 2024-10-23 | 2024-10-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-19 | 2024-11-20 | 2024-11-19 | 2024-11-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1003D-2051B | Taman Langat Utama(REL) | DU00004364891 | Central | Selangor | 2.800845 | 101.664825 |  |  | W49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 3/12: D1: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_1003D 23G_DP_0.6m(MAC)+OMT x1. ISM8 x1. 23G_XMC_3E-2+0 , Sub A & B_Lo x2. FE_2051B 23G_DP_0.6m(MAC)+OMT x1. ISM8 x1. 23G_XMC_3E-2+0 , Sub A & B_Hi x2. | MW Swap | Existing link 18G_1+0_56M. Hardware ODU Low Power for 112M config. Swap existing link to 23G_2+0_112M. Site Impacted: 1003D. NE_1003D 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Reuse existing 1003D_RTN01. 3.Install new 3_ISM8-2+0 into existing 1003D_RTN01. 4.Install new 23G_XMC_3E-2+0 , Sub A & B_Lo. 5.Config 112M_256QAM. 6.Enable EPLA and service cross connect 7.Traffic migrate to new link 23G_2+0_112M. 8. Decom existing ODU and Ant. FE_2051B 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Reuse existing 2051B_RTN03. 3.Install new 3_ISM8-2+0 into existing 2051B_RTN03. 4.Install new 23G_XMC_3E-2+0 , Sub A & B_Hi. 5.Config 112M_256QAM. 6.Enable EPLA and service cross connect. 7.Traffic migrate to new link 23G_2+0_112M. 8.Decom existing ODU and Ant. | [7 empty] | GTSB | SQ202502120383-GTSB | GTSB | SQ202411260103-GTSB // SQ202504260131-GTSB | 2025-10-08 | 2025-10-07 | Completed | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2024-12-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2024-12-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241105CB |  | 2024-11-06 | 2024-11-25 | Completed | 2024-11-05 | 2024-11-06 | 2024-11-05 | 2024-11-25 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-02 | 2024-12-30 | 2024-12-02 | 2024-12-29 | NOR HELMI BIN ISMAIL6799000200 | GTSB TI | 2024-12-02 | 2024-12-30 | 2024-12-02 | 2024-12-29 | NOR HELMI BIN ISMAIL6799000200 | GTSB TI | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2024-12-04 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-12-02 | 2024-12-30 | 2024-12-02 | 2024-12-05 | NOR HELMI BIN ISMAIL6799000200 | 2024-12-02 | 2024-12-30 | 2024-12-02 | 2024-12-03 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
4032K-4496A | A040C_A01124OD_TMN_BERTUAH_CHEMOR | DU00004364892 | Northern | Perak | 4.662830 | 101.103850 | [7 empty] | 00. Integrated/RFS Done | 28/11: Cutover done. Post-CO T/S ongoing | AA | PAC | NA | MW Remote Upgrade | MW Remote Software upgrade from 18G_1+0_56M to 18G_1+0_112M_256QAM from 4032K-4496A. NE_4032K config to 112M with Modulation 256QAM , TX Power at 19dbm. FE_4496A Config to 112M with Modulation 256QAM , TX Power at 19 dbm. | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
4672B-4959A | Padang Sira | DU00004364893 | Northern | Kedah | 6.347048 | 100.346775 |  |  | W49-52 | DEC 24 | Integrated/RFS Done |  |  | 00. Integrated/RFS Done | 14/05: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M_CA. NE_4672B 15G_DP_1.2m(MDD) x1. ISM8 x2 XMC_5D , Sub A x1. FE_4959A 15G_DP_1.2m(MDD) x1. ISM8 x2. XMC_5D , Sub A x1. | MW Swap | Existing link 15G_2+0_28M Swap existing link to 15G_4+0_28M_CA. Site Impacted: 4672B,Pi1M Tunjang. NE_4672B 1.Install new 15G_DP_1.2m(MDD). 2.Reuse existing 4672B_RTN02. 3.Install 3_ISM8-2+0 and 4_ISM8-2+0 into existing 4672B_RTN02. 4.Install new XMC_5D-4+0 with CA configuration , Sub_A_Lo. 5.Enable EPLA , service cross connect and CA. 6.Migrate traffic to new link 15G_4+0_28M_CA. 7.Decom existing XMC_3 ODU and Ant. FE_4959A 1.Install new 15G_DP_1.2m(MDD). 2.Reuse existing 4959A_RTN05. 3.Install 3_ISM8-2+0 and 4_ISM8-2+0 into existing 4959A_RTN05. 4.Install new XMC_5D-4+0 with CA configuration , Sub_A_Hi. 5.Enable EPLA , service cross connect and CA. 6.Remain ETH cable interconnect to 4959A_RTN01. 7.Traffic migrate to new link 15G_4+0_28M_CA. 8.Decom existing XMC_3 ODU , Ant and 3_ISV3. | [7 empty] | GTSB | SQ202504280474-GTSB | GTSB | SQ202505070638-GTSB // SQ202505070639-GTSB // SQ202509110359-GTSB | 2026-01-21 | 2026-01-21 | Completed | 2025-06-19 | 2025-07-03 | 2025-06-19 | 2025-06-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250320AN |  | 2025-03-21 | 2025-05-08 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-05-08 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-06-02 | FAZAL ABBAS6799000222 | GTSB TI | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-06-13 | FAZAL ABBAS6799000222 | GTSB TI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-06-12 | FAZAL ABBAS6799000222 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-10 | 2025-10-13 | 2025-10-13 | 2025-10-13 |  |  |  | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | CHEONG/SENG/WAH/7018000306
3404B_HU_1 | Syabas Bangi Lama | DU00005975712 | Central | Selangor | 2.896875 | 101.792034 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 2x ODU 18G XMC3E SUB B HI 2X ODU 18G XMC3E SUB B LO | MW Parallel Link | [MW PARALLEL LINK 3404B-2400A WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_128QAM_1352MBPS_XMC3E_SUB_B_3.56KM IMPACTED: 3404B, 2997C NEW LINK CARRY TRAFFIC BBU 3404B AND 2997C] | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM 5. PATCH IDU 3404B RTN01 TO NEW IDU TO BRING TRAFFIC 2997C 6. PATCH BBU 3404B TO NEW LINK IDU | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG | XMC3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202508200493-GCI | GCI | SQ202508200482-GCI // SQ202508200487-GCI | 2025-11-08 | 2025-11-07 | Completed | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-09-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-30 | 2025-10-01 | 2025-09-30 | 2025-09-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082545 |  | 2025-08-26 | 2025-08-28 | Completed | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-08-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-18 | 2025-09-25 | 2025-09-18 | 2025-09-18 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-09-18 | 2025-09-25 | 2025-09-18 | 2025-09-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-20 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-09-18 | 2025-09-25 | 2025-09-18 | 2025-09-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2024-11-12: 2025-09-18; 2024-11-12: 2025-09-25; 2024-11-12: 2025-09-18; 2024-11-13: 2025-09-19 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509041074-GCI | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
N00188_HU | FELDA JELAI | DU00005975713 | Southern | Sembilan | 2.647250 | 102.486700 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 2X 15G 1.2M DP ANTENNA 1x ODU 15G XMC3 SUB A HI 1X ODU 15G XMC3 SUB A LO 1x ODU 15G XMC3 SUB B HI 1X ODU 15G XMC3 SUB B LO | MW Parallel Link | MW PARALLEL LINK UPGRADE N00188-N00117 WITH HUAWEI_15G_2+0_1.2M/1.2M_DP_28MHZ_512QAM_450MBPS_XMC3_SUB_A & B_6.9KM IMPACTED: N00188 EPLA NEW LINK 2+0 WITH EXISTING LINK 4+0 | 1. INSTALL NEW 1PCS ISM8 AT SLOT 4 EXISTING IDU 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. EPLA NEW LINK 2+0 WITH EXISTING LINK 4+0 | 1. INSTALL NEW 1PCS ISM8 AT SLOT 4 EXISTING IDU 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. EPLA NEW LINK 2+0 WITH EXISTING LINK 4+0 6. PATCH TO NEW CP PORT AND DO PORTLAG 2G | XMC3 | MAC | 15G | 1.2 | 1.2 | GTSB | SQ202511190869-GTSB | GTSB | SQ202511190863-GTSB // SQ202511190866-GTSB // SQ202602040252-GTSB // SQ202602040263-GTSB | 2026-01-16 | 2026-01-06 | Completed | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | KANNAN A/L RAMACHANDRAN6799000115 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-02 | 2026-01-16 | 2026-01-02 | 2026-01-02 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-05 | 2026-01-06 | 2026-01-05 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092696 |  | 2025-09-27 | 2025-09-30 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-06 | 2025-10-31 | 2025-10-06 | 2025-12-13 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-10-06 | 2025-10-31 | 2025-10-06 | 2026-01-26 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-09 | 2025-10-06 | 2025-10-31 | 2025-10-06 | 2026-01-24 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-10-06 | 2025-10-31 | 2025-10-06 | 2026-01-23 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | NG HONG JIE7018000036 | Logistic Team | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202511250907-GCI | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
K00396_HU | KGCINA | DU00005975714 | Northern | Kedah | 6.061100 | 100.609900 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 4X ISM8 CARD 2X RTN910A 2X 13G 1.8M MDD ANTENNA 1x ODU 13G XMC5D SUB B HI 1X ODU 13G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL LINK K00396-K00325 WITH HUAWEI_13G_4+0_1.8M/1.8M_MDD_28MHZ_256QAM_800MBPS_XMC5D_SUB_B_XPIC WITH CA_12.03KM IMPACTED: K00899 THIS LINK ONLY CARRY K00899 (CURRENT LINK 889) | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M DP ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM XPIC WITH CA 5. PATCH IDU K00899 TO NEW LINK | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M DP ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM XPIC WITH CA | XMC5D | MDD | 13G | 1.8 | 1.8 | MTK | SQ202602160083-MTK | MTK | SQ202511110819-MTK // SQ202511110823-MTK |  |  | Ongoing | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092317 |  | 2025-09-24 | 2025-09-26 | Completed | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-26 | 2026-03-18 | 2026-02-27 | 2026-02-27 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2026-02-26 | 2026-03-18 | 2026-03-01 | 2026-03-01 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-04 | 2026-02-26 | 2026-03-18 | 2026-03-10 | 2026-03-10 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | 2024-11-12: 2026-02-26; 2024-11-12: 2026-03-18; 2024-11-12: 2026-02-27; 2024-11-13: 2026-02-27 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509041075-GCI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
4013B_HU | Kg Machang Bubuk | DU00005975715 | Northern | Penang | 5.341444 | 100.512500 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x 1 | MW IDU Patching | Site Impacted : 4282H FE_4013B/P00077 1.Existing 4013B_BBU has been patched to Cisco Fiber port Ge_0/0/3. 2.NLOS Radio , at 4013B ETH LAN patch to Cisco Fiber Port Ge_0/0/23. 3.Creare New In Band DCN. Note : 4013B pair site with P00077. |  | Site Impacted : 4282H 1.NLOS Radio , at 4013B ETH LAN patch to Cisco Fiber Port Ge_0/0/23. 2.Create New In Band DCN. | [5 empty] | NWAVE | SQ202508200590-N-Wave | NWAVE | SQ202508200586-N-Wave | 2026-01-20 | 2026-01-19 | Completed | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-03 | Khairul Azman Bin Din7160000001 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082046 |  | 2025-08-21 | 2025-08-26 | Completed | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-11-30 | 2025-10-31 | 2025-11-24 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-10-31 | 2025-11-30 | 2025-10-31 | 2025-12-03 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-03 | 2025-10-31 | 2025-11-30 | 2025-10-31 | 2025-12-03 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2024-11-12: 2025-10-31; 2024-11-12: 2025-11-30; 2024-11-12: 2025-10-31; 2024-11-13: 2025-10-31 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509041075-GCI | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | CHEONG/SENG/WAH/7018000306
1586C_HU | ILKKM Sg Buloh | DU00005975716 | Central | Selangor | 3.221333 | 101.585568 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing 23G_1+0_56M. Remote Software Upgrade to 23G_1+0_112M with 512QAM. | Link Existing 23G_1+0_56M. Remote Software Upgrade to 23G_1+0_112M with 512QAM. | Link Existing 23G_1+0_56M. Remote Software Upgrade to 23G_1+0_112M with 512QAM. | [5 empty] | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-25 | [15 empty] | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509041074-GCI | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | CHEONG/SENG/WAH/7018000306
3458C_HU | Botanic Business Gateway (REL) | DU00005975717 | Central | Selangor | 2.987010 | 101.454826 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M. NE_3458C. 23G_SP_0.6M(MAC)+OMT. RTN910A x1. XMC_3E , Sub A_Lo x1. FE_B00644. 23G_SP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A_Hi x1. | MW New Link / Reroute | Link existing 15G_2+0_28M Link reroute to new FE B00664 with 23G_1+0_112M due to LOS Block Issue. Site Impacted : 3458C NE_3458C. 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Intstall new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. FE_B00644 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Intsall new RTN910A , 7_ISM8-1+0. (RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Traffic migrate to new link and new FE routing 6.Decom existing MW link. | Link existing 15G_2+0_28M Link reroute to new FE B00664 with 23G_1+0_112M due to LOS Block Issue. Site Impacted : 3458C NE_3458C. 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Intstall new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. | Link existing 15G_2+0_28M Link reroute to new FE B00664 with 23G_1+0_112M due to LOS Block Issue. Site Impacted : 3458C FE_B00644 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Intsall new RTN910A , 7_ISM8-1+0. (RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and New In band DCN. 5.Traffic migrate to new link and new FE routing 6.Decom existing MW link except IDU | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202509100066-GTSB | GTSB | SQ202509100062-GTSB // SQ202509100064-GTSB | 2025-12-04 | 2025-12-03 | Completed | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-10-28 | 2025-10-29 | 2025-10-28 | 2025-10-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25091003 |  | 2025-09-11 | 2025-09-30 | Completed | 2025-09-10 | 2025-09-11 | 2025-09-22 | 2025-09-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-21 | 2025-10-15 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2025-09-22 | 2025-09-22 | 2025-09-21 | 2025-10-23 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-15 | 2025-09-22 | 2025-09-22 | 2025-09-21 | 2025-10-22 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | 2025-09-22 | 2025-09-22 | 2025-09-21 | 2025-10-15 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509041074-GCI | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | CHEONG/SENG/WAH/7018000306
7118K_HU | BAIDURIAYU | DU00005975718 | Sabah | Sabah | 5.103708 | 118.977400 | [7 empty] | 05. Doable |  | TSS+AA+TI+Dismantle |  | "15G_4+0_28M_256QAM_CA NE_7118K New 15G_1.2M(MDD) x1. Re-use existing RTN910AF. New ISM8 x1. New XMC_5, Sub B_Lo x1. FE_7278B/S00326 New 15G_1.2M(MDD) x1. Re-use existing RTN910AF. New ISM8 x1. New XMC_5, Sub B_Hi x1." | MW Swap | "Existing HW MW Link_7118K-7278B, 13G_2+0_28MHZ_512QAM_EPLA. MW Swap to new HW MW Link 7118K-7278B, 15G_4+0_28MHZ_512QAM_CA. Later, decom antenna and ODU of existing HW MW Link_7118K-7278B, 13G_2+0_28MHZ_512QAM_EPLA. Re-use RTN910AF at both sites(NE & FE). Site Impacted : 7118K. NE_7118K 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF. 3.Insert new ISM8 x1 into slot 03 of existing RTN910AF. 4.Install new XMC_5, Sub B_Lo x1. Configure it. 5.Re-use existing xC vlan dcn and vlan services. 6.Migrate traffic 70118K via new HW MW Link 7118K-7278B, 15G_4+0_28MHZ_512QAM_CA. 7.Later, decom antenna and ODU of existing HW MW Link_7118K-7278B, 13G_2+0_28MHZ_512QAM_EPLA. Re-use RTN910AF at both sites(NE & FE). FE_7278B/S00326 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF. 3.Insert new ISM8 x1 into slot 03 of existing RTN910AF. 4.Install new XMC_5, Sub B_Hi x1. Configure it. 5.Re-use existing xC vlan dcn and vlan services. 6.Migrate traffic 7118K via existing port at PTN/Cisco at S00326. 7.Later, decom antenna and ODU of existing HW MW Link_7118K-7278B, 13G_2+0_28MHZ_512QAM_EPLA. Re-use RTN910AF at both sites(NE & FE)." | "Existing HW MW Link_7118K-7278B, 13G_2+0_28MHZ_512QAM_EPLA. MW Swap to new HW MW Link 7118K-7278B, 15G_4+0_28MHZ_512QAM_CA. Later, decom antenna and ODU of existing HW MW Link_7118K-7278B, 13G_2+0_28MHZ_512QAM_EPLA. Re-use RTN910AF at both sites(NE & FE). Site Impacted : 7118K. NE_7118K 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF. 3.Insert new ISM8 x1 into slot 03 of existing RTN910AF. 4.Install new XMC_5, Sub B_Lo x1. Configure it. 5.Re-use existing xC vlan dcn and vlan services. 6.Migrate traffic 70118K via new HW MW Link 7118K-7278B, 15G_4+0_28MHZ_512QAM_CA. 7.Later, decom antenna and ODU of existing HW MW Link_7118K-7278B, 13G_2+0_28MHZ_512QAM_EPLA. Re-use RTN910AF at both sites(NE & FE)." | "Existing HW MW Link_7118K-7278B, 13G_2+0_28MHZ_512QAM_EPLA. MW Swap to new HW MW Link 7118K-7278B, 15G_4+0_28MHZ_512QAM_CA. Later, decom antenna and ODU of existing HW MW Link_7118K-7278B, 13G_2+0_28MHZ_512QAM_EPLA. Re-use RTN910AF at both sites(NE & FE). Site Impacted : 7118K. FE_7278B/S00326 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF. 3.Insert new ISM8 x1 into slot 03 of existing RTN910AF. 4.Install new XMC_5, Sub B_Hi x1. Configure it. 5.Re-use existing xC vlan dcn and vlan services. 6.Migrate traffic 7118K via existing port at PTN/Cisco at S00326. 7.Later, decom antenna and ODU of existing HW MW Link_7118K-7278B, 13G_2+0_28MHZ_512QAM_EPLA. Re-use RTN910AF at both sites(NE & FE)." | XMC_5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | NR services |  | NR services | SQ202511110813-NR Services // SQ202511110815-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25110205 |  | 2025-11-03 | 2025-11-04 | Completed | 2025-11-02 | 2025-11-03 | 2025-11-02 | 2025-11-04 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202509041080-GTSB
K00626_HU | MN_KGPADANG | DU00005975719 | Northern | Kedah | 6.079456 | 100.722660 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB A HI 1X ODU 18G XMC5D SUB A LO | MW Swap | MW SWAP LINK K00626-K00625 WITH HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_256QAM_1556MBPS_XMC5D_SUB_A_2.89KM IMPACTED: K00626 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | XMC5D | MDD | 18G | 0.6 | 0.6 | Magicell | SQ202509180710-Magicell | Magicell | SQ202509180686-Magicell // SQ202509180692-Magicell // SQ202511240514-Magicell // SQ202511260115-Magicell | 2025-12-04 | 2025-12-03 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092320 |  | 2025-09-24 | 2025-10-07 | Completed | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-10-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-10 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-28 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-13 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509041075-GCI | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | EZRIN TASNIM BIN ABDUL GANI6798000128
2408B_HU | Kg Londah(RM) | DU00005975720 | Southern | Sembilan | 2.631638 | 102.588795 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 2X RTN910A 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1X ODU 15G XMC5D SUB B LO | MW Swap | MW SWAP LINK 2408B-2384B WITH HUAWEI_15G_4+0_1.2M/1.2M_DP_28MHZ_512QAM_896MBPS_XMC5D_WITH CA_SUB_B_6.0KM IMPACTED: 6133Z DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 AT SLOT 3 AND 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. REPATCH IF CABLE LINK 6133Z-2408B SLOT 4 TO NEW IDU 6. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 AT SLOT 3 AND 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK | XMC5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202511190872-Magicell | Magicell | SQ202511190870-Magicell // SQ202511190871-Magicell // SQ202511260585-Magicell | 2025-12-04 | 2025-12-03 | Completed | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082532 |  | 2025-08-26 | 2025-08-27 | Completed | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-08-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-11-03 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-11-21 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-04 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-11-21 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-11-04 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | NG HONG JIE7018000036 | Logistic Team | [5 empty] | GCI | SQ202511250907-GCI | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | EZRIN TASNIM BIN ABDUL GANI6798000128
4188R_HU | RPA Gelung Pepuyu | DU00005975721 | Northern | Perak | 4.371111 | 100.826667 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 4X ISM8 CARD | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 4188R-4404A WITH HUAWEI_13G_4+0_1.2M/1.2M_MDD_112MHZ_512QAM_8896MBPS_XMC5D_WITH CA_SUB_B_5.8KM IMPACTED: 4188R | 1. INSTALL NEW 2PCS ISM8 AT EXISTING RTN910 SLOT 3 & 4 2. REUSE EXISTING ODU 13G XMC5D 28MHZ SUB B 3. REUSE EXISTING 13G 1.2M MDD ANTENNA 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA | 1. INSTALL NEW 2PCS ISM8 AT EXISTING RTN910 SLOT 3 & 4 2. REUSE EXISTING ODU 13G XMC5D 28MHZ SUB B 3. REUSE EXISTING 13G 1.2M MDD ANTENNA 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA | XMC5D | MDD | 13G | 1.2 | 1.2 | MTK | SQ202508250295-MTK | MTK | SQ202508250288-MTK // SQ202508250291-MTK | 2026-01-20 | 2026-01-19 | Completed | 2025-09-10 | 2025-09-30 | 2025-09-10 | 2025-09-22 | AMIRUL SYAHRINI BIN MOHD ZIN6000023342 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082188 |  | 2025-08-22 | 2025-08-28 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-10 | 2025-09-20 | 2025-09-10 | 2025-09-10 | MOHD//SUFRI BIN AZHAR/8225000013 | MTK TI | 2025-09-10 | 2025-09-30 | 2025-09-10 | 2025-09-19 | MOHD//SUFRI BIN AZHAR/8225000013 | MTK TI | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | AKMAL//BIN RAZALI/6794000078 |  | 2025-09-11 | 2025-09-10 | 2025-09-30 | 2025-09-10 | 2025-09-22 | MOHD//SUFRI BIN AZHAR/8225000013 | 2025-10-28: 2025-09-10; 2025-10-28: 2025-09-30; 2025-10-28: 2025-09-10; 2025-11-04: 2025-09-10 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509041075-GCI | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
S00981_HU | KAMPUNG ULU TIKU | DU00005975722 | Sabah | Sabah | 4.359400 | 117.918300 |  |  |  |  | DT February |  |  | 04. BOM / Material Issue |  | TSS+AA+TI |  | 18G_2+0_55M_512QAM_EPLA NE_S00981 New 18G_1.2M(MDD) x1. Re-use existing RTN910AF(NEID 88-28559). New ISM8 x1. New XMC_5D Pro, Sub A_Lo x1. FE_S00491 New 18G_1.2M(MDD) x1. Re-use existing RTN910AF(NEID 88-28564). New ISM8 x1. New XMC_5D Pro, Sub A_Hi x1. | MW Parallel Link | Existing HW MW Link S00981-S00491, 15G_2+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. Later, combine existing HW MW Link S00981-S00491, 15G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. Become 15G&18G_4+0_28MHZ&55MHZ_2048QAM&256QAM_EPLA. Site Impacted : S00981 & S01449. NE_S00981 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 88-28559) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1. Build new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. 4.Later, combine existing HW MW Link S00981-S00491, 15G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. Become 15G&18G_4+0_28MHZ&55MHZ_2048QAM&256QAM_EPLA. FE_S00491 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 88-28564) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. Build new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. 4.Later, combine existing HW MW Link S00981-S00491, 15G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. Become 15G&18G_4+0_28MHZ&55MHZ_2048QAM&256QAM_EPLA. | Existing HW MW Link S00981-S00491, 15G_2+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. Later, combine existing HW MW Link S00981-S00491, 15G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. Become 15G&18G_4+0_28MHZ&55MHZ_2048QAM&256QAM_EPLA. Site Impacted : S00981 & S01449. NE_S00981 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 88-28559) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1. Build new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. 4.Later, combine existing HW MW Link S00981-S00491, 15G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. Become 15G&18G_4+0_28MHZ&55MHZ_2048QAM&256QAM_EPLA. | Existing HW MW Link S00981-S00491, 15G_2+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. Later, combine existing HW MW Link S00981-S00491, 15G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. Become 15G&18G_4+0_28MHZ&55MHZ_2048QAM&256QAM_EPLA. Site Impacted : S00981 & S01449. FE_S00491 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 88-28564) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. Build new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. 4.Later, combine existing HW MW Link S00981-S00491, 15G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link S00981-S00491, 18G_2+0_55MHZ_256QAM_EPLA. Become 15G&18G_4+0_28MHZ&55MHZ_2048QAM&256QAM_EPLA. | XMC-5D Pro | MDD | 18G | 18G_1.2M(MDD) x1 | 18G_1.2M(MDD) x1 | Seri Pancar | SQ202602040268-Seri Pancar |  |  | 2026-03-20 | 2026-03-17 | Completed | 2026-02-04 | 2026-02-28 | 2026-02-04 | 2026-02-04 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-20 | 2026-03-13 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202509041080-GTSB
1865B_HU | ERL Wetland(TMTouch) | DU00005975723 | Central | Selangor | 2.972138 | 101.673423 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_1865B 23G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. ETH LAN Cable x1. FE_2984A. 23G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Hi x2. | MW New Link / Reroute | Link existing 18G_2+0_112M ( Exclusive Zone Cyberjaya at original FE_2057A) Link reroute to new FE 2984A with configuration 23G_2+0_112M. Site Impacted : 1865B , 2984A. New TX Route : 1865B - 2984A - 1313B. Install upstream link is priority 2984A-1313B. (Refer DU ID 2984A_HU). NE_1865B 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 1865B_RTN01 ( ID : 34216). 3.Install new 3_ISM8-2+0 into existing 1865B_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Existing GE1 ,to patching BBU_1865B and remove existing IDU interconnect LAN cable. 6.Create service cross connect and EPLA for new link. 7.Traffic migrate to new link and new FE routing. 8.Decom existing ODU and ANT. FE_2984A. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 2984A_RTN02. ( ID : 34215). 3.Install new 3_ISM8-2+0 into existing 2948A_RTN02. 4.Install new XMC_3E , Sub A & B_Hi. 5.Existing GE1 , remain connection for BBU_2984A. 6.Create service cross connect and EPLA for new link. 7.Traffic migrate to new link and new FE routing. 8.Decom existing ODU and ANT. | Link existing 18G_2+0_112M ( Exclusive Zone Cyberjaya at FE_2057A) Link reroute to new FE 2984A with configuration 23G_2+0_112M. Site Impacted : 1865B , 2984A. New TX Route : 1865B - 2984A - 1313B. Install upstream link is priority 2984A-1313B. (Refer DU ID 2984A_HU). NE_1865B 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 1865B_RTN01 ( ID : 34216). 3.Install new 3_ISM8-2+0 into existing 1865B_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Existing GE1 ,to patching BBU_1865B and remove existing IDU interconnect LAN cable. 6.Create service cross connect and EPLA for new link. 7.Traffic migrate to new link and new FE routing. 8.Decom existing ODU and ANT. | Link existing 18G_2+0_112M ( Exclusive Zone Cyberjaya at 2057A) Link reroute to new FE 2984A with configuration 23G_2+0_112M. Site Impacted : 1865B , 2984A. New TX Route : 1865B - 2984A - 1313B. Install upstream link is priority 2984A-1313B. (Refer DU ID 2984A_HU). FE_2984A. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 2984A_RTN02. ( ID : 34215). 3.Install new 3_ISM8-2+0 into existing 2948A_RTN02. 4.Install new XMC_3E , Sub A & B_Hi. 5.Existing GE1 , remain connection for BBU_2984A. 6.Create service cross connect and EPLA for new link. 7.Traffic migrate to new link and new FE routing. 8.Decom existing ODU and ANT. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202509030923-GTSB | GTSB | SQ202509030913-GTSB // SQ202509030917-GTSB | 2026-01-14 | 2026-01-13 | Completed | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | KANNAN A/L RAMACHANDRAN6799000115 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-24 | 2026-01-07 | 2025-12-24 | 2025-12-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092721 |  | 2025-09-28 | 2025-09-30 | Completed | 2025-09-27 | 2025-09-28 | 2025-09-27 | 2025-09-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-12-13 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2026-01-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-13 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2026-01-26 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2026-01-26 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509041074-GCI | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | CHEONG/SENG/WAH/7018000306
7076D_HU | Masjid Tambunan REL | DU00005975724 | Sabah | Sabah | 5.669937 | 116.361326 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | "23G_2+0_56M_512QAM_EPLA NE_7076D New 23G_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01). New XMC_3, Sub A&B_Lo x2. FE_7341A New 23G_1.2M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01). New XMC_3, Sub A&B_Hi x2." | MW Swap | "Existing HW MW Link_7076D-7341A, 23G_1+0_56MHZ_512QAM. MW Swap to HW MW Link 7076D-7341A, 23G_2+0_56MHZ_512QAM_EPLA. Later, decom existing antenna 23G 0.3/0.3 and ODU 23G for existing HW MW Link_7076D-7341A, 23G_1+0_56MHZ_512QAM. Existing RTN910AF will be re-used. Site Impacted : 7076D. NE_7076D 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01). 3.Install New XMC_3, Sub A&B_Lo x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7076D via new HW MW Link 7076D-7341A, 23G_2+0_56MHZ_512QAM_EPLA. 6.Later, decom existing existing antenna 23G 0.3/0.3 and ODU 23G for existing HW MW Link_7076D-7341A, 23G_1+0_56MHZ_512QAM. Existing RTN910AF will be re-used. FE_7341A 1.Install new 23G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN03). 3.Install New XMC_3, Sub A&B_Hi x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7076D via existing port at IBeam/CP 7000A. 6.Later, decom existing existing antenna 23G 0.3/0.3 and ODU 23G for existing HW MW Link_7076D-7341A, 23G_1+0_56MHZ_512QAM. Existing RTN910AF will be re-used." | "Existing HW MW Link_7076D-7341A, 23G_1+0_56MHZ_512QAM. MW Swap to HW MW Link 7076D-7341A, 23G_2+0_56MHZ_512QAM_EPLA. Later, decom existing antenna 23G 0.3/0.3 and ODU 23G for existing HW MW Link_7076D-7341A, 23G_1+0_56MHZ_512QAM. Existing RTN910AF will be re-used. Site Impacted : 7076D. NE_7076D 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01). 3.Install New XMC_3, Sub A&B_Lo x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7076D via new HW MW Link 7076D-7341A, 23G_2+0_56MHZ_512QAM_EPLA. 6.Later, decom existing existing antenna 23G 0.3/0.3 and ODU 23G for existing HW MW Link_7076D-7341A, 23G_1+0_56MHZ_512QAM. Existing RTN910AF will be re-used." | "Existing HW MW Link_7076D-7341A, 23G_1+0_56MHZ_512QAM. MW Swap to HW MW Link 7076D-7341A, 23G_2+0_56MHZ_512QAM_EPLA. Later, decom existing existing antenna 23G 0.3/0.3 and ODU 23G for existing HW MW Link_7076D-7341A, 23G_1+0_56MHZ_512QAM. Existing RTN910AF will be re-used. Site Impacted : 7076D. FE_7341A 1.Install new 23G_1.2M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN03). 3.Install New XMC_3, Sub A&B_Hi x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7076D via existing port at IBeam/CP 7000A. 6.Later, decom existing existing antenna 23G 0.3/0.3 and ODU 23G for existing HW MW Link_7076D-7341A, 23G_1+0_56MHZ_512QAM. Existing RTN910AF will be re-used." | XMC_3 | MAC | 23G | 23G_0.6M(MAC)+OMT x1. | 23G_1.2M(MAC)+OMT x1. | NR services | SQ202512160988-NR Services | NR services | SQ202511110813-NR Services // SQ202511110815-NR Services // SQ202512190088-NR Services // SQ202601060542-NR Services | 2026-03-04 | 2026-03-02 | Completed | 2025-12-17 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-24 | 2026-03-03 | 2026-02-24 | 2026-02-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-24 | 2026-03-03 | 2026-02-24 | 2026-02-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-25 | 2026-03-04 | 2026-02-25 | 2026-03-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110313 |  | 2025-11-04 | 2025-11-04 | Completed | 2025-11-03 | 2025-11-04 | 2025-11-03 | 2025-11-04 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-25 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-25 | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-12-01 | RALPH O'BRYAN HILARY7167000030 | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | tseping//wang/6819000006 | Logistic Team | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-16 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202509041080-GTSB
1053L_HU | Kpg Delek 2 | DU00005975725 | Central | Selangor | 3.038075 | 101.406220 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_28M. Remote support upgrade not support. NE_1053L XMC_3E , Sub A_Hi Note : Support for 112Mhz. FE_1610B XMC_3E , Sub A_Lo Note : Support for 112Mhz. | MW Hardware Upgrade | Link existing 18G_1+0_28M. Remote support upgrade not support. Site Impacted : 1053L. NE_1053L 1.Swap existing ODU to new XMC_3E with support 112Mhz. 2.Reuse existing 18G antenna. 3.Reuse existing RTN910A , 7_ISM8-1+0. 4.If RSL not achieve LB , Re-alignment is necessary. 5.Decom existing ODU. FE_1610B 1.Swap existing ODU to new XMC_3E with support 112Mhz. 2.Reuse existing 18G antenna. 3.Reuse existing RTN910A , 7_ISM8-1+0. 4.If RSL not achieve LB , Re-alignment is necessary. 5.Decom existing ODU. | Link existing 18G_1+0_28M. Remote support upgrade not support. Site Impacted : 1053L. NE_1053L 1.Swap existing ODU to new XMC_3E with support 112Mhz. 2.Reuse existing 18G antenna. 3.Reuse existing RTN910A , 7_ISM8-1+0. 4.If RSL not achieve LB , Re-alignment is necessary. 5.Decom existing ODU | Link existing 18G_1+0_28M. Remote support upgrade not support. Site Impacted : 1053L. FE_1610B 1.Swap existing ODU to new XMC_3E with support 112Mhz. 2.Reuse existing 18G antenna. 3.Reuse existing RTN910A , 7_ISM8-1+0. 4.If RSL not achieve LB , Re-alignment is necessary. 5.Decom existing ODU. | [5 empty] | Magicell | SQ202508250724-Magicell | Magicell | SQ202508250716-Magicell // SQ202508250720-Magicell | 2025-12-04 | 2025-12-03 | Completed | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082533 |  | 2025-08-26 | 2025-08-27 | Completed | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-08-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-11-10 | Azam/Azri/Roslan/7018000276 | Magicell TI | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-11-10 | Azam/Azri/Roslan/7018000276 | Magicell TI | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-13 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-11-10 | Azam/Azri/Roslan/7018000276 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-11-05 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | NG HONG JIE7018000036 | Logistic Team | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509041074-GCI | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-23 | CHEONG/SENG/WAH/7018000306
Q02235_HU | SK SUNGAI BURI BAKONG 1 | DU00005975726 | Sarawak | Sarawak | 4.205450 | 114.076930 | [7 empty] | 03. TSS Only | 19022026 : TSS only due to wrong link ID. To proceed survey under new DU - Q02235_HU_1 | TSS |  | 18G_1+0_56M_1024QAM NE_Q02235 New 18G_SP_1.2M(MAC) x1. New RTN910AF(RTN01). New XMC_3E, Sub B_Lo x1. New CAT6 cable x1. FE_Q00344 New 18G_SP_1.2M(MAC) x1. New RTN910AF(RTN01). New XMC_3E, Sub B_Hi x1. New CAT6 cable x1. | MW Swap | 27 Jan 2026: TSS done based on wrong link ID provided by GOP. Need to resurvey after correct link ID provided. To resurvey and install using DU Q02235_HU_1 DU Q02235_HU for TSS only ****IMPORTANT NOTE: 1. OPS TEAM NEED TO BE AWARE, SEEM QUITE CONFUSE IN WHICH TRAFFICS Q02235, Q02234, Q02236, Q02310 WILL BACKHAUL TO Q01732(PTN/CISCO-30470) PORT Gi0/0/1 AND NOT TO Q00344(PTN/CISCO). 2.ENSURE SPACING TO MOUNT ANTENNA 1.2M/1.2M AVAILABLE.**** Existing SM MW link_ID SW04226 13G_1+0_28M_2048QAM. Swap existing link to new HW MW Link 18G_1+0_56M_1024QAM. Later, decom existing SM MW link_ID SW04226 13G_1+0_28M_2048QAM. Site Impacted : Q02235, Q02234, Q02236, Q02310. NE_Q02235 1.Install new 18G_SP_1.2M(MAC) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub B_Lo x1. Build new HW MW Link 18G_1+0_56M_1024QAM. 4.Re-use existing Vlan DCN and Vlan services. 5.Migrate traffic via new HW MW Link 18G_1+0_56M_1024QAM. 6.Later, decom existing SM MW link_ID SW04226 13G_1+0_28M_2048QAM. FE_Q00344 1.Install new 18G_SP_1.2M(MAC) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub B_Hi x1. Build new HW MW Link 18G_1+0_56M_1024QAM. 4.Re-use existing Vlan DCN and Vlan services. 5.Later, decom existing SM MW link_ID SW04226 13G_1+0_28M_2048QAM. | ****IMPORTANT NOTE: 1. OPS TEAM NEED TO BE AWARE, SEEM QUITE CONFUSE IN WHICH TRAFFICS Q02235, Q02234, Q02236, Q02310 WILL BACKHAUL TO Q01732(PTN/CISCO-30470) PORT Gi0/0/1 AND NOT TO Q00344(PTN/CISCO). 2.ENSURE SPACING TO MOUNT ANTENNA 1.2M/1.2M AVAILABLE.**** Existing SM MW link_ID SW04226 13G_1+0_28M_2048QAM. Swap existing link to new HW MW Link 18G_1+0_56M_1024QAM. Later, decom existing SM MW link_ID SW04226 13G_1+0_28M_2048QAM. Site Impacted : Q02235, Q02234, Q02236, Q02310. NE_Q02235 1.Install new 18G_SP_1.2M(MAC) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub B_Lo x1. Build new HW MW Link 18G_1+0_56M_1024QAM. 4.Re-use existing Vlan DCN and Vlan services. 5.Migrate traffic via new HW MW Link 18G_1+0_56M_1024QAM. 6.Later, decom existing SM MW link_ID SW04226 13G_1+0_28M_2048QAM. | ****IMPORTANT NOTE: 1. OPS TEAM NEED TO BE AWARE, SEEM QUITE CONFUSE IN WHICH TRAFFICS Q02235, Q02234, Q02236, Q02310 WILL BACKHAUL TO Q01732(PTN/CISCO-30470) PORT Gi0/0/1 AND NOT TO Q00344(PTN/CISCO). 2.ENSURE SPACING TO MOUNT ANTENNA 1.2M/1.2M AVAILABLE.**** Existing SM MW link_ID SW04226 13G_1+0_28M_2048QAM. Swap existing link to new HW MW Link 18G_1+0_56M_1024QAM. Later, decom existing SM MW link_ID SW04226 13G_1+0_28M_2048QAM. Site Impacted : Q02235, Q02234, Q02236, Q02310. FE_Q00344 1.Install new 18G_SP_1.2M(MAC) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub B_Hi x1. Build new HW MW Link 18G_1+0_56M_1024QAM. 4.Re-use existing Vlan DCN and Vlan services. 5.Later, decom existing SM MW link_ID SW04226 13G_1+0_28M_2048QAM. | XMC_3E | MAC | 18G | 18G_SP_1.2M(MAC) x1. | 18G_SP_1.2M(MAC) x1. | Allstar | SQ202512120606-Allstar | Allstar | No PR required-Work at TSS only | 2025-12-25 | 2025-12-22 | Completed | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-19 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Full site DR | 2025-11-13 | 2025-11-21 | Completed | 2025-11-12 | 2025-11-13 | 2025-11-12 | 2025-11-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-01 | 2025-12-07 | 2025-12-01 | 2025-12-01 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-12-01 | 2025-12-07 |  |  | TONI//ANAK KUMBONG/6798000163 | Allstar TI | [7 empty] | 2025-12-01 | 2025-12-07 |  |  | TONI//ANAK KUMBONG/6798000163 | 2025-10-09: 2025-12-01; 2025-10-09: 2025-12-07; 2025-10-09: 2025-12-01; 2025-11-05: 2025-12-01 | [7 empty] | GTSB | SQ202509041083-GTSB
7494B_HU_1 | Kg Koya | DU00005975727 | Sabah | Sabah | 5.275885 | 118.105145 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | "15G_3+0_28M_256QAM_EPLA NE_7494B New 15G_1.2M(MDD) x1. New RTN910A(RTN05). New ISM8 x1. New XMC_5D, Sub A_Lo x2. New IF cables with suitable length. New Flexi WG with suitable length x2. New CAT6 cable x1. FE_7581A New 15G_1.2M(MDD) x1. New RTN910A(RTN03). New ISM8 x1. New XMC_5D, Sub A_Hi x2. New IF cables with suitable length. New Flexi WG with suitable length x2. New CAT6 cable x1." | MW Parallel Link | "Existing Huawei MW Link 13G_3+0_28MHZ_512QAM_630_EPLA. Build new parallel HW MW Link 7494B(RTN05)-7581A(RTN03) 15G_3+0_28M_256QAM_600_EPLA. Do not decom existing Huawei MW Link 13G_3+0_28MHZ_512QAM_630_EPLA as it will use for backhauling child site traffic 7487B. Site Impacted : 7494B. NE_7494B 1.Install 15G_1.2M(MDD) x1. 2.Install new RTN910A(RTN05) x1 and insert ISM8 x1 into slot 03. 3.Install new XMC_5D, Sub A_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN05). 5.Patching BBU 7494B to port 8-EM6-1 of new RTN910AF(RTN05). 6.Request new Vlan services and new Vlan DCN from ZTE IPRAN team. 7.Migrate traffic 7494B via new parallel HW MW Link 7494B(RTN05)-7581A(RTN03) 15G_3+0_28M_256QAM_600_EPLA. 8.Do not decom existing Huawei MW Link 13G_3+0_28MHZ_512QAM_630_EPLA as it will use for backhauling child site traffic 7487B. FE_7581A 1.Install 15G_1.2M(MDD) x1. 2.Install new RTN910A(RTN03) x1 and insert ISM8 x1 into slot 03. 3.Install new XMC_5D, Sub A_Hi x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN03). 5.Request new IBeam port from ZTE IPRAN team. 6.Patching port 8-EM6-1 of new RTN910AF(RTN03) to new IBeam port. 7.Request new Vlan services and new Vlan DCN from ZTE IPRAN team. 8.Migrate traffic for 7494B to new IBeam port. 9.Do not decom existing Huawei MW Link 13G_3+0_28MHZ_512QAM_630_EPLA as it will use for backhauling child site traffic 7487B." | "Existing Huawei MW Link 13G_3+0_28MHZ_512QAM_630_EPLA. Build new parallel HW MW Link 7494B(RTN05)-7581A(RTN03) 15G_3+0_28M_256QAM_600_EPLA. Do not decom existing Huawei MW Link 13G_3+0_28MHZ_512QAM_630_EPLA as it will use for backhauling child site traffic 7487B. Site Impacted : 7494B. NE_7494B 1.Install 15G_1.2M(MDD) x1. 2.Install new RTN910A(RTN05) x1 and insert ISM8 x1 into slot 03. 3.Install new XMC_5D, Sub A_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN05). 5.Patching BBU 7494B to port 8-EM6-1 of new RTN910AF(RTN05). 6.Request new Vlan services and new Vlan DCN from ZTE IPRAN team. 7.Migrate traffic 7494B via new parallel HW MW Link 7494B(RTN05)-7581A(RTN03) 15G_3+0_28M_256QAM_600_EPLA. 8.Do not decom existing Huawei MW Link 13G_3+0_28MHZ_512QAM_630_EPLA as it will use for backhauling child site traffic 7487B." | "Existing Huawei MW Link 13G_3+0_28MHZ_512QAM_630_EPLA. Build new parallel HW MW Link 7494B(RTN05)-7581A(RTN03) 15G_3+0_28M_256QAM_600_EPLA. Do not decom existing Huawei MW Link 13G_3+0_28MHZ_512QAM_630_EPLA as it will use for backhauling child site traffic 7487B. Site Impacted : 7494B. FE_7581A 1.Install 15G_1.2M(MDD) x1. 2.Install new RTN910A(RTN03) x1 and insert ISM8 x1 into slot 03. 3.Install new XMC_5D, Sub A_Hi x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN03). 5.Request new IBeam port from ZTE IPRAN team. 6.Patching port 8-EM6-1 of new RTN910AF(RTN03) to new IBeam port. 7.Request new Vlan services and new Vlan DCN from ZTE IPRAN team. 8.Migrate traffic for 7494B to new IBeam port. 9.Do not decom existing Huawei MW Link 13G_3+0_28MHZ_512QAM_630_EPLA as it will use for backhauling child site traffic 7487B." | XMC_5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | NR services | SQ202512160988-NR Services | NR services | SQ202511110813-NR Services // SQ202511110815-NR Services | 2026-03-02 | 2026-02-23 | Completed | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110206 |  | 2025-11-03 | 2025-11-04 | Completed | 2025-11-02 | 2025-11-03 | 2025-11-02 | 2025-11-04 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-10 | 2026-01-10 | 2025-12-10 | 2025-12-17 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-12-10 | 2026-01-10 | 2025-12-10 | 2025-12-18 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-30 | 2025-12-10 | 2026-01-10 | 2025-12-10 | 2025-12-30 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-10-09: 2025-12-10; 2025-10-09: 2026-01-10; 2025-10-09: 2025-12-10; 2025-11-05: 2025-12-11 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202509041080-GTSB
7958A_HU | Taman Marudu | DU00005975728 | Sabah | Sabah | 6.496800 | 116.781600 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M_256QAM_EPLA NE_7958A New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 9-43350). New XMC_5D, Sub B_Lo x1. FE_7957A New 18G_0.6M(MDD) x1. New RTN910AF(RTN03). New XMC_5D, Sub B_Hi x1. New CAT6 cable x1. | MW Swap | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Existing HW MW Link_7958A-7957A, 18G_1+0_110MHZ_512QAM. MW Swap to HW MW Link 7958A-7957A, 18G_2+0_110MHZ_256QAM_EPLA. Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7958A-7957A, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE(IDU shared with other existing MW Link) will be re-used. Site Impacted : 7958A & 7323C. NE_7958A 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43350). Use existing ISM8 slot 07(Port 1 & 2). 3.Install new XMC_5D, Sub B_Lo x1. Configure it. Build new HW MW Link 7958A-7957A, 18G_2+0_110MHZ_256QAM_EPLA. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffics 7958A & 7323C via new HW MW Link 7958A-7957A, 18G_2+0_110MHZ_256QAM_EPLA. 6.Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7958A-7957A, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE(shared with other MW Link) will be re-used. FE_7957A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN03). 3.Install new XMC_5D, Sub B_Lo x1. Configure it. Build new HW MW Link 7958A-7957A, 18G_2+0_110MHZ_256QAM_EPLA. 4.Enable port 8-EM6-1 of new RTN910AF(RTN03). 5.Enable port 4-EG4-4 of existing RTN910AF(RTN01, NEID 9-20577). 6.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN03) & port 4-EG4-4 of existing RTN910AF(RTN01, NEID 9-20577). 7.Re-use existing xD vlan dcn and vlan services. 8.Migrate traffic 7958A & 7323C via existing port at IBeam/CP 7000A. 9.Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7958A-7957A, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE(shared with other MW Link) will be re-used. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Existing HW MW Link_7958A-7957A, 18G_1+0_110MHZ_512QAM. MW Swap to HW MW Link 7958A-7957A, 18G_2+0_110MHZ_256QAM_EPLA. Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7958A-7957A, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE(IDU shared with other existing MW Link) will be re-used. Site Impacted : 7958A & 7323C. NE_7958A 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43350). Use existing ISM8 slot 07(Port 1 & 2). 3.Install new XMC_5D, Sub B_Lo x1. Configure it. Build new HW MW Link 7958A-7957A, 18G_2+0_110MHZ_256QAM_EPLA. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffics 7958A & 7323C via new HW MW Link 7958A-7957A, 18G_2+0_110MHZ_256QAM_EPLA. 6.Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7958A-7957A, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE(shared with other MW Link) will be re-used. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Existing HW MW Link_7958A-7957A, 18G_1+0_110MHZ_512QAM. MW Swap to HW MW Link 7958A-7957A, 18G_2+0_110MHZ_256QAM_EPLA. Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7958A-7957A, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE(IDU shared with other existing MW Link) will be re-used. Site Impacted : 7958A & 7323C. FE_7957A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN03). 3.Install new XMC_5D, Sub B_Lo x1. Configure it. Build new HW MW Link 7958A-7957A, 18G_2+0_110MHZ_256QAM_EPLA. 4.Enable port 8-EM6-1 of new RTN910AF(RTN03). 5.Enable port 4-EG4-4 of existing RTN910AF(RTN01, NEID 9-20577). 6.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN03) & port 4-EG4-4 of existing RTN910AF(RTN01, NEID 9-20577). 7.Re-use existing xD vlan dcn and vlan services. 8.Migrate traffic 7958A & 7323C via existing port at IBeam/CP 7000A. 9.Later, decom existing antenna 18G and ODU 18G ONLY for existing HW MW Link_7958A-7957A, 18G_1+0_110MHZ_512QAM. Anyway, existing RTN910AF at NE & FE(shared with other MW Link) will be re-used. | XMC_5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_0.6M(MDD) x1. | NR services | SQ202602160101-NR Services | NR services | SQ202602090118-NR Services // SQ202602090125-NR Services | 2026-04-09 | 2026-04-06 | Completed | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-30 | 2026-04-06 | 2026-03-30 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26020321 |  | 2026-02-04 | 2026-02-07 | Completed | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-07 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-06 | 2026-03-06 | 2026-02-06 | 2026-02-07 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-06 | 2026-03-06 | 2026-02-06 | 2026-02-10 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-02-07 | 2026-02-06 | 2026-03-06 | 2026-02-06 | 2026-02-12 | RALPH O'BRYAN HILARY7167000030 | 2026-02-07 | 2026-02-09 | 2026-02-07 | 2026-02-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202509041080-GTSB
3058C8_EVT | PBTS KG MONSOPIAD | DU00006220534 | Sabah | Sabah | 5.890723 | 116.075516 | [13 empty] | Planning and integration support only for event site 3058C8 PBTS KG MONSOPIAD Tx route: 3058C8/3058C8-7117A-LL-7000A 1) Share port with 7117A at 7000A 2) New NE ID FE IDU 7117A RTN04 3) New NE ID NE IDU 3058C8 RTN01 4) At far end 7117Apatch GE5 RTN04 to GE5 RTN02 (use optical due to no electrical port available) | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
S01445_HU_1 | S106A_S01445OD_T3_KGPAKALANGAN | DU00006220535 | Sabah | Sabah | 4.375600 | 118.560100 |  |  |  |  | DT February |  |  | 04. BOM / Material Issue |  | TSS+AA+TI |  | 18G_2+0_112M_256QAM_EPLA NE_S01445 New 18G_DP_1.2M(MAC) x1. New RTN910AF(RTN04) x1. New ISM8 x2. New XMC_3E, Sub B_Lo x2. New IF cables with suitable type and length 2x RUN. New CAT6 cable x1. FE_S00468 New 18G_DP_1.2M(MAC) x1. New RTN910AF(RTN04) x1. New ISM8 x2. New XMC_3E, Sub B_Hi x2. New IF cables with suitable type and length 2x RUN. New SFP Module 10G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Parallel Link | Build new Parallel HW MW Link, S01445-S00468 18G_2+0_112M_256QAM_EPLA. Site Impacted : S00589/7032K. NE_S01445 1.Install new 18G_DP_1.2M(MAC) x1. 2.Install new RTN910AF(RTN04) x1 and insert ISM8 x2 into slot slot 03 & 04. 3.Install new XMC_3E, Sub A_Lo x2 and lay new IF cables with suitable type and length 2x RUN . Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN04). 5.Disconnect/remove existing cascading in between existing RTN910AF(RTN01, NEID 16-27107) and existing RTN910AF(RTN02, NEID 88-28554). 6.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 16-27107). 7.Perform new cascading between port 8-EM6-1 of new RTN910AF(RTN04) and port 8-EM6-1 of existing RTN910AF(RTN01, NEID 16-27107). 8.Request new xC Vlan DCN from ZTE IPRAN team and re-use existing Vlan Services. 9.Migrate traffics S00589 ONLY via new Parallel HW MW Link, S01445-S00468 18G_2+0_112M_256QAM_EPLA. FE_S00468 1.Install new 18G_DP_1.2M(MAC) x1. 2.Install new RTN910AF(RTN04) x1 and insert ISM8 x2 into slot slot 03 & 04. 3.Install new XMC_53E, Sub A_Hi x2 and lay new IF cables with suitable type and length 2x RUN . Configure it. 4.Enable port 8-EM6-3 of new RTN910AF(RTN04) and insert Optical SFP Module 10G 10Km 1310nm or equivalent. 5.Enable port 17-SLF2EM6-5 of existing RTN950A(RTN01, NEID 88-23008) and insert Optical SFP Module 10G 10Km 1310nm or equivalent. 6.Perform new cascading in between port 8-EM6-3 of new RTN910AF(RTN04) and port 17-SLF2EM6-5 of existing RTN950A(RTN01, NEID 88-23008). 7.Request new xC Vlan DCN from ZTE IPRAN team and re-use existing Vlan Services. 8.Migrate traffics S00589 into existing port at PTN/Cisco S00250. | Build new Parallel HW MW Link, S01445-S00468 18G_2+0_112M_256QAM_EPLA. Site Impacted : S00589/7032K. NE_S01445 1.Install new 18G_DP_1.2M(MAC) x1. 2.Install new RTN910AF(RTN04) x1 and insert ISM8 x2 into slot slot 03 & 04. 3.Install new XMC_3E, Sub A_Lo x2 and lay new IF cables with suitable type and length 2x RUN . Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN04). 5.Disconnect/remove existing cascading in between existing RTN910AF(RTN01, NEID 16-27107) and existing RTN910AF(RTN02, NEID 88-28554). 6.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 16-27107). 7.Perform new cascading between port 8-EM6-1 of new RTN910AF(RTN04) and port 8-EM6-1 of existing RTN910AF(RTN01, NEID 16-27107). 8.Request new xC Vlan DCN from ZTE IPRAN team and re-use existing Vlan Services. 9.Migrate traffics S00589 ONLY via new Parallel HW MW Link, S01445-S00468 18G_2+0_112M_256QAM_EPLA. | Build new Parallel HW MW Link, S01445-S00468 18G_2+0_112M_256QAM_EPLA. Site Impacted : S00589/7032K. FE_S00468 1.Install new 18G_DP_1.2M(MAC) x1. 2.Install new RTN910AF(RTN04) x1 and insert ISM8 x2 into slot slot 03 & 04. 3.Install new XMC_53E, Sub A_Hi x2 and lay new IF cables with suitable type and length 2x RUN . Configure it. 4.Enable port 8-EM6-3 of new RTN910AF(RTN04) and insert Optical SFP Module 10G 10Km 1310nm or equivalent. 5.Enable port 17-SLF2EM6-5 of existing RTN950A(RTN01, NEID 88-23008) and insert Optical SFP Module 10G 10Km 1310nm or equivalent. 6.Perform new cascading in between port 8-EM6-3 of new RTN910AF(RTN04) and port 17-SLF2EM6-5 of existing RTN950A(RTN01, NEID 88-23008). 7.Request new xC Vlan DCN from ZTE IPRAN team and re-use existing Vlan Services. 8.Migrate traffics S00589 into existing port at PTN/Cisco S00250. | XMC-3E | MAC | 18G | 18G_DP_1.2M(MAC) x1 | 18G_DP_1.2M(MAC) x1 | Seri Pancar | SQ202602090132-Seri Pancar | GCI |  |  |  | Ongoing | 2026-02-04 | 2026-02-28 | 2026-02-06 | 2026-02-06 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-30 | 2026-04-06 | 2026-03-30 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26042753 |  | 2026-04-28 |  | Ongoing | 2026-04-27 | 2026-04-28 | 2026-04-27 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202510300419-GTSB
2274A_AD | Tmn Kajang Mulia | DU00006220536 | Central | Selangor | 2.998300 | 101.797200 | [7 empty] | 02. Pending Access |  | TSS+AA+TI |  | 2X RTN910A 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB A HI 1X ODU 18G XMC5D SUB A LO | MW Parallel Link | MW PARALLEL LINK 2274A-2715B WITH HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_256QAM_1556MBPS_XMC5D_SUB_A_LINK_2.60KM IMPACTED: 1949H NEW LINK WILL CARRY TRAFFIC 1949H | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. NEW LINK CARRY 1949H TRAFFIC | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. PATCH TO NEW CP AND DO PORT LAG 6. NEW LINK CARRY 1949H TRAFFIC | XMC5D | MDD | 18G | 0.6 | 0.6 | MTK |  | MTK | SQ202511190715-MTK // SQ202511190823-MTK |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25110601 |  | 2025-12-06 | 2025-11-15 | Completed | 2025-11-06 | 2025-12-06 | 2025-11-06 | 2025-11-15 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-12-19 | 2025-11-27 | 2025-11-27 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-11-27 | 2025-12-19 |  |  | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | [7 empty] | 2025-11-27 | 2025-12-19 |  |  | RIDHUAN//BIN MANSOR/8225000011 | 2025-10-09: 2025-11-27; 2025-10-09: 2025-12-19; 2025-10-09: 2025-11-27; 2025-11-05: 2025-11-27 | [7 empty] | GCI | SQ202510300390-GCI | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
2069B_HU_1 | WT_UITMPNCKALAM | DU00006220537 | Central | Selangor | 3.204196 | 101.453258 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X 10G SFP 2X ISM8 CARD 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Parallel Link | MW PARALLEL LINK 2069B-1612B WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_256QAM_1556MBPS_XMC3E_SUB_A & B_LINK_3.88KM EPLA WITH EXISTING 18G 2+0 112MHZ SLOT 3 IMPACTED: 2680B, 3804A, 1518C 2069B-UITM PNCK ALAM-RTN01_2069B-UITM PNCK ALAM-RTN01-3-ISM8-1(1612B-RTN09 (V-01)) FE 10G PORT | 1. INSTALL NEW 1PCS ISM8 AT EXISTING RTN01 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM EPLA WITH EXISTING 18G 2+0 112MHZ | 1. INSTALL NEW 1PCS ISM8 AT EXISTING RTN09 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM EPLA WITH EXISTING 18G 2+0 112MHZ 5. PATCH TO NEW CP 10G PORT | XMC_3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202512120107-Magicell | Magicell | SQ202511260090-Magicell // SQ202511260101-Magicell | 2026-01-14 | 2026-01-13 | Completed | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2025-12-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251118AF |  | 2025-11-19 | 2025-11-20 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2026-01-19 | 2026-01-19 | 2026-01-19 |  | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 |  | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-10-09: 2026-01-19; 2025-10-09: 2026-01-19; 2025-10-09: 2026-01-19 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510300390-GCI | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
4097A_HU | Bukit Segenting | DU00006220538 | Northern | Penang | 5.310546 | 100.222560 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_110M_256QAM_EPLA NE_4097A New 23G_1.2M(MS) x1. Re-use existing RTN910AF(RTN03). New ISM8 x1. New XMC_3E, Sub A_Lo x2. FE_4017B New 23G_1.2M(MS) x1. Re-use existing RTN910AF(RTN06). New ISM8 x1. New XMC_3E, Sub A_Hi x2. | MW Swap | Existing HW MW link 18G_1+0_110M_512QAM. Swap existing link to new HW MW Link 23G_2+0_110M_256QAM_EPLA. Later, decom existing HW MW link 18G_1+0_110M_512QAM. Decom existing ODU & Antenna ONLY and do not decom IDU(Re-use). Site Impacted : 4097A & 4706C. NE_4097A 1.Install new 23G_1.2M(MS) x1. 2.Re-use existing RTN910AF(RTN03-NEID 23673). Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN03-NEID 23673). 3.Install new XMC_3E, Sub A_Lo x2. Build new HW MW Link 23G_2+0_110M_256QAM_EPLA. 4.Re-use existing Vlan DCN and Vlan services. 5.Migrate traffic via new HW MW Link 23G_2+0_110M_256QAM_EPLA. 6.Later, decom existing HW MW link 18G_1+0_110M_512QAM. Decom existing ODU & Antenna ONLY and do not decom IDU(Re-use). FE_4017B 1.Install new 23G_0.6M(MS) x1. 2.Re-use existing RTN910AF(RTN06-NEID 23674). Insert new ISM8 x1 into slot 03 of existing RTN910AF(RTN06-NEID 23674). 3.Install new XMC_3E, Sub A_Hi x2. Build new HW MW Link 23G_2+0_110M_256QAM_EPLA. 4.Re-use existing port at IBeam and reuse existing Vlan DCN & Vlan Services. 5.Migrate traffic via existing port at IBeam. 6.Later, decom existing HW MW link 18G_1+0_110M_512QAM. Decom existing ODU & Antenna ONLY and do not decom IDU(Re-use). | Existing HW MW link 18G_1+0_110M_512QAM. Swap existing link to new HW MW Link 23G_2+0_110M_256QAM_EPLA. Later, decom existing HW MW link 18G_1+0_110M_512QAM. Decom existing ODU & Antenna ONLY and do not decom IDU(Re-use). Site Impacted : 4097A & 4706C. NE_4097A 1.Install new 23G_1.2M(MS) x1. 2.Re-use existing RTN910AF(RTN03-NEID 23673). Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN03-NEID 23673). 3.Install new XMC_3E, Sub A_Lo x2. Build new HW MW Link 23G_2+0_110M_256QAM_EPLA. 4.Re-use existing Vlan DCN and Vlan services. 5.Migrate traffic via new HW MW Link 23G_2+0_110M_256QAM_EPLA. 6.Later, decom existing HW MW link 18G_1+0_110M_512QAM. Decom existing ODU & Antenna ONLY and do not decom IDU(Re-use). | Existing HW MW link 18G_1+0_110M_512QAM. Swap existing link to new HW MW Link 23G_2+0_110M_256QAM_EPLA. Later, decom existing HW MW link 18G_1+0_110M_512QAM. Decom existing ODU & Antenna ONLY and do not decom IDU(Re-use). Site Impacted : 4097A & 4706C. FE_4017B 1.Install new 23G_0.6M(MS) x1. 2.Re-use existing RTN910AF(RTN06-NEID 23674). Insert new ISM8 x1 into slot 03 of existing RTN910AF(RTN06-NEID 23674). 3.Install new XMC_3E, Sub A_Hi x2. Build new HW MW Link 23G_2+0_110M_256QAM_EPLA. 4.Re-use existing port at IBeam and reuse existing Vlan DCN & Vlan Services. 5.Migrate traffic via existing port at IBeam. 6.Later, decom existing HW MW link 18G_1+0_110M_512QAM. Decom existing ODU & Antenna ONLY and do not decom IDU(Re-use). | XMC-3E | MS | 23G | 23G_1.2M(MS) x1. | 23G_1.2M(MS) x1. | GTSB | SQ202512160971-GTSB | GTSB | SQ202512160957-GTSB // SQ202512300366-GTSB |  |  | Ongoing | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY251118AG |  | 2025-11-19 | 2025-11-20 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-13 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-13 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2026-02-27 | HAMZAH BIN ABDUL MUTALIF6799000301 | 2025-10-09: 2025-12-10; 2025-10-09: 2025-12-10; 2025-10-09: 2025-12-10; 2025-11-05: 2025-12-10 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202510300410-GTSB
4770A_1 | Toklin (Trunk ) | DU00003714289 | Northern | Kedah | 5.630050 | 100.570910 | [7 empty] | 00. Integrated/RFS Done | 6/6: D1: Cutover done 28/5: DO Ready, Pending Collection | TSS+TI | L1+ATP+PAC | 1x IDU 910A 2x Fiber 1G 1330nm 40km Module 2x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN port reengineering at IBeam 4770A for RTN14 NE (4770A) at IBeam: 1) 1G port at GE0/4/6. 2) Insert new Fiber SFP module 1G SFP SM 1330 40km at port GE0/4/6. NE (4770A) at new Huawei RTN 910A(RTN14 & New 910A): 1) Install new IDU 910A. Reengineering link 4631A-4770A from RTN14 to new IDU 910A. 1) Insert new Fiber SFP module 1G SFP SM 13300 40km at 8-EM6-5(Port 5). Impact sites: 4631A | [7 empty] | GCI | SQ202408300869-GCI | GCI | SQ202407020120-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-08-20 | 2024-08-20 | 2024-08-20 | 2024-08-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-20 | 2024-08-20 | 2024-08-20 | 2024-08-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24052488 |  | 2024-05-25 | 2024-05-28 | Completed | 2024-05-24 | 2024-05-25 | 2024-05-24 | 2024-05-28 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-30 | 2024-05-31 | 2024-05-29 | 2024-08-08 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2024-05-30 | 2024-09-30 | 2024-05-29 | 2024-08-08 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-06-06 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-05-30 | 2024-05-31 | 2024-05-29 | 2024-08-03 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | 2025-10-09: 2024-05-30; 2025-10-09: 2024-05-31; 2025-10-09: 2024-05-29; 2025-11-05: 2024-06-08 |  |  | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
9128B-9363B | Samalaju-Lodging | DU00003726371 | Sarawak | Sarawak | 3.541144 | 113.329585 |  |  |  |  | Planning |  | ZTE | 00. Integrated/RFS Done | Cutover done | AA | PAC |  | MW Remote Upgrade | Remote Upgrade modulation to 512QAM | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2024-09-26 | 2024-10-26 | 2024-09-26 | 2024-09-26 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300154-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
4243B-4683A | kg Selamat (REL) | DU00003726372 | Northern | Penang | 5.507125 | 100.523600 |  |  |  |  | Planning |  |  | 00. Integrated/RFS Done | 18/7: D2: Cutover done. Replacement material issued 15/7: Use material from TX NIC 4489B_PostMOCN | TSS+AA+TI | L1+ATP+PAC | 2X RTN 910A 2X 23G 0.6M DP ANTENNA 1X 23G 112MHZ XMC-3 SUB A HI 1X 23G 112MHZ XMC-3 SUB A LO | MW New Link / Reroute | ADD NEW MW LINK 4243B-4281A WITH HUAWEI_23GHZ_1+0_112MHZ_0.6M_0.64KM (RE-ROUTE) REMAIN 4243B-4683A FOR LOAD BALANCE IMPACTED SITES: 4243B NE (4243B): 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 1+0 23G 112MHZ XMC-3 SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. PATCH 4243B BBU TO NEW RTN 910A FE (4281A): 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 1+0 23G 112MHZ XMC-3 SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. PATCH NEW RTN 910A TO NEW CP PORT | [7 empty] | CCSMY | SQ202408220933-CCS | CCSMY | SQ202408080059-CCS | 2024-11-26 | 2024-11-26 | Completed | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-06 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24072011 |  | 2024-07-22 | 2024-07-23 | Completed | 2024-07-21 | 2024-07-22 | 2024-07-21 | 2024-07-23 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-18 | 2024-07-31 | 2024-07-18 | 2024-08-15 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2024-07-18 | 2024-07-31 | 2024-07-18 | 2024-07-19 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-07-18 | 2024-07-31 | 2024-07-18 | 2024-08-19 | MUHAMMAD//MUZAMMAL/7021000054 | 2025-10-09: 2024-07-18; 2025-10-09: 2024-07-31; 2025-10-09: 2024-07-18; 2025-11-05: 2024-08-15 |  |  | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
7009K-S00023 | S093G_S00965OD_UITMADMINHILL | DU00003726373 | Sabah | Sabah | 6.066116 | 116.139886 |  |  |  |  | Drop/Cancel | Solution Issue | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Use EPMS link ID S00965-7165A DU code DU00005038781 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3364C-1799A | Kuaters Guru Seksyen 24 Shah Alam (REL) | DU00003726374 | Central | Selangor | 3.041528 | 101.517600 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 6/7: D1: Cutover done. Remote upgrade | AA | PAC |  | MW Remote Upgrade | MW Remote Upgrade 56Mhz to 112Mhz | [7 empty] | Allstar | No PR required-Remote Upgrade | Allstar | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-09-23 | AG//MOHD SHAFFIQ BIN AG SIDEK/6798000203 |  | 2024-09-23 | 2024-09-23 | 2024-09-23 |  |  |  | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
3452A_HU | WISMA DANI1 | DU00006182004 | Central | Kuala Lumpur | 3.127849 | 101.729963 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_1+0_56M. NE_3452A 18G_SP_0.6M(MAC) x1. XMC_3E , Sub A_Hi x1. ETH LAN Cable FE_1271A. 18G_SP_0.6M(MAC) x1. XMC_3E , Sub A_Lo. ETH LAN Cable x1. | MW Parallel Link | Existing link 15G_4+0_28M. Install parallel link 18G_1+0_56M. Site Impacted : 3452A. NE_3452A 1.Install 18G_SP_0.6M(MAC). 2.Reuse existing 7_ISM8-1+0 , 3452A_RTN04 (ID : 26862). 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and EPLA with existing 15G. 5.Traffic migrate to new EPLA link. 6.No link to be decom. FE_1271A. 1.Install new 18G_SP_0.6M(MAC). 2.Reuse existing 7_ISM8-1+0 , 1271A-RTN10 (ID : 26861). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA with existing 15G. 5.Enable GE2 , Create LAG , ETH patching to new PFS port. 6.Traffic migrate to new EPLA link. 7.No link to be decom. | Existing link 15G_4+0_28M. Install parallel link 18G_1+0_56M. Site Impacted : 3452A. NE_3452A 1.Install 18G_SP_0.6M(MAC). 2.Reuse existing 7_ISM8-1+0 , 3452A_RTN04 (ID : 26862). 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and EPLA with existing 15G. 5.Traffic migrate to new EPLA link. 6.No link to be decom. | Existing link 15G_4+0_28M. Install parallel link 18G_1+0_56M. Site Impacted : 3452A. FE_1271A. 1.Install new 18G_SP_0.6M(MAC). 2.Reuse existing 7_ISM8-1+0 , 1271A-RTN10 (ID : 26861). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA with existing 15G. 5.Enable GE2 , Create LAG , ETH patching to new PFS port. 6.Traffic migrate to new EPLA link. 7.No link to be decom. | [5 empty] | MTK | SQ202510220678-MTK | MTK | SQ202510220635-MTK // SQ202510220646-MTK | 2026-02-11 | 2026-02-11 | Completed | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102433 |  | 2025-10-28 | 2025-10-30 | Completed | 2025-10-27 | 2025-10-28 | 2025-10-25 | 2025-10-30 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-12 | 2025-12-24 | 2025-12-17 | 2025-12-17 | RAMIZAH BINTI ZAINON ABIDIN6000014055 | MTK TI | 2025-12-12 | 2025-12-24 | 2026-01-19 | 2026-01-19 | RAMIZAH BINTI ZAINON ABIDIN6000014055 | MTK TI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-17 | 2025-12-12 | 2025-12-24 | 2025-12-17 | 2026-01-19 | RAMIZAH BINTI ZAINON ABIDIN6000014055 | 2025-10-09: 2025-12-12; 2025-10-09: 2025-12-24; 2025-10-09: 2026-01-17; 2025-11-05: 2026-01-17 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510300390-GCI | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-10-21 | CHEONG/SENG/WAH/7018000306
K00277_HU | BUKITAPING | DU00006182005 | Northern | Kedah | 5.132325 | 100.585734 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | REMOTE UPGRADE LINK K00277-K00179 FORM 13G 2+0 TO 13G 4+0 256QAM 512MHZ WITH CA |  |  | XMC5D | MAC | 13G | 1.2 | 1.2 | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-29 | [15 empty] | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510300396-GCI | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-22 | EZRIN TASNIM BIN ABDUL GANI6798000128
4927A_HU | Kg Tersusun | DU00006182006 | Northern | Perak | 4.096261 | 101.283835 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 4927A-4311A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB_B_1.59KM IMPACTED: 4927A | 1. REUSE EXISTING RTN910 2. SWAP EXISTING ODU TO NEW ODU 23G XMC3E 112MHZ SUB B 3. REUSE EXISTING 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM | 1. REUSE EXISTING RTN910 2. SWAP EXISTING ODU TO NEW ODU 23G XMC3E 112MHZ SUB B 3. REUSE EXISTING 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM | XMC3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202510220709-Magicell | Magicell | SQ202510220690-Magicell // SQ202510220702-Magicell | 2025-12-04 | 2025-12-03 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102327 |  | 2025-10-24 | 2025-10-27 | Completed | 2025-10-23 | 2025-10-24 | 2025-10-23 | 2025-10-27 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-08 | 2026-11-20 | 2025-11-08 | 2025-12-24 | WAN NURMISWARI BIN WAN ISMAIL6000014316 |  | 2025-11-08 | 2026-11-20 | 2025-11-08 | 2025-12-24 | WAN NURMISWARI BIN WAN ISMAIL6000014316 |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-08 | 2025-11-08 | 2026-11-20 | 2025-11-08 | 2025-12-24 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-11-08 | 2026-11-20 | 2025-11-08 | 2025-12-08 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | NG HONG JIE7018000036 | Logistic Team | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510300396-GCI | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-22 | EZRIN TASNIM BIN ABDUL GANI6798000128
4311A_IPR | Dunlop Kliniktrak | DU00006182007 | Northern | Perak | 4.110030 | 101.289130 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x 1. | IDU-IPRAN | Perform LAG at CP site for IDU 4311A-DUNLOP KLINIKTRAK-RTN02 to 4311A-MAC-001 Dunlop Kliniktrak (MIP201X) Impact sites: 4314A,4927A. 1) Patch 4311A-DUNLOP KLINIKTRAK-RTN02 GE2 to new CP port 2) Create LAG | Perform LAG at CP site for IDU 4311A-DUNLOP KLINIKTRAK-RTN02 to 4311A-MAC-001 Dunlop Kliniktrak (MIP201X) Impact sites: 4314A,4927A. 1) Patch 4311A-DUNLOP KLINIKTRAK-RTN02 GE2 to new CP port 2) Create LAG | [6 empty] | GTSB | SQ202512160971-GTSB | GTSB | SQ202512030574-GTSB | 2026-01-06 | 2026-01-05 | Completed | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-05 | 2026-01-06 | 2026-01-05 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-05 | 2026-01-06 | 2026-01-05 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102158 |  | 2025-10-23 | 2025-10-23 | Completed | 2025-10-22 | 2025-10-23 | 2025-10-21 | 2025-10-23 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-12-03 | MHD FARID/BIN/NGADININ ADININ/6000054868 | Magicell TI | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-12-12 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  | 2025-12-24 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-12-17 | MHD FARID/BIN/NGADININ ADININ/6000054868 | 2025-10-09: 2025-10-30; 2025-10-09: 2025-10-30; 2025-10-09: 2025-10-30; 2025-11-05: 2025-12-15 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510300396-GCI | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | CHEONG/SENG/WAH/7018000306
Q01861_PL | Q132A_Q01861OD_LDGBLT | DU00006182008 | Sarawak | Sarawak | 3.612100 | 113.763800 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New CAT6 cable with suitable length x2. | BBU Patching | ****Important Note: **** 1.Mandatory to perform simultaneously DU Q01861_PL(For NE site task) and DU 9544A_PL(For FE site task) and assign to same subcon. 2.Due to site Q01861 still not MOCN yet, therefore current Ericsson BBU/RAN must backhauling the traffic to xC PTN. 3.Do not decom current xC MW Link_ID SW02951 until MOCN plan to implement in Y2026). Site Impacted: Q01861. NE_Q01861/9254K(Perform under DU Q01861_PL) 1.Enable port 8-EM6-1 of existing RTN910AF(RTN01-NEID_24477). 2.Patching Ericsson BBU Q01861 to port 8-EM6-1 of existing RTN910AF(NEID_24477) of existing HW MW Link 9254K/Q01861-9544A(15G_2+0_28MHZ_1024QAM_EPLA). 3.Request new xC Vlan DCN and Vlan Services to PTN/Cisco(Q00268) or may reuse existing. 4.Ensure cascading perform at FE(9544A/Q00685) site before can divert traffic Q01861 to PTN/Cisco(Q00268). FE_9544A/Q00685(Perform under DU 9544A_PL) 1.Disconnect existing cascading port 8-EM6-1 of existing RTN910AF(RTN02-NEID_24476) and port 8-EM6-1 of existing RTN910AF(RTN01-NEID_20303). 2.Perform new cascading between port 8-EM6-1 of existing RTN910AF(RTN02-NEID_24476) and port 8-EM6-2 of existing RTN910AF(NEID_43725) of existing HW MW Link_ID SW03996. 3.Request new xC Vlan DCN and Vlan Services to PTN/Cisco(Q00268) or may reuse existing. 4.Migrate traffic Q01861 to existing PTN/Cisco(Q00268). | ****Important Note: **** 1.Mandatory to perform simultaneously DU Q01861_PL(For NE site task) and DU 9544A_PL(For FE site task) and assign to same subcon. 2.Due to site Q01861 still not MOCN yet, therefore current Ericsson BBU/RAN must backhauling the traffic to xC PTN. 3.Do not decom current xC MW Link_ID SW02951 until MOCN plan to implement in Y2026). Site Impacted: Q01861. NE_Q01861/9254K(Perform under DU Q01861_PL) 1.Enable port 8-EM6-1 of existing RTN910AF(RTN01-NEID_24477). 2.Patching Ericsson BBU Q01861 to port 8-EM6-1 of existing RTN910AF(NEID_24477) of existing HW MW Link 9254K/Q01861-9544A(15G_2+0_28MHZ_1024QAM_EPLA). 3.Request new xC Vlan DCN and Vlan Services to PTN/Cisco(Q00268) or may reuse existing. 4.Ensure cascading perform at FE(9544A/Q00685) site before can divert traffic Q01861 to PTN/Cisco(Q00268). | ****Important Note: **** 1.Mandatory to perform simultaneously DU Q01861_PL(For NE site task) and DU 9544A_PL(For FE site task) and assign to same subcon. 2.Due to site Q01861 still not MOCN yet, therefore current Ericsson BBU/RAN must backhauling the traffic to xC PTN. 3.Do not decom current xC MW Link_ID SW02951 until MOCN plan to implement in Y2026). Site Impacted: Q01861. FE_9544A/Q00685(Perform under DU 9544A_PL) 1.Disconnect existing cascading port 8-EM6-1 of existing RTN910AF(RTN02-NEID_24476) and port 8-EM6-1 of existing RTN910AF(RTN01-NEID_20303). 2.Perform new cascading between port 8-EM6-1 of existing RTN910AF(RTN02-NEID_24476) and port 8-EM6-2 of existing RTN910AF(NEID_43725) of existing HW MW Link_ID SW03996. 3.Request new xC Vlan DCN and Vlan Services to PTN/Cisco(Q00268) or may reuse existing. 4.Migrate traffic Q01861 to existing PTN/Cisco(Q00268). | [5 empty] | Allstar | SQ202511050236-Allstar | Allstar | SQ202511050151-Allstar | 2026-01-28 | 2026-01-30 | Completed | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-28 | 2025-12-22 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102338 |  | 2025-10-24 | 2025-10-24 | Completed | 2025-10-23 | 2025-10-24 | 2025-10-23 | 2025-10-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-11-05 | 2025-11-04 | 2025-11-04 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-10-30 | 2025-11-05 | 2025-11-03 | 2025-11-04 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-31 | 2025-10-30 | 2025-11-05 | 2025-11-02 | 2025-11-02 | TONI//ANAK KUMBONG/6798000163 | 2025-10-09: 2025-10-30; 2025-10-09: 2025-11-05; 2025-10-09: 2025-10-30; 2025-11-05: 2025-10-30 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202510300425-GTSB
9544A_PL | Rumah Datu Anduh | DU00006182009 | Sarawak | Sarawak | 3.640912 | 113.720359 | [9 empty] | TSS+TI |  | New CAT6 cable with suitable length x2. | MW IDU Patching | ****Important Note: **** 1.Mandatory to perform simultaneously DU 9544A_PL(For NE site task) and DU Q01861_PL(For FE site task) and assign to same subcon. 2.Due to site Q01861 still not MOCN yet, therefore current Ericsson BBU/RAN must backhauling the traffic to xC PTN. 3.Do not decom current xC MW Link_ID SW02951 until MOCN plan to implement in Y2026). Site Impacted: Q01861. NE_9544A/Q00685(Perform under DU 9544A_PL) 1.Disconnect existing cascading port 8-EM6-1 of existing RTN910AF(RTN02-NEID_24476) and port 8-EM6-1 of existing RTN910AF(RTN01-NEID_20303). 2.Perform new cascading between port 8-EM6-1 of existing RTN910AF(RTN02-NEID_24476) and port 8-EM6-2 of existing RTN910AF(NEID_43725) of existing HW MW Link_ID SW03996. 3.Request new xC Vlan DCN and Vlan Services to PTN/Cisco(Q00268) or may reuse existing. 4.Migrate traffic Q01861 to existing PTN/Cisco(Q00268). FE_Q01861/9254K(Perform under DU Q01861_PL) 1.Enable port 8-EM6-1 of existing RTN910AF(RTN01-NEID_24477). 2.Patching Ericsson BBU Q01861 to port 8-EM6-1 of existing RTN910AF(NEID_24477) of existing HW MW Link 9254K/Q01861-9544A(15G_2+0_28MHZ_1024QAM_EPLA). 3.Request new xC Vlan DCN and Vlan Services to PTN/Cisco(Q00268) or may reuse existing. 4.Ensure cascading perform at FE(9544A/Q00685) site before can divert traffic Q01861 to PTN/Cisco(Q00268). | ****Important Note: **** 1.Mandatory to perform simultaneously DU 9544A_PL(For NE site task) and DU Q01861_PL(For FE site task) and assign to same subcon. 2.Due to site Q01861 still not MOCN yet, therefore current Ericsson BBU/RAN must backhauling the traffic to xC PTN. 3.Do not decom current xC MW Link_ID SW02951 until MOCN plan to implement in Y2026). Site Impacted: Q01861. NE_9544A/Q00685(Perform under DU 9544A_PL) 1.Disconnect existing cascading port 8-EM6-1 of existing RTN910AF(RTN02-NEID_24476) and port 8-EM6-1 of existing RTN910AF(RTN01-NEID_20303). 2.Perform new cascading between port 8-EM6-1 of existing RTN910AF(RTN02-NEID_24476) and port 8-EM6-2 of existing RTN910AF(NEID_43725) of existing HW MW Link_ID SW03996. 3.Request new xC Vlan DCN and Vlan Services to PTN/Cisco(Q00268) or may reuse existing. 4.Migrate traffic Q01861 to existing PTN/Cisco(Q00268). | ****Important Note: **** 1.Mandatory to perform simultaneously DU 9544A_PL(For NE site task) and DU Q01861_PL(For FE site task) and assign to same subcon. 2.Due to site Q01861 still not MOCN yet, therefore current Ericsson BBU/RAN must backhauling the traffic to xC PTN. 3.Do not decom current xC MW Link_ID SW02951 until MOCN plan to implement in Y2026). Site Impacted: Q01861. FE_Q01861/9254K(Perform under DU Q01861_PL) 1.Enable port 8-EM6-1 of existing RTN910AF(RTN01-NEID_24477). 2.Patching Ericsson BBU Q01861 to port 8-EM6-1 of existing RTN910AF(NEID_24477) of existing HW MW Link 9254K/Q01861-9544A(15G_2+0_28MHZ_1024QAM_EPLA). 3.Request new xC Vlan DCN and Vlan Services to PTN/Cisco(Q00268) or may reuse existing. 4.Ensure cascading perform at FE(9544A/Q00685) site before can divert traffic Q01861 to PTN/Cisco(Q00268). | [5 empty] | Allstar | SQ202603180484-Allstar | Allstar | SQ202603180480-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030629 |  | 2026-03-07 | 2026-03-31 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202510300425-GTSB
7174D_HU | Kg Batangan REL | DU00006182010 | Sabah | Sabah | 6.125560 | 116.136720 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 23G_2+0_56M_256QAM_EPLA NE_7174D New 23G_1.2M(MAC)+OMT x1. Re-use RTN910AF(RTN01) New ISM8 x1. New XMC_3, Sub B_Hi x2. FE_7160A New 23G_1.2M(MAC)+OMT x1. Re-use RTN910AF(RTN01) New ISM8 x1. New XMC_3, Sub B_Lo x2. | MW Parallel Link | Existing HW MW Link 7174D-7160A, 13G_2+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA. Later, combine existing HW MW Link 7174D-7160A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA become HW MW Link 7174D-7160A, 13G&23G_4+0_28MHZ&56MHZ_2048QAM&256QAM_EPLA. Site Impacted : 7174D. NE_7174D 1.Install new 23G_1.2M(MAC)+OMT x1. 2.Re-use RTN910AF(RTN01) and insert new ISM8 x1 into slot 03 of existing RTN910AF(RTN01). 3.Install new XMC_3, Sub B_Hi x2. 4.Build HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA. 5.Later, combine existing HW MW Link 7174D-7160A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA become HW MW Link 7174D-7160A, 13G&23G_4+0_28MHZ&56MHZ_2048QAM&256QAM_EPLA. FE_7160A 1.Install new 23G_1.2M(MAC)+OMT x1. 2.Re-use RTN910AF(RTN01) and insert new ISM8 x1 into slot 03 of existing RTN910AF(RTN01). 3.Install new XMC_3, Sub B_Lo x2. 4.Build HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA. 5.Later, combine existing HW MW Link 7174D-7160A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA become HW MW Link 7174D-7160A, 13G&23G_4+0_28MHZ&56MHZ_2048QAM&256QAM_EPLA. | Existing HW MW Link 7174D-7160A, 13G_2+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA. Later, combine existing HW MW Link 7174D-7160A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA become HW MW Link 7174D-7160A, 13G&23G_4+0_28MHZ&56MHZ_2048QAM&256QAM_EPLA. Site Impacted : 7174D. NE_7174D 1.Install new 23G_1.2M(MAC)+OMT x1. 2.Re-use RTN910AF(RTN01) and insert new ISM8 x1 into slot 03 of existing RTN910AF(RTN01). 3.Install new XMC_3, Sub B_Hi x2. 4.Build HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA. 5.Later, combine existing HW MW Link 7174D-7160A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA become HW MW Link 7174D-7160A, 13G&23G_4+0_28MHZ&56MHZ_2048QAM&256QAM_EPLA. | Existing HW MW Link 7174D-7160A, 13G_2+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA. Later, combine existing HW MW Link 7174D-7160A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA become HW MW Link 7174D-7160A, 13G&23G_4+0_28MHZ&56MHZ_2048QAM&256QAM_EPLA. Site Impacted : 7174D. FE_7160A 1.Install new 23G_1.2M(MAC)+OMT x1. 2.Re-use RTN910AF(RTN01) and insert new ISM8 x1 into slot 03 of existing RTN910AF(RTN01). 3.Install new XMC_3, Sub B_Lo x2. 4.Build HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA. 5.Later, combine existing HW MW Link 7174D-7160A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 7174D-7160A, 23G_2+0_56MHZ_256QAM_EPLA become HW MW Link 7174D-7160A, 13G&23G_4+0_28MHZ&56MHZ_2048QAM&256QAM_EPLA. | XMC-3 | MAC | 23G | 23G_1.2M(MAC)+OMT x1. | 23G_1.2M(MAC)+OMT x1. | NR services | SQ202512160988-NR Services | NR services | SQ202512010589-NR Services // SQ202512010600-NR Services | 2026-01-26 | 2026-01-21 | Completed | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111914 |  | 2025-11-20 | 2025-11-24 | Completed | 2025-11-19 | 2025-11-20 | 2025-11-19 | 2025-11-24 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-02 | 2026-01-02 | 2025-12-02 | 2025-12-07 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-12-02 | 2026-01-02 | 2025-12-02 | 2025-12-07 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-09 | 2025-12-02 | 2026-01-02 | 2025-12-02 | 2025-12-12 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2025-10-09: 2025-12-02; 2025-10-09: 2026-01-02; 2025-10-09: 2025-12-02; 2025-11-05: 2025-12-02 |  |  | 2025-12-24 | 2026-01-24 | 2025-12-24 | 2025-12-24 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202510300419-GTSB
7150D_HU | Taman Kenari | DU00006182011 | Sabah | Sabah | 5.894106 | 118.043662 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M_512QAM NE_7150D New 23G_DP_0.6M(MAC)+OMT x1. New RTN910AF(RTN02). New XMC_3E, Sub A_Hi x1. FE_7092K/S00167 New 23G_DP_0.6M(MAC)+OMT x1. New RTN910AF(RTN02). New XMC_3E, Sub A_Lo x1. | MW Swap | Existing HW MW link 23G_1+0_56M. Swap existing link to new HW MW Link 23G_1+0_112M. Later, decom existing HW MW link 23G_1+0_56M. Site Impacted : 7150D NE_7150D 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_3E, Sub A_Hi x1. Build new HW MW Link 23G_1+0_112M. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Shifting BBU 7150D from port 8-EG6-1 of existing RTN910A(RTN01) to port 8-EM6-1 of new RTN910AF(RTN02). 6.Re-use existing Vlan DCN and Vlan services. 7.Migrate traffic via new HW MW Link 23G_1+0_112M. 8.Later, decom existing HW MW link 23G_1+0_56M. FE_7092K 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_3E, Sub A_Lo x1. Build new HW MW Link 23G_1+0_112M. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Re-use existing port at PTN/Cisco and patching to port 8-EM6-1 of new RTN910AF(RTN02). 6.Reuse existing Vlan DCN & Vlan Services. 7.Migrate traffic via existing port at PTN/Cisco. 8.Later, decom existing HW MW link 23G_1+0_56M. | Existing HW MW link 23G_1+0_56M. Swap existing link to new HW MW Link 23G_1+0_112M. Later, decom existing HW MW link 23G_1+0_56M. Site Impacted : 7150D NE_7150D 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_3E, Sub A_Hi x1. Build new HW MW Link 23G_1+0_112M. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Shifting BBU 7150D from port 8-EG6-1 of existing RTN910A(RTN01) to port 8-EM6-1 of new RTN910AF(RTN02). 6.Re-use existing Vlan DCN and Vlan services. 7.Migrate traffic via new HW MW Link 23G_1+0_112M. 8.Later, decom existing HW MW link 23G_1+0_56M. | Existing HW MW link 23G_1+0_56M. Swap existing link to new HW MW Link 23G_1+0_112M. Later, decom existing HW MW link 23G_1+0_56M. Site Impacted : 7150D FE_7092K 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_3E, Sub A_Lo x1. Build new HW MW Link 23G_1+0_112M. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Re-use existing port at PTN/Cisco and patching to port 8-EM6-1 of new RTN910AF(RTN02). 6.Reuse existing Vlan DCN & Vlan Services. 7.Migrate traffic via existing port at PTN/Cisco. 8.Later, decom existing HW MW link 23G_1+0_56M. | XMC_3E | MAC | 23G | 23G_0.6M(MAC)+OMT x1. | 23G_0.6M(MAC)+OMT x1. | NR services | SQ202601210165-NR Services | NR services | SQ202512300312-NR Services // SQ202512300318-NR Services | 2026-03-02 | 2026-02-23 | Completed | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-23 | 2026-01-30 | 2026-01-23 | 2026-01-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-23 | 2026-01-30 | 2026-01-23 | 2026-01-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121766 |  | 2025-12-18 | 2025-12-21 | Completed | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-21 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-29 | 2026-01-29 | 2025-12-29 | 2026-01-06 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-12-29 | 2026-01-29 | 2025-12-29 | 2026-01-21 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-22 | 2025-12-29 | 2026-01-29 | 2025-12-29 | 2026-01-29 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-12-29 | 2026-01-29 | 2025-12-29 | 2026-01-06 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | tseping//wang/6819000006 | Logistic Team | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202510300419-GTSB
9063C_HU | Klinik Kesihatan Sibujaya | DU00006182012 | Sarawak | Sarawak | 2.245102 | 111.971610 | [7 empty] | 05. Doable |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M_512QAM_EPLA NE_9063C New 18G_DP_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01) New XMC_3E, Sub A&B_Hi x2. FE_9384B New 18G_DP_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01) New XMC_3E, Sub A&B_Lo x2. | MW Swap | Existing HW MW link 18G_1+0_112M. MW Swap for existing link to new HW MW Link 18G_2+0_112M_512QAM_EPLA. Later, decom existing 18G ODU & Antenna ONLY. Keep RTN910AF at both NE & FE sites. Site Impacted : 9063C. NE_9063C 1.Install new 18G_DP_0.6M(MAC)+OMT x1. 2.Reuse existing RTN910AF(RTN01). 3.Install new XMC_3E, Sub A&B_Hi x2. 4.Reuse existing ISM8 Slot 07 Port 1 & 2. Build new HW MW Link 18G_2+0_112M_512QAM_EPLA. 5.Reuse existing Vlan DCN & Vlan Services. 6.Later, decom existing 18G ODU & 18G Antenna ONLY. FE_9384B 1.Install new 18G_DP_0.6M(MAC)+OMT x1. 2.Reuse existing RTN910AF(RTN01). 3.Install new XMC_3E, Sub A&B_Lo x2. 4.Reuse existing ISM8 Slot 07 Port 1 & 2. Build new HW MW Link 18G_2+0_112M_512QAM_EPLA. 5.Reuse existing Vlan DCN & Vlan Services. 6.Re-use existing xD existing IBeam port. 7.Later, decom existing 18G ODU & 18G Antenna ONLY. | Existing HW MW link 18G_1+0_112M. MW Swap for existing link to new HW MW Link 18G_2+0_112M_512QAM_EPLA. Later, decom existing 18G ODU & Antenna ONLY. Keep RTN910AF at both NE & FE sites. Site Impacted : 9063C. NE_9063C 1.Install new 18G_DP_0.6M(MAC)+OMT x1. 2.Reuse existing RTN910AF(RTN01). 3.Install new XMC_3E, Sub A&B_Hi x2. 4.Reuse existing ISM8 Slot 07 Port 1 & 2. Build new HW MW Link 18G_2+0_112M_512QAM_EPLA. 5.Reuse existing Vlan DCN & Vlan Services. 6.Later, decom existing 18G ODU & 18G Antenna ONLY. | Existing HW MW link 18G_1+0_112M. MW Swap for existing link to new HW MW Link 18G_2+0_112M_512QAM_EPLA. Later, decom existing 18G ODU & Antenna ONLY. Keep RTN910AF at both NE & FE sites. Site Impacted : 9063C. FE_9384B 1.Install new 18G_DP_0.6M(MAC)+OMT x1. 2.Reuse existing RTN910AF(RTN01). 3.Install new XMC_3E, Sub A&B_Lo x2. 4.Reuse existing ISM8 Slot 07 Port 1 & 2. Build new HW MW Link 18G_2+0_112M_512QAM_EPLA. 5.Reuse existing Vlan DCN & Vlan Services. 6.Re-use existing xD existing IBeam port. 7.Later, decom existing 18G ODU & 18G Antenna ONLY. | XMC_3E | MAC | 18G | 18G_0.6M(MAC)+OMT x1. | 18G_0.6M(MAC)+OMT x1. | Allstar | SQ202603130180-Allstar | Iezzpro | SQ202603260165-Iezzpro // SQ202603260168-Iezzpro |  |  | Ongoing | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-10 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-16 | 2026-03-10 | 2026-03-10 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-16 | 2026-04-23 | 2026-04-16 | 2026-04-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-20 | 2026-04-27 | 2026-04-20 | 2026-04-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26030914 |  | 2026-03-10 | 2026-04-06 | Completed | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-04-06 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-06 | 2026-05-06 | 2026-04-05 | 2026-04-06 | Hairil Nizam//Maliki/6000033206 | Iezzpro TI | 2026-04-06 | 2026-05-06 | 2026-04-05 | 2026-04-07 | Hairil Nizam//Maliki/6000033206 | Iezzpro TI | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-07 | 2026-04-06 | 2026-05-06 | 2026-04-05 | 2026-04-14 | Hairil Nizam//Maliki/6000033206 | 2026-04-06 | 2026-05-06 | 2026-04-05 | 2026-04-06 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-05 | Chin Sau Jiet6000063978 | Warehouse Team | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202510300425-GTSB
4584A_HU | Batu Kurau | DU00005805669 | Northern | Perak | 4.983135 | 100.798053 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1X LAN CABLE | MW IDU Patching | MW IDU PATCHING IDU RTN03 910A 4584A TO RTN 4584A-A00228 TO USE CELCOM TM LL. TO CARRY TRAFFIC 4721D TO XC FOR OFFLOAD. IMPACTED: 4721D | 1. IDU PATCHING IDU RTN03 910A 4584A TO RTN 4584A-A00228 TO USE CELCOM TM LL 2. BREAK CASCADE RTN03 AND RTN04 3. CONFIGURE TRAFFIC 4721D TO XC | [6 empty] | GCI | SQ202509240936-GCI | GCI | SQ202507290119-GCI | 2025-09-22 | 2025-09-22 | Completed | [8 empty] | Unassigned | Disabled |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071920 |  | 2025-07-20 | 2025-07-22 | Completed | 2025-07-19 | 2025-07-20 | 2025-07-19 | 2025-07-22 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-08 | 2025-08-22 | 2025-08-08 | 2025-08-21 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2025-08-08 | 2025-08-22 | 2025-08-08 | 2025-08-21 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-09 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-08-08 | 2025-08-22 | 2025-08-08 | 2025-09-16 | JUTI//ANAK RICHARD/6800000216 | 2025-10-09: 2025-08-08; 2025-10-09: 2025-08-22; 2025-10-09: 2025-08-08; 2025-11-05: 2025-09-13 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507100583-GCI | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | NOOR AZLIN/BINTI/TEH KAMARUDDIN/6000034898
4480B_HU | Perpaduan Ria Ipoh RCC | DU00005805670 | Northern | Perak | 4.634950 | 101.142240 | [7 empty] | 03. TSS Only |  | TSS |  | 2X IDU RTN910A 1x ODU 18G XMC3E SUB A HI 1x ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1x ODU 18G XMC3E SUB B LO 2X 0.6 18G ANTENNA DP | MW Swap | MW SWAP LINK 4480B-4498A WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_2.56KM IMPACTED: 4125C DISMANTLE EXISTING LINK | MW SWAP LINK 4480B-4498A WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_2.56KM IMPACTED: 4125C DISMANTLE EXISTING LINK | [6 empty] | Magicell | SQ202508290696-Magicell | Magicell | No PR required-Work at TSS only | 2025-11-27 | 2025-11-26 | Completed | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090327 |  | 2025-09-04 | 2025-10-18 | Completed | 2025-09-03 | 2025-09-04 | 2025-09-03 | 2025-10-18 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-24 | 2025-09-27 | 2025-09-24 | 2025-10-18 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-09-24 | 2025-09-27 | 2025-09-24 | 2025-10-18 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | [7 empty] | 2025-09-24 | 2025-09-27 | 2025-09-24 | 2025-10-18 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-10-09: 2025-09-24; 2025-10-09: 2025-09-27; 2025-10-09: 2025-09-24; 2025-11-05: 2025-09-25 | [7 empty] | GCI | SQ202507100583-GCI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | NOOR AZLIN/BINTI/TEH KAMARUDDIN/6000034898
Q01902_HU | ULUSGMERAH3 | DU00005805671 | Sarawak | Sarawak | 2.332761 | 111.843399 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_0.6/0.6_DP_XMC-3_SB A_112Mhz 1 pair SFP10G 1km + patch cord (due to 9380B LL using 10G port) | MW Swap | MW SWAP Q01902-Q00668 WITH 23G_1+0_0.6/0.6_DP_256QAM_XMC-3_SB A. DISMANTLE EXISITNG SM LINK | MW SWAP Q01902-Q00668 WITH 23G_1+0_0.6/0.6_DP_256QAM_XMC-3_SB A. NE: 1. Swap exisiting SM IDU with RTN901A. 2. Swap exisitng SM ODU with XMC-3_SB A. 3. Swap exisitng antenna with 23G_0.6_DP. 4. Configure 23G_1+0_0.6/0.6_DP_112Mhz_256QAM. 5. Dismantle SM link. | Update 07 Oct 2025: Additional task 1) Patch new RTN to SACOFA LL. Create new DCN 2) Patch 9380B BBU to new RTN MW SWAP Q01902-Q00668 WITH 23G_1+0_0.6/0.6_DP_256QAM_XMC-3_SB A. FE: 1. Swap exisiting SM IDU with RTN901A. 2. Swap exisitng SM ODU with XMC-3_SB A. 3. Swap exisitng antenna with 23G_0.6_DP. 4. Configure 23G_1+0_0.6/0.6_DP_112Mhz_256QAM. 5. Dismantle SM link. | XMC-3_SB A |  | 23 | 0.6 | 0.6 | NR Services | SQ202507230768-NR Services | Trintel | SQ202510090458-Trintel // SQ202510090481-Trintel | 2025-10-10 | 2025-10-06 | Completed | 2025-07-15 | 2025-07-18 | 2025-07-15 | 2025-07-21 | DINESH SINGH CHEEMA7167000003 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-19 | 2025-07-21 | 2025-07-20 | 2025-07-21 | DINESH SINGH CHEEMA7167000003 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-25 | 2025-07-21 | 2025-07-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-06 | 2025-10-10 | 2025-10-06 | 2025-10-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100738 |  | 2025-10-08 | 2025-10-08 | Completed | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-08 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | MUHAMMAD NAJIB BIN RAMLI6000011524 | Trintel TI | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-16 | MUHAMMAD NAJIB BIN RAMLI6000011524 | Trintel TI | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-11 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-16 | MUHAMMAD NAJIB BIN RAMLI6000011524 | 2025-10-09: 2025-10-09; 2025-10-09: 2025-10-09; 2025-10-09: 2025-10-09; 2025-11-05: 2025-10-11 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507100593-GTSB | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | HSU//MYET CHAE/6799000011
Q00020_HU | TMBKTDJIN | DU00005805672 | Sarawak | Sarawak | 1.539466 | 110.351480 | [6 empty] | ZTE | 00. Site Out/Drop | 4/9/2025 : Task will do under NIC TX |  |  |  | Under NIC | SW02458 carrying only Q01218. Q01218 will reoute to 9481A in NIC plan_MOCN done | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507100593-GTSB | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | HSU//MYET CHAE/6799000011
2482A_HU | Rawang Old Road (Maxis) | DU00005805673 | Central | Selangor | 3.300870 | 101.590010 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X 23G 0.6M DP ANTENNA 1X 23G 1.2M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP UPGRADE 2482A-1413A WITH HUAWEI_23G_2+0_1.2M/0.6M_DP_112MHZ_256QAM_1778MBPS_XMC3E_SUB_A & B_2.57KM IMPACTED: 2482A, 1440H, 1007K DISMANTLE EXISTING LINK | 1. REUSE EXISTING RTN910 SLOT 7 2. INSTALL NEW 23G 1.2M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. REUSE EXISTING RTN910 SLOT 7 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 1.2 | 0.6 | GCI | SQ202509300119-GCI | GCI | SQ202507250397-GCI // SQ202507250407-GCI // SQ202511060402-GCI | 2025-11-11 | 2025-11-10 | Completed | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-03 | 2025-10-04 | 2025-10-03 | 2025-10-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071161 |  | 2025-07-12 | 2025-07-17 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-24 | 2025-09-30 | 2025-09-23 | 2025-09-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-09-24 | 2025-09-30 | 2025-09-23 | 2025-09-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-25 | 2025-09-24 | 2025-09-30 | 2025-09-23 | 2025-09-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-09-24 | 2025-09-30 | 2025-09-23 | 2025-09-25 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507100581-GCI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q02239_HU | RUMAH PANTING | DU00005805674 | Sarawak | Sarawak | 4.259975 | 114.110220 | [6 empty] | ZTE | 00. Site Out/Drop | 11/9/2025 : Others - No more link Q02239-Q00344 | TSS+AA+TI+Dismantle |  | 13G_4+0_1.2/1.2_MDD_256QAM_XMC-5D_SB A 2xRTN910A 4xISM8 | MW Swap | MW SWAP Q02239-Q00344 WITH 13G_4+0_1.2/1.2_MDD_256QAM_XMC-5D_SB A Dismantle SW04228 SM link. | MW SWAP Q02239-Q00344 WITH 13G_4+0_1.2/1.2_MDD_256QAM_XMC-5D_SB A NE: 1. Swap exisitng SM IDU with RTN910A. 2. Swap exisitng SM ODU with XMC_5D_SB A. 3. Swap existing antenna with 13G_1.2MDD. 4. Configure 13G_4+0_1.2MDD_256QAM_800M_CA> 5. Dismantle SM link. | MW SWAP Q02239-Q00344 WITH 13G_4+0_1.2/1.2_MDD_256QAM_XMC-5D_SB A FE: 1. Swap exisitng SM IDU with RTN910A. 2. Swap exisitng SM ODU with XMC_5D_SB A. 3. Swap existing antenna with 13G_1.2MDD. 4. Configure 13G_4+0_1.2MDD_256QAM_800M_CA> 5. Dismantle SM link. | XMC-5D_A |  | 13 | 1.2 | 1.2 | Magicell | No PR required-Site drop/cancel | Magicell | No PR required-Site drop/cancel |  |  | Not started | 2025-09-03 | 2025-09-30 | [6 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | DO Cancel (30 days) | 2025-08-26 |  | Ongoing | 2025-08-25 | 2025-08-26 | 2025-08-25 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202507100593-GTSB | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | HSU//MYET CHAE/6799000011
9253R_HU | Kg. Kuala Nyalau | DU00005805675 | Sarawak | Sarawak | 3.639780 | 113.382500 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_1.2/1.2_MDD_256QAM_800M_XMC-5D_SB A 4xISM8 | MW Swap | MW SWAP WITH 13G_4+0_1.2/1.2_MDD_256QAM_800M_XMC-5D_SB A DISMANTLE EXISTING 13G_2+0. | MW SWAP WITH 13G_4+0_1.2/1.2_MDD_256QAM_800M_XMC-5D_SB A NE: 1. Reuse existing RTN910A. 2. Install new 2xISM8 at Slot 3 and 4. 3. Install new antenna 13G_1.2m_MDD. 4. Install new 13G_XMC-5D_SB A. 5. Configure 13G_4+0_1.2/1.2 MDD_CA_800M. 6. Dismantle existing 13G_2+0 link. | MW SWAP WITH 13G_4+0_1.2/1.2_MDD_256QAM_800M_XMC-5D_SB A FE: 1. Reuse existing RTN910A_RTN1 2. Install new 2xISM8 at Slot 3 and 4. 3. Install new antenna 13G_1.2m_MDD. 4. Install new 13G_XMC-5D_SB A. 5. Configure 13G_4+0_1.2/1.2 MDD_CA_800M. 6. Dismantle existing 13G_2+0 link. | XMC-5D_SB A |  | 13 | 1.2 | 1.2 | Magicell | SQ202509030212-Magicell | Magicell | SQ202510240603-Magicell // SQ202510240608-Magicell | 2025-10-17 | 2025-10-13 | Completed | 2025-09-03 | 2025-09-30 | 2025-09-29 | 2025-09-29 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-13 | 2025-10-17 | 2025-10-13 | 2025-10-13 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102356 |  | 2025-10-25 | 2025-10-24 | Completed | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-28 | 2025-11-08 | 2025-10-28 | 2025-10-28 | DAMIEN OH BOON PAR7018000155 | Magicell TI | 2025-10-29 | 2025-11-08 | 2025-11-13 | 2025-11-21 | WATSON ANAK MAMBA7018000213 | Magicell TI | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-04 | 2025-10-29 | 2025-11-08 | 2025-11-21 | 2025-12-10 | WATSON ANAK MAMBA7018000213 | 2025-10-29 | 2025-11-08 | 2025-10-30 | 2025-10-30 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507100593-GTSB | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | HSU//MYET CHAE/6799000011
3456B_HU | Menara Felda FGV IB | DU00005805676 | Central | Kuala Lumpur | 3.155578 | 101.718718 | [7 empty] | 06. Other Issue | 6/4/2026: Modulation degrade, TT raised on 3/4, pending TT clearance to proceed Remote Upgrade | AA |  |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 3456B-1266A 23G_2+0_0.6M/0.6M_DP_56MHZ_256QAM TO 23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: 2210A, 3456B | MW REMOTE UPGRADE LINK 3456B-1266A 23G_2+0_0.6M/0.6M_DP_56MHZ_256QAM TO 23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: 2210A, 3456B | MW REMOTE UPGRADE LINK 3456B-1266A 23G_2+0_0.6M/0.6M_DP_56MHZ_256QAM TO 23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: 2210A, 3456B | XMC3 | MAC | 23G | 0.6 | 0.6 | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202507100581-GCI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | EZRIN TASNIM BIN ABDUL GANI6798000128
1054K_HU | BDRMAHKOTABNTG | DU00005805677 | Central | Selangor | 2.822114 | 101.569200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 1x ODU 15G XMC3 SUB A HI 1x ODU 15G XMC3 SUB A LO 1x ODU 15G XMC3 SUB B HI 1x ODU 15G XMC3 SUB B LO 2x COUPLER 4x WAVEGUIDE 4X ODU MOUNTING | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 1054K/B02670-3366B WITH HUAWEI_15G_4+0_0.6M/1.2M_DP_28MHZ_512QAM_896MBPS_XMC3_SUB_A & B_4.55KM IMPACTED: B02670 | 1. INSTALL NEW ISM8 CARD AT EXISTING IDU RTN910A SLOT 3 2. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 3. REUSE EXISTING 15G 0.6M DPMS ANTENNA 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. CREATE EPLA NEW 15G 2+0 WITH EXISTING 15G 2+0 SLOT 7 | 1. INSTALL NEW ISM8 CARD AT EXISTING IDU RTN910A SLOT 3 2. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 3. REUSE EXISTING 15G 1.2M DPMS ANTENNA 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. CREATE EPLA NEW 15G 2+0 WITH EXISTING 15G 2+0 SLOT 7 | XMC3 | MS | 15G | 0.6 | 1.2 | Magicell | SQ202507230730-Magicell | Magicell | SQ202507250421-Magicell // SQ202507250427-Magicell | 2025-08-19 | 2025-08-18 | Completed | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-06 | 2025-08-07 | 2025-08-06 | 2025-08-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-19 | 2025-08-18 | 2025-08-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071163 |  | 2025-07-12 | 2025-07-15 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-08-01 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-08-19 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | SITI HAFIZAH BINTI NOH6237001145 |  |  | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-08-18 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-10-09: 2025-07-28; 2025-10-09: 2025-07-28; 2025-10-09: 2025-07-28; 2025-11-05: 2025-08-02 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507100581-GCI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | NOOR AZLIN/BINTI/TEH KAMARUDDIN/6000034898
7745B_HU | Sime Darby | DU00005805678 | Sabah | Sabah | 5.639700 | 118.178900 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_512Q_28Mhz_448Mbps | MW Parallel Link | Install new link 15G_2+0_512Q_28Mhz_448Mbps to be parallel with existing link Existing 15G_4+0_896Mbps_Util 100% Link will become 6+0 Impact site: 7745B, 7172K | NE: 1. Install new RTN910 - will be swap with existing IDU 2. Install new 15G 1.2m DP XMC ant 3. Install new 15G XMC-3 sb A Lo 4. Configure link 15G 2+0 28MHZ 512QAM 5. Re-engineering existing 4+0 link from old IDU to new IDU 5. EPLA existing and new link become 6+0 | FE: 1. Install new ISM8 at slot 4 RTN01 2. Install new 15G 1.2m DP XMC ant 3. Install new 15G XMC-3 sb A Hi 4. Configure link 15G 2+0 28MHZ 512QAM 5. EPLA existing and new link become 6+0 | XMC-3 | XMC | 15G | 1.2m | 1.2m | NR services |  | NR services | SQ202512300312-NR Services // SQ202512300318-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25121768 |  | 2025-12-18 | 2025-12-21 | Completed | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-21 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-04-03 | 2026-03-03 | 2026-04-09 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-03-03 | 2026-04-03 | 2026-03-03 | 2026-04-27 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-13 | 2026-03-03 | 2026-04-03 | 2026-03-03 | 2026-04-27 | IBRAHIM//BIN SAHABU/7167000007 | 2025-10-09: 2026-03-03; 2025-10-09: 2026-04-03; 2025-10-09: 2026-03-03; 2025-11-05: 2026-04-09 | [7 empty] | GTSB | SQ202507100587-GTSB | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
7493B_HU | Morisem 2 | DU00005805679 | Sabah | Sabah | 5.417540 | 118.350500 | [7 empty] | 00. Integrated/RFS Done | 17/12/2025: TX Integration updated when integrator open port only. Work at site not yet done due to DO not ready | TSS+TI | L1+ATP+PAC |  | IDU-IPRAN | Re engineering divert traffic for 7104Z,7650E,7649E from ibeam, Port GE 0/2/20 to same ibeam, Port GE 0/2/22 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | SHAHARIN BIN RUSLAN6799000052 |  | 2025-08-13 | [15 empty] | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507100587-GTSB
A01082_HU | KG_SG_BATU_PREMIS | DU00005805680 | Northern | Perak | 4.439378 | 100.625754 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK A01082-4383A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB_B_1.12KM IMPACTED: A01082 DISMANTLE EXISTING LINK A01082-A00133 FE IDU PATCHING TO A00133 OB FIBER | 1. INSTALL NEW RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. IDU PATCHING AT FE TO USE A00133 OB FIBER 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202509130051-GCI | GCI | SQ202508270947-GCI // SQ202508270956-GCI | 2025-11-26 | 2025-11-25 | Completed | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | 2025-09-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082141 |  | 2025-08-22 | 2025-08-23 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-27 | 2025-09-03 | 2025-08-27 | 2025-08-30 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2025-08-27 | 2025-09-03 | 2025-08-27 | 2025-08-30 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-08 | 2025-08-27 | 2025-09-03 | 2025-08-27 | 2025-09-10 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2025-08-27 | 2025-09-03 | 2025-08-27 | 2025-08-27 | 2025-10-05 | 2025-10-05 | 2025-10-05 | 2025-10-05 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507100583-GCI | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | EZRIN TASNIM BIN ABDUL GANI6798000128
4954B_HU | Kg Sedim | DU00005805681 | Northern | Kedah | 5.405880 | 100.739740 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Existing HW link 13G_4+0_28M This DU to Cancel / Drop , because solution proposed under the following 3 DU ID : 4963B_HU ( DU code : DU00005826245) , 4982B_HU ( DU Code : DU00005244032) , K00416_HU ( DU Code : DU00005832682) Instead to upgrade the Link follow NE Identifier , proposed to reroute the child site 4963B. Old TX route : 4963B-4982B-4954B-4685B New TX Route : 4963B-4982B-K00416-4982B. | [7 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25071159 |  | 2025-07-12 | 2025-07-26 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202507100583-GCI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | CHEONG/SENG/WAH/7018000306
4071C_AD | Seri Jaya | DU00005824902 | Northern | Perak | 4.474615 | 101.072211 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Patching | MW IDU Patching 4071C-4594B to Huawei 4594A-4566A | N/A | MW IDU Patching 4071C-4594B to Huawei 4594A-4566A | [5 empty] | GTSB | SQ202508040494-GTSB | GTSB | SQ202507290125-GTSB | 2026-01-22 | 2026-01-22 | Completed | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071918 |  | 2025-07-20 | 2025-08-09 | Completed | 2025-07-19 | 2025-07-20 | 2025-07-19 | 2025-08-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-23 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-25 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-23 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-23 | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-23 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-10-09: 2025-08-22; 2025-10-09: 2025-08-22; 2025-10-09: 2025-08-22; 2025-11-05: 2025-08-23 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510300396-GCI | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | CHEONG/SENG/WAH/7018000306
Q02210_AD | KG SEGA | DU00006719137 | Sarawak | Sarawak | 1.417720 | 110.238700 | [9 empty] | TSS+AA+TI |  | Perform MW Hardware Upgrade 15G_6+0_28MHZ_512QAM_EPLA. NE_9114P/Q02210 Re-use existing 15G_1.2M(MDD)+Dual Coupler. Re-use existing RTN910AF(RTN01, NEID 9-36492). New ISM8x1. Re-use existing XMC_5D Pro, Sub A&B_Hi x2. New IF cable with suitable length and type x2 RUN. FE_9414A Re-use existing 15G_1.2M(MDD)+Dual Coupler. Re-use existing RTN910AF(RTN03, NEID 9-36493). New ISM8x1. Re-use existing XMC_5D Pro, Sub A&B_Lo x2. New IF cable with suitable length and type x2 RUN. New SFP Module 1G 10Km 1310nm x2(IDU Huawei) or equivalent. New Optical Patchcord with suitable type and length x1. | MW Hardware Upgrade | Existing HW MW Link, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Link 15G_4+0_28MHZ_512QAM_EPLA. Later combine existing HW MW Link, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Link 15G_4+0_28MHZ_512QAM_EPLA. Become new HW MW Link 15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : NE_9114P/Q02210. NE_9114P/Q02210 1.Re-use 15G_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN01, NEID 9-36492) and insert new ISM8 into slot 04. 3.Lay new IF cable with suitable length and type 2x RUN as below: - from existing ODU XMC-5D Sub A IF port 1(Vertical) to Slot 07 Port 2 of existing RTN910AF(RTN01, NEID 9-36492). - from existing ODU XMC-5D Sub B IF port 1(Horizontal) to Slot 04 Port 1 of existing RTN910AF(RTN01, NEID 9-36492). 4.Build new new HW MW Link 15G_6+0_28MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN & Vlan Services. 6.Migrate traffic 9114P/Q02210 into new HW MW Link 15G_6+0_28MHZ_512QAM_EPLA. FE_9414A 1.Re-use 15G_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN03, NEID 9-36493) and insert new ISM8 into slot 04. 3.Lay new IF cable with suitable length and type 2x RUN as below: - from existing ODU XMC-5D Sub A IF port 1(Vertical) to Slot 07 Port 2 of existing RTN910AF(RTN03, NEID 9-36493). - from existing ODU XMC-5D Sub B IF port 1(Horizontal) to Slot 04 Port 1 of existing RTN910AF(RTN03, NEID 9-36493). 4.Build new new HW MW Link 15G_6+0_28MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN & Vlan Services. 6.Enable port 8-EM6-6 of existing RTN910AF(RTN03, NEID 9-36493) and insert SFP Module 1G 10Km 1310nm or equivalent. 7.Enable port 8-EM6-6 of existing RTN910AF(RTN02, NEID 9-21069) and insert SFP Module 1G 10Km 1310nm or equivalent. 8.Perform LAG 2x 1G in between port 8-EM6-1 & 8-EM6-6 of existing RTN910AF(RTN03, NEID 9-36493) and port 8-EM6-2 & 8-EM6-6 of existing RTN910AF(RTN02, NEID 9-21069). 9.Migrate traffic 9114P/Q02210 into existing port of IBeam at CP(9999A). | Existing HW MW Link, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Link 15G_4+0_28MHZ_512QAM_EPLA. Later combine existing HW MW Link, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Link 15G_4+0_28MHZ_512QAM_EPLA. Become new HW MW Link 15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : NE_9114P/Q02210. NE_9114P/Q02210 1.Re-use 15G_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN01, NEID 9-36492) and insert new ISM8 into slot 04. 3.Lay new IF cable with suitable length and type 2x RUN as below: - from existing ODU XMC-5D Sub A IF port 1(Vertical) to Slot 07 Port 2 of existing RTN910AF(RTN01, NEID 9-36492). - from existing ODU XMC-5D Sub B IF port 1(Horizontal) to Slot 04 Port 1 of existing RTN910AF(RTN01, NEID 9-36492). 4.Build new new HW MW Link 15G_6+0_28MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN & Vlan Services. 6.Migrate traffic 9114P/Q02210 into new HW MW Link 15G_6+0_28MHZ_512QAM_EPLA. | Existing HW MW Link, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Link 15G_4+0_28MHZ_512QAM_EPLA. Later combine existing HW MW Link, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Link 15G_4+0_28MHZ_512QAM_EPLA. Become new HW MW Link 15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : NE_9114P/Q02210. FE_9414A 1.Re-use 15G_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN03, NEID 9-36493) and insert new ISM8 into slot 04. 3.Lay new IF cable with suitable length and type 2x RUN as below: - from existing ODU XMC-5D Sub A IF port 1(Vertical) to Slot 07 Port 2 of existing RTN910AF(RTN03, NEID 9-36493). - from existing ODU XMC-5D Sub B IF port 1(Horizontal) to Slot 04 Port 1 of existing RTN910AF(RTN03, NEID 9-36493). 4.Build new new HW MW Link 15G_6+0_28MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN & Vlan Services. 6.Enable port 8-EM6-6 of existing RTN910AF(RTN03, NEID 9-36493) and insert SFP Module 1G 10Km 1310nm or equivalent. 7.Enable port 8-EM6-6 of existing RTN910AF(RTN02, NEID 9-21069) and insert SFP Module 1G 10Km 1310nm or equivalent. 8.Perform LAG 2x 1G in between port 8-EM6-1 & 8-EM6-6 of existing RTN910AF(RTN03, NEID 9-36493) and port 8-EM6-2 & 8-EM6-6 of existing RTN910AF(RTN02, NEID 9-21069). 9.Migrate traffic 9114P/Q02210 into existing port of IBeam at CP(9999A). | XMC_5D | MDD | 15G | Re-use existing 15G_1.2M(MDD)+Dual Coupler | Re-use existing 15G_1.2M(MDD)+Dual Coupler | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604110003-GTSB
1183D_HU | MasjidHidayatul Muttaqin | DU00006719138 | Central | Selangor | 2.979995 | 101.566359 | [9 empty] | TSS+AA+TI |  | 23G_2+0_56M. NE_1183D 23G_DP_0.6M(MAC) x1. XMC_3E , Sub A & B_Hi x2. FE_1228A. 23G_DP_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. | MW Parallel Link | Existing link 18G_2+0_112M Install parallel link 23G_2+0_56M. Site Impacted : 2901A , 1183D NE_1183D 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decom MW link. FE_1228A. 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing RTN910A , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW link. | Existing link 18G_2+0_112M Install parallel link 23G_2+0_56M. Site Impacted : 2901A , 1183D NE_1183D 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decom MW link. | Existing link 18G_2+0_112M Install parallel link 23G_2+0_56M. Site Impacted : 2901A , 1183D FE_1228A. 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing RTN910A , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | MTK |  | MTK | SQ202604290759-MTK |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042183 |  | 2026-04-22 | 2026-04-27 | Completed | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-05-13 | 2026-04-29 | 2026-04-29 | RAMIZAH BINTI ZAINON ABIDIN6000014055 | MTK TI | 2026-04-29 | 2026-05-13 |  |  | RAMIZAH BINTI ZAINON ABIDIN6000014055 | MTK TI | [7 empty] | 2026-04-29 | 2026-05-13 |  |  | RAMIZAH BINTI ZAINON ABIDIN6000014055 | 2025-10-09: 2026-04-29; 2025-10-09: 2026-05-13; 2025-10-09: 2026-04-30; 2025-11-05: 2026-04-30 | [7 empty] | GCI | SQ202604030167-GCI | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-04 | CHEONG/SENG/WAH/7018000306
9536A_PORT | Pujut2 MP | DU00006773192 | Sarawak | Sarawak | 4.430468 | 114.018940 | [9 empty] | TSS+TI | L1+ATP+PAC | Fiber Patch Cord x1 pairs 10G SFP Module x2. | MW IDU Patching | 9536A_RTN02 to RTN01 upgrade to 10G | 9536A_RTN02 to RTN01 upgrade to 10G | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050464 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-07 | 2026-05-13 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-05-07 | 2026-05-13 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-05-07 | 2026-05-13 |  |  | ROYSTON//AHHOLE/6000038561 | 2025-10-09: 2026-05-07; 2025-10-09: 2026-05-13; 2025-10-09: 2026-05-07; 2025-11-05: 2026-05-07 | [7 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | CHEONG/SENG/WAH/7018000306
1035H_LOS | GINMEITICK SDNBHD | DU00006719140 | Central | Selangor | 3.037808 | 101.768076 | [9 empty] | TSS+TI+Dismantle |  | NLOS Radio (RTN510). NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Link reroute to new FE 2587A due to LOS Block. NLOS Radio RTN510 Site Impacted : 1035H NE_1035H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1035H-NLOS-3351B FE_2587A 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1035H-NLOS-3351B | Link reroute to new FE 2587A due to LOS Block. NLOS Radio RTN510 Site Impacted : 1035H NE_1035H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1035H-NLOS-3351B FE_2587A 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1035H-NLOS-3351B | Link reroute to new FE 2587A due to LOS Block. NLOS Radio RTN510 Site Impacted : 1035H NE_1035H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1035H-NLOS-3351B FE_2587A 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1035H-NLOS-3351B | [5 empty] | GTSB | SQ202604290755-GTSB | MTK | SQ202604290759-MTK |  |  | Ongoing | 2026-05-01 | 2026-05-15 | 2026-05-01 | 2026-05-01 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-01 | 2026-05-15 | 2026-05-01 | 2026-05-01 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604030167-GCI | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
7938A_HU | IOIBaturong 2 | DU00006719141 | Sabah | Sabah | 4.747485 | 118.055651 | [9 empty] | TSS+AA+TI |  | 4X ISM8 CARD 2X RTN910A 1X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1x ODU 15G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL LINK 7938A-7933A WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_B_WITH CA_LINK_4.88KM NEW LINK CARRY TRAFFIC 7346K IMPACTED: 7346K | 1. INSTALL NEW RTN910A WITH 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. PATCH EXISTING IDU LINK 7346K-7938A 6. NEW LINK CARRY 7346K TRAFFIC | 1. INSTALL NEW RTN910A WITH 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. NEW LINK CARRY 7346K TRAFFIC 6. PATCH TO NEW CP PORT | XMC5D | MDD | 15G | 0.6 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604030180-GCI | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01724_HU_1 | Q132A_Q01724OD_CB_RHKUPANG | DU00006719142 | Sarawak | Sarawak | 3.858017 | 113.934059 | [9 empty] | TSS+AA+TI |  | Perform upgrade 13G_2+0_28MHZ_256QAM_386M_EPLA to 13G_4+0_28MHZ_256QAM_772M_EPLA(Without CA). NE_Q01724 Re-use existing 13G_1.8M(MDD). New 13G Dual Coupler x1 Re-use existing RTN910AF(RTN01, NEID 82-15988). New XMC_5D Pro, Sub B_Lo x1. New ISM8 x1 for Slot 04. New IF cables 2x RUN for Slot 04. FE_Q00311 Re-use existing 13G_1.8M(MDD). New 13G Dual Coupler x1 Re-use existing RTN910AF(RTN01, NEID 82-25988). New XMC_5D Pro, Sub B_Hi x1. New ISM8 x1 for Slot 04. New IF cables 2x RUN for Slot 04. | MW Hardware Upgrade | Perform upgrade 13G_2+0_28MHZ_256QAM_386M_EPLA to 13G_4+0_28MHZ_256QAM_772M_EPLA(Without CA). Site Impacted : Q01724. NE_Q01724 1.Re-use existing 13G_1.8M(MDD). 2.Remove existing XMC_5D Pro, Sub A_Lo x1 and install new 13G Dual Coupler x1. 3.Install back existing XMC_5D Pro, Sub A_Lo x1 and also install new XMC_5D Pro, Sub B_Lo x1. 4.Re-use existing RTN910AF(RTN01, NEID 82-15988) and insert new ISM8 into slot 04. 5.Shifting existing IF cables currently terminated at ISM8 slot 07 Port 1 to ISM8 slot 03 Port 2. 6.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Lo to ISM8 slot 04 Port 1 & 2. 7.Perform MW Hardware Upgrade to 13G_4+0_28MHZ_256QAM_772M_EPLA(Without CA). 8.Re-use existing Vlan DCN and Vlan Services. 9.Migrate traffic Q01724 into new HW MW Link 13G_4+0_28MHZ_256QAM_772M_EPLA(Without CA). FE_Q00311 1.Re-use existing 13G_1.8M(MDD). 2.Remove existing XMC_5D Pro, Sub A_Hi x1 and install new 13G Dual Coupler x1. 3.Install back existing XMC_5D Pro, Sub A_Hi x1 and also install new XMC_5D Pro, Sub B_Hi x1. 4.Re-use existing RTN910AF(RTN01, NEID 82-25988) and insert new ISM8 into slot 04. 5.Shifting existing IF cables currently terminated at ISM8 slot 07 Port 1 to ISM8 slot 03 Port 2. 6.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Hi to ISM8 slot 04 Port 1 & 2. 7.Perform MW Hardware Upgrade to 13G_4+0_28MHZ_256QAM_772M_EPLA(Without CA). 8.Re-use existing Vlan DCN and Vlan Services. 9.Migrate traffic Q01724 into existing port at PTN/Cisco. | Perform upgrade 13G_2+0_28MHZ_256QAM_386M_EPLA to 13G_4+0_28MHZ_256QAM_772M_EPLA(Without CA). Site Impacted : Q01724. NE_Q01724 1.Re-use existing 13G_1.8M(MDD). 2.Remove existing XMC_5D Pro, Sub A_Lo x1 and install new 13G Dual Coupler x1. 3.Install back existing XMC_5D Pro, Sub A_Lo x1 and also install new XMC_5D Pro, Sub B_Lo x1. 4.Re-use existing RTN910AF(RTN01, NEID 82-15988) and insert new ISM8 into slot 04. 5.Shifting existing IF cables currently terminated at ISM8 slot 07 Port 1 to ISM8 slot 03 Port 2. 6.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Lo to ISM8 slot 04 Port 1 & 2. 7.Perform MW Hardware Upgrade to 13G_4+0_28MHZ_256QAM_772M_EPLA(Without CA). 8.Re-use existing Vlan DCN and Vlan Services. 9.Migrate traffic Q01724 into new HW MW Link 13G_4+0_28MHZ_256QAM_772M_EPLA(Without CA). | Perform upgrade 13G_2+0_28MHZ_256QAM_386M_EPLA to 13G_4+0_28MHZ_256QAM_772M_EPLA(Without CA). Site Impacted : Q01724. FE_Q00311 1.Re-use existing 13G_1.8M(MDD). 2.Remove existing XMC_5D Pro, Sub A_Hi x1 and install new 13G Dual Coupler x1. 3.Install back existing XMC_5D Pro, Sub A_Hi x1 and also install new XMC_5D Pro, Sub B_Hi x1. 4.Re-use existing RTN910AF(RTN01, NEID 82-25988) and insert new ISM8 into slot 04. 5.Shifting existing IF cables currently terminated at ISM8 slot 07 Port 1 to ISM8 slot 03 Port 2. 6.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Hi to ISM8 slot 04 Port 1 & 2. 7.Perform MW Hardware Upgrade to 13G_4+0_28MHZ_256QAM_772M_EPLA(Without CA). 8.Re-use existing Vlan DCN and Vlan Services. 9.Migrate traffic Q01724 into existing port at PTN/Cisco. | XMC-5D Pro | MDD | 13G | 13G_1.8M(MDD) | 13G_1.8M(MDD) | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604110003-GTSB
7723E_PL | IOI PLT Unico 5 | DU00006721415 | Sabah | Sabah | 5.373420 | 118.538355 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI |  | TX Mini Project, 7723E-7104Z, 15G 2+0 Non CA, ODU XMC-5D 28MHz Sub band A x 2, RTN910A x 1, ISM8 x 4, A15D06MDD-3NX x 1, A15D06MDD-3NX x 1, Ant ht NE/FE: 30m/30m, Each MODU install 2 IF cables | MW Parallel Link | Install MW Parallel Link | Install 15G 0.6DP dish, 2+0 Non CA, ODU TX low, ODU XMC-5D Sub band A x 1, ISM8 x 2, Each MODU install 2 IF cables(1 connect to Slot 3-1, 1 connect to Slot 4-1); Add 2 ISM8 card at existing 7723E-IOI PLT Unico 5-RTN01; Configure 4+0 PLA with existing 2+0 link. | Install 15G 0.6DP dish, 2+0 Non CA, ODU TX high, ODU XMC-5D Sub band A x 1, IDU RTN910A x 1, ISM8 x 2, Each MODU install 2 IF cables(1 connect to Slot 3-1, 1 connect to Slot 4-1); Install 2 ISM8 card at new IDU Slot 3 and 4. Relocate existing IF cables from 7104Z-IOI UNICO DESA-RTN05 Slot 7-1 and 7-2 to new IDU Slot 7-1, 7-2. Configure 4+0 PLA. New IDU patch to 7104Z-IOI UNICO DESA-RTN05 GE2 | XMC-5D | MDD | 15G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604100702-GTSB | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | LIM//WEI CHONG/6798000110
Q00508_LOS | Q115A_Q00508OD_KGJUGAN | DU00006721416 | Sarawak | Sarawak | 1.484892 | 110.077155 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 2X RTN910A 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB A HI 1x ODU 15G XMC5D SUB A LO | MW New Link / Reroute | MW NEW LINK Q00508-Q00222 WITH HUAWEI_15G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_A_WITH CA_LINK_5.26KM DISMANTLE EXISTING LINK Q00508-Q00029 IMPACTED: Q00508 | 1. INSTALL NEW RTN910A WITH 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK Q00508-Q00029 | 1. INSTALL NEW RTN910A WITH 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO NEW LL PORT 6. DISMANTLE EXISTING LINK Q00508-Q00029 | XMC5D | MDD | 15G | 1.2 | 1.2 | Allstar | SQ202604080087-Allstar | Allstar | SQ202604080079-Allstar // SQ202604080086-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040728 |  | 2026-05-12 | 2026-04-20 | Completed | 2026-04-07 | 2026-05-12 | 2026-04-07 | 2026-04-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-08 | 2026-04-14 | 2026-04-20 | 2026-04-20 | BETARMOKE//ANAK COSIT/6798000181 | Allstar TI | 2026-04-08 | 2026-04-14 | 2026-04-20 | 2026-04-20 | BETARMOKE//ANAK COSIT/6798000181 | Allstar TI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-13 | 2026-04-08 | 2026-04-14 | 2026-04-22 | 2026-04-22 | BETARMOKE//ANAK COSIT/6798000181 | 2025-10-09: 2026-04-08; 2025-10-09: 2026-04-14; 2025-10-09: 2026-04-08; 2025-11-05: 2026-04-08 | [7 empty] | GCI | SQ202604030185-GCI | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | EZRIN TASNIM BIN ABDUL GANI6798000128
B00553_AD | B065B_B00553OD_CB_BKTTUNGGAL | DU00006722827 | Central | Selangor | 3.578100 | 101.465800 | [9 empty] | TSS+TI | L1+ATP+PAC | ETH Cat 6 cable x1. | MW IDU Patching | Patch at FE to 1891B new PTN for new traffic B01572-B00553 under MW Swap EOS. Tx route before: B01572-1013P-B00308 Tx route after: B01572-1013P/B00553-1891B. Site Impacted : 1891B , B01572. NE_1891B. 1.1891B_RTN01_GE2 IDU patching to New PTN. 2.New PTN port allocate by OPS Team. 3.Create New Inband DCN. | Patch at FE to 1891B new PTN for new traffic B01572-B00553 under MW Swap EOS. Tx route before: B01572-1013P-B00308 Tx route after: B01572-1013P/B00553-1891B. Site Impacted : 1891B , B01572. NE_1891B 1.1891B_RTN01_GE2 IDU patching to New PTN. 2.New PTN port allocate by OPS Team. 3.Create New Inband DCN | [6 empty] | GCI |  | GCI | SQ202605070514-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042817 |  | 2026-04-29 |  | Ongoing | 2026-04-28 | 2026-04-29 | 2026-04-28 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-28 | 2026-05-05 | 2026-04-27 |  | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-04-28 | 2026-05-05 | 2026-04-27 |  | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-05 | 2026-04-28 | 2026-05-05 | 2026-04-27 |  | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-10-09: 2026-04-28; 2025-10-09: 2026-05-05; 2025-10-09: 2026-04-27; 2025-11-05: 2026-04-28 | [7 empty] | GCI | SQ202604100691-GCI | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | CHEONG/SENG/WAH/7018000306
7187R_HU | Kg.Binuou Tengah (Sk Binuou) | DU00006744706 | Sabah | Sabah | 5.148148 | 116.360908 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604150440-GCI
7496R_HU | KGBARIAWA ULU | DU00006744707 | Sabah | Sabah | 5.368290 | 116.123748 | [9 empty] | AA |  |  | MW Remote Upgrade | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604150447-GTSB | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | LIM//WEI CHONG/6798000110
8008Z_HU | KgHuluChemperuh | DU00006744708 | Central | Pahang | 3.318711 | 101.871812 | [9 empty] | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 2X 13G 1.2M MS ANTENNA 2x ODU 13G XMC3 SUB A HI 2x ODU 13G XMC3 SUB A LO 2x ODU 13G XMC3 SUB B HI 2x ODU 13G XMC3 SUB B LO | MW Swap | MW SWAP LINK 8008Z-1017A WITH HUAWEI_13G_4+0_1.2M/1.2M_MS_28MHZ_512QAM_896MBPS_XMC3_SUB_A&B_LINK_8.42KM DISMANTLE EXISTING LINK IMPACTED: 8008Z SWAP EXISTING LINK 15G 1+0 28MHZ TO 13G 4+0 28MHZ TO BECOME 6+0 (EXISTING 2+0, NEW 4+0) | 1. INSTALL NEW 1PCS ISM8 CARD AT EXISTING IDU SLOT 4 2. INSTALL NEW 13G 1.2M MS ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM USING SLOT 3 & 4 5. EPLA WITH EXISTING LINK SLOT 7 TO BECOME 6+0 6. DISMANTLE EXISTING LINK 15G 1+0 SLOT 3 | 1. INSTALL NEW 1PCS ISM8 CARD AT EXISTING IDU SLOT 4 2. INSTALL NEW 13G 1.2M MS ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM USING SLOT 3 & 4 5. EPLA WITH EXISTING LINK SLOT 7 TO BECOME 6+0 6. DISMANTLE EXISTING LINK 15G 1+0 SLOT 3 7. PATCH TO NEW CP PORT AND DO PORT LAG | XMC3 | MS | 13G | 1.2 | 1.2 | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050724 |  | 2026-05-08 |  | Ongoing | 2026-05-07 | 2026-05-08 | 2026-05-07 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604150406-GCI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | EZRIN TASNIM BIN ABDUL GANI6798000128
A00184_HU | A044A_A00184OD_TRONOH | DU00006744709 | Northern | Perak | 4.374985 | 100.973364 | [9 empty] | TSS+AA+TI+Dismantle |  | 13G_4+0_28M_512QAM NE_4526K/A00184 Re-use existing 13G_1.2M(MDD). Re-use existing RTN910AF(RTN01, NEID 44-13661). New ISM8 x2. New XMC_5D Pro, Sub B_Lo x1. New IF cables with suitable length and type x2 RUN. FE_A00086 Re-use existing 13G_1.8M(MDD). Re-use existing RTN910AF(RTN01, NEID 44-23661). New ISM8 x2. New XMC_5D Pro, Sub B_Hi x1. New IF cables with suitable length and type x2 RUN. | MW Hardware Upgrade | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link 4526K/A00184-A00086, 13G_2+0_28MHZ_512QAM_EPLA_448M. MW Hardware upgrade to HW MW Link 4526K/A00184-A00086, 13G_4+0_28MHZ_512QAM_EPLA_896M. Site Impacted : 4526K/A00184. NE_4526K/A00184 1.Re-use existing 13G_1.2M(MDD). 2.Re-use existing RTN910AF(RTN01, NEID 44-13661) and insert new ISM8 x2 into slot 03 & 04. 3.Swap existing ODU XMC-5D to new XMC_5D Pro, Sub A_Lo x1. 4.Lay new x2 RUN of new IF cables from new XMC_5D Pro to existing RTN910AF(RTN01, NEID 44-13661) slot 03 Port 1 and Slot 04 Port 1. 5.Build new MW Hardware upgrade to HW MW Link 4526K/A00184-A00086, 13G_4+0_28MHZ_512QAM_EPLA_896M. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic 4526K/A00184 to new HW MW Link 4526K/A00184-A00086, 13G_4+0_28MHZ_512QAM_EPLA_896M. FE_A00086 1.Re-use existing 13G_1.8M(MDD). 2.Re-use existing RTN910AF(RTN01, NEID 44-23661) and insert new ISM8 x2 into slot 03 & 04. 3.Swap existing ODU XMC-5D to new XMC_5D Pro, Sub A_Hi x1. 4.Lay new x2 RUN of new IF cables from new XMC_5D Pro to existing RTN910AF(RTN01, NEID 44-23661) slot 03 Port 1 and Slot 04 Port 1. 5.Build new MW Hardware upgrade to HW MW Link 4526K/A00184-A00086, 13G_4+0_28MHZ_512QAM_EPLA_896M. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic 4526K/A00184 to existing port of PTN/Cisco. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link 4526K/A00184-A00086, 13G_2+0_28MHZ_512QAM_EPLA_448M. MW Hardware upgrade to HW MW Link 4526K/A00184-A00086, 13G_4+0_28MHZ_512QAM_EPLA_896M. Site Impacted : 4526K/A00184. NE_4526K/A00184 1.Re-use existing 13G_1.2M(MDD). 2.Re-use existing RTN910AF(RTN01, NEID 44-13661) and insert new ISM8 x2 into slot 03 & 04. 3.Swap existing ODU XMC-5D to new XMC_5D Pro, Sub A_Lo x1. 4.Lay new x2 RUN of new IF cables from new XMC_5D Pro to existing RTN910AF(RTN01, NEID 44-13661) slot 03 Port 1 and Slot 04 Port 1. 5.Build new MW Hardware upgrade to HW MW Link 4526K/A00184-A00086, 13G_4+0_28MHZ_512QAM_EPLA_896M. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic 4526K/A00184 to new HW MW Link 4526K/A00184-A00086, 13G_4+0_28MHZ_512QAM_EPLA_896M. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link 4526K/A00184-A00086, 13G_2+0_28MHZ_512QAM_EPLA_448M. MW Hardware upgrade to HW MW Link 4526K/A00184-A00086, 13G_4+0_28MHZ_512QAM_EPLA_896M. Site Impacted : 4526K/A00184. FE_A00086 1.Re-use existing 13G_1.8M(MDD). 2.Re-use existing RTN910AF(RTN01, NEID 44-23661) and insert new ISM8 x2 into slot 03 & 04. 3.Swap existing ODU XMC-5D to new XMC_5D Pro, Sub A_Hi x1. 4.Lay new x2 RUN of new IF cables from new XMC_5D Pro to existing RTN910AF(RTN01, NEID 44-23661) slot 03 Port 1 and Slot 04 Port 1. 5.Build new MW Hardware upgrade to HW MW Link 4526K/A00184-A00086, 13G_4+0_28MHZ_512QAM_EPLA_896M. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic 4526K/A00184 to existing port of PTN/Cisco. | XMC-5D Pro | MDD | 13G | Existing 13G_1.2M(MDD) | Existing 13G_1.8M(MDD) | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070545-GTSB // SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042182 |  | 2026-04-22 | 2026-04-29 | Completed | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604150433-GTSB
2476A_HU_2 | SgSerai (Maxis) | DU00006744710 | Central | Selangor | 3.284510 | 101.549880 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | 13G_28Mhz_2+0_512QAM_448M 1x RTN910 2x ISM8 card 2x 1.2m 13G DP ant 1x ODU 13G XMC-5D sub A_Hi 1x ODU 13G XMC-5D sub A_Lo IF cable standby for re-engineering at NE - need confirm during survey | MW Parallel Link | Install new parallel link HW MW 13G_28Mhz_2+0_512QAM_448M)_3.3km Site Impacted : 3256C, 2673B, 3256A, 2002B Re-engineering work at NE for RTN05 (confirm IF cable if long enough to transfer from RTN05 to new IDU) Cascade RTN03 to new IDU at NE Cascade RTN05 to new IDU at NE Remove cascade RTN03 to RTN05 at NE | NE: 1. Install new IDU RTN910 and insert ISM8 card at slot 3 2. Install new 13G 1.2m DP ant 3. Install new ODU 13G XMC-5D sub A_Lo 4. Config link 13G 2+0 28Mhz 512QAM 5. Re-engineering existing 18G_2+0 IF cable from RTN05 slot 7 to new IDU ISM8 slot 3 6. Config EPLA 18G_2+0 with 13G_2+0 7. Cascade RTN03 and RTN05 to new IDU 8. Remove cascade RTN03 to RTN05 | FE: 1. Insert new ISM8 card to slot 3 RTN02 2. Install new 13G 1.2m DP ant 3. Install new ODU 13G XMC-5D sub A_Lo 4. Config link 13G 2+0 28Mhz 512QAM | XMC-5D Pro | MDD | 13G | 1.2m | 1.2m | GCI |  | GCI | SQ202604290727-GCI // SQ202604290731-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042012 |  | 2026-04-21 | 2026-04-23 | Completed | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-28 | 2026-05-05 | 2026-04-28 |  | MUHAMMAD ADIL6800000278 | GCI TI | 2026-04-28 | 2026-05-05 | 2026-04-28 |  | MUHAMMAD ADIL6800000278 | GCI TI | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-02 | 2026-04-28 | 2026-05-05 | 2026-04-28 |  | MUHAMMAD ADIL6800000278 | 2025-10-09: 2026-04-28; 2025-10-09: 2026-05-05; 2025-10-09: 2026-04-28; 2025-11-05: 2026-04-28 | [7 empty] | GTSB | SQ202604150418-GTSB | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
3097A_HU | NKVEDamansara KM21 (REL) | DU00006744711 | Central | Selangor | 3.169676 | 101.597473 | [9 empty] | TSS+AA+TI |  | 18G_2+0_112M. Add New SRU2 ODU. NE_3097A SRU2 , Sub A_Hi x1 FE_1409A SRU2 , Sub A_Lo x1. | MW Hardware Upgrade | Existing ZTE MW 18G_1+0_112M with OMT (DP) antenna. Hardware upgrade to 18G_2+0_112M. Add New SRU2 ODU. Site Impacted : 3097A NE_3097A 1.Reuse existing 18G_DP_0.6M 2.Install new SRU2 , Sub A_Hi on H polar. 3.Reuse existing IDU NR9150 , Port 2. 4.Create service cross connect and PLA with existing link. 5.Traffic migrate to new config 18G_2+0_112M. 6.No decom MW link. FE_1409A 1.Reuse existing 18G_DP_0.6M. 2.Install new SRU2 , Sub A_Lo on H polar. 3.Reuse existing IDU NR91050 , Port2. 4.Create service cross connect and PLA with existing link. 5.Traffic migrate to new config 18G_2+0_112M. 6.No decom MW link. | Existing ZTE MW 18G_1+0_112M with OMT (DP) antenna. Hardware upgrade to 18G_2+0_112M. Add New SRU2 ODU. Site Impacted : 3097A NE_3097A 1.Reuse existing 18G_DP_0.6M 2.Install new SRU2 , Sub A_Hi on H polar. 3.Reuse existing IDU NR9150 , Port 2. 4.Create service cross connect and PLA with existing link. 5.Traffic migrate to new config 18G_2+0_112M. 6.No decom MW link. | Existing ZTE MW 18G_1+0_112M with OMT (DP) antenna. Hardware upgrade to 18G_2+0_112M. Add New SRU2 ODU. Site Impacted : 3097A FE_1409A 1.Reuse existing 18G_DP_0.6M. 2.Install new SRU2 , Sub A_Lo on H polar. 3.Reuse existing IDU NR91050 , Port2. 4.Create service cross connect and PLA with existing link. 5.Traffic migrate to new config 18G_2+0_112M. 6.No decom MW link. | SRU2 | DP | 18G | 0.6 | 0.6 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604150406-GCI | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | CHEONG/SENG/WAH/7018000306
9463B_HU | KgSepinang | DU00006744712 | Sarawak | Sarawak | 1.674881 | 111.118298 | [9 empty] | TSS+AA+TI |  | 13G_4+0_28M_128QAM_CA NE_9463B New 13G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN03, NEID 9-38870). New ISM8 x2. New XMC_5D Pro, Sub A_Lo x1. New IF cables with suitable length and type x2 RUN. FE_9188A New 13G_1.8M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 9-38871). New ISM8 x2. New XMC_5D Pro, Sub A_Hi x1. New IF cables with suitable length and type x2 RUN. | MW Parallel Link | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604200059-GTSB
4023L_HU | TamanKubang Rotan 2 | DU00006744713 | Northern | Kedah | 6.135286 | 100.300624 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 1X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1x ODU 15G XMC5D SUB B LO | MW Swap | MW SWAP LINK 4023L-4669A WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_B_LINK_3.48KM DISMANTLE EXISTING LINK IMPACTED: 4023L | 1. INSTALL NEW 2PCS ISM8 CARD AT EXISTING IDU 4023L RTN01 SLOT 3 & 4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW 2PCS ISM8 CARD AT EXISTING IDU 4669A RTN19 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK | XMC5D | MDD | 15G | 0.6 | 1.2 | GCI |  | GCI | SQ202605070533-GCI // SQ202605070538-GCI |  |  | Ongoing | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042834 |  | 2026-04-29 | 2026-04-30 | Completed | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-04-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-05 | 2026-06-01 | 2026-05-05 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-05-05 | 2026-06-01 | 2026-05-05 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-06 | 2026-05-05 | 2026-06-01 | 2026-05-05 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2026-05-05 | 2026-06-01 | 2026-05-05 | 2026-05-05 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | NG HONG JIE7018000036 | Logistic Team | [5 empty] | GCI | SQ202604150423-GCI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | EZRIN TASNIM BIN ABDUL GANI6798000128
2565B_LOS | Twin Tech | DU00006744714 | Central | Selangor | 3.200900 | 101.613000 | [9 empty] | TSS+AA+TI |  | 23G_2+0_56M. NE_2565B 23G_DP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. FE_1049B 23G_DP_0.6M(MAC) x1. ISM8 x1 XMC_3E , Sub A & B_Hi x1. | MW New Link / Reroute | Link reroute to new FE 1049B due to LOS Block. Link Config 23G_2+0_56M. Site Impacted : 2565B. NE_2565B 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. FE_1049B 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 1049B_RTN08 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | Link reroute to new FE 1049B due to LOS Block. Link Config 23G_2+0_56M. Site Impacted : 2565B. NE_2565B 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. | Link reroute to new FE 1049B due to LOS Block. Link Config 23G_2+0_56M. Site Impacted : 2565B. FE_1049B 1.Install new 23G_DP_0.6M(MAC). 2.Reuse existing 1049B_RTN08 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Ongoing | 2026-05-04 | 2026-05-18 | 2026-05-04 | 2026-05-04 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-18 | 2026-05-04 | 2026-05-04 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26042441 |  | 2026-04-27 | 2026-04-29 | Completed | 2026-04-24 | 2026-04-27 | 2026-04-24 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202604150406-GCI | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | CHEONG/SENG/WAH/7018000306
2661C_HU | KawasanPerindustrian Olak Lempit | DU00006744715 | Central | Selangor | 2.824700 | 101.603600 | [9 empty] | TSS+AA+TI |  | 15G_4+0_CA_28M. NE_2661C MD2 x1. FE_B00719. MD2 x1. | MW Hardware Upgrade | Existing ZTE MW 15G_2+0_28M with SRU3D ODU. Hardware upgrade to ZTE MW 15G_4+0_CA_28M. Site Impacted : 2661C. NE_2661C 1.Reuse existing 15G_DP_1.2M 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub B_Hi. 5.Create service cross connect , CA and PLA existing link. 6.Traffic migrate to new 15G_4+0_CA_28M link. 7.No Decom MW link. FE_B00719. 1.Reuse existing 15G_DP_1.2M 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub A_Lo. 5.Create service cross connect , CA and PLA existing link. 6.Traffic migrate to new 15G_4+0_CA_28M link. 7.No decom MW link. | Existing ZTE MW 15G_2+0_28M with SRU3D ODU. Hardware upgrade to ZTE MW 15G_4+0_CA_28M. Site Impacted : 2661C. NE_2661C 1.Reuse existing 15G_DP_1.2M 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub B_Hi. 5.Create service cross connect , CA and PLA existing link. 6.Traffic migrate to new 15G_4+0_CA_28M link. 7.No Decom MW link. | Existing ZTE MW 15G_2+0_28M with SRU3D ODU. Hardware upgrade to ZTE MW 15G_4+0_CA_28M. Site Impacted : 2661C. FE_B00719. 1.Reuse existing 15G_DP_1.2M 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub A_Lo. 5.Create service cross connect , CA and PLA existing link. 6.Traffic migrate to new 15G_4+0_CA_28M link. 7.No decom MW link. | SRU3D | DP | 15G | 1.2 | 1.2 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604150406-GCI | 2026-04-19 | 2026-04-19 | 2026-04-19 | 2026-04-19 | CHEONG/SENG/WAH/7018000306
4021C_HU | RingletRata | DU00006744716 | Northern | Pahang | 4.450352 | 101.365750 | [9 empty] | TSS+AA+TI |  | 15G_4+0_CA_28M. NE_4021C MD2 x1 FE_4443B MD2 x1 | MW Hardware Upgrade | Existing ZTE MW 15G_2+0_28M with SRU3D ODU. Hardware upgrade to ZTE MW 15G_4+0_CA_28M. Site Impacted : 4021C. NE_4021C 1.Reuse existing 15G_DP_1.2M 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub B_Hi. 5.Create service cross connect , CA and PLA existing link. 6.Traffic migrate to new 15G_4+0_CA link. 7.No Decom MW link. FE_4443B 1.Reuse existing 15G_DP_1.2M 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub B_Lo. 5.Create service cross connect , CA and PLA existing link. 6.Traffic migrate to new 15G_4+0_CA_28M link. 7.No decom MW link. | Existing ZTE MW 15G_2+0_28M with SRU3D ODU. Hardware upgrade to ZTE MW 15G_4+0_CA_28M. Site Impacted : 4021C. NE_4021C 1.Reuse existing 15G_DP_1.2M 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse SRU3D , Sub B_Hi. 5.Create service cross connect , CA and PLA existing link. 6.Traffic migrate to new 15G_4+0_CA link. 7.No Decom MW link. | Existing ZTE MW 15G_2+0_28M with SRU3D ODU. Hardware upgrade to ZTE MW 15G_4+0_CA_28M. Site Impacted : 4021C. FE_4443B 1.Reuse existing 15G_DP_1.2M 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub B_Lo. 5.Create service cross connect , CA and PLA existing link. 6.Traffic migrate to new 15G_4+0_CA_28M link. 7.No decom MW link. | SRU3D | DP | 15G | 1.2 | 1.2 | GCI | SQ202605050374-GCI | GCI | SQ202605050356-GCI // SQ202605050364-GCI |  |  | Ongoing | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604150423-GCI | 2026-04-19 | 2026-04-19 | 2026-04-19 | 2026-04-19 | CHEONG/SENG/WAH/7018000306
4756A_HU | KgSiputih | DU00006744717 | Northern | Kedah | 6.361471 | 100.332981 | [9 empty] | TSS+AA+TI |  | 13G_28Mhz_2+0_512QAM_448M 2x ISM8 card 2x 1.2m 13G DP ant 1x ODU 13G XMC-5D sub A_Hi 1x ODU 13G XMC-5D sub A_Lo | MW Parallel Link | Install new parallel link HW MW 13G_28Mhz_2+0_512QAM_448M)_5.92km Site Impacted : 4756A EPLA existing link 13G_4+0 and new link 13G_2+0 | NE: 1. Insert ISM8 card at slot 4 RTN01 2. Install new 13G 1.2m DP ant 3. Install new ODU 13G XMC-5D sub A_Lo 4. Config link 13G 2+0 28Mhz 512QAM 5. Config EPLA 13G_4+0 with 13G_2+0 | FE: 1. Insert new ISM8 card at slot 4 RTN03 2. Install new 13G 1.2m DP ant 3. Install new ODU 13G XMC-5D sub A_Hi 4. Config link 13G 2+0 28Mhz 512QAM 5. Config EPLA 13G_4+0 with 13G_2+0 | XMC-5D Pro | MDD | 13G | 1.2m | 1.2m | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070545-GTSB // SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042017 |  | 2026-04-21 | 2026-04-30 | Completed | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604150433-GTSB | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
4321B_HU | KgKoh (Maxis) | DU00006744718 | Northern | Perak | 4.174080 | 100.709000 | [9 empty] | TSS+AA+TI |  | 15G_4+0_CA_28M. NE_4321B MD2 x1 IF cable per drum. FE_4403B. MD2 x1. IF Cable per drum. | MW Hardware Upgrade | Existing ZTE MW 15G_2+0_28M with (SRU3D) ODU. Hardware upgrade to ZTE MW 15G_4+0_CA_28M. Site Impacted : 4321B. NE_4321B 1.Reuse existing 15G_DP_1.2M 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub_B_Hi. 5.Create service cross connect , CA and PLA. 6.Traffic migrate to new 15G_4+0_CA_28M. 7.No Decom MW link. FE_4403B. 1.Reuse existing 15G_DP_1.2M. 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub B_Lo. 5.Create service cross connect , CA and PLA. 6.Traffic migrate to new 15G_4+0_CA_28M. 7.No decom MW link. | Existing ZTE MW 15G_2+0_28M with (SRU3D) ODU. Hardware upgrade to ZTE MW 15G_4+0_CA_28M. Site Impacted : 4321B. NE_4321B 1.Reuse existing 15G_DP_1.2M 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub_B_Hi. 5.Create service cross connect , CA and PLA. 6.Traffic migrate to new 15G_4+0_CA_28M. 7.No Decom MW link. | Existing ZTE MW 15G_2+0_28M with (SRU3D) ODU. Hardware upgrade to ZTE MW 15G_4+0_CA_28M. Site Impacted : 4321B. FE_4403B. 1.Reuse existing 15G_DP_1.2M. 2.Reuse existing IDU NR9150 , 4_MD2-2+0. 3.Install new 4_MD2-2+0. 4.Reuse existing SRU3D , Sub B_Lo. 5.Create service cross connect , CA and PLA. 6.Traffic migrate to new 15G_4+0_CA_28M. 7.No decom MW link. | SRU3D | DP | 15G | 1.2 | 1.2 | GCI | SQ202605070541-GCI | GCI |  |  |  | Ongoing | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604150423-GCI | 2026-04-19 | 2026-04-19 | 2026-04-19 | 2026-04-19 | CHEONG/SENG/WAH/7018000306
7647C_HU | TamanMiramas Semporna | DU00006744719 | Sabah | Sabah | 4.471828 | 118.609076 | [9 empty] | TSS+AA+TI |  | 23G_2+0_112M_512QAM_EPLA NE_7647C New 23G_DP_0.6M(MAC) x1. Re-use existing RTN910AF(RTN02, NEID 9-23074). New XMC_3E, Sub B_Lo x2. New IF cables with suitable type and length 2x RUN. FE_7209A New 23G_DP_0.6M(MAC) x1. Re-use existing RTN910AF(RTN07, NEID 9-23075). New XMC_3E, Sub B_Hi x2. New IF cables with suitable type and length 2x RUN. | MW Parallel Link | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604150447-GTSB
7330R_HU | SkLipasu (Kg. Lipasu) | DU00006744720 | Sabah | Sabah | 5.973950 | 116.632090 | [9 empty] | TSS+AA+TI |  | 1x ODU 18G XMC3 SUB A HI 1x ODU 18G XMC3 SUB A LO 2x SFP 1G | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 7330R-S00905 FROM 18G_1+0_1.2M/1.2M_DP_56MHZ_512QAM TO HUAWEI_18G_2+0_1.2M/1.2M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_LINK_3.30KM IMPACTED: 7330R | 1. REUSE EXISTING RTN910 2. REUSE EXISTING 18G 1.2M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3 112MHZ SUB A (EXISTING SUB B) 4. CONFIGURE LINK 18G 2+0 112MHZ_512QAM (CONFIGURE WITH EXISTING ODU B AND NEW ODU A) | 1. REUSE EXISTING RTN910 2. REUSE EXISTING 18G 1.2M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3 112MHZ SUB A (EXISTING SUB B) 4. CONFIGURE LINK 18G 2+0 112MHZ_512QAM (CONFIGURE WITH EXISTING ODU B AND NEW ODU A) 5. PATCH AT NEW CP PORT AND DO PORT LAG 2G | XMC3 | MAC | 18G | 1.2 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604150440-GCI | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
7269C_HU | Jalan Sin SanTawau | DU00006744721 | Sabah | Sabah | 4.298138 | 117.867581 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604150447-GTSB
4243B_AD_1 | kg Selamat(REL) | DU00006744722 | Northern | Penang | 5.507125 | 100.523581 | [9 empty] | TSS+AA+TI | L1+ATP+MRCF+PAC | 13G_4+0_28M_1024QAM_CA NE_4243B New 13G_1.2M(MDD) x1. New RTN910AF(RTN04). New ISM8 x2. New IF cables with suitable length and type x2 RUN. New XMC_5D Pro, Sub B_Lo x1. New CAT6 cable x1. FE_4148A/K00224 New 13G_1.2M(MDD) x1. New RTN910AF(RTN05). New ISM8 x2. New IF cables with suitable length and type x2 RUN. New XMC_5D Pro, Sub B_Hi x1. New CAT6 cable x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G WITH BW 28MHZ IN ORDER TO ENSURE CHANNEL AVAILABILITY AT CP.**** Existing 2x HW MW Links as stated below: 1.4243B(RTN01, NEID 9-27568)-4281A(RTN02, NEID 9-27567), 23G_1+0_112MHZ_1024QAM. Later, perform decom once new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD) ready. 2.4243B(RTN04, NEID 9-30141)-4683A(RTN13, NEID 9-30140), 13G_4+0_28MHZ_512QAM_EPLA. Later, perform decom once new MW Parallel HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD_1) ready. Site Impacted : 4243B(DU 4243B_AD) & 4578D(DU 4243B_AD_1). NE_4243B 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04) and insert new ISM8 x2 into slot 03 & slot 04. 3.Install XMC_5D Pro, Sub B_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN04). 7.Perform cascading port 8-EM6-1 of new RTN910AF(RTN02) to port 8-EG6-1 of existing RTN910A(RTN03, NEID 9-41466) 8.Request new xC Vlan DCN and Vlan Services. 9.Migrate traffics 4578D via new MW Link/Reroute HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA. 10.Later, decom existing 4243B(RTN04, NEID 9-30141)-4683A(RTN13, NEID 9-30140), 13G_4+0_28MHZ_512QAM_EPLA. FE_4148A/K00224 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN05) x1 and insert new ISM8 x2 into slot 03 & slot 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA. 6.Request new 1x 1G(Electrical) port of PTN/Cisco(K00224) from ZTE IPRAN Team and also request new xC Vlan DCN and Vlan Services. 7.Enable port 8-EM6-1 of new RTN910AF(RTN05). 8.Perform patching port 8-EM6-1 of new RTN910AF(RTN05) to new 1x 1G(Electrical) port of PTN/Cisco. 9.Migrate traffics 4578D via new 1x 1G(Electrical) port of PTN/Cisco(K00224). 10.Later, decom existing 4243B(RTN04, NEID 9-30141)-4683A(RTN13, NEID 9-30140), 13G_4+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G WITH BW 28MHZ IN ORDER TO ENSURE CHANNEL AVAILABILITY AT CP.**** Existing 2x HW MW Links as stated below: 1.4243B(RTN01, NEID 9-27568)-4281A(RTN02, NEID 9-27567), 23G_1+0_112MHZ_1024QAM. Later, perform decom once new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD) ready. 2.4243B(RTN04, NEID 9-30141)-4683A(RTN13, NEID 9-30140), 13G_4+0_28MHZ_512QAM_EPLA. Later, perform decom once new MW Parallel HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD_1) ready. Site Impacted : 4243B(DU 4243B_AD) & 4578D(DU 4243B_AD_1). NE_4243B 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04) and insert new ISM8 x2 into slot 03 & slot 04. 3.Install XMC_5D Pro, Sub B_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN04). 7.Perform cascading port 8-EM6-1 of new RTN910AF(RTN02) to port 8-EG6-1 of existing RTN910A(RTN03, NEID 9-41466) 8.Request new xC Vlan DCN and Vlan Services. 9.Migrate traffics 4578D via new MW Link/Reroute HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA. 10.Later, decom existing 4243B(RTN04, NEID 9-30141)-4683A(RTN13, NEID 9-30140), 13G_4+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G WITH BW 28MHZ IN ORDER TO ENSURE CHANNEL AVAILABILITY AT CP.**** Existing 2x HW MW Links as stated below: 1.4243B(RTN01, NEID 9-27568)-4281A(RTN02, NEID 9-27567), 23G_1+0_112MHZ_1024QAM. Later, perform decom once new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD) ready. 2.4243B(RTN04, NEID 9-30141)-4683A(RTN13, NEID 9-30140), 13G_4+0_28MHZ_512QAM_EPLA. Later, perform decom once new MW Parallel HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD_1) ready. Site Impacted : 4243B(DU 4243B_AD) & 4578D(DU 4243B_AD_1). FE_4148A/K00224 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN05) x1 and insert new ISM8 x2 into slot 03 & slot 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA. 6.Request new 1x 1G(Electrical) port of PTN/Cisco(K00224) from ZTE IPRAN Team and also request new xC Vlan DCN and Vlan Services. 7.Enable port 8-EM6-1 of new RTN910AF(RTN05). 8.Perform patching port 8-EM6-1 of new RTN910AF(RTN05) to new 1x 1G(Electrical) port of PTN/Cisco. 9.Migrate traffics 4578D via new 1x 1G(Electrical) port of PTN/Cisco(K00224). 10.Later, decom existing 4243B(RTN04, NEID 9-30141)-4683A(RTN13, NEID 9-30140), 13G_4+0_28MHZ_512QAM_EPLA. | XMC_5D Pro | MDD | 13G | 13G_1.2M(MDD) x1 | 13G_1.2M(MDD) x1 | GCI | SQ202605050374-GCI | GCI | SQ202604230170-GCI // SQ202604230175-GCI // SQ202604280634-GCI |  |  | Ongoing | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042013 |  | 2026-04-21 | 2026-04-21 | Completed | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-28 | 2026-05-09 | 2026-04-28 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-04-28 | 2026-05-09 | 2026-04-28 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | AKMAL//BIN RAZALI/6794000078 |  |  | 2026-04-28 | 2026-05-09 | 2026-04-28 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2025-10-09: 2026-04-28; 2025-10-09: 2026-05-09; 2025-10-09: 2026-04-28; 2025-11-05: 2026-04-28 | [7 empty] | GTSB | SQ202604150433-GTSB
J01928_HU | J079J_J01928OD_KONTENANASIONALPG | DU00006744723 | Southern | Johor | 1.455152 | 103.898947 | [9 empty] | AA |  |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK J01928-J00102 ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_SUB A_833MBPS IMPACTED SITE: J01928 | MW REMOTE UPGRADE LINK J01928-J00102 ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_SUB A_833MBPS IMPACTED SITE: J01928 | MW REMOTE UPGRADE LINK J01928-J00102 ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_SUB A_833MBPS IMPACTED SITE: J01928 | SRU2 | DP | 18G | 0.6 | 0.6 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604150455-GCI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | EZRIN TASNIM BIN ABDUL GANI6798000128
2772C_HU | Tropicanaaman dahlia | DU00006744724 | Central | Selangor | 2.939660 | 101.523240 | [9 empty] | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 1X RTN910A 1X 15G 0.6M MS ANTENNA 1X 15G 1.2M MS ANTENNA 2x ODU 15G XMC3 SUB A HI 2x ODU 15G XMC3 SUB A LO 2x ODU 15G XMC3 SUB B HI 2x ODU 15G XMC3 SUB B LO | MW Swap | MW SWAP LINK 2772C-1605B WITH HUAWEI_15G_4+0_0.6M/1.2M_MS_28MHZ_512QAM_896MBPS_XMC3_SUB_A&B_LINK_4.26KM DISMANTLE EXISTING LINK IMPACTED: 2772C REUSE FREQUENCY EXISTING 2+0 | 1. INSTALL NEW 2PCS ISM8 CARD AT EXISTING IDU SLOT 3 & 4 2. INSTALL NEW 15G 0.6M MS ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM USING SLOT 3 & 4 6. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910A WITH 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MS ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM USING SLOT 3 & 4 5. PATCH TO NEW CP PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK | XMC3 | MS | 15G | 0.6 | 1.2 | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042831 |  | 2026-04-29 | 2026-04-30 | Completed | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-04-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-05-07 | 2026-05-07 | 2026-05-07 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | [7 empty] | 2026-05-07 | 2026-05-07 | 2026-05-07 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2025-10-09: 2026-05-07; 2025-10-09: 2026-05-07; 2025-10-09: 2026-05-07; 2025-11-05: 2026-05-08 | [7 empty] | GCI | SQ202604150406-GCI | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | EZRIN TASNIM BIN ABDUL GANI6798000128
K01039_HU | KG BELAT | DU00006744725 | Northern | Kedah | 6.059830 | 100.560170 | [9 empty] | TSS+AA+TI |  | 13G_28Mhz_2+0_512QAM_448M | MW Parallel Link | Install new parallel link HW MW 13G_28Mhz_2+0_512QAM_448M)_5.92km Site Impacted : 4026P/K01039 EPLA existing link 15G_2+0 and new link 13G_2+0 | NE: 1. Insert ISM8 card at slot 4 RTN01 2. Install new 13G 1.2m DP ant 3. Install new ODU 13G XMC-5D sub A_Hi 4. Config link 13G 2+0 28Mhz 512QAM 5. Config EPLA 15G_2+0 with 13G_2+0 | FE: 1. Insert new ISM8 card at slot 4 RTN06 2. Install new 13G 1.2m DP ant 3. Install new ODU 13G XMC-5D sub A_Lo 4. Config link 13G 2+0 28Mhz 512QAM 5. Config EPLA 15G_2+0 with 13G_2+0 | XMC-5D Pro | MDD | 13G | 1.2m | 1.2m | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070545-GTSB // SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042019 |  | 2026-04-21 | 2026-04-30 | Completed | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604150433-GTSB | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
4178C_HU | GrandKampar Hotel | DU00006744726 | Northern | Perak | 4.327561 | 101.145218 | [9 empty] | TSS+AA+TI |  | 18G_2+0_112M.Add new SRU2. NE_4178C. SRU2 , Sub A_Hi x1 FE_4370A. SRU2 , Sub A_Lo x1. | MW Hardware Upgrade | Existing link ZTE MW 18G_1+0_112M with OMT(DP) Hardware upgrade to ZTE MW 18G_2+0_112M.Add new SRU2. Site Impacted : 4178C. NE_4178C. 1.Reuse existing 18G_DP_0.6M 2.Reuse existing IDU NR9150 , Port 2. 3.Install new SRU2 , Sub A_Hi on H Polar. 4.Create service cross connect and PLA with existing link. 5.Traffic migrate to new config 18G_2+0_112M. 6.No decom MW link. FE_4370A. 1.Reuse existing 18G_DP_0.6M. 2.Reuse existing IDU NR9150 , Port 2. 3.Install new SRU2 , Sub A_Lo on H Polar. 4.Create service cross connect and PLA with existing link. 5.Traffic migrate to new config 18G_2+0_112M. 6.No decom MW link. | Existing link ZTE MW 18G_1+0_112M with OMT(DP) Hardware upgrade to ZTE MW 18G_2+0_112M.Add new SRU2. Site Impacted : 4178C. NE_4178C. 1.Reuse existing 18G_DP_0.6M 2.Reuse existing IDU NR9150 , Port 2 3.Install new SRU2 , Sub A_Hi on H Polar. 4.Create service cross connect and PLA with existing link. 5.Traffic migrate to new config 18G_2+0_112M. 6.No decom MW link. | Existing link ZTE MW 18G_1+0_112M with OMT(DP) Hardware upgrade to ZTE MW 18G_2+0_112M.Add new SRU2. Site Impacted : 4178C. FE_4370A. 1.Reuse existing 18G_DP_0.6M. 2.Reuse existing IDU NR9150 , Port 2. 3.Install new SRU2 , Sub A_Lo on H Polar. 4.Create service cross connect and PLA with existing link. 5.Traffic migrate to new config 18G_2+0_112M. 6.No decom MW link. | SRU2 | DP | 18G | 0.6 | 0.6 | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070545-GTSB // SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604150423-GCI | 2026-04-19 | 2026-04-19 | 2026-04-19 | 2026-04-19 | CHEONG/SENG/WAH/7018000306
4227C_AD_1 | KgTok Dik | DU00006744727 | Northern | Kedah | 5.511864 | 100.540471 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | 23G_2+0_112M_256QAM_EPLA. NE_4227C New 23G_0.6M(MAC)+OMT x1. Re-use RTN910AF(RTN04) under DU 4227C_AD. New IF cables with suitable length and type x2 RUN. New XMC_3E, Sub A_Lo x2. FE_4148A/K00224 New 23G_0.6M(MAC)+OMT x1. New RTN910AF(RTN03) under DU 4227C_AD. New IF cables with suitable length and type x2 RUN. New XMC_3E, Sub A_Hi x2. | MW Parallel Link | ****IMPORTANT NOTE: 1. PLEASE PERFORM DU AS PER SEQUENCES BELOW. 1ST DU 4227C_AD - 18G_2+0_110MHZ_256QAM_EPLA. 2ND DU 4227C_AD_1 - 23G_2+0_110MHZ_256QAM_EPLA. 2.LATER COMBINE 18G_2+0_110MHZ_256QAM_EPLA & 23G_2+0_110MHZ_256QAM_EPLA, BECOME 18G&23G_4+0_110MHZ_256QAM_EPLA**** Install new Parallel HW MW Link 4227C-4148A, 23G_2+0_112MHZ_256QAM_EPLA. Site Impacted : 4227C & 4007D. NE_4227C 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use RTN910AF(RTN04) under DU 4227C_AD. 3.Install XMC_3E, Sub A_Lo x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 port 1 & 2. 5.Build new Parallel HW MW Link 4227C-4148A, 23G_2+0_112MHZ_256QAM_EPLA. 6.Migrate traffics 4227C(DU 4227C_AD) & 4007D(DU 4227C_AD_1) via new combination HW MW Link 4227C-4148A, 18G&23G_4+0_110/112MHZ_256QAM_EPLA. FE_4148A/K00224 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use RTN910AF(RTN03) under DU 4227C_AD. 3.Install XMC_3E, Sub A_Hi x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 port 1 & 2. 5.Build new Parallel HW MW Link 4227C-4148A, 23G_2+0_112MHZ_256QAM_EPLA. 6.Later, combine DU 4227C_AD & DU 4227C_AD_1 become new HW MW Link 4227C-4148A, 18G&23G_4+0_110/112MHZ_256QAM_EPLA. 7.Migrate traffics 4227C & 4007D via new 1x 10G port of PTN/Cisco(K00224). | ****IMPORTANT NOTE: 1. PLEASE PERFORM DU AS PER SEQUENCES BELOW. 1ST DU 4227C_AD - 18G_2+0_110MHZ_256QAM_EPLA. 2ND DU 4227C_AD_1 - 23G_2+0_110MHZ_256QAM_EPLA. 2.LATER COMBINE 18G_2+0_110MHZ_256QAM_EPLA & 23G_2+0_110MHZ_256QAM_EPLA, BECOME 18G&23G_4+0_110MHZ_256QAM_EPLA**** Install new Parallel HW MW Link 4227C-4148A, 23G_2+0_112MHZ_256QAM_EPLA. Site Impacted : 4227C & 4007D. NE_4227C 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use RTN910AF(RTN04) under DU 4227C_AD. 3.Install XMC_3E, Sub A_Lo x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 port 1 & 2. 5.Build new Parallel HW MW Link 4227C-4148A, 23G_2+0_112MHZ_256QAM_EPLA. 6.Migrate traffics 4227C(DU 4227C_AD) & 4007D(DU 4227C_AD_1) via new combination HW MW Link 4227C-4148A, 18G&23G_4+0_110/112MHZ_256QAM_EPLA. | ****IMPORTANT NOTE: 1. PLEASE PERFORM DU AS PER SEQUENCES BELOW. 1ST DU 4227C_AD - 18G_2+0_110MHZ_256QAM_EPLA. 2ND DU 4227C_AD_1 - 23G_2+0_110MHZ_256QAM_EPLA. 2.LATER COMBINE 18G_2+0_110MHZ_256QAM_EPLA & 23G_2+0_110MHZ_256QAM_EPLA, BECOME 18G&23G_4+0_110MHZ_256QAM_EPLA**** Install new Parallel HW MW Link 4227C-4148A, 23G_2+0_112MHZ_256QAM_EPLA. Site Impacted : 4227C & 4007D. FE_4148A/K00224 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use RTN910AF(RTN03) under DU 4227C_AD. 3.Install XMC_3E, Sub A_Hi x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 port 1 & 2. 5.Build new Parallel HW MW Link 4227C-4148A, 23G_2+0_112MHZ_256QAM_EPLA. 6.Later, combine DU 4227C_AD & DU 4227C_AD_1 become new HW MW Link 4227C-4148A, 18G&23G_4+0_110/112MHZ_256QAM_EPLA. 7.Migrate traffics 4227C & 4007D via new 1x 10G port of PTN/Cisco(K00224). | XMC_3E | MAC | 23G | 23G_0.6M(MAC)+OMT x1 | 23G_0.6M(MAC)+OMT x1 | GCI | SQ202605050374-GCI | GCI | SQ202604290760-GCI // SQ202604290770-GCI |  |  | Ongoing | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042149 |  | 2026-04-22 | 2026-04-22 | Completed | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-05-02 | 2026-04-23 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-04-23 | 2026-05-02 | 2026-04-23 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-30 | 2026-04-23 | 2026-05-02 | 2026-04-23 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2025-10-09: 2026-04-23; 2025-10-09: 2026-05-02; 2025-10-09: 2026-04-23; 2025-11-05: 2026-04-23 | [7 empty] | GTSB | SQ202604150433-GTSB
2437A_HU | Lembah Beringin (MAXIS) | DU00005403462 | Central | Selangor | 3.575040 | 101.524963 |  | APR 25 |  | APR 25 | DO | Doable, just waiting material | ZTE | 00. Integrated/RFS Done | 21/4/2025: MAXIS - Tower - NE site 2437A Lembah Beringin (MAXIS), EDOTCO(M)-CSU - 60M 3 Legged Tower - FE site 1069A Lembah Beringin | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X ISM8 CARD 2X RTN910 2X 23G 0.6M MDD ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO | MW Swap | MW SWAP LINK 2437A-1069A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB_A_1.31KM IMPACTED: 2437A DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202505020369-GTSB | GTSB | SQ202504240805-GTSB // SQ202504240806-GTSB | 2025-06-25 | 2025-06-25 | Completed | 2025-04-24 | 2025-06-09 | 2025-06-09 | 2025-06-09 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-10 | 2025-06-24 | 2025-06-10 | 2025-06-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052162 |  | 2025-05-22 | 2025-05-27 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-08 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-08 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-29 | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-10 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-05-29 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202507080560-GTSB
1084E_LOS | Menara CIMB UOB | DU00004463318 | Central | Kuala Lumpur | 3.150559 | 101.695710 | WK07 | FEB 25 | WK07 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 15/2/2025 : Cutover done 8/2/2025 : FE installation and patching complete, pending install NE site due to waiting new CRQ approval 6/2/2025 : FE installation 30% complete, pending install NE due to access only 8PM to 10PM 6/1/2025 : Digi OB - Enterprise driven site - NE site 1084E Menara CIMB UOB, Digi OB - 3M RT - Wall Mounted Pole - FE site 1261A Bangunan Kuasa | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_1084E 23G_SP_0.6m(MAC) x1. RTN910A x1. XMC_3E-1+0 ,Sub A_Lo x1. FE_1261A 23G_SP_0.6m(MAC) x1. RTN910A x1. XMC_3E-1+0 ,Sub A_Hi x1. RTN910A x1 | MW New Link / Reroute | Link reroute to new FE 1261A with 23G_1+0_112M due to LOS block and for 3rd leg Fiber protection. NE_1084E 1.Install 23G_SP_0.6m(MAC). 2.Install new RTN910A,7_ISM8-1+0. 3.Install new XMC_3E-1+0 ,Sub A_Lo. 4.Create EPLA and service cross connect. 5.Decom existing MW link (1084E - 1253A) . FE_1261A 1.Install 23G_SP_0.6m(MAC). 2.Install new RTN910A,7_ISM8-1+0. 3.Install new XMC_3E-1+0 ,Sub A_Hi. 4.Install new RTN910A, 7_ISM8-1+0. 5.Create new In Band DCN and service cross connect. 6.Decom existing MW link (1253A-1084E). | Link reroute to new FE 1261A with 23G_1+0_112M due to LOS block and for 3rd leg Fiber protection. NE_1084E 1.Install 23G_SP_0.6m(MAC). 2.Install new RTN910A,7_ISM8-1+0. 3.Install new XMC_3E-1+0 ,Sub A_Lo. 4.Create EPLA and service cross connect. 5.Decom existing MW link (1084E - 1253A) . | Link reroute to new FE 1261A with 23G_1+0_112M due to LOS block and for 3rd leg Fiber protection. FE_1261A 1.Install 23G_SP_0.6m(MAC). 2.Install new RTN910A,7_ISM8-1+0. 3.Install new XMC_3E-1+0 ,Sub A_Hi. 4.Install new RTN910A, 7_ISM8-1+0. 5.Create new In Band DCN and service cross connect. 6.Decom existing MW link (1253A-1084E). | XMC_3E | MAC | 21504.0000 | 0.6 | 0.6 | YPTT | SQ202411190745-YPTT | YPTT | SQ202411250784-YPTT // SQ202504160577-YPTT // SQ202504260171-YPTT |  |  | Ongoing | 2025-03-11 | 2025-03-31 | 2025-03-11 | 2025-03-11 | MOHD//SHAHREEZAN BIN RAZALI/6794000119 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-11 | 2025-03-11 | 2025-03-11 | 2025-03-11 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24112534 |  | 2024-11-26 | 2024-12-30 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2024-12-30 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-05 | 2025-02-28 | 2025-02-05 | 2025-06-05 | JOSEF/BIN/ABSARI/6794000120 | YPTT TI | 2025-02-05 | 2025-02-28 | 2025-02-05 | 2025-06-05 | JOSEF/BIN/ABSARI/6794000120 | YPTT TI | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-15 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-02-05 | 2025-02-28 | 2025-02-05 | 2025-03-04 | JOSEF/BIN/ABSARI/6794000120 | 2025-02-05 | 2025-02-28 | 2025-02-05 | 2025-02-06 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358
K00468_LOS | K002A_K00468OD_MRSMBALING | DU00005595151 | Northern | Kedah | 5.639743 | 100.909037 | [7 empty] | 00. Integrated/RFS Done | 21/07: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M_EPLA NE_K00468 New 18G_0.6M(MDD) x1. New RTN910A x1. New XMC_5D, Sub A_Hi x1. FE_K00282 New 18G_0.6M(MDD) x1. New ISM8 x1. New XMC_5D, Sub A_Lo x1. | MW New Link / Reroute | Existing SM MW Link 18G_1+0_112M_512QAM. Install new HW MW Link 18G_2+0_56M_512QAM_EPLA. Decom existing SM MW Link ID NT05360(K00468-K00159) 18G_1+0_112M_512QAM. Site Impacted : K00468. NE_K00468 1.Install new 18G_0.6M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub A_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of new RTN910A(RTN01). 6.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 7.Request new xD vlan services from ZTE IPRAN Team. 8.Migrate traffic to new link. 9.Decom existing SM MW Link ID NT05360(K00468-K00159) 18G_1+0_112M_512QAM. FE_K00282 1.Install new 18G_0.6M(MDD) x1. 2.Use existing build in ISM8 slot 7(port 1 &2) of existing RTN910A(RTN05). 3.Insert new 1xISM8 into slot 04 of existing RTN910A(RTN05) for uplink(K00282-4950B) use purposes. Configure it. 4.Install new 1x XMC_5D, Sub A_Lo. Configure it. 5.Request new xD vlan services from ZTE IPRAN Team. 6.Migrate traffic K00468 to the existing port at IBeam(CP 4950B) similar with existing traffics(K00282). 7.Decom existing SM MW Link ID NT05360(K00468-K00159) 18G_1+0_112M_512QAM. | Existing SM MW Link 18G_1+0_112M_512QAM. Install new HW MW Link 18G_2+0_56M_512QAM_EPLA. Decom existing SM MW Link ID NT05360(K00468-K00159) 18G_1+0_112M_512QAM. Site Impacted : K00468. NE_K00468 1.Install new 18G_0.6M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub A_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of new RTN910A(RTN01). 6.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 7.Request new xD vlan services from ZTE IPRAN Team. 8.Migrate traffic to new link. 9.Decom existing SM MW Link ID NT05360(K00468-K00159) 18G_1+0_112M_512QAM. | Existing SM MW Link 18G_1+0_112M_512QAM. Install new HW MW Link 18G_2+0_56M_512QAM_EPLA. Decom existing SM MW Link ID NT05360(K00468-K00159) 18G_1+0_112M_512QAM. Site Impacted : K00468. FE_K00282 1.Install new 18G_0.6M(MDD) x1. 2.Use existing build in ISM8 slot 7(port 1 &2) of existing RTN910A(RTN05). 3.Insert new 1xISM8 into slot 04 of existing RTN910A(RTN05) for uplink(K00282-4950B) use purposes. Configure it. 4.Install new 1x XMC_5D, Sub A_Lo. Configure it. 5.Request new xD vlan services from ZTE IPRAN Team. 6.Migrate traffic K00468 to the existing port at IBeam(CP 4950B) similar with existing traffics(K00282). 7.Decom existing SM MW Link ID NT05360(K00468-K00159) 18G_1+0_112M_512QAM. | XMC_5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_0.6M(MDD) x1. | CCSMY | SQ202510010663-CCS | CCSMY | SQ202506130245-CCS // SQ202506130250-CCS |  |  | Ongoing | 2026-01-14 | 2026-01-29 | 2026-01-14 | 2026-01-14 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250605B3 |  | 2025-06-06 | 2025-06-10 | Completed | 2025-06-05 | 2025-06-06 | 2025-06-05 | 2025-06-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-12 | 2025-06-30 | 2025-06-12 |  | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | CCS TI | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2025-06-12 | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | CCS TI | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-23 | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2026-03-31 | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2025-07-21 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB
7443A_AD | Nabawan | DU00005595152 | Sabah | Sabah | 5.042950 | 116.429456 |  |  |  |  | Pending TSS | MwAntenna HW-15G_1.2M_Dual Polarization_A15D12MDD-3NX |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_1.2/1.2_MDD_512QAM 4xISM8 | MW Swap | MW SWAP 7443A-7476A EXISITING LINK 18G_1+0 WITH 15G_4+0_1.2/1.2_MDD_512QAM_SB A | MW SWAP 7443A-7476A EXISITING LINK 18G_1+0 WITH 15G_4+0_1.2/1.2_MDD_512QAM_SB A NE: 1. reuse exisitng RTN910A_RTN01. 2. Install new 2xISM8 at slot 3 and 4. 3. Install new 15G_XMC_5D_SB A. 4. Install antenna 15G_1.2_MDD. 5. Configure 15G_4+0_1.2/1.2_512QAM_CA. 6. Dismantle 18G_1+0 link. | MW SWAP 7443A-7476A EXISITING LINK 18G_1+0 WITH 15G_4+0_1.2/1.2_MDD_512QAM_SB A FE: 1. reuse exisitng RTN910A_RTN04. 2. Install new 2xISM8 at slot 3 and 4. 3. Install new 15G_XMC_5D_SB A. 4. Install antenna 15G_1.2_MDD. 5. Configure 15G_4+0_1.2/1.2_512QAM_CA. 6. Dismantle 18G_1+0 link. 7. Create 1+1 LAG | XMC-5D_ SB A |  | 15G | 1.2 | 1.2 | NR services | SQ202510070049-NR Services | NR services | SQ202507290140-NR Services // SQ202507290144-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-10-05 | 2025-10-05 | 2025-10-05 | 2025-10-05 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072279 |  | 2025-07-23 | 2025-08-20 | Completed | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-08-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-02 | 2025-10-04 | 2025-10-02 | 2025-10-02 | WILFRED BALANG7167000026 | NR Service TI | 2025-10-02 | 2025-10-04 | 2025-10-02 | 2025-10-02 | WILFRED BALANG7167000026 | NR Service TI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-26 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-13 | WILFRED BALANG7167000026 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505280702-GTSB | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | HSU//MYET CHAE/6799000011
1246H_AD | 99 Speedmart TMN SRI PUTRA | DU00005595153 | Central | Selangor | 3.249105 | 101.558187 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | 1246H reroute to xC backhaul due to uplink HW MW vandalized and swap the existing NLOS equipment suspicious NLOS equipment having a problem. Site Impacted : 1246H. NE_1246H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio. FE_2481A/B00476. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.Traffic migrate to new route FE site and with new NLOS. 6.ETH cable patching to Cisco Fiber Port. 7.Decom existing NLOS Radio | 1246H reroute to xC backhaul due to uplink HW MW vandalized and swap the existing NLOS equipment suspicious NLOS equipment having a problem. Site Impacted : 1246H. NE_1246H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio. | MW IDU PATCHING NLOS AT FE 2481A TO B00476 TO USE TM LL1246H reroute to xC backhaul due to uplink HW MW vandalized and swap the existing NLOS equipment suspicious NLOS equipment having a problem. 1246H reroute to xC backhaul due to uplink HW MW vandalized and swap the existing NLOS equipment suspicious NLOS equipment having a problem. Site Impacted : 1246H. FE_2481A/B00476. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.Traffic migrate to new route FE site and with new NLOS. 6.ETH cable patching to Cisco Fiber Port. 7.Decom existing NLOS Radio | [5 empty] | GTSB | SQ202506120231-GTSB | GTSB | SQ202506120218-GTSB // SQ202506120222-GTSB | 2025-12-04 | 2025-12-03 | Completed | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-12 | 2025-08-13 | 2025-08-12 | 2025-08-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250611AZ |  | 2025-06-12 | 2025-06-12 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2025-06-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2025-06-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-14 | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2025-06-26 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-06-12 | 2025-06-30 | 2025-06-12 | 2025-06-13 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050638-GCI | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
S00589_AD | S106A_S00589OD_CB_PULAUMABUL | DU00006721010 | Sabah | Sabah | 4.244894 | 118.631061 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4(1+1 SD)_28M_256QAM_CA NE_7032K/S00589 New 13G_1.2M(MDD)+Dual Coupler x2. New RTN950AF x1. New ISM8 x4. New XMC_5D Pro, Sub A&B_Lo x4. New IF cables with suitable length and type x8 RUN. New CAT6 cable x1. FE_S01445 New 13G_1.2M(MDD)+Dual Coupler x2. New RTN950AF x1. New ISM8 x4. New XMC_5D Pro, Sub A&B_Hi x4. New IF cables with suitable length and type x8 RUN. New CAT6 cable x1. | MW Swap | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.AT S01445 HAVING 1X EB SITES WHICH IS ENT MABUL/ENT SEAVENTURE. BE AWARE TASK PERFORM AT S01445.**** Existing HW MW Link S00589-S01445. Swap existing with new HW MW Link S00589-S01445, 13G_4(1+1 SD)_28M_256QAM_CA. Later, decom existing HW MW Link S00589-S01445. Site Impacted : 7032K/S00589 & S01172. NE_7032K/S00589 1.Install new 13G_1.2M(MDD)+Dual Coupler x2. 2.Install new RTN950A(RTN01) and insert new ISM8 x4 into slot 03, 04, 05 & 06. 3.Install new XMC_5D Pro, Sub A&B_Lo x4. 4.Lay new IF cables from new XMC_5D Pro to new RTN950A(RTN01) as per below: - Slot 03 Port 1 to ODU Sub Band B Vertical Main Antenna and Port 2 to ODU Sub Band B Vertical Diversity Antenna. - Slot 05 Port 1 to ODU Sub Band A Vertical Main Antenna and Port 2 to ODU Sub Band A Vertical Diversity Antenna. - Slot 04 Port 1 to ODU Sub Band B Horizontal Main Antenna and Port 2 to ODU Sub Band B Horizontal Diversity Antenna. - Slot 06 Port 1 to ODU Sub Band A Horizontal Main Antenna and Port 2 to ODU Sub Band A Horizontal Diversity Antenna. 4.Build new HW MW Link S00589-S01445, 13G_4(1+1 SD)_28M_256QAM_CA. 5.Enable port 17-EG6-1 of new RTN950A(RTN01). 6.Perform cascading between port 17-EG6-1 of new RTN950A(RTN01) and port 7-EM4T-1 of existing RTN910(NEID 88-13152). 7.Re-use existing xC Vlan DCN & Vlan Services. 8.Migrate traffics 7032K/S00589 & S01172 to new HW MW Link S00589-S01445, 13G_4(1+1 SD)_28M_256QAM_CA. 9.Later, decom existing HW MW Link S00589-S01445. FE_S01445 1.Install new 13G_1.2M(MDD)+Dual Coupler x2. 2.Install new RTN950A(RTN01) and insert new ISM8 x4 into slot 03, 04, 05 & 06. 3.Install new XMC_5D Pro, Sub A&B_Hi x4. 4.Lay new IF cables from new XMC_5D Pro to new RTN950A(RTN01) as per below: - Slot 03 Port 1 to ODU Sub Band B Vertical Main Antenna and Port 2 to ODU Sub Band B Vertical Diversity Antenna. - Slot 05 Port 1 to ODU Sub Band A Vertical Main Antenna and Port 2 to ODU Sub Band A Vertical Diversity Antenna. - Slot 04 Port 1 to ODU Sub Band B Horizontal Main Antenna and Port 2 to ODU Sub Band B Horizontal Diversity Antenna. - Slot 06 Port 1 to ODU Sub Band A Horizontal Main Antenna and Port 2 to ODU Sub Band A Horizontal Diversity Antenna. 4.Build new HW MW Link S00589-S01445, 13G_4(1+1 SD)_28M_256QAM_CA. 5.Enable port 17-EG6-1 of new RTN950A(RTN01). 6.Perform patching port 17-EG6-1 of new RTN950A(RTN01) and port 8-EM6-3 of existing RTN910A(NEID 88-28554). 7.Re-use existing xC Vlan DCN & Vlan Services. 8.Migrate traffics 7032K/S00589 & S01172 to existing port at PTN/Cisco(S00250). 9.Later, decom existing HW MW Link S00589-S01445. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.AT S01445 HAVING 1X EB SITES WHICH IS ENT MABUL/ENT SEAVENTURE. BE AWARE TASK PERFORM AT S01445.**** Existing HW MW Link S00589-S01445. Swap existing with new HW MW Link S00589-S01445, 13G_4(1+1 SD)_28M_256QAM_CA. Later, decom existing HW MW Link S00589-S01445. Site Impacted : 7032K/S00589 & S01172. NE_7032K/S00589 1.Install new 13G_1.2M(MDD)+Dual Coupler x2. 2.Install new RTN950A(RTN01) and insert new ISM8 x4 into slot 03, 04, 05 & 06. 3.Install new XMC_5D Pro, Sub A&B_Lo x4. 4.Lay new IF cables from new XMC_5D Pro to new RTN950A(RTN01) as per below: - Slot 03 Port 1 to ODU Sub Band B Vertical Main Antenna and Port 2 to ODU Sub Band B Vertical Diversity Antenna. - Slot 05 Port 1 to ODU Sub Band A Vertical Main Antenna and Port 2 to ODU Sub Band A Vertical Diversity Antenna. - Slot 04 Port 1 to ODU Sub Band B Horizontal Main Antenna and Port 2 to ODU Sub Band B Horizontal Diversity Antenna. - Slot 06 Port 1 to ODU Sub Band A Horizontal Main Antenna and Port 2 to ODU Sub Band A Horizontal Diversity Antenna. 4.Build new HW MW Link S00589-S01445, 13G_4(1+1 SD)_28M_256QAM_CA. 5.Enable port 17-EG6-1 of new RTN950A(RTN01). 6.Perform cascading between port 17-EG6-1 of new RTN950A(RTN01) and port 7-EM4T-1 of existing RTN910(NEID 88-13152). 7.Re-use existing xC Vlan DCN & Vlan Services. 8.Migrate traffics 7032K/S00589 & S01172 to new HW MW Link S00589-S01445, 13G_4(1+1 SD)_28M_256QAM_CA. 9.Later, decom existing HW MW Link S00589-S01445. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.AT S01445 HAVING 1X EB SITES WHICH IS ENT MABUL/ENT SEAVENTURE. BE AWARE TASK PERFORM AT S01445.**** Existing HW MW Link S00589-S01445. Swap existing with new HW MW Link S00589-S01445, 13G_4(1+1 SD)_28M_256QAM_CA. Later, decom existing HW MW Link S00589-S01445. Site Impacted : 7032K/S00589 & S01172. FE_S01445 1.Install new 13G_1.2M(MDD)+Dual Coupler x2. 2.Install new RTN950A(RTN01) and insert new ISM8 x4 into slot 03, 04, 05 & 06. 3.Install new XMC_5D Pro, Sub A&B_Hi x4. 4.Lay new IF cables from new XMC_5D Pro to new RTN950A(RTN01) as per below: - Slot 03 Port 1 to ODU Sub Band B Vertical Main Antenna and Port 2 to ODU Sub Band B Vertical Diversity Antenna. - Slot 05 Port 1 to ODU Sub Band A Vertical Main Antenna and Port 2 to ODU Sub Band A Vertical Diversity Antenna. - Slot 04 Port 1 to ODU Sub Band B Horizontal Main Antenna and Port 2 to ODU Sub Band B Horizontal Diversity Antenna. - Slot 06 Port 1 to ODU Sub Band A Horizontal Main Antenna and Port 2 to ODU Sub Band A Horizontal Diversity Antenna. 4.Build new HW MW Link S00589-S01445, 13G_4(1+1 SD)_28M_256QAM_CA. 5.Enable port 17-EG6-1 of new RTN950A(RTN01). 6.Perform patching port 17-EG6-1 of new RTN950A(RTN01) and port 8-EM6-3 of existing RTN910A(NEID 88-28554). 7.Re-use existing xC Vlan DCN & Vlan Services. 8.Migrate traffics 7032K/S00589 & S01172 to existing port at PTN/Cisco(S00250). 9.Later, decom existing HW MW Link S00589-S01445. | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD)+Dual Coupler x2 | 13G_1.2M(MDD)+Dual Coupler x2 | GCI |  | GCI | SQ202604200224-GCI // SQ202604200228-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040844 |  | 2026-04-09 | 2026-04-09 | Completed | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-12 | 2026-04-30 | 2026-04-12 | 2026-04-20 | Konli//Bernabas/6000043571 | GCI TI | 2026-04-12 | 2026-04-30 | 2026-04-12 | 2026-05-05 | Konli//Bernabas/6000043571 | GCI TI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-21 | 2026-04-12 | 2026-04-30 | 2026-04-12 |  | Konli//Bernabas/6000043571 | 2025-10-01: 2026-04-12; 2025-10-01: 2026-04-30; 2025-10-01: 2026-04-12; 2025-10-01: 2026-04-13 | [7 empty] | GTSB | SQ202604100702-GTSB
Test 2 | Test 2 | DU00006734528 | Central | Selangor | 3.068738 | 101.568935 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [42 empty] | 2025-08-19
1550H_LOS | Jalan MetroPerdana Timur 2 | DU00006753374 | Central | Kuala Lumpur | 3.214466 | 101.644911 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | RTN 510 (NLOS) NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | NLOS reroute to new FE 1256A due to existing NLOS LOS Block. Site Impacted : 1550H NE_1550H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new NLOS RTN510 and new FE routing. 6.Decom existing NLOS radio (1150H-NLOS-1183B). FE_1256A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.Enable GE1 , ETH patching to existing 1256A_RTN01_GE2 ( ID : 26645). 6.Traffic migrate to new NLOS RTN510 and New FE routing.. 7.Decom existing NLOS Radio (1183B-NLOS-1150H). | NLOS reroute to new FE 1256A due to existing NLOS LOS Block. Site Impacted : 1550H NE_1550H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new NLOS RTN510 and new FE routing. 6.Decom existing NLOS radio (1150H-NLOS-1183B). | NLOS reroute to new FE 1256A due to existing NLOS LOS Block. Site Impacted : 1550H FE_1256A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.Enable GE1 , ETH patching to existing 1256A_RTN01_GE2 ( ID : 26645). 6.Traffic migrate to new NLOS RTN510 and New FE routing.. 7.Decom existing NLOS Radio (1183B-NLOS-1150H). | [5 empty] | GTSB | SQ202604240944-GTSB | MTK | SQ202604280454-MTK |  |  | Ongoing | 2026-04-23 | 2026-05-07 | 2026-04-23 | 2026-04-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-05-07 | 2026-04-23 | 2026-04-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-04-24 | 2026-04-23 | 2026-04-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042026 |  | 2026-04-21 | 2026-04-21 | Completed | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-22 | 2026-04-30 | 2026-04-24 | 2026-04-24 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2026-04-22 | 2026-04-30 |  |  | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-02 | 2026-04-22 | 2026-04-30 |  |  | RIDHUAN//BIN MANSOR/8225000011 | 2025-10-01: 2026-04-22; 2025-10-01: 2026-04-30; 2025-10-01: 2026-04-23; 2025-10-01: 2026-04-23 | [7 empty] | GCI | SQ202604200052-GCI | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | CHEONG/SENG/WAH/7018000306
B01317_HU | LUBUK PUSING | DU00005479162 | Central | Selangor | 3.763111 | 101.084111 |  |  |  | JUN 25 |  |  |  | 00. Integrated/RFS Done | 05/6: CO done | TSS+TI | L1+ATP+PAC | 1x CAT6 cable(suitable length) | BBU Patching | Existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965). Existing HW Link 15G_4+0_28MHz_512QAM_CA&EPLA(1651K/B01317(RTN910-RTN01) - 1812K/B00695(RTN03)). **Do not decom existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965) as it still carry child site A00835(via existing MW Link ID CT10986).** NE_B01317/1651K 1.Enable port 8-EM6-1 of existing HW Link 15G_4+0_28MHz_512QAM_CA&EPLA(1651K/B01317(RTN910-RTN01) - 1812K/B00695(RTN03)). 2.Shifting BBU from port LAN1(double check) of existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965) to port 8-EM6-1 of existing HW Link 15G_4+0_28MHz_512QAM_CA&EPLA(1651K/B01317(RTN910-RTN01) - 1812K/B00695(RTN03)). 3.Request new vlan services for BBU B01317/1651K from ZTE IPRAN team. 4.Migrate B01317/1651K from ZTE IPRAN team in which diverting from xC to xD. Configure it. 5.Do not decom existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965) as it still carry child site A00835(via existing MW Link ID CT10986). FE_B00695/1812K 1.Request new vlan services for BBU B01317/1651K from ZTE IPRAN team. 2.Migrate B01317/1651K from ZTE IPRAN team in which diverting from xC to xD. Configure it. 3.Do not decom existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965) as it still carry child site A00835(via existing MW Link ID CT10986). | Existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965). Existing HW Link 15G_4+0_28MHz_512QAM_CA&EPLA(1651K/B01317(RTN910-RTN01) - 1812K/B00695(RTN03)). **Do not decom existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965) as it still carry child site A00835(via existing MW Link ID CT10986).** NE_B01317/1651K 1.Enable port 8-EM6-1 of existing HW Link 15G_4+0_28MHz_512QAM_CA&EPLA(1651K/B01317(RTN910-RTN01) - 1812K/B00695(RTN03)). 2.Shifting BBU from port LAN1(double check) of existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965) to port 8-EM6-1 of existing HW Link 15G_4+0_28MHz_512QAM_CA&EPLA(1651K/B01317(RTN910-RTN01) - 1812K/B00695(RTN03)). 3.Request new vlan services for BBU B01317/1651K from ZTE IPRAN team. 4.Migrate B01317/1651K from ZTE IPRAN team in which diverting from xC to xD. Configure it. 5.Do not decom existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965) as it still carry child site A00835(via existing MW Link ID CT10986). | Existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965). Existing HW Link 15G_4+0_28MHz_512QAM_CA&EPLA(1651K/B01317(RTN910-RTN01) - 1812K/B00695(RTN03)). **Do not decom existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965) as it still carry child site A00835(via existing MW Link ID CT10986).** FE_B00695/1812K 1.Request new vlan services for BBU B01317/1651K from ZTE IPRAN team. 2.Migrate B01317/1651K from ZTE IPRAN team in which diverting from xC to xD. Configure it. 3.Do not decom existing SM Link 13G_4+0_28MHz_1024QAM_LAG(CT10965) as it still carry child site A00835(via existing MW Link ID CT10986). | [5 empty] | Magicell | SQ202506050549-Magicell | Magicell | SQ202505300201-Magicell // SQ202505300201-Magicell | 2025-12-02 | 2025-11-26 | Completed | 2025-06-05 | 2025-06-06 | 2025-06-04 | 2025-07-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-13 | 2025-08-04 | 2025-08-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250520AJ |  | 2025-05-21 | 2025-05-23 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-04 | 2026-06-22 | 2025-06-04 | 2025-07-11 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | 2025-06-04 | 2026-06-22 | 2025-06-04 | 2025-07-11 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-05 | 2025-06-04 | 2026-06-22 | 2025-06-04 | 2025-07-11 | UMI NOR PADZILAH BINTI PAUZI7018000120 | 2025-10-01: 2025-06-04; 2025-10-01: 2026-06-22; 2025-10-01: 2025-06-04; 2025-10-01: 2025-06-05 |  |  | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202505070162-GTSB
7684B_HU | Kg Simunul Semporna | DU00005479163 | Sabah | Sabah | 4.467961 | 118.614498 |  |  |  |  | Pending TSS |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_1+0_0.6/0.6_SP_XMC-3E_SB A 2XISM8 | MW Parallel Link | MW PARALLEL LINK 7684B-7209A 18G_1+0_0.6/0.6_SP_XMC-3E_SB A_EPLA WITN EXISTING 23G LINK. | MW PARALLEL LINK 7684B-7209A 18G_1+0_0.6/0.6_SP_XMC-3E_SB A NE: 1. Reuse exisiting RTN910A_RTN_01 2. Install new ISM8 at slot 3. 3. Install new 18G_XMC-3E_SB_A. 4. Install new antenna 18G_0.6SP. 5. Configure 18G_1+0_0.6/0.6_512QAM_110Mhz_EPLA with exisitng 23G link. | MW PARALLEL LINK 7684B-7209A 18G_1+0_0.6/0.6_SP_XMC-3E_SB A FE: 1. Reuse exisiting RTN910A_RTN_08 2. Install new ISM8 at slot 4. 3. Install new 18G_XMC-3E_SB A. 4. Install new antenna 18G_0.6SP. 5. Configure 18G_1+0_0.6/0.6_512QAM_110Mhz_EPLA with exisitng 23G link. | XMC-3E | SP | 18G | 0.6 | 0.6 | Seri Pancar | SQ202506230417-Seri Pancar | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services | 2025-07-04 | 2025-07-02 | Completed | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-23 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-18 | 2025-06-27 | 2025-06-25 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-04 | 2025-07-02 | 2025-07-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090210 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-09 | 2025-10-09 | 2025-09-09 | 2025-09-10 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-09-09 | 2025-10-09 | 2025-09-09 | 2025-09-13 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-12 | 2025-09-09 | 2025-10-09 | 2025-09-09 | 2025-10-09 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2025-10-01: 2025-09-09; 2025-10-01: 2025-10-09; 2025-10-01: 2025-09-09; 2025-10-01: 2025-09-10 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505020434-GTSB | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | HSU//MYET CHAE/6799000011
A00314_HU | A038A_A00314OD_CB_TMMALIMNAWAR | DU00005479164 | Northern | Perak | 4.353600 | 101.117700 |  |  |  |  | 30/1: plan on week 6 4/2: decom material at site FE(no key) |  |  | 00. Integrated/RFS Done | 23/07: Pending access TM | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_A00314 New 23G_SP_1.2M(MAC) x1. New RTN910A x1. New XMC_3E, Sub B_Hi x1. FE_4918B New 23G_SP_1.2M(MAC) x1. New RTN910A x1. New XMC_3E, Sub B_Lo x1. | MW Swap | Link Existing SM 18G_1+0_56M. Swap existing SM link to new HW 23G_1+0_112M_512QAM. Site Impacted : A00314. NE_A00314 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN01). Configure it. 3.Install new XMC_3E, Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A(RTN01). 6.Migrate traffic to new link in which BBU A00314 will be patching to port 8-EM6-1 of RTN910A(RTN01). Configure it. 7.Decom existing SM MW link A00314-A00155, if no other traffic backhauled. FE_4918B/A00155 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN02). Configure it. 3.Install new XMC_3E, Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A(RTN02). 6.Request and enable new port of Cisco/PTN at A00155. 7.Migrate traffic to xC A00155 by patching port 8-EM6-1 of new RTN910A(RTN02) to new port of Cisco/PTN and request new xC vlan services from ZTE IPRAN Team. Configure it. 8.Decom existing SM MW link A00314-A00155, if no other traffic backhauled. | Link Existing SM 18G_1+0_56M. Swap existing SM link to new HW 23G_1+0_112M_512QAM. Site Impacted : A00314. NE_A00314 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN01). Configure it. 3.Install new XMC_3E, Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A(RTN01). 6.Migrate traffic to new link in which BBU A00314 will be patching to port 8-EM6-1 of RTN910A(RTN01). Configure it. 7.Decom existing SM MW link A00314-A00155, if no other traffic backhauled. | Link Existing SM 18G_1+0_56M. Swap existing SM link to new HW 23G_1+0_112M_512QAM. Site Impacted : A00314. FE_4918B/A00155 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN02). Configure it. 3.Install new XMC_3E, Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A(RTN02). 6.Request and enable new port of Cisco/PTN at A00155. 7.Migrate traffic to xC A00155 by patching port 8-EM6-1 of new RTN910A(RTN02) to new port of Cisco/PTN and request new xC vlan services from ZTE IPRAN Team. Configure it. 8.Decom existing SM MW link A00314-A00155, if no other traffic backhauled. | XMC_3E | MAC | 23G | 23G_SP_1.2M(MAC) x1. | 23G_SP_1.2M(MAC) x1. | GCI | SQ202602090112-GCI | GCI | SQ202508270947-GCI // SQ202508270956-GCI // SQ202603270199-GCI | 2026-03-23 | 2026-03-17 | Completed | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-12 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-16 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052828 |  | 2025-05-29 | 2025-05-31 | Completed | 2025-05-28 | 2025-05-29 | 2025-05-28 | 2025-05-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-04 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-04 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-04 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-24 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-04 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202507080632-GTSB
4106B_HU | Taman Alma Jaya | DU00005479165 | Northern | Penang | 5.313959 | 100.463924 |  |  |  |  | TI IN PLAN | ZTE |  | 00. Integrated/RFS Done | 26/06: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 1+0 0.6/0.6 112MHz SUB A NE 4106D 1) 1 x 23G XMC3 sub A Hi support 112MHz FE 4215A 4) 1 x 23G XMC3 sub A Lo support 112MHz | MW Hardware Upgrade | MW Hardware Upgrade 4106B to 4215A with HW 23G 1+0 112MHz 0.6m/0.6m 2.08km Antenna realignment at both NE and FE required if RSL not meet calculated Link Budget expectations NE 4106B TAMAN ALMA JAYA 1. Hardware Upgrade ODU XMC-3 Support 112MHz 23G Sub A 2. Reconfigure 112MHz Frequency 3. Antenna realignment at both NE and FE required if RSL not meet calculated Link Budget expectations FE 4215A ALMA KG KIJANG 2 1. Hardware Upgrade ODU XMC-3 Support 112MHz 23G Sub A 2. Reconfigure 112MHz Frequency 3. Antenna realignment at both NE and FE required if RSL not meet calculated Link Budget expectations | NE 4106B TAMAN ALMA JAYA 1. Hardware Upgrade ODU XMC-3 Support 112MHz 23G Sub A 2. Reconfigure 112MHz Frequency 3. Antenna realignment at both NE and FE required if RSL not meet calculated Link Budget expectations | FE 4215A ALMA KG KIJANG 2 1. Hardware Upgrade ODU XMC-3 Support 112MHz 23G Sub A 2. Reconfigure 112MHz Frequency 3. Antenna realignment at both NE and FE required if RSL not meet calculated Link Budget expectations | XMC3 | MAC SP | 23G | 0.6m | 0.6m | GTSB | SQ202506110171-GTSB | GTSB | SQ202506110176-GTSB // SQ202506110181-GTSB | 2025-08-14 | 2025-08-14 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-08-04 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052036 |  | 2025-05-21 | 2025-06-12 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-06-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | AMIRUL AFIF BIN MANSOR6000002563 | GTSB TI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-07-21 | ALI RAZA AKBAR ALI6799000298 | GTSB TI | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-26 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-07-21 | ALI RAZA AKBAR ALI6799000298 | 2025-10-01: 2025-06-24; 2025-10-01: 2025-06-24; 2025-10-01: 2025-06-24; 2025-10-01: 2025-06-24 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
4109B-4211A | Simpang Empat RT | DU00003430933 | Northern | Penang | 5.272089 | 100.477203 | WK07 | FEB 24 | WK09 | MAR 24 | RFS | Pending TX OPS update EPMS | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 23G 0.6M SP ANTENNA 1X 23G 112MHZ XMC-3 SUB A HI 1X 23G 112MHZ XMC-3 SUB A LO | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/6 NE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M SP ANTENNA 3. INSTALL NEW 23G 112MHZ XMC-3 SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. DISMANTLE EXISTING LINK FE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M SP ANTENNA 3. INSTALL NEW 23G 112MHZ XMC-3 SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. PATCH NEW RTN 910A TO NEW CP PORT 5. DISMANTLE EXISTING LINK EXCEPT IDU | [7 empty] | CCSMY | SQ202402220007-CCS | CCSMY | SQ202402220008-CCS | 2024-08-21 | 2024-08-21 | Completed | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  |  | Unassigned | Completed |  | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-22 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022022 |  | 2024-02-21 | 2024-02-26 | Completed | 2024-02-20 | 2024-02-21 | 2024-02-20 | 2024-02-26 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-03-01 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-03-01 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | SengKee Seow10241846 |  |  | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-03-02 | Muhamad//rais bin mat isa/7021000043 | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-02-29 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | NG HONG JIE7018000036 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
4519A-4517A | PENGKALAN IND 3 | DU00003430934 | Northern | Perak | 4.533889 | 101.056667 | WK07 | FEB 24 | WK11 | MAR 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 1X 18G 0.6M MDD ANTENNA 1X 18G 1.2M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Swap | DCN VLAN : 415, PORT NUMBER : GigabitEthernet0/1/3 NE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 2+0 56MHZ 5. CASCADE 4358B- 4165H NLOS AND 4358B BBU TO NEW RTN 910A 6. DISMANTLE EXISTING SM 15G 2+0 LINK FE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 2+0 56MHZ 5. PATCH NEW RTN 910A TO NEW CP PORT 6. DISMANTLE EXISTING SM 15G 2+0 LINK | [7 empty] | CCSMY | SQ202402220007-CCS | CCSMY | SQ202402220008-CCS | 2024-08-21 | 2024-08-21 | Completed | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  |  | Unassigned | Completed |  | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022023 |  | 2024-02-21 | 2024-02-26 | Completed | 2024-02-20 | 2024-02-21 | 2024-02-20 | 2024-02-26 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-03-11 | Saleem//Muhammed/7021000077 | CCS TI | 2024-03-04 | 2024-03-08 | 2024-03-11 | 2024-03-11 | Saleem//Muhammed/7021000077 | CCS TI | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-03-14 | Saleem//Muhammed/7021000077 | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-03-11 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-07 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
4624B-4640A | Bdr Aman Jaya Utara | DU00003430935 | Northern | Kedah | 5.703220 | 100.541134 | WK08 | FEB 24 | WK11 | MAR 24 | RFS | Pending TX OPS update EPMS | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+TI | L1+ATP+PAC | 1X RTN 910A | MW Hardware Upgrade | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/14 NE 1. PATCH 4624B RTN06 TO 4624B RTN04 FE 1. INSTALL NEW RTN 910A 2. SHIFT IF CABLE & CONFIGURATION FROM RTN18 7-ISM6-1 AND RTN18 7-ISM8-2 TO NEW RTN 910A 3. PATCH NEW RTN 910A TO NEW CP PORT | [7 empty] | CCSMY | SQ202402260336-CCS | CCSMY | SQ202402260336-CCS // SQ202411120061-CCS | 2026-01-23 | 2026-01-23 | Completed | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  |  | Unassigned | Completed |  | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022024 |  | 2024-02-21 | 2024-02-26 | Completed | 2024-02-20 | 2024-02-21 | 2024-02-20 | 2024-02-26 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-05-29 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-03-15 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-03-15 | Muhamad//rais bin mat isa/7021000043 | 2025-10-01: 2024-03-12; 2025-10-01: 2024-03-31; 2025-10-01: 2024-03-12; 2025-10-01: 2024-03-14 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300164-GCI | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
S01440_USP | LADANG KERUING | DU00005423263 | Sabah | Sabah | 4.574350 | 117.649090 |  |  |  |  | Pending TSS |  |  | 05. Doable |  | TSS+AA+TI+Dismantle |  | 13G 4+0 MDD DP 28MHz 1.8M/1.8M SUB A/SUB B 10.6KM 688Mbps 2X RTN 910A 4X IF CARD ISM8 2X 13G 1.8M MDD DP ANTENNA 1X 13G XMC-5D SUB A HI 1X 13G XMC-5D SUB B HI 1X 13G XMC-5D SUB A LO 1X 13G XMC-5D SUB B LO Additional ; FE : 1X SFP 1G and 1Pair Fiber PatchCord | MW New Link / Reroute | MW New Link Reroute S01440 to 7642B with HW 13G 4+0 CA 28MHz 1.2m/1.2m 10km Existing MW Config: HW 13G 1+0 28MHz Impacted Sites: S01440 NE S01440 T3 LDG KERUING 1. INSTALL NEW RTN 910A 2. INSTALL 2x IF CARD ISM8 AT SLOT 3 & 4 3. INSTALL NEW 13G 1.8M MDD DP ANTENNA 4. INSTALL NEW 4+0 13G XMC-5D SUB A & SUB B 5. CONFIGURE LINK 13G 4+0 CA 28MHZ 128QAM 6. PATCH S01440 BBU TO NEW RTN 910A 7. CREATE SERVICE 8. DISMANTLE EXISTING LINK SB02726 FE 7642B BROMAS SBC 1. INSTALL NEW RTN 910A 2. INSTALL 2x IF CARD ISM8 AT SLOT 3 & 4 3. INSTALL NEW 13G 1.8M MDD DP ANTENNA 4. INSTALL NEW 4+0 13G XMC-5D SUB A & SUB B 5. CONFIGURE LINK 13G 4+0 CA 28MHZ 128QAM 6. PATCH S01440 BBU TO NEW RTN 910A 7. CREATE SERVICE 8. PATCH NEW RTN 910A TO PORT 5 7642B BROMAS RTN04 using SFP 1G and Fiber PatchCord 9. DISMANTLE EXISTING LINK SB02726 | NE S01440 T3 LDG KERUING 1. INSTALL NEW RTN 910A 2. INSTALL 2x IF CARD ISM8 AT SLOT 3 & 4 3. INSTALL NEW 13G 1.8M MDD DP ANTENNA 4. INSTALL NEW 4+0 13G XMC-5D SUB A & SUB B 5. CONFIGURE LINK 13G 4+0 CA 28MHZ 128QAM 6. PATCH S01440 BBU TO NEW RTN 910A 7. CREATE SERVICE 8. DISMANTLE EXISTING LINK SB02726 | FE 7642B BROMAS SBC 1. INSTALL NEW RTN 910A 2. INSTALL 2x IF CARD ISM8 AT SLOT 3 & 4 3. INSTALL NEW 13G 1.8M MDD DP ANTENNA 4. INSTALL NEW 4+0 13G XMC-5D SUB A & SUB B 5. CONFIGURE LINK 13G 4+0 CA 28MHZ 128QAM 6. PATCH S01440 BBU TO NEW RTN 910A 7. CREATE SERVICE 8. PATCH NEW RTN 910A TO PORT 5 7642B BROMAS RTN04 using SFP 1G and Fiber PatchCord 9. DISMANTLE EXISTING LINK SB02726 | XMC-5D | MDD DP | 13G | 1.8m | 1.8m | Seri Pancar | SQ202506190634-Seri Pancar | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services | 2026-03-13 | 2026-03-13 | Completed | 2025-06-19 | 2025-07-31 | 2025-06-19 | 2025-06-19 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-20 | 2025-09-30 | 2025-06-24 | 2026-03-10 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090216 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202505190529-GCI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
S01607_USP | S01607_SABAHMAS CENTRAL OFFICE_PBB OIL OFFICE | DU00005423264 | Sabah | Sabah | 5.171860 | 118.407780 |  |  |  |  | Pending SOW | [7 empty] | Existing TX | REUSE EXISTING TX. UPLINK S00330 ALREADY REROUTE TO 7604A | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505190529-GCI | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | EZRIN TASNIM BIN ABDUL GANI6798000128
S00529_USP | S00529_TABIN WILDLIFE RESERVE | DU00005423265 | Sabah | Sabah | 5.191600 | 118.503100 |  |  |  |  | Pending SOW | [7 empty] | Existing TX | REUSE EXISTING TX. UPLINK S00330 ALREADY REROUTE TO 7604A | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505190529-GCI | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | EZRIN TASNIM BIN ABDUL GANI6798000128
S01882_EB | UOB PRIMA SANDAKAN | DU00005423266 | Sabah | Sabah | 5.857419 | 118.074011 |  |  |  |  | Pending TSS |  |  | 03. Pending TSS |  | TSS+AA+TI+Dismantle |  | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE S01882-7123A WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB_B_2.34KM IMPACTED: S01882 DISMANTLE EXISTING LINK S01882-S00214 POI NEEDED: YES | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK S01882-S00214 | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK S01882-S00214 | XMC3E | MAC | 18G | 0.6 | 0.6 | NR services | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505190529-GCI | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
S01753_EB | S01753_SABAHMAS PLANTATION PPB WILMAR_EXIMIUS MARKETING ENTERPRISE | DU00005423267 | Sabah | Sabah | 5.176257 | 118.406533 |  |  |  |  | Pending SOW |  |  | 01. Pending Planning | [5 empty] | S00330_EB Replaced with S01753_EB due to scope need to do at S00330 patching | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505190529-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | EZRIN TASNIM BIN ABDUL GANI6798000128
S00524_AD | S00524_SUAN LAMBA ESTATE | DU00005423268 | Sabah | Sabah | 5.577241 | 118.139713 |  |  |  |  | Pending TSS |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M NE_S00524. 18G_DP_1.2M(MDD) x1. RTN910A x1. XCM_3E , Sub A & B_Hi x2. FE_7583A. 18G_DP_1.2M(MDD). RTN910A x1. XMC_3E , Sub A & B_Lo x2. | MW New Link / Reroute | Existing link 7G_4+0_28M_XPIC. Link reroute to new FE 7583A with 18G_2+0_112M configuration. S00524 is pair site with 7421B. Site Impacted : 7421B. NE_S00524/7421B 1.Install new 18G_DP_1.2M(MAC)+OMT 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XCM_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , transfer BBU_7421B. 6.Traffic migrate to new link 18G_2+0_112M and new FE route. 7.No decomm existing MW link (S00524 - S00166)_SB02911 due to DCN has allocated to other SM links. FE_7583A. 1.Install new 18G_DP_1.2M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create new In band DCN 6.Migrate traffic to new link 18G_2+0_112M and new FE routing. 7.No decom existing MW link (S00166 - S00524)_SB02911 due to DCN has allocated to other SM links. | Existing link 7G_4+0_28M_XPIC. Link reroute to new FE 7583A with 18G_2+0_112M configuration. S00524 is pair site with 7421B. Site Impacted : 7421B. NE_S00524/7421B 1.Install new 18G_DP_1.2M(MAC)+OMT 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XCM_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , transfer BBU_7421B. 6.Traffic migrate to new link 18G_2+0_112M and new FE route. 7.No existing MW link (S00524 - S00166)_SB02911 due to DCN has allocated to other SM links. | Existing link 7G_4+0_28M_XPIC. Link reroute to new FE 7583A with 18G_2+0_112M configuration. S00524 is pair site with 7421B. Site Impacted : 7421B. FE_7583A. 1.Install new 18G_DP_1.2M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create new In band DCN 6.Migrate traffic to new link 18G_2+0_112M and new FE routing. 7.No decom existing MW link (S00166 - S00524)_SB02911 due to DCN has allocated to other SM links. | XMC_3E | MAC | 18G | 1.2 | 0.6 | NR services | SQ202512160988-NR Services | NR services | SQ202511110813-NR Services // SQ202511110815-NR Services // SQ202512190088-NR Services | 2026-01-21 | 2026-01-21 | Completed | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110204 |  | 2025-11-03 | 2025-11-04 | Completed | 2025-11-02 | 2025-11-03 | 2025-11-02 | 2025-11-04 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-02 | 2026-01-02 | 2025-12-02 | 2025-12-08 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-12-02 | 2026-01-02 | 2025-12-02 | 2025-12-10 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-11 | 2025-12-02 | 2026-01-02 | 2025-12-02 | 2025-12-17 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-10-01: 2025-12-02; 2025-10-01: 2026-01-02; 2025-10-01: 2025-12-02; 2025-10-01: 2025-12-08 |  |  | 2025-12-24 | 2026-01-24 | 2025-12-24 | 2025-12-24 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202505190529-GCI | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | CHEONG/SENG/WAH/7018000306
S01545_EB | S01545_UOB TUARAN_GLOBAL FORWAY | DU00005423269 | Sabah | Sabah | 6.177887 | 116.233823 |  |  |  |  | Pending TSS |  |  | 05. TI WIP |  | TSS+AA+TI+Dismantle |  | 18G_1+0_112M NE_S01545 18G_SP_0.6M(MDD x1. RTN910A x1. XMC_5D , Sub A_Lo x1. FE_7515A. 18G_SP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW New Link / Reroute | Existing link 13G_1+0_28M (SB02244) Link reroute to new FE 7151A with 18G_1+0_112M config. Site Impacted : S01545. NE_S01545 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic migrate to new FE route with new MW link. 6.Decom existing MW link (S01545 - S00039)_SB02244. Ensure traffic migrated successful before decom. FE_7515A. 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Traffic migrate to new FE route with new MW link. 6.Enable GE1 , ETH Patching to existing 7515A_RTN01_GE3 (ID : 43502). 7.POI back to xC backhaul. 8.Decom existing MW link (S00039 - S01545)_SB02244.Ensure traffic migrated successful before decom. | Existing link 13G_1+0_28M (SB02244) Link reroute to new FE 7151A with 18G_1+0_112M config. Site Impacted : S01545. NE_S01545 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic migrate to new FE route with new MW link. 6.Decom existing MW link (S01545 - S00039)_SB02244. Ensure traffic migrated successful before decom. | Existing link 13G_1+0_28M (SB02244) Link reroute to new FE 7151A with 18G_1+0_112M config. Site Impacted : S01545. FE_7515A. 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Traffic migrate to new FE route with new MW link. 6.Enable GE1 , ETH Patching to existing 7515A_RTN01_GE3 (ID : 43502). 7.POI back to xC backhaul. 8.Decom existing MW link (S00039 - S01545)_SB02244.Ensure traffic migrated successful before decom. | XMC_5D | MDD | 18G | 0.6 | 0.6 | YPTT | SQ202507180630-YPTT | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services | 2026-02-24 | 2026-02-25 | Completed | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | DOMINIC DAVIES6794000049 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | DOMINIC DAVIES6794000049 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-25 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090219 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-17 | 2025-10-17 | 2025-09-17 | 2025-09-17 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-09-17 | 2025-10-17 | 2025-09-17 |  | RALPH O'BRYAN HILARY7167000030 | NR Service TI | [7 empty] | 2025-09-17 | 2025-10-17 | 2025-09-17 |  | RALPH O'BRYAN HILARY7167000030 | 2025-10-01: 2025-09-17; 2025-10-01: 2025-10-17; 2025-10-01: 2025-09-17; 2025-10-01: 2025-11-18 | [7 empty] | GCI | SQ202505190529-GCI | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | CHEONG/SENG/WAH/7018000306
S01059_EB | PI KAMPUNG KUALA | DU00005423270 | Sabah | Sabah | 5.744339 | 115.910796 |  |  |  |  | Pending TSS |  |  | 03. Pending TSS |  | TSS+TI+Dismantle |  | New NLOS RTN510 equipment NE_S01059 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_7547A 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH cable / LAN Cable. | MW New Link / Reroute | Link reroute to new FE 7547A with new NLOS RTN510 equipment due to FE S00428 Site Decom // Require POI xC to xD NE_S01059 1.Install new RTN510 2.Install new NLOS Antenna 3.Install new PI 4.Create service cross connect 5.Traffic migrate to new route FE site 6.Decom existing NLOS radio FE_7547A 1.Install new RTN510 2.Install new NLOS Antenna 3.Install new PI 4.Create Service cross connect and new In band DCN 5.ETH cable patching to New Eth Port existing xD HW MW 7547A-7701A 6.Decom existing NLOS Radio | NE_S01059 1.Install new RTN510 2.Install new NLOS Antenna 3.Install new PI 4.Create service cross connect 5.Traffic migrate to new route FE site 6.Decom existing NLOS radio | FE_7547A 1.Install new RTN510 2.Install new NLOS Antenna 3.Install new PI 4.Create Service cross connect and new In band DCN 5.ETH cable patching to New Eth Port existing xD HW MW 7547A-7701A 6.Decom existing NLOS Radio | RTN510 | Flat Panel | 5 | 0.3 | 0.3 | NR services | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505190529-GCI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
S01462_EB | SABAH ELECTRICITY PMU PENAMPANG | DU00005423271 | Sabah | Sabah | 5.928476 | 116.093529 |  |  |  |  | Pending TSS |  |  | 03. Pending TSS |  | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | . Reroute & build new MW link S01462-7239A with Huawei 23G_28MHz_1+0_0.6M_0.5KM . Dismantle Old Microwave link S01462-S00058 POI Needed : Yes | [7 empty] | NR services | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300153-GTSB
S01808_EB | S01808_PI TAMAN SABANA | DU00005423272 | Sabah | Sabah | 5.371257 | 116.158326 |  |  |  |  | Plan TI |  |  | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | New NLOS RTN510 equipment NE_S01808 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_7068A 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH cable / LAN Cable. | MW New Link / Reroute | Link reroute to new FE 7068A with new NLOS RTN510 equipment due to FE S00276 Site Decom // Require POI xC to xD NE_S01808 1.Install new RTN510 2.Install new NLOS Antenna 3.Install new PI 4.Create service cross connect 5.Traffic migrate to new route FE site 6.Decom existing NLOS radio FE_7068A 1.Install new RTN510 2.Install new NLOS Antenna 3.Install new PI 4.Create Service cross connect and new In band DCN 5.ETH cable patching to existing Fiber_Ibeam 6.Decom existing NLOS Radio | NE_S01808 1.Install new RTN510 2.Install new NLOS Antenna 3.Install new PI 4.Create service cross connect 5.Traffic migrate to new route FE site 6.Decom existing NLOS radio | FE_7068A 1.Install new RTN510 2.Install new NLOS Antenna 3.Install new PI 4.Create Service cross connect and new In band DCN 5.ETH cable patching to existing Fiber_Ibeam 6.Decom existing NLOS Radio | RTN510 | Flat Panel | 5 | 0.3 | 0.3 | YPTT | SQ202507180630-YPTT | NR services | SQ202509040251-NR Services // SQ202509040256-NR Services |  |  | Ongoing | 2025-07-19 | 2025-07-19 | 2025-07-20 | 2025-07-20 | DOMINIC DAVIES6794000049 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-24 | 2025-09-25 | 2025-09-24 | 2025-09-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-03 | 2026-04-04 | 2026-04-03 | 2026-04-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25081114 |  | 2025-08-12 | 2025-08-19 | Completed | 2025-08-11 | 2025-08-12 | 2025-08-11 | 2025-08-19 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-25 | 2025-10-25 | 2025-09-25 | 2025-09-29 | WILFRED BALANG7167000026 | NR Service TI | 2025-09-25 | 2025-10-25 | 2025-09-25 | 2025-09-30 | WILFRED BALANG7167000026 | NR Service TI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-03 | 2025-09-25 | 2025-10-25 | 2025-09-25 | 2025-10-06 | WILFRED BALANG7167000026 | 2025-10-01: 2025-09-25; 2025-10-01: 2025-10-25; 2025-10-01: 2025-09-25; 2025-10-01: 2025-09-27 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202505190529-GCI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
S00378_EB | S00378_PETRONAS CARIGALI KOTA KINABALU_MENARA PETRONAS | DU00005423273 | Sabah | Sabah | 5.963767 | 116.069967 |  |  |  |  | Pending TSS |  |  | 03. Pending TSS |  | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | . Reroute & build new MW link S00378-7239A with Huawei 23G_28MHz_1+0_0.6M_1.0KM . Dismantle Old Microwave link S00378-S00058 POI Needed : Yes | [7 empty] | NR services | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300153-GTSB
3546A44_EVT | MBTS DEWAN LIMBARAN SANDAKAN (PRN) | DU00006250614 | Sabah | Sabah | 5.905330 | 118.055630 | [13 empty] | Planning and integration support only for event site 3546A44 MBTS DEWAN LIMBARAN SANDAKAN (PRN) Tx route: 3546A44/3546A44-7145A-LL-7124A 1) Share port with 7145A at 7124A 2) New NE ID FE IDU 7145A RTN02 3) New NE ID NE IDU 3546A44 RTN01 4) At FE site 7145A patch RTN02 GE2 to existing RTN GE2 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
9254A_EB | Bunan Gega | DU00006250615 | Sarawak | Sarawak | 0.935247 | 110.535505 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch EB site to RTN GE2 port 4) Create new DCN | To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch EB site to RTN GE2 port 4) Create new DCN | [6 empty] | Allstar | SQ202601280703-Allstar | Allstar | SQ202601280698-Allstar | 2026-03-02 | 2026-02-27 | Completed | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-24 | 2026-03-02 | 2026-02-24 | 2026-02-24 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010553 |  | 2026-01-06 | 2026-01-06 | Completed | 2026-01-05 | 2026-01-06 | 2026-01-05 | 2026-01-06 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-07 | 2026-01-13 | 2026-02-13 | 2026-02-13 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-01-07 | 2026-01-13 | 2026-02-13 | 2026-02-13 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-22 | 2026-01-07 | 2026-01-13 | 2026-02-11 | 2026-02-11 | BONG NEE NYEEbong.allstar@gmail.com | 2025-10-01: 2026-01-07; 2025-10-01: 2026-01-13; 2025-10-01: 2026-01-08; 2025-10-01: 2026-01-08 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202602260597-GCI
7180D6_EVT | LBTS PUSAT KEBUDAYAAN SABAH | DU00006250616 | Sabah | Sabah | 5.915982 | 116.109275 | [13 empty] | Planning and integration support only for event site 7180D6 LBTS PUSAT KEBUDAYAAN SABAH Tx route: 7180D6/7180D6-7039A 1) New port at IBEAM 7039A-MAC-001 Donggongon 2) New DCN IP 7039A RTN10 3) New DCN VLAN 7039A RTN10 4) New NE ID FE IDU 77039A RTN10 5) New NE ID NE IDU 7180D6 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
R00012_IPR | R001C_R00012OD_SPG4PERLIS | DU00006250617 | Northern | Perlis | 6.349770 | 100.187050 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | MW IDU Patching | Upgrade patching from IDU to PTN 1G to 10G. Existing: Huawei 4614A/R00012_SPG 4 PERLIS - 4729A_KG SG DUA GE5 to PTN 60017-SPG4PERLIS GE0/0/10 Integration team to assign new 10G port at IDU and PTN during migration Impacted site: 4729A | Upgrade patching from IDU to PTN 1G to 10G. Existing: Huawei 4614A/R00012_SPG 4 PERLIS - 4729A_KG SG DUA GE5 to PTN 60017-SPG4PERLIS GE0/0/10 Integration team to assign new 10G port at IDU and PTN during migration Impacted site: 4729A | [6 empty] | Magicell | SQ202512120144-Magicell | Magicell | SQ202511260115-Magicell | 2025-12-06 | 2025-12-10 | Completed | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111798 |  | 2025-12-13 | 2025-11-20 | Completed | 2025-11-18 | 2025-12-13 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-28 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-02 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | AKMAL//BIN RAZALI/6794000078 |  | 2025-11-26 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2026-02-23 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | 2025-10-01: 2025-11-25; 2025-10-01: 2025-11-25; 2025-10-01: 2025-11-25; 2025-10-01: 2025-11-28 |  |  | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510300396-GCI | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
9356A_EB | Durin Ferry | DU00006250618 | Sarawak | Sarawak | 2.159597 | 112.020063 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to new (dedicated for EB Borneo Restu) LL port 3) Patch EB site to RTN GE2 port 4) Create new DCN | To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to new (dedicated for EB Borneo Restu) LL port 3) Patch EB site to RTN GE2 port 4) Create new DCN | [6 empty] | Allstar | SQ202601190153-Allstar | Allstar | SQ202601190148-Allstar | 2026-02-25 | 2026-02-25 | Completed | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-04 | 2026-02-10 | 2026-02-04 | 2026-02-04 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010554 |  | 2026-01-06 | 2026-01-06 | Completed | 2026-01-05 | 2026-01-06 | 2026-01-05 | 2026-01-06 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-20 | 2026-02-19 | 2026-02-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-14 | 2026-01-20 | 2026-02-19 | 2026-02-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-15 | 2026-01-14 | 2026-01-20 | 2026-02-19 | 2026-02-19 | ROYSTON//AHHOLE/6000038561 | 2025-10-01: 2026-01-14; 2025-10-01: 2026-01-20; 2025-10-01: 2026-01-26; 2025-10-01: 2026-01-26 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202602260597-GCI
K00326_HU_1 | K011A_K00326OD_CB_KGBUKIT | DU00006250619 | Northern | Kedah | 6.130400 | 100.608300 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 1X 15G 1.2M DP ANTENNA 1X 15G 0.6M DP ANTENNA 2x ODU 15G XMC3 SUB B HI 2X ODU 15G XMC3 SUB B LO | MW Parallel Link | MW PARALLEL LINK K00326-K00073 WITH HUAWEI_15G_2+0_1.2M/0.6M_DP_28MHZ_256QAM_400MBPS_XMC3_SUB_B_LINK_5.93KM IMPACTED: K00326 LINK WILL INSTALL WITH DU K00326_HU (15G 4+0) EPLA TO BECOME 15G 6+0 | 1. REUSE EXISTING IDU RTN910 (DU K00326_HU) SLOT 7 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 256QAM 5. LINK WILL EPLA WITH DU K00326_HU 15G 4+0 AT SLOT 3 & 4 6. CONFIGURE LINK 15G 6+0 28MHZ 256QAM WITH CA SLOT 3 & 4(4+0) AND 7(2+0) | 1. REUSE EXISTING IDU RTN910 (DU K00326_HU) SLOT 7 2. INSTALL NEW 15G 0.6M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 256QAM 5. LINK WILL EPLA WITH DU K00326_HU 15G 4+0 AT SLOT 3 & 4 6. CONFIGURE LINK 15G 6+0 28MHZ 256QAM WITH CA SLOT 3 & 4(4+0) AND 7(2+0) | XMC3 | MAC | 15G | 1.2 | 0.6 | Magicell | SQ202512120144-Magicell | Magicell | SQ202511260111-Magicell // SQ202511260115-Magicell | 2025-12-17 | 2025-12-16 | Completed | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251118AJ |  | 2025-11-19 | 2025-11-20 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-02 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-02 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-12 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-10-01: 2025-11-29; 2025-10-01: 2025-11-29; 2025-10-01: 2025-11-29; 2025-10-01: 2025-11-29 |  |  | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510300396-GCI | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
7328H2_EVT | IMACRO DEWAN MAKSAK KOTA KINABALU (PRN) | DU00006250620 | Sabah | Sabah | 5.989054 | 116.095166 | [13 empty] | Planning and integration support only for event site 7328H2 IMACRO DEWAN MAKSAK KOTA KINABALU (PRN) Tx route: 7328H2/7328H2-7223A-LL-7000A 1) Share port with 7223A at 7000A 2) New NE ID FE IDU 7223A RTN02 3) New NE ID NE IDU 7328H2 RTN01 4) At FE site 7223A patch RTN02 GE2 to existing RTN01 GE3 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
9353B_EB | Mile 39 Bintulu | DU00006250621 | Sarawak | Sarawak | 3.406637 | 113.493998 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x RTN910A (CD request to reuse re-deploy IDU with CSHR board - 6 GE electrical port. If not available to use RTN910A with CSHRF board and to inform CD to prepare electrical SFP) 2 x Cat6 cable | IPRAN Port Upgrade | To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch EB site to RTN GE2 port 4) Create new DCN | To install new IDU as switch. 1) Install new RTN910A 2) Patch GE1 to existing LL port 3) Patch EB site to RTN GE2 port 4) Create new DCN | [6 empty] | Allstar | SQ202602160105-Allstar | Allstar | SQ202602160103-Allstar | 2026-03-04 | 2026-03-04 | Completed | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-24 | 2026-03-03 | 2026-02-24 | 2026-02-24 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010555 |  | 2026-01-06 | 2026-01-06 | Completed | 2026-01-05 | 2026-01-06 | 2026-01-05 | 2026-01-06 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-02-02 | 2026-01-27 | 2026-01-27 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-27 | 2026-02-02 | 2026-01-30 | 2026-01-30 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-27 | 2026-01-27 | 2026-02-02 | 2026-02-11 | 2026-02-11 | ROYSTON//AHHOLE/6000038561 | 2025-10-01: 2026-01-27; 2025-10-01: 2026-02-02; 2025-10-01: 2026-01-27; 2025-10-01: 2026-01-27 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202602260597-GCI
Q00206_IPR | Q122A_Q00206OD_TMKANOWIT | DU00006250622 | Sarawak | Sarawak | 2.097198 | 112.151163 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New SFP Module 1.25G/1G 1310nm 10Km x2.(For IDU Huawei & Cisco) New Optical Patchcord with suitable type and length x1. | MW IDU Patching | Perform MW IDU Patching by doing migration at Q00206(Existing HW MW Link_ID SW03578, Q00206-Q01152). Site Impacted: 9042Z & 9043Z ONLY. NE_Q00206 1.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into port 8-EM6-5 of RTN910A(NEID 40893). Enable port. 2.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into new port Gi0/0/8 of Cisco. Enable port. 3.Patching port 8-EM6-5 of RTN910A(NEID 40893) and new port Gi0/0/8 of Cisco. 4.Request new xC Vlan services for traffic 9042Z & 9043Z. 5.Divert traffics 9042Z & 9043Z ONLY to new port of Cisco. | Perform MW IDU Patching by doing migration at Q00206(Existing HW MW Link_ID SW03578, Q00206-Q01152). Site Impacted: 9042Z & 9043Z ONLY. NE_Q00206 1.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into port 8-EM6-5 of RTN910A(NEID 40893). Enable port. 2.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into new port Gi0/0/8 of Cisco. Enable port. 3.Patching port 8-EM6-5 of RTN910A(NEID 40893) and new port Gi0/0/8 of Cisco. 4.Request new xC Vlan services for traffic 9042Z & 9043Z. 5.Divert traffics 9042Z & 9043Z ONLY to new port of Cisco. | [6 empty] | Allstar | SQ202512120287-Allstar | Allstar | SQ202511190850-Allstar | 2025-12-29 | 2025-12-22 | Completed | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110725 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-24 | 2025-11-18 | 2025-11-18 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-18 | 2025-11-24 | 2025-12-03 | 2025-12-03 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-18 | 2025-11-18 | 2025-11-24 | 2025-12-02 | 2025-12-02 | ROYSTON//AHHOLE/6000038561 | 2025-10-01: 2025-11-18; 2025-10-01: 2025-11-24; 2025-10-01: 2025-11-18; 2025-10-01: 2025-11-18 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202510300425-GTSB
2632A_IPR | Ecopark | DU00006250623 | Central | Selangor | 3.116279 | 101.468755 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x1. | MW IDU Patching | Perform LAG at CP site for IDU 2632A-ECOPARK-RTN07 to 2632A-MAC-001 Ecopark Impact sites: 3174A , 1474C , 2632A-MAC-001 Ecopark/GigabitEthernet0/2/23. 1) Patch IDU 2632A-ECOPARK-RTN07 GE2 to new CP port. 2) Create LAG. | Perform LAG at CP site for IDU 2632A-ECOPARK-RTN07 to 2632A-MAC-001 Ecopark Impact sites: 3174A,1474C 2632A-MAC-001 Ecopark/GigabitEthernet0/2/23. 1) Patch IDU 2632A-ECOPARK-RTN07 GE2 to new CP port. 2) Create LAG. | [6 empty] | Magicell | SQ202510300097-Magicell | Magicell | SQ202510300094-Magicell | 2025-11-28 | 2025-11-27 | Completed | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102915 |  | 2025-10-30 | 2025-11-10 | Completed | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-10 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-10 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-10 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-04 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-10 | AHMAD RASHIDI BIN SAFRI7018000135 | 2025-10-01: 2025-10-30; 2025-10-01: 2025-10-30; 2025-10-01: 2025-10-30; 2025-10-01: 2025-11-04 |  |  | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202510300390-GCI | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | CHEONG/SENG/WAH/7018000306
7328H5_EVT | DEWAN KESENIAN ISLAM MEMBAKUT | DU00006263568 | Sabah | Sabah | 5.476080 | 115.800967 | [13 empty] | Planning and integration support only for event site 7328H5 DEWAN KESENIAN ISLAM MEMBAKUT Tx route: 7328H5/7328H5-7375A-LL-7000A 1) Share port with 7375A at 7000A 2) New NE ID FE IDU 7375A RTN04 3) New NE ID NE IDU 7328H5 RTN01 4) At FE site 7375A patch RTN04 GE1 to existing RTN01 GE1 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
4529D_HU | Felda Teloi Timur | DU00005613447 | Northern | Kedah | 5.712500 | 100.676700 | [7 empty] | 00. Integrated/RFS Done | 14/06: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_28M. NE_4529D. 15G_DP_1.2M(MDD) x1. ISM8 x1. XMC_5D , Sub B_Hi x1, FE_4623B 15G_DP_1.2M(MDD) x1. ISM8 x1. XMC_5D , Sub B_Lo x1. | MW Swap | Link existing 15G_1+0_28M. Swap existing to 15G_2+0_28M. Site Impacted : 4529D. NE_4529D. 1.Install new 15G_DP_1.2M(MDD). 2.Reuse existing 4592D_RTN01 (ID : 23647). 3.Install new 3_ISM8 into existing 4592D_RTN01 (ID : 23647). 4.Install new XMC_5D , Sub B_Hi, 5.Create service cross connect and EPLA. 6.Traffic migrate to new link. 7.Decom existing ODU and ANT. FE_4623B 1.Install new 15G_DP_1.2M(MDD). 2.Reuse existing 4623B_RTN05 (ID : 30319). 3.Install new 4_ISM8-2+0 into existing 4623B_RTN05 (ID : 30319). 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link. 7.Decom existing ODU and ANT. | Link existing 15G_1+0_28M. Swap existing to 15G_2+0_28M. Site Impacted : 4529D. NE_4529D. 1.Install new 15G_DP_1.2M(MDD). 2.Reuse existing 4592D_RTN01 (ID : 23647). 3.Install new 3_ISM8 into existing 4592D_RTN01 (ID : 23647). 4.Install new XMC_5D , Sub B_Hi, 5.Create service cross connect and EPLA. 6.Traffic migrate to new link. 7.Decom existing ODU and ANT. | Link existing 15G_1+0_28M. Swap existing to 15G_2+0_28M. Site Impacted : 4529D. FE_4623B 1.Install new 15G_DP_1.2M(MDD). 2.Reuse existing 4623B_RTN05 (ID : 30319). 3.Install new 4_ISM8-2+0 into existing 4623B_RTN05 (ID : 30319). 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link. 7.Decom existing ODU and ANT. | XMC_5D | MDD | 15G | 1.2M | 1.2M | GTSB | SQ202506110171-GTSB | GTSB | SQ202506110176-GTSB // SQ202506110181-GTSB |  |  | Ongoing | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25060432 |  | 2025-06-05 | 2025-06-12 | Completed | 2025-06-04 | 2025-06-05 | 2025-06-04 | 2025-06-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2026-03-27 | ALI RAZA AKBAR ALI6799000298 | GTSB TI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-07-18 | ALI RAZA AKBAR ALI6799000298 | GTSB TI | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-07-21 | ALI RAZA AKBAR ALI6799000298 | 2025-10-01: 2025-06-13; 2025-10-01: 2025-06-13; 2025-10-01: 2025-06-13; 2025-10-01: 2025-07-04 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506050639-GCI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | CHEONG/SENG/WAH/7018000306
7069C-7687B | Batu Apas | DU00003952980 | Sabah | Sabah | 4.249779 | 117.904162 |  |  | WK32-WK35 | AUG 24 |  |  |  | 00. Integrated/RFS Done | 5/11: Cutover done. Post-CO T/S ongoing 23/10: Interim solution: MW Remote upgrade done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_0.6/0.6m_DP 2x SB A | MW Swap | SWAP MW LINK 7069C-7687B_23G_2+0_0.6/0.6M from 23G-1+0 link. NE: 1. Reuse existing RTN910A. 2. Reuse existing ODU SB_B and install new XMC-3_112Mhz_SB A. 3. Swap existing Antenna with 23G_0.6m_DP. 4.Configure 23G_2+0_0.6m_112Mhz_EPLA. FE: 1. Reuse existing RTN910A and use Slot 7 port 2 2. Reuse existing ODU SB_B and install new XMC-3_112Mhz_SB A. 3. Swap existing Antenna with 23G_0.6m_DP. 4.Configure 23G_2+0_0.6m_112Mhz_EPLA. | [7 empty] | NR services | SQ202411120053-NR Services | NR services | SQ202411120063-NR Services // SQ202504260199-NR Services | 2024-11-15 | 2024-11-11 | Completed | 2024-11-04 | 2024-11-04 | 2024-11-04 | 2024-11-04 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-08 | 2024-11-15 | 2024-11-08 | 2024-11-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-08 | 2024-11-15 | 2024-11-08 | 2024-11-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-11 | 2024-11-15 | 2024-11-11 | 2024-11-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241024AJ |  | 2024-10-25 | 2024-11-01 | Completed | 2024-10-24 | 2024-10-25 | 2024-10-24 | 2024-11-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-04 | 2024-11-30 | 2024-11-04 | 2024-11-04 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-11-04 | 2024-11-30 | 2024-11-04 | 2024-11-04 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-11-04 | 2024-11-04 | 2024-11-04 | 2024-11-04 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-11-04 | 2024-11-30 | 2024-11-04 | 2024-11-06 | RALPH O'BRYAN HILARY7167000030 | 2024-11-04 | 2024-11-30 | 2024-11-04 | 2024-11-04 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-27 | tseping//wang/6819000006 | Logistic Team | 2024-12-20 | 2025-01-20 | 2024-12-20 | 2024-12-20 | ASTI//GANIS PUTRIANI/6237001358
3546A41_EVT | MBTS SAMBUTAN IIAU KALIMARAN | DU00005920903 | Sabah | Sabah | 4.911970 | 115.918980 | [13 empty] | Planning and integration support only for event site 3546A41 MBTS SAMBUTAN IIAU KALIMARAN Tx route: 3546A41/3546A41-7186A-LL-7000A 1) Share port with 7571B,7186A at 7000A 2) New NE ID FE IDU 7186A RTN02 3) New NE ID NE IDU 3546A41 RTN01 4) At far end 7186A patch new IDU PATCH RTN02 GE1 to RTN01 GE3 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
Q01492_LOS | LDG WTK MYY | DU00005232397 | Sarawak | Sarawak | 3.746327 | 113.886730 | [7 empty] | 00. Site Out/Drop | 09/6: existing route LOS cleared, this DU TSS only | TSS+AA+TI+Dismantle |  | 13G_4+0_28M. NE_Q01492. 13G_DP_1.2M(MDD) x1. 2.Install new RTN910A x1. ISM8 x2 FE_Q00345 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. | MW New Link / Reroute | Existing SM link Q01492-Q00311. (SW02420). Link reroute to the new FE Q00345 due to LOS Block with 13G_4+0_28M. Site Impacted :Q01492 NE_Q01492. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Create service cross connect , CA and EPLA. 5.Traffic migrate to new link with reroute to new FE. 6.Decom existing SM link.Ensure traffic migrate to new link before decom. FE_Q00345 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Create service cross connect , CA and EPLA. 5.Traffic migrate to new link with reroute to new FE. 6.Enable GE1 , ETH patching to SM IDU link.(SW03007). 7.Decom existing SM link.Ensure traffic migrate to new link before decom. | Existing SM link Q01492-Q00311. (SW02420). Link reroute to the new FE Q00345 due to LOS Block with 13G_4+0_28M. Site Impacted :Q01492 NE_Q01492. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Create service cross connect , CA and EPLA. 5.Traffic migrate to new link with reroute to new FE. 6.Decom existing SM link.Ensure traffic migrate to new link before decom. | Existing SM link Q01492-Q00311. (SW02420). Link reroute to the new FE Q00345 due to LOS Block with 13G_4+0_28M. Site Impacted :Q01492 FE_Q00345 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Create service cross connect , CA and EPLA. 5.Traffic migrate to new link with reroute to new FE. 6.Enable GE1 , ETH patching to SM IDU link.(SW03007). 7.Decom existing SM link.Ensure traffic migrate to new link before decom. | [5 empty] | Magicell | No PR required-Site drop/cancel |  |  | 2026-01-26 | 2026-01-21 | Completed | 2025-04-19 | 2025-04-19 | 2025-04-19 | 2025-04-19 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050655-GTSB | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | HSU//MYET CHAE/6799000011
4418B_AD | Changkat Sulaiman Sungkai | DU00005239883 | Northern | Perak | 3.975862 | 101.289193 | [7 empty] | 00. Integrated/RFS Done | 18/07: TI Started 19/07: CO Done | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M NE_4418B New 18G_DP_1.2M(MS) x1. Re-use exsiting RTN910A(RTN01). New XMC_3E, Sub B_Lo x2. New CAT6 Cable with suitable length x1. FE_4414A New 18G_DP_1.2M(MS) x1. Re-use exsiting RTN910A(RTN03). New XMC_3E, Sub B_Hi x2. New CAT6 Cable with suitable length x1. | MW New Link / Reroute | Existing HW MW Link 15G_2+0_28M_256QAM_400M_EPLA. Install new HW MW Link 18G_2+0_112M_512QAM_1778M_EPLA. Combine existing and new HW MW Link 15G&18G_4+0_28MHz&112MHz_256QAM&512QAM_EPLA . Site Impacted : 4418B, A00834 & Y00029. NE_4418B 1.Install new 18G_DP_1.2M(MS) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub B_Lo. Configure it. 4.Build new HW MW Link 18G_2+0_112M_512QAM_1778M_EPLA. 5.Combine existing and new HW MW Link 15G&18G_4+0_28MHz&112MHz_EPLA. 6.Migrate RAN Traffic to HW MW Link 15G&18G_4+0_28MHz&112MHz_EPLA. FE_4414A 1.Install new 18G_DP_1.2M(MS) x1. 2.Re-use existing RTN910A(RTN03). 3.Install new 2x XMC_3E, Sub B_Hi. Configure it. 4.Enable port 8-EM6-2 of existing RTN910A(RTN03). 5.Enable new 1G port at IBeam(GE0/1/4). 6.Patching port 8-EM6-2 of existing RTN910A(RTN03) and new 1G port at IBeam(GE0/1/4). 7.Perform LAG in between existing(GE0/2/3) and new(GE0/1/4) IBeam 1G port . Configure it. 8.RAN Traffic will backhaul thru these 2 IBeam port. | Existing HW MW Link 15G_2+0_28M_256QAM_400M_EPLA. Install new HW MW Link 18G_2+0_112M_512QAM_1778M_EPLA. Combine existing and new HW MW Link 15G&18G_4+0_28MHz&112MHz_256QAM&512QAM_EPLA . Site Impacted : 4418B, A00834 & Y00029. NE_4418B 1.Install new 18G_DP_1.2M(MS) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub B_Lo. Configure it. 4.Build new HW MW Link 18G_2+0_112M_512QAM_1778M_EPLA. 5.Combine existing and new HW MW Link 15G&18G_4+0_28MHz&112MHz_EPLA. 6.Migrate RAN Traffic to HW MW Link 15G&18G_4+0_28MHz&112MHz_EPLA. | Existing HW MW Link 15G_2+0_28M_256QAM_400M_EPLA. Install new HW MW Link 18G_2+0_112M_512QAM_1778M_EPLA. Combine existing and new HW MW Link 15G&18G_4+0_28MHz&112MHz_256QAM&512QAM_EPLA . Site Impacted : 4418B, A00834 & Y00029. FE_4414A 1.Install new 18G_DP_1.2M(MS) x1. 2.Re-use existing RTN910A(RTN03). 3.Install new 2x XMC_3E, Sub B_Hi. Configure it. 4.Enable port 8-EM6-2 of existing RTN910A(RTN03). 5.Enable new 1G port at IBeam(GE0/1/4). 6.Patching port 8-EM6-2 of existing RTN910A(RTN03) and new 1G port at IBeam(GE0/1/4). 7.Perform LAG in between existing(GE0/2/3) and new(GE0/1/4) IBeam 1G port . Configure it. 8.RAN Traffic will backhaul thru these 2 IBeam port. | XMC_3E | MS | 18G | 18G_DP_1.2M(MS) x1 | 18G_DP_1.2M(MS) x1 | Magicell | SQ202504280482-Magicell | Magicell | SQ202507190097-Magicell // SQ202507190099-Magicell // SQ202511030393-Magicell | 2025-12-02 | 2025-11-26 | Completed | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062330 |  | 2025-06-24 | 2025-06-26 | Completed | 2025-06-23 | 2025-06-24 | 2025-06-23 | 2025-06-26 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-18 | 2026-08-06 | 2025-07-18 | 2025-08-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-07-18 | 2026-08-06 | 2025-07-18 | 2025-07-18 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-19 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-19 | 2025-07-18 | 2026-08-06 | 2025-07-18 | 2025-07-31 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-10-01: 2025-07-18; 2025-10-01: 2026-08-06; 2025-10-01: 2025-07-18; 2025-10-01: 2025-08-05 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202507080632-GTSB
K00915_HU | KOMP. HIJAU KUNING | DU00005249937 | Northern | Kedah | 6.107194 | 100.366468 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M. NE_K00915 18G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. FE_4295B 18G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. | MW Swap | Link existing 15G_2+0_28M. Swap existing link to 18G_2+0_112M. Site Impacted : K00915. NE_K00915 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create cross connect and EPLA. 5.Traffic migrate to new MW link 18G_2+0_112M. 6.Decomm existing SM link.Ensure no traffic before decomm. FE_4295B 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create cross connect and EPLA. 5.Create In Band DCN. 6.Traffic migrate to new link 18G_2+0_112M. 7.Decomm existing SM link. Ensure no traffic before decomm. | Link existing 15G_2+0_28M. Swap existing link to 18G_2+0_112M. Site Impacted : K00915. NE_K00915 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create cross connect and EPLA. 5.Traffic migrate to new MW link 18G_2+0_112M. 6.Decomm existing SM link.Ensure no traffic before decomm. | Link existing 15G_2+0_28M. Swap existing link to 18G_2+0_112M. Site Impacted : K00915. FE_4295B 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create cross connect and EPLA. 5.Create New In band DCN. 6.Traffic migrate to new link 18G_2+0_112M. 7.Decomm existing SM link.Ensure no traffic before decomm. | XMC_3E | MAC | 18G | 0.6 | 0.6 | NWAVE | SQ202505240072-N-Wave | NWAVE | SQ202505240112-N-Wave // SQ202505240115-N-Wave | 2026-01-20 | 2026-01-19 | Completed | 2025-05-23 | 2025-05-30 | 2025-05-23 | 2025-07-15 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-23 | 2025-05-30 | 2025-05-23 | 2025-07-29 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051367 |  | 2025-05-14 | 2025-05-17 | Completed | 2025-05-13 | 2025-05-14 | 2025-05-13 | 2025-05-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-23 | 2025-05-30 | 2025-05-23 | 2025-05-23 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-06-16 | 2025-06-24 | 2025-06-16 | 2025-07-15 | Muhammad Faiq Bin Aidan6000022582 | NWAVE TI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-18 | 2025-06-16 | 2025-06-24 | 2025-06-16 | 2025-11-06 | Muhammad Faiq Bin Aidan6000022582 | 2025-06-16 | 2025-06-24 | 2025-06-16 | 2025-06-18 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | CHEONG/SENG/WAH/7018000306
1924B_HU | Bdr Seri Ehsan | DU00005275451 | Central | Selangor | 2.788836 | 101.635348 |  | APR 25 |  | APR 25 | DO | Doable, just waiting material | ZTE | 00. Integrated/RFS Done | 21/4/2025 : Digi OB - 45M Tower - NE site 1924B Bdr Seri Ehsan, Digi OB - 45M 3 Legged Tower - FE site 1439B Jln Dengkil Banting 2 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X ISM8 CARD 2X RTN910 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB A HI 1X ODU 15G XMC5D SUB A LO | MW Swap | MW SWAP LINK 1924B-1439B WITH HUAWEI_15G_4+0_1.2M/1.2M_DP_28MHZ_512QAM_896MBPS_XMC5D_SUB_A_4.61KM_WTIH CA IMPACTED: 1924B DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 CARD AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 CARD AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK | XMC5D | MDD | 15 | 1.2 | 1.2 | GTSB | SQ202505020369-GTSB | GTSB | SQ202504240805-GTSB // SQ202504240806-GTSB | 2025-07-05 | 2025-07-03 | Completed | 2025-05-29 | 2025-06-12 | 2025-05-29 | 2025-05-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-29 | 2025-06-12 | 2025-05-29 | 2025-05-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050947 |  | 2025-05-10 | 2025-05-15 | Completed | 2025-05-09 | 2025-05-10 | 2025-05-09 | 2025-05-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2025-06-08 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2025-06-08 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-18 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2025-06-10 | Aminuddin bin che azibA0563734967123169280 | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2025-05-16 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202507080560-GTSB
4187D_HU | Vnion Bk Minyak (REL) | DU00005275452 | Northern | Penang | 5.306164 | 100.457223 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 110MHz 0.6m/0.6m Sub B 2X RTN 910A 2X 18G 0.6M SP ANTENNA 1X 18G XMC-3E SUB B HI 1X 18G XMC-3E SUB B LO | MW Swap | SWAP MW LINK 4187D-4085B WITH HUAWEI_18G_1+0_110MHZ_0.6M/0.6M_1.04KM EXISTING MW CFG: HW_18GHZ_1+0_56MHZ IMPACTED SITES: 4187D,4085B,4260E,4018L NE 4187D VNION BK MINYAK (REL) 1. Install New RTN910A 2. Install New 18G 0.6m SP Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service FE 4085B BKT TENGAH 2 1. Install New RTN910A 2. Install New 18G 0.6m SP Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service 6. Repatch All Existing LAN Cable towards 2 Port ODF , 1 BBU 4085B & 1 4085B RTN01/RTN02 | NE 4187D VNION BK MINYAK (REL) 1. Install New RTN910A 2. Install New 18G 0.6m SP Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service | FE 4085B BKT TENGAH 2 1. Install New RTN910A 2. Install New 18G 0.6m SP Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service 6. Repatch All Existing LAN Cable towards 2 Port ODF , 1 BBU 4085B & 1 4085B RTN01/RTN02 | XMC3E | MAC SP | 18G | 0.6m | 0.6m | GCI | SQ202506030421-GCI | GCI | SQ202505280624-GCI // SQ202505280628-GCI | 2025-07-04 | 2025-07-04 | Completed | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052032 |  | 2025-05-21 | 2025-05-23 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-26 | 2025-05-31 | 2025-05-26 | 2025-06-03 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2025-05-26 | 2025-05-31 | 2025-05-26 | 2025-06-03 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-27 | 2025-05-26 | 2025-05-31 | 2025-05-26 | 2025-06-12 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | 2025-05-26 | 2025-05-31 | 2025-05-26 | 2025-05-28 | 2025-10-05 | 2025-10-05 | 2025-10-05 | 2025-10-05 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
4639B_HU | Kg Kura | DU00005275453 | Northern | Kedah | 5.935684 | 100.666779 | [7 empty] | 00. Integrated/RFS Done | 25/06: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G 2+0 1.8m/1.8m MAC DP XMC3 sub A/A NE: 1) 1 x RTN910A 2) 1 x ISM8 Card 3) 1 x 13G XMC3 sub A Hi 4) 1 x 13G XMC3 sub A Hi 5) 1 x 13G 1.8m MAC DP FE: 1) 1 x RTN910A 2) 1 x ISM8 Card 3) 1 x 13G XMC3 sub A Lo 4) 1 x 13G XMC3 sub A Lo 5) 1 x 13G 1.8m MAC DP | MW Swap | MW Swap (Linked DU 4106D_HU + 4996B_NIC)) Suggest Activity Flow : 1. 4996B_NIC - Transfer Traffic 4996B 2. 4639B_HU - Additional IF Card Pre Install for 4106D_HU 3. 4106D_HU NE Swap new IDU RTN910A and transfer IF card for existing link FE Swap new IDU RTN910A and transfer IF card for existing link Create 2+0 EPLA NE (4639B KG KURA): 1) Install new RTN910A 2) Add ISM8 card slot 3 3) Install 2+0 link to 4106D at 7-ISM8-1 and 7-ISM8-2 4) Create 2+0 EPLA for Link 4106D 5) Transfer existing link from 4996B RTN01 7-ISM6-1 to new IF Card 3-ISM8-1 6) Transfer existing link from 4638B RTN01 3-ISV3-1 to new IF Card 3-ISM8-2 6) Create Service & Patch 4639B RTN02 GE01 to New 4639B RTN01 GE02 FE (4106D NAMI SBC): 1) Install new RTN910A 2) Add ISM8 card slot 3 3) Install 2+0 link to 4639B RTN01 at 7-ISM8-1 and 7-ISM8-2 4) Create 2+0 EPLA for Link 4639B RTN01 5) Transfer existing link from 4930B RTN01 7-ISM6-1 to new IF Card 3-ISM8-1 6) Create Service | NE (4639B KG KURA): Swap before 4106D_HU 1) Install new RTN910A 2) Add ISM8 card slot 3 3) Install 2+0 link to 4106D at 7-ISM8-1 and 7-ISM8-2 4) Create 2+0 EPLA for Link 4106D 5) Transfer existing link from 4996B RTN01 7-ISM6-1 to new IF Card 3-ISM8-1 6) Transfer existing link from 4638B RTN01 3-ISV3-1 to new IF Card 3-ISM8-2 6) Create Service & Patch 4639B RTN02 GE01 to New 4639B RTN01 GE02 | FE (4106D NAMI SBC): Swap before 4106D_HU 1) Install new RTN910A 2) Add ISM8 card slot 3 3) Install 2+0 link to 4639B RTN01 at 7-ISM8-1 and 7-ISM8-2 4) Create 2+0 EPLA for Link 4639B RTN01 5) Transfer existing link from 4930B RTN01 7-ISM6-1 to new IF Card 3-ISM8-1 6) Create Service | XMC3 | MAC DP | 13G | 1.8m | 1.8m | CCSMY | SQ202505300135-CCS | CCSMY | SQ202505300205-CCS // SQ202505300210-CCS |  |  | Ongoing | 2025-05-20 | 2025-05-22 | 2025-05-21 | 2025-05-21 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051477 |  | 2025-05-15 | 2025-05-19 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-24 | 2025-06-30 | 2025-06-24 |  | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | CCS TI | 2025-06-24 | 2025-06-30 | 2025-06-24 | 2025-07-11 | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | CCS TI | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-06-25 | 2025-06-24 | 2025-06-30 | 2025-06-24 | 2025-08-16 | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | 2025-06-24 | 2025-06-30 | 2025-06-24 | 2025-06-24 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
4106D_HU | Nami SBC (Tx) | DU00005275454 | Northern | Kedah | 6.055474 | 100.762210 | [5 empty] | TI WIP | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G 2+0 1.2m/1.2m MAC DP XMC3 sub A/B NE: 1) 1 x 15G XMC3 sub A Hi 2) 1 x 15G XMC3 sub B Hi 3) 1 x 15G 1.2m MAC DP FE: 1) 1 x RTN910A 2) 1 x 15G XMC3 sub A Lo 3) 1 x 15G XMC3 sub B Lo 4) 1 x 15G 1.2m MAC DP | MW Swap | MW Swap (Linked DU 4639B_HU + 4996B_NIC) Suggest Activity Flow : 1. 4996B_NIC - Transfer Traffic 4996B 2. 4639B_HU - Additional IF Card Pre Install for 4106D_HU 3. 4106D_HU NE Swap new IDU RTN910A and transfer IF card for existing link FE Swap new IDU RTN910A Create 2+0 EPLA NE (4106D NAMI SBC): 1) Install 2+0 link to 4930B at 3-ISM8-1 and 3-ISM8-2 2) Create 2+0 EPLA for Link 4390B 3) Create Service FE (4930B LUBUK MERBAU): 1) Install new RTN910A 2) Install 2+0 link to 4106D RTN01 at 7-ISM8-1 and 7-ISM8-2 4) Create 2+0 EPLA for Link 4106D RTN01 5) Patch GE01 to LL 4930B (reuse the same Port) 6) Create Service | NE (4106D NAMI SBC): 1) Install 2+0 link to 4930B at 3-ISM8-1 and 3-ISM8-2 2) Create 2+0 EPLA for Link 4390B 3) Create Service | FE (4930B LUBUK MERBAU): 1) Install new RTN910A 2) Install 2+0 link to 4106D RTN01 at 7-ISM8-1 and 7-ISM8-2 4) Create 2+0 EPLA for Link 4106D RTN01 5) Patch GE01 to LL 4930B (reuse the same Port) 6) Create Service | XMC3 | MAC DP | 15G | 1.2m | 1.2m | CCSMY | SQ202505240069-CCS | CCSMY | SQ202505240083-CCS // SQ202505240084-CCS | 2025-11-26 | 2025-11-28 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-21 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051478 |  | 2025-05-15 | 2025-05-19 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-27 | 2025-05-31 | 2025-05-27 | 2025-06-04 | IMRAN//JAVED/7021000061 | CCS TI | 2025-05-27 | 2025-05-31 | 2025-05-27 | 2025-06-04 | IMRAN//JAVED/7021000061 | CCS TI | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-05-27 | 2025-05-31 | 2025-05-27 | 2025-06-02 | IMRAN//JAVED/7021000061 | 2025-05-27 | 2025-05-31 | 2025-05-27 | 2025-05-27 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
1621H_LOS | 99 Speedmart TMN GREENWOOD | DU00005007378 | Central | Selangor | 3.233705 | 101.702124 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 17/2/2025 : Cutover done 14/2/2025 : Cutover done with issue 100M speed 13/2/2025 : Installation complete, pending cutover 12/2/2025 : FE installation complete, pending install NE site 10/2/2025 : Digi OB - Small Cell - NE site 1621H 99 Speedmart TMN GREENWOOD, EDOTCO (M) SDN BHD - BOOM 3M ROOFTOP - FE site W00506 B057D_W00506OD_MASJIDRAHIMAH | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | New NLOS Equipment NE_1621H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_W00506 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH cable x 1 | MW New Link / Reroute | Link reroute to new FE W00506 with new NLOS equipment due to LOS block. Site Impacted : 1621H NE_1621H 1.Install Power injector. 2.Install RTN510 Microwave/4.91-5.97GHz/AP/ 3.Install Nlos-Microwave. Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual. polarization/Separate Mount with bracket. 4.Install Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5.Install Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. 6.Traffic migrate to new FE with NLOS new equipment via existing MW link 1621H-NLOS-W00506 7.Decom existing NLOS (1621H-NLOS-1038B), Ensure traffic migrate successful before proceed decom existing equipment. FE_W00506 1.Install Power injector. 2.Install RTN510 Microwave/4.91-5.97GHz/AP/ 3.Install Nlos-Microwave. Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual. polarization/Separate Mount with bracket. 4.Install Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5.Install Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. 6.Traffic migrate to new FE with NLOS new equipment via existing MW link 1621H-NLOS-W00506 7.ETH cable patching to Fiber port & Create new In Band DCN. 8.Decom existing NLOS (1038B-NLOS-1621H) , Ensure traffic migrate successful before proceed decom existing equipment. | Link reroute to new FE W00506 with new NLOS equipment due to LOS block. Site Impacted : 1621H NE_1621H 1.Install Power injector. 2.Install RTN510 Microwave/4.91-5.97GHz/AP/ 3.Install Nlos-Microwave. Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual. polarization/Separate Mount with bracket. 4.Install Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5.Install Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. 6.Traffic migrate to new FE with NLOS new equipment via existing MW link 1621H-NLOS-W00506 7.Decom existing NLOS (1621H-NLOS-1038B), Ensure traffic migrate successful before proceed decom existing equipment. | Link reroute to new FE W00506 with new NLOS equipment due to LOS block. Site Impacted : 1621H FE_W00506 1.Install Power injector. 2.Install RTN510 Microwave/4.91-5.97GHz/AP/ 3.Install Nlos-Microwave. Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual. polarization/Separate Mount with bracket. 4.Install Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5.Install Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable. 6.Traffic migrate to new FE with NLOS new equipment via existing MW link 1621H-NLOS-W00506 7.ETH cable patching to Fiber port & Create new In Band DCN. 8.Decom existing NLOS (1038B-NLOS-1621H) , Ensure traffic migrate successful before proceed decom existing equipment. | [5 empty] | Magicell | SQ202502180246-Magicell | Magicell | SQ202502180514-Magicell // SQ202504260146-Magicell | 2026-01-29 | 2026-01-30 | Completed | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-02-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-02-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-05 | 2025-03-06 | 2025-03-05 | 2025-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-29 | 2026-01-22 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020442 |  | 2025-02-05 | 2025-02-06 | Completed | 2025-02-04 | 2025-02-05 | 2025-02-04 | 2025-02-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-12 | 2025-02-28 | 2025-02-17 | 2025-02-17 | MUHAMAD//SYAZWAN BIN KHIRRUL ANUAR/7018000168 | Magicell TI | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-02-17 | MUHAMAD//SYAZWAN BIN KHIRRUL ANUAR/7018000168 | Magicell TI | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-17 | 2025-02-12 | 2025-02-28 | 2025-03-13 | 2025-03-13 | MUHAMAD//SYAZWAN BIN KHIRRUL ANUAR/7018000168 | 2025-02-12 | 2025-02-28 | 2025-03-10 | 2025-03-10 | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300116-GTSB
9042Z_LOS | RumahLambai_RumahMinda_LadangMapai | DU00005007379 | Sarawak | Sarawak | 2.113270 | 112.284130 | [7 empty] | 00. Site Out/Drop | 4/9/2025 : Doing under DU 9042Z_LOS_1 | TSS |  | 13G_4+0_1.2/1.2_MDD_XMC-5D_SB B 4xISM8 | MW New Link / Reroute | NEW LINK TO 9042Z TO Q01152 WITH 13G_4+0_1.2/1.2MDD_SB B. DISMANTLE EXISITNG 9042Z-9354A. (Existing Tx route: 9042Z-9354A-LL-9368A LOS block. To reroute to new FE. FE options: option 1 9042Z-Q01155 option 2 9042Z-Q01152 option 3 9042Z-9245Z option 4 9042Z-9254B) | NEW LINK TO 9042Z TO Q01152 WITH 13G_4+0_1.2/1.2MDD_SB B. NE: 1. Reuse RTN910A_RTN01. 2. Install new 2xISM8 at slot 3 & 4. 3. Install new XMC-5D_SB B. 4. Install new 13G_1.2m_MDD. 5. Configure 13G_4+0_1.2/1.2_256QAM_CA. | NEW LINK TO 9042Z TO 9245Z WITH 13G_4+0_1.2/1.2MDD_SB B. NE: 1. Reuse RTN910A_RTN01. 2. Install new 2x ISM8 at Slot 3 and 4. 3. Install new XMC-5D_SB B. 4. Install new 13G_1.2m_MDD. 5. Configure 13G_4+0_1.2/1.2_256QAM_CA. | XMC-5D_SB B | MDD | 13G | 1.2 | 1.2 | MTK | SQ202502260445-MTK |  |  | 2025-06-13 | 2025-06-09 | Completed | 2025-02-21 | 2025-02-28 | 2025-02-20 | 2025-02-27 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-09 | 2025-06-13 | 2025-06-09 | 2025-06-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-09 | 2025-06-13 | 2025-06-09 | 2025-06-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-09 | 2025-06-13 | 2025-06-09 | 2025-06-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507080651-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | HSU//MYET CHAE/6799000011
1605B-3230B | Kemuning Green Ville (Kota Kem | DU00005010603 | Central | Selangor | 2.976155 | 101.534896 |  |  |  |  | Cancel / Drop | Done under DU 3230B-1605B TX Mini | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 3230B-1605B TX Mini |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1693B-1612B_1 | Puncak Alam Highway 2 (ZED) | DU00005010604 | Central | Selangor | 3.145270 | 101.474623 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 28/2/2025 : Cutover done 27/2/2025 : Installtion 80% complete due to raining day 24/2/2025 : SBC KJS - 60M 4 Legged Tower - NE site 1693B Puncak Alam Highway 2 (ZED), Digi OB - 60M 4 Legged Tower - FE site 1612B Bkt Cherakah Kapar | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1X ODU 15G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL 1693B-1612B WITH HUAWEI_15G_2+0_1.2M/1.2M_MDD_28MHZ_256QAM_400MBPS_XMC5D_SUB B_7.86KM EPLA WITH EXISTING LINK IMPACTED: 1693B,1465H, B01514 NE: 1. INSTALL NEW ISM8 CARD AT SLOT 3 RTN01 1693B 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 2+0 28MHZ 256QAM EPLA WITH EXISTING FE: 1. INSTALL NEW ISM8 CARD AT SLOT 3 RTN01 1612B 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 2+0 28MHZ 256QAM EPLA WITH EXISTING 5. PATCH TO NEW CP PORT AND DO PORT LAG | 1. INSTALL NEW ISM8 CARD AT SLOT 3 RTN01 1693B 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 2+0 28MHZ 256QAM EPLA WITH EXISTING | 1. INSTALL NEW ISM8 CARD AT SLOT 3 RTN01 1612B 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 2+0 28MHZ 256QAM EPLA WITH EXISTING 5. PATCH TO NEW CP PORT AND DO PORT LAG | 5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202503190673-Magicell | Magicell | SQ202502270723-Magicell // SQ202504260146-Magicell | 2025-07-05 | 2025-07-03 | Completed | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022405 |  | 2025-02-25 | 2025-02-25 | Completed | 2025-02-24 | 2025-02-25 | 2025-02-24 | 2025-02-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-26 | 2025-02-28 | 2025-02-28 | 2025-02-28 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-02-26 | 2025-02-28 | 2025-02-25 | 2025-02-28 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-28 | 2025-02-26 | 2025-02-28 | 2025-03-11 | 2025-03-11 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-10-01: 2025-02-26; 2025-10-01: 2025-02-28; 2025-10-01: 2025-03-03; 2025-10-01: 2025-03-03 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202506050715-GTSB
2633B-1110A | Jalan Mohd Yamin Klang | DU00005010605 | Central | Selangor | 3.029862 | 101.405586 |  |  |  |  | Cancel / Drop | Done under DU 2633B_PostMOCN, 2633B_PostMOCN1 and 2633B_PostMOCN2 TX NIC | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed due to done under DU 2633B_PostMOCN, 2633B_PostMOCN1 and 2633B_PostMOCN2 |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2982A-1412A | Kampung Subang | DU00005010606 | Central | Selangor | 3.159730 | 101.523940 |  |  |  |  | Site Out | Proceed under DU 2982A-1361A TX Mini | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Create new DU 2982A-1361A TX Mini |  |  |  | Cancel / Drop | Divert to new FE(1361A) on 23-05-2025. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
1017L-1355B | Sek 6 Kota Damansara (REL) | DU00005010607 | Central | Selangor | 3.157817 | 101.569983 |  |  |  |  | RFS | Remote Upgrade done | ZTE | 00. Integrated/RFS Done | 24/2/2025 : Cutover done | AA | PAC | 23G_1+0_112MHZ_0.3M/0.6M_512QAM | MW Remote Upgrade | MW REMOTE UPGRADE LINK 1017L-1355B WITH HUAWEI_23G_1+0_112MHZ_0.3M/0.6M_512QAM_XMC3 SUB A_889MBPS | [9 empty] | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-24 | [15 empty] | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
2443A-1156A_1 | Ijok (CELCOM) | DU00005010608 | Central | Selangor | 3.296836 | 101.447680 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 26/2/2025 : Cutover done 25/2/2025 : Installation complete, alignment WIP 24/2/2025 : NE installation complete, pending install FE site due to raining day 23/2/2025 : EDOTCO(M)-CSU - Tower - NE site 2443A Ijok (CELCOM), Digi OB - 60M 4 Legged Tower - FE site 1156A Btg. Berjuntai | TSS+AA+TI | L1+ATP+PAC | 2X 13G 1.2M DP ANTENNA 2x ODU 13G XMC3E SUB A HI 2X ODU 13G XMC3E SUB A LO | MW Parallel Link | MW PARALLEL 2443A-1156A WITH HUAWEI_13G_1+0_1.2M/1.2M_DP_28MHZ_XPIC_512QAM_450MBPS_XMC3_SUB A_10.1KM EPLA WITH EXISTING LINK IMPACTED: 2443A, 2675B, 1584C, 3685C | NE: 1. REUSE EXISTING IDU RTN910 SLOT 3-2 AND SLOT 4-2 2. INSTALL NEW 13G 1.2M DP ANTENNA 3. INSTALL NEW 13G XMC-3 SUB BAND A 4. CONFIGURE LINK 13G 1+0 28MHZ 512QAM XPIC EPLA WITH EXISTING | NE: 1. REUSE EXISTING IDU RTN910 SLOT 3-2 AND SLOT 4-2 2. INSTALL NEW 13G 1.2M DP ANTENNA 3. INSTALL NEW 13G XMC-3 SUB BAND A 4. CONFIGURE LINK 13G 1+0 28MHZ 512QAM XPIC EPLA WITH EXISTING | [5 empty] | Magicell | SQ202503190673-Magicell | Magicell | SQ202502270723-Magicell // SQ202504260146-Magicell | 2025-03-13 | 2025-03-14 | Completed | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022107 |  | 2025-02-22 | 2025-02-22 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-02-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-24 | 2026-02-24 | 2025-02-24 | 2025-02-24 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-02-24 | 2026-02-24 | 2025-02-24 | 2025-02-27 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-26 | 2025-02-24 | 2026-02-24 | 2025-02-24 | 2025-02-28 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-10-01: 2025-02-24; 2025-10-01: 2026-02-24; 2025-10-01: 2025-02-24; 2025-10-01: 2025-02-28 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
B02795-2632A | B061A_B02795OD_MERUINDPARK2 | DU00005010609 | Central | Selangor | 3.119620 | 101.453140 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 22/2/2025 : Cutover done 21/2/2025 : Installation complete, pending alignment 10/2/2025 : EDOTCO (M) SDN BHD - RAPOLE 24M LAND - NE site B02795 B061A_B02795OD_MERUINDPARK2, SBC KJS - 45M Monopole - FE site 2632A Ecopark | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2x IDU RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E HI 1X ODU 23G XMC3E LO | MW Swap | MW SWAP LINK SM MW1 B02795-2632A WITH HUAWEI_23G_1+0_112MHZ_0.6M/0.6M_DP_112MHZ_512QAM_XMC3E_SUB B_1.77KM IMPACTED: B02795 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3E SUB BAND B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | XMC3E | DP | 23G | 0.6 | 0.6 | GCI | SQ202503060118-GCI | GCI | SQ202502270715-GCI // SQ202504150088-GCI | 2025-03-22 | 2025-03-20 | Completed | 2025-02-22 | 2025-03-22 | 2025-02-22 | 2025-02-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-19 | 2025-03-20 | 2025-03-19 | 2025-03-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021920 |  | 2025-02-20 | 2025-02-20 | Completed | 2025-02-19 | 2025-02-20 | 2025-02-19 | 2025-02-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-21 | 2025-02-28 | 2025-02-20 | 2025-02-21 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-21 | 2025-02-28 | 2025-02-20 | 2025-02-27 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-22 | 2025-02-22 | 2025-02-22 | 2025-02-22 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-22 | 2025-02-21 | 2025-02-28 | 2025-02-20 | 2025-02-27 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-02-21 | 2025-02-28 | 2025-02-20 | 2025-02-27 | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | NG HONG JIE7018000036 | Logistic Team | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
3298A-1080A_1 | pBTS Bandar Botanic (M) | DU00005010610 | Central | Selangor | 2.989340 | 101.425410 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 20/2/2025 : Cutover done 19/2/2025 : Plan change ODU at NE and FE site - Cancel proceed due to shortage ODU bracket 10/2/2025 : Digi OB - 25M PBTS - NE site 3298A pBTS Bandar Botanic (M), Digi OB - 3M RT - Wall Mounted Pole - FE site 1080A WIT | TSS+AA+TI+Dismantle | L1+ATP+PAC | 1X 23G XMC-3E SUB B HI 1X 23G XMC-3E SUB B LO | MW Swap | MW SWAP UPGRADE LINK 3298A-1080A WITH HUAWEI_23G_2+0_112MHZ_0.6M/0.6M_DP_512QAM_XMC-3_SUB A & B_1778MBPS_0.72KM EXISTING LINK 23G 1+0 IMPACTED: 3298A, 1425H NE: 1. REUSE EXISTING IDU RTN910 2. DECOM EXISTING ANTENNA 23G 0.6M DP ANTENNA AND RE-INSTALL AT HIGHER HEIGHT DUE TO BLOCK BY TNB POWER LINE 3. ADDING INSTALL NEW 23G XMC-3 SUB BAND B AT POLAR H 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM AT EXISTING LINK 5. PATCH NLOS 1425H TO HW IDU FE: 1. REUSE EXISTING IDU RTN910 2. DECOM EXISTING ANTENNA 23G 0.6M DP ANTENNA AND RE-INSTALL AT LOWER HEIGHT DUE TO BLOCK BY TNB POWER LINE 3. ADDING INSTALL NEW 23G XMC-3 SUB BAND B AT POLAR H 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM AT EXISTING LINK | NE: 1. REUSE EXISTING IDU RTN910 2. REUSE EXISTING 23G 0.6M DP ANTENNA 3. ADDING INSTALL NEW 23G XMC-3 SUB BAND B AT POLAR H 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM AT EXISTING LINK 5. PATCH NLOS 1425H TO HW IDU | FE: 1. REUSE EXISTING IDU RTN910 2. DECOM EXISTING ANTENNA 23G 0.6M DP ANTENNA AND RE-INSTALL AT LOWER HEIGHT DUE TO BLOCK BY TNB POWER LINE 3. ADDING INSTALL NEW 23G XMC-3 SUB BAND B AT POLAR H 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM AT EXISTING LINK | [5 empty] | Magicell | SQ202502120386-Magicell | Magicell | SQ202502270723-Magicell // SQ202504260146-Magicell | 2025-07-03 | 2025-06-30 | Completed | 2025-02-06 | 2025-02-06 | 2025-02-06 | 2025-02-06 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-12 | 2025-02-12 | 2025-02-12 | 2025-02-12 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-30 | 2025-07-03 | 2025-06-30 | 2025-06-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020437 |  | 2025-02-05 | 2025-02-06 | Completed | 2025-02-04 | 2025-02-05 | 2025-02-04 | 2025-02-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-19 | 2025-02-28 | 2025-02-19 | 2025-02-19 | MUHAMAD//SYAZWAN BIN KHIRRUL ANUAR/7018000168 | Magicell TI | 2025-02-19 | 2025-02-28 | 2025-02-19 | 2025-02-27 | MUHAMAD//SYAZWAN BIN KHIRRUL ANUAR/7018000168 | Magicell TI | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-20 | 2025-02-19 | 2025-02-28 | 2025-02-19 | 2025-03-13 | MUHAMAD//SYAZWAN BIN KHIRRUL ANUAR/7018000168 | 2025-10-01: 2025-02-19; 2025-10-01: 2025-02-28; 2025-10-01: 2025-02-19; 2025-10-01: 2025-03-10 |  |  | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358
4410K | BUKIT9 | DU00005018180 | Northern | Kedah | 5.586150 | 100.680948 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cable x 1. | MW IDU Patching | Util 100% of 1G Port. 1. 4410K_RTN01 . RTN01_GE2 to RTN02_GE2 , Patching with ETH cable. | 1. 4410K_RTN01 . GE1 transfer to GE3 Optical with 10G SFP Module + 1 Pair Patch Cord Fiber cables. | [6 empty] | CCSMY | SQ202503190701-CCS | CCSMY | SQ202502270734-CCS // SQ202504260175-CCS | 2025-08-06 | 2025-08-06 | Completed | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25012498 |  | 2025-01-25 | 2025-02-04 | Completed | 2025-01-24 | 2025-01-25 | 2025-01-24 | 2025-02-04 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-13 | 2025-03-31 | 2025-02-21 | 2025-03-13 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2025-02-21 | 2025-02-28 | 2025-02-21 | 2025-03-13 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-02-21 | 2025-02-28 | 2025-02-21 | 2025-03-06 | Arif//Afif Bin Mohd Zabidi/7021000041 | 2025-10-01: 2025-02-21; 2025-10-01: 2025-02-28; 2025-10-01: 2025-02-21; 2025-10-01: 2025-03-05 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250716-GCI | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
7081Z_LOS | BerakanMajuEstate | DU00005018181 | Sabah | Sabah | 6.237397 | 117.483281 |  |  |  |  | RFS | Pending RFS declare |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+PAC | 13G 4+0 1.2m/1.2m DP XMC3 sub AB NE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 13G XMC3 sub A Lo 4) 1 x 13G XMC3 sub B Lo 5) 1 x 13G 1.2m DP + waveguides FE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 13G XMC3 sub A Hi 4) 1 x 13G XMC3 sub B Hi 5) 1 x 13G 1.2m DP + waveguides | MW New Link / Reroute | Existing MW link LOS block. Reroute to new FE NE (7081Z): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Patch existing RTN950A GE2 to new RTN GE1 5) Patch existing RTN03 GE1 to new RTN GE2 6) Migrate traffic to new link 7) Decom old link FE (S00768): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Patch new RTN GE1 to existing SM IDU 5) Migrate traffic to new link. Create DCN for all NEs involved 6) Decom old link | NE (7081Z): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Patch existing RTN950A GE2 to new RTN GE1 5) Patch existing RTN03 GE1 to new RTN GE2 6) Migrate traffic to new link 7) Decom old link | FE (S00768): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Patch new RTN GE1 to existing SM IDU 5) Migrate traffic to new link. Create DCN for all NEs involved 6) Decom old link | XMC3 | DP | 13G | 1.2m | 1.2m | YPTT | SQ202502180267-YPTT | NR services | SQ202504210220-NR Services // SQ202504210225-NR Services // SQ202504260199-NR Services | 2025-07-11 | 2025-07-07 | Completed | 2025-02-15 | 2025-02-15 | 2025-02-17 | 2025-02-17 | DOMINIC DAVIES6794000049 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031646 |  | 2025-03-17 | 2025-03-28 | Completed | 2025-03-16 | 2025-03-17 | 2025-03-16 | 2025-03-28 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-10 | 2025-05-10 | 2025-04-10 | 2025-04-14 | WILFRED BALANG7167000026 | NR Service TI | 2025-04-10 | 2025-05-10 | 2025-04-10 | 2025-04-14 | WILFRED BALANG7167000026 | NR Service TI | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-04-10 | 2025-05-10 | 2025-04-10 | 2025-04-19 | WILFRED BALANG7167000026 | 2025-10-01: 2025-04-10; 2025-10-01: 2025-05-10; 2025-10-01: 2025-04-10; 2025-10-01: 2025-04-11 |  |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016
1149A-3761A | KJS Bukit Beruntung | DU00005018182 | Central | Selangor | 3.412976 | 101.541967 | WK10 | MAR 25 | WK10 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 8/3/2025 : Cutover done 7/3/2025 : FE site patching done, NE site patching WIP 6/3/2025 : Plan to do IDU patching - PMSC pending, cancel proceed due to pending apply PMSC 7/2/2025 : SBC KJS - 60M 4 Legged Tower - NE site 1149A KJS Bukit Beruntung, OSI TECHNOLOGY SDN BHD - 30M Monopole - FE site 3761A Jalan Kantan 2H, SH COMMUNICATION - LAMP POLE 24M ROOFTOP - Patching site B02213 B065B_B02213OD_SENTOSAINDUSTRI | TSS+TI | L1+ATP+PAC | SFP 1km and patch cord | MW IDU Patching | Offload 1149A traffic from MW link 1149A-1066A Tx route before: 1149A-1166A Tx route after: 1149A-3761A/B02213 Impact site: 1149A To include 2794C in CRQ request due to temporary traffic interruption during IDU patching process. NE (1149A): 1) Change patching RTN10 GE1 direct to RTN05 GE2 (bypass RTN03) 2) Transfer 1149A BBU to RTN03 GE1 3) Migrate 1149A to new route FE (3761A/B02213): 1) Patch RTN02 to xC PTN (use optical) 2) Migrate 1149A to new route 3) Create DCN | NE (1149A): 1) Change patching RTN10 GE1 direct to RTN05 GE2 (bypass RTN03) 2) Transfer 1149A BBU to RTN03 GE1 3) Migrate 1149A to new route | FE (3761A/B02213): 1) Patch RTN02 to xC PTN (use optical) 2) Migrate 1149A to new route 3) Create DCN | [5 empty] | MTK | SQ202503190677-MTK | MTK | SQ202503200174-MTK // SQ202504260152-MTK | 2025-05-24 | 2025-05-23 | Completed | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-06 | 2025-05-07 | 2025-05-06 | 2025-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-06 | 2025-05-07 | 2025-05-06 | 2025-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-23 | 2025-05-24 | 2025-05-23 | 2025-05-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020434 |  | 2025-02-05 | 2025-02-10 | Completed | 2025-02-04 | 2025-02-05 | 2025-02-04 | 2025-02-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-07 | 2025-03-21 | 2025-03-10 | 2025-03-10 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2025-03-07 | 2025-03-21 | 2025-03-10 | 2025-03-10 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-03-07 | 2025-03-21 | 2025-03-10 | 2025-03-10 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | 2025-10-01: 2025-03-07; 2025-10-01: 2025-03-21; 2025-10-01: 2025-03-07; 2025-10-01: 2025-03-07 |  |  | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | CHEONG/SENG/WAH/7018000306
9318A | Kpg Merdang Gayam (SACOFA) | DU00005039632 | Sarawak | Sarawak | 1.449753 | 110.407135 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x 10G 1km SFP for IBEAM + patch cord | BBU Patching | Change patching BBU to IBEAM from 1G to 10G port (ops team and swap room to assign IBEAM and BBU port) | Change patching BBU to IBEAM from 1G to 10G port (ops team and swap room to assign IBEAM and BBU port) | [6 empty] | Allstar | SQ202502260439-Allstar | Allstar | SQ202502270769-Allstar // SQ202504260202-Allstar | 2025-05-09 | 2025-04-29 | Completed | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-04-29 | 2025-05-09 | 2025-04-29 | 2025-04-29 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-29 | 2025-05-09 | 2025-04-29 | 2025-04-29 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-29 | 2025-05-09 | 2025-04-29 | 2025-04-29 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021364 |  | 2025-02-20 | 2025-02-20 | Completed | 2025-02-19 | 2025-02-20 | 2025-02-19 | 2025-02-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-25 | MOK//CHUANG YONG/6799000076 |  | 2025-02-25 | 2025-03-03 | 2025-02-24 | 2025-02-26 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-18 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-02-25 | 2025-03-03 | 2025-05-28 | 2025-07-15 | BONG NEE NYEEbong.allstar@gmail.com | 2025-10-01: 2025-02-25; 2025-10-01: 2025-03-03; 2025-10-01: 2025-05-04; 2025-10-01: 2025-05-08 |  |  | 2025-04-22 | 2025-05-22 | 2025-04-22 | 2025-04-22 | IDA//NAJEEHA BINTI MAZLAN/7018000019
7647B_AD | SMK Bum Bum SBC | DU00006397686 | Sabah | Sabah | 4.448181 | 118.691654 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cat 6 cable x1. | BBU Patching | Patch 7647B BBU to 7647B SMK BUM_BUM RTN04 port GE1 | Patch 7647B BBU to 7647B SMK BUM_BUM RTN04 port GE1 | [6 empty] | NR services | SQ202512160988-NR Services | NR services | SQ202512160985-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26021237 |  | 2026-02-13 | 2026-02-26 | Completed | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-26 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-03-24 | 2026-02-24 | 2026-02-26 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-24 | 2026-03-24 | 2026-02-24 | 2026-02-26 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-06 | 2026-02-24 | 2026-03-24 | 2026-02-24 | 2026-02-27 | RALPH O'BRYAN HILARY7167000030 | 2025-10-01: 2026-02-24; 2025-10-01: 2026-03-24; 2025-10-01: 2026-02-24; 2025-10-01: 2026-02-25 |  |  | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-16 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512170731-GCI | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | CHEONG/SENG/WAH/7018000306
A00851_AD | FELCRANASARUDDINBELIA | DU00006414658 | Northern | Perak | 4.324200 | 100.952600 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | At far end site A00474 patch IDU A00474-CKT MELINTANG-RTN04 GE1 to PTN 66231-CKTMELINTANG. Impacted site: 1) A00851 Current Tx route: A00851-A00474-A00460 Proposed Tx route: A00851-A00474 |  | At far end site A00474 patch IDU A00474-CKT MELINTANG-RTN04 GE1 to PTN 66231-CKTMELINTANG. Impacted site: 1) A00851 Current Tx route: A00851-A00474-A00460 Proposed Tx route: A00851-A00474 | [5 empty] | GTSB | SQ202601150547-GTSB | GTSB | SQ202601150542-GTSB | 2026-02-28 | 2026-02-20 | Completed | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-20 | 2026-02-21 | 2026-02-20 | 2026-02-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011445 |  | 2026-01-15 | 2026-01-22 | Completed | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-11 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-10-01: 2026-01-31; 2025-10-01: 2026-02-28; 2025-10-01: 2026-01-31; 2025-10-01: 2026-02-07 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170724-GCI | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | EZRIN TASNIM BIN ABDUL GANI6798000128
W00687-W00417 | Wangsaria Condo | DU00003793826 | Central | Kuala Lumpur | 3.135300 | 101.665260 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 17/2/2025 : Cutover done 14/2/2025 : Installation complete, pending alignment 10/2/2025 : EDOTCO (M) SDN BHD - BOOM 3M ROOFTOP - NE site W00687 Wangsaria Condo, EDOTCO (M) SDN BHD - INBUILDING - FE site W00417 W066V_W00417OD_PR_NST | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2+0_23G_XMC3_512Q_56M_889M_(0.6m,0.6m) | MW Swap | NE: 1. Reuse existing IDU 910A (Installation from W01416-W00687). Install 1x ISM8 Card at Slot 3. 2. Swap existing Antenna with 0.6m DP Antenna. 3. Swap existing ODU with 23G 2+0 XMC3 ODU (Sub A and Sub B). 4. Configure link 23G 2+0 512QAM 56Mhz and EPLA. FE: 1. Swap existing IDU with new IDU 910A. 2. Swap existing Antenna with 0.6m DP Antenna. 3. Swap existing ODU with 23G 2+0 XMC3 ODU (Sub A and Sub B). 4. Configure link 23G 2+0 512QAM 56Mhz and EPLA. 5. Impact sites: W00687 & W01416 | [7 empty] | GCI | SQ202502260369-GCI | GCI | SQ202502180507-GCI // SQ202504150088-GCI | 2025-03-10 | 2025-03-11 | Completed | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-02-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO | 2025-02-20 | 2025-02-19 | Completed | 2025-02-19 | 2025-02-20 | 2025-02-19 | 2025-02-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-14 | 2025-02-20 | 2025-02-13 | 2025-02-21 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-14 | 2025-02-20 | 2025-02-13 | 2025-02-27 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-02-14 | 2025-02-20 | 2025-02-13 | 2025-02-27 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-02-14 | 2025-02-20 | 2025-02-13 | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | NG HONG JIE7018000036 | Logistic Team | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
4673C-P00269 | Pine Residence | DU00003911391 | Northern | Penang | 5.381510 | 100.275338 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Solution Provided Under DU00002041147 , current utilization 50% , cancel / Drop DU00003911391 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4956C-K00089 | Jalan Tiong SP | DU00003911392 | Northern | Kedah | 5.656601 | 100.497510 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 23/07: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0 TO 23G_2+0_0.6/0.6_DP 2xXMC 3 SB A | MW Swap | MW SWAP 4956C-4637A FROM 23G_1+0 TO 23G_2+0_0.6/0.6_DP_SB B,A | MW SWAP 4956C-4637A FROM 23G_1+0 TO 23G_2+0_0.6/0.6_DP_SB B,A NE: 1. Reuse existing RTN910A. 2. Reuse exisitng XMC-3 SB B. 3. Install new XMC-3 SB A. 4. Swap exisitng antenna with 23G_0.6m_DP. 5. Configure 23G_2+0_0.6/0.6_EPLA. | MW SWAP 4956C-4637A FROM 23G_1+0 TO 23G_2+0_0.6/0.6_DP_SB B,A FE: 1. Install new RTN910A at 4637A Digi cabinet 2. Reuse exisitng XMC-3 SB B. 3. Install new XMC-3 SB A. 4. Swap exisitng antenna with 23G_0.6m_DP. 5. Configure 23G_2+0_0.6/0.6_EPLA. | XMC-3 SB A,B |  | 23 | 0.6 | 0.6 | CCSMY | SQ202510010663-CCS | CCSMY | SQ202507190093-CCS // SQ202507190094-CCS | 2025-10-10 | 2025-10-04 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-03 | 2025-10-10 | 2025-10-03 | 2025-10-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061154 |  | 2025-06-12 | 2025-06-19 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-07-31 | 2025-07-22 |  | SAFDAR//HUSSAIN TALIB/7021000081 | CCS TI | 2025-07-22 | 2025-07-31 | 2025-07-22 | 2025-07-22 | SAFDAR//HUSSAIN TALIB/7021000081 | CCS TI | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-07-23 | 2025-07-22 | 2025-07-31 | 2025-07-22 | 2025-08-01 | SAFDAR//HUSSAIN TALIB/7021000081 | 2025-07-22 | 2025-07-31 | 2025-07-22 | 2025-07-22 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505070167-GTSB | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | HSU//MYET CHAE/6799000011
9038B-9056A | Simunjan 2 | DU00003911393 | Sarawak | Sarawak | 1.383822 | 110.760558 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_0.6/0.6_112Mhz_SB B | MW Swap | MW SWAP 9038B-9056A WITH 23G_1+0_0.6/0.6_112Mz. NE: 1. Swap existing IDU with RTN910A. 2. Swap with XMC-3_SB B. 3. Swap exisitng antenna with 23G_0.6m. 4. Configure 23G_1+0_0.6m_112mHz 5. Dismantle NEC link. FE: 1. Swap existing IDU with RTN910A. 2. Swap with XMC-3_SB B. 3. Swap exisitng antenna with 23G_0.6m. 4. Configure 23G_1+0_0.6m_112mHz 5. Dismantle NEC link. | [7 empty] | Trintel | SQ202501140167-Trintel | Trintel | SQ202502120283-Trintel // SQ202504260214-Trintel | 2025-01-10 | 2025-01-09 | Completed | 2025-01-07 | 2025-01-08 | 2025-01-07 | 2025-01-08 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-08 | 2025-01-08 | 2025-01-08 | 2025-01-08 | CHRISTINE IVY ANAK GIRIN7667000067 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-09 | 2025-01-10 | 2025-01-09 | 2025-01-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25012120 |  | 2025-01-22 | 2025-01-22 | Completed | 2025-01-21 | 2025-01-22 | 2025-01-21 | 2025-01-22 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-22 | 2025-02-22 | 2025-02-07 | 2025-02-07 | ALBERT//TAY KAI WEN/7667000070 | Trintel TI | 2025-01-22 | 2025-02-22 | 2025-02-04 | 2025-02-10 | ALBERT//TAY KAI WEN/7667000070 | Trintel TI | 2025-02-06 | 2025-02-06 | 2025-02-06 | 2025-02-06 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-01-22 | 2025-02-22 | 2025-04-28 | 2025-04-28 | ALBERT//TAY KAI WEN/7667000070 | 2025-01-22 | 2025-02-22 | 2025-02-05 | 2025-02-05 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-04 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
4571C-4966A | Kulim Landmark | DU00003911394 | Northern | Kedah | 5.384560 | 100.546143 | WK36-40 | SEP 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 14/10: Pending Site DO | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE_4571C a. 2xXMC_3E ODU , sub (A,B_Lo). b. 18G_DP_0.6M FE_4966A a. 2xXMC_3E ODU , sub (A,B_Hi). | MW Swap | Existing 18G_1+0_56M Hardware upgrade 18G_1+0_56M to 18G_2+0_112M with EPLA , Existing 15G_2+0_28M has been decom , therefore , plan upgrade to 18G_2+0_112M. Site Impacted: 4571C. NE_4571C. 1.Install new 2xXMC_3E ODU, sub (A,B_Lo) to config 18G_2+0. 2.Configure existing 7_ISM8_1+0 to 2+0 with EPLA. 3.Configure 56Mhz to 112Mhz for 18G link. 4.Install new 0.6DP antenna. 5.Decom existing 18G_XMC_3 ODU x 1. 6.Apply EPLA 8G_2+0. FE_4966A 1.Install new 2xXMC_3E ODU, sub (A,B_Hi) to config 18G_2+0. 2.Configure existing 3_ISM8_1+0 to 2+0 with EPLA 3.Configure 56Mhz to 112Mhz for 18G link. 4.Reuse existing 1.2DP antenna. 5.Decomm existing 1x18G_XMC_3 ODU. 6.Apply EPLA 18G_2+0 parallel link. 7.Enable additional GE port 2 patching to Ibeam/PFS. 8.Create physical LAG for existing GE port1 & New GE port 2. | [7 empty] | CCSMY | SQ202411140303-CCS | CCSMY | SQ202411150552-CCS // SQ202504260175-CCS // SQ202512190225-CCS |  |  | Ongoing | 2024-12-28 | 2024-12-28 | 2024-12-28 | 2024-12-28 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24110814 |  | 2024-11-09 | 2024-11-12 | Completed | 2024-11-08 | 2024-11-09 | 2024-11-08 | 2024-11-12 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-28 | 2024-12-06 | 2024-11-28 | 2025-03-07 | MOHD//FADZRI BIN SUFIAN/7021000033 | CCS TI | 2024-11-28 | 2024-12-06 | 2024-11-28 | 2025-07-06 | MOHD//FADZRI BIN SUFIAN/7021000033 | CCS TI | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-26 | 2024-11-28 | 2024-12-06 | 2024-11-28 | 2026-04-01 | MOHD//FADZRI BIN SUFIAN/7021000033 | 2024-11-28 | 2024-12-06 | 2024-11-28 | 2024-11-28 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 |  | Assign Subcon
4675A-4669A | Mergong Barrage | DU00003911395 | Northern | Kedah | 6.117881 | 100.343221 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M_CA. NE_4675A. 13G_DP_1.2m(MDD) x1. ISM8 x2. XMC_5D , Sub _ B_Lo x1. FE_4669A. 13G_DP_1.2m(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub_B_Hi x1. | MW Parallel Link | Existing link 15G_4+0_28M_CA. Establish new parallel link 13G_4+0_28M_CA. Site Impacted: 4100K,4675A. NE_4675A. 1.Install new 13G_DP_1.2m(MDD). 2.Install XMC_5D-4+0_CA , Sub B_Lo. 3.Reuse existing 4675A_RTN02. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 as 4+0 config. 5.Create EPLA, service cross connect and CA. 6.Traffic 4100K migrate to new parallel link 13G_4+0_28M_CA. 7.Disconnect the ETH cable between RTN02 & RTN01. 8.No decom due to install new parallel link. FE_4669A. 1.Install new 13G_DP_1.2m(MDD). 2.Install XMC_5D-4+0_CA , Sub B_Hi. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 as 4+0 config. 5.Create EPLA, service cross connect and CA. 6.Traffic 4100K migrate to new parallel link. 7.Create Inband DCN. 8.No decom due to install new parallel link. | [7 empty] | Magicell | SQ202505160534-Magicell | Magicell | SQ202504260072-Magicell // SQ202504260076-Magicell // SQ202507290130-Magicell | 2025-11-26 | 2025-11-28 | Completed | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041375 |  | 2025-04-14 | 2025-04-15 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-15 | 2026-05-05 | 2025-05-15 | 2025-05-22 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | Magicell TI | 2025-05-15 | 2026-05-05 | 2025-05-15 | 2025-07-06 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | Magicell TI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-14 | 2025-05-15 | 2026-05-05 | 2025-05-15 | 2025-08-05 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | 2025-10-01: 2025-05-23; 2025-10-01: 2025-05-23; 2025-10-01: 2025-05-23; 2025-10-01: 2025-05-23 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505190519-GCI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | CHEONG/SENG/WAH/7018000306
4311D-4085A | Jazz Hotel RT | DU00003911396 | Northern | Penang | 5.458003 | 100.309564 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 25/10: Cutover SW Upgrade done. RSL different 6dbm 23/10: Interim solution: To proceed with SW Upgrade activity on existing link before proceed with the proposed solution in EPMS 24/10: Solution released, pending Site BOM | AA | PAC | NE: 1) 1xISM8 FE: 1) 1xISM8 | MW Remote Upgrade | Perform remote upgrade existing MW link 4311D-4085A Existing link is 2+0 (1+0 15G 28MHz + 1+0 18G 56MHz) Upgrade existing 18G link from 56MHz to 112MHz 15G link remain as it is | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300164-GCI | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
1152C_LOS | Jalan Semerah Padi | DU00006357848 | Central | Kuala Lumpur | 3.107642 | 101.741973 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M_256QAM NE_1152C New 23G_0.3M(MAC)+OMT x1. New RTN910AF(RTN02). New XMC_3E, Sub A_Lo x1. New CAT6 cable x1. FE_2876A New 23G_0.3M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 9-34977). New ISM8 x1. New XMC_3E, Sub A_Hi x1. | MW New Link / Reroute | Existing HW MW Link 1152C-1477A, 23G_1+0_112MHZ_256QAM. Install new HW MW Link 1152C-2876A, 23G_1+0_112MHZ_256QAM. Later, decom existing HW MW Link 1152C-1477A, 23G_1+0_112MHZ_256QAM. Site Impacted : 1152C. NE_1152C 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_3E, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching traffic to port 8-EM6-1 of new RTN910A(RTN02). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic 1152C via new HW MW Link 1152C-2876A, 23G_1+0_112MHZ_256QAM. 8.Decom existing HW MW Link 1152C-1477A, 23G_1+0_112MHZ_256QAM. FE_2876A 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01, NEID 9-34977). 3.Insert new ISM8 into slot 03 of existing RTN910A(RTN01, NEID 9-34977). 4.Install new XMC_3E, Sub A_Hi x1. Configure it. 5.Request new xD vlan dcn and vlan services. 6.Migrate traffic 1152C via existing IBeam port at CP 1264A in which similar with existing traffic such as 2876A. 7.Decom existing HW MW Link 1152C-1477A, 23G_1+0_112MHZ_256QAM. | Existing HW MW Link 1152C-1477A, 23G_1+0_112MHZ_256QAM. Install new HW MW Link 1152C-2876A, 23G_1+0_112MHZ_256QAM. Later, decom existing HW MW Link 1152C-1477A, 23G_1+0_112MHZ_256QAM. Site Impacted : 1152C. NE_1152C 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_3E, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching traffic to port 8-EM6-1 of new RTN910A(RTN02). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic 1152C via new HW MW Link 1152C-2876A, 23G_1+0_112MHZ_256QAM. 8.Decom existing HW MW Link 1152C-1477A, 23G_1+0_112MHZ_256QAM. | Existing HW MW Link 1152C-1477A, 23G_1+0_112MHZ_256QAM. Install new HW MW Link 1152C-2876A, 23G_1+0_112MHZ_256QAM. Later, decom existing HW MW Link 1152C-1477A, 23G_1+0_112MHZ_256QAM. Site Impacted : 1152C. FE_2876A 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01, NEID 9-34977). 3.Insert new ISM8 into slot 03 of existing RTN910A(RTN01, NEID 9-34977). 4.Install new XMC_3E, Sub A_Hi x1. Configure it. 5.Request new xD vlan dcn and vlan services. 6.Migrate traffic 1152C via existing IBeam port at CP 1264A in which similar with existing traffic such as 2876A. 7.Decom existing HW MW Link 1152C-1477A, 23G_1+0_112MHZ_256QAM. | XMC_3E | MAC | 23G | 23G_0.3M(MAC)+OMT x1. | 23G_0.3M(MAC)+OMT x1. | GCI | SQ202512120099-GCI | GCI | SQ202512160886-GCI // SQ202512160934-GCI | 2026-01-29 | 2026-01-30 | Completed | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-29 | 2026-01-22 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25120493 |  | 2026-01-05 | 2025-12-06 | Completed | 2025-12-05 | 2026-01-05 | 2025-12-04 | 2025-12-06 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-12 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-13 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-10 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-10-01: 2025-12-02; 2025-10-01: 2025-12-08; 2025-10-01: 2025-12-01; 2025-10-01: 2025-12-02 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280921-GTSB
7125H_AD | 99 Speedmart TMN DESA | DU00006357849 | Sabah | Sabah | 5.876922 | 116.056469 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS Radio (RTN510). NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | NLOS Link reroute to new FE 7238B due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 7125H NE_7125H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (7125H-NLOS-7166A). FE_7238B 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.Traffic migrate to new route FE and with new NLOS radio. 7.Decom existing NLOS Radio (7125H-NLOS-7166A). | NLOS Link reroute to new FE 7238B due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 7125H NE_7125H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (7125H-NLOS-7166A). FE_7238B 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.Traffic migrate to new route FE and with new NLOS radio. 7.Decom existing NLOS Radio (7125H-NLOS-7166A). | NLOS Link reroute to new FE 7238B due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 7125H NE_7125H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (7125H-NLOS-7166A). FE_7238B 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.Traffic migrate to new route FE and with new NLOS radio. 7.Decom existing NLOS Radio (7125H-NLOS-7166A). | [5 empty] | NR services | SQ202512160988-NR Services | NR services | SQ202512190080-NR Services // SQ202512190088-NR Services | 2026-03-14 | 2026-03-13 | Completed | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121201 |  | 2025-12-13 | 2025-12-15 | Completed | 2025-12-12 | 2025-12-13 | 2025-12-12 | 2025-12-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-18 | 2026-01-18 | 2025-12-18 | 2025-12-19 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-12-18 | 2026-01-18 | 2025-12-18 | 2026-01-12 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-07 | 2025-12-18 | 2026-01-18 | 2025-12-18 | 2026-01-12 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2025-12-18 | 2026-01-18 | 2025-12-18 | 2025-12-19 | 2026-02-05 | 2026-02-19 | 2026-02-05 | 2026-02-05 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202511280806-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
7120D_AD | Taman Ketiau WT | DU00006357850 | Sabah | Sabah | 5.871811 | 116.064160 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE 7120D-7604A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB_B_1.83KM IMPACTED: 7120D DISMANTLE EXISTING LINK 7120D-7166A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 7120D-7166A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 7120D-7166A 6. PATCH TO XD LL | XMC3E | MAC | 23G | 0.6 | 0.6 | NR services | SQ202512160988-NR Services | NR services | SQ202512240373-NR Services // SQ202512240383-NR Services |  |  | Ongoing | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Disabled | [9 empty] | Unassigned | Disabled | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25121587 |  | 2025-12-16 | 2025-12-17 | Completed | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-17 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-22 | 2026-01-22 | 2025-12-22 | 2025-12-28 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-12-22 | 2026-01-22 | 2025-12-22 | 2026-01-06 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-30 | 2025-12-22 | 2026-01-22 | 2025-12-22 | 2026-01-06 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2025-12-22 | 2026-01-22 | 2025-12-22 | 2025-12-28 | 2026-02-05 | 2026-02-19 | 2026-02-05 | 2026-02-05 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202511280806-GCI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
S01556_AD | S102A_S01556OD_JLNKGTARADAS | DU00006626189 | Sabah | Sabah | 6.603739 | 117.280500 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1228A_AD | KgJaya Sepakat (Maxis) | DU00006626190 | Central | Selangor | 2.972428 | 101.563193 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X 10G SFP 1KM | MW IDU Patching | Perform 10G patching between 1228A RTN03-1228A RTN01 to solve potential IDU-IDU bottleneck issue 10G SFP PATCHING DUE TO DU: 1183D_AD MW SWAP TO 18G 2+0 112MHZ | Perform 10G patching between 1228A RTN03-1228A RTN01 to solve potential IDU-IDU bottleneck issue 10G SFP PATCHING DUE TO DU: 1183D_AD MW SWAP TO 18G 2+0 112MHZ | [6 empty] | GCI | SQ202602270388-GCI | GCI | SQ202602270382-GCI | 2026-04-15 | 2026-04-20 | Completed | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022622 |  | 2026-02-27 | 2026-03-02 | Completed | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-03-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-12 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-16 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-16 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-10-01: 2026-03-12; 2025-10-01: 2026-03-19; 2025-10-01: 2026-03-12; 2025-10-01: 2026-03-12 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602260549-GCI | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
S00773_AD | S102A_S00773OD_T3_KGRANGGAL | DU00006626191 | Sabah | Sabah | 6.596076 | 117.219595 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1183D_AD | MasjidHidayatul Muttaqin | DU00006626192 | Central | Selangor | 2.979995 | 101.566359 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X ISM8 CARD 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB A HI 1x ODU 18G XMC5D SUB A LO | MW Swap | MW SWAP LINK 1183D-1228A WITH HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_512QAM_1778MBPS_XMC3_SUB_A_LINK_0.91KM IMPACTED: 1183D DISMANTLE EXISTING LINK 1183D RTN01-1228A RTN03 EXCEPT FE IDU NEW LINK USE EXISTING RTN910 IDU 1183D RTN02-1228A RTN03 | 1. INSTALL NEW 1PCS ISM8 AT IDU RTN910 RTN02 SLOT 3 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 1183D RTN01 | 1. REUSE EXISTING IDU RTN910 RTN03 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 1228A MW EXCEPT FE IDU | XMC5D | MDD | 18G | 0.6 | 0.6 | GTSB | SQ202602270377-GTSB | GTSB | SQ202602270370-GTSB // SQ202602270373-GTSB | 2026-03-31 | 2026-03-18 | Completed | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-17 | 2026-03-31 | 2026-03-17 | 2026-03-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-18 | 2026-03-19 | 2026-03-18 | 2026-03-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022621 |  | 2026-02-27 | 2026-02-28 | Completed | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-28 | 2026-03-31 | 2026-02-28 | 2026-03-05 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-02-28 | 2026-03-31 | 2026-02-28 | 2026-03-05 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-02-28 | 2026-03-31 | 2026-02-28 | 2026-03-18 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2025-10-01: 2026-02-28; 2025-10-01: 2026-03-31; 2025-10-01: 2026-02-28; 2025-10-01: 2026-03-03 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602260549-GCI | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
S00774_AD | S102A_S00774OD_KGBONGKOL | DU00006626193 | Sabah | Sabah | 6.702800 | 117.195500 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S01993_AD | SMKKANIBONGAN (KG. RUGADING) | DU00006626194 | Sabah | Sabah | 6.662755 | 117.206483 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S00489_AD | S102A_S00489OD_CB_KGKANIBONGAN | DU00006626195 | Sabah | Sabah | 6.640750 | 117.217350 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S01558_AD | S102A_S01558OD_KGPANGKALAN | DU00006626196 | Sabah | Sabah | 6.652760 | 117.261600 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S01554_AD | S102A_S01554OD_KGGOLOM | DU00006626197 | Sabah | Sabah | 6.608528 | 117.265500 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01838_AD | UOB KUCHING | DU00006756929 | Sarawak | Sarawak | 1.551458 | 110.372030 | [9 empty] | TSS+TI |  |  | MW Re-engineering | Existing link 15G_1+1_28M, Swap existing ODU Hi-Lo. Site Impacted : Q01838. NE_Q01838 1.Swap existing 1+1 15G_Sub B from Hi frequency to Lo frequency channels. 2.if RSL not meeting LB , re-alignment is required. FE_9454A. 1.Swap existing 1+1 15G_Sub B from Lo frequency to Hi frequncy channels. 2.If RSL not meeting LB , re-alignment is required. | Existing link 15G_1+1_28M, Swap existing ODU Hi-Lo. Site Impacted : Q01838. NE_Q01838 1.Swap existing 1+1 15G_Sub B from Hi frequency to Lo frequency channels. 2.if RSL not meeting LB , re-alignment is required. | Existing link 15G_1+1_28M, Swap existing ODU Hi-Lo. Site Impacted : Q01838. FE_9454A. 1.Swap existing 1+1 15G_Sub B from Lo frequency to Hi frequncy channels. 2.If RSL not meeting LB , re-alignment is required. | XMC_3 | MAC | 15G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604280379-GCI | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | CHEONG/SENG/WAH/7018000306
9316B_AD | Taman Kali | DU00006756930 | Sarawak | Sarawak | 1.539286 | 110.376846 | [9 empty] | TSS+AA+TI |  |  | MW Hardware Upgrade | Existing HW MW Link 9316B-9451A, 18G_2+0_112MHz_512QAM_EPLA_1666M. Downgrade to new HW MW Link 9316B-9451A, 18G_2+0_27.5MHz&112MHz_512QAM_EPLA_1057M. Site Impacted : 9316B. NE_9316B 1.Re-use existing 18G_DP_0.6M(HS). 2.Re-use existing XMC_3E, Sub A_Lo x2. 3.Re-use existing RTN910A(RTN01, NEID 9-20122). 4.Re-use existing ISM8 Slot 07 Port 1 & 2. 5.Re-use existing IF cables 2x RUN. 6.Swap existing ODU XMC-3E, Sub Band A_Lo(Horizontal Polarization) with FE site(9451A) ODU XMC-3E, Sub Band A_Hi(Horizontal Polarization). 7.Do not swap ODU XMC-3E, Sub Band A_Lo(Vertical Polarization). Remain Lo. FE_9451A 1.Re-use existing 18G_DP_0.6M(HS). 2.Re-use existing XMC_3E, Sub A_Hi x2. 3.Re-use existing RTN910A(RTN02, NEID 9-20842). 4.Re-use existing ISM8 Slot 07 Port 1 & 2. 5.Re-use existing IF cables 2x RUN. 6.Swap existing ODU XMC-3E, Sub Band A_Hi(Horizontal Polarization) with NE site(9316B) ODU XMC-3E, Sub Band A_Lo(Horizontal Polarization). 7.Do not swap ODU XMC-3E, Sub Band A_Hi(Vertical Polarization). Remain Hi. | Existing HW MW Link 9316B-9451A, 18G_2+0_112MHz_512QAM_EPLA_1666M. Downgrade to new HW MW Link 9316B-9451A, 18G_2+0_27.5MHz&112MHz_512QAM_EPLA_1057M. Site Impacted : 9316B. NE_9316B 1.Re-use existing 18G_DP_0.6M(HS). 2.Re-use existing XMC_3E, Sub A_Lo x2. 3.Re-use existing RTN910A(RTN01, NEID 9-20122). 4.Re-use existing ISM8 Slot 07 Port 1 & 2. 5.Re-use existing IF cables 2x RUN. 6.Swap existing ODU XMC-3E, Sub Band A_Lo(Horizontal Polarization) with FE site(9451A) ODU XMC-3E, Sub Band A_Hi(Horizontal Polarization). 7.Do not swap ODU XMC-3E, Sub Band A_Lo(Vertical Polarization). Remain Lo. | Existing HW MW Link 9316B-9451A, 18G_2+0_112MHz_512QAM_EPLA_1666M. Downgrade to new HW MW Link 9316B-9451A, 18G_2+0_27.5MHz&112MHz_512QAM_EPLA_1057M. Site Impacted : 9316B. FE_9451A 1.Re-use existing 18G_DP_0.6M(HS). 2.Re-use existing XMC_3E, Sub A_Hi x2. 3.Re-use existing RTN910A(RTN02, NEID 9-20842). 4.Re-use existing ISM8 Slot 07 Port 1 & 2. 5.Re-use existing IF cables 2x RUN. 6.Swap existing ODU XMC-3E, Sub Band A_Hi(Horizontal Polarization) with NE site(9316B) ODU XMC-3E, Sub Band A_Lo(Horizontal Polarization). 7.Do not swap ODU XMC-3E, Sub Band A_Hi(Vertical Polarization). Remain Hi. | XMC-3E | HS | 18G | 18G_DP_0.6M(HS) | 18G_DP_0.6M(HS) | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604280383-GTSB
9425A_AD | KUCHING DIGI CENTER | DU00006756931 | Sarawak | Sarawak | 1.554087 | 110.332175 | [9 empty] | TSS+AA+TI+Dismantle |  | NE_9425A Re-use existing 23G_SP_0.6M(MAC)+HSB Coupler. Re-use existing RTN910AF(RTN01, NEID 9-24378). New XMC_3, Sub A_Lo x2. Re-use existing IF cables. FE_9441A Re-use existing 23G_SP_0.6M(MAC)+HSB Coupler. Re-use existing RTN910AF(RTN01, NEID 9-24379) & re-use ISM8 Slot 07 Port 1 & 2. New XMC_3, Sub A_Hi x2. Re-use existing IF cables. | MW Hardware Upgrade | Existing HW MW Link 9425A-9441A, 23G_1+1 HSB_56MHz_1024QAM_491M. Downgrade to new HW MW Link 9425A-9441A, 23G_1+1 HSB_28MHz_256QAM_200M. Site Impacted : 9425A & 9002M. For 9002M traffic require ZTE OPS team to cross check. NE_9425A 1.Re-use existing 23G_SP_0.6M(MAC)+HSB Coupler. 2.New XMC_3, Sub A_Lo x2. 3.Re-use existing RTN910AF(RTN01, NEID 9-24378). 4.Re-use existing ISM8 Slot 07 Port 1 & 2. 5.Re-use existing IF cables 2x RUN. 6.Swap existing ODU XMC-3, Sub Band B_Lo x2 with new XMC_3, Sub A_Lo x2. 7.Build new new HW MW Link 9425A-9441A, 23G_1+1 HSB_28MHz_256QAM_200M. 8.Re-use existing Vlan DCN & Vlan Services. 9.Migrate traffics 9425A & 9002M to new HW MW Link 9425A-9441A, 23G_1+1 HSB_28MHz_256QAM_200M. FE_9441A 1.Re-use existing 23G_SP_0.6M(MAC)+HSB Coupler. 2.New XMC_3, Sub A_Hi x2. 3.Re-use existing RTN910AF(RTN01, NEID 9-24379). 4.Re-use existing ISM8 Slot 07 Port 1 & 2. 5.Re-use existing IF cables 2x RUN. 6.Swap existing ODU XMC-3, Sub Band B_Hi x2 with new XMC_3, Sub A_Hi x2. 7.Build new new HW MW Link 9425A-9441A, 23G_1+1 HSB_28MHz_256QAM_200M. 8.Re-use existing Vlan DCN & Vlan Services. 9.Migrate traffics 9425A & 9002M to existing port of IBeam at CP(9999A). | Existing HW MW Link 9425A-9441A, 23G_1+1 HSB_56MHz_1024QAM_491M. Downgrade to new HW MW Link 9425A-9441A, 23G_1+1 HSB_28MHz_256QAM_200M. Site Impacted : 9425A & 9002M. For 9002M traffic require ZTE OPS team to cross check. NE_9425A 1.Re-use existing 23G_SP_0.6M(MAC)+HSB Coupler. 2.New XMC_3, Sub A_Lo x2. 3.Re-use existing RTN910AF(RTN01, NEID 9-24378). 4.Re-use existing ISM8 Slot 07 Port 1 & 2. 5.Re-use existing IF cables 2x RUN. 6.Swap existing ODU XMC-3, Sub Band B_Lo x2 with new XMC_3, Sub A_Lo x2. 7.Build new new HW MW Link 9425A-9441A, 23G_1+1 HSB_28MHz_256QAM_200M. 8.Re-use existing Vlan DCN & Vlan Services. 9.Migrate traffics 9425A & 9002M to new HW MW Link 9425A-9441A, 23G_1+1 HSB_28MHz_256QAM_200M. | Existing HW MW Link 9425A-9441A, 23G_1+1 HSB_56MHz_1024QAM_491M. Downgrade to new HW MW Link 9425A-9441A, 23G_1+1 HSB_28MHz_256QAM_200M. Site Impacted : 9425A & 9002M. For 9002M traffic require ZTE OPS team to cross check. FE_9441A 1.Re-use existing 23G_SP_0.6M(MAC)+HSB Coupler. 2.New XMC_3, Sub A_Hi x2. 3.Re-use existing RTN910AF(RTN01, NEID 9-24379). 4.Re-use existing ISM8 Slot 07 Port 1 & 2. 5.Re-use existing IF cables 2x RUN. 6.Swap existing ODU XMC-3, Sub Band B_Hi x2 with new XMC_3, Sub A_Hi x2. 7.Build new new HW MW Link 9425A-9441A, 23G_1+1 HSB_28MHz_256QAM_200M. 8.Re-use existing Vlan DCN & Vlan Services. 9.Migrate traffics 9425A & 9002M to existing port of IBeam at CP(9999A). | XMC-3 | MAC | 23G | 23G_SP_0.6M(MAC)+HSB Coupler | 23G_SP_0.6M(MAC)+HSB Coupler | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220807-Allstar |  |  | Ongoing | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI |  |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI |  |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI |  |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI |  |  | Assigned | Ongoing | To be Submitted |  |  |  | 2026-04-30 |  | Ongoing | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI |  |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | [7 empty] | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-10-01: 2026-04-19; 2025-10-01: 2026-04-30; 2025-10-01: 2026-04-19 | [7 empty] | GTSB | SQ202604280383-GTSB
9316B_AD_1 | Taman Kali | DU00006756932 | Sarawak | Sarawak | 1.539286 | 110.376846 | [9 empty] | TSS+AA+TI |  |  | MW Hardware Upgrade | Fallback to original configuration after MCMC audit completed. | Fallback to original configuration after MCMC audit completed. | Fallback to original configuration after MCMC audit completed | XMC-3E | HS | 18G | 18G_DP_0.6M(HS) | 18G_DP_0.6M(HS) | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604280383-GTSB
Q01394_AD | Q124B_Q01394OD_LRGHJTAHA | DU00006756933 | Sarawak | Sarawak | 1.554687 | 110.339029 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | 18G_1+0_56M NE_9228K/Q01394. 18G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub B_Hi x1. FE_9056K/Q00054. 18G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub B_Lo x1.. | MW Parallel Link | Install new parallel link 18G_1+0_56M Site Impacted : Q01394 NE_9228K/Q01394. 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 9228K_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_5D , Sub B_Hi. 5.Create service cross connect. 6.Traffic migrate to new 18G_1+0_56M. 7.Turn Off Existing 23G MW link. FE_9056K/Q00054. 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 9056K_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect. 6.Traffic migrate to new 18G_1+0_56M. 7.Turn Off Existing 23G MW link. | Install new parallel link 18G_1+0_56M Site Impacted : Q01394 NE_9228K/Q01394. 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 9228K_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_5D , Sub B_Hi. 5.Create service cross connect. 6.Traffic migrate to new 18G_1+0_56M. 7.Turn Off Existing 23G MW link. | Install new parallel link 18G_1+0_56M Site Impacted : Q01394 FE_9056K/Q00054. 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 9056K_RTN01 , 3_ISM8-1+0. 3.Install new 3_ISM8-1+0. 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect. 6.Traffic migrate to new 18G_1+0_56M. 7.Turn Off Existing 23G MW link. | B | MDD | 18G | 0.6 | 0.6 | YPTT | SQ202604230191-YPTT | YPTT | SQ202604230183-YPTT // SQ202604230187-YPTT |  |  | Ongoing | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. |  | Assigned | Ongoing | To be Submitted |  |  |  | 2026-04-30 |  | Ongoing | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-21 | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | 2025-10-01: 2026-04-19; 2025-10-01: 2026-04-30; 2025-10-01: 2026-04-19; 2025-10-01: 2026-04-20 | [7 empty] | GCI | SQ202604280379-GCI | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | CHEONG/SENG/WAH/7018000306
9995A_AD | Polar Link Samajaya | DU00006756934 | Sarawak | Sarawak | 1.534729 | 110.393427 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | 23G_1+0_56M_512QAM NE_9995A New 23G_DP_0.6M(MAC) x1. Re-use existing RTN910AF(RTN01, NEID 148-47033). New XMC_3, Sub B_Hi x1. New IF cables with suitable type and length 1x RUN. FE_9061B New 23G_DP_0.6M(MAC) x1. Re-use existing RTN910AF(RTN01, NEID 148-26855). New XMC_3, Sub B_Hi x1. New IF cables with suitable type and length 1x RUN. | MW Parallel Link | Build new Parallel HW MW Link, 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. Site Impacted : 9995A. NE_9995A 1.Install new 23G_DP_0.6M(MAC) x1. 2.Re-use existing RTN910AF(RTN01, NEID 148-47033) and use existing Slot 07 Port1. 3.Install new XMC_3, Sub B_Hi x1 and lay new IF cables with suitable type and length 1x RUN . Configure it. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffics 9995A via new Parallel HW MW Link, 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. 6.Shut down existing HW MW Link 18G_2+0_112MHz_256QAM_EPLA.(Temporary ONLY during MCMC Audit) FE_9061B 1.Install new 23G_DP_0.6M(MAC) x1. 2.Re-use existing RTN910AF(RTN01, NEID 148-26855) and use existing Slot 07 Port1. 3.Install new XMC_3, Sub B_Lo x1 and lay new IF cables with suitable type and length 1x RUN . Configure it. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffics 9995A via existing port at IBeam(CP 9999A). 6.Shut down existing HW MW Link 18G_2+0_112MHz_256QAM_EPLA.(Temporary ONLY during MCMC Audit) | Build new Parallel HW MW Link, 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. Site Impacted : 9995A. NE_9995A 1.Install new 23G_DP_0.6M(MAC) x1. 2.Re-use existing RTN910AF(RTN01, NEID 148-47033) and use existing Slot 07 Port1. 3.Install new XMC_3, Sub B_Hi x1 and lay new IF cables with suitable type and length 1x RUN . Configure it. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffics 9995A via new Parallel HW MW Link, 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. 6.Shut down existing HW MW Link 18G_2+0_112MHz_256QAM_EPLA.(Temporary ONLY during MCMC Audit) | Build new Parallel HW MW Link, 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. Site Impacted : 9995A. FE_9061B 1.Install new 23G_DP_0.6M(MAC) x1. 2.Re-use existing RTN910AF(RTN01, NEID 148-26855) and use existing Slot 07 Port1. 3.Install new XMC_3, Sub B_Lo x1 and lay new IF cables with suitable type and length 1x RUN . Configure it. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffics 9995A via existing port at IBeam(CP 9999A). 6.Shut down existing HW MW Link 18G_2+0_112MHz_256QAM_EPLA.(Temporary ONLY during MCMC Audit) | XMC-3 | MAC | 23G | 23G_DP_0.6M(MAC) x1 | 23G_DP_0.6M(MAC) x1 | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220805-Allstar // SQ202604220807-Allstar |  |  | Ongoing | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI |  |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI |  |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI |  |  | Assigned | Ongoing |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI |  |  | Assigned | Ongoing | To be Submitted |  |  |  | 2026-04-30 | 2026-04-28 | Completed | 2026-04-19 | 2026-04-30 | 2026-04-19 | 2026-04-28 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI |  | 1.00 | Assigned | Completed |  | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-04-19 | 2026-04-19 | 2026-04-19 | 2026-04-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-19 | 2026-04-19 | 2026-04-30 | 2026-04-19 |  | BONG NEE NYEEbong.allstar@gmail.com | 2025-10-01: 2026-04-19; 2025-10-01: 2026-04-30; 2025-10-01: 2026-04-19; 2025-10-01: 2026-04-20 | [7 empty] | GTSB | SQ202604280383-GTSB
9995A_AD_1 | Polar Link Samajaya | DU00006756935 | Sarawak | Sarawak | 1.534729 | 110.393427 | [9 empty] | TSS+TI |  |  | MW Re-engineering | Existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M and existing HW MW Link 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. Site Impacted : 9995A. NE_9995A 1.After completion MCMC Audit, turn ON existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M. 2.Later, perform EPLA in between existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M and existing HW MW Link 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. 3.Become new HW MW Link 9995A-9061B, 23G&18G_3+0_56MHz&112MHz_512QAM&256QAM_EPLA_1984M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffics 9995A via new HW MW Link 9995A-9061B, 23G&18G_3+0_56MHz&112MHz_512QAM&256QAM_EPLA_1984M. FE_9061B 1.After completion MCMC Audit, turn ON existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M. 2.Later, perform EPLA in between existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M and existing HW MW Link 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. 3.Become new HW MW Link 9995A-9061B, 23G&18G_3+0_56MHz&112MHz_512QAM&256QAM_EPLA_1984M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffics 9995A via existing port at IBeam(CP 9999A). | Existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M and existing HW MW Link 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. Site Impacted : 9995A. NE_9995A 1.After completion MCMC Audit, turn ON existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M. 2.Later, perform EPLA in between existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M and existing HW MW Link 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. 3.Become new HW MW Link 9995A-9061B, 23G&18G_3+0_56MHz&112MHz_512QAM&256QAM_EPLA_1984M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffics 9995A via new HW MW Link 9995A-9061B, 23G&18G_3+0_56MHz&112MHz_512QAM&256QAM_EPLA_1984M. | Existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M and existing HW MW Link 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. Site Impacted : 9995A. FE_9061B 1.After completion MCMC Audit, turn ON existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M. 2.Later, perform EPLA in between existing HW MW Link 9995A-9061B, 18G_2+0_112MHz_256QAM_EPLA_1534M and existing HW MW Link 9995A-9061B, 23G_1+0_56MHZ_512QAM_450M. 3.Become new HW MW Link 9995A-9061B, 23G&18G_3+0_56MHz&112MHz_512QAM&256QAM_EPLA_1984M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffics 9995A via existing port at IBeam(CP 9999A). | [5 empty] | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220807-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604280383-GTSB
Q01394_AD_1 | Q124B_Q01394OD_LRGHJTAHA | DU00006756936 | Sarawak | Sarawak | 1.554687 | 110.339029 | [9 empty] | TSS+TI |  |  | MW Re-engineering | Turn on existing 23G 1+0 MW link after MCMC audit completed. Parallel with new 18G 1+0 link under DU ID (Q01394_AD) and create 3+0 EPLA. Apply AA for existing 23G_1+0_112M | Turn on existing 23G 1+0 MW link after MCMC audit completed. Parallel with new 18G 1+0 link under DU ID (Q01394_AD) and create 3+0 EPLA. Apply AA for existing 23G_1+0_112M | Turn on existing 23G 1+0 MW link after MCMC audit completed. Parallel with new 18G 1+0 link under DU ID (Q01394_AD) and create 3+0 EPLA. Apply AA for existing 23G_1+0_112M | A | XMC_3 | 23G | 0.6 | 0.6 | YPTT |  | YPTT |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604280379-GCI
Q01905_AD | Q124D_Q01905OD_IPGBTLINTANG | DU00006756937 | Sarawak | Sarawak | 1.529850 | 110.351800 | [9 empty] | TSS+AA+TI |  |  | MW Hardware Upgrade | Swap ODU Hi/Lo and retune frequency to match AA | Swap ODU Hi/Lo and retune frequency to match AA | Swap ODU Hi/Lo and retune frequency to match AA | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604280383-GTSB
7328H4_EVT | DEWAN SRI PUTATAN | DU00006257005 | Sabah | Sabah | 5.896140 | 116.039150 | [13 empty] | Planning and integration support only for event site 7328H4 DEWAN SRI PUTATAN Tx route: 7328H4/7328H4-7273A-LL-7000A 1) Share port with 7273A at 7000A 2) New NE ID FE IDU 7273A RTN03 3) New NE ID NE IDU 7328H4 RTN01 4) At FE site 7273A patch RTN03 GE2 to existing RTN01 GE3 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
3443A_LOS | JINJANG_UTARA21 | DU00006257015 | Central | Kuala Lumpur | 3.216954 | 101.662449 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M. NE_3443A. 23G_SP_0.6M(MAC) x1. RTN910A XMC_3E , Sub B_Lo x1. FE_2376A/W01218 23G_SP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub B_Hi x1. | MW New Link / Reroute | Reroute existing SM link to new FE 2376A due to LOS Block. Link config 23G_1+0_112M. Site Impacted : 3443A , 1897H. NE_3443A. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Lo. 4.Enable GE2 , ETH patching to existing NLOS 1897H. 5.Enable GE1 , 3443A_BBU patching. 6.Create service cross connect. 7.Traffic migrate to new MW link and new FE routing. 8.Decom existing SM link. FE_2376A/W01218 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect and New Inband DCN. 5.Traffic migrate to new link and new FE routing. 6.Decom existing SM link. | Reroute existing SM link to new FE 2376A due to LOS Block. Link config 23G_1+0_112M. Site Impacted : 3443A , 1897H. NE_3443A. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Lo. 4.Enable GE2 , ETH patching to existing NLOS 1897H. 5.Enable GE1 , 3443A_BBU patching. 6.Create service cross connect. 7.Traffic migrate to new MW link and new FE routing. 8.Decom existing SM link. | Reroute existing SM link to new FE 2376A due to LOS Block. Link config 23G_1+0_112M. Site Impacted : 3443A , 1897H. FE_2376A/W01218 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect and New Inband DCN. 5.Traffic migrate to new link and new FE routing. 6.Decom existing SM link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202511270694-Magicell | GCI | SQ202512020081-GCI // SQ202512020084-GCI | 2025-11-25 | 2025-11-25 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251125B4 |  | 2025-12-26 | 2025-11-28 | Completed | 2025-11-25 | 2025-12-26 | 2025-11-25 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-10 | 2025-12-02 | 2025-12-03 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-03 | 2025-12-10 | 2025-12-02 | 2025-12-12 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-05 | 2025-12-03 | 2025-12-10 | 2025-12-02 | 2025-12-12 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-12-03 | 2025-12-10 | 2025-12-02 | 2025-12-03 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280798-GCI | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | CHEONG/SENG/WAH/7018000306
3970B_POC | Jln Permata 2 | DU00004249186 | Central | Selangor | 2.866717 | 101.491465 |  |  |  |  | Closed | Under MW POC | ZTE | 00. Integrated/RFS Done | Move to CelcomDigi MW POC | NA | NA |  | Cancel / Drop | [8 empty] | GTSB | No PR required-Under MW POC | GTSB | No PR required-Under MW POC |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-01-04 | RONALD SHAN A/L AMBUROSE6800000089
9381A_IPR | Paradom Ferry | DU00006158638 | Sarawak | Sarawak | 2.231840 | 111.787550 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module x2 Fiber Patch Cord x 1 pairs | IDU-IPRAN | Site affected : 9381A , 9370A , 9833B. NE_9381A 1.Install new 10G SFP module at existing 9381A_RTN01_GE3 (ID : 22157). 2.Install new 10G SFP module at new Sacofa Port 10G_ ETH 1-2-4. 3.Patching Fiber patch cord from 10G 9381A_RTN01_GE3 to new 10G SFP Module Sacofa Port ETH 1-2-4. 5.Disconnect ETH cable at old Sacofa Ports and disable unused port and put proper port labelling. 6.Create service cross connect and migrate entire traffic to new sacofa 10G port ETH 1-2-4. | Site affected : 9381A , 9370A , 9833B. NE_9381A 1.Install new 10G SFP module at existing 9381A_RTN01_GE3 (ID : 22157). 2.Install new 10G SFP module at new Sacofa Port 10G_ ETH 1-2-4. 3.Patching Fiber patch cord from 10G 9381A_RTN01_GE3 to new 10G SFP Module Sacofa Port ETH 1-2-4. 5.Disconnect ETH cable at old Sacofa Ports and disable unused port and put proper port labelling. 6.Create service cross connect and migrate entire traffic to new sacofa 10G port ETH 1-2-4. | [6 empty] | Allstar | SQ202510070053-Allstar | Allstar | SQ202510070050-Allstar | 2025-12-25 | 2026-01-05 | Completed | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-19 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-23 | 2025-12-22 | 2025-12-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100734 |  | 2025-10-08 | 2025-10-09 | Completed | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-28 | 2025-11-17 | 2025-11-17 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-10-22 | 2025-10-28 | 2025-12-19 | 2025-12-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-22 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-22 | 2025-10-22 | 2025-10-28 | 2025-12-17 | 2025-12-17 | ROYSTON//AHHOLE/6000038561 | 2025-10-01: 2025-10-22; 2025-10-01: 2025-10-28; 2025-10-01: 2025-11-17; 2025-10-01: 2025-11-17 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202510100632-GCI | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | CHEONG/SENG/WAH/7018000306
9037B_IPR | 10th Mile Bazaar MP | DU00006158639 | Sarawak | Sarawak | 1.425540 | 110.325700 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module x2 Fiber Patch Cord x 1 pairs | BBU Patching | Site Affected 9037B (BBU Site) NE_9037B 1.Install new 10G SFP Module at new sacofa port 10G_ETH 1-2-15 2.Install new 10G SFP Module at 9037B_BBU ( port will be provide by OPS team). 3.Patching Fiber patch cord 10G from 9037B_BBU to new sacofa port 10G_ETH 1-2-15. | Site Affected 9037B (BBU Site) NE_9037B 1.Install new 10G SFP Module at new sacofa port 10G_ETH 1-2-15 2.Install new 10G SFP Module at 9037B_BBU ( port will be provide by OPS team). 3.Patching Fiber patch cord 10G from 9037B_BBU to new sacofa port 10G_ETH 1-2-15. | [6 empty] | Allstar | SQ202510070053-Allstar | Allstar | SQ202510070050-Allstar | 2025-12-18 | 2025-12-17 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100735 |  | 2025-10-15 | 2025-10-09 | Completed | 2025-10-09 | 2025-10-15 | 2025-10-07 | 2025-10-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-09 | 2025-10-15 | 2025-10-17 | 2025-10-17 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-09 | 2025-10-09 | 2025-10-15 | 2025-10-17 | 2025-10-17 | ROYSTON//ANAK RAMSY/6798000228 | 2025-10-01: 2025-10-09; 2025-10-01: 2025-10-15; 2025-10-01: 2025-10-09; 2025-10-01: 2025-10-09 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202510100632-GCI | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | CHEONG/SENG/WAH/7018000306
9481A_IPR | Bkt Djin(TM-Sacofa) | DU00006158640 | Sarawak | Sarawak | 1.539861 | 110.351306 | [7 empty] | 05. Doable |  | TSS+TI |  | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9481A 10G PORT 9481A/9481A-LL-9999A INSTALL 1 10G SFP OPTICAL AT SACOFA PORT ETH 1-1-3 INSTALL 1 10G SFP OPTICAL AT HW 9481A RTN01 8-EM6-3(PORT-3) PATCHING OPTICAL PATCH CORD SACOFA Port ETH 1-1-3 to HW 9481A RTN01 8-EM6-3(PORT-3) RECONFIGURE TRAFFIC FOR ALL SITES: 9481A,9636B, 9273K, 9182K | 9481A 10G PORT 9481A/9481A-LL-9999A INSTALL 1 10G SFP OPTICAL AT SACOFA PORT ETH 1-1-3 INSTALL 1 10G SFP OPTICAL AT HW 9481A RTN01 8-EM6-3(PORT-3) PATCHING OPTICAL PATCH CORD SACOFA Port ETH 1-1-3 to HW 9481A RTN01 8-EM6-3(PORT-3) RECONFIGURE TRAFFIC FOR ALL SITES: 9481A,9636B, 9273K, 9182K | N/A | [5 empty] | Allstar | SQ202510070053-Allstar | Allstar | SQ202510070050-Allstar | 2026-02-10 | 2026-02-04 | Completed | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-04 | 2026-02-10 | 2026-02-04 | 2026-02-04 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100736 |  | 2025-10-08 | 2025-10-09 | Completed | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-21 | 2025-10-28 | 2025-11-14 | 2025-11-14 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-21 | 2025-10-28 |  |  | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | [7 empty] | 2025-10-21 | 2025-10-28 |  |  | ROYSTON//ANAK RAMSY/6798000228 | 2025-10-01: 2025-10-21; 2025-10-01: 2025-10-28 | [7 empty] | GCI | SQ202510100632-GCI | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
9338B_IPR | Ngiu Kee MP | DU00006158641 | Sarawak | Sarawak | 3.172977 | 113.039278 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9338B 10G PORT 9338B/9338B-LL-9106A INSTALL 1 10G SFP OPTICAL AT SACOFA PORT ETH 1-2-2 INSTALL 1 10G SFP OPTICAL AT HW 9338B RTN01 8-EM6-3(PORT-3) PATCHING OPTICAL PATCH CORD SACOFA Port ETH 1-1-3 to HW 9338B RTN01 8-EM6-3(PORT-3) RECONFIGURE TRAFFIC FOR ALL SITES: 9338B, 9936A | 9338B 10G PORT 9338B/9338B-LL-9106A INSTALL 1 10G SFP OPTICAL AT SACOFA PORT ETH 1-2-2 INSTALL 1 10G SFP OPTICAL AT HW 9338B RTN01 8-EM6-3(PORT-3) PATCHING OPTICAL PATCH CORD SACOFA Port ETH 1-1-3 to HW 9338B RTN01 8-EM6-3(PORT-3) RECONFIGURE TRAFFIC FOR ALL SITES: 9338B, 9936A | N/A | [5 empty] | Allstar | SQ202510070053-Allstar | Allstar | SQ202510070050-Allstar | 2026-02-10 | 2026-02-04 | Completed | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-04 | 2026-02-10 | 2026-02-04 | 2026-02-04 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100737 |  | 2025-10-08 | 2025-10-09 | Completed | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-23 | 2025-10-30 | 2026-01-28 | 2026-01-28 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-10-23 | 2025-10-30 | 2026-01-30 | 2026-01-30 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-16 | 2025-10-23 | 2025-10-30 | 2026-02-11 | 2026-02-11 | ROYSTON//AHHOLE/6000038561 | 2025-10-01: 2026-01-28; 2025-10-01: 2026-02-03; 2025-10-01: 2026-01-29; 2025-10-01: 2026-01-29 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202510100632-GCI | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
7511A_HU_1 | KEMBARA SAKTI(CELCOM) | DU00005799640 | Sabah | Sabah | 5.329433 | 119.055700 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI |  | 7G_2+0_28Q_28Mhz_424Mbps NE: 1x ISM8 1x 2.4m DP XMC ant (7G) 1x ODU 7G_XMC-3 sb-J&L_Lo FE: 1x ISM8 1x 2.4m DP XMC ant (7G) 1x ODU 7G_XMC-3 sb-J&L_Hi | MW Parallel Link | THIS LINK MUST DO SURVEY FOR SPACE AND PERFORM FREQUENCY SCANNING TO ENSURE HAS AVAILABE 7G CHANNEL Install new link 7G_2+0_28Q_28Mhz_424Mbps to be parallel with existing link Existing 7G_4+0_424Mbps Link will become 6+0 Impact site: 7510A Recommended to perform freq scanning first due to ch spacing 116 already 2ch used. ODU sb must follow as config | NE: 1.Install ISM8 into slot 4 RTN 03 2. Install new 7G 2.4m DP XMC ant 3. Install new 7G XMC-3 sb A Lo 4. Configure link 7G 2+0 28MHZ 28QAM 5. EPLA existing and new link become 6+0 | FE: 1.Install ISM8 into slot 4 RTN 02 2. Install new 7G 2.4m DP XMC ant 3. Install new 7G XMC-3 sb A Lo 4. Configure link 7G 2+0 28MHZ 28QAM 5. EPLA existing and new link become 6+0 | XMC-3 | XMC | 7G | 2.4m | 2.4m | Seri Pancar | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507190087-GTSB | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
7510A_HU | Tomanggong (Celcom) | DU00005799641 | Sabah | Sabah | 5.388325 | 118.648017 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI |  | 7G_2+0_28M_256QAM_EPLA NE_7510AA New A7S24HS+Coupler x1. Re-use existing RTN910AF(RTN03, NEID 9-23314). New ISM8 x1. New XMC_3, Sub J&L_Lo x2. FE_7511A New A7S24HS+Coupler x1. Re-use existing RTN910AF(RTN02, NEID 9-23317). New ISM8 x1. New XMC_3, Sub J&L_Hi x2. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 2.4M ANTENNA DIS AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 7G & 8G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL.**** Existing HW MW Link 7510A-7511A, 7G&8G_4+0_28&29.65MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA. Later, will combine existing HW MW Link 7510A-7511A, 7G&8G_4+0_28&29.65MHZ_512QAM_EPLA and new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA become 7G&8G_6+0_28&29.65MHZ_512QAM_EPLA. Site Impacted : 7510A. NE_7510A 1.Install new A7S24HS+Coupler x1. 2.Re-use existing RTN910AF(RTN03, NEID 9-23314). 3.Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN03, NEID 9-23314). 4.Install new XMC_3, Sub J,&L_Lo x2. 5.Build new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA. 6.Later, will combine existing HW MW Link 7510A-7511A, 7G&8G_4+0_28&29.65MHZ_512QAM_EPLA and new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA become 7G&8G_6+0_28&29.65MHZ_512QAM_EPLA. FE_7511A 1.Install new A7S24HS+Coupler x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-23317). 3.Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN02, NEID 9-23317). 4.Install new XMC_3, Sub J&L_Hi x2. 5.Build new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA. 6.Later, will combine existing HW MW Link 7510A-7511A, 7G&8G_4+0_28&29.65MHZ_512QAM_EPLA and new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA become 7G&8G_6+0_28&29.65MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 2.4M ANTENNA DIS AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 7G & 8G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL.**** Existing HW MW Link 7510A-7511A, 7G&8G_4+0_28&29.65MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA. Later, will combine existing HW MW Link 7510A-7511A, 7G&8G_4+0_28&29.65MHZ_512QAM_EPLA and new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA become 7G&8G_6+0_28&29.65MHZ_512QAM_EPLA. Site Impacted : 7510A. NE_7510A 1.Install new A7S24HS+Coupler x1. 2.Re-use existing RTN910AF(RTN03, NEID 9-23314). 3.Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN03, NEID 9-23314). 4.Install new XMC_3, Sub J,&L_Lo x2. 5.Build new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA. 6.Later, will combine existing HW MW Link 7510A-7511A, 7G&8G_4+0_28&29.65MHZ_512QAM_EPLA and new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA become 7G&8G_6+0_28&29.65MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 2.4M ANTENNA DIS AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 7G & 8G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL.**** Existing HW MW Link 7510A-7511A, 7G&8G_4+0_28&29.65MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA. Later, will combine existing HW MW Link 7510A-7511A, 7G&8G_4+0_28&29.65MHZ_512QAM_EPLA and new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA become 7G&8G_6+0_28&29.65MHZ_512QAM_EPLA. Site Impacted : 7510A. FE_7511A 1.Install new A7S24HS+Coupler x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-23317). 3.Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN02, NEID 9-23317). 4.Install new XMC_3, Sub J&L_Hi x2. 5.Build new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA. 6.Later, will combine existing HW MW Link 7510A-7511A, 7G&8G_4+0_28&29.65MHZ_512QAM_EPLA and new HW MW Parallel Link 7510A-7511A, 7G_2+0_28MHZ_512QAM_EPLA become 7G&8G_6+0_28&29.65MHZ_512QAM_EPLA. | XMC_3 | HS | 7G | A7S24HS+Coupler x1 | A7S24HS+Coupler x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507190087-GTSB
7018L_HU | Delima Village | DU00005799642 | Sabah | Sabah | 6.036089 | 116.134609 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2xXMC-3 (support 112Mhz) | MW Hardware Upgrade | MW HARDWARE UPGRADE 7018L-7286A_23G_1+0_56mHZ TO 112MHz. CHANGE XMC-3_SUPPORT 112MHz | MW HARDWARE UPGRADE 7018L-7286A_23G_1+0_56mHZ TO 112MHz. NE: Reuse exisiting RTN and Antenna. Change exisitng ODU from XMC-3_112Mz_SB A. Configure 23G_1+0_112Mhz_512QAM_889M | MW HARDWARE UPGRADE 7018L-7286A_23G_1+0_56mHZ TO 112MHz. FE: Reuse exisiting RTN and Antenna. Change exisitng ODU from XMC-3_112Mz_SB A. Configure 23G_1+0_112Mhz_512QAM_889M | XMC-3 SB A (112Mhz) |  | 23 |  |  | NR services | SQ202509130056-NR Services | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-26 | 2025-09-22 | 2025-09-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-26 | 2025-09-22 | 2025-09-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090207 |  | 2025-09-03 | 2025-09-06 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-07 | 2025-10-07 | 2025-09-07 | 2025-09-10 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-09-07 | 2025-10-07 | 2025-09-07 | 2025-09-13 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-12 | 2025-09-07 | 2025-10-07 | 2025-09-07 | 2025-09-19 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-09-07 | 2025-10-07 | 2025-09-07 | 2025-09-09 | 2025-11-03 | 2025-11-24 | 2025-11-03 | 2025-11-03 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507100587-GTSB | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | HSU//MYET CHAE/6799000011
2656B_LOS_1 | Meranti | DU00005806556 | Central | Selangor | 2.969993 | 101.604195 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X IDU RTN910A 1x ODU 23G XMC3E SUB A HI 1x ODU 23G XMC3E SUB A LO 2X 0.6 23G ANTENNA DP | MW New Link / Reroute | MW NEW LINK REROUTE 2656B-B00587 WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB_A_2.3KM IMPACTED: 2656B | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 3. INSTALL NEW 23G 0.6M MAC ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 2656B-1372B | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 3. INSTALL NEW 23G 0.6M MAC ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. PATCHING TO NEW CP PORT 6. DISMANTLE EXISTING LINK 2656B-1372B | XMC3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202507090484-Magicell | Magicell | SQ202507250421-Magicell // SQ202507250427-Magicell | 2025-08-07 | 2025-08-07 | Completed | 2025-07-11 | 2025-07-11 | 2025-07-10 | 2025-07-11 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-08-01 | 2025-07-31 | 2025-07-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-06 | 2025-08-07 | 2025-08-06 | 2025-08-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071436 |  | 2025-07-15 | 2025-07-18 | Completed | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-18 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-28 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-04 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-28 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-02 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | NG HONG JIE7018000036 | Logistic Team | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507190083-GCI | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | NOOR AZLIN/BINTI/TEH KAMARUDDIN/6000034898
7493B_AD | Morisem 2 | DU00005521162 | Sabah | Sabah | 5.417540 | 118.350500 | [7 empty] | 05. Doable |  | TSS+TI |  |  | BBU Patching | Need to patch BBU to RTN03 and Remove IDU cascade within RTN03 and RTN08 | Need to patch BBU to RTN03 and Remove IDU cascade within RTN03 and RTN08 | [6 empty] | NR services |  | NR services | SQ202509090323-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25090201 |  | 2025-09-03 | 2025-09-03 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-03 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-23 | 2026-02-23 | 2026-01-23 |  | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-01-23 | 2026-02-23 | 2026-01-23 |  | LEONARD//EDUAN/6000038538 | NR Service TI | [7 empty] | 2026-01-23 | 2026-02-23 | 2026-01-23 |  | LEONARD//EDUAN/6000038538 | 2025-07-24: 2026-01-23; 2025-07-24: 2026-02-23; 2025-07-24: 2026-01-23 | [7 empty] | GTSB | SQ202505280702-GTSB | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | HSU//MYET CHAE/6799000011
7691B | TUN FUAD T3 | DU00003807070 | Sabah | Sabah | 4.620591 | 118.184266 |  |  |  |  | Drop/Cancel | Drop/Cancel |  | 03. TSS Only | 11/02: site not under HU list( | TSS |  |  | MW Re-engineering | Pathcing BBU at 7263B to Celcom Microwave Link SB02801 Port 1 | [7 empty] | NR services | SQ202501210429-NR Services |  |  | 2025-10-31 | 2025-10-28 | Completed | 2025-02-03 | 2025-02-04 | 2025-02-03 | 2025-02-03 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-15 | 2025-01-17 | 2025-01-15 | 2025-01-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-15 | 2025-01-17 | 2025-01-15 | 2025-01-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25011612 |  |  |  | Not started | [8 empty] | Unassigned | Not started
9135K_HU | DESALAVANG2 | DU00005750758 | Sarawak | Sarawak | 3.374150 | 113.602780 | [6 empty] | ZTE | 05. TI WIP |  | TSS+AA+TI |  | 2x ISM8 1X 1.2m MAC Antenna (13G) 1X 1.8m MAC Antenna (13G) 1x ODU 13G XMC-3 sb_A HI 1x ODU 13G XMC-3 sb_B HI 1x ODU 13G XMC-3 sb_A LO 1x ODU 13G XMC-3 sb_B LO 2x COUPLER 13G and Acessories | MW Parallel Link | Install new mw link 9135K-9353B with Huawei 13G_2+0_28mhz_256QAM_400Mbps_1.2/1.8m_MAC_XMC-3 sb A and B_12.6km. This link will be parallel with existing 13G_2+0_56Mhz_900Mbps. Config EPLA new link and existing link Impact site: 9135K, 9085K, 9128K, 9136K | NE: 1. Install new ISM8 to existing RTN910A slot 3 2. Install new 13G 1.2m MAC Antenna 3. Install new 13G XMC-3 sb A and B with Coupler 4. Configure link 13G 2+0_28MHZ_256QAM 5. Config EPLA with existing link 13G_2+0 | FE: 1. Install new ISM8 to existing RTN910A slot 3 2. Install new 13G 1.8m MAC Antenna 3. Install new 13G XMC-3E sb A and B with coupler 4. Configure link 13G 2+0_28MHZ_256QAM 5. Config EPLA with existing link 13G_2+0 | XMC-3 | MAC | 13G | 1.2m | 1.8m | Magicell | SQ202509030212-Magicell | iEzzpro | SQ202511190855-Iezzpro // SQ202511190857-Iezzpro | 2025-12-02 | 2025-11-26 | Completed | 2025-09-03 | 2025-09-30 | 2025-09-29 | 2025-09-29 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111034 |  | 2025-11-11 | 2025-11-13 | Completed | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-03 | 2026-05-04 | 2026-04-02 | 2026-04-05 | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | 2026-04-03 | 2026-05-04 | 2026-04-02 |  | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | 2026-04-03 | 2026-04-03 | 2026-04-03 |  | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-03 | 2026-04-03 | 2026-05-04 | 2026-04-02 |  | MOHAMAD TARMIZI//ISWANDI/6000060946 | 2025-07-24: 2026-04-03; 2025-07-24: 2026-05-04; 2025-07-24: 2026-04-02; 2025-07-28: 2026-04-03 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507080651-GTSB | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AB.RAHMAN//BIN MAT NOOH/6237001519
7996B54_EVT | MBTS_DATARAN KARNIVAL USAHAWAN PMKS | DU00005750759 | Sabah | Sabah | 5.333130 | 116.152120 | [13 empty] | Planning and integration support only for event site | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
9181X_HU | BT39BTU | DU00005750760 | Sarawak | Sarawak | 3.406580 | 113.493971 | [6 empty] | ZTE | 03. Pending TSSR Submission |  | TSS+AA+TI | L1+ATP+PAC | 2x ISM8 2x 1.2m MDD Antenna (15G) 1x ODU 15G XMC-5D sb A Hi 1x ODU 15G XMC-5D sb A_Lo | MW Parallel Link | Install 15G_2+0_256Qam_28Mhz_400Mbps Parallel with existing link existing 13G_4+0_896Mbps Config EPLA new link and existing Impact site: 9181X, 9135K, 9128K | NE: 1. Insert ISM8 at slot 4 at existing RTN910A 2. Install new 15G 1.2m MDD Antenna 3. Install new 15G XMC-5D sb A 4. Configure link 15G 2+0_ 28MHZ_256QAM 5. Config EPLA with existing link | FE: 1. Insert ISM8 at slot 4 at existing RTN910A 2. Install new 15G 1.2m MDD Antenna 3. Install new 15G XMC-5D sb A 4. Configure link 15G 2+0_ 28MHZ_256QAM 5. Config EPLA with existing link | XMC-5D | MDD | 15G | 1.2m | 1.2m | Magicell | SQ202509030212-Magicell | Allstar | SQ202511190846-Allstar // SQ202511190850-Allstar | 2025-11-24 | 2025-11-17 | Completed | 2025-09-03 | 2025-09-30 | 2025-09-29 | 2025-09-29 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-12 | 2025-11-19 | 2025-11-12 | 2025-11-12 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-17 | 2025-11-24 | 2025-11-17 | 2025-11-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111032 |  | 2025-11-11 | 2025-11-11 | Completed | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-07 | 2026-03-14 | 2026-03-09 | 2026-03-09 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2026-03-07 | 2026-03-14 |  |  | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-14 | 2026-03-07 | 2026-03-14 |  |  | TONI//ANAK KUMBONG/6798000163 | 2025-07-24: 2026-03-07; 2025-07-24: 2026-03-14; 2025-07-24: 2026-03-09; 2025-07-28: 2026-03-09 | [7 empty] | GTSB | SQ202507080651-GTSB | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | AB.RAHMAN//BIN MAT NOOH/6237001519
4942B-4950B | Baling Mxs | DU00004315630 | Northern | Kedah | 5.665358 | 100.917737 | [7 empty] | 00. Integrated/RFS Done | 16/11: MW Remote upgrade done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 4942B-4950B (RTN01-RTN04) 2+0 56MHz To upgrade to 2+0 112MHz Impact site: 4942B,K00680 Tx route: 4942B-4950B NE (4942B RTN01): 1) Configure Tx power, frequency channel and BW 112MHz FE (4950B RTN04): 1) Configure Tx power, frequency channel and BW 112MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
4632B-4281A | Lubuk Saga | DU00004315631 | Northern | Kedah | 5.560245 | 100.559285 | [7 empty] | 00. Integrated/RFS Done | 16/11: MW Remote upgrade done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 4632B-4281A 4+0 (RTN02-RTN04) 1x15G 28MHz 1x15G 56MHz 2x13G 28MHz To convert 13G to 56MHz Impact sites: 4632B,4337C NE (4632B RTN02): 1) Configure channel and BW 56MHz FE (4281A RTN04): 1) Configure channel and BW 56MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
4715D-4053A | Taman Sri Pinang | DU00004315632 | Northern | Penang | 5.406620 | 100.323110 | [7 empty] | 00. Integrated/RFS Done | 29/10: Cutover done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 4715D-4053A-01_ZBAU 1+0 56MHz To upgrade to 1+0 112MHz Impact site: 4715D Tx route: 4715D-4053A NE (4715D RTN01): 1) Configure Tx power, frequency channel and BW 112MHz FE (4053A RTN01): 1) Configure Tx power, frequency channel and BW 112MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
9258B-9699B | Sing Kwong | DU00004315633 | Sarawak | Sarawak | 2.267690 | 111.860961 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done |  | AA | PAC | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M from 9699B-9258B | MW Remote Upgrade | MW Remote Upgrade from 18G_56Mhz to 18G_128QAM_112Mhz NE: 1. Remote upgrade from 56Mhz to 128QAM_112Mhz. 2. Configure 18G_1+0_128QAM_112Mhz. FE: 1. Remote upgrade from 56Mhz to 128QAM_112Mhz. 2. Configure 18G_1+0_128QAM_112Mhz. | [9 empty] | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300174-GCI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | CHEONG/SENG/WAH/7018000306
4549D-4560A | Masjid Kg Seri Kinta | DU00004315634 | Northern | Perak | 4.562233 | 101.065110 | [7 empty] | 00. Integrated/RFS Done | 29/10: Cutover done. Upgrade SW done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 4549D-4560A (RTN01-RTN01) 1+0 56MHz To upgrade to 112MHz Impact site: 4549D Tx route: 4549D-4560A NE (4549D RTN01): 1) Configure Tx power and BW 56MHz FE (4560A RTN01): 1) Configure Tx power and BW 56MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
2642A-2021B | Pinggiran USJ | DU00004315635 | Central | Selangor | 3.047030 | 101.557800 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 29/10: Cutover done. Upgrade SW done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 2642A-2021B (RTN01-RTN02) 1+0 28MHz To upgrade to 56MHz Impact site: 2642A Tx route: 2642A-2021B NE (2642A RTN01): 1) Configure channel and BW 56MHz FE (2021 RTN02): 1) Configure channel and BW 56MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
2069B-1612B_2 | WT_UITMPNCKALAM | DU00004315636 | Central | Selangor | 3.204196 | 101.453258 |  |  | W49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 20/12: Cutover done | TSS+TI | L1+ATP+PAC | FE: 1) 1xISM8 | MW Hardware Upgrade | Existing link 2069B-1612B 4+0 (2069B RTN03-1612B RTN04) 2069B RTN03 7-ISM8-1 to 1612B RTN04 3-ISM6-1 56MHz 2069B RTN03 7-ISM8-2 to 1612B RTN04 3-ISM6-2 28MHz 2069B RTN03 3-ISM8-1 to 1612B RTN04 7-ISM8-1 112MHz 2069B RTN03 3-ISM8-2 to 1612B RTN04 7-ISM8-2 112MHz To convert 56MHz and 28MHz link to 112MHz To replace ISM6 card at 1612B RTN04 slot 3 to ISM8 Impact site: 3804A,2680B,1518C,3651A_6,1608B,1020L NE (2069B RTN03) 1. Upgrade link slot 7-ISM8 to 112MHZ (V 128QAM H 64QAM) 2. Change IF mode to IS8 FE (1612B RTN04) 1. Swap IF card slot 3 to ISM8 2. Upgrade link slot 3 to 112MHz 3. Change IF mode to IS8 (V 128QAM H 64QAM) | [7 empty] | GTSB | SQ202411140220-GTSB | GTSB | SQ202411150545-GTSB // SQ202504260131-GTSB | 2025-07-05 | 2025-07-03 | Completed | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2024-12-31 | laina@girobumi.com.mylaina@girobumi.com.my |  |  | 1.00 | Unassigned | Completed |  | 2025-02-17 | 2025-03-03 | 2025-02-17 | 2025-02-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24103034 |  | 2024-10-31 | 2024-11-05 | Completed | 2024-10-30 | 2024-10-31 | 2024-10-30 | 2024-11-05 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-19 | 2024-12-31 | 2024-12-29 | 2024-12-29 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2024-12-19 | 2024-12-31 | 2024-12-29 | 2025-03-24 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-20 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-12-19 | 2024-12-31 | 2024-12-21 | 2024-12-21 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-07-24: 2024-12-19; 2025-07-24: 2024-12-31; 2025-07-24: 2025-05-10; 2025-07-28: 2025-05-10 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202507080560-GTSB
9570B-9363B_1 | Kampung Hulu Nyalau | DU00004315637 | Sarawak | Sarawak | 3.602191 | 113.426530 | [6 empty] | ZTE | 00. Integrated/RFS Done | 25/11: Cutover done 22/11: EB CRQ approved. Plan W48 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 9570B-9363B-01_ZNIC XPIC 28MHz To upgrade to XPIC 56MHz Impact site: 9570B Tx route: 9570B/Q00674-Q00704/9363B NE (9570B/Q00674-KAMPUNG HULU NYALAU-RTN01): 1) Configure Tx power, frequency channel and BW 56MHz FE (9363B/Q00704-SPG SIMILAJAU-RTN01): 1) Configure Tx power, frequency channel and BW 56MHz | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | SHUJAAT//ALI/6800000124 | [17 empty] | 2024-12-13 | 2025-01-13 | 2024-12-13 | 2024-12-13 | ASTI//GANIS PUTRIANI/6237001358
2049B-2901A_1 | Taman Mas Sepang(Celcom) | DU00004315638 | Central | Selangor | 2.968462 | 101.581551 |  |  |  |  | Cancel / Drop |  | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9004C-9106A_1 | Batu 5 Bintulu | DU00004315639 | Sarawak | Sarawak | 3.193403 | 113.095606 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3688C-3256A_1 | Jalan Desa 1 | DU00004315640 | Central | Selangor | 3.323356 | 101.529859 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Current utilization under DU00001912372 is 63% Only. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
7937A-7935A_2 | Ladang Giram | DU00004315641 | Sabah | Sabah | 4.597610 | 118.190610 |  |  |  |  | Drop/Cancel | Drop | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3569B-1071A_1 | Sg Rasau Toll Shoplot | DU00004315642 | Central | Selangor | 3.063792 | 101.488243 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 2X RTN910 1X 18G 0.6M DP ANTENNA 1X 18G 1.2M DP ANTENNA 1x ODU 18G XMC5DSUB B HI 1X ODU 18G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL LINK 3569B-1071A WITH HUAWEI_18G_2+0_0.6M/1.2M_DP_28MHZ_64QAM_1150MBPS_XMC5D_SUB_B_4.55KM IMPACTED: 1171C, 3464B SHIFT IF CABLE 3367B FROM RTN04 TO RTN03 (INSTALL NEW ISM8 CARD) BREAKCASCADE BETWEEN RTN03 AND RTN04 NEW LINK CARRY 1171C AND 3464B | 1. INSTALL NEW RTN910 WITH NEW 2PCS ISM8 CARD AT SLOT 3 & 4 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 64QAM AT SLOT 7 5. SHIFT IF CABLE 1171C FROM RTN04 TO NEW RTN ISM8 CARD SLOT 3 6. SHIFT IF CABLE 3464B FROM RTN04 TO NEW RTN ISM8 CARD SLOT 4 | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 64QAM AT SLOT 7 5. PATCH TO NEW CP PORT | XMC5D | MDD | 18G | 0.6 | 1.2 | GCI | SQ202506100555-GCI | GCI | SQ202506100578-GCI // SQ202506100586-GCI | 2025-11-27 | 2025-11-26 | Completed | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-06 | 2025-08-07 | 2025-08-06 | 2025-08-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072105 |  | 2025-07-23 | 2025-07-23 | Completed | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-23 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-29 | 2025-08-05 | 2025-07-29 | 2025-07-29 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-29 | 2025-08-05 | 2025-07-29 | 2025-08-05 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-31 | 2025-07-29 | 2025-08-05 | 2025-07-29 | 2025-08-05 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-07-24: 2025-07-29; 2025-07-24: 2025-08-05; 2025-07-24: 2025-07-29; 2025-07-28: 2025-07-29 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506050638-GCI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
3313C-1082A_1 | Jalan Sidang | DU00004315643 | Central | Selangor | 2.939386 | 101.326464 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Already MOCN. Current utilization under DU00002029392 is 53% Only. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
4986A | Binjul | DU00004322409 | Northern | Kedah | 5.576192 | 100.727481 | [7 empty] | 00. Integrated/RFS Done | 28/11: D1: Cutover done | TSS+TI | L1+ATP+PAC | 1. ETH Cat 6 Cable | IDU-IPRAN | Enable new GE port , perform LAG physical Port with existing GE port. | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202411150562-GCI | 2025-04-21 | 2025-04-21 | Completed | 2024-11-30 | 2024-11-30 | 2024-11-30 | 2024-11-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-19 | 2025-04-19 | 2025-04-19 | 2025-04-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241107A6 |  | 2024-11-08 | 2024-11-18 | Completed | 2024-11-07 | 2024-11-08 | 2024-11-07 | 2024-11-18 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-27 | 2024-12-06 | 2024-11-27 | 2024-12-10 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2024-11-27 | 2024-12-06 | 2024-11-27 | 2024-12-04 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-11-27 | 2024-12-06 | 2024-11-27 | 2024-11-28 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-07-24: 2024-11-27; 2025-07-24: 2024-12-06; 2025-07-24: 2024-11-27; 2025-07-28: 2024-11-28 |  |  | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358
K01040-K00321 | PEKAN MALAU | DU00004322666 | Central | Kedah | 5.505261 | 100.729011 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 28/11: D1: Cutover done | TSS+TI | L1+ATP+PAC | 1. ETH Cat 6 cable. | MW IDU Patching | At K00321/4423K 1.Enable GE Port, interconnect existing SM IDU (NT05903 Bakai) to 4423K_RTN01. 2.Create In band DCN and traffic route to 4986A CP via link Huawei 4423K-4986A. | [7 empty] | GCI | SQ202411140211-GCI | GCI | SQ202411150539-GCI // SQ202504150088-GCI | 2025-01-13 | 2025-01-13 | Completed | 2024-11-30 | 2024-11-30 | 2024-11-30 | 2024-11-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241107A8 |  | 2024-11-08 | 2024-11-18 | Completed | 2024-11-07 | 2024-11-08 | 2024-11-07 | 2024-11-18 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-27 | 2024-12-06 | 2024-11-27 | 2024-12-06 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2024-11-27 | 2024-12-06 | 2024-11-27 | 2024-12-06 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-11-27 | 2024-12-06 | 2024-11-27 | 2024-11-28 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-07-24: 2024-11-27; 2025-07-24: 2024-12-06; 2025-07-24: 2024-11-27; 2025-07-28: 2024-11-28 |  |  | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
1077B | Penchala Link Tunnel -CAS(ZED) | DU00004345170 | Central | Kuala Lumpur | 3.164250 | 101.632324 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_1077B/W00308 New 23G_DP_0.6M(MAC)+OMT x1. New RTN910A(RTN01). New XMC_3E, Sub B_Lo x1. FE_B00632 New 23G_DP_1.2M(MS) x1. New RTN910A(RTN01). New XMC_3E, Sub B_Hi x1. New 23G Flexi WG x1. New Optical SFP Module 1.25G 10Km x2. New Optical Patch Cord with suitable type and suitable length x1. | MW Swap | Existing HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M. Install new HW MW Link 1077B(RTN01)-B00632(RTN01), 23G_1+0_112MHZ_512QAM. **IMPORTANT NOTE: 1. EXISTING HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M CURRENTLY DCN LOSSCOMM. 2. MANDATORY TO PERFORM TSS & LOS SURVEY AT 1077B/W00308 FIRST TO CONFIRM STRUCTURE TYPE AND LOS CLEARANCES STATUS TOWARD FE(B00632). 3. DO NOT DECOM IF OTHER TRAFFIC STILL BACKHAUL USING EXISTING HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M.** Later, decom existing HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M. Site Impacted : 1077B. NE_1077B/W00308 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub B_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new xC vlan dcn and vlan services. 7.Migrate traffic 1077B via new HW MW Link 1077B(RTN01)-B00632(RTN01), 23G_1+0_112MHZ_512QAM. 8.Decom existing HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M after confirm no other traffic backhauled via this link. FE_B00632 1.Install new 23G_DP_1.2M(MS) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub B_Hi. Configure it. 4.Enable port 8-EM6-3 of new RTN910A(RTN01) and insert Optical SFP Module 1.25G 10Km. 5.Enable port Gi0/6/5 at PTN/Cisco B00632 and insert Optical SFP Module 1.25G 10Km. 6.Patching port 8-EM6-3 of new RTN910A(RTN01) to new port Gi0/6/5 at PTN/Cisco B00632. 7.Request new xC vlan dcn and vlan services. 8.Decom existing HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M after confirm no other traffic backhauled via this link. | Existing HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M. Install new HW MW Link 1077B(RTN01)-B00632(RTN01), 23G_1+0_112MHZ_512QAM. **IMPORTANT NOTE: 1. EXISTING HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M CURRENTLY DCN LOSSCOMM. 2. MANDATORY TO PERFORM TSS & LOS SURVEY AT 1077B/W00308 FIRST TO CONFIRM STRUCTURE TYPE AND LOS CLEARANCES STATUS TOWARD FE(B00632). 3. DO NOT DECOM IF OTHER TRAFFIC STILL BACKHAUL USING EXISTING HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M.** Later, decom existing HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M. Site Impacted : 1077B. NE_1077B/W00308 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub B_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new xC vlan dcn and vlan services. 7.Migrate traffic 1077B via new HW MW Link 1077B(RTN01)-B00632(RTN01), 23G_1+0_112MHZ_512QAM. 8.Decom existing HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M after confirm no other traffic backhauled via this link. | Existing HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M. Install new HW MW Link 1077B(RTN01)-B00632(RTN01), 23G_1+0_112MHZ_512QAM. **IMPORTANT NOTE: 1. EXISTING HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M CURRENTLY DCN LOSSCOMM. 2. MANDATORY TO PERFORM TSS & LOS SURVEY AT 1077B/W00308 FIRST TO CONFIRM STRUCTURE TYPE AND LOS CLEARANCES STATUS TOWARD FE(B00632). 3. DO NOT DECOM IF OTHER TRAFFIC STILL BACKHAUL USING EXISTING HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M.** Later, decom existing HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M. Site Impacted : 1077B. FE_B00632 1.Install new 23G_DP_1.2M(MS) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_3E, Sub B_Hi. Configure it. 4.Enable port 8-EM6-3 of new RTN910A(RTN01) and insert Optical SFP Module 1.25G 10Km. 5.Enable port Gi0/6/5 at PTN/Cisco B00632 and insert Optical SFP Module 1.25G 10Km. 6.Patching port 8-EM6-3 of new RTN910A(RTN01) to new port Gi0/6/5 at PTN/Cisco B00632. 7.Request new xC vlan dcn and vlan services. 8.Decom existing HW MW Link ID_CT08825 W00308-B00632, 18G_1+0_56MHZ_501M after confirm no other traffic backhauled via this link. | XMC_3E | MAC & MS | 23G | 23G_DP_0.6M(MAC)+OMT x1. | 23G_DP_1.2M(MS) x1. | GTSB | SQ202507100522-GTSB | GTSB | SQ202507100526-GTSB // SQ202507100534-GTSB // SQ202509230590-GTSB | 2025-12-04 | 2025-11-27 | Completed | 2025-07-30 | 2025-08-13 | 2025-07-30 | 2025-07-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-30 | 2025-08-13 | 2025-07-30 | 2025-07-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-04 | 2025-08-13 | 2025-08-04 | 2025-08-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-11-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071082 |  | 2025-07-13 | 2025-07-22 | Completed | 2025-07-12 | 2025-07-13 | 2025-07-12 | 2025-07-22 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-07-31 | 2025-07-22 | 2025-07-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-07-22 | 2025-07-31 | 2025-07-22 | 2025-08-05 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-28 | 2025-07-22 | 2025-07-31 | 2025-07-22 | 2025-08-06 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-07-22 | 2025-07-31 | 2025-07-22 | 2025-07-28 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505280699-GTSB
Q02056_AD_1 | Q126A_Q02056OD_T3_RHAGIH | DU00006263591 | Sarawak | Sarawak | 4.391530 | 114.907660 | [9 empty] | TSS+AA+TI |  | 13G_4+0_28M_512QAM_EPLA(WITHOUT CA) NE_Q02056 New 13G_1.8M(MDD)+Flange Adapter/Dual Coupler x1. New RTN910AF(RTN01). New ISM8 x1. New XMC_5D Pro, Sub A_Lo x2. New 13G Flexi WG x2. New IF cables with suitable type and length 4x RUN. FE_SMART 176120588 New 13G_1.8M(MDD)+Flange Adapter/Dual Coupler x1. New RTN910AF(RTN03). New ISM8 x1. New XMC_5D Pro, Sub A_Hi x2. New 13G Flexi WG x2. New IF cables with suitable type and length 4x RUN. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.STILL AWAITING LOS SURVEY FOR SMART 176120588. THEREFORE, E2E TRAFFIC(TX ROUTE AFTER) STILL NOT CONFIRM YET. 2.PERFORM DU BASED ON SEQUENCES BELOW: 1ST - DU SMART76120588_AD. 2ND - Q01490_AD_1. 3RD - Q02056_AD_1.*** Existing HW MW Link_ID SW03838, Q02056-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Reroute to new HW MW Link Q02056-SMART 176120588, 13G_4+0_28MHZ_512QAM_EPLA(WITHOUT CA). Later, decom existing HW MW Link_ID SW03838, Q02056-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Site Impacted : Q02056. NE_Q02056 1.Install new 13G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF(RTN01). Insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 5.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 6.Migrate traffic Q02056 via new HW MW Link Q02056-SMART 176120588, 13G_4+0_28MHZ_512QAM_EPLA(WITHOUT CA). 7.Later, decom existing decom existing HW MW Link_ID SW03838, Q02056-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. FE_SMART 176120588 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF(RTN03). Insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN03). 5.Enable port 8-EM6-2 of new RTN910AF(RTN02) under DU Q01490_AD_1. 6.Perform cascading in between 8-EM6-1 of new RTN910AF(RTN03) and port 8-EM6-2 of new RTN910AF(RTN02) under DU Q01490_AD_1. 7.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 8.Migrate traffic Q02056 via new PTN/IBeam(still awaiting LOS Survey for final FE). 9.Later, decom existing decom existing HW MW Link_ID SW03838, Q02056-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. | ****IMPORTANT NOTE: 1.STILL AWAITING LOS SURVEY FOR SMART 176120588. THEREFORE, E2E TRAFFIC(TX ROUTE AFTER) STILL NOT CONFIRM YET. 2.PERFORM DU BASED ON SEQUENCES BELOW: 1ST - DU SMART76120588_AD. 2ND - Q01490_AD_1. 3RD - Q02056_AD_1.*** Existing HW MW Link_ID SW03838, Q02056-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Reroute to new HW MW Link Q02056-SMART 176120588, 13G_4+0_28MHZ_512QAM_EPLA(WITHOUT CA). Later, decom existing HW MW Link_ID SW03838, Q02056-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Site Impacted : Q02056. NE_Q02056 1.Install new 13G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF(RTN01). Insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 5.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 6.Migrate traffic Q02056 via new HW MW Link Q02056-SMART 176120588, 13G_4+0_28MHZ_512QAM_EPLA(WITHOUT CA). 7.Later, decom existing decom existing HW MW Link_ID SW03838, Q02056-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. | ****IMPORTANT NOTE: 1.STILL AWAITING LOS SURVEY FOR SMART 176120588. THEREFORE, E2E TRAFFIC(TX ROUTE AFTER) STILL NOT CONFIRM YET. 2.PERFORM DU BASED ON SEQUENCES BELOW: 1ST - DU SMART76120588_AD. 2ND - Q01490_AD_1. 3RD - Q02056_AD_1.*** Existing HW MW Link_ID SW03838, Q02056-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Reroute to new HW MW Link Q02056-SMART 176120588, 13G_4+0_28MHZ_512QAM_EPLA(WITHOUT CA). Later, decom existing HW MW Link_ID SW03838, Q02056-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Site Impacted : Q02056. FE_SMART 176120588 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF(RTN03). Insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN03). 5.Enable port 8-EM6-2 of new RTN910AF(RTN02) under DU Q01490_AD_1. 6.Perform cascading in between 8-EM6-1 of new RTN910AF(RTN03) and port 8-EM6-2 of new RTN910AF(RTN02) under DU Q01490_AD_1. 7.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 8.Migrate traffic Q02056 via new PTN/IBeam(still awaiting LOS Survey for final FE). 9.Later, decom existing decom existing HW MW Link_ID SW03838, Q02056-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. | XMC_5D Pro | MDD | 13G | 13G_1.8M(MDD)+Flange Adapter/Dual Coupler x1 | 13G_1.8M(MDD)+Flange Adapter/Dual Coupler x1 | Trintel | SQ202601130230-Trintel |  |  | 2026-03-20 | 2026-03-17 | Completed | 2025-12-09 | 2025-12-14 | 2025-12-09 | 2025-12-16 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-20 | 2026-03-13 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202511130580-GTSB
9000B23_EVT | PBTS SK LIMAU-LIMAUN | DU00006263592 | Sarawak | Sabah | 6.821680 | 116.859310 | [13 empty] | Planning and integration support only for event site 9000B23 PBTS SK LIMAU-LIMAUN Tx route: 9000B23/9000B23-7780B-7391A-LL-7000A 1) Share port with 7391A at 7000A 2) New NE ID FE IDU 7780B RTN02 3) New NE ID NE IDU 9000B23 RTN01 4) At FE site 7780B patch RTN02 GE1 to existing RTN01 GE2 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241133-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
Q01461_AD_1 | Q126A_Q01461OD_MN_NANGAMEDAMIT | DU00006263593 | Sarawak | Sarawak | 4.450749 | 114.937020 | [9 empty] | TSS+AA+TI |  | 15G_4+0_28M_512QAM_EPLA(WITHOUT CA) NE_Q01461 New 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. New RTN910AF(RTN01). New ISM8 x1. New XMC_5D Pro, Sub A_Lo x2. New 15G Flexi WG x2. New IF cables with suitable type and length 4x RUN. New CAT6 cable x1. FE_SMART 176120588 New 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. Re-use existing RTN910AF(RTN02) under DU Q01490_AD_1. New ISM8 x2. New XMC_5D Pro, Sub A_Hi x2. New 15G Flexi WG x2. New IF cables with suitable type and length 4x RUN. New CAT6 cable x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.STILL AWAITING LOS SURVEY FOR SMART 176120588. THEREFORE, E2E TRAFFIC(TX ROUTE AFTER) STILL NOT CONFIRM YET. 2.PERFORM DU BASED ON SEQUENCES BELOW: 1ST - DU SMART76120588_AD. 2ND - Q01490_AD_1. 3RD - Q01461_AD_1*** Existing HW MW Link_ID SW03609, Q01461-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Reroute to new HW MW Link Q01461-SMART 176120588, 15G_4+0_28MHZ_512QAM_EPLA(WITHOUT CA). Later, decom existing HW MW Link_ID SW03609, Q01461-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Site Impacted : Q01461. NE_Q01461 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF(RTN01). Insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 5.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 6.Migrate traffic Q01461 via new HW MW Link Q01461-SMART 176120588, 15G_4+0_28MHZ_512QAM_EPLA(WITHOUT CA). 7.Later, decom existing HW MW Link_ID SW03609, Q01461-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. FE_SMART 176120588 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Re-use existing RTN910AF(RTN02) under DU Q01490_AD_1. Insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Hi x2. Configure it. 4.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Migrate traffic Q01461 via new PTN/IBeam(still awaiting LOS Survey for final FE). 6.Later, decom existing HW MW Link_ID SW03609, Q01461-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. | ****IMPORTANT NOTE: 1.STILL AWAITING LOS SURVEY FOR SMART 176120588. THEREFORE, E2E TRAFFIC(TX ROUTE AFTER) STILL NOT CONFIRM YET. 2.PERFORM DU BASED ON SEQUENCES BELOW: 1ST - DU SMART76120588_AD. 2ND - Q01490_AD_1. 3RD - Q01461_AD_1*** Existing HW MW Link_ID SW03609, Q01461-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Reroute to new HW MW Link Q01461-SMART 176120588, 15G_4+0_28MHZ_512QAM_EPLA(WITHOUT CA). Later, decom existing HW MW Link_ID SW03609, Q01461-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Site Impacted : Q01461. NE_Q01461 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF(RTN01). Insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 5.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 6.Migrate traffic Q01461 via new HW MW Link Q01461-SMART 176120588, 15G_4+0_28MHZ_512QAM_EPLA(WITHOUT CA). 7.Later, decom existing HW MW Link_ID SW03609, Q01461-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. | ****IMPORTANT NOTE: 1.STILL AWAITING LOS SURVEY FOR SMART 176120588. THEREFORE, E2E TRAFFIC(TX ROUTE AFTER) STILL NOT CONFIRM YET. 2.PERFORM DU BASED ON SEQUENCES BELOW: 1ST - DU SMART76120588_AD. 2ND - Q01490_AD_1. 3RD - Q01461_AD_1*** Existing HW MW Link_ID SW03609, Q01461-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Reroute to new HW MW Link Q01461-SMART 176120588, 15G_4+0_28MHZ_512QAM_EPLA(WITHOUT CA). Later, decom existing HW MW Link_ID SW03609, Q01461-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. Site Impacted : Q01461. FE_SMART 176120588 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Re-use existing RTN910AF(RTN02) under DU Q01490_AD_1. Insert new ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A_Hi x2. Configure it. 4.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Migrate traffic Q01461 via new PTN/IBeam(still awaiting LOS Survey for final FE). 6.Later, decom existing HW MW Link_ID SW03609, Q01461-Q00324, 13G_2+0_28MHZ_2048QAM_EPLA. | XMC_5D Pro | MDD | 15G | 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. | 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. | Trintel | SQ202601130230-Trintel |  |  |  |  | Ongoing | 2025-12-09 | 2025-12-14 | 2025-12-09 | 2025-12-16 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202511130580-GTSB
Q01490_AD_1 | Q126A_Q01490OD_NANGADAMIT | DU00006263594 | Sarawak | Sarawak | 4.489642 | 114.907830 | [9 empty] | TSS+AA+TI |  | 18G_1+0_55M_512QAM NE_Q01490 New 18G_0.6M(MDD) x1. New RTN910AF(RTN01). New XMC_5D Pro, Sub A_Lo x1. New CAT6 cable x1. FE_SMART 176120588 New 18G_0.6M(MDD) x1. New RTN910AF(RTN02). New XMC_5D Pro, Sub A_Hi x1. New CAT6 cable x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.STILL AWAITING LOS SURVEY FOR SMART 176120588. THEREFORE, E2E TRAFFIC(TX ROUTE AFTER) STILL NOT CONFIRM YET. 2.PERFORM DU BASED ON SEQUENCES BELOW: 1ST - DU SMART76120588_AD. 2ND - Q01490_AD_1. 3RD - Q01461_AD_1**** Existing SM MW Link_ID SW02437, Q01490-Q00324, 18G_1+0_28MHZ_256QAM. Reroute to new HW MW Link Q01490-SMART 176120588, 18G_1+0_55MHZ_512QAM. Later, decom existing SM MW Link_ID SW02437, Q01490-Q00324, 18G_1+0_28MHZ_256QAM. Site Impacted : Q01490. NE_Q01490 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 5.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 6.Migrate traffic Q01490 via new HW MW Link Q01490-SMART 176120588, 18G_1+0_55MHZ_512QAM. 7.Later, decom existing SM MW Link_ID SW02437, Q01490-Q00324, 18G_1+0_28MHZ_256QAM. FE_SMART 176120588 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Enable port 8-EM6-2 of new RTN910AF(RTN01). 6.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN02) and port 8-EM6-2 of new RTN910AF(RTN01) under DU SMART76120588_AD. 7.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 8.Migrate traffic Q01490 via new PTN/IBeam(still awaiting LOS Survey for final FE). 9.Later, decom existing SM MW Link_ID SW02437, Q01490-Q00324, 18G_1+0_28MHZ_256QAM. | ****IMPORTANT NOTE: 1.STILL AWAITING LOS SURVEY FOR SMART 176120588. THEREFORE, E2E TRAFFIC(TX ROUTE AFTER) STILL NOT CONFIRM YET. 2.PERFORM DU BASED ON SEQUENCES BELOW: 1ST - DU SMART76120588_AD. 2ND - Q01490_AD_1. 3RD - Q01461_AD_1**** Existing SM MW Link_ID SW02437, Q01490-Q00324, 18G_1+0_28MHZ_256QAM. Reroute to new HW MW Link Q01490-SMART 176120588, 18G_1+0_55MHZ_512QAM. Later, decom existing SM MW Link_ID SW02437, Q01490-Q00324, 18G_1+0_28MHZ_256QAM. Site Impacted : Q01490. NE_Q01490 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 5.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 6.Migrate traffic Q01490 via new HW MW Link Q01490-SMART 176120588, 18G_1+0_55MHZ_512QAM. 7.Later, decom existing SM MW Link_ID SW02437, Q01490-Q00324, 18G_1+0_28MHZ_256QAM. | ****IMPORTANT NOTE: 1.STILL AWAITING LOS SURVEY FOR SMART 176120588. THEREFORE, E2E TRAFFIC(TX ROUTE AFTER) STILL NOT CONFIRM YET. 2.PERFORM DU BASED ON SEQUENCES BELOW: 1ST - DU SMART76120588_AD. 2ND - Q01490_AD_1. 3RD - Q01461_AD_1**** Existing SM MW Link_ID SW02437, Q01490-Q00324, 18G_1+0_28MHZ_256QAM. Reroute to new HW MW Link Q01490-SMART 176120588, 18G_1+0_55MHZ_512QAM. Later, decom existing SM MW Link_ID SW02437, Q01490-Q00324, 18G_1+0_28MHZ_256QAM. Site Impacted : Q01490. FE_SMART 176120588 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Enable port 8-EM6-2 of new RTN910AF(RTN01). 6.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN02) and port 8-EM6-2 of new RTN910AF(RTN01) under DU SMART76120588_AD. 7.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 8.Migrate traffic Q01490 via new PTN/IBeam(still awaiting LOS Survey for final FE). 9.Later, decom existing SM MW Link_ID SW02437, Q01490-Q00324, 18G_1+0_28MHZ_256QAM. | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | Trintel | SQ202601130230-Trintel |  |  | 2026-03-20 | 2026-03-17 | Completed | 2025-12-09 | 2025-12-14 | 2025-12-09 | 2025-12-16 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-20 | 2026-03-13 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202511130580-GTSB
9318A_IPR | Kpg Merdang Gayam (SACOFA) | DU00006263595 | Sarawak | Sarawak | 1.449753 | 110.407135 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New CAT6 cable with suitable length(IDU HW to Ibeam) | MW IDU Patching | Perform MW IDU Patching by doing migration at 9318A - Existing RTN910AF(RTN04) with NEID 24263. Site Impacted: 9029C & 9422B. NE_9318A 1.Enable port 8-EM6-2 of existing RTN910AF(RTN04) with NEID 24263. 2.Request new IBeam port from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN04) with NEID 24263 and new IBeam port. 4.Create LAG between existing IDU port-IBeam port and new IDU port-IBeam port . 5.Divert traffics 9029C & 9422B to new IBeam port. | Perform MW IDU Patching by doing migration at 9318A - Existing RTN910AF(RTN04) with NEID 24263. Site Impacted: 9029C & 9422B. NE_9318A 1.Enable port 8-EM6-2 of existing RTN910AF(RTN04) with NEID 24263. 2.Request new IBeam port from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN04) with NEID 24263 and new IBeam port. 4.Create LAG between existing IDU port-IBeam port and new IDU port-IBeam port . 5.Divert traffics 9029C & 9422B to new IBeam port. | [6 empty] | Allstar | SQ202511170524-Allstar | Allstar | SQ202511170485-Allstar | 2025-12-29 | 2025-12-22 | Completed | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110726 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-12 | 2025-11-18 | 2025-11-12 | 2025-11-12 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-12 | 2025-11-18 | 2025-11-21 | 2025-11-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-11-12 | 2025-11-18 | 2025-11-22 | 2025-11-22 | ROYSTON//AHHOLE/6000038561 | 2025-07-24: 2025-11-12; 2025-07-24: 2025-11-18; 2025-07-24: 2025-11-12; 2025-07-28: 2025-11-12 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511040438-GTSB
SMART76120588_AD | SDEC KG SEPANGAH NG MEDAMIT | DU00006263596 | Sarawak | Sarawak | 4.505490 | 114.892600 | [9 empty] | NA |  |  | Cancel / Drop | [8 empty] | Trintel | SQ202602160113-Trintel |  |  |  |  | Ongoing | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-05 | 2026-02-12 | 2026-02-05 | 2026-02-05 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-05 | 2026-02-12 | 2026-02-05 | 2026-02-05 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202511130580-GTSB
7207A_IPR | Sim Seng Lee | DU00006263597 | Sabah | Sabah | 4.463995 | 118.567644 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 7207A. NE_7207A New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For 2X HW RTN910AF(RTN01 & RTN02). New Optical Patch Cord cable with suitable type and length. | IPRAN Port Upgrade | IPRAN Port Upgrade from existing Optical 1G to 10G port at 7207A at RTN910AF(RTN01) and RTN910AF(RTN02). Site Impacted : 7207A, 7355A, 7064K & 7208R. NE_7207A 1.Insert new suitable SFP Module 10G into port 8-EM6-4 of existing RTN910AF(RTN01 NEID 9-19464). Enable and configure. 2.Insert new suitable SFP Module 10G into port 8-EM6-3 of existing RTN910AF(RTN02 NEID 9-23067). Enable and configure. 3.Perform cascading using Optical Patch Cord cable from port 8-EM6-4 of existing RTN910AF(RTN01 NEID 9-19464) and port 8-EM6-3 of existing RTN910AF(RTN02 NEID 9-23067). 4.Disconnect/remove existing cascading 1G between port 8-EM6-2 of existing RTN910AF(RTN01 NEID 9-19464) and port 8-EM6-1 of existing RTN910AF(RTN02 NEID 9-23067). 5.Disconnect/remove existing patching port 8-EM6-2 of existing RTN910AF(RTN02 NEID 9-23067) from xC CTS LL. 6.Request new Vlan services for 7064K/S01754 and migrate from xC to xD(CP 7205A). | IPRAN Port Upgrade from existing Optical 1G to 10G port at 7207A at RTN910AF(RTN01) and RTN910AF(RTN02). Site Impacted : 7207A, 7355A, 7064K & 7208R. NE_7207A 1.Insert new suitable SFP Module 10G into port 8-EM6-4 of existing RTN910AF(RTN01 NEID 9-19464). Enable and configure. 2.Insert new suitable SFP Module 10G into port 8-EM6-3 of existing RTN910AF(RTN02 NEID 9-23067). Enable and configure. 3.Perform cascading using Optical Patch Cord cable from port 8-EM6-4 of existing RTN910AF(RTN01 NEID 9-19464) and port 8-EM6-3 of existing RTN910AF(RTN02 NEID 9-23067). 4.Disconnect/remove existing cascading 1G between port 8-EM6-2 of existing RTN910AF(RTN01 NEID 9-19464) and port 8-EM6-1 of existing RTN910AF(RTN02 NEID 9-23067). 5.Disconnect/remove existing patching port 8-EM6-2 of existing RTN910AF(RTN02 NEID 9-23067) from xC CTS LL. 6.Request new Vlan services for 7064K/S01754 and migrate from xC to xD(CP 7205A). | [6 empty] | NR services | SQ202512010610-NR Services | NR services | SQ202512010600-NR Services | 2025-12-24 | 2025-12-17 | Completed | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112422 |  | 2025-11-25 | 2025-11-26 | Completed | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-26 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-26 | 2025-12-26 | 2025-11-26 | 2025-12-01 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-11-26 | 2025-12-26 | 2025-11-26 | 2025-12-01 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-04 | 2025-11-26 | 2025-12-26 | 2025-11-26 | 2025-12-05 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2025-07-24: 2025-11-26; 2025-07-24: 2025-12-26; 2025-07-24: 2025-11-26; 2025-07-28: 2025-11-27 |  |  | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-16 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511040432-GTSB
1737A_IPR | Bernama | DU00006263598 | Central | Kuala Lumpur | 3.171420 | 101.712134 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 10KM 2x Patch Cord(Pair) | MW IDU Patching | Perform LAG at CP site for IDU 1737A-BERNAMA-RTN06 to 1737A-MAC-001 Bernama 1) Patch IDU 1737A-BERNAMA-RTN06 GE2 to new CP port 2) Create LAG 3) Impact sites: 3714A,W01588,1313A | Perform LAG at CP site for IDU 1737A-BERNAMA-RTN06 to 1737A-MAC-001 Bernama 1) Patch IDU 1737A-BERNAMA-RTN06 GE2 to new CP port 2) Create LAG 3) Impact sites: 3714A,W01588,1313A | [6 empty] | Magicell | SQ202511260105-Magicell | Magicell | SQ202512120476-Magicell | 2025-11-28 | 2025-11-27 | Completed | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111799 |  | 2025-11-18 | 2025-11-21 | Completed | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-21 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-21 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-21 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-19 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-20 | AHMAD RASHIDI BIN SAFRI7018000135 | 2025-07-24: 2025-11-18; 2025-07-24: 2025-11-18; 2025-07-24: 2025-11-18; 2025-07-28: 2025-11-19 |  |  | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202511040420-GCI | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
K00326_HU | CB_KGBUKIT | DU00006149661 | Northern | Kedah | 6.130400 | 100.608300 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 2X RTN910A 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB A HI 1X ODU 15G XMC5D SUB A LO | MW Swap | MW SWAP LINK K00326-K00073 WITH HUAWEI_15G_4+0_1.2M/1.2M_DP_28MHZ_256QAM_800MBPS_XMC5D_SUB_A_WITH CA_LINK_5.93KM IMPACTED: K00326 LINK WILL INSTALL WITH DU K00326_HU_1 (15G 2+0) EPLA TO BECOME 15G 6+0 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910A WITH 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA SLOT 3 & 4 5. DISMANTLE EXISTING LINK 6. LINK WILL EPLA WITH DU K00326_HU_1 15G 2+0 AT SLOT 7 7. CONFIGURE LINK 15G 6+0 28MHZ 256QAM WITH CA SLOT 3 & 4(4+0) AND 7(2+0) | 1. INSTALL NEW IDU RTN910A WITH 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA SLOT 3 & 4 5. DISMANTLE EXISTING LINK 6. LINK WILL EPLA WITH DU K00326_HU_1 15G 2+0 AT SLOT 7 7. CONFIGURE LINK 15G 6+0 28MHZ 256QAM WITH CA SLOT 3 & 4(4+0) AND 7(2+0) | XMC5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202512120144-Magicell | Magicell | SQ202512190076-Magicell // SQ202512190079-Magicell | 2025-12-17 | 2025-12-16 | Completed | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111257 |  | 2025-12-13 | 2025-11-15 | Completed | 2025-11-12 | 2025-12-13 | 2025-11-12 | 2025-11-15 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-01 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-02 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-01 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-12 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510100628-GCI | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
9073K_HU | BB1_Q132A_Q00509OD_CB_MYYBTUTRUNK | DU00006149662 | Sarawak | Sarawak | 3.497000 | 113.580100 | [9 empty] | TSS+AA+TI |  | 13G_4+0_28M_256QAM_EPLA NE_9073K/Q00509 New 13G_1.2M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x1. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN. FE_Q00268 New 13G_1.8M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x1. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x4 RUN. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & 1.8M ANTENNA DISH AT FE. 2.CHANNEL AVAILABLE FOR 13G WILL BE CRUCIAL AS CHANNEL OFFER UNDER 13G SPECTRUM NOT MANY. 3.PLEASE BE REMINDER: SOLUTION/SOW BELOW PERHAPS NEED TO REVISE DUE TO LOSSCOMM STILL OCCUR. DEAL WITH PLANNER ONCES TSS DONE IN ORDER FOR FINALIZE THE SOLUTION/SOW.**** Build new parallel HW MW Link 9073K/Q00509-Q00268,13G_4+0_28M_256QAM_EPLA. Site Impacted : 9073K, 9375P & 9129K. NE_9073K/Q00509 1.Install 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Lay new IF cables with suitable length and type x2 RUN. 5.Build new parallel HW MW Link 9073K/Q00509-Q00268,13G_4+0_28M_256QAM_EPLA. 6.Request new xC Vlan DCN and Vlan Services. 7.Migrate traffics 9073K, 9375P & 9129K via new parallel HW MW Link 9073K/Q00509-Q00268,13G_4+0_28M_256QAM_EPLA. FE_Q00268 1.Install 13G_1.8M(MDD)+Dual Coupler x1. 2.Install new RTN910AF and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new IF cables with suitable length and type x2 RUN. 5.Build new parallel HW MW Link 9073K/Q00509-Q00268,13G_4+0_28M_256QAM_EPLA. 6.Request new xC Vlan DCN and Vlan Services. 7.Migrate traffics 9073K, 9375P & 9129K via new port at PTN/Cisco Router. |  |  | XMC_5D Pro | MDD | 13G | 13G_1.2M(MDD)+Dual Coupler x1 | 13G_1.8M(MDD)+Dual Coupler x1 | Magicell | SQ202603260172-Magicell |  |  |  |  | Ongoing | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100649-GTSB
4482A_HU_1 | University MARA (AsiaSpace) RCC | DU00006149663 | Northern | Perak | 4.361100 | 100.967510 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC | 13G_4+0_1.8M/1.8M_MDD_28MHZ_512QAM | MW Remote Upgrade | MW REMOTE UPGRADE LINK 4482A-4733A 13G_3+0_1.8M/1.8M_MDD_28MHZ_512QAM TO 13G_4+0_1.8M/1.8M_MDD_28MHZ_512QAM IMPACTED SITE: 4711D | MW REMOTE UPGRADE LINK 4482A-4733A 13G_3+0_1.8M/1.8M_MDD_28MHZ_512QAM TO 13G_4+0_1.8M/1.8M_MDD_28MHZ_512QAM IMPACTED SITE: 4711D | MW REMOTE UPGRADE LINK 4482A-4733A 13G_3+0_1.8M/1.8M_MDD_28MHZ_512QAM TO 13G_4+0_1.8M/1.8M_MDD_28MHZ_512QAM IMPACTED SITE: 4711D | XMC5D | MDD | 13G | 1.8 | 1.8 | MTK | No PR required-Remote Upgrade | MTK | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-07 | [15 empty] | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510100628-GCI | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-22 | EZRIN TASNIM BIN ABDUL GANI6798000128
7159R_HU | Kg. Sangkabok | DU00006149664 | Sabah | Sabah | 5.406130 | 115.383810 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M NE_7159R 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub B_Lo x1. FE_7372A. 13G_DP_1.2M(MDD) x1. RTN910A. x1. ISM8 x2. XMC_5D , Sub B_Hi x1. | MW Parallel Link | Existing link 15G_2+0_28M to carry two BBU 7159R & 7157R. Install parallel link 13G_4+0_28M to support 7159R_BBU. Site Impacted : 7159R. NE_7159R 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. ( RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , 7159R_BBU migrate to new parallel link. 7.No link to be decomm. FE_7372A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub B_Hi. 5.Create service cross connect , CA and EPLA. 6.Create new In band DCN. 7.Traffic migrate to new parallel link. 8.No link to be decomm. | Existing link 15G_2+0_28M to carry two BBU 7159R & 7157R. Install parallel link 13G_4+0_28M to support 7159R_BBU. Site Impacted : 7159R. NE_7159R 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. ( RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , 7159R_BBU migrate to new parallel link. 7.No link to be decomm. | Existing link 15G_2+0_28M to carry two BBU 7159R & 7157R. Install parallel link 13G_4+0_28M to support 7159R_BBU. Site Impacted : 7159R. FE_7372A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub B_Hi. 5.Create service cross connect , CA and EPLA. 6.Create new In band DCN. 7.Traffic migrate to new parallel link. 8.No link to be decomm. | XMC_5D | MDD | 13G | 1.2 | 1.2 | YPTT | SQ202512170180-YPTT | NR services | SQ202512160980-NR Services // SQ202512160985-NR Services | 2025-12-25 | 2026-01-05 | Completed | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-22 | 2025-12-23 | 2025-12-22 | 2025-12-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111917 |  | 2025-11-20 | 2025-12-10 | Completed | 2025-11-19 | 2025-11-20 | 2025-11-19 | 2025-12-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-05 | 2026-01-05 | 2025-12-05 | 2025-12-10 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-12-05 | 2026-01-05 | 2025-12-05 | 2025-12-10 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-12-05 | 2026-01-05 | 2025-12-05 | 2025-12-23 | RALPH O'BRYAN HILARY7167000030 | 2025-11-29: 2025-12-05; 2025-11-29: 2026-01-05; 2025-11-29: 2025-12-05; 2025-12-01: 2025-12-09 |  |  | 2025-12-24 | 2026-01-24 | 2025-12-24 | 2025-12-24 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202510100630-GCI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | CHEONG/SENG/WAH/7018000306
2952A_HU | Taman Kota Sungai Rambai | DU00006149665 | Central | Selangor | 2.888530 | 101.492510 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X RTN910A 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO | MW Hardware Upgrade | MW HARDWARE UPGRADE 2952A-1122A WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_778MBPS_XMC3E_SUB_A_3.06KM IMPACTED: 2952A DISMANTLE EXISTING LINK ODU ONLY | 1. REUSE EXISTING IDU RTN910 2. REUSE EXISTING 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK ODU ONLY | 1. INSTALL NEW IDU RTN910 2. REUSE EXISTING 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK ODU ONLY 6. PATCH TO NEW CP PORT | XMC3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202510090302-Magicell | Magicell | SQ202510090253-Magicell // SQ202510090295-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100947 |  | 2025-10-12 | 2025-10-13 | Completed | 2025-10-11 | 2025-10-12 | 2025-10-09 | 2025-10-13 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-31 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-11-10 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-31 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-11-10 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-31 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | NG HONG JIE7018000036 | Logistic Team | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510100626-GCI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
4014B_HU | Valdor | DU00006149666 | Northern | Penang | 5.234460 | 100.476000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 23G_2+0_112M. NE_4014B 23G_DP_0.6(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2.. FE_4116B/P00172. 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B _Hi x2. | MW New Link / Reroute | Existing link 13G_6+0_28M. Link reroute to new FE 4116B/P00172 with 23G_2+0_112M. TSS Survey is required. Site Impacted : 4014B. NE_4014B 1.Install new 23G_DP_0.6(MAC)+OMT 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching 4014B_BBU. 6.Traffic migrate to new link and new FE routing. 7.No link to be decomm due to support two sites 4372D & 4399E. FE_4116B/P00172. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B _Hi. 4.Create service cross connect and EPLA. 5.Create In band DCN. 6.Traffic migrate to new link and new FE routing. 7.No link to be decomm due to support two sites 4372D & 4399E. | Existing link 13G_6+0_28M. Link reroute to new FE 4116B/P00172 with 23G_2+0_112M. TSS Survey is required. Site Impacted : 4014B. NE_4014B 1.Install new 23G_DP_0.6(MAC)+OMT 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching 4014B_BBU. 6.Traffic migrate to new link and new FE routing. 7.No link to be decomm due to support two sites 4372D & 4399E. | Existing link 13G_6+0_28M. Link reroute to new FE 4116B/P00172 with 23G_2+0_112M. TSS Survey is required. Site Impacted : 4014B. FE_4116B/P00172. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B _Hi. 4.Create service cross connect and EPLA. 5.Create In band DCN. 6.Traffic migrate to new link and new FE routing. 7.No link to be decomm due to support two sites 4372D & 4399E. | XMC_3E | MAC | 23G | 0.6 | 0.6 | MTK | SQ202510090411-MTK | MTK | SQ202510090382-MTK // SQ202510090386-MTK |  |  | Ongoing | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110569 |  | 2025-12-05 | 2025-11-15 | Completed | 2025-11-05 | 2025-12-05 | 2025-11-05 | 2025-11-15 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-11 | 2026-02-20 | 2026-03-03 | 2026-03-03 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2026-02-11 | 2026-02-20 | 2026-03-03 | 2026-03-03 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-12 | 2026-02-11 | 2026-02-20 | 2026-03-03 | 2026-03-03 | DZULFAIZAL//BIN MAULUF/8225000001 | 2025-10-28: 2026-02-11; 2025-10-28: 2026-02-20; 2025-10-28: 2026-02-12; 2025-10-31: 2026-02-12 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510100628-GCI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | CHEONG/SENG/WAH/7018000306
9600C_HU | Kampung Engkeroh | DU00006149667 | Sarawak | Sarawak | 1.011580 | 110.537700 | [9 empty] | TSS+AA+TI |  | 13G_2+0_512Q_28Mhz_448Mbps NE: 1x ISM8 1x 1.2m MDD ant (13G) 1x ODU 13G_XMC-5D sb-B_Hi FE: 1x ISM8 1x 1.2m MDD ant (13G) 1x ODU 13G_XMC-5D sb-B_Lo | MW Parallel Link | Install new link 9600C-Q00642_13G_2+0_512Q_28Mhz_448Mbps to be parallel with existing link Config EPLA new link and existing link Impact site: 9600C Existing link 13G_2+0_28Mhz | NE: 1. Install ISM8 card at slot 3 at existing IDU RTN01 2. Install new 13G 1.2m MDD ANTENNA 3. Install new 13G XMC-5D sb B 4. Configure link 13G 2+0 28MHZ 512QAM EPLA 5. Config EPLA existing link and new link become 4+0 | FE: 1. Install ISM8 card at slot 4 at existing IDU RTN01 2. Install new 13G 1.2m MDD ANTENNA 3. Install new 13G XMC-5D sb B 4. Configure link 13G 2+0 28MHZ 512QAM EPLA 5. Config EPLA existing link and new link become 4+0 | XMC-5D | MDD | 13G | 1.2m | 1.2m | Magicell | SQ202601210174-Magicell |  |  | 2026-03-23 | 2026-03-17 | Completed | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-16 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100649-GTSB | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | AB.RAHMAN//BIN MAT NOOH/6237001519
4400A_HU | Kuala Gula RDD | DU00006149668 | Northern | Perak | 4.948310 | 100.456830 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M. NE_4400A. 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Hi x1.. FE_4334A 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Lo x1. ETH cable x3. | MW Swap | Existing link 13G_2+0_28M Swap existing link to 13G_4+0_28M. Site Impacted : 4281H , 4159R. NE_4400A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , ETH patching to existing 4400A_RTN03. carry 4159R. 7.Enable GE2 , ETH patching to existing 4400A_NLOS.Carry 4281H. 8.All traffic migrate to new MW link. 9.Decom existing MW link. FE_4334A 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , ETH patching to existing 4334A_RTN03. (ID : 41940). 7.All traffic migrate to new MW link. 8.Decom existing MW link. | Existing link 13G_2+0_28M Swap existing link to 13G_4+0_28M. Site Impacted : 4281H , 4159R. NE_4400A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , ETH patching to existing 4400A_RTN03. carry 4159R. 7.Enable GE2 , ETH patching to existing 4400A_NLOS.Carry 4281H. 8.All traffic migrate to new MW link. 9.Decom existing MW link. | Existing link 13G_2+0_28M Swap existing link to 13G_4+0_28M. Site Impacted : 4281H , 4159R. FE_4334A 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , ETH patching to existing 4334A_RTN03. (ID : 41940). 7.All traffic migrate to new MW link. 8.Decom existing MW link. | XMC_5D | MDD | 13G | 1.2M | 1.2M | Magicell | SQ202510220709-Magicell | Magicell | SQ202510220690-Magicell // SQ202510220702-Magicell | 2026-01-20 | 2026-01-19 | Completed | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102326 |  | 2025-10-24 | 2025-10-27 | Completed | 2025-10-23 | 2025-10-24 | 2025-10-23 | 2025-10-27 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-28 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-12-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-12-13 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-12-02 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | NG HONG JIE7018000036 | Logistic Team | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510100628-GCI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | CHEONG/SENG/WAH/7018000306
S00567_HU | CB_KGSAGINDAIBARU | DU00006149669 | Sabah | Sabah | 5.847050 | 116.815750 |  |  |  |  | DT February |  |  | 04. Pending DO |  |  |  | 15G_4+0_28M_512QAM_EPLA NE_7128P/S00567 New 15G_1.2M(MDD)+Dual Coupler x1. Re-use existing RTN910AF(NEID 88-12567). New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN. FE_7199R/S00383 New 15G_1.2M(MDD)+Dual Coupler x1. Re-use existing RTN910AF(NEID 88-22567). New ISM8 x2. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x4 RUN. | Cancel / Drop | Existing HW MW Link S00567-S00383, 15G_2+0_28MHZ_1024QAM_EPLA. Build new HW MW Parallel S00567-S00383, 15G_4+0_28M_512QAM_EPLA. Later, combine existing HW MW Link S00567-S00383, 15G_2+0_28MHZ_1024QAM_EPLA and new HW MW Parallel Link S00567-S00383, 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_1024QAM&256QAM_EPLA. Site Impacted : 7128P/S00567 & 2684A20. NE_7128P/S00567 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Re-use existing RTN910AF(NEID 88-12567) and insert ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. 4.Lay new IF cables with suitable length and type x4 RUN from new XMC_5D Pro, Sub A&B_Lo x2 to existing RTN910AF(NEID 88-12567) ISM8 slot 03(Port 1 & 2) and slot 04(Port 1 & 2). 5.Build new HW MW Parallel S00567-S00383, 15G_4+0_28M_512QAM_EPLA. 6.Later, combine existing HW MW Link S00567-S00383, 15G_2+0_28MHZ_1024QAM_EPLA and new HW MW Parallel Link S00567-S00383, 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_1024QAM&256QAM_EPLA. 7.Re-use existing Vlan DCN & Vlan Services. 8.Migrate 7128P/S00567 & 2684A20 into new HW MW Link 15G_6+0_28MHZ_1024QAM&256QAM_EPLA. FE_7199R/S00383 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Re-use existing RTN910AF(NEID 88-22567) and insert ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. 4.Lay new IF cables with suitable length and type x4 RUN from new XMC_5D Pro, Sub A&B_Lo x2 to existing RTN910AF(NEID 88-22567) ISM8 slot 03(Port 1 & 2) and slot 04(Port 1 & 2). 5.Build new HW MW Parallel S00567-S00383, 15G_4+0_28M_512QAM_EPLA. 6.Later, combine existing HW MW Link S00567-S00383, 15G_2+0_28MHZ_1024QAM_EPLA and new HW MW Parallel Link S00567-S00383, 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_1024QAM&256QAM_EPLA. 7.Re-use existing PTN/Cisco Router port at S00566. 8.Migrate 7128P/S00567 & 2684A20 into existing PTN/Cisco Router port at S00566. | Existing HW MW Link S00567-S00383, 15G_2+0_28MHZ_1024QAM_EPLA. Build new HW MW Parallel S00567-S00383, 15G_4+0_28M_512QAM_EPLA. Later, combine existing HW MW Link S00567-S00383, 15G_2+0_28MHZ_1024QAM_EPLA and new HW MW Parallel Link S00567-S00383, 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_1024QAM&256QAM_EPLA. Site Impacted : 7128P/S00567 & 2684A20. NE_7128P/S00567 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Re-use existing RTN910AF(NEID 88-12567) and insert ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. 4.Lay new IF cables with suitable length and type x4 RUN from new XMC_5D Pro, Sub A&B_Lo x2 to existing RTN910AF(NEID 88-12567) ISM8 slot 03(Port 1 & 2) and slot 04(Port 1 & 2). 5.Build new HW MW Parallel S00567-S00383, 15G_4+0_28M_512QAM_EPLA. 6.Later, combine existing HW MW Link S00567-S00383, 15G_2+0_28MHZ_1024QAM_EPLA and new HW MW Parallel Link S00567-S00383, 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_1024QAM&256QAM_EPLA. 7.Re-use existing Vlan DCN & Vlan Services. 8.Migrate 7128P/S00567 & 2684A20 into new HW MW Link 15G_6+0_28MHZ_1024QAM&256QAM_EPLA. | Existing HW MW Link S00567-S00383, 15G_2+0_28MHZ_1024QAM_EPLA. Build new HW MW Parallel S00567-S00383, 15G_4+0_28M_512QAM_EPLA. Later, combine existing HW MW Link S00567-S00383, 15G_2+0_28MHZ_1024QAM_EPLA and new HW MW Parallel Link S00567-S00383, 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_1024QAM&256QAM_EPLA. Site Impacted : 7128P/S00567 & 2684A20. FE_7199R/S00383 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Re-use existing RTN910AF(NEID 88-22567) and insert ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. 4.Lay new IF cables with suitable length and type x4 RUN from new XMC_5D Pro, Sub A&B_Lo x2 to existing RTN910AF(NEID 88-22567) ISM8 slot 03(Port 1 & 2) and slot 04(Port 1 & 2). 5.Build new HW MW Parallel S00567-S00383, 15G_4+0_28M_512QAM_EPLA. 6.Later, combine existing HW MW Link S00567-S00383, 15G_2+0_28MHZ_1024QAM_EPLA and new HW MW Parallel Link S00567-S00383, 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_1024QAM&256QAM_EPLA. 7.Re-use existing PTN/Cisco Router port at S00566. 8.Migrate 7128P/S00567 & 2684A20 into existing PTN/Cisco Router port at S00566. | XMC-5D Pro | MDD | 15G | 15G_1.2M(MDD)+Dual Coupler x1 | 15G_1.2M(MDD)+Dual Coupler x1 | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100645-GTSB
1869B_HU | KJS Kg Semarang(KJS) | DU00006149670 | Central | Selangor | 2.871390 | 101.695840 | [7 empty] | 03. TSS Only |  | TSS |  |  | MW New Link / Reroute | TSS ONLY. HU WILL BE DONE AT DU 3393A_HU | [7 empty] | Magicell | SQ202510090302-Magicell | Magicell | No PR required-Work at TSS only | 2026-03-13 | 2026-03-12 | Completed | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100946 |  | 2025-10-12 | 2025-10-13 | Completed | 2025-10-11 | 2025-10-12 | 2025-10-09 | 2025-10-13 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-21 | 2025-10-21 | 2025-10-21 |  | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-10-21 | 2025-10-21 | 2025-10-21 |  | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | [7 empty] | 2025-10-21 | 2025-10-21 | 2025-10-21 |  | MOHD//SAFRI BIN ARIF/7018000166 | 2025-11-04: 2025-10-21; 2025-11-04: 2025-10-21; 2025-11-04: 2025-10-21 | [7 empty] | GCI | SQ202510100626-GCI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
7063D_HU_1 | TAMAN SABANA (REL) | DU00006149671 | Sabah | Sabah | 5.374420 | 116.156330 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 23G_1+0_112M. NE_7063D 23G_SP_1.2M(MAC)+OMT x1.. ISM8 x1. XMC_3E , Sub B_HI x1.. FE_7068A 23G_SP_1.2M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub B_Lo x1. | MW Parallel Link | Existing link 18G_1+0_112M Install parallel link 23G_1+0_112M. Site Impacted : 7063D. NE_7063D 1.Install new 23G_SP_1.2M(MAC)+OMT. 2.Reuse existing 7063D_RTN01 ( ID : 23412). 3.Install new 3_ISM8-1+0 into existing 7063D_RTN01. 4.Install new XMC_3E , Sub B_HI. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No link to be decomm. FE_7068A 1.Install new 23G_SP_1.2M(MAC)+OMT. 2.Reuse existing 7068A_RTN05 ( ID : 23413). 3.Install new 3_ISM8-1+0 into existing 7068A_RTN05. 4.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect and EPLA with existing link. 6.Enable GE2 , ETH patching new port to Ibeam port Ge_0/2/2 and create LAG port. 7.Traffic migrate to new parallel and new LAG port. 8.No link to be decomm. | Existing link 18G_1+0_112M Install parallel link 23G_1+0_112M. Site Impacted : 7063D. NE_7063D 1.Install new 23G_SP_1.2M(MAC)+OMT. 2.Reuse existing 7063D_RTN01 ( ID : 23412). 3.Install new 3_ISM8-1+0 into existing 7063D_RTN01. 4.Install new XMC_3E , Sub B_HI. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new parallel link. 7.No link to be decomm. | Existing link 18G_1+0_112M Install parallel link 23G_1+0_112M. Site Impacted : 7063D. FE_7068A 1.Install new 23G_SP_1.2M(MAC)+OMT. 2.Reuse existing 7068A_RTN05 ( ID : 23413). 3.Install new 3_ISM8-1+0 into existing 7068A_RTN05. 4.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect and EPLA with existing link. 6.Enable GE2 , ETH patching new port to Ibeam port Ge_0/2/2 and create LAG port. 7.Traffic migrate to new parallel and new LAG port. 8.No link to be decomm. | XMC_3E | MAC | 23G | 0.6 | 0.6 | NR services | SQ202512160988-NR Services | NR services | SQ202512160980-NR Services // SQ202512160985-NR Services // SQ202512240383-NR Services |  |  | Ongoing | 2025-12-16 | 2025-12-18 | 2025-12-16 | 2025-12-16 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25111919 |  | 2025-11-20 | 2025-12-11 | Completed | 2025-11-19 | 2025-11-20 | 2025-11-19 | 2025-12-11 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-08 | 2026-01-08 | 2025-12-06 | 2025-12-11 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-12-08 | 2026-01-08 | 2025-12-06 | 2025-12-11 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-11 | 2025-12-08 | 2026-01-08 | 2025-12-06 | 2025-12-15 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2025-11-04: 2025-12-08; 2025-11-04: 2026-01-08; 2025-11-04: 2025-12-06; 2025-12-02: 2025-12-09 |  |  | 2025-12-24 | 2026-01-24 | 2025-12-24 | 2025-12-24 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202510100630-GCI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | CHEONG/SENG/WAH/7018000306
7118D_HU | JALAN BAWAH KUDAT | DU00006149672 | Sabah | Sabah | 6.905770 | 116.849000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M_512QAM NE_7118D Re-use existing Antenna. Re-use existing RTN910A(RTN01). New XMC_3E, Sub B_Hi x1. FE_7013A Re-use existing Antenna. Re-use existing RTN910A(RTN07). New XMC_3E, Sub B_Lo x1. | MW Hardware Upgrade | Existing HW MW link 18G_1+0_56M_1024QAM. MW Hardware Upgrade from BW 56MHz to 112MHz. Site Impacted : 7118D. NE_7118D 1.Swap existing 18G ODU XMC-3 to new 18G ODU XMC_3E, Sub B_Hi x1. 2.Configure HW MW Link 18G_1+0_112M_512QAM. FE_7013A 1.Swap existing 18G ODU XMC-3 to new 18G ODU XMC_3E, Sub B_Lo x1. 2.Configure HW MW Link 18G_1+0_112M_512QAM. | Existing HW MW link 18G_1+0_56M_1024QAM. MW Hardware Upgrade from BW 56MHz to 112MHz. Site Impacted : 7118D. NE_7118D 1.Swap existing 18G ODU XMC-3 to new 18G ODU XMC_3E, Sub B_Hi x1. 2.Configure HW MW Link 18G_1+0_112M_512QAM. | Existing HW MW link 18G_1+0_56M_1024QAM. MW Hardware Upgrade from BW 56MHz to 112MHz. Site Impacted : 7118D. FE_7013A 1.Swap existing 18G ODU XMC-3 to new 18G ODU XMC_3E, Sub B_Lo x1. 2.Configure HW MW Link 18G_1+0_112M_512QAM. | XMC-3E | MAC | 18G | 18G_SP_0.6M(MAC) x1. | 18G_SP_0.6M(MAC) x1. | NR services | SQ202512300323-NR Services | NR services | SQ202512190080-NR Services // SQ202512190088-NR Services | 2026-03-02 | 2026-02-23 | Completed | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-23 | 2026-01-30 | 2026-01-23 | 2026-01-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-23 | 2026-01-30 | 2026-01-23 | 2026-01-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111916 |  | 2025-11-20 | 2025-12-20 | Completed | 2025-11-19 | 2025-11-20 | 2025-11-19 | 2025-12-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-20 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-20 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-12-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-21 | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-29 | RALPH O'BRYAN HILARY7167000030 | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-20 | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-11 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202510100645-GTSB
7554B_HU | Batu 86 Sandakan (REL) | DU00006149673 | Sabah | Sabah | 5.640760 | 117.195200 | [7 empty] | 05. TI WIP |  | TSS+AA+TI |  | 15G_2+0_28M_512QAM_EPLA NE_7554B New 15G_1.2M(MDD) x1. Re-use existing RTN950A(RTN01, NEID 9-19302). New ISM8 x1. New XMC_5D Pro, Sub B_Lo x1. FE_7438B New 15G_1.2M(MDD) x1. Re-use existing RTN950A(RTN01, NEID 9-19303). New ISM8 x1. New XMC_5D Pro, Sub B_Hi x1. | MW Parallel Link | ****IMPORTANT NOTE: PLEASE APPLY CRQ FOR ALL EB RELATED SITES AS MENTION AT IMPACTED SITE BELOW. DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET**** Existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7554B, 7105Z, 7709E, 7635E, 7636E, 7647E, 7626E, 7627E, 7726E, 7653E, 7643E, 7711E & 7637E. NE_7554B 1.Install new 15G1.2M(MDD) x1. 2.Re-use existing RTN950A(RTN01, NEID 9-19302) and insert ISM8 into slot 06. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. FE_7438B 1.Install new 15G1.2M(MDD) x1. 2.Re-use RTN950A(RTN01, NEID 9-19303) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: PLEASE APPLY CRQ FOR ALL EB RELATED SITES AS MENTION AT IMPACTED SITE BELOW. DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET**** Existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7554B, 7105Z, 7709E, 7635E, 7636E, 7647E, 7626E, 7627E, 7726E, 7653E, 7643E, 7711E & 7637E. NE_7554B 1.Install new 15G1.2M(MDD) x1. 2.Re-use existing RTN950A(RTN01, NEID 9-19302) and insert ISM8 into slot 06. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: PLEASE APPLY CRQ FOR ALL EB RELATED SITES AS MENTION AT IMPACTED SITE BELOW. DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET**** Existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7554B, 7105Z, 7709E, 7635E, 7636E, 7647E, 7626E, 7627E, 7726E, 7653E, 7643E, 7711E & 7637E. FE_7438B 1.Install new 15G1.2M(MDD) x1. 2.Re-use RTN950A(RTN01, NEID 9-19303) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. | XMC-5D Pro | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | Seri Pancar | SQ202602090132-Seri Pancar | NR services | SQ202602250589-NR Services // SQ202602250593-NR Services |  |  | Ongoing | 2026-02-04 | 2026-02-28 | 2026-02-24 | 2026-02-27 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26021235 |  | 2026-02-13 | 2026-02-21 | Completed | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-19 | 2026-03-19 | 2026-02-19 | 2026-03-15 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-02-19 | 2026-03-19 | 2026-02-19 |  | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | [7 empty] | 2026-02-19 | 2026-03-19 | 2026-02-19 |  | IBRAHIM//BIN SAHABU/7167000007 | 2025-11-04: 2026-02-21; 2025-11-04: 2026-03-21; 2025-11-04: 2026-02-21; 2025-12-02: 2026-02-23 | [7 empty] | GTSB | SQ202510100645-GTSB
1561B6_HU | pBTS Tmn Kapar Setia (C ) | DU00006161021 | Central | Selangor | 3.131140 | 101.392780 | [7 empty] | 06. Other Issue | 6/4/2026: Modulation degrade, TT raised on 3/4, pending TT clearance to proceed Remote Upgrade | AA |  |  | MW Remote Upgrade | Link Existing HW 18G_2+0_56M_512QAM_844M_EPLA. MW Remote Upgrade to HW 18G_2+0_110M_128QAM_1352M_EPLA. Site Impacted : 1561B6. NE_1561B6 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz(128QAM). FE_2475A 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz(128QAM). | Link Existing HW 18G_2+0_56M_512QAM_844M_EPLA. MW Remote Upgrade to HW 18G_2+0_110M_128QAM_1352M_EPLA. Site Impacted : 1561B6. NE_1561B6 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz(128QAM). | Link Existing HW 18G_2+0_56M_512QAM_844M_EPLA. MW Remote Upgrade to HW 18G_2+0_110M_128QAM_1352M_EPLA. Site Impacted : 1561B6. FE_2475A 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz(128QAM). | XMC_3 | MAC | 18G | 18G_DP_0.6M(MAC)+OMT x1. | 18G_DP_1.2M(MAC)+OMT x1. | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202510100638-GTSB | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | AB.RAHMAN//BIN MAT NOOH/6237001519
1063L_HU | Telipot | DU00006161022 | Central | Selangor | 3.407610 | 101.597170 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 23G_1+0_56M_512QAM_395M. MW Remote Upgrade to HW 23G_1+0_112M_512QAM_889M. Site Impacted : 1063L. NE_1063L 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz(512QAM). FE_2069A/B00135 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz(512QAM). | Link Existing HW 23G_1+0_56M_512QAM_395M. MW Remote Upgrade to HW 23G_1+0_112M_512QAM_889M. Site Impacted : 1063L. NE_1063L 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz(512QAM). | Link Existing HW 23G_1+0_56M_512QAM_395M. MW Remote Upgrade to HW 23G_1+0_112M_512QAM_889M. Site Impacted : 1063L. FE_2069A/B00135 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz(512QAM). | XMC-3 | MAC | 23G | 23G_SP_0.6M(MAC) x1. | 23G_SP_0.6M(MAC) x1. | In-House |  | In-House |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-12 | [15 empty] | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202605080161-GTSB
2007B_HU | Tmn Bunga Raya | DU00006161023 | Central | Selangor | 3.445270 | 101.542190 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_110M_128QAM_EPLA NE_2007B New 18G_DP_1.2M(MDD) x1. Re-use existing RTN910AF(RTN04). New XMC_5D, Sub A_Lo x2. New ISM8 x1. FE_1892B New 18G_DP_1.2M(MDD) x1. Re-use existing RTN910AF(RTN02). New XMC_5D, Sub A_Hi x2. New ISM8 x1. | MW Swap | Existing HW MW link 13G&15G_4+0_28M_512QAM_EPLA. Swap existing link to new HW MW Link 18G_2+0_110M_128QAM_EPLA. Later, decom existing HW MW link 13G&15G_4+0_28M_512QAM_EPLA(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. Site Impacted : 2007B & 1019R(Ops Team please confirm, seem no traffic for 1019R) NE_2007B 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN04). Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN04). 3.Install new XMC_5D, Sub A_Lo x1. Build new HW MW Link 18G_2+0_110M_128QAM_EPLA. 4.Re-use existing Vlan DCN and Vlan services. 5.Migrate traffics via new HW MW Link 18G_2+0_110M_128QAM_EPLA. 6.Later, decom existing HW MW link 13G&15G_4+0_28M_512QAM_EPLA(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. FE_1892B 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02). Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN02). 3.Install new XMC_5D, Sub A_Hi x1. Build new HW MW Link 18G_2+0_110M_128QAM_EPLA. 4.Re-use existing Vlan DCN and Vlan services. 5.Migrate traffics to existing IBeam port at CP(1413A). 6.Re-use existing Vlan DCN and Vlan services. 7.Later, decom existing HW MW link 13G&15G_4+0_28M_512QAM_EPLA(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. | Existing HW MW link 13G&15G_4+0_28M_512QAM_EPLA. Swap existing link to new HW MW Link 18G_2+0_110M_128QAM_EPLA. Later, decom existing HW MW link 13G&15G_4+0_28M_512QAM_EPLA(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. Site Impacted : 2007B & 1019R(Ops Team please confirm, seem no traffic for 1019R) NE_2007B 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN04). Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN04). 3.Install new XMC_5D, Sub A_Lo x1. Build new HW MW Link 18G_2+0_110M_128QAM_EPLA. 4.Re-use existing Vlan DCN and Vlan services. 5.Migrate traffics via new HW MW Link 18G_2+0_110M_128QAM_EPLA. 6.Later, decom existing HW MW link 13G&15G_4+0_28M_512QAM_EPLA(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. | Existing HW MW link 13G&15G_4+0_28M_512QAM_EPLA. Swap existing link to new HW MW Link 18G_2+0_110M_128QAM_EPLA. Later, decom existing HW MW link 13G&15G_4+0_28M_512QAM_EPLA(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. Site Impacted : 2007B & 1019R(Ops Team please confirm, seem no traffic for 1019R) FE_1892B 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02). Insert new ISM8 x1 into slot 04 of existing RTN910AF(RTN02). 3.Install new XMC_5D, Sub A_Hi x1. Build new HW MW Link 18G_2+0_110M_128QAM_EPLA. 4.Re-use existing Vlan DCN and Vlan services. 5.Migrate traffics to existing IBeam port at CP(1413A). 6.Re-use existing Vlan DCN and Vlan services. 7.Later, decom existing HW MW link 13G&15G_4+0_28M_512QAM_EPLA(ODU & Antenna ONLY). Anyway, do not decom(re-use) IDU(RTN910AF) at NE and FE sites. | XMC_3E | MDD | 18G | 18G_1.2M(MDD) x1. | 18G_1.2M(MDD) x1. | MTK | SQ202510220678-MTK | MTK | SQ202510220635-MTK // SQ202510220646-MTK | 2026-03-02 | 2026-02-23 | Completed | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-28 | 2026-02-04 | 2026-01-28 | 2026-01-28 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110706 |  | 2025-12-11 | 2025-11-15 | Completed | 2025-11-10 | 2025-12-11 | 2025-11-07 | 2025-11-15 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-05 | 2025-12-15 | 2025-12-05 | 2025-12-05 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-12-05 | 2025-12-15 | 2026-01-06 | 2026-01-06 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-10 | 2025-12-05 | 2025-12-15 | 2026-01-09 | 2026-01-09 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-12-05 | 2025-12-15 | 2025-12-08 | 2025-12-08 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202510100638-GTSB
1413A_IPR | KTM Rawang | DU00006161024 | Central | Selangor | 3.319439 | 101.576111 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cable x1 | MW IDU Patching | Perform LAG at CP site for IDU 1413A-KTM RAWANG-RTN15 to 1413A-MAC-001 KTM Rawang 1) Patch 1413A-KTM RAWANG-RTN15 GE2 to new CP port 2) Create LAG 3) Impact sites: 3690C,2001B,1015C,1687H | Perform LAG at CP site for IDU 1413A-KTM RAWANG-RTN15 to 1413A-MAC-001 KTM Rawang 1) Patch 1413A-KTM RAWANG-RTN15 GE2 to new CP port 2) Create LAG 3) Impact sites: 3690C,2001B,1015C,1687H | [6 empty] | GCI | SQ202601300931-GCI | GCI | SQ202601300924-GCI | 2026-01-30 | 2026-02-03 | Completed | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-29 | 2026-01-30 | 2026-01-29 | 2026-01-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-29 | 2026-01-30 | 2026-01-29 | 2026-02-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100949 |  | 2025-10-12 | 2025-11-28 | Completed | 2025-10-11 | 2025-10-12 | 2025-10-09 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-28 | 2026-02-04 | 2026-01-27 | 2026-01-28 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-28 | 2026-02-04 | 2026-01-27 | 2026-02-13 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-28 | 2026-01-28 | 2026-02-04 | 2026-01-27 | 2026-02-13 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-11-04: 2026-01-28; 2025-11-04: 2026-02-04; 2025-11-04: 2026-01-27; 2025-12-02: 2026-01-28 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510100626-GCI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | CHEONG/SENG/WAH/7018000306
1015C_HU | Tmn Saujana Rawang | DU00006161025 | Central | Selangor | 3.342710 | 101.513000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M ant changed to 0.6M due to structure and space. NE_1015C 15G_DP_0.6M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Hi x1. FE_2001B 15G_DP_1.2M(MDD) x1. RTN910A. x1. ISM8 x2. XMC_5D , Sub A_Lo x1. | MW Swap | Existing link 15G_2+0_28M. Swap existing link to 15G_4+0_28M. ant changed to 0.6M due to structure and space. Site Impacted : 1051C. 1.Install 15G_DP_0.6M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new MW link. 7.Decom existing MW link. FE_2001B 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Create service cross connect , CA and EPLA. 5.Enable GE1 , ETH patching to existing 2001B_RTN08_GE2 (ID : 48387). 6.Traffic migrate to new MW link. 7.Decom existing MW link. | Existing link 15G_2+0_28M. Swap existing link to 15G_4+0_28M. Site Impacted : 1051C. NE_1015C. 1.Install 15G_DP_0.6M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new MW link. 7.Decom existing MW link. | Existing link 15G_2+0_28M. Swap existing link to 15G_4+0_28M. Site Impacted : 1051C. FE_2001B 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Create service cross connect , CA and EPLA. 5.Enable GE1 , ETH patching to existing 2001B_RTN08_GE2 (ID : 48387). 6.Traffic migrate to new MW link. 7.Decom existing MW link. | XMC_5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202511260105-Magicell | Magicell | SQ202512120476-Magicell // SQ202601190530-Magicell // SQ202602220060-Magicell // SQ202603060051-Magicell | 2025-12-04 | 2025-12-03 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111255 |  | 2025-12-13 | 2025-11-18 | Completed | 2025-11-12 | 2025-12-13 | 2025-11-12 | 2025-11-18 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2026-01-06 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2026-01-06 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-11 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2026-01-07 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-10 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510100626-GCI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | CHEONG/SENG/WAH/7018000306
3310C_HU | Desa Alam Seksyen U12 Shah Alam | DU00006161026 | Central | Selangor | 3.079016 | 101.482350 | [7 empty] | 05. Doable |  | TSS+AA+TI | L1+ATP+PAC |  | MW Hardware Upgrade | MW HARDWARE UPGRADE (REALIGNMENT ANTENNA DUE TO RSL LOW) IDU PATCHING AT FE 1713B/B00640_SEKSYEN 7 BKT RAJA - 3310C_DESA ALAM U12 (3310C (RTN02-V)) PATCH TO NEW 10G PORT MW REMOTE UPGRADE LINK 3310C-1713B 23G_2+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: 3310C, 3293A | REALLIGNMENT ANTENNA DUE TO RSL LOW REMOTE UPGRADE LINK 3310C-1713B 23G_2+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: 3310C | REALLIGNMENT ANTENNA DUE TO RSL LOW MW IDU PATCHING AT FE 1713B/B00640_SEKSYEN 7 BKT RAJA - 3310C_DESA ALAM U12 (3310C (RTN02-V)) PATCH TO NEW 10G PORT MW REMOTE UPGRADE LINK 3310C-1713B 23G_2+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: 3310C | XMC3 | MS | 23G | 0.6 | 0.6 | Magicell | SQ202601210060-Magicell | Magicell | SQ202512120476-Magicell // SQ202601210057-Magicell // SQ202601210059-Magicell |  |  | Ongoing | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25111254 |  | 2025-11-17 | 2025-12-03 | Completed | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-12-03 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-12-03 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2026-04-20 | 2027-04-15 | 2026-04-20 |  | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-20 | 2027-04-15 | 2026-04-20 |  | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | 2025-12-09: 2026-04-20; 2025-12-09: 2027-04-15; 2025-12-09: 2026-04-20; 2025-12-10: 2026-04-27 | [7 empty] | GCI | SQ202510100626-GCI | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-22 | EZRIN TASNIM BIN ABDUL GANI6798000128
1007A_IPR | Mimaland | DU00006161027 | Central | Selangor | 3.286610 | 101.723330 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 1KM 2x Patch Cord(Pair) | IDU-IPRAN | Perform LAG at CP site for IDU 1007A-MIMALAND-RTN01 to 1007A-MAC-001 Mimaland 1) Patch 1007A-MIMALAND-RTN01 GE2 to new CP port 2) Create LAG 3) Impact sites: 2012B,B01469,1097L | Perform LAG at CP site for IDU 1007A-MIMALAND-RTN01 to 1007A-MAC-001 Mimaland 1) Patch 1007A-MIMALAND-RTN01 GE2 to new CP port 2) Create LAG 3) Impact sites: 2012B,B01469,1097L | N/A | [5 empty] | GTSB | SQ202510090246-GTSB | Magicell | SQ202511030654-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100948 |  | 2025-10-30 | 2025-11-13 | Completed | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-13 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-13 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-13 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-11 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-13 | AHMAD RASHIDI BIN SAFRI7018000135 | 2025-12-09: 2025-10-30; 2025-12-09: 2025-10-30; 2025-12-09: 2025-10-30; 2025-12-10: 2025-11-05 |  |  | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202510100626-GCI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | EZRIN TASNIM BIN ABDUL GANI6798000128
A00406_HU | PKLNBARU | DU00006161028 | Northern | Perak | 4.482610 | 100.652410 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M NE_A00406 13G_DP_1.2M(MDD) x1. RTN910A. x1. ISM8 x2. XMC_5D , Sub B_Lo x1. FE_A00133 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub B_Hi x1. | MW Swap | Existing SM link 13G_2+0_28M Swap existing to 13G_4+0_28M Site Impacted : A00406. NE_A00406 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to mw new link. 7.Decom existing SM MW link (NT05397). FE_A00133 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Install new XMC_5D , Sub B_Hi. 5.Create service cross connect , CA and EPLA. 6.Create new Inband DCN. 7.Traffic migrate to mw new link. 8.Decom existing SM MW link (NT05397). | Existing SM link 13G_2+0_28M. Swap existing to 13G_4+0_28M. Site Impacted : A00406. NE_A00406 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to mw new link. 7.Decom existing SM MW link (NT05397). | Existing SM link 13G_2+0_28M Swap existing to 13G_4+0_28M Site Impacted : A00406. FE_A00133 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 4.Install new XMC_5D , Sub B_Hi. 5.Create service cross connect , CA and EPLA. 6.Create new Inband DCN. 7.Traffic migarte to mw new link. 8.Decom existing SM MW link (NT05397). | [5 empty] | Magicell | SQ202510220709-Magicell | Magicell | SQ202510220690-Magicell // SQ202510220702-Magicell // SQ202511260115-Magicell | 2025-12-04 | 2025-12-03 | Completed | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102325 |  | 2025-10-24 | 2025-10-27 | Completed | 2025-10-23 | 2025-10-24 | 2025-10-23 | 2025-10-27 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-08 | 2026-11-07 | 2025-11-08 | 2025-11-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-08 | 2026-11-07 | 2025-11-08 | 2025-12-10 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-10 | 2025-11-08 | 2026-11-07 | 2025-11-08 | 2025-12-10 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-11-08 | 2026-11-07 | 2025-11-08 | 2025-11-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510100628-GCI | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | CHEONG/SENG/WAH/7018000306
7221A_IPR | Kinarut | DU00006161029 | Sabah | Sabah | 5.822128 | 116.044786 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 1KM 2x Patch Cord(Pair) | IDU-IPRAN | Perform LAG at CP site for IDU 7221A- KINARUT-RTN03 to 7221A-MAC-001 Kinarut 1) Patch 7221A- KINARUT-RTN03 GE2 to new CP port 2) Create LAG 3) Impact sites: 7185B,7259C | Perform LAG at CP site for IDU 7221A- KINARUT-RTN03 to 7221A-MAC-001 Kinarut 1) Patch 7221A- KINARUT-RTN03 GE2 to new CP port 2) Create LAG 3) Impact sites: 7185B,7259C | N/A | [5 empty] | NR services | SQ202511270722-NR Services | NR services | SQ202511190097-NR Services | 2026-01-13 | 2026-01-13 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111393 |  | 2025-11-14 | 2025-11-15 | Completed | 2025-11-13 | 2025-11-14 | 2025-11-13 | 2025-11-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-12-18 | 2025-11-18 | 2025-11-19 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-11-18 | 2025-12-18 | 2025-11-18 | 2025-11-19 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-19 | 2025-11-18 | 2025-12-18 | 2025-11-18 | 2025-11-19 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-12-09: 2025-11-18; 2025-12-09: 2025-12-18; 2025-12-09: 2025-11-18; 2025-12-10: 2025-11-19 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202510100630-GCI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | EZRIN TASNIM BIN ABDUL GANI6798000128
1435A_HU | Rampaitown | DU00006161030 | Central | Kuala Lumpur | 3.194680 | 101.731890 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_110M_128QAM_EPLA NE_1435A New 18G_0.6M(MDD) x1. New RTN910AF(RTN05). New XMC_5D, Sub B_Lo x1. New CAT6 cable x2. FE_1737A New 18G_0.6M(MDD) x1. New RTN910AF(RTN18). New XMC_5D, Sub B_Hi x1. New CAT6 cable x2. | MW Parallel Link | Build new HW MW Parallel Link 1435A-1737A, 18G_2+0_110MHZ_128QAM_EPLA. Site Impacted : 1435A & 1271C. NE_1435A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN05). 3.Install new XMC_5D, Sub B_Lo x1. 4.Build new HW MW Parallel Link 1435A-1737A, 18G_2+0_110MHZ_128QAM_EPLA. 5.Disconnect cascade between port 8-EM6-1 of existing RTN910AF(RTN04) and port 8-EM6-1 of existing RTN910AF(RTN01). 6.Enable port 8-EM6-1 of new RTN910AF(RTN05). 7.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN05) and port 8-EM6-1 of existing RTN910AF(RTN01). 8.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 9.Later, perform load balancing by diverting traffics 1435A & 1271C via new HW MW Parallel Link 1435A-1737A, 18G_2+0_110MHZ_128QAM_EPLA. FE_1737A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN18). 3.Install new XMC_5D, Sub B_Hi x1. 4.Build new HW MW Parallel Link 1435A-1737A, 18G_2+0_110MHZ_128QAM_EPLA. 5.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN18) and perform LAG. 6.Request 2x new IBeam ports 1G and perform LAG. 7.Later, perform load balancing by diverting traffics 1435A & 1271C via new 2x new IBeam ports. | Build new HW MW Parallel Link 1435A-1737A, 18G_2+0_110MHZ_128QAM_EPLA. Site Impacted : 1435A & 1271C. NE_1435A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN05). 3.Install new XMC_5D, Sub B_Lo x1. 4.Build new HW MW Parallel Link 1435A-1737A, 18G_2+0_110MHZ_128QAM_EPLA. 5.Disconnect cascade between port 8-EM6-1 of existing RTN910AF(RTN04) and port 8-EM6-1 of existing RTN910AF(RTN01). 6.Enable port 8-EM6-1 of new RTN910AF(RTN05). 7.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN05) and port 8-EM6-1 of existing RTN910AF(RTN01). 8.Request new Vlan DCN and Vlan services from ZTE IPRAN Team. 9.Later, perform load balancing by diverting traffics 1435A & 1271C via new HW MW Parallel Link 1435A-1737A, 18G_2+0_110MHZ_128QAM_EPLA. | Build new HW MW Parallel Link 1435A-1737A, 18G_2+0_110MHZ_128QAM_EPLA. Site Impacted : 1435A & 1271C. FE_1737A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN18). 3.Install new XMC_5D, Sub B_Hi x1. 4.Build new HW MW Parallel Link 1435A-1737A, 18G_2+0_110MHZ_128QAM_EPLA. 5.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN18) and perform LAG. 6.Request 2x new IBeam ports 1G and perform LAG. 7.Later, perform load balancing by diverting traffics 1435A & 1271C via new 2x new IBeam ports. | XMC-5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_0.6M(MDD) x1. | MTK | SQ202510220678-MTK | MTK | SQ202510220635-MTK // SQ202510220646-MTK | 2026-01-28 | 2026-01-30 | Completed | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102432 |  | 2025-10-28 | 2025-10-30 | Completed | 2025-10-27 | 2025-10-28 | 2025-10-25 | 2025-10-30 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-18 | 2025-12-31 | 2025-12-22 | 2025-12-22 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-12-18 | 2025-12-31 | 2026-01-13 | 2026-01-13 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-30 | 2025-12-18 | 2025-12-31 | 2026-01-13 | 2026-01-13 | RIDHUAN//BIN MANSOR/8225000011 | 2025-12-09: 2025-12-18; 2025-12-09: 2025-12-31; 2025-12-09: 2025-12-22; 2025-12-10: 2025-12-22 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202510100638-GTSB
1350A_HU | Sri Muda | DU00006161031 | Central | Selangor | 3.036530 | 101.535420 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_55M_128QAM_EPLA NE_1350A New 18G_DP_0.6M(MAC)+OMT x1. New RTN910AF(RTN03) x1. New XMC_3, Sub A_Hi x2. New CAT6 cable x1. FE_1342A New 18G_DP_0.6M(MAC)+OMT x1. New RTN910AF(RTN15) x1. New XMC_3, Sub A_Lo x2. New CAT6 cable x1. | MW Parallel Link | Build new HW MW Parallel Link 1350A-1342A, 18G_2+0_55MHZ_128QAM_EPLA. Site Impacted : 1350A NE_1350A 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN03). 3.Install new XMC_3, Sub A_Hi x2. 4.Build new HW MW Parallel Link 1350A-1342A, 18G_2+0_55MHZ_128QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910AF(RTN03). 6.Disconnect BBU 1350A from port 8-EG6-2 of existing RTN910(RTN01). 7.Perform patching BBU 1350A to port 8-EM6-1 of new RTN910AF(RTN03). 8.Request new Vlan DCN and Vlan Services from ZTE IPRAN Team. 9.Migrate traffic 1350A ONLY via new HW MW Parallel Link 1350A-1342A, 18G_2+0_55MHZ_128QAM_EPLA. FE_1737A 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN15). 3.Install new XMC_3, Sub A_Lo x2. 4.Build new HW MW Parallel Link 1350A-1342A, 18G_2+0_55MHZ_128QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910AF(RTN15). 6.Request new IBeam port, new Vlan DCN and Vlan Services from ZTE IPRAN Team. 7.Migrate traffic 1350A ONLY via new IBeam port. | Build new HW MW Parallel Link 1350A-1342A, 18G_2+0_55MHZ_128QAM_EPLA. Site Impacted : 1350A NE_1350A 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN03). 3.Install new XMC_3, Sub A_Hi x2. 4.Build new HW MW Parallel Link 1350A-1342A, 18G_2+0_55MHZ_128QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910AF(RTN03). 6.Disconnect BBU 1350A from port 8-EG6-2 of existing RTN910(RTN01). 7.Perform patching BBU 1350A to port 8-EM6-1 of new RTN910AF(RTN03). 8.Request new Vlan DCN and Vlan Services from ZTE IPRAN Team. 9.Migrate traffic 1350A ONLY via new HW MW Parallel Link 1350A-1342A, 18G_2+0_55MHZ_128QAM_EPLA. | Build new HW MW Parallel Link 1350A-1342A, 18G_2+0_55MHZ_128QAM_EPLA. Site Impacted : 1350A FE_1737A 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN15). 3.Install new XMC_3, Sub A_Lo x2. 4.Build new HW MW Parallel Link 1350A-1342A, 18G_2+0_55MHZ_128QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910AF(RTN15). 6.Request new IBeam port, new Vlan DCN and Vlan Services from ZTE IPRAN Team. 7.Migrate traffic 1350A ONLY via new IBeam port. | XMC_3 | MAC | 18G | 18G_DP_0.6M(MAC)+OMT x1. | 18G_DP_0.6M(MAC)+OMT x1. | MTK | SQ202510220678-MTK | MTK | SQ202510220635-MTK // SQ202510220646-MTK | 2026-04-09 | 2026-04-06 | Completed | 2025-12-17 | 2026-02-26 | 2026-02-26 | 2026-02-26 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-01 | 2026-04-08 | 2026-04-01 | 2026-04-01 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102431 |  | 2025-10-28 | 2025-10-30 | Completed | 2025-10-27 | 2025-10-28 | 2025-10-25 | 2025-10-30 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-13 | 2025-11-30 | 2026-01-17 | 2026-01-17 | MOHD FADZILLAH BIN TARMIJI8225000017 | MTK TI | 2025-11-13 | 2025-11-30 | 2026-01-19 | 2026-01-19 | MOHD FADZILLAH BIN TARMIJI8225000017 | MTK TI | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-20 | 2025-11-13 | 2025-11-30 | 2026-01-19 | 2026-01-19 | MOHD FADZILLAH BIN TARMIJI8225000017 | 2025-12-09: 2025-11-13; 2025-12-09: 2025-11-30; 2025-12-09: 2025-11-20; 2025-12-10: 2025-11-20 |  |  | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202510100638-GTSB
4199R_HU | Kg. Rahmat | DU00006161032 | Northern | Perak | 4.111810 | 100.783450 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_512QAM_889M. Site Impacted : 4199R NE_4199R 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. FE_4027C 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_512QAM_889M. Site Impacted : 4199R NE_4199R 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | Link Existing HW 18G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 18G_1+0_110M_512QAM_889M. Site Impacted : 4199R FE_4027C 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | XMC_3E | MAC | 18G | 18G_SP_1.2M(MAC) x1. | 18G_SP_1.2M(MAC) x1. | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25102324 |  | 2025-10-24 | 2025-10-27 | Completed | 2025-10-23 | 2025-10-24 | 2025-10-23 | 2025-10-27 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [13 empty] | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-29 | [15 empty] | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202510100642-GTSB
2981Q_AD | Qcell CD StoreKLCC Suria 2 | DU00006816481 | Central | Kuala Lumpur | 3.157530 | 101.712065 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7257R_AD | Kg. BonsikuMatunggong | DU00006816482 | Sabah | Sabah | 6.861191 | 116.729305 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2974B_AD | KLCCConvention Center | DU00006816483 | Central | Kuala Lumpur | 3.153908 | 101.713238 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4948B_LOS_1 | Kg Pida 3 | DU00006816484 | Northern | Kedah | 6.278111 | 100.314723 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
W00705_AD | W066N_W00705IB1_KLCONVENTION | DU00006816485 | Central | Kuala Lumpur | 3.153908 | 101.713700 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2799A_LOS | Kemuning UtamaApartment | DU00006816486 | Central | Selangor | 3.001643 | 101.542320 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9413A-Q00085 | Jln. Stadium | DU00004238841 | Sarawak | Sarawak | 1.583710 | 110.369750 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done | 14/10: Pending Site DO | TSS+TI | L1+ATP+PAC |  | BBU Patching | BBU Patching from MW to xD LL 9413A. | [7 empty] | Trintel | SQ202504170489-Trintel | Trintel | SQ202504210232-Trintel // SQ202504260214-Trintel | 2025-04-25 | 2025-04-21 | Completed | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-16 | 2025-04-18 | 2025-04-16 | 2025-04-16 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-16 | 2025-04-18 | 2025-04-16 | 2025-04-16 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2025-04-08 | 2025-04-08 | Completed | 2025-04-07 | 2025-04-08 | 2025-04-08 | 2025-04-08 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-08 | 2025-05-08 | 2025-04-08 | 2025-04-08 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-04-08 | 2025-05-08 | 2025-04-08 | 2025-04-08 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  | 2025-04-08 | 2025-04-08 | 2025-05-08 | 2025-04-18 | 2025-04-18 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | 2025-12-09: 2025-04-08; 2025-12-09: 2025-05-08; 2025-12-09: 2025-04-08; 2025-12-10: 2025-04-08 |  |  | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
2739A-2737A | Pst Perindustrian KL | DU00004255519 | Central | Kuala Lumpur | 3.084444 | 101.670555 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | Cutover done | AA | PAC | Remote Software Upgrade from 2+0_56M to 2+0_112M | MW Remote Upgrade | Software upgrade from 18G_2+0_56M to 18G_2+0_112M for link 2739A-2737A. | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 | [17 empty] | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
3773C_LOS | Taman Subang Damai (REL) | DU00004255520 | Central | Kuala Lumpur | 3.167063 | 101.543092 |  |  | W49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 2/12: Cutover done. Post-CO T/S ongoing | TSS+TI | L1+ATP+PAC | BBU Patching | BBU Patching | BBU Patching at 3773C/B00732 | [7 empty] | Datasco | SQ202411140206-Datasco | Datasco | SQ202411150529-Datasco // SQ202504260127-Datasco | 2025-11-25 | 2025-11-25 | Completed | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-04 | 2025-07-05 | 2025-07-04 | 2025-07-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-04 | 2025-07-05 | 2025-07-04 | 2025-07-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241105CC |  | 2024-11-06 | 2024-11-26 | Completed | 2024-11-05 | 2024-11-06 | 2024-11-05 | 2024-11-26 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2025-02-25 | MOHAMMAD//FAIZ BIN ABDUL RAHIM/7019000040 | Datasco TI | 2024-12-02 | 2024-12-02 | 2024-12-02 |  | MOHAMMAD//FAIZ BIN ABDUL RAHIM/7019000040 | Datasco TI | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2024-12-02 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  |  | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2024-12-02 | MOHAMMAD//FAIZ BIN ABDUL RAHIM/7019000040 | 2025-12-09: 2024-12-02; 2025-12-09: 2024-12-02; 2025-12-09: 2024-12-02; 2025-12-10: 2024-12-02 |  |  | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202507080517-GCI | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
7456A_LOS | Kg Lunguyan | DU00004255521 | Sabah | Sabah | 5.341996 | 116.438890 |  |  |  |  | Drop/Cancel |  |  | 00. Site Out/Drop | 20/9: Pending Tx Solution for HU | TSS |  | NA | MW New Link / Reroute | Proposed to Fiber due to No LOS found via TSS survey. | [7 empty] | YPTT | SQ202411120054-YPTT |  |  | 2025-05-24 | 2025-05-23 | Completed | 2024-11-02 | 2024-11-02 | 2024-11-03 | 2024-11-03 | DOMINIC DAVIES6794000049 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-08 | 2025-01-10 | 2025-01-08 | 2025-01-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-08 | 2025-01-10 | 2025-01-08 | 2025-01-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-23 | 2025-05-24 | 2025-05-23 | 2025-05-23 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4627C_LOS | Masjid Batu Kg Pertama | DU00004255522 | Northern | Penang | 5.390040 | 100.417535 | [7 empty] | 00. Integrated/RFS Done | 27/11: D2: Cutover done 22/11: NE PTW expired (Omnix), plan continue W48 12/11: TI NE done, Pending FE - need new antenna (faulty) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M NE_4627C 18G_SP_0.6m x1. 18G_XMC_3E-1+0 x1. ISM8 x1. FE_4083B 18G_SP_0.6m x1. 18G_XMC_3E-1+0 x1. RTN 910A x1. | MW New Link / Reroute | Existing link 18G_1+0_56M. Link Reroute to new FE 4083B with 18G_1+0_112M due to LOS Block. Site Impacted: 4627C. NE_4627C 1.Install 18G_SP_0.6m 2.Install a new 18G_XMC_3E-1+0. 3.Reuse existing 4627C RTN_01. 4.Install 4_ISM8-1+0 into existing 4627C_RTN01. 5.Create service cross connect. 6.Traffic route to new FE_4083B. 7.Decom existing ODU and Ant. FE_4083B 1.Install 18G_SP_0.6m 2.Install a new 18G_XMC_3E-1+0. 3.Install new RTN 910A , 7_ISM8-1+0. 4.Create Inband DCN and service cross connect. 5.Enable GE1 patching ETH cable to PTN Fiber. 6.Traffic migrate to new FE 4083B PTN Fiber. 7.Decom existing MW link (4172A-4627C). | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202411150562-GCI | 2025-08-21 | 2025-08-20 | Completed | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-07 | 2025-08-08 | 2025-08-07 | 2025-08-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241022AD |  | 2024-10-23 | 2024-10-29 | Completed | 2024-10-22 | 2024-10-23 | 2024-10-22 | 2024-10-29 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-12 | 2024-11-30 | 2024-11-12 | 2024-12-06 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | GCI TI | 2024-11-12 | 2024-11-30 | 2024-11-12 | 2024-12-06 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | GCI TI | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-11-12 | 2024-11-30 | 2024-11-12 | 2024-11-29 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | 2025-12-09: 2024-11-12; 2025-12-09: 2024-11-30; 2025-12-09: 2024-11-12; 2025-12-10: 2024-11-29 |  |  | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202509041075-GCI | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
2105B_LOS | Hartamas Regency | DU00004255523 | Central | Kuala Lumpur | 3.172858 | 101.663336 | WK10 | MAR 25 | WK10 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 7/3/2025 : Cutover done 6/3/2025 : Installation complete, pending cutover due to access limit 5/3/2025 : Plan install NE and FE site - CRQ approved, cancel proceed due to waiting TM Adhoc PTW approved 4/3/2025 : Plan install NE and FE site - Cancel proceed due to TM PTW not yet approved 6/1/2025 : Digi OB - 3M Bipod - RT - NE site 2105B Hartamas Regency, TELEKOM (M) - 60M 3 Legged Tower - FE site 1054B TM Bukit Tungku(TMTouch) 20/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_2105B 18G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E-2+0 , Sub A & B_Hi x2.. FE_W00074 18G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E-2+0 , Sub A & B_Lo x2. | MW New Link / Reroute | Link reroute to new FE W00074 with 18G_2+0_112M due to LOS Block. NE_2105B 1.Install new 18G_DP_0.6m(MAC)+OMT 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E-2+0. 4.Enable EPLA and Service cross connect. 5.Traffic migrate to new route FE. 6.Decom existing MW link. FE_W00074 1.Install new 18G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E-2+0. 4.Enable EPLA and service cross connect. 5.Enable GE1 , ETH patching to Fiber_PTN (Gi0/0/1). 6.Traffic migrate to new link with new FE site. 7.Create new In Band DCN. 8.Decom existing MW link. | [7 empty] | Magicell | SQ202504150442-Magicell | Magicell | SQ202504260146-Magicell // SQ202505020406-Magicell // SQ202505020413-Magicell | 2025-07-02 | 2025-07-01 | Completed | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-07 | 2025-04-08 | 2025-04-07 | 2025-04-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25030555 |  | 2024-11-26 | 2024-12-30 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2024-12-30 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-04 | 2026-03-11 | 2025-03-04 | 2025-03-27 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-03-04 | 2026-03-11 | 2025-03-04 | 2025-03-27 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-03-07 | 2025-03-04 | 2026-03-11 | 2025-03-04 | 2025-03-19 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-03-04 | 2026-03-11 | 2025-03-04 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358
3863C_LOS | Taman Bukit Angkasa | DU00004255524 | Central | Kuala Lumpur | 3.107810 | 101.669810 |  |  |  |  | Cancel / Drop | Under TX NIC | ZTE | 00. Site Out/Drop | 6/3/2025 : Cancel / drop. Solution done under TX NIC 3863C |  |  | 3863C-1735A | Cancel / Drop | Follow SOW TX Rollout. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7332B_LOS | Kg Nahaba | DU00004255525 | Sabah | Sabah | 6.283383 | 116.517750 | [7 empty] | 00. Integrated/RFS Done | 25/11: D3: Cutover done. Post-CO T/S ongoing 22/11: Pre-install WIP. Continue 23/11 13/11: Pending Site DO 28/10: Need northbound link TX Mini 7426A-7401A ready | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Link reroute to new FE 7772B with config 15G_4+0_28M_CA due to LOS block. NE_7332B. 1.Install new 15G_DP_1.2m(MDD) x1. 2.Install new RTN910A x1. 3.Install ISM8 x2. 4.Install XMC-5D, Sub_A_Hi x1. FE_7772B 1.Install new 15G_DP_1.2m(MDD) x1. 2.Install new RTN910A x1. 3.Install new ISM8 x2. 4.Install XMC-5D,Sub_A_Lo x1. Create Parallel link for 7426A-7401A | MW New Link / Reroute | Existing link 18G_1+0_112M. Link reroute to new FE 7772B with config 15G_4+0_28M_CA due to LOS block. Create Parallel link for 7426A-7401A Site Impacted:7332B , 7772B NE_7332B. 1.Install new 15G_DP_1.2m(MDD). 2.Install new RTN910A.(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install XMC-5D, Sub_A_Hi. 5.Create EPLA , CA and service cross connect. 6.Migrate traffic to new link 15G_4+0_28M(7332B-7772B) and via existing link 7772B_RTN01. 7.Decom existing 18G MW link(7332B-7426A). FE_7772B 1.Install new 15G_DP_1.2m(MDD). 2.Install new RTN910A.(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install XMC-5D, Sub_A_Lo. 5.Create EPLA, CA and service cross connect. 6.Enable GE port, interconnect ETH cable to existing 7772B_RTN01. 7.Traffic migrate via existing link (7772B_RTN01-7426A_RTN01). 8.Decom existing 18G MW link. (7426A-7332B). | [7 empty] | YPTT | SQ202410280494-YPTT | NR services | SQ202411260121-NR Services // SQ202504260199-NR Services | 2025-07-11 | 2025-07-10 | Completed | 2024-10-19 | 2024-10-19 | 2024-10-20 | 2024-10-20 | DOMINIC DAVIES6794000049 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-22 | 2024-10-25 | 2024-10-22 | 2024-10-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-22 | 2024-10-25 | 2024-10-22 | 2024-10-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-10 | 2025-07-11 | 2025-07-10 | 2025-07-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241115BL |  | 2024-11-30 | 2024-11-23 | Completed | 2024-11-22 | 2024-11-30 | 2024-11-21 | 2024-11-23 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-22 | 2024-11-30 | 2024-11-21 | 2024-11-23 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-11-22 | 2024-11-30 | 2024-11-23 | 2024-11-23 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-27 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2024-11-22 | 2024-11-30 | 2024-11-21 | 2024-11-25 | RALPH O'BRYAN HILARY7167000030 | 2024-11-22 | 2024-11-30 | 2024-11-21 | 2024-11-22 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | tseping//wang/6819000006 | Logistic Team | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
1193H_LOS | 99 Speedmart TMN SAUJANA PUCHONG | DU00004267300 | Central | Kuala Lumpur | 2.989949 | 101.640076 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 23/1/2025 : Cutover done 22/1/2025 : NE installation complete, pending install FE site 6/1/2025 : Digi OB - Small Cell - NE site 1193H 99 Speedmart TMN SAUJANA PUCHONG, EDOTCO (M) SDN BHD - Monopole - FE site 3657C Persiaran Saujana Puchong | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | New NLOS RTN510 equipment NE_1193H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_3657C 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH Cable / LAN Cable. | MW New Link / Reroute | Link reroute to new FE 3657C with New NLOS RTN510 equipment due to LOS block NE_1193H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. FE_3657C 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.Enable GE1 , patching ETH cable to existing 3657C_RTN01(GE2). 6.Decom existing NLOS Radio. | [7 empty] | GCI | SQ202502260369-GCI | GCI | SQ202501030380-GCI // SQ202504150088-GCI | 2025-03-08 | 2025-03-07 | Completed | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-02-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-05 | 2025-03-06 | 2025-03-05 | 2025-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-07 | 2025-03-08 | 2025-03-07 | 2025-03-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010394 |  | 2025-01-04 | 2025-01-17 | Completed | 2025-01-03 | 2025-01-04 | 2025-01-03 | 2025-01-17 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-22 | 2025-01-29 | 2025-01-22 | 2025-01-24 | MUHAMMAD//MUBEEN/6800000279 | GCI TI | 2025-01-22 | 2025-01-29 | 2025-01-22 | 2025-02-04 | MUHAMMAD//MUBEEN/6800000279 | GCI TI | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-23 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-01-22 | 2025-01-29 | 2025-01-22 | 2025-02-02 | MUHAMMAD//MUBEEN/6800000279 | 2025-01-22 | 2025-01-29 | 2025-01-22 | 2025-01-24 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505070146-GCI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | CHEONG/SENG/WAH/7018000306
2600A_LOS | Lebuh Ampang | DU00004267301 | Central | Kuala Lumpur | 3.148806 | 101.697351 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 30/11: D2: Cutover done 28/11: MOS & TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_2600A 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E-2+0 , Sub A & B_Lo x2. FE_W01036 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E-2+0 , Sub A & B_Hi x2. | MW New Link / Reroute | Link reroute to new FE W01036 with 23G_2+0_112M due to LOS Block. NE_2600A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install XMC_3E-2+0 , Sub A & B_Lo. 4.Enable EPLA and service cross connect. 5.Traffic migrate to new route FE. 6.Decom existing MW link. FE_W01036 1.Install new 23G_DP_0.6M(MAC)+OMT 2.Install new RTN910A,7_ISM8-2+0. 3.Install XMC_3E-2+0 , Sub A & B_Hi. 4.Enable EPLA and service cross connect. 5.Create In Band DCN. 6.Traffic migrate to new link. 7.Decom existing MW link. | [7 empty] | Magicell | SQ202411180345-Magicell | Magicell | SQ202411250781-Magicell // SQ202504260146-Magicell | 2025-02-15 | 2025-02-14 | Completed | 2024-11-14 | 2024-11-14 | 2024-11-20 | 2024-11-20 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-13 | 2025-02-14 | 2025-02-13 | 2025-02-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-14 | 2025-02-15 | 2025-02-14 | 2025-02-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112528 |  | 2024-12-29 | 2024-12-13 | Completed | 2024-11-29 | 2024-12-29 | 2024-11-25 | 2024-12-13 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-29 | 2024-12-29 | 2024-12-12 | 2024-12-12 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2024-11-29 | 2024-12-29 | 2024-12-13 | 2024-12-13 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2024-12-04 | MOHD//AMIR BIN SAMSI/6799000184 | Magicell TI |  | 2024-11-29 | 2024-12-29 | 2024-12-09 | 2024-12-09 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | 2024-11-29 | 2024-12-29 | 2024-12-03 | 2024-12-03 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
7258R_HU | Sk Dampirit (Kg. Dampirit) | DU00006392382 | Sabah | Sabah | 6.887300 | 116.760800 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | XMC_3E NE XMC_3E , Sub A & B_Hi x 2. FE XMC_3E , Sub A & B_Lo x2. | MW Hardware Upgrade | Existing link 18G_2+0_28M with 256QAM Remote Software upgrade Modulation KPI not meeting. Hardware upgrade XMC_3 ODU to XMC_3E in order to get the higher TX Power. Alignment is required if not tally with LB. | Existing link 18G_2+0_28M with 256QAM Remote Software upgrade Modulation KPI not meeting. Hardware upgrade XMC_3 ODU to XMC_3E in order to get the higher TX Power. Alignment is required if not tally with LB. | Existing link 18G_2+0_28M with 256QAM Remote Software upgrade Modulation KPI not meeting. Hardware upgrade XMC_3 ODU to XMC_3E in order to get the higher TX Power. Alignment is required if not tally with LB. | [5 empty] | NR services | SQ202601210165-NR Services | NR services | SQ202512240373-NR Services // SQ202512240383-NR Services | 2026-02-23 | 2026-02-23 | Completed | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251210A9 |  | 2025-12-11 | 2025-12-11 | Completed | 2025-12-10 | 2025-12-11 | 2025-12-10 | 2025-12-11 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-17 | 2026-02-17 | 2026-01-17 | 2026-01-18 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-01-17 | 2026-02-17 | 2026-01-17 | 2026-01-18 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-20 | 2026-01-17 | 2026-02-17 | 2026-01-17 | 2026-01-23 | RALPH O'BRYAN HILARY7167000030 | 2026-01-17 | 2026-02-17 | 2026-01-17 | 2026-01-18 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | tseping//wang/6819000006 | Logistic Team | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512170731-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | CHEONG/SENG/WAH/7018000306
7498B_HU | SK Sangau | DU00006392383 | Sabah | Sabah | 5.389010 | 117.729030 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI |  | 13G_2+0_28M_512QAM_EPLA NE_7498B New 13G_1.8M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 9-43917). New ISM8 x1. New XMC_5D Pro, Sub B_Lo x1. FE_7961A New 13G_1.8M(MDD) x1. Re-use existing RTN910AF(RTN03, NEID 9-45333). New ISM8 x1. New XMC_5D Pro, Sub B_Hi x1. New CAT 6 cable with suitable length x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.8M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY AS EXISTING LINK ALREADY USE SOME CHANNEL UNDER 13G. THEREFORE, CHANCES SLIM FOR OBTAIN 13G CHANNEL. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL. 4.PLEASE APPLY CRQ FOR ALL EB RELATED SITES AS MENTION AT IMPACTED SITE BELOW. DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET**** Existing HW MW Link 7498B-7961A, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7498B-7961A, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7498B, 7088Z, 7763E, 7690E, 7689E, 7764E & 7691E. NE_7498B 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43917) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7498B-7961A, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. FE_7961A 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910AF(RTN03, NEID 9-45333) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7498B-7961A, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. 5.Request new IBeam port from ZTE IPRAN team. 6.Enable port 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-45333). 7.Patching port 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-45333) and new port of IBeam. 8.Perform LAG 2x 1G(Electrical) in between port 8-EM6-1 & 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-45333) and existing and new 1G port of IBeam. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.8M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY AS EXISTING LINK ALREADY USE SOME CHANNEL UNDER 13G. THEREFORE, CHANCES SLIM FOR OBTAIN 13G CHANNEL. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL. 4.PLEASE APPLY CRQ FOR ALL EB RELATED SITES AS MENTION AT IMPACTED SITE BELOW. DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET**** Existing HW MW Link 7498B-7961A, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7498B-7961A, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7498B, 7088Z, 7763E, 7690E, 7689E, 7764E & 7691E. NE_7498B 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43917) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7498B-7961A, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.8M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY AS EXISTING LINK ALREADY USE SOME CHANNEL UNDER 13G. THEREFORE, CHANCES SLIM FOR OBTAIN 13G CHANNEL. 3.DO NOT INSTALL NEW HW MW PARALLEL LINK 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA IF ITEM 1 & 2 NOT FULFILL. 4.PLEASE APPLY CRQ FOR ALL EB RELATED SITES AS MENTION AT IMPACTED SITE BELOW. DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET**** Existing HW MW Link 7498B-7961A, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 7498B-7961A, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7498B, 7088Z, 7763E, 7690E, 7689E, 7764E & 7691E. FE_7961A 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910AF(RTN03, NEID 9-45333) and insert ISM8 into slot 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 7498B-7961A, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7498B-7961A, 13G_2+0_28MHZ_512QAM_EPLA. Become 13G_6+0_28MHZ_512QAM_EPLA. 5.Request new IBeam port from ZTE IPRAN team. 6.Enable port 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-45333). 7.Patching port 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-45333) and new port of IBeam. 8.Perform LAG 2x 1G(Electrical) in between port 8-EM6-1 & 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-45333) and existing and new 1G port of IBeam. | XMC-5D Pro | MDD | 13G | 13G_1.8M(MDD) x1. | 13G_1.8M(MDD) x1. | Seri Pancar | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202512180098-GTSB
7493B_HU_1 | Morisem 2 | DU00006392384 | Sabah | Sabah | 5.417540 | 118.350500 | [7 empty] | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202512180098-GTSB
Q01660_HU | Q133A_Q01660OD_CB_KUALABALINGIAN2 | DU00006392385 | Sarawak | Sarawak | 3.011540 | 112.587570 | [9 empty] | TSS+AA+TI |  | 15G_2+0_28M_256QAM_EPLA NE_9340K/Q01660 New 15G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-24468). New ISM8 x1. New XMC_5D Pro, Sub B_Lo x1. FE_9386B New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN04, NEID 9-24469). New ISM8 x1. New XMC_5D Pro, Sub B_Hi x1. | MW Parallel Link | Existing HW MW Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Build new HW MW Parallel 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Later, combine existing HW MW Link9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA and new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Become 15G_4+0_28MHZ_256QAM_EPLA. Site Impacted : 9340K/Q01660. NE_9340K/Q01660 1.Install new 15G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-24468) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Later, combine existing HW MW Link9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA and new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Become 15G_4+0_28MHZ_256QAM_EPLA. FE_9386B 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN04, NEID 9-24469) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Later, combine existing HW MW Link9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA and new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Become 15G_4+0_28MHZ_256QAM_EPLA. | Existing HW MW Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Build new HW MW Parallel 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Later, combine existing HW MW Link9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA and new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Become 15G_4+0_28MHZ_256QAM_EPLA. Site Impacted : 9340K/Q01660. NE_9340K/Q01660 1.Install new 15G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-24468) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Later, combine existing HW MW Link9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA and new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Become 15G_4+0_28MHZ_256QAM_EPLA. | Existing HW MW Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Build new HW MW Parallel 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Later, combine existing HW MW Link9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA and new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Become 15G_4+0_28MHZ_256QAM_EPLA. Site Impacted : 9340K/Q01660. FE_9386B 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN04, NEID 9-24469) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Later, combine existing HW MW Link9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA and new HW MW Parallel Link 9340K/Q01660-9386B, 15G_2+0_28MHZ_256QAM_EPLA. Become 15G_4+0_28MHZ_256QAM_EPLA. | XMC-5D Pro | MDD | 15G | 15G_0.6M(MDD) x1 | 15G_1.2M(MDD) x1 | Allstar | SQ202603060642-Allstar |  |  |  |  | Ongoing | 2026-03-03 | 2026-03-10 | 2026-03-03 | 2026-03-03 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-03-03 | 2026-03-10 | 2026-03-03 | 2026-03-03 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202512180102-GTSB
7455B_IPR | Rancangan Sg. Manila (Celcom) | DU00006392386 | Sabah | Sabah | 5.945611 | 117.985361 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New CAT6 cable with suitable length(IDU HW to IBeam) x1. | MW IDU Patching | Request 2nd of IBeam port and perform LAG for boths port at IDU & IBeam. Site Impacted: 7235R & 7551B. NE_7455B 1.Enable port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-23128). 2.Request new 2nd of IBeam port from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-23128) and new 2nd IBeam port. 4.Create and configure LAG between 2xport of IDU-IBeam. 5.Traffic 7235R & 7551B will backhaul into LAG of IDU-IBeam | Request 2nd of IBeam port and perform LAG for boths port at IDU & IBeam. Site Impacted: 7235R & 7551B. NE_7455B 1.Enable port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-23128). 2.Request new 2nd of IBeam port from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-23128) and new 2nd IBeam port. 4.Create and configure LAG between 2xport of IDU-IBeam. 5.Traffic 7235R & 7551B will backhaul into LAG of IDU-IBeam | [6 empty] | NR services | SQ202512300323-NR Services | NR services | SQ202512160985-NR Services | 2026-01-02 | 2025-12-30 | Completed | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-26 | 2026-01-02 | 2025-12-26 | 2025-12-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251210A8 |  | 2025-12-11 | 2025-12-11 | Completed | 2025-12-10 | 2025-12-11 | 2025-12-10 | 2025-12-11 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-12 | 2026-01-12 | 2025-12-12 | 2025-12-18 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2025-12-12 | 2026-01-12 | 2025-12-12 | 2025-12-18 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | SITI HAFIZAH BINTI NOH6237001145 |  |  | 2025-12-12 | 2026-01-12 | 2025-12-12 | 2025-12-17 | IBRAHIM//BIN SAHABU/7167000007 | 2025-12-09: 2025-12-12; 2025-12-09: 2026-01-12; 2025-12-09: 2025-12-12; 2025-12-10: 2025-12-12 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202512180098-GTSB
3256A_HU_1 | COUNTRYHOMES1 | DU00006392387 | Central | Selangor | 3.331740 | 101.535210 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M. NE_3256A. 13G_DP_1.2M(MDD) x1. XMC_5D , Sub A_Hi x1. FE_2476A. 13G_DP_1.2M(MDD) x1. XMC_5D , Sub A_Lo x1. | MW Parallel Link | Existing link 15G_2+0_28M with 256QAM. Install parallel link 13G_2+0_28M. Site Impacted : 2746C. NE_3256A. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 3256A_RTN01. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decom existing MW link. FE_2476A. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 2476A_RTN05. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decom existing MW link. | Existing link 15G_2+0_28M with 256QAM. Install parallel link 13G_2+0_28M. Site Impacted : 2746C. NE_3256A. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 3256A_RTN01. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decom existing MW link. | Existing link 15G_2+0_28M with 256QAM. Install parallel link 13G_2+0_28M. Site Impacted : 2746C. FE_2476A. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 2476A_RTN05. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decom existing MW link. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202601220764-GCI | GCI | SQ202601210049-GCI // SQ202601210050-GCI | 2026-02-04 | 2026-02-05 | Completed | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-28 | 2026-01-29 | 2026-01-28 | 2026-01-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121665 |  | 2025-12-17 | 2026-01-14 | Completed | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2026-01-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-17 | 2026-01-24 | 2026-01-17 | 2026-01-21 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-17 | 2026-01-24 | 2026-01-17 | 2026-01-21 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-20 | 2026-01-17 | 2026-01-24 | 2026-01-17 | 2026-01-24 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-12-09: 2026-01-17; 2025-12-09: 2026-01-24; 2025-12-09: 2026-01-17; 2025-12-10: 2026-01-17 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170715-GCI | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | CHEONG/SENG/WAH/7018000306
Q01049_HU | Q135A_Q01049OD_KAMPUSTIMUR | DU00006392388 | Sarawak | Sarawak | 1.460516 | 110.449870 | [9 empty] | TSS+AA+TI |  | 23G_1+0_56M 23G_SP_0.3M(MAC) x1. XMC_3E , Sub A_Lo x1. FE_9964A 23G_SP_0.3M(MAC) x1. XMC_3E , Sub A_Hi x1. | MW Parallel Link | Existing link 23G_1+0_56M with 1024QAM. Install parallel link 23G_1+0_56M with 512QAM. Site Impacted : Q010149. NE_Q01049 1.Install new 23G_SP_0.3M(MAC). 2.Reuse existing Q01049_RTN01 , 7_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW link to decomm. FE_9964A 1.Install new 23G_SP_0.3M(MAC). 2.Reuse existing 9964A_RTN01 , 4_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW link to decomm. | Existing link 23G_1+0_56M with 1024QAM. Install parallel link 23G_1+0_56M with 512QAM. Site Impacted : Q010149. NE_Q010149 1.Install new 23G_SP_0.3M(MAC). 2.Reuse existing Q01049_RTN01 , 7_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW link to decomm. | Existing link 23G_1+0_56M with 1024QAM. Install parallel link 23G_1+0_56M with 512QAM. Site Impacted : Q010149. FE_9964A 1.Install new 23G_SP_0.3M(MAC). 2.Reuse existing 9964A_RTN01 , 4_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to new parallel link. 6.No MW link to decomm. | XMC_3E | MAC | 23G | 0.3 | 0.3 | Magicell | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512170742-GCI | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | CHEONG/SENG/WAH/7018000306
Q00700_HU | Q133A_Q00700OD_CB_BAYAN | DU00006392389 | Sarawak | Sarawak | 2.912041 | 112.323195 | [9 empty] | TSS+AA+TI |  | 2X ISM8 CARD 2X 8G 1.8M HS ANTENNA 1x ODU 8G XMC3 SUB A HI 1x ODU 8G XMC3 SUB A LO 1x ODU 8G XMC3 SUB B HI 1x ODU 8G XMC3 SUB B LO 2x 10G SFP 10KM | MW Parallel Link | MW PARALLEL LINK Q0700-Q00191 WITH HUAWEI_8G_2+0_1.8M/1.8M_DP_28MHZ_458QAM_800MBPS_XMC3_SUB_A & B_LINK_17.20KM EPLA EXISTING LINK 7G 4+0 WITH NEW LINK 8G 2+0 TO BECOME 6+0 IMPACTED: Q0700 10G SFP NEW IDU | 1. INSTALL NEW 1PCS ISM8 CARD SLOT 4 AT EXISTING IDU SW03882 Q00700 2. INSTALL NEW 8G 1.8M DP ANTENNA 3. INSTALL NEW ODU 8G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 8G 2+0 28MHZ 1024QAM 5. EPLA EXISTING LINK 7G 4+0 WITH NEW LINK 8G 2+0 TO BECOME 6+0 | 1. INSTALL NEW 1PCS ISM8 CARD SLOT 4 AT EXISTING IDU SW03882 Q00191 2. INSTALL NEW 8G 1.8M DP ANTENNA 3. INSTALL NEW ODU 8G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 8G 2+0 28MHZ 1024QAM 5. EPLA EXISTING LINK 7G 4+0 WITH NEW LINK 8G 2+0 TO BECOME 6+0 6. PATCH NEW IDU SUING 10G SFP PORT | XMC3 | DP | 8G | 1.8 | 1.8 | Allstar | SQ202604220808-Allstar |  |  |  |  | Ongoing | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512170742-GCI | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00677_LOS | Q118B_Q00677OD_CB_RHGILAN | DU00006392390 | Sarawak | Sarawak | 3.181400 | 113.258800 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M_512QAM. NE_Q00677/9167P New 18G_DP_1.2M(MAC)+OMT x1. New RTN910AF x1. New XMC_3E, Sub A_Hi x1. New CAT6 cable x1. FE_9268R New 18G_DP_1.2M(MAC)+OMT x1. New RTN910AF x1. New XMC_3E, Sub A_Lo x1. New CAT6 cable x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM UPGRADING FOR EXISTING MW LINK AND SACOFA LL: 1ST - PERFORM UPGRADING FOR EXISTING LL SACOFA AT 9119A(9119A-LL_9106A). 2ND - PERFORM UPGRADING FOR EXISTING UPLINK HW MW LINK 9272R-9119A. 3RD - PERFORM UPGRADING FOR EXISTING UPLINK HW MW LINK 9268R-9272R.**** Existing SM MW Link 13G_1+0_28MHZ_512QAM_EPLA. Install new HW MW Link Q00677-9268R, 18G_1+0_112M_512QAM. Later may decom existing SM MW Link 13G_1+0_28MHZ_512QAM_EPLA. Site Impacted : Q00677. NE_Q00677/9167P. 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01) x1. 3.Install new XMC_3E, Sub A_Hi x1. Configure HW MW Link Q00677-9268R, 18G_1+0_112M_512QAM. 4.Request new xD Vlan DCN & Vlan Services. 5.Enable port 8-EM6-1 of new RTN910AF(RTN01). 6.Patching BBU Q00677 at port 8-EM6-1 of new RTN910AF(RTN01). Configure it. 7.Migrate traffic Q00677 to new HW MW Link Q00677-9268R, 18G_1+0_112M_512QAM. 8.Later may decom existing SM MW Link 13G_1+0_28MHZ_512QAM_EPLA. FE_9268R 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02) x1. 3.Install new XMC_3E, Sub A_Lo x1. Configure HW MW Link Q00677-9268R, 18G_1+0_112M_512QAM. 4.Request new xD Vlan DCN & Vlan Services. 5.Enable port 8-EM6-1 of new RTN910AF(RTN02). 6.Enable port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-36482). 7.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN02) to port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-36482). 8.Request new xD vlan services from ZTE IPRAN team. 9.Migrate traffic Q00677 to existing port of IBeam at CP 9119A similar with existing traffics like 9268R, 9272R, 9261R, 9265R, 9262R & 9263R. 10.Later may decom existing SM MW Link 13G_1+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM UPGRADING FOR EXISTING MW LINK AND SACOFA LL: 1ST - PERFORM UPGRADING FOR EXISTING LL SACOFA AT 9119A(9119A-LL_9106A). 2ND - PERFORM UPGRADING FOR EXISTING UPLINK HW MW LINK 9272R-9119A. 3RD - PERFORM UPGRADING FOR EXISTING UPLINK HW MW LINK 9268R-9272R.**** Existing SM MW Link 13G_1+0_28MHZ_512QAM_EPLA. Install new HW MW Link Q00677-9268R, 18G_1+0_112M_512QAM. Later may decom existing SM MW Link 13G_1+0_28MHZ_512QAM_EPLA. Site Impacted : Q00677. NE_Q00677/9167P. 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01) x1. 3.Install new XMC_3E, Sub A_Hi x1. Configure HW MW Link Q00677-9268R, 18G_1+0_112M_512QAM. 4.Request new xD Vlan DCN & Vlan Services. 5.Enable port 8-EM6-1 of new RTN910AF(RTN01). 6.Patching BBU Q00677 at port 8-EM6-1 of new RTN910AF(RTN01). Configure it. 7.Migrate traffic Q00677 to new HW MW Link Q00677-9268R, 18G_1+0_112M_512QAM. 8.Later may decom existing SM MW Link 13G_1+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM UPGRADING FOR EXISTING MW LINK AND SACOFA LL: 1ST - PERFORM UPGRADING FOR EXISTING LL SACOFA AT 9119A(9119A-LL_9106A). 2ND - PERFORM UPGRADING FOR EXISTING UPLINK HW MW LINK 9272R-9119A. 3RD - PERFORM UPGRADING FOR EXISTING UPLINK HW MW LINK 9268R-9272R.**** Existing SM MW Link 13G_1+0_28MHZ_512QAM_EPLA. Install new HW MW Link Q00677-9268R, 18G_1+0_112M_512QAM. Later may decom existing SM MW Link 13G_1+0_28MHZ_512QAM_EPLA. Site Impacted : Q00677. FE_9268R 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02) x1. 3.Install new XMC_3E, Sub A_Lo x1. Configure HW MW Link Q00677-9268R, 18G_1+0_112M_512QAM. 4.Request new xD Vlan DCN & Vlan Services. 5.Enable port 8-EM6-1 of new RTN910AF(RTN02). 6.Enable port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-36482). 7.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN02) to port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-36482). 8.Request new xD vlan services from ZTE IPRAN team. 9.Migrate traffic Q00677 to existing port of IBeam at CP 9119A similar with existing traffics like 9268R, 9272R, 9261R, 9265R, 9262R & 9263R. 10.Later may decom existing SM MW Link 13G_1+0_28MHZ_512QAM_EPLA. | XMC-3E | MAC | 18G | 18G_DP_1.2M(MAC)+OMT x1 | 18G_DP_1.2M(MAC)+OMT x1 | Trintel | SQ202602090179-Trintel | Trintel | SQ202604200384-Trintel // SQ202604200391-Trintel // SQ202604280673-Trintel |  |  | Ongoing | 2026-01-21 | 2026-01-31 | 2026-01-21 | 2026-01-23 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-11 | 2026-02-18 | 2026-02-11 | 2026-02-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-30 | 2026-05-07 | 2026-04-30 | 2026-05-01 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26040856 |  | 2026-04-09 | 2026-04-13 | Completed | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-22 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2026-04-13 | 2026-04-13 | 2026-04-13 |  | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-24 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2025-12-09: 2026-04-13; 2025-12-09: 2026-04-13; 2025-12-09: 2026-04-13; 2025-12-10: 2026-04-22 | [7 empty] | GTSB | SQ202512180102-GTSB
1491C_HU | Taman Intan Jaya | DU00006392391 | Central | Selangor | 3.142400 | 101.377000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M_256QAM_EPLA(Without CA) NE_1491C New 15G_0.6M(MDD)+Flange Adapter/Dual Coupler x1. Re-use existing RTN910AF(RTN01, NEID 9-35864). New ISM8 x2. New XMC_5D Pro, Sub A&B_Hi x2. New IF cable with suitable length and type x4 RUN. FE_1612B New 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. New RTN910AF(RTN02). New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cable with suitable length and type x4 RUN.(x2 IF cable RUN for existing channel in which require shifting existing IF cables from existing RTN910AF(RTN06, NEID 9-48819) slot 07 Port 1 & 2 to new RTN910AF(RTN02) slot 07 Port 1 & 2. Another x2 IF cable RUN for new 4 channels for slot 03 & 04. New CAT6 cable with suitable length x1. | MW Parallel Link | Existing HW MW Link 1491C-1612B, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). Later, combine existing HW MW Link 1491C-1612B, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA. Become 15G_6+0_28MHZ_512QAM&256QAM_EPLA. Site Impacted : 1491C. NE_1491C 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-35864) and insert 2x new ISM8 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). 4.Request new xD Vlan DCN & Vlan Services. 5.Later, combine existing HW MW Link 1491C-1612B, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA. Become 15G_6+0_28MHZ_512QAM&256QAM_EPLA. FE_1612B 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF and insert 2x new ISM8 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). 4.Disconnect existing IF cable connected from existing RTN910AF(RTN06, NEID 9-48819) slot 07 Port 1 & 2. And lay new x2 IF cable from existing ODU to new RTN910AF(RTN02) slot 07 Port 1 & 2. 5.Enable port 8-EM6-1 of new RTN910AF(RTN02) and perform patching yo new IBeam port(request from ZTE IPRAN Team) 6.Enable port Gi0/0/7 of existing PTN ID 30131 and new suitable Optical SFP Module. 7.Request new xD Vlan DCN & Vlan Services. 8.Later, combine existing HW MW Link 1491C-1612B, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA. Become 15G_6+0_28MHZ_512QAM&256QAM_EPLA. | Existing HW MW Link 1491C-1612B, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). Later, combine existing HW MW Link 1491C-1612B, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA. Become 15G_6+0_28MHZ_512QAM&256QAM_EPLA. Site Impacted : 1491C. NE_1491C 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-35864) and insert 2x new ISM8 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). 4.Request new xD Vlan DCN & Vlan Services. 5.Later, combine existing HW MW Link 1491C-1612B, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA. Become 15G_6+0_28MHZ_512QAM&256QAM_EPLA. | Existing HW MW Link 1491C-1612B, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). Later, combine existing HW MW Link 1491C-1612B, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA. Become 15G_6+0_28MHZ_512QAM&256QAM_EPLA. Site Impacted : 1491C. FE_1612B 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF and insert 2x new ISM8 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). 4.Disconnect existing IF cable connected from existing RTN910AF(RTN06, NEID 9-48819) slot 07 Port 1 & 2. And lay new x2 IF cable from existing ODU to new RTN910AF(RTN02) slot 07 Port 1 & 2. 5.Enable port 8-EM6-1 of new RTN910AF(RTN02) and perform patching yo new IBeam port(request from ZTE IPRAN Team) 6.Enable port Gi0/0/7 of existing PTN ID 30131 and new suitable Optical SFP Module. 7.Request new xD Vlan DCN & Vlan Services. 8.Later, combine existing HW MW Link 1491C-1612B, 15G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 1491C-1612B, 15G_4+0_28MHZ_256QAM_EPLA. Become 15G_6+0_28MHZ_512QAM&256QAM_EPLA. | XMC-5D Pro | MDD | 15G | 15G_0.6M(MDD)+Flange Adapter/Dual Coupler x1 | 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. | GTSB | SQ202601190053-GTSB | GTSB | SQ202601160487-GTSB // SQ202601160493-GTSB |  |  | Ongoing | 2026-01-27 | 2026-01-31 | 2026-01-27 | 2026-02-10 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-17 | 2026-03-31 | 2026-03-17 | 2026-03-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-05 | 2026-05-12 | 2026-05-05 | 2026-05-05 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26011709 |  | 2026-01-18 | 2026-01-22 | Completed | 2026-01-17 | 2026-01-18 | 2026-01-17 | 2026-01-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-01-31 | 2026-01-27 | 2026-02-10 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-01-27 | 2026-01-31 | 2026-01-27 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-02-03 | 2026-01-27 | 2026-01-31 | 2026-01-27 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2025-12-09: 2026-01-27; 2025-12-09: 2026-01-31; 2025-12-09: 2026-01-27; 2025-12-10: 2026-03-09 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512180092-GTSB
B02709_HU | B065A_B02709OD_JLN4TMNTUNTEJA | DU00006392392 | Central | Selangor | 3.305556 | 101.594900 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X 10G 1KM SFP 1X ISM8 CARD 1X RTN910A 2X 23G 0.3M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1x ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1x ODU 23G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE B02709-2482A WITH HUAWEI_23G_2+0_0.3M/0.3M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_0.75KM IMPACTED: B02709 DISMANTLE EXISTING LINK B02709-B00460 | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK B02709-B00460 | 1. INSTALL NEW ISM8 CARD 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. INSTALL NEW 10G SFP TO 2482A RTN01 6. DISMANTLE EXISTING LINK B02709-B00460 | XMC3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202512190067-GCI | GCI | SQ202512160886-GCI // SQ202512160934-GCI | 2026-01-14 | 2026-01-13 | Completed | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25120494 |  | 2026-01-05 | 2025-12-06 | Completed | 2025-12-05 | 2026-01-05 | 2025-12-04 | 2025-12-06 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-15 | 2025-12-16 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-16 | 2025-12-23 | 2025-12-15 | 2025-12-20 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-17 | 2025-12-16 | 2025-12-23 | 2025-12-15 | 2025-12-23 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-12-16 | 2025-12-23 | 2025-12-15 | 2025-12-16 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170715-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
2070B_1 | Sri Gombak (TX) | DU00004219316 | Central | Kuala Lumpur | 3.244528 | 101.710361 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 25/9: Cutover done | TSS+TI | L1+ATP+PAC | 4 x SFP1G 2 pair patch cord | IDU-IPRAN | 2070B RTN09 GE1 port congested. To patch new GE port to new CP port and create LAG 2070B MAC001 electrical port full. To use optical port. Impacted sites: 3911B,1306K,1326K,1418K,2441A NE (2070B): 1) Patch 2 GE optical port from RTN09 (GE5 and GE6) to new CP port (ops team to assign CP port) 2) Create LAG 3) Migrate all traffic to new CP port and create DCN | [7 empty] | Datasco | SQ202410080235-Datasco | Datasco | SQ202410080232-Datasco | 2025-05-21 | 2025-05-20 | Completed | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24092008 |  | 2024-09-21 | 2024-11-18 | Completed | 2024-09-20 | 2024-09-21 | 2024-09-20 | 2024-11-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-24 | 2024-09-30 | 2024-09-24 | 2024-11-18 | NORSHAMSUDIN//BIN DAUD/7019000007 | Datasco TI | 2024-09-24 | 2024-09-30 | 2024-09-24 | 2024-11-18 | NORSHAMSUDIN//BIN DAUD/7019000007 | Datasco TI | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-09-25 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-09-24 | 2024-09-30 | 2024-09-24 | 2024-09-25 | NORSHAMSUDIN//BIN DAUD/7019000007 | 2025-12-09: 2024-09-24; 2025-12-09: 2024-09-30; 2025-12-09: 2024-09-24; 2025-12-10: 2024-11-18 |  |  | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | CHEONG/SENG/WAH/7018000306
S01942_AD | SEBABPAUL | DU00005783795 | Sabah | Sabah | 5.043880 | 118.840280 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | SFP and Patch cord | MW Re-engineering | Patching IDU to IDU to change route | [7 empty] | NR services | SQ202510070049-NR Services | NR services | SQ202509090323-NR Services | 2025-11-17 | 2025-11-10 | Completed | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-03 | 2025-11-10 | 2025-11-03 | 2025-11-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090202 |  | 2025-09-03 | 2025-09-03 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-03 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-02 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-02 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-06 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-06 | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-02 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-12-09: 2025-10-01; 2025-12-09: 2025-11-01; 2025-12-09: 2025-10-01; 2025-12-10: 2025-10-02 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507080638-GTSB | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | AB.RAHMAN//BIN MAT NOOH/6237001519
3951B10_EVT | PBTS BORNEO ARTS FESTIVAL LABUAN 2025 (E) | DU00006300643 | Sabah | Labuan | 5.275990 | 115.257600 | [13 empty] | Planning and integration support only for event site 3951B10 PBTS BORNEO ARTS FESTIVAL LABUAN 2025 (E) Tx route: 3951B10/3951B10-7084A 1) New port at 7084A-MAC-001 IOFC 2) New NE ID FE IDU 7084A RTN09 3) New NE ID NE IDU 3951B10 RTN01 2) New DCN IP 7084A RTN09 3) New DCN VLAN 7084A RTN09 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
4627C-4083B | Masjid Batu Kg Pertama | DU00006001349 | Northern | Penang | 5.390040 | 100.417535 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M. NE_4627C 18G_SP_0.6m(MAC)+OMT. XMC_3E-1+0 , Sub_A_Lo x1. RTN910 x1 FE_4083B 18G_SP_0.6m(MAC)+OMT x1. XMC_3E-1+0 , Sub_A_Hi x1. ISM8 x1. | MW Parallel Link | Install Parallel link with config 18G_1+0_112M. Site Impacted: 4627C. NE_4627C 1.Install new 18G_SP_0.6m(MAC)+OMT. 2.Install new XMC_3E-1+0 , Sub_A_Lo. 3.Install new RTN910, 7_ISM8-2+0 with transfer existing IF cable to new 7_ISM8. 4.Create service cross connect and EPLA. 5.Migrate traffic to new parallel link. 6.Decom old version existing IDU only. FE_4083B 1.Install new 18G_SP_0.6m(MAC)+OMT. 2.Install new XMC_3E-1+0 , Sub_A_Hi. 3.Install 4_ISM8-1+0 into existing 4083B_RTN01. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No link to be decom. | Install Parallel link with config 18G_1+0_112M. Site Impacted: 4627C. NE_4627C 1.Install new 18G_SP_0.6m(MAC)+OMT. 2.Install new XMC_3E-1+0 , Sub_A_Lo. 3.Install new RTN910, 7_ISM8-2+0 with transfer existing IF cable to new 7_ISM8. 4.Create service cross connect and EPLA. 5.Migrate traffic to new parallel link. 6.Decom old version existing IDU only. | Install Parallel link with config 18G_1+0_112M. Site Impacted: 4627C. FE_4083B 1.Install new 18G_SP_0.6m(MAC)+OMT. 2.Install new XMC_3E-1+0 , Sub_A_Hi. 3.Install 4_ISM8-1+0 into existing 4083B_RTN01. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No link to be decom. | XMC_3E | MAC | 18G | 0.6 | 0.6 | GTSB | SQ202508270907-GTSB | GTSB | SQ202508270962-GTSB // SQ202508270967-GTSB // SQ202509110849-GTSB // SQ202510090320-GTSB // SQ202510090370-GTSB | 2026-01-23 | 2026-01-23 | Completed | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO |  |  | Disabled | 2025-08-27 | 2025-08-28 | 2025-08-27 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Disabled |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-12-13 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-09-10 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-28 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-09-08 | HAMZAH BIN ABDUL MUTALIF6799000301 | 2025-12-09: 2025-08-27; 2025-12-09: 2025-08-27; 2025-12-09: 2025-08-27; 2025-12-10: 2025-09-08 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509041075-GCI | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | CHEONG/SENG/WAH/7018000306
B00276-B00646 | V LAND PASIR PANJANG | DU00005020836 | Central | Selangor | 3.577170 | 101.075330 | WK06 | FEB 25 | WK06 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 8/2/2025 : Cutover done 7/2/2025 : EDOTCO (M) SDN BHD - TOWER 61M LAND - NE site B00276 V LAND PASIR PANJANG, EDOTCO (M) SDN BHD - TOWER 106M LAND - FE site B00646 B062B_B00646OD_SGNIBONGHOT | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_B00276 18G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Hi x1. FE_B00646 18G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub_B_Lo x1. | MW Swap | Link Existing SM 13G_2+0_28M Swap existing to 18G_2+0_112M Site Impacted : B00276. NE_B00276 1.Install 18G_DP_1.2M(MDD). 2.Install RTN910A , 7_ISM8-2+0 3.Install XMC_5D , Sub B_Hi. 4.Create cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing SM link(CT10553).Ensure no traffic before decom. FE_B00646 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub_B_Lo. 4.Create service cross connect and EPLA. 5.Create new In band DCN. 6.Tarffic migrate to new link. 7.Decom existing SM link ( CT10553).Ensure no traffic before decom. | Link Existing SM 13G_2+0_28M Swap existing to 18G_2+0_112M Site Impacted : B00276. NE_B00276 1.Install 18G_DP_1.2M(MDD). 2.Install RTN910A , 7_ISM8-2+0 3.Install XMC_5D , Sub B_Hi. 4.Create cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing SM link(CT10553).Ensure no traffic before decom. | Link Existing SM 13G_2+0_28M Swap existing to 18G_2+0_112M Site Impacted : B00276. FE_B00646 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub_B_Lo. 4.Create service cross connect and EPLA. 5.Create new In band DCN. 6.Tarffic migrate to new link. 7.Decom existing SM link ( CT10553).Ensure no traffic before decom. | XMC_5D | MDD | 19260.000 19590.000 | 1.2 | 1.2 | GCI | SQ202502180244-GCI | GCI | SQ202502120274-GCI // SQ202504150088-GCI | 2025-03-10 | 2025-03-11 | Completed | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020836 |  | 2025-02-10 | 2025-02-10 | Completed | 2025-02-08 | 2025-02-10 | 2025-02-08 | 2025-02-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-08 | 2025-02-15 | 2025-02-07 | 2025-02-10 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-08 | 2025-02-15 | 2025-02-07 | 2025-02-12 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-08 | 2025-02-08 | 2025-02-15 | 2025-02-07 | 2025-02-10 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-02-08 | 2025-02-15 | 2025-02-07 | 2025-02-10 | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-02-14 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
3657B-2631A | Jalan Dato Dagang | DU00005039608 | Central | Selangor | 3.000299 | 101.463309 |  |  |  |  | RFS | Remote Upgrade done | ZTE | 00. Integrated/RFS Done | 24/2/2025 : Cutover done | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE 3657B-2631A WITH HUAWEI_18G_1+0_112MHZ_0.6M/0.6M_DP_112MHZ_512QAM_XMC3E_SUB B_3.09KM IMPACTED: 3657B |  |  | XMC3E | DP | 18G | 0.6M | 0.6M |  |  | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-24 | [15 empty] | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
1352B-1372B | PUAS Saujana Puchong(KJS) | DU00005039609 | Central | Selangor | 2.995470 | 101.637888 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 27/2/2025 : Cutover done 26/2/2025 : Installation complete, alignment WIP 25/2/2025 : NE installation complete, pending install FE site 24/2/2025 : Plan install NE and FE site - CRQ approved, cancel proceed due to keys issue 10/2/2025 : SBC KJS - 60M 4 Legged Tower - NE site 1352B PUAS Saujana Puchong(KJS), SBC KJS - 60M 4 Legged Tower - FE site 1372B PUAS Tmn Meranti Jaya(KJS) | TSS+AA+TI | L1+ATP+PAC | 1X 18G 0.6M DP ANTENNA 1X 18G 1.2M DP ANTENNA 1x ODU 18G XMC3E HI 1X ODU 18G XMC3E LO | MW Parallel Link | MW PARALLEL LINK RTN01 1352B-1372B WITH HUAWEI_18G_1+0_112MHZ_1.2M/0.6M_DP_112MHZ_512QAM_XMC3E_SUB A_3.87KM_EPLA WITH EXISTING LINK IMPACTED: 1352B, 3657C, 1193H, 1148D NE 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM AT SLOT 7-2 AND EPLA WITH EXISTING LINK FE 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM AT SLOT 7-2 AND EPLA WITH EXISTING LINK 5. PATCH TO NEW CP AND DO PORT LAG | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM AT SLOT 7-2 AND EPLA WITH EXISTING LINK | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3E SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM AT SLOT 7-2 AND EPLA WITH EXISTING LINK 5. PATCH TO NEW CP AND DO PORT LAG | XMC3E | DP | 18G | 1.2M | 0.6M | MTK | SQ202503060132-MTK | MTK | SQ202503050465-MTK // SQ202504260152-MTK | 2025-04-12 | 2025-04-11 | Completed | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-25 | 2025-03-26 | 2025-03-25 | 2025-03-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-26 | 2025-03-27 | 2025-03-26 | 2025-03-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-11 | 2025-04-12 | 2025-04-11 | 2025-04-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022023 |  | 2025-02-21 | 2025-02-21 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2025-03-10 | 2025-02-27 | 2025-02-27 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-02-25 | 2025-03-10 | 2025-02-27 | 2025-03-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-27 | 2025-02-25 | 2025-03-10 | 2025-03-17 | 2025-03-17 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-12-09: 2025-02-25; 2025-12-09: 2025-03-10; 2025-12-09: 2025-03-10; 2025-12-10: 2025-03-10 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
4424A-4466A | Ulu Sepetang | DU00005043103 | Northern | Perak | 4.955448 | 100.723144 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M NE_4424A 18G_DP_1.2M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. FE_4466A 18G_DP_1.2M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Hi x2. | MW Parallel Link | Existing link 18G_1+0_56M Install parallel link 18G_2+0_112M and perform remote software upgrade existing link from 56M to 112M. Site Impacted : 4466A , 4424A , 4565D. NE_4424A 1.Install new 18G_DP_1.2M(MAC)+OMT 2.Install new 3_ISM8-2+0 into existing 4424A_RTN01. 3.Reuse existing 4424A_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.No decom existing MW link. FE_4466A 1.Install new 18G_DP_1.2M(MAC)+OMT. 2.Install new 3_ISM8-2+0 into existing 4466A_RTN02. 3.Reuse existing 4466A_RTN02. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.No decom existing MW link. | Existing link 18G_1+0_56M Install parallel link 18G_2+0_112M and perform remote software upgrade existing link from 56M to 112M. Site Impacted : 4466A , 4424A , 4565D. NE_4424A 1.Install new 18G_DP_1.2M(MAC)+OMT 2.Install new 3_ISM8-2+0 into existing 4424A_RTN01. 3.Reuse existing 4424A_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.No decom existing MW link. | Existing link 18G_1+0_56M Install parallel link 18G_2+0_112M and perform remote software upgrade existing link from 56M to 112M. Site Impacted : 4466A , 4424A , 4565D. FE_4466A 1.Install new 18G_DP_1.2M(MAC)+OMT. 2.Install new 3_ISM8-2+0 into existing 4466A_RTN02. 3.Reuse existing 4466A_RTN02. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.No decom existing MW link. | XMC_3E | MAC | 17920.000 18580.000 | 1.2 | 1.2 | Magicell | SQ202503270808-Magicell | Magicell | SQ202503200275-Magicell // SQ202503200278-Magicell // SQ202504260184-Magicell // SQ202507290130-Magicell | 2025-11-26 | 2025-11-26 | Completed | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-20 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022666 |  | 2025-02-27 | 2025-03-19 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-03-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-09 | 2026-03-04 | 2025-03-09 | 2025-03-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | 2025-03-09 | 2026-03-04 | 2025-03-09 | 2025-03-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-03-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-12 | 2025-03-09 | 2026-03-04 | 2025-03-09 | 2025-03-20 | UMI NOR PADZILAH BINTI PAUZI7018000120 | 2025-12-09: 2025-03-09; 2025-12-09: 2026-03-04; 2025-12-09: 2025-03-09; 2025-12-10: 2025-03-20 |  |  | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | CHEONG/SENG/WAH/7018000306
4820C-4395B | Tmn Kledang Jaya | DU00005043104 | Northern | Perak | 4.679620 | 101.121660 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_4820C 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. FE_4359B 23G_DP_0.6m(MAC)+OMT x1. RTN910A , 7_ISM8-2+0 x1. XMC_3E , Sub A & B_Hi x2. | MW Swap | Existing SM link 23G_1+0_112M Swap existing link to 23G_2+0_112M Site Impacted : 4820C , 4527D and 4374H. NE_4820C 1.Install 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Migrate traffic to new MW link. 6.Decom existing SM link. FE_4359B 1.Install 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create new In Band DCN. 5.Migrate all traffic to new MW link. 6.Decom existing SM link. | Existing SM link 23G_1+0_112M Swap existing link to 23G_2+0_112M Site Impacted : 4820C , 4527D and 4374H. NE_4820C 1.Install 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Migrate traffic to new MW link. 6.Decom existing SM link. | Existing SM link 23G_1+0_112M Swap existing link to 23G_2+0_112M Site Impacted : 4820C , 4527D and 4374H. FE_4359B 1.Install 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create new In Band DCN. 5.Migrate all traffic to new MW link. 6.Decom existing SM link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202504280482-Magicell | Magicell | SQ202506130259-Magicell // SQ202506130266-Magicell // SQ202507290130-Magicell | 2025-11-26 | 2025-11-26 | Completed | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25060376 |  | 2025-06-04 | 2025-06-05 | Completed | 2025-06-03 | 2025-06-04 | 2025-06-03 | 2025-06-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-12 | 2026-06-25 | 2025-06-12 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-06-12 | 2026-06-25 | 2025-06-12 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-13 | 2025-06-12 | 2026-06-25 | 2025-06-12 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-06-12 | 2026-06-25 | 2025-06-12 | 2025-06-17 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | CHEONG/SENG/WAH/7018000306
4622B_LOS | Sik Town | DU00005043105 | Northern | Kedah | 5.820505 | 100.742662 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_4622B 18G_DP_0.6M(MDD) x1. RTN910A , 7_ISM8-2+0 x1. XMC_5D , Sub A_Lo x1. FE_K00420. 18G_DP_0.6M(MDD) x1. RTN 910A , 7_ISM8-2+0 x1. XMC_5D , Sub A_Hi x1. ETH Cable x1. | MW New Link / Reroute | Link reroute to new FE K00420 due to LOS Block Site Impacted : 4622B NE_4622B 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link and new route FE site. 6.Decom existing MW link (4622B - 4623B). FE_K00420. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN 910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Create new In Band DCN. 6.Traffic migrate to new MW link and new route FE site. 7.Enable GE1 , ETH patching to PTN Fiber port. 8.Decom existing MW link (4623B-4622B). | Link reroute to new FE K00420 due to LOS Block Site Impacted : 4622B NE_4622B 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link and new route FE site. 6.Decom existing MW link (4622B - 4623B). | Link reroute to new FE K00420 due to LOS Block Site Impacted : 4622B FE_K00420. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN 910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Create new In Band DCN. 6.Traffic migrate to new MW link and new route FE site. 7.Enable GE1 , ETH patching to PTN Fiber port. 8.Decom existing MW link (4623B-4622B). | XMC_5D | MDD | 18G | 0.6M | 0.6M | GCI | SQ202504280464-GCI | GCI | SQ202505050094-GCI // SQ202505050127-GCI // SQ202506240302-GCI // SQ202508140739-GCI | 2026-01-23 | 2026-01-23 | Completed | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032070 |  | 2025-03-21 | 2025-04-12 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-04-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2025-05-29 | team7gcitechnicalteam7gcitechnical | GCI TI | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2025-06-07 | team7gcitechnicalteam7gcitechnical | GCI TI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-27 | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2026-03-30 | team7gcitechnicalteam7gcitechnical | 2025-12-09: 2025-03-24; 2025-12-09: 2025-03-31; 2025-12-09: 2025-03-24; 2025-12-10: 2025-03-24 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | CHEONG/SENG/WAH/7018000306
4586B-4475B | Lorong 3A Sg Manik | DU00005043106 | Northern | Perak | 4.066273 | 101.057474 |  |  |  |  | Integrated/RFS Done |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE_4586B 18G_DB_1.2M (MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. FE_4475B 18G_DB_1.2m(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. | MW Swap | Existing SM link 18G_1+0_56M Swap existing link to 18G_2+0_112M Site Impacted : 4586B NE_4586B 1.Install new 18G_DB_1.2M (MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link. 6.Decom existing SM link. FE_4475B 1.Install new 18G_DB_1.2m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.Traffic migrate to new link. 7.Decom existing SM link. | Existing SM link 18G_1+0_56M Swap existing link to 18G_2+0_112M Site Impacted : 4586B NE_4586B 1.Install new 18G_DB_1.2M (MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link. 6.Decom existing SM link. | Existing SM link 18G_1+0_56M Swap existing link to 18G_2+0_112M Site Impacted : 4586B FE_4475B 1.Install new 18G_DB_1.2m(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.Traffic migrate to new link. 7.Decom existing SM link. | XMC_3E | MAC | 17920.000 18580.000 | 1.2 | 1.2 | GTSB | SQ202504170477-GTSB | GTSB | SQ202503240709-GTSB // SQ202503240710-GTSB // SQ202504260178-GTSB | 2025-11-26 | 2025-11-26 | Completed | 2025-03-20 | 2025-03-21 | 2025-04-10 | 2025-04-10 | BARANEEDARAN//A/L SELVADASS SEBASTIN/6799000111 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-08-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022161 |  | 2025-02-22 | 2025-03-15 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-03-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-20 | 2025-03-31 | 2025-03-20 | 2025-10-09 | ALI RAZA AKBAR ALI6799000298 | GTSB TI | 2025-03-20 | 2025-03-31 | 2025-03-20 | 2025-06-13 | ALI RAZA AKBAR ALI6799000298 | GTSB TI | 2025-03-23 | 2025-03-23 | 2025-03-23 | 2025-03-23 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-23 | 2025-03-20 | 2025-03-31 | 2025-03-20 | 2025-04-14 | ALI RAZA AKBAR ALI6799000298 | 2025-03-20 | 2025-03-31 | 2025-03-20 | 2025-03-21 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | CHEONG/SENG/WAH/7018000306
9791C_LOS | Long Urun Tx Repeater | DU00005049167 | Sarawak | Sarawak | 3.038963 | 114.136863 | [7 empty] | 00. Site Out/Drop |  | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | 2 sites 9574B and 9575B are having intermittent connectivity due to LL issue To explore 9791C feasibility as Tx repeater by checking possible LOS from 9791C to FE options below: option 1 9791C-9347B option 2 9791C-Q01423 option 3 9791C-Q01424 option 4 9791C-Q01808 Also to verify LOS: 9791C-9574B 9791C-9575B | [7 empty] | MTK | No PR required-Site drop/cancel |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300154-GTSB
4482A_HU | University MARA (AsiaSpace) RCC | DU00005584028 | Northern | Perak | 4.361101 | 100.967508 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G 3+0 28MHz 1.2m/1.8m DP MDD XMC-5D Sub A/B NCA 672Mbps 9.47KM 2X RTN 910A 2X 13G 1.8m DP MDD ANTENNA 2X ISM8 CARD 1X 13G XMC-5D SUB A HI 1X 13G XMC-5D SUB B HI 1X 13G XMC-5D SUB A LO 1X 13G XMC-5D SUB B LO | MW Swap | MW Swap Link 4482A-4733A With HUAWEI_13G_3+0_28MHz_1.2M/1.8M_SUB A/B_9.47Km to Carry 4711D & 4186R IMPACTED SITES: 4711D, 4186R NE 4482A 1. Install New RTN910A 2. Install New 13G 1.8m DP MDD Antenna 3. Install New 3+0 13G XMC-5D Sub B & A 4. Configure Link 13G 3+0 28Mhz 5. Create Service & Patch Traffic 4711D from Eth Port 4482A-RTN04 6. Dismantle Existing Link 4482A RTN01-4733A RTN04 7. Dismantle Existing Link 4482A RTN02-4733A RTN08 (No Traffic) FE 4733A 1. Install New RTN910A 2. Install New 13G 1.8m DP MDD Antenna 3. Install New 3+0 13G XMC-5D Sub B & A 4. Configure Link 13G 3+0 28Mhz 5. Create Service & Patch to HW iBEAM 6. Transfer/Install Existing Link 18G 1+0 56MHz Sub A 4186R from Old 4733A-RTN04 Slot 03 and Slot to New RTN Slot 04 7. Dismantle Existing Link 4482A RTN01-4733A RTN04 8. Dismantle Existing Link 4482A RTN02-4733A RTN08 (No Traffic) | MW Swap Link 4482A-4733A With HUAWEI_13G_3+0_28MHz_1.2M/1.8M_SUB A/B_9.47Km to Carry 4711D & 4186R IMPACTED SITES: 4711D, 4186R NE 4482A 1. Install New RTN910A 2. Install New 13G 1.8m DP MDD Antenna 3. Install New 3+0 13G XMC-5D Sub B & A 4. Configure Link 13G 3+0 28Mhz 5. Create Service & Patch Traffic 4711D from Eth Port 4482A-RTN04 6. Dismantle Existing Link 4482A RTN01-4733A RTN04 7. Dismantle Existing Link 4482A RTN02-4733A RTN08 (No Traffic) | MW Swap Link 4482A-4733A With HUAWEI_13G_3+0_28MHz_1.2M/1.8M_SUB A/B_9.47Km to Carry 4711D & 4186R IMPACTED SITES: 4711D, 4186R FE 4733A 1. Install New RTN910A 2. Install New 13G 1.8m DP MDD Antenna 3. Install New 3+0 13G XMC-5D Sub B & A 4. Configure Link 13G 3+0 28Mhz 5. Create Service & Patch to HW iBEAM 6. Transfer/Install Existing Link 18G 1+0 56MHz Sub A 4186R from Old 4733A-RTN04 Slot 03 and Slot to New RTN Slot 04 7. Dismantle Existing Link 4482A RTN01-4733A RTN04 8. Dismantle Existing Link 4482A RTN02-4733A RTN08 (No Traffic) | XMC-5D | DP MDD | 13G | 1.8m | 1.8m | Magicell | SQ202507030709-Magicell | Magicell | SQ202507080917-Magicell // SQ202507080924-Magicell // SQ202509100078-Magicell | 2026-02-23 | 2026-02-23 | Completed | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061179 |  | 2025-06-19 | 2025-06-25 | Completed | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-27 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-20 | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506050639-GCI | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
1308B_HU | Bukit Rahman Putra Sg Buloh | DU00005584029 | Central | Selangor | 3.224453 | 101.564306 | [7 empty] | 00. Integrated/RFS Done | 25/6: CO done. | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_0.6m/0.6m_SP_1+0_112Mhz_512Q_889Mbps | MW Swap | SWAP MW LINK 1308B-1406B WITH HUAWEI_23G_1+0_112MHZ_0.6M_1.17KM EXISTING MW CFG: HW_23GHZ_1+0_56MHZ IMPACTED SITES: 1308B NE 1308B BUKIT RAHMAN PUTRA SG BULOH 1. Install New RTN910A 2. Install New 23G 0.6m SP MAC Antenna 3. Install New 1+0 23G XMC-3 Sub B 4. Configure Link 23G 1+0 112Mhz 5. Create Service & Repatch BBU 1308B 6. Dismantle Existing Link xD 1308B-1406B FE 1406B NS HWY KM 454.3 1. Install New RTN910A 2. Install New 23G 0.6m DP Antenna 3. Install New 1+0 18G XMC-3 Sub B 4. Configure Link 23G 1+0 112Mhz 5. Create Service & Repatch to HW iBEAM 6. Dismantle Existing Link xD 1308B-1406B | SWAP MW LINK 1308B-1406B WITH HUAWEI_23G_1+0_112MHZ_0.6M_1.17KM EXISTING MW CFG: HW_23GHZ_1+0_56MHZ IMPACTED SITES: 1308B NE 1308B BUKIT RAHMAN PUTRA SG BULOH 1. Install New RTN910A 2. Install New 23G 0.6m SP MAC Antenna 3. Install New 1+0 23G XMC-3 Sub B 4. Configure Link 23G 1+0 112Mhz 5. Create Service & Repatch BBU 1308B 6. Dismantle Existing Link xD 1308B-1406B | SWAP MW LINK 1308B-1406B WITH HUAWEI_23G_1+0_112MHZ_0.6M_1.17KM EXISTING MW CFG: HW_23GHZ_1+0_56MHZ IMPACTED SITES: 1308B FE 1406B NS HWY KM 454.3 1. Install New RTN910A 2. Install New 23G 0.6m DP Antenna 3. Install New 1+0 18G XMC-3 Sub B 4. Configure Link 23G 1+0 112Mhz 5. Create Service & Repatch to HW iBEAM 6. Dismantle Existing Link xD 1308B-1406B | XMC3 | MAC SP | 23G | 0.6m | 0.6m | GCI | SQ202506100555-GCI | GCI | SQ202506100578-GCI // SQ202506100586-GCI | 2025-07-08 | 2025-07-08 | Completed | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-03 | 2025-07-02 | 2025-07-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-07 | 2025-07-08 | 2025-07-07 | 2025-07-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061037 |  | 2025-06-11 | 2025-06-12 | Completed | 2025-06-10 | 2025-06-11 | 2025-06-10 | 2025-06-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-06-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-06-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | SITI HAFIZAH BINTI NOH6237001145 |  |  | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-01 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-06-25 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050638-GCI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
4197C_HU | Kg Batu 6 Ulu Selama Perak | DU00005584030 | Northern | Perak | 5.293581 | 100.739235 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X ISM8 CARD | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 4197C-4952B WITH HUAWEI_13G_2+0_1.8M/1.8M_MDD DP_28MHZ_512QAM_896MBPS_XMC5D_SUB_A_9.3KM_WITH CA IMPACTED: 4197C,4151R,4132R | 1. INSTALL NEW 1PCS ISM8 AT SLOT 4 EXISTING IDU 2. REUSE EXISTING 13G 1.8M MDD DP ANTENNA 3. REUSE EXISTING ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA SLOT 3 & 4 | 1. INSTALL NEW 1PCS ISM8 AT SLOT 4 EXISTING IDU 2. REUSE EXISTING 13G 1.8M MDD DP ANTENNA 3. REUSE EXISTING ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA SLOT 3 & 4 | [5 empty] | GCI | SQ202506260719-GCI | GCI | SQ202506190684-GCI // SQ202506190693-GCI | 2025-07-04 | 2025-07-04 | Completed | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061162 |  | 2025-06-12 | 2025-06-13 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-07-04 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-25 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-20 | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-07-03 | JUTI//ANAK RICHARD/6800000216 | 2025-06-19: 2025-06-19; 2025-06-19: 2025-06-30; 2025-06-19: 2025-06-19; 2025-06-20: 2025-07-03 |  |  | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506050639-GCI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
1021R_HU | Kg. Bukit Hijau | DU00005584031 | Central | Selangor | 3.252056 | 101.383561 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2x ISM8 | MW Parallel Link | MW MW Parallel 13G_2+0_1.2/1.2_512QAM_EPLA | MW MW Parallel 13G_2+0_1.2/1.2_512QAM_EPLA NE: 1. Reuse RTN910A_RTN01. 2. Install new ISM8 at slot 3. 3. Install new XMC-3 SB A and B. 4. Configure 13G_2+0_1.2/1.2_EPLA with exisitng 2+0 link. | MW MW Parallel 13G_2+0_1.2/1.2_512QAM_EPLA FE: 1. Reuse RTN910A_RTN01. 2. Install new ISM8 at slot 3. 3. Install new XMC-3 SB A and B. 4. Configure 13G_2+0_1.2/1.2_EPLA with exisitng 2+0 link. | [5 empty] | GCI | SQ202506100555-GCI | GCI | SQ202506100578-GCI // SQ202506100586-GCI // SQ202507030665-GCI | 2025-11-14 | 2025-11-07 | Completed | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-07 | 2025-08-14 | 2025-08-07 | 2025-08-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Manager | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-14 | 2025-11-07 | 2025-11-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061038 |  | 2025-06-11 | 2025-06-12 | Completed | 2025-06-10 | 2025-06-11 | 2025-06-10 | 2025-06-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-26 | 2025-07-03 | 2025-06-25 | 2025-07-08 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-06-26 | 2025-07-03 | 2025-06-25 | 2025-07-08 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-07 | 2025-06-26 | 2025-07-03 | 2025-06-25 | 2025-07-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-06-19: 2025-06-26; 2025-06-19: 2025-07-03; 2025-06-19: 2025-06-25; 2025-06-20: 2025-07-03 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505280699-GTSB | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | HSU//MYET CHAE/6799000011
7487B_HU | Kg Gaban | DU00005584032 | Sabah | Sabah | 5.319390 | 118.239430 | [5 empty] | 8G_2+0_1.8/1.8_DP_SB A,B |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 8G_2+0_1.8/1.8_DP_SB A,A 1xRTN910A | MW Parallel Link | MW PARALLEL LINK 7487B-7494B WITH 8G_2+0_1.8/1.8_DP_SB A,A | MW PARALLEL LINK 7487B-7494B WITH 8G_2+0_1.8/1.8_DP_SB A,B NE: 1. Install new RTN910A. 2. Install new XMC-3_A,A. 3. Install new 8G_1.8m_DP. 4. Configure 8G_2+0_1.8/1.8_EPLA 5. Carry only 7487B | MW PARALLEL LINK 7487B-7494B WITH 8G_2+0_1.8/1.8_DP_SB A,B FE: 1.Reuse RTN910A_RTN02 use Slot 7. 2. Install new XMC-3_A,A 3. Install new 8G_1.8m_DP. 4. Configure 8G_2+0_1.8/1.8_EPLA 5. Carry only 7487B | XMC-3 A,A |  | 8 | 1.8 | 1.8 | Seri Pancar | SQ202506200661-Seri Pancar | NR services | SQ202507230780-NR Services // SQ202507230784-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-06-19 | 2025-07-31 | 2025-06-20 | 2025-06-23 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-06-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-06-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071522 |  | 2025-07-16 | 2025-07-21 | Completed | 2025-07-15 | 2025-07-16 | 2025-07-15 | 2025-07-21 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-08-22 | 2025-07-22 | 2025-07-24 | WILFRED BALANG7167000026 | NR Service TI | 2025-07-22 | 2025-08-22 | 2025-07-22 | 2025-08-05 | WILFRED BALANG7167000026 | NR Service TI | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-04 | 2025-07-22 | 2025-08-22 | 2025-07-22 | 2025-08-08 | WILFRED BALANG7167000026 | 2025-06-19: 2025-07-22; 2025-06-19: 2025-08-22; 2025-06-19: 2025-07-22; 2025-06-20: 2025-07-24 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505280702-GTSB | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | HSU//MYET CHAE/6799000011
4969A_HU_1 | Sungai Kob | DU00005602284 | Northern | Kedah | 5.429180 | 100.644020 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | NE RTN910A x1 | MW Hardware Upgrade | Hardware upgrade RTN950 to RTN910A due to old version not support for EPLA. Site Impacted : 3508A NE_4969A. 1. Install new RTN910A. 2.Ttransfer existing 4_ISM8-2+0 from RTN950__NE D : 13494 into RTN910A , 4_ISM8-2+0. 3.Install new 3_ISM8-2+0 into new RTN910A. 4.Transfer existing 3_ISV3 & 5_ISV3 IF cable to new 3_ISM8-2+0. 5.RTN910A , 7_ISM8-2+0 , install new parallel link 15G_2+0_28M. (refer to DU ID 4969A_HU , DU Code DU00005172945). | Hardware upgrade RTN950 to RTN910A due to old version not support for EPLA. Site Impacted : 3508A NE_4969A. 1. Install new RTN910A. 2.Ttransfer existing 4_ISM8-2+0 from RTN950__NE D : 13494 into RTN910A , 4_ISM8-2+0. 3.Install new 3_ISM8-2+0 into new RTN910A. 4.Transfer existing 3_ISV3 & 5_ISV3 IF cable to new 3_ISM8-2+0. 5.RTN910A , 7_ISM8-2+0 , install new parallel link 15G_2+0_28M. (refer to DU ID 4969A_HU , DU Code DU00005172945). | Refer to 4969A_HU (DU Code : DU00005172945). | [5 empty] | NWAVE | SQ202507160641-N-Wave | NWAVE | SQ202505280637-N-Wave // SQ202505280653-N-Wave | 2025-11-26 | 2025-11-28 | Completed | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-07-30 | 2025-07-30 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25053027 |  | 2025-05-31 | 2025-06-05 | Completed | 2025-05-30 | 2025-05-31 | 2025-05-30 | 2025-06-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-27 | 2025-05-28 | 2025-05-28 | 2025-05-28 | Khairul Azman Bin Din7160000001 |  | 2025-05-28 | 2025-05-31 | 2025-05-28 | 2025-06-07 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-28 | 2025-05-28 | 2025-05-31 | 2025-05-28 | 2025-06-13 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2025-05-28 | 2025-05-31 | 2025-05-28 | 2025-05-28 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | NG HONG JIE7018000036 | Logistic Team | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050639-GCI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | CHEONG/SENG/WAH/7018000306
9195A_EB | Ulu Krain Junction | DU00005602285 | Sarawak | Sarawak | 1.752155 | 111.401068 | [6 empty] | ZTE | 00. Integrated/RFS Done | 0717: Sacofa Port 1-5-4 | TSS+TI | L1+ATP+PAC | 1x 910A RTN (prioritize re-deploy IDU with CSHR board for 4xGE electrical port availability) | IDU-IPRAN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | [6 empty] | Allstar | SQ202507180633-Allstar | Allstar | SQ202507190105-Allstar // SQ202512170142-Allstar | 2026-02-09 | 2026-02-04 | Completed | 2025-07-17 | 2025-07-31 | 2025-07-23 | 2025-07-23 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-09 | 2026-02-03 | 2026-02-03 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070359 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-16 | 2025-07-22 | 2025-07-17 | 2025-07-17 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-16 | 2025-07-22 | 2025-07-17 | 2025-07-21 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-17 | 2025-07-16 | 2025-07-22 | 2026-01-29 | 2026-01-29 | MICHEAL//BICKSON ANAK BANING/6798000201 | 2025-06-19: 2025-07-16; 2025-06-19: 2025-07-22; 2025-06-19: 2025-07-17; 2025-06-20: 2025-07-17 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202602260597-GCI | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | CHEONG/SENG/WAH/7018000306
9124A_EB | Sg Selat | DU00005602286 | Sarawak | Sarawak | 3.083311 | 112.986649 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1x 910A RTN (prioritize re-deploy IDU with CSHR board for 4xGE electrical port availability) | IDU-IPRAN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | [6 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507190105-Allstar | 2025-10-31 | 2025-10-28 | Completed | 2025-06-26 | 2025-06-30 | 2025-07-04 | 2025-07-04 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070747 |  | 2025-07-08 | 2025-07-15 | Completed | 2025-07-07 | 2025-07-08 | 2025-07-07 | 2025-07-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-26 | 2025-08-01 | 2025-07-26 | 2025-07-26 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-26 | 2025-08-01 | 2025-07-31 | 2025-07-31 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-07-26 | 2025-08-01 | 2025-07-31 | 2025-07-31 | TONI//ANAK KUMBONG/6798000163 | 2025-06-19: 2025-07-26; 2025-06-19: 2025-08-01; 2025-06-19: 2025-07-26; 2025-06-20: 2025-07-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507080651-GTSB | 2025-08-11 | 2025-08-18 | 2025-08-11 | 2025-08-11 | HSU//MYET CHAE/6799000011
9097A_EB | Bukit Lambir(Celcom) | DU00005602287 | Sarawak | Sarawak | 4.214106 | 114.047374 |  |  |  | AUG 25 |  |  | ZTE | 08. Pending RFS | 10.10.25 - IDU ready, Pending Patching to sacofa port 11/8/2025 : Cancel due to some TX route change 9/8/2025 : Cutover done, pending declare | TSS+TI |  | 1x 910A RTN (prioritize re-deploy IDU with CSHR board for 4xGE electrical port availability) | IDU-IPRAN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | [6 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507190105-Allstar | 2025-07-11 | 2025-07-07 | Completed | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-04 | 2025-07-02 | 2025-07-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-04 | 2025-07-02 | 2025-07-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070748 |  | 2025-07-08 | 2025-07-15 | Completed | 2025-07-07 | 2025-07-08 | 2025-07-07 | 2025-07-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-09 | 2025-08-15 | 2025-08-09 | 2025-08-09 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-08-09 | 2025-08-15 | 2025-10-18 | 2025-10-18 | TONI//ANAK KUMBONG/6798000163 | Allstar TI |  |  |  |  | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-09 | 2025-08-09 | 2025-08-15 | 2025-08-25 | 2025-10-18 | TONI//ANAK KUMBONG/6798000163 | 2025-06-19: 2025-08-09; 2025-06-19: 2025-08-15; 2025-06-19: 2025-08-09; 2025-06-20: 2025-08-09 | [7 empty] | GTSB | SQ202507080651-GTSB | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | HSU//MYET CHAE/6799000011
9236A_EB | Kg Hilir | DU00005602288 | Sarawak | Sarawak | 1.249509 | 111.454762 |  |  |  | AUG 25 |  |  | ZTE | 00. Site Out/Drop | 9/10/25 - site cancel by CD 11/8/2025 : Port Tejas info already have - Cancel proceed due to raining day | TSS+TI |  | 1x 910A RTN (prioritize re-deploy IDU with CSHR board for 4xGE electrical port availability) | IDU-IPRAN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | [6 empty] | Allstar | SQ202507100507-Allstar | Allstar | No PR required-Work at TSS only | 2025-07-11 | 2025-07-09 | Completed | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-09 | 2025-07-11 | 2025-07-09 | 2025-07-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070746 |  | 2025-07-08 | 2025-07-09 | Completed | 2025-07-07 | 2025-07-08 | 2025-07-07 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-10 | 2025-07-16 | 2025-07-10 | 2025-07-10 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-10 | 2025-07-16 | 2025-09-07 | 2025-11-14 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | [7 empty] | 2025-07-10 | 2025-07-16 | 2026-02-03 | 2026-02-03 | KENISTON//ANAK SPANCER/6798000184 | 2025-06-19: 2025-07-10; 2025-06-19: 2025-07-16; 2025-06-19: 2025-07-10; 2025-06-20: 2025-07-10 | [7 empty] | GTSB | SQ202507080651-GTSB | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | HSU//MYET CHAE/6799000011
9057C-9156A | Kampong Sg Alo 2 | DU00004123583 | Sarawak | Sarawak | 2.900028 | 112.105090 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done | 15/8/2025 : Cutover done 14/8/2025 : Cutover done, pending declare 13/8/2025 : Cutover done 20/9: Pending Site BoM. Req regional to verifty on materials availability | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_0.6/0.6_DP 2xXMC-3_A,B | MW Swap | MW SWAP FROM 23G_1+0 TO 23G_2+0_0.6/0.6_DP_EPLA. | MW SWAP FROM 23G_1+0 TO 23G_2+0_0.6/0.6_DP_EPLA. NE: 1. Reuse exisitng RTN910A. 2. Install XMC-3_SB A,B. 3. Install new 23G_0.6_DP. 4. Configure 23G_2+0_0.6/0.6_EPLA. | MW SWAP FROM 23G_1+0 TO 23G_2+0_0.6/0.6_DP_EPLA. FE: 1. Reuse exisitng RTN910A. 2. Install XMC-3_SB A,B. 3. Install new 23G_0.6_DP. 4. Configure 23G_2+0_0.6/0.6_EPLA. | XMC-3_SB A,B |  | 23 | 0.6 | 0.6 | Allstar | SQ202508270919-Allstar | Allstar | SQ202507290147-Allstar // SQ202507290151-Allstar |  |  | Ongoing | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25072008 |  | 2025-07-21 | 2025-08-09 | Completed | 2025-07-20 | 2025-07-21 | 2025-07-20 | 2025-08-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-12 | 2025-08-19 | 2025-08-12 | 2025-08-12 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-12 | 2025-08-19 | 2025-08-19 | 2025-08-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-15 | 2025-08-12 | 2025-08-19 | 2025-08-18 | 2025-08-18 | ROYSTON//AHHOLE/6000038561 | 2025-08-12 | 2025-08-19 | 2025-08-12 | 2025-08-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-12-09 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202506050655-GTSB | 2025-07-02 | 2025-07-02 | 2025-07-10 | 2025-07-10 | HSU//MYET CHAE/6799000011
Q01246-Q00570 | Q139A_Q01246OD_LDGSEMATAN | DU00004123584 | Sarawak | Sarawak | 1.135952 | 110.757810 |  | FEB 25 | [5 empty] | 00. Integrated/RFS Done | 27/10 - FE done pending NE due to skylift avaible on 29/10 and plan integrated on 29/10 22/10: Pending Site DO 3/9: BoM Ready, Pending DO 16/8: Pending TSS completion. Drone required. TS raised pending RPD approval | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_0.6/1.2_MDD_SB A | MW New Link / Reroute | SWAP LINK Q01246-9257A, WITH HUAWEI_15GHZ_2+0_28MHZ_0.6/1.2_MDD_10.07KM NE: Q01246 1. Swap existing RTN910 with new RTN910A. 2. Swap existing ODU with XMC_5D_SB A. 3. Swap exisitng antenna with 15G_0.6m_MDD. 4. Configure 15G_2+0_0.6_MDD_EPLA. 5. Dismantle Q01246-Q00570_13G_1+0 link. FE: 9257A 1. Install new RTN910A . 2. Swap existing ODU with XMC_5D_SB A. 3. Swap exisitng antenna with 15G_1.2m_MDD. 4. Configure 15G_2+0_1.2_MDD_EPLA. 5. Dismantle Q01246-Q00570_13G_1+0 link. | [7 empty] | Trintel | SQ202505020377-Trintel | Allstar | SQ202511260494-Allstar // SQ202511260502-Allstar | 2025-12-23 | 2025-12-16 | Completed | 2025-04-30 | 2025-05-02 | 2025-04-30 | 2025-05-02 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-11-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102339 |  | 2025-10-24 | 2025-10-24 | Completed | 2025-10-23 | 2025-10-24 | 2025-10-23 | 2025-10-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-30 | 2025-11-12 | 2025-11-12 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-10-24 | 2025-10-30 | 2025-11-12 | 2025-11-21 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-10-24 | 2025-10-30 | 2025-11-22 | 2025-11-22 | BONG NEE NYEEbong.allstar@gmail.com | 2025-06-19: 2025-10-24; 2025-06-19: 2025-10-30; 2025-06-19: 2025-10-29; 2025-06-20: 2025-10-29 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB_AA | SQ202510300154-GTSB
Q01021-Q00672 | Q141A_Q01021OD_KGKENIONG | DU00004123585 | Sarawak | Sarawak | 1.265592 | 110.882990 | [6 empty] | ZTE | 03. Pending TSS | 17/4/2026: Site proposed TSS only due to space constraint. Email from 29/1/2026 confirm with planner. 0616: SOW updated with parellel link due to HU still persist. 31/10: NIS TSS completed in April with remark FE site tower spacing issue. Cannot accomodate additional MW antenna. Pending planner solution. 22/10: Pending Site DO 20/9: Pending Site DO. Req regional to verifty on materials availability 16/8: Pending TP submission 1/8: Planner hold solutions due space issue | TSS+AA+TI |  | 13G_1.2m/1.2m_MDD_2+0_28Mhz_256Q_400Mbps(XMC5D sub A) | MW Parallel Link | ADD MW PARALLEL LINK Q01021-Q00672, WITH HUAWEI_13GHZ_2+0_28MHZ_1.2M_18.75KM NE: 1- Install 1 new ISM8 card at existing RTN-910, 2- Install 1 new 13G 1.2 m DP Antenna. 3- Install new 2+0 13G XMC5D sub band A. 4- Configure link 2+0_28Mhz with modulation 256QAM_EPLA FE: 1- Install 1 new ISM8 card at existing RTN-910, 2- Install 1 new 13G 1.2m DP Antenna. 3- Install new 2+0 13G XMC5D sub band A. 4- Configure link 2+0_28Mhz with modulation 256QAM_EPLAa | [7 empty] | Magicell | SQ202509030212-Magicell | GTSB | SQ202509040325-GTSB // SQ202509040348-GTSB |  |  | Not started | 2025-09-03 | 2025-09-30 | [6 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | DO Canceled (More than 30 days) | 2025-08-26 |  | Ongoing | 2025-08-25 | 2025-08-26 | 2025-08-25 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB_AA | SQ202510300154-GTSB
Q00933-Q00345 | Q132A_Q00933OD_JLNSUAI | DU00004123586 | Sarawak | Sarawak | 3.806694 | 113.632020 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done | 22/10: Pending Site DO 20/9: Pending Site DO. Req regional to verifty on materials availability | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_2+0_1.8/1.8_MDD_XMC-5D_SB A | MW Swap | MW SWAP LINK Q0933-Q0345 WITH HW 13G_2+0_1.8/1.8_MDD_SB A DISMANTLE 7G NE: 1. Swap existing IDU with RTN910A. 2. Swap existing ODU with XMC_5D_SB A. 3. Swap exisitng antenna with 1.8m_MDD. 4. Configure 13G_2+0_1.2m_MDD_EPLA. 5. Dismantle 7G. FE: 1. Swap existing IDU with RTN910A. 2. Swap existing ODU with XMC_5D_SB A. 3. Swap exisitng antenna with 1.8m_MDD. 4. Configure 13G_2+0_1.2m_MDD_EPLA. 5. Dismantle 7G. | NE: 1. Swap existing IDU with RTN910A. 2. Swap existing ODU with XMC_5D_SB A. 3. Swap exisitng antenna with 1.8m_MDD. 4. Configure 13G_2+0_1.2m_MDD_EPLA. 5. Dismantle 7G. | FE: 1. Swap existing IDU with RTN910A. 2. Swap existing ODU with XMC_5D_SB A. 3. Swap exisitng antenna with 1.8m_MDD. 4. Configure 13G_2+0_1.2m_MDD_EPLA. 5. Dismantle 7G. |  |  | 13 | 1.8 | 1.8 | Datasco | SQ202411180382-Datasco | Allstar | SQ202411150579-Allstar // SQ202504260202-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24111336 |  | 2024-11-14 | 2025-02-25 | Completed | 2024-11-13 | 2024-11-14 | 2024-11-13 | 2025-02-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-12 | 2025-03-18 | 2025-03-18 | 2025-03-18 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-03-12 | 2025-03-18 | 2025-04-11 | 2025-04-11 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-15 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-03-12 | 2025-03-18 | 2025-05-21 | 2025-05-21 | TONI//ANAK KUMBONG/6798000163 | 2025-03-12 | 2025-03-18 | 2025-03-19 | 2025-03-19 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-11 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-06-19 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB_AA | SQ202510300154-GTSB | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | HSU//MYET CHAE/6799000011
Q00391-Q00152 | Q139A_Q00391OD_CB_TMTEBEDU | DU00004123587 | Sarawak | Sarawak | 1.025934 | 110.361870 | [6 empty] | ZTE | 00. Integrated/RFS Done | 30/8: D3: Cutover done. Post-CO T/shooting WIP 28/8: D2: Continue TI 26/8: MOS & Pre-installation WIP. Planner to update SOW in EPMS | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_0.6m/0.6m_SP_1+0_112Mhz_512Q_778Mbps(XMC3 sub A) | MW Swap | SWAP MW LINK Q00391-Q00152,WITH HUAWEI_23GHZ_1+0_112MHZ_0.6M_1.86KM NE: 1- Swap existing IDU with new IDU RTN910A. 2- Install 23G 0.6m SP Antenna . 3- Install new 1+0 23G XMC3 sub band A. 4- Configure link 1+0_112Mhz with modulation 256QAM 5- Decom the existing HW link FE: 1- Swap existing IDU with new IDU RTN910A. 2- Install 23G 0.6m SP Antenna . 3- Install new 1+0 23G XMC3 sub band A. 4- Configure link 1+0_112Mhz with modulation 256QAM 5- Decom the existing HW link | [7 empty] | Trintel | SQ202411140419-Trintel | Allstar | SQ202409070072-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY240814AS |  | 2024-09-10 | 2024-09-10 | Completed | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-30 | 2024-09-05 | 2024-09-10 | 2024-09-11 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2024-08-30 | 2024-09-05 | 2024-08-23 | 2024-09-10 | BETARMOKE//ANAK COSIT/6798000181 | Allstar TI | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-08-30 | 2024-09-05 | 2024-09-02 | 2024-09-02 | BETARMOKE//ANAK COSIT/6798000181 | 2024-08-30 | 2024-09-05 | 2024-09-02 | 2024-09-02 | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-10-24 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
9110C-9708A | Shanghai Electric Mukah (REL) | DU00004123588 | Sarawak | Sarawak | 2.740877 | 112.473030 |  | FEB 25 | [5 empty] | 00. Site Out/Drop | 4/9/2025 : Doing under DU 9110C NIC TX 20/9: Pending Site BoM. Req regional to verifty on materials availability | TSS+AA+TI |  | 7G_2+0_1.8/1.2_DP_ 1x ISM8 | MW Parallel Link | ADD MW PARALLEL LINK 9110C-9708A, WITH HUAWEI_7G_2+0_1.8/1.2_DP_22.5KM Need freq scanning | NE: 1. Reuse existing RTN910A and add 1 ISM8 at Slot 4 2. Install new XMC-3_7GG_SB 3. Install new Antenna 7G_1.8m_DP. 4. Configure 7G_2+0_1.8m_256QAM. | FE: 1. Install new RTN910A. 2. Install new XMC-3_7G_SB 3. Install new Antenna 7G_1.2m_DP. 4. Configure 7G_2+0_1.2m_256QAM. | [11 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2025-05-10 | 2025-06-19 | [6 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300154-GTSB
9279A-Q00407 | TM Jalan Glumbia | DU00004123589 | Sarawak | Sarawak | 1.232613 | 111.462350 | [6 empty] | ZTE | 00. Integrated/RFS Done | 6/9: Cutover done 3/9: BOM issued wrong item. need to amend. already amended bom, pending DO | TSS+TI | L1+ATP+PAC |  | BBU Patching | BBU patch to use xC LL_Q00407 Dismantle MW link 9279A-9236A | [7 empty] | Datasco | SQ202411180382-Datasco | Datasco | SQ202409060594-Datasco |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24082768 |  | 2024-08-28 | 2024-08-29 | Completed | 2024-08-27 | 2024-08-28 | 2024-08-27 | 2024-08-29 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-12 | 2024-09-30 | 2024-10-10 | 2024-10-10 | Wong Ching Chai7019000072 | Datasco TI | 2024-09-12 | 2024-09-30 | 2024-09-09 | 2024-09-25 | Wong Ching Chai7019000072 | Datasco TI | 2024-09-06 | 2024-09-09 | 2024-09-06 | 2024-09-09 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  |  | 2024-09-12 | 2024-09-30 | 2024-10-09 | 2024-10-09 | Wong Ching Chai7019000072 | 2025-03-12: 2024-09-12; 2025-03-18: 2024-09-30; 2025-03-19: 2024-10-09; 2025-03-19: 2024-10-09 |  |  | 2024-11-28 | 2024-12-28 | 2024-11-28 | 2024-11-28 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
9611A-Q00503 | Kampung Riih | DU00004123590 | Sarawak | Sarawak | 1.145110 | 110.526410 | [7 empty] | 00. Site Out/Drop | 4/11: Proceed under TX NIC (SSM list) 22/10: Pending Site DO 20/9: Pending Site DO. Req regional to verifty on materials availability 16/8: To proceed after BBU swap (MOCN done) + LL Upgrade |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q00502-Q00380 | Q129A_Q00502OD_CB_MERADONGPASI | DU00004123591 | Sarawak | Sarawak | 2.081310 | 111.610210 |  | FEB 25 |  | AUG 25 |  |  | ZTE | 06. Other Issue | 26/9/2025 : Aligment WIP 25/9/2025 : Plan to continue aligment - Cancel proceed 24/9/2025 : Aligment WIP - Cancel proceed 30/8/2025 : Team give up 29/8/2025 : Aligment WIP 23/8/2025 : Alignment still not complete due to raining day 22/8/2025 : Alignment still not complete 18/8/2025 : Plan continue alignment - cancel proceed due to team attend other site 16/8/2025 : Plan continue alignment - cancel proceed 15/8/2025 : Alignment still WIP 14/8/2025 : Alignment not yet done, still WIP 13/8/2025 : Installation done, pending alignment 12/8/2025 : FE installation still WIP 11/8/2025 : FE installation still not complete due to raining day 9/8/2025 : Plan to continue FE installation - Cancel proceed due to raining day 8/8/2025 : FE installation still not complete, raining 7/8/2025 : NE installation done, FE installation WIP 6/8/2025 : NE installation done, FE installation WIP 5/8/2025 : NE installation done, FE pending install 4/8/2025 : NE installation still not complete due to raining day, FE pending install 2/8/2025 : NE 60% installation complete, FE pending install 1/8/2025 : NE 30% installation complete, FE pending install 2605: Doable. Pending material DT. 22/10: Pending Site DO 20/9: Pending Site DO. Req regional to verifty on materials availability | TSS+AA+TI |  | 13G_2+0_1.2/1.2_MDD_ XMC-5D_SB A | MW Parallel Link | Parallel MW LINK Q00502-Q00380 WITH HUAWEI_13G_2+0_28MHZ_1.2M_MDD_XMC-5D_SB A Carry Traffic Q00502 only | Parallel MW LINK Q00502-Q00380 WITH HUAWEI_13G_2+0_28MHZ_1.2M_MDD_XMC-5D_SB A NE: 1. Install new RTN910A 2. Install XMC-5D 13GHz (Sub A) 3. Install Huawei Antenna 13GHz 1.2m MDD 4. Configure link as 13GHz 2+0 1.2m_28Mhz_450M_EPLA carry Q00502. | FE: 1. Install new RTN910A 2. Install XMC-5D 13GHz (Sub A) 3. Install Huawei Antenna 13GHz 1.2m MDD 4. Configure link as 13GHz 2+0 1.2m_28Mhz_450M_EPLA carry Q00502. | XMC-5D SB A |  | 13G | 1.2 | 1.2 | MTK | SQ202502060434-MTK | NR Services | SQ202507290163-NR Services // SQ202507290164-NR Services | 2025-03-08 | 2025-03-07 | Completed | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-08 | 2025-03-08 | 2025-03-07 | 2025-03-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-07 | 2025-03-08 | 2025-03-07 | 2025-03-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071087 |  | 2025-07-11 | 2025-07-31 | Completed | 2025-07-10 | 2025-07-11 | 2025-07-10 | 2025-07-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-17 | 2025-07-22 | 2025-08-23 | 2025-08-23 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | [13 empty] | 2025-07-17 | 2025-07-22 |  |  |  | 2025-03-12: 2025-07-17; 2025-03-18: 2025-07-22 | [7 empty] | GTSB | SQ202507080651-GTSB | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | HSU//MYET CHAE/6799000011
Q01612-Q00649 | QS50202_4_1-KGSEKUDUK | DU00004123592 | Sarawak | Sarawak | 1.257290 | 110.431810 | [6 empty] | ZTE | 00. Integrated/RFS Done | 24/10: D3: Cutover done. Post-CO T/S ongoing 16/10: MOS & Pre-installation in plan 11/10: pending ti start. antenna wind brace not included. already talking to guna on whether can use BS material else need to cancel rollout | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_0.61.2M/1.2M MDD 2+0 28MHz | MW Swap | SWAP MW LINK Q01612-Q00649 WITH HUAWEI_15G_2+0_28MHZ_0.6M/1.2M_4.73KM EXISTING MW CFG:HUAWEI_15G_1+0_28MHZ NE: 1. Swap existing IDU with HW RTN910A. 2. Swap existing ODU with XMC-5D 15G ( SB A). 3. Swap existing Antenna with 15G _0.6m MDD. 4. Configure 15G_2+0_0.6m_28MHz. FE: 1. Swap existing IDU with HW RTN910A. 2. Swap existing ODU with XMC-5D 15G ( SB A). 3. Swap existing Antenna with 15G _1.2m MDD. 4. Configure 15G_2+0_0.6m_28MHz. | [7 empty] | GCI | SQ202411180386-GCI | Allstar | SQ202410100851-Allstar |  |  | Ongoing | 2024-09-05 | 2024-09-06 | 2024-09-05 | 2024-09-09 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24092632 |  | 2024-09-27 | 2024-10-16 | Completed | 2024-09-26 | 2024-09-27 | 2024-09-26 | 2024-10-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-17 | 2024-10-23 | 2024-10-23 | 2024-10-23 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2024-10-17 | 2024-10-23 | 2024-10-18 | 2024-11-01 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2024-10-28 | 2024-10-28 | 2024-10-29 | 2024-10-29 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-10-17 | 2024-10-23 | 2024-11-05 | 2024-11-05 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2024-10-17 | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045
3186B11_EVT | PBTS SMK BENGKOGAN KOTA MARUDU PRN SABAH 2025 (E) | DU00006289592 | Sabah | Sabah | 6.582570 | 116.716170 | [13 empty] | Planning and integration support only for event site 3186B11 PBTS SMK BENGKOGAN, KOTA MARUDU PRN SABAH 2025 (E) Tx route: 3186B11/3186B11-7037B-7399A-LL-7000A 1) Share port with 7037B at 7000A 2) New NE ID FE IDU 7037B RTN02 3) New NE ID NE IDU 3186B11 RTN01 4) At FE site 7037B patch new RTN02 GE1 to existing RTN01 GE2 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
K00098_HU | K009A_K00098OD_LUBOKMERBAU | DU00006289593 | Northern | Kedah | 6.001342 | 100.725603 | [7 empty] | 04. BOM / Material Issue | 17/3: No 15G material | TSS+AA+TI |  | 13G_4+0_28M_1024QAM_EPLA(Without CA) NE_K00098/4156P New 13G_1.2M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x2. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x6 RUN(x4 RUN for new link and another x2 RUN for existing link if existing IF cables short). FE_K00423/4153P New 13G_1.2M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x6 RUN(x4 RUN for new link and another x2 RUN for existing link if existing IF cables short). | MW Parallel Link | ****IMPORTANT NOTE: 1.PLEASE DEAL WITH ZTE RAVIN FOR OBTAIN TT STATUS - CURRENTLY HAVING LOSSCOMM ISSUE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Build new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA). Later, combine new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA) with existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Become 15G&13G_6+0_28M_2048QAM&1024QAM_EPLA. Decom existing RTN950A(NEID 165-49096) and existing RTN950A(NEID 187-46235) ONLY. Anyway, do not decom existing ODU and existing Antenna for existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Site Impacted : K01107/4056P, K00628/4118P, K00626/4187P, K00625/4116P & K00098/4156P. NE_K00098/4156P 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF and insert x2 new ISM8 into slot 03 and 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA) using x2 new ISM8 into slot 03 and 04. Lay new IF cables with suitable type and length x4 RUN accordingly. 4.Shifting existing x2 IF cables from slot 05 and slot 06 of existing RTN950A(NEID 165-49096) to slot 07 Port 1 & 2 of new RTN910AF. If existing IF cables length short, lay new x2 IF cables with suitable length and type. 5.Later, combine new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA) with existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Become 15G&13G_6+0_28M_2048QAM&1024QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF and perform new cascading with LAN1 of existing SM IDU AGS20(IP Address 10.125.144.3) of existing SM MW Link_ID NT05700(K00098-K00625). 7.Re-use existing xC Vlan DCN & Vlan Services. 8.Decom existing RTN950A(NEID 165-49096) and existing RTN950A(NEID 187-46235) ONLY. Anyway, do not decom existing ODU and existing Antenna for existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. FE_K00423/4153P 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF and insert x2 new ISM8 into slot 03 and 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA) using x2 new ISM8 into slot 03 and 04. 4.Shifting existing x2 IF cables from slot 05 and slot 06 of existing RTN950A(NEID 187-46235) to slot 07 Port 1 & 2 of new RTN910AF. If existing IF cables length short, lay new x2 IF cables with suitable length and type. 5.Later, combine new HW MW Parallel K00098-K00423, 153G_4+0_28M_1024QAM_EPLA(Without CA) with existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Become 15G&13G_6+0_28M_2048QAM&1024QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF and perform new cascading with LAN2 of existing SM IDU AGS20(IP Address 10.127.14.114) of existing SM MW Link_ID NT05576(K00423-K00417). 7.Re-use existing xC Vlan DCN & Vlan Services. 8.Re-use existing port of PTN/Cisco for all traffics impacted. 9.Decom existing RTN950A(NEID 165-49096) and existing RTN950A(NEID 187-46235) ONLY. Anyway, do not decom existing ODU and existing Antenna for existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. | ****IMPORTANT NOTE: 1.PLEASE DEAL WITH ZTE RAVIN FOR OBTAIN TT STATUS - CURRENTLY HAVING LOSSCOMM ISSUE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Build new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA). Later, combine new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA) with existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Become 15G&13G_6+0_28M_2048QAM&1024QAM_EPLA. Decom existing RTN950A(NEID 165-49096) and existing RTN950A(NEID 187-46235) ONLY. Anyway, do not decom existing ODU and existing Antenna for existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Site Impacted : K01107/4056P, K00628/4118P, K00626/4187P, K00625/4116P & K00098/4156P. NE_K00098/4156P 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF and insert x2 new ISM8 into slot 03 and 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA) using x2 new ISM8 into slot 03 and 04. Lay new IF cables with suitable type and length x4 RUN accordingly. 4.Shifting existing x2 IF cables from slot 05 and slot 06 of existing RTN950A(NEID 165-49096) to slot 07 Port 1 & 2 of new RTN910AF. If existing IF cables length short, lay new x2 IF cables with suitable length and type. 5.Later, combine new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA) with existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Become 15G&13G_6+0_28M_2048QAM&1024QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF and perform new cascading with LAN1 of existing SM IDU AGS20(IP Address 10.125.144.3) of existing SM MW Link_ID NT05700(K00098-K00625). 7.Re-use existing xC Vlan DCN & Vlan Services. 8.Decom existing RTN950A(NEID 165-49096) and existing RTN950A(NEID 187-46235) ONLY. Anyway, do not decom existing ODU and existing Antenna for existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. | ****IMPORTANT NOTE: 1.PLEASE DEAL WITH ZTE RAVIN FOR OBTAIN TT STATUS - CURRENTLY HAVING LOSSCOMM ISSUE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G IN ORDER TO ENSURE CHANNEL AVAILABILITY.**** Existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Build new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA). Later, combine new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA) with existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Become 15G&13G_6+0_28M_2048QAM&1024QAM_EPLA. Decom existing RTN950A(NEID 165-49096) and existing RTN950A(NEID 187-46235) ONLY. Anyway, do not decom existing ODU and existing Antenna for existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Site Impacted : K01107/4056P, K00628/4118P, K00626/4187P, K00625/4116P & K00098/4156P. FE_K00423/4153P 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF and insert x2 new ISM8 into slot 03 and 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel K00098-K00423, 13G_4+0_28M_1024QAM_EPLA(Without CA) using x2 new ISM8 into slot 03 and 04. 4.Shifting existing x2 IF cables from slot 05 and slot 06 of existing RTN950A(NEID 187-46235) to slot 07 Port 1 & 2 of new RTN910AF. If existing IF cables length short, lay new x2 IF cables with suitable length and type. 5.Later, combine new HW MW Parallel K00098-K00423, 153G_4+0_28M_1024QAM_EPLA(Without CA) with existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. Become 15G&13G_6+0_28M_2048QAM&1024QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF and perform new cascading with LAN2 of existing SM IDU AGS20(IP Address 10.127.14.114) of existing SM MW Link_ID NT05576(K00423-K00417). 7.Re-use existing xC Vlan DCN & Vlan Services. 8.Re-use existing port of PTN/Cisco for all traffics impacted. 9.Decom existing RTN950A(NEID 165-49096) and existing RTN950A(NEID 187-46235) ONLY. Anyway, do not decom existing ODU and existing Antenna for existing HW MW Link_ID NT05914, K00098-K00423, 15G_2+0_28M_2048QAM_EPLA. | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD)+Dual Coupler x1 | 13G_1.2M(MDD)+Dual Coupler x1 | GTSB | SQ202602230050-GTSB | GTSB | SQ202602230039-GTSB // SQ202602230045-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022582 |  | 2026-02-26 | 2026-03-05 | Completed | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-03-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-09 | 2026-03-31 | 2026-03-09 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-03-09 | 2026-03-31 | 2026-03-09 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | [7 empty] | 2026-03-09 | 2026-03-31 | 2026-03-09 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2024-10-17: 2026-03-09; 2024-10-23: 2026-03-31; 2024-10-23: 2026-03-09 | [7 empty] | GTSB | SQ202511130577-GTSB
7391A_IPR | Kg Nangka | DU00006317432 | Sabah | Sabah | 6.782620 | 116.790980 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_7391A New SFP Module 1G with 10Km 1310nm x1(For CTS). New Optical Patch Cord cable x1 with suitable type and length. New CAT6 cable x1. | IPRAN Port Upgrade | Perform LAG between 1st(existing) and 2nd(new) port of existing RTN910AF(RTN01-NEID 9-18552) and CTS at 7391A. Site Impacted :7391A, S00940/7780B, 7256R & 9000B23 NE_7391A. 1.Enable port 8-EM6-2 of existing RTN910AF(RTN01-NEID 9-18552). 2.Enable port 8-EM6-2 of existing RTN910AF(RTN02-NEID 9-36009). 3.Disconnect existing cascading port 8-EM6-6 of existing RTN910AF(RTN01-NEID 9-18552) and port 8-EM6-5 of existing RTN910AF(RTN02-NEID 9-36009). 4.Perform new cascading electrical CAT6 cable between 8-EM6-2 of existing RTN910AF(RTN01-NEID 9-18552) and port 8-EM6-2 of existing RTN910AF(RTN02-NEID 9-36009). 5.Patching new Optical patch cord cable between port 8-EM6-6 of existing RTN910AF(RTN01-NEID 9-18552) and 2nd port of CTS. 6.Perform LAG between for port 8-EM6-5 & port 8-EM6-6 at existing RTN910AF(RTN01-NEID 9-18552 and existing 1G port and new 1G port at CTS. | Perform LAG between 1st(existing) and 2nd(new) port of existing RTN910AF(RTN01-NEID 9-18552) and CTS at 7391A. Site Impacted :7391A, S00940/7780B, 7256R & 9000B23 NE_7391A. 1.Enable port 8-EM6-2 of existing RTN910AF(RTN01-NEID 9-18552). 2.Enable port 8-EM6-2 of existing RTN910AF(RTN02-NEID 9-36009). 3.Disconnect existing cascading port 8-EM6-6 of existing RTN910AF(RTN01-NEID 9-18552) and port 8-EM6-5 of existing RTN910AF(RTN02-NEID 9-36009). 4.Perform new cascading electrical CAT6 cable between 8-EM6-2 of existing RTN910AF(RTN01-NEID 9-18552) and port 8-EM6-2 of existing RTN910AF(RTN02-NEID 9-36009). 5.Patching new Optical patch cord cable between port 8-EM6-6 of existing RTN910AF(RTN01-NEID 9-18552) and 2nd port of CTS. 6.Perform LAG between for port 8-EM6-5 & port 8-EM6-6 at existing RTN910AF(RTN01-NEID 9-18552 and existing 1G port and new 1G port at CTS. | [6 empty] | NR services | SQ202512160988-NR Services | NR services | SQ202512010600-NR Services | 2026-01-02 | 2025-12-30 | Completed | 2025-12-16 | 2025-12-18 | 2025-12-16 | 2025-12-16 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-26 | 2026-01-02 | 2025-12-26 | 2025-12-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112423 |  | 2025-11-25 | 2025-11-26 | Completed | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-26 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-04 | 2026-01-04 | 2025-12-04 | 2025-12-05 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-12-04 | 2026-01-04 | 2025-12-04 | 2025-12-09 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-28 | 2025-12-04 | 2026-01-04 | 2025-12-04 | 2025-12-08 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2024-10-17: 2025-12-04; 2024-10-23: 2026-01-04; 2024-10-23: 2025-12-04; 2024-10-23: 2025-12-05 |  |  | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-16 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511280936-GTSB
7001A_IPR | Wisma Luth | DU00006317433 | Sabah | Sabah | 5.345616 | 115.745779 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_7001A New CAT6 cable x1. New SFP Module 1G with 10Km 1310nm x3(For 1x IDU & 2x CTS). New Optical Patch Cord cable x2 with suitable type and length. | IPRAN Port Upgrade | Existing use electrical TDC LL and plan to swap with 2x optical CTS LL. Perform LAG between 1st(new) and 2nd(new) port of existing RTN910AF(RTN01-NEID 9-36413) and 2x new port of CTS LL. Site Impacted :7001A, 7327K, 7201K & 7328H6. NE_7001A. 1.Insert Optical SFP Module into port 8-EM6-6 of existing RTN910AF(RTN02-NEID 9-36413). Enable port and config. 2.Insert Optical SFP Module into new 2x port of CTS. Enable and config. 3.Disconnect existing optical cascading between port 8-EM6-5 of existing RTN910AF(RTN02-NEID 9-36413) and port 8-EM6-5 of existing RTN910AF(RTN01-NEID 9-23321). 4.Disconnect existing CAT6 cable in between port 8-EM6-1 of existing RTN910AF(RTN02-NEID 9-36413) and existing TDC LL. 5.Perform new CAT6 cascading in between port 8-EM6-1 of existing RTN910AF(RTN02-NEID 9-36413) and port 8-EM6-2 of existing RTN910AF(RTN01-NEID 9-23321). 6.Perform new optical patching between port 8-EM6-5 of existing RTN910AF(RTN02-NEID 9-36413) and 1st new port of CTS. 7.Perform new optical patching between port 8-EM6-6 of existing RTN910AF(RTN02-NEID 9-36413) and 2nd new port of CTS. 8.Perform LAG between for port 8-EM6-5 & port 8-EM6-6 of existing RTN910AF(RTN02-NEID 9-36413) and new 1G port(1st & 2nd) of CTS. | Existing use electrical TDC LL and plan to swap with 2x optical CTS LL. Perform LAG between 1st(new) and 2nd(new) port of existing RTN910AF(RTN01-NEID 9-36413) and 2x new port of CTS LL. Site Impacted :7001A, 7327K, 7201K & 7328H6. NE_7001A. 1.Insert Optical SFP Module into port 8-EM6-6 of existing RTN910AF(RTN02-NEID 9-36413). Enable port and config. 2.Insert Optical SFP Module into new 2x port of CTS. Enable and config. 3.Disconnect existing optical cascading between port 8-EM6-5 of existing RTN910AF(RTN02-NEID 9-36413) and port 8-EM6-5 of existing RTN910AF(RTN01-NEID 9-23321). 4.Disconnect existing CAT6 cable in between port 8-EM6-1 of existing RTN910AF(RTN02-NEID 9-36413) and existing TDC LL. 5.Perform new CAT6 cascading in between port 8-EM6-1 of existing RTN910AF(RTN02-NEID 9-36413) and port 8-EM6-2 of existing RTN910AF(RTN01-NEID 9-23321). 6.Perform new optical patching between port 8-EM6-5 of existing RTN910AF(RTN02-NEID 9-36413) and 1st new port of CTS. 7.Perform new optical patching between port 8-EM6-6 of existing RTN910AF(RTN02-NEID 9-36413) and 2nd new port of CTS. 8.Perform LAG between for port 8-EM6-5 & port 8-EM6-6 of existing RTN910AF(RTN02-NEID 9-36413) and new 1G port(1st & 2nd) of CTS. | [6 empty] | NR services | SQ202512160988-NR Services | NR services | SQ202512010600-NR Services | 2025-12-24 | 2025-12-17 | Completed | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112424 |  | 2025-11-25 | 2025-11-27 | Completed | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-27 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-01 | 2026-01-01 | 2025-12-01 | 2025-12-03 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-12-01 | 2026-01-01 | 2025-12-01 | 2025-12-03 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-27 | 2025-12-01 | 2026-01-01 | 2025-12-01 | 2025-12-03 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2024-10-17: 2025-12-01; 2024-10-23: 2026-01-01; 2024-10-23: 2025-12-01; 2024-10-23: 2025-12-03 |  |  | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-16 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511280936-GTSB
Q01001-Q00120 | Q127A_Q01001OD_CB_MERINDUN | DU00004161354 | Sarawak | Sarawak | 1.180517 | 111.753553 | [6 empty] | ZTE | 00. Site Out/Drop | 22/10: Pending Site DO Proceed HU Upgrade under Tx Mini due site MOCN 2025 20/9: Pending Site DO. Req regional to verifty on materials availability |  |  | 13GHz_2.4m/2.4m_DP_4+0_28MHz | Cancel / Drop | 31 Oct 2025: Cancel/drop. Link already upgrade under NIC Swap Existing Huawei MW Link, Q01001-Q00120 with New Huawei_13GHz_2.4m/2.4m_DP_4+0_28MHz NE: 1. Swap Existing Huawei IDU with new RTN910A 2. Install New 2 pcs of ISM8 Card into Slot 3, 4 3. Swap Existing Huawei ODU with new XMC 3E (Hi Power) 13GHz 4+0 28MHz ODU (Sub A + Sub A + Sub B + Sub B) 4. Swap Existing Huawei Antenna with New Huawei 13GHz 2.4m DP Antenna 5. Config link as 13GHz 4+0 28MHz (256QAM) (EPLA) FE: 1. Swap Existing Huawei IDU with new RTN910A 2. Install New 2 pcs of ISM8 Card into Slot 3, 4 3. Swap Existing Huawei ODU with new XMC 3E (Hi Power) 13GHz 4+0 28MHz ODU (Sub A + Sub A + Sub B + Sub B) 4. Swap Existing Huawei Antenna with New Huawei 13GHz 2.4m DP Antenna 5. Config link as 13GHz 4+0 28MHz (256QAM) (EPLA) 6. MW IDU Patching from Q00120's IDU to 9233A's Router (LL) | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | DO Canceled (More than 30 days) | 2025-08-23 |  | Ongoing | 2025-08-22 | 2025-08-23 | 2025-08-22 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB_AA | SQ202510300154-GTSB
Q00437-Q00990 | Q143A_Q00437OD_PANTU | DU00004161355 | Sarawak | Sarawak | 1.141507 | 111.119135 |  | FEB 25 |  |  |  |  | ZTE | 00. Site Out/Drop | 0221: Same Config with NIC site. Plan rollout NIC site to resolve this issue. Proceed HU Upgrade under Tx Mini due site MOCN 2025 20/9: Pending Site DO. Req regional to verifty on materials availability |  |  | 13GHz_1.2m/1.2m_MDD_4+0_28MHz_SB B | Cancel / Drop | 31 Oct 2025: Cancel/drop. Link upgraded under NIC Swap Existing Huawei MW Link, Q00437-Q00990 with New Huawei_13GHz_1.2m/1.2m_MDD_4+0_28MHz NE: 1. Swap Existing Huawei IDU with new RTN910A. 2. Install 2xISM 8 at slot 3 and 4. 3. Swap Existing Huawei ODU with new XMC_5D SB B. 4. Swap Existing Huawei Antenna with New Huawei 13GHz 1.2m MDD Antenna 4. Config link as 13GHz 4+0 28MHz_CA_256QAM. FE: 1. Swap Existing Huawei IDU with new RTN910A. 2. Install 2xISM 8 at slot 3 and 4. 3. Swap Existing Huawei ODU with new XMC_5D SB B. 4. Swap Existing Huawei Antenna with New Huawei 13GHz 1.2m MDD Antenna 4. Config link as 13GHz 4+0 28MHz_CA_256QAM. | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | DO Canceled (More than 30 days) | 2025-08-23 |  | Ongoing | 2025-08-22 | 2025-08-23 | 2025-08-22 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB_AA | SQ202510300154-GTSB
Q01851-Q00618 | Q120A_Q01851OD_KGDARO | DU00004161356 | Sarawak | Sarawak | 2.522210 | 111.412060 |  | DEC 24 |  |  |  |  | ZTE | 00. Site Out/Drop | Proceed HU Upgrade under Tx Mini due site MOCN 2025 20/9: Pending Site DO. Req regional to verifty on materials availability |  |  | 18G_1+0_0.6/0.6M_SP_110Mhz_SB A | Cancel / Drop | 31 Oct 2025: Completed under NIC MW NEW LINK Q01851-9366A WITH HUAWEI_18GHZ_1+0_110MHZ_0.6M NE: 1. Install new RTN910A. 2. Install new XMC-3E_SB B. 4. Install new antenna 18G_0.6m_SP 5. Configure 18G_1+0_110Mhz_256QAM 6. Dismantle Q01851-Q00618 Link. FE: 1. Install new RTN910A. 2. Install new XMC-3E_SB B. 3. Install new antenna 18G_0.6m_SP 4. Configure 18G_1+0_110Mhz_256QAM 6. Dismantle Q01851-Q00618 Link. | [7 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300154-GTSB
1107L-1799B | PROTON CITY 3 | DU00004161781 | Northern | Perak | 3.746731 | 101.520881 | [7 empty] | 00. Integrated/RFS Done | 20/9: Cutover done. Post-CO T/S WIP 13/9: TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub B Lo 3) 1x18GHz 0.6m SP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub B Hi 3) 1x18GHz 0.6m SP | MW Swap | Existing link Huawei NT90163 (1107L-A00125) To swap Existing link 15GHz 2+0 with new Huawei link 18GHz 1+0 112MHz (1107L-1799B) Impacted sites: 1107L Current Tx route: 1107L-A00125-A00336 New Tx route: 1107L-1799B-fiber-1701A NE (1107L): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link FE (1799B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Patch new RTN GE1 to existing RTN02 GE1 4) Migrate 1107L traffic to new link/CP 5) Decom existing link | [7 empty] | CCSMY | SQ202411140303-CCS | CCSMY | SQ202410100845-CCS // SQ202504260175-CCS |  |  | Not started | 2025-02-25 | [6 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY240902AM |  | 2024-09-03 | 2024-09-03 | Completed | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-09-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-12 | 2024-09-27 | 2024-09-11 |  |  | CCS TI | 2024-09-11 | 2024-09-28 | 2024-09-11 | 2025-05-21 | MUHAMMAD SYAFIQ BIN AHMAD SUHAIMI7021000007 | CCS TI | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-09-11 | 2024-09-28 | 2024-09-11 | 2026-03-31 | MUHAMMAD SYAFIQ BIN AHMAD SUHAIMI7021000007 | 2024-09-11 | 2024-09-28 | 2024-09-11 | 2024-09-21 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
Q00238-Q00094 | JLN CAUSEWAY | DU00003480917 | Sarawak | Sarawak | 2.290620 | 111.826040 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050655-GTSB | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | AB.RAHMAN//BIN MAT NOOH/6237001519
A01171-A00099 | TMN SILIBIN_IPH | DU00003480918 | Northern | Perak | 4.616578 | 101.051376 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop |  |  |  | Cancel / Drop | MW Swap completed under A01171_PostMOCN | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q00794-Q00115 | TM TEBAKANG | DU00003480919 | Sarawak | Sarawak | 1.099722 | 110.506417 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | process under other DU, wafi email 16-jun'25 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050655-GTSB | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q01814-Q01892 | LDG RASAN | DU00003480921 | Sarawak | Sarawak | 3.414429 | 113.645815 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050655-GTSB | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | AB.RAHMAN//BIN MAT NOOH/6237001519
7454A-7442A | TMB Sook | DU00003480922 | Sabah | Sabah | 5.117029 | 116.424512 | WK17 | APR 24 |  |  | Drop/Cancel | Pass to Huawei |  | 00. Site Out/Drop |  |  |  | 13GHz_1.8m/1.8m_DP_2+0_28MHz | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S00991-S00607 | KAMPUNG KEBULU | DU00003480924 | Sabah | Sabah | 5.165370 | 116.198776 |  |  |  |  | Drop/Cancel | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01627-Q01114 | RH BAYAN | DU00003480925 | Sarawak | Sarawak | 3.117300 | 112.948940 |  | APR 24 |  | JUN 24 | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  | 15G 2+0 28MHz 1.2m/1.2m | Cancel / Drop | MW Swap Huawei 15G 2+0 28MHz NE: 1. Swap Existing Huawei IDU with new RTN910A 2. Swap Existing Huawei ODU with new XMC 5D 15GHz 2+0 28MHz ODU (Sub B) 3. Swap Existing Huawei Antenna with New Huawei 15GHz 1.2m DP MDD Antenna 4. Configure link as 15GHz 2+0 28MHz FE: 1. Swap Existing Huawei IDU with new RTN910A 2. Swap Existing Huawei ODU with new XMC 5D 15GHz 2+0 28MHz ODU (Sub B) 3. Swap Existing Huawei Antenna with New Huawei 15GHz 0.6m DP MDD Antenna 4. Configure link as 15GHz 2+0 28MHz | [7 empty] | Trintel | No PR required-Site drop/cancel |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
P00520-4839B | TESCO JELUTONG | DU00003480926 | Northern | Penang | 5.377956 | 100.315150 |  | MAY 25 | WK32-WK35 | AUG 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 1X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Swap | SWAP P00520-P00188 WITH HUAWEI_18GHZ_1+0_56MHZ_0.6M_4.37KM EXISTING CFG: HW_15G_1+0_28MHZ IMPACTED SITES: P00520 NE AT P00520: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 56MHZ 5. PATCH P00520 BBU TO NEW RTN 910A 6. DISMANTLE EXISTING P00520-P00188 (NT04968) LINK FE AT P00188: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 56MHZ 5. PATCH NEW RTN 910A TO CELCOM P00188 OB FIBER 6. DISMANTLE EXISTING P00520-P00188 (NT04968) LINK | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202408150460-GCI // SQ202504150095-GCI // SQ202508140739-GCI | 2025-11-26 | 2025-11-28 | Completed | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240801BH |  | 2024-08-09 | 2024-08-03 | Completed | 2024-08-08 | 2024-08-09 | 2024-08-02 | 2024-08-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-28 | 2024-10-31 | 2024-10-28 | 2024-11-07 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-10-28 | 2024-10-31 | 2024-10-28 | 2025-02-27 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-25 | 2024-10-14 | 2024-10-25 | 2024-10-15 | 2025-02-26 | SAFUAN//BIN YUSOFF/6800000178 | 2024-10-14 | 2024-10-25 | 2024-10-15 | 2024-10-28 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | NG HONG JIE7018000036 | Logistic Team | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358
Q01408-Q00067 | KG BT KITANG | DU00003480927 | Sarawak | Sarawak | 1.451182 | 110.282704 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Link has been decom under NIC | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4459B-A00460 | Kg Bakar Bata | DU00003480928 | Northern | Perak | 4.385900 | 100.789200 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop |  |  |  | Cancel / Drop | MW Swap completed under 4459B_PostMOCN | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
P00759-P00204 | DESARIA_PNG | DU00003480929 | Northern | Penang | 5.318512 | 100.264316 |  |  |  |  | RFS | Pending plan | ZTE | 00. Integrated/RFS Done | D1: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 23G 0.6M SP ANTENNA 1X 23G 112MHZ XMC-3 SUB B HI 1X 23G 112MHZ XMC-3 SUB B LO | MW Swap | SWAP EXISTING P00759-P00204 MW WITH HUAWEI_23GHZ_1+0_112MHZ_0.6M_1.14KM EXISTING MW CFG: 15GHZ_1+1_28MHZ. IMPACTED SITES: P00759 NE: P00759: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M SP ANTENNA 3. INSTALL NEW 1+0 23G 112MHZ XMC-3 SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 5. PATCH P00759 BBU TO NEW RTN 910A 6. DISMANTLE P00759-P00204 MW (NT05554) FE: P00204: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M SP ANTENNA 3. INSTALL NEW 1+0 23G 112MHZ XMC-3 SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 5. PATCH NEW RTN 910A TO CELCOM P00204 TM LL 6. DISMANTLE P00759-P00204 MW (NT05554) | [7 empty] | GCI | SQ202404030074-GCI | GCI | SQ202409100506-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240315AN |  | 2024-03-16 | 2024-03-19 | Completed | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-19 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-22 | 2024-03-31 | 2024-03-22 | 2024-03-22 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-03-22 | 2024-03-31 | 2024-03-22 | 2024-03-22 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-22 | 2024-03-31 | 2024-03-22 | 2024-03-23 | SAFUAN//BIN YUSOFF/6800000178 | 2024-10-17: 2024-03-22; 2024-10-23: 2024-03-31; 2024-10-23: 2024-03-22; 2024-10-23: 2024-03-22 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
A00852-A00458 | DESATERATAISBRGPRK | DU00003480930 | Northern | Perak | 4.132690 | 100.895600 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop |  |  |  | Cancel / Drop | Remain existing TX, current max utilization 62.3% out of 908Mbps | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Y00048-A00125 | EMOS PROTON CITY | DU00003480931 | Northern | Perak | 3.746830 | 101.520900 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Solution Provided Under DU00002850222 , cancel / Drop DU00003480931 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q00632-Q00254 | BT 16 BTU | DU00003480932 | Sarawak | Sarawak | 3.242440 | 113.220690 | WK17 | MAR 24 | WK18 | JUN 24 | 00. On air | Integrated/RFS done | ZTE | 00. Integrated/RFS Done | 5/6: D3: Cutover done 4/6: D2: TI done, Pending CO. Continue 5/6 21/5: Pending edotco PTW to enter site 15/5: Waveguide faulty. Replacement DO issued | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13GHz_1.8m/1.8m_DP_4+0_28MHz | MW Swap | MW Swap Huawei 13G 2+0 28MHz NE: 1. Swap Existing SM IDU with new RTN910A 2. Swap Existing SM ODU with new XMC 3 13GHz 4+0 28MHz ODU (Sub A + Sub A + Sub B + Sub B) 3. Swap Existing SM Antenna with New Huawei 13GHz 1.8m DP Antenna 4. Configure link as 13GHz 4+0 28MHz (256 QAM) FE: 1. Swap Existing SM IDU with new RTN910A 2. Swap Existing SM ODU with new XMC 3 13GHz 4+0 28MHz ODU (Sub A + Sub A + Sub B + Sub B) 3. Swap Existing SM Antenna with New Huawei 13GHz 1.8m DP Antenna 4. Configure link as 13GHz 4+0 28MHz (256 QAM) 5. Patch the new RTN 910A to the new CP Port | [7 empty] | Satellite | SQ202403220448-Satellite | YPTT | SQ202407020308-YPTT | 2024-03-15 | 2024-03-11 | Completed | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | RICK//JASON A/L DAVID/8217000004 |  | BINASAT DIGITAL SDN. BHD. |  | Unassigned | Completed |  | 2024-03-08 | 2024-03-15 | 2024-03-08 | 2024-03-08 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-08 | 2024-03-15 | 2024-03-08 | 2024-03-08 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2024-03-11 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24042386 |  | 2024-04-24 | 2024-04-27 | Completed | 2024-04-23 | 2024-04-24 | 2024-04-23 | 2024-04-27 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-08-29 | 2024-08-29 | 2024-08-28 | 2024-08-29 | NUR//AMIRAH FARHANA BINTI MOHAMAD BAKRI/6800000110 |  | 2024-06-04 | 2024-09-30 | 2024-06-04 | 2024-08-28 | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-06-04 | 2024-06-06 | 2024-06-04 | 2025-02-24 | NORAZHARI BIN MOHAMAD SALIM6794000032 | 2024-06-04 | 2024-06-06 | 2024-06-04 | 2024-06-05 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-09 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045
Q01599-Q00194 | KG NG BELALANG | DU00003480933 | Sarawak | Sarawak | 2.215897 | 111.925598 |  | APR 24 |  | JUN 24 | Drop | Pass to Huawei | ZTE | 03. TSS Only |  | TSS |  | 15G 4+0 28MHz 1.2m/1.2m MDD | MW Swap | MW Swap Huawei 15G 4+0 28MHz NE: 1. Swap Existing Huawei IDU with new RTN910A 2. Install New 2 pcs of ISM 8 Cards at Slot 3, 4 3. Swap Existing Huawei ODU with new XMC 5D 15GHz 4+0 28MHz ODU (Sub B) 4. Swap Existing Huawei Antenna with New Huawei 15GHz 1.2m DP MDD Antenna 5. Configure link as 15GHz 4+0 28MHz (EPLA) FE: 1. Swap Existing Huawei IDU with new RTN910A 2. Install New 2 pcs of ISM 8 Cards at Slot 3, 4 3. Swap Existing Huawei ODU with new XMC 5D 15GHz 4+0 28MHz ODU (Sub B) 4. Swap Existing Huawei Antenna with New Huawei 15GHz 1.2m DP MDD Antenna 5. Configure link as 15GHz 4+0 28MHz (EPLA) | [7 empty] | Trintel | SQ202409100111-Trintel |  |  | 2024-06-28 | 2024-06-24 | Completed | 2024-04-29 | 2024-04-30 | 2024-04-29 | 2024-04-30 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | 2024-06-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | 2024-06-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-06-24 | 2024-06-28 | 2024-06-24 | 2024-06-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
P00749-P00045 | TMN GAMBIR_PNG | DU00003480934 | Northern | Penang | 5.361378 | 100.293422 |  |  | WK13 | MAR 24 | RFS | Pending plan | ZTE | 00. Integrated/RFS Done | 29/3: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB A HI 1X 18G XMC-5D SUB A LO | MW Swap | SWAP EXISTING P00749-P00045 MW WITH HUAWEI_18G_2+0_55MHZ_0.6M_2.8KM EXISTING MW CFG: SM_15GHZ_2+0_28MHZ. IMPACTED SITES: P00749 NE: P00749: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB A 4. CONFIGURE LINK 18G 2+0 56MHZ 5. PATCH P00749 BBU TO NEW RTN 910A 6. DISMANTLE P00749-P00045 MW (NT05525) FE: P00045: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB A 4. CONFIGURE LINK 18G 2+0 56MHZ 5. PATCH NEW RTN 910A TO P00045 TM LL 6. DISMANTLE P00749-P00045 MW (NT05525) | [7 empty] | GCI | SQ202407010442-GCI | GCI | SQ202409100506-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-04-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24031218 |  | 2024-03-13 | 2024-03-19 | Completed | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-19 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-22 | 2024-03-31 | 2024-03-22 | 2024-04-02 | team41gcitechnicalteam41gcitechnical | GCI TI | 2024-03-22 | 2024-03-31 | 2024-03-22 | 2024-04-02 | team41gcitechnicalteam41gcitechnical | GCI TI | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-22 | 2024-03-31 | 2024-03-22 | 2024-03-30 | team41gcitechnicalteam41gcitechnical | 2024-03-22 | 2024-03-31 | 2024-03-22 | 2024-03-22 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
Q00612-Q00199 | KEM SEKAWIE | DU00003480935 | Sarawak | Sarawak | 2.518444 | 112.830920 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Pass to HW | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050655-GTSB | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | AB.RAHMAN//BIN MAT NOOH/6237001519
S00965-S00023 | UITMADMINHILL | DU00003480936 | Sabah | Sabah | 6.066116 | 116.139886 | WK17 | APR 24 | WK32-WK35 | AUG 24 |  |  | ZTE | 00. Integrated/RFS Done | 29/10: D2: Cutover done. Post-CO T/S ongoing 28/10: MOS & Pre-installation in progress | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_SP_1+0_56MHz | MW Swap | MW Swap Huawei 15G 1+0 0.6m&0.6m 28MHz to 23G 1+0 0.6M&0.6m 56MHz NE: 1. Swap new HW RTN910A. 2. Swap new HW SP antenna 23G 0.6m with existing antenna. 3. Swap new HW 23G ODU. 4. Configure link as 23G_1+0_56MHz. FE: 1. Swap new HW RTN910A. 2. Swap new HW SP antenna 23G 0.6m with existing antenna. 3. Swap new HW 23G ODU. 4. Configure link as 23G_1+0_56MHz. | [7 empty] | Seri Pancar | SQ202408220960-Seri Pancar | NR services | SQ202410280602-NR Services // SQ202504260199-NR Services | 2024-11-22 | 2024-11-19 | Completed | 2024-08-14 | 2024-09-20 | 2024-08-15 | 2024-08-15 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-15 | 2024-11-15 | 2024-10-02 | 2024-10-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-02 | 2024-10-04 | 2024-10-02 | 2024-10-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-19 | 2024-11-22 | 2024-11-19 | 2024-11-19 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241024AH |  | 2024-10-25 | 2024-10-25 | Completed | 2024-10-24 | 2024-10-25 | 2024-10-24 | 2024-10-25 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-28 | 2024-10-31 | 2024-10-27 | 2024-10-29 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-10-28 | 2024-10-31 | 2024-10-27 | 2024-10-29 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-10-28 | 2024-10-31 | 2024-10-27 | 2024-10-29 | RALPH O'BRYAN HILARY7167000030 | 2024-10-28 | 2024-10-31 | 2024-10-27 | 2024-10-28 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-20 | tseping//wang/6819000006 | Logistic Team | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
Q01057-Q00315 | JLN BUANG SIOL | DU00003480937 | Sarawak | Sarawak | 4.760365 | 115.006799 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Util max 50% | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01117-Q00254 | RH RANGGA | DU00003480938 | Sarawak | Sarawak | 3.089222 | 113.211667 | WK17 | DEC 24 |  | SEP 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done | 22/10: Pending Site DO 3/9: BoM Ready, Pending DO 16/8: No Material 8G 2.4m | TSS+AA+TI | L1+ATP+PAC | 8GHz_2.4m/2.4m_DP_4+0_29.65MHz | MW Parallel Link | MW Parallel Link Huawei 8GHz 4+0 29.65MHz NE: 1. Install New Huawei IDU RTN 910A 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Install New Huawei 8GHz 4+0 XMC 3 29.65MHz ODU (Sub A + Sub A + Sub B + Sub B) 4. Install New Huawei 8GHz 2.4m DP Antenna 5. Configure link as 8GHz 4+0 29.65MHz 6. Migrate Q01810, Q01812 traffic to this new link FE: 1. Install New Huawei IDU RTN 910A 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Install New Huawei 8GHz 4+0 XMC 3 29.65MHz ODU (Sub A + Sub A + Sub B + Sub B) 4. Install New Huawei 8GHz 2.4m DP Antenna 5. Configure link as 8GHz 4+0 29.65MHz 6. Patch the new RTN 910A to the new CP Port | [7 empty] | Satellite | SQ202403220448-Satellite | Trintel | SQ202502120283-Trintel // SQ202504260214-Trintel | 2024-03-15 | 2024-03-11 | Completed | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-05 | RICK//JASON A/L DAVID/8217000004 |  | BINASAT DIGITAL SDN. BHD. |  | Unassigned | Completed |  | 2024-03-08 | 2024-03-15 | 2024-03-08 | 2024-03-08 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-08 | 2024-03-15 | 2024-03-08 | 2024-03-08 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2024-03-11 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24122346 |  | 2024-12-24 | 2025-02-06 | Completed | 2024-12-23 | 2024-12-24 | 2024-12-23 | 2025-02-06 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-07 | 2025-02-15 | 2025-02-07 | 2025-02-10 | CHRISTINE IVY ANAK GIRIN7667000067 | Trintel TI | 2025-02-07 | 2025-02-15 | 2025-02-09 | 2025-02-13 | CHRISTINE IVY ANAK GIRIN7667000067 | Trintel TI | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-13 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-02-07 | 2025-02-15 | 2025-02-06 | 2025-02-24 | CHRISTINE IVY ANAK GIRIN7667000067 | 2024-10-17: 2025-02-07; 2024-10-23: 2025-02-15; 2024-10-23: 2025-02-06; 2024-10-23: 2025-02-17 |  |  | 2025-04-22 | 2025-05-22 | 2025-04-22 | 2025-04-22 | IDA//NAJEEHA BINTI MAZLAN/7018000019
Q01858-Q00215 | JLN WAWASAN | DU00003480940 | Sarawak | Sarawak | 2.326036 | 111.809366 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  | 2X ISM8 2x 1.2m MDD Antenna (15G) 1x ODU 15G XMC-5D sb A Hi 1x ODU 15G XMC-5D sb A_Lo | Cancel / Drop | Build new mw link A00572-4455B with Huawei_15G_2+0_28mhz_512QAM_448Mbps_1.2/1.2m_MDD_XMC-5D sb A_3.83km. This link will be parallel with existing 18G_1+0. Config EPLA between 18G and 15G Impact site: Q01858 | NE: 1. Install new ISM8 to existing RTN910A 2. Install new 15G 1.2m MDD Antenna 3. Install new 15G XMC-5D sb A 4. Configure link 15G 2+0_28MHZ_512QAM 5. Config EPLA with existing link 18G_1+0 | FE: 1. Install new ISM8 to existing RTN910A 2. Install new 15G 1.2m MDD Antenna 3. Install new 15G XMC-5D sb A 4. Configure link 15G 2+0_28MHZ_512QAM 5. Config EPLA with existing link 18G_1+0 | XMC-5D | MDD | 15G | 1.2m | 1.2m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050656-GTSB | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q00675-Q00509 | BT 46 BTU MYY | DU00003480941 | Sarawak | Sarawak | 3.450041 | 113.557902 |  | APR 24 |  |  | Drop | Pass to Huawei | ZTE | 03. TSS Only |  | TSS |  | 15G 4+0 28MHz 1.2m/1.2m MDD | MW Swap | "MW Swap Huawei 15G 4+0 28MHz NE: 1. Swap Existing Huawei IDU with new RTN910A 2. Install New 2 pcs of ISM 8 Cards at Slot 3, 4 3. Swap Existing Huawei ODU with new XMC 5D 15GHz 4+0 28MHz ODU (Sub A) 4. Swap Existing Huawei Antenna with New Huawei 15GHz 1.2m DP MDD Antenna 5. Configure link as 15GHz 4+0 28MHz (EPLA) FE: 1. Swap Existing Huawei IDU with new RTN910A 2. Install New 2 pcs of ISM 8 Cards at Slot 3, 4 3. Swap Existing Huawei ODU with new XMC 5D 15GHz 4+0 28MHz ODU (Sub A) 4. Swap Existing Huawei Antenna with New Huawei 15GHz 1.2m DP MDD Antenna 5. Configure link as 15GHz 4+0 28MHz (EPLA)" | [7 empty] | Trintel | SQ202409100111-Trintel |  |  | 2024-05-03 | 2024-05-03 | Completed | 2024-04-29 | 2024-04-30 | 2024-04-29 | 2024-04-30 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300154-GTSB
9135A-Q00169 | Zeninth Minth Cinema | DU00003480942 | Sarawak | Sarawak | 2.306658 | 111.836803 |  |  |  |  | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | Cutover done | AA | PAC |  | MW Remote Upgrade | MW Remote Upgrade 56Mhz to 112Mhz | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | C.PRATHABAN///6798000081 | [17 empty] | 2024-09-26 | 2024-10-26 | 2024-09-26 | 2024-09-26 | ASTI//GANIS PUTRIANI/6237001358
Q01626-Q00264 | RH GEMAT | DU00003480943 | Sarawak | Sarawak | 3.134128 | 112.982640 |  | APR 24 |  | JUN 24 | Drop | Pass to Huawei |  | 03. TSS Only |  | TSS |  | 15G 4+0 28MHz 1.2m/1.2m MDD | MW Hardware Upgrade | MW Hardware Upgrade Huawei 15G 4+0 CA 28MHz NE: 1. Reused existing Huawei IDU RTN910A. 2. Install New 2 pcs of ISM 8 Cards at Slot 3, 4 3. Transfer IF Cable from SLot 7-ISM8-1 to Slot 3-ISM8-1 4. Transfer IF Cable from SLot 7-ISM8-2 to Slot 4-ISM8-1 5. Reuse Existing Huawei Antenna Huawei 15GHz 1.2m DP MDD Antenna 6. Configure link as 15GHz 4+0 CA 28MHz (EPLA) FE: 1. Reused existing Huawei IDU RTN910A. 2. Install New 2 pcs of ISM 8 Cards at Slot 3, 4 3. Transfer IF Cable from SLot 7-ISM8-1 to Slot 3-ISM8-1 4. Transfer IF Cable from SLot 7-ISM8-2 to Slot 4-ISM8-1 5. Reuse Existing Huawei Antenna Huawei 15GHz 1.2m DP MDD Antenna 6. Configure link as 15GHz 4+0 CA 28MHz (EPLA) | [7 empty] | Trintel | SQ202409100111-Trintel |  |  | 2024-05-03 | 2024-05-03 | Completed | 2024-04-23 | 2024-04-24 | 2024-04-23 | 2024-04-24 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q00469-Q00267 | BT 39 BTU | DU00003480944 | Sarawak | Sarawak | 3.406597 | 113.493997 | WK18 | MAR 24 | WK32-WK35 | AUG 24 | TI WIP | Pending PTW approval | ZTE | 00. Integrated/RFS Done | 27/11: Rectifiy L1 & alarm clearance - replan 28/10: D6: Cutover done. Post-CO T/S ongoing 7/10: Reported sited vandalisme Q00469, Police report lodge 9/5: D1: NE installation complete. FE pending edotco PTW approval (TP review) | TSS+AA+TI | L1+ATP+PAC | 13GHz_1.8m/1.8m_MDD_4+0_28MHz | MW Parallel Link | MW Parallel Link Huawei 13GHz 4+0 28MHz NE: 1. Install New Huawei IDU RTN 910A 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Install New Huawei 13GHz 4+0 XMC 5D 28MHz ODU (Sub A) 4. Install New Huawei 13GHz 1.8m MDD Antenna 5. Configure link as 13GHz 4+0 28MHz 6. Patch the new RTN 910A to the new CP Port 7. Additional IDU patching from SM IDU Q00469 link toward Q01892 Patch to new link huawei idu ,to load balance and split services to new link. FE: 1. Install New Huawei IDU RTN 910A 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Install New Huawei 13GHz 4+0 XMC 5D 28MHz ODU (Sub A) 4. Install New Huawei 13GHz 1.8m MDD Antenna 5. Configure link as 13GHz 4+0 28MHz 6. Migrate Q01892, Q01814, 9353B traffic to this new link | [7 empty] | Datasco | SQ202403220440-Datasco | YPTT | SQ202408140610-YPTT | 2024-03-22 | 2024-03-19 | Completed | 2024-03-11 | 2024-03-15 | 2024-03-14 | 2024-03-15 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. |  | Unassigned | Completed |  | 2024-03-19 | 2024-03-22 | 2024-03-19 | 2024-03-19 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-19 | 2024-03-22 | 2024-03-19 | 2024-03-19 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-19 | 2024-03-22 | 2024-03-19 | 2024-03-19 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24042385 |  | 2024-04-24 | 2024-05-04 | Completed | 2024-04-23 | 2024-04-24 | 2024-04-23 | 2024-05-04 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-10-24 | 2024-11-08 | 2024-10-25 | 2024-12-15 | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2024-10-24 | 2024-11-08 | 2024-10-25 | 2024-11-28 | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2024-10-28 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-10-24 | 2024-11-08 | 2024-10-25 | 2024-12-06 | NORAZHARI BIN MOHAMAD SALIM6794000032 | 2024-10-17: 2024-10-24; 2024-10-23: 2024-11-08; 2024-10-23: 2024-10-25; 2024-10-23: 2024-12-04 |  |  | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045
Q01815-Q00675 | LDG RUAI | DU00003480947 | Sarawak | Sarawak | 3.460504 | 113.618871 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | 9Aug - HU drop. Closed |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050656-GTSB | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q01613-Q00130 | KG MAMBONG | DU00003480949 | Sarawak | Sarawak | 1.360301 | 110.347695 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop |  |  |  | Cancel / Drop | Link CT10582 to decom | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
B01469-B01707 | UIA8 | DU00003480950 | Central | Selangor | 3.248900 | 101.737100 | WK13 | MAY 24 | WK32-WK35 | AUG 24 | RFS | Pending L1 | ZTE | 00. Integrated/RFS Done | 14/9: D4: Cutover done. Post-CO T/S WIP 28/8: Pending T/shooting due need CR approved by CD 12/8: D3: TI done, no signal/RSL low. T/shooting antenna suspect faulty | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1) 1 x RTN910A 2) 1 x XMC3 112MHz Sub A Hi 3) 1 x 23G 1.2m SP FE: 1) 1 x RTN910A 2) 1 x XMC3 112MHz Sub A Lo 3) 1 x 23G 1.2m SP | MW New Link / Reroute | Replace existing B01469-B01707 1+0 56MHz with B01469-2012B 1+0 112MHz Impacted sites: B01469 NE (B01469): 1) Install new RTN910A (ops team to assign RTN number 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom link B01469-B01707 FE (2012B): 1) Install new RTN910A (ops team to assign RTN number 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom link B01469-B01707 | [7 empty] | Allstar | SQ202408220872-Allstar | Allstar | SQ202408140500-Allstar | 2024-09-28 | 2024-09-27 | Completed | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-07 | 2024-08-08 | 2024-08-07 | 2024-08-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-04 | 2024-09-05 | 2024-09-04 | 2024-09-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-27 | 2024-09-28 | 2024-09-27 | 2024-09-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO req by Hady | 2024-08-07 | 2024-08-23 | Completed | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-08-23 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-08 | 2024-08-31 | 2024-08-07 | 2024-08-08 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | Allstar TI | 2024-08-08 | 2024-08-31 | 2024-08-07 | 2024-09-23 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | Allstar TI | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-14 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-08-28 | 2024-08-31 | 2024-08-28 | 2025-01-16 | NAVUKKARASON//A/L KALAIVANAN/6237000881 | 2024-08-08 | 2024-08-31 | 2024-08-07 | 2024-08-08 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | NG HONG JIE7018000036 | Logistic Team | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
B02715-B01461 | PSRNBESTARISK7_SHAHALAM | DU00003480951 | Central | Selangor | 3.074991 | 101.486400 | WK13 | MAY 24 | WK18 | MAY 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 2/5: D2: Cutover done 30/4: D1: MOS & TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112MHZ_0.6M/0.6M_512QAM_SUB A & B | MW Swap | MW SWAP MW LINK B02715-B01461 HW CT10103 WITH HUAWEI_18G_2+0_112MHZ_0.6M/0.6M_512QAM_SUB A & B NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | MTK | SQ202407050120-MTK | MTK | SQ202407050174-MTK | 2024-08-03 | 2024-08-02 | Completed | 2024-04-30 | 2024-05-06 | 2024-05-06 | 2024-05-06 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. |  | Unassigned | Completed |  | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-07-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-07-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-02 | 2024-08-03 | 2024-08-02 | 2024-08-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24041858 |  | 2024-04-19 | 2024-04-26 | Completed | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-26 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-29 | 2024-04-30 | 2024-04-29 | 2024-05-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-04-29 | 2024-05-08 | 2024-04-29 | 2024-05-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | C.PRATHABAN///6798000081 |  |  | 2024-04-29 | 2024-04-30 | 2024-04-29 | 2024-05-05 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-04-29 | 2024-04-30 | 2024-04-29 | 2024-05-04 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-16 | NG HONG JIE7018000036 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
Q00238-Q00181 | JLN CAUSEWAY | DU00003480952 | Sarawak | Sarawak | 2.290620 | 111.826040 |  | APR 24 |  |  | Drop | Pass to Huawei | ZTE | 03. TSS Only |  | TSS |  | 23G 1+0 112MHz 0.6m/0,6m | MW Swap | MW Swap Huawei 23G 1+0 112MHz 0.6m/0.6m NE: 1. Swap Existing Huawei IDU with new RTN910A 2. Swap Existing Huawei ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 3. Swap Existing Huawei Antenna with New Huawei 23GHz 0.6m DP MS Antenna 4. Configure link as 23GHz 1+0 112MHz FE: 1. Swap Existing Huawei IDU with new RTN910A 2. Swap Existing Huawei ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 3. Swap Existing Huawei Antenna with New Huawei 23GHz 0.6m DP MS Antenna 4. Configure link as 23GHz 1+0 112MHz | [7 empty] | Trintel | SQ202409100111-Trintel |  |  | 2024-05-09 | 2024-05-03 | Completed | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-05-02 | 2024-05-09 | 2024-05-02 | 2024-05-03 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 | Trintel TI | TRINTEL (M) SDN. BHD. |  | Assigned | Completed |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
A00249-A00301 | TMPANGKOR | DU00003480953 | Northern | Perak | 4.212800 | 100.574500 |  |  | W49-52 | DEC 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done | 14/10: Pending Site DO | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 18G 1.2M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Swap | SWAP EXISTING A00249-A00301 MW WITH HUAWEI_18G_1+0_112MHZ_1.2M_4.64KM EXISTING MW CFG: HW_15GHZ_2+0_28MHZ. IMPACTED SITES: A00249 NE: A00249: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. PATCH A00249 BBU TO NEW RTN 910A 6. DISMANTLE A00249-A00301 MW (NT06165) FE: A00301: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. PATCH NEW RTN 910A TO A00301 TM LL 6. DISMANTLE A00249-A00301 MW (NT06165) | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202505020423-GCI // SQ202505020426-GCI // SQ202508140739-GCI | 2025-08-09 | 2025-08-12 | Completed | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-08 | 2025-08-09 | 2025-08-08 | 2025-08-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112592 |  | 2024-03-13 | 2024-03-18 | Completed | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2025-03-26 | 2025-03-31 | 2025-03-26 | 2025-04-18 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | GCI TI | 2025-03-26 | 2025-03-31 | 2025-03-26 | 2025-04-26 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | GCI TI | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-18 | 2025-03-26 | 2025-03-31 | 2025-03-26 | 2025-05-05 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | 2024-10-17: 2025-03-26; 2024-10-23: 2025-03-31; 2024-10-23: 2025-03-26; 2024-10-23: 2025-05-07 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202508150516-GCI | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
B00572-B00542 | BT11_CHRS | DU00003480954 | Central | Selangor | 3.042114 | 101.780633 |  | MAR 24 | WK14 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 19/4: Cutover done 17/4: Req PMSC for Celcom | TSS+TI | L1+ATP+PAC |  | BBU Patching | BBU PATCHING TO USE B00572 TM NGBH 10000Mbps FIBER | [7 empty] | MTK | SQ202407050120-MTK | MTK | SQ202407050174-MTK | 2024-06-21 | 2024-06-25 | Completed | 2024-04-25 | 2024-04-25 | 2024-04-25 | 2024-04-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. |  | Unassigned | Completed |  | 2024-06-12 | 2024-06-13 | 2024-06-12 | 2024-06-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-06-12 | 2024-06-13 | 2024-06-12 | 2024-06-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-06-20 | 2024-06-21 | 2024-06-20 | 2024-06-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24040201 |  | 2024-04-03 | 2024-04-03 | Completed | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-18 | 2024-04-30 | 2024-04-18 | 2024-04-23 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2024-04-18 | 2024-04-30 | 2024-04-18 | 2024-04-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-04-18 | 2024-04-30 | 2024-04-18 | 2024-04-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | 2024-10-17: 2024-04-18; 2024-10-23: 2024-04-30; 2024-10-23: 2024-04-18; 2024-10-23: 2024-04-19 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
W01442-W00145 | BT41_4_JLNGOMBAK | DU00003480955 | Central | Kuala Lumpur | 3.205463 | 101.701785 | WK13 | MAY 24 | WK19 | JUN 24 | Cancel / Drop | Site has been decom | ZTE | 03. TSS Only | 16/7: Site decom. Not proceed | TSS |  | 23G_1+0_112MHZ_0.6M/0.6M_512QAM_SUB B | MW Swap | MW SWAP MW LINK W01442-W00145 WITH HUAWEI_23G_1+0_112MHZ_0.6M/0.6M_512QAM_SUB B NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | Perwira | SQ202409100192-Perwira | Perwira | No PR required-Work at TSS only | 2024-08-03 | 2024-08-02 | Completed | 2024-04-03 | 2024-04-03 | 2024-04-04 | 2024-04-04 | Muhammad//Norfikri Bin Ramlee/7238000003 |  | PERWIRA ENERGY SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-02 | 2024-07-03 | 2024-07-02 | 2024-07-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-02 | 2024-07-03 | 2024-07-02 | 2024-07-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-02 | 2024-08-03 | 2024-08-02 | 2024-08-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24041860 |  | 2024-04-19 | 2024-05-02 | Completed | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-05-02 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-15 | 2024-05-22 |  |  | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI
Q00220-Q00169 | JLN KG DATU | DU00003480956 | Sarawak | Sarawak | 2.293900 | 111.821900 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Cancle passed to HW | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050656-GTSB | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | HSU//MYET CHAE/6799000011
A00687-A00044 | V_POINT_G9 | DU00003480957 | Northern | Perak | 4.679900 | 101.043300 |  |  | WK14 | APR 24 | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | 3/4: D1: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 15G 0.6M MDD ANTENNA 1X 15G XMC-5D SUB B HI 1X 15G XMC-5D SUB B LO | MW Swap | SWAP A00687-A00044 WITH HUAWEI_15GHZ_2+0_28MHZ_0.6M_3.68KM. IMPACTED SITES: A00687 NE: A00687: 1. INSTALL NEW RTN 910A 2. INSTALL 15G 0.6M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 5. PATCH A00687 BBU TO NEW RTN 910A 6. DISMANTLE EXISTING LINK FE: A00044: 1. INSTALL NEW RTN 910A 2. INSTALL 15G 0.6M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 5. PATCH NEW RTN 910A TO A00044 OB FIBER 6. DISMANTLE EXISTING LINK | [7 empty] | GCI | SQ202404030074-GCI | GCI | SQ202409100506-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240315AO |  | 2024-03-16 | 2024-03-18 | Completed | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-31 | 2024-04-06 | 2024-03-31 | 2024-04-18 | MAT//SAFAREED BIN MAT DESA/6800000177 | GCI TI | 2024-03-31 | 2024-06-30 | 2024-03-31 | 2024-08-27 | MAT//SAFAREED BIN MAT DESA/6800000177 | GCI TI | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-04-03 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-31 | 2024-04-06 | 2024-03-31 | 2024-04-07 | MAT//SAFAREED BIN MAT DESA/6800000177 | 2024-10-17: 2024-03-31; 2024-10-23: 2024-04-06; 2024-10-23: 2024-03-31; 2024-10-23: 2024-04-01 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
Q01350-Q00110 | TMN UNI | DU00003480959 | Sarawak | Sarawak | 1.463440 | 110.412150 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050656-GTSB | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | HSU//MYET CHAE/6799000011
Q01087-Q00620 | KG HIJRAH | DU00003480960 | Sarawak | Sarawak | 2.296400 | 111.915100 |  | APR 24 |  |  | Drop | Pass to Huawei | ZTE | 00. Site Out/Drop |  | TSS |  | 18G 1+0 110MHz 1.2m/1.2m MDD | MW Swap | "MW Swap Huawei 18G 1+0 110MHz NE: 1. Swap Existing Huawei IDU with new RTN910A 2. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub A) 3. Swap Existing Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 4. Configure link as 18GHz 1+0 110MHz FE: 1. Swap Existing Huawei IDU with new RTN910A 2. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub A) 3. Swap Existing Huawei Antenna with New Huawei 18GHz 1.2m DP MDD Antenna 4. Configure link as 18GHz 1+0 110MHz" | [7 empty] | Trintel | SQ202411190747-Trintel |  |  | 2024-05-24 | 2024-05-21 | Completed | 2024-04-24 | 2024-04-25 | 2024-04-24 | [5 empty] | Unassigned | Disabled |  | 2024-05-21 | 2024-05-24 | 2024-05-21 | 2024-05-21 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-21 | 2024-05-24 | 2024-05-21 | 2024-05-21 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-21 | 2024-05-24 | 2024-05-21 | 2024-05-21 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01892-Q00469 | DESA LAVANG | DU00003480961 | Sarawak | Sarawak | 3.374260 | 113.602600 | WK10 | MAR 24 | WK32-WK35 | AUG 24 | Planning | Pending DO | ZTE | 00. Integrated/RFS Done | 30/10: Cutover done. Post-CO T/S ongoing 16/10: Waiting link Q00469-Q00267 ready for CO 7/9: TI done, Pending CO due upperlink not ready (Q00469-Q00267) 27/8: D3: TI done. Continue configure & alignment 6/6: SRF Approved @Q01892 UPG-797458 | TSS+AA+TI | L1+ATP+PAC | 13G 2+0 ODU XMC-3 Sub band B x 2, Sub band A x 2, A13D12MAC-3NX x 1, A13D18MAC-3NX x 1, RTN910AF x 2 | MW New Link / Reroute | NE: Install: 1. Antenna: Install 13G 1.2m DP A13D12MAC-3NX x 1 2. ODU: Install XMC-3 28MHz Sub-band B x 1, Sub-band A x 1 3. IDU: Install RTN910A x 1 4. IF card: Built-in SLot 7 5. IF cable: Connect IF cable x 2 from ODUs to Slot 7-1, 7-2 6. Configure Link: 13G 2+0 ePLA 28MHz 450Mbps 7. BBU: Re-patch Q01892 to the new RTN 910A IDU Dismantle: None FE: Install: 1. Antenna: Install 13G 1.8m DP A13D18MAC-3NX x 1 2. ODU: Install XMC-3 28MHz Sub-band B x 1, Sub-band A x 1 3. IDU: Install RTN910A x 1 4. IF card: Built-in SLot 7 5. IF cable: Connect IF cable x 2 from ODUs to Slot 7-1, 7-2 6. Configure Link: 13G 2+0 ePLA 28MHz 450Mbps 7. Patch the new IDU to SM backhaul and migrate Q01892 BBU into the new link Dismantle: None | [7 empty] | Satellite | SQ202403220448-Satellite | Allstar | SQ202408220991-Allstar // SQ202408260929-Allstar | 2024-03-15 | 2025-11-04 | Completed | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | RICK//JASON A/L DAVID/8217000004 |  | BINASAT DIGITAL SDN. BHD. |  | Unassigned | Completed |  | 2024-03-08 | 2024-03-15 | 2024-03-08 | 2025-11-04 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Unassigned | Completed |  | 2024-03-08 | 2024-03-15 | 2024-03-08 | 2024-10-21 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Unassigned | Completed |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2024-04-01 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240801AB |  | 2024-08-02 | 2024-08-09 | Completed | 2024-08-01 | 2024-08-02 | 2024-08-01 | 2024-08-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-14 | 2024-08-20 | 2024-10-30 | 2024-10-30 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2024-08-14 | 2024-08-20 | 2024-08-13 | 2024-10-30 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2024-09-06 | 2024-10-30 | 2024-10-30 | 2024-10-30 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-08-14 | 2024-08-20 | 2024-11-02 | 2024-11-02 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | 2024-10-17: 2024-08-14; 2024-10-23: 2024-08-20; 2024-10-23: 2024-08-26; 2024-10-23: 2024-08-26 |  |  | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045
Q01884-Q01123 | SAMARAKAN NURSERY | DU00003480962 | Sarawak | Sarawak | 2.934380 | 113.121400 | WK16 | MAR 24 | WK19 | MAY 24 | RFS | Site Vandalized | ZTE | 00. Integrated/RFS Done | 23/5: D3: Cutover done 17/5: Power restored to site after vandalised. Plan to continue after Q00632 complete. 7/5: Site vandalised. Pending power restoration (MSP) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13GHz_1.8m/1.8m_DP_2+0_28MHz | MW Swap | MW Swap Huawei 13G 2+0 28MHz NE: 1. Swap Existing Huawei IDU with new RTN910A 2. Swap Existing Huawei ODU with new XMC 3 13GHz 2+0 28MHz ODU (Sub A + Sub B) 3. Swap Existing SP Huawei Antenna with New Huawei 13GHz 1.8m DP Antenna 4. Configure link as 13GHz 2+0 28MHz (256 QAM) FE: 1. Swap Existing Huawei IDU with new RTN910A 2. Swap Existing Huawei ODU with new XMC 3 13GHz 2+0 28MHz ODU (Sub A + Sub B) 3. Swap Existing SP Huawei Antenna with New Huawei 13GHz 1.8m DP Antenna 4. Configure link as 13GHz 2+0 28MHz (256 QAM) | [7 empty] | Datasco | SQ202403220440-Datasco | YPTT | SQ202407020308-YPTT | 2024-03-22 | 2024-03-20 | Completed | 2024-03-11 | 2024-03-15 | 2024-03-14 | 2024-03-15 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. |  | Unassigned | Completed |  | 2024-03-19 | 2024-03-22 | 2024-03-19 | 2024-03-19 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-19 | 2024-03-22 | 2024-03-19 | 2024-03-19 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-20 | 2024-03-22 | 2024-03-20 | 2024-03-20 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24042388 |  | 2024-04-24 | 2024-04-27 | Completed | 2024-04-23 | 2024-04-24 | 2024-04-23 | 2024-04-27 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2024-08-29 | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2024-05-02 | 2024-05-30 | 2024-08-26 | 2025-09-22 | HERALD GELMA ANAK JIFFERY7019000017 | YPTT TI | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-12-16 | 2024-12-31 | 2024-12-16 | 2024-12-23 | FREDRICK TUAH ANAK EDMUND6794000054 | 2024-10-17: 2024-12-16; 2024-10-23: 2024-12-31; 2024-10-23: 2024-12-16; 2024-10-23: 2024-12-23 |  |  | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045
B02274-B00545 | SURAU_AR_RAHIMAH_SEK2_P_ALAM | DU00003480963 | Central | Selangor | 3.218560 | 101.433610 | WK19 | MAY 24 | WK19 | MAY 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 1/6: D2: Cutover done 31/5: D1: TI NE done, Pending FE | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112MHZ_0.6M/0.6M_256QAM_SUB A | MW Swap | MW SWAP MW LINK B02274-B00545 HW CT08430 WITH HUAWEI_18G_1+0_112MHZ_0.6M/0.6M_256QAM_SUB A NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | MTK | SQ202407050120-MTK | MTK | SQ202407050174-MTK | 2024-08-03 | 2024-08-02 | Completed | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2024-06-07 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-18 | 2024-07-19 | 2024-07-18 | 2024-07-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-18 | 2024-07-19 | 2024-07-18 | 2024-07-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-02 | 2024-08-03 | 2024-08-02 | 2024-08-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24051826 |  | 2024-05-19 | 2024-05-27 | Completed | 2024-05-18 | 2024-05-19 | 2024-05-18 | 2024-05-27 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-30 | 2024-05-31 | 2024-05-30 | 2024-06-07 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-05-30 | 2024-05-31 | 2024-05-30 | 2024-06-07 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-10 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-05-30 | 2024-05-31 | 2024-05-30 | 2024-06-05 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-05-30 | 2024-05-31 | 2024-05-30 | 2024-06-01 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-06-26 | NG HONG JIE7018000036 | Logistic Team | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358
S00994-S00989 | KAMPUNG SINULIHAN | DU00003480964 | Sabah | Sabah | 5.297480 | 116.393120 | WK17 | APR 24 | WK20 | MAY 24 | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | 17/5: Cutover done | TSS+AA+TI | L1+ATP+PAC | 15GHz_1.2m/1.2m_MDD_4+0_28MHz | MW Hardware Upgrade | MW Hardware upgrade Huawei 15G 2+0 1.2m&1.2m 28MHz to 15G 4+0 1.2m&1.2m 28MHz NE: 1. Reuse existing RTN910A . 2. Install new 2xISM_8 at Slot 3 and 4. 3. Remain Antenna HW 1.2m MDD 4. Remain existing ODU. 5. Configure link as 15GHz 4+0 28MHz_CA. FE: 1. Reuse existing RTN910A . 2. Install new 2xISM_8 at Slot 3 and 4. 3. Remain Antenna HW 1.2m MDD. 4. Remain existing ODU. 5. Configure link as 15GHz 4+0 28MHz_CA. | [7 empty] | Seri Pancar | SQ202411140366-Seri Pancar | Magicell | SQ202409120165-Magicell | 2025-10-24 | 2025-10-24 | Completed | 2024-04-22 | 2024-04-26 | 2024-04-25 | 2024-04-25 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-02 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-02 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24051334 |  | 2024-05-14 | 2024-05-14 | Completed | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-14 | 2024-05-31 | 2024-05-13 | 2024-05-18 | SONLEE//BERNABAS/7018000158 | Magicell TI | 2024-05-14 | 2024-05-31 | 2024-05-13 | 2024-05-18 | SONLEE//BERNABAS/7018000158 | Magicell TI | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2024-09-04 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-05-14 | 2024-05-31 | 2024-05-13 | 2024-06-15 | SONLEE//BERNABAS/7018000158 | 2024-10-17: 2024-05-14; 2024-10-23: 2024-05-31; 2024-10-23: 2024-05-13; 2024-10-23: 2024-06-13 |  |  | 2024-11-30 | 2024-12-30 | 2024-11-30 | 2024-11-30 | ASTI//GANIS PUTRIANI/6237001358
Q00972-Q00655 | KG TG ASSAM | DU00003480965 | Sarawak | Sarawak | 1.467000 | 111.409400 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU | TSS+TI | L1+ATP+PAC | 1 x SFP 1km and patch cord | MW IDU Patching | IDU SW03668 Q00655 PKN SPAOH - Q00972 KPG TG ASSAM GE1 port to PTN having congestion. To offload 2 sites (Q01584,Q01559) to new PTN port NE (Q00972): 1) Remain existing FE (IDU SW03668 Q00655 PKN SPAOH - Q00972 KPG TG ASSAM): 1) Patch GE5 (optical) to new PTN port 2) Transfer sites Q01584,Q01559 to new PTN port | NE (Q00972): 1) Remain existing | FE (IDU SW03668 Q00655 PKN SPAOH - Q00972 KPG TG ASSAM): 1) Patch GE5 (optical) to new PTN port 2) Transfer sites Q01584,Q01559 to new PTN port | [5 empty] | NR Services | SQ202504220166-NR Services | NR Services | SQ202504210230-NR Services // SQ202504260213-NR Services |  |  | Ongoing | [8 empty] | Unassigned | Not started |  | 2025-05-07 | 2025-05-08 | 2025-05-07 | 2025-05-08 | DINESH SINGH CHEEMA7167000003 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25022566 |  | 2025-02-26 | 2025-03-17 | Completed | 2025-02-25 | 2025-02-26 | 2025-02-25 | 2025-03-17 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-25 | HADYNATA BIN HARUN7167000010 | NR Service TI | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-28 | HADYNATA BIN HARUN7167000010 | NR Service TI | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-14 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-05-05 | HADYNATA BIN HARUN7167000010 | 2024-10-17: 2025-04-14; 2024-10-23: 2025-04-14; 2024-10-23: 2025-04-14; 2024-10-23: 2025-04-14 |  |  | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
B00437-B00723 | TMN_DAHLIA | DU00003480966 | Central | Selangor | 2.831400 | 101.725000 | WK17 | MAY 24 | WK32-WK35 | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 30/8: D1: Cutover done 19/8: Pending Edotco PTW approval (NE: AC-818169, FE: AC-818176) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW Swap | MW SWAP MW LINK B00437-B00723 CT08636 WITH HUAWEI_18G_2+0_112MHZ_0.6M/0.6M_512QAM_SUB A NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | Perwira | SQ202407050123-Perwira | GTSB | SQ202408140515-GTSB | 2024-06-26 | 2024-06-25 | Completed | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | WB80041943 |  | PERWIRA ENERGY SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-06-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-06-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-06-25 | 2024-06-26 | 2024-06-25 | 2024-06-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24041703 |  | 2024-04-18 | 2024-05-02 | Completed | 2024-04-17 | 2024-04-18 | 2024-04-17 | 2024-05-02 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-08-31 | 2024-09-30 | 2024-09-23 | 2024-09-23 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2024-09-02 | 2024-09-30 | 2024-09-23 | 2024-09-23 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-08-31 | SHUJAAT//ALI/6800000124 |  |  | 2024-08-31 | 2024-09-30 | 2024-09-02 | 2024-09-02 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2024-08-31 | 2024-09-30 | 2024-09-02 | 2024-09-02 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | NG HONG JIE7018000036 | Logistic Team | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
B02329-B00440 | PORT KLANG 2 | DU00003480967 | Central | Selangor | 2.992980 | 101.408550 |  |  | WK17 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 5/4: Cutover done 4/4: D1: MOS & TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112MHZ_0.6M/0.6M_256QAM_SUB A | MW Swap | MW SWAP MW LINK B02329-B00440 HW CT09199 WITH HUAWEI_18G_2+0_112MHZ_0.6M/0.6M_256QAM_SUB A NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | MTK | SQ202404170286-MTK | MTK | SQ202409110359-MTK | 2024-08-03 | 2024-08-02 | Completed | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. |  | Unassigned | Completed |  | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2024-04-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2024-04-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-08-02 | 2024-08-03 | 2024-08-02 | 2024-08-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24040202 |  | 2024-04-03 | 2024-04-03 | Completed | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-04 | 2024-04-30 | 2024-04-04 | 2024-04-18 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-04-04 | 2024-04-30 | 2024-04-04 | 2024-04-23 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-04-05 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-04-04 | 2024-04-30 | 2024-04-04 | 2024-04-25 | RIDHUAN//BIN MANSOR/8225000011 | 2024-04-04 | 2024-04-30 | 2024-04-04 | 2024-04-25 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | NG HONG JIE7018000036 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
4936A-4770A | Bandar Perdana | DU00003822877 | Northern | Kedah | 5.606120 | 100.507410 | [7 empty] | 00. Integrated/RFS Done | 249/: D2: Cutover done. Post-CO T/S WIP 23/9: MOS & Pre-installation WIP. Continue 24/9 | TSS+AA+TI | L1+ATP+PAC | 15G 2+0 1.2m/1.2m DP NE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Lo 3) 1x15GHz XMC3 Sub B Lo 4) 1x15GHz 1.2m DP FE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Hi 3) 1x15GHz XMC3 Sub B Hi 4) 1x15GHz 1.2m DP | MW Parallel Link | Existing link 4936A-4770A 2+0 (4936A RTN01-4770A RTN05) Add parallel 2+0 Final config will be 4+0 Impact site: 4936A NE (4936A RTN01) 1. Add ISM8 at RTN01 slot 3 2. Install new 2+0 link at RTN01 3-ISM8 3. Create 4+0 EPLA FE (4770A RTN05) 1. Add ISM8 at RTN05 slot 3 2. Install new 2+0 link at RTN01 3-ISM8 3. Create 4+0 EPLA | [7 empty] | CCSMY | SQ202410010443-CCS | CCSMY | SQ202410010451-CCS | 2025-08-14 | 2025-08-14 | Completed | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2024-09-29 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24090944 |  | 2024-09-10 |  | Ongoing | 2024-09-09 | 2024-09-10 | 2024-09-09 |  | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2024-09-23 | 2024-09-30 | 2024-09-23 | 2024-09-25 | TAIB//MUHAMMAD/7021000060 | CCS TI | 2024-09-23 | 2024-09-30 | 2024-09-23 | 2024-09-25 | TAIB//MUHAMMAD/7021000060 | CCS TI | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-24 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-09-23 | 2024-09-30 | 2024-09-23 | 2024-09-28 | TAIB//MUHAMMAD/7021000060 | 2024-10-17: 2024-09-23; 2024-10-23: 2024-09-30; 2024-10-23: 2024-09-23; 2024-10-23: 2024-09-23 |  |  | 2024-10-16 | 2024-11-16 | 2024-10-16 | 2024-10-16 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202508150516-GCI | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
1149A-1066A | KJS Bukit Beruntung | DU00003822878 | Central | Selangor | 3.412976 | 101.542110 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 23/1/2025 : Cutover done 22/1/2025 : Installation complete, pending alignment 21/1/2025 : NE installation complete, pending install FE site 14/1/2025 : SBC KJS - 60M 4 Legged Tower - NE site 1149A KJS Bukit Beruntung, MAXIS - 45M 3 Legged Tower - FE site 1066A Sg.Choh (Timecell) 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M_CA. NE_1149A 13G_DP_1.2m(MDD) x1. XMC_5D , Sub_B_Hi x1. RTN910A x1. ISM8 x2. FE_1066A. 13G_DP_1.2m(MDD) x1. ISM8 x2. XMC_5D, Sub_B_Lo x1. | MW Swap | Existing link 15G_2+0_28M. Swap existing to 13G_4+0_28M_CA. Site Impacted : 1851H,3623B. NE_1149A 1.Install new 13G_DP_1.2m(MDD). 2.Install new XMC_5D , Sub_B_Hi. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install 3_ISM8-2+0 & 4_ISM8-2+0 as 4+0 config. 5.Create EPLA , service cross connect and CA. 6.Traffic 1851H and 3623B migrate to new link 13G_4+0_28M_CA. 7.Enable GE1 , existing ETH cable (1149A_RTN02) transfer to new link. 8.Traffic 3623B migrate to new link 13G_4+0_28M_CA (New RTN910A). 9.Decom existing MW link IDU , Ant , ODU (Pls confirm traffic successful migrated and stable before decom). FE_1066A. 1.Install new 13G_DP_1.2m(MDD). 2.Reuse existing 1066A_RTN09. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 1066A_RTN09 , as 4+0 config. 4.Install XMC_5D, Sub_B_Lo. 5.Create EPLA, service cross connect and CA. 6.Traffic 1851H and 3623B migrate to new MW link. 7.Decom existing MW link ODU and Ant. | [7 empty] | YPTT | SQ202503270802-YPTT | YPTT | SQ202501210491-YPTT // SQ202504260171-YPTT |  |  | Ongoing | 2025-03-11 | 2025-03-31 | 2025-03-11 | 2025-03-11 | MOHD//SHAHREEZAN BIN RAZALI/6794000119 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25010849 |  | 2025-01-09 | 2025-01-16 | Completed | 2025-01-08 | 2025-01-09 | 2025-01-08 | 2025-01-16 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-01-23 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-01-23 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2025-01-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-24 | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-01-28 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-01-21 | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
7069A-7068A | Ulu Kimanis (Celcom) | DU00003822879 | Sabah | Sabah | 5.469163 | 116.059210 |  |  |  |  | Drop/Cancel | Solution Issue | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Current 1 week utilization <70%. Link also not in latest GOP high utilization list | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4752B-4584A | Bendang Rawa | DU00003822880 | Northern | Perak | 4.935670 | 100.805310 | [7 empty] | 00. Integrated/RFS Done | Under observation | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M NE_4752B 18G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. FE_4584A 18G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. | MW Parallel Link | Link Existing 15G_4+0_28M Install Parallel link 18G_2+0_112M Site Impacted : 4245A , A01094. NE_4752B 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH cable patching to exsiting SM link.(Traffic A01094_NT05801 migrate to new link). 6. 4752B_BBU maintain at existing MW link.No decomm. FE_4584A 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH cable patching to existing 4584A_RTN02(GE1). 6.No decomm existing MW link. | Link Existing 15G_4+0_28M Install Parallel link 18G_2+0_112M Site Impacted : 4245A , A01094. NE_4752B 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH cable patching to exsiting SM link.(Traffic A01094_NT05801 migrate to new link). 6. 4752B_BBU maintain at existing MW link.No decomm. | Link Existing 15G_4+0_28M Install Parallel link 18G_2+0_112M Site Impacted : 4245A , A01094. FE_4584A 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH cable patching to existing 4584A_RTN02(GE1). 6.No decomm existing MW link. | XMC_5D | MDD | 18G | 1.2 | 1.2 | Magicell | SQ202504280482-Magicell | Magicell | SQ202509020108-Magicell // SQ202509020111-Magicell // SQ202510100595-Magicell | 2025-07-03 | 2025-06-30 | Completed | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-30 | 2025-07-03 | 2025-06-30 | 2025-06-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082151 |  | 2025-08-22 | 2025-08-25 | Completed | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-05 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | AKMAL//BIN RAZALI/6794000078 |  | 2025-09-29 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-10-13 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2024-10-17: 2025-09-23; 2024-10-23: 2025-09-23; 2024-10-23: 2025-09-23; 2024-10-23: 2025-10-06 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202507080632-GTSB
9692A-9351B | RPR Kidurong | DU00003822881 | Sarawak | Sarawak | 3.239410 | 113.087910 | [6 empty] | ZTE | 00. Integrated/RFS Done | 28/10: Cutover done. Post-CO T/S ongoing 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 9692A-9351B-01_ZNIC 1+0 link using MODU To enable CA and create 2+0 CA link Impacted sites: 9692A Tx route: 9692A/9692A-9351B-LL-9106A NE (9692A): 1) Set IF conflux and enable CA 2) Configure 2nd lihk 3) Create EPLA 2+0 CA FE (9351B): 1) Set IF conflux and enable CA 2) Configure 2nd lihk 3) Create EPLA 2+0 CA | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-04 | 2024-11-04 | 2024-11-04 | 2024-11-04 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2024-11-28 | 2024-12-28 | 2024-11-28 | 2024-11-28 | ASTI//GANIS PUTRIANI/6237001358
P00007_HU | Bukit Tambun (REL) | DU00003822882 | Northern | Penang | 5.269318 | 100.415620 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 15/8: Pending BoQ, TX SoW Details | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_0.6/1.2_MDD_XMC-5D_B | MW Swap | MW SWAP P00007-4291C WITH 18G_2+0_0.6/1.2_MDD_XMC-5D_B | MW SWAP P00007-4291C WITH 18G_2+0_0.6/1.2_MDD_XMC-5D_B NE: 1. Reuse exisiting RTN910A. 2. Install new XMC-5D_SB B. 3. Install new antenna 18G_1.2_MDD. 4. Configure 18G_2+0_1.2/1.2_MDD_256QAM_EPLA | MW SWAP P00007-4291C WITH 18G_2+0_1.2/1.2_MDD_XMC-5D_B FE: 1. Reuse exisiting RTN910A_RTN03 2. Install new XMC-5D_SB B. 3. Install new antenna 18G_1.2_MDD. 4. Configure 18G_2+0_1.2/1.2_MDD_256QAM_EPLA | XMC-5D |  | 18G | 0.6 | 1.2 | GTSB | SQ202508040494-GTSB | GTSB | SQ202508040521-GTSB // SQ202508040522-GTSB | 2025-11-17 | 2025-11-10 | Completed | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-03 | 2025-11-10 | 2025-11-03 | 2025-11-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092720 |  | 2025-09-28 | 2025-09-30 | Completed | 2025-09-27 | 2025-09-28 | 2025-09-27 | 2025-09-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-06 | 2025-10-31 | 2025-10-06 | 2025-10-16 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-10-06 | 2025-10-31 | 2025-10-06 | 2025-10-16 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-09 | 2025-10-06 | 2025-10-31 | 2025-10-06 | 2025-10-16 | HAMZAH BIN ABDUL MUTALIF6799000301 | 2024-10-17: 2025-10-06; 2024-10-23: 2025-10-31; 2024-10-23: 2025-10-06; 2024-10-23: 2025-10-08 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505070167-GTSB | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | HSU//MYET CHAE/6799000011
3887C-1620B | Central i-City Shopping Centre IB | DU00003822883 | Central | Selangor | 3.062279 | 101.481910 |  |  |  |  | Cancel / Drop | Done under DU 3887C TX NIC | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 3887C TX NIC 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9698B-9456A | A RPR Batu Kawa | DU00003822884 | Sarawak | Sarawak | 1.517812 | 110.317110 |  |  |  |  | Under observation | Under observation |  | 00. Site Out/Drop | Under observation |  |  |  | Cancel / Drop | no morre in MSP tracker_W22 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050656-GTSB | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | HSU//MYET CHAE/6799000011
9619B-9387B | Lorong Ding | DU00003822885 | Sarawak | Sarawak | 2.336416 | 111.835110 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  | 18GHz_0.6m/0.6m_SP_1+0_110MHz | Cancel / Drop | MW SWAP 9619B-9387B _18GHz_0.6m/0.6m_SP_1+0_110MHz NE: 1. Swap existing IDU with RTN910A. 2. SWAP existing ODU with XMC-3E_SB A 3. Swap existing Antenna with 0.6m SP. 4. Configure 18G_1+0_110Mhz_256QAM FE: 1. Swap existing IDU with RTN910A. 2. SWAP existing ODU with XMC-3E_SB A 3. Swap existing Antenna with 0.6m SP. 4. Configure 18G_1+0_110Mhz_256QAM | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2582A-1062A | UPSI (Maxis) | DU00003822886 | Central | Perak | 3.685681 | 101.530210 |  |  |  |  | Cancel / Drop | Done under DU 2582A TX NIC | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 2582A TX NIC |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3621A-1704B | Monfort Boys Town (REL) | DU00003822887 | Central | Selangor | 3.087488 | 101.554410 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 25/10: Cutover done. Planner to revise LB due TX Power max. | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_56Mhz_XMC_3 ODU to 1+0_112Mhz_XMC_3E ODU NE_3621A 1. 1+0_XMC_3E , Sub A_Hi. 2. ISM8_1+0 FE_1704B_RTN01 1. 1+0_XMC_3E , Sub A_Lo. 2. ISM8_1+0. | MW Hardware Upgrade | Existing link 18G_1+0_56Mhz Hardware upgrade 18G_1+0_56Mhz_XMC_3 ODU to 1+0_112Mhz_XMC_3E ODU. Site Impacted :3621A,1704B,1314H. NE_3621A 1.Upgrade 1+0_XMC_3 to 1+0_XMC_3E , Sub A_Hi. 2.Configure bandwidth from 56Mhz to 112Mhz. 3.Install new 3_ISM8_1+0. 4.Transfer IF cable from 7_ISM6 to new 3_ISM8. 5.Migrate traffic to new 3_ISM8_1+0. 6.Decom Old XMC_3 ODU. FE_1704B_RTN01. 1.Upgrade 1+0 XMC_3 to 1+0_XMC_3E , Sub A_Lo 2.Configure bandwidth from 56Mhz to 112Mhz. 3.Install new 3_ISM8_1+0. 4.Transfer IF cable from 7_ISM6 to new 3_ISM8. 5.Decom Old XMC_3 ODU. | [7 empty] | Datasco | SQ202411140206-Datasco | Datasco | SQ202410280549-Datasco |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24101027 |  | 2024-10-11 | 2024-10-22 | Completed | 2024-10-10 | 2024-10-11 | 2024-10-10 | 2024-10-22 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-22 | 2024-10-23 | 2024-10-22 | 2025-03-11 | Muhammad//Shahbaz/7019000128 | Datasco TI | 2024-10-22 | 2024-10-23 | 2024-10-22 | 2025-03-11 | Muhammad//Shahbaz/7019000128 | Datasco TI | 2024-10-29 | 2024-10-29 | 2024-10-29 | 2024-10-29 | SHUJAAT//ALI/6800000124 |  |  | 2024-10-22 | 2024-10-23 | 2024-10-22 | 2024-11-02 | Muhammad//Shahbaz/7019000128 | 2024-10-22 | 2024-10-23 | 2024-10-22 | 2024-10-25 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | NG HONG JIE7018000036 | Logistic Team | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
7071D-7196A | Selera Indah REL | DU00003822888 | Sabah | Sabah | 4.281650 | 117.859110 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-20 | 2025-06-20 | 2025-06-19 | 2025-06-19 | HSU//MYET CHAE/6799000011
2624B-1349A | IDS Kesas | DU00003822889 | Central | Selangor | 3.032056 | 101.549410 |  |  |  |  | Under observation | MSP still observe | Digi | 00. Site Out/Drop | 28/2/2025 : Under observation | NA | [17 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
2031A-1413A | Surau Nur Ikhwan | DU00003822890 | Central | Selangor | 3.317770 | 101.595310 | WK11 | MAR 25 | WK11 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 11/3/2025 : Cutover done 27/2/2025 : NE installation complete, pending install FE site due to need Fiberail PTW 14/1/2025 : Digi OB - 20M Monopole - NE site 2031A Surau Nur Ikhwan, Digi OB - Tower - FE site 1413A KTM Rawang 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M. NE_2031A 18G_DP_0.6m(MAC)+OMT x1. ISM8 x1 XMC_3E , Sub A & B_Lo x2. FE_1413A. 18G_DP_0.6m(MAC)+OMT x1. ISM8 x1 XMC_3E , Sub A & B_Hi x2. | MW Swap | Existing link 15G_2_0_28M Swap existing link to 18G_2+0_112M. Site Impacted: 2031A. NE_2031A 1.Install 18G_DP_0.6m(MAC)+OMT. 2.Reuse existing 2031A_RTN01. 3.Install 3_ISM8-2+0 into existing 2031A_RTN04. 4.Install XMC_3E , Sub A & B_Lo. 5.Create EPLA and service cross connect. 6.Migrate traffic to new link 18G_2+0_112M. 7.Decom existing Ant and ODU. FE_1413A. 1.Install 18G_DP_0.6m(MAC)+OMT. 2.Reuse existing 1413A_RTN17. 3.Install 3_ISM8-2+0 into existing 1413A_RTN17. 4.Install XMC_3E , Sub A & B_Hi. 5.Create EPLA and service cross connect. 6.Migrate traffic to new link 18G_2+0_112M. 7.Decom existing ODU and Ant. | [7 empty] | GTSB | SQ202505050038-GTSB | GTSB | SQ202504260131-GTSB // SQ202505020396-GTSB // SQ202505130135-GTSB | 2025-07-05 | 2025-07-03 | Completed | 2025-02-25 | 2025-03-31 | 2025-02-25 | 2025-03-28 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Completed |  | 2025-04-15 | 2025-04-29 | 2025-04-15 | 2025-04-15 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-05 | 2025-05-06 | 2025-05-05 | 2025-05-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO | 2024-11-29 | 2024-12-30 | Completed | 2024-11-28 | 2024-11-29 | 2024-11-28 | 2024-12-30 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-27 | 2025-01-31 | 2024-12-27 | 2024-12-30 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2025-02-25 | 2025-03-31 | 2025-02-25 | 2025-03-24 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-03-11 | 2025-03-11 | 2025-03-11 | 2025-03-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-11 | 2025-02-25 | 2025-03-31 | 2025-02-25 | 2025-03-14 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2024-12-27 | 2025-01-31 | 2024-12-27 | 2024-12-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI
4706C-4136B | The Lexis Suites RT | DU00003822891 | Northern | Penang | 5.286409 | 100.232610 | W49-52 | DEC 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | Under observation | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_4706C 23G_DP_0.6m(MAC)+OMT x1. XMC_3E , Sub A&B_Hi x2. ISM8 x1. FE_4136B 23G_DP_0.6m(MAC)+OMT x1. XMC_3E , Sub A&B_Lo x2. ISM8 x1. | MW Swap | Existing link 18G_1+0_112M Swap Existing link to 23G_2+0_112M Site Impacted: 4706C,4136B NE_4706C 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install XMC_3E-2+0 , Sub A&B_Hi. 3.Reuse existing 4706C_RTN01. 4.Install 3_ISM8-2+0 into existing 4706C_RTN01. 5.Enable EPLA and service cross connect. 6.Traffic migrate to new link 23G_2+0_112M. 7.Decom existing ODU and Ant.(18G). FE_4136B 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install XMC_3E-2+0 , Sub A&B_Lo. 3.Reuse existing 4136B_RTN01. 4.Install 3_ISM8-2+0 into existing 4136B_RTN01. 5.Remain same In Band DCN patching. 6.Enable EPLA and service cross connect. 7.Decom existing ODU and Ant (18G). | [7 empty] | CCSMY | SQ202502180251-CCS | CCSMY | SQ202502180524-CCS // SQ202504260175-CCS // SQ202506231042-CCS | 2025-08-05 | 2025-08-06 | Completed | 2025-02-11 | 2025-02-14 | 2025-02-12 | 2025-02-12 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-04 | 2025-08-05 | 2025-08-04 | 2025-08-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2025-02-15 | 2025-02-15 | Completed | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-15 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-02-15 | IMRAN//JAVED/7021000061 | CCS TI | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-02-15 | IMRAN//JAVED/7021000061 | CCS TI | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-13 | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-04-28 | IMRAN//JAVED/7021000061 | 2025-02-12 | 2025-02-28 | 2025-02-12 | 2025-03-10 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-20 | NG HONG JIE7018000036 | Logistic Team | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202507250716-GCI | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
2225A-2945A | Pulapot water tank Tmn Bunga Raya | DU00003822892 | Central | Kuala Lumpur | 3.208116 | 101.738510 |  |  | WK32-WK35 | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 7/8: D1: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz 112MHz HW Upgrade NE: 1) 1xISM8 card 2) 1x23GHz XMC3 Sub A Lo FE: 1) 1xISM8 card 2) 1x23GHz XMC3 Sub A Hi | MW Hardware Upgrade | Existing link 2225A-2945A 1+0 56MHz (2225A RTN01-2945A RTN01) To perform HW and SW upgrade to 112MHz Impact site: 2225A NE (2225A) 1. Add ISM8 at RTN01 slot 3 2. Swap ODU to 112MHz 3. Configure 112MHz IS8 FE (2945A) 1. Add ISM8 at RTN05 slot 3 2. Swap ODU to 112MHz 3. Transfer IF cable from RTN01 7-ISM6-2 to RTN05 3-ISM8-1 4. Configure 112MHz IS8 | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202408140523-MTK | 2024-09-27 | 2024-09-25 | Completed | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-14 | 2024-08-15 | 2024-08-14 | 2024-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-14 | 2024-08-15 | 2024-08-14 | 2024-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-25 | 2024-09-27 | 2024-09-25 | 2024-09-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240730AD |  | 2024-07-31 | 2024-08-01 | Completed | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-08-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-06 | 2024-08-31 | 2024-08-06 | 2024-08-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-08-06 | 2024-08-31 | 2024-08-06 | 2024-08-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-08-09 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-08-06 | 2024-08-31 | 2024-08-06 | 2024-08-10 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-08-06 | 2024-08-31 | 2024-08-06 | 2024-08-08 | 2025-01-10 | 2025-01-10 | 2025-01-10 | 2025-01-10 | NG HONG JIE7018000036 | Logistic Team | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
9302A-9999A | Ericsson | DU00003822893 | Sarawak | Sarawak | 1.552670 | 110.366610 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list |  | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050656-GTSB | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | HSU//MYET CHAE/6799000011
4245A-4215A | Titi Panjang | DU00003822894 | Northern | Penang | 5.327470 | 100.452110 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | History Performance Link Utilization < 65% 4245A_RTN02 to 4215A_RTN20 , (26 March 2025 to 9 April 2025). DU00003822894 , Cancel / Drop. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9257A-9256A | Balai Ringin | DU00003822895 | Sarawak | Sarawak | 1.046260 | 110.744110 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | no more in MSP tracker_W22 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050656-GTSB | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | HSU//MYET CHAE/6799000011
4272A-4276A | Permatang Bera 2 | DU00003822896 | Northern | Penang | 5.509877 | 100.384510 | W49-52 | DEC 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M_CA. NE_4272A 15G_DP_1.2m(MDD) x1. RTN910A x1 ISM8 x2. XMC_5D_Sub B x1. FE_4276A 15G_DP_1.2m(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D_Sub B x1. | MW Swap | Existing link 15G_2+0_28M. Swap existing link to 15G_4+0_28M_CA. Site impacted : 4117R. NE_4272A 1.Install new 15G_DP_1.2m(MDD). 2.Install new RTN910A.(RTN no provide by MSP team). 3.Install XMC_5D , Sub B_Hi 4.Install 3_ISM8-2+0 and 4_ISM8-2+0 config to 4+0_CA. 5.Create EPLA , service cross connect and CA. 6.Enable GE port , patching ETH cable to existing 4272A_RTN07 due to traffic 4117R. 7.Migrate traffic (4117R) to new link 15G_4+0_28M_CA. 8.Decom existing ODU,Ant and 1_ISV3 & 2_ISV3.(4272A_RTN07-4276A). FE_4276A 1.Install new 15G_DP_1.2m(MDD). 2.Install new RTN910A.(RTN no provide by MSP team). 3.Install 3_ISM8-2+0 and 4_ISM8-2+0 config to 4+0_CA. 4.Install XMC_5D , Sub B_Lo. 5.Create EPLA, service cross connect and CA. 6.Traffic 4117R migrate to new link 15G_4+0_28M_CA. 7.Enable GE1 port patching to Ibeam and create In-band DCN. 8.Decom existing IDU , ODU and Ant.(4276A_RTN06-4272A). | [7 empty] | CCSMY | SQ202412230234-CCS | CCSMY | SQ202504260061-CCS // SQ202504260064-CCS // SQ202504260175-CCS | 2025-08-06 | 2025-08-06 | Completed | 2024-12-18 | 2024-12-18 | 2024-12-18 | 2024-12-18 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032061 |  | 2025-03-21 | 2025-03-22 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-09 | 2025-04-30 | 2025-05-07 | 2025-05-07 | MUHAMMAD//AWAIS/7021000082 | CCS TI | 2025-04-09 | 2025-04-30 | 2025-05-07 | 2025-05-07 | MUHAMMAD//AWAIS/7021000082 | CCS TI | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-23 | 2025-04-09 | 2025-04-30 | 2025-05-08 | 2025-05-08 | MUHAMMAD//AWAIS/7021000082 | 2025-04-09 | 2025-04-30 | 2025-04-11 | 2025-04-11 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | CHEONG/SENG/WAH/7018000306
2619B-1120A | Tmn Alam Megah MP | DU00003822897 | Central | Selangor | 2.996675 | 101.558310 |  |  |  |  | Cancel / Drop | Done under DU 2619B TX NIC | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 2619B TX NIC |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [17 empty] | RAVIN//MUNISWARAN A/L MOHANADAS6800000087
7626B-7976A | Kg. Kubang (Celcom) | DU00003822898 | Sabah | Sabah | 4.414070 | 118.522210 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | HSU//MYET CHAE/6799000011
4460A-4427B | TAIPING HAWKER | DU00003822899 | Northern | Perak | 4.846685 | 100.740510 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M. NE_4460A 18G_DP_1.2m(MDD) x1. XMC_5D-2+0 , Sub_A_Hi x1. ISM8 x1. FE_4427B 18G_DP_1.2m(MDD) x1. XMC_5D-2+0 ,Sub_A_Lo x1. ISM8 x1. | MW Swap | Existing link 15G_4+0_28M Swap existing to 18G_2+0_112M. Site Impacted: 4211C. NE_4460A 1.Install new 18G_DP_1.2m(MDD). 2.Install new XMC_5D-2+0 , Sub_A_Hi. 3.Reuse existing 4460A_RTN02. 4.Install 4_ISM8-2+0_112M. 5.Enable EPLA and service cross connect. 6.Migrate 4211C traffic to new link with transfer 3_ISM8 card from 4460A_RTN01. 7.Remove ETH cable interconnect between RTN 02 & RTN 01. 8.Decom existing ODU , Ant and 4460A_RTN01. FE_4427B 1.Install new 18G_DP_1.2m(MDD). 2.Install new XMC_5D-2+0 ,Sub_A_Lo. 3.Reuse existing 4427B_RTN06. 4.Install 4_ISM8-2+0_112M. 5.Enable EPLA and service cross connect. 6.Migrate 4211C traffic to new link. 7.Decom existing ODU and Ant. | [7 empty] | Magicell | SQ202503190721-Magicell | Magicell | SQ202503200275-Magicell // SQ202503200278-Magicell // SQ202504260184-Magicell // SQ202507290130-Magicell | 2025-11-26 | 2025-11-28 | Completed | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022097 |  | 2025-02-21 | 2025-03-19 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-03-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-15 | 2026-03-18 | 2025-03-15 | 2025-03-19 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 |  | 2025-03-15 | 2026-03-18 | 2025-03-15 | 2025-03-19 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 |  | 2025-03-16 | 2025-03-16 | 2025-03-16 | 2025-03-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-16 | 2025-03-15 | 2026-03-18 | 2025-03-15 | 2025-03-21 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-03-15 | 2026-03-18 | 2025-03-15 | 2025-03-20 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-10-21 | CHEONG/SENG/WAH/7018000306
Q01479-Q00265 | KIDURONGIND3 | DU00003822900 | Central | Sarawak | 3.267910 | 113.083110 |  |  |  |  | Cancel / Drop | Pass to Huawei | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1337B-1203A | Sungai Buloh R&R(AsiaSpace) | DU00003822901 | Central | Selangor | 3.188731 | 101.587810 |  |  |  |  | Cancel / Drop | Done under DU 1663C_PostMOCN and 3101A_Additional TX NIC | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 1663C_PostMOCN and 3101A_Additional TX NIC |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1050A-1475A | Tmn Uniindah | DU00003822902 | Central | Selangor | 3.006510 | 101.688610 |  |  |  |  | Cancel / Drop | Done under DU 1050A_Additional1 TX NIC | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 1050A_Additional1 TX NIC |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4403B-4300B | Simpang Dua Manjung-100Q4 | DU00003822903 | Northern | Perak | 4.200910 | 100.723710 | WK36-40 | SEP 24 | WK45-48 | NOV 24 |  |  |  | 00. Integrated/RFS Done | 29/10: Cutover done. To amend LB & follow Ch# use on site 23/10: Interim solution: To proceed with SW Upgrade activity on existing link before proceed with the proposed solution in EPMS 21/10: New solution released. Pending Site BOM | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_4403B New 18G_1.2M(MDD) x1. Reuse existing RTN910A(RTN01). New XMC_5D, Sub A_Hi x1. New IF cable for 2nd channel(Horizontal) with suitable length. FE_4300B New 18G_0.6M(MDD) x1. Reuse existing RTN910A(RTN01). New XMC_5D, Sub A_Lo x1. New IF cable for 2nd channel(Horizontal) with suitable length. | MW Swap | Link Existing HW 18G_1+0_112M_512QAM. Swap existing link to new HW 18G_2+0_112M_512QAM_EPLA. Site Impacted : 4403B. NE_4403B 1.Install new 18G_1.2M(MDD). 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_5D , Sub A_Hi. Configure new HW 18G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and migrate RAN traffic to new MW link. 5.Later, decom existing HW 18G_1+0_112M_512QAM but decom existing ODU 18G and existing antenna 18G(1.2m-SP) ONLY. Do not decom RTN910A(RTN01). FE_4300B 1.Install new 18G_0.6M(MDD). 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_5D , Sub A_Lo. Configure new HW 18G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and existing port at IBeam. 5.Later, decom existing HW 18G_1+0_112M_512QAM but decom existing ODU 18G and existing antenna 18G(0.6m-SP) ONLY. Do not decom RTN910A(RTN01). | Link Existing HW 18G_1+0_112M_512QAM. Swap existing link to new HW 18G_2+0_112M_512QAM_EPLA. Site Impacted : 4403B. NE_4403B 1.Install new 18G_1.2M(MDD). 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_5D , Sub A_Hi. Configure new HW 18G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and migrate RAN traffic to new MW link. 5.Later, decom existing HW 18G_1+0_112M_512QAM but decom existing ODU 18G and existing antenna 18G(1.2m-SP) ONLY. Do not decom RTN910A(RTN01). | Link Existing HW 18G_1+0_112M_512QAM. Swap existing link to new HW 18G_2+0_112M_512QAM_EPLA. Site Impacted : 4403B. FE_4300B 1.Install new 18G_0.6M(MDD). 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_5D , Sub A_Lo. Configure new HW 18G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and existing port at IBeam. 5.Later, decom existing HW 18G_1+0_112M_512QAM but decom existing ODU 18G and existing antenna 18G(0.6m-SP) ONLY. Do not decom RTN910A(RTN01). | XMC_5D | MDD | 18G | 18G_1.2M(MDD) x1. | 18G_0.6M(MDD) x1. | CCSMY | SQ202411180356-CCS | CCSMY | SQ202411150552-CCS // SQ202504260175-CCS | 2025-12-02 | 2025-11-26 | Completed | 2025-02-25 | 2025-04-17 | 2025-04-17 | 2025-04-17 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092655 |  | 2025-09-27 | 2025-10-09 | Completed | 2025-09-26 | 2025-09-27 | 2025-10-01 | 2025-10-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2026-01-13 | 2026-01-13 | 2026-01-13 | Muhammad Afiq Bin Mat Jalil7539000007 |  | 2026-01-13 | 2026-01-13 | 2026-01-13 |  |  | CCS TI | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202508150539-GTSB
2391A-1197A | BU 12 LP | DU00003822904 | Central | Selangor | 3.125067 | 101.602311 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop |  |  |  | Cancel / Drop | Cancel Tx Upgrade under BAU HU. Tx Upgrade completed under NIC. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9179B-9122A | Taman Seberkas | DU00003822905 | Sarawak | Sarawak | 3.281350 | 113.119210 | [6 empty] | ZTE | 00. Integrated/RFS Done | 11/10: D2: Cutover done 10/10: Pre-installation & TSS | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | XMC-3E SB A | MW Hardware Upgrade | Propose MW Hardware Upgrade from 512QAM to 1024QAM NE: 1. Change existing ODU with new XMC_3E_SBA. 2. Configure 18G_1+0_1024QAM. FE: 1. 1. Change existing ODU with new XMC_3E_SBA. 2. Configure 18G_1+0_1024QAM. | [7 empty] | Datasco | SQ202410280509-Datasco | Datasco | SQ202410100853-Datasco | 2024-11-22 | 2024-11-15 | Completed | 2024-10-10 | 2024-10-10 | 2024-10-16 | 2024-10-16 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-11 | 2024-10-18 | 2024-10-11 | 2024-10-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-11 | 2024-10-18 | 2024-10-11 | 2024-10-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-15 | 2024-11-22 | 2024-11-15 | 2024-11-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24100750 |  | 2024-10-08 | 2024-10-09 | Completed | 2024-10-07 | 2024-10-08 | 2024-10-07 | 2024-10-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-10 | 2024-10-31 | 2024-10-16 | 2024-10-16 | JIKLON//BIN HASAN/7019000089 | Datasco TI | 2024-10-10 | 2024-10-31 | 2024-10-11 | 2024-10-14 | JIKLON//BIN HASAN/7019000089 | Datasco TI | 2024-10-11 | 2024-10-11 | 2024-10-11 | 2024-10-11 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-10-10 | 2024-10-31 | 2024-10-24 | 2024-10-24 | JIKLON//BIN HASAN/7019000089 | 2024-10-10 | 2024-10-31 | 2024-10-10 | 2024-10-10 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-11 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-11-28 | 2024-12-28 | 2024-11-28 | 2024-11-28 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300154-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
2475A-1096A | Kg Perepat | DU00003822906 | Central | Selangor | 3.125344 | 101.369510 |  |  |  |  | Cancel / Drop | Close due to utization reduce | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Close due to utization reduce 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Traffics 2475A(DU00002029539) & 1561B(DU00002029569) already divert to xC PTN(B00539). | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
4301D-4650B | Tesco Mergong (REL) | DU00003822907 | Northern | Kedah | 6.135802 | 100.343510 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M. NE_4301D 18G_DP_0.6m(MDD) x1. ISM8 x1 XMC_5D-2+0 , Sub_B_Hi x1. FE_4650B. 18G_DP_0.6m(MDD) x1. RTN910A x1. XMC_5D-2+0 , Sub_B_Lo x1. | MW Swap | Existing link 18G_1+0_112M Swap existing to 18G_2+0_112M. Site Impacted : 4088K,4119H,4301D. NE_4301D 1.Install 18G_DP_0.6m(MDD). 2.Reuse existing 4301D_RTN02. 3.Install 3_ISM8-2+0 into existing 4301D_RTN02. 4.Install new XMC_5D-2+0 , Sub_B_Hi. 5.Enable EPLA and service cross connect. 6.Enable GE1 , NLOS 4119H ETH cable transfer to existing 4301D_RTN02. 7.Traffic 4088K,4119H and 4301D migrate to new link 18G_2+0_112M. 8.Decom existing MW link. FE_4650B. 1.Install 18G_DP_0.6m(MDD). 2.Install new RTN910A,7_ISM8-2+0. 3.Install XMC_5D-2+0 , Sub_B_Lo. 4.Enable EPLA and service cross connect. 5.Traffic 4088K,4119H and 4301D migrate to new link 18G_2+0_112M. 6.Create new Inband DCN. 7.Decom existing MW link. | [7 empty] | GCI | SQ202502120339-GCI | GCI | SQ202502050297-GCI // SQ202504150095-GCI | 2025-12-10 | 2025-12-10 | Completed | 2025-02-04 | 2025-02-04 | 2025-02-04 | 2025-02-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-10 | 2025-02-10 | 2025-02-10 | 2025-02-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2025-02-11 | 2025-02-11 | Completed | 2025-02-11 | 2025-02-11 | 2025-02-11 | 2025-02-11 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-03 | 2025-02-28 | 2025-02-03 | 2025-02-11 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-02-03 | 2025-02-28 | 2025-02-03 | 2025-02-11 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-02-04 | 2025-02-04 | 2025-02-04 | 2025-02-04 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-04 | 2025-02-03 | 2025-02-28 | 2025-02-03 | 2025-02-16 | SAFUAN//BIN YUSOFF/6800000178 | 2025-02-03 | 2025-02-28 | 2025-02-03 | 2025-02-03 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
2799B-7640A | pBTS Kg Meruntum (KM) | DU00003822908 | Sabah | Sabah | 5.866111 | 116.047910 |  |  |  |  | Drop/Cancel | Solution Issue | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Latest 1 week utilization <70%. Link also not in GOP weekly high utilization list | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9000B19_EVT | Pbts_REGATTA SEMPORNA | DU00005687216 | Sabah | Sabah | 4.477302 | 118.612850 | [13 empty] | Planning and integration support only for event site 9000B19 Tx route: 9000B19-7209A 1) New port at 7209A-MAC-001 Bubul Road Semporna (Maxis) 2) New DCN IP 7209A RTN15 3) New DCN VLAN 7209A RTN15 4) New NE ID FE IDU 7209A RTN15 5) New NE ID NE IDU 9000B19 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | CHEONG/SENG/WAH/7018000306
S00330_EB | S00330_BUKIT TOWER_BUKIT RASUL | DU00005687218 | Sabah | Sabah | 5.158721 | 118.480627 | [7 empty] | 05. Doable |  | TSS+TI |  |  | MW IDU Patching | IDU PATCHING TO BRING NLOS EB S01753-NLOS-S01607-S00330-S00320. PATCH TO XD TO USE ROUTE S01753-NLOS-S01607-S00330-7604A-LL-7100A | [7 empty] | NR services |  | NR services | SQ202509090323-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25090203 |  | 2025-09-03 | 2025-09-03 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-03 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-28 | 2025-10-28 | 2025-09-28 |  | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-09-28 | 2025-10-28 | 2025-09-28 |  | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | [7 empty] | 2025-09-28 | 2025-10-28 | 2025-09-28 |  | DATU//AZRUN BIN DATU HARUN/7167000004 | 2024-10-17: 2025-09-28; 2024-10-23: 2025-10-28; 2024-10-23: 2025-09-28 | [7 empty] | GCI | SQ202506160757-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | EZRIN TASNIM BIN ABDUL GANI6798000128
7494B_HU_3 | KgKoya | DU00006529611 | Sabah | Sabah | 5.275170 | 118.105220 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M_256QAM_EPLA NE_7494B New 15G_1.2M(MDD)+Dual Coupler x1. New RTN910A(RTN06). New ISM8 x2. New XMC_5D Pro, Sub B_Lo x2. New IF cables with suitable length and type x4 RUN(x2 existing channels and x2 for new channels). New CAT6 cable x1. FE_7581A New 15G_1.2M(MDD)+Dual Coupler x1. New RTN910A(RTN10). New ISM8 x2. New XMC_5D Pro, Sub B_Hi x2. New IF cables with suitable length and type x4 RUN(x2 existing channels and x2 for new channels). New CAT6 cable x1. | MW Swap | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 15G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7494B_HU_3. 2ND - DU 7487B_HU_2.**** Existing Huawei MW Link 13G_1+0_28MHZ_512QAM. Swap existing Huawei MW Link 13G_1+0_28MHZ_512QAM with HW MW Link 7494B(RTN03)-7581A(RTN10) 15G_4+0_28M_256QAM_800_EPLA. Later, decom existing Huawei MW Link 13G_1+0_28MHZ_512QAM - 7494B(RTN02, NEID 9-19520, Slot 03-ISV3) and 7581A(RTN05, NEID 9-19391, Slot 01-ISV3). Site Impacted : 7487B. NE_7494B 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910A(RTN06) x1 and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub B_Lo x2. Configure it. 4.Lay new x2 RUN of IF cables from existing 2x ODU XMC-3 13G due to need to shifting existing 13G_2+0_28MHZ_512QAM from existing RTN910A(RTN02, NEID 9-19520) slot 07(ISM6 Port 1 & 2) to new RTN910A(RTN06) slot 07(ISM8 Port 1 & 2). 5.Lay new x2 RUN of IF cables from new 2x ODU XMC_5D Pro, Sub B_Lo 15G to new RTN910A(RTN06) slot 03(ISM8 Port 1) and slot 04(ISM8 Port 1). 6.Enable port 8-EM6-1 of new RTN910AF(RTN06). 7.Perform cascading between port 8-EG6-1 of existing RTN910A(RTN02, NEID 9-19520) and port 8-EM6-1 of new RTN910AF(RTN06). 8.Request new Vlan DCN from ZTE IPRAN team. 9.Re-use existing Vlan Services. 10.Migrate traffic 7487B via new 13G&15G_6+0_28MHZ_512QAM&256QAM_1210M. FE_7581A 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910A(RTN10) x1 and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub B_Hi x2. Configure it. 4.Lay new x2 RUN of IF cables from existing 2x ODU XMC-3 13G due to need to shifting existing 13G_2+0_28MHZ_512QAM from existing RTN950A(RTN05, NEID 9-19391) slot 04(ISV3 Port 1) to new RTN910A(RTN10) slot 07(ISM8 Port 1), existing RTN950A(RTN05, NEID 9-19391) slot 06(ISV3 Port 1) to new RTN910A(RTN10) slot 07(ISM8 Port 2). 5.Lay new x2 RUN of IF cables from new 2x ODU XMC_5D Pro, Sub B_Hi 15G to new RTN910A(RTN10) slot 03(ISM8 Port 1 & 2) and slot 04(ISM8 Port 1 & 2). 6.Enable port 8-EM6-1 of new RTN910AF(RTN10). 7.Perform patching between port 8-EM6-1 of new RTN910AF(RTN10) and existing IBeam port. 8.Request new Vlan DCN from ZTE IPRAN team. 9.Re-use existing Vlan Services. 10.Migrate traffic 7487B via existing port of IBeam. 11.Later, decom existing RTN950A(RTN05, NEID 9-19391). | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 15G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7494B_HU_3. 2ND - DU 7487B_HU_2.**** Existing Huawei MW Link 13G_1+0_28MHZ_512QAM. Swap existing Huawei MW Link 13G_1+0_28MHZ_512QAM with HW MW Link 7494B(RTN03)-7581A(RTN10) 15G_4+0_28M_256QAM_800_EPLA. Later, decom existing Huawei MW Link 13G_1+0_28MHZ_512QAM - 7494B(RTN02, NEID 9-19520, Slot 03-ISV3) and 7581A(RTN05, NEID 9-19391, Slot 01-ISV3). Site Impacted : 7487B. NE_7494B 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910A(RTN06) x1 and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub B_Lo x2. Configure it. 4.Lay new x2 RUN of IF cables from existing 2x ODU XMC-3 13G due to need to shifting existing 13G_2+0_28MHZ_512QAM from existing RTN910A(RTN02, NEID 9-19520) slot 07(ISM6 Port 1 & 2) to new RTN910A(RTN06) slot 07(ISM8 Port 1 & 2). 5.Lay new x2 RUN of IF cables from new 2x ODU XMC_5D Pro, Sub B_Lo 15G to new RTN910A(RTN06) slot 03(ISM8 Port 1) and slot 04(ISM8 Port 1). 6.Enable port 8-EM6-1 of new RTN910AF(RTN06). 7.Perform cascading between port 8-EG6-1 of existing RTN910A(RTN02, NEID 9-19520) and port 8-EM6-1 of new RTN910AF(RTN06). 8.Request new Vlan DCN from ZTE IPRAN team. 9.Re-use existing Vlan Services. 10.Migrate traffic 7487B via new 13G&15G_6+0_28MHZ_512QAM&256QAM_1210M. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 15G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7494B_HU_3. 2ND - DU 7487B_HU_2.**** Existing Huawei MW Link 13G_1+0_28MHZ_512QAM. Swap existing Huawei MW Link 13G_1+0_28MHZ_512QAM with HW MW Link 7494B(RTN03)-7581A(RTN10) 15G_4+0_28M_256QAM_800_EPLA. Later, decom existing Huawei MW Link 13G_1+0_28MHZ_512QAM - 7494B(RTN02, NEID 9-19520, Slot 03-ISV3) and 7581A(RTN05, NEID 9-19391, Slot 01-ISV3). Site Impacted : 7487B. FE_7581A 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910A(RTN10) x1 and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub B_Hi x2. Configure it. 4.Lay new x2 RUN of IF cables from existing 2x ODU XMC-3 13G due to need to shifting existing 13G_2+0_28MHZ_512QAM from existing RTN950A(RTN05, NEID 9-19391) slot 04(ISV3 Port 1) to new RTN910A(RTN10) slot 07(ISM8 Port 1), existing RTN950A(RTN05, NEID 9-19391) slot 06(ISV3 Port 1) to new RTN910A(RTN10) slot 07(ISM8 Port 2). 5.Lay new x2 RUN of IF cables from new 2x ODU XMC_5D Pro, Sub B_Hi 15G to new RTN910A(RTN10) slot 03(ISM8 Port 1 & 2) and slot 04(ISM8 Port 1 & 2). 6.Enable port 8-EM6-1 of new RTN910AF(RTN10). 7.Perform patching between port 8-EM6-1 of new RTN910AF(RTN10) and existing IBeam port. 8.Request new Vlan DCN from ZTE IPRAN team. 9.Re-use existing Vlan Services. 10.Migrate traffic 7487B via existing port of IBeam. 11.Later, decom existing RTN950A(RTN05, NEID 9-19391). | XMC_5D Pro | MDD | 15G | 15G_1.2M(MDD)+Dual Coupler x1 | 15G_1.2M(MDD)+Dual Coupler x1 | GTSB | SQ202604240980-GTSB | GTSB | SQ202604100652-GTSB // SQ202604100653-GTSB |  |  | Ongoing | [8 empty] | Unassigned | Not started |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | PAVITRAN AL CHINNAKOLANDAY6799000150 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031151 |  | 2026-03-12 | 2026-04-02 | Completed | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-04-02 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-07 | 2026-05-09 | 2026-04-07 | 2026-04-20 | ABDULLAH//BIN NASIB/6000059295 | GTSB TI | 2026-04-07 | 2026-05-09 | 2026-04-07 | 2026-04-28 | ABDULLAH//BIN NASIB/6000059295 | GTSB TI | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-20 | 2026-04-07 | 2026-05-09 | 2026-04-07 | 2026-04-28 | ABDULLAH//BIN NASIB/6000059295 | 2024-10-17: 2026-04-07; 2024-10-23: 2026-05-09; 2024-10-23: 2026-04-07; 2024-10-23: 2026-04-09 | [7 empty] | GTSB | SQ202601210802-GTSB
7487B_HU_2 | KgGaban | DU00006529612 | Sabah | Sabah | 5.319390 | 118.239430 | [7 empty] | 05. TI WIP |  | TSS+AA+TI+Dismantle |  | 13G_4+0_28M_256QAM_EPLA NE_7487B New 13G_1.2M(MDD)+Dual Coupler x1. Re-use existing RTN910AF(RTN03, NEID 9-36022). New ISM8 x2. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x4 RUN(x2 for new channels). FE_7494B New 13G_1.8M(MDD)+Dual Coupler x1. New RTN910AF(RTN07). New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN(x2 for existing & x2 for new channels). New CAT6 cable x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7494B_HU_3. 2ND - DU 7487B_HU_2.**** Existing Huawei MW Link 8G_2+0_28MHZ_1024QAM_EPLA. Add new parallel Huawei MW Link 13G_4+0_28MHZ_256QAM_EPLA. Later, combine existing Huawei MW Link 8G_2+0_28MHZ_1024QAM_EPLA and new parallel Huawei MW Link 13G_4+0_28MHZ_256QAM_EPLA. Become new Huawei MW Link 8G&13G_6+0_28MHZ_1024QAM&256QAM_EPLA. Decom existing RTN910A(RTN02, NEID 9-19520). Site Impacted : 7487B. NE_7487B 1.Install 13G_1.2M(MDD)+Dual Coupler x1. 2.Re-use existing RTN910AF(RTN03, NEID 9-36022) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new x2 RUN of IF cables from new 2x ODU XMC_5D Pro, Sub A&B_Hi to existing RTN910AF(RTN03, NEID 9-36022) slot 03(ISM8 Port 1) and slot 04(ISM8 Port 1). 5.Re-use existing Vlan DCN and Vlan Services. 6.Migrate traffic 7487B via new 8G&13G_6+0_28MHZ_1024QAM&256QAM_EPLA. FE_7494B 1.Install 13G_1.8M(MDD)+Dual Coupler x1. 2.Install new RTN910A(RTN07) x1 and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Lay new x2 RUN of IF cables from existing 2x ODU XMC-3 8G(27-ODU & 47-ODU) due to need to shifting existing 8G_2+0_28MHZ_1024QAM_EPLA from existing RTN910A(RTN02, NEID 9-19520) slot 04(ISM8 Port 1 & 2) to new RTN910A(RTN07) slot 07(ISM8 Port 1 & 2). 5.Lay new x2 RUN of IF cables from new 2x ODU XMC_5D Pro, Sub A&B_Lo x2 to new RTN910A(RTN07) slot 03(ISM8 Port 1) and slot 04(ISM8 Port 1). 6.Enable port 8-EM6-1 of new RTN910AF(RTN07). 7.Perform patching between port 8-EM6-1 of new RTN910AF(RTN07) and port 8-EM6-1 of new RTN910AF(RTN06) under 1st DU 7494B_HU_3. 8.May re-use existing Vlan DCN and Vlan Services. 9.Migrate traffic 7487B via existing port of IBeam. 10.Later, decom existing RTN910A(RTN02, NEID 9-19520). | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7494B_HU_3. 2ND - DU 7487B_HU_2.**** Existing Huawei MW Link 8G_2+0_28MHZ_1024QAM_EPLA. Add new parallel Huawei MW Link 13G_4+0_28MHZ_256QAM_EPLA. Later, combine existing Huawei MW Link 8G_2+0_28MHZ_1024QAM_EPLA and new parallel Huawei MW Link 13G_4+0_28MHZ_256QAM_EPLA. Become new Huawei MW Link 8G&13G_6+0_28MHZ_1024QAM&256QAM_EPLA. Decom existing RTN910A(RTN02, NEID 9-19520). Site Impacted : 7487B. NE_7487B 1.Install 13G_1.2M(MDD)+Dual Coupler x1. 2.Re-use existing RTN910AF(RTN03, NEID 9-36022) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new x2 RUN of IF cables from new 2x ODU XMC_5D Pro, Sub A&B_Hi to existing RTN910AF(RTN03, NEID 9-36022) slot 03(ISM8 Port 1) and slot 04(ISM8 Port 1). 5.Re-use existing Vlan DCN and Vlan Services. 6.Migrate traffic 7487B via new 8G&13G_6+0_28MHZ_1024QAM&256QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU 7494B_HU_3. 2ND - DU 7487B_HU_2.**** Existing Huawei MW Link 8G_2+0_28MHZ_1024QAM_EPLA. Add new parallel Huawei MW Link 13G_4+0_28MHZ_256QAM_EPLA. Later, combine existing Huawei MW Link 8G_2+0_28MHZ_1024QAM_EPLA and new parallel Huawei MW Link 13G_4+0_28MHZ_256QAM_EPLA. Become new Huawei MW Link 8G&13G_6+0_28MHZ_1024QAM&256QAM_EPLA. Decom existing RTN910A(RTN02, NEID 9-19520). Site Impacted : 7487B. FE_7494B 1.Install 13G_1.8M(MDD)+Dual Coupler x1. 2.Install new RTN910A(RTN07) x1 and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Lay new x2 RUN of IF cables from existing 2x ODU XMC-3 8G(27-ODU & 47-ODU) due to need to shifting existing 8G_2+0_28MHZ_1024QAM_EPLA from existing RTN910A(RTN02, NEID 9-19520) slot 04(ISM8 Port 1 & 2) to new RTN910A(RTN07) slot 07(ISM8 Port 1 & 2). 5.Lay new x2 RUN of IF cables from new 2x ODU XMC_5D Pro, Sub A&B_Lo x2 to new RTN910A(RTN07) slot 03(ISM8 Port 1) and slot 04(ISM8 Port 1). 6.Enable port 8-EM6-1 of new RTN910AF(RTN07). 7.Perform patching between port 8-EM6-1 of new RTN910AF(RTN07) and port 8-EM6-1 of new RTN910AF(RTN06) under 1st DU 7494B_HU_3. 8.May re-use existing Vlan DCN and Vlan Services. 9.Migrate traffic 7487B via existing port of IBeam. 10.Later, decom existing RTN910A(RTN02, NEID 9-19520). | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD)+Dual Coupler x1 | 13G_1.8M(MDD)+Dual Coupler x1 | GTSB | SQ202604150174-GTSB | GTSB | SQ202603130143-GTSB // SQ202603130149-GTSB |  |  | Ongoing | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | PAVITRAN AL CHINNAKOLANDAY6799000150 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | PAVITRAN AL CHINNAKOLANDAY6799000150 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030331 |  | 2026-03-04 | 2026-03-05 | Completed | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-05 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-11 | 2026-03-31 | 2026-03-11 | 2026-04-03 | ABDULLAH//BIN NASIB/6000059295 | GTSB TI | 2026-03-11 | 2026-03-31 | 2026-03-11 |  | ABDULLAH//BIN NASIB/6000059295 | GTSB TI | [7 empty] | 2026-03-11 | 2026-03-31 | 2026-03-11 |  | ABDULLAH//BIN NASIB/6000059295 | 2024-10-17: 2026-03-11; 2024-10-23: 2026-03-31; 2024-10-23: 2026-03-11; 2024-10-23: 2026-03-29 | [7 empty] | GTSB | SQ202601210802-GTSB
9223A_PL | TemudokSri Aman-Core(Celcom) | DU00006529613 | Sarawak | Sarawak | 1.167829 | 111.473619 | [9 empty] | TSS+TI |  | MW Re-engineering at 9223A. NE_9223A New CAT6 cable x1. New SFP Module 10G with 10Km 1310nm x1(For IDU HW RTN910AF-RTN01). New Optical Patch Cord cable x1 with suitable type and length. | BBU Patching | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_2(TX MINI). 3RD - DU 9223A_PL(TX MINI).**** MW Re-engineering at 9223A. Site Impacted :9223A & Q01605. NE_9223A 1.Disconnect or remove existing patching in between BBU 9223A and Sacofa LL 10G port. 2.Enable electrical port 8-EM6-1 of new RTN910AF(RTN01) under DU Q00701_PL. 3.Patching existing BBU 9223A to electrical 1G port 8-EM6-1 of new RTN910AF(RTN01) under DU Q00701_PL. 3.Enable optical 10G port 8-EM6-3 of new RTN910AF(RTN01) under DU Q00701_PL. 4.Insert new suitable SFP Module 10G into port 8-EM6-3 of new RTN910AF(RTN01). Enable it. 5.Patching optical patch cord of 10G port 8-EM6-3 of new RTN910AF(RTN01) to existing Sacofa LL 10G port. 6.Request new xD Vlan Services for traffic Q01605. 7.Finally, both traffics 9223A & Q01605 will backhaul into existing 10G IBeam port at CP 9999A. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_2(TX MINI). 3RD - DU 9223A_PL(TX MINI).**** MW Re-engineering at 9223A. Site Impacted :9223A & Q01605. NE_9223A 1.Disconnect or remove existing patching in between BBU 9223A and Sacofa LL 10G port. 2.Enable electrical port 8-EM6-1 of new RTN910AF(RTN01) under DU Q00701_PL. 3.Patching existing BBU 9223A to electrical 1G port 8-EM6-1 of new RTN910AF(RTN01) under DU Q00701_PL. 3.Enable optical 10G port 8-EM6-3 of new RTN910AF(RTN01) under DU Q00701_PL. 4.Insert new suitable SFP Module 10G into port 8-EM6-3 of new RTN910AF(RTN01). Enable it. 5.Patching optical patch cord of 10G port 8-EM6-3 of new RTN910AF(RTN01) to existing Sacofa LL 10G port. 6.Request new xD Vlan Services for traffic Q01605. 7.Finally, both traffics 9223A & Q01605 will backhaul into existing 10G IBeam port at CP 9999A. | [12 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601210805-GTSB
9766B_PL | RPR Taman IndahLandeh | DU00006529614 | Sarawak | Sarawak | 1.423467 | 110.293852 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M. NE_9766B 18G_SP_0.6M(MAC)+OMT x1. RTN910A x1 XMC_3E , Sub A_Hi x1. FE_9303A. 18G_SP_1.2M(MAC)+OMT x1. ISM8 x2 XMC_3E , Sub A_Lo x1. | MW Swap | Swap NEC MW link 9766B-9303A. with HW MW config 18G_1+0_112M. Site Impacted : 9766B , 9312B NE_9766B 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Traffic migrate to new MW link. 6.Decom NEC MW link. FE_9303A. 1.Install new 18G_SP_1.2M(MAC)+OMT. 2.Reuse existing 9303A_RTN01 ( NE ID : 24176). 3.Install new 4_ISM8-1+0 into existing 9303A_RTN01. Support 9766B. 4.Install new XMC_3E , Sub A_Lo. 5.Install new 3_ISM8-1+0 into existing 9303A_RTN01. Support 9312B. 6.Transfer existing IF cable from existing 9303A_RTN02 , 7_ISM8-1+0 , port 1 to existing 9303A_RTN01 ,3_ISM8-1+0 , port 1. 7.Remove existing ETH cable interconnect from 9303A_RTN02 to 9303A_RTN01 and disable unsued GE ports. 8.Create service cross connect. 9.All traffic migrate to existing 9303A_RTN01 , Sacofa 10G port_GE3. 10.Decom NEC MW link and existing 9303A_RTN02 ( NE ID : 24336). | Swap NEC MW link 9766B-9303A. with HW MW config 18G_1+0_112M. Site Impacted : 9766B , 9312B NE_9766B 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Traffic migrate to new MW link. 6.Decom NEC MW link. | Swap NEC MW link 9766B-9303A. with HW MW config 18G_1+0_112M. Site Impacted : 9766B , 9312B FE_9303A. 1.Install new 18G_SP_1.2M(MAC)+OMT. 2.Reuse existing 9303A_RTN01 ( NE ID : 24176). 3.Install new 4_ISM8-1+0 into existing 9303A_RTN01. Support 9766B. 4.Install new XMC_3E , Sub A_Lo. 5.Install new 3_ISM8-1+0 into existing 9303A_RTN01. Support 9312B. 6.Transfer existing IF cable from existing 9303A_RTN02 , 7_ISM8-1+0 , port 1 to existing 9303A_RTN01 ,3_ISM8-1+0 , port 1. 7.Remove existing ETH cable interconnect from 9303A_RTN02 to 9303A_RTN01 and disable unsued GE ports. 8.Create service cross connect. 9.All traffic migrate to existing 9303A_RTN01 , Sacofa 10G port_GE3. 10.Decom NEC MW link and existing 9303A_RTN02 ( NE ID : 24336). | XMC_3E | MAC | 18G | 0.6 | 1.2 | Allstar | SQ202601210169-Allstar | Allstar | SQ202603060640-Allstar // SQ202603060641-Allstar // SQ202604220807-Allstar | 2026-01-30 | 2026-01-29 | Completed | 2026-01-24 | 2026-01-30 | 2026-01-24 | 2026-01-24 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-01-24 | 2026-01-30 | 2026-01-24 | 2026-01-24 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2026-02-14 | 2026-02-20 | Completed | 2026-02-13 | 2026-02-14 | 2026-02-13 | 2026-02-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2026-02-24 | 2026-03-02 | 2026-03-12 | 2026-03-12 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-02-24 | 2026-03-02 | 2026-03-12 | 2026-03-12 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-01 | 2026-02-24 | 2026-03-02 | 2026-03-16 | 2026-03-16 | BONG NEE NYEEbong.allstar@gmail.com | 2026-02-24 | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | CHONG QIEW LEK7018000038 | Warehouse Team | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202601210786-GCI | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | CHEONG/SENG/WAH/7018000306
Q00701_PL | Q143A_Q00701OD_CB_RHSAMBAU | DU00006529615 | Sarawak | Sarawak | 1.262900 | 111.404400 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M_512QAM_EPLA NE_Q00701 New 13G_1.8M(MDD)+Dual Coupler x1. New RTN910AF(RTN01). New ISM8 x1. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x2. FE_9223A New 13G_1.8M(MDD)+Dual Coupler x1. New RTN910AF(RTN01). New ISM8 x1. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x4 RUN. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.RECOMMENDED TO CHECK LOS OK & PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.8M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL SOLUTION DU Q00701_PL & DU Q00701_PL_1 IF ITEM 1 & 2 NOT FULFILL. 4.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_1(TX MINI). 3RD - DU 9223A_PL(TX MINI). 4TH - DU Q00701_PL_2(TX MINI). 5TH - Q00701(NIC).**** Build new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M. Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. Site Impacted : Q01605. NE_Q00701 1.Install 13G_1.8M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN01)and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Lay new x4 RUN of IF cables for new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M. 5.Request new xD Vlan DCN and Vlan Services that use similar with site 9223A port at IBeam CP 9999A. 6.Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. 7.Enable electrical port 8-EM6-1 of new RTN910AF(RTN01) and also enable electrical port 7-EM10-2 of existing RTN905(NEID 82-13716) of existing HW MW Link_ID SW03716. Perform new cascading between port 8-EM6-1 of new RTN910AF(RTN01) and port 7-EM10-2 of existing RTN905(NEID 82-13716). 8.Migrate traffic Q01605 ONLY via HW MW Link 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. Traffics Q00701 & Q01569 still remain existing TX route. FE_9223A 1.Install 13G_1.8M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN01)and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new x4 RUN of IF cables for new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M. 5.Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. 6.Perform DU 9223A_PL in order for migrating traffics Q01605 and 9223A ONLY to existing 10G port IBeam(currently use by BBU 9223A) at CP 9999A. | ****IMPORTANT NOTE: 1.RECOMMENDED TO CHECK LOS OK & PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.8M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL SOLUTION DU Q00701_PL & DU Q00701_PL_1 IF ITEM 1 & 2 NOT FULFILL. 4.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_1(TX MINI). 3RD - DU 9223A_PL(TX MINI). 4TH - DU Q00701_PL_2(TX MINI). 5TH - Q00701(NIC).**** Build new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M. Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. Site Impacted : Q01605. NE_Q00701 1.Install 13G_1.8M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN01)and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Lay new x4 RUN of IF cables for new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M. 5.Request new xD Vlan DCN and Vlan Services that use similar with site 9223A port at IBeam CP 9999A. 6.Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. 7.Enable electrical port 8-EM6-1 of new RTN910AF(RTN01) and also enable electrical port 7-EM10-2 of existing RTN905(NEID 82-13716) of existing HW MW Link_ID SW03716. Perform new cascading between port 8-EM6-1 of new RTN910AF(RTN01) and port 7-EM10-2 of existing RTN905(NEID 82-13716). 8.Migrate traffic Q01605 ONLY via HW MW Link 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. Traffics Q00701 & Q01569 still remain existing TX route. | ****IMPORTANT NOTE: 1.RECOMMENDED TO CHECK LOS OK & PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.8M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL SOLUTION DU Q00701_PL & DU Q00701_PL_1 IF ITEM 1 & 2 NOT FULFILL. 4.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_1(TX MINI). 3RD - DU 9223A_PL(TX MINI). 4TH - DU Q00701_PL_2(TX MINI). 5TH - Q00701(NIC).**** Build new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M. Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. Site Impacted : Q01605. FE_9223A 1.Install 13G_1.8M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN01)and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new x4 RUN of IF cables for new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M. 5.Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. 6.Perform DU 9223A_PL in order for migrating traffics Q01605 and 9223A ONLY to existing 10G port IBeam(currently use by BBU 9223A) at CP 9999A. | XMC_5D Pro | MDD | 13G | 13G_1.8M(MDD)+Dual Coupler x1 | 13G_1.8M(MDD)+Dual Coupler x1 | NR Services | SQ202601280710-NR Services | YPTT | SQ202604100684-YPTT // SQ202604100687-YPTT | 2026-03-23 | 2026-03-17 | Completed | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-16 | 2026-03-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-16 | 2026-03-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-16 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26032748 |  | 2026-03-27 | 2026-03-31 | Completed | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-01 | 2026-04-15 | 2026-04-01 | 2026-04-24 | MUHAMMAD//NAZIRUL HAKIMI BIN DILMI/6794000014 | YPTT TI | 2026-04-01 | 2026-04-15 | 2026-04-01 | 2026-04-24 | MUHAMMAD//NAZIRUL HAKIMI BIN DILMI/6794000014 | YPTT TI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-13 | 2026-04-01 | 2026-04-15 | 2026-04-01 | 2026-04-25 | MUHAMMAD//NAZIRUL HAKIMI BIN DILMI/6794000014 | 2024-10-17: 2026-04-01; 2024-10-23: 2026-04-15; 2024-10-23: 2026-04-01; 2024-10-23: 2026-04-08 | [7 empty] | GTSB | SQ202601210805-GTSB
Q00701_PL_1 | Q143A_Q00701OD_CB_RHSAMBAU | DU00006529616 | Sarawak | Sarawak | 1.262900 | 111.404400 | [9 empty] | TSS+AA+TI |  | 15G_2+0_28M_256QAM_EPLA NE_Q00701 New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN01) under DU Q00701_PL. New ISM8 x1. New XMC_5D Pro, Sub A_Lo x1. New IF cables with suitable length and type x1 RUN. FE_9223A New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN01) under DU Q00701_PL. New ISM8 x1. New XMC_5D Pro, Sub A_Hi x1. New IF cables with suitable length and type x1 RUN. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO CHECK LOS OK & PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL SOLUTION DU Q00701_PL & DU Q00701_PL_1 IF ITEM 1 & 2 NOT FULFILL. 4.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_1(TX MINI). 3RD - DU 9223A_PL(TX MINI). 4TH - DU Q00701_PL_2(TX MINI). 5TH - Q00701(NIC).**** Build new HW MW Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M. Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. Site Impacted : Q01605. NE_Q00701 1.Install 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01) under DU Q00701_PL and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Lay new x1 RUN of IF cables for new HW MW Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M. 5.Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. 6.Migrate traffic Q01605 via HW MW Link 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. FE_9223A 1.Install 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01)and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Lay new x4 RUN of IF cables for new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M. 5.Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become HW MW Link 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. 6.Perform DU 9223A_PL in order for migrating traffics Q01605 and 9223A ONLY to existing 10G port IBeam(use currently by BBU 9223A) at CP 9999A. | ****IMPORTANT NOTE: 1.RECOMMENDED TO CHECK LOS OK & PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL SOLUTION DU Q00701_PL & DU Q00701_PL_1 IF ITEM 1 & 2 NOT FULFILL. 4.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_1(TX MINI). 3RD - DU 9223A_PL(TX MINI). 4TH - DU Q00701_PL_2(TX MINI). 5TH - Q00701(NIC).**** Build new HW MW Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M. Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. Site Impacted : Q01605. NE_Q00701 1.Install 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01) under DU Q00701_PL and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Lay new x1 RUN of IF cables for new HW MW Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M. 5.Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. 6.Migrate traffic Q01605 via HW MW Link 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. | ****IMPORTANT NOTE: 1.RECOMMENDED TO CHECK LOS OK & PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL SOLUTION DU Q00701_PL & DU Q00701_PL_1 IF ITEM 1 & 2 NOT FULFILL. 4.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_1(TX MINI). 3RD - DU 9223A_PL(TX MINI). 4TH - DU Q00701_PL_2(TX MINI). 5TH - Q00701(NIC).**** Build new HW MW Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M. Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. Site Impacted : Q01605. FE_9223A 1.Install 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01)and insert ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Lay new x4 RUN of IF cables for new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M. 5.Later, combine DU Q00701_PL(new HW MW Link Q00701-9223A, 13G_4+0_28MHZ_512QAM_EPLA_896M) and DU Q00701_PL_1(new HW MW Parallel Link Q00701-9223A, 15G_2+0_28MHZ_256QAM_EPLA_400M) and become HW MW Link 13G&15G_6+0_28MHZ_512QAM&256QAM_EPLA_1296M. 6.Perform DU 9223A_PL in order for migrating traffics Q01605 and 9223A ONLY to existing 10G port IBeam(use currently by BBU 9223A) at CP 9999A. | XMC_5D Pro | MDD | 15G | 15G_1.2M(MDD) x1 | 15G_1.2M(MDD) x1 | NR Services | SQ202601280710-NR Services | YPTT |  |  |  | Ongoing | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-16 | 2026-03-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601210805-GTSB
7494B_HU_2 | KgKoya | DU00006535519 | Sabah | Sabah | 5.275170 | 118.105220 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 15G_3+0_28M_256QAM_579M. MW Remote Upgrade to HW 15G_4+0_28M_256QAM_772M. Site Impacted : 7494B. NE_7494B 1.Remotely upgrade from 3+0_28M_256QAM_579M to 4+0_28M_256QAM_772M. FE_7581A 1.Remotely upgrade from 3+0_28M_256QAM_579M to 4+0_28M_256QAM_772M. | Link Existing HW 15G_3+0_28M_256QAM_579M. MW Remote Upgrade to HW 15G_4+0_28M_256QAM_772M. Site Impacted : 7494B. NE_7494B 1.Remotely upgrade from 3+0_28M_256QAM_579M to 4+0_28M_256QAM_772M. | Link Existing HW 15G_3+0_28M_256QAM_579M. MW Remote Upgrade to HW 15G_4+0_28M_256QAM_772M. Site Impacted : 7494B. FE_7581A 1.Remotely upgrade from 3+0_28M_256QAM_579M to 4+0_28M_256QAM_772M. | XMC_3 | MS | 15G | 15G_1.2M(MS)+Coupler x1. | 15G_1.2M(MS)+Coupler x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-25 | [15 empty] | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202601210802-GTSB
Q02310_HU | PBH Lambir 2 | DU00006545266 | Sarawak | Sarawak | 4.193250 | 114.039848 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M_512QAM_EPLA NE_Q02310 New 18G_0.6M(MDD) x1. New RTN910AF(RTN01). New XMC_5D Pro, Sub A_Hi x1. New CAT6 cable x1. FE_Q01732 New 18G_1.2M(MDD) x1. New RTN910AF(RTN01). New XMC_5D Pro, Sub A_Lo x1. New CAT6 cable x1. | MW Swap | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q02310_HU. 2ND - DU Q02235_HU_1. 2.CURRENT RSL FOR EXISTING SM MW LINK LINK_ID SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM SHOWN -43DBM(SEEM DEGRADED). THEREFORE, PLEASE CHECK LOS CLEARANCES BEFORE MOUNTING NEW ANTENNA FOR NEW SWAP HW MW LINK.**** Existing SM MW Link_SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM. MW Swap to new HW MW Link Q02310-Q01732, 18G_1+0_110MHZ_512QAM_EPLA. Later, decom existing SM MW Link_SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM after perform installation for 2nd DU Q02235_HU_1. Site Impacted : Q02310, Q02235, Q02234 & Q02236. NE_Q02310 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 5.Request new xC Vlan DCN and re-use existing Vlan Services. 6.Before perform migration traffics Q02235, Q02234 & Q02236 via new HW MW Link Q02310-Q01732, 18G_1+0_110MHZ_512QAM_EPLA. Ensure perform installation for 2nd DU Q02235_HU_1. Thus, all traffics Q02235, Q02234 & Q02236 will smooth backhauling until Q01732. 7.Later, decom existing SM MW Link_SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM after perform installation for 2nd DU Q02235_HU_1. FE_Q01732 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing port at PTN/Cisco Router. 5.Request new xC Vlan DCN and re-use existing Vlan Services. 6.Before perform migration traffics Q02235, Q02234 & Q02236 via new HW MW Link Q02310-Q01732, 18G_1+0_110MHZ_512QAM_EPLA. Ensure perform installation for 2nd DU Q02235_HU_1. Thus, all traffics Q02235, Q02234 & Q02236 will smooth backhauling until Q01732. 7.Later, decom existing SM MW Link_SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM after perform installation for 2nd DU Q02235_HU_1. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q02310_HU. 2ND - DU Q02235_HU_1. 2.CURRENT RSL FOR EXISTING SM MW LINK LINK_ID SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM SHOWN -43DBM(SEEM DEGRADED). THEREFORE, PLEASE CHECK LOS CLEARANCES BEFORE MOUNTING NEW ANTENNA FOR NEW SWAP HW MW LINK.**** Existing SM MW Link_SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM. MW Swap to new HW MW Link Q02310-Q01732, 18G_1+0_110MHZ_512QAM_EPLA. Later, decom existing SM MW Link_SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM after perform installation for 2nd DU Q02235_HU_1. Site Impacted : Q02310, Q02235, Q02234 & Q02236. NE_Q02310 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 5.Request new xC Vlan DCN and re-use existing Vlan Services. 6.Before perform migration traffics Q02235, Q02234 & Q02236 via new HW MW Link Q02310-Q01732, 18G_1+0_110MHZ_512QAM_EPLA. Ensure perform installation for 2nd DU Q02235_HU_1. Thus, all traffics Q02235, Q02234 & Q02236 will smooth backhauling until Q01732. 7.Later, decom existing SM MW Link_SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM after perform installation for 2nd DU Q02235_HU_1. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q02310_HU. 2ND - DU Q02235_HU_1. 2.CURRENT RSL FOR EXISTING SM MW LINK LINK_ID SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM SHOWN -43DBM(SEEM DEGRADED). THEREFORE, PLEASE CHECK LOS CLEARANCES BEFORE MOUNTING NEW ANTENNA FOR NEW SWAP HW MW LINK.**** Existing SM MW Link_SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM. MW Swap to new HW MW Link Q02310-Q01732, 18G_1+0_110MHZ_512QAM_EPLA. Later, decom existing SM MW Link_SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM after perform installation for 2nd DU Q02235_HU_1. Site Impacted : Q02310, Q02235, Q02234 & Q02236. FE_Q01732 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing port at PTN/Cisco Router. 5.Request new xC Vlan DCN and re-use existing Vlan Services. 6.Before perform migration traffics Q02235, Q02234 & Q02236 via new HW MW Link Q02310-Q01732, 18G_1+0_110MHZ_512QAM_EPLA. Ensure perform installation for 2nd DU Q02235_HU_1. Thus, all traffics Q02235, Q02234 & Q02236 will smooth backhauling until Q01732. 7.Later, decom existing SM MW Link_SW04226, Q02310-Q01732, 13G_1+0_28MHZ_2048QAM after perform installation for 2nd DU Q02235_HU_1. | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_1.2M(MDD) x1 | NR Services | SQ202603180539-NR Services | NR Services | SQ202603180535-NR Services // SQ202603180535-NR Services |  |  | Ongoing | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030637 |  | 2026-03-19 |  | Ongoing | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. |  | Assigned | Ongoing |  | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | NR Service TI | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | NR Service TI | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-17 | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | 2024-10-17: 2026-03-12; 2024-10-23: 2026-03-19; 2024-10-23: 2026-03-12; 2024-10-23: 2026-03-13 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202601210805-GTSB
7177A_HU | Telipok3 | DU00006545267 | Sabah | Sabah | 6.109500 | 116.206900 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI+Dismantle |  | 18G_2+0_0.6M/0.6M_MDD_112MHZ_256QAM_1556MBPS_XMC5D_SUB_A | MW Swap | MW SWAP UPGRADE LINK 7177A-7637A WITH HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_256QAM_1556MBPS_XMC5D_SUB_A_LINK_2.88KM IMPACTED: 7177A DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU AND ISM8 CARD 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | XMC5D | MDD | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601210780-GCI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
1497B_LOS | Park Royal Hotel IB | DU00006545268 | Central | Kuala Lumpur | 3.144590 | 101.712310 | [7 empty] | 03. Pending TSS |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_1497B 23G_DP_0.6M(MAC) x1 RTN910A x1. XMC_3E , Sub A & B_Hi x2. ETH cat 6 cable x1. FE_1461A. 23G_DP_0.6M (MAC) x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. | MW New Link / Reroute | Link reroute to new FE 1461A due to existing link LOS block. Install new link 23G_2+0_112M. Site Impacted : 1497B , 3209B. NE_1497B 1.Install new 23G_DP_0.6M 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Enable GE1 , transfer existing ETH patching from 1497B_RTN01_GE2 to new RTN910A_GE1. Carry 3209B. 5.Enable GE2 , ETH patching 1497B_BBU. 6.Create service cross connect and EPLA. 7.Traffic migrate to new link and new FE routing. 8.Decomm existing MW link. FE_1461A. 1.Install new 23G_DP_0.6M (MAC) 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create new Inband DCN & Create LAG. 6.Traffic migreate to new link and new FE routing. 7.Decomm existing MW link. | Link reroute to new FE 1461A due to existing link LOS block. Install new link 23G_2+0_112M. Site Impacted : 1497B , 3209B. NE_1497B 1.Install new 23G_DP_0.6M 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Enable GE1 , transfer existing ETH patching from 1497B_RTN01_GE2 to new RTN910A_GE1. Carry 3209B. 5.Enable GE2 , ETH patching 1497B_BBU. 6.Create service cross connect and EPLA. 7.Traffic migrate to new link and new FE routing. 8.Decomm existing MW link. | Link reroute to new FE 1461A due to existing link LOS block. Install new link 23G_2+0_112M. Site Impacted : 1497B , 3209B. FE_1461A. 1.Install new 23G_DP_0.6M (MAC) 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create new Inband DCN & Create LAG. 6.Traffic migreate to new link and new FE routing. 7.Decomm existing MW link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202601210056-GCI | GCI | SQ202603130067-GCI // SQ202603130074-GCI | 2026-04-15 | 2026-04-14 | Completed | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022451 |  | 2026-02-25 | 2026-02-26 | Completed | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-04-30 | 2026-04-23 | 2026-04-23 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-05-04 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | AKMAL//BIN RAZALI/6794000078 |  |  | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-05-04 | Ragunalan//A/L L.Krisnan6000006720 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-04-18 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601290544-GCI | 2026-02-24 | 2026-03-03 | 2026-02-24 | 2026-02-24 | CHEONG/SENG/WAH/7018000306
1239D_HU | JALANPENGGAWA (REL) | DU00006545269 | Central | Selangor | 3.057223 | 101.783720 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 23G_1+0_56M Remote Software Upgrade to 23G_1+0_112M | Existing link 23G_1+0_56M Remote Software Upgrade to 23G_1+0_112M | Existing link 23G_1+0_56M Remote Software Upgrade to 23G_1+0_112M | XMC_3E | MAC | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601210773-GCI | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | CHEONG/SENG/WAH/7018000306
S00186_HU_1 | S112A_S00186OD_CB_SOGOSOGO | DU00006545270 | Sabah | Sabah | 5.362920 | 116.960800 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601210802-GTSB
9523B_HU | KampungTegak | DU00006545271 | Sarawak | Sarawak | 2.885181 | 112.145214 | [9 empty] | TSS+AA+TI |  | 15G_2+0_28M_512QAM_EPLA NE_9523B New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-24445). New ISM8 x1. New XMC_5D Pro, Sub A_Hi x1. FE_9156A New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 9-24446). New ISM8 x1. New XMC_5D Pro, Sub A_Lo x1. | MW Parallel Link | Existing Huawei MW Link 13G&15G_4+0_28MHZ_256QAM&512QAM_EPLA. Build new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing Huawei MW Link 13G&15G_4+0_28MHZ_256QAM&512QAM_EPLA and new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. Site Impacted : 9523B. NE_9523B 1.Install 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-24445) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Build new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. 5.Re-use existing Vlan DCN and Vlan Services. 6.Later, combine existing Huawei MW Link 13G&15G_4+0_28MHZ_256QAM&512QAM_EPLA and new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. 7.Migrate traffic 9523B via new 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. FE_9156A 1.Install 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-24446) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Build new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. 5.Re-use existing Vlan DCN and Vlan Services. 6.Later, combine existing Huawei MW Link 13G&15G_4+0_28MHZ_256QAM&512QAM_EPLA and new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. 7.Migrate traffic 9523B via existing port of IBeam. | Existing Huawei MW Link 13G&15G_4+0_28MHZ_256QAM&512QAM_EPLA. Build new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing Huawei MW Link 13G&15G_4+0_28MHZ_256QAM&512QAM_EPLA and new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. Site Impacted : 9523B. NE_9523B 1.Install 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-24445) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Build new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. 5.Re-use existing Vlan DCN and Vlan Services. 6.Later, combine existing Huawei MW Link 13G&15G_4+0_28MHZ_256QAM&512QAM_EPLA and new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. 7.Migrate traffic 9523B via new 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. | Existing Huawei MW Link 13G&15G_4+0_28MHZ_256QAM&512QAM_EPLA. Build new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing Huawei MW Link 13G&15G_4+0_28MHZ_256QAM&512QAM_EPLA and new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. Site Impacted : 9523B. FE_9156A 1.Install 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-24446) and insert ISM8 x1 into slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Build new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. 5.Re-use existing Vlan DCN and Vlan Services. 6.Later, combine existing Huawei MW Link 13G&15G_4+0_28MHZ_256QAM&512QAM_EPLA and new parallel HW MW Link 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. 7.Migrate traffic 9523B via existing port of IBeam. | XMC_5D Pro | MDD | 15G | 15G_1.2M(MDD) x1 | 15G_1.2M(MDD) x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601210805-GTSB
9581A_HU | Tudan | DU00006545272 | Sarawak | Sarawak | 4.480804 | 114.030802 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_110M_512QAM_EPLA NE_9581A New 18G_0.6M(MDD) x1. New RTN910AF(RTN01) x1 New ISM8 x1. New XMC_5D Pro, Sub A_Lo x1. FE_9080A New 18G_0.6M(MDD) x1. New RTN910AF(RTN01) x1 New ISM8 x1. New XMC_5D Pro, Sub A_Hi x1. | MW Swap | Existing HW MW Link 9581A-9080A, 18G_1+0_55MHZ_512QAM. MW Swap HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link 9581A-9080A, 18G_1+0_55MHZ_512QAM. Site Impacted : 9581A & 9721C. NE_9581A. 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN01) and insert x1 new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Build new HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffics 9581A & 9721C via new HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. 7.Later, decom existing HW MW Link 9581A-9080A, 18G_1+0_55MHZ_512QAM. FE_9080A. 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN01) and insert x1 new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Build new HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Re-use existing port at IBeam. 7.Migrate traffics 9581A & 9721C via new HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. 8.Later, decom existing HW MW Link 9581A-9080A, 18G_1+0_55MHZ_512QAM. | Existing HW MW Link 9581A-9080A, 18G_1+0_55MHZ_512QAM. MW Swap HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link 9581A-9080A, 18G_1+0_55MHZ_512QAM. Site Impacted : 9581A & 9721C. NE_9581A. 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN01) and insert x1 new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Build new HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffics 9581A & 9721C via new HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. 7.Later, decom existing HW MW Link 9581A-9080A, 18G_1+0_55MHZ_512QAM. | Existing HW MW Link 9581A-9080A, 18G_1+0_55MHZ_512QAM. MW Swap HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link 9581A-9080A, 18G_1+0_55MHZ_512QAM. Site Impacted : 9581A & 9721C. FE_9080A. 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN01) and insert x1 new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Build new HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Re-use existing port at IBeam. 7.Migrate traffics 9581A & 9721C via new HW MW Link 9581A-9080A, 18G_2+0_110MHZ_512QAM_EPLA. 8.Later, decom existing HW MW Link 9581A-9080A, 18G_1+0_55MHZ_512QAM. | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | Magicell | SQ202603130137-Magicell | Magicell | SQ202603180492-Magicell // SQ202603180495-Magicell |  |  | Ongoing | 2026-03-12 | 2026-03-31 | 2026-03-12 | 2026-03-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-22 | 2026-04-29 | 2026-04-22 | 2026-04-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030533 |  | 2026-03-06 | 2026-04-07 | Completed | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-04-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-14 | 2026-03-31 | 2026-03-14 | 2026-04-14 | WATSON ANAK MAMBA7018000213 | Magicell TI | 2026-03-14 | 2026-03-31 | 2026-03-14 | 2026-04-14 | WATSON ANAK MAMBA7018000213 | Magicell TI | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-27 | 2026-03-14 | 2026-03-31 | 2026-03-14 | 2026-04-14 | WATSON ANAK MAMBA7018000213 | 2024-10-17: 2026-03-12; 2024-10-23: 2026-03-31; 2024-10-23: 2026-03-12; 2024-10-23: 2026-03-13 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202601210805-GTSB
9407B_HU_1 | Sungai Kut | DU00006545273 | Sarawak | Sarawak | 2.720735 | 111.839789 | [7 empty] | 05. Doable |  | TSS+AA+TI+Dismantle |  | 13G_6+0_28M NE_9407B 13G_DP_1.8M(MDD) + DP Coupler x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A & B_Lo x2. FE_9159A. 13G_DP_1.8M(MDD) + DP Coupler x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A & B_Hi x2. | MW Swap | 13/4: This DU ID for TSS only , Upon team site visit / TSS , found FE at 9159A unbale to install ant 1.8M because of space constrain issue although Hot Swap existing link. Existing link 15G_4+0_28M Due to space constraint issue. Hot Swap the existing link to new 13G_6+0_28M by using MDD+XMC_5G Pro+Dual Polar Coupler. Site Impacted : 9407B , 9560B. NE_9407B 1.Install new 13G_DP_1.8M(MDD) with DP Coupler. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A & B_Lo. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , 9407B_BBU. 7.Enable GE2 , transfer existing ETH from 9407B_RTN04_GE2 to new RTN910A_GE2 , carry 9506B child site. 8.All Traffic migrate to new MW link. 9.Decomm existing MW link (15G_4+0_28M). FE_9159A. 1.Install new 13G_DP_1.8M(MDD) with DP coupler. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A & B_Hi. 5.Create service cross connect , CA and EPLA. 6.Create New Inband DCN. 7.All Traffic migrate to new MW link. 8.Decom existing MW link.(15G_4+0_28M) | 13/4:This DU ID for TSS only , Upon team site visit / TSS , found FE at 9159A unbale to install ant 1.8M because of space constrain issue although Hot Swap existing link. Existing link 15G_4+0_28M Due to space constraint issue. Hot Swap the existing link to new 13G_6+0_28M by using MDD+XMC_5G Pro+Dual Polar Coupler. Site Impacted : 9407B , 9560B. NE_9407B 1.Install new 13G_DP_1.8M(MDD) with DP Coupler. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A & B_Lo. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , 9407B_BBU. 7.Enable GE2 , transfer existing ETH from 9407B_RTN04_GE2 to new RTN910A_GE2 , carry 9506B child site. 8.All Traffic migrate to new MW link. 9.Decomm existing MW link (15G_4+0_28M). | 13/4: This DU ID for TSS only , Upon team site visit / TSS , found FE at 9159A unbale to install ant 1.8M because of space constrain issue although Hot Swap existing link. Existing link 15G_4+0_28M Due to space constraint issue. Hot Swap the existing link to new 13G_6+0_28M by using MDD+XMC_5G Pro+Dual Polar Coupler. Site Impacted : 9407B , 9560B. FE_9159A. 1.Install new 13G_DP_1.8M(MDD) with DP coupler. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A & B_Hi. 5.Create service cross connect , CA and EPLA. 6.Create New Inband DCN. 7.All Traffic migrate to new MW link. 8.Decom existing MW link.(15G_4+0_28M) | XMC_5D | MDD | 13G | 1.8 | 1.8 | Iezzpro | SQ202604060621-Iezzpro | Iezzpro | SQ202604060613-Iezzpro // SQ202604060617-Iezzpro |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030916 |  | 2026-03-10 |  | Ongoing | 2026-03-09 | 2026-03-10 | 2026-03-09 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-08 | 2026-05-08 | 2026-04-08 |  | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | 2026-04-08 | 2026-05-08 | 2026-04-08 |  | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | [7 empty] | 2026-04-08 | 2026-05-08 | 2026-04-08 |  | MOHAMAD TARMIZI//ISWANDI/6000060946 | 2024-10-17: 2026-04-08; 2024-10-23: 2026-05-08; 2024-10-23: 2026-04-08; 2024-10-23: 2026-04-08 | [7 empty] | GCI | SQ202601210786-GCI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | CHEONG/SENG/WAH/7018000306
7670B_HU | GreatEastern Tawau | DU00006545274 | Sabah | Sabah | 4.245961 | 117.886028 | [7 empty] | 08. Pending RFS |  | TSS+AA+TI+Dismantle |  | 23G_2+0_110M_512QAM_EPLA NE_7670B New 23G_0.6M(MAC)+OMT x1. New RTN910AF(RTN02). New XMC_3E, Sub A_Lo x2. New SFP Module 10G with 10Km 1310nm x1(For patching IDU-BBU). New Optical Patch Cord cable x1 with suitable type and length. FE_7192A New 23G_0.6M(MAC)+OMT x1. New RTN910AF(RTN01). New XMC_3E, Sub A_Hi x2. New CAT6 cable x2. | MW Swap | Existing HW MW Link 7670B-7192A, 23G_1+0_55MHZ_256QAM. MW Swap HW MW Link 7670B-7192A, 23G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link 7670B-7192A, 23G_1+0_55MHZ_256QAM. Anyway, do not decom RTN910A(RTN06, NEID 9-37319) at 7192A as it share with another MW Link 7192A-->7676B. Site Impacted : 7670B. NE_7670B. 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_3E, Sub A_Lo x2. Configure it. 4.Build new HW MW Link 7670B-7192A, 23G_2+0_110MHZ_512QAM_EPLA. 5.Enable port 8-EM6-3(10G) and insert SFP Module 10G with 10Km 1310nm x1. 6.Patching port 8-EM6-3(10G) to BBU(RAN) 10G port. 7.Request new xD Vlan DCN and Vlan Services. 8.Migrate traffics 7670B via new HW MW Link 7670B-7192A, 23G_2+0_110MHZ_512QAM_EPLA. 9.Later, decom existing HW MW Link 7670B-7192A, 23G_1+0_55MHZ_256QAM. Anyway, do not decom RTN910A(RTN06, NEID 9-37319) at 7192A as it share with another MW Link 7192A-->7676B. FE_7192A. 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub A_Hi x2. Configure it. 4.Build new HW MW Link 7670B-7192A, 23G_2+0_110MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN01). 6.Request 2x new port at IBeam from ZTE IPRAN Team. 7.Perform patching and LAG 2 x1G(Electrical) between port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN01) and 2x new port at IBeam. 8.Request new xD Vlan DCN and Vlan Services. 9.Migrate traffics 7670B via new LAG 2 x1G(Electrical) at IBeam. 10.Later, decom existing HW MW Link 7670B-7192A, 23G_1+0_55MHZ_256QAM. Anyway, do not decom RTN910A(RTN06, NEID 9-37319) at 7192A as it share the same IDU with another MW Link 7192A-->7676B. | Existing HW MW Link 7670B-7192A, 23G_1+0_55MHZ_256QAM. MW Swap HW MW Link 7670B-7192A, 23G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link 7670B-7192A, 23G_1+0_55MHZ_256QAM. Anyway, do not decom RTN910A(RTN06, NEID 9-37319) at 7192A as it share with another MW Link 7192A-->7676B. Site Impacted : 7670B. NE_7670B. 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_3E, Sub A_Lo x2. Configure it. 4.Build new HW MW Link 7670B-7192A, 23G_2+0_110MHZ_512QAM_EPLA. 5.Enable port 8-EM6-3(10G) and insert SFP Module 10G with 10Km 1310nm x1. 6.Patching port 8-EM6-3(10G) to BBU(RAN) 10G port. 7.Request new xD Vlan DCN and Vlan Services. 8.Migrate traffics 7670B via new HW MW Link 7670B-7192A, 23G_2+0_110MHZ_512QAM_EPLA. 9.Later, decom existing HW MW Link 7670B-7192A, 23G_1+0_55MHZ_256QAM. Anyway, do not decom RTN910A(RTN06, NEID 9-37319) at 7192A as it share with another MW Link 7192A-->7676B. | Existing HW MW Link 7670B-7192A, 23G_1+0_55MHZ_256QAM. MW Swap HW MW Link 7670B-7192A, 23G_2+0_110MHZ_512QAM_EPLA. Later, decom existing HW MW Link 7670B-7192A, 23G_1+0_55MHZ_256QAM. Anyway, do not decom RTN910A(RTN06, NEID 9-37319) at 7192A as it share with another MW Link 7192A-->7676B. Site Impacted : 7670B. FE_7192A. 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub A_Hi x2. Configure it. 4.Build new HW MW Link 7670B-7192A, 23G_2+0_110MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN01). 6.Request 2x new port at IBeam from ZTE IPRAN Team. 7.Perform patching and LAG 2 x1G(Electrical) between port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN01) and 2x new port at IBeam. 8.Request new xD Vlan DCN and Vlan Services. 9.Migrate traffics 7670B via new LAG 2 x1G(Electrical) at IBeam. 10.Later, decom existing HW MW Link 7670B-7192A, 23G_1+0_55MHZ_256QAM. Anyway, do not decom RTN910A(RTN06, NEID 9-37319) at 7192A as it share the same IDU with another MW Link 7192A-->7676B. | XMC_3E | MAC | 23G | 23G_0.6M(MAC)+OMT x1 | 23G_0.6M(MAC)+OMT x1 | GCI |  | GCI | SQ202604100650-GCI // SQ202604100651-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031156 |  | 2026-03-12 | 2026-03-16 | Completed | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-10 | 2026-04-30 | 2026-04-10 | 2026-05-10 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-04-10 | 2026-04-30 | 2026-04-10 |  | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | [7 empty] | 2026-04-10 | 2026-04-30 | 2026-04-10 |  | RAI//JORDAN RICHARD RIBU/7018000190 | 2024-10-17: 2026-04-10; 2024-10-23: 2026-04-30; 2024-10-23: 2026-04-10; 2024-10-23: 2026-04-10 | [7 empty] | GTSB | SQ202601210802-GTSB
4694B_HU | HutanKampung(ZED) | DU00006545275 | Northern | Kedah | 6.173190 | 100.408970 |  |  |  |  | 6/2: fe hv beehive(pending clear by ff) |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X ISM8 CARD 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB B HI 1x ODU 18G XMC5D SUB B LO | MW Swap | MW SWAP UPGRADE LINK 4694B-4678A WITH HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_512QAM_1778MBPS_XMC5D_SUB_B_LINK_2.67KM IMPACTED: 4694B, 4043L DISMANTLE EXISTING LINK | 1. INSTALL NEW 1PCS ISM8 AT EXISTING RTN910A 4694B RTN02 SLOT 3 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW ISM8 AT RTN12 9-41574 SLOT 4 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK | XMC5D | MDD | 18G | 0.6 | 0.6 | GCI | SQ202603060620-GCI | GCI | SQ202602250651-GCI // SQ202602250654-GCI // SQ202603270199-GCI | 2026-03-13 | 2026-03-13 | Completed | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26012718 |  | 2026-01-28 | 2026-02-03 | Completed | 2026-01-27 | 2026-01-28 | 2026-01-27 | 2026-02-03 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-28 | 2026-02-24 | 2026-03-09 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-02-24 | 2026-02-28 | 2026-02-24 | 2026-03-09 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-05 | 2026-02-24 | 2026-02-28 | 2026-02-24 | 2026-03-09 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | 2026-02-24 | 2026-02-28 | 2026-02-24 | 2026-03-03 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | NG HONG JIE7018000036 | Logistic Team | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601210776-GCI | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | EZRIN TASNIM BIN ABDUL GANI6798000128
4043L_HU | PPAMBukit Pinang | DU00006545276 | Northern | Kedah | 6.189795 | 100.433204 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M. | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M. | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M. | XMC_3E | MAC | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601210776-GCI | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | CHEONG/SENG/WAH/7018000306
7704B-7455A | Kg. Kandang Besar | DU00005090758 | Sabah | Sabah | 5.442666 | 116.202306 |  |  |  |  | RFS | 29/05: TI done, pending RFS declare | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1x18GHz XMC3E Sub B Lo 1x18GHz XMC3E Sub B Hi | MW Hardware Upgrade | Swap ODU to XMC3E and upgrade link to 112MHz | Swap ODU to XMC3E and upgrade link to 112MHz | Swap ODU to XMC3E and upgrade link to 112MHz | XMC3E |  | 18G |  |  | YPTT | SQ202504210299-YPTT | NR services | SQ202506030434-NR Services // SQ202506030440-NR Services | 2025-05-02 | 2025-04-28 | Completed | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | DOMINIC DAVIES6794000049 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-24 | 2025-04-25 | 2025-04-24 | 2025-04-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-24 | 2025-04-25 | 2025-04-24 | 2025-04-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-28 | 2025-05-02 | 2025-04-28 | 2025-04-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051625 |  | 2025-05-17 | 2025-05-29 | Completed | 2025-05-16 | 2025-05-17 | 2025-05-16 | 2025-05-29 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-06-28 | 2025-05-28 | 2025-06-03 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-05-28 | 2025-06-28 | 2025-05-28 | 2025-07-06 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-03 | 2025-05-28 | 2025-06-28 | 2025-07-24 | 2025-07-24 | RALPH O'BRYAN HILARY7167000030 | 2025-05-28 | 2025-06-28 | 2025-05-28 | 2025-05-28 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016
7078D_HU | Glowbest Tenom REL 2 | DU00006329204 | Sabah | Sabah | 5.118467 | 115.943073 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M_512QAM_EPLA NE_7078D New 15G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01). New ISM8 x1. New XMC_5D, Sub B_Hi x1. FE_7187A New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN02). New ISM8 x1. New XMC_5D, Sub B_Lo x1. | MW Parallel Link | Existing HW MW Link 7078D-7187A, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7078D-7187A, 15G_2+0_28MHZ_512QAM_EPLA. Later combine existing and new HW MW Link become 7078D-7187A, 15G_4+0_28MHZ_512QAM_EPLA. Site Impacted : 7078D. NE_7078D 1.Install new 15G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01). Insert new ISM8 x1 into slot 03. Configure it. 3.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Parallel Link 7078D-7187A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later combine existing and new HW MW Link become 7078D-7187A, 15G_4+0_28MHZ_512QAM_EPLA. 5.Migrate traffics 7078D via HW MW Parallel Link 7078D-7187A, 15G_4+0_28MHZ_512QAM_EPLA. FE_7187A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02). Insert new ISM8 x1 into slot 03. Configure it. 3.Install new XMC_5D, Sub B_Lo x1. Build new HW MW Parallel Link 7078D-7187A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later combine existing and new HW MW Link become 7078D-7187A, 15G_4+0_28MHZ_512QAM_EPLA. 5.Migrate traffics 7078D via existing IBeam port. | Existing HW MW Link 7078D-7187A, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7078D-7187A, 15G_2+0_28MHZ_512QAM_EPLA. Later combine existing and new HW MW Link become 7078D-7187A, 15G_4+0_28MHZ_512QAM_EPLA. Site Impacted : 7078D. NE_7078D 1.Install new 15G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01). Insert new ISM8 x1 into slot 03. Configure it. 3.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Parallel Link 7078D-7187A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later combine existing and new HW MW Link become 7078D-7187A, 15G_4+0_28MHZ_512QAM_EPLA. 5.Migrate traffics 7078D via HW MW Parallel Link 7078D-7187A, 15G_4+0_28MHZ_512QAM_EPLA. | Existing HW MW Link 7078D-7187A, 15G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7078D-7187A, 15G_2+0_28MHZ_512QAM_EPLA. Later combine existing and new HW MW Link become 7078D-7187A, 15G_4+0_28MHZ_512QAM_EPLA. Site Impacted : 7078D. FE_7187A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02). Insert new ISM8 x1 into slot 03. Configure it. 3.Install new XMC_5D, Sub B_Lo x1. Build new HW MW Parallel Link 7078D-7187A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later combine existing and new HW MW Link become 7078D-7187A, 15G_4+0_28MHZ_512QAM_EPLA. 5.Migrate traffics 7078D via existing IBeam port. | XMC_5D | MDD | 15G | 15G_0.6M(MDD) x1. | 15G_1.2M(MDD) x1. | GTSB | SQ202512160977-GTSB | GTSB | SQ202512020094-GTSB // SQ202512020096-GTSB | 2026-01-26 | 2026-01-21 | Completed | 2025-12-16 | 2025-12-18 | 2025-12-16 | 2025-12-16 | PAVITRAN AL CHINNAKOLANDAY6799000150 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | PAVITRAN AL CHINNAKOLANDAY6799000150 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112425 |  | 2025-11-25 | 2025-11-27 | Completed | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-27 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-12-25 | 2025-11-25 | 2025-11-27 | ROLANDO ABIA6000017373 | GTSB TI | 2025-11-25 | 2025-12-25 | 2025-11-25 | 2025-11-27 | ROLANDO ABIA6000017373 | GTSB TI | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-28 | 2025-11-25 | 2025-12-25 | 2025-11-25 | 2025-12-03 | ROLANDO ABIA6000017373 | 2024-10-17: 2025-11-25; 2024-10-23: 2025-12-25; 2024-10-23: 2025-11-25; 2024-10-23: 2025-11-26 |  |  | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-16 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511180736-GTSB
1747H_LOS | 99 Speedmart Tmn Pelangi Semenyih 2 | DU00006342192 | Central | Selangor | 2.931340 | 101.857500 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS Radio (RTN510). NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | NLOS Link reroute to new FE 3867C due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 1747H. NE_1747H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (1747H-NLOS-2171A). FE_3867C. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.3867C_RTN01 , Enable GE2 , ETH patching to new NLOS radio. 6.Traffic migrate to new route FE and with new NLOS radio. 7.Decom existing NLOS Radio (2171A-NLOS-1747H). | NLOS Link reroute to new FE 3867C due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 1747H. NE_1747H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (1747H-NLOS-2171A). | NLOS Link reroute to new FE 3867C due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 1747H. FE_3867C. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.3867C_RTN01 , Enable GE2 , ETH patching to new NLOS radio. 6.Traffic migrate to new route FE and with new NLOS radio. 7.Decom existing NLOS Radio (2171A-NLOS-1747H). | [5 empty] | GCI | SQ202512120099-GCI | GTSB | SQ202512190073-GTSB // SQ202512190075-GTSB | 2025-12-16 | 2025-12-16 | Completed | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121785 |  | 2026-01-24 | 2025-12-22 | Completed | 2025-12-22 | 2026-01-24 | 2025-12-22 | 2025-12-22 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-22 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-22 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-22 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-29 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-02 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280798-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | CHEONG/SENG/WAH/7018000306
9388B-9366A_1 | Rh Semop | DU00004453938 | Sarawak | Sarawak | 2.418034 | 111.396973 |  | FEB 25 | [5 empty] | 00. Site Out/Drop |  |  |  | NA | Cancel / Drop | Upon TSS survey at FE 9366A Tower Full equipped with existing antenna , no space is available to install new parallel link. |  | Upon TSS survey at FE 9366A Tower Full equipped with existing antenna , no space is available to install new parallel link. | [5 empty] | Datasco | No PR required-Site drop/cancel |  |  |  |  | Ongoing | 2025-02-07 | 2025-02-11 | 2025-02-10 | [5 empty] | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01892-Q00469_1 | Q118B_Q01892OD_DESALAVANG2 | DU00004486620 | Sarawak | Sarawak | 3.374150 | 113.602780 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Upgrade existing link from 2+0 28MHz to 2+0 56MHz due to difficulty to add parallel link. Impacted site: Q01892 and Q01814 Tx route: Q01892-Q00469-Q00267 NE (Q01892): 1) Upgrade link to 56MHz FE (Q00469): 1) Upgrade link to 56MHz | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2025-04-22 | 2025-05-22 | 2025-04-22 | 2025-04-22 | IDA//NAJEEHA BINTI MAZLAN/7018000019
1069A-1702A | Lembah Beringin | DU00004486621 | Central | Selangor | 3.572448 | 101.536463 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 3/2/2025 : Decom and L1 done 26/1/2025 : Cutover done 25/1/2025 : Cutover WIP 24/1/2025 : NE installation complete, FE installation WIP 21/1/2025 : EDOTCO(M)-CSU - 60M 3 Legged Tower - NE site 1069A Lembah Beringin, Digi OB - 60M 4 Legged Tower - FE site 1702A Bkt. Tagar (Trunk) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G 2+0 1.2m/1.2m DP NE: 1) 1xRTN910A 2) 1x13GHz XMC3 Sub A Hi 3) 1x13GHz XMC3 Sub B Hi 4) 1x13GHz 1.2m DP FE: 1) 1xRTN910A 2) 1x13GHz XMC3 Sub A Lo 3) 1x13GHz XMC3 Sub B Lo 4) 1x13GHz 1.2m DP | MW Swap | Existing link SM 1069A-1702A MW3 To swap Existing link SM 13GHz 1+0 with new Huawei link 13GHz 2+0 Impacted sites: 2437A Current Tx route: 1069A-1702A New Tx route: 1069A-1702A NE (1069A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8 3) Migrate traffic to new link 4) Patch existing SM IDU for link 2437A-1069A to new RTN GE1 5) Reconfigure SM DCN 6) Decom existing link FE (1702A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8 3) Reuse existing port at CP. Migrate traffic to new link 4) Decom existing link | [7 empty] | GTSB | SQ202501270097-GTSB | GTSB | SQ202501270123-GTSB // SQ202504260131-GTSB | 2025-02-18 | 2025-02-18 | Completed | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-01-23 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-06 | 2025-02-06 | 2025-02-06 | 2025-02-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | TSSR Approved by CD | DOWMY25012021 |  | 2025-01-21 | 2025-01-23 | Completed | 2025-01-20 | 2025-01-21 | 2025-01-20 | 2025-01-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-02-27 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-02-27 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-01-26 | 2025-01-26 | 2025-01-26 | 2025-01-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-01-26 | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-02-05 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2024-10-17: 2025-01-23; 2024-10-23: 2025-01-31; 2024-10-23: 2025-01-23; 2024-10-23: 2025-01-24 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
1263C_LOS | TAMAN SERI HANECO (REL) | DU00004501217 | Central | Selangor | 2.970352 | 101.866014 |  |  |  |  | Cancel / Drop | No need proceed | ZTE | 00. Site Out/Drop | 22/11: Solution done under TX NIC 1263C_Additional |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7476A_AD | KG.PADIWAN | DU00006353968 | Sabah | Sabah | 4.998200 | 116.466800 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | Re-arrange IDU connection at 7476A to avoid bottleneck NE_7476A New CAT6 cable x2. | MW Re-engineering | ****IMPORTANT NOTE: 1.ENSURE UNDER DU 7443A_HU_1 ALREADY PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILD SITES. 2.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Site Impacted : 2788B18, 7339C, 7443A, 7476A, 7461A, 7063C & 7198R(Due to SW Version Upgrade from R21 to R23). NE_7476A 1.Ensure at RTN950A(RTN01, NEID 9-19182). Port 17-EG6-1 patching to CTS LL(Main). Port 17-EG6-2 patching to BBU 7476A. Port 17-EG6-3 disconnect/remove cascading to port 8-EM6-1 of RTN910AF(RTN03, NEID 9-43564) and perform new cascading to port 8-EM6-1 of RTN910AF(RTN05, NEID 9-36032). Port 17-EG6-4 patching to CTS LL(Standby). Port 17-EG6-5 cascading to port 8-EM6-1 of RTN910AF(RTN04, NEID 9-43864). Port 17-EG6-6 cascading to port 8-EM6-5 of RTN910AF(RTN04, NEID 9-43864). 2.Ensure at RTN910AF(RTN04, NEID 9-43864). Port 8-EM6-1 cascading to port 17-EG6-5 of RTN950A(RTN01, NEID 9-19182). Port 8-EM6-5 cascading to port 17-EG6-6 of RTN950A(RTN01, NEID 9-19182). 3.Ensure at RTN910AF(RTN05, NEID 9-36032). Port 8-EM6-1 cascading to port 17-EG6-3 of RTN950A(RTN01, NEID 9-19182). 4.Ensure at RTN910AF(RTN03, NEID 9-43564). Decom under DU 7461A_HU_1. Port 8-EM6-1 disconnect/remove cascading to port 17-EG6-3 of RTN950A(RTN01, NEID 9-19182). Port 8-EM6-2 disconnect/remove cascading to port 8-EM6-1 of RTN910AF(RTN05, NEID 9-36032). | ****IMPORTANT NOTE: 1.ENSURE UNDER DU 7443A_HU_1 ALREADY PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILD SITES. 2.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Site Impacted : 2788B18, 7339C, 7443A, 7476A, 7461A, 7063C & 7198R(Due to SW Version Upgrade from R21 to R23). NE_7476A 1.Ensure at RTN950A(RTN01, NEID 9-19182). Port 17-EG6-1 patching to CTS LL(Main). Port 17-EG6-2 patching to BBU 7476A. Port 17-EG6-3 disconnect/remove cascading to port 8-EM6-1 of RTN910AF(RTN03, NEID 9-43564) and perform new cascading to port 8-EM6-1 of RTN910AF(RTN05, NEID 9-36032). Port 17-EG6-4 patching to CTS LL(Standby). Port 17-EG6-5 cascading to port 8-EM6-1 of RTN910AF(RTN04, NEID 9-43864). Port 17-EG6-6 cascading to port 8-EM6-5 of RTN910AF(RTN04, NEID 9-43864). 2.Ensure at RTN910AF(RTN04, NEID 9-43864). Port 8-EM6-1 cascading to port 17-EG6-5 of RTN950A(RTN01, NEID 9-19182). Port 8-EM6-5 cascading to port 17-EG6-6 of RTN950A(RTN01, NEID 9-19182). 3.Ensure at RTN910AF(RTN05, NEID 9-36032). Port 8-EM6-1 cascading to port 17-EG6-3 of RTN950A(RTN01, NEID 9-19182). 4.Ensure at RTN910AF(RTN03, NEID 9-43564). Decom under DU 7461A_HU_1. Port 8-EM6-1 disconnect/remove cascading to port 17-EG6-3 of RTN950A(RTN01, NEID 9-19182). Port 8-EM6-2 disconnect/remove cascading to port 8-EM6-1 of RTN910AF(RTN05, NEID 9-36032). | [6 empty] | NR services | SQ202602250627-NR Services | NR services | SQ202602160089-NR Services | 2026-04-02 | 2026-03-30 | Completed | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-17 | 2026-03-24 | 2026-03-17 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26020455 |  | 2026-02-05 | 2026-02-14 | Completed | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-12 | 2026-03-12 | 2026-02-12 | 2026-02-14 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-12 | 2026-03-12 | 2026-02-12 | 2026-02-15 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-16 | 2026-02-12 | 2026-03-12 | 2026-02-12 | 2026-03-05 | RALPH O'BRYAN HILARY7167000030 | 2024-10-17: 2026-02-12; 2024-10-23: 2026-03-12; 2024-10-23: 2026-02-12; 2024-10-23: 2026-02-13 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511280936-GTSB
4986A_IPR | Binjul | DU00006353969 | Northern | Kedah | 5.576192 | 100.727481 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH CAT 6 Cable x 1. | IDU-IPRAN | Perform LAG at CP site for IDU 4986A-BINJUL-RTN08 to 4986A-MAC-001 Binjul Impact sites: K00320,4635A. 1) Patch IDU 4986A-BINJUL-RTN08 GE2 to new CP port 2) Create LAG | Perform LAG at CP site for IDU 4986A-BINJUL-RTN08 to 4986A-MAC-001 Binjul Impact sites: K00320,4635A. 1) Patch IDU 4986A-BINJUL-RTN08 GE2 to new CP port 2) Create LAG | [6 empty] | GTSB | SQ202512160971-GTSB | GTSB | SQ202512010617-GTSB | 2026-01-22 | 2026-01-22 | Completed | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251125BA |  | 2025-12-26 | 2025-11-28 | Completed | 2025-11-25 | 2025-12-26 | 2025-11-25 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-12 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2024-10-17: 2025-12-09; 2024-10-23: 2025-12-09; 2024-10-23: 2025-12-09; 2024-10-23: 2025-12-12 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280776-GCI | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | CHEONG/SENG/WAH/7018000306
9094A_IPR | Niah Town | DU00006353970 | Sarawak | Sarawak | 3.803504 | 113.751683 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New CAT6 cable with suitable length x1. | BBU Patching | Site Impacted: 9094A. NE_9094A 1.Request new IBeam port(Electrical) from ZTE IPRAN Team. 2.Patching BBU 9094A to new IBeam port(Electrical). 3.Migrate traffic 9094A to new IBeam port. 4.Later, disable port 8-EM6-2 at RTN910AF(RTN02, NEID 9-20636). | Site Impacted: 9094A. NE_9094A 1.Request new IBeam port(Electrical) from ZTE IPRAN Team. 2.Patching BBU 9094A to new IBeam port(Electrical). 3.Migrate traffic 9094A to new IBeam port. 4.Later, disable port 8-EM6-2 at RTN910AF(RTN02, NEID 9-20636). | [6 empty] | Allstar | SQ202601280703-Allstar | Allstar | SQ202601080404-Allstar | 2026-03-02 | 2026-02-23 | Completed | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-09 | 2026-02-03 | 2026-02-03 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122949 |  | 2025-12-31 | 2026-01-03 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-03 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-17 | 2026-01-23 | 2026-01-17 | 2026-01-17 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-17 | 2026-01-23 | 2026-01-26 | 2026-01-26 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-17 | 2026-01-17 | 2026-01-23 | 2026-01-26 | 2026-01-26 | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2026-01-17; 2024-10-23: 2026-01-23; 2024-10-23: 2026-01-17; 2024-10-23: 2026-01-17 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202511280943-GTSB
7461A_HU_1 | Nabawan RT (REL) | DU00006353971 | Sabah | Sabah | 5.041634 | 116.425916 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M_2048QAM NE_7461A New 23G_0.6M(MAC)+OMT x1. New RTN910AF(RTN02). New XMC_3E, Sub A_Hi x1. New Cat6 cables x2. FE_7443A New 23G_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN04) under DU 7443A_HU_1. New ISM8 x1. New XMC_3E, Sub A_Lo x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILDS. 3.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Existing HW MW Link 7461A(RTN03, NEID 9-43563)-7476A(RTN03, NEID 9-43564) 15G_4+0_28MHZ_512QAM_EPLA.(All Channels RSL degraded) Build new HW MW Link/Reroute 7461A-7443A, 23G_1+0_110MHZ_2048QAM. Later, may decom existing HW MW Link 7461A(RTN03, NEID 9-43563)-7476A(RTN03, NEID 9-43564) 15G_4+0_28MHZ_512QAM_EPLA. Site Impacted : 7461A & 7063C. NE_7461A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_3E, Sub A_Hi x1. Build new HW MW Link/Reroute 7461A-7443A, 23G_1+0_110MHZ_2048QAM. 4.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN02). 5.Patching BBU 7461A to port 8-EM6-1 of new RTN910AF(RTN02). 6.Perform new cascading in between port 8-EM6-2 of new RTN910AF(RTN02) and port 8-EM6-1 of existing RTN910A(RTN01, NEID 9-19553). 7.Re-use existing Vlan DCN and Vlan Services. 8.Migrate traffics 7461A & 7063C via new HW MW Link/Reroute 7461A-7443A, 23G_1+0_110MHZ_2048QAM. 9.Later, may decom existing HW MW Link 7461A(RTN03, NEID 9-43563)-7476A(RTN03, NEID 9-43564) 15G_4+0_28MHZ_512QAM_EPLA. FE_7443A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN04) under DU 7443A_HU_1. Insert new ISM8 into slot 03. 3.Install new XMC_3E, Sub A_Lo x1. Build new HW MW Link/Reroute 7461A-7443A, 23G_1+0_110MHZ_2048QAM. 4.Re-use existing Vlan DCN and Vlan Services. 5.Migrate traffics 7461A & 7063C via new uplink HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1) under DU 7443A_HU_1. 6.Later, may decom existing HW MW Link 7461A(RTN03, NEID 9-43563)-7476A(RTN03, NEID 9-43564) 15G_4+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILDS. 3.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Existing HW MW Link 7461A(RTN03, NEID 9-43563)-7476A(RTN03, NEID 9-43564) 15G_4+0_28MHZ_512QAM_EPLA.(All Channels RSL degraded) Build new HW MW Link/Reroute 7461A-7443A, 23G_1+0_110MHZ_2048QAM. Later, may decom existing HW MW Link 7461A(RTN03, NEID 9-43563)-7476A(RTN03, NEID 9-43564) 15G_4+0_28MHZ_512QAM_EPLA. Site Impacted : 7461A & 7063C. NE_7461A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_3E, Sub A_Hi x1. Build new HW MW Link/Reroute 7461A-7443A, 23G_1+0_110MHZ_2048QAM. 4.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN02). 5.Patching BBU 7461A to port 8-EM6-1 of new RTN910AF(RTN02). 6.Perform new cascading in between port 8-EM6-2 of new RTN910AF(RTN02) and port 8-EM6-1 of existing RTN910A(RTN01, NEID 9-19553). 7.Re-use existing Vlan DCN and Vlan Services. 8.Migrate traffics 7461A & 7063C via new HW MW Link/Reroute 7461A-7443A, 23G_1+0_110MHZ_2048QAM. 9.Later, may decom existing HW MW Link 7461A(RTN03, NEID 9-43563)-7476A(RTN03, NEID 9-43564) 15G_4+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILDS. 3.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Existing HW MW Link 7461A(RTN03, NEID 9-43563)-7476A(RTN03, NEID 9-43564) 15G_4+0_28MHZ_512QAM_EPLA.(All Channels RSL degraded) Build new HW MW Link/Reroute 7461A-7443A, 23G_1+0_110MHZ_2048QAM. Later, may decom existing HW MW Link 7461A(RTN03, NEID 9-43563)-7476A(RTN03, NEID 9-43564) 15G_4+0_28MHZ_512QAM_EPLA. Site Impacted : 7461A & 7063C. FE_7443A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN04) under DU 7443A_HU_1. Insert new ISM8 into slot 03. 3.Install new XMC_3E, Sub A_Lo x1. Build new HW MW Link/Reroute 7461A-7443A, 23G_1+0_110MHZ_2048QAM. 4.Re-use existing Vlan DCN and Vlan Services. 5.Migrate traffics 7461A & 7063C via new uplink HW MW Parallel Link 7443A-7476A, 18G_2+0_110MHZ_256QAM_EPLA(LINK 1) under DU 7443A_HU_1. 6.Later, may decom existing HW MW Link 7461A(RTN03, NEID 9-43563)-7476A(RTN03, NEID 9-43564) 15G_4+0_28MHZ_512QAM_EPLA. | XMC-3E | MAC | 23G | 23G_0.6M(MAC)+OMT x1. | 23G_0.6M(MAC)+OMT x1. | NR services | SQ202602250627-NR Services | NR services | SQ202602160087-NR Services // SQ202602160089-NR Services // SQ202602240605-NR Services |  |  | Ongoing | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-03 | 2026-04-10 | 2026-04-03 | 2026-04-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26020454 |  | 2026-02-05 | 2026-02-07 | Completed | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-07 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-12 | 2026-03-12 | 2026-02-12 | 2026-02-27 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-12 | 2026-03-12 | 2026-02-12 | 2026-02-27 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-13 | 2026-02-12 | 2026-03-12 | 2026-02-12 | 2026-02-27 | RALPH O'BRYAN HILARY7167000030 | 2026-02-12 | 2026-03-12 | 2026-02-12 | 2026-02-13 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511280936-GTSB
3951B11_EVT | PBTS PPR GUM-GUM (E) | DU00006353972 | Sabah | Sabah | 5.899910 | 117.922144 | [13 empty] | Planning and integration support only for event site 3951B11 PBTS PPR GUM-GUM (E) Tx route: 3951B11/3951B11-7147A-LL-7124A 1) Share port at 7147A at 7124A 2) At FE, to install link at existing 7147A RTN02 7-ISM8-1 (only 10G port left at RTN02) 3) New NE ID NE IDU 3951B11 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
4221A_IPR | Nibong Tebal | DU00006353973 | Northern | Penang | 5.167788 | 100.477854 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW Re-engineering | MW Re-Engineering for perform LAG on 2x existing IBeam(MAC 001) port and 2x existing IDU port. Site Impacted: 4222A,4102H & 4265H NE_4221A 1.Perform LAG for 2x existing port 8-EM6-1 & 8-EM6-1 of RTN910AF(RTN02 NEID 9-23718) and 2x existing port GE 0/1/0 & GE 0/1/2 of IBeam(MAC 001). 2.Migrate existing traffics 4222A,4102H & 4265H into 2x 1G LAG port. | MW Re-Engineering for perform LAG on 2x existing IBeam(MAC 001) port and 2x existing IDU port. Site Impacted: 4222A,4102H & 4265H NE_4221A 1.Perform LAG for 2x existing port 8-EM6-1 & 8-EM6-1 of RTN910AF(RTN02 NEID 9-23718) and 2x existing port GE 0/1/0 & GE 0/1/2 of IBeam(MAC 001). 2.Migrate existing traffics 4222A,4102H & 4265H into 2x 1G LAG port. | [6 empty] | GTSB | SQ202512160971-GTSB | GTSB | SQ202512010617-GTSB |  |  | Ongoing | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-17 | 2026-03-24 | 2026-03-17 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251125B9 |  | 2025-12-26 | 2025-11-28 | Completed | 2025-11-25 | 2025-12-26 | 2025-11-25 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-09 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2026-02-23 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2024-10-17: 2025-12-08; 2024-10-23: 2025-12-08; 2024-10-23: 2025-12-08; 2024-10-23: 2025-12-09 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280932-GTSB
K00704_HU_1 | K005D_K00704OD_TMNSRIBAYU | DU00006368139 | Northern | Kedah | 5.718150 | 100.545988 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 18G_2+0_56M with 256QAM. Software Remote upgrade to 18G_2+0_112M with 256QAM. | Existing link 18G_2+0_56M with 256QAM. Software Remote upgrade to 18G_2+0_112M with 256QAM. | Existing link 18G_2+0_56M with 256QAM. Software Remote upgrade to 18G_2+0_112M with 256QAM. | [5 empty] | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280776-GCI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | CHEONG/SENG/WAH/7018000306
S01598_HU | S098C_S01598OD_SKBUKITBALACON | DU00006368140 | Sabah | Sabah | 5.098294 | 118.233800 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI+Dismantle |  | 15G_2+0_28M. NE_7135K/S01598. 15G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub B_Lo FE_7101K/S00324 13G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub B_Hi | MW Parallel Link | Existing link 15G_2+0_28M. Install parallel link 15G_2+0_28M. Site Impacted : S01598. NE_7135K/S01598. 1.Install 15G_DP_0.6M(MDD) 2.Reuse existing 7135K/S01598_RTN01. 3.Install new 3_ISM8-2+0 into existing 7135K/S01598_RTN01. 4.Install new XMC_5D , Sub B_Lo. 5.Traffic migrate to new parallel link. 6.No link to decom. FE_7101K/S00324 1.Install new 15G_DP_0.6M(MDD). 2.Reuse existing 7101K/S00324_RTN01. 3.Install new 3_ISM8-2+0 into existing 7101K/S00324_RTN01. 4.Install new XMC_5D , Sub_B_Hi. 5.Traffic migrate to new parallel link. 6.No decom MW link. | Existing link 15G_2+0_28M. Install parallel link 15G_2+0_28M. Site Impacted : S01598. NE_7135K/S01598. 1.Install 15G_DP_0.6M(MDD) 2.Reuse existing 7135K/S01598_RTN01. 3.Install new 3_ISM8-2+0 into existing 7135K/S01598_RTN01. 4.Install new XMC_5D , Sub B_Lo. 5.Traffic migrate to new parallel link. 6.No link to decomm. | Existing link 15G_2+0_28M. Install parallel link 15G_2+0_28M. Site Impacted : S01598. FE_7101K/S00324 1.Install new 15G_DP_0.6M(MDD). 2.Reuse existing 7101K/S00324_RTN01. 3.Install new 3_ISM8-2+0 into existing 7101K/S00324_RTN01. 4.Install new XMC_5D , Sub_B_Hi. 5.Traffic migrate to new parallel link. 6.No decom MW link. | XMC_5D | MDD | 15G | 0.6 | 0.6 | Seri Pancar | SQ202602090132-Seri Pancar |  |  | 2026-03-05 | 2026-03-04 | Completed | 2026-02-04 | 2026-02-28 | 2026-02-12 | 2026-02-12 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202511280806-GCI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | CHEONG/SENG/WAH/7018000306
S00947_HU | S096A_S00947OD_T3_KGTELUTU | DU00006368141 | Sabah | Sabah | 7.261800 | 117.274000 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI |  | 7G_4+0_28M. NE_7092R/S00947 7G_DP_2.4M(MS)+Coupler+Waveguide x1. RTN910A x1. ISM8 x1. XMC_3E , Sub I & J_Hi x2. XMC_3E , Sub L & J_Hi x2. FE_7396A/S00576. 7G_DP_2.4M(MS)+Coupler+Waveguide x1.. RTN910A x1. ISM8 x1. XMC_3E , Sub I & J_Lo x2. XMC_3E , Sub L & J_Lo x2. ETH Cat 6 cable x2. | MW Parallel Link | Existing link 7G_2+0_28M Install parallel link parallel link 7G_4+0_28M. Upstream parallel link is priority , refer DU ID 7396A (DU code : DU00002884574). ***TSS survey and freq scanning perform upfront is necessary. Site Impacted : 7172P/S00936. NE_7092R/S00947 1.Install new 7G_DP_2.4M(MS)+Coupler + Waveguide. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub I & J_Hi for V polar. 5.Install new XMC_3E , Sub L & J_Hi for H polar. 6.Enable GE1 , transfer existing ETH from 7092R/S00947_RTN02_GE1 to new RTN910A_GE1. 7.Create service cross connect and EPLA. 8.Traffic migrate to new parallel link. 9.No MW link decomm. FE_7396A/S00576. 1.Install new 7G_DP_2.4M(MS)+Coupler+Waveguide. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub I & J_Lo for V polar. 5.Install new XMC_3E , Sub L & J_Lo for H polar. 6.Enable GE1 , transfer existing ETH from 7396A/S00576_RTN03_GE2 to new RTN910A_GE1. 7.Create service cross connect , EPLA and New Inband DCN.. 8.Traffic migrate to new parallel link. 9.No MW link decomm. | Existing link 7G_2+0_28M Install parallel link parallel link 7G_4+0_28M. TSS survey and freq scanning perform upfront is necessary. Site Impacted : 7172P/S00936. NE_7092R/S00947 1.Install new 7G_DP_2.4M(MS)+Coupler+Waveguide. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub I & J_Hi for V polar. 5.Install new XMC_3E , Sub L & J_Hi for H polar. 6.Enable GE1 , transfer existing ETH from 7092R/S00947_RTN02_GE1 to new RTN910A_GE1. 7.Create service cross connect and EPLA. 8.Traffic migrate to new parallel link. 9.No MW link decomm. | Existing link 7G_2+0_28M Install parallel link parallel link 7G_4+0_28M. TSS survey and freq scanning perform upfront is necessary. Site Impacted : 7172P/S00936. FE_7396A/S00576. 1.Install new 7G_DP_2.4M(MS)+Coupler+Waveguide. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub I & J_Lo for V polar. 5.Install new XMC_3E , Sub L & J_Lo for H polar. 6.Enable GE1 , transfer existing ETH from 7396A/S00576_RTN03_GE2 to new RTN910A_GE1. 7.Create service cross connect , EPLA and New Inband DCN.. 8.Traffic migrate to new parallel link. 9.No MW link decomm. | XMC_3E | MS | 7G | 2.4 | 2.4 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202511280806-GCI | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | CHEONG/SENG/WAH/7018000306
Q01348_HU | Q124D_Q01348OD_SENTOSACOMM | DU00006368142 | Sarawak | Sarawak | 1.477800 | 110.333250 | [9 empty] | TSS+TI |  | 2X PATCHCORD | BBU Patching | BBU patching to new link installed under NIC (NMS xD. NE 9225K/Q01348-SENTOSACOMM-RTN01) | BBU patching to new link installed under NIC (NMS xD. NE 9225K/Q01348-SENTOSACOMM-RTN01) | [6 empty] | NR Services | SQ202601210177-NR Services | NR Services | SQ202601210175-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26011502 |  | 2026-01-16 | 2026-01-15 | Completed | 2026-01-15 | 2026-01-16 | 2026-01-15 | 2026-01-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202511280911-GCI | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
1434B_HU | Sek 16 Suria Apt | DU00006368143 | Central | Selangor | 3.057870 | 101.507497 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 4X ISM8 CARD 2X 15G 0.6M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1x ODU 15G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL UPGRADE LINK 1434B-1342A WITH HUAWEI_15G_4+0_0.6M/0.6M_MDD_28MHZ_512QAM_896MBPS_XMC5D_WITH CA_SUB_B_2.2KM IMPACTED: 1434B, 1227D EPLA WITH EXISTING LINK 1+0 WITH NEW LINK 4+0 | 1. INSTALL NEW 2PCS ISM8 AT SLOT 3&4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. EPLA EXISTING LINK 1+0 WITH NEW LINK 4+0 | 1. INSTALL NEW 2PCS ISM8 AT SLOT 3&4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. EPLA EXISTING LINK 1+0 WITH NEW LINK 4+0 6. PATCH TO NEW CP PORT AND DO PORT LAG 2G | MDD | XMC5D | 15G | 0.6 | 0.6 | GTSB | SQ202512160952-GTSB | GTSB | SQ202512010569-GTSB // SQ202512010581-GTSB | 2026-01-22 | 2026-01-13 | Completed | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-08 | 2026-01-22 | 2026-01-08 | 2026-01-08 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-10 | 2026-01-09 | 2026-01-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112713 |  | 2025-12-27 | 2025-11-28 | Completed | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-24 | 2025-12-02 | 2025-12-13 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2025-12-02 | 2025-12-24 | 2025-12-02 | 2025-12-22 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2025-12-02 | 2025-12-24 | 2025-12-02 | 2026-02-24 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2024-10-17: 2025-12-02; 2024-10-23: 2025-12-24; 2024-10-23: 2025-12-02; 2024-10-23: 2025-12-15 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280798-GCI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
3240B_HU | Gamuda Walk Mall | DU00006368144 | Central | Selangor | 3.000565 | 101.533845 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M. NE_3240B 23G_SP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A_Lo x1. FE_1435B/B00056. 23G_SP_0.6M(MAC) x1. RTN910A x1. 3XMC_3E , Sub A_Hi x1. | MW Swap | Existing SM link 23G_1+0_28M. Swap existing link to 23G_1+0_112M. Site Impacted : 3240B , 3047M , 3048M. NE_3240B 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Enable GE1 , ETH patching to existing SM link , carry 3047M , 3048M. 6.Enable GE2 , ETH patching to BBU_3240B. 7.Traffic migrate to new MW link. 8.Decomm existing SM link (3240B - 1435B MW1). FE_1435B/B00056. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and New Inband DCN. 5.Traffic migrate to new MW link. 6.Decomm existing SM ;ink (1435B - 3240B MW1). | Existing SM link 23G_1+0_28M. Swap existing link to 23G_1+0_112M. Site Impacted : 3240B , 3047M , 3048M. NE_3240B 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Enable GE1 , ETH patching to existing SM link , carry 3047M , 3048M . 6.Enable GE2 , ETH patching to BBU_3240B. 7.Traffic migrate to new MW link. 8.Decomm existing SM link (3240B - 1435B MW1). | Existing SM link 23G_1+0_28M. Swap existing link to 23G_1+0_112M. Site Impacted : 3240B , 3047M , 3048M. FE_1435B/B00056. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect and New Inband DCN. 5.Traffic migrate to new MW link. 6.Decomm existing SM link (1435B - 3240B MW1). | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202512160952-GTSB | GTSB | SQ202512160942-GTSB // SQ202512160947-GTSB | 2026-03-13 | 2026-03-04 | Completed | 2026-02-09 | 2026-02-28 | 2026-02-09 | 2026-02-27 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-27 | 2026-03-13 | 2026-02-27 | 2026-02-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-27 | 2026-02-28 | 2026-02-27 | 2026-02-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25120354 |  | 2026-01-04 | 2025-12-31 | Completed | 2025-12-04 | 2026-01-04 | 2025-12-04 | 2025-12-31 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-09 | 2026-02-28 | 2026-02-09 | 2026-02-24 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-02-09 | 2026-02-28 | 2026-02-09 | 2026-02-24 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-23 | 2026-02-09 | 2026-02-28 | 2026-02-09 | 2026-03-16 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2026-02-09 | 2026-02-28 | 2026-02-09 | 2026-02-12 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280798-GCI | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | CHEONG/SENG/WAH/7018000306
4689D_HU | Klebang Ria Shoplot | DU00006368145 | Northern | Perak | 4.684521 | 101.108180 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M_512QAM_EPLA NE_4689D New 15G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-24434). New ISM8 x1. New XMC_5D, Sub B_Hi x1. FE_4346A New 15G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN23, NEID 9-24435). New ISM8 x1. New XMC_5D, Sub B_Lo x1. | MW Parallel Link | Existing HW MW Link 4689D-4346A, 18G_1+0_55MHZ_512QAM. Build new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4689D-4346A, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. Site Impacted : 4689D. NE_4689D 1.Install new 15G_0.6M(MDD) x1. 2.Re-use exsiting RTN910AF(RTN01, NEID 9-24434) insert ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 4689D-4346A, 18G_1+0_56MHZ_512QAM and new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. FE_4346A 1.Install new 15G_0.6M(MDD) x1. 2.Re-use exsiting RTN910AF(RTN01, NEID 9-24435) insert ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Lo x1. Build new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 4689D-4346A, 18G_1+0_56MHZ_512QAM and new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. | Existing HW MW Link 4689D-4346A, 18G_1+0_55MHZ_512QAM. Build new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4689D-4346A, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. Site Impacted : 4689D. NE_4689D 1.Install new 15G_0.6M(MDD) x1. 2.Re-use exsiting RTN910AF(RTN01, NEID 9-24434) insert ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 4689D-4346A, 18G_1+0_56MHZ_512QAM and new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. | Existing HW MW Link 4689D-4346A, 18G_1+0_55MHZ_512QAM. Build new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4689D-4346A, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. Site Impacted : 4689D. FE_4346A 1.Install new 15G_0.6M(MDD) x1. 2.Re-use exsiting RTN910AF(RTN01, NEID 9-24435) insert ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Lo x1. Build new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 4689D-4346A, 18G_1+0_56MHZ_512QAM and new HW MW Parallel Link 4689D-4346A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. | XMC-5D | MDD | 15G | 15G_0.6M(MDD) x1. | 15G_0.6M(MDD) x1. | GCI | SQ202512170161-GCI | GCI | SQ202512020089-GCI // SQ202512020091-GCI | 2026-01-28 | 2026-01-30 | Completed | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112652 |  | 2025-12-27 | 2025-11-28 | Completed | 2025-11-27 | 2025-12-27 | 2025-11-26 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-20 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-20 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-15 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-23 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2024-10-17: 2025-12-10; 2024-10-23: 2025-12-17; 2024-10-23: 2025-12-10; 2024-10-23: 2025-12-11 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280932-GTSB
Q02033_HU_1 | Q118B_Q02033OD_T3_COASTALHIGHWAYPLANTATIONCAMP3 | DU00006368146 | Sarawak | Sarawak | 3.461900 | 113.385940 | [9 empty] | TSS+AA+TI |  | 15G_4+0_28M_256QAM_EPLA(Without CA) NE_9316P/Q02033 New 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. New RTN910AF. New ISM8 x1. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type 4x RUN. New CAT6 cable x1. FE_Q00704 New 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. New RTN910AF. New ISM8 x1. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type 4x RUN. New SFP Module 1.25G/1G 1310nm 10Km x2.(For IDU Huawei & Cisco) New Optical Patchcord with suitable type and length x1. | MW Parallel Link | Perform Load Balancing by re-engineering. Build new HW MW Parallel 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). Site Impacted : 9316P/Q02033. NE_9316P/Q02033 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel Link 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). 4.Disconnect/remove existing patching BBU 9316P/Q02033 from port 8-EM6-2 of existing RTN910AF(RTN01, NEID 82-13831). 5.Enable port 8-EM6-1 and patching existing BBU 9316P/Q02033 into it. 6.Request new xC Vlan DCN & Vlan Services. 7.Later, migrate traffic 9316P/Q02033 into new HW MW Parallel 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). FE_Q00704 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_LHi x2. Build new HW MW Parallel Link 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). 4.Enable port 8-EM6-5 of new RTN910AF and insert new suitable Optical SFP Module. 5.Enable port Gi0/0/7 of existing PTN ID 30131 and new suitable Optical SFP Module. 6.Patching port 8-EM6-5 of new RTN910AF and port Gi0/0/7 of existing PTN ID 30131. 7.Request new xC Vlan DCN & Vlan Services. 8.Later, migrate traffic 9316P/Q02033 into new HW MW Parallel 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). | Perform Load Balancing by re-engineering. Build new HW MW Parallel 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). Site Impacted : 9316P/Q02033. NE_9316P/Q02033 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel Link 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). 4.Disconnect/remove existing patching BBU 9316P/Q02033 from port 8-EM6-2 of existing RTN910AF(RTN01, NEID 82-13831). 5.Enable port 8-EM6-1 and patching existing BBU 9316P/Q02033 into it. 6.Request new xC Vlan DCN & Vlan Services. 7.Later, migrate traffic 9316P/Q02033 into new HW MW Parallel 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). | Perform Load Balancing by re-engineering. Build new HW MW Parallel 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). Site Impacted : 9316P/Q02033. FE_Q00704 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Install new RTN910AF and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_LHi x2. Build new HW MW Parallel Link 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). 4.Enable port 8-EM6-5 of new RTN910AF and insert new suitable Optical SFP Module. 5.Enable port Gi0/0/7 of existing PTN ID 30131 and new suitable Optical SFP Module. 6.Patching port 8-EM6-5 of new RTN910AF and port Gi0/0/7 of existing PTN ID 30131. 7.Request new xC Vlan DCN & Vlan Services. 8.Later, migrate traffic 9316P/Q02033 into new HW MW Parallel 9316P/Q02033-Q00704, 15G_4+0_28MHZ_256QAM_EPLA(Without CA). | XMC-5D Pro | MDD | 15G | 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. | 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202511280943-GTSB
4047L_HU | Taman Tunku Sarina | DU00006368147 | Northern | Kedah | 6.242954 | 100.452891 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M_512QAM_EPLA NE_4047L New 15G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 44-13752). New ISM8 x1. New XMC_5D, Sub A_Hi x1. FE_K00033 New 15G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 44-23752). New ISM8 x1. New XMC_5D, Sub B_Lo x1. | MW Parallel Link | Existing HW MW Link 4047L-K00033, 18G_1+0_55MHZ_512QAM. Build new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4047L-K00033, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. Site Impacted : 4047L. NE_4047L 1.Install new 15G_0.6M(MDD) x1. 2.Re-use exsiting RTN910AF(RTN01, NEID 44-13752) insert ISM8 into slot 03. 3.Install new XMC_5D, Sub A_Hi x1. Build new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 4047L-K00033, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. FE_K00033 1.Install new 15G_0.6M(MDD) x1. 2.Re-use exsiting RTN910AF(RTN02, NEID 44-23752) insert ISM8 into slot 03. 3.Install new XMC_5D, Sub A_Lo x1. Build new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 4047L-K00033, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. | Existing HW MW Link 4047L-K00033, 18G_1+0_55MHZ_512QAM. Build new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4047L-K00033, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. Site Impacted : 4047L. NE_4047L 1.Install new 15G_0.6M(MDD) x1. 2.Re-use exsiting RTN910AF(RTN01, NEID 44-13752) insert ISM8 into slot 03. 3.Install new XMC_5D, Sub A_Hi x1. Build new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 4047L-K00033, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. | Existing HW MW Link 4047L-K00033, 18G_1+0_55MHZ_512QAM. Build new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4047L-K00033, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. Site Impacted : 4047L. FE_K00033 1.Install new 15G_0.6M(MDD) x1. 2.Re-use exsiting RTN910AF(RTN02, NEID 44-23752) insert ISM8 into slot 03. 3.Install new XMC_5D, Sub A_Lo x1. Build new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, combine existing HW MW Link 4047L-K00033, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4047L-K00033, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. | XMC-5D | MDD | 15G | 15G_0.6M(MDD) x1. | 15G_0.6M(MDD) x1. | GCI | SQ202601190071-GCI | GCI | SQ202512020089-GCI // SQ202512020091-GCI | 2026-03-02 | 2026-02-23 | Completed | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-13 | 2026-02-20 | 2026-02-13 | 2026-02-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112648 |  | 2025-12-27 | 2025-11-28 | Completed | 2025-11-27 | 2025-12-27 | 2025-11-26 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-19 | 2026-01-13 | 2026-01-14 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-01-13 | 2026-01-19 | 2026-01-13 | 2026-01-16 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-14 | 2026-01-13 | 2026-01-19 | 2026-01-13 | 2026-01-21 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2024-10-17: 2026-01-13; 2024-10-23: 2026-01-19; 2024-10-23: 2026-01-13; 2024-10-23: 2026-01-14 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280932-GTSB
4979B_HU | Naka | DU00006368148 | Northern | Kedah | 6.135834 | 100.659782 | [7 empty] | 00. Site Out/Drop |  | NA |  | 13G_4+0_28M_1028QAM_CA NE_K00623 New 13G_1.2M(MDD) x1. New RTN910AF(RTN01). New ISM8 x1. New XMC_5, Sub B_Hi x1. New CAT6 cable x1. FE_4979B New 13G_1.2M(MDD) x1. New RTN910AF(RTN05) x1. New ISM8 x1. New XMC_5, Sub B_Lo x1. New CAT6 cable x1. | Cancel / Drop | Existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Reroute to new HW MW Link K00623-4749B, 13G_4+0_28MHZ_1024QAM_CA. Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Site Impacted : K00623. NE_K00623 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01). 4.Install new XMC_5, Sub B_Hi x2. Configure it. 5.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 6.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 7.Migrate traffic K00623 via new HW MW Link K00623-4749B, 13G_4+0_28MHZ_1024QAM_CA. 8.Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. FE_4979B 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN05) and insert new ISM8 x1 into slot 03 of new RTN910AF(RTN05). 3.Install new XMC_5, Sub B_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN05). 5.Enable port 8-EM6-2 of new RTN910AF(RTN03, NEID 9-36240). 6.Perform cascading in between port 8-EM6-1 of new RTN910AF(RTN05) and port 8-EM6-2 of new RTN910AF(RTN03, NEID 9-36240). 7.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 8.Migrate traffics K00623 at IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). Seem no other traffic backhaul to IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). K00781 traffic also plan to divert into same port at IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). 9.Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. | Existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Reroute to new HW MW Link K00623-4749B, 13G_4+0_28MHZ_1024QAM_CA. Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Site Impacted : K00623. NE_K00623 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01). 4.Install new XMC_5, Sub B_Hi x2. Configure it. 5.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 6.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 7.Migrate traffic K00623 via new HW MW Link K00623-4749B, 13G_4+0_28MHZ_1024QAM_CA. 8.Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. | Existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Reroute to new HW MW Link K00623-4749B, 13G_4+0_28MHZ_1024QAM_CA. Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Site Impacted : K00623. FE_4979B 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN05) and insert new ISM8 x1 into slot 03 of new RTN910AF(RTN05). 3.Install new XMC_5, Sub B_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN05). 5.Enable port 8-EM6-2 of new RTN910AF(RTN03, NEID 9-36240). 6.Perform cascading in between port 8-EM6-1 of new RTN910AF(RTN05) and port 8-EM6-2 of new RTN910AF(RTN03, NEID 9-36240). 7.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 8.Migrate traffics K00623 at IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). Seem no other traffic backhaul to IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). K00781 traffic also plan to divert into same port at IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). 9.Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. | XMC_5D | MDD | 13G | 13G_1.2M(MDD) x1. | 13G_1.2M(MDD) x1. | GTSB | No PR required-Work done at K00623_HU | GTSB | No PR required-Work done at K00623_HU |  |  | Ongoing | 2026-01-14 | 2026-01-31 | 2026-01-14 |  | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25120495 | Material DM to K00623_HU | 2026-01-05 | 2025-12-31 | Completed | 2025-12-05 | 2026-01-05 | 2025-12-05 | 2025-12-31 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-17 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2026-01-14 | 2026-01-31 | 2026-01-14 |  | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | [7 empty] | 2026-01-14 | 2026-01-31 | 2026-01-14 |  | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | 2024-10-17: 2026-01-14; 2024-10-23: 2026-01-31; 2024-10-23: 2026-01-14 | [7 empty] | GTSB | SQ202511280932-GTSB
Q00539_HU | Q132B_Q00539OD_TUDANLOT | DU00006368149 | Sarawak | Sarawak | 4.495500 | 114.040630 | [9 empty] | TSS+AA+TI+Dismantle |  | 18G_1+0_55M_256QAM NE_Q00539/9074K New 18G_1.2M(MDD) x1. New RTN910AF. New XMC_5D Pro, Sub B_Hi x1. New CAT6 cable x1. FE_9088A New 18G_0.6M(MDD) x1. New RTN910AF. New XMC_5D Pro, Sub B_Lo x1. New CAT6 cable x1. | MW Swap | Existing SM MW Link 9074K-9088A, 18G_1+0_55MHZ_256QAM. MW Swap to new HW MW Link 9074K-9088A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing SM MW Link 9074K-9088A, 18G_1+0_55MHZ_256QAM. Site Impacted : 9074K. NE_Q00539/9074K 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF. 3.Install new XMC_5D Pro, Sub B_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF. 5.Patching existing BBU to port 8-EM6-1 of new RTN910AF. 6.May re-use existing xD vlan dcn and vlan services. 7.Migrate traffic 9074K via new HW MW Link 9074K-9088A, 18G_2+0_55MHZ_512QAM_EPLA. 8.Later, decom existing SM MW Link 9074K-9088A, 18G_1+0_55MHZ_256QAM. FE_9088A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF. 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF. 5.Patching existing LL to port 8-EM6-1 of new RTN910AF. 6.May re-use existing xD vlan dcn and vlan services. 7.Migrate traffic 9074K via existing port of IBeam. 8.Later, decom existing SM MW Link 9074K-9088A, 18G_1+0_55MHZ_256QAM. | Existing SM MW Link 9074K-9088A, 18G_1+0_55MHZ_256QAM. MW Swap to new HW MW Link 9074K-9088A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing SM MW Link 9074K-9088A, 18G_1+0_55MHZ_256QAM. Site Impacted : 9074K. NE_Q00539/9074K 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF. 3.Install new XMC_5D Pro, Sub B_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF. 5.Patching existing BBU to port 8-EM6-1 of new RTN910AF. 6.May re-use existing xD vlan dcn and vlan services. 7.Migrate traffic 9074K via new HW MW Link 9074K-9088A, 18G_2+0_55MHZ_512QAM_EPLA. 8.Later, decom existing SM MW Link 9074K-9088A, 18G_1+0_55MHZ_256QAM. | Existing SM MW Link 9074K-9088A, 18G_1+0_55MHZ_256QAM. MW Swap to new HW MW Link 9074K-9088A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing SM MW Link 9074K-9088A, 18G_1+0_55MHZ_256QAM. Site Impacted : 9074K. FE_9088A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF. 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF. 5.Patching existing LL to port 8-EM6-1 of new RTN910AF. 6.May re-use existing xD vlan dcn and vlan services. 7.Migrate traffic 9074K via existing port of IBeam. 8.Later, decom existing SM MW Link 9074K-9088A, 18G_1+0_55MHZ_256QAM. | XMC_5D Pro | MDD | 18G | 18G_1.2M(MDD) x1. | 18G_0.6M(MDD) x1. | Magicell | SQ202602160107-Magicell | Magicell | SQ202604150290-Magicell // SQ202604150306-Magicell |  |  | Ongoing | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26032418 |  | 2026-03-25 | 2026-03-25 | Completed | 2026-03-24 | 2026-03-25 | 2026-03-24 | 2026-03-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202511280943-GTSB
S02006_HU | Pontian Hillco Plantations | DU00006368150 | Sabah | Sabah | 5.471570 | 118.020029 | [7 empty] | 05. Doable |  | TSS+AA+TI |  | 13G_2+0_28M_512QAM_EPLA NE_S02006 New 13G_1.2M(MDD) x1. Re-use existing RTN910AF(NEID 88-12006). New ISM8 x1. New XMC_5D Pro, Sub B_Lo x1. New IF cables with suitable length x2 RUN. FE_S00324 New 13G_1.2M(MDD) x1. Re-use existing RTN910AF(NEID 88-22006). New ISM8 x1. New XMC_5D Pro, Sub B_Hi x1. New IF cables with suitable length x2 RUN. | MW Parallel Link | **IMPORTANT NOTE:** 1. Mandatory to perform physical Frequency Scanning for 13G.**** Existing HW MW Link S02006-S00324, 13G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel S02006-S00324, 13G_2+0_28M_512QAM_EPLA. Later, combine existing HW MW Link S02006-S00324, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. Become 13G_4+0_28MHZ_512QAM_EPLA. Site Impacted : S02006. NE_S02006 1.Install new 13G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 88-12006) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Re-use existing Vlan DCN & Vlan Services. 6.Later, combine existing HW MW Link S02006-S00324, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. Become 13G_4+0_28MHZ_512QAM_EPLA. FE_S00324 1.Install new 13G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 88-22006) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Re-use existing Vlan DCN & Vlan Services. 6.Later, combine existing HW MW Link S02006-S00324, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. Become 13G_4+0_28MHZ_512QAM_EPLA. | **IMPORTANT NOTE:** 1. Mandatory to perform physical Frequency Scanning for 13G.**** Existing HW MW Link S02006-S00324, 13G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel S02006-S00324, 13G_2+0_28M_512QAM_EPLA. Later, combine existing HW MW Link S02006-S00324, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. Become 13G_4+0_28MHZ_512QAM_EPLA. Site Impacted : S02006. NE_S02006 1.Install new 13G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 88-12006) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Re-use existing Vlan DCN & Vlan Services. 6.Later, combine existing HW MW Link S02006-S00324, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. Become 13G_4+0_28MHZ_512QAM_EPLA. | **IMPORTANT NOTE:** 1. Mandatory to perform physical Frequency Scanning for 13G.**** Existing HW MW Link S02006-S00324, 13G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel S02006-S00324, 13G_2+0_28M_512QAM_EPLA. Later, combine existing HW MW Link S02006-S00324, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. Become 13G_4+0_28MHZ_512QAM_EPLA. Site Impacted : S02006. FE_S00324 1.Install new 13G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 88-22006) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Re-use existing Vlan DCN & Vlan Services. 6.Later, combine existing HW MW Link S02006-S00324, 13G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link S02006-S00324, 13G_2+0_28M_512QAM_EPLA. Become 13G_4+0_28MHZ_512QAM_EPLA. | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD) x1 | 13G_1.2M(MDD) x1 | Seri Pancar | SQ202602090132-Seri Pancar | GCI | SQ202604200224-GCI // SQ202604200228-GCI |  |  | Ongoing | 2026-02-04 | 2026-02-28 | 2026-02-12 | 2026-02-12 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-26 | 2026-03-05 | 2026-02-26 | 2026-02-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040846 |  | 2026-04-09 | 2026-04-13 | Completed | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-03 | 2026-05-31 | 2026-05-05 | 2026-05-05 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | [33 empty] | GTSB | SQ202511280936-GTSB
2712B_HU | Sek 16 Shah Alam | DU00006368151 | Central | Selangor | 3.060145 | 101.518747 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X PATCH CORD | MW IDU Patching | MW IDU PATCHING Patch MW link 2712B-1038C-01_HNIC_Project at FE site to xC PTN 70330 (1038C/B00568) IMPACTED SITE: 2712B, 1038C |  | MW IDU PATCHING Patch MW link 2712B-1038C-01_HNIC_Project at FE site to xC PTN 70330 (1038C/B00568) IMPACTED SITE:2712B, 1038C | [5 empty] | GTSB | SQ202512160952-GTSB | GTSB | SQ202512160947-GTSB | 2026-02-11 | 2026-02-11 | Completed | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-02-10 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-11 | 2026-02-10 | 2026-02-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25120355 |  | 2026-01-04 | 2025-12-31 | Completed | 2025-12-04 | 2026-01-04 | 2025-12-04 | 2025-12-31 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-02-10 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-02-10 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-29 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-02-11 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2024-10-17: 2026-01-27; 2024-10-23: 2026-01-27; 2024-10-23: 2026-01-27; 2024-10-23: 2026-01-27 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280798-GCI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
3730C_HU | SubangHiTech Shoplot (REL) | DU00006552800 | Central | Selangor | 3.067300 | 101.561700 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing ZTE 18G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 18G_1+0_112M_512QAM. Site Impacted : 3730C. NE_3730C 1.Remotely upgrade from 18G_1+0_56M_512QAM to 18G_1+0_112M_512QAM. FE_2021B 1.Remotely upgrade from 18G_1+0_56M_512QAM to 18G_1+0_112M_512QAM. | Link Existing ZTE 18G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 18G_1+0_112M_512QAM. Site Impacted : 3730C. NE_3730C 1.Remotely upgrade from 18G_1+0_56M_512QAM to 18G_1+0_112M_512QAM. | Link Existing ZTE 18G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 18G_1+0_112M_512QAM. Site Impacted : 3730C. FE_2021B 1.Remotely upgrade from 18G_1+0_56M_512QAM to 18G_1+0_112M_512QAM. | SRU2 | DP | 18G | 0.6m | 0.6m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601290586-GTSB
B02839_HU | B065A_B02839OD_TMNBKTRWGJAYAAPTORCHID | DU00006552801 | Central | Selangor | 3.329416 | 101.586820 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK B02839-B01300 ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: B02839 | MW REMOTE UPGRADE LINK B02839-B01300 ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: B02839 | MW REMOTE UPGRADE LINK B02839-B01300 ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: B02839 | SRU2 | Z3 | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601290544-GCI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
W01460_HU | W066S_W01460OD_JLN_BKTJALIL_INDAH1 | DU00006552802 | Central | Kuala Lumpur | 3.053309 | 101.659640 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC | 18G_1+0_112Mhz_512QAM_833.3Mbps | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | B |  | 18 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601290586-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
W00660_HU | W066L_W00660IB_MENARAOCBC | DU00006552803 | Central | Kuala Lumpur | 3.150133 | 101.696182 | [9 empty] | AA | PAC | 23G_1+0_112Mhz_512QAM_833.5Mbps | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | A |  | 23 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GTSB | SQ202601290586-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
B02690_HU | B061I_B02690OD_KGKENANGAN | DU00006552804 | Central | Selangor | 3.024719 | 101.594625 | [9 empty] | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK B02690-2556B ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_1024QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_2048QAM IMPACTED SITE: B02690 | MW REMOTE UPGRADE LINK B02690-2556B ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_1024QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_2048QAM IMPACTED SITE: B02690 | MW REMOTE UPGRADE LINK B02690-2556B ZTE MW 18G_1+0_0.6M/0.6M_DP_56MHZ_1024QAM TO 18G_1+0_0.6M/0.6M_DP_112MHZ_2048QAM IMPACTED SITE: B02690 | SRU2 | Z3 | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-12 | 2026-04-12 | 2026-04-12 | 2026-04-12 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GCI | SQ202601290544-GCI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
4675D_HU | Asia Hills | DU00006552805 | Northern | Penang | 5.345670 | 100.292730 | [9 empty] | AA |  | 23G_1+0_112Mhz_512QAM_833.5Mbps | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | B |  | 23 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601290597-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
4546B_HU | MonexTimber | DU00006552806 | Northern | Perak | 4.670660 | 101.156200 | [9 empty] | AA |  |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 4546B-4515A ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_833MBPS IMPACTED SITE: 4546B | MW REMOTE UPGRADE LINK 4546B-4515A ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_833MBPS IMPACTED SITE: 4546B | MW REMOTE UPGRADE LINK 4546B-4515A ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_833MBPS IMPACTED SITE: 4546B | SRU2 | Z3 | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601290549-GCI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
4032C_HU | TamanDesa Pantai | DU00006552807 | Northern | Perak | 4.445434 | 100.626332 | [9 empty] | AA |  |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 4032C-4485A ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_256QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_737MBPS IMPACTED SITE: 4032C | MW REMOTE UPGRADE LINK 4032C-4485A ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_256QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_737MBPS IMPACTED SITE: 4032C | MW REMOTE UPGRADE LINK 4032C-4485A ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_256QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_737MBPS IMPACTED SITE: 4032C | SRU2 | Z3 | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601290549-GCI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
2608B_HU | SIMEUEP Industrial | DU00006552808 | Central | Selangor | 3.044041 | 101.553687 | [12 empty] | Existing TX | CANT REMOTE UPGRADE DUE TO TO RSL LOW | CANT REMOTE UPGRADE DUE TO TO RSL LOW | CANT REMOTE UPGRADE DUE TO TO RSL LOW | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601290544-GCI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
3753A_HU | MasjidAl-Huda Seksyen 19 | DU00006552809 | Central | Selangor | 3.053733 | 101.527931 | [9 empty] | AA | PAC | 23G_1+0_112Mhz_512QAM_833.5Mbps | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | A |  | 23 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-12 | 2026-04-12 | 2026-04-12 | 2026-04-12 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GTSB | SQ202601290586-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
4270C_HU | IKMLumut | DU00006552810 | Northern | Perak | 4.186019 | 100.652320 | [9 empty] | AA |  | 23G_1+0_112Mhz_512QAM_833.5Mbps | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | A |  | 23 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601290597-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
1906B_HU | JlnSg Tekali | DU00006552811 | Central | Selangor | 3.106247 | 101.870543 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI |  | 2X MD2 CARD 1x ODU 15G SRU2 SUB B HI 1X ODU 15G SRU2 SUB B LO 4X IF CABLE SUITABLE LENGTH | MW Hardware Upgrade | MW HARDWARE UPGRADE 1906B-1833B WITH ZXMW_15G_2+0_1.2M/1.2M_DP_28MHZ_512QAM_408MBPS_SRU2_SUB_B_WITH CA_6.00KM EXISTING ZTE MW 15G 2+0 ADDING ODU AND CARD TO BECOME 15G_4+0_1.2M/1.2M_DP_28MHZ_512QAM_816MBPS_SRU2_SUB_A&B_WITH CA IMPACTED: 1906B NE: 1. INSTALL NEW MD2 CARD AT EXISTING IDU SLOT 2 2. REUSE EXISTING 15G 1.2M ANTENNA 3. INSTALL NEW ODU 15G SRU2 28MHZ SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. CONFIGURE CA EXISTING LINK 15G 2+0 WITH NEW LINK 15G 2+0 BECOME 15G 4+0 CA FE: 1. INSTALL NEW MD2 CARD AT EXISTING IDU SLOT 2 2. REUSE EXISTING 15G 1.2M ANTENNA 3. INSTALL NEW ODU 15G SRU2 28MHZ SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. CONFIGURE CA EXISTING LINK 15G 2+0 WITH NEW LINK 15G 2+0 BECOME 15G 4+0 CA | 1. INSTALL NEW MD2 CARD AT EXISTING IDU SLOT 2 2. REUSE EXISTING 15G 1.2M ANTENNA 3. INSTALL NEW ODU 15G SRU2 28MHZ SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. CONFIGURE CA EXISTING LINK 15G 2+0 WITH NEW LINK 15G 2+0 BECOME 15G 4+0 CA | 1. INSTALL NEW MD2 CARD AT EXISTING IDU SLOT 2 2. REUSE EXISTING 15G 1.2M ANTENNA 3. INSTALL NEW ODU 15G SRU2 28MHZ SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. CONFIGURE CA EXISTING LINK 15G 2+0 WITH NEW LINK 15G 2+0 BECOME 15G 4+0 CA | SRD2 | Z3 | 15G | 1.2 | 1.2 | GTSB | SQ202601300950-GTSB | GTSB | SQ202601300939-GTSB // SQ202601300942-GTSB |  |  | Ongoing | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started |  | 2026-02-27 | 2026-02-28 | 2026-02-27 | 2026-02-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Full Site DR | 2026-01-29 | 2026-02-07 | Completed | 2026-01-28 | 2026-01-29 | 2026-01-28 | 2026-02-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-28 | 2026-02-23 |  | SYLVESTER JULUS6000068068 | GTSB TI | 2026-02-23 | 2026-02-28 | 2026-02-23 |  | SYLVESTER JULUS6000068068 | GTSB TI | [7 empty] | 2026-02-23 | 2026-02-28 | 2026-02-23 |  | SYLVESTER JULUS6000068068 | 2024-10-17: 2026-02-23; 2024-10-23: 2026-02-28; 2024-10-23: 2026-02-23 | [7 empty] | GCI | SQ202601290544-GCI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
4295C_HU | IpohBestari Shoplot | DU00006552812 | Northern | Perak | 4.616215 | 101.120100 | [9 empty] | AA |  | 23G_1+0_112Mhz_512QAM_833.5Mbps | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | A |  | 23 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601290597-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
2605B_HU | KesasBillboard USJ 3 | DU00006552813 | Central | Selangor | 3.063438 | 101.572142 | [9 empty] | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 2605B-2021B ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1666MBPS IMPACTED SITE: 2605B | MW REMOTE UPGRADE LINK 2605B-2021B ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1666MBPS IMPACTED SITE: 2605B | MW REMOTE UPGRADE LINK 2605B-2021B ZTE MW 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1666MBPS IMPACTED SITE: 2605B | SRU3D | Z3 | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-12 | 2026-04-12 | 2026-04-12 | 2026-04-12 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GCI | SQ202601290544-GCI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
B01721_HU | B061I_B01721OD_PT235 | DU00006552814 | Central | Selangor | 3.041370 | 101.570500 | [9 empty] | AA | PAC |  | MW Remote Upgrade | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M Site Impacted : 1277K / B01721 | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M Site Impacted : 1277K / B01721 | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M Site Impacted : 1277K / B01721 | SRU2 | SP | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-12 | 2026-04-12 | 2026-04-12 | 2026-04-12 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GCI | SQ202601290544-GCI | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | CHEONG/SENG/WAH/7018000306
2746C_HU | PalmaApartment - Country Homes | DU00006552815 | Central | Selangor | 3.325730 | 101.533510 | [9 empty] | AA |  |  | MW Remote Upgrade | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 2746C. NE_2746C 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. FE_3256A 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 2746C. NE_2746C 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 2746C. FE_3256A 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | SRU2 | DP | 23G | 0.6m | 0.6m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601290586-GTSB
1576B_HU | pBTSArulmigu Sri Muneeswarar Temple | DU00006552816 | Central | Selangor | 3.245367 | 101.680344 | [9 empty] | AA | PAC |  | MW Remote Upgrade | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M Site Impacted : 1576B | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M Site Impacted : 1576B | Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M Site Impacted : 1576B | SRU2 | DP | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GCI | SQ202601290544-GCI | 2026-01-24 | 2026-01-24 | 2026-01-24 | 2026-01-24 | CHEONG/SENG/WAH/7018000306
4063B_HU | pBTSKg. Pasir Hor ( C) | DU00006552817 | Northern | Kelantan | 6.081107 | 102.267440 | [9 empty] | AA | PAC | 23G_1+0_112Mhz_512QAM_833.5Mbps | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | B |  | 23 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601290597-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
4469D_HU | TamanSeri Bunga | DU00006552818 | Northern | Perak | 4.114340 | 101.285220 | [9 empty] | AA | PAC |  | MW Remote Upgrade | Existing link 23G_1+0_56M Remote Software Upgrade to 23G_1+0_112M Site Impacted : 4469D | Existing link 23G_1+0_56M Remote Software Upgrade to 23G_1+0_112M Site Impacted : 4469D | Existing link 23G_1+0_56M Remote Software Upgrade to 23G_1+0_112M Site Impacted : 4469D | SRU2 | DP | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-27 | [20 empty] | GCI | SQ202601290549-GCI | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-25 | CHEONG/SENG/WAH/7018000306
4053C_HU | TMJelapang | DU00006552819 | Northern | Perak | 4.629454 | 101.061998 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC | 18G_1+0_55Mhz_1024QAM_430Mbps | MW Remote Upgrade | Upgrade remotely Modulation 512QAMMhz to 1024QAM |  |  | A |  | 18 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601290597-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
B02613_HU | B058C_B02613OD_JLNIMPIAN3BDRBOTANIKKLG | DU00006552820 | Central | Selangor | 2.994630 | 101.457178 | [9 empty] | AA | PAC | 23G_1+0_112Mhz_512QAM_833.5Mbps | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | B |  | 23 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-12 | 2026-04-12 | 2026-04-12 | 2026-04-12 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GTSB | SQ202601290586-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
4531B_HU | IpohGarden 2 RDD | DU00006552821 | Northern | Perak | 4.610930 | 101.110070 | [9 empty] | AA |  |  | MW Remote Upgrade | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 4531B & 4311H. NE_4531B 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. FE_4520A 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 4531B & 4311H. NE_4531B 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 4531B & 4311H. FE_4520A 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | SRU2 | DP | 23G | 0.6m | 0.6m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601290597-GTSB
A00950_HU | A040C_A00950OD_ANJUNGTAWASIPH | DU00006552822 | Northern | Perak | 4.654325 | 101.120870 | [9 empty] | AA |  |  | MW Remote Upgrade | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M. Site Impacted : 4019K/A00950 | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M. Site Impacted : 4019K/A00950 | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M. Site Impacted : 4019K/A00950 | SRU2 | DP | 18 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601290549-GCI | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-25 | CHEONG/SENG/WAH/7018000306
4606C_HU | JalanTeluk BatikLumut | DU00006552823 | Northern | Perak | 4.209390 | 100.613000 | [9 empty] | AA |  | 23G_1+0_112Mhz_512QAM_833.5Mbps | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | A |  | 23 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601290597-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
3182B_HU | pBTSBkt Serdang Ind (M) | DU00006552824 | Central | Selangor | 3.032895 | 101.692366 | [9 empty] | AA | PAC |  | MW Remote Upgrade | Existing link 18G_1+0_28M Remote Software Upgrade to 18G_1+0_112M Site Impacted : 3182B | Existing link 18G_1+0_28M Remote Software Upgrade to 18G_1+0_112M Site Impacted : 3182B | Existing link 18G_1+0_28M Remote Software Upgrade to 18G_1+0_112M Site Impacted : 3182B | SRU2 | DP | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GCI | SQ202601290544-GCI | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-25 | CHEONG/SENG/WAH/7018000306
N00759_HU | WTKOLEJ MATRIX N9 | DU00006552825 | Southern | Sembilan | 2.713224 | 102.240280 | [9 empty] | AA |  |  | MW Remote Upgrade | Existing link 18G_1+0_56M Remote Software upgrade to 18G_1+0_112M Site Impacted : N00759 | Existing link 18G_1+0_56M Remote Software upgrade to 18G_1+0_112M Site Impacted : N00759 | Existing link 18G_1+0_56M Remote Software upgrade to 18G_1+0_112M Site Impacted : N00759 | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601290576-GCI | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-25 | CHEONG/SENG/WAH/7018000306
1114A_HU | JlnTepi Sungai | DU00006552826 | Central | Selangor | 3.046130 | 101.435948 | [9 empty] | AA |  |  | MW Remote Upgrade | Link Existing ZTE 18G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 18G_1+0_112M_512QAM. Site Impacted : 1114A. NE_1114A 1.Remotely upgrade from 18G_1+0_56M_512QAM to 18G_1+0_112M_512QAM. FE_1071A 1.Remotely upgrade from 18G_1+0_56M_512QAM to 18G_1+0_112M_512QAM. | Link Existing ZTE 18G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 18G_1+0_112M_512QAM. Site Impacted : 1114A. NE_1114A 1.Remotely upgrade from 18G_1+0_56M_512QAM to 18G_1+0_112M_512QAM. | Link Existing ZTE 18G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 18G_1+0_112M_512QAM. Site Impacted : 1114A. FE_1071A 1.Remotely upgrade from 18G_1+0_56M_512QAM to 18G_1+0_112M_512QAM. | SRU2 | DP | 18G | 0.6m | 0.6m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601290586-GTSB
1206B_HU | Jln Kastam | DU00006552827 | Central | Selangor | 3.010830 | 101.402816 | [9 empty] | AA |  |  | MW Remote Upgrade | Existing link 23G_1+0_56M Remote Software upgrade to 23G_1+0_112M Site Impacted : 1206B ,4351H | Existing link 23G_1+0_56M Remote Software upgrade to 23G_1+0_112M Site Impacted : 1206B ,4351H | Existing link 23G_1+0_56M Remote Software upgrade to 23G_1+0_112M Site Impacted : 1206B ,4351H | SRU2 | DP | 23G | 0.6 | 0.6 | GCI | No PR required-Remote Upgrade | GCI | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | Cancel DO | 2026-02-24 |  | Ongoing | 2026-02-23 | 2026-02-24 | 2026-02-23 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202601290544-GCI | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-25 | CHEONG/SENG/WAH/7018000306
4038C_HU | SeriLarut | DU00006552828 | Northern | Perak | 4.829946 | 100.701532 | [9 empty] | AA |  |  | MW Remote Upgrade | Existing link 23G_1+0_56M Remote Software upgrade to 23G_1+0_112M Site Impacted : 4038C | Existing link 23G_1+0_56M Remote Software upgrade to 23G_1+0_112M Site Impacted : 4038C | Existing link 23G_1+0_56M Remote Software upgrade to 23G_1+0_112M Site Impacted : 4038C | SRU2 | DP | 23G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601290549-GCI | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-25 | CHEONG/SENG/WAH/7018000306
3593B_HU | pBTSKesas Kebun Interchange (C) | DU00006552829 | Central | Selangor | 2.988987 | 101.515703 | [9 empty] | AA |  |  | MW Remote Upgrade | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 3593B. NE_3593B 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. FE_1110A 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 3593B. NE_3593B 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 3593B. FE_1110A 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | SRU2 | DP | 23G | 0.6m | 0.6m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601290586-GTSB
B00798_HU | TmBeranang | DU00006552830 | Central | Selangor | 2.868090 | 101.870350 | [9 empty] | AA |  | 18G_1+0_112Mhz_512QAM_833.5Mbps | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | A |  | 18 | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601290586-GTSB | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | AB.RAHMAN//BIN MAT NOOH/6237001519
K00416_HU_1 | K007B_K00416OD_BATUPUTEH | DU00006552831 | Northern | Kedah | 5.452032 | 100.633393 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M_512QAM_EPLA(WO CA) NE_K00416/4202K New 13G_1.2M(MDD)+Dual Coupler x1. New RTN910AF(RTN06). New ISM8 x1. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x2. FE_4968A New 13G_1.2M(MDD)+Dual Coupler x1. New RTN910AF(RTN10). New ISM8 x1. New XMC_5D Pro, Sub A&B_Lox2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. BOTH DU K00416_HU_1 & DU 4982B_HU_1 PROPOSE TO USE 13GHZ CHANNEL. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K00416_HU_1. 2ND - DU 4982B_HU_1.**** Build new HW MW Link 4202K/K00416-4968A, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). Site Impacted : 4982B & 4135R. NE_4202K/K00416 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN06) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel Link 4202K/K00416-4968A, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). 4.Enable port 8-EM6-1 of new RTN910AF(RTN06). 5.Enable port 8-EM6-1 of new RTN910AF(RTN07).(under DU 4982B_HU_1) 6.Perform cascading in between port 8-EM6-1 of new RTN910AF(RTN06) to port 8-EM6-1 of new RTN910AF(RTN07).(under DU 4982B_HU_1) 7.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 8.Migrate traffics 4982B & 4135R into new HW MW Link 4202K/K00416-4968A, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). FE_4968A 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN10) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel Link 4202K/K00416-4968A, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). 4.Enable port 8-EM6-1 of new RTN910AF(RTN10). 5.Enable port 8-EM6-2 of new RTN910AF(RTN10). 6.Request new x2 port of 1G electrical of IBeam. 7.Patching port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN10) to x2 port of 1G electrical of IBeam and perform LAG. 8.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 9.Migrate traffics 4982B & 4135R into new 2x electrical port of 1G(LAG) at IBeam CP 4968A. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. BOTH DU K00416_HU_1 & DU 4982B_HU_1 PROPOSE TO USE 13GHZ CHANNEL. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K00416_HU_1. 2ND - DU 4982B_HU_1.**** Build new HW MW Link 4202K/K00416-4968A, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). Site Impacted : 4982B & 4135R. NE_4202K/K00416 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN06) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel Link 4202K/K00416-4968A, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). 4.Enable port 8-EM6-1 of new RTN910AF(RTN06). 5.Enable port 8-EM6-1 of new RTN910AF(RTN07).(under DU 4982B_HU_1) 6.Perform cascading in between port 8-EM6-1 of new RTN910AF(RTN06) to port 8-EM6-1 of new RTN910AF(RTN07).(under DU 4982B_HU_1) 7.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 8.Migrate traffics 4982B & 4135R into new HW MW Link 4202K/K00416-4968A, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. BOTH DU K00416_HU_1 & DU 4982B_HU_1 PROPOSE TO USE 13GHZ CHANNEL. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K00416_HU_1. 2ND - DU 4982B_HU_1.**** Build new HW MW Link 4202K/K00416-4968A, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). Site Impacted : 4982B & 4135R. FE_4968A 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN10) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel Link 4202K/K00416-4968A, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). 4.Enable port 8-EM6-1 of new RTN910AF(RTN10). 5.Enable port 8-EM6-2 of new RTN910AF(RTN10). 6.Request new x2 port of 1G electrical of IBeam. 7.Patching port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN10) to x2 port of 1G electrical of IBeam and perform LAG. 8.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 9.Migrate traffics 4982B & 4135R into new 2x electrical port of 1G(LAG) at IBeam CP 4968A. | XMC_5D Pro | MDD | 13G | 13G_1.2M(MDD)+Dual Coupler x1 | 13G_1.2M(MDD)+Dual Coupler x1 | GTSB | SQ202602100694-GTSB | GTSB | SQ202602100661-GTSB // SQ202602100668-GTSB |  |  | Ongoing | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-31 | 2026-04-07 | 2026-03-31 | 2026-03-31 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26020912 |  | 2026-02-10 | 2026-02-11 | Completed | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-11 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-03-05 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-03-05 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | AKMAL//BIN RAZALI/6794000078 |  |  | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-03-10 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2024-10-17: 2026-02-10; 2024-10-23: 2026-02-28; 2024-10-23: 2026-02-10; 2024-10-23: 2026-02-11 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202602120266-GTSB
2295A-1288A | Estana Court | DU00004259883 | Central | Selangor | 3.200658 | 101.764130 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 21/10: D2: Cutover done. Post-CO T/S ongoing 18/10: EB CRQ approved. Plan RFS by 23/10 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub B Lo 3) 1x18GHz 0.6m SP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub B Hi 3) 1x18GHz 0.6m SP | MW Swap | Existing link SM 2295A-1288A MW1 To swap Existing link 15GHz 2+0 with new Huawei link 18GHz 1+0 112MHz Impacted sites: 2295A Current Tx route: 2295A-1288A New Tx route: 2295A-1288A NE (2295A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Patch BBU 2295A to new RTN910A port GE1 4) Decom existing link FE (1288A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Patch new RTN GE1 to new CP port (if no port available can reuse existing port) 4) Migrate 2295A traffic to new link. Create DCN 5) Decom existing link | [7 empty] | YPTT | SQ202410280478-YPTT | YPTT | SQ202410100843-YPTT | 2024-11-28 | 2024-11-27 | Completed | 2024-10-24 | 2024-10-24 | 2024-10-24 | 2024-10-24 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-24 | 2024-10-24 | 2024-10-24 | 2024-10-24 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-21 | 2024-11-22 | 2024-11-21 | 2024-11-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-27 | 2024-11-28 | 2024-11-27 | 2024-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24100869 |  | 2024-10-09 | 2024-10-11 | Completed | 2024-10-08 | 2024-10-09 | 2024-10-08 | 2024-10-11 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-18 | 2024-11-17 | 2024-10-18 |  | NORDIN/BIN/MAT REJAB/6794000106 | YPTT TI | 2024-10-18 | 2024-11-17 | 2024-10-18 |  | NORDIN/BIN/MAT REJAB/6794000106 | YPTT TI | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-22 | SHUJAAT//ALI/6800000124 |  |  | 2024-10-18 | 2024-11-17 | 2024-10-18 | 2024-10-23 | NORDIN/BIN/MAT REJAB/6794000106 | 2024-10-17: 2024-10-18; 2024-10-23: 2024-11-17; 2024-10-23: 2024-10-18; 2024-10-23: 2024-10-18 |  |  | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
1731H_LOS | 99 Speedmart Tmn Bkt Kinrara | DU00004286218 | Central | Selangor | 3.041720 | 101.636480 | WK06 | FEB 25 | WK06 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 4/2/2025 : Cutover done 9/1/2025 : NE installation complete, pending install FE site due to keys issue 8/1/2025 : Cancel proceed due to raining day 6/1/2025 : Digi OB - Small Cell - NE site 1731H 99 Speedmart Tmn Bkt Kinrara, EDOTCO (M) SDN BHD - MINI STRUCTURE 9M LAND - FE site B01483 B061J_B01483OD_BK4BDRKINRARA 24/12: Proceed NLOS solution. Pending TSS 29/11: Drop, no available LOS, will be fiberized | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | Swap new NLOS equipment and change to new height NE_1731H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. FE_1373B 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. 6. ETH Cable x1. | MW New Link / Reroute | Based on actual TSS survey , no LOS block to existing FE 1373B.Maintain the same FE 1373B. | 1731H to 1373B , no LOS block based on actual TSS LOS survey. | 1373B-1731H , no LOS block via actual TSS LOS survey. | [5 empty] | YPTT | SQ202412230230-YPTT | YPTT | SQ202501030384-YPTT // SQ202504260171-YPTT | 2025-07-02 | 2025-07-01 | Completed | 2024-12-24 | 2025-02-20 | 2025-02-20 | 2025-02-20 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-20 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-05 | 2025-03-06 | 2025-03-05 | 2025-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010398 |  | 2025-01-04 | 2025-02-20 | Completed | 2025-01-03 | 2025-01-04 | 2025-01-03 | 2025-02-20 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-07 | 2025-01-31 | 2025-01-07 |  | YAP//WEI LOON/6794000068 | YPTT TI | 2025-01-08 | 2025-01-31 | 2025-01-08 |  | YAP//WEI LOON/6794000068 | YPTT TI | 2025-02-03 | 2025-02-03 | 2025-02-03 | 2025-02-03 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-02-05 | YAP//WEI LOON/6794000068 | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-01-08 | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300116-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
1739H_LOS | 99 Speedmart Puchong Bandar Puteri 2 | DU00004286219 | Central | Selangor | 3.026320 | 101.624070 | WK02 | JAN 25 | WK02 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 10/1/2025 : Cutover done 9/1/2025 : Cutover WIP 8/1/2025 : Cancel proceed due to raining day 6/1/2025 : Digi OB - Small Cell - NE site 1739H 99 Speedmart Puchong Bandar Puteri 2, Digi OB - 3M Boom - RT - FE site 1320B Bandar Puteri 1 24/12: Proceed NLOS solution. Pending TSS 29/11: Drop, no available LOS, will be fiberized | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | New NLOS equipment due to LOS Block. NE_1739H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. FE_1320B 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1 6. ETH cable / LAN cable x1. | MW New Link / Reroute | Link reroute to new FE 1320B with new NLOS equipment due to LOS Block. NE_1739H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. FE_1320B 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect & In Band DCN. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. | [7 empty] | YPTT | SQ202412230230-YPTT | YPTT | SQ202501030384-YPTT // SQ202504260171-YPTT |  |  | Ongoing | 2025-03-11 | 2025-03-31 | 2025-03-11 | 2025-03-11 | MOHD//SHAHREEZAN BIN RAZALI/6794000119 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250103A2 |  | 2025-01-04 | 2025-01-10 | Completed | 2025-01-03 | 2025-01-04 | 2025-01-03 | 2025-01-10 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-10 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-10 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-09 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-10 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-08 | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2025-01-24 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300116-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
1675H_LOS | 99 Speedmart Tmn Kinrara Sek 5 | DU00004286220 | Central | Selangor | 3.037687 | 101.646770 | WK03 | JAN 25 | WK03 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 14//2025 : Cutover done 13/1/2025 : FE installation complete, pending install NE site 6/1/2025 : Digi OB - Small Cell - NE site 1675H 99 Speedmart Tmn Kinrara Sek 5, CELCOM (M) Rainbow - 3M Boom - RT - FE site 3289A LADANGKINRARA1 24/12: Proceed NLOS solution. Pending TSS 29/11: Drop, no available LOS, will be fiberized | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Swap new NLOS equipment and change NLOS height NE_1675H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. FE_1420B 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. 6. ETH / LAN cable x1. | MW New Link / Reroute | Actual TSS LOS survey no LOS block , follow existing FE 1420B. | No LOS Block via TSS LOS survey. Remain existing FE 1420B | No LOS Block via TSS LOS survey. Remain existing FE 1420B | [5 empty] | YPTT | SQ202412230230-YPTT | YPTT | SQ202501030384-YPTT // SQ202504260171-YPTT |  |  | Ongoing | 2025-03-11 | 2025-03-31 | 2025-03-11 | 2025-03-11 | MOHD//SHAHREEZAN BIN RAZALI/6794000119 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250103A6 |  | 2025-01-04 | 2025-01-17 | Completed | 2025-01-03 | 2025-01-04 | 2025-01-03 | 2025-01-17 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-13 | 2025-01-31 | 2025-01-13 | 2025-01-17 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2025-01-12 | 2025-01-31 | 2025-01-12 | 2025-01-17 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2025-01-14 | 2025-01-14 | 2025-01-14 | 2025-01-14 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-01-12 | 2025-01-31 | 2025-01-12 | 2025-01-15 | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | 2025-01-12 | 2025-01-31 | 2025-01-12 | 2025-01-14 | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2025-01-24 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300116-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
4490B_LOS | Digi Telemart Greentown Business | DU00004286221 | Northern | Perak | 4.598673 | 101.093824 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_4490B 18G_DP_0.6m(MDD) x1. RTN910A x1. XMC_5D , Sub B_Hi x1. FE_4546A 18G_DP_0.6m(MDD) x1. RTN910A x1. XMC_5D ,Sub B_Lo x1. | MW New Link / Reroute | Link reroute to new FE 4546A with 18G_2+0_112M due to LOS Block. NE_4490B 1.Install new 18G_DP_0.6m(MDD). 2.Install new RTN910A , 7_ISM8-2+0 3.Install XMC_5D-2+0 , Sub B_Hi. 4.Enable EPLA and service cross connect. 5.Traffic migrate to new route FE. 6.Decom existing MW link. FE_4546A 1.Install new 18G_DP_0.6m(MDD). 2.Install new RTN910A ,7_ISM8-2+0. 3.Install XMC_5D-2+0 ,Sub B_Lo. 4.Enable EPLA and service cross connect. 5.Traffic migrate to new link. 6.Create In Band DCN. 7.Decom existing MW link. | [7 empty] | GCI | SQ202505160529-GCI | GCI | SQ202411260115-GCI // SQ202505150106-GCI // SQ202505150106-GCI // SQ202508140738-GCI | 2025-11-11 | 2025-11-10 | Completed | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-24 | 2025-07-23 | 2025-07-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021057 |  | 2025-02-11 | 2025-02-13 | Completed | 2025-02-10 | 2025-02-11 | 2025-02-10 | 2025-02-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-09 | 2025-05-31 | 2025-05-09 | 2025-05-19 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2025-05-09 | 2025-05-31 | 2025-05-09 | 2025-07-06 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-16 | 2025-05-09 | 2025-05-31 | 2025-05-09 | 2026-03-31 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2024-10-17: 2025-05-09; 2024-10-23: 2025-05-31; 2024-10-23: 2025-05-09; 2024-10-23: 2025-05-14 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505190519-GCI | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | CHEONG/SENG/WAH/7018000306
1234H_LOS | 99 Speedmart TMN WAWASAN PUCHONG 2 | DU00004286222 | Central | Selangor | 3.035660 | 101.625130 | WK04 | JAN 25 | WK04 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 27/1/2025 : Cutover done 23/1/2025 : Rectify NMS, need to troubleshoot IF cable to declare 22/1/2025 : Cancel proceed due to team stuck at other site 21/1/2025 : Cancel proceed spillover tomorrow 20/1/2025 : Cutover WIP 16/1/2025 : EB CRQ000005047457 approved 20 - 22 Jan 13/1/2025 : Installation complete, pending cutover due to need waiting EB CRQ 9/1/2025 : FE installation complete, pending install NE site due to waiting ACDC material release 8/1/2025 : Cancel proceed due to raining day 6/1/2025 : Digi OB - Small Cell - NE site 1234H 99 Speedmart TMN WAWASAN PUCHONG 2, Digi OB - 30M Monopole - FE site 2508A Puchong Jaya LP (REL) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Swap new NLOS equipment and change to new Height NE_1234H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable x1. FE_1410B 1. Nlos-OptiX RTN /PI-DC B10 /Power injector x1. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material x1. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket x1. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V x1. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH /LAN Cable x1 | MW Swap | Based on actual TSS LOS survey , there has No LOS block from NE to FE (1234H to 1410B). TSS Report is require to capture the picture after survey on the site. | NE to existing FE 1410B no LOS block based on actual TSS LOS survey. | [6 empty] | YPTT | SQ202412230230-YPTT | YPTT | SQ202501030384-YPTT // SQ202504260171-YPTT | 2025-07-02 | 2025-07-01 | Completed | 2024-12-24 | 2025-01-31 | 2025-01-20 | 2025-01-21 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-05 | 2025-03-06 | 2025-03-05 | 2025-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250103AA |  | 2025-01-04 | 2025-01-21 | Completed | 2025-01-03 | 2025-01-04 | 2025-01-03 | 2025-01-21 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-21 | JOSEF/BIN/ABSARI/6794000120 | YPTT TI | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-01-21 | JOSEF/BIN/ABSARI/6794000120 | YPTT TI | 2025-01-27 | 2025-01-27 | 2025-01-27 | 2025-01-27 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-27 | JOSEF/BIN/ABSARI/6794000120 | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-08 | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 | GTSB_AA | SQ202510300116-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
1323H_LOS | 99 Speedmart TMN KAJANG MEWAH | DU00004286223 | Central | Selangor | 2.975859 | 101.780200 | WK03 | JAN 25 | WK03 | JAN 25 | Cancel / Drop | No LOS to proceed | ZTE | 00. Site Out/Drop | 15/1/2025 : Survey not done, need to change FE site 6/1/2025 : Digi OB - Small Cell - NE site 1323H 99 Speedmart TMN KAJANG MEWAH, Digi OB - Small Cell - FE site 1482H 99 Speedmart TMN SEPAKAT INDAH 29/11: Drop, no available LOS, will be fiberized | TSS |  | New NLOS RTN510 equipment . NE_1323H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_1482H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH Cable or LAN Cable | MW New Link / Reroute | NO LOS DURING SURVEY. CANCEL DROP | [7 empty] | YPTT | No PR required-Site drop/cancel | YPTT | No PR required-Site drop/cancel |  |  | Ongoing | 2025-03-11 | 2025-03-31 | 2025-03-11 | 2025-03-11 | MOHD//SHAHREEZAN BIN RAZALI/6794000119 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250103AI |  | 2025-01-04 |  | Ongoing | 2025-01-03 | 2025-01-04 | 2025-01-03 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2025-01-15 | 2025-01-31 | 2025-01-15 |  | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | 2025-01-15 | 2025-01-31 | 2025-01-15 |  | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | YPTT TI | [7 empty] | 2025-01-15 | 2025-01-31 | 2025-01-15 |  | MOHD//AZLIY BIN ABDUL RAHMAN/6794000045 | 2024-10-17: 2025-01-15; 2024-10-23: 2025-01-31; 2024-10-23: 2025-01-15; 2024-10-23: 2025-01-15
1035D_AD | Salak South Garden (REL) | DU00006759680 | Central | Kuala Lumpur | 3.084262 | 101.692182 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X 23G 0.6M MAC ANTENNA 1x ODU 23G XMC3 SUB A HI 1x ODU 23G XMC3 SUB A LO 1x ODU 23G XMC3 SUB B HI 1x ODU 23G XMC3 SUB B LO | MW Swap | MW SWAP LINK 1035D-1121B WITH HUAWEI_23G_2+0_0.6M/0.6M_MAC_112MHZ_512QAM_1776MBPS_XMC3_SUB_A&B_LINK_0.99KM DISMANTLE EXISTING LINK IMPACTED: 1035D NEW LINK UPGRADE DUE TO WILL ALSO CARRY DU 3292B_LOS REROUTE | 1. REUSE EXISTING RTN910 RNT01 SLOT 7-1 AND 7-2 2. INSTALL NEW 23G 0.6M MAC ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM | 1. REUSE EXISTING RTN910 SLOT 7-1 AND 7-2 2. INSTALL NEW 23G 0.6M MAC ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM | XMC3 | MAC | 23G | 0.6 | 0.6 | GCI | SQ202604280451-GCI | GCI | SQ202604280454-GCI // SQ202604280620-GCI |  |  | Ongoing | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042151 |  | 2026-04-22 | 2026-04-22 | Completed | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-05-06 | 2026-04-28 | 2026-04-30 | LEEROY QUIRINUS6000070995 | GCI TI | 2026-04-29 | 2026-05-06 | 2026-04-28 |  | LEEROY QUIRINUS6000070995 | GCI TI | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | AZRUL FIKRAM BIN MOHD THANI6237000863 |  | 2026-05-01 | 2026-04-29 | 2026-05-06 | 2026-04-28 |  | LEEROY QUIRINUS6000070995 | 2026-04-29 | 2026-05-06 | 2026-04-28 | 2026-04-30 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | NG HONG JIE7018000036 | Logistic Team | [5 empty] | GCI | SQ202604280367-GCI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | EZRIN TASNIM BIN ABDUL GANI6798000128
7960A_PORT | Umas | DU00006773189 | Sabah | Sabah | 4.476952 | 117.666226 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | TRANSFER BBU FROM 7960A RTN01 8-EM6-1 TO 10G PORT 8-EM6-3 IMPACTED SITE: 7960A,7667A | TRANSFER BBU FROM 7960A RTN01 8-EM6-1 TO 10G PORT 8-EM6-3 IMPACTED SITE: 7960A,7667A | [6 empty] | NR Services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050457 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | [7 empty] | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2024-10-17: 2026-05-06; 2024-10-23: 2026-06-06; 2024-10-23: 2026-05-06 | [7 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
S00468_PORT | S106A_S00468OD_CB_TAGASAN | DU00006773190 | Sabah | Sabah | 4.414137 | 118.522111 | [9 empty] | TSS+TI |  | NE_S00468 New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF x2). New Optical Patch Cord cable with suitable type and length. | MW Re-engineering | Site Impacted :S00468, S01445, S01443, S00589 & S01172. NE_S00468 1.Perform 10G port upgrade. 2.RTN02(no 10G port)-RTN01 10G and swap existing RTN910AF(RTN02, NEID 88-28555) with new RTN910AF. 3.RTN02(8-EM6-1)-RTN01(17SLF2EM6-1) cascade remove. 4.RTN02(8-EM6-3)-RTN01(17SLF2EM6-2) cascade remove. 5.RTN02(8-EM6-4)-RTN01(17SLF2EM6-4) cascade remove. | Site Impacted :S00468, S01445, S01443, S00589 & S01172. NE_S00468 1.Perform 10G port upgrade. 2.RTN02(no 10G port)-RTN01 10G and swap existing RTN910AF(RTN02, NEID 88-28555) with new RTN910AF. 3.RTN02(8-EM6-1)-RTN01(17SLF2EM6-1) cascade remove. 4.RTN02(8-EM6-3)-RTN01(17SLF2EM6-2) cascade remove. 5.RTN02(8-EM6-4)-RTN01(17SLF2EM6-4) cascade remove. | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050452 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | [7 empty] | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2024-10-17: 2026-05-06; 2024-10-23: 2026-06-06; 2024-10-23: 2026-05-06 | [7 empty] | GTSB | SQ202604280434-GTSB
9340A_PORT | BatuKitang | DU00006773191 | Sarawak | Sarawak | 1.456350 | 110.290920 | [9 empty] | TSS+TI |  | Fiber Patch Cord x1 pairs 10G SFP Module x2. | MW IDU Patching | 9340A_RTN01 to NR01 upgrade to 10G. | 9340A_RTN01 to 9340A_NR01 upgrade to 10G. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050463 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | CHEONG/SENG/WAH/7018000306
9085A_PORT | HolidayPark | DU00006773209 | Sarawak | Sarawak | 4.323753 | 113.972735 | [9 empty] | TSS+TI | L1+ATP+PAC | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 9085A RTN01-RTN02 10G 10G PORT IDU RTN01-RTN02 IMPACTED SITE: 9085A, 9933A, 9928A 1. INSTALL 1 10G SFP OPTICAL AT HW 9085A RTN01 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9085A RTN02 8-EM6-3 3. PATCHING PATCH CORD 9085A RTN01 8-EM6-3 TO HW 9085A RTN02 8-EM6-3 4. RECONFIGURE TRAFFIC | 9085A RTN01-RTN02 10G 10G PORT IDU RTN01-RTN02 IMPACTED SITE: 9085A, 9933A, 9928A 1. INSTALL 1 10G SFP OPTICAL AT HW 9085A RTN01 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9085A RTN02 8-EM6-3 3. PATCHING PATCH CORD 9085A RTN01 8-EM6-3 TO HW 9085A RTN02 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050470 |  | 2026-05-14 |  | Ongoing | 2026-05-08 | 2026-05-14 | 2026-05-04 |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | ALL STAR ENGINEERING SDN. BHD. |  | Assigned | Ongoing |  | 2026-05-08 | 2026-05-14 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | [6 empty] | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-08 | 2026-05-08 | 2026-05-14 |  |  | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2026-05-08; 2024-10-23: 2026-05-14; 2024-10-23: 2026-05-08; 2024-10-23: 2026-05-08 | [7 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00939_PORT | Q120A_Q00939OD_KGBRUIT | DU00006773193 | Sarawak | Sarawak | 2.711986 | 111.367744 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber Patch Cord x 1 pairs | MW IDU Patching | SW03727 Q00939_GE2 to SW03546 Q00939_GE1 upgrade to 10G | SW03727 Q00939_GE2 to SW03546 Q00939_GE1 upgrade to 10G | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050465 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
K00337_PORT | K010A_K00337OD_BKTPATONG | DU00006773194 | Northern | Kedah | 6.036521 | 100.530932 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x patch cord | MW Re-engineering | Re-enginnering RTN01-RTN02 from 1G port to 10G port Site impact: 4676B 1. Insert 10GE SFP into RTN01 Slot 8 port 3 and RTN02 Slot 8 port 3 2. Patch cable from RTN01 Slot 8 port 3 10GE and RTN02 Slot 8 port 3 10GE 3. Migrate tracffic to the new 10GE connection 4, Remove connection RTN01 Slot 8 port 1 to RTN02 Slot 8 port 1 | 1. Insert 10GE SFP into RTN01 Slot 8 port 3 and RTN02 Slot 8 port 3 2. Patch cable from RTN01 Slot 8 port 3 10GE and RTN02 Slot 8 port 3 10GE 3. Migrate tracffic to the new 10GE connection 4, Remove connection RTN01 Slot 8 port 1 to RTN02 Slot 8 port 1 Site impact: 4676B | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050503 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280421-GTSB | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | LIM//WEI CHONG/6798000110
7015C_PORT | TamanBerjaya | DU00006773195 | Sabah | Sabah | 4.249394 | 117.922412 | [9 empty] | TSS+TI |  | NE_7015C New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and ZTE BBU). New Optical Patch Cord cable with suitable type and length. | MW Re-engineering | Site Impacted :7015C. NE_7015C 1.Perform BBU upgrade from 1G(Electrical) port to 10G(Optical) port. 2.Enable port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-43229) and insert suitable SFP Module 10G 10Km 1310nm. Configure it. 3.Patching 10G port of BBU and port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-43229). | Site Impacted :7015C. NE_7015C 1.Perform BBU upgrade from 1G(Electrical) port to 10G(Optical) port. 2.Enable port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-43229) and insert suitable SFP Module 10G 10Km 1310nm. Configure it. 3.Patching 10G port of BBU and port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-43229). | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050458 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | [7 empty] | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2024-10-17: 2026-05-06; 2024-10-23: 2026-06-06; 2024-10-23: 2026-05-06 | [7 empty] | GTSB | SQ202604280434-GTSB
9469A_PORT_1 | LunduFerry | DU00006773196 | Sarawak | Sarawak | 1.655920 | 109.864623 | [9 empty] | TSS+AA+TI+Dismantle |  | RTN910AF x1 | MW Hardware Upgrade | NE_9469A_RTN01 1.9469A_910A_RTN01 upgrade to RTN910AF with support 10G Fiber port. 2.Reconfigure all existing 2+0 Radio parameters into New RTN910A. 3.Reconfigure existing DCN VLAN and Traffic. 4.Upgrade Port to 10G for cascading 9469A_RTN03. 5.All traffic migrate to new RTN910AF. 6.Decom existing Old RTN910A (ID : 20021) only. | NE_9469A_RTN01 1.9469A_910A_RTN01 upgrade to RTN910AF with support 10G Fiber port. 2.Reconfigure all existing 2+0 Radio parameters into New RTN910A. 3.Reconfigure existing DCN VLAN and Traffic. 4.Upgrade Port to 10G for cascading 9469A_RTN03. 5.All traffic migrate to new RTN910AF. 6.Decom existing Old RTN910A (ID : 20021) only. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050466 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | CHEONG/SENG/WAH/7018000306
9469A_PORT | LunduFerry | DU00006773197 | Sarawak | Sarawak | 1.655920 | 109.864623 | [9 empty] | TSS+TI |  | Fiber Patch Cord x1 pairs 10G SFP Module x2. | MW IDU Patching | ***Required Hardware upgrade for 9469A_RTN01 first under DU 9469A_Port_1. NE_9469A_RTN01 9469A_RTN04 to 9469A_RTN01 upgrade 10G. | ***Required Hardware upgrade for 9469A_RTN01 first under DU 9469A_Port_1. NE_9469A_RTN01 9469A_RTN04 to 9469A_RTN01 upgrade 10G. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050467 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | CHEONG/SENG/WAH/7018000306
7586A_PORT | Kg.Suan Lamba | DU00006773198 | Sabah | Sabah | 5.646599 | 118.128209 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7586A RTN01-RTN03 10G 10G PORT IDU RTN01-RTN03 IMPACTED SITE: 7745B, 7127K 1. INSTALL 1 10G SFP OPTICAL AT HW 7586A RTN01 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7586A RTN03 8-EM6-3 3. PATCHING PATCH CORD 7586A RTN01 8-EM6-3 TO HW 7586A RTN03 8-EM6-3 4. RECONFIGURE TRAFFIC | 7586A RTN01-RTN03 10G 10G PORT IDU RTN01-RTN03 IMPACTED SITE: 7745B, 7127K 1. INSTALL 1 10G SFP OPTICAL AT HW 7586A RTN01 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7586A RTN03 8-EM6-3 3. PATCHING PATCH CORD 7586A RTN01 8-EM6-3 TO HW 7586A RTN03 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050430 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
4477C_PORT | TamanRia Jaya - KCY88 | DU00006773199 | Northern | Kedah | 5.650962 | 100.519544 | [9 empty] | TSS+TI |  | NE_4477C New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and ZTE BBU). New Optical Patch Cord cable with suitable type and length. | MW Re-engineering | Site Impacted :4477C. NE_4477C 1.Perform BBU upgrade from 1G(Electrical) port to 10G(Optical) port. 2.Enable port 8-EM6-3 of existing RTN910AF(RTN02, NEID 9-30356) and insert suitable SFP Module 10G 10Km 1310nm. Configure it. 3.Patching 10G port of BBU and port 8-EM6-3 of existing RTN910AF(RTN02, NEID 9-30356). | Site Impacted :4477C. NE_4477C 1.Perform BBU upgrade from 1G(Electrical) port to 10G(Optical) port. 2.Enable port 8-EM6-3 of existing RTN910AF(RTN02, NEID 9-30356) and insert suitable SFP Module 10G 10Km 1310nm. Configure it. 3.Patching 10G port of BBU and port 8-EM6-3 of existing RTN910AF(RTN02, NEID 9-30356). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050310 |  | 2026-05-04 | 2026-05-05 | Completed | 2026-05-03 | 2026-05-04 | 2026-05-03 | 2026-05-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604280421-GTSB
4731A_PORT | Trolak(Trunk) | DU00006773200 | Northern | Perak | 3.924760 | 101.329880 | [9 empty] | TSS+TI |  | NE_4731A New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted :4416B, 4196R & 4786B. NE_4731A Perform 1G LAG for RTN05(Port 8-EM6-1 & 8-EM6-5) and RTN02(Port 8-EM6-2 & 8-EM6-5). | Site Impacted :4416B, 4196R & 4786B. NE_4731A Perform 1G LAG for RTN05(Port 8-EM6-1 & 8-EM6-5) and RTN02(Port 8-EM6-2 & 8-EM6-5). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050309 |  | 2026-05-04 | 2026-05-05 | Completed | 2026-05-03 | 2026-05-04 | 2026-05-03 | 2026-05-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604280421-GTSB
9375B_PORT | RantauPanjang | DU00006773201 | Sarawak | Sarawak | 2.416068 | 111.839302 | [9 empty] | TSS+TI |  | Fiber Patch Cord x 1 pairs. 10G SFP Module x 2. | BBU Patching | 9375B_BBU upgrade to 10G at 9375B_RTN01. | 9375B_BBU upgrade to 10G at 9375B_RTN01. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050468 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | CHEONG/SENG/WAH/7018000306
3141C_PORT | ManipalHospital IB | DU00006773202 | Central | Selangor | 3.009942 | 101.431765 | [9 empty] | TSS+TI | L1+ATP+PAC | NE_3141C New CAT 6 cable with suitable length x1. | MW Re-engineering | Site Impacted :3638B & 1634B. NE_3141C Perform 1G LAG for RTN01(Port 8-EG6-3 & 8-EG6-4) and RTN02(Port 8-EM6-1 & 8-EM6-2). | Site Impacted :3638B & 1634B. NE_3141C Perform 1G LAG for RTN01(Port 8-EG6-3 & 8-EG6-4) and RTN02(Port 8-EM6-1 & 8-EM6-2). | [6 empty] | Magicell |  | Magicell | SQ202605070530-Magicell |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042957 |  | 2026-05-04 | 2026-05-04 | Completed | 2026-04-29 | 2026-05-04 | 2026-04-29 | 2026-05-04 | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2027-04-23 | 2026-04-29 | 2026-05-08 | RAZALI//BIN ABDUL HALIM/7018000224 | Magicell TI | 2026-04-29 | 2027-04-23 | 2026-04-29 |  | RAZALI//BIN ABDUL HALIM/7018000224 | Magicell TI | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-29 | 2027-04-23 | 2026-04-29 |  | RAZALI//BIN ABDUL HALIM/7018000224 | 2024-10-17: 2026-04-29; 2024-10-23: 2027-04-23; 2024-10-23: 2026-04-29; 2024-10-23: 2026-05-08 | [7 empty] | GTSB | SQ202604280393-GTSB
7061C_PORT | SandakanSquare | DU00006773203 | Sabah | Sabah | 5.868025 | 118.115544 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | TRANSFER BBU FROM 7061C RTN01 8-EM6-1 TO 10G PORT 8-EM6-3 IMPACTED SITE: 7061C | TRANSFER BBU FROM 7061C RTN01 8-EM6-1 TO 10G PORT 8-EM6-3 IMPACTED SITE: 7061C | [6 empty] | NR services |  | NR services |  |  |  | Ongoing | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050449 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-08 | 2026-06-08 | 2026-05-08 |  | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-05-08 | 2026-06-08 | 2026-05-08 |  | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | [7 empty] | 2026-05-08 | 2026-06-08 | 2026-05-08 |  | IBRAHIM//BIN SAHABU/7167000007 | 2024-10-17: 2026-05-08; 2024-10-23: 2026-06-08; 2024-10-23: 2026-05-08; 2024-10-23: 2026-05-08 | [7 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
7399A_PORT | Kg.Tigaman SBC | DU00006773204 | Sabah | Sabah | 6.623917 | 116.731470 | [9 empty] | TSS+TI |  | NE_7399A New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted :7596A, 7955A & 7214H. NE_7399A Perform 1G LAG for RTN03(Port 8-EM6-1 & 8-EM6-5) and RTN01(Port 8-EM6-1 & 8-EM6-5). | Site Impacted :7596A, 7955A & 7214H. NE_7399A Perform 1G LAG for RTN03(Port 8-EM6-1 & 8-EM6-5) and RTN01(Port 8-EM6-1 & 8-EM6-5). | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050438 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280434-GTSB
1960A_PORT | IntercitySubang | DU00006773205 | Central | Selangor | 3.050312 | 101.595032 | [9 empty] | TSS+TI |  | NE_1960A New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted : 1655C, 1380B & 2555B. NE_1960A Perform 1G LAG for RTN01(Port 8-EM6-1 & 8-EM6-5) and RTN04(Port 8-EM6-2 & 8-EM6-5). | Site Impacted : 1655C, 1380B & 2555B. NE_1960A Perform 1G LAG for RTN01(Port 8-EM6-1 & 8-EM6-5) and RTN04(Port 8-EM6-2 & 8-EM6-5). | [6 empty] | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042973 |  | 2026-05-04 |  | Ongoing | 2026-04-29 | 2026-05-04 | 2026-04-29 |  | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280393-GTSB
7031C_PORT_1 | KampungLandung Ayang | DU00006773206 | Sabah | Sabah | 6.884027 | 116.840887 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | PATCH BBU TO NEW IDU 910AF 10G PORT 8-EM6-3 WITH 10G SFP | PATCH BBU TO NEW IDU 910AF 10G PORT 8-EM6-3 WITH 10G SFP | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050440 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
7104Z_PORT | T3E_0697_IOIUnico Desa Plantation | DU00006773207 | Sabah | Sabah | 5.417608 | 118.528320 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x Optical cable | MW Re-engineering | Upgrade 1G to 10G RTN05-RTN02 Connect casscade 10G port RTN05-RTN02 Remove existing casscade RTN05-RTN02 site impact: 3055C, 7104Z, 7648E, 7649E, 7650E, 7651E, 7656E | Patch cable 10G port and remove exsiting cascade | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050444 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280434-GTSB | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | AB.RAHMAN//BIN MAT NOOH/6237001519
7031C_PORT | KampungLandung Ayang | DU00006773208 | Sabah | Sabah | 6.884027 | 116.840887 | [9 empty] | TSS+TI+Dismantle |  | 1X IDU RTN910A | MW Re-engineering | SWAP EXISTING 7031C RTN01 WITH NEW IDU RTN910A 2. REPATCH IF CABLE LINK 7031C-7014A SLOT 7-1 & 7-2 3. REPATCH CASCADE TO RTN02 4. DU 7031C_PORT_1 (PATCH BBU TO 10G PORT 8-EM6-3) IMPACTED SITE: 7031C, 7014A | 1. SWAP EXISTING 7031C RTN01 WITH NEW IDU RTN910A 2. REPATCH IF CABLE LINK 7031C-7014A SLOT 7-1 & 7-2 3. REPATCH CASCADE TO RTN02 4. DU 7031C_PORT_1 (PATCH BBU TO 10G PORT 8-EM6-3) IMPACTED SITE: 7031C, 7014A | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050441 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
K01033_AD | KG BUKIT JAMBUL | DU00006786424 | Northern | Kedah | 5.949400 | 100.462230 | [9 empty] | TSS+AA+TI |  | Perform MW Hardware Upgrade 18G_2+0_110MHZ_512QAM_EPLA. NE_K01033 Re-use existing 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 44-13963). Re-use existing ISM8 Slot 03. Re-use existing XMC_5D Pro, Sub B_Lo x1. New IF cable with suitable length and type x1 RUN. FE_K00828 Re-use existing 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 44-23963). Re-use existing ISM8 Slot 03. Re-use existing XMC_5D Pro, Sub B_Hi x1. New IF cable with suitable length and type x1 RUN. | MW Hardware Upgrade | Perform MW Hardware Upgrade 18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : K01033. NE_K01033 1.Re-use existing 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-13963) and re-use existing ISM8 slot 03. 3.Re-use existing XMC_5D Pro, Sub B_Lo x1. 4.Lay new IF cable with suitable length and type 1x RUN from 2nd IF port at existing ODU, XMC_5D Pro, Sub B_Lo and terminate at existing ISM8 slot 03 Port 1 of existing RTN910AF(RTN01, NEID 44-13963). 5.Build new HW MW Link 18G_2+0_110MHZ_512QAM_EPLA. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic K01033 into new HW MW Link 18G_2+0_110MHZ_512QAM_EPLA. FE_K00828 1.Re-use existing 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-23963) and re-use existing ISM8 slot 03. 3.Re-use existing XMC_5D Pro, Sub B_Hi x1. 4.Lay new IF cable with suitable length and type 1x RUN from 2nd IF port at existing ODU, XMC_5D Pro, Sub B_Hi and terminate at existing ISM8 slot 03 Port 1 of existing RTN910AF(RTN01, NEID 44-23963). 5.Build new HW MW Link 18G_2+0_110MHZ_512QAM_EPLA. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic K01033 into existing port of PTN/Cisco at CP(K00148). | Perform MW Hardware Upgrade 18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : K01033. NE_K01033 1.Re-use existing 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-13963) and re-use existing ISM8 slot 03. 3.Re-use existing XMC_5D Pro, Sub B_Lo x1. 4.Lay new IF cable with suitable length and type 1x RUN from 2nd IF port at existing ODU, XMC_5D Pro, Sub B_Lo and terminate at existing ISM8 slot 03 Port 1 of existing RTN910AF(RTN01, NEID 44-13963). 5.Build new HW MW Link 18G_2+0_110MHZ_512QAM_EPLA. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic K01033 into new HW MW Link 18G_2+0_110MHZ_512QAM_EPLA. | Perform MW Hardware Upgrade 18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : K01033. FE_K00828 1.Re-use existing 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-23963) and re-use existing ISM8 slot 03. 3.Re-use existing XMC_5D Pro, Sub B_Hi x1. 4.Lay new IF cable with suitable length and type 1x RUN from 2nd IF port at existing ODU, XMC_5D Pro, Sub B_Hi and terminate at existing ISM8 slot 03 Port 1 of existing RTN910AF(RTN01, NEID 44-23963). 5.Build new HW MW Link 18G_2+0_110MHZ_512QAM_EPLA. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic K01033 into existing port of PTN/Cisco at CP(K00148). | XMC_5D Pro | MDD | 18G | Re-use existing 18G_0.6M(MDD) x1 | Re-use existing 18G_0.6M(MDD) x1 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050512 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-08 | 2026-06-01 | 2026-05-08 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-05-08 | 2026-06-01 | 2026-05-08 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-05-09 | 2026-05-09 | 2026-05-09 | 2026-05-09 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-09 | 2026-05-08 | 2026-06-01 | 2026-05-08 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2024-10-17: 2026-05-08; 2024-10-23: 2026-06-01; 2024-10-23: 2026-05-08; 2024-10-23: 2026-05-09 | [7 empty] | GTSB | SQ202605060266-GTSB
9386B_PORT | Balingian | DU00006773210 | Sarawak | Sarawak | 2.929831 | 112.542775 | [9 empty] | TSS+TI |  | Fiber Patch Cord x 1pairs 10G SFP Module x2. | MW IDU Patching | 9386B_RTN01 to RTN02 upgrade to 10G. | 9386B_RTN01 to RTN02 upgrade to 10G. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050471 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | CHEONG/SENG/WAH/7018000306
Q00122_PORT | Q117A_Q00122OD_CB_TMSPAOH | DU00006773211 | Sarawak | Sarawak | 1.536516 | 111.490485 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber patch cord x 1 pairs. | MW IDU Patching | SW03506 Q00122_GE1 upgrade to 10G. | SW03506 Q00122_GE1 upgrade to 10G. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050473 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | CHEONG/SENG/WAH/7018000306
7110A_PORT | KgMelewar | DU00006773212 | Sabah | Sabah | 5.254450 | 118.050045 | [9 empty] | TSS+TI |  | 2x SFP 1G 1x Optical cable | MW Re-engineering | LAG 1G port RTN03-RTN02 Remove existing casscade RTN04-RTN03 (to have free port to do 1G LAG) Connect new casscade RTN04-RTN05 site impact: 7107K,S00479,S00343, 7807E | Patch cable 1G port and config LAG | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050445 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280434-GTSB | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | AB.RAHMAN//BIN MAT NOOH/6237001519
1005A_PORT | Tmn Melati | DU00006773213 | Central | Kuala Lumpur | 3.225550 | 101.727500 | [9 empty] | TSS+TI |  | NE_1005A New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted : 1005A, 1029L, 3246D, 3142C, 3509B, 3707A, 1401C, 1724C & 1151C. NE_1005A Perform 1G LAG for RTN03(Port 8-EM6-1 & 8-EM6-5) and RTN06(Port 8-EM6-2 & 8-EM6-6). | Site Impacted : 1005A, 1029L, 3246D, 3142C, 3509B, 3707A, 1401C, 1724C & 1151C. NE_1005A Perform 1G LAG for RTN03(Port 8-EM6-1 & 8-EM6-5) and RTN06(Port 8-EM6-2 & 8-EM6-6). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042965 |  | 2026-05-04 | 2026-05-06 | Completed | 2026-04-29 | 2026-05-04 | 2026-04-29 | 2026-05-06 | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604280393-GTSB
1098B_PORT | PekanJinjang | DU00006773214 | Central | Kuala Lumpur | 3.210028 | 101.657889 | [9 empty] | TSS+TI |  | NE_1098B New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted : 1098B, 1268H, 1752B, 1260H, 1087B, 2338A & 1439K/W01221. NE_1098B Perform 1G LAG for RTN01(Port 8-EM6-2 & 8-EM6-5) and RTN03(Port 8-EM6-1 & 8-EM6-5). | Site Impacted : 1098B, 1268H, 1752B, 1260H, 1087B, 2338A & 1439K/W01221. NE_1098B Perform 1G LAG for RTN01(Port 8-EM6-2 & 8-EM6-5) and RTN03(Port 8-EM6-1 & 8-EM6-5). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042966 |  | 2026-05-04 | 2026-05-06 | Completed | 2026-04-29 | 2026-05-04 | 2026-04-29 | 2026-05-06 | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604280393-GTSB
7178A_PORT_1 | KKTimes Square Mall | DU00006773215 | Sabah | Sabah | 5.970311 | 116.067044 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | TRANSFER BBU FROM 7178A NEW RTN01 8-EM6-1 TO 10G PORT 8-EM6-3 IMPACTED SITE: 7176Q, 7178A | TRANSFER BBU FROM 7178A NEW RTN01 8-EM6-1 TO 10G PORT 8-EM6-3 IMPACTED SITE: 7176Q, 7178A | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050435 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
3887C_PORT | Centrali-City Shopping Centre IB | DU00006773216 | Central | Selangor | 3.062279 | 101.481925 | [9 empty] | TSS+TI |  | NE_3887C New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and ZTE BBU). New Optical Patch Cord cable with suitable type and length. | MW Re-engineering | Site Impacted :3887C. NE_3887C 1.Perform BBU upgrade from 1G(Electrical) port to 10G(Optical) port. 2.Enable port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-42489) and insert suitable SFP Module 10G 10Km 1310nm. Configure it. 3.Patching 10G port of BBU and port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-42489). | Site Impacted :3887C. NE_3887C 1.Perform BBU upgrade from 1G(Electrical) port to 10G(Optical) port. 2.Enable port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-42489) and insert suitable SFP Module 10G 10Km 1310nm. Configure it. 3.Patching 10G port of BBU and port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-42489). | [6 empty] | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042976 |  | 2026-05-04 |  | Ongoing | 2026-04-29 | 2026-05-04 | 2026-04-29 |  | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280393-GTSB
7585A_PORT_1 | SukauTown | DU00006773217 | Sabah | Sabah | 5.519955 | 118.270244 | [9 empty] | TSS+TI+Dismantle |  | 1X IDU RTN910A | MW Re-engineering | 7585A RTN07 SWAP EXISTING IDU 7585A RTN07 TO NEW IDU RTN910AF IMPACTED SITE: 7489B, 7732B, 7493B 1. SWAP 7585A RTN07 WITH NEW IDU RTN910AF 2. RECONFIGURE EXISTING ATN AND REPATCH TO RTN09 3. DO 10G PORT UPGRADE USING DU 7585A_PORT | SWAP 7585A RTN07 WITH NEW IDU RTN910AF RECONFIGURE EXISTING ATN AND REPATCH TO RTN09 DO 10G PORT UPGRADE USING DU 7585A_PORT 1. SWAP 7585A RTN07 WITH NEW IDU RTN910AF 2. RECONFIGURE EXISTING ATN AND REPATCH TO RTN09 3. DO 10G PORT UPGRADE USING DU 7585A_PORT | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050431 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
7461B_PORT | TungHup Estate (Celcom) | DU00006773218 | Sabah | Sabah | 5.317990 | 117.866749 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7461B RTN04-RTN01 10G 10G PORT IDU RTN04-RTN01 IMPACTED SITE: 7144K, 7727E, 7654E, 7728E, 7760E, 7687E, 7718E, 7645E, 7765E, 7692E, 7655E 1. INSTALL 1 10G SFP OPTICAL AT HW 7461B RTN04 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7461B RTN01 8-EM6-3 3. PATCHING PATCH CORD 7461B RTN04 8-EM6-3 TO HW 7461B RTN01 8-EM6-3 4. RECONFIGURE TRAFFIC | 7461B RTN04-RTN01 10G 10G PORT IDU RTN04-RTN01 IMPACTED SITE: 7144K, 7727E, 7654E, 7728E, 7760E, 7687E, 7718E, 7645E, 7765E, 7692E, 7655E 1. INSTALL 1 10G SFP OPTICAL AT HW 7461B RTN04 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7461B RTN01 8-EM6-3 3. PATCHING PATCH CORD 7461B RTN04 8-EM6-3 TO HW 7461B RTN01 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050446 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00191_PORT | Q133A_Q00191OD_CB_KINGWOODRST | DU00006773219 | Sarawak | Sarawak | 2.926538 | 112.168884 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber Patch Cord x 1 pairs | MW IDU Patching | SW03882 Q00191_GE5 Upgrade to 10G | SW03882 Q00191_GE5 Upgrade to 10G | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050475 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
9165A_PORT | Siburan2 | DU00006773220 | Sarawak | Sarawak | 1.355174 | 110.411072 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 9165A RTN01-RTN04 10G 10G PORT IDU RTN01-RTN04 IMPACTED SITE: 9663C, 9743C, 9005B9, 3426B, 9101C 1. INSTALL 1 10G SFP OPTICAL AT HW 9165A RTN01 8-EM6-4 2. INSTALL 1 10G SFP OPTICAL AT HW 9165A RTN04 8-EM6-3 3. PATCHING PATCH CORD 9165A RTN01 8-EM6-4 TO HW 9165A RTN04 8-EM6-3 4. RECONFIGURE TRAFFIC | 9165A RTN01-RTN04 10G 10G PORT IDU RTN01-RTN04 IMPACTED SITE: 9663C, 9743C, 9005B9, 3426B, 9101C 1. INSTALL 1 10G SFP OPTICAL AT HW 9165A RTN01 8-EM6-4 2. INSTALL 1 10G SFP OPTICAL AT HW 9165A RTN04 8-EM6-3 3. PATCHING PATCH CORD 9165A RTN01 8-EM6-4 TO HW 9165A RTN04 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050477 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
S01442_PORT | S106A_S01442OD_T3_KGSGBUAYA | DU00006773221 | Sabah | Sabah | 4.469530 | 118.525280 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x Optical cable | MW Re-engineering | RTN01(RTN910AF, NEID 88-28614)-RTN01(RTN950A, NEID 88-13008) 10G RTN910AF(8-EM6-2)-RTN950A(17-SLF2EM6-1) remove cascade RTN910AF(8-EM6-3)-RTN950A(17-SLF2EM6-2) remove cascade | Patch cable 10G port and remove existing cascade | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050453 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | [7 empty] | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2024-10-17: 2026-05-06; 2024-10-23: 2026-06-06; 2024-10-23: 2026-05-06 | [7 empty] | GTSB | SQ202604280434-GTSB | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | AB.RAHMAN//BIN MAT NOOH/6237001519
S00250_PORT | S106A_S00250OD_CB_TGKAPOR | DU00006773222 | Sabah | Sabah | 4.507158 | 118.549030 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber Patch Cord x 1 pairs | MW IDU Patching | NE_S00250 1.S00250_RTN01_GE2 upgrade to 10G. 2.S00250_RTN01_ GE3 upgrade to 10G. | [7 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050454 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | [7 empty] | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2024-10-17: 2026-05-06; 2024-10-23: 2026-06-06; 2024-10-23: 2026-05-06 | [7 empty] | GCI | SQ202604280429-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
7313B_PORT | RichPark | DU00006773223 | Sabah | Sabah | 4.243830 | 117.911580 | [9 empty] | TSS+TI |  | 2x SFP 1G 1x Optical cable | MW Re-engineering | LAG 1G port RTN05-RTN03 Connect new cable casscade RTN05-RTN03 site impact: 7107K,S00479,S00343, 7807E | Patch cable 1G port and config LAG | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050459 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | [7 empty] | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2024-10-17: 2026-05-06; 2024-10-23: 2026-06-06; 2024-10-23: 2026-05-06 | [7 empty] | GTSB | SQ202604280434-GTSB | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | AB.RAHMAN//BIN MAT NOOH/6237001519
4584A_PORT_1 | BayviewRCC | DU00006773224 | Northern | Perak | 4.211629 | 100.565673 | [9 empty] | TSS+TI |  | NE_4584A New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted : A00800. NE_4584A Perform 1G LAG for RTN04(Port 8-EM6-1 & 8-EM6-5) and RTN05(Port 8-EM6-1 & 8-EM6-5). | Site Impacted : A00800. NE_4584A Perform 1G LAG for RTN04(Port 8-EM6-1 & 8-EM6-5) and RTN05(Port 8-EM6-1 & 8-EM6-5). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050504 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280421-GTSB
7028A_PORT | KgMengkabung | DU00006773225 | Sabah | Sabah | 6.146823 | 116.204252 | [9 empty] | TSS+TI |  | NE_7028A New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and ZTE BBU). New Optical Patch Cord cable with suitable type and length. | MW Re-engineering | Site Impacted :7028A. NE_7028A 1.Perform BBU upgrade from 1G(Electrical) port to 10G(Optical) port. 2.Swap existing RTN910A(RTN01, NEID 9-19567) with new RTN910AF. 3.Enable port 8-EM6-3 of new RTN910AF and insert suitable SFP Module 10G 10Km 1310nm. Configure it. 4.Patching 10G port of BBU and port 8-EM6-3 of new RTN910AF. | Site Impacted :7028A. NE_7028A 1.Perform BBU upgrade from 1G(Electrical) port to 10G(Optical) port. 2.Swap existing RTN910A(RTN01, NEID 9-19567) with new RTN910AF. 3.Enable port 8-EM6-3 of new RTN910AF and insert suitable SFP Module 10G 10Km 1310nm. Configure it. 4.Patching 10G port of BBU and port 8-EM6-3 of new RTN910AF. | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050436 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280434-GTSB
3510B_PORT | TamanSemenyih | DU00006773226 | Central | Selangor | 2.955591 | 101.842863 | [9 empty] | TSS+TI |  | NE_3510B New CAT 6 cable with suitable length x1. | MW Re-engineering | Site Impacted :3834B, 3645A_10 & 1664H. NE_3510B Perform 1G LAG for RAN01(RTN950)(Port 4-EM6T-2 & 4-EM6T-3) and RAN03(RTN910AF)(Port 8-EM6-1 & 8-EM6-2). | Site Impacted :3834B, 3645A_10 & 1664H. NE_3510B Perform 1G LAG for RAN01(RTN950)(Port 4-EM6T-2 & 4-EM6T-3) and RAN03(RTN910AF)(Port 8-EM6-1 & 8-EM6-2). | [6 empty] | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042977 |  | 2026-05-04 |  | Ongoing | 2026-04-29 | 2026-05-04 | 2026-04-29 |  | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280393-GTSB
9313A_PORT | Tapah(SACOFA) | DU00006773227 | Sarawak | Sarawak | 1.299740 | 110.406710 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber Patch Cord x 1 pairs | MW IDU Patching | 9313A_RTN02 to 9313A_RTN05 upgrade to 10G | 9313A_RTN02 to 9313A_RTN05 upgrade to 10G | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050479 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
7365B_PORT_1 | CBRICHARDLIND | DU00006773228 | Sabah | Sabah | 5.341290 | 118.482297 | [9 empty] | TSS+TI |  | Not Required | MW Re-engineering | RTN06-RTN05 10G RTN06(8-EM6-1)-RTN05(8-EM6-1) remove cascade | remove existing cascade cabel after 10G upgrade done | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050447 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280434-GTSB | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q00618_PORT | Q120A_Q00618OD_PKNDARO | DU00006773229 | Sarawak | Sarawak | 2.511213 | 111.432068 | [9 empty] | TSS+TI |  | 10G SFP Module x 2 Fiber patch cord x 1 pairs | MW IDU Patching | SW03727 Q00618_PKN DARO - Q00939_KG BRUIT RTN910A_GE3 , upgrade to 10G. | SW03727 Q00618_PKN DARO - Q00939_KG BRUIT RTN910A_GE3 , upgrade to 10G. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050480 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
9192B_PORT | JalanTeo Chee Beng | DU00006773230 | Sarawak | Sarawak | 2.012680 | 112.935380 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 9192B RTN02-RTN01 10G 10G PORT IDU RTN02-RTN01 IMPACTED SITE: 9192B, 9572B, 9699C, 9701C, 9698C 1. INSTALL 1 10G SFP OPTICAL AT HW 9192B RTN02 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9192B RTN01 8-EM6-4 3. PATCHING PATCH CORD 9192B RTN02 8-EM6-3 TO HW 9192B RTN01 8-EM6-4 4. RECONFIGURE TRAFFIC | 9192B RTN02-RTN01 10G 10G PORT IDU RTN02-RTN01 IMPACTED SITE: 9192B, 9572B, 9699C, 9701C, 9698C 1. INSTALL 1 10G SFP OPTICAL AT HW 9192B RTN02 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9192B RTN01 8-EM6-4 3. PATCHING PATCH CORD 9192B RTN02 8-EM6-3 TO HW 9192B RTN01 8-EM6-4 4. RECONFIGURE TRAFFIC | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050482 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
7421B_PORT | Kg.Suan Lamba SBC | DU00006773231 | Sabah | Sabah | 5.577336 | 118.139746 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7421B RTN04-RTN05 10G 10G PORT IDU RTN04-RTN05 IMPACTED SITE: 7586A, 7745B, 7127K 1. INSTALL 1 10G SFP OPTICAL AT HW 7421B RTN04 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7421B RTN05 8-EM6-3 3. PATCHING PATCH CORD 7421B RTN04 8-EM6-3 TO HW 7421B RTN05 8-EM6-3 4. RECONFIGURE TRAFFIC | 7421B RTN04-RTN05 10G 10G PORT IDU RTN04-RTN05 IMPACTED SITE: 7586A, 7745B, 7127K 1. INSTALL 1 10G SFP OPTICAL AT HW 7421B RTN04 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7421B RTN05 8-EM6-3 3. PATCHING PATCH CORD 7421B RTN04 8-EM6-3 TO HW 7421B RTN05 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050432 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
K00116_PORT | K006B_K00116OD_ASUN | DU00006773232 | Northern | Kedah | 6.331120 | 100.420770 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x patch cord | MW Re-engineering | Re-engineering BBU from Slot 8 Port 2 GE port to Slot 8 Port 3 10GE port Insert 10GE SFP into 4183K_ASUN - 4192K_KGIMAM Slot 8 Port 3 BBU re-patch to Slot 8 Port 3 10GE Site impact: 4183K | Insert SFP into 4183K Slot 8 Port 3 BBU re-patch to Slot 8 Port 3 10GE | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050505 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280421-GTSB | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | LIM//WEI CHONG/6798000110
7585A_PORT | SukauTown | DU00006773233 | Sabah | Sabah | 5.519955 | 118.270244 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7585A RTN09-RTN07 10G 10G PORT IDU RTN09-RTN07 IMPACTED SITE: 7489B, 7732B, 7493B 1. INSTALL 1 10G SFP OPTICAL AT HW 7585A RTN09 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7585A RTN07 8-EM6-3 3. PATCHING PATCH CORD 7585A RTN09 8-EM6-3 TO HW 7585A RTN07 8-EM6-3 4. RECONFIGURE TRAFFIC | 7585A RTN09-RTN07 10G 10G PORT IDU RTN09-RTN07 IMPACTED SITE: 7489B, 7732B, 7493B 1. INSTALL 1 10G SFP OPTICAL AT HW 7585A RTN09 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7585A RTN07 8-EM6-3 3. PATCHING PATCH CORD 7585A RTN09 8-EM6-3 TO HW 7585A RTN07 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050433 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
9352A_PORT | HilltopKapit | DU00006773234 | Sarawak | Sarawak | 1.998305 | 112.976012 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber Patch Cord x 1 pairs | MW IDU Patching | 9352A_RTN02 to RTN01 upgrade to 10G. | 9352A_RTN02 to RTN01 upgrade to 10G. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050483 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
3213B_PORT | SalakTinggi (REL) | DU00006773235 | Central | Selangor | 2.804290 | 101.744000 | [9 empty] | TSS+TI |  | NE_3213B New CAT6 cable x1. | MW Re-engineering | Site Impacted : 1233A, 3421B, 3577B & 1487A. NE_3213B Perform 1G LAG for RTN05(Port 8-EM6-2 & 8-EM6-1) and RTN03(Port 8-EM6-2 & 8-EM6-1). | Site Impacted : 1233A, 3421B, 3577B & 1487A. NE_3213B Perform 1G LAG for RTN05(Port 8-EM6-2 & 8-EM6-1) and RTN03(Port 8-EM6-2 & 8-EM6-1). | [6 empty] | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050519 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280393-GTSB
Q00228_PORT | Q123A_Q00228OD_TMKAPITTV | DU00006773236 | Sarawak | Sarawak | 2.013463 | 112.934075 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber Patch Cord x 1 pairs | MW IDU Patching | Q00228_TM KAPIT TV -RTN01 to - Q00228_TM KAPIT TV -9334P/Q01429_ULU YONG upgrade to 10G | Q00228_TM KAPIT TV -RTN01 to - Q00228_TM KAPIT TV -9334P/Q01429_ULU YONG upgrade to 10G | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050484 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
4466A_PORT | TamanRakyat RDD | DU00006773237 | Northern | Perak | 4.921788 | 100.724654 | [9 empty] | TSS+TI |  | NE_4466A New CAT 6 cable with suitable length x1. | MW Re-engineering | Site Impacted :4424A & 4565D. NE_4466A Perform 1G LAG for RAN02(Port 8-EM6-1 & 8-EM6-2) and RAN03(Port 8-EM6-1 & 8-EM6-2). | Site Impacted :4424A & 4565D. NE_4466A Perform 1G LAG for RAN02(Port 8-EM6-1 & 8-EM6-2) and RAN03(Port 8-EM6-1 & 8-EM6-2). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050308 |  | 2026-05-04 | 2026-05-05 | Completed | 2026-05-03 | 2026-05-04 | 2026-05-03 | 2026-05-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604280421-GTSB
9193A_PORT | Spaoh | DU00006773238 | Sarawak | Sarawak | 1.453003 | 111.481640 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 9193A RTN02-RTN04 10G 10G PORT IDU RTN02-RTN04 IMPACTED SITE: 9193A, 9565B, 9158Z, 9511B 1. INSTALL 1 10G SFP OPTICAL AT HW 9193A RTN02 8-EM6-4 2. INSTALL 1 10G SFP OPTICAL AT HW 9193A RTN04 8-EM6-3 3. PATCHING PATCH CORD 9193A RTN02 8-EM6-4 TO HW 9193A RTN04 8-EM6-3 4. RECONFIGURE TRAFFIC | 9193A RTN02-RTN04 10G 10G PORT IDU RTN02-RTN04 IMPACTED SITE: 9193A, 9565B, 9158Z, 9511B 1. INSTALL 1 10G SFP OPTICAL AT HW 9193A RTN02 8-EM6-4 2. INSTALL 1 10G SFP OPTICAL AT HW 9193A RTN04 8-EM6-3 3. PATCHING PATCH CORD 9193A RTN02 8-EM6-4 TO HW 9193A RTN04 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050485 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
1869B_PORT_1 | KJSKg Semarang(KJS) | DU00006773239 | Central | Selangor | 2.871396 | 101.695840 | [9 empty] | TSS+TI |  | NE_1869B New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted : 3251C. NE_1869B Perform 1G LAG for RTN03(Port 8-EM6-1 & 8-EM6-5) and RTN06(Port 8-EM6-1 & 8-EM6-5). | Site Impacted : 3251C. NE_1869B Perform 1G LAG for RTN03(Port 8-EM6-1 & 8-EM6-5) and RTN06(Port 8-EM6-1 & 8-EM6-2). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042971 |  | 2026-05-04 | 2026-05-06 | Completed | 2026-04-29 | 2026-05-04 | 2026-04-29 | 2026-05-06 | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604280393-GTSB
4279A_PORT | PinangTunggal (KJS) | DU00006773240 | Northern | Penang | 5.553310 | 100.498330 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x patch cord 1x IDU RTN910AF | MW Re-engineering | Re-engineering, 1. Swap IDU RTN01 with RTN910AF model to support 10GE SFP. 2. Insert 10GE SFP into RTN01 Slot 8 Port 3 3. BBU re-patch to RTN01 Slot 8 Port 3 Site impact: 4729A | 1. Swap IDU RTN01 with RTN910AF model to support 10GE SFP. 2. Insert 10GE SFP into RTN01 Slot 8 Port 3 3. BBU re-patch to RTN01 Slot 8 Port 3 Site impact: 4729A | [6 empty] | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050517 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280421-GTSB | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | LIM//WEI CHONG/6798000110
4584A_PORT | BayviewRCC | DU00006773241 | Northern | Perak | 4.211629 | 100.565673 | [9 empty] | TSS+TI |  | NE_4584A New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted : 4715A. NE_4584A Perform 1G LAG for RTN02(Port 8-EM6-1 & 8-EM6-5) and RTN01(Port 8-EM6-2 & 8-EM6-5). | Site Impacted : 4715A. NE_4584A Perform 1G LAG for RTN02(Port 8-EM6-1 & 8-EM6-5) and RTN01(Port 8-EM6-2 & 8-EM6-5). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050507 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280421-GTSB
2171A_PORT | SyabasTmn Pelangi | DU00006773242 | Central | Selangor | 2.932861 | 101.862870 | [9 empty] | TSS+TI |  | NE_2171A New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted : 2171A, 1259C, 1439C, 3501B, 1514C & 1539H. NE_2171A Perform 1G LAG for RTN05(Port 8-EM6-2 & 8-EM6-6) and RTN03(Port 8-EM6-2 & 8-EM6-5). | Site Impacted : 2171A, 1259C, 1439C, 3501B, 1514C & 1539H. NE_2171A Perform 1G LAG for RTN05(Port 8-EM6-2 & 8-EM6-6) and RTN03(Port 8-EM6-2 & 8-EM6-5). | [6 empty] | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042978 |  | 2026-05-04 |  | Ongoing | 2026-04-29 | 2026-05-04 | 2026-04-29 |  | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280393-GTSB
2646A_PORT | TelukPulai 2 | DU00006773243 | Central | Selangor | 3.045266 | 101.424866 | [9 empty] | TSS+TI | L1+ATP+PAC | NE_2646A New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted : 2765C. NE_2646A Perform 1G LAG for RTN03(Port 8-EM6-5 & 8-EM6-6) andRTN02(Port 8-EM6-5 & 8-EM6-6) | Site Impacted : 2765C. NE_2646A Perform 1G LAG for RTN03(Port 8-EM6-5 & 8-EM6-6) andRTN02(Port 8-EM6-5 & 8-EM6-6) | [6 empty] | Magicell |  | Magicell | SQ202605070530-Magicell |  |  | Ongoing | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042958 |  | 2026-05-04 | 2026-05-06 | Completed | 2026-04-29 | 2026-05-04 | 2026-04-29 | 2026-05-06 | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2027-04-23 | 2026-04-29 | 2026-05-07 | RAZALI//BIN ABDUL HALIM/7018000224 | Magicell TI | 2026-04-29 | 2027-04-23 | 2026-04-29 | 2026-05-07 | RAZALI//BIN ABDUL HALIM/7018000224 | Magicell TI | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-29 | 2027-04-23 | 2026-04-29 | 2026-05-07 | RAZALI//BIN ABDUL HALIM/7018000224 | 2024-10-17: 2026-04-29; 2024-10-23: 2027-04-23; 2024-10-23: 2026-04-29; 2024-10-23: 2026-05-06 | [7 empty] | GTSB | SQ202604280393-GTSB
4222A_PORT | BukitPanchor | DU00006773244 | Northern | Penang | 5.176778 | 100.479883 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x patch cord | MW Re-engineering | Re-enginnering RTN01-RTN03 from 1G port to 10G port Site impact: 4222A Insert 10GE SFP into RTN01 Slot 8 port 4 and RTN03 Slot 8 port 3 Patch cable from RTN01 Slot 8 port 4 10GE to RTN03 Slot 8 port 3 10GE Remove connection RTN01 Slot 8 port 1 to RTN03 Slot 8 port 2 | 1. Survey on site at 4222A RTN01 port connection to RTN03 port. 2. Insert 10GE SFP into RTN01 Slot 8 port 4 and RTN03 Slot 8 port 3 3. Patch cable from RTN01 Slot 8 port 4 10GE to RTN03 Slot 8 port 3 10GE 4. Remove connection RTN01 Slot 8 port 1 to RTN03 Slot 8 port 2 Site impact: 7219R,7475B | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050509 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280421-GTSB | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | LIM//WEI CHONG/6798000110
7936A_PORT | PengkalanMadai (Celcom) | DU00006773245 | Sabah | Sabah | 4.732220 | 118.196376 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7936A RTN02-RTN01 10G 10G PORT IDU RTN02-RTN01 IMPACTED SITE: 7936A, 7059K, 7309C 1. INSTALL 1 10G SFP OPTICAL AT HW 7936A RTN02 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7936A RTN01 8-EM6-3 3. PATCHING PATCH CORD 7936A RTN02 8-EM6-3 TO HW 7936A RTN01 8-EM6-3 4. RECONFIGURE TRAFFIC | 7936A RTN02-RTN01 10G 10G PORT IDU RTN02-RTN01 IMPACTED SITE: 7936A, 7059K, 7309C 1. INSTALL 1 10G SFP OPTICAL AT HW 7936A RTN02 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7936A RTN01 8-EM6-3 3. PATCHING PATCH CORD 7936A RTN02 8-EM6-3 TO HW 7936A RTN01 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050442 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | [7 empty] | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2024-10-17: 2026-05-06; 2024-10-23: 2026-06-06; 2024-10-23: 2026-05-06 | [7 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
9099A_PORT | Lambir(Celcom) | DU00006773246 | Sarawak | Sarawak | 4.303598 | 114.017996 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 9099A RTN01-RTN02 10G 10G PORT IDU RTN01-RTN02 IMPACTED SITE: 9099A, 9590A, 9721B, 9739C 1. INSTALL 1 10G SFP OPTICAL AT HW 9099A RTN01 8-EM6-4 2. INSTALL 1 10G SFP OPTICAL AT HW 9099A RTN02 8-EM6-3 3. PATCHING PATCH CORD 9099A RTN01 8-EM6-4 TO HW 9099A RTN02 8-EM6-3 4. RECONFIGURE TRAFFIC | 9099A RTN01-RTN02 10G 10G PORT IDU RTN01-RTN02 IMPACTED SITE: 9099A, 9590A, 9721B, 9739C 1. INSTALL 1 10G SFP OPTICAL AT HW 9099A RTN01 8-EM6-4 2. INSTALL 1 10G SFP OPTICAL AT HW 9099A RTN02 8-EM6-3 3. PATCHING PATCH CORD 9099A RTN01 8-EM6-4 TO HW 9099A RTN02 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050486 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-07 | 2026-05-13 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-05-07 | 2026-05-13 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | [7 empty] | 2026-05-07 | 2026-05-13 |  |  | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2026-05-07; 2024-10-23: 2026-05-13; 2024-10-23: 2026-05-07; 2024-10-23: 2026-05-07 | [7 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
9334A_PORT_1 | PusatLatihan Polis 2 | DU00006773247 | Sarawak | Sarawak | 1.379258 | 110.323919 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber patch cord x 1 pairs | BBU Patching | 9334A_BBU upgrade to 10G patching at 9334A_RTN02_GE4. | 9334A_BBU upgrade to 10G patching at 9334A_RTN02_GE4. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050487 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
7683B_PORT | SempornaTown | DU00006773248 | Sabah | Sabah | 4.481844 | 118.607361 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | TRANSFER BBU FROM 7683B RTN01 8-EM6-2 TO 10G PORT 8-EM6-3 IMPACTED SITE: 7683B,7115D | TRANSFER BBU FROM 7683B RTN01 8-EM6-2 TO 10G PORT 8-EM6-3 IMPACTED SITE: 7683B,7115D | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050455 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | [7 empty] | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2024-10-17: 2026-05-06; 2024-10-23: 2026-06-06; 2024-10-23: 2026-05-06 | [7 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
7178A_PORT | KKTimes Square Mall | DU00006773249 | Sabah | Sabah | 5.970311 | 116.067044 | [9 empty] | TSS+TI+Dismantle |  | 1X IDU RTN910A | MW Re-engineering | 1. SWAP 7178A RTN01 WITH NEW IDU RTN910AF 2. RECONFIGURE EXISTING CTS AND QCELL REPATCH TO NEW RTN910 3. DU 7178A_PORT_1 (PATCHING BBU TO 10G PORT) | 1. SWAP 7178A RTN01 WITH NEW IDU RTN910AF 2. RECONFIGURE EXISTING CTS AND QCELL REPATCH TO NEW RTN910 3. DO 10G PORT UPGRADE USING DU 7178A_PORT_1 | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050437 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
9353B_PORT | Mile39 Bintulu | DU00006773250 | Sarawak | Sarawak | 3.406637 | 113.493998 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber patch cord x 1 pairs | MW IDU Patching | 9353B/Q00469_GE1 upgrade to 10G 9181X/Q00469_GE2 upgrade to 10G Both RTN cascade with 10G port | 9353B/Q00469_GE1 upgrade to 10G 9181X/Q00469_GE2 upgrade to 10G Both RTN cascade with 10G port | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050488 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
3041C_PORT | IdamanSentosa (REL) | DU00006773251 | Central | Selangor | 3.012800 | 101.474952 | [9 empty] | TSS+TI | L1+ATP+PAC | NE_2646A New CAT 6 cable with suitable length x1. | MW Re-engineering | Site Impacted :3041C, 3723C, 3656B, 3063M & 1387H. NE_3041C Perform 1G LAG for RTN04(Port 8-EG6-2 & 8-EG6-3) and RTN01(Port 8-EM6-1 & 8-EM6-2). | Site Impacted :3041C, 3723C, 3656B, 3063M & 1387H. NE_3041C Perform 1G LAG for RTN04(Port 8-EG6-2 & 8-EG6-3) and RTN01(Port 8-EM6-1 & 8-EM6-2). | [6 empty] | Magicell |  | Magicell | SQ202605070530-Magicell |  |  | Ongoing | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042961 |  | 2026-05-04 | 2026-05-04 | Completed | 2026-04-29 | 2026-05-04 | 2026-04-29 | 2026-05-04 | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2027-04-23 | 2026-04-29 | 2026-05-07 | RAZALI//BIN ABDUL HALIM/7018000224 | Magicell TI | 2026-04-29 | 2027-04-23 | 2026-04-29 | 2026-05-07 | RAZALI//BIN ABDUL HALIM/7018000224 | Magicell TI | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-29 | 2027-04-23 | 2026-04-29 | 2026-05-07 | RAZALI//BIN ABDUL HALIM/7018000224 | 2024-10-17: 2026-04-29; 2024-10-23: 2027-04-23; 2024-10-23: 2026-04-29; 2024-10-23: 2026-05-05 | [7 empty] | GTSB | SQ202604280393-GTSB
7976A_PORT | Kunak-SempornaRoudabout | DU00006773252 | Sabah | Sabah | 4.422103 | 118.487086 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7976A RTN02-RTN03 10G 10G PORT IDU RTN02-RTN03 IMPACTED SITE: 7976A, 7626B, 7975A 1. INSTALL 1 10G SFP OPTICAL AT HW 7976A RTN02 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7976A RTN03 8-EM6-3 3. PATCHING PATCH CORD 7976A RTN02 8-EM6-3 TO HW 7976A RTN03 8-EM6-3 4. RECONFIGURE TRAFFIC | 7976A RTN02-RTN03 10G 10G PORT IDU RTN02-RTN03 IMPACTED SITE: 7976A, 7626B, 7975A 1. INSTALL 1 10G SFP OPTICAL AT HW 7976A RTN02 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7976A RTN03 8-EM6-3 3. PATCHING PATCH CORD 7976A RTN02 8-EM6-3 TO HW 7976A RTN03 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050443 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | [7 empty] | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2024-10-17: 2026-05-06; 2024-10-23: 2026-06-06; 2024-10-23: 2026-05-06 | [7 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
9407B_PORT | SungaiKut | DU00006773253 | Sarawak | Sarawak | 2.720735 | 111.839789 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber patch cord x 1 pairs | MW IDU Patching | 9407B_RTN04 to RTN01 upgrade to 10G. | 9407B_RTN04 to RTN01 upgrade to 10G. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050489 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
7414A_PORT | JlnK.Belud-K.Ambai | DU00006773254 | Sabah | Sabah | 6.383049 | 116.367040 | [9 empty] | TSS+TI |  | NE_7414A New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted :9003B_10 & 7771B. NE_7414A Perform 1G LAG for RTN02(RTN910AF)(Port 8-EM6-1 & 8-EM6-5) and RTN01(RTN950A)(Port 8-EG6-4 & 8-EG6-3). | Site Impacted :9003B_10 & 7771B. NE_7414A Perform 1G LAG for RTN02(RTN910AF)(Port 8-EM6-1 & 8-EM6-5) and RTN01(RTN950A)(Port 8-EG6-4 & 8-EG6-3). | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050434 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280434-GTSB
9334A_PORT | PusatLatihan Polis 2 | DU00006773255 | Sarawak | Sarawak | 1.379258 | 110.323919 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber patch cords x 1 pairs | MW IDU Patching | 9334A_RTN03_GE3 to 9334A_RTN02_GE3 upgrade to 10G. | 9334A_RTN03_GE3 to 9334A_RTN02_GE3 upgrade to 10G. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050490 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
4932A_PORT | BktTok Acheh | DU00006773256 | Northern | Kedah | 5.621126 | 100.504429 | [9 empty] | TSS+TI |  | NE_4932A New CAT 6 cable with suitable length x1. | MW Re-engineering | Site Impacted :4932A, 4153D, 4152D & 4332H. NE_4932A 1.Request new Ibeam 1G(Electrical) port from ZTE IPRAN team. 2.Perform 1G LAG for RTN04(RTN910A)(Port 8-EG6-1 & 8-EG6-2) and IBEAM(Port existing & new). | Site Impacted :4932A, 4153D, 4152D & 4332H. NE_4932A 1.Request new Ibeam 1G(Electrical) port from ZTE IPRAN team. 2.Perform 1G LAG for RTN04(RTN910A)(Port 8-EG6-1 & 8-EG6-2) and IBEAM(Port existing & new). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050307 |  | 2026-05-04 | 2026-05-05 | Completed | 2026-05-03 | 2026-05-04 | 2026-05-03 | 2026-05-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604280421-GTSB
9014L_HU_1 | JalanKemuyang | DU00006719139 | Sarawak | Sarawak | 2.345155 | 111.961550 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | 1x ODU 23G XMC3 SUB A HI 1x ODU 23G XMC3 SUB A LO 2x IF CABLE (SUITABLE LENGTH) | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 9014L-9182B FROM 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM TO HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3_SUB_A & B_LINK_1.14KM INSTALL NEW ODU SUB A (H POLAR) TO SLOT 7-2 TO BECOME 2+0 IMPACTED: 9014L | 1. REUSE EXISTING IDU RTN910 2. REUSE EXISTING 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 SUB A TO SLOT 7-2 TO BECOME 2+0 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM | 1. REUSE EXISTING IDU RTN910 2. REUSE EXISTING 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 SUB A TO SLOT 7-2 TO BECOME 2+0 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM | XMC3 | MAC | 23G | 0.6 | 0.6 | Iezzpro |  | Iezzpro |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2026-05-07 | 2026-06-07 | 2026-05-07 |  | Halim bin Bohari6000069011 | Iezzpro TI | 2026-05-07 | 2026-06-07 | 2026-05-07 |  | Halim bin Bohari6000069011 | Iezzpro TI | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2026-05-07 | 2026-06-07 | 2026-05-07 |  | Halim bin Bohari6000069011 | 2024-10-17: 2026-05-07; 2024-10-23: 2026-06-07; 2024-10-23: 2026-05-07; 2024-10-23: 2026-05-07 | [7 empty] | GCI | SQ202604030185-GCI | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
3142B_PORT_1 | IOICity Mall | DU00006773258 | Central | Selangor | 2.970534 | 101.713893 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x patch cord | MW Re-engineering | Re-enginnering BBU from RTN02 Slot 8 Port 6 GE port to Slot 8 Port 3 10GE port Site impact: 3142B Insert 10GE SFP into RTN02 Slot 8 Port 3 BBU re-patch to RTN02 Slot 8 Port 3 | Insert 10GE SFP into RTN02 Slot 8 Port 3 BBU re-patch to RTN02 Slot 8 Port 3 | [6 empty] | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050515 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280393-GTSB | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | LIM//WEI CHONG/6798000110
7957A_PORT | SimpangEmpat | DU00006773259 | Sabah | Sabah | 6.495910 | 116.760090 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7957A RTN01-RTN03 10G 10G PORT IDU RTN01-RTN03 IMPACTED SITE: 7957A, 7958A, 7169H, 7348C, 7323C, 7596B, 3059C 1. INSTALL 1 10G SFP OPTICAL AT HW 7957A RTN01 8-EM6-4 2. INSTALL 1 10G SFP OPTICAL AT HW 7957A RTN03 8-EM6-3 3. PATCHING PATCH CORD 7957A RTN01 8-EM6-4 TO HW 7957A RTN03 8-EM6-3 4. RECONFIGURE TRAFFIC | 7957A RTN01-RTN03 10G 10G PORT IDU RTN01-RTN03 IMPACTED SITE: 7957A, 7958A, 7169H, 7348C, 7323C, 7596B, 3059C 1. INSTALL 1 10G SFP OPTICAL AT HW 7957A RTN01 8-EM6-4 2. INSTALL 1 10G SFP OPTICAL AT HW 7957A RTN03 8-EM6-3 3. PATCHING PATCH CORD 7957A RTN01 8-EM6-4 TO HW 7957A RTN03 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050439 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
3601B_PORT | JalanBangi Semenyih | DU00006773260 | Central | Selangor | 2.924111 | 101.829413 | [9 empty] | TSS+TI |  | NE_3601B New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF x2). New Optical Patch Cord cable with suitable type and length. | MW Re-engineering | Site Impacted :1853B, 3836A, 2903C, 3835A & 1861H. NE_3601B 1.Perform 10G port upgrade for RTN02(8-EM6-3) and RTN01(8-EM6-3). 2.RTN02(8-EM6-1)-RTN01(8-EM6-2) - remove cascade. | Site Impacted :1853B, 3836A, 2903C, 3835A & 1861H. NE_3601B 1.Perform 10G port upgrade for RTN02(8-EM6-3) and RTN01(8-EM6-3). 2.RTN02(8-EM6-1)-RTN01(8-EM6-2) - remove cascade. | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042969 |  | 2026-05-04 |  | Ongoing | 2026-04-29 | 2026-05-04 | 2026-04-29 |  | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280393-GTSB
2001B_PORT | KgSg Bakau Rawang(ZED) | DU00006773261 | Central | Selangor | 3.306300 | 101.541600 | [9 empty] | TSS+TI |  | NE_2001B New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted : 1015C. NE_2001B Perform 1G LAG for RAN01(Port 8-EM6-1 & 8-EM6-5) and RAN08(Port 8-EM6-2 & 8-EM6-5). | Site Impacted : 1015C. NE_2001B Perform 1G LAG for RAN01(Port 8-EM6-1 & 8-EM6-5) and RAN08(Port 8-EM6-2 & 8-EM6-5). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042970 |  | 2026-05-04 | 2026-05-06 | Completed | 2026-04-29 | 2026-05-04 | 2026-04-29 | 2026-05-06 | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604280393-GTSB
9358A_PORT | SibuAirport Road (Maxis) | DU00006773262 | Sarawak | Sarawak | 2.251626 | 111.979086 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber patch cords x 1 pairs | MW IDU Patching | 9358A_RTN01_GE1 upgrade to 10G. | 9358A_RTN01_GE1 upgrade to 10G. | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050491 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
3027C_PORT | SgKapar Industrial (REL) | DU00006773263 | Central | Selangor | 3.102880 | 101.400100 | [9 empty] | TSS+TI | L1+ATP+PAC | NE_3027C New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and ZTE BBU). New Optical Patch Cord cable with suitable type and length. | MW Re-engineering | Site Impacted :3027C. NE_3027C 1.Perform BBU upgrade from 1G(Electrical) port to 10G(Optical) port. 2.Enable port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-32013) and insert suitable SFP Module 10G 10Km 1310nm. Configure it. 3.Patching 10G port of BBU and port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-32013). | Site Impacted :3027C. NE_3027C 1.Perform BBU upgrade from 1G(Electrical) port to 10G(Optical) port. 2.Enable port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-32013) and insert suitable SFP Module 10G 10Km 1310nm. Configure it. 3.Patching 10G port of BBU and port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-32013). | [6 empty] | Magicell |  | Magicell | SQ202605070530-Magicell |  |  | Ongoing | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042963 |  | 2026-05-04 | 2026-05-06 | Completed | 2026-04-29 | 2026-05-04 | 2026-04-29 | 2026-05-06 | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2027-04-23 | 2026-04-29 | 2026-05-07 | RAZALI//BIN ABDUL HALIM/7018000224 | Magicell TI | 2026-04-29 | 2027-04-23 | 2026-04-29 | 2026-05-07 | RAZALI//BIN ABDUL HALIM/7018000224 | Magicell TI | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-29 | 2027-04-23 | 2026-04-29 | 2026-05-07 | RAZALI//BIN ABDUL HALIM/7018000224 | 2024-10-17: 2026-04-29; 2024-10-23: 2027-04-23; 2024-10-23: 2026-04-29; 2024-10-23: 2026-05-06 | [7 empty] | GTSB | SQ202604280393-GTSB
9288A_PORT_1 | Tedungan(SACOFA) | DU00006773264 | Sarawak | Sarawak | 4.731470 | 114.801514 | [9 empty] | TSS+TI |  | 10G SFP Module x2 Fiber Patch Cord x 1 pairs | MW IDU Patching | 9288A TEDUNGAN-RTN02-8-EM6-2(RTN04-GE2) | 9288A TEDUNGAN-RTN02-8-EM6-2(RTN04-GE2) | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050492 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
S01445_PORT | S106A_S01445OD_T3_KGPAKALANGAN | DU00006773265 | Sabah | Sabah | 4.375600 | 118.560100 | [9 empty] | TSS+TI |  | NE_S01445 New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF x2). New Optical Patch Cord cable with suitable type and length. | MW Re-engineering | Site Impacted :S00589 & S01172. NE_S01445 1.Perform 10G port upgrade at RTN01(8-EM6-3)-RTN02(8-EM6-5). 2.RTN02(8-EM6-1)-RTN02(8-EM6-3) remove cascade. 3.RTN02(8-EM6-2)-RTN02(8-EM6-4) remove cascade. | Site Impacted :S00589 & S01172. NE_S01445 1.Perform 10G port upgrade at RTN01(8-EM6-3)-RTN02(8-EM6-5). 2.RTN02(8-EM6-1)-RTN02(8-EM6-3) remove cascade. 3.RTN02(8-EM6-2)-RTN02(8-EM6-4) remove cascade. | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050456 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | [7 empty] | 2026-05-06 | 2026-06-06 | 2026-05-06 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2024-10-17: 2026-05-06; 2024-10-23: 2026-06-06; 2024-10-23: 2026-05-06 | [7 empty] | GTSB | SQ202604280434-GTSB
7757B_PORT | Tongkabira | DU00006773266 | Sabah | Sabah | 5.490600 | 116.992600 | [9 empty] | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7757B RTN02-RTN01 10G 10G PORT IDU RTN02-RTN01 IMPACTED SITE: 7757B, 7756B, 3511A, 7095Z, 7094Z, 7091Z, 7011D, 7092Z 1. INSTALL 1 10G SFP OPTICAL AT HW 7757B RTN02 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7757B RTN01 8-EM6-3 3. PATCHING PATCH CORD 7757B RTN02 8-EM6-3 TO HW 7757B RTN01 8-EM6-3 4. RECONFIGURE TRAFFIC | 7757B RTN02-RTN01 10G 10G PORT IDU RTN02-RTN01 IMPACTED SITE: 7757B, 7756B, 3511A, 7095Z, 7094Z, 7091Z, 7011D, 7092Z 1. INSTALL 1 10G SFP OPTICAL AT HW 7757B RTN02 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7757B RTN01 8-EM6-3 3. PATCHING PATCH CORD 7757B RTN02 8-EM6-3 TO HW 7757B RTN01 8-EM6-3 4. RECONFIGURE TRAFFIC | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050460 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
9213A_PORT | SarikeiTown MP | DU00006773267 | Sarawak | Sarawak | 2.131433 | 111.519932 | [9 empty] | TSS+TI |  | 10G SFP Module x2. Fiber patch cord x 1 pairs. | MW IDU Patching | 9213A_RTN01 to ZTE NR9150_NR01 upgrade to 10G | 9213A_RTN01 to ZTE NR9150_NR01 upgrade to 10G | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050493 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
1869B_PORT | KJSKg Semarang(KJS) | DU00006773268 | Central | Selangor | 2.871396 | 101.695840 | [9 empty] | TSS+TI |  | NE_1869B New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Site Impacted : 3393A & 2736C. NE_1869B Perform 1G LAG for RTN01(Port 8-EM6-1 & 8-EM6-5) and RTN03(Port 8-EM6-2 & 8-EM6-5). | Site Impacted : 3393A & 2736C. NE_1869B Perform 1G LAG for RTN01(Port 8-EM6-1 & 8-EM6-5) and RTN03(Port 8-EM6-2 & 8-EM6-5). | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042967 |  | 2026-05-04 | 2026-05-06 | Completed | 2026-04-29 | 2026-05-04 | 2026-04-29 | 2026-05-06 | ZHANG DONG6000003031 | executive project manager group | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604280393-GTSB
9484A_IPR | Jalan Astana 2 MP | DU00006260210 | Sarawak | Sarawak | 1.570667 | 110.338000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9484A. NE_9484A New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and Sacofa Equipment-Tejas). New Optical Patch Cord cable with suitable type and length. | IPRAN Port Upgrade | ****IMPORTANT NOTE: 1.9484A traffic currently divert to xC(Q00085), therefore need to redivert to xD CP(9999A). 2.Please aware, at 9484A having existing NEC MW Link 9484A-->9871A. TOPO Huawei NMS, not draw the NEC Link completely.**** IPRAN Port Upgrade from existing Optical 1G to 10G port at 9484A. Site Impacted : 9484A, 9143B, 9980A & 9871A(NEC). SACOFA PORT INFO: 10GE 1-3-3 NE_9484A 1.Enable port 8-EM6-3 of existing RTN910AF(RTN02-NEID 24125). 2.Insert new suitable SFP Module 10G into port 8-EM6-3 of existing RTN910AF(RTN02-NEID 24125). Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910AF(RTN02-NEID 24125) to Sacofa Tejas(Request port from ZTE IPRAN team). 4.Request new xD Vlan DCN and Vlan services if needed from ZTE IPRAN Team. 5.Migrate traffics 9484A, 9143B, 9980A & 9871A(NEC) to new 10G port. 6.Later, 1G port for LL at NEC IDU may disable and remove the cable. | ****IMPORTANT NOTE: 1.9484A traffic currently divert to xC(Q00085), therefore need to redivert to xD CP(9999A). 2.Please aware, at 9484A having existing NEC MW Link 9484A-->9871A. TOPO Huawei NMS, not draw the NEC Link completely.**** IPRAN Port Upgrade from existing Optical 1G to 10G port at 9484A. Site Impacted : 9484A, 9143B, 9980A & 9871A(NEC). SACOFA PORT INFO: 10GE 1-3-3 NE_9484A 1.Enable port 8-EM6-3 of existing RTN910AF(RTN02-NEID 24125). 2.Insert new suitable SFP Module 10G into port 8-EM6-3 of existing RTN910AF(RTN02-NEID 24125). Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910AF(RTN02-NEID 24125) to Sacofa Tejas(Request port from ZTE IPRAN team). 4.Request new xD Vlan DCN and Vlan services if needed from ZTE IPRAN Team. 5.Migrate traffics 9484A, 9143B, 9980A & 9871A(NEC) to new 10G port. 6.Later, 1G port for LL at NEC IDU may disable and remove the cable. | [6 empty] | Allstar | SQ202511170524-Allstar | Allstar | SQ202511170485-Allstar | 2025-12-29 | 2025-12-22 | Completed | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110729 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-12 | 2025-11-18 | 2025-11-12 | 2025-11-12 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-12 | 2025-11-18 | 2025-11-21 | 2025-11-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-11-12 | 2025-11-18 | 2025-11-22 | 2025-11-22 | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2025-11-12; 2024-10-23: 2025-11-18; 2024-10-23: 2025-11-12; 2024-10-23: 2025-11-12 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511040438-GTSB
9367A_IPR | Matu | DU00006260211 | Sarawak | Sarawak | 2.676213 | 111.529865 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9367A. NE_9367A New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and Sacofa Equipment-Tejas). New Optical Patch Cord cable with suitable type and length. New Optical Patch Cord cable x1 with suitable type and length. | IPRAN Port Upgrade | IPRAN Port Upgrade from existing Optical 1G to 10G port at 9367A. Site Impacted : 9367A & 9032Z. SACOFA PORT INFO: 1-1-4 NE_9367A 1.Enable port 8-EM6-3 of existing RTN910A(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Request new xD vlan services from ZTE IPRAN Team. 5.Disable port 8-EM6-1 of existing RTN910A(RTN01) and remove existing CAT6 cable. | IPRAN Port Upgrade from existing Optical 1G to 10G port at 9367A. Site Impacted : 9367A & 9032Z. SACOFA PORT INFO: 1-1-4 NE_9367A 1.Enable port 8-EM6-3 of existing RTN910A(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Request new xD vlan services from ZTE IPRAN Team. 5.Disable port 8-EM6-1 of existing RTN910A(RTN01) and remove existing CAT6 cable. | [6 empty] | Allstar | SQ202512120287-Allstar | Allstar | SQ202511190850-Allstar | 2025-12-29 | 2025-12-22 | Completed | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110730 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-20 | 2025-11-26 | 2025-11-21 | 2025-11-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-20 | 2025-11-26 | 2025-12-03 | 2025-12-03 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 2025-12-02 | 2025-12-02 | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2025-11-20; 2024-10-23: 2025-11-26; 2024-10-23: 2025-11-21; 2024-10-23: 2025-11-21 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511040438-GTSB
9530A_IPR | Desa Pujut 2 | DU00006260212 | Sarawak | Sarawak | 4.456974 | 114.043911 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9530A. NE_9530A New SFP Module 10G with 10Km 1310nm x2(For ZTE RAN & Sacofa). New Optical Patch Cord cable x1 with suitable type and length. | IPRAN Port Upgrade | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 9530A. Site Impacted : 9530A & 9608A. SACOFA PORT INFO: 10GE 1-2-3 NE_9530A 1.Insert new suitable SFP Module 10G into port 8-EM6-3(10G port) of existing RTN910A(RTN01). Enable it. 2.Patching new Optical Patch Cord cable to port 8-EM6-3(10G port) of existing RTN910A(RTN01). 3.Request new xD Vlan Services. | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 9530A. Site Impacted : 9530A & 9608A. SACOFA PORT INFO: 10GE 1-2-3 NE_9530A 1.Insert new suitable SFP Module 10G into port 8-EM6-3(10G port) of existing RTN910A(RTN01). Enable it. 2.Patching new Optical Patch Cord cable to port 8-EM6-3(10G port) of existing RTN910A(RTN01). 3.Request new xD Vlan Services. | [6 empty] | Allstar | SQ202512190089-Allstar | Allstar | SQ202511190850-Allstar | 2026-01-02 | 2025-12-30 | Completed | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-26 | 2026-01-02 | 2025-12-26 | 2025-12-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110731 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-04 | 2025-12-10 | 2025-12-16 | 2025-12-16 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-12-04 | 2025-12-10 | 2025-12-19 | 2025-12-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-12-04 | 2025-12-10 | 2025-12-17 | 2025-12-17 | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2025-12-04; 2024-10-23: 2025-12-10; 2024-10-23: 2025-12-11; 2024-10-23: 2025-12-11 |  |  | 2025-12-23 | 2026-01-23 | 2025-12-23 | 2025-12-23 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511040438-GTSB
9450A_IPR | Fortune Lane MP | DU00006260213 | Sarawak | Sarawak | 1.526670 | 110.342300 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9450A. NE_9450A New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and Sacofa Equipment-Tejas). New Optical Patch Cord cable with suitable type and length. | IPRAN Port Upgrade | IPRAN Port Upgrade from existing Optical 1G to 10G port at 9450A. Site Impacted : 9450A, 9301B & 9155K/Q00149. SACOFA PORT INFO: ETH 1-3-4 NE_9450A 1.Enable port 8-EM6-3 of existing RTN910A(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Request new xD vlan services if needed from ZTE IPRAN Team. 5.Disable port 8-EM6-1 of existing RTN910A(RTN01) and remove existing CAT6 cable. | IPRAN Port Upgrade from existing Optical 1G to 10G port at 9450A. Site Impacted : 9450A, 9301B & 9155K/Q00149. SACOFA PORT INFO: ETH 1-3-4 NE_9450A 1.Enable port 8-EM6-3 of existing RTN910A(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Request new xD vlan services if needed from ZTE IPRAN Team. 5.Disable port 8-EM6-1 of existing RTN910A(RTN01) and remove existing CAT6 cable. | [6 empty] | Allstar | SQ202511260518-Allstar | Allstar | SQ202511110826-Allstar | 2026-01-02 | 2025-12-30 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-26 | 2026-01-02 | 2025-12-26 | 2025-12-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110732 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-11 | 2025-11-18 | 2025-11-21 | 2025-11-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-11 | 2025-11-18 | 2025-11-21 | 2025-11-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-11 | 2025-11-11 | 2025-11-18 | 2025-11-22 | 2025-11-22 | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2025-11-11; 2024-10-23: 2025-11-18; 2024-10-23: 2025-11-11; 2024-10-23: 2025-11-11 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511040438-GTSB
9374A_IPR | Stapang | DU00006260214 | Sarawak | Sarawak | 2.374023 | 112.114455 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9374A. NE_9374A New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and Sacofa Equipment). New Optical Patch Cord cable with suitable type and length. | IPRAN Port Upgrade | IPRAN Port Upgrade from existing Optical 1G to 10G port at 9374A. Site Impacted : 9374A, 9050Z & 9051Z. SACOFA PORT INFO: 10GE 1-21 NE_9374A 1.Enable port 8-EM6-3 of existing RTN910A(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Request new xD vlan services if needed from ZTE IPRAN Team. 5.Disable port 8-EM6-1 of existing RTN910A(RTN01) and remove existing CAT6 cable. 6.If NEC IDU that use as a switch currently, once upgrade 10G port at HW RTN910AF. Thus may decom, if no other traffic backhauling via it. | IPRAN Port Upgrade from existing Optical 1G to 10G port at 9374A. Site Impacted : 9374A, 9050Z & 9051Z. SACOFA PORT INFO: 10GE 1-21 NE_9374A 1.Enable port 8-EM6-3 of existing RTN910A(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Request new xD vlan services if needed from ZTE IPRAN Team. 5.Disable port 8-EM6-1 of existing RTN910A(RTN01) and remove existing CAT6 cable. 6.If NEC IDU that use as a switch currently, once upgrade 10G port at HW RTN910AF. Thus may decom, if no other traffic backhauling via it. | [6 empty] | Allstar | SQ202512120287-Allstar | Allstar | SQ202511190850-Allstar | 2026-01-02 | 2025-12-30 | Completed | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-26 | 2026-01-02 | 2025-12-26 | 2025-12-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110733 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-19 | 2025-11-25 | 2025-11-19 | 2025-11-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-19 | 2025-11-25 | 2025-12-03 | 2025-12-03 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-19 | 2025-11-19 | 2025-11-25 | 2025-12-02 | 2025-12-02 | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2025-11-19; 2024-10-23: 2025-11-25; 2024-10-23: 2025-11-19; 2024-10-23: 2025-11-19 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511040438-GTSB
9849A_IPR | Park City Mall IB | DU00006260215 | Sarawak | Sarawak | 3.180330 | 113.037500 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9849A. NE_9849A New RTN910AF x1. New CAT6 cables x2. New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and Sacofa Equipment). New Optical Patch Cord cable with suitable type and length. | IPRAN Port Upgrade | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS FIRST IN ORDER TO CONFIRM CONNECTIVITY RAN 9849A & RAN 9670A AT 9849A. 2.IF "YES" CURRENTLY USING IDU NEC AS A SWITCH IN WHICH BOTH RAN(9849A & 9670A) CONNECTED TO IDU NEC AND IDU NEC WILL CONNECTED TO NORTHBOUND WITH SACOFA. THUS MAY PROCEED BELOW SOW. IF "NO", THEN NEED TO AMEND SOW BELOW. 3.PLEASE TRIGGER IMMEDIATE PLANNER WHEN TEAM AT SITE PERFORM SURVEY.**** IPRAN Port Upgrade from existing Optical 1G to 10G port at 9849A. Site Impacted : 9849A & 9670A SACOFA PORT INFO: 1-1-3 10g NE_9849A 1.Install new RTN910AF and power-up. 2.Enable port 8-EM6-3 of new RTN910A(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Enable port 8-EM6-1 of new RTN910A(RTN01) and patching tu RAN 9849A. 5.Enable port 8-EM6-2 of new RTN910A(RTN01) and patching tu RAN 9670A. 6.Request new xD Vlan DCN and Vlan Services for 9849A & 9670A from ZTE IPRAN Team. 7.If confirm during survey, NEC IDU currently use as a switch, once upgrade 10G port done at HW RTN910AF and both traffics backhaul via it. Later may decom, if still no other traffic backhauling via it. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS FIRST IN ORDER TO CONFIRM CONNECTIVITY RAN 9849A & RAN 9670A AT 9849A. 2.IF "YES" CURRENTLY USING IDU NEC AS A SWITCH IN WHICH BOTH RAN(9849A & 9670A) CONNECTED TO IDU NEC AND IDU NEC WILL CONNECTED TO NORTHBOUND WITH SACOFA. THUS MAY PROCEED BELOW SOW. IF "NO", THEN NEED TO AMEND SOW BELOW. 3.PLEASE TRIGGER IMMEDIATE PLANNER WHEN TEAM AT SITE PERFORM SURVEY.**** IPRAN Port Upgrade from existing Optical 1G to 10G port at 9849A. Site Impacted : 9849A & 9670A SACOFA PORT INFO: 1-1-3 10g NE_9849A 1.Install new RTN910AF and power-up. 2.Enable port 8-EM6-3 of new RTN910A(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Enable port 8-EM6-1 of new RTN910A(RTN01) and patching tu RAN 9849A. 5.Enable port 8-EM6-2 of new RTN910A(RTN01) and patching tu RAN 9670A. 6.Request new xD Vlan DCN and Vlan Services for 9849A & 9670A from ZTE IPRAN Team. 7.If confirm during survey, NEC IDU currently use as a switch, once upgrade 10G port done at HW RTN910AF and both traffics backhaul via it. Later may decom, if still no other traffic backhauling via it. | [6 empty] | Allstar | SQ202512170182-Allstar | Allstar | SQ202511190850-Allstar | 2026-01-22 | 2026-01-15 | Completed | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110734 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-04 | 2025-12-10 | 2025-12-04 | 2025-12-04 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-12-04 | 2025-12-10 | 2025-12-12 | 2025-12-12 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-04 | 2025-12-04 | 2025-12-10 | 2025-12-08 | 2025-12-10 | TONI//ANAK KUMBONG/6798000163 | 2024-10-17: 2025-12-04; 2024-10-23: 2025-12-10; 2024-10-23: 2025-12-04; 2024-10-23: 2025-12-04 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511040438-GTSB
9423A_IPR | Siniawan | DU00006260216 | Sarawak | Sarawak | 1.439590 | 110.221460 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9423A. NE_9423A New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF-RTN02 and Sacofa Equipment-Tejas). New Optical Patch Cord cable with suitable type and length. | IPRAN Port Upgrade | IPRAN Port Upgrade from existing Optical 1G to 10G port at 9423A. Site Impacted : 9423A & 9359K. SACOFA PORT INFO: 10GE 1-3-15 NE_9423A 1.Enable port 8-EM6-3 of existing RTN910A(RTN02). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN02) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Request new xD vlan services if needed from ZTE IPRAN Team. 5.Disable port 8-EM6-1 of existing RTN910A(RTN02) and remove existing CAT6 cable. | IPRAN Port Upgrade from existing Optical 1G to 10G port at 9423A. Site Impacted : 9423A & 9359K. SACOFA PORT INFO: 10GE 1-3-15 NE_9423A 1.Enable port 8-EM6-3 of existing RTN910A(RTN02). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN02) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Request new xD vlan services if needed from ZTE IPRAN Team. 5.Disable port 8-EM6-1 of existing RTN910A(RTN02) and remove existing CAT6 cable. | [6 empty] | Allstar | SQ202511170524-Allstar | Allstar | SQ202511170485-Allstar | 2026-01-02 | 2025-12-30 | Completed | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-26 | 2026-01-02 | 2025-12-26 | 2025-12-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110735 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-11 | 2025-11-18 | 2025-11-21 | 2025-11-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-11 | 2025-11-18 | 2025-11-21 | 2025-11-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-11-11 | 2025-11-18 | 2025-11-22 | 2025-11-22 | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2025-11-11; 2024-10-23: 2025-11-18; 2024-10-23: 2025-11-11; 2024-10-23: 2025-11-11 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511040438-GTSB
9516A_IPR | Morsjaya MP | DU00006260217 | Sarawak | Sarawak | 4.354708 | 113.988501 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9516A. NE_9516A New SFP Module 10G with 10Km 1310nm x2(For ZTE RAN & Sacofa). New Optical Patch Cord cable x1 with suitable type and length. | BBU Patching | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 9516A. Site Impacted : 9516A. SACOFA PORT INFO: 10GE 1-4-1 NE_9516A 1.Insert new suitable SFP Module 10G into port 10G RAN. Enable it. 2.Patching new Optical Patch Cord cable to port 10G RAN and Sacofa eqpt. 3.Request new xD Vlan Services. | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 9516A. Site Impacted : 9516A. SACOFA PORT INFO: 10GE 1-4-1 NE_9516A 1.Insert new suitable SFP Module 10G into port 10G RAN. Enable it. 2.Patching new Optical Patch Cord cable to port 10G RAN and Sacofa eqpt. 3.Request new xD Vlan Services. | [6 empty] | Allstar | SQ202512240390-Allstar | Allstar | SQ202511190850-Allstar | 2026-01-02 | 2025-12-30 | Completed | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-26 | 2026-01-02 | 2025-12-26 | 2025-12-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110736 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-04 | 2025-12-10 | 2025-12-16 | 2025-12-16 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-12-04 | 2025-12-10 | 2025-12-19 | 2025-12-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-10 | 2025-12-04 | 2025-12-10 | 2025-12-17 | 2025-12-17 | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2025-12-04; 2024-10-23: 2025-12-10; 2024-10-23: 2025-12-06; 2024-10-23: 2025-12-06 |  |  | 2025-12-23 | 2026-01-23 | 2025-12-23 | 2025-12-23 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511040438-GTSB
9375B_IPR | Rantau Panjang | DU00006260218 | Sarawak | Sarawak | 2.416068 | 111.839302 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9375B. NE_9375B New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and Sacofa Equipment-Tejas). New Optical Patch Cord cable with suitable type and length. | IPRAN Port Upgrade | ****IMPORTANT NOTE: 1.AS 2X EB SITES EXIST, NEED TO APPLY CRQ FOR EB SITES. 2.PLEASE DRAW NE ICON FOR 2X EB SITES(9238E & 9239E) IN HUAWEI NMS. IPRAN Port Upgrade from existing Optical 1G to 10G port at 9375B. Site Impacted : 9375B, 9048Z, 9038K, 9238E & 9239E. SACOFA PORT INFO: 10GE 1-3-4 NE_9375B 1.Enable port 8-EM6-3 of existing RTN910AF(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910AF(RTN01) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffics 9375B, 9048Z, 9038K, 9238E & 9239E into new 10G port at 8-EM6-3 of existing RTN910AF(RTN01). 6.Disable port 8-EM6-1 & 8-EM6-4 of existing RTN910AF(RTN01) and remove existing CAT6 cable. | ****IMPORTANT NOTE: 1.AS 2X EB SITES EXIST, NEED TO APPLY CRQ FOR EB SITES. 2.PLEASE DRAW NE ICON FOR 2X EB SITES(9238E & 9239E) IN HUAWEI NMS. IPRAN Port Upgrade from existing Optical 1G to 10G port at 9375B. Site Impacted : 9375B, 9048Z, 9038K, 9238E & 9239E. SACOFA PORT INFO: 10GE 1-3-4 NE_9375B 1.Enable port 8-EM6-3 of existing RTN910AF(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910AF(RTN01) to Sacofa Tejas(Request from ZTE IPRAN team). 4.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffics 9375B, 9048Z, 9038K, 9238E & 9239E into new 10G port at 8-EM6-3 of existing RTN910AF(RTN01). 6.Disable port 8-EM6-1 & 8-EM6-4 of existing RTN910AF(RTN01) and remove existing CAT6 cable. | [6 empty] | Allstar | SQ202512020099-Allstar | Allstar | SQ202511190850-Allstar // SQ202602040270-Allstar | 2026-03-02 | 2026-02-23 | Completed | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-09 | 2026-02-03 | 2026-02-03 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110737 |  | 2025-11-08 | 2025-11-11 | Completed | 2025-11-07 | 2025-11-08 | 2025-11-07 | 2025-11-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-17 | 2025-11-24 | 2025-11-17 | 2025-11-17 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-17 | 2025-11-24 | 2025-11-26 | 2025-11-26 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-17 | 2025-11-17 | 2025-11-24 | 2025-11-30 | 2025-11-30 | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2025-11-17; 2024-10-23: 2025-11-24; 2024-10-23: 2025-11-17; 2024-10-23: 2025-11-17 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202511040438-GTSB
1694B_POC | Puncak Alam Highway 3(ZED) | DU00004244948 | Central | Selangor | 3.173260 | 101.465065 | [7 empty] | 06. Other Issue | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2021B_EMS_POC | DiGi TOC (Lot 43) | DU00004244949 | Central | Selangor | 3.067712 | 101.569274 | [7 empty] | 06. Other Issue | POC for ZTE MW FNI | NA | [11 empty] | GTSB | No PR required-Under MW POC | GTSB | No PR required-Under MW POC |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24101032 |  | 2024-10-11 | 2024-10-15 | Completed | 2024-10-10 | 2024-10-11 | 2024-10-10 | 2024-10-15 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-04-17 | ALI//ATIF/6799000118 | GTSB TI | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-04-17 | ALI//ATIF/6799000118 | GTSB TI | [7 empty] | 2025-01-20 | 2025-01-31 | 2025-01-20 | 2025-05-04 | ALI//ATIF/6799000118 | 2024-10-17: 2025-01-20; 2024-10-23: 2025-01-31; 2024-10-23: 2025-01-20; 2024-10-23: 2026-01-29
K00321-K00399 | BAKAI | DU00004244950 | Northern | Kedah | 5.527910 | 100.739410 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Current existing SM link 15G_4+0_28M_XPIC_(NT05599) Keep for USP MONC , History Performance Utilization 66%. Cancel / Drop. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9115A_AD | Bukit Setiam (Celcom) | DU00005815237 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 28/8/2025 : Cutover done 27/8/2025 : MW IDU Relocation WIP 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: SM SW03337 Q00865-Q00254 MW1 | [7 empty] | Magicell | SQ202508140686-Magicell | Trintel | SQ202508271005-Trintel // SQ202508271008-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080843 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-28 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9000B20_EVT | PBTS BORNEO FLORA FESTIVAL 2025 | DU00005815238 | Sarawak | Sabah | 5.276370 | 115.255331 | [6 empty] | ZTE | 01. Pending Planning | [5 empty] | Planning and integration support only for event site 9000B20 Tx route: 9000B20-7084A 1) New port at 7084A-MAC-001 IOFC 2) New DCN IP 7084A RTN09 3) New DCN VLAN 7084A RTN09 4) New NE ID FE IDU 7084A RTN09 5) New NE ID NE IDU 9000B20 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241133-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
9115A_AD_3 | Bukit Setiam (Celcom) | DU00005815239 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 29/8/2025 : Cutover done 28/8/2025 : MW IDU Relocation WIP 27/8/2025 : MW IDU Relocation WIP 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW00934 Q00690_KUALA SANGAN - Q00865_BKT SETIAM | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080844 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-29 | 2025-08-29 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-29 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9115A_AD_8 | Bukit Setiam (Celcom) | DU00005815240 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 29/8/2025 : Cutover done 28/8/2025 : MW IDU Relocation WIP 27/8/2025 : MW IDU Relocation WIP 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW03606 Q00269_RHDINGON - Q00865_BKT SETIAM | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080846 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-29 | 2025-08-29 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-29 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9115A_AD_11 | Bukit Setiam (Celcom) | DU00005815241 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 27/8/2025 : Cutover done 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW03509 Q00262_BKT TT - Q00865_BKT SETIAM | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080847 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-27 | 2025-08-27 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-27 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9115A_AD_7 | Bukit Setiam (Celcom) | DU00005815242 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 28/8/2025 : Cutover done 27/8/2025 : MW IDU Relocation WIP 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW03533 Q01123 KelabuCamp - Q00865 BktSetiam | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080848 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-28 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9115A_AD_9 | Bukit Setiam (Celcom) | DU00005815243 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 27/8/2025 : Cutover done 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW03681 Q00258 RhChabi - Q00865 BktSetiam | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080849 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-27 | 2025-08-27 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-27 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9115A_AD_4 | Bukit Setiam (Celcom) | DU00005815244 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 27/8/2025 : Cutover done 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW03866 Q00262 Bkttt - Q00865 BktSetiam | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080850 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-27 | 2025-08-27 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-27 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9115A_AD_6 | Bukit Setiam (Celcom) | DU00005815245 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 28/8/2025 : Cutover done 27/8/2025 : MW IDU Relocation WIP 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW03532 Q01121 Kualaanau - Q00865 BktSetiam | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-30 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080851 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-28 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9115A_AD_5 | Bukit Setiam (Celcom) | DU00005815246 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 28/8/2025 : Cutover done 27/8/2025 : MW IDU Relocation WIP 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW03517 Q01122 Rumahmandau - Q00865 BktSetiam | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080852 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-29 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-28 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9115A_AD_10 | Bukit Setiam (Celcom) | DU00005815247 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 27/8/2025 : Cutover done 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW03761 Q00471 LdgWoodman - Q00865 BktSetiam | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080853 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-27 | 2025-08-27 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-27 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9115A_AD_2 | Bukit Setiam (Celcom) | DU00005815248 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 28/8/2025 : Cutover done 27/8/2025 : MW IDU Relocation WIP 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW03784 Q00254_BKT NYABAU - Q00865_BKTSETIAM | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080854 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-29 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-28 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
9115A_AD_1 | Bukit Setiam (Celcom) | DU00005815249 | Sarawak | Sarawak | 2.968716 | 112.929950 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 28/8/2025 : Cutover done 27/8/2025 : MW IDU Relocation WIP 26/8/2025 : MW IDU Relocation WIP | TSS+AA+TI | L1+ATP+PAC |  | MW IDU Relocation | Relocate IDU from xC Cabin to xD Cabin. Involved MW link: Huawei SW03785 Q00254_BKT NYABAU - Q00865_BKTSETIAM | [7 empty] | Magicell | SQ202510010089-Magicell | Trintel | SQ202508271008-Trintel // SQ202509040608-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-29 | 2025-08-27 | 2025-08-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080855 |  | 2025-08-10 | 2025-08-25 | Completed | 2025-08-09 | 2025-08-10 | 2025-08-09 | 2025-08-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-25 | 2025-08-30 | 2025-08-28 | 2025-08-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-28 | 2025-08-25 | 2025-08-30 | 2025-10-28 | 2025-10-28 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-10-17: 2025-08-25; 2024-10-23: 2025-08-30; 2024-10-23: 2025-08-26; 2024-10-23: 2025-08-26 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507190089-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
1228H_AD | 99 Speedmart LESTARI PERDANA | DU00005525673 | Central | Selangor | 2.999170 | 101.665800 |  |  |  |  | On Hold | On Hold |  | 03. TSS Only | 14/7: Direction from CD, to perform MW survey only. | TSS |  | 23G_1+0_0.6/0.6_SP_56MHz_512QAM 2xRTN910A 2xXMC-3 SB A | MW Swap | MW SWAP 1228H-1401B WITH 23G_1+0_0.6/0.6_SP_56MHz_512QAM | MW SWAP 1228H-1401B WITH 23G_1+0_0.6/0.6_SP_56MHz_512QAM NE: 1. Swap new RTN910A. 2. Swap existing with XMC-3_SB A. 3. Swap new antenna 23G_0.6_SP. 4. Configure 23G_1+0_0.6/0.6_512QAM_56Mhz. | MW SWAP 1228H-1401B WITH 23G_1+0_0.6/0.6_SP_56MHz_512QAM FE: 1. Swap new RTN910A. 2. Swap existing with XMC-3_SB A. 3. Swap new antenna 23G_0.6_SP. 4. Configure 23G_1+0_0.6/0.6_512QAM_56Mhz. | XMC-3 SB A |  | 23 | 0.6 | 0.6 | Magicell | SQ202508010572-Magicell | Magicell | No PR required-Work at TSS only | 2025-11-29 | 2025-11-22 | Completed | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-25 | 2025-09-01 | 2025-08-25 | 2025-08-25 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072978 | WIP A23D06MAC-3NX x 2 | 2025-07-30 | 2025-08-01 | Completed | 2025-07-29 | 2025-07-30 | 2025-07-29 | 2025-08-01 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202505190547-GTSB | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | HSU//MYET CHAE/6799000011
4328A_IPR | Tronoh Tower | DU00006301127 | Northern | Perak | 4.430210 | 100.977000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x 10G SFP 40KM 2X PATCHCORD | MW IDU Patching | IDU Fiber 4328A-FIBER-4323A port upgrade to 10G Impact sites: 4161H,4328A,4551A,4050L,4599B,4551A Require 10G SFP and patch cord for 4328A-FIBER-4323A upgrade. Current 1G SFP is 40km Remarks: related to 4328A_IPR_1. Need to implement both at same time NE (4328A): 1) Install 10G SFP at 4328A RTN02 2) Upgrade IDU Fiber 4328A-FIBER-4323A to 10G FE (4323A): 1) Install 10G SFP at 4323A-MAC-001 (ops team to assign port. Recommend 0/2/3) 2) Upgrade IDU Fiber 4328A-FIBER-4323A to 10G | IDU Fiber 4328A-FIBER-4323A port upgrade to 10G Impact sites: 4161H,4328A,4551A,4050L,4599B,4551A Require 10G SFP and patch cord for 4328A-FIBER-4323A upgrade. Current 1G SFP is 40km Remarks: related to 4328A_IPR_1. Need to implement both at same time NE (4328A): 1) Install 10G SFP at 4328A RTN02 2) Upgrade IDU Fiber 4328A-FIBER-4323A to 10G FE (4323A): 1) Install 10G SFP at 4323A-MAC-001 (ops team to assign port. Recommend 0/2/3) 2) Upgrade IDU Fiber 4328A-FIBER-4323A to 10G | IDU Fiber 4328A-FIBER-4323A port upgrade to 10G Impact sites: 4161H,4328A,4551A,4050L,4599B,4551A Require 10G SFP and patch cord for 4328A-FIBER-4323A upgrade. Current 1G SFP is 40km Remarks: related to 4328A_IPR_1. Need to implement both at same time NE (4328A): 1) Install 10G SFP at 4328A RTN02 2) Upgrade IDU Fiber 4328A-FIBER-4323A to 10G FE (4323A): 1) Install 10G SFP at 4323A-MAC-001 (ops team to assign port. Recommend 0/2/3) 2) Upgrade IDU Fiber 4328A-FIBER-4323A to 10G | [5 empty] | GCI | SQ202601130193-GCI | GCI | SQ202601080374-GCI | 2026-01-15 | 2026-01-15 | Completed | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121666 |  | 2025-12-17 | 2026-01-02 | Completed | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2026-01-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-09 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-09 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-06 | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-12 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2024-10-17: 2026-01-04; 2024-10-23: 2026-01-13; 2024-10-23: 2026-01-04; 2024-10-23: 2026-01-07 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511130557-GCI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
4017B_IPR | Balik Pulau Town | DU00006301128 | Northern | Penang | 5.342800 | 100.225083 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cat 6 LAN Cable x1. | IDU-IPRAN | Perform LAG at CP site for IDU 4017B-BALIK PULAU TOWN-RTN06 to 4017B-MAC-001 Balik Pulau Town. Impact sites: 4097A,4706C 1) Patch IDU 4017B-BALIK PULAU TOWN-RTN06 GE2 to new CP port 2) Create LAG | Perform LAG at CP site for IDU 4017B-BALIK PULAU TOWN-RTN06 to 4017B-MAC-001 Balik Pulau Town. Impact sites: 4097A,4706C 1) Patch IDU 4017B-BALIK PULAU TOWN-RTN06 GE2 to new CP port 2) Create LAG | [6 empty] | GTSB | SQ202512160971-GTSB | GTSB | SQ202512160962-GTSB | 2025-12-31 | 2025-12-19 | Completed | 2025-12-17 | 2025-12-31 | 2025-12-17 | 2025-12-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25120353 |  | 2026-01-04 | 2025-12-05 | Completed | 2025-12-04 | 2026-01-04 | 2025-12-03 | 2025-12-05 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-12 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2024-10-17: 2025-12-11; 2024-10-23: 2025-12-11; 2024-10-23: 2025-12-11; 2024-10-23: 2025-12-12 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511130557-GCI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | CHEONG/SENG/WAH/7018000306
1831B_IPR | Taman Maju Kajang | DU00006301129 | Central | Selangor | 2.980282 | 101.819854 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_1831B New SFP Module 10G with 10Km 1310nm or suitable SFP Module x1(For HW RTN910AF and OB Fiber at ODF). New Optical Patch Cord cable with suitable type and length x1. FE_2715B New SFP Module 10G with 10Km 1310nm or suitable SFP Module x1(For IBeam and OB Fiber at ODF). New Optical Patch Cord cable with suitable type and length x1. | MW IDU Patching | Port upgrade from existing Optical 1G to 10G port at 1831B and 2715B. Site Impacted : 1900B,1263C,1831B,3933B & 3239D. NE_1831B 1.Enable port 8-EM6-3 of existing RTN910A(RTN01, NEID 9-34304). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01, NEID 9-34304) to OB Fiber at ODF. 4.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Migrate traffics 1900B,1263C,1831B,3933B & 3239D into new 10G port at IBeam(CP 2715B). 6.Disable port 8-EM6-1 of existing RTN910A(RTN01, NEID 9-34304) and remove existing CAT6 cable. FE_2715B 1.Insert new suitable SFP Module 10G into IBeam port. Please obtain info from ZTE IPRAN Team for new 10G port. 2.Patching Optical Patch Cord cable from IBeam(RTN910C) to ODF. 3.Request new vlan services from ZTE IPRAN Team. | Port upgrade from existing Optical 1G to 10G port at 1831B and 2715B. Site Impacted : 1900B,1263C,1831B,3933B & 3239D. NE_1831B 1.Enable port 8-EM6-3 of existing RTN910A(RTN01, NEID 9-34304). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01, NEID 9-34304) to OB Fiber at ODF. 4.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Migrate traffics 1900B,1263C,1831B,3933B & 3239D into new 10G port at IBeam(CP 2715B). 6.Disable port 8-EM6-1 of existing RTN910A(RTN01, NEID 9-34304) and remove existing CAT6 cable. | Port upgrade from existing Optical 1G to 10G port at 1831B and 2715B. Site Impacted : 1900B,1263C,1831B,3933B & 3239D. FE_2715B 1.Insert new suitable SFP Module 10G into IBeam port. Please obtain info from ZTE IPRAN Team for new 10G port. 2.Patching Optical Patch Cord cable from IBeam(RTN910C) to ODF. 3.Request new vlan services from ZTE IPRAN Team. | [5 empty] | GTSB | SQ202601130167-GTSB | GTSB | SQ202601130159-GTSB | 2026-03-02 | 2026-02-23 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-02-04 | 2026-01-21 | 2026-01-21 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25120848 |  | 2026-01-09 | 2026-01-10 | Completed | 2025-12-08 | 2026-01-09 | 2025-12-08 | 2026-01-10 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-10 | 2026-01-10 | 2026-01-10 | 2026-01-12 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-10 | 2026-01-10 | 2026-01-10 | 2026-01-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-12 | 2026-01-10 | 2026-01-10 | 2026-01-10 | 2026-01-14 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2024-10-17: 2026-01-10; 2024-10-23: 2026-01-10; 2024-10-23: 2026-01-10; 2024-10-23: 2026-01-12 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511130573-GTSB
4770A_IPR | Toklin (Trunk ) | DU00006301130 | Northern | Kedah | 5.630050 | 100.570910 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New CAT6 cable with suitable length(IDU HW to IBeam) x1. | MW IDU Patching | Perform LAG for 2x port of IDU & IBeam. Site Impacted: 4477C. NE_4770A 1.Enable port 8-EM6-2 of existing RTN910AF(RTN18, NEID 9-30355). 2.Request new IBeam port from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN18, NEID 9-30355) and new IBeam port(recommended GE0/2/18). 4.Create LAG between 2xport of IDU-IBeam. 5.Traffic 4477C will backhaul into LAG of IDU-IBeam. | Perform LAG for 2x port of IDU & IBeam. Site Impacted: 4477C. NE_4770A 1.Enable port 8-EM6-2 of existing RTN910AF(RTN18, NEID 9-30355). 2.Request new IBeam port from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN18, NEID 9-30355) and new IBeam port(recommended GE0/2/18). 4.Create LAG between 2xport of IDU-IBeam. 5.Traffic 4477C will backhaul into LAG of IDU-IBeam. | [6 empty] | GCI | SQ202601300955-GCI | GCI | SQ202601080374-GCI | 2026-03-02 | 2026-02-23 | Completed | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-13 | 2026-02-20 | 2026-02-13 | 2026-02-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121667 |  | 2025-12-17 | 2026-01-02 | Completed | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2026-01-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-28 | 2026-01-31 | 2026-01-28 | 2026-01-29 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2026-01-28 | 2026-01-31 | 2026-01-28 | 2026-01-29 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-30 | 2026-01-28 | 2026-01-31 | 2026-01-28 | 2026-02-11 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | 2024-10-17: 2026-01-28; 2024-10-23: 2026-01-31; 2024-10-23: 2026-01-28; 2024-10-23: 2026-01-29 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511130577-GTSB
1196A_IPR | JBA Puchong | DU00006301131 | Central | Selangor | 3.059004 | 101.630309 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New CAT6 cable with suitable length(IDU HW to IBeam) x1. | MW IDU Patching | Perform LAG for 2x port of IDU & IBeam. Site Impacted: 1243B,1283H & 3853B. NE_1196A 1.Enable port 17-EG6-2 of existing RTN910AF(RTN04, NEID 9-11822). 2.Request new IBeam port from ZTE IPRAN team and enable port. 3.Patching port 17-EG6-2 of existing RTN910AF(RTN04, NEID 9-11822) and new IBeam port. 4.Create LAG between 2xport of IDU-IBeam. 5.Traffics 1243B,1283H & 3853B will backhaul into LAG of IDU-IBeam. | Perform LAG for IDU & IBeam. Site Impacted: 1243B,1283H & 3853B. NE_1196A 1.Enable port 17-EG6-2 of existing RTN910AF(RTN04, NEID 9-11822). 2.Request new IBeam port from ZTE IPRAN team and enable port. 3.Patching port 17-EG6-2 of existing RTN910AF(RTN04, NEID 9-11822) and new IBeam port. 4.Create LAG between 2xport of IDU-IBeam. 5.Traffics 1243B,1283H & 3853B will backhaul into LAG of IDU-IBeam. | [6 empty] | GCI | SQ202601190064-GCI | GCI | SQ202512300465-GCI | 2026-03-02 | 2026-02-23 | Completed | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-23 | 2026-01-30 | 2026-01-23 | 2026-01-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121668 |  | 2025-12-17 | 2025-12-19 | Completed | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-15 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-16 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-15 | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-16 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2024-10-17: 2026-01-15; 2024-10-23: 2026-01-22; 2024-10-23: 2026-01-15; 2024-10-23: 2026-01-15 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511130573-GTSB
9354A_IPR | Kanowit | DU00006301132 | Sarawak | Sarawak | 2.097218 | 112.151161 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 9354A. NE_9354A New SFP Module 10G with 10Km 1310nm x2(For ZTE RAN & HW IBeam). New Optical Patch Cord cable x1 with suitable type and length. | BBU Patching | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 9354A. Site Impacted : 9354A. NE_9354A 1.Insert new suitable SFP Module 10G into new port 10G RAN. Enable it. 2.Patching new Optical Patch Cord cable to port 10G RAN and port 10G HW IBeam. 3.Request new 10G port at HW IBeam from ZTE IPRAN team and insert SFP Module 10G. 4.Patching Optical patch cord cable between new new port 10G RAN and new 10G port at HW IBeam. | IPRAN Port Upgrade from existing Electrical 1G to new Optical 10G port at 9354A. Site Impacted : 9354A. NE_9354A 1.Insert new suitable SFP Module 10G into new port 10G RAN. Enable it. 2.Patching new Optical Patch Cord cable to port 10G RAN and port 10G HW IBeam. 3.Request new 10G port at HW IBeam from ZTE IPRAN team and insert SFP Module 10G. 4.Patching Optical patch cord cable between new new port 10G RAN and new 10G port at HW IBeam. | [6 empty] | Allstar | SQ202601280703-Allstar | Allstar | SQ202601080404-Allstar |  |  | Ongoing | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-26 | 2026-04-01 | 2026-03-26 | 2026-03-26 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-07 | 2026-04-14 | 2026-04-07 | 2026-04-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25122950 |  | 2025-12-31 | 2026-01-03 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-03 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-26 | 2026-02-01 | 2026-01-26 | 2026-01-26 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-26 | 2026-02-01 | 2026-01-30 | 2026-01-30 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | SHIV KUMAR6800000084 |  | 2026-01-26 | 2026-01-26 | 2026-02-01 | 2026-02-24 | 2026-02-24 | ROYSTON//AHHOLE/6000038561 | 2024-10-17: 2026-01-26; 2024-10-23: 2026-02-01; 2024-10-23: 2026-01-26; 2024-10-23: 2026-01-26 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202511130580-GTSB
4328A_IPR_1 | Tronoh Tower | DU00006301133 | Northern | Perak | 4.430210 | 100.977000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+PAC | 2x 10G SFP 1KM 2X PATCHCORD | IPRAN Port Upgrade | To re-arrange IDU to IDU connection to avoid GE port bottleneck Require 10G SFP and patch cord for RTN03-RTN02 new connection Remarks: related to 4328A_IPR. Need to implement both at same time Proposed final IDU-IDU interconnection: 1) RTN02 RTN910A CSHRF GE3 10G IDU Fiber GE4 10G RTN03 4599B GE1 BBU GE2 RTN04 4050L 2) RTN03 RTN910A CSHRF GE3 10G RTN02 GE1 NLOS 4161H RTN01 RTN910A CSHR - decom SM IDU - decom | To re-arrange IDU to IDU connection to avoid GE port bottleneck Require 10G SFP and patch cord for RTN03-RTN02 new connection Remarks: related to 4328A_IPR. Need to implement both at same time Proposed final IDU-IDU interconnection: 1) RTN02 RTN910A CSHRF GE3 10G IDU Fiber GE4 10G RTN03 4599B GE1 BBU GE2 RTN04 4050L 2) RTN03 RTN910A CSHRF GE3 10G RTN02 GE1 NLOS 4161H RTN01 RTN910A CSHR - decom SM IDU - decom | [6 empty] | GCI | SQ202601130193-GCI | GCI | SQ202601080371-GCI // SQ202601080374-GCI | 2026-01-15 | 2026-01-15 | Completed | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121670 |  | 2025-12-17 | 2026-01-02 | Completed | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2026-01-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-09 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-09 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-06 | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-12 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2024-10-17: 2026-01-04; 2024-10-23: 2026-01-13; 2024-10-23: 2026-01-04; 2024-10-23: 2026-01-07 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511130557-GCI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
4445A_AD | Chui Chak | DU00006323186 | Northern | Perak | 4.048391 | 101.173610 | [7 empty] | 05. Doable |  | TSS+TI | L1+ATP+PAC | BBU Patching direct to existing TM LL. NE_4445A New CAT6 cable x1. | BBU Patching | ****IMPORTANT NOTE: 1.PLEASE ENSURE DU 4302B_AD PERFORM FIRST BEFORE PERFORM DU 4445A_AD. IF NOT 4302B WILL HAVE OUTAGE AND LOSSCOMM**** BU Patching direct to existing TM LL. Site Impacted : 4445A. NE_4445A. 1.Disable port 8-EM6-1(TM LL) & 8-EM6-2(BBU) at RTN910AF(NEID 30485) and remove existing CAT6 cables from these ports. 2.Patching existing BBU 4445A direct to existing TM LL and using same port at IBeam(CP 4521A). | ****IMPORTANT NOTE: 1.PLEASE ENSURE DU 4302B_AD PERFORM FIRST BEFORE PERFORM DU 4445A_AD. IF NOT 4302B WILL HAVE OUTAGE AND LOSSCOMM**** BBU Patching direct to existing TM LL. Site Impacted : 4445A. NE_4445A. 1.Disable port 8-EM6-1(TM LL) & 8-EM6-2(BBU) at RTN910AF(NEID 30485) and remove existing CAT6 cables from these ports. 2.Patching existing BBU 4445A direct to existing TM LL and using same port at IBeam(CP 4521A). | [6 empty] | GTSB | SQ202512160971-GTSB | GTSB | SQ202512240260-GTSB |  |  | Ongoing | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-30 | 2026-05-07 | 2026-04-30 | 2026-05-01 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251118AK |  | 2025-11-19 | 2025-11-20 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2026-04-07 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2026-04-08 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2026-04-20 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2024-10-17: 2025-12-15; 2024-10-23: 2025-12-15; 2024-10-23: 2025-12-15; 2024-10-23: 2025-12-15 | [7 empty] | GTSB | SQ202511180725-GTSB
4410C_IPR | Uitm Sri Iskandar Perak | DU00006323187 | Northern | Perak | 4.351519 | 100.954200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module x2 Fiber patch cord x 1 pairs. | BBU Patching | Impact site: 4410C Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Impact site: 4410C Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | [6 empty] | GCI | SQ202601080397-GCI | GCI | SQ202601080374-GCI | 2026-01-10 | 2026-01-09 | Completed | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-07 | 2026-01-08 | 2026-01-07 | 2026-01-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-10 | 2026-01-09 | 2026-01-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121671 |  | 2025-12-17 | 2026-01-02 | Completed | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2026-01-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-13 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-13 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | SHIV KUMAR6800000084 |  | 2026-01-06 | 2026-01-04 | 2026-01-13 | 2026-01-04 | 2026-01-14 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2024-10-17: 2026-01-04; 2024-10-23: 2026-01-13; 2024-10-23: 2026-01-04; 2024-10-23: 2026-01-06 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511180718-GCI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | CHEONG/SENG/WAH/7018000306
R00023_AD | R001B_R00023OD_KUALAPERLIS | DU00006323188 | Northern | Perlis | 6.383942 | 100.152053 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 4X ISM8 CARD 2X RTN910A 2X 13G 1.2M MDD ANTENNA 1x ODU 13G XMC5D SUB B HI 1x ODU 13G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL LINK R00023-R00028 WITH HUAWEI_13G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_B_WITH CA_4.88KM IMPACTED: 4608B THIS LINK WILL BE EPLA WITH DU R00023_AD_1 13G 2+0 AND BECOME 6+0 THIS LINK CARRY 4608B NEW LINK | 1. INSTALL NEW IDU RTN 910 AND 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. EPLA WITH DU R00023_AD_1 13G 2+0 BECOME 13G 6+0 | 1. INSTALL NEW IDU RTN 910 AND 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. EPLA WITH DU R00023_AD_1 13G 2+0 BECOME 13G 6+0 6. PATCH TO NEW 10G PORT | XMC5D | MDD | 13G | 1.2 | 1.2 | Magicell | SQ202511260138-Magicell | Magicell | SQ202511260111-Magicell // SQ202511260115-Magicell | 2025-12-10 | 2025-12-10 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251118AL |  | 2025-11-19 | 2025-11-24 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-21 | 2025-11-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-01 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-13 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2024-10-17: 2025-11-25; 2024-10-23: 2025-11-25; 2024-10-23: 2025-11-25; 2024-10-23: 2025-11-28 |  |  | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511180718-GCI | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
4859B_IPR | Kuala Tekai (Celcom) | DU00005837040 | Northern | Kedah | 6.227086 | 100.651661 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module 1KM x 3. Fiber patch cord x 3 pairs RTN910A x1. | MW Hardware Upgrade | IDU Fiber Port Upgrade to 10G SFP Module for link 4859B/4859B-Fiber-4999A. Impact sites: 4859B,4720B,K00336 NE (4859B): 1) Swap existing RTN950A_RTN 02 (ID : 13570) to new RTN910AF. (RTN no provide by Ops team). 2) Transfer traffic 4859B BBU and 2xSM xC IDU for 4720B and 4622K/K00336 to new RTN910AF. 3) Install 10G SFP at new RTN910AF_GE3. 4) Upgrade IDU Fiber 4859B-4999A to 10G. 5) Create New IN Band DCN. 6) Decom existing RTN950A_RTN02. FE (4999A): 1) Install 10G SFP at 4999A-MAC-001 GE0/2/24. 2) Upgrade IDU Fiber 4999A-4859B to 10G. | IDU Fiber Port Upgrade to 10G SFP Module for link 4859B/4859B-Fiber-4999A. Impact sites: 4859B,4720B,K00336 NE (4859B): 1) Swap existing RTN950A_RTN 02 (ID : 13570) to new RTN910AF. (RTN no provide by Ops team). 2) Transfer traffic 4859B BBU and 2xSM xC IDU for 4720B and 4622K/K00336 to new RTN910AF. 3) Install 10G SFP at new RTN910AF GE3. 4) Upgrade IDU Fiber 4859B-4999A to 10G. 5) Create New IN Band DCN. 6) Decom existing RTN950A_RTN02. | IDU Fiber Port Upgrade to 10G SFP Module for link 4859B/4859B-Fiber-4999A. Impact sites: 4859B,4720B,K00336 FE (4999A): 1) Install 10G SFP at 4999A-MAC-001 GE0/2/24. 2) Upgrade IDU Fiber 4999A-4859B to 10G. | [5 empty] | CCSMY | SQ202508290687-CCS | CCSMY | SQ202509020097-CCS // SQ202509020101-CCS |  |  | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25072282 |  | 2025-07-23 | 2025-07-25 | Completed | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-25 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-31 | 2025-08-13 | 2025-09-18 | CHEN TAK//EOH YANG/7021000004 | CCS TI | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | CHEN TAK//EOH YANG/7021000004 | CCS TI | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-08-13 | 2025-08-31 | 2025-08-13 | 2026-04-01 | CHEN TAK//EOH YANG/7021000004 | 2024-10-17: 2025-08-13; 2024-10-23: 2025-08-31; 2024-10-23: 2025-08-13; 2024-10-23: 2025-08-13 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507250560-GCI | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | CHEONG/SENG/WAH/7018000306
Q00313_IPR | Q125A_Q00313OD_CB_BKTTIONG | DU00005837041 | Sarawak | Sarawak | 4.881264 | 115.395869 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 17/9/2025 : Cutover done 13/9/2025 : Plan to do MW IDU Patching - Re-plan due to OSS not available to collect keys 12/9/2025 : Plan to do MW IDU Patching - Re-plan tomorrow due to CRQ late approved 29/8/2025 : Plan to do MW IDU Patching - Shortage 2 SFP Cisco 1G | TSS+TI | L1+ATP+PAC | 1X LAN Cable | MW IDU Patching | Split traffic at IDU Huawei SW03619 Q00313_BKT TIONG - Q00362_SUNDAR GE1 to PTN 30108-BKTTIONG GE0/0/3 NE (Q00313): 1) Patch IDU Huawei SW03619 Q00313_BKT TIONG - Q00362_SUNDAR GE2 to new PTN port (ops team to assign) 2) Transfer traffic from site Q00604_KG AWAT AWAT to new PTN port Q00604 is still using ERICSSON BBU. Require assistant from xC NOC to verify site status during reengineering work | Split traffic at IDU Huawei SW03619 Q00313_BKT TIONG - Q00362_SUNDAR GE1 to PTN 30108-BKTTIONG GE0/0/3 NE (Q00313): 1) Patch IDU Huawei SW03619 Q00313_BKT TIONG - Q00362_SUNDAR GE2 to new PTN port (ops team to assign) 2) Transfer traffic from site Q00604_KG AWAT AWAT to new PTN port Q00604 is still using ERICSSON BBU. Require assistant from xC NOC to verify site status during reengineering work | N/A | [5 empty] | CCSMY | SQ202508040508-CCS | CCSMY | SQ202508040528-CCS | 2025-11-25 | 2025-11-24 | Completed | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | Hermanwijaya bin suardi7021000085 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080517 |  | 2025-08-06 | 2025-08-21 | Completed | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-17 | 2025-09-30 | 2025-09-17 |  | MUHAMMAD SYAFIQ BIN AHMAD SUHAIMI7021000007 | CCS TI | 2025-09-17 | 2025-09-30 | 2025-09-17 |  | MUHAMMAD SYAFIQ BIN AHMAD SUHAIMI7021000007 | CCS TI | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-17 | 2025-09-17 | 2025-09-30 | 2025-09-17 |  | MUHAMMAD SYAFIQ BIN AHMAD SUHAIMI7021000007 | [10 empty] | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
2070B | 2070B | DU00003671276 | Central | Selangor | 3.244528 | 101.710361 |  | JUN 24 | 31 | JUN 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 4/7: Cutover done 27/6: Revise solution. Need 10G 10km SFP module | TSS+TI | L1+ATP+PAC |  | IDU-IPRAN | Expansion from 1G TO 10G ,10G IPRAN port reengineering at IBeam 2070B-MAC-001 Gombak TX/GigabitEthernet0/6/0 FE (2070B) at IBeam: 1) Transfer fiber patch cord from GE0/3/1 1G TO NEW port GE0/6/0 2) Insert new Fiber SFP module 10G SFP SM 1330 40km at port GE0/6/0 AND migrate traffic to new interface | [7 empty] | Allstar | SQ202407050105-Allstar | Allstar | SQ202409110341-Allstar | 2024-08-23 | 2024-08-22 | Completed | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-25 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-17 | 2024-07-18 | 2024-07-17 | 2024-07-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24053073 |  | 2024-05-31 | 2024-07-30 | Completed | 2024-05-30 | 2024-05-31 | 2024-05-30 | 2024-07-30 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-06-27 | 2024-06-30 | 2024-06-26 | 2024-11-19 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | Allstar TI | 2024-06-27 | 2024-09-30 | 2024-06-26 | 2024-09-23 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | Allstar TI | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2024-07-04 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-06-27 | 2024-06-30 | 2024-06-26 | 2024-07-10 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | 2024-10-17: 2024-06-27; 2024-10-23: 2024-06-30; 2024-10-23: 2024-06-26; 2024-10-23: 2024-06-27 |  |  | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358
1413A | 1413A | DU00003671277 | Central | Selangor | 3.319439 | 101.576111 |  |  |  |  | Cancel / Drop | No need proceed | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4368A | 4368A | DU00003671278 | Northern | Perak | 4.330629 | 101.145286 |  |  | WK32-WK35 | AUG 24 | Planning |  |  | 00. Site Out/Drop | 3/10: Link Drop. SOW done by MSP |  |  | 1x new suitable Fiber 1G SFP SM 1550 40km Module 1x Fiber Patch Cord cable | Cancel / Drop | 1G IPRAN reengineering at IBeam 4368A. FE (4368A) at IBeam: 1) Insert new Fiber SFP module 1G SF at new 1G port GE (GE0/3/5). 2) Re-patching existing Fiber patch cord cable to new 1G port (GE0/3/5). Impact sites:4361A,4362A,4975C | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24071006 |  | 2024-07-11 | 2024-08-17 | Completed | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-08-17 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed
3354A_1_HU | pBTS SP Heights | DU00005361185 | Northern | Kedah | 5.630889 | 100.545155 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 3354A 1. RTN910A x1. 4770A 1.RTN910A x1. | MW Hardware Upgrade | Existing link 23G_1+0_112M 23G_2+0_112M Site Impacted : 3354A. NE_3354A 1.Install new RTN910A due to existing legacy IDU cant support for EPLA new 2+0 with existing 1+0. 2.Continue SOW with 3354A-4770A_1 FE_4479A. 1.Install new RTN910A due to existing legacy IDU cant support for EPLA new 2+0 with existing 1+0. 2.Continue SOW with 3354A - 4470A_1 | 3354A_HU_1 | FE_4479A. 1.Install new RTN910A due to existing legacy IDU cant support for EPLA new 2+0 with existing 1+0. 2.Continue SOW with 3354A-4770A_1 | [5 empty] | CCSMY | SQ202506300682-CCS | CCSMY | SQ202504260175-CCS // SQ202505020417-CCS // SQ202505020420-CCS | 2025-10-17 | 2025-10-10 | Completed | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | NG XIN NI6237001561 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-09-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-09-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-10 | 2025-10-17 | 2025-10-10 | 2025-10-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041710 |  | 2025-04-18 |  | Ongoing | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [7 empty] | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-07-22 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2026-04-27 | 2026-04-30 | 2026-04-27 |  | MOHAMMAD FAIZ BIN AHMAD6000068531 | 2024-10-17: 2026-04-27; 2024-10-23: 2026-04-30; 2024-10-23: 2026-04-27; 2024-10-23: 2026-05-06 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB_AA | SQ202510300144-GTSB
S01766-S00052 | RAMO SIMPANG TENGHILAN | DU00003426900 | Sabah | Sabah | 6.252500 | 116.333300 | WK06 | FEB 24 | WK21 | MAY 24 | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | 27/5: Cutover done 24/5: MOS & TI In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | DCN VLAN : 220, PORT NUMBER : Eth-Trunk3 NE 1. Swap Existing SM IDU with new RTN910A 2. Swap Existing SM ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub A) 3. Swap Existing SM Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 4. Configure link as 18GHz 1+0 110MHz FE 1. Swap Existing SM IDU with new RTN910A 2. Swap Existing SM ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub A) 3. Swap Existing SM Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 4. Configure link as 18GHz 1+0 110MHz | [7 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202411150570-NR Services | 2024-02-29 | 2024-02-28 | Completed | 2024-02-02 | 2024-02-02 | 2024-02-09 | 2024-02-09 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-15 | 2024-02-16 | 2024-02-15 | 2024-02-15 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-15 | 2024-02-16 | 2024-02-15 | 2024-02-15 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-02-28 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24052119 |  | 2024-05-22 | 2024-05-21 | Completed | 2024-05-21 | 2024-05-22 | 2024-05-21 | 2024-05-21 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-24 | 2024-05-31 | 2024-05-24 | 2024-05-27 | WILFRED BALANG7167000026 | NR Service TI | 2024-05-24 | 2024-05-31 | 2024-05-24 | 2024-05-27 | WILFRED BALANG7167000026 | NR Service TI | 2024-07-09 | 2024-07-09 | 2024-07-09 | 2024-07-09 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2024-05-24 | 2024-05-31 | 2024-05-24 | 2024-05-28 | WILFRED BALANG7167000026 | 2024-05-24 | 2024-05-31 | 2024-05-24 | 2024-05-24 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-06-26 | tseping//wang/6819000006 | Logistic Team | 2024-09-25 | 2024-10-25 | 2024-09-25 | 2024-09-25 | ASTI//GANIS PUTRIANI/6237001358
7076Z-7398A | T3E_0216_ Paitan-Nangoh 1 | DU00003426901 | Sabah | Sabah | 6.459857 | 117.351816 |  |  | WK32-WK35 | AUG 24 |  |  | ZTE | 00. Integrated/RFS Done | 10/9: D4: Cutover done. Post-CO T/Shooting WIP 7/9: D3: Installation done, pending alignment & CO 5/9: MOS & Pre-installation In Plan | TSS+AA+TI | L1+ATP+PAC | 13GHz_1.2m/1.2m_MDD_2+0_28MHz | MW Parallel Link | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/20 NE 1. Install New RTN910A 2. Install New 2 pcs of ISM 8 Cards at Slot 3, 4 3. Migrate Existing 13GHz 4+0 28MHz link into Slot 3, 4 4. Install New 13GHz 2+0 28MHz link into Slot 7 5. Install new XMC 5D 13GHz 2+0 28MHz ODU (Sub B + Sub B) 6. Install New Huawei 13GHz 1.2m DP MDD Antenna 7. Configure link as 13GHz 2+0 28MHz (EPLA with Existing 13GHz 4+0 28MHz link) FE 1. Install New RTN910A 2. Install New 2 pcs of ISM 8 Cards at Slot 3, 4 3. Migrate Existing 13GHz 4+0 28MHz link into Slot 3, 4 4. Install New 13GHz 2+0 28MHz link into Slot 7 5. Install new XMC 5D 13GHz 2+0 28MHz ODU (Sub B + Sub B) 6. Install New Huawei 13GHz 1.2m DP MDD Antenna 7. Configure link as 13GHz 2+0 28MHz (EPLA with Existing 13GHz 4+0 28MHz link) | [7 empty] | NR services | SQ202403220502-NR Services | NR services | SQ202409070071-NR Services // SQ202504260199-NR Services | 2024-11-15 | 2024-11-11 | Completed | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-14 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-14 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-11-11 | 2024-11-15 | 2024-11-11 | 2024-11-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240903A9 |  | 2024-09-04 | 2024-09-04 | Completed | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-05 | 2024-09-30 | 2024-09-05 | 2024-09-09 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-09-05 | 2024-09-30 | 2024-09-05 | 2024-09-09 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-09-05 | 2024-09-30 | 2024-09-05 | 2024-09-11 | RALPH O'BRYAN HILARY7167000030 | 2024-10-17: 2024-09-05; 2024-10-23: 2024-09-30; 2024-10-23: 2024-09-05; 2024-10-23: 2024-09-06 |  |  | 2024-12-20 | 2025-01-20 | 2024-12-20 | 2024-12-20 | ASTI//GANIS PUTRIANI/6237001358
7633B-7625A | Luasong Junction SBC | DU00003426902 | Sabah | Sabah | 4.542297 | 117.524510 | WK08 | FEB 24 |  |  | Pending TI | Team at other sites | ZTE | 05. Doable | Non-doable | TSS+AA+TI |  | 8GHz_1.8m/1.8m_DP_4+0_29.65MHz | MW Parallel Link | NE 1. Install New Huawei IDU RTN 910A 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Install New Huawei 8GHz 4+0 XMC 3 29.65MHz ODU (Sub A) 4. Install New Huawei 8GHz 1.8m DP Antenna 5. Configure link as 8GHz 4+0 29.65MHz 6. Offload 7633B-7625A-02/03 (V/H) & 7633B-7625A-01/02/03/04 traffic to this new link FE 1. Install New Huawei IDU RTN 910A 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Install New Huawei 8GHz 4+0 XMC 3 29.65MHz ODU (Sub A) 4. Install New Huawei 8GHz 1.8m DP Antenna 5. Configure link as 8GHz 4+0 29.65MHz 6. Patch the new RTN 910A to the new CP Port | NE 1. Install New Huawei IDU RTN 910A 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Install New Huawei 8GHz 4+0 XMC 3 29.65MHz ODU (Sub A) 4. Install New Huawei 8GHz 1.8m DP Antenna 5. Configure link as 8GHz 4+0 29.65MHz 6. Offload 7633B-7625A-02/03 (V/H) & 7633B-7625A-01/02/03/04 traffic to this new link | FE 1. Install New Huawei IDU RTN 910A 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Install New Huawei 8GHz 4+0 XMC 3 29.65MHz ODU (Sub A) 4. Install New Huawei 8GHz 1.8m DP Antenna 5. Configure link as 8GHz 4+0 29.65MHz 6. Patch the new RTN 910A to the new CP Port | [5 empty] | GTSB | SQ202403220495-GTSB | NR services | SQ202508270992-NR Services // SQ202508270995-NR Services | 2025-09-26 | 2025-09-23 | Completed | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | PAVITRAN AL CHINNAKOLANDAY6799000150 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-02-22 | 2024-02-23 | 2024-02-22 | 2024-02-22 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-22 | 2024-02-23 | 2024-02-22 | 2024-02-22 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2025-09-23 | 2025-09-26 | 2025-09-23 | 2025-09-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080130 | No 8G 1.8/1.8 DP antenna | 2025-08-02 | 2025-08-22 | Completed | 2025-08-01 | 2025-08-02 | 2025-08-01 | 2025-08-22 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed
S01516-7209A | SIPADAN INN 3 | DU00003426903 | Sabah | Sabah | 4.479200 | 118.614100 |  |  | WK05 | FEB 24 | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC |  | MW Remote Upgrade | NE 1. Change Bandwidth from 23GHz_1+0_56MHz to 23GHz_1+0_112MHz (will use new freq) 2. Please capture (screen shot) current metering (Tx Power, Rsl, etc) before proceed with this activity FE 1. Change Bandwidth from 23GHz_1+0_56MHz to 23GHz_1+0_112MHz (will use new freq) 2. Please capture (screen shot) current metering (Tx Power, Rsl, etc) before proceed with this activity | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-01 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 | [17 empty] | 2024-07-26 | 2024-08-26 | 2024-07-26 | 2024-07-26 | ASTI//GANIS PUTRIANI/6237001358
9677B-9069B | Jalan Bangau | DU00003426904 | Sarawak | Sarawak | 1.586844 | 110.316500 | WK08 | FEB 24 | WK21 | JUN 24 | TI In Plan | Pending Collection | ZTE | 00. Integrated/RFS Done | 27/6: D3: Cutover done 26/6: D2: Continue TI | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | DCN VLAN : 411, PORT NUMBER : GigabitEthernet0/5/2 NE 1. Swap Existing NEC IDU with new RTN910A 2. Swap Existing NEC ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub B) 3. Swap Existing NEC Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 4. Configure link as 18GHz 1+0 110MHz FE 1. Swap Existing NEC IDU with new RTN910A 2. Swap Existing NEC ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub B) 3. Swap Existing NEC Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 4. Configure link as 18GHz 1+0 110MHz | [7 empty] | Trintel | SQ202402210485-Trintel | Datasco | SQ202407020298-Datasco | 2024-03-31 | 2024-03-29 | Completed | 2024-02-16 | 2024-02-17 | 2024-02-19 | 2024-02-20 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-02-28 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-02-28 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-29 | 2024-03-31 | 2024-03-29 | 2024-03-29 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24050833 |  | 2024-05-09 | 2024-05-17 | Completed | 2024-05-08 | 2024-05-09 | 2024-05-08 | 2024-05-17 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-06-25 | 2024-06-29 | 2024-08-21 | 2024-08-21 | CHRISTOPER//YUSUF PANGIRAN/7019000051 | Datasco TI | 2024-06-25 | 2024-09-30 | 2024-08-12 | 2024-08-20 | CHRISTOPER//YUSUF PANGIRAN/7019000051 | Datasco TI | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-28 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-06-25 | 2024-06-29 | 2024-06-30 | 2024-06-30 | CHRISTOPER//YUSUF PANGIRAN/7019000051 | 2024-06-25 | 2024-06-29 | 2024-06-26 | 2024-06-26 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-05 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-07-30 | 2024-08-30 | 2024-07-30 | 2024-07-30 | ASTI//GANIS PUTRIANI/6237001358
Q00292-Q00267 | TM TUBAU | DU00003426905 | Sarawak | Sarawak | 3.144300 | 113.698300 | WK11 | MAR 24 |  |  | Drop | Pass to Huawei |  | 03. TSS Only | 14/3: Require get 2.4M antenna from E/// 7Mar: Parallel Link. FE Edotco site. Need Tower owner to study tower load issue | TSS |  | 8GHz_2.4m/2.4m_DP_4+0_29.65MHz | MW Parallel Link | - Proceed Survey with 2 Scenarios: 1. MW Parallel Link: 8GHz_2.4m/2.4m_DP_4+0_29.65MHz 2. MW Swap Link: 8GHz_2.4m/2.4m_DP_8+0_29.65MHz - Based on design, Rsl is quite low. Celcom quite flexible with link KPI | [7 empty] | Datasco | SQ202403220440-Datasco |  |  | 2024-04-05 | 2024-04-01 | Completed | 2024-03-11 | 2024-03-15 | 2024-03-13 | 2024-03-13 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. |  | Unassigned | Completed |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-03-28 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-03-28 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-01 | 2024-04-05 | 2024-04-01 | 2024-04-01 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [7 empty] | 2024-04-01 | 2024-04-05
7011C-7542B | Masjid Tuaran | DU00003426906 | Sabah | Sabah | 6.183694 | 116.235941 | WK06 | FEB 24 | WK09 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_SP_1+0_112MHz | MW Hardware Upgrade | NE 1. Reuse Existing RTN910A (RTN01) 2. Reuse Existing ISM 6 Card at Slot 7 3. Configure link as 23GHz 1+0 112MHz FE 1. Reuse Existing RTN910A (RTN02) 2. Swap Existing ISV 3 Card with New ISM 8 Card at Slot 4 3. Configure link as 23GHz 1+0 112MHz | [7 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202403220526-NR Services | 2024-05-31 | 2024-05-31 | Completed | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2024-02-04 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-09 | 2024-02-07 | 2024-02-07 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-09 | 2024-02-07 | 2024-02-07 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-31 | 2024-05-31 | 2024-05-31 | 2024-05-31 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240220AU |  | 2024-03-02 | 2024-03-01 | Completed | 2024-03-01 | 2024-03-02 | 2024-03-01 | 2024-03-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-27 | 2024-02-29 | 2024-02-26 | 2024-02-29 | RONNEY//LOUIS LUSIN/7167000022 | NR Service TI | 2024-02-27 | 2024-02-29 | 2024-02-26 | 2024-02-27 | RONNEY//LOUIS LUSIN/7167000022 | NR Service TI | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-27 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-27 | 2024-02-29 | 2024-02-26 | 2024-02-29 | RONNEY//LOUIS LUSIN/7167000022 | 2024-02-27 | 2024-02-29 | 2024-02-26 | 2024-02-27 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-03-19 | tseping//wang/6819000006 | Logistic Team | 2024-09-25 | 2024-10-25 | 2024-09-25 | 2024-09-25 | ASTI//GANIS PUTRIANI/6237001358
9971A-9069B | Masjid Matang Jaya Baru | DU00003426907 | Sarawak | Sarawak | 1.579944 | 110.297029 | WK16 | FEB 24 | WK19 | JUN 24 | TI In Plan | Pending Collection | ZTE | 00. Integrated/RFS Done | 24/6: D2: Cutover done 6/6: Pending TM Permit approval @9677B. TM team resource limited | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_MS_1+0_110MHz | MW Swap | DCN VLAN : 412, PORT NUMBER : GigabitEthernet0/5/2 NE 1. Swap Existing NEC IDU with new RTN910A 2. Swap Existing NEC ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 3. Swap Existing NEC Antenna with New Huawei 23GHz 0.6m DP MS Antenna 4. Configure link as 23GHz 1+0 112MHz FE 1. Swap Existing NEC IDU with new RTN910A 2. Swap Existing NEC ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 3. Swap Existing NEC Antenna with New Huawei 23GHz 0.6m DP MS Antenna 4. Configure link as 23GHz 1+0 112MHz | [7 empty] | Trintel | SQ202402210485-Trintel | Datasco | SQ202407020298-Datasco | 2024-03-31 | 2024-03-29 | Completed | 2024-02-16 | 2024-02-17 | 2024-02-19 | 2024-02-20 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-02-28 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-02-28 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-29 | 2024-03-31 | 2024-03-29 | 2024-03-29 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24042290 |  | 2024-04-23 | 2024-05-17 | Completed | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2024-05-17 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-24 | 2024-05-31 | 2024-08-21 | 2024-08-21 | CHRISTOPER//YUSUF PANGIRAN/7019000051 | Datasco TI | 2024-05-24 | 2024-05-31 | 2024-06-03 | 2024-06-25 | CHRISTOPER//YUSUF PANGIRAN/7019000051 | Datasco TI | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-06-24 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-05-24 | 2024-05-31 | 2024-06-28 | 2024-06-28 | CHRISTOPER//YUSUF PANGIRAN/7019000051 | 2024-05-24 | 2024-05-31 | 2024-06-15 | 2024-06-15 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-05 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-07-30 | 2024-08-30 | 2024-07-30 | 2024-07-30 | ASTI//GANIS PUTRIANI/6237001358
7255C-7155A | Tambalang | DU00003426908 | Sabah | Sabah | 6.184122 | 116.200080 | WK06 | FEB 24 | WK14 | APR 24 | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | 23/10: Suspect interference WK43: Link require rectification: Huawei 7255C-7155A_01_ZNIC_High error on MW link_Impact site: WOW 7255C | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/27 NE 1. Reuse Existing RTN950A (RTN01) 2. Swap Existing ISV 3 Card with New ISM 8 Card at Slot 1 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub A) 4. Swap Existing Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHz FE 1. Install New RTN910A 2. Dismantle ISV 3 Card at Slot 3 (RTN01) (RTN950) 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub A) 4. Swap Existing Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHz | [7 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202404030679-NR Services | 2024-02-16 | 2024-02-14 | Completed | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-02 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-09 | 2024-02-07 | 2024-02-07 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-09 | 2024-02-07 | 2024-02-07 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-14 | 2024-02-16 | 2024-02-14 | 2024-02-14 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24032848 |  | 2024-03-29 | 2024-03-30 | Completed | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-03-30 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-30 | 2024-04-06 | 2024-03-30 | 2024-04-03 | RONNEY//LOUIS LUSIN/7167000022 | NR Service TI | 2024-03-30 | 2024-04-06 | 2024-03-30 | 2024-04-03 | RONNEY//LOUIS LUSIN/7167000022 | NR Service TI | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-04-03 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2024-03-30 | 2024-04-06 | 2024-03-30 | 2024-04-04 | RONNEY//LOUIS LUSIN/7167000022 | 2024-03-30 | 2024-04-06 | 2024-03-30 | 2024-04-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
9338B-9106A | Ngiu Kee MP | DU00003426909 | Sarawak | Sarawak | 3.172977 | 113.039278 | WK10 | MAR 24 | WK09 | FEB 24 | TI | Pending L1 | ZTE | 00. Integrated/RFS Done | #N/A | TSS+TI+Dismantle | L1+ATP+MRCF+PAC |  | BBU Patching | - Sacofa LL at 9338B has been upgraded to 950Mbps - Current utilization (Wk 52) - 14.84% - Migrate back 9338B's Node B traffic to Sacofa LL thru BBU Patching Solution - Dismantle Interim Solution MW Link, 9338B-9106A (15GHz_0.6m/1.2m_DP_2+0_28MHz) | [7 empty] | NR Services | SQ202403220441-NR Services | NR Services | SQ202402210524-NR Services // SQ202409040308-NR Services // SQ202509260785-NR Services | 2024-04-05 | 2024-04-02 | Completed | 2024-02-26 | 2024-03-01 | 2024-03-02 | 2024-03-02 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-02 | 2024-03-02 | 2024-03-02 | 2024-03-02 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-08 | 2024-03-15 | 2024-03-08 | 2024-03-08 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-02 | 2024-04-05 | 2024-04-02 | 2024-04-02 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021312 |  | 2024-02-14 | 2024-02-17 | Completed | 2024-02-13 | 2024-02-14 | 2024-02-13 | 2024-02-17 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-21 | 2024-03-15 |  |  | Royson//Anak Stephen/7167000020 | NR Service TI | 2024-02-21 | 2024-03-15 | 2024-02-21 | 2024-03-03 | Royson//Anak Stephen/7167000020 | NR Service TI | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | C.PRATHABAN///6798000081 |  |  | 2024-02-21 | 2024-03-15 | 2024-03-15 | 2024-03-15 | Royson//Anak Stephen/7167000020 | 2024-02-21 | 2024-03-15 | 2024-02-21 | 2024-02-21 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-13 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-09-26 | 2024-10-26 | 2024-09-26 | 2024-09-26 | ASTI//GANIS PUTRIANI/6237001358
2187A7-7280B | pBTS Kampung Sepakat Jaya (C) | DU00003426910 | Sabah | Sabah | 6.065250 | 116.148151 | WK06 | FEB 24 | WK07 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_SP_1+0_112MHz | MW Hardware Upgrade | NE 1. Reuse Existing RTN910A 2. Install New ISM 8 Card at Slot 3 3. Dismantle Existing 2187A-7280B-01 (15GHz) link at Slot 7 4. Swap Existing Huawei ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 5. Configure link as 23GHz 1+0 112MHz FE 1. Reuse Existing RTN910A 2. Install New ISM 8 Card at Slot 3 3. Dismantle Existing 2187A-7280B-01 (15GHz) link at Slot 7 4. Swap Existing Huawei ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 5. Configure link as 23GHz 1+0 112MHz | [7 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202402210514-NR Services // SQ202409030641-NR Services | 2024-02-16 | 2024-02-14 | Completed | 2024-02-03 | 2024-02-03 | 2024-02-04 | 2024-02-04 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-09 | 2024-02-07 | 2024-02-07 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-09 | 2024-02-07 | 2024-02-07 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-14 | 2024-02-16 | 2024-02-14 | 2024-02-14 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021308 |  | 2024-02-14 | 2024-02-14 | Completed | 2024-02-13 | 2024-02-14 | 2024-02-13 | 2024-02-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-17 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-17 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-17 | 2024-02-17 | 2024-02-17 | 2024-02-17 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-18 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-17 | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-04-29 | tseping//wang/6819000006 | Logistic Team | 2024-09-25 | 2024-10-25 | 2024-09-25 | 2024-09-25 | ASTI//GANIS PUTRIANI/6237001358
7360A-7649B | Jeti Balimbang | DU00003426911 | Sabah | Sabah | 4.477665 | 118.628759 | WK08 | FEB 24 | WK09 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/16 NE 1. Reuse Existing RTN910A (RTN01) 2. Install New ISM 8 Card at Slot 3 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub A) 4. Swap Existing Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHz FE 1. Swap Existing RTN950 with New RTN910A 2. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub A) 3. Swap Existing Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 4. Configure link as 18GHz 1+0 110MHz | [7 empty] | Seri Pancar | SQ202402210501-Seri Pancar | Seri Pancar | SQ202403220527-Seri Pancar | 2024-11-15 | 2024-11-12 | Completed | 2024-02-12 | 2024-02-16 | 2024-02-18 | 2024-02-18 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-19 | 2024-02-23 | 2024-02-19 | 2024-02-19 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-19 | 2024-02-23 | 2024-02-19 | 2024-02-19 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-11-12 | 2024-11-15 | 2024-11-12 | 2024-11-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020652 |  | 2024-02-07 | 2024-02-07 | Completed | 2024-02-06 | 2024-02-07 | 2024-02-06 | 2024-02-07 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-27 | 2024-03-11 | 2024-02-27 | 2024-02-29 | SYLVERINUS//AHMUI MINIK/8366000008 | Seri Pancar TI | 2024-02-27 | 2024-03-11 | 2024-02-27 | 2024-02-29 | SYLVERINUS//AHMUI MINIK/8366000008 | Seri Pancar TI | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-28 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-27 | 2024-03-11 | 2024-02-27 | 2024-03-02 | SYLVERINUS//AHMUI MINIK/8366000008 | 2024-05-24: 2024-02-27; 2024-05-31: 2024-03-11; 2024-06-15: 2024-02-27; 2024-06-15: 2024-02-27 |  |  | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
7201B-7154A | KK Kg Sinompuro - UCA | DU00003426912 | Sabah | Sabah | 6.041343 | 116.170410 | WK06 | FEB 24 | WK07 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_SP_1+0_112MHz | MW Hardware Upgrade | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/1 NE 1. Swap Existing Huawei IDU with new RTN910A 2. Swap Existing ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 3. Configure link as 23GHz 1+0 112MHz FE 1. Install New Huawei IDU RTN910A 2. Dismantle Existing ISV 3 Card at Slot 3 (RTN02) 3. Swap Existing ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 4. Configure link as 23GHz 1+0 112MHz | [7 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202402210514-NR Services // SQ202409050206-NR Services | 2024-02-16 | 2024-02-16 | Completed | 2024-02-05 | 2024-02-05 | 2024-02-06 | 2024-02-06 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-15 | 2024-02-16 | 2024-02-15 | 2024-02-15 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-15 | 2024-02-16 | 2024-02-15 | 2024-02-15 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021303 |  | 2024-02-14 | 2024-02-14 | Completed | 2024-02-13 | 2024-02-14 | 2024-02-13 | 2024-02-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-16 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-17 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-16 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-17 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | tseping//wang/6819000006 | Logistic Team | 2024-09-25 | 2024-10-25 | 2024-09-25 | 2024-09-25 | ASTI//GANIS PUTRIANI/6237001358
9257R-9725C | Samalaju Township | DU00003426913 | Sarawak | Sarawak | 3.540140 | 113.298800 | WK08 | FEB 24 | WK11 | MAR 24 | RFS | TI WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | NE 1. Reuse Existing RTN910A (RTN01) 2. Install New ISM 8 Card at Slot 3 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub B) 4. Swap Existing Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHz FE 1. Reuse Existing RTN910A (RTN01) 2. Install New ISM 8 Card at Slot 3 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub B) 4. Swap Existing Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHz | [7 empty] | NR Services | SQ202402210489-NR Services | YPTT | SQ202403220516-YPTT | 2024-03-29 | 2024-03-26 | Completed | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-02-27 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-26 | 2024-03-29 | 2024-03-26 | 2024-03-26 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24030698 |  | 2024-03-07 | 2024-03-08 | Completed | 2024-03-06 | 2024-03-07 | 2024-03-06 | 2024-03-08 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-04-01 | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-04-01 | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-23 | NORAZHARI BIN MOHAMAD SALIM6794000032 | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-15 | 2024-06-14 | 2024-06-14 | 2024-06-14 | 2024-06-14 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-07-30 | 2024-08-30 | 2024-07-30 | 2024-07-30 | ASTI//GANIS PUTRIANI/6237001358
2710C-2047A | Bandar Seri Coalfield | DU00003441184 | Central | Selangor | 3.242156 | 101.490514 | WK09 | MAR 24 | WK09 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28MHZ_0.6M/1.2M_256QAM_B | MW Swap | MW SWAP MW LINK 2710C-2047A WITH HUAWEI_15G_4+0_28MHZ_0.6M/1.2M NE: 1. INSTALL 2 UNIT ISM8 CARD AT RTN01 SLOT 3&4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. REUSE EXISTING ISM8 SLOT 3 5. CONFIGURE LINK 15G 4+0 28MHZ WITH CA SLOT 3 & 4 6. DISMANTLE EXISTING LINK FE: 1. INSTALL 2 UNIT ISM8 CARD AT RTN03 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 4+0 28MHZ WITH CA 5. DISMANTLE EXISTING LINK | [7 empty] | Perwira | SQ202407050123-Perwira | Perwira | SQ202402270744-Perwira | 2024-08-16 | 2024-08-15 | Completed | 2024-02-26 | 2024-03-01 | 2024-03-01 | 2024-03-01 | WB80041943 |  | PERWIRA ENERGY SDN. BHD. |  | Unassigned | Completed |  | 2024-07-04 | 2024-07-05 | 2024-07-04 | 2024-07-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-04 | 2024-07-05 | 2024-07-04 | 2024-07-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-15 | 2024-08-16 | 2024-08-15 | 2024-08-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021006 |  | 2024-02-12 | 2024-02-29 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-02-29 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-03-01 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-03-01 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-02 | 2024-03-02 | 2024-03-02 | 2024-03-02 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-03-04 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-05-24: 2024-02-29; 2024-05-31: 2024-02-29; 2024-06-15: 2024-02-29; 2024-06-15: 2024-03-04 |  |  | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7511A-7623B | Kembara Sakti (Celcom | DU00003441185 | Sabah | Sabah | 5.329433 | 119.055700 | WK11 | MAR 24 | WK10 | MAR 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW Hardware Upgrade | NE 1. Reuse IDU 910A. Install 2x ISM8 Card at Slot 3 and Slot 4. 2. Swap existing Antenna with 1.8m MDD Antenna. 3. Swap existing 3+0 ODU with 4+0 5D ODU CA. 4.Configure link 4+0_800M_512QAM with EPLA FE 1. Reuse IDU 910A. Install 2x ISM8 Card at Slot 3 and Slot 4. 2. Swap existing Antenna with 1.8m MDD Antenna. 3. Swap existing 3+0 ODU with 4+0 5D ODU CA. 4. Configure link 4+0_800M_512QAM with EPLA. | [7 empty] | NR services | SQ202403220502-NR Services | NR services | SQ202402210514-NR Services | 2024-03-15 | 2024-03-08 | Completed | 2024-03-11 | 2024-03-15 | 2024-03-08 | 2024-03-08 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-03-07 | 2024-03-15 | 2024-03-07 | 2024-03-07 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-07 | 2024-03-15 | 2024-03-07 | 2024-03-07 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-08 | 2024-03-15 | 2024-03-08 | 2024-03-08 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021309 |  | 2024-02-14 | 2024-02-20 | Completed | 2024-02-13 | 2024-02-14 | 2024-02-13 | 2024-02-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-02 | 2024-03-31 | 2024-03-02 | 2024-03-07 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-03-02 | 2024-03-31 | 2024-03-02 | 2024-03-07 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-02 | 2024-03-31 | 2024-03-02 | 2024-03-09 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2024-03-02 | 2024-03-31 | 2024-03-02 | 2024-03-04 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | tseping//wang/6819000006 | Logistic Team | 2024-11-30 | 2024-12-30 | 2024-11-30 | 2024-11-30 | ASTI//GANIS PUTRIANI/6237001358
1087B-1002A | Jinjang Utara 2 | DU00003441186 | Central | Kuala Lumpur | 3.219550 | 101.656680 | WK08 | FEB 24 | WK08 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+AA+TI | L1+ATP+PAC | 18G 2+0 112Mhz 256QAM 0.6M/0.6M 1556M | MW Parallel Link | MW Parallel Huawei 18G 2+0 112Mhz 1087B-1099A to carry traffic of 1087B BBU only NE: 1) Install new RTN910A (ops team to assign new RTN number) 2) Install new 18G 2+0 112MHz at new RTN 7-ISM8 3) Migrate 1087B BBU only to new link FE: 1) Install new RTN910A (ops team to assign new RTN number) 2) Install new 18G 2+0 112MHz at new RTN 7-ISM8 3) Migrate 1087B BBU only to new link 4) Patch new IDU to new CP port and establish new DCN | [7 empty] | Perwira | SQ202402270787-Perwira | Perwira | SQ202402270744-Perwira | 2024-08-03 | 2024-08-02 | Completed | 2024-02-19 | 2024-02-23 | 2024-02-21 | 2024-02-21 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | PERWIRA ENERGY SDN. BHD. |  | Assigned | Completed |  | 2024-02-21 | 2024-06-30 | 2024-04-20 | 2024-04-20 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | PERWIRA ENERGY SDN. BHD. |  | Assigned | Completed |  | 2024-04-20 | 2024-04-21 | 2024-04-20 | 2024-04-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-08-02 | 2024-08-03 | 2024-08-02 | 2024-08-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021007 |  | 2024-02-28 | 2024-02-29 | Completed | 2024-02-21 | 2024-02-28 | 2024-02-10 | 2024-02-29 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | PERWIRA ENERGY SDN. BHD. |  | Assigned | Completed |  | 2024-02-21 | 2024-02-28 | 2024-02-29 | 2024-02-29 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-02-21 | 2024-02-28 | 2024-02-21 | 2024-02-29 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-02-21 | 2024-02-28 | 2024-03-15 | 2024-03-15 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI |  | 2024-02-21 | 2024-02-28 | 2024-03-09 | 2024-03-09 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-02-21 | 2024-02-28 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-06-30 |  |  | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
3012A-1314C | JLN SRI PERMAISURI 2 | DU00003441187 | Central | Kuala Lumpur | 3.095787 | 101.712853 |  |  | WK05 | JAN 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC |  | MW Remote Upgrade | NE 1- Upgrade link to 1+0_889M_512QAM_112MHz. FE 1- Upgrade link to 1+0_889M_512QAM_112MHz | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358
3352B | Bukit Tinggi (REL) | DU00003441188 | Central | Pahang | 3.360350 | 101.822280 | WK07 | FEB 24 | WK07 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | D1: Cutover done | TSS+TI | L1+ATP+PAC |  | BBU Patching | NE 1) BBU PATCHING AT 3352B/C00639 USING OB FIBER | [7 empty] | Perwira | SQ202402270787-Perwira | Perwira | SQ202402190174-Perwira | 2024-03-16 | 2024-03-25 | Completed | 2024-02-12 | 2024-02-16 | 2024-02-14 | 2024-02-14 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24013163 |  | 2024-02-01 | 2024-02-02 | Completed | 2024-01-31 | 2024-02-01 | 2024-01-31 | 2024-02-02 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-13 | 2024-02-29 | 2024-02-13 | 2024-02-14 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-02-13 | 2024-02-29 | 2024-02-13 | 2024-02-14 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-14 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  |  | 2024-02-13 | 2024-02-29 | 2024-02-13 | 2024-02-16 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-05-24: 2024-02-13; 2024-05-31: 2024-02-29; 2024-06-15: 2024-02-13; 2024-06-15: 2024-02-14 |  |  | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358
2695B-2001B | Taman Bayu Permai | DU00003441189 | Central | Selangor | 3.314789 | 101.533600 | WK09 | MAR 24 | WK09 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112MHZ_0.6/0.6M_256QAM_SUB A&B | MW Swap | MW SWAP MW LINK 2695B-2001B WITH HUAWEI_23G_2+0_112MHZ_0.6/0.6M NE: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC3 SUB BAND A&B 4. CONFIGURE LINK 23G 2+0 112MHZ 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND A&B 4. CONFIGURE LINK 23G 2+0 112MHZ 5. DISMANTLE EXISTING LINK | [7 empty] | Perwira | SQ202407050123-Perwira | Perwira | SQ202402270744-Perwira | 2024-08-04 | 2024-08-03 | Completed | 2024-02-26 | 2024-03-01 | 2024-02-28 | 2024-02-28 | WB80041943 |  | PERWIRA ENERGY SDN. BHD. |  | Unassigned | Completed |  | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-02-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2024-08-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021427 |  | 2024-02-15 | 2024-02-23 | Completed | 2024-02-14 | 2024-02-15 | 2024-02-14 | 2024-02-23 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-23 | 2024-02-29 | 2024-02-23 | 2024-02-29 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-02-23 | 2024-02-29 | 2024-02-23 | 2024-02-26 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-23 | 2024-02-29 | 2024-02-23 | 2024-03-14 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-02-23 | 2024-02-29 | 2024-02-23 | 2024-02-26 | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-01-20 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
3291A-1094A | pBTS Jalan Bukit Kapar ( C ) | DU00003441190 | Central | Selangor | 3.146231 | 101.369492 | WK08 | FEB 24 | WK08 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112MHZ_0.6/0.6M_512QAM_SUB A | MW Swap | MW SWAP MW LINK 3291A-1094A WITH HUAWEI_18G_1+0_112MHZ_0.6/0.6M NE: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK | [7 empty] | Perwira | SQ202402270787-Perwira | Perwira | SQ202402270744-Perwira | 2024-08-04 | 2024-08-03 | Completed | 2024-02-19 | 2024-02-23 | 2024-02-19 | 2024-02-19 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2024-08-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021009 |  | 2024-02-12 | 2024-02-17 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-02-17 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-17 | 2024-02-29 | 2024-02-17 | 2024-02-23 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-02-17 | 2024-02-29 | 2024-02-17 | 2024-02-19 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-22 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-17 | 2024-02-29 | 2024-02-17 | 2024-02-27 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-02-17 | 2024-02-29 | 2024-02-17 | 2024-02-17 | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-01-20 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
3310C-3293A | Desa Alam Seksyen U12 Shah Alam | DU00003451842 | Central | Selangor | 3.079016 | 101.482358 |  |  | WK07 | FEB 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC |  | MW Remote Upgrade | Upgrade 56Mhz to 112Mhz | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-02-17 | 2024-02-17 | 2024-02-17 | 2024-02-17 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 | [17 empty] | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358
4498A-4428D | LAP Tambun 1&2 | DU00003451843 | Northern | Perak | 4.612500 | 101.147500 | WK13 | MAR 24 | WK14 | APR 24 | RFS | Plan WIP | ZTE | 00. Integrated/RFS Done | 27/3: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X RTN 910A 1X 23G 1.2M SP ANTENNA | MW Swap | SWAP EXISTING MW WITH HUAWEI_23G_1+0_112MHZ_0.6M/1.2M_1.41KM 4428D: 1. CHANGE FROM HUAWEI_23G_1+0_56MHZ TO 1+0_112MHZ 4498A: 1. INSTALL NEW RTN 910A 2. SWAP EXISTING 0.6M ANTENNA WITH NEW 23G 1.2M SP ANTENNA 3. SHIFT EXISTING IF CABLE AND CONFIGURATION FROM RTN02 4-ISV3-1 TO NEW RTN 910A 4. CHANGE FROM HUAWEI_23G_1+0_56MHZ TO 1+0_112MHZ 5. PATCH NEW RTN 910A TO NEW CP PORT | [7 empty] | CCSMY | SQ202402260336-CCS | CCSMY | SQ202403190614-CCS | 2024-08-21 | 2024-08-21 | Completed | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  |  | Unassigned | Completed |  | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022849 |  | 2024-02-29 | 2024-03-02 | Completed | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-03-02 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-26 | 2024-03-31 | 2024-03-26 | 2024-05-29 | MUHAMMAD//NOMAN ALI/7021000044 | Datasco TI | 2024-03-26 | 2024-03-31 | 2024-03-26 | 2024-03-29 | MUHAMMAD//NOMAN ALI/7021000044 | Datasco TI | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-26 | 2024-03-31 | 2024-03-26 | 2024-04-01 | MUHAMMAD//NOMAN ALI/7021000044 | 2024-03-26 | 2024-03-31 | 2024-03-26 | 2024-03-26 | 2025-02-03 | 2025-02-03 | 2025-02-03 | 2025-02-03 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
2663B-1054C | Kesas Bdr Puteri Klang | DU00003451844 | Central | Selangor | 2.980753 | 101.479996 |  | MAR 24 | WK10 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112MHZ_0.6/0.6M_512QAM_SUB B | MW Swap | MW SWAP MW LINK 1054C-2663B WITH HUAWEI_18G_1+0_112MHZ_0.6/0.6M NE: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK | [7 empty] | Allstar | SQ202403120253-Allstar | Allstar | SQ202403120466-Allstar // SQ202510070055-Allstar | 2024-04-26 | 2024-04-29 | Completed | 2024-03-05 | 2024-03-31 | 2024-03-08 | 2024-03-08 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-12 | 2024-03-12 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-04-17 | 2024-04-18 | 2024-04-17 | 2024-04-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2024-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24022903 |  | 2024-03-01 | 2024-03-01 | Completed | 2024-02-29 | 2024-03-01 | 2024-02-29 | 2024-03-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-04-19 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 | Allstar TI | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-09 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 | Allstar TI | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-03-09 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-16 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-15 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7475A-7156B | Taman Seri Indah (REL) | DU00003451845 | Sabah | Sabah | 6.054390 | 116.147670 | WK08 | FEB 24 | WK17 | APR 24 | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | 18/4: D2: Cutover done 17/4: D1: TI done, pending alignment & cutover | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_MS_2+0_112MHz | MW Swap | NE 1. Reuse Existing RTN910A (RTN01) 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Swap Existing Huawei ODU with new XMC 3 23GHz 2+0 112MHz ODU (Sub A + Sub B) 4. Swap Existing Huawei Antenna with New Huawei 23GHz 0.6m DP MS Antenna 5. Configure link as 23GHz 2+0 112MHz FE 1. Reuse Existing RTN910A (RTN02) 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Swap Existing Huawei ODU with new XMC 3 23GHz 2+0 112MHz ODU (Sub A + Sub B) 4. Swap Existing Huawei Antenna with New Huawei 23GHz 0.6m DP MS Antenna 5. Configure link as 23GHz 2+0 112MHz | [7 empty] | Seri Pancar | SQ202409030650-Seri Pancar // SQ202409120134-Seri Pancar | GTSB | SQ202409120182-GTSB | 2024-02-29 | 2024-02-29 | Completed | 2024-02-22 | 2024-02-23 | 2024-02-22 | 2024-02-22 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-25 | 2024-02-29 | 2024-02-25 | 2024-02-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-25 | 2024-02-29 | 2024-02-25 | 2024-02-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240405C2 |  | 2024-04-06 | 2024-04-15 | Completed | 2024-04-05 | 2024-04-06 | 2024-04-05 | 2024-04-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-19 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-19 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-04-18 | 2024-04-18 | 2024-04-19 | 2024-04-19 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-20 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
2436A-1893B | Bukit Beruntung (CELCOM) | DU00003451846 | Central | Selangor | 3.433820 | 101.576520 |  |  | WK16 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 30/4: D1: Cutover done 22/4: EB CRQ approved, CR date 30/4 | TSS+TI | L1+ATP+PAC |  | MW Re-engineering | Pathcing BBU at 1893B to Celcom Cisco Router B01947 | [7 empty] | MTK | SQ202409100243-MTK | MTK | SQ202409110359-MTK | 2024-07-31 | 2024-07-30 | Completed | 2024-04-30 | 2024-05-06 | 2024-05-06 | 2024-05-06 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. |  | Unassigned | Completed |  | 2024-05-08 | 2024-05-09 | 2024-05-08 | 2024-05-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24040207 |  | 2024-04-03 | 2024-04-03 | Completed | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-29 | 2024-04-30 | 2024-04-29 | 2024-05-02 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-04-29 | 2024-05-08 | 2024-04-29 | 2024-05-08 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  |  | 2024-04-29 | 2024-04-30 | 2024-04-29 | 2024-04-30 | RIDHUAN//BIN MANSOR/8225000011 | 2024-05-24: 2024-04-29; 2024-05-31: 2024-04-30; 2024-06-15: 2024-04-29; 2024-06-15: 2024-04-30 |  |  | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358
4366D-4522B | Gugusan Manjoi | DU00003451847 | Northern | Perak | 4.621100 | 101.063025 |  | MAR 24 | WK10 | MAR 24 | RFS | Pending compliance | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1+0 XMC3 ODU 23G SubA (for support 112Mhz Upgrade) | MW Hardware Upgrade | Swap existing 1+0 ODU with new 1+0 23G ODU XMC3 Sub A for 112Mhz Upg | [7 empty] | GCI | SQ202403110198-GCI | GCI | SQ202409100506-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022853 |  | 2024-02-29 | 2024-03-06 | Completed | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-03-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-17 | team7gcitechnicalteam7gcitechnical | GCI TI | 2024-03-07 | 2024-09-30 | 2024-03-07 | 2024-09-23 | team7gcitechnicalteam7gcitechnical | GCI TI | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-03-09 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-05-21 | team7gcitechnicalteam7gcitechnical | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-07 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2024-11-01 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
1921B-1640B | Jugra Banting(Smart) | DU00003451848 | Central | Selangor | 2.815263 | 101.449552 | WK10 | MAR 24 | WK14 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 16/4: D1: Cutover done 3/4: TM WP approved | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112MHZ_0.6/0.6M_512QAM_Sub A | MW Swap | MW SWAP MW LINK 1640B-1921B WITH HUAWEI_18G_1+0_112MHZ_0.6/0.6M NE: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK | [7 empty] | Allstar | SQ202403120253-Allstar | Allstar | SQ202403120466-Allstar // SQ202510070055-Allstar | 2024-05-28 | 2024-05-27 | Completed | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-06 | 2024-03-06 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-27 | 2024-05-28 | 2024-05-27 | 2024-05-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24022904 |  | 2024-03-01 | 2024-03-01 | Completed | 2024-02-29 | 2024-03-01 | 2024-02-29 | 2024-03-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-15 | 2024-04-30 | 2024-04-15 | 2024-04-18 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | Allstar TI | 2024-04-15 | 2024-04-30 | 2024-04-15 | 2024-04-30 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | Allstar TI | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | C.PRATHABAN///6798000081 |  | 2024-05-28 | 2024-04-15 | 2024-04-30 | 2024-04-15 | 2024-05-09 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | 2024-04-15 | 2024-04-30 | 2024-04-15 | 2024-04-15 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-23 | NG HONG JIE7018000036 | Logistic Team | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358
1786A-1087A | Kop. Kopema Bhdh | DU00003451849 | Central | Selangor | 3.013700 | 101.387150 | WK11 | MAR 24 | WK11 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28MHZ_0.6M/1.2M_MDD_256QAM_SUB B | MW Swap | MW SWAP MW LINK 1786A-1087A HW (1786A RTN03-1087A RTN06) WITH HUAWEI_15G_4+0_28MHZ_0.6M/1.2M_MDD_256QAM_SUB B NE: 1. REUSE EXISTING IDU RTN910A 2. INSTALL NEW 2PCS ISM8 AT EXISTING RTN03 SLOT 3 & 4 3. INSTALL NEW 15G 0.6M MDD ANTENNA 4. INSTALL NEW 15G XMC-5D SUB BAND B 5. CONFIGURE LINK 15G 4+0 28MHZ 256QAM WITH CA 6. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 WITH 2PCS NEW ISM8 AT SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | Perwira | SQ202403180282-Perwira | Perwira | SQ202403120476-Perwira | 2024-08-03 | 2024-08-02 | Completed | 2024-03-11 | 2024-03-11 | 2024-03-12 | 2024-03-12 | WB80041943 |  | PERWIRA ENERGY SDN. BHD. |  | Unassigned | Completed |  | 2024-07-05 | 2024-07-06 | 2024-07-05 | 2024-07-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-05 | 2024-07-06 | 2024-07-05 | 2024-07-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-02 | 2024-08-03 | 2024-08-02 | 2024-08-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240301BI |  | 2024-03-02 | 2024-03-05 | Completed | 2024-03-01 | 2024-03-02 | 2024-03-01 | 2024-03-05 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-11 | 2024-03-31 | 2024-03-11 | 2024-03-14 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-11 | 2024-03-31 | 2024-03-11 | 2024-03-23 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | C.PRATHABAN///6798000081 |  |  | 2024-03-11 | 2024-03-31 | 2024-03-11 | 2024-03-27 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-05-24: 2024-03-11; 2024-05-31: 2024-03-31; 2024-06-15: 2024-03-11; 2024-06-15: 2024-03-14 |  |  | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7649B-7628A | Seafest Hotel | DU00003451850 | Sabah | Sabah | 4.478526 | 118.617523 | WK17 | APR 24 | WK21 | JUN 24 | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | 4/6: D4: Cutover done, Post-cutover TS WIP 29/5: D4: Continue TI - raining 22/5: D2: TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/1.2m_MDD_2+0_110MHz | MW Swap | MW SWAP 7649B-7628A _18GHz_0.6m/1.2m_MDD_2+0_110MHz NE: 1. Reuse existing IDU RTN 05 and existing ISM 8 at Slot 7. 2. SWAP existing ODU with XMC-5D Sub B _112Mhz. 3.Swap existing Antenna with 0.6m MDD. 4. Configure 18G_2+0_110Mhz. FE: 1. Reuse existing IDU RTN 05 and existing ISM 8 at Slot 7. 2. SWAP existing ODU with XMC-5D Sub B _112Mhz. 3.Swap existing Antenna with 1.2m MDD. 4. Configure 18G_2+0_110Mhz. | [7 empty] | GTSB | SQ202403220495-GTSB | GTSB | SQ202409120182-GTSB | 2024-02-29 | 2024-02-29 | Completed | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | PAVITRAN AL CHINNAKOLANDAY6799000150 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-02-28 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-02-28 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2024-05-21 | 2024-05-31 | 2024-05-21 | 2024-06-03 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-05-21 | 2024-05-31 | 2024-05-21 | 2024-06-03 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-06-04 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-05-21 | 2024-05-31 | 2024-05-21 | 2024-06-05 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | 2024-05-21 | 2024-05-31 | 2024-05-21 | 2024-05-21 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
3294B-2662B | Jln Sungai Batu | DU00003451851 | Central | Selangor | 3.088801 | 101.414605 |  | MAR 24 | WK10 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI | L1+ATP+PAC | 15G 4+0 28MHZ 0.6M/1.2M_512QAM SUB A | MW Hardware Upgrade | HARDWARE UPGRADE FROM 15G 2+0 28MHZ TO 15G 4+0 28MHZ 0.6M/1.2M_512QAM SUB A 3294B-2662B NE: 1. INSTALL NEW 2PCS ISM8 SLOT 3 AND SLOT 4 2. INSTALL 2PCS IF CABLE ON EXISTING ODU 15G XMC-5D 28MHZ SUB A 3. REUSE EXISTING 15G 0.6M MDD ANTENNA 4. SHIFT CABLE FROM SLOT 7 TO NEW ISM8 CARD SLOT 3 5. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA FE: 1. INSTALL NEW 2PCS ISM8 SLOT 3 AND SLOT 4 2. INSTALL 2PCS IF CABLE ON EXISTING ODU 15G XMC-5D 28MHZ SUB A 3. REUSE EXISTING 15G 1.2M MDD ANTENNA 4. SHIFT CABLE FROM SLOT 7 TO NEW ISM8 CARD SLOT 3 5. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 6. REPATCH TO EXISTING CP PORT | [7 empty] | Perwira | SQ202407050123-Perwira | Perwira | SQ202403120476-Perwira | 2024-08-04 | 2024-08-03 | Completed | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | WB80041943 |  | PERWIRA ENERGY SDN. BHD. |  | Unassigned | Completed |  | 2024-07-12 | 2024-07-13 | 2024-07-12 | 2024-07-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-12 | 2024-07-13 | 2024-07-12 | 2024-07-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2024-08-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240301BG |  | 2024-03-02 | 2024-03-05 | Completed | 2024-03-01 | 2024-03-02 | 2024-03-01 | 2024-03-05 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-07 | 2024-03-31 | 2024-03-07 | 2024-03-08 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-07 | 2024-03-31 | 2024-03-07 | 2024-03-17 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-07 | 2024-03-31 | 2024-03-07 | 2024-03-21 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-05-24: 2024-03-07; 2024-05-31: 2024-03-31; 2024-06-15: 2024-03-07; 2024-06-15: 2024-03-08 |  |  | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
2443A-1156A | Ijok (CELCOM) | DU00003451852 | Central | Selangor | 3.296836 | 101.447680 |  | AUG 24 | WK32-WK35 | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 4/9: D4: Cutover done. Pending declare due child site link issue (NMS issue) 23/8: D2: TI NE done, Pending EB CRQ approval FE. Plan CRQ 3/9 - 4/9 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28MHZ_1.8M/1.2M_256QAM_SUB B | MW Swap | MW SWAP MW LINK 2443A-1156A SM MW3 WITH HUAWEI_13G_4+0_28MHZ_1.8M/1.2M_256QAM_SUB B IMPACTED: 2675B, 1584C, 3685C THIS IS HAVE EB CONNECTED TO CP 1180E-1156A AND 1115E-3583B-1156A NE: 1. INSTALL NEW IDU RTN910 2. INSTALL 2 UNIT ISM8 CARD AT NEW IDU SLOT 3&4 3. INSTALL NEW 13G 1.8M MDD ANTENNA 4. INSTALL NEW 13G XMC-5D SUB BAND B 5. CONFIGURE LINK 13G 4+0 28MHZ WITH CA SLOT 3 & 4 6. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL 2 UNIT ISM8 CARD AT NEW IDU SLOT 3&4 3. INSTALL NEW 13G 1.2M MDD ANTENNA 4. INSTALL NEW 13G XMC-5D SUB BAND B 5. CONFIGURE LINK 13G 4+0 28MHZ WITH CA SLOT 3 & 4 6. PATCH IDU TO NEW CP PORT 7. DISMANTLE EXISTING LINK | [7 empty] | MTK | SQ202409210230-MTK | MTK | SQ202408220979-MTK // SQ202411040623-MTK | 2024-11-07 | 2024-11-06 | Completed | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-17 | 2024-10-18 | 2024-10-17 | 2024-10-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-17 | 2024-10-18 | 2024-10-17 | 2024-10-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-06 | 2024-11-07 | 2024-11-06 | 2024-11-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240730AH |  | 2024-07-31 | 2024-08-07 | Completed | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-08-07 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-22 | 2024-08-31 | 2024-08-21 | 2024-08-26 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-09-02 | 2024-10-17 | 2024-09-02 | 2024-10-17 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-09-09 | 2024-09-09 | 2024-10-17 | 2024-10-17 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-09-02 | 2024-09-30 | 2024-09-02 | 2024-10-15 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-08-22 | 2024-08-31 | 2024-08-21 | 2024-08-24 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 | NG HONG JIE7018000036 | Logistic Team | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
1415A-1413A | Midas Industries | DU00003451853 | Central | Selangor | 3.302896 | 101.578089 | WK16 | APR 24 | WK32-WK35 | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 29/8: Cutover done 2/8: D3: TI done. Pending CO. Access limited 20/6: Subcon req CR for approval (manual carry) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112MHZ_1.2M/1.2M_DP_256QAM_SUB A & B | MW Swap | TX MINI PROJECT 1415A-1413A MW SWAP MW LINK 1415A-1413A HW (1415A RTN01-1413A RTN02) WITH HUAWEI_23G_2+0_112MHZ_1.2M/1.2M_DP_256QAM_SUB A & B NE: 1. INSTALL NEW RTN910A 2. INSTALL NEW 23G 1.2M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW RTN910A 2. INSTALL NEW 23G 1.2M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202409260091-MTK | 2024-10-12 | 2024-10-11 | Completed | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-13 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2024-09-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-30 | 2024-10-01 | 2024-09-30 | 2024-09-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-11 | 2024-10-12 | 2024-10-11 | 2024-10-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24031863 |  | 2024-03-19 | 2024-03-18 | Completed | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-08-05 | 2024-10-08 | 2024-08-05 | 2024-10-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-08-05 | 2024-08-31 | 2024-08-05 | 2024-08-23 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-08-05 | 2024-08-31 | 2024-08-05 | 2024-09-02 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-08-05 | 2024-08-31 | 2024-08-05 | 2024-08-12 | 2024-11-05 | 2024-11-05 | 2024-11-05 | 2024-11-05 | NG HONG JIE7018000036 | Logistic Team | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
3650A-1349A | pBTS Persiaran Sabak Bernam (KM) | DU00003451854 | Central | Selangor | 3.030750 | 101.555740 | WK09 | FEB 24 | WK14 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 17/4: Cutover done 16/4: D1: TI In plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_110MHZ_0.6M/0.6M_512QAM_SUB A | MW Swap | MW SWAP MW LINK 3650A1-1349A SM MW1 WITH HUAWEI_18G_1+0_110MHZ_0.6M/0.6M_512QAM_SUB A NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 1+0 28MHZ 512QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4. CONFIGURE LINK 18G 1+0 28MHZ 512QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | Allstar | SQ202403040099-Allstar | Allstar | SQ202403120466-Allstar // SQ202510070055-Allstar | 2024-05-10 | 2024-05-06 | Completed | 2024-02-26 | 2024-03-01 | 2024-02-26 | 2024-02-26 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-06 | 2024-03-06 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-30 | 2024-05-10 | 2024-04-30 | 2024-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240305BP |  | 2024-03-06 | 2024-03-18 | Completed | 2024-03-05 | 2024-03-06 | 2024-03-05 | 2024-03-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-04-18 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | Allstar TI | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-04-30 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | Allstar TI | 2024-04-17 | 2024-04-17 | 2024-04-17 | 2024-04-17 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-05-13 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-04-17 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | NG HONG JIE7018000036 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
4292C-4241A | Juru Tol | DU00003451855 | Northern | Penang | 5.324604 | 100.435375 | WK07 | FEB 24 |  | JUN 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done | 6/11: Change new LAN cable & re-setting IPRAN port setting done WK37: Link require rectification_4292C-4241A-01_ZNIC_Port capped 100Mbps at FE/CP site 4241A 10/7: D3: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Swap | SWAP 4292C-4241A WITH HUAWEI_18GHZ_1+0_112MHZ_0.6M_1.02KM. IMPACTED SITES: 4292C NE: AT 4292C: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. PATCH 4292C BBU TO NEW RTN 910A 6. DISMANTLE EXISTING LINK FE: AT 4241A: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. PATCH NEW RTN 910A TO NEW CP PORT 6. DISMANTLE EXISTING LINK EXCEPT IDU | [7 empty] | CCSMY | SQ202402220007-CCS | CCSMY | SQ202409120138-CCS | 2024-11-26 | 2024-11-26 | Completed | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  |  | Unassigned | Completed |  | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240619AD |  | 2024-06-20 | 2024-06-26 | Completed | 2024-06-19 | 2024-06-20 | 2024-06-19 | 2024-06-26 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-07-10 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-07-10 | MUHAMMAD//MUZAMMAL/7021000054 | CCS TI | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2024-07-10 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-08-20 | MUHAMMAD//MUZAMMAL/7021000054 | 2024-07-09 | 2024-07-28 | 2024-07-09 | 2024-07-10 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
1892B-1413A | NS HW KM435(Maxis) | DU00003451856 | Central | Selangor | 3.380000 | 101.559833 |  | MAR 24 | WK32-WK35 | AUG 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 2/8: D2: Cutover done. Post-CO T/shooting WIP 31/7: MOS & Pre-installation WIP 20/6: Subcon req CR for approval (manual carry) | TSS+AA+TI | L1+ATP+PAC | 15G 4+0 28MHz 896Mbps | MW Parallel Link | NE: Install: 1. Antenna: Install new 15G 1.2m DP A15D12MAC-3NX x 2 2. ODU: Install XMC-3 Sub-band B x 2 3. IDU: Install new RTN910A x 1, named RTN02 4. IF card: Install new ISM8 x 2 at Slot 3 and Slot 4 5. IF cables: a) Connect IF cable x 2 from the new ODUs to Slot 3 and Slot 7 b) Disconnect IF cables from RTN04 Slot 3-1,3-2 and re-connct to new RTN02 Slot 4-1,4-2 6. Configure new link 1892B RTN02-1413A RTN11 15G 4+0 ePLA 28MHz 890Mbps 7. Configure: Link 1892B RTN02-1413A RTN11 15G 4+0 ePLA 28MHz 8. Disconnect BBU 1892B and connect to RTN02 GE1. 9. Re-route 2007B BBU into this new link in order to offload the existing link Dismantle/ Remain: 1. Remain old Huawei link (still using) FE: Install: 1. Antenna: Install new 15G 1.2m DP A15D12MCA-3NX x 2 2. ODU: Install XMC-3 Sub-band B x 2 3. IDU: Install new RTN910A x 1, named RTN11 and patch to CP router new port 4. IF card: Install new ISM8 x 2 at Slot 3,4 5. IF cables: Connect IF cable x 2 from the new ODUs to Slot 3 and Slot 7 6. Configure: Link 1892B RTN02-1413A RTN11 15G 4+0 ePLA 28MHz 7. DCN IP and VLAN: Configure for 1413A RTN11 Dismantle/ Remain: 1. Remain old Huawei link (still using) | [7 empty] | MTK | SQ202408220896-MTK | MTK | SQ202409270135-MTK | 2025-02-25 | 2025-02-24 | Completed | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-13 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-21 | 2024-11-22 | 2024-11-21 | 2024-11-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-13 | 2025-02-14 | 2025-02-13 | 2025-02-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-24 | 2025-02-25 | 2025-02-24 | 2025-02-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24031283 |  | 2024-03-13 | 2024-03-18 | Completed | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-09-06 | 2024-09-30 | 2024-09-06 | 2024-09-19 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-09-06 | 2024-09-30 | 2024-09-06 | 2024-09-19 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-08-02 | 2024-08-09 | 2024-08-02 | 2024-08-02 | SHUJAAT//ALI/6800000124 |  |  | 2024-09-06 | 2024-09-30 | 2024-09-06 | 2024-09-23 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-05-24: 2024-09-06; 2024-05-31: 2024-09-30; 2024-06-15: 2024-09-06; 2024-06-15: 2024-09-11 |  |  | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
4620D-4086A | Balai Bomba Jalan Perak Penang (REL) | DU00003451857 | Northern | Penang | 5.401825 | 100.315681 | WK08 |  | WK09 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW Hardware Upgrade | HARDWARE UPGRADE FOR MW 4620D-4086A: ADD NEW IDU WITH AT FE. CHANGE FROM HUAWEI_18G_1+0_56MHZ TO 1+0_112MHZ. NE: 1. CHANGE FROM HUAWEI_18G_1+0_56MHZ TO 1+0_112MHZ FE: 1. INSTALL NEW RTN 910A 2. SHIFT IF CABLE & CONFIGURATION FROM RTN01 7-ISM6-1 TO NEW RTN 910A 3. CHANGE FROM HUAWEI_18G_1+0_56MHZ TO 1+0_112MHZ 4. REUSE EXISTING CP PORT | [7 empty] | CCSMY | SQ202411140303-CCS | CCSMY | SQ202402260340-CCS // SQ202411120061-CCS | 2025-12-10 | 2025-12-10 | Completed | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-12-12 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022385 |  | 2024-02-24 | 2024-02-28 | Completed | 2024-02-23 | 2024-02-24 | 2024-02-23 | 2024-02-28 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-01 | 2024-03-08 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2024-03-01 | 2024-03-31 | 2024-03-01 | 2024-03-01 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-01 | 2024-03-31 | 2024-03-01 | 2024-03-05 | Arif//Afif Bin Mohd Zabidi/7021000041 | 2024-05-24: 2024-03-01; 2024-05-31: 2024-03-31; 2024-06-15: 2024-03-01; 2024-06-15: 2024-03-01 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202507250560-GCI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
9980A-9484A | Kampung Tanjung Kuching | DU00003451858 | Sarawak | Sarawak | 1.564295 | 110.341859 | WK11 | MAR 24 | WK12 | MAR 24 | RFS | TI WIP | ZTE | 00. Integrated/RFS Done | D2: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_SP_1+0_112MHz | MW Hardware Upgrade | NE 1. Reuse Existing RTN910A 2. Install New 1 pcs of ISM 8 Card at Slot 3 2. Swap Existing ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 3. Configure link as 23GHz 1+0 112MHz FE 1. Reuse Existing RTN910A 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Swap Existing ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 4. Configure link as 23GHz 1+0 112MHz | [7 empty] | Trintel | SQ202403220491-Trintel | Trintel | SQ202403220513-Trintel // SQ202404180449-Trintel | 2024-04-19 | 2024-04-17 | Completed | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2024-03-12 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-14 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-14 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-17 | 2024-04-19 | 2024-04-17 | 2024-04-17 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24031163 |  | 2024-02-21 | 2024-03-15 | Completed | 2024-02-20 | 2024-02-21 | 2024-02-20 | 2024-03-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-15 | 2024-03-31 | 2024-03-15 | 2024-03-19 | SITI//NURASHIKIN FARAHAIN BINTI MOHAMAD DAUD/7667000041 | Trintel TI | 2024-03-15 | 2024-03-31 | 2024-03-15 | 2024-03-19 | SITI//NURASHIKIN FARAHAIN BINTI MOHAMAD DAUD/7667000041 | Trintel TI | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-15 | 2024-03-31 | 2024-03-15 | 2024-03-27 | SITI//NURASHIKIN FARAHAIN BINTI MOHAMAD DAUD/7667000041 | 2024-03-15 | 2024-03-31 | 2024-03-15 | 2024-03-19 | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-11-28 | 2024-12-28 | 2024-11-28 | 2024-11-28 | ASTI//GANIS PUTRIANI/6237001358
3090B-1781B | Pinggiran Batu Caves (REL) | DU00003451859 | Central | Selangor | 3.253452 | 101.694483 |  | MAR 24 | WK10 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 0.6m/0.6m 23G 1+0 112MHz 890Mbps | MW Swap | NE: 1. Antenna: Install new 0.6 SP MAC model x 1 2. ODU: Install XMC-3 112MHz Sub-band A x 1 3. IDU: Install new RTN910A x 1, named RTN01 4. IF card: Built-in Slot 7 5. Configure 23G 1+0 112MHz 890Mbps 6. BBU re-patch to this new RTN01 7. Decom old SIAE link FE: 1. Antenna: Install new 0.6 SP MAC model x 1 2. ODU: Install XMC-3 112MHz Sub-band A x 1 3. IDU: Install new RTN910A x 1, named RTN01 and patch to CP router port 4. IF card: Built-in Slot 7 5. Configure 23G 1+0 112MHz 890Mbps 6. Decom old SIAE link | [7 empty] | Allstar | SQ202403180278-Allstar | Allstar | SQ202403180799-Allstar // SQ202510070055-Allstar | 2024-04-27 | 2024-04-29 | Completed | 2024-03-01 | 2024-03-31 | 2024-03-06 | 2024-03-06 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-13 | 2024-03-13 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-04-17 | 2024-04-18 | 2024-04-17 | 2024-04-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24022905 |  | 2024-03-01 | 2024-03-01 | Completed | 2024-02-29 | 2024-03-01 | 2024-02-29 | 2024-03-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-05-08 | ALI//HAMZA/6798000192 | Allstar TI | 2024-03-08 | 2024-06-30 | 2024-03-08 | 2024-03-09 | ALI//HAMZA/6798000192 | Allstar TI | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-03-09 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-27 | ALI//HAMZA/6798000192 | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-22 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
K00376-4678A | KOTA SETAR | DU00003451860 | Northern | Perak | 6.144600 | 100.409100 |  |  | WK07 | FEB 24 | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC |  | MW Remote Upgrade | REMOTE UPGRADE FOR MW K00376-4678A: CHANGE FROM HUAWEI_18G_1+0_56MHZ TO 1+0_112MHZ | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-02-17 | 2024-02-17 | 2024-02-17 | 2024-02-17 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
4559D-4039A | Sri Saujana Macallum | DU00003451861 | Northern | Penang | 5.408275 | 100.334200 |  |  | WK07 | FEB 24 | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC |  | MW Remote Upgrade | REMOTE UPGRADE FOR MW 4559D-4039A: CHANGE FROM HUAWEI_23G_1+0_56MHZ TO 1+0_112MHZ | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-02-17 | 2024-02-17 | 2024-02-17 | 2024-02-17 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
1424A-1412A | Maxis Tower Batu Arang | DU00003451862 | Central | Selangor | 3.315091 | 101.468469 |  |  | WK14 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 29/4: D4: Cutover done 22/4: Team issue - team support NES Digi Project 19/4: D3: TI done, Pending alignment & cutover 16/4: D1: MOS & TI In plan | TSS+AA+TI | L1+ATP+PAC | 13G 4+0 28MHz 840Mbps | MW Parallel Link | NE: Install: 1. Antenna: Install new 13G 1.2m DP A13D12MAC-3NX x 2 2. ODU: Install XMC-3 Sub-band A x 2; XMC-3 Sub-band B x 2 3. IDU: Install new RTN910A x 1, named RTN03 4. IF card: Install new ISM8 x 1 at Slot 3 5. IF cable: Connect new IF cable x 4 from the new ODUs to Slot 7-1, 7-2, 3-1, 3-2 6. Configure: Link 1424A RTN03->1412A RTN09 4+0 ePLA 28MHz 840Mbps 7. Disconnect BBU 1424A and connect to RTN03 GE1 8. Configure routing 1424A BBU into this new link in order to offload the existing link Dismantle/ Remain: 1. Remain old Huawei link as parallel link FE: Install: 1. Antenna: Install new 13G 1.2m DP A13D12MAC-3NX x 2 2. ODU: Install XMC-3 Sub-band A x 2; XMC-3 Sub-band B x 2 3. IDU: Install new RTN910A x 1, named RTN09 and patch to CP router new port 4. IF card: Install new ISM8 x 1 at Slot 3 5. IF cable: Connect new IF cable x 4 from the new ODUs to Slot 7-1, 7-2, 3-1, 3-2 6. Configure: Link 1424A RTN03->1412A RTN09 4+0 ePLA 28MHz 840Mbps 7. DCN IP and VLAN: Configure for 1412A RTN09 Dismantle/ Remain: 1. Remain old Huawei link as parallel link | [7 empty] | Perwira | SQ202407050123-Perwira | Perwira | SQ202407050175-Perwira | 2024-09-20 | 2024-09-18 | Completed | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | SAMANTHA LOOI SHU-YI6237001479 |  |  |  | Unassigned | Completed |  | 2024-08-02 | 2024-08-03 | 2024-08-02 | 2024-08-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-02 | 2024-08-03 | 2024-08-02 | 2024-08-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24040213 |  | 2024-04-03 | 2024-04-03 | Completed | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-05-02 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-04-30 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-04-29 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-05-18 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-05-24: 2024-04-16; 2024-05-31: 2024-04-30; 2024-06-15: 2024-04-16; 2024-06-15: 2024-04-20 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
4591A-4475A | Kg.Tebok Pulai | DU00003451863 | Central | Selangor | 3.725100 | 100.972370 |  | MAR 24 | WK14 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 3/9: SOW not completed (EPLA not created as 4+0) 2/4: D3: Cutover done 26/3: TI done, pending config 4+0_CA - need add 1 pcs ISM8 card | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 2X 15G 1.2M MDD ANTENNA 1X 15G XMC-5D SUB B HI 1X 15G XMC-5D SUB B LO | MW Parallel Link | ADD MW PARALLEL LINK 4591A-4475A WITH HUAWEI_15GHZ_2+0_28MHZ_1.2M_4.58KM EXISTING MW CFG: 15GHZ_2+0_28MHZ. IMPACTED SITES: 4591A 4591A: 1. INSTALL NEW ISM8 CARD AT EXISTING RTN01 SLOT 3 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 5. EPLAN EXISTING 15G 2+0 WITH NEW 15G 2+0 4475A: 1. INSTALL NEW ISM8 CARD AT EXISTING RTN02 SLOT 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 5. EPLAN EXISTING 15G 2+0 WITH NEW 15G 2+0 | [7 empty] | Ascentrack | SQ202409100315-Ascentrack | Ascentrack | SQ202403120472-Ascentrack // SQ202409100362-Ascentrack | 2025-01-22 | 2025-01-21 | Completed | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Nor//Syamsyairi Bin Hashim/7539000044 |  | ASCENTRACK SDN. BHD. |  | Unassigned | Completed |  | 2024-04-01 | 2024-04-02 | 2024-04-01 | 2024-04-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-01 | 2024-04-02 | 2024-04-01 | 2024-04-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2025-01-21 | 2025-01-22 | 2025-01-21 | 2025-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240301BJ |  | 2024-03-02 | 2024-03-07 | Completed | 2024-03-01 | 2024-03-02 | 2024-03-01 | 2024-03-07 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-14 | 2024-03-24 | 2024-03-14 | 2024-04-18 | LOW//CHUN WAI/7539000013 | Ascentrack TI | 2024-03-14 | 2024-06-30 | 2024-03-14 | 2024-05-09 | LOW//CHUN WAI/7539000013 | Ascentrack TI | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-14 | 2024-03-24 | 2024-03-14 | 2024-04-09 | LOW//CHUN WAI/7539000013 | 2024-05-24: 2024-03-14; 2024-05-31: 2024-03-24; 2024-06-15: 2024-03-14; 2024-06-15: 2024-03-20 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
2641B-1073A | Desa Alam | DU00003451864 | Central | Selangor | 3.088384 | 101.486711 | WK19 | MAY 24 | WK19 | MAY 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 2/5: D5: Cutover done 30/4: D4: TI done, pending alignment & cutover (raining) 29/4: D3: TI FE done, Pending NE (raining). Continue 30/4 26/4: D2: TI WIP. Got extra MODU XMC5D 2 pcs to return back. Request DR. Continue 29/4 | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_0.6M/1.2M_MDD_28MHZ_512QAM_SUB B] to [15G_4+0_0.6M/1.2M_MDD_28MHZ_512QAM_SUB A] | MW Parallel Link | MW PARALLEL LINK 2641B-1073A 15G_4+0_0.6M/1.2M_MDD_28MHZ_512QAM SUB B TO CARRY TRAFFIC OF 2461B BBU AND CHILD 1524C IMPACTED SITE: 1524C, 26411B NE: 1) INSTALL 2PCS ISM8 AT SLOT 3 & 4 AT EXISTING IDU RTN01 2) INSTALL NEW 15G 4+0 28MHZ AT EXISTING RTN01 3-ISM8 AND 4-ISM8 WITH CA 3) INSTALL NEW ANTENNA 15G 0.6M AND ODU SUBBAND B 4) MIGRATE 2641B BBU AND CHILD 1524C TO NEW LINK FE: 1) INSTALL NEW RTN910A (OPS TEAM TO ASSIGN NEW RTN NUMBER) 2) INSTALL NEW 15G 4+0 28MHZ AT NEW RTN 3-ISM8 AND 4-ISM8 WITH CA 3) INSTALL NEW ANTENNA 15G 1.2M AND ODU SUBBAND B 4) MIGRATE 2641B BBU AND CHILD 1524C TO NEW LINK 5) PATCH NEW IDU TO NEW CP PORT AND ESTABLISH NEW DCN. | [7 empty] | Allstar | SQ202407050105-Allstar | Allstar | SQ202411120057-Allstar | 2024-05-31 | 2024-05-27 | Completed | 2024-04-01 | 2024-04-30 | 2024-04-16 | 2024-04-16 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-05-01 | 2024-05-31 | 2024-05-08 | 2024-05-08 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-27 | 2024-05-28 | 2024-05-27 | 2024-05-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24032002 |  | 2024-03-21 | 2024-03-25 | Completed | 2024-03-20 | 2024-03-21 | 2024-03-20 | 2024-03-25 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-18 | 2024-04-30 | 2024-04-18 | 2024-11-19 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | Allstar TI | 2024-04-18 | 2024-09-30 | 2024-04-18 | 2024-09-23 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | Allstar TI | 2024-06-21 | 2024-06-21 | 2024-06-21 | 2024-06-21 | C.PRATHABAN///6798000081 |  |  | 2024-04-18 | 2024-04-30 | 2024-04-18 | 2024-07-01 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | 2024-05-24: 2024-04-18; 2024-05-31: 2024-04-30; 2024-06-15: 2024-04-18; 2024-06-15: 2024-04-26 |  |  | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
4939C-4320C | Wisma Ganda RT | DU00003451865 | Northern | Perak | 4.215874 | 100.695958 | WK07 | FEB 24 |  | JUL 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done | 26/7: D3: Cutover done. Post-CO Tshooting WIP 25/7: MOS & TI In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 23G 0.6M SP ANTENNA 1X 23G 112MHZ XMC-3 SUB B HI 1X 23G 112MHZ XMC-3 SUB B LO | MW Swap | SWAP 4320C-4939C WITH HUAWEI_23GHZ_1+0_112MHZ_0.6M_1.1KM. IMPACTED SITES: 4320C NE: AT 4320C: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M SP ANTENNA 3. INSTALL NEW 1+0 23G 112MHZ XMC-3 SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 5. PATCH 4320C BBU TO NEW RTN 910A 6. DISMANTLE EXISTING SM LINK FE: AT 4939C: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M SP ANTENNA 3. INSTALL NEW 1+0 23G 112MHZ XMC-3 SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 5. REUSE EXISTING CP PORT 6. DISMANTLE EXISTING SM LINK | [7 empty] | CCSMY | SQ202402220007-CCS | CCSMY | SQ202408080059-CCS | 2024-11-26 | 2024-11-26 | Completed | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  |  | Unassigned | Completed |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2024-07-25 | 2024-07-31 | 2024-07-24 | 2024-07-26 | HASHIM//BIN AHMAD ZAIDI/7021000032 | CCS TI | 2024-07-25 | 2024-07-31 | 2024-07-24 | 2024-07-26 | HASHIM//BIN AHMAD ZAIDI/7021000032 | CCS TI | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-07-25 | 2024-07-31 | 2024-07-24 | 2024-08-01 | HASHIM//BIN AHMAD ZAIDI/7021000032 | 2024-07-25 | 2024-07-31 | 2024-07-24 | 2024-07-27 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-06 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-09-09 | 2024-10-09 | 2024-09-09 | 2024-09-09 | ASTI//GANIS PUTRIANI/6237001358
3580C-1099A | Persiaran Setia Prima | DU00003451868 | Central | Selangor | 3.091481 | 101.455155 | WK16 | APR 24 | WK13 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 26/4: Cutover done 22/4:Hazard resolved. Cutover plan 25/4 17/4: D2: Stop work due hazard at FE 1099A (power leakage) 16/4: D1: TI done, pending alignment | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112MHZ_0.6/0.6M_512QAM Sub B | MW Swap | MW SWAP MW LINK 3580C-1099A WITH HUAWEI_18G_1+0_112MHZ_0.6/0.6M NE: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK | [7 empty] | Allstar | SQ202403120253-Allstar | Allstar | SQ202403120466-Allstar // SQ202510070055-Allstar | 2024-09-06 | 2024-09-05 | Completed | 2024-03-01 | 2024-03-06 | 2024-03-05 | 2024-03-05 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-19 | 2024-03-19 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-09-05 | 2024-09-06 | 2024-09-05 | 2024-09-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022907 |  | 2024-03-01 | 2024-03-01 | Completed | 2024-02-29 | 2024-03-01 | 2024-02-29 | 2024-03-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-04-19 | RAHMAD//HIDAYAT BIN LAMRI/6798000206 | Allstar TI | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-04-30 | RAHMAD//HIDAYAT BIN LAMRI/6798000206 | Allstar TI | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-05-24 | RAHMAD//HIDAYAT BIN LAMRI/6798000206 | 2024-04-16 | 2024-04-30 | 2024-04-16 | 2024-04-17 | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | NG HONG JIE7018000036 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
4465A-4178D | Taman Long Jaafar RDD | DU00003451869 | Northern | Perak | 4.841750 | 100.726100 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop | TSS |  |  | Cancel / Drop | Upgrade under NIC DU: 4178D | [13 empty] | Ongoing | 2024-03-25 | 2024-03-25 | 2024-03-25 |  | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2776B-1365B | Denai Alam 2 | DU00003451870 | Central | Selangor | 3.162173 | 101.508036 | WK07 | FEB 24 | WK08 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE IDU: 1x 910A FE IDU: 1x 910A NE ODU: XMC3 18G 1+0 (Sub B) FE ODU: XMC3 18G 1+0 (Sub B) | MW Hardware Upgrade | MW Hardware Upgrade change IDU to 910A and ODU. Upgrade link from 56Mhz to 112Mhz. | [7 empty] | Allstar | SQ202402270775-Allstar | Allstar | SQ202402270708-Allstar // SQ202510070055-Allstar | 2024-04-03 | 2024-04-03 | Completed | 2024-02-12 | 2024-02-16 | 2024-02-15 | 2024-02-16 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-22 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24022132 |  | 2024-02-22 | 2024-02-22 | Completed | 2024-02-21 | 2024-02-22 | 2024-02-21 | 2024-02-22 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-07-01 | MUHAMMAD//NIZAM BIN SIJAOL KHAN/6798000188 | Allstar TI | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-02-24 | MUHAMMAD//NIZAM BIN SIJAOL KHAN/6798000188 | Allstar TI | 2024-02-24 | 2024-02-24 | 2024-02-24 | 2024-02-24 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-03-02 | MUHAMMAD//NIZAM BIN SIJAOL KHAN/6798000188 | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7695B-7196A | Tawau Taman Air Panas | DU00003451871 | Sabah | Sabah | 4.286325 | 117.903075 | WK08 | FEB 24 | WK20 | MAY 24 | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | 26/5: D4: Cutover done 23/5: Spare arrival 24/5, plan CO by 25/5 20/5: D3: Continue TI & Plan CO. ODU faulty, pending spare | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_2+0_110MHz | MW Swap | [8 empty] | GTSB | SQ202403220495-GTSB |  | SQ202409120182-GTSB // SQ202411120062-GTSB | 2024-04-05 | 2024-04-03 | Completed | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | PAVITRAN AL CHINNAKOLANDAY6799000150 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-04-03 | 2024-04-05 | 2024-04-03 | 2024-04-03 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-03 | 2024-04-05 | 2024-04-03 | 2024-04-03 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-03 | 2024-04-05 | 2024-04-03 | 2024-04-03 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  |  | DO Canceled request by email | 2026-03-13 |  | Ongoing | 2026-03-12 | 2026-03-13 | 2026-03-12 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2024-05-17 | 2024-05-31 | 2024-05-16 | 2024-05-27 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-05-17 | 2024-05-31 | 2024-05-16 | 2024-05-27 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-05-17 | 2024-05-31 | 2024-05-16 | 2024-06-05 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | 2024-05-17 | 2024-05-31 | 2024-05-16 | 2024-05-20 | 2024-06-14 | 2024-06-14 | 2024-06-14 | 2024-06-14 | tseping//wang/6819000006 | Logistic Team | 2024-07-26 | 2024-08-26 | 2024-07-26 | 2024-07-26 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202603170137-GTSB
4758B-4464A | Lake Garden Taiping | DU00003451872 | Northern | Perak | 4.858210 | 100.755260 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop | TSS |  |  | Cancel / Drop | [14 empty] | Ongoing | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1782B-1156A | Berjuntai Bestari(UNISEL) | DU00003451873 | Central | Selangor | 3.423215 | 101.441823 |  | MAR 24 | WK14 | APR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 22/4: D2: Cutover done 19/4: Cutover WIP. Link interference. Spillover 17/4: D1: TI done, alignment WIP 16/4: Pending EB CRQ approval | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM SUB B | MW Parallel Link | MW PARALLEL LINK 1782B-1156A 15G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM SUB B TO CARRY TRAFFIC OF 1782B BBU ONLY IMPACTED SITE: 2680A NE: 1) INSTALL NEW RTN910A (OPS TEAM TO ASSIGN NEW RTN NUMBER) 2) INSTALL NEW 15G 4+0 28MHZ AT NEW RTN 3-ISM8 AND 4-ISM8 WITH CA 3) INSTALL NEW ANTENNA 15G 1.2M AND ODU SUBBAND B 4) MIGRATE 1782B BBU ONLY TO NEW LINK FE: 1) INSTALL NEW RTN910A (OPS TEAM TO ASSIGN NEW RTN NUMBER) 2) INSTALL NEW 15G 4+0 28MHZ AT NEW RTN 3-ISM8 AND 4-ISM8 WITH CA 3) INSTALL NEW ANTENNA 15G 1.2M AND ODU SUBBAND B 4) MIGRATE 1782B BBU ONLY TO NEW LINK 5) PATCH NEW IDU TO NEW CP PORT AND ESTABLISH NEW DCN | [7 empty] | Ascentrack | SQ202409100315-Ascentrack | Ascentrack | SQ202403120472-Ascentrack | 2024-05-28 | 2024-05-27 | Completed | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | SAMANTHA LOOI SHU-YI6237001479 |  |  |  | Unassigned | Completed |  | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-27 | 2024-05-28 | 2024-05-27 | 2024-05-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240301BK |  | 2024-03-02 | 2024-03-07 | Completed | 2024-03-01 | 2024-03-02 | 2024-03-01 | 2024-03-07 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-07 | 2024-03-31 | 2024-03-07 | 2024-05-02 | LOW//CHUN WAI/7539000013 | Ascentrack TI | 2024-03-07 | 2024-06-30 | 2024-03-07 | 2024-05-09 | LOW//CHUN WAI/7539000013 | Ascentrack TI | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-07 | 2024-03-31 | 2024-03-07 | 2024-04-25 | LOW//CHUN WAI/7539000013 | 2024-05-24: 2024-03-07; 2024-05-31: 2024-03-31; 2024-06-15: 2024-03-07; 2024-06-15: 2024-04-22 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
9256B-9283A | Bukit Tiong-Core | DU00003451874 | Sarawak | Sarawak | 4.881684 | 115.395736 |  | APR 24 |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4248A-4104C | Kuala Juru | DU00003451875 | Northern | Penang | 5.316140 | 100.418857 | WK08 | FEB 24 | WK10 | MAR 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 1X 18G 0.6M MDD ANTENNA 1X 18G 1.2M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Swap | SWAP EXISTING MW WITH HUAWEI_18G_2+0_56MHZ_0.6M/1.2M_2.48KM 4014C: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 2+0 56MHZ 5. DISMANTLE EXISTING LINK 4248A: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 2+0 56MHZ 5. PATCH NEW RTN 910A TO RTN02 6. DISMANTLE EXISTING LINK EXCEPT IDU | [7 empty] | CCSMY | SQ202402220007-CCS | CCSMY | SQ202403110217-CCS // SQ202411120061-CCS | 2024-08-21 | 2024-08-21 | Completed | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  |  | Unassigned | Completed |  | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022851 |  | 2024-02-29 | 2024-03-02 | Completed | 2024-02-28 | 2024-02-29 | 2024-02-28 | 2024-03-02 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-08 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-07 | Muhamad//rais bin mat isa/7021000043 | CCS TI | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-14 | Muhamad//rais bin mat isa/7021000043 | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-06 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | NG HONG JIE7018000036 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
4310C-4007B | Taman Seri Damai Flat (REL) | DU00003451876 | Northern | Penang | 5.390842 | 100.307816 |  |  | WK07 | FEB 24 | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC |  | MW Remote Upgrade | REMOTE UPGRADE FOR MW 4310C-4007B: CHANGE FROM HUAWEI_18G_1+0_56MHZ TO 1+0_112MHZ | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-02-17 | 2024-02-17 | 2024-02-17 | 2024-02-17 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
2000C-1017A | Janda Baik Industrial (REL) | DU00003451877 | Eastern | Pahang | 3.334929 | 101.856850 |  | MAY 24 | WK19 | MAY 24 | TI | Pending EB CRQ | ZTE | 00. Integrated/RFS Done | 18/7: D2: Cutover done 17/7: D2: Pending DO for change ODU Sub A wit ODU Sub B 16/7: D1: TI done, all Ch# on Sub A interference. Need change MODU 10/7: Change subcon from Perwira | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_2+0_1.2M/1.2M_MDD_28MHZ_512QAM SUB A | MW Parallel Link | MW PARALLEL LINK 2000C-1017A 13G_2+0_1.2M/1.2M_MDD_28MHZ_512QAM SUB A TO EPLA WITH EXISTING 13G_1+0_28MHZ NE: 1. INSTALL NEW RTN 910A + 1 UNIT ISM8 CARD 2. INSTALL NEW 1.2M MDD DP ANTENNA 3. INSTALL NEW 13G 28MHZ XMC-5D ODU SUB BAND B 4. TRANSFER EXISTING 13G 1+0 LINK FROM EXISTING IDU TO NEW RTN 910A 5. CONFIGURE LINK 13G 2+0 28MHZ AND EPLA WITH EXISTING 13G 1+0 FE: 1. INSTALL NEW RTN 910A + 1 UNIT ISM8 CARD 2. INSTALL NEW 1.2M MDD DP ANTENNA 3. INSTALL NEW 13G 28MHZ XMC-5D ODU SUB BAND B 4. TRANSFER EXISTING 13G 1+0 LINK FROM EXISTING IDU TO NEW RTN 910A 5. CONFIGURE LINK 13G 2+0 28MHZ AND EPLA WITH EXISTING 13G 1+0 6. PATCH TO NEW CP PORT | [7 empty] | Magicell | SQ202408220911-Magicell | Magicell | SQ202408080054-Magicell (have dismantle) | 2025-03-04 | 2025-03-03 | Completed | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-20 | 2024-08-21 | 2024-08-20 | 2024-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-03 | 2025-03-04 | 2025-03-03 | 2025-03-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24030669 |  | 2025-01-16 | 2025-01-16 | Completed | 2025-01-16 | 2025-01-16 | 2025-01-16 | 2025-01-16 | AHMAD//ASHRAF BIN MOHAMAD/7018000082 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-16 | 2025-07-22 | 2024-07-16 | 2025-01-16 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 |  | 2024-07-16 | 2025-07-22 | 2024-07-16 | 2025-01-16 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 |  | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | C.PRATHABAN///6798000081 |  |  | 2024-07-16 | 2025-07-22 | 2024-07-16 | 2024-07-19 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2024-07-16 | 2025-07-22 | 2024-07-16 | 2024-07-18 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | NG HONG JIE7018000036 | Logistic Team | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
4959A-4665A | Tunjang | DU00003451879 | Northern | Kedah | 6.283209 | 100.376308 |  | MAY 24 |  | MAY 24 | Planning | Planning WIP | ZTE | 00. Site Out/Drop |  |  |  | 1X RTN 910A 2X ISM8 CARD 2X 13G 1.2M MDD ANTENNA 1X 13G XMC-5D SUB B HI 1X 13G XMC-5D SUB B LO | Cancel / Drop | *Upgrade under NIC DU: 4959A_PostMOCN* ADD MW PARALLEL LINK 4959A-4665A WITH HUAWEI_13GHZ_2+0_28MHZ_1.2M_5.17KM EXISTING MW CFG: 15GHZ_2+0_28MHZ. IMPACTED SITES: 4959A NE: AT 4959A: 1. INSTALL NEW ISM8 CARD AT EXISTING RTN03 SLOT 3 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW 13G XMC-5D SUB B 4. CONFIGURE LINK 13G 2+0 28MHZ 5. EPLA EXISTING 15G 2+0 WITH NEW 13G 2+0 FE: AT 4665A: 1. INSTALL NEW RTN 910A + 1 ISM8 CARD 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW 13G XMC-5D SUB B 4. CONFIGURE LINK 13G 2+0 28MHZ 5. SHIFT EXISTING 15G 2+0 IF CABLE & CONFIGURATION FROM RTN05 7-ISM8 TO NEW RTN 910A 6. EPLA EXISTING 15G 2+0 WITH NEW 13G 2+0 7. PATCH NEW RTN 910A TO NEW CP PORT | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1737A-1299B | Bernama | DU00003451880 | Central | Kuala Lumpur | 3.171420 | 101.712134 | WK12 | MAR 24 | WK11 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 15/3: D2: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_0.6m/0.6m_2+0_56Mhz | MW Swap | DCN VLAN : 412, PORT NUMBER : Eth-Trunk6 NE 1- Swap SM IDU with Huawei IDU 910A 2- Swap SM 1+0 ODU with Huawei 2+0 ODU. 3- Swap SM Antenna with new Huawei 0.6m Antenna. 4- Configure link 2+0_890M_512QAM.. 5- Cascade child sites SM IDU towards the new link. FE 1- Swap SM IDU with Huawei IDU 910A 2- Swap SM 1+0 ODU with Huawei 2+0 ODU. 3- Swap SM Antenna with new Huawei 0.6m Antenna. 4- Configure link 2+0_890M_512QAM. 5- Configure new DCN VLAN for monitoring. | [7 empty] | Allstar | SQ202404170262-Allstar | Allstar | SQ202402270708-Allstar // SQ202510070055-Allstar | 2024-05-24 | 2024-05-23 | Completed | 2024-02-26 | 2024-03-01 | 2024-03-28 | 2024-04-01 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-04-01 | 2024-04-30 | 2024-04-04 | 2024-04-04 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-05-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24022219 |  | 2024-02-23 | 2024-02-27 | Completed | 2024-02-22 | 2024-02-23 | 2024-02-22 | 2024-02-27 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-15 | 2024-03-31 | 2024-03-15 | 2024-04-26 | MOHAMMAD//FIKHRI ADHA BIN SAYUTI/6798000187 | Allstar TI | 2024-03-15 | 2024-06-30 | 2024-03-15 | 2024-05-09 | MOHAMMAD//FIKHRI ADHA BIN SAYUTI/6798000187 | Allstar TI | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | C.PRATHABAN///6798000081 |  |  | 2024-03-15 | 2024-03-31 | 2024-03-15 | 2024-05-30 | MOHAMMAD//FIKHRI ADHA BIN SAYUTI/6798000187 | 2024-03-15 | 2024-03-31 | 2024-03-15 | 2024-03-15 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | NG HONG JIE7018000036 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
9983A-9999A | Demak Siol Kandis | DU00003451881 | Sarawak | Sarawak | 1.578217 | 110.359389 | WK10 | MAR 24 |  | MAY 24 | RFS |  | ZTE | 00. Integrated/RFS Done | 11/5: D3: Continue TI 10/5: D2: TI WIP 9/5: MOS & TI In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/1.2m_MDD_1+0_110MHz | MW Swap | [8 empty] | Trintel | SQ202403220491-Trintel | Trintel | SQ202409120139-Trintel | 2024-04-05 | 2024-04-02 | Completed | 2024-02-29 | 2024-03-01 | 2024-03-04 | 2024-03-05 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-04 | 2024-03-05 | 2024-03-04 | 2024-03-05 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-05 | 2024-03-08 | 2024-03-05 | 2024-03-05 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-02 | 2024-04-05 | 2024-04-02 | 2024-04-02 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240506D4 |  | 2024-05-07 | 2024-05-08 | Completed | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2024-05-08 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-07 | 2024-06-07 | 2024-05-13 | 2024-05-13 | LAU//HOCK KWANG/7667000005 | Trintel TI | 2024-05-07 | 2024-06-07 | 2024-05-08 | 2024-05-13 | LAU//HOCK KWANG/7667000005 | Trintel TI | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2024-05-11 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-05-07 | 2024-06-07 | 2024-05-14 | 2024-05-14 | LAU//HOCK KWANG/7667000005 | 2024-05-07 | 2024-06-07 | 2024-05-09 | 2024-05-09 | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-07-11 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-07-30 | 2024-08-30 | 2024-07-30 | 2024-07-30 | ASTI//GANIS PUTRIANI/6237001358
2300A-1783B | JHEOA | DU00003451882 | Central | Selangor | 3.294465 | 101.732100 | WK10 | MAR 24 | WK10 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Re-use antenna, 23G 1+0 112MHz 889Mbps | MW Hardware Upgrade | NE: 1. Antenna: Existing 2. ODU: Swap with new XMC-3E 112MHz Sub-band A x 1 3. IDU: Swap existing RTN950 with new RTN910A x 1, re-use name RTN01 4. IF card: New RTN910A Built-in Slot 7 5. Configure 23G 1+0 112MHz 890Mbps 6. BBU re-patch to this new RTN01 FE: 1. Antenna: Existing 2. ODU: Swap with new XMC-3E 112MHz Sub-band A x 1 3. IDU: Swap existing RTN950 with new RTN910A, named RTN01 4. IF card: New RTN910A Built-in Slot 7 5. Configure 23G 1+0 112MHz 890Mbps 6. Fiber re-patch to this new RTN01 | [7 empty] | Allstar | SQ202403120253-Allstar | Allstar | SQ202403260107-Allstar // SQ202411040256-Allstar | 2024-04-04 | 2024-04-03 | Completed | 2024-03-02 | 2024-03-02 | 2024-03-02 | 2024-03-02 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-04 | 2024-03-04 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-03-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-03 | 2024-04-04 | 2024-04-03 | 2024-04-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24022908 |  | 2024-03-01 | 2024-03-01 | Completed | 2024-02-29 | 2024-03-01 | 2024-02-29 | 2024-03-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-03 | 2024-03-31 | 2024-03-03 | 2024-05-29 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | Allstar TI | 2024-03-03 | 2024-03-31 | 2024-03-03 | 2024-03-07 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | Allstar TI | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-03 | 2024-03-31 | 2024-03-03 | 2024-03-11 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | 2024-03-03 | 2024-03-31 | 2024-03-03 | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
3363C-2663B | Taman Muthu 3 (REL) | DU00003451883 | Central | Selangor | 3.032278 | 101.477861 | WK09 | MAR 24 | WK09 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28MHZ_0.6M/1.2M_128QAM | MW Swap | MW SWAP MW LINK 3363C-2663B WITH HUAWEI_15G_4+0_28MHZ_0.6M/1.2M_128QAM NE: 1. INSTALL NEW RTN910A 2. INSTALL 2 UNIT ISM8 CARD AT NEW RTN910A SLOT 3&4 3. INSTALL NEW 15G 0.6M MDD ANTENNA 4. INSTALL NEW 15G XMC-5D SUB BAND B 5. CONFIGURE LINK 15G 4+0 28MHZ WITH CA SLOT 3 & 4 6. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW RTN910A 2. INSTALL 2 UNIT ISM8 CARD AT NEW RTN910A SLOT 3 & 4 3. INSTALL NEW 15G 1.2M MDD ANTENNA 4. INSTALL NEW 15G XMC-5D SUB BAND B 5. CONFIGURE LINK 15G 4+0 28MHZ WITH CA 6. DISMANTLE EXISTING LINK | [7 empty] | Perwira | SQ202407050123-Perwira | Perwira | SQ202402270744-Perwira | 2024-09-20 | 2024-09-19 | Completed | 2024-02-27 | 2024-06-30 | 2024-02-28 | 2024-02-28 | Ahmad//Kamal Ikhwan Bin Mohd Ariffin/7238000004 | Perwira TI | PERWIRA ENERGY SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-14 | 2024-08-15 | 2024-08-14 | 2024-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-14 | 2024-08-15 | 2024-08-14 | 2024-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022386 |  | 2024-02-24 | 2024-02-27 | Completed | 2024-02-23 | 2024-02-24 | 2024-02-23 | 2024-02-27 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-02-28 | Ahmad//Kamal Ikhwan Bin Mohd Ariffin/7238000004 | Perwira TI | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-02-29 | Ahmad//Kamal Ikhwan Bin Mohd Ariffin/7238000004 | Perwira TI | 2024-02-27 | 2024-03-05 | 2024-02-29 | 2024-02-29 | C.PRATHABAN///6798000081 | Perwira TI |  | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-03-07 | Ahmad//Kamal Ikhwan Bin Mohd Ariffin/7238000004 | 2024-02-27 | 2024-02-29 | 2024-02-27 | 2024-02-28 | 2024-02-27 | 2024-06-30 |  |  | Ahmad//Kamal Ikhwan Bin Mohd Ariffin/7238000004 | Perwira TI | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
3661B-2631A | Jalan Demang 5 | DU00003451884 | Central | Selangor | 3.028432 | 101.460820 |  | MAR 24 | WK11 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Re-use antenna, 23G 1+0 112MHz 890Mbps | MW Hardware Upgrade | NE: 1. Antenna: Existing 2. ODU: Swap with new XMC-3E 112MHz Sub-band A x 1 3. IDU: Swap existing with new RTN910A x 1, re-use name RTN01 4. IF card: New RTN910A Built-in Slot 7 5. Remove IF cable from RTN01 Slot 7-1 and connect to new RTN01 Slot 7-1 5. Configure 23G 1+0 112MHz 890Mbps FE: 1. Antenna: Existing 2. ODU: Swap with new XMC-3E 112MHz Sub-band A x 1 3. IDU: Install new RTN910A, named RTN02, patch to existing RTN01 4. IF card: New RTN910A Built-in Slot 7 5. Remove IF cable from RTN01 Slot 5 and connect to new RTN02 Slot 7-1 6. Configure 23G 1+0 112MHz 890Mbps 7. Fiber re-patch to this new RTN02 | [7 empty] | Perwira | SQ202403180282-Perwira | Perwira | SQ202403260178-Perwira | 2024-08-30 | 2024-08-29 | Completed | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | WB80041943 |  | PERWIRA ENERGY SDN. BHD. |  | Unassigned | Completed |  | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-07-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-07-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240305BQ |  | 2024-03-06 | 2024-03-13 | Completed | 2024-03-05 | 2024-03-06 | 2024-03-05 | 2024-03-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-15 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-15 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-14 | 2024-03-31 | 2024-03-14 | 2024-03-18 | RIO//RINALDI BIN YUNDARI/7238000002 | 2024-05-24: 2024-03-14; 2024-05-31: 2024-03-31; 2024-06-15: 2024-03-14; 2024-06-15: 2024-03-15 |  |  | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4315B-3167B | HUTANMLTG | DU00003451885 | Northern | Perak | 3.885009 | 100.937208 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop |  |  |  | Cancel / Drop | Upgrade under NIC DU: 3167B4 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7975A-7626B | Seaventures Mabul | DU00003451886 | Sabah | Sabah | 4.253610 | 118.633237 | WK09 | FEB 24 |  | JUN 25 | Design change | New material to released after design change | Digi | 00. Integrated/RFS Done | Non-doable | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 8GHz_1.2m (Main), 2.4m (Div) / 1.2m (Main), 2.4m (Div)_2*(1+1)_SD_29.65MHz | MW Parallel Link | NE: 1. Swap exisitng RTN950 with New Huawei IDU RTN 910A 2. Install 1xISM 8 at Slot 3 and reconfig for exisitng 13G_1+1 link. 3. Install new 8G_XMC-3(SB A) 4. Install New Huawei 8GHz 1.2m Antenna (Main) 5. Install New Huawei 8GHz 1.2m Antenna (Div) 6. Configure link as 8GHz (1+1) (SD) 29.65MHz FE 1. Swap exisitng RTN950RTN01 with New Huawei IDU RTN 910A 2. Install 1xISM 8 at Slot 3 and reconfig for exisitng 13G_1+1 link. 3. Install new 8G_XMC-3(SB A) 4. Install New Huawei 8GHz 2.4m Antenna (Main) 5. Install New Huawei 8GHz 2.4m Antenna (Div) 6. Configure link as 8GHz 2*(1+1) (SD) 29.65MHz and EPLA with exisitng 13G link. | [7 empty] | GTSB | SQ202403220495-GTSB | NR services | SQ202507190102-NR Services // SQ202507190103-NR Services | 2024-11-22 | 2024-11-20 | Completed | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | PAVITRAN AL CHINNAKOLANDAY6799000150 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-07-11 | 2024-07-12 | 2024-07-11 | 2024-07-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-11 | 2024-07-12 | 2024-07-11 | 2024-07-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-20 | 2024-11-22 | 2024-11-20 | 2024-11-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022491 | No 8G 1.8/1.8 DP antenna | 2025-02-25 | 2025-02-26 | Completed | 2025-02-24 | 2025-02-25 | 2025-02-24 | 2025-02-26 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-23 | 2025-05-17 | 2025-04-23 | 2025-08-21 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-04-23 | 2025-05-17 | 2025-04-23 |  | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-21 | 2025-04-23 | 2025-05-17 | 2025-04-23 |  | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | 2024-05-24: 2025-04-23; 2024-05-31: 2025-05-17; 2024-06-15: 2025-04-23; 2024-06-15: 2025-10-11
4627C-4172A | Masjid Batu Kg Pertama | DU00003451887 | Northern | Penang | 5.390040 | 100.417535 | WK09 | FEB 24 | WK36-40 | SEP 24 | Planning | Link Engineering Report WIP | ZTE | 03. TSS Only | 26/8: Change new DU 12/11: SOW to be done under 4627C_LOS 22/10: Pending Site DO | TSS |  | 18G_1+0_112M. NE_4627C 1.Install new 18G_SP_0.6m(MAC)+OMT x1. 2.Install new XMC_3E-1+0 , Sub_A_Lo x1. 3.Install new RTN910,7_ISM8-1+0 x1. FE_4175A 1.Install new 18G_SP_0.6m(MAC)+OMT x1. 2.Install new XMC_3E-1+0 , Sub_A_Hi x1. 3.Install 4_ISM8-1+0 x1. | MW Hardware Upgrade | Existing link 18G_1+0_56M.Having LOSS Comm Alrm. Hardware upgrade to 18G_1+0_112M. Site Impacted: 4627C. NE_4627C 1.Reuse 18G_SP_0.6m(MAC)+OMT. 2.Hardware upgrade to XMC_3E-1+0 , Sub_A_Lo. 3.Reuse RTN910, 7_ISM8-1+0. 4.Create service cross connect. FE_4175A 1.Reuse 18G_SP_0.6m(MAC)+OMT. 2.Hardware upgrade XMC_3E-1+0 , Sub_A_Hi. 3.Create service cross connect. | [7 empty] | CCSMY | SQ202403110208-CCS | GTSB | No PR required-Work at TSS only |  |  | Ongoing | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-27 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  |  | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25072952 |  | 2025-07-30 | 2025-08-25 | Completed | 2025-07-29 | 2025-07-30 | 2025-07-29 | 2025-08-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | [7 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | HAMZAH BIN ABDUL MUTALIF6799000301 | 2024-05-24: 2025-08-25; 2024-05-31: 2025-08-25; 2024-06-15: 2025-08-25; 2024-06-15: 2025-08-26 | [7 empty] | GCI_AA | SQ202510300164-GCI | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-10-21 | CHEONG/SENG/WAH/7018000306
4597B-4410C | Desa Sri Iskandar RDC | DU00003451889 | Northern | Perak | 4.358610 | 100.937000 | WK08 | FEB 24 |  |  | Planning | Link Engineering Report WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop | TSS |  |  | Cancel / Drop | Upgrade under NIC DU: 4410C | [13 empty] | Ongoing | 2024-02-18 | 2024-02-18 | 2024-02-18 |  | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  |  | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2024-04-18
3645B-2772A | Tmn Klang Utama 2 | DU00003451890 | Central | Selangor | 3.083812 | 101.412261 | WK10 | MAR 24 | WK10 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 0.6m/0.6m 1+0 112Mhz (Sub B) | MW Swap | NE 1- Swap SM IDU with Huawei IDU 910A. 2- Swap SM ODU with Huawei 23G 1+0 ODU Sub B. 3- Swap SM Antenna with Huawei 23G 0.6m Antenna. 4- Configure link 1+0_800M_512QAM. FE 1- Swap SM IDU with Huawei IDU 910A. 2- Swap SM ODU with Huawei 23G 1+0 ODU Sub B. 3- Swap SM Antenna with Huawei 23G 0.6m Antenna. 4- Configure link 1+0_800M_512QAM. 5- Required new DCN VLAN. 5. Impact sites: 3645B | [7 empty] | Allstar | SQ202403120253-Allstar | Allstar | SQ202403120466-Allstar // SQ202510070055-Allstar | 2024-04-27 | 2024-04-29 | Completed | 2024-03-01 | 2024-03-01 | 2024-03-05 | 2024-03-05 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-17 | 2024-04-18 | 2024-04-17 | 2024-04-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24022909 |  | 2024-03-01 | 2024-03-01 | Completed | 2024-02-29 | 2024-03-01 | 2024-02-29 | 2024-03-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-03-12 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 | Allstar TI | 2024-03-04 | 2024-06-30 | 2024-03-07 | 2024-05-09 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 | Allstar TI | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-06-13 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 | 2024-03-12 | 2024-03-31 | 2024-03-12 |  | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4756B-4462A | Taman Kaya Taiping | DU00003451892 | Northern | Perak | 4.824629 | 100.724607 | WK07 | FEB 24 |  |  | Planning | Link Engineering Report WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop | TSS |  |  | Cancel / Drop | Upgrade under NIC DU: 4756B | [13 empty] | Ongoing | 2024-02-16 | 2024-02-16 | 2024-02-16 |  | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  |  | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1411B_LOS | Wisma Kesas (ZED) | DU00004230773 | Central | Kuala Lumpur | 3.059610 | 101.608410 |  |  |  |  | Cancel / Drop | No need proceed | ZTE | 00. Site Out/Drop | 21/6: Solution done under TX NIC 1411B_PostMOCN (Reroute Link Activity) |  |  |  | Cancel / Drop | [8 empty] | Datasco | No PR required-Site drop/cancel |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7042A_BBU | Telipok | DU00004230774 | Sabah | Sabah | 6.116350 | 116.207130 | [7 empty] | 00. Integrated/RFS Done | 14/10: D2: Cutover done. Post-CO T/S ongoing 8/10: MOS & TI In Plan | TSS+TI | L1+ATP+PAC |  | BBU Patching | Patching from 1G port to 10G port (10G Ge0/2/2) | [7 empty] | NR Services | SQ202410280486-NR Services | NR services | SQ202410100848-NR Services | 2024-11-08 | 2024-11-05 | Completed | 2024-10-14 | 2024-10-14 | 2024-10-14 | 2024-10-14 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-15 | 2024-10-18 | 2024-10-15 | 2024-10-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-15 | 2024-10-18 | 2024-10-15 | 2024-10-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-05 | 2024-11-08 | 2024-11-05 | 2024-11-05 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24100242 |  | 2024-10-03 | 2024-10-03 | Completed | 2024-10-02 | 2024-10-03 | 2024-10-02 | 2024-10-03 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-14 | 2024-10-31 | 2024-10-14 | 2024-10-14 | MARTO FERDANEND BIN MOTIAS7167000021 | NR Service TI | 2024-10-14 | 2024-10-31 | 2024-10-14 | 2024-10-26 | MARTO FERDANEND BIN MOTIAS7167000021 | NR Service TI | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-10-14 | 2024-10-31 | 2024-10-14 | 2024-10-14 | MARTO FERDANEND BIN MOTIAS7167000021 | 2024-05-24: 2024-10-14; 2024-05-31: 2024-10-31; 2024-06-15: 2024-10-14 |  |  | 2024-11-30 | 2024-12-30 | 2024-11-30 | 2024-11-30 | ASTI//GANIS PUTRIANI/6237001358
4367B_LOS | Utar Kampar RCC | DU00004230775 | Northern | Perak | 4.330119 | 101.129844 | [7 empty] | 00. Site Out/Drop | 7/10: Site already MOCN - direct fiber. Link SM 4367B-4368A no traffic |  |  | BBU Patching | Cancel / Drop | BBU Patching at 4367B/A00383 | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042168 | Release fixing clip for MW EOS due to cannot cross project | 2026-04-22 | 2026-04-23 | Completed | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed
9368A_BBU | Salim Road Sacofa | DU00004230776 | Sarawak | Sarawak | 2.267322 | 111.866617 | [6 empty] | ZTE | 00. Integrated/RFS Done | 16/10: Cutover done. Post-CO T/S ongoing | TSS+TI | L1+ATP+PAC |  | BBU Patching | Patching from 1G port to 10G port (10G Ge0/2/2) | [7 empty] | Datasco | SQ202410280509-Datasco | Datasco | SQ202410100853-Datasco | 2025-01-03 | 2024-12-30 | Completed | 2024-10-17 | 2024-10-24 | 2024-10-17 | 2024-10-24 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-17 | 2024-10-18 | 2024-10-17 | 2024-10-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-17 | 2024-10-18 | 2024-10-17 | 2024-10-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-30 | 2025-01-03 | 2024-12-30 | 2024-12-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24100143 |  | 2024-10-02 | 2024-10-02 | Completed | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-09 | 2024-10-31 | 2024-10-16 | 2024-10-16 | Wong Ching Chai7019000072 | Datasco TI | 2024-10-09 | 2024-10-31 | 2024-10-15 | 2024-10-19 | Wong Ching Chai7019000072 | Datasco TI | 2024-10-16 | 2024-10-16 | 2024-10-16 | 2024-10-16 | MOHAMAD//NAZRIL HISYAM BIN RUSLI/6237001080 |  |  | 2024-10-09 | 2024-10-31 | 2024-10-19 | 2024-10-19 | Wong Ching Chai7019000072 | 2024-05-24: 2024-10-09; 2024-05-31: 2024-10-31; 2024-06-15: 2024-10-19; 2024-06-15: 2024-10-19 |  |  | 2024-11-28 | 2024-12-28 | 2024-11-28 | 2024-11-28 | ASTI//GANIS PUTRIANI/6237001358
3102A_LOS | DESA PARK CITY NKVE (REL) | DU00004230777 | Central | Kuala Lumpur | 3.180489 | 101.635208 | WK10 | APR 25 | WK10 | APR 25 | TI | Pending NKVE work permit | ZTE | 00. Integrated/RFS Done | 7/3/2025 : FE installation complete, pending install NE site due to pending NKVE permit approval 6/3/2025 : Plan install NE and FE site - CRQ approved, cancel proceed due to team stuck at site 3811A 13/1/2025 : STEALTH - 30M Minaret - NE site 3102A DESA PARK CITY NKVE (REL), Digi OB - 3M Boom - RT - FE site 3501C KL Baptist Church Desa Park City (REL) 20/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M. NE_3102A 23G_SP_0.6m(MAC) x1. RTN910A x1 XMC_3E-1+0 , Sub A_Lo x1. FE_3501C 23G_SP_0.6m(MAC) x1. ISM8 x1. | MW New Link / Reroute | Link reroute to new FE 3501C with 23G_1+0_112M. For 3501C, give priority to the installation of the 3501C LOS Block before the 3102A_LOS. Site Impacted 3102A,3501C NE_3102A 1.Install new 23G_SP_0.6m(MAC). 2.Install new RTN910A,7_ISM8-1+0. 3.Install XMC_3E-1+0 , Sub A_Lo. 4.Create Cross connect. 5.Migrate traffic to new route FE site. 6.Decom existing MW link. FE_3501C 1.Install new 23G_SP_0.6m(MAC). 2.Reuse existing new RTN910A. 3.Install 3_ISM8-1+0 into existing 3501C RTN910A. 4.Create cross connect. 5.Traffic migrate to new link. 6.Decom existing MW link. | [7 empty] | GCI | SQ202504170453-GCI | GCI | SQ202504260057-GCI // SQ202504260058-GCI // SQ202505150098-GCI | 2025-07-02 | 2025-07-01 | Completed | 2025-04-08 | 2025-04-08 | 2025-05-05 | 2025-05-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-07 | 2025-05-08 | 2025-05-07 | 2025-05-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010850 |  | 2025-01-09 | 2025-02-07 | Completed | 2025-01-08 | 2025-01-09 | 2025-02-06 | 2025-02-07 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-07 | 2025-03-21 | 2025-03-07 | 2025-05-06 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-07 | 2025-03-21 | 2025-03-07 | 2025-05-06 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-04-29 | 2025-03-07 | 2025-03-21 | 2025-03-07 | 2025-05-16 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-07 | 2025-03-21 | 2025-03-07 | 2025-04-25 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI
1881B-1702A | NS Highway KM 422 (KJS) | DU00004230778 | Central | Selangor | 3.497446 | 101.532073 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 27/2/2025 : Cutover done 26/2/2025 : FE installation complete, NE installation WIP 24/2/2025 : SBC KJS - Tower - NE site 1881B NS Highway KM 422 (KJS), Digi OB - 60M 4 Legged Tower - FE site 1702A Bkt. Tagar (Trunk) | TSS+AA+TI | L1+ATP+PAC | 2X RTN910 4X ISM8 CARD 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1X ODU 15G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL 1881B-1702A WITH HUAWEI_15G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB B_6.7KM CA AND EPLA WITH EXISTING LINK IMPACTED: 1882B, 1881B NE: 1. INSTALL NEW RTN910 WITH 2PCS ISM8 CARD SLOT 7 & 8 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. SHIFT EXISTING IF CABLE FROM RTN01 SLOT 7 TO NEW RTN SLOT 7 6. EPLA BOTH NEW AND EXISTING LINK 7. CASCADE EXISTING IDU DUE TO CARRY 1882B TRAFFIC FE: 1. INSTALL NEW RTN910 WITH 2PCS ISM8 CARD SLOT 7 & 8 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. SHIFT EXISTING IF CABLE FROM RTN01 SLOT 7 TO NEW RTN SLOT 7 6. EPLA BOTH NEW AND EXISTING LINK 7. PATCH TO NEW CP PORT AND DO PORT LAG | 1. INSTALL NEW RTN910 WITH 2PCS ISM8 CARD SLOT 7 & 8 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. SHIFT EXISTING IF CABLE FROM RTN01 SLOT 7 TO NEW RTN SLOT 7 6. EPLA BOTH NEW AND EXISTING LINK 7. CASCADE EXISTING IDU DUE TO CARRY 1882B TRAFFIC | 1. INSTALL NEW RTN910 WITH 2PCS ISM8 CARD SLOT 7 & 8 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. SHIFT EXISTING IF CABLE FROM RTN01 SLOT 7 TO NEW RTN SLOT 7 6. EPLA BOTH NEW AND EXISTING LINK 7. PATCH TO NEW CP PORT AND DO PORT LAG | 5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202503060127-Magicell | Magicell | SQ202502270723-Magicell // SQ202504260146-Magicell | 2025-07-05 | 2025-07-03 | Completed | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022410 |  | 2025-02-25 | 2025-02-25 | Completed | 2025-02-24 | 2025-02-25 | 2025-02-24 | 2025-02-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-28 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-28 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-27 | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-03-04 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2024-05-24: 2025-02-26; 2024-05-31: 2025-02-28; 2024-06-15: 2025-02-26; 2024-06-15: 2025-03-03 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202506050715-GTSB
3624A_LOS | Persiaran Bukit Kiara | DU00004230779 | Central | Kuala Lumpur | 3.147345 | 101.649271 |  |  |  |  | Cancel / Drop | No need proceed | ZTE | 00. Site Out/Drop | 27/6: Solution done under TX NIC 3624A (Swap Activity) |  |  |  | Cancel / Drop | [8 empty] | Datasco | No PR required-Site drop/cancel |  |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1234B_LOS | PJU1 Lamp Pole (KJS) | DU00004551332 | Central | Selangor | 3.127788 | 101.602357 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 18/2/2025 : Cutover done 6/1/2025 : SBC KJS - 30M Lampole - NE site 1234B PJU1 Lamp Pole (KJS), Digi OB - 3M Bipod - RT - FE site 1407A Menara Luxor | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_1234B 18G_DP_0.6m(MDD) x1. RTN910A x1. XMC_5D , Sub_B_Hi x1. FE_1407A 18G_DP_0.6m(MDD) x1. RTN910A x1. XMC_5D , Sub_B_Lo x1. ETH Cable x1. | MW New Link / Reroute | Link reroute to new FE 1407A due to LOS block with config 18G_2+0_112M Site Impacted : 1234B , 1197A. NE_1234B 1.Install new 18G_DP_0.6m(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub_B_Hi. 4.Create service cross connect and EPLA. 5.Migrate traffic to new FE route. 6.Decom existing SM link (1234B-1197A).Ensure service migrate successful before decom. FE_1407A 1.Install new 18G_DP_0.6m(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub_B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new FE with config 18G_2+0_112M. 6.Enable GE port , ETH cable patching to existing 1407A_RTN05 (GE2). 7.Decom existing SM link(1197A-1234B).Ensure service migrate successful before decom. | [7 empty] | Magicell | SQ202502120386-Magicell | Magicell | SQ202503280442-Magicell // SQ202503280449-Magicell // SQ202504260146-Magicell |  |  | Ongoing | 2025-02-06 | 2025-02-06 | 2025-02-06 | 2025-02-06 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-12 | 2025-02-12 | 2025-02-12 | 2025-02-12 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250103AN |  | 2025-01-04 | 2025-02-03 | Completed | 2025-01-03 | 2025-01-04 | 2025-01-03 | 2025-02-03 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-02-19 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-02-27 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-18 | 2025-02-18 | 2025-02-28 | 2025-03-13 | 2025-03-13 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-02-18 | 2025-02-28 | 2025-03-10 | 2025-03-10 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358
Q00699-Q00025 | KG EMPILA | DU00004646674 | Sarawak | Sarawak | 1.431193 | 110.507921 | [6 empty] | ZTE | 00. Integrated/RFS Done | 18/12: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1x AGS 20 | MW Hardware Upgrade | MW HARDWARE UPGRADE Q00699-Q00025 FROM 18G_1+0_56MHZ TO 18G_1+0_112MHZ. NE: 1. Change AGS 20 support 112Mhz. 2. Reuse existing SM ODU. 3. Reuse existing SM antenna. 4. Configure 18G_1+0_112Mhz_256QAM. FE: 1. Reuse SM AGS 20. 2. Reuse existing SM ODU. 3. Reuse existing SM antenna. 4. Configure 18G_1+0_112Mhz_256QAM. (Tempory Upgrade due to HU, Decom site) | [7 empty] | Allstar | SQ202502260439-Allstar | Allstar | SQ202412180565-Allstar // SQ202504260202-Allstar | 2025-04-25 | 2025-04-21 | Completed | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24121424 |  | 2024-12-15 | 2024-12-18 | Completed | 2024-12-14 | 2024-12-15 | 2024-12-14 | 2024-12-18 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-18 | 2024-12-24 | 2024-12-20 | 2024-12-20 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2024-12-18 | 2024-12-24 | 2024-12-18 | 2024-12-19 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2024-12-18 | 2024-12-18 | 2024-12-18 | 2024-12-18 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-12-18 | 2024-12-24 | 2024-12-19 | 2024-12-19 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2024-12-18 | 2024-12-24 | 2025-02-27 | 2025-02-27 | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-24 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-02-20 | 2025-03-20 | 2025-02-20 | 2025-02-20 | NURUL//NADIA BINTI ABDULLAH/6800000045
K00082-K00325 | POKOK SENA | DU00003523220 | Northern | Kedah | 6.155580 | 100.519560 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | TX SOW: Cancel/drop |  |  |  | Cancel / Drop | Week 14 utilization 30.37% out of 4188Mbps | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
K00199-K00128 | JENUN | DU00003523221 | Northern | Kedah | 5.907600 | 100.474700 |  | MAY 24 |  | JUN 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done | 18/7: D2: Continue TI 16/7: D1: MOS & TI In Plan 12/6: NE Road access issue (high bushes), escalated to CD/OSS | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 18G 1.2M MDD ANTENNA 1X 18G XMC-5D SUB A HI 1X 18G XMC-5D SUB A LO | MW Swap | SWAP K00199-K00128 WITH HUAWEI_18GHZ_1+0_112MHZ_1.2M_3.71KM. IMPACTED SITES: K00199 NE: AT K00199: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 5. PATCH K00199 BBU TO NEW RTN 910A 6. DISMANTLE EXISTING K00199-K00128 (NT03473) FE: AT K00128: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 5. PATCH NEW RTN 910A TO K00128 OB FIBER 6. DISMANTLE EXISTING K00199-K00128 (NT03473) | [7 empty] | GCI | SQ202408220943-GCI | GCI | SQ202408080062-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-07-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24060323 |  | 2024-06-04 | 2024-07-24 | Completed | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-07-24 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-06-12 | 2024-06-30 | 2024-06-12 | 2024-07-24 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-06-12 | 2024-09-30 | 2024-06-12 | 2024-07-24 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-06-12 | 2024-06-30 | 2024-06-12 | 2024-07-19 | HIMAN//BIN ADAM/6800000183 | 2025-02-18: 2024-06-12; 2025-02-28: 2024-06-30; 2025-03-10: 2024-06-12; 2025-03-10: 2024-07-16 |  |  | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
Q01603-Q00648 | KG BENUK | DU00003523222 | Sarawak | Sarawak | 1.307290 | 110.296929 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050656-GTSB | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | HSU//MYET CHAE/6799000011
A00405-A00860 | A043A_A00405OD_KGCINASITIAWAN | DU00003523223 | Northern | Perak | 4.182893 | 100.670019 |  |  |  | MAY 24 | RFS |  | ZTE | 00. Integrated/RFS Done | 18/5: D3: Cutover done 13/5: D2: Installation done, pending alignment & CO 10/5: D1: TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X ISM8 2X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Swap | SWAP MW LINK A00405-A00860 WITH HUAWEI_18G_2+0_112MHZ_0.6M_1.86KM EXISTING MW CFG: HW_18GHZ_1+0 IMPACTED SITES: A00405,A01111 NE: AT A00405 1. INSTALL NEW ISM8 AT EXISTING RTN 910A(5-16148) SLOT 3 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 5. DISMANTLE EXISTING LINK EXCEPT IDU FE: AT A00860 1. INSTALL NEW ISM8 AT EXISTING RTN 910A(5-26148) SLOT 3 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 5. DISMANTLE EXISTING LINK EXCEPT IDU | [7 empty] | GCI | SQ202407010442-GCI | GCI | SQ202407020120-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24050399 |  | 2024-05-04 | 2024-05-09 | Completed | 2024-05-03 | 2024-05-04 | 2024-05-03 | 2024-05-09 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-10 | 2024-05-24 | 2024-05-10 | 2024-05-20 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-05-10 | 2024-05-24 | 2024-05-10 | 2024-05-20 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-05-10 | 2024-05-24 | 2024-05-10 | 2024-05-21 | team21gcitechnicalteam21gcitechnical | 2024-05-10 | 2024-05-24 | 2024-05-10 | 2024-05-10 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
N00094-N00162 | N00094_BATANGBENAR | DU00003523224 | Central | Selangor | 2.868388 | 101.823952 |  |  |  |  | Cancel / Drop | Close due to not in XC HU list | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Close due to not in XC HU list |  |  |  | Cancel / Drop | [8 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4156D-K00253 | Lorong Serampang | DU00003523225 | Northern | Kedah | 5.659854 | 100.524060 |  |  | WK32-WK35 | AUG 24 | Planning |  | ZTE | 00. Integrated/RFS Done | 13/8: D2: Cutover done 12/8: MOS & Pre-installation WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X ISM8 CARD 1X 23G 0.6M DP ANTENNA 1X 23G 1.2M DP ANTENNA 1X 23G 112MHZ XMC-3 SUB A HI 1X 23G 112MHZ XMC-3 SUB A LO | MW Swap | SWAP MW LINK 4156D-4628B WITH HUAWEI_23G_2+0_112MHZ_0.6M/1.2M_2.62KM EXISTING MW CFG: HW_23GHZ_1+0_112MHZ IMPACTED SITES: 4156D NE (4156D): 1. INSTALL NEW ISM8 CARD AT RTN01(44-12275) SLOT 3 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. REUSE EXISTING 1+0 23G 112MHZ XMC-3 SUB A + INSTALL NEW 1+0 23G 112MHZ XMC-3 SUB A 4. CONFIGURE LINK 23G 2+0 112MHZ 5. DISMANTLE EXISTING LINK EXCEPT IDU & ODU FE (4628B): 1. REUSE EXISTING RTN01(44-22275) 7-ISM8 2. INSTALL NEW 23G 1.2M DP ANTENNA 3. REUSE EXISTING 1+0 23G 112MHZ XMC-3 SUB A + INSTALL NEW 1+0 23G 112MHZ XMC-3 SUB A 4. CONFIGURE LINK 23G 2+0 112MHZ 5. DISMANTLE EXISTING LINK EXCEPT IDU & ODU | [7 empty] | GCI | SQ202408220943-GCI | GCI | SQ202408150460-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-08-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240806AA |  | 2024-08-07 | 2024-08-22 | Completed | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-08-22 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-12 | 2024-08-31 | 2024-08-12 | 2024-08-22 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-08-12 | 2024-08-31 | 2024-08-12 | 2024-08-22 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-08-20 | 2024-08-20 | 2024-08-20 | 2024-08-20 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-08-12 | 2024-08-31 | 2024-08-12 | 2024-08-14 | HIMAN//BIN ADAM/6800000183 | 2024-08-12 | 2024-08-31 | 2024-08-12 | 2024-08-12 | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-09-09 | 2024-10-09 | 2024-09-09 | 2024-09-09 | ASTI//GANIS PUTRIANI/6237001358
Q01819-Q00054 | Q124B_Q01819OD_TMNCHERRYWOOD | DU00003523226 | Sarawak | Sarawak | 1.571283 | 110.322246 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050656-GTSB | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | HSU//MYET CHAE/6799000011
Q00642-Q00236 | BUNAN GEGA | DU00003523227 | Sarawak | Sarawak | 0.935362 | 110.535539 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | upgrade unde | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S01637-S00281 | KAMPUNG MAWAO | DU00003523228 | Sabah | Sabah | 5.451600 | 115.779200 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB
B02709-B00460 | B065A_B02709OD_JLN4TMNTUNTEJA | DU00003523229 | Central | Selangor | 3.305556 | 101.594900 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop 2/9: Pending Tx Solution for HU |  |  | NA | Cancel / Drop | CANT PERFORM REMOTE UPGRADE DUE TO LINK STILL IN XC AND SM EQUIPMENT |  |  |  |  | 23408.000 MHz 22176.000 MHz |  |  | MTK | No PR required-Site drop/cancel | MTK | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01553-T3E_0803 | NG PELAGUS | DU00003523230 | Sarawak | Sarawak | 2.179490 | 113.069580 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050656-GTSB | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | HSU//MYET CHAE/6799000011
B02847-B00368 | B061B_B02847OD_PLAZAJELUTONGSHAHALAM | DU00003523231 | Central | Selangor | 3.115348 | 101.529425 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 26/2/2025 : Cutover done 25/2/2025 : Installation complete, pending alignment due to access limit 24/2/2025 : Plan install NE and FE site - PMSC approved, cancel proceed due to keys issue 10/2/2025 : THREESIXTY TECHNOLOGIES SDN BHD - TRIPOD - NE site B02847 B061B_B02847OD_PLAZAJELUTONGSHAHALAM, TELEKOM (M) - Tower - FE site 2597B TM Bkt Cherakah 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M_EPLA NE_B02847 18G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E, Sub A & B_Lo x2. FE_2597B 18G_DP_1.2M(MAC)+OMT x1. RTN910A x1. XMC_3E, Sub A & B_Hi x2. | MW New Link / Reroute | Link Existing 18G_1+0_56M_PLA Swap existing link to 18G_2+0_56M_EPLA Site Impacted : B02847 & 2597B NE_B02847 1.Install new 18G_DP_0.6M(MAC)+OMC 2.Install new RTN910A(RTN01) , 7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Lo. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). FE_2597B 1.Install new 18G_DP_1.2M(MAC)+OMC 2.Install new RTN910A(RTN01) , 7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Hi. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). 7.RTN910A will patching to TM LL xC B00368. 8. Use existing port at PTN(B00368). | Link Existing 18G_1+0_56M_PLA Swap existing link to 18G_2+0_56M_EPLA Site Impacted : B02847 & 2597B NE_B02847 1.Install new 18G_DP_0.6M(MAC)+OMC 2.Install new RTN910A(RTN01) , 7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Lo. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). | Link Existing 18G_1+0_56M_PLA Swap existing link to 18G_2+0_56M_EPLA Site Impacted : B02847 & 2597B FE_2597B 1.Install new 18G_DP_1.2M(MAC)+OMC 2.Install new RTN910A(RTN01) , 7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Hi. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). 7.RTN910A will patching to TM LL xC B00368. 8. Use existing port at PTN(B00368). | XMC 3E | MAC | 18G | 0.6M | 1.2M | MTK | SQ202503060132-MTK | MTK | SQ202502270729-MTK // SQ202504260152-MTK | 2025-04-09 | 2025-04-08 | Completed | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-25 | 2025-03-26 | 2025-03-25 | 2025-03-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-26 | 2025-03-27 | 2025-03-26 | 2025-03-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-08 | 2025-04-09 | 2025-04-08 | 2025-04-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022025 |  | 2025-02-21 | 2025-02-21 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-24 | 2025-03-18 | 2025-02-26 | 2025-02-26 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-02-24 | 2025-03-18 | 2025-02-26 | 2025-02-26 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-26 | 2025-02-24 | 2025-03-18 | 2025-02-26 | 2025-02-26 | RIDHUAN//BIN MANSOR/8225000011 | 2025-02-24 | 2025-03-18 | 2025-02-26 | 2025-02-26 | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | NG HONG JIE7018000036 | Logistic Team | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
Q00529-Q00315 | TM PAHLAWAN | DU00003523232 | Sarawak | Sarawak | 4.686664 | 115.024446 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | HSU//MYET CHAE/6799000011
2440A-2027A | Elmina Sg Buloh | DU00003523233 | Central | Selangor | 3.190206 | 101.508286 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop | TSS |  |  | Cancel / Drop | HU ON 8May - Utilization 52% | [7 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Ongoing | 2024-05-31 | 2024-05-31 | 2024-05-31 |  | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4339D-4272A | Penaga Town 2 (Celcom) | DU00003523234 | Northern | Penang | 5.535480 | 100.378291 |  | MAY 24 |  | MAY 24 | Planning | Planning WIP | ZTE | 00. Integrated/RFS Done | 30/5: D3: Cutover done 29/5: TI WIP, continue 30/5 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X 18G 0.6M MDD ANTENNA 1X 18G 1.2M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Swap | SWAP MW LINK 4339D-4272A WITH HUAWEI_18G_1+0_0.6M/1.2M_2.91KM EXISTING MW CFG: HW_23GHZ_1+0_112MHZ IMPACTED SITES: 4339D NE: AT 4339D: 1. REUSE EXISTING RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK EXCEPT IDU FE: AT 4272A: 1. REUSE EXISTING RTN 910A 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. DISMANTLE EXISTING LINK EXCEPT IDU | [7 empty] | CCSMY | SQ202409251047-CCS | CCSMY | SQ202409100380-CCS | 2025-08-06 | 2025-08-06 | Completed | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240503A1 |  | 2024-05-04 | 2024-06-04 | Completed | 2024-05-03 | 2024-05-04 | 2024-05-03 | 2024-06-04 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-29 | 2024-05-31 | 2024-05-29 | 2024-06-04 | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | CCS TI | 2024-05-29 | 2024-05-31 | 2024-05-29 | 2024-06-04 | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | CCS TI | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2024-05-30 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-05-29 | 2024-05-31 | 2024-05-29 | 2024-05-31 | MOHD//HAIQAL HAQIMIE BIN RAMLI/7021000052 | 2024-05-29 | 2024-05-31 | 2024-05-29 | 2024-05-30 | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | NG HONG JIE7018000036 | Logistic Team | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506050701-GCI
B00213-B00552 | B064H_B00213OD_MPIBANGI | DU00003523235 | Central | Selangor | 2.948100 | 101.750900 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Cancel / Drop | Close due to link already decom | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Close due to link already decom 15/8: Pending BoQ, TX SoW Details |  |  |  | Cancel / Drop | [8 empty] | MTK | No PR required-Site drop/cancel | MTK | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
A00489-A00219 | POSSLIM18_RDC | DU00003523236 | Northern | Perak | 4.539770 | 101.150803 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Current SM Link under xC will be proposed to decomm. Cancel / Drop Under DU00003523236. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01856-Q00772 | KG MUNGGUL LIMO | DU00003523237 | Sarawak | Sarawak | 1.157610 | 110.574100 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | HSU//MYET CHAE/6799000011
S00968-S00350 | BUKIT TAMU | DU00003515505 | Sabah | Sabah | 4.759719 | 117.940740 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB
A00322-A00086 | TMTRONOH | DU00003515506 | Northern | Perak | 4.421400 | 100.984400 |  | MAY 24 | WK32-WK35 | AUG 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done | 8/10: D5: Cutover done 3/10: PTW Edotco approved until 8/10 28/8: D4: Pending CO. Pending TM Adhoc WP & ePTW (Hizima key) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 4X ISM8 CARD 2X 15G 1.2M MDD ANTENNA 1X 15G XMC-5D SUB B HI 1X 15G XMC-5D SUB B LO | MW Swap | SWAP MW LINK A00322-A00086 WITH HUAWEI_15G_4+0_28MHZ_1.2M_5.33KM EXISTING MW CFG: HW_15GHZ_2+0_28MHZ_CH9V_CH11V IMPACTED SITES: A00322,A00629 NE: AT A00322: 1. INSTALL NEW RTN 910A + 2 ISM8 CARD 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB B 4. CONFIGURE LINK 15G 4+0 CA 28MHZ 5. PATCH A00322 BBU & CASCADE NT02525 IDU TO NEW RTN 910A 6. DISMANTLE EXISTING LINK FE: AT A00086: 1. INSTALL NEW RTN 910A + 2 ISM8 CARD 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB B 4. CONFIGURE LINK 15G 4+0 CA 28MHZ 5. PATCH NEW RTN 910A TO A00086 OB FIBER 6. DISMANTLE EXISTING LINK | [7 empty] | GCI | SQ202408300869-GCI | GCI | SQ202408150460-GCI // SQ202504150095-GCI | 2024-11-28 | 2024-11-28 | Completed | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-08-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240801BF |  | 2024-08-09 | 2024-08-03 | Completed | 2024-08-08 | 2024-08-09 | 2024-08-02 | 2024-08-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-11-26 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-11-26 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-11-21 | ANWAR//BIN ABDUL RASID/6800000149 | 2024-08-16 | 2024-08-31 | 2024-08-16 | 2024-08-21 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
K00915-K00522 | KOMP. HIJAU KUNING | DU00003515507 | Northern | Kedah | 6.107194 | 100.366470 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Planning | Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Solution Done Under DU00005249937 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S01491-S00178 | PI1M KAMPUNG BILIT | DU00003515508 | Sabah | Sabah | 5.499947 | 118.205530 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | HSU//MYET CHAE/6799000011
A00525-K00262 | SGSIPUTEH | DU00003515509 | Northern | Perak | 5.260500 | 100.811400 | [6 empty] | ZTE | 00. Site Out/Drop | SOW done under A00525 TX Rollout | TSS |  |  | Cancel / Drop | [14 empty] | Ongoing | 2024-08-02 | 2024-08-02 | 2024-08-02 |  | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
P00108-P00079 | SOLECTRON1 | DU00003515510 | Northern | Penang | 5.365771 | 100.401440 |  | MAY 25 | W49-52 | DEC 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done | 11/9: DO ready, Pending collection | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 2X 23G 0.6M ANTENNA 1X 23G XMC-3 SUB A HI 1X 23G XMC-3 SUB A LO | MW Swap | SWAP MW LINK P00108-P00079 WITH HUAWEI_23G_1+0_0.6M_1.16KM MW IDU PATCHING AT P00079 & 4171A, TO PATCH NEW RTN 910A TO NEW 4171A CP PORT EXISTING MW CFG: HW_15GHZ_1+1_28MHZ IMPACTED SITES: P00108 NE (P00108): 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M ANTENNA 3. INSTALL NEW 23G XMC-3 SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. PATCH P00108 BBU TO NEW RTN 910A 6. DISMANTLE EXISTING LINK FE (P00079): 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M ANTENNA 3. INSTALL NEW 23G XMC-3 SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. PATCH NEW RTN 910A TO NEW 4171A CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202409060591-GCI // SQ202504150095-GCI // SQ202508140738-GCI | 2025-12-10 | 2025-12-10 | Completed | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-20 | 2025-03-21 | 2025-03-21 | 2025-03-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24082728 |  | 2024-08-28 | 2025-03-24 | Completed | 2024-08-27 | 2024-08-28 | 2024-08-27 | 2025-03-24 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-27 | 2024-09-30 | 2024-09-27 | 2025-03-24 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2024-09-27 | 2024-09-30 | 2024-09-27 | 2025-03-24 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | GCI TI | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-20 | 2024-09-27 | 2024-09-30 | 2024-09-27 | 2025-03-21 | MUHAMMAD MUIZZ BIN ALIAS6800000213 | 2025-02-18: 2024-09-27; 2025-02-28: 2024-09-30; 2025-03-10: 2024-09-27; 2025-03-10: 2025-03-20 |  |  | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045
4466A-4457A | Taman Rakyat RDD | DU00003515511 | Northern | Perak | 4.921788 | 100.724700 |  | MAY 24 |  | JUN 24 |  | Pending DO | ZTE | 00. Integrated/RFS Done | 1/7: D2: Cutover done 28/6: D1: MOS & TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 1X 18G 1.2M MDD ANTENNA 1X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Swap | SWAP 4466A-4457A SM MW1 WITH HUAWEI_18GHZ_1+0_112MHZ_1.2M/0.6M_3.32KM. IMPACTED SITES: 4424A NE: AT 4466A: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 1.2M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. CASCADE 4466A-4424A IDU TO NEW RTN 910A 6. DISMANTLE EXISTING SM MW1 LINK FE: AT 4457A: 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. REUSE EXISTING CP PORT 6. DISMANTLE EXISTING SM MW1 LINK | [7 empty] | GCI | SQ202409120132-GCI | GCI | SQ202408080062-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2024-07-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240619AM |  | 2024-06-20 | 2024-06-27 | Completed | 2024-06-19 | 2024-06-20 | 2024-06-19 | 2024-06-27 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-06-28 | 2024-07-05 | 2024-06-28 | 2024-08-08 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-06-28 | 2024-09-30 | 2024-06-28 | 2024-08-16 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | C.PRATHABAN///6798000081 |  |  | 2024-06-28 | 2024-07-05 | 2024-06-28 | 2024-08-21 | ANWAR//BIN ABDUL RASID/6800000149 | 2024-06-28 | 2024-07-05 | 2024-06-28 | 2024-06-28 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-08-19 | 2024-09-19 | 2024-08-19 | 2024-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
2726C-2631A | Taman Bunga Raya (REL) | DU00003515512 | Central | Selangor | 3.018207 | 101.469000 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Integrated/RFS Done | Remote Upgrade DONE | AA | PAC |  | MW Remote Upgrade | MW Remote Upgrade to 112Mhz | [9 empty] | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-06 | [15 empty] | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358
B02821-B01471 | KLGUTAMAINDUSTRI_OFFJLNSGPULOH | DU00003515513 | Central | Selangor | 3.089200 | 101.402640 |  |  | WK32-WK35 | AUG 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 21/8: D2: Cutover done. Post-CO T/shooting WIP 20/8: MOS & Pre-installation WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112MHz_512QAM_0.6M/0.6M_XMC3 SUB A_889MBPS | MW Swap | MW SWAP LINK B02821-B01471 WITH HUAWEI_18G_1+0_112MHz_512QAM_0.6M/0.6M_XMC3 SUB A_889MBPS 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | [7 empty] | Allstar | SQ202408220872-Allstar | Allstar | SQ202409020176-Allstar // SQ202510070055-Allstar | 2025-03-26 | 2025-03-25 | Completed | 2024-06-08 | 2024-06-08 | 2024-06-08 | 2024-08-06 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-07 | 2024-08-08 | 2024-08-07 | 2024-08-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-15 | 2024-08-16 | 2024-08-15 | 2024-08-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-25 | 2025-03-26 | 2025-03-25 | 2025-03-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240814AH |  | 2024-08-15 | 2024-09-12 | Completed | 2024-08-14 | 2024-08-15 | 2024-08-14 | 2024-09-12 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-20 | 2024-08-31 | 2024-08-20 | 2024-10-17 | ALI//HAMZA/6798000192 | Allstar TI | 2024-08-20 | 2024-08-31 | 2024-08-20 | 2024-09-12 | ALI//HAMZA/6798000192 | Allstar TI | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-08-20 | 2024-08-31 | 2024-08-20 | 2024-09-06 | ALI//HAMZA/6798000192 | 2024-08-20 | 2024-08-31 | 2024-08-20 | 2024-08-20 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-06 | NG HONG JIE7018000036 | Logistic Team | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
S01065-S00023 | BRISS | DU00003515514 | Sabah | Sabah | 6.027250 | 116.018610 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB
2133A-2027A | Surau Al-Hidayah Saujana Utama | DU00003515515 | Central | Selangor | 3.205887 | 101.479000 |  |  |  | JUN 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | Remote Upgrade DONE | AA | PAC |  | MW Remote Upgrade | MW REMOTE Upgrade link 2133A-2027A HW_18G 2+0 0.6m/0.6m_110Mhz NE: 1. Reuse existing HW RTN910A . 2. reuse existing ODU 18G_110MHz_SB B. 3. reuse existing Antenna 18G. 4. Configure link as 18GHz_2+0_110MHz_1200M FE: 1. Reuse existing HW RTN910A . 2. reuse existing ODU 18G_110MHz_SB B. 3. reuse existing Antenna 18G. 4. Configure link as 18GHz_2+0_110MHz_1200M | [7 empty] | N/A | No PR required-Remote Upgrade | N/A | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-06-24 | C.PRATHABAN///6798000081 | [17 empty] | 2024-08-16 | 2024-09-16 | 2024-08-16 | 2024-08-16 | NOOR//UMIRA BINTI NORDIN/6237001468
2984C-1378B | Sunway Pyramid New | DU00003515516 | Central | Selangor | 3.072500 | 101.607200 | WK19 | FEB 25 |  | FEB 25 | Cancel / Drop | Colo site | Celcom | 03. TSS Only | 24/2/2025 : No need proceed due to colo site 10/2/2025 : Digi OB - IBC Rooftop - NE site 2984C Sunway Pyramid New, SBC KJS - 20M Lampole - FE site 1378B PJS 10 | TSS |  | 18G_1+0_112MHZ_0.6M/0.6M_256AM_SUB B | MW Swap | MW SWAP SM MW1 LINK 2984C-1378B WITH HUAWEI_18G_1+0_112MHZ_0.6M/0.6M_256AM_SUB B NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND B 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | Allstar | SQ202408220872-Allstar | GCI | No PR required-Work at TSS only | 2025-04-25 | 2025-04-24 | Completed | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-26 | 2025-03-27 | 2025-03-26 | 2025-03-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-24 | 2025-04-25 | 2025-04-24 | 2025-04-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021924 |  | 2025-02-20 | 2025-02-20 | Completed | 2025-02-19 | 2025-02-20 | 2025-02-19 | 2025-02-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed
9595C-9115A | Kuala Sangan 2 | DU00003515517 | Sarawak | Sarawak | 2.764468 | 112.970200 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | HSU//MYET CHAE/6799000011
B01804-B00781 | SEK 17 SHAH ALAM RD | DU00003515518 | Central | Selangor | 3.046780 | 101.505500 | WK36-40 | SEP 24 | WK32-WK35 | AUG 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 6/9: D2: Cutover done 5/9: MOS & Pre-installation In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112MHZ_0.6M/0.6M_256QAM_SUB B | MW Swap | MW SWAP MW LINK B01804-B00781 WITH HUAWEI_18G_1+0_112MHZ_0.6M/0.6M_256QAM_SUB B NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | MTK | SQ202409210230-MTK | MTK | SQ202409020182-MTK | 2024-12-06 | 2024-12-05 | Completed | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-19 | 2024-11-20 | 2024-11-19 | 2024-11-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-19 | 2024-11-20 | 2024-11-19 | 2024-11-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-12-05 | 2024-12-06 | 2024-12-05 | 2024-12-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24082733 |  | 2024-08-28 | 2024-08-29 | Completed | 2024-08-27 | 2024-08-28 | 2024-08-27 | 2024-08-29 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-05 | 2024-09-30 | 2024-09-04 | 2024-09-09 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-09-05 | 2024-09-30 | 2024-09-04 | 2024-09-09 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-09 | SHUJAAT//ALI/6800000124 |  |  | 2024-09-05 | 2024-09-30 | 2024-09-04 | 2024-09-11 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2024-09-05 | 2024-09-30 | 2024-09-04 | 2024-09-07 | 2024-11-05 | 2024-11-05 | 2024-11-05 | 2024-11-05 | NG HONG JIE7018000036 | Logistic Team | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
7014C-7169A | Kalansanan Village | DU00003515519 | Sabah | Sabah | 6.008174 | 116.131000 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | HSU//MYET CHAE/6799000011
Q00219-Q00388 | KG SIMBOH | DU00003515520 | Sarawak | Sarawak | 1.322260 | 110.347860 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | HSU//MYET CHAE/6799000011
K00256-K00109 | LEMBAHBUJANG | DU00003515521 | Northern | Kedah | 5.737000 | 100.415100 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Integrated/RFS Done | 25/06: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_28M NE_K00256 New 15G_1.2M(MDD) x1. RTN910A x1. XMC_5D, Sub B_Lo x1. FE_4779A New 15G_1.2M(MDD) x1. RTN910A x1. XMC_5D, Sub B_Hi x1. | MW Swap | Link Existing HW 13G_1+1 HSB_28M_256QAM Swap existing SM link to new HW 15G_2+0_28M_512QAM_EPLA. Site Impacted : K00256. NE_K00256 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. 4.Configure DCN Inband. 5.Enable port 8-EM6-1 of RTN910A(RTN01). 6.Migrate traffic to new link in which BBU K00256 will patching to port 8-EM6-1 of RTN910A(RTN01). Configure it. 7.Decom existing HW 13G_1+1 HSB_28M_256QAM(Link ID NT02314 - IDU, ODU & Ant) , if no other traffic backhauled. FE_4779A 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. 4.Configure DCN Inband. 5.Enable port 8-EM6-1 of RTN910A(RTN01). 6.Patching port 8-EM6-1 of RTN910A(RTN01) to xC PTN K00109. May reuse existing port at xC PTN K00109 for K00256. Configure it. 7.Decom existing HW 13G_1+1 HSB_28M_256QAM(Link ID NT02314 - IDU, ODU & Ant) , if no other traffic backhauled. | Link Existing HW 13G_1+1 HSB_28M_256QAM Swap existing SM link to new HW 15G_2+0_28M_512QAM_EPLA. Site Impacted : K00256. NE_K00256 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. 4.Configure DCN Inband. 5.Enable port 8-EM6-1 of RTN910A(RTN01). 6.Migrate traffic to new link in which BBU K00256 will patching to port 8-EM6-1 of RTN910A(RTN01). Configure it. 7.Decom existing HW 13G_1+1 HSB_28M_256QAM(Link ID NT02314 - IDU, ODU & Ant) , if no other traffic backhauled. | Link Existing HW 13G_1+1 HSB_28M_256QAM Swap existing SM link to new HW 15G_2+0_28M_512QAM_EPLA. Site Impacted : K00256. FE_4779A 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. 4.Configure DCN Inband. 5.Enable port 8-EM6-1 of RTN910A(RTN01). 6.Patching port 8-EM6-1 of RTN910A(RTN01) to xC PTN K00109. May reuse existing port at xC PTN K00109 for K00256. Configure it. | XMC_5D | MDD | 15G | 15G_1.2M(MDD) x1 | 15G_1.2M(MDD) x1 | GCI | SQ202504280464-GCI | GCI | SQ202505300215-GCI // SQ202505300224-GCI // SQ202508140739-GCI |  |  | Ongoing | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-06-30 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-25 | 2025-07-24 | 2025-07-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250520A2 |  | 2025-05-21 | 2025-05-23 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-29 | 2025-06-27 | 2025-05-29 | 2025-06-30 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-05-29 | 2025-06-27 | 2025-05-29 | 2025-06-30 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-29 | 2025-06-27 | 2025-05-29 | 2025-07-01 | MOHD SAIDI BIN ABD RAZAK6800000181 | 2025-05-29 | 2025-06-27 | 2025-05-29 | 2025-05-29 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB
B02031-B00409 | KM10.2 ELITEHIGHWAY | DU00003515522 | Central | Selangor | 3.010800 | 101.581050 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 28/2/2025 : Cutover done 27/2/2025 : Installation complete, pending alignment 10/2/2025 : VERTICOM SDN BHD - AESTHETIC MONOPOLE 45M LAND - NE site B02031 KM10.2 ELITEHIGHWAY, KONSORTIUM JARINGAN SELANGOR SDN BHD - TOWER 61M LAND - FE site B00409 B061L_B00409OD_KUALASGBARU 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M_EPLA NE_B02031 18G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E, Sub A & B_Lo x2. FE_B00409 18G_DP_1.2M(MAC)+OMT x1. RTN910A x1. XMC_3E, Sub A & B_Hi x2. | MW Swap | Link Existing 18G_2+0_56M PLA Swap existing link to 18G_2+0_112M Site Impacted : 1946B NE_B02031 1.Install new 18G_DP_0.6M(MAC) 2.Install new RTN910A(RTN01) , 7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Lo. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). FE_B00409 1.Install new 18G_DP_1.2M(MAC) 2.Install new RTN910A(RTN01) , 7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Hi. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). 7.RTN910A will patching to TM LL xC B00409. | Link Existing 18G_2+0_56M PLA Swap existing link to 18G_2+0_112M Site Impacted : 1946B NE_B02031 1.Install new 18G_DP_0.6M(MAC) 2.Install new RTN910A(RTN01) , 7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Lo. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). | Link Existing 18G_2+0_56M PLA Swap existing link to 18G_2+0_112M Site Impacted : 1946B FE_B00409 1.Install new 18G_DP_1.2M(MAC) 2.Install new RTN910A(RTN01) , 7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Hi. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Decom existing MW link (ODU & Ant). 7.RTN910A will patching to TM LL xC B00409. 8.Use existing port at PTN(B00409). | XMC 3E | MAC | 18GHZ | 0.6M | 1.2M | MTK | SQ202503060132-MTK | MTK | SQ202503050465-MTK // SQ202504260152-MTK | 2026-01-22 | 2026-01-22 | Completed | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-25 | 2025-03-26 | 2025-03-25 | 2025-03-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-25 | 2025-03-26 | 2025-03-25 | 2025-03-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-22 | 2026-01-21 | 2026-01-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022027 |  | 2025-02-21 | 2025-02-21 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-27 | 2025-03-18 | 2025-02-28 | 2025-02-28 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-02-27 | 2025-03-18 | 2025-02-27 | 2025-02-28 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-28 | 2025-02-27 | 2025-03-18 | 2025-02-28 | 2025-02-28 | RIDHUAN//BIN MANSOR/8225000011 | 2025-02-27 | 2025-03-18 | 2025-02-28 | 2025-02-28 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | NG HONG JIE7018000036 | Logistic Team | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
B02588-B01087 | TANJUNG INDUSTRIAL PARK_KLG | DU00003515523 | Central | Selangor | 2.971214 | 101.403890 | WK19 | MAY 24 | WK36-40 | SEP 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 12/9: D2: Cutover done 11/9: MOS & Pre-installation start | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112MHZ_0.6M/0.6M_512AM_SUB A | MW Swap | MW SWAP MW LINK B02588-B01087 WITH HUAWEI_18G_1+0_112MHZ_0.6M/0.6M_512AM_SUB A NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW 18G XMC-3 SUB BAND A 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. PATCH IDU TO NEW CP PORT 6. DISMANTLE EXISTING LINK | [7 empty] | MTK | SQ202409251045-MTK | MTK | SQ202409020182-MTK | 2025-08-30 | 2025-09-03 | Completed | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-09-13 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-17 | 2024-10-18 | 2024-10-17 | 2024-10-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-17 | 2024-10-18 | 2024-10-17 | 2024-10-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-29 | 2025-08-30 | 2025-08-29 | 2025-09-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24082731 |  | 2024-08-28 | 2024-08-29 | Completed | 2024-08-27 | 2024-08-28 | 2024-08-27 | 2024-08-29 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-09-11 | 2024-09-30 | 2024-09-11 | 2024-09-13 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-09-11 | 2024-09-30 | 2024-09-11 | 2024-09-13 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-09-11 | 2024-09-30 | 2024-09-11 | 2024-09-20 | RIDHUAN//BIN MANSOR/8225000011 | 2024-09-11 | 2024-09-30 | 2024-09-11 | 2024-09-11 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 | NG HONG JIE7018000036 | Logistic Team | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
4634D-P00211 | Kelab Gelugor (REL) | DU00003515524 | Northern | Penang | 5.369328 | 100.309780 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | DUPLICATE DU 4634D-4018B | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Y00029-A00834 | eMOS SRI GANDA OIL MILL | DU00003515525 | Northern | Perak | 3.913389 | 101.198950 |  |  |  |  | Planning | Planning WIP | ZTE | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | Follow TX Rollout Solution | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S00769-S00770 | AUMKAR OIL MILL | DU00003515526 | Sabah | Sabah | 4.747936 | 117.868220 |  |  |  |  | Drop | Pass to Huawei |  | 00. Site Out/Drop | Pass to Huawei |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | HSU//MYET CHAE/6799000011
4969A-4968A_1 | Sungai Kob | DU00004065739 | Northern | Kedah | 5.429180 | 100.644020 | [7 empty] | 00. Integrated/RFS Done | 24/8: D3: Cutover done 22/8: MOS & Pre-installation WIP 20/8: EQ CRQ applied. MOS & TI Plan 23/8 | TSS+AA+TI | L1+ATP+PAC | 15G 2+0 1.2m/1.2m DP NE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Lo 3) 1x15GHz XMC3 Sub B Lo 4) 1x15GHz 1.2m DP FE: 1) 1xISM8 card 2) 1x15GHz XMC3 Sub A Hi 3) 1x15GHz XMC3 Sub B Hi 4) 1x15GHz 1.2m DP | MW Parallel Link | Link 4967A-4685B congested due to additional child site 3508A being offloaded to this link by other party. Not possible to upgrade 4967A-4685B due to long distance. To reroute 3508A traffic to its original route: 3508A-4969A-4968A To install parallel 15G 2+0 at 4969A-4968A and EPLA with existing 2+0 link to create 4+0 Impact site: 3508A3 NE (4969A): 1) Add ISM8 card at RTN02 slot 4 2) Install new link at RTN02 4-ISM8 3) Create EPLA 4+0 slot 3, 4, and 5 FE (4968A): 1) Add ISM8 card at RTN03 slot 3 2) Install new link at RTN03 3-ISM8 3) Create EPLA 4+0 slot 7 & 3 4) Migrate 3508A to CP 4968A | [7 empty] | GCI | SQ202408300869-GCI | GCI | SQ202409060591-GCI | 2025-05-08 | 2025-05-08 | Completed | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-08-24 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-08-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240813CK |  | 2024-08-14 | 2024-08-27 | Completed | 2024-08-13 | 2024-08-14 | 2024-08-13 | 2024-08-27 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-22 | 2024-08-31 | 2024-08-21 | 2024-08-27 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-08-22 | 2024-08-31 | 2024-08-21 | 2024-08-24 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-08-24 | SHUJAAT//ALI/6800000124 |  |  | 2024-08-22 | 2024-08-31 | 2024-08-21 | 2024-08-24 | SAFUAN//BIN YUSOFF/6800000178 | 2025-02-18: 2024-08-22; 2025-02-28: 2024-08-31; 2025-03-10: 2024-08-21; 2025-03-10: 2024-08-22 |  |  | 2024-09-09 | 2024-10-09 | 2024-09-09 | 2024-09-09 | ASTI//GANIS PUTRIANI/6237001358
4578C_HU_2 | TamanSg Bakap | DU00006714614 | Northern | Penang | 5.237069 | 100.497144 | [7 empty] | 04. Pending DO |  | TSS+AA+TI |  | 23G_2+0_110M_256QAM_EPLA NE_4578C New 23G_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 44-13945) x1. New ISM8 x2. New XMC_3E, Sub A&B_Lo x2. New IF cables with suitable length and type x2 RUN. FE_P00360 New 23G_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 44-23945) x1. New ISM8 x2. New XMC_3E, Sub A&B_Hi x2. New IF cables with suitable length and type x2 RUN. New CAT6 cable x1. | MW Parallel Link | Build new HW MW Parallel Link 4578C-P00360, 23G_2+0_112MHZ_256QAM_EPLA_448M. Later, combine existing HW MW Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA_448M with new HW MW Parallel Link 4578C-P00360, 23G_2+0_112MHZ_256QAM_EPLA_1556M. Become HW MW Link 4578C-P00360, 15G&23G_4+0_28MHZ&112MHZ_512QAM&256QAM_EPLA_2004M. Site Impacted : 4578C. NE_4578C 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-13945). Insert ISM8 x2 into slot 03 & 04. 3.Lay new IF cables with suitable length and type x2 RUN from new XMC_3E, Sub A&B_Lo x2 to existing RTN910AF(RTN01, NEID 44-13945) at ISM8 slot 03(Port 1) and slot 04(Port 1). 4.Install new XMC_3E, Sub A&B_Lo x2. Build new HW MW Parallel Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA. 5.Later, combine existing HW MW Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA_448M with new HW MW Parallel Link 4578C-P00360, 23G_2+0_112MHZ_256QAM_EPLA_1556M. Become HW MW Link 4578C-P00360, 15G&23G_4+0_28MHZ&112MHZ _512QAM&256QAM_EPLA_2004M. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic 4578C to new HW MW Link 4578C-P00360, 15G&23G_4+0_28MHZ&112MHZ _512QAM&256QAM_EPLA_2004M. FE_P00360 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-23945). Insert ISM8 x2 into slot 03 & 04. 3.Lay new IF cables with suitable length and type x2 RUN from new XMC_3E, Sub A&B_Lo x2 to existing RTN910AF(RTN01, NEID 44-23945) at ISM8 slot 03(Port 1) and slot 04(Port 1). 4.Install new XMC_3E, Sub A&B_Hi x2. Build new HW MW Parallel Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA. 5.Later, combine existing HW MW Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA_448M with new HW MW Parallel Link 4578C-P00360, 23G_2+0_112MHZ_256QAM_EPLA_1556M. Become HW MW Link 4578C-P00360, 15G&23G_4+0_28MHZ&112MHZ _512QAM&256QAM_EPLA_2004M. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Enable port 8-EM6-2 of existing RTN910AF(RTN01, NEID 44-23945). 8.Request new port 1G(Electrical) of existing PTN/Cisco from ZTE IPRAN Team. 9.Perform LAG for port 8-EM6-1 & 8-EM6-2 of existing RTN910AF(RTN01, NEID 44-23945) and 2x 1G(Electrical) of PTN/Cisco. 10.Migrate traffic 4578C to 2x 1G LAG at PTN/Cisco. | Build new HW MW Parallel Link 4578C-P00360, 23G_2+0_112MHZ_256QAM_EPLA_448M. Later, combine existing HW MW Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA_448M with new HW MW Parallel Link 4578C-P00360, 23G_2+0_112MHZ_256QAM_EPLA_1556M. Become HW MW Link 4578C-P00360, 15G&23G_4+0_28MHZ&112MHZ_512QAM&256QAM_EPLA_2004M. Site Impacted : 4578C. NE_4578C 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-13945). Insert ISM8 x2 into slot 03 & 04. 3.Lay new IF cables with suitable length and type x2 RUN from new XMC_3E, Sub A&B_Lo x2 to existing RTN910AF(RTN01, NEID 44-13945) at ISM8 slot 03(Port 1) and slot 04(Port 1). 4.Install new XMC_3E, Sub A&B_Lo x2. Build new HW MW Parallel Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA. 5.Later, combine existing HW MW Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA_448M with new HW MW Parallel Link 4578C-P00360, 23G_2+0_112MHZ_256QAM_EPLA_1556M. Become HW MW Link 4578C-P00360, 15G&23G_4+0_28MHZ&112MHZ _512QAM&256QAM_EPLA_2004M. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Migrate traffic 4578C to new HW MW Link 4578C-P00360, 15G&23G_4+0_28MHZ&112MHZ _512QAM&256QAM_EPLA_2004M. | Build new HW MW Parallel Link 4578C-P00360, 23G_2+0_112MHZ_256QAM_EPLA_448M. Later, combine existing HW MW Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA_448M with new HW MW Parallel Link 4578C-P00360, 23G_2+0_112MHZ_256QAM_EPLA_1556M. Become HW MW Link 4578C-P00360, 15G&23G_4+0_28MHZ&112MHZ_512QAM&256QAM_EPLA_2004M. Site Impacted : 4578C. FE_P00360 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-23945). Insert ISM8 x2 into slot 03 & 04. 3.Lay new IF cables with suitable length and type x2 RUN from new XMC_3E, Sub A&B_Lo x2 to existing RTN910AF(RTN01, NEID 44-23945) at ISM8 slot 03(Port 1) and slot 04(Port 1). 4.Install new XMC_3E, Sub A&B_Hi x2. Build new HW MW Parallel Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA. 5.Later, combine existing HW MW Link 4578C-P00360, 15G_2+0_28MHZ_512QAM_EPLA_448M with new HW MW Parallel Link 4578C-P00360, 23G_2+0_112MHZ_256QAM_EPLA_1556M. Become HW MW Link 4578C-P00360, 15G&23G_4+0_28MHZ&112MHZ _512QAM&256QAM_EPLA_2004M. 6.Re-use existing xC Vlan DCN & Vlan Services. 7.Enable port 8-EM6-2 of existing RTN910AF(RTN01, NEID 44-23945). 8.Request new port 1G(Electrical) of existing PTN/Cisco from ZTE IPRAN Team. 9.Perform LAG for port 8-EM6-1 & 8-EM6-2 of existing RTN910AF(RTN01, NEID 44-23945) and 2x 1G(Electrical) of PTN/Cisco. 10.Migrate traffic 4578C to 2x 1G LAG at PTN/Cisco. | XMC_3E | MAC | 23G | 23G_0.6M(MAC)+OMT x1 | 23G_0.6M(MAC)+OMT x1 | GTSB | SQ202604060636-GTSB | GTSB | SQ202604060630-GTSB // SQ202604060633-GTSB // SQ202604280656-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040927 |  | 2026-04-10 | 2026-04-23 | Completed | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604030176-GTSB
4363C_HU | MydinMeru (REL) | DU00006714615 | Northern | Perak | 4.670154 | 101.075942 | [7 empty] | 04. Pending DO |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M_256QAM_EPLA_1556M NE_4363C New 23G_0.3M(MAC)+OMT x1. New RTN910AF(RTN01). New XMC_3E, Sub A&B_Lox2. New IF cables with suitable length and type x2 RUN. FE_4474C/A00951 New 23G_0.6M(MAC)+OMT x1. New RTN910AF(RTN01). New XMC_3E, Sub A&B_Hi x2. New IF cables with suitable length and type x2 RUN. | MW Swap | Existing SM MW Link 4363C-4474C, 23G_1+0_112MHZ_512QAM_718M. Swap new HW MW Link 4363C-4474C, 23G_2+0_112MHZ_256QAM_1556M. Later, decom existing SM MW Link 4363C-4474C, 23G_1+0_112MHZ_512QAM_718M. Site Impacted : 4363C. NE_4363C 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub A&B_Lo x2. Build new HW MW Link 4363C-4474C, 23G_2+0_112MHZ_256QAM_1556M. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to BBU(4363C). 5.Re-use existing xC Vlan DCN & Vlan Services. 6.Migrate traffic 4363C to new HW MW Link 4363C-4474C, 23G_2+0_112MHZ_256QAM_1556M. 7.Later, decom existing SM MW Link 4363C-4474C, 23G_1+0_112MHZ_512QAM_718M. FE_4474C/A00951 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub A&B_Hi x2. Build new HW MW Link 4363C-4474C, 23G_2+0_112MHZ_256QAM_1556M. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing port of PTN/Cisco at A00951. 5.Re-use existing xC Vlan DCN & Vlan Services. 6.Migrate traffic 4363C to existing PTN/Cisco port at A00951. 7.Later, decom existing SM MW Link 4363C-4474C, 23G_1+0_112MHZ_512QAM_718M. | Existing SM MW Link 4363C-4474C, 23G_1+0_112MHZ_512QAM_718M. Swap new HW MW Link 4363C-4474C, 23G_2+0_112MHZ_256QAM_1556M. Later, decom existing SM MW Link 4363C-4474C, 23G_1+0_112MHZ_512QAM_718M. Site Impacted : 4363C. NE_4363C 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub A&B_Lo x2. Build new HW MW Link 4363C-4474C, 23G_2+0_112MHZ_256QAM_1556M. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to BBU(4363C). 5.Re-use existing xC Vlan DCN & Vlan Services. 6.Migrate traffic 4363C to new HW MW Link 4363C-4474C, 23G_2+0_112MHZ_256QAM_1556M. 7.Later, decom existing SM MW Link 4363C-4474C, 23G_1+0_112MHZ_512QAM_718M. | Existing SM MW Link 4363C-4474C, 23G_1+0_112MHZ_512QAM_718M. Swap new HW MW Link 4363C-4474C, 23G_2+0_112MHZ_256QAM_1556M. Later, decom existing SM MW Link 4363C-4474C, 23G_1+0_112MHZ_512QAM_718M. Site Impacted : 4363C. FE_4474C/A00951 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN01). 3.Install new XMC_3E, Sub A&B_Hi x2. Build new HW MW Link 4363C-4474C, 23G_2+0_112MHZ_256QAM_1556M. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing port of PTN/Cisco at A00951. 5.Re-use existing xC Vlan DCN & Vlan Services. 6.Migrate traffic 4363C to existing PTN/Cisco port at A00951. 7.Later, decom existing SM MW Link 4363C-4474C, 23G_1+0_112MHZ_512QAM_718M. | XMC-3E | MAC+OMT | 23G | 23G_0.3M(MAC)+OMT x1 | 23G_0.6M(MAC)+OMT x1 | GTSB | SQ202604060636-GTSB | GTSB | SQ202604060630-GTSB // SQ202604060633-GTSB // SQ202604280656-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040929 |  | 2026-04-10 | 2026-04-23 | Completed | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-26 | 2026-04-30 | 2026-04-26 | 2026-04-30 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-04-26 | 2026-04-30 | 2026-04-26 |  | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-02 | 2026-04-26 | 2026-04-30 | 2026-04-26 |  | HAMZAH BIN ABDUL MUTALIF6799000301 | 2025-02-18: 2026-04-26; 2025-02-28: 2026-04-30; 2025-03-10: 2026-04-26; 2025-03-10: 2026-04-30 | [7 empty] | GTSB | SQ202604030176-GTSB
B01348_HU | B062B_B01348OD_T3_PT7SGPJG | DU00006714616 | Central | Selangor | 3.708600 | 101.026600 | [7 empty] | 01. Pending Planning |  | TSS+AA+TI |  | 13G_4+0_28M_512QAM_CA NE_1120K/B01348 New 13G_1.2M(MDD) x1. New RTN910AF(RTN04) x1. New ISM8 x2. New XMC_5D Pro, Sub B_Lo x1. New IF cables with suitable length and type x2 RUN. New CAT6 cable x1. FE_4591A New 13G_1.2M(MDD) x1. New RTN910AF(RTN01) x1. New ISM8 x2. New XMC_5D Pro, Sub B_Hi x1. New IF cables with suitable length and type x2 RUN. New CAT6 cable x1. | MW Parallel Link | Build new HW MW Parallel Link 1120K/B01348-4591A, 13G_4+0_28MHZ_512QAM_CA. Site Impacted : 1771C. NE_1120K/B01348 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub B_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Lo x1 to ISM8 slot 03(Port 1) and slot 04(Port 1) of new RTN910AF(RTN04). 5.Build new HW MW Parallel Link 1120K/B01348-4591A, 13G_4+0_28MHZ_512QAM_CA. 6.Disconnect/remove existing cascading in between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 33-28065) and port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-34813). 7.Perform new cascading in between port 8-EM6-1 of new RTN910AF(RTN04) and port 8-EM6-1 of existing RTN910AF(RTN03, NEID 33-28065). 8.Request new xC Vlan DCN and re-use existing Vlan Services from ZTE IPRAN team. 9.Migrate 1771C into new HW MW Parallel Link 1120K/B01348-4591A, 13G_4+0_28MHZ_512QAM_CA. FE_4591A 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Hi x1 to ISM8 slot 03(Port 1) and slot 04(Port 1) of new RTN910AF(RTN01). 5.Build new HW MW Parallel Link 1120K/B01348-4591A, 15G_4+0_28MHZ_512QAM_CA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN01) and also port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-34814). 7.Perform new cascading in between port 8-EM6-1 of new RTN910AF(RTN01) and port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-34814). 8.Request new xC Vlan DCN and re-use existing Vlan Services from ZTE IPRAN team. 9.Traffic 1771C still using existing port at PTN/Cisco(B01049). | Build new HW MW Parallel Link 1120K/B01348-4591A, 13G_4+0_28MHZ_512QAM_CA. Site Impacted : 1771C. NE_1120K/B01348 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub B_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Lo x1 to ISM8 slot 03(Port 1) and slot 04(Port 1) of new RTN910AF(RTN04). 5.Build new HW MW Parallel Link 1120K/B01348-4591A, 13G_4+0_28MHZ_512QAM_CA. 6.Disconnect/remove existing cascading in between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 33-28065) and port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-34813). 7.Perform new cascading in between port 8-EM6-1 of new RTN910AF(RTN04) and port 8-EM6-1 of existing RTN910AF(RTN03, NEID 33-28065). 8.Request new xC Vlan DCN and re-use existing Vlan Services from ZTE IPRAN team. 9.Migrate 1771C into new HW MW Parallel Link 1120K/B01348-4591A, 13G_4+0_28MHZ_512QAM_CA. | Build new HW MW Parallel Link 1120K/B01348-4591A, 13G_4+0_28MHZ_512QAM_CA. Site Impacted : 1771C. FE_4591A 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01) and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub B_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN from new XMC_5D Pro, Sub B_Hi x1 to ISM8 slot 03(Port 1) and slot 04(Port 1) of new RTN910AF(RTN01). 5.Build new HW MW Parallel Link 1120K/B01348-4591A, 13G_4+0_28MHZ_512QAM_CA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN01) and also port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-34814). 7.Perform new cascading in between port 8-EM6-1 of new RTN910AF(RTN01) and port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-34814). 8.Request new xC Vlan DCN and re-use existing Vlan Services from ZTE IPRAN team. 9.Traffic 1771C still using existing port at PTN/Cisco(B01049). | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD) x1 | 13G_1.2M(MDD) x1 | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042022 |  | 2026-04-21 | 2026-04-23 | Completed | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604030172-GTSB
7059P_HU | KG.BUKIT BESI | DU00006714617 | Sabah | Sabah | 5.982740 | 117.523300 | [9 empty] | TSS+AA+TI |  |  | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 7059P-7150A FROM 13G_1+0_1.2M/1.2M_MDD_28MHZ_512QAM TO HUAWEI_13G_4+0_1.2M/1.2M_MDD_28MHZ_256QAM-V_128QAM-H_746MBPS_XMC5D_SUB_A_LINK_10.7KM INSTALL NEW ISM8 CARD. LAY NEW HORIZONTAL CABLE. CONFIGURE 4+0 CA. V-256QAM. H-128QAM IMPACTED: 7059P | 1. INSTALL NEW ISM8 AT SLOT 4 EXISTING RTN910 2. REUSE EXISTING 13G 1.2M MDD ANTENNA 3. LAY IF CABLE FOR HORIZONTAL SLOT 4 4. CONFIGURE LINK 13G 4+0 28MHZ WITH CA. V-256QAM. H-128QAM | 1. INSTALL NEW ISM8 AT SLOT 4 EXISTING RTN910 2. REUSE EXISTING 13G 1.2M MDD ANTENNA 3. LAY IF CABLE FOR HORIZONTAL SLOT 4 4. CONFIGURE LINK 13G 4+0 28MHZ WITH CA. V-256QAM. H-128QAM | XMC5D | MDD | 13G | 1.2 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604030180-GCI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
7210R_HU_1 | Kg Senang Hati | DU00006714618 | Sabah | Sabah | 4.506467 | 118.573314 | [9 empty] | TSS+AA+TI |  | 3X ISM8 CARD 2X 15G 0.6M MDD ANTENNA 1x ODU 15G XMC5DPRO SUB B HI 1x ODU 15G XMC5DPRO SUB B LO 2x 1G SFP | MW Parallel Link | MW PARALLEL LINK 7210R-7209A WITH HUAWEI_15G_2+0_0.6M/0.6M_MDD_28MHZ_256QAM_400MBPS_XMC5D_SUB_A_LINK_4.86KM EPLA WITH EXISTING 18G 1+0 IMPACTED: 7210R | 1. INSTALL NEW 1PCS ISM8 CARD AT SLOT 3 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 2+0 28MHZ 256QAM AT SLOT 3 5. EPLA SLOT 7 AND SLOT 3 | 1. INSTALL NEW 2PCS ISM8 CARD AT SLOT 3 & 4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 2+0 28MHZ 256QAM AT SLOT 3 5. SHIFT IF CABLE FROM EXISTING LINK SLOT 7-2 TO SLOT 4-1 6. EPLA SLOT 3 AND SLOT 4 7. PATCH TO NEW CP PORT AND DO PORT LAG 2G | XMC5D | MDD | 15G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604030180-GCI | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00616_HU_1 | Q141A_Q00616OD_CB_TMSEBANGAN | DU00006714619 | Sarawak | Sarawak | 1.557000 | 110.772200 | [9 empty] | TSS+AA+TI |  | 4X 1G 1KM SFP 1X RTN910A 2X 15G 1.2M DP ANTENNA 1x ODU 15G XMC5D SUB A HI 1x ODU 15G XMC5D SUB A LO | MW Parallel Link | MW PARALLEL LINK Q00616-9350A WITH HUAWEI_15G_2+0_1.2M/1.2M_MDD_28MHZ_512QAM_448MBPS_XMC5D_SUB_A_LINK_6.1KM EPLA WITH EXISTING LINK 13G 4+0 1.2/1.2 IMPACTED: Q00616 | 1. REUSE EXISTING IDU 9270P RTN910A RTN01 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. EPLA WITH EXISTING LINK 13G 4+0 SLOT 3 & 4 | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. TRANSFER ISM8 SLOT 3 & 4 FROM EXISTING 9350A RTN04 TO NEW IDU RTN910A 6. EPLA NEW LINK WITH EXISTING LINK 13G 4+0 SLOT 3 & 4 TO BECOME 6+0 7. DO PORT LAG 2G TO CP PORT | XMC5D | MDD | 15G | 1.2 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604030185-GCI | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
4782D_HU | KampungPadang Kunyit | DU00006714620 | Northern | Kedah | 6.178331 | 100.437750 | [7 empty] | 04. Pending DO | 17/4:TI AND MOS 16/4: MC | TSS+AA+TI | L1+ATP+PAC | 1X RTN910A 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB B HI 1x ODU 18G XMC3E SUB B LO | MW Parallel Link | MW PARALLEL LINK 4782D-4678A WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM_449MBPS_XMC3_SUB_B_LINK_4.1KM EPLA WITH EXISTING LINK 18G 1+0 0.6M/0.6M TO BECOME 2+0 IMPACTED: 4782D | 1. REUSE EXISTING IDU 4782D RTN910A RTN01 SLOT 7 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3 56MHZ SUB B 4. CONFIGURE LINK 18G 1+0 56MHZ 512QAM 5. EPLA NEW LINK WITH EXISTING LINK 18G 1+0 SLOT 7-1 TO BECOME 2+0 | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3 56MHZ SUB B 4. CONFIGURE LINK 18G 1+0 56MHZ 512QAM 5. SHIFT CABLE FROM ISM8 SLOT 3 FROM EXISTING 4678A RTN12 TO NEW IDU RTN910A 6. EPLA NEW LINK WITH EXISTING LINK 18G 1+0 7-1 TO BECOME 2+0 7. PATCH TO NEW CP PORT | XMC3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202605050374-GCI | GCI | SQ202604200146-GCI // SQ202604200170-GCI // SQ202604280634-GCI |  |  | Ongoing | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-06 | 2026-05-07 | 2026-05-06 | 2026-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-08 | 2026-05-09 | 2026-05-08 |  | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. |  | Assigned | Ongoing | To be Submitted |  | DOWMY26040918 |  | 2026-04-10 | 2026-04-16 | Completed | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-17 | 2026-04-30 | 2026-04-17 | 2026-05-03 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-04-17 | 2026-04-30 | 2026-04-17 | 2026-05-03 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-22 | 2026-04-17 | 2026-04-30 | 2026-04-17 | 2026-05-03 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-02-18: 2026-04-17; 2025-02-28: 2026-04-30; 2025-03-10: 2026-04-17; 2025-03-10: 2026-04-21 | [7 empty] | GCI | SQ202604030175-GCI | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
2833A_IPR | First WorldHotel Indoor | DU00006714621 | Central | Pahang | 3.425396 | 101.794359 | [9 empty] | TSS+TI |  | Perform LAG at Ibeam & HW IDU. NE_2833A New CAT6 cable x1. | MW IDU Patching | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(2235E). BEFORE START DEPLOY TEAM TO SITE.**** Perform new patching at new port of IBeam and at new port at existing HW IDU/RTN and do LAG. Site Impacted: 3459B, 3322B & 3459C currently using IBeam port(GE 0/2/19). EB 2235E currently using IBeam port(GE 0/2/21) NE_2833A 1.Request new port 1G(Electrical) of IBeam from ZTE IPRAN Team. Suggest use port GE 0/2/4. 2.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-26533). 3.Patching in between port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-26533) and new port 1G(Electrical) of IBeam. 4.Perform LAG for port 8-EM6-1 & 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-26533) and port GE 0/2/19 & GE 0/2/4 of existing IBeam. Please do not touch port 8-EM6-5 of existing RTN910AF(RTN01, NEID 9-26533) port GE 0/2/21 of IBeam. 5.Migrate Traffics 3459B, 3322B & 3459C into LAG GE 0/2/19 & GE 0/2/4 of existing IBeam. | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(2235E). BEFORE START DEPLOY TEAM TO SITE.**** Perform new patching at new port of IBeam and at new port at existing HW IDU/RTN and do LAG. Site Impacted: 3459B, 3322B & 3459C currently using IBeam port(GE 0/2/19). EB 2235E currently using IBeam port(GE 0/2/21) NE_2833A 1.Request new port 1G(Electrical) of IBeam from ZTE IPRAN Team. Suggest use port GE 0/2/4. 2.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-26533). 3.Patching in between port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-26533) and new port 1G(Electrical) of IBeam. 4.Perform LAG for port 8-EM6-1 & 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-26533) and port GE 0/2/19 & GE 0/2/4 of existing IBeam. Please do not touch port 8-EM6-5 of existing RTN910AF(RTN01, NEID 9-26533) port GE 0/2/21 of IBeam. 5.Migrate Traffics 3459B, 3322B & 3459C into LAG GE 0/2/19 & GE 0/2/4 of existing IBeam. | [6 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
4005P_HU | KAMPUNGPERMATANG RAJA | DU00006714622 | Northern | Perak | 4.548362 | 100.669786 | [9 empty] | AA |  |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 4005P-4704B ZTE MW 13G_2+0_1.2M/1.2M_MDD_28MHZ_512QAM TO 13G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_SUB A&B_WITH CA_896MBPS IMPACTED SITE: 4005P | MW REMOTE UPGRADE LINK 4005P-4704B ZTE MW 13G_2+0_1.2M/1.2M_MDD_28MHZ_512QAM TO 13G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_SUB A&B_WITH CA_896MBPS IMPACTED SITE: 4005P | MW REMOTE UPGRADE LINK 4005P-4704B ZTE MW 13G_2+0_1.2M/1.2M_MDD_28MHZ_512QAM TO 13G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_SUB A&B_WITH CA_896MBPS IMPACTED SITE: 4005P | XMC5D | MDD | 13G | 1.2 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604030175-GCI | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
1196B_AD | BukitBelimbing | DU00006714623 | Central | Selangor | 3.377529 | 101.268375 | [9 empty] | TSS+TI | L1+ATP+PAC | ETN Cat x Cable x1 | BBU Patching | BBU Patching to New PTN. NE_1196B 1.BBU_1196B direct patching to New PTN Fiber. 2.PTN Fiber port allocate by OPS Team. 3.Decom MW link (1196B-1153A) refer to DU ID 1196B_Decom | BBU Patching to New PTN. NE_1196B 1.BBU_1196B direct patching to New PTN Fiber. 2.PTN Fiber port allocate by OPS Team. 3.Decom MW link (1196B-1153A) refer to DU ID 1196B_Decom | [6 empty] | GCI | SQ202604100646-GCI | GCI | SQ202604100645-GCI | 2026-04-15 | 2026-04-14 | Completed | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26040639 |  | 2026-04-11 | 2026-04-11 | Completed | 2026-04-08 | 2026-04-11 | 2026-04-08 | 2026-04-11 | Ragunalan//A/L L.Krisnan6000006720 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-08 | 2026-04-15 | 2026-04-08 | 2026-04-11 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-04-08 | 2026-04-15 | 2026-04-08 | 2026-04-11 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-08 | 2026-04-15 | 2026-04-08 | 2026-04-11 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-02-18: 2026-04-08; 2025-02-28: 2026-04-15; 2025-03-10: 2026-04-08; 2025-03-10: 2026-04-08 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202604030167-GCI
2680A17_HU | pBTSHartalega Hostel 2 | DU00006714624 | Central | Selangor | 2.809768 | 101.686240 | [9 empty] | TSS+AA+TI |  | 23G_2+0_112M. NE_2680A_17 23G_DP_0.3M(MAC) x1. RTN910A_RTN01 x1. ISM8 x1. FE_1155B. 23G_DP_0.3M(MAC) x1. ISM8 x1. XMC_3E , Sub A & B_Lo x1.. | MW Parallel Link | Existing link 23G_1+0_56M. Install parallel link 23G_2+0_112M. Site Impacted : 2047E , 2680A. NE_2680A_17 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing RTN910A_RTN01 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW link. FE_1155B. 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing RTN950_RTN02 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom existing MW link. | Existing link 23G_1+0_56M. Install parallel link 23G_2+0_112M. Site Impacted : 2047E , 2680A. NE_2680A_17 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing RTN910A_RTN01 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW link. | Existing link 23G_1+0_56M. Install parallel link 23G_2+0_112M. Site Impacted : 2047E , 2680A. FE_1155B. 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing RTN950_RTN02 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom existing MW link. | XMC_3E | MAC | 23G | 0.3 | 0.3 | GTSB | SQ202604060610-GTSB | GTSB | SQ202604060602-GTSB // SQ202604060606-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040307 |  | 2026-04-04 | 2026-04-23 | Completed | 2026-04-03 | 2026-04-04 | 2026-04-03 | 2026-04-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-04-30 | 2026-04-23 |  | MHD FAKHRON NASIRIE BIN MUSTAFFA6000075524 | GTSB TI | 2026-04-23 | 2026-04-30 | 2026-04-23 |  | MHD FAKHRON NASIRIE BIN MUSTAFFA6000075524 | GTSB TI | [7 empty] | 2026-04-23 | 2026-04-30 | 2026-04-23 |  | MHD FAKHRON NASIRIE BIN MUSTAFFA6000075524 | 2025-02-18: 2026-04-23; 2025-02-28: 2026-04-30; 2025-03-10: 2026-04-23; 2025-03-10: 2026-04-23 | [7 empty] | GCI | SQ202604030167-GCI | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | CHEONG/SENG/WAH/7018000306
9009R_HU | KAMPUNGPENGALEH | DU00006714625 | Sarawak | Sarawak | 4.830200 | 115.445900 | [9 empty] | TSS+AA+TI |  | 15G_2+0_28M. NE_9009R 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D Pro , Sub A_Hi x1. FE_9659B 15G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub A-Lo x1. | MW Parallel Link | Existing link 15G_2+0_28M Install pararllel link 15G_2+0_28M. Site Impacted : 9009R. NE_9009R 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D Pro , Sub A_Hi 4.Create service cross connect and EPLA with existing link. 5.Migrate traffic to new parallel link. 6.No decom MW link. FE_9659B 1.Install new 15G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A-Lo. 4.Create service cross connect and EPLA existing MW link. 5.Create new Iband DCN and Enable GE1 , patching to existing NEC link. 6.Migrate service to new parallel link. 7.No decom MW link. | Existing link 15G_2+0_28M Install pararllel link 15G_2+0_28M. Site Impacted : 9009R. NE_9009R 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D Pro , Sub A_Hi 4.Create service cross connect and EPLA with existing link. 5.Migrate traffic to new parallel link. 6.No decom MW link. | Existing link 15G_2+0_28M Install pararllel link 15G_2+0_28M. Site Impacted : 9009R. FE_9659B 1.Install new 15G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A-Lo. 4.Create service cross connect and EPLA existing MW link. 5.Create new Iband DCN and Enable GE1 , patching to existing NEC link. 6.Migrate service to new parallel link. 7.No decom MW link. | XMC_5D Pro | MDD | 15G | 1.2 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604030185-GCI | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | CHEONG/SENG/WAH/7018000306
7208R_HU_1 | Kg. Kabogan | DU00006714626 | Sabah | Sabah | 4.419182 | 118.611956 | [9 empty] | TSS+AA+TI |  |  | MW Parallel Link | MW NEW PARALLEL LINK 7208R-7207A WITH HUAWEI_15G_2+0_0.6M/1.2M_MDD_28MHZ_256QAM_400MBPS_XMC5D_SUB_B_LINK_6.90KM EPLA WITH EXISTING 15G 4+0 SLOT 3&4 TO BECOME 6+0 LINK IMPACTED: 7208R | 1. REUSE EXISTING RTN910 RNT01 SLOT 7 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 256QAM 5. EPLA WITH EXISTING 15G 4+0 SLOT 3&4 TO BECOME 6+0 LINK | 1. REUSE EXISTING RTN910 RNT03 SLOT 7 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 2+0 28MHZ 256QAM 5. EPLA WITH EXISTING 15G 4+0 SLOT 3&4 TO BECOME 6+0 LINK 6. PATCH 1G LAG PORT IDU TO IDU RTN03-RTN01 | XMC5D | MDD | 15G | 0.6 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604030180-GCI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
1132D_HU | KgPadang Jawa | DU00006714627 | Central | Selangor | 3.047708 | 101.491404 | [7 empty] | 04. Pending DO |  | TSS+AA+TI+Dismantle |  | 23G_2+0_112M_256QAM_EPLA_1556M NE_1132D New 23G_0.3M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 9-35770). New XMC_3E, Sub A&B_Lo x2. New ISM8 x1. New IF cables with suitable length and type x2 RUN. FE_1073A New 23G_0.3M(MAC)+OMT x1. Re-use existing RTN910AF(RTN10, NEID 9-35771). New XMC_3E, Sub A&B_Hi x2. New ISM8 x1. New IF cables with suitable length and type x2 RUN. | MW Swap | Existing HW MW Link 1132D-1073A, 23G_1+0_56MHZ_512QAM_450M. Swap existing HW MW Link 1132D-1073A, 23G_1+0_56MHZ_512QAM_450M(ODU & Antenna ONLY) to new HW MW Link 1132D-1073A, 23G_2+0_110MHZ_256QAM_EPLA_1556M. Anyway, do not decom existing RTN910AF(RTN01, NEID 9-35770) at 1132D and existing RTN910AF(RTN10, NEID 9-35771) at 1073A. Site Impacted : 1132D. NE_1132D 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-35770) and insert new ISM8 x1 into slot 03. 3.Install new XMC_3E, Sub A&B_Lo x2 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN01, NEID 9-35770) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 1132D-1073A, 23G_2+0_110MHZ_256QAM_EPLA_1556M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 1132D to new HW MW Link 1132D-1073A, 23G_2+0_110MHZ_256QAM_EPLA_1556M. 6.Later, decom existing HW MW Link 1132D-1073A, 23G_1+0_56MHZ_512QAM_450M.(ODU & Antenna ONLY). FE_1073A 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN10, NEID 9-35771) and insert new ISM8 x1 into slot 03. 3.Install new XMC_3E, Sub A&B_Hi x2 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN10, NEID 9-35771) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 1132D-1073A, 23G_2+0_110MHZ_256QAM_EPLA_1556M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 1132D to to existing port at IBeam. 6.Later, decom existing HW MW Link 1132D-1073A, 23G_1+0_56MHZ_512QAM_450M.(ODU & Antenna ONLY). | Existing HW MW Link 1132D-1073A, 23G_1+0_56MHZ_512QAM_450M. Swap existing HW MW Link 1132D-1073A, 23G_1+0_56MHZ_512QAM_450M(ODU & Antenna ONLY) to new HW MW Link 1132D-1073A, 23G_2+0_110MHZ_256QAM_EPLA_1556M. Anyway, do not decom existing RTN910AF(RTN01, NEID 9-35770) at 1132D and existing RTN910AF(RTN10, NEID 9-35771) at 1073A. Site Impacted : 1132D. NE_1132D 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-35770) and insert new ISM8 x1 into slot 03. 3.Install new XMC_3E, Sub A&B_Lo x2 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN01, NEID 9-35770) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 1132D-1073A, 23G_2+0_110MHZ_256QAM_EPLA_1556M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 1132D to new HW MW Link 1132D-1073A, 23G_2+0_110MHZ_256QAM_EPLA_1556M. 6.Later, decom existing HW MW Link 1132D-1073A, 23G_1+0_56MHZ_512QAM_450M.(ODU & Antenna ONLY). | Existing HW MW Link 1132D-1073A, 23G_1+0_56MHZ_512QAM_450M. Swap existing HW MW Link 1132D-1073A, 23G_1+0_56MHZ_512QAM_450M(ODU & Antenna ONLY) to new HW MW Link 1132D-1073A, 23G_2+0_110MHZ_256QAM_EPLA_1556M. Anyway, do not decom existing RTN910AF(RTN01, NEID 9-35770) at 1132D and existing RTN910AF(RTN10, NEID 9-35771) at 1073A. Site Impacted : 1132D. FE_1073A 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN10, NEID 9-35771) and insert new ISM8 x1 into slot 03. 3.Install new XMC_3E, Sub A&B_Hi x2 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN10, NEID 9-35771) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 1132D-1073A, 23G_2+0_110MHZ_256QAM_EPLA_1556M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 1132D to to existing port at IBeam. 6.Later, decom existing HW MW Link 1132D-1073A, 23G_1+0_56MHZ_512QAM_450M.(ODU & Antenna ONLY). | XMC-3E | MAC+OMT | 23G | 23G_0.3M(MAC)+OMT x1 | 23G_0.3M(MAC)+OMT x1 | GCI |  | GCI | SQ202604150067-GCI // SQ202604150085-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040924 |  | 2026-04-10 | 2026-04-11 | Completed | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-11 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604030172-GTSB
K00063_HU | K004A_K00063OD_TMNJAYA | DU00006714628 | Northern | Kedah | 6.136800 | 100.392300 | [9 empty] | AA | PAC |  | MW Remote Upgrade | Existing link 18G_1+0_56M Software upgrade 18G_1+0_112M Site Impacted : K00063 | Existing link 18G_1+0_56M Software upgrade 18G_1+0_112M Site Impacted : K00063 | Existing link 18G_1+0_56M Software upgrade 18G_1+0_112M Site Impacted : K00063 | XMC_3E | MAC | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-26 | 2026-04-27 | 2026-04-27 | 2026-04-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-27 | [20 empty] | GCI | SQ202604030175-GCI | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-04 | CHEONG/SENG/WAH/7018000306
9995A_HU | PolarLink Samajaya | DU00006714629 | Sarawak | Sarawak | 1.534751 | 110.393000 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M_256QAM_EPLA_1556M NE_9995A New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 148-47033). New XMC_5D Pro, Sub A_Hi x1. New ISM8 x1. New IF cables with suitable length and type x2 RUN. FE_9061B New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 148-26855). New XMC_5D Pro, Sub A_Lo x1. New ISM8 x1. New IF cables with suitable length and type x2 RUN. | MW Swap | Existing HW MW Link 9995A-9061B, 18G_1+0_56MHZ_512QAM_450M. Swap existing HW MW Link 9995A-9061B, 18G_1+0_56MHZ_512QAM_450M(ODU & Antenna ONLY) to new HW MW Link 9995A-9061B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. Anyway, do not decom existing RTN910AF(RTN01, NEID 148-47033) at 9995A and existing RTN910AF(RTN02, NEID 148-26855) at 9061B. Site Impacted : 9995A. NE_9995A 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 148-47033) and insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN(IF1 & IF2) and terminate to existing RTN910AF(RTN01, NEID 148-47033) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 9995A-9061B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 9995A to new HW MW Link 9995A-9061B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. 6.Later, decom existing HW MW Link 9995A-9061B, 18G_1+0_56MHZ_512QAM_450M.(ODU & Antenna ONLY). FE_9061B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 148-26855) and insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN(IF1 & IF2) and terminate to existing RTN910AF(RTN02, NEID 148-26855) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 9995A-9061B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 9995A to existing port at IBeam(CP 9999A). 6.Later, decom existing HW MW Link 9995A-9061B, 18G_1+0_56MHZ_512QAM_450M.(ODU & Antenna ONLY). | Existing HW MW Link 9995A-9061B, 18G_1+0_56MHZ_512QAM_450M. Swap existing HW MW Link 9995A-9061B, 18G_1+0_56MHZ_512QAM_450M(ODU & Antenna ONLY) to new HW MW Link 9995A-9061B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. Anyway, do not decom existing RTN910AF(RTN01, NEID 148-47033) at 9995A and existing RTN910AF(RTN02, NEID 148-26855) at 9061B. Site Impacted : 9995A. NE_9995A 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 148-47033) and insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN(IF1 & IF2) and terminate to existing RTN910AF(RTN01, NEID 148-47033) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 9995A-9061B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 9995A to new HW MW Link 9995A-9061B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. 6.Later, decom existing HW MW Link 9995A-9061B, 18G_1+0_56MHZ_512QAM_450M.(ODU & Antenna ONLY). | Existing HW MW Link 9995A-9061B, 18G_1+0_56MHZ_512QAM_450M. Swap existing HW MW Link 9995A-9061B, 18G_1+0_56MHZ_512QAM_450M(ODU & Antenna ONLY) to new HW MW Link 9995A-9061B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. Anyway, do not decom existing RTN910AF(RTN01, NEID 148-47033) at 9995A and existing RTN910AF(RTN02, NEID 148-26855) at 9061B. Site Impacted : 9995A. FE_9061B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 148-26855) and insert new ISM8 x1 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN(IF1 & IF2) and terminate to existing RTN910AF(RTN02, NEID 148-26855) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 9995A-9061B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 9995A to existing port at IBeam(CP 9999A). 6.Later, decom existing HW MW Link 9995A-9061B, 18G_1+0_56MHZ_512QAM_450M.(ODU & Antenna ONLY). | XMC-5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | Allstar |  | Allstar | SQ202604100675-Allstar // SQ202604100677-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040616 |  | 2026-04-07 | 2026-04-08 | Completed | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-08 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-08 | 2026-04-14 | 2026-04-20 | 2026-04-20 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-04-08 | 2026-04-14 | 2026-04-20 | 2026-04-20 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-04-12 | 2026-04-12 | 2026-04-12 | 2026-04-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-12 | 2026-04-08 | 2026-04-14 | 2026-04-22 | 2026-04-22 | BONG NEE NYEEbong.allstar@gmail.com | 2025-02-18: 2026-04-08; 2025-02-28: 2026-04-14; 2025-03-10: 2026-04-08; 2025-03-10: 2026-04-08 | [7 empty] | GTSB | SQ202604030186-GTSB
4443B_HU | BOHEstate | DU00006714630 | Northern | Pahang | 4.449825 | 101.422383 | [7 empty] | 01. Pending Planning | [13 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030176-GTSB
1097L_HU | SungaiChinchin | DU00006714631 | Central | Selangor | 3.248343 | 101.715588 | [7 empty] | 04. Pending DO |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M_128QAM_EPLA_1352M NE_1097L New 23G_0.3M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01, NEID 9-34272). New XMC_3E, Sub A&B_Hix2. New ISM8 x1. New IF cables with suitable length and type x2 RUN. FE_2012B New 23G_0.6M(MAC)+OMT x1. Re-use existing RTN910A(RTN04, NEID 9-34273). New XMC_3E, Sub A&B_Lo x2. New ISM8 x1. New IF cables with suitable length and type x2 RUN. | MW Swap | Existing HW MW Link 1097L-2012B, 18G_1+0_56MHZ_1024QAM_447M. Swap existing HW MW Link 1097L-2012B, 18G_1+0_56MHZ_1024QAM_447M(ODU & Antenna ONLY) to new HW MW Link 1097L-2012B, 23G_2+0_110MHZ_128QAM_EPLA_1352M. Anyway, do not decom existing RTN910A(RTN01, NEID 9-34272) at 1097L and existing RTN910AF(RTN04, NEID 9-34273) at 2012B. Site Impacted : 1097L. NE_1097L 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01, NEID 9-342720) and insert new ISM8 x1 into slot 03. 3.Install new XMC_3E, Sub A&B_Hi x2 and lay new IF cable x2 RUN and terminate to existing RTN910A(RTN01, NEID 9-342720) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 1097L-2012B, 23G_2+0_110MHZ_128QAM_EPLA_1352M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 1097L to new HW MW Link 1097L-2012B, 23G_2+0_110MHZ_128QAM_EPLA_1352M. 6.Later, decom existing HW MW Link 1097L-2012B, 18G_1+0_56MHZ_1024QAM_447M.(ODU & Antenna ONLY). FE_2012B 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN04, NEID 9-34273) and insert new ISM8 x1 into slot 03. 3.Install new XMC_3E, Sub A&B_Lo x2 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN04, NEID 9-34273) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 1097L-2012B, 23G_2+0_110MHZ_128QAM_EPLA_1352M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 1097L to to existing port at IBeam. 6.Later, decom existing HW MW Link 1097L-2012B, 18G_1+0_56MHZ_1024QAM_447M.(ODU & Antenna ONLY). | Existing HW MW Link 1097L-2012B, 18G_1+0_56MHZ_1024QAM_447M. Swap existing HW MW Link 1097L-2012B, 18G_1+0_56MHZ_1024QAM_447M(ODU & Antenna ONLY) to new HW MW Link 1097L-2012B, 23G_2+0_110MHZ_128QAM_EPLA_1352M. Anyway, do not decom existing RTN910A(RTN01, NEID 9-34272) at 1097L and existing RTN910AF(RTN04, NEID 9-34273) at 2012B. Site Impacted : 1097L. NE_1097L 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01, NEID 9-342720) and insert new ISM8 x1 into slot 03. 3.Install new XMC_3E, Sub A&B_Hi x2 and lay new IF cable x2 RUN and terminate to existing RTN910A(RTN01, NEID 9-342720) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 1097L-2012B, 23G_2+0_110MHZ_128QAM_EPLA_1352M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 1097L to new HW MW Link 1097L-2012B, 23G_2+0_110MHZ_128QAM_EPLA_1352M. 6.Later, decom existing HW MW Link 1097L-2012B, 18G_1+0_56MHZ_1024QAM_447M.(ODU & Antenna ONLY). | Existing HW MW Link 1097L-2012B, 18G_1+0_56MHZ_1024QAM_447M. Swap existing HW MW Link 1097L-2012B, 18G_1+0_56MHZ_1024QAM_447M(ODU & Antenna ONLY) to new HW MW Link 1097L-2012B, 23G_2+0_110MHZ_128QAM_EPLA_1352M. Anyway, do not decom existing RTN910A(RTN01, NEID 9-34272) at 1097L and existing RTN910AF(RTN04, NEID 9-34273) at 2012B. Site Impacted : 1097L. FE_2012B 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910AF(RTN04, NEID 9-34273) and insert new ISM8 x1 into slot 03. 3.Install new XMC_3E, Sub A&B_Lo x2 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN04, NEID 9-34273) ISM8 slot 03 Port 1 & 2. Build new HW MW Link 1097L-2012B, 23G_2+0_110MHZ_128QAM_EPLA_1352M. 4.Re-use existing xD Vlan DCN & Vlan Services. 5.Migrate traffic 1097L to to existing port at IBeam. 6.Later, decom existing HW MW Link 1097L-2012B, 18G_1+0_56MHZ_1024QAM_447M.(ODU & Antenna ONLY). | XMC-3E | MAC+OMT | 23G | 23G_0.3M(MAC)+OMT x1 | 23G_0.6M(MAC)+OMT x1 | GCI | SQ202605070521-GCI | GCI | SQ202604150067-GCI // SQ202604150085-GCI |  |  | Ongoing | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040925 |  | 2026-04-10 | 2026-04-11 | Completed | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-11 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-04-29 | 2026-04-22 | 2026-04-23 | LEEROY QUIRINUS6000070995 | GCI TI | 2026-04-23 | 2026-04-29 | 2026-04-22 | 2026-05-04 | LEEROY QUIRINUS6000070995 | GCI TI | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-23 | 2026-04-23 | 2026-04-29 | 2026-04-22 | 2026-05-04 | LEEROY QUIRINUS6000070995 | 2026-04-23 | 2026-04-29 | 2026-04-22 | 2026-04-23 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | NG HONG JIE7018000036 | Logistic Team | [5 empty] | GTSB | SQ202604030172-GTSB
2980B_HU | GalaxyAmpang Mall Indoor | DU00006714632 | Central | Selangor | 3.146211 | 101.755619 | [7 empty] | 01. Pending Planning |  | AA | PAC |  | MW Remote Upgrade | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 2980B. NE_2980B 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. FE_1747A 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 2980B. NE_2980B 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 2980B. FE_1747A 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-27 | [20 empty] | GTSB | SQ202604030172-GTSB
1911B_HU | SILKSg Long KM14 | DU00006714633 | Central | Selangor | 3.000338 | 101.833111 | [7 empty] | 01. Pending Planning |  | AA | PAC |  | MW Remote Upgrade | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 1911B. NE_1911B 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. FE_1912B 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 1911B. NE_1911B 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | Link Existing ZTE 23G_1+0_56M_512QAM. MW Remote Upgrade to ZTE 23G_1+0_112M_512QAM. Site Impacted : 1911B. FE_1912B 1.Remotely upgrade from 23G_1+0_56M_512QAM to 23G_1+0_112M_512QAM. | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-27 | [20 empty] | GTSB | SQ202604030172-GTSB
1891B_AD | Sg Tengi(Celcom) | DU00006714634 | Central | Selangor | 3.608652 | 101.421548 | [9 empty] | TSS+TI | L1+ATP+PAC | 2X PATCH CORD | BBU Patching | MW BBU PATCHING AT 1891B TO NEW CISCO 1891B BBU 1891B DIRECT PATCHING TO NEW CISCO 1891B CARRY 1891B MIGRATE TO NEW CISCO | MW BBU PATCHING AT 1891B TO NEW CISCO 1891B BBU 1891B DIRECT PATCHING TO NEW CISCO 1891B CARRY 1891B MIGRATE TO NEW CISCO | [6 empty] | GCI | SQ202605070521-GCI | GCI | SQ202604290731-GCI |  |  | Ongoing | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-05 | 2026-05-06 | 2026-05-05 | 2026-05-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-05 | 2026-05-06 | 2026-05-05 | 2026-05-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040637 |  | 2026-04-07 | 2026-04-11 | Completed | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-11 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-28 | 2026-05-05 | 2026-04-27 | 2026-04-28 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-04-28 | 2026-05-05 | 2026-04-27 | 2026-05-04 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-02 | 2026-04-28 | 2026-05-05 | 2026-04-27 | 2026-05-04 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-02-18: 2026-04-28; 2025-02-28: 2026-05-05; 2025-03-10: 2026-04-27; 2025-03-10: 2026-04-28 | [7 empty] | GCI | SQ202604030167-GCI | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
1733A_HU | TmnAmpang Jaya | DU00006714635 | Central | Selangor | 3.158457 | 101.761563 | [9 empty] | TSS+TI | L1+ATP+PAC | Cat 6 ETH cable x1 | MW Re-engineering | Migrate all child sites traffic to route 1733A-FIBER-1747A Site Impacted : 1733A , 1446A. NE_1733A. 1.1733A_RTN02 pathcing to existing DDF Port. 2.1733A_BBU transfer to existing 1733A_RTN02_GE2. 3,Disconnect existing ETH cable between RTN01 & RTN02 and disable unused port. 4.Create New Inband DCN. 5.Ensure all child sites traffic migrate to new TX route. FE_1747A. 1.Ensure all child site traffic migrate to new TX route. | Migrate all child sites traffic to route 1733A-FIBER-1747A Site Impacted : 1733A , 1446A. NE_1733A. 1.1733A_RTN02 pathcing to existing DDF Port. 2.1733A_BBU transfer to existing 1733A_RTN02_GE2. 3,Disconnect existing ETH cable between RTN01 & RTN02 and disable unused port. 4.Create New Inband DCN. 5.Ensure all child sites traffic migrate to new TX route. | [6 empty] | GCI | SQ202604150090-GCI | GCI | SQ202604150085-GCI |  |  | Ongoing | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040308 |  | 2026-04-04 | 2026-04-07 | Completed | 2026-04-03 | 2026-04-04 | 2026-04-03 | 2026-04-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-13 | 2026-04-20 | 2026-04-13 | 2026-04-13 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-04-13 | 2026-04-20 | 2026-04-13 | 2026-04-15 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-13 | 2026-04-13 | 2026-04-20 | 2026-04-13 | 2026-04-15 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-02-18: 2026-04-13; 2025-02-28: 2026-04-20; 2025-03-10: 2026-04-13; 2025-03-10: 2026-04-13 | [7 empty] | GCI | SQ202604030167-GCI | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | CHEONG/SENG/WAH/7018000306
2615A3_HU | pBTSKg Getisan | DU00006714636 | Sabah | Sabah | 6.094324 | 116.122774 | [9 empty] | AA |  |  | MW Remote Upgrade | Existing link 18G_1+0_56M. Siftware upgrade to 18G_1+0_112M. Site Impacted : 2615A. | Existing link 18G_1+0_56M. Siftware upgrade to 18G_1+0_112M. Site Impacted : 2615A. | Existing link 18G_1+0_56M. Siftware upgrade to 18G_1+0_112M. Site Impacted : 2615A. | XMC_5D | MDD | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604030180-GCI | 2026-04-05 | 2026-04-05 | 2026-04-05 | 2026-04-05 | CHEONG/SENG/WAH/7018000306
1892B_HU_2 | NSHW KM435(Maxis) | DU00006714637 | Central | Selangor | 3.380000 | 101.559900 | [9 empty] | TSS+AA+TI |  | 2X 13G 1.2M DP ANTENNA 1x ODU 13G XMC3 SUB A HI 1X ODU 13G XMC3 SUB A LO | MW Parallel Link | MW PARALLEL LINK 1892B-1413A WITH HUAWEI_13G_2+0_1.2M/1.M_DP_28MHZ_512QAM_450MBPS_XMC3_SUB A_6.94KM_EPLA WITH EXISTING 15G 4+0 IMPACTED: 1892B, 2007B, 1019R | 1. REUSE EXISTING RTN910 2. INSTALL NEW 13G 1.2M DP ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A 3. CONFIGURE LINK 13G 2+0 28MHZ 512QAM EPLA WITH EXISTING 15G 4+0 | 1. REUSE EXISTING RTN910 2. INSTALL NEW 13G 1.2M DP ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A 3. CONFIGURE LINK 13G 2+0 28MHZ 512QAM EPLA WITH EXISTING 15G 4+0 4. PATCH TO NEW CP PORT AND DO PORT LAG |  |  | 13G | 1.2 | 1.2 | GTSB | SQ202604060610-GTSB | GTSB | SQ202604060602-GTSB // SQ202604060606-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040306 |  | 2026-04-04 | 2026-04-30 | Completed | 2026-04-03 | 2026-04-04 | 2026-04-03 | 2026-04-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202604030167-GCI
7623B_IPR_1 | Bandar Fajar Harapan | DU00005725027 | Sabah | Sabah | 5.230057 | 119.204792 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1x LAN Cable | BBU Patching | 7623B_IPR_1 : BBU Patching to RTN06 - Transfer Patch from 7623B RTN05 8-EM6-1(to 2G,3G,4G BBU) to 7623B RTN06 8-EM6-1(Rename as BBU 7623B) | 7623B_IPR_1 : BBU Patching to RTN06 - Transfer Patch from 7623B RTN05 8-EM6-1(to 2G,3G,4G BBU) to 7623B RTN06 8-EM6-1(Rename as BBU 7623B) | N/A | [5 empty] | NR services | SQ202507230743-NR Services | NR services | SQ202507190103-NR Services | 2025-11-11 | 2025-11-10 | Completed | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-08-01 | 2025-07-31 | 2025-07-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-31 | 2025-08-01 | 2025-07-31 | 2025-07-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062803 |  | 2025-06-29 | 2025-07-01 | Completed | 2025-06-28 | 2025-06-29 | 2025-06-28 | 2025-07-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-19 | 2025-08-19 | 2025-07-19 | 2025-07-21 | WILFRED BALANG7167000026 | NR Service TI | 2025-07-19 | 2025-08-19 | 2025-07-19 | 2025-07-22 | WILFRED BALANG7167000026 | NR Service TI | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-21 | 2025-07-19 | 2025-08-19 | 2025-07-19 | 2025-07-22 | WILFRED BALANG7167000026 | 2025-02-18: 2025-07-19; 2025-02-28: 2025-08-19; 2025-03-10: 2025-07-19; 2025-03-10: 2025-07-21 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507080534-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
7401A_IPR | RTM Station | DU00005725028 | Sabah | Sabah | 6.359369 | 116.420833 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | BBU Patching | Change patching BBU to IBEAM from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Change patching BBU to IBEAM from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | [6 empty] | NR services | SQ202512160988-NR Services | NR services | SQ202511250894-NR Services | 2025-12-25 | 2025-12-22 | Completed | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071930 |  | 2025-07-24 | 2025-12-04 | Completed | 2025-07-23 | 2025-07-24 | 2025-07-23 | 2025-12-04 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-23 | 2025-12-23 | 2025-11-23 | 2025-12-04 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-11-23 | 2025-12-23 | 2025-11-23 | 2025-12-04 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-04 | 2025-11-23 | 2025-12-23 | 2025-11-23 | 2025-12-06 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-02-18: 2025-11-23; 2025-02-28: 2025-12-23; 2025-03-10: 2025-11-23; 2025-03-10: 2025-12-04 |  |  | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-16 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507190087-GTSB | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | HSU//MYET CHAE/6799000011
7623B_IPR_2 | Bandar Fajar Harapan | DU00005725029 | Sabah | Sabah | 5.230057 | 119.204792 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | MW Hardware Upgrade | 7623B_IPR_2 : Hardware Upgrade (10G Port RTN04-RTN06 & Decom RTN02 RTN950A) i. 10G Port Upgrade to 7623B RTN04 to 7623B RTN06 - Install 1 10G SFP Optical at HW 7623B RTN04 8-EM6-4(PORT-4) - Rename as Cascade RTN04 to RTN06 - Install 1 10G SFP Optical at HW 7623B RTN06 8-EM6-4(PORT-4) - Rename as Cascade RTN06 to RTN04 - Patching Optical Patch Cord HW 7623B RTN04 8-EM6-4(PORT-4) to HW 7623B RTN06 8-EM6-4(PORT-4) ii. Decom 7623B RTN02 IDU RTN950A Reconfigure Traffic for All 10 Sites; 7623B, 7146K, 7363B, 7109K, 7357B, 7511A, 7510A, 7475B, S00331 & 7482B Site affected : 7623B 7146K 7363B 7109K 7357B 7511A 7510A 7475B S00331 7482B | 7623B_IPR_2 : Hardware Upgrade (10G Port RTN04-RTN06 & Decom RTN02 RTN950A) i. 10G Port Upgrade to 7623B RTN04 to 7623B RTN06 - Install 1 10G SFP Optical at HW 7623B RTN04 8-EM6-4(PORT-4) - Rename as Cascade RTN04 to RTN06 - Install 1 10G SFP Optical at HW 7623B RTN06 8-EM6-4(PORT-4) - Rename as Cascade RTN06 to RTN04 - Patching Optical Patch Cord HW 7623B RTN04 8-EM6-4(PORT-4) to HW 7623B RTN06 8-EM6-4(PORT-4) ii. Decom 7623B RTN02 IDU RTN950A Reconfigure Traffic for All 10 Sites; 7623B, 7146K, 7363B, 7109K, 7357B, 7511A, 7510A, 7475B, S00331 & 7482B Site affected : 7623B 7146K 7363B 7109K 7357B 7511A 7510A 7475B S00331 7482B | N/A | [5 empty] | NR services | SQ202510010672-NR Services | NR services | SQ202508200592-NR Services // SQ202508200595-NR Services | 2025-11-01 | 2025-10-31 | Completed | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-11-01 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071931 |  | 2025-07-24 | 2025-10-07 | Completed | 2025-07-23 | 2025-07-24 | 2025-07-23 | 2025-10-07 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-10-07 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-10-07 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-30 | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-10-05 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-09-29 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507080534-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9122A_IPR | Sg. Plant | DU00005725030 | Sarawak | Sarawak | 3.263333 | 113.113304 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | Split traffic at IDU SM 9122A-9367B MW1 LAN1 to 9122A-MAC-001 Sg Plant/GigabitEthernet0/2/23 Patch IDU Huawei 9122A-SG PLANT-RTN01 to new IBEAM port and transfer traffic from sites below: 1) 9696C-KG SG PLAN 2) Associated existing DCN configuration | [7 empty] | Allstar | SQ202507180633-Allstar | Allstar | SQ202507290151-Allstar | 2025-09-22 | 2025-09-22 | Completed | 2025-07-28 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-19 | 2025-09-20 | 2025-09-19 | 2025-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-09-20 | 2025-09-19 | 2025-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070910 |  | 2025-07-10 | 2025-09-07 | Completed | 2025-07-09 | 2025-07-10 | 2025-07-09 | 2025-09-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-29 | 2025-08-05 | 2025-07-30 | 2025-09-07 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-29 | 2025-08-05 | 2025-07-31 | 2025-07-31 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-29 | 2025-07-29 | 2025-08-05 | 2025-07-31 | 2025-07-31 | TONI//ANAK KUMBONG/6798000163 | 2025-02-18: 2025-07-29; 2025-02-28: 2025-08-05; 2025-03-10: 2025-07-29; 2025-03-10: 2025-07-29 |  |  | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507190089-GTSB | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | HSU//MYET CHAE/6799000011
4950B_IPR | Pulai | DU00005725031 | Northern | Kedah | 5.657840 | 100.880318 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | New patching from 4950B-PULAI-RTN04 GE2 to new CP port and create LAG (GE1 and GE2) Impacted sites: 1) 4942B 2) K00680 3) K00697 | New patching from 4950B-PULAI-RTN04 GE2 to new CP port and create LAG (GE1 and GE2) Impacted sites: 1) 4942B 2) K00680 3) K00697 | [6 empty] | GCI | SQ202507250118-GCI | GCI | SQ202509260758-GCI | 2025-11-19 | 2025-11-20 | Completed | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062378 |  | 2025-06-24 | 2025-06-24 | Completed | 2025-06-23 | 2025-06-24 | 2025-06-23 | 2025-06-24 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-11 | 2025-07-25 | 2025-07-11 |  | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-07-11 | 2025-07-25 | 2025-07-11 | 2025-07-21 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-11 | 2025-07-11 | 2025-07-25 | 2025-07-11 | 2025-07-21 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-02-18: 2025-07-11; 2025-02-28: 2025-07-25; 2025-03-10: 2025-07-11; 2025-03-10: 2025-07-11 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507080524-GCI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
7457A-7063A | Survey Keningau | DU00003237408 | Sabah | Sabah | 5.337170 | 116.154300 | WK03 | JAN 24 | WK10 | MAR 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | [8 empty] | Magicell | SQ202402130373-Magicell | NR services | SQ202403220526-NR Services | 2024-03-15 | 2024-03-11 | Completed | 2024-01-13 | 2024-01-13 | 2024-01-13 | 2024-01-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. |  | Unassigned | Completed |  | 2024-01-22 | 2024-01-22 | 2024-01-22 | 2024-01-24 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-22 | 2024-01-26 | 2024-01-22 | 2024-01-22 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2024-03-11 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24030473 |  | 2024-03-05 | 2024-03-05 | Completed | 2024-03-04 | 2024-03-05 | 2024-03-04 | 2024-03-05 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-09 | Royson//Anak Stephen/7167000020 | NR Service TI | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-09 | Royson//Anak Stephen/7167000020 | NR Service TI | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-03-09 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-11 | Royson//Anak Stephen/7167000020 | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-08 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
3971B-1122A | Jenjarum | DU00003237409 | Central | Selangor | 2.876888 | 101.502805 |  | MAR 24 | WK11 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | D2: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_SP_1+0_110MHz | MW Swap | DCN VLAN : 416, PORT NUMBER : GigabitEthernet0/2/27 NE 1- Swap SM IDU with Huawei IDU 910A 2- Swap SM 1+0 ODU with Huawei 1+0 ODU. 3- Swap SM Antenna with new Huawei 0.6m Antenna MDD. 4- Configure link 1+0_800M_512QAM. FE 1- Swap SM IDU with Huawei IDU 910A 2- Swap SM 1+0 ODU with Huawei 1+0 ODU. 3- Swap SM Antenna with new Huawei 0.6m Antenna MDD. 4- Configure link 1+0_800M_512QAM. 5- Configure new DCN VLAN for monitoring. | [7 empty] | Allstar | SQ202403180278-Allstar | Allstar | SQ202402190097-Allstar // SQ202510070055-Allstar | 2024-04-30 | 2024-03-25 | Completed | 2024-03-12 | 2024-04-30 | 2024-03-11 | 2024-03-11 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-03-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020124 |  | 2024-02-02 | 2024-02-03 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-05-08 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 | Allstar TI | 2024-03-12 | 2024-06-30 | 2024-03-12 | 2024-05-09 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 | Allstar TI | 2024-03-23 | 2024-03-23 | 2024-03-23 | 2024-03-23 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-06-24 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 | 2024-03-12 | 2024-03-31 | 2024-03-12 | 2024-03-23 | 2024-07-24 | 2024-07-24 | 2024-07-24 | 2024-07-24 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7308B-7617A | Kinabutan Tiku | DU00003237410 | Sabah | Sabah | 4.264110 | 117.955600 | WK04 | JAN 24 | WK07 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | DCN VLAN : 400, PORT NUMBER : Eth-Trunk19 | [7 empty] | Seri Pancar | SQ202402130369-Seri Pancar | GTSB | SQ202402210517-GTSB | 2024-02-02 | 2024-02-01 | Completed | 2024-01-23 | 2024-01-31 | 2024-01-23 | 2024-01-23 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-01-26 | 2024-01-31 | 2024-01-26 | 2024-01-26 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-26 | 2024-01-31 | 2024-01-26 | 2024-01-26 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-01 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020513 |  | 2024-02-06 | 2024-02-07 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-07 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-08 | 2024-02-29 | 2024-02-08 | 2024-02-13 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-02-08 | 2024-02-29 | 2024-02-08 | 2024-02-14 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-14 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-02-08 | 2024-02-29 | 2024-02-08 | 2024-02-16 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | 2024-02-08 | 2024-02-29 | 2024-02-08 | 2024-02-13 | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-27 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
1693B-1612B | Puncak Alam Highway 2 (ZED) | DU00003237411 | Central | Selangor | 3.145290 | 101.474650 | WK14 | APR 24 | WK13 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 3/9: Initial SOW not enough capacity | TSS+AA+TI | L1+ATP+PAC | 13G 1.2m/1.2m 4+0 256QAM 28Mhz | MW Parallel Link | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/3 NE 1. INSTALL NEW RTN 910A + 2 UNIT ISM8 CARD 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW 13G XMC-5D SUB BAND A 4. CONFIGURE LINK 13G 4+0 CA 28MHZ 5. SHIFT 1503C-1693B IF CABLE AND CONFIGURATION FROM RTN01 3-ISM8-1 TO NEW RTN 910A 7-ISM8-1 FE 1. INSTALL NEW RTN 910A + 2 UNIT ISM8 CARD 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW 13G XMC-5D SUB BAND A 4. CONFIGURE LINK 13G 4+0 CA 28MHZ 5. PATCH NEW RTN 910A TO NEW CP PORT | [7 empty] | Allstar | SQ202403180278-Allstar | Allstar | SQ202403180799-Allstar | 2024-04-04 | 2024-04-03 | Completed | 2024-03-01 | 2024-03-31 | 2024-03-06 | 2024-03-06 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-14 | 2024-03-14 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-03-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-03 | 2024-04-04 | 2024-04-03 | 2024-04-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021021 |  | 2024-02-12 | 2024-03-08 | Completed | 2024-02-10 | 2024-02-12 | 2024-02-10 | 2024-03-08 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-21 | 2024-03-31 | 2024-03-21 | 2024-04-18 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | Allstar TI | 2024-03-21 | 2024-09-30 | 2024-03-21 | 2024-09-23 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | Allstar TI | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | C.PRATHABAN///6798000081 |  | 2024-05-28 | 2024-03-21 | 2024-03-31 | 2024-03-21 | 2024-06-07 | ARIF//HISHAMUDIN BIN AHMAD/6798000190 | 2025-02-18: 2024-03-21; 2025-02-28: 2024-03-31; 2025-03-10: 2024-03-21; 2025-03-10: 2024-03-25 |  |  | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358
1431B-1367A | WorldWideBusiness | DU00003237412 | Central | Selangor | 3.071544 | 101.541113 | WK10 | MAR 24 | WK12 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | D2: Cutover done | TSS+AA+TI | L1+ATP+PAC | 23G 2+0 112Mhz 256QAM 0.6M/0.6M | MW Parallel Link | NE 1) Install new RTN910A (RTN02) 2) Install new 23G 2+0 112MHz at RTN02 7-ISM8 3) Migrate 1431B BBU only to new link FE 1) Install new RTN910A (ops team to assign new RTN number) 2) Install new 23G 2+0 112MHz at new RTN 7-ISM8 3) Migrate 1431B BBU only to new link 4) Patch new IDU to new CP port and establish new DCN | [7 empty] | Allstar | SQ202403180278-Allstar | Allstar | SQ202411120057-Allstar | 2024-04-30 | 2024-04-29 | Completed | 2024-03-12 | 2024-04-30 | 2024-03-12 | 2024-03-12 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-19 | 2024-03-19 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-20 | 2024-03-21 | 2024-03-20 | 2024-03-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021507 |  | 2024-02-16 | 2024-03-20 | Completed | 2024-02-15 | 2024-02-16 | 2024-02-15 | 2024-03-20 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-23 | 2024-04-30 | 2024-04-23 | 2024-11-25 | RAHMAD//HIDAYAT BIN LAMRI/6798000206 | Allstar TI | 2024-04-23 | 2024-04-30 | 2024-04-23 | 2024-04-23 | RAHMAD//HIDAYAT BIN LAMRI/6798000206 | Allstar TI | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-04-23 | 2024-04-30 | 2024-04-23 | 2024-04-24 | RAHMAD//HIDAYAT BIN LAMRI/6798000206 | 2025-02-18: 2024-04-23; 2025-02-28: 2024-04-30; 2025-03-10: 2024-04-23; 2025-03-10: 2024-12-20 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
1503C-1693B | Puncak Alam Highway 2 (ZED) | DU00003237413 | Central | Selangor | 3.145270 | 101.474623 |  |  | WK04 | JAN 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC |  | MW Remote Upgrade | [8 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-01-22 | 2024-01-27 | 2024-01-23 | 2024-01-23 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
9258B-9368A | Sing Kwong | DU00003260696 | Sarawak | Sarawak | 2.267690 | 111.860961 | WK13 | MAR 24 | WK16 | APR 24 | RFS | Pending plan | ZTE | 00. Integrated/RFS Done | 16/4: Complete 2+0 config 25/3: Cutover done. Link need to full config 2+0 (incompleted material) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_0.6,0.6 SP_55MHz | MW Swap | [8 empty] | Trintel | SQ202402130359-Trintel | Datasco | SQ202404030681-Datasco | 2024-04-19 | 2024-04-17 | Completed | 2024-01-30 | 2024-01-31 | 2024-01-25 | 2024-01-29 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-07 | 2024-02-20 | 2024-02-20 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2024-03-11 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-17 | 2024-04-19 | 2024-04-17 | 2024-04-17 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240314BE |  | 2024-03-15 | 2024-03-20 | Completed | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-22 | 2024-03-28 | 2024-03-22 | 2024-04-16 | Chiew Hua Kai7019000037 | Datasco TI | 2024-03-22 | 2024-03-28 | 2024-03-22 | 2024-04-16 | Chiew Hua Kai7019000037 | Datasco TI | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-22 | 2024-03-28 | 2024-03-22 | 2024-04-24 | Chiew Hua Kai7019000037 | 2024-03-22 | 2024-03-28 | 2024-03-22 | 2024-03-22 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-28 | CHONG QIEW LEK7018000038 | Logistic Team | 2024-07-30 | 2024-08-30 | 2024-07-30 | 2024-07-30 | ASTI//GANIS PUTRIANI/6237001358
1011C-1786A | Surau Darul Hikmah | DU00003260697 | Central | Selangor | 3.032100 | 101.384700 | WK07 | FEB 24 | WK07 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_SP_1+0_110MHz FE_ISM8 | MW Hardware Upgrade | NE 1- Configure link 1+0_900M_512QAM FE 1- Swap existing ISV3 with new ISM8 at Slot 3. 2- Configure link 1+0_900M_512QAM | [7 empty] | Nera | SQ202402270797-Nera | Nera | SQ202402190127-Nera | 2024-05-03 | 2024-05-06 | Completed | 2024-02-16 | 2024-02-23 | 2024-02-16 | 2024-02-16 | NUR//AFIQAH BINTI MOHD ROSDI/7670000015 | Nera TI | NERA (MALAYSIA) SDN. BHD. |  | Assigned | Completed |  | 2024-03-19 | 2024-03-20 | 2024-03-19 | 2024-03-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-19 | 2024-03-20 | 2024-03-19 | 2024-03-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-30 | 2024-05-03 | 2024-04-30 | 2024-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020145 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  |  | Assigned | Completed |  | 2024-02-16 | 2024-02-23 | 2024-02-16 | 2024-02-16 | NUR//AFIQAH BINTI MOHD ROSDI/7670000015 | Nera TI | 2024-02-16 | 2024-02-23 | 2024-02-16 | 2024-02-16 | NUR//AFIQAH BINTI MOHD ROSDI/7670000015 | Nera TI | 2024-02-16 | 2024-02-23 | 2024-02-16 | 2024-02-16 | RONALD SHAN A/L AMBUROSE6800000089 | Nera TI |  | 2024-02-16 | 2024-02-23 | 2024-02-16 | 2024-02-20 | NUR//AFIQAH BINTI MOHD ROSDI/7670000015 | 2024-02-16 | 2024-02-23 | 2024-02-16 | 2024-02-16 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4725B | Wang Tepus | DU00003260698 | Northern | Kedah | 6.244348 | 100.476747 | WK14 | APR 24 |  |  | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | 1/4: Cutover done | TSS+TI | L1+ATP+PAC |  | New Starlink | VSAT conversion to Starlink | [7 empty] | GTSB | SQ202402290678-GTSB (CR Starlink) | GTSB | SQ202402290678-GTSB (CR Starlink) | 2024-02-29 | 2024-02-29 | Completed | 2023-12-27 | 2023-12-27 | 2023-12-27 | 2023-12-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2023-12-27 | 2023-12-27 | 2023-12-27 | 2023-12-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-29 | 2024-02-29 | 2024-02-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-02-01 | 2024-02-29 | 2024-02-29 | 2024-02-29 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24033056 |  | 2024-03-31 | 2024-04-01 | Completed | 2024-03-30 | 2024-03-31 | 2024-03-30 | 2024-04-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-01 | 2024-04-30 | 2024-04-01 | 2024-04-18 | MUHAMMAD//HUSNIAN/6799000146 | GTSB TI | 2024-04-01 | 2024-04-30 | 2024-04-01 | 2024-05-21 | MUHAMMAD//HUSNIAN/6799000146 | GTSB TI | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-13 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-04-01 | 2024-04-30 | 2024-04-01 | 2024-04-04 | MUHAMMAD//HUSNIAN/6799000146 | 2025-02-18: 2024-04-01; 2025-02-28: 2024-04-30; 2025-03-10: 2024-04-01; 2025-03-10: 2024-04-02 |  |  | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | RIZAL//FA'IZ BIN RAMLI/6799000024 | GCI | SQ202507080524-GCI | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | EZRIN TASNIM BIN ABDUL GANI6798000128
7971B-7155A | Jalan Mengkabung Timbok | DU00003260699 | Sabah | Sabah | 6.161967 | 116.220398 | WK04 | JAN 24 | WK21 | JUN 24 |  |  | ZTE | 00. Integrated/RFS Done | 10/7: D2: Cutover done 9/7: MOS & TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_1.2,1.2 DP_55Mhz | MW Swap | [8 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202411080628-NR Services | 2024-02-09 | 2024-02-07 | Completed | 2024-01-22 | 2024-01-22 | 2024-01-22 | 2024-01-22 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-05 | 2024-02-09 | 2024-02-05 | 2024-02-05 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-05 | 2024-02-09 | 2024-02-05 | 2024-02-05 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-09 | 2024-02-07 | 2024-02-07 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24070536 |  | 2024-07-06 | 2024-07-06 | Completed | 2024-07-05 | 2024-07-06 | 2024-07-05 | 2024-07-06 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-09 | 2024-07-31 | 2024-07-09 | 2024-07-10 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-07-09 | 2024-07-31 | 2024-07-09 | 2024-07-10 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2024-07-11 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2024-07-09 | 2024-07-31 | 2024-07-09 | 2024-07-12 | RALPH O'BRYAN HILARY7167000030 | 2024-07-09 | 2024-07-31 | 2024-07-09 | 2024-07-09 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 | tseping//wang/6819000006 | Logistic Team | 2024-09-25 | 2024-10-25 | 2024-09-25 | 2024-09-25 | ASTI//GANIS PUTRIANI/6237001358
4176R_HU | Kg. Batu 3 Temoh | DU00005431603 | Northern | Perak | 4.225290 | 101.223510 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 4176R-4484B FROM 18G_2+0_1.2M/1.2M_DP_28MHZ_512QAM_224MBPS TO 18G_2+0_1.2M/1.2M_DP_112MHZ_128QAM_676MBPS_XMC3E_SUB A & B_4.33KM IMPACTED SITE: 4176R | MW REMOTE UPGRADE LINK 4176R-4484B FROM 18G_2+0_1.2M/1.2M_DP_28MHZ_512QAM_224MBPS TO 18G_2+0_1.2M/1.2M_DP_112MHZ_128QAM_676MBPS_XMC3E_SUB A & B_4.33KM IMPACTED SITE: 4176R | MW REMOTE UPGRADE LINK 4176R-4484B FROM 18G_2+0_1.2M/1.2M_DP_28MHZ_512QAM_224MBPS TO 18G_2+0_1.2M/1.2M_DP_112MHZ_128QAM_676MBPS_XMC3E_SUB A & B_4.33KM IMPACTED SITE: 4176R | XMC3E | MAC | 18G | 1.2 | 1.2 | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505020432-GCI | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
S00287_HU | S00287_MILE 16 KIMANIS | DU00005431604 | Sabah | Sabah | 5.469070 | 116.058886 |  |  |  |  | Pending TI | Team at other sites |  | 05. Doable |  | TSS+AA+TI |  | 8G_2+0_1.8/1.8_DP_SB A,B 2xISM8 | MW Parallel Link | MW PARALLEL LINK S00287-7702A WITH 8G_2+0_1.8/1.8_DP_SB A,B | MW PARALLEL LINK S00287-7702A WITH 8G_2+0_1.8/1.8_DP_SB A,B NE: 1. Reuse existing RTN910A_RTN02. 2. Install new ISM8 at slot 3. 3. Install new XMC-3_SB A,B 4.Install new 8G_1.8m. 5. Configure 8G_2+0_1.8/1.8_EPLA with existing MW link. | MW PARALLEL LINK S00287-7702A WITH 8G_2+0_1.8/1.8_DP_SB A,B FE: 1. Reuse existing RTN910A_RTN06. 2. Install new ISM8 at slot 3. 3. Install new XMC-3_SB A,B 4.Install new 8G_1.8m. 5. Configure 8G_2+0_1.8/1.8_EPLA with existing MW link. | XMC-3 | MS | 8G | 1.8 | 1.8 | Seri Pancar | SQ202506230417-Seri Pancar | NR services | SQ202508270992-NR Services // SQ202508270995-NR Services | 2025-11-24 | 2025-11-17 | Completed | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-23 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-24 | 2025-07-25 | 2025-07-24 | 2025-07-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-17 | 2025-11-24 | 2025-11-17 | 2025-11-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080140 |  | 2025-08-02 | 2025-08-22 | Completed | 2025-08-01 | 2025-08-02 | 2025-08-01 | 2025-08-22 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202505020434-GTSB | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | HSU//MYET CHAE/6799000011
2443A_HU_1 | Ijok (CELCOM) | DU00005431605 | Central | Selangor | 3.296836 | 101.447680 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X ISM8 CARD 1X RTN910 2X 15G 1.2M DP ANTENNA 1x ODU 15G XMC3E SUB A HI 1X ODU 15G XMC3E SUB A LO 1x ODU 15G XMC3E SUB B HI 1X ODU 15G XMC3E SUB B LO | MW Parallel Link | MW PARALLEL LINK 2443A-1964B WITH HUAWEI_15G_2+0_1.2M/1.2M_DP_28MHZ_512QAM_450MBPS_XMC3_SUB_A & B_6.71KM DISMANTLE ISM8 CARD AT EXISTING IDU | 1. REUSE EXISTING RTN910 SLOT 7 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM EPLA WITH EXISTING LINK 4+0 | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 CARD 2. INSTALL NEW 15G 1.2M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM AT SLOT 7 5. TRANSFER EXISTING 4+0 TO NEW IDU SLOT 3 & 4 AND CREATE EPLA WITH NEW 2+0 6. DISMANTLE CARD AT EXISTING IDU | XMC3 | MAC | 15G | 1.2 | 1.2 | GCI | SQ202505090486-GCI | GCI | SQ202505090491-GCI // SQ202505090501-GCI // SQ202506160499-GCI | 2025-06-21 | 2025-06-20 | Completed | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-04 | 2025-06-05 | 2025-06-04 | 2025-06-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-20 | 2025-06-21 | 2025-06-20 | 2025-06-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051358 |  | 2025-05-14 | 2025-05-16 | Completed | 2025-05-13 | 2025-05-14 | 2025-05-13 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-22 | 2025-05-29 | 2025-05-22 | 2025-05-30 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-05-22 | 2025-05-29 | 2025-05-22 | 2025-05-30 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-27 | 2025-05-22 | 2025-05-29 | 2025-05-22 | 2025-06-05 | Ragunalan//A/L L.Krisnan6000006720 | 2025-05-22 | 2025-05-29 | 2025-05-22 | 2025-05-22 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505020429-GCI | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
4752B_HU | Bendang Rawa | DU00005431606 | Northern | Perak | 4.935671 | 100.805310 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | SOW DONE UNDER DU 4752B-4584A | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505020432-GCI | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
4916A_HU | Iconic Hill | DU00005431607 | Northern | Penang | 5.369655 | 100.284189 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 110MHz 0.6m/0.6m Sub B 889Mbps 2X RTN 910A 2X 18G 0.6M SP ANTENNA 1X 18G XMC-3E SUB B HI 1X 18G XMC-3E SUB B LO | MW Swap | SWAP MW LINK 4916A-4042A WITH HUAWEI_18G_1+0_110MHZ_0.6M/0.6M_1.95KM EXISTING MW CFG: HW_23GHZ_1+0_110MHZ IMPACTED SITES: 4916A NE 4916A ICONIC HILL 1. Install New RTN910A 2. Install New 18G 0.6m SP Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service & Repatch BBU 4916A FE 4042A LONE PINE CARPARK 1. Install New RTN910A 2. Install New 18G 0.6m SP Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service 6. Repatch to Existing iBEAM Port | NE 4916A ICONIC HILL 1. Install New RTN910A 2. Install New 18G 0.6m SP Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service & Repatch BBU 4916A | FE 4042A LONE PINE CARPARK 1. Install New RTN910A 2. Install New 18G 0.6m SP Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service 6. Repatch to Existing iBEAM Port | XMC3E | MAC SP | 18G | 0.6m | 0.6m | NWAVE | SQ202506300701-N-Wave | NWAVE | SQ202505240112-N-Wave // SQ202505240115-N-Wave // SQ202508250727-N-Wave | 2025-08-19 | 2025-08-19 | Completed | 2025-06-10 | 2025-06-10 | 2025-06-11 | 2025-06-11 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-09 | 2025-07-15 | 2025-07-15 | 2025-07-30 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-19 | 2025-08-18 | 2025-08-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052039 |  | 2025-05-21 | 2025-05-22 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-09 | 2025-06-10 | 2025-06-09 | 2025-06-10 | Khairul Azman Bin Din7160000001 |  | 2025-06-10 | 2025-06-10 | 2025-06-11 | 2025-07-06 | Khairul Azman Bin Din7160000001 |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-12 | 2025-06-18 | 2025-06-25 | 2025-06-18 | 2026-01-14 | Muhammad Faiq Bin Aidan6000022582 | 2025-06-18 | 2025-06-25 | 2025-06-18 | 2025-09-24 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
B02314_AD_1 | RICOH Bukit Raja | DU00005469517 | Central | Selangor | 3.074543 | 101.458978 | [7 empty] | 00. Site Out/Drop | 11//7/25-activity done under DU B02314_AD |  |  |  | Cancel / Drop |  | DECOM | DECOM | [5 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
4017D-4979B | Kg Bukit Pokok Sena | DU00003530216 | Northern | Kedah | 6.130556 | 100.608330 |  |  |  |  | RFS | RFS | ZTE | 00. Integrated/RFS Done | D2: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN 910A 4X ISM8 CARD 2X 15G 1.2M MDD ANTENNA 1X 15G XMC-5D SUB A HI 1X 15G XMC-5D SUB A LO | MW Swap | SWAP 4017D-4979B WITH HUAWEI_15GHZ_4+0_28MHZ_1.2M_5.72KM. IMPACTED SITES: 4017D NE: 4017D: 1. INSTALL NEW RTN 910A + 2 ISM8 CARD 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB A 4. CONFIGURE LINK 15G 4+0 CA 28MHZ 5. PATCH 4017D BBU TO NEW RTN 910A 6. DISMANTLE EXISTING LINK FE: 4979B: 1. INSTALL NEW RTN 910A + 2 ISM8 CARD 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB A 4. CONFIGURE LINK 15G 4+0 CA 28MHZ 5. PATCH NEW RTN 910A TO 4979B RTN03 6. DISMANTLE EXISTING LINK EXCEPT IDU | [7 empty] | GCI | SQ202411040337-GCI | GCI | SQ202409100506-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240315AP |  | 2024-03-16 | 2024-03-18 | Completed | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  |  | Assigned | Completed |  | 2024-03-21 | 2024-03-31 | 2024-03-21 | 2024-03-21 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-03-21 | 2024-03-31 | 2024-03-21 | 2024-03-21 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-03-21 | 2024-03-31 | 2024-03-21 | 2024-03-23 | SAFUAN//BIN YUSOFF/6800000178 | 2025-02-18: 2024-03-21; 2025-02-28: 2024-03-31; 2025-03-10: 2024-03-21; 2025-03-10: 2024-03-21 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
4017E_AD | Light Up Sg Petani | DU00006760824 | Northern | Kedah | 5.649763 | 100.537247 | [9 empty] | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS Radio (RTN510). NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Link reroute to new FE 4628B due to LOS Block. NLOS Radio RTN510 Site Impacted : 4017E. NE_4017E 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio FE_4156D 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio | Link reroute to new FE 4628B due to LOS Block. NLOS Radio RTN510 Site Impacted : 4017E. NE_4017E 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio FE_4156D 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio | Link reroute to new FE 4628B due to LOS Block. NLOS Radio RTN510 Site Impacted : 4017E. NE_4017E 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio FE_4156D 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio | [5 empty] | GCI | SQ202604220819-GCI | GCI | SQ202604280626-GCI // SQ202604280634-GCI |  |  | Ongoing | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-07 | 2026-05-08 | 2026-05-07 | 2026-05-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-08 | 2026-05-09 | 2026-05-08 |  | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. |  | Assigned | Ongoing | To be Submitted |  | DOWMY26042040 |  | 2026-04-21 | 2026-04-21 | Completed | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-28 | 2026-05-09 | 2026-04-28 | 2026-05-05 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2026-04-28 | 2026-05-09 | 2026-04-28 | 2026-05-05 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-28 | 2026-05-09 | 2026-04-28 | 2026-05-05 | MOHD FAIZ BIN MD YUNUS6800000186 | 2025-02-18: 2026-04-28; 2025-02-28: 2026-05-09; 2025-03-10: 2026-04-28; 2025-03-10: 2026-04-28 | [7 empty] | GCI | SQ202604280370-GCI | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01169_HU | Q140B_Q01169OD_CB_TGBEKAKAP | DU00006643864 | Sarawak | Sarawak | 2.317060 | 111.682868 | [9 empty] | TSS+AA+TI |  | 4X ISM8 CARD IF CABLE SUITABLE LENGHT | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 9035K/Q01169-9833B WITH FROM 15G_2+0_1.2M/1.2M_MDD_28MHZ_2048QAM TO HUAWEI_15G_4+0_1.2M/1.2M_MDD_28MHZ_1024QAM_976MBPS_XMC5D_SUB_A_WITH CA_LINK_5.80KM IMPACTED: Q01169, 9371K, 9372K | 1. INSTALL NEW 2PCS ISM8 SLOT 3 & 4 2. REUSE EXISTING 15G 1.2M MDD ANTENNA 3. REUSE EXISTING ODU 15G XMC5D SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 1024QAM WITH CA SLOT 3 & 4 | 1. INSTALL NEW 2PCS ISM8 SLOT 3 & 4 2. REUSE EXISTING 15G 1.2M MDD ANTENNA 3. REUSE EXISTING ODU 15G XMC5D SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 1024QAM WITH CA SLOT 3 & 4 | XMC5D | MDD | 15G | 1.2 | 1.2 | Iezzpro |  | Iezzpro |  |  |  | Ongoing | 2026-05-09 | 2026-05-16 | 2026-05-09 |  | Halim bin Bohari6000069011 | Iezzpro TI | IEZZPRO INCORPORATION SDN. BHD. |  | Assigned | Ongoing |  | 2026-05-09 | 2026-05-16 | 2026-05-09 |  | Halim bin Bohari6000069011 | Iezzpro TI | IEZZPRO INCORPORATION SDN. BHD. |  | Assigned | Ongoing |  | 2026-05-09 | 2026-05-16 | 2026-05-09 |  | Halim bin Bohari6000069011 | Iezzpro TI | IEZZPRO INCORPORATION SDN. BHD. |  | Assigned | Ongoing |  | 2026-05-09 | 2026-05-16 | 2026-05-09 |  | Halim bin Bohari6000069011 | Iezzpro TI | IEZZPRO INCORPORATION SDN. BHD. |  | Assigned | Ongoing | To be Submitted |  | DOWMY26050635 |  | 2026-05-07 |  | Ongoing | 2026-05-06 | 2026-05-07 | 2026-05-06 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [7 empty] | 2026-05-09 | 2026-05-16 | 2026-05-09 |  | Halim bin Bohari6000069011 | Iezzpro TI | [7 empty] | 2026-05-09 | 2026-05-16 | 2026-05-09 |  | Halim bin Bohari6000069011 | 2025-02-18: 2026-05-09; 2025-02-28: 2026-05-16; 2025-03-10: 2026-05-09; 2025-03-10: 2026-05-09 | [7 empty] | GCI | SQ202603170140-GCI | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
4979C_HU | Tanjung Piandang Town | DU00005244020 | Northern | Perak | 5.072482 | 100.393294 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M. NE_4979C 18G_DP_1.2M(MDD) x1. XMC_5D , Sub B_Hi x1. FE_4398A 18G_DP_1.2M(MDD) x1. XMC_5D , Sub B_Lo x1. | MW Parallel Link | Existing link 15G_4+0_28M Install parallel link 18G_2+0_112M. Site Impacted : 4979C. NE_4979C 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 4979C_RTN01 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Hi. 4.Create cross connect and EPLA with new 18G_2+0 and existing 15G_4+0. 5.No decomm existing MW link. FE_4398A 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 4389A_RTN01. 3.Install new XMC_5D , Sub B_Lo. 4.Create cross connect and EPLA with new 18G_2+0 and existing 15G_4+0. 5.No decomm existing MW link. | Existing link 15G_4+0_28M Install parallel link 18G_2+0_112M. Site Impacted : 4979C. NE_4979C 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 4979C_RTN01 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Hi. 4.Create cross connect and EPLA with new 18G_2+0 and existing 15G_4+0. 5.No decomm existing MW link. | Existing link 15G_4+0_28M Install parallel link 18G_2+0_112M. Site Impacted : 4979C. FE_4398A 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 4389A_RTN01. 3.Install new XMC_5D , Sub B_Lo. 4.Create cross connect and EPLA with new 18G_2+0 and existing 15G_4+0. 5.No decomm existing MW link. | XMC_5D | MDD | 18G | 1.2 | 1.2 | GCI | SQ202507160591-GCI | GCI | SQ202510090309-GCI // SQ202510090314-GCI | 2025-11-27 | 2025-11-28 | Completed | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251001BA |  | 2025-10-03 | 2025-10-04 | Completed | 2025-10-02 | 2025-10-03 | 2025-10-01 | 2025-10-04 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-06 | 2025-10-09 | 2025-10-06 | 2025-10-12 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-10-06 | 2025-10-09 | 2025-10-06 | 2025-10-12 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-09 | 2025-10-06 | 2025-10-09 | 2025-10-06 | 2025-10-17 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-02-18: 2025-10-06; 2025-02-28: 2025-10-09; 2025-03-10: 2025-10-06; 2025-03-10: 2025-10-08 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | CHEONG/SENG/WAH/7018000306
Q01175_HU | Q133A_Q01175OD_T3_RHMUNGANG | DU00005244021 | Sarawak | Sarawak | 2.684230 | 112.345540 |  |  |  | AUG 25 | Pending SOW |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2x ISM8 | MW Hardware Upgrade | HARDWARE UPGRADE EXISTING LINK Q01175-Q00507 BY INSTALL ISM8 CARD AT NE/FE RE-ENGINEERING IF CABLE FOR CONFIG 4+0 CA CONFIGURE FROM 15G_2+0 BECOME 15G_4+0_CA_28MHZ_128QAM_896Mbps EXISTING LINK: 15G_2+0_28MHZ_2048QAM_576Mbps_1.2M/1.2M_MDD_XMC-5D_SB A_5.31KM | NE: 1. INSTALL NEW ISM8 CARD TO SLOT 3 2. RE-CONNECT IF CABLE FROM EXISTING ISM8 SLOT 7_IF2 TO ISM8 SLOT 3 IF 1 3. CONFIGURE 4+0_CA (SLOT 7 POLAR V AND SLOT 3 POLAR H) | FE: 1. INSTALL NEW ISM8 CARD TO SLOT 3 2. CONNECT IF CABLE FROM EXISTING ISM8 SLOT 7_IF2 TO ISM8 SLOT 3 IF 1 3. CONFIGURE 4+0_CA (SLOT 7 POLAR V AND SLOT 3 POLAR H) | XMC-5D | MDD | 15G | 1.2m | 1.2m | Trintel | SQ202509040637-Trintel | Trintel | SQ202509040608-Trintel // SQ202509040617-Trintel | 2026-01-26 | 2026-01-21 | Completed | 2025-11-06 | 2025-11-07 | 2025-11-06 | 2025-12-17 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25110140 |  | 2025-11-02 | 2025-11-04 | Completed | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-04 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-05 | AINA MARINI//ATON/6794000115 | Trintel TI | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-12-18 | AINA MARINI//ATON/6794000115 | Trintel TI | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-07 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-12-17 | AINA MARINI//ATON/6794000115 | 2025-02-18: 2025-11-03; 2025-02-28: 2025-11-03; 2025-03-10: 2025-11-03; 2025-03-10: 2025-12-16 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202505020435-GTSB | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | AB.RAHMAN//BIN MAT NOOH/6237001519
7435A_HU | Kg Timbou Tambunan | DU00005244022 | Sabah | Sabah | 5.695550 | 116.377490 |  |  |  |  | Drop/Cancel |  |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Upgrade done under DU 7435A-7343A DU00004073909 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9288A_HU | Tedungan(SACOFA) | DU00005244023 | Sarawak | Sarawak | 4.731470 | 114.801514 |  |  |  | AUG 25 | Pending SOW |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 7G_4+0_28M_512QAM_EPLA NE_9288A New A7WD18MS-3NX+Coupler x1. Re-use existing RTN910AF(RTN01). New ISM8 x2. New XMC_3, Sub I,J,K&L_Lo x4. FE_9284A New A7WD18MS-3NX+Coupler x1. Re-use existing RTN910AF(RTN03). New ISM8 x2. New XMC_3, Sub I,J,K&L_Hi x4. New Optical SFP Module 1G 10Km 1310nm x2. New Optical Patch cord with suitable type and length x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 7G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY**** Existing HW MW Link 9288A-9284A, 13G_2+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA. Later, will combine existing HW MW Link 9288A-9284A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA become 13G&7G_6+0_28MHZ_2048QAM+512QAM_EPLA. Site Impacted : 9288A, 9277R, 9772B, 9280R, 9646B, 9252Z, Q01548, 9288R & 9287R. NE_9288A 1.Install new 7G_1.8M(A7WD18MS-3NX)+Coupler x1. 2.Re-use existing RTN910AF(RTN01). 3.Insert new ISM8 x2 into slot 03 & 04 of existing RTN910AF(RTN01). 4.Install new XMC_3, XMC_3, Sub I,J,K&L_Lo x4. 5.Build new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA. 6.Later, will combine existing HW MW Link 9288A-9284A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA become 13G&7G_6+0_28MHZ_2048QAM+512QAM_EPLA. FE_9284A 1.Install new 7G_1.8M(A7WD18MS-3NX)+Coupler x1. 2.Re-use existing RTN910AF(RTN03). 3.Insert new ISM8 x2 into slot 03 & 04 of existing RTN910AF(RTN03). 4.Install new XMC_3, XMC_3, Sub I,J,K&L_Hi x4. 5.Build new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA. 6.Later, will combine existing HW MW Link 9288A-9284A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA become 13G&7G_6+0_28MHZ_2048QAM+512QAM_EPLA. 7.Insert Optical SFP Module into port 8-EM6-6 of existing RTN910AF(RTN03). 8.Insert Optical SFP Module into new port of IBeam. Please request new IBeam port from ZTE IPRAN Team. 9.Patching port 8-EM6-6 of existing RTN910AF(RTN03) and new port of IBeam. 10.Perform LAG between these 2 port at IDU and IBeam. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 7G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY**** Existing HW MW Link 9288A-9284A, 13G_2+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA. Later, will combine existing HW MW Link 9288A-9284A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA become 13G&7G_6+0_28MHZ_2048QAM+512QAM_EPLA. Site Impacted : 9288A, 9277R, 9772B, 9280R, 9646B, 9252Z, Q01548, 9288R & 9287R. NE_9288A 1.Install new 7G_1.8M(A7WD18MS-3NX)+Coupler x1. 2.Re-use existing RTN910AF(RTN01). 3.Insert new ISM8 x2 into slot 03 & 04 of existing RTN910AF(RTN01). 4.Install new XMC_3, XMC_3, Sub I,J,K&L_Lo x4. 5.Build new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA. 6.Later, will combine existing HW MW Link 9288A-9284A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA become 13G&7G_6+0_28MHZ_2048QAM+512QAM_EPLA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 7G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY**** Existing HW MW Link 9288A-9284A, 13G_2+0_28MHZ_2048QAM_EPLA. Build new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA. Later, will combine existing HW MW Link 9288A-9284A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA become 13G&7G_6+0_28MHZ_2048QAM+512QAM_EPLA. Site Impacted : 9288A, 9277R, 9772B, 9280R, 9646B, 9252Z, Q01548, 9288R & 9287R. FE_9284A 1.Install new 7G_2.4M(A7WD18MS-3NX)+Coupler x1. 2.Re-use existing RTN910AF(RTN03). 3.Insert new ISM8 x2 into slot 03 & 04 of existing RTN910AF(RTN03). 4.Install new XMC_3, XMC_3, Sub I,J,K&L_Hi x4. 5.Build new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA. 6.Later, will combine existing HW MW Link 9288A-9284A, 13G_2+0_28MHZ_2048QAM_EPLA and new HW MW Parallel Link 9288A-9284A, 7G_4+0_28MHZ_512QAM_EPLA become 13G&7G_6+0_28MHZ_2048QAM+512QAM_EPLA. 7.Insert Optical SFP Module into port 8-EM6-6 of existing RTN910AF(RTN03). 8.Insert Optical SFP Module into new port of IBeam. Please request new IBeam port from ZTE IPRAN Team. 9.Patching port 8-EM6-6 of existing RTN910AF(RTN03) and new port of IBeam. 10.Perform LAG between these 2 port at IDU and IBeam. | XMC-3 | MS | 7G | 7G_A7WD18MS-3NX+Coupler x1. | 7G_A7WD18MS-3NX+Coupler x1. | Datasco | SQ202507180618-Datasco | Trintel | SQ202509090366-Trintel // SQ202509090378-Trintel | 2025-07-17 | 2025-07-17 | Completed | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | Aaron//anak Meta/7019000019 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-06-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-06-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102993 |  | 2025-10-30 | 2025-10-31 | Completed | 2025-10-29 | 2025-10-30 | 2025-10-29 | 2025-10-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-14 | PATRIK WEI ANAK EDUIN7667000018 | Trintel TI | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-12-11 | PATRIK WEI ANAK EDUIN7667000018 | Trintel TI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-12-11 | PATRIK WEI ANAK EDUIN7667000018 | 2025-02-18: 2025-11-03; 2025-02-28: 2025-11-03; 2025-03-10: 2025-11-03; 2025-03-10: 2025-11-15 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202506050659-GTSB | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | HSU//MYET CHAE/6799000011
9407B_HU | Sungai Kut | DU00005244024 | Sarawak | Sarawak | 2.720735 | 111.839789 |  |  |  |  | Pending SOW |  |  | 03. TSS Only |  | TSS |  | 13G_4+0_28M NE_9407B 13G_DP_1.8M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Lo x1. FE_9159A. 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Hi x1. | MW Swap | 13/4 : This DU ID for TSS only , Upon team site visit / TSS , found FE at 9159A unbale to install because of space constrain issue although Hot Swap existing link. Existing link 13G_4+0_28M with two units different ANT installed at 7_ISM8-2+0 and 3_ISM8-2+0. Based on TSS survey info , space constraint issue. Hot Swap existing 13G_2+0_28M (3_ISM8-2+0) to 13G_4+0_28M with EPLA existing 13G_2+0_28M (7_ISM8-2+0) to become 13G_6+0_28M. ***Pls refer to DU ID 9407B_HU_1 , to transfer 9506B traffic and Hot Swap existing link 15G_4+0_28M. Site Impacted : Q01041 , 9506B. NE_9407B 1.Install new 13G_DP_1.8M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 9407B_RTN04. 3.Install new XMC_5D , Sub A_Lo. 4.Transfer existing ETH patching from 9407B_RTN04 to 9407B_RTN02 , carry 9506B child site. 5.Create service cross connect , CA and EPLA with existing MW link. 6.Traffic migrate to new MW link. 7.Decom existing 3_ISM8-2+0 , ODU and ANT. FE_9159A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 9159A_RTN02. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect , CA and EPLA with existing MW link. 5.Traffic migrate to new MW link. 6.Decomm existing 3_ISM8-2+0 , ODU and ANT. | 13/4 : This DU ID for TSS only , Upon team site visit / TSS , found FE at 9159A unbale to install because of space constrain issue although Hot Swap existing link. Existing link 13G_4+0_28M with two units different ANT installed at 7_ISM8-2+0 and 3_ISM8-2+0. Based on TSS survey info , space constraint issue. Hot Swap existing 13G_2+0_28M (3_ISM8-2+0) to 13G_4+0_28M with EPLA existing 13G_2+0_28M (7_ISM8-2+0) to become 13G_6+0_28M. ***Pls refer to DU ID 9407B_HU_1 , to transfer 9506B traffic and Hot Swap existing link 15G_4+0_28M. Site Impacted : Q01041 , 9506B. NE_9407B 1.Install new 13G_DP_1.8M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 9407B_RTN04. 3.Install new XMC_5D , Sub A_Lo. 4.Transfer existing ETH patching from 9407B_RTN04 to 9407B_RTN02 , carry 9506B child site. 5.Create service cross connect , CA and EPLA with existing MW link. 6.Traffic migrate to new MW link. 7.Decom existing 3_ISM8-2+0 , ODU and ANT. | 13/4 : This DU ID for TSS only , Upon team site visit / TSS , found FE at 9159A unbale to install because of space constrain issue although Hot Swap existing link. Existing link 13G_4+0_28M with two units different ANT installed at 7_ISM8-2+0 and 3_ISM8-2+0. Based on TSS survey info , space constraint issue. Hot Swap existing 13G_2+0_28M (3_ISM8-2+0) to 13G_4+0_28M with EPLA existing 13G_2+0_28M (7_ISM8-2+0) to become 13G_6+0_28M. ***Pls refer to DU ID 9407B_HU_1 , to transfer 9506B traffic and Hot Swap existing link 15G_4+0_28M. Site Impacted : Q01041 , 9506B. FE_9159A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 9159A_RTN02. 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect , CA and EPLA with existing MW link. 5.Traffic migrate to new MW link. 6.Decomm existing 3_ISM8-2+0 , ODU and ANT. | XMC_5D | MDD | 13G | 1.8 | 1.2 | Trintel | SQ202601210184-Trintel |  |  | 2026-02-28 | 2026-02-12 | Completed | 2026-01-31 | 2026-02-28 | 2026-02-04 | 2026-02-04 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601210786-GCI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | CHEONG/SENG/WAH/7018000306
4117R_HU | Kg. Batu Lintang | DU00005244025 | Northern | Kedah | 5.620302 | 100.398053 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M. NE_4117R 18G_SP_1.2M(MAC)+OMT x1. XMC_3E , Sub A_Hi x1. FE_4947A 18G_SP_1.2M(MAC)+OMT x1. XMC_3E , Sub A_Lo x1. | MW Swap | Existing link 13G_2+0_28M Swap existing link to 18G_1+0_112M. Site Impacted : 4117R NE_4117R 1.Install 18G_SP_1.2M(MAC)+OMT. 2.Reuse existing 4117R_RTN01. 3.Install XMC_3E , Sub A_Hi. 4.Create service cross connect and traffic migrate to new link 18G_1+0_112M. 5.Decom existing ODU and Ant. FE_4947A 1.Install new 18G_SP_1.2M(MAC)+OMT. 2.Reuse existing 4947A_RTN01. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and traffic migrate to new link 18G_1+0_112M. 5.Decom existing ODU and Ant. | Existing link 13G_2+0_28M Swap existing link to 18G_1+0_112M. Site Impacted : 4117R NE_4117R 1.Install 18G_SP_1.2M(MAC)+OMT. 2.Reuse existing 4117R_RTN01. 3.Install XMC_3E , Sub A_Hi. 4.Create service cross connect and traffic migrate to new link 18G_1+0_112M. 5.Decom existing ODU and Ant. | Existing link 13G_2+0_28M Swap existing link to 18G_1+0_112M. Site Impacted : 4117R FE_4947A 1.Install new 18G_SP_1.2M(MAC)+OMT. 2.Reuse existing 4947A_RTN01. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and traffic migrate to new link 18G_1+0_112M. 5.Decom existing ODU and Ant. | XMC_3E | MAC | 18G | 1.2 | 1.2 | GTSB | SQ202508040494-GTSB | GTSB | SQ202508040521-GTSB // SQ202508040522-GTSB | 2025-11-07 | 2025-11-07 | Completed | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | KANNAN A/L RAMACHANDRAN6799000115 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251001B8 |  | 2025-10-03 | 2025-10-07 | Completed | 2025-10-02 | 2025-10-03 | 2025-10-01 | 2025-10-07 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-12 | 2025-10-31 | 2025-10-12 | 2025-10-16 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2025-10-12 | 2025-10-31 | 2025-10-12 | 2025-10-16 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-15 | 2025-10-12 | 2025-10-31 | 2025-10-12 | 2025-10-18 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | 2025-02-18: 2025-10-12; 2025-02-28: 2025-10-31; 2025-03-10: 2025-10-12; 2025-03-10: 2025-10-15 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | CHEONG/SENG/WAH/7018000306
4407D_HU | Taman Kemboja | DU00005244026 | Northern | Kedah | 5.643399 | 100.557986 | [7 empty] | 00. Integrated/RFS Done | 24/06: CO Done | TSS+TI | L1+ATP+PAC |  | IDU-IPRAN | need to do 1+1 LAG at 4770A |  | need 1+1 LAG at 4770A | [5 empty] | GCI | SQ202506300690-GCI | GCI | SQ202506250210-GCI | 2025-11-14 | 2025-11-07 | Completed | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-06-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-06-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-14 | 2025-11-07 | 2025-11-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061175 |  | 2025-06-12 | 2025-06-13 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-24 | 2025-07-15 | 2025-06-24 | 2026-04-20 | SITI NATRAH BINTI NASIRUN6800000142 | GCI TI | 2025-06-24 | 2025-06-30 | 2025-06-24 | 2025-07-06 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-24 | 2025-06-24 | 2025-06-30 | 2025-06-24 | 2025-07-16 | JUTI//ANAK RICHARD/6800000216 | 2025-02-18: 2025-06-24; 2025-02-28: 2025-06-30; 2025-03-10: 2025-06-24; 2025-03-10: 2025-07-15 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505070167-GTSB | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | HSU//MYET CHAE/6799000011
7747B_HU | By Tunku Estate | DU00005244027 | Sabah | Sabah | 5.706514 | 118.180758 |  |  |  |  | Drop/Cancel | Cancel/Drop |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Upgrade under DU 7747B NIC DU00002884346 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
8037Z_HU | Brook | DU00005244028 | Eastern | Kelantan | 4.675209 | 101.495277 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Solution similar to 8037Z under TX Rollout (DU00002885628) | Solution similar to 8037Z under TX Rollout (DU00002885628) | Solution similar to 8037Z under TX Rollout (DU00002885628) | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7078Z_HU | SabangMill | DU00005244029 | Sabah | Sabah | 6.329630 | 117.481230 | [5 empty] | MwAccessories-Coupler Bracket 13G x 4pc | ZTE | 00. Integrated/RFS Done | Non-doable | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_1.2/1.2_MDD XMC-5D_SB A, 4xISM8 | MW Parallel Link | MW NEWLINK 7078Z-7398A WITH 13G_4+0_1.2/1.2_MDD CARRY 7078Z TRAFFIC. | MW NEWLINK 7078Z-7398A WITH 13G_4+0_1.2/1.2_MDD NE: 1. Install new RTN910A and install ISM8 at Slot 3 and 4. 2. Install new XMC-5D_SB A. 3. Install new antenna 13G_1.2_MDD. 4. Configure 13G_4+0_1.2m_CA. 5. Carry 7078Z traffic. | MW NEWLINK 7078Z-7398A WITH 13G_4+0_1.2/1.2_MDD FE: 1. Install new RTN910A and install ISM8 at Slot 3 and 4. 2. Install new XMC-5D_SB A. 3. Install new antenna 13G_1.2_MDD. 4. Configure 13G_4+0_1.2m_CA. 5. Carry 7078Z traffic. | XMC-5D_SB A | MDD | 13G | 1.2 | 1.2 | NR services | SQ202602230063-NR Services | NR services | SQ202507290140-NR Services // SQ202507290144-NR Services |  |  | Ongoing | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-03 | 2026-04-10 | 2026-04-03 | 2026-04-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25071524 |  | 2025-07-16 | 2025-08-22 | Completed | 2025-07-15 | 2025-07-16 | 2025-07-15 | 2025-08-22 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-02-22 | 2026-01-22 | 2026-01-23 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-01-22 | 2026-02-22 | 2026-01-22 | 2026-02-07 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-12 | 2026-01-22 | 2026-02-22 | 2026-01-22 | 2026-02-23 | RALPH O'BRYAN HILARY7167000030 | 2025-02-18: 2026-01-22; 2025-02-28: 2026-02-22; 2025-03-10: 2026-01-22; 2025-03-10: 2026-01-23 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202602120275-GTSB
7179R_HU | Jalan Tenom Keningau | DU00005244030 | Sabah | Sabah | 5.168800 | 115.964360 |  |  |  |  | RFS |  |  | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE FROM 56MHz TO 112MHZ | REMOTE UPGRADE FROM 56MHz TO 112MHz | REMOTE UPGRADE FROM 56MHz TO 112MHz | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2025-05-29 | 2025-06-29 | 2025-05-29 | 2025-05-29 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
4687A_HU | Taman Meranti | DU00005244031 | Northern | Kedah | 5.360884 | 100.539723 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_4687A New 23G_DP_0.6M(MAC) x1. RTN910A x1. XMC_3E, Sub B_Lo x1. FE_4689A New 23G_SP_1.2M(MAC) x1. RTN910A x1. XMC_3E, Sub B_Hi x1. | MW Swap | Link Existing HW 23G_1+0_56M Swap existing link to new HW 23G_1+0_112M_512QAM Site Impacted : 4687A NE_4687A 1.Install new 23G_DP_0.6M(MAC) x1. 2.Install new RTN910A(RTN02). 3.Install new 1x XMC_3E, Sub B_Lo. Configure it. 4.Configure DCN Inband. 5.Migrate RAN traffic to new MW link. Configure it. 6.Decom existing MW link (IDU, ODU & Ant) if no other traffic backhauled. FE_4689A 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN05). 3.Install new 1x XMC_3E, Sub B_Hi. Configure it. 4.Configure DCN Inband. 5.Reuse existing port at IBeam. 6.Migrate RAN traffic to new MW link. Configure it. 7.Decom existing MW link (IDU, ODU & Ant) if no other traffic backhauled. | Link Existing HW 23G_1+0_56M Swap existing link to new HW 23G_1+0_112M_512QAM Site Impacted : 4687A NE_4687A 1.Install new 23G_DP_0.6M(MAC) x1. 2.Install new RTN910A(RTN02). 3.Install new 1x XMC_3E, Sub B_Lo. Configure it. 4.Configure DCN Inband. 5.Migrate RAN traffic to new MW link. Configure it. 6.Decom existing MW link (IDU, ODU & Ant) if no other traffic backhauled. | Link Existing HW 23G_1+0_56M Swap existing link to new HW 23G_1+0_112M_512QAM Site Impacted : 4687A FE_4689A 1.Install new 23G_SP_1.2M(MAC) x1. 2.Install new RTN910A(RTN05). 3.Install new 1x XMC_3E, Sub B_Hi. Configure it. 4.Configure DCN Inband. 5.Reuse existing port at IBeam. 6.Migrate RAN traffic to new MW link. Configure it. 7.Decom existing MW link (IDU, ODU & Ant) if no other traffic backhauled. | XMC_3E | MAC | 23G | 23G_DP_0.6M(MAC) x1. | 23G_SP_1.2M(MAC) x1. | GCI | SQ202507160591-GCI | GCI | SQ202507290116-GCI // SQ202507290119-GCI | 2026-01-26 | 2026-01-21 | Completed | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-08-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-19 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071548 |  | 2025-07-17 | 2025-07-17 | Completed | 2025-07-16 | 2025-07-17 | 2025-07-16 | 2025-07-17 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-25 | 2025-08-08 | 2025-07-25 | 2025-07-25 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-07-25 | 2025-08-08 | 2025-07-25 | 2025-08-30 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-28 | 2025-07-25 | 2025-08-08 | 2025-07-25 | 2025-09-04 | ANAS FIKRI ADHA BIN RAZMI6000009598 | 2025-07-25 | 2025-08-08 | 2025-07-25 | 2025-07-25 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB
4982B_HU | Selarong Panjang | DU00005244032 | Northern | Kedah | 5.404690 | 100.686915 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M NE_4982B 13G_DP_1.8M(MDD) x1. RTN910A x1 XMC_5D , Sub B_Lo x1. ISM8 x2. FE_K00416 13G_DP_1.2(MDD) x1. RTN910A. x1. XMC_5D , Sub B_Hi x1. ISM8 x2. | MW New Link / Reroute | Install new MW link/Reroute with 13G_4+0_28M to support child site 4963B , refer DU ID 4963B_HU ( DU code : DU00005826245). 2nd Priority to install 4982B - K00416. Site Impacted : 4963B NE_4982B 1.Install new 13G_DP_1.8M(MDD). 2.Install new RTN910A.(RTN no will provide by Ops team). 3.Install new XMC_5D , Sub B_Lo. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , ETH cable interconnect to existing 4982B_RTN03_GE1 ( ID : 27994). 7. Decom existing MW link 4982B_RTN02 to 4954B_RTN02.After traffic successful migrate to new route with new ETH cable interconnect to existing 4982B_RTN03_GE1 (ID : 27994) , pls refer DU ID 4963B_HU as well. FE_K00416 1.Install new 13G_DP_1.2(MDD). 2.Install new RTN910A. ( RTN no will provide by GOP team). 3.Install new XMC_5D , Sub B_Hi. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Enable GE1 , interconnect ETH between new RTN910A ( New RTN910A under DU ID K00416_HU). 6.Create service cross connect , CA and EPLA. 7.Decom existing MW link 4982B_RTN02 to 4954B_RTN02.After traffic successful migrate to new route with new ETH cable interconnect to existing 4982B_RTN03_GE1 (ID : 27994) , pls refer DU ID 4963B_HU as well. | Install new MW link/Reroute 13G_4+0_28M to support child site 4963B , refer DU ID 4963B_HU ( DU code : DU00005826245). 2nd Priority to install 4982B - K00416. Site Impacted : 4963B NE_4982B 1.Install new 13G_DP_1.8M(MDD). 2.Install new RTN910A.(RTN no will provide by Ops team). 3.Install new XMC_5D , Sub B_Lo. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , CA and EPLA. 6.Enable GE1 , ETH cable interconnect to existing 4982B_RTN03_GE1 ( ID : 27994). 7. Decom existing MW link 4982B_RTN02 to 4954B_RTN02.After traffic successful migrate to new route with new ETH cable interconnect to existing 4982B_RTN03_GE1 (ID : 27994) , pls refer DU ID 4963B_HU as well. | Install new MW link 13G_4+0_28M to support child site 4963B , refer DU ID 4963B_HU ( DU code : DU00005826245). 2nd Priority to install 4982B - K00416. Site Impacted : 4963B FE_K00416 1.Install new 13G_DP_1.2(MDD). 2.Install new RTN910A. ( RTN no will provide by GOP team). 3.Install new XMC_5D , Sub B_Hi. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Enable GE1 , interconnect ETH between new RTN910A ( New RTN910A under link K00416-4968A). 6.Create service cross connect , CA and EPLA. 7. Decom existing MW link 4982B_RTN02 to 4954B_RTN02.After traffic successful migrate to new route with new ETH cable interconnect to existing 4982B_RTN03_GE1 (ID : 27994) , pls refer DU ID 4963B_HU as well. | XMC_5D | MDD | 13G | 1.8 | 1.2 | Magicell | SQ202508060640-Magicell | Magicell | SQ202508060644-Magicell // SQ202508060648-Magicell | 2025-11-27 | 2025-11-26 | Completed | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080801 |  | 2026-08-12 | 2025-08-28 | Completed | 2025-08-14 | 2026-08-12 | 2025-08-14 | 2025-08-28 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-14 | 2026-08-12 | 2025-08-14 | 2025-08-28 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-08-14 | 2026-08-12 | 2025-08-14 | 2025-08-28 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-14 | 2025-08-14 | 2026-08-12 | 2025-08-14 | 2025-08-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-02-18: 2025-08-14; 2025-02-28: 2026-08-12; 2025-03-10: 2025-08-14; 2025-03-10: 2025-08-14 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507190085-GCI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | CHEONG/SENG/WAH/7018000306
4769B_HU | Jln Tun Razak (maxis) | DU00005244033 | Northern | Kedah | 6.143663 | 100.380243 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M NE_4769B 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. FE_4678A. 18G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing link 15G_4+0_28M Install parallel link 18G_2+0_112M Site Impacted : 4769B , 4086K/K00063. NE_4769B 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0 (RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo. 4.Create cross connect and EPLA. 5.Enable GE1 , 4769B traffic migrate to new parallel link 18G_2+0_112M. 6.No decomm existing MW link. FE_4678A. 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0 (RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.No decomm existing MW link. | Existing link 15G_4+0_28M Install parallel link 18G_2+0_112M Site Impacted : 4769B , 4086K/K00063. NE_4769B 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0 (RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo. 4.Create cross connect and EPLA. 5.Enable GE1 , 4769B traffic migrate to new parallel link 18G_2+0_112M. 6.No decomm existing MW link. | Existing link 15G_4+0_28M Install parallel link 18G_2+0_112M Site Impacted : 4769B , 4086K/K00063. FE_4678A. 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0 (RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.No decomm existing MW link. | XMC_5D | MDD | 18G | 0.6 | 1.2 | GCI | SQ202507160591-GCI | GCI | SQ202510070041-GCI // SQ202510070042-GCI | 2025-09-27 | 2025-09-26 | Completed | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-08-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092651 |  | 2025-09-27 | 2025-09-29 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-09 | 2025-10-14 | 2025-10-09 | 2025-10-09 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-10-09 | 2025-10-14 | 2025-10-09 | 2025-10-22 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-11 | 2025-10-09 | 2025-10-14 | 2025-10-09 | 2025-10-20 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-02-18: 2025-10-09; 2025-02-28: 2025-10-14; 2025-03-10: 2025-10-09; 2025-03-10: 2025-10-18 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | CHEONG/SENG/WAH/7018000306
4755C_HU | Setia Vista | DU00005244034 | Northern | Penang | 5.340809 | 100.268255 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | CANCEL DROP DUE TO UNDER DU TX MINI 4755C-4034A | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4174A_HU | LBSB Factory | DU00005244035 | Northern | Penang | 5.354917 | 100.408861 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | MW HU closed by MSP WK12 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7338C_HU | Kg.Mambalua | DU00005244036 | Sabah | Sabah | 4.250640 | 118.012571 |  |  |  | JUN 25 | In Plan | TI DONE | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 112MHz 0.6m/0.6m XMC3E NE: 1) 1xISM8 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz 0.6m SP FE: 1) 1xISM8 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz 0.6m SP | MW Swap | To swap Existing link 15GHz 1+0 with new Huawei link 18GHz 1+0 112MHz NE (7338C): 1) Install new ISM8 card at existing RTN slot 3 2) Install new link at 3-ISM8-1 3) Migrate traffic to new link 4) Decom existing link FE (7206A RTN02): 1) Install new ISM8 card at RTN02 slot 1 2) Install new link at RTN02 1-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | NE (7338C): 1) Install new ISM8 card at existing RTN slot 3 2) Install new link at 3-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | FE (7206A RTN02): 1) Install new ISM8 card at RTN02 slot 1 2) Install new link at RTN02 1-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | XMC3E | MAC SP | 18G | 0.6m | 0.6m | NR services | SQ202506190628-NR Services | NR services | SQ202506160529-NR Services // SQ202506160577-NR Services | 2025-07-04 | 2025-06-30 | Completed | 2025-06-17 | 2025-06-18 | 2025-06-17 | 2025-06-18 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-19 | 2025-06-20 | 2025-06-19 | 2025-06-19 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-30 | 2025-07-04 | 2025-06-30 | 2025-06-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051623 |  | 2025-05-17 | 2025-05-19 | Completed | 2025-05-16 | 2025-05-17 | 2025-05-16 | 2025-05-19 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-16 | 2025-07-16 | 2025-06-16 | 2025-06-16 | WILFRED BALANG7167000026 | NR Service TI | 2025-06-16 | 2025-07-16 | 2025-06-16 | 2025-07-06 | WILFRED BALANG7167000026 | NR Service TI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-16 | 2025-06-16 | 2025-07-16 | 2025-06-16 | 2025-08-12 | WILFRED BALANG7167000026 | 2025-06-16 | 2025-07-16 | 2025-06-16 | 2025-06-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507080638-GTSB | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | HSU//MYET CHAE/6799000011
4265B_HU | Bandar Putri Jaya 2 | DU00005244037 | Northern | Kedah | 5.607045 | 100.528034 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M CA. NE_4256B 13G_DP_0.6M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Lo x1. FE_4770A 13G_DP_1.2M(MDD). ISM8 x2. XMC_5D , Sub A_Hi x1. | MW Swap | Existing link 15G_2+0_28M+18G_2+0_112M (4265B-4770A) , 100% HU. Distance 5.4KM. Swap existing link 15G_2+0_28M to 13G_4+0_28M CA. Site Impacted : 4256B NE_4256B 1.Install new 13G_DP_0.6M(MDD). 2.Reuse existing 4256B_RTN02 (ID : 13877). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 4256B_RTN02. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA new link and existing 18G link. 6.Traffic migrate to new link 13G_4+0_28M CA. 7.Decom existing ODU and ANT. FE_4770A 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4770A_RTN12( ID : 13799). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 4770A_RTN12. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA new link and existing 18G link. 6.Traffic migrate to new link 13G_4+0_28M CA. 7.Existing LAG created. 8.Decom existing ODU and ANT. | Existing link 15G_2+0_28M+18G_2+0_112M (4265B-4770A) , 100% HU. Distance 5.4KM. Swap existing link 15G_2+0_28M to 13G_4+0_28M CA. Site Impacted : 4256B NE_4256B 1.Install new 13G_DP_0.6M(MDD). 2.Reuse existing 4256B_RTN02 (ID : 13877). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 4256B_RTN02. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA new link and existing 18G link. 6.Traffic migrate to new link 13G_4+0_28M CA. 7.Decom existing ODU and ANT. | Existing link 15G_2+0_28M+18G_2+0_112M (4265B-4770A) , 100% HU. Distance 5.4KM. Swap existing link 15G_2+0_28M to 13G_4+0_28M CA. Site Impacted : 4256B FE_4770A 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4770A_RTN12( ID : 13799). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 4770A_RTN12. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA new link and existing 18G link. 6.Traffic migrate to new link 13G_4+0_28M CA. 7.Existing LAG created. 8.Decom existing ODU and ANT. | XMC_5D | MDD | 15G | 0.6 | 1.2 | NWAVE | SQ202508200590-N-Wave | NWAVE | SQ202508200581-N-Wave // SQ202508200586-N-Wave // SQ202510160486-N-Wave | 2026-01-15 | 2026-01-16 | Completed | 2025-09-22 | 2025-10-22 | 2025-09-22 | 2025-09-23 | Khairul Azman Bin Din7160000001 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082047 |  | 2025-08-21 | 2025-08-26 | Completed | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-10-22 | 2025-09-22 | 2025-09-23 | Khairul Azman Bin Din7160000001 | NWAVE TI | 2025-09-22 | 2025-10-22 | 2025-09-22 | 2025-09-29 | Khairul Azman Bin Din7160000001 | NWAVE TI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | AKMAL//BIN RAZALI/6794000078 |  |  | 2025-09-22 | 2025-10-22 | 2025-09-22 | 2025-10-09 | Khairul Azman Bin Din7160000001 | 2025-09-22 | 2025-10-22 | 2025-09-22 | 2025-09-23 | 2026-01-18 | 2026-01-18 | 2026-01-18 | 2026-01-18 | NG HONG JIE7018000036 | Logistic Team | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150530-GCI | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | CHEONG/SENG/WAH/7018000306
4260B_HU | KG NAWA | DU00005244038 | Northern | Kedah | 6.116903 | 100.514197 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M Site Impacted : 4049R , 4700D. NE_4260B 18G_DP_1.2M(MDD) x1. ISM8 x1. FE_4261B 18G_DP_0.6M(MDD) x1. ISM8 x1 XMC_5D , Sub B_Lo x1. | MW Swap | Existing link 18G_1+0_56M and 15G_2+0_28M , Not support remote upgrade to 112M. Swap existing 18G_1+0_56M to 18G_2+0_112M and EPLA with existing 15G_2+0_28M Site Impacted : 4049R , 4700D. NE_4260B 1.Install new 18G_DP_1.2M(MDD) 2.Reuse existing 4260B_RTN03. 3.Install new 4_ISM8-2+0 into existing 4260B_RTN03 (ID: 30261). 4.Install new XMC_5D , Sub B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 18G_2+0_112M and EPLA with existing 15G_2+0_28M. 7.Decom existing 18G ODU , 3_ISM6 and Ant. FE_4261B 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4261B_RTN04. 3.Install new 4_ISM8-2+0 into existing 4261B_RTN04.(ID : 30260). 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 18G_2+0_112M and EPLA with existing 15G_2+0_28M. 7.Decom existing 18G ODU , 3_ISM6 and Ant. | Existing link 18G_1+0_56M and 15G_2+0_28M , Not support remote upgrade to 112M. Swap existing 18G_1+0_56M to 18G_2+0_112M and EPLA with existing 15G_2+0_28M Site Impacted : 4049R , 4700D. NE_4260B 1.Install new 18G_DP_1.2M(MDD) 2.Reuse existing 4260B_RTN03. 3.Install new 4_ISM8-2+0 into existing 4260B_RTN03 (ID: 30261). 4.Install new XMC_5D , Sub B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 18G_2+0_112M and EPLA with existing 15G_2+0_28M. 7.Decom existing 18G ODU , 3_ISM6 and Ant. | Existing link 18G_1+0_56M and 15G_2+0_28M , Not support remote upgrade to 112M. Swap existing 18G_1+0_56M to 18G_2+0_112M and EPLA with existing 15G_2+0_28M Site Impacted : 4049R , 4700D. FE_4261B 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4261B_RTN04. 3.Install new 4_ISM8-2+0 into existing 4261B_RTN04.(ID : 30260). 4.Install new XMC_5D , Sub B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 18G_2+0_112M and EPLA with existing 15G_2+0_28M. 7.Decom existing 18G ODU , 3_ISM6 and Ant. | XMC_5D | MDD | 18G | 1.2 | 0.6 | GTSB | SQ202507110773-GTSB | GTSB | SQ202507110777-GTSB // SQ202507110781-GTSB | 2025-11-20 | 2025-11-24 | Completed | [8 empty] | Unassigned | Disabled |  | 2025-08-11 | 2025-08-23 | 2025-08-11 | 2025-08-12 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092650 |  | 2025-09-27 | 2025-09-30 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-09 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-16 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-10 | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-16 | HAMZAH BIN ABDUL MUTALIF6799000301 | 2025-02-18: 2025-10-06; 2025-02-28: 2025-10-06; 2025-03-10: 2025-10-06; 2025-03-10: 2025-10-09 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | CHEONG/SENG/WAH/7018000306
4272A_HU | Permatang Bera 2 | DU00005244039 | Northern | Penang | 5.509877 | 100.384527 | [5 empty] | TI WIP | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M_256QAM_CA&EPLA LINK 1 NE_4272A New 15G_1.2M(MDD) x1. New RTN910A x1. New ISM8 x1. New XMC_5D, Sub B_Hi x1. FE_4276A New 15G_1.2M(MDD) x1. New RTN910A x1. New ISM8 x1. XMC_5D, Sub B_Lo x1. | MW Parallel Link | Adding new MW parallel Link HW(LINK 1 - 15G_4+0_28M_256QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_256QAM_CA&EPLA) and final become 15G_6+0_28M_256QAM_CA&EPLA with total capacity 1200Mbps. Perform LAG for 2x 1G port at IBeam. LINK 1 use 4272A_HU and LINK 2 use 4272A_1_HU. 2 separate DU will be created. Site Impacted : 4272A & 4286A. LINK 1 NE_4272A 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN04). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN04). Configure it. 5.Configure CA & EPLA for LINK 1 & LINK 2(see below) and become 15G_6+0_28MHz_256QAM_CA&EPLA. 6.Configure DCN Inband. 7.Remove cascading in between RTN910A(RTN03) & RTN910A(RTN11). 8.Later, perform cascading in between port 8-EM6-1 of existing RTN910A(RTN03) & port 8-EM6-1 of new RTN910A(RTN04). Configure it. 9.Enable port 8-EM6-2 of RTN910A(RTN04) and patching to BBU 4272A. 10.Migrate RAN Traffics(4272A & 4286A)traffic to new HW MW link 15G_6+0_28MHz_256QAM_CA&EPLA. Configure it. 11.Do not decom existing HW MW Link 4272A(RTN11)-4276A(RTN11) as its still backhauling existing traffic for child site 4631D ONLY. FE_4276A 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN05). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN05). Configure it. 5.Configure CA & EPLA for LINK 1 & LINK 2(see below) and become 15G_6+0_28MHz_256QAM_CA&EPLA. 6.Configure DCN Inband. 7.Request 2x 1G new port at IBeam from ZTE IPRAN team and enable and patching to port 8-EM6-1 & port 8-EM6-2 of RTN910A(RTN05). 8.Both port need to perform LAG. 9.Migrate RAN Traffics(4272A & 4286A)traffic to new HW MW link 15G_6+0_28MHz_256QAM_CA&EPLA. Configure it. 10.Do not decom existing HW MW Link 4272A(RTN11)-4276A(RTN11) as its still backhauling existing traffic for child site 4631D ONLY. LINK 2 NE_4272A 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN04). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_256QAM_CA&EPLA. 5.Do not decom existing HW MW Link 4272A(RTN11)-4276A(RTN11) as its still backhauling existing traffic for child site 4631D ONLY. FE_4276A 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN05). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_256QAM_CA&EPLA. 5.Do not decom existing HW MW Link 4272A(RTN11)-4276A(RTN11) as its still backhauling existing traffic for child site 4631D ONLY. | Adding new MW parallel Link HW(LINK 1 - 15G_4+0_28M_256QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_256QAM_CA&EPLA) and final become 15G_6+0_28M_256QAM_CA&EPLA with total capacity 1200Mbps. Perform LAG for 2x 1G port at IBeam. LINK 1 use 4272A_HU and LINK 2 use 4272A_1_HU. 2 separate DU will be created. Site Impacted : 4272A & 4286A. LINK 1 NE_4272A 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN04). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN04). Configure it. 5.Configure CA & EPLA for LINK 1 & LINK 2(see below) and become 15G_6+0_28MHz_256QAM_CA&EPLA. 6.Configure DCN Inband. 7.Remove cascading in between RTN910A(RTN03) & RTN910A(RTN11). 8.Later, perform cascading in between port 8-EM6-1 of existing RTN910A(RTN03) & port 8-EM6-1 of new RTN910A(RTN04). Configure it. 9.Enable port 8-EM6-2 of RTN910A(RTN04) and patching to BBU 4272A. 10.Migrate RAN Traffics(4272A & 4286A)traffic to new HW MW link 15G_6+0_28MHz_256QAM_CA&EPLA. Configure it. 11.Do not decom existing HW MW Link 4272A(RTN11)-4276A(RTN11) as its still backhauling existing traffic for child site 4631D ONLY. | Adding new MW parallel Link HW(LINK 1 - 15G_4+0_28M_256QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_256QAM_CA&EPLA) and final become 15G_6+0_28M_256QAM_CA&EPLA with total capacity 1200Mbps. Perform LAG for 2x 1G port at IBeam. LINK 1 use 4272A_HU and LINK 2 use 4272A_1_HU. 2 separate DU will be created. Site Impacted : 4272A & 4286A. LINK 1 FE_4276A 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN05). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN05). Configure it. 5.Configure CA & EPLA for LINK 1 & LINK 2(see below) and become 15G_6+0_28MHz_256QAM_CA&EPLA. 6.Configure DCN Inband. 7.Request 2x 1G new port at IBeam from ZTE IPRAN team and enable and patching to port 8-EM6-1 & port 8-EM6-2 of RTN910A(RTN05). 8.Both port need to perform LAG. 9.Migrate RAN Traffics(4272A & 4286A)traffic to new HW MW link 15G_6+0_28MHz_256QAM_CA&EPLA. Configure it. 10.Do not decom existing HW MW Link 4272A(RTN11)-4276A(RTN11) as its still backhauling existing traffic for child site 4631D ONLY. | XMC_5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | CCSMY | SQ202504280454-CCS | CCSMY | SQ202505190351-CCS // SQ202505190357-CCS | 2025-08-09 | 2025-08-12 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-20 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | ainfatinainfatin28@gmail.com |  |  | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-08 | 2025-08-09 | 2025-08-08 | 2025-08-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25043074 |  | 2025-05-01 | 2025-05-10 | Completed | 2025-04-30 | 2025-05-01 | 2025-04-30 | 2025-05-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-14 | 2025-05-31 | 2025-05-14 | 2025-06-04 | Muhammad Afiq Bin Mat Jalil7539000007 | CCS TI | 2025-05-14 | 2025-05-31 | 2025-05-14 | 2025-07-11 | Muhammad Afiq Bin Mat Jalil7539000007 | CCS TI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-14 | 2025-05-31 | 2025-05-14 | 2026-03-31 | Muhammad Afiq Bin Mat Jalil7539000007 | 2025-02-18: 2025-05-14; 2025-02-28: 2025-05-31; 2025-03-10: 2025-05-14; 2025-03-10: 2025-07-04 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202504140801-GCI | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | CHEONG/SENG/WAH/7018000306
9979A_HU | Taman Matang | DU00005244040 | Sarawak | Sarawak | 1.575161 | 110.280586 |  |  |  |  | Pending SOW |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 112MHz 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz 0.6m SP FE: 1) 1xISM8 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz 0.6m SP | MW Swap | To swap Existing link 23GHz 1+0 56MHz with new Huawei link 23GHz 1+0 112MHz NE (9979A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link FE (9458A): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at RTN01 3-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | NE (9979A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | FE (9458A): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at RTN01 3-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | XMC3 | MAC S | 23G | 0.6m | 1.2m | Allstar | SQ202506160462-Allstar | Allstar | SQ202509040262-Allstar // SQ202509040270-Allstar | 2025-07-11 | 2025-07-07 | Completed | 2025-05-28 | 2025-05-29 | 2025-06-13 | 2025-06-13 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-04 | 2025-07-02 | 2025-07-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-04 | 2025-07-02 | 2025-07-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25101734 |  | 2025-10-18 | 2025-10-18 | Completed | 2025-10-17 | 2025-10-18 | 2025-10-17 | 2025-10-18 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-17 | 2025-10-23 | 2025-10-21 | 2025-10-21 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-10-17 | 2025-10-23 | 2025-10-27 | 2025-10-27 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-22 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-22 | 2025-10-17 | 2025-10-23 | 2025-11-07 | 2025-11-07 | BONG NEE NYEEbong.allstar@gmail.com | 2025-10-17 | 2025-10-23 | 2025-10-18 | 2025-10-18 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-21 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202507080651-GTSB | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | HSU//MYET CHAE/6799000011
7056C_HU | Taman Fajar lahad datu | DU00005244041 | Sabah | Sabah | 5.026186 | 118.322731 |  |  |  |  | RFS | DONE |  | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE FROM 18G_56Mhz_450M to 18G_110Mhz_889M | MW REMOTE UPGRADE FROM 18G_56Mhz_450M to 18G_110Mhz_889M Configure 18G_1+0_110Mhz_889M | MW REMOTE UPGRADE FROM 18G_56Mhz_450M to 18G_110Mhz_889M Configure 18G_1+0_110Mhz_889M | [5 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 | [17 empty] | 2025-05-29 | 2025-06-29 | 2025-05-29 | 2025-05-29 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
9254B_HU | Kanowit Town 1 | DU00005244042 | Sarawak | Sarawak | 2.113537 | 112.152055 |  |  |  |  | Pending SOW |  |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | under NIC upgrade DU00002884412 MOCN date 20_04_2025 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
S01593_HU | S088A_S01593OD_LUMADANPALMOILMILL | DU00005244043 | Sabah | Sabah | 5.232270 | 115.648000 |  |  |  |  | DT February |  |  | 04. BOM / Material Issue |  | TSS+AA+TI+Dismantle |  | 18G_2+0_55M_512QAM_EPLA. NE_S01593 New 18G_1.2M(MDD) x1. New RTN910AF. New XMC_5D Pro, Sub A_Hi x1. New CAT6 cable x1. FE_S00640 New 18G_1.2M(MDD) x1. New RTN910AF. New XMC_5D Pro, Sub A_Lo x1. New CAT6 cable x1. | MW Swap | Existing HW MW Link_S01593-S00640, 15G_1+1 HSB_28MHZ_256QAM_183M. MW Swap to new HW MW Link S01593-S00640, 18G_2+0_55MHZ_512QAM_EPLA_900M. Later, decom existing HW MW Link_S01593-S00640, 15G_1+1 HSB_28MHZ_256QAM_183M. Site Impacted : S01593. NE_S01593 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Re-use existing xC vlan dcn and vlan services. 5.Migrate traffic S01593 via new HW MW Link S01593-S00640, 18G_2+0_55MHZ_512QAM_EPLA_900M. 6.Later, decom existing HW MW Link_S01593-S00640, 15G_1+1 HSB_28MHZ_256QAM_183M. FE_S00640 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Re-use existing xC vlan dcn and vlan services. 5.Migrate traffic S01593 via existing port of PTN/Cisco Router. 6.Later, decom existing HW MW Link_S01593-S00640, 15G_1+1 HSB_28MHZ_256QAM_183M. | Existing HW MW Link_S01593-S00640, 15G_1+1 HSB_28MHZ_256QAM_183M. MW Swap to new HW MW Link S01593-S00640, 18G_2+0_55MHZ_512QAM_EPLA_900M. Later, decom existing HW MW Link_S01593-S00640, 15G_1+1 HSB_28MHZ_256QAM_183M. Site Impacted : S01593. NE_S01593 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Re-use existing xC vlan dcn and vlan services. 5.Migrate traffic S01593 via new HW MW Link S01593-S00640, 18G_2+0_55MHZ_512QAM_EPLA_900M. 6.Later, decom existing HW MW Link_S01593-S00640, 15G_1+1 HSB_28MHZ_256QAM_183M. | Existing HW MW Link_S01593-S00640, 15G_1+1 HSB_28MHZ_256QAM_183M. MW Swap to new HW MW Link S01593-S00640, 18G_2+0_55MHZ_512QAM_EPLA_900M. Later, decom existing HW MW Link_S01593-S00640, 15G_1+1 HSB_28MHZ_256QAM_183M. Site Impacted : S01593. FE_S00640 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Re-use existing xC vlan dcn and vlan services. 5.Migrate traffic S01593 via existing port of PTN/Cisco Router. 6.Later, decom existing HW MW Link_S01593-S00640, 15G_1+1 HSB_28MHZ_256QAM_183M. | XMC_5D Pro | MDD | 18G | 18G_1.2M(MDD) x1 | 18G_1.2M(MDD) x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505020434-GTSB
3354A_HU | pBTS SP Heights | DU00005244044 | Northern | Kedah | 5.630889 | 100.545155 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | CANCEL/DROP. USE DU 3354A-4770A_1 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4031A_HU | GeorgeTownHotel (Trunk) | DU00005244045 | Northern | Penang | 5.433889 | 100.308331 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Please refer to DU ID 4058A_HU (DU Code DU00005172942) , due to 4031A is FE site ID. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505020432-GCI | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | CHEONG/SENG/WAH/7018000306
9511B_HU | Kampung Bakong | DU00005244046 | Sarawak | Sarawak | 1.321881 | 111.305005 |  |  |  |  | Pending SOW |  |  | 00. Site Out/Drop | Site drop. |  |  |  | Cancel / Drop | 9511B_HU created before MOCN Mar 2025 9511B RAN decom. Pair Q00997 Q00997 MOCN Apr 2025 | [7 empty] | Trintel | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7421B_HU | Kg. Suan Lamba SBC | DU00005244047 | Sabah | Sabah | 5.577336 | 118.139746 |  |  |  |  | Drop/Cancel |  |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Upgrade done under DU 7421B_Additional DU00004502320 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1069A_HU | Lembah Beringin | DU00005244048 | Central | Selangor | 3.572448 | 101.536463 |  |  |  |  | Cancel / Drop | Change to DU 2437A_HU | ZTE | 00. Site Out/Drop | 18/4/2025 : No need proceed. CHANGE TO DU 2437A_HU |  |  |  | Cancel / Drop | CHANGE TO DU 2437A_HU | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
A00600_HU | A042C_A00600OD_CKTJERINGTOWN | DU00005244049 | Northern | Perak | 4.789891 | 100.726453 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | A00600 is Colo site for 4408D. OB Fiber A00600 will be relocate to 4408D. 4408D BBU direct patching to OB Fiber Port. Same solution for DU ID 4408D (DU00002885721) under TX Rollout. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4406D_HU | Puncak Surya | DU00005244050 | Northern | Kedah | 5.627960 | 100.558454 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_4406D New 23G_DP_0.6M(MAC)+OMT x1. New XMC_3E, Sub B_Hi x2. FE_4770A New 23G_DP_1.2M(MAC)+OMT x2. New XMC_3E, Sub B_Lo x2. | MW Swap | Link Existing HW 23G_1+0_112M Swap existing link to new HW 23G_2+0_112M_512QAM Site Impacted : 4406D NE_4406D 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing RTN910A(RTN01). 3.Install new 2x XMC_3E , Sub B_Hi. Configure it. 4.Configure DCN Inband. 5.Migrate RAN traffic to new MW link. 6.Decom existing MW link (ODU & Ant). FE_4770A 1.Install new 23G_DP_1.2M(MAC)+OMT. 2.Reuse existing RTN910A(RTN17). 3.Install new 2x XMC_3E , Sub B_Lo. Configure it. 4.Configure DCN Inband. 5.Migrate RAN traffic to new MW link. 6.Reuse existing port at IBeam. 7.Decom existing MW link (ODU & Ant). | Swap existing link to new HW 23G_2+0_112M_512QAM Site Impacted : 4406D NE_4406D 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing RTN910A(RTN01). 3.Install new 2x XMC_3E , Sub B_Hi. Configure it. 4.Configure DCN Inband. 5.Migrate RAN traffic to new MW link. 6.Decom existing MW link (ODU & Ant). | Link Existing HW 23G_1+0_112M Swap existing link to new HW 23G_2+0_112M_512QAM Site Impacted : 4406D FE_4770A 1.Install new 23G_DP_1.2M(MAC)+OMT. 2.Reuse existing RTN910A(RTN17). 3.Install new 2x XMC_3E , Sub B_Lo. Configure it. 4.Configure DCN Inband. 5.Migrate RAN traffic to new MW link. 6.Reuse existing port at IBeam. 7.Decom existing MW link (ODU & Ant). | XMC_3E | MAC | 23G | 23G_DP_0.6M(MAC)+OMT x1. | 23G_DP_1.2M(MAC)+OMT x1. | GCI | SQ202505240071-GCI | GCI | SQ202505190405-GCI // SQ202505190415-GCI // SQ202508140739-GCI | 2025-10-24 | 2025-10-24 | Completed | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050934 |  | 2025-05-10 | 2025-05-14 | Completed | 2025-05-09 | 2025-05-10 | 2025-05-09 | 2025-05-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-05-20 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-06-03 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-07-11 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-05-21 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB
W01132_HU | W066S_W01132OD_DE_EARTH_PUCHONG | DU00005244051 | Central | Kuala Lumpur | 3.048470 | 101.672100 |  | APR 25 |  | APR 25 | DO | Doable, just waiting material | ZTE | 00. Integrated/RFS Done | 21/4/2025 : ASIASPACE SDN BHD - TOWER 61M LAND - NE site W01132 W066S_W01132OD_DE_EARTH_PUCHONG, ASIASPACE SDN BHD - TOWER 61M LAND - FE site W00053 W066R_W00053OD_PR_TPM | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap | MW SWAP LINK W01132-W00053 (ALREADY RELOCATE AS A 3666A RTN03 RTN905-1855B RTN01 RTN905) WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_2.08KM IMPACTED: W01132, 3666A, 1457K, 1448K, 1370B DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 18G | 0.6 | 0.6 | GTSB | SQ202505020369-GTSB | GTSB | SQ202504240805-GTSB // SQ202504240806-GTSB | 2025-10-31 | 2025-10-24 | Completed | 2025-04-24 | 2025-06-09 | 2025-06-09 | 2025-06-09 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-29 | 2025-06-12 | 2025-05-29 | 2025-05-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-24 | 2025-10-31 | 2025-10-24 | 2025-10-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050948 |  | 2025-05-10 | 2025-05-15 | Completed | 2025-05-09 | 2025-05-10 | 2025-05-09 | 2025-05-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2025-06-08 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2025-06-08 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | GTSB TI | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-22 | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2025-06-08 | MUHAMMAD AMIRUL BIN KHAMIS6799000229 | 2025-05-16 | 2025-05-31 | 2025-05-16 | 2025-05-22 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202507080560-GTSB
4425A_HU | Changkat Lobak RDD | DU00005244052 | Northern | Perak | 5.131190 | 100.627210 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1.2x SFP Module 10G 1310nm 40Km.(1x Cisco/PTN and 1x Huawei RTN910A) 2.2xPatchcord LC-2K with suitable length(or equivalent). | MW IDU Patching | MW IDU Patching need to perform at 4425A in order for diverting traffic 4538D & 4146R from existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) to existing xC PTN A00064. *PLEASE DO NOT TOUCH BBU 4425A IN WHICH ALREADY DIVERT THE TRAFFIC TO A00064 LAST TIME* *PLEASE DO NOT DECOM EXISTING XD HW MW LINK 4425A(RTN01)-4773A(RTN01) FOR FUTURE USE* Site Impacted : 4538D & 4146R. NE_4425A/A00064 1.Disable port 8-EM6-1(RTN910A-RTN02). 2.Disable port 8-EG6-3(RTN910A-RTN01). 3.Remove cascading between RTN01(port 8-EG6-3) and RTN02(port 8-EM6-1). 4.Insert suitable 10G SFP Module into existing PTN at A00064(request new port and new vlan services from IPRAN Team). 5.Also insert suitable 10G SFP Module into existing port 8-EM6-3 of RTN910A(RTN02) at 4425A. 6.Patching new Fiber patch cord cable from existing PTN(new port) at A00064 to port 8-EM6-3 of existing RTN910A(RTN02) at 4425A and configure it. 7.Configure DCN Inband for RTN02. 8.Later, after diverting traffics for 4538D & 4146R success to xC A00064 and ensure no other traffic backhaul via existing xD HW MW Link 4425A(RTN01)-4773A(RTN01). 9.Please do not decom existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) - for future plan use. FE_4770A 1. Please disable existing port of IBeam that had been use priviously for carry traffics 4538D & 4146R. 2.Please do not decom existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) - for future plan use. | MW IDU Patching need to perform at 4425A in order for diverting traffic 4538D & 4146R from existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) to existing xC PTN A00064. *PLEASE DO NOT TOUCH BBU 4425A IN WHICH ALREADY DIVERT THE TRAFFIC TO A00064 LAST TIME* *PLEASE DO NOT DECOM EXISTING XD HW MW LINK 4425A(RTN01)-4773A(RTN01) FOR FUTURE USE* Site Impacted : 4538D & 4146R. NE_4425A/A00064 1.Disable port 8-EM6-1(RTN910A-RTN02). 2.Disable port 8-EG6-3(RTN910A-RTN01). 3.Remove cascading between RTN01(port 8-EG6-3) and RTN02(port 8-EM6-1). 4.Insert suitable 10G SFP Module into existing PTN at A00064(request new port and new vlan services from IPRAN Team). 5.Also insert suitable 10G SFP Module into existing port 8-EM6-3 of RTN910A(RTN02) at 4425A. 6.Patching new Fiber patch cord cable from existing PTN(new port) at A00064 to port 8-EM6-3 of existing RTN910A(RTN02) at 4425A and configure it. 7.Configure DCN Inband for RTN02. 8.Later, after diverting traffics for 4538D & 4146R success to xC A00064 and ensure no other traffic backhaul via existing xD HW MW Link 4425A(RTN01)-4773A(RTN01). 9.Please do not decom existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) - for future plan use. | MW IDU Patching need to perform at 4425A in order for diverting traffic 4538D & 4146R from existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) to existing xC PTN A00064. *PLEASE DO NOT TOUCH BBU 4425A IN WHICH ALREADY DIVERT THE TRAFFIC TO A00064 LAST TIME* *PLEASE DO NOT DECOM EXISTING XD HW MW LINK 4425A(RTN01)-4773A(RTN01) FOR FUTURE USE* Site Impacted : 4538D & 4146R. FE_4770A 1. Please disable existing port of IBeam that had been use priviously for carry traffics 4538D & 4146R. 2.Please do not decom existing xD HW MW Link 4425A(RTN01)-4773A(RTN01) - for future plan use. | [5 empty] | NWAVE | SQ202507160641-N-Wave | NWAVE | SQ202505190428-N-Wave | 2025-08-19 | 2025-08-19 | Completed | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-07-31 | 2025-07-31 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-19 | 2025-08-18 | 2025-08-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051599 |  | 2025-05-31 | 2025-07-15 | Completed | 2025-05-29 | 2025-05-31 | 2025-05-29 | 2025-07-15 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-15 | Khairul Azman Bin Din7160000001 |  | 2025-05-29 | 2025-05-31 | 2025-05-29 | 2025-05-30 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-29 | 2025-05-29 | 2025-05-31 | 2025-05-29 | 2025-07-15 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2025-02-18: 2025-05-19; 2025-02-28: 2025-05-26; 2025-03-10: 2025-05-19; 2025-03-10: 2025-05-20 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050639-GCI | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | CHEONG/SENG/WAH/7018000306
2604A_HU | Tmn Daya Meru (TM) -132 | DU00005244053 | Central | Selangor | 3.130098 | 101.440754 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Under NIC | Existing SM link 18G_1+0_112M , already swap to Huawei 18G_2+0_112M under 2604A (Tx Rollout project _ DU Code DU00002042061) | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505020429-GCI | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | CHEONG/SENG/WAH/7018000306
Q02312_AD | KAMPUNG BENAWA | DU00005244054 | Sarawak | Sarawak | 4.031131 | 114.348110 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | NA | PAC |  | MW IDU Patching | Q02312 Change backhaul to xD 9294A |  | Change backhaul to xD 9294A | [5 empty] | N/A | No PR required-N/A | In-House | No PR required-by In-House |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-21 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-03-19 | [15 empty] | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-06-19 | IDA//NAJEEHA BINTI MAZLAN/7018000019
7272C_HU | Kampung Sungai | DU00005244055 | Sabah | Labuan | 5.294325 | 115.238807 |  |  |  |  | RFS |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 2+0 0.6m/0.6m XMC3 NE: 1) 1xISM8 2) 1x23GHz XMC3E Sub A Lo 3) 1x23GHz XMC3E Sub B Lo 4) 1x23GHz 0.6m DP FE: 1) 1xISM8 2) 1x23GHz XMC3E Sub A Hi 3) 1x23GHz XMC3E Sub B Hi 4) 1x23GHz 0.6m DP | MW Swap | To swap Existing link 23GHz 1+0 112MHz with new Huawei link 23GHz 2+0 112MHz Reuse existing channel for V polarization NE (7272C RTN01): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at new RTN 3-ISM8 3) Migrate traffic to new link 4) Decom existing link FE (7073A RTN01): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at new RTN 3-ISM8 3) Migrate traffic to new link 4) Decom existing link | NE (7272C RTN01): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at new RTN 3-ISM8 3) Migrate traffic to new link 4) Decom existing link | FE (7073A RTN01): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at new RTN 3-ISM8 3) Migrate traffic to new link 4) Decom existing link | XMC3 | MAC DP | 23G | 0.6m | 0.6m | NR services | SQ202505070642-NR Services | NR services | SQ202504260112-NR Services // SQ202504260119-NR Services | 2025-07-04 | 2025-06-30 | Completed | 2025-05-03 | 2025-05-05 | 2025-05-03 | 2025-05-05 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-16 | 2025-05-14 | 2025-05-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-16 | 2025-05-14 | 2025-05-14 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-30 | 2025-07-04 | 2025-06-30 | 2025-06-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041504 |  | 2025-04-16 | 2025-04-21 | Completed | 2025-04-15 | 2025-04-16 | 2025-04-15 | 2025-04-21 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-03 | 2025-06-03 | 2025-05-03 | 2025-05-05 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-05-03 | 2025-06-03 | 2025-05-03 | 2025-05-05 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-05 | 2025-05-03 | 2025-06-03 | 2025-05-03 | 2025-05-10 | RALPH O'BRYAN HILARY7167000030 | 2025-05-03 | 2025-06-03 | 2025-05-03 | 2025-05-05 | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-10-21 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506050733-GTSB | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | HSU//MYET CHAE/6799000011
7511A_HU | KEMBARA SAKTI(CELCOM) | DU00005244056 | Sabah | Sabah | 5.329433 | 119.055700 | [5 empty] | Link perf under monitoring |  | 00. Integrated/RFS Done | Non-doable | TSS+AA+TI | L1+ATP+PAC | 13G 2+0 1.8m/1.8m MDD XMC5D sub B NE: 1) 1 x 13G XMC5D sub B Hi 2) 1 x 13G 1.8m MDD FE: 1) 1 x 13G XMC5D sub B Lo 2) 1 x 13G 1.8m MDD | MW Parallel Link | Add parallel 2+0 to existing 4+0 link Use existing IDU Create 6+0 EPLA NE (7511A RTN03): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA FE (7623B RTN06): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA | NE (7511A RTN03): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA | FE (7623B RTN06): 1) Install new link at 7-ISM8 2) Create 6+0 EPLA | XMC5D | MDD | 13G | 1.8m | 1.8m | NR services | SQ202504240795-NR Services | GCI | SQ202509130054-GCI // SQ202509130055-GCI | 2025-07-04 | 2025-06-30 | Completed | 2025-04-21 | 2025-04-25 | 2025-04-23 | 2025-04-23 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-30 | 2025-05-09 | 2025-04-30 | 2025-04-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-30 | 2025-05-09 | 2025-04-30 | 2025-04-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-30 | 2025-07-04 | 2025-06-30 | 2025-06-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090221 |  | 2025-09-08 | 2025-09-08 | Completed | 2025-09-08 | 2025-09-08 | 2025-09-02 | 2025-09-08 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-08 | 2025-09-30 | 2025-10-07 | 2025-10-07 | JACKSON//BIN MAKANSIM/6000027984 | GCI TI | 2025-09-08 | 2025-09-30 | 2025-10-09 | 2025-10-09 | JACKSON//BIN MAKANSIM/6000027984 | GCI TI | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-14 | 2025-09-08 | 2025-09-30 | 2025-10-21 | 2025-10-21 | JACKSON//BIN MAKANSIM/6000027984 | 2025-02-18: 2025-09-08; 2025-02-28: 2025-09-30; 2025-03-10: 2025-10-07; 2025-03-10: 2025-10-07 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
9696C_HU | Kg Sg Plan | DU00005244057 | Sarawak | Sarawak | 3.261063 | 113.100680 |  |  |  | AUG 25 | Pending SOW |  |  | 00. Integrated/RFS Done | 23/8/2025 : Cutover done, pending declare 22/8/2025 : Plan to do MW Hardware Upgrade - cancel proceed | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1x ODU XMC-3E SB_A HI 1x ODU XMC-3E SB_A LO | MW Hardware Upgrade | HARDWARE UPGRADE EXISTING LINK 9696C-9122A BY SWAP OLD IDU TO NEW ODU AND RE-ALLIGNMENT TO GET RSL AS PER LB CONFIGURE 23G_1+0_112MHZ_512QAM_896Mbps EXISTING LINK: 23G_1+0_56MHZ_512QAM_449Mbps_1.43KM | NE: 1. CHANGE OLD ODU TO NEW ODU (SUPPORT 112Mhz) 2. Re-allignment RSL follow LB | FE: 1. CHANGE OLD ODU TO NEW ODU (SUPPORT 112Mhz) 2. Re-allignment RSL follow LB | XMC-3E | MAC | 23G | 0.6m | 0.6m | Allstar | SQ202507180633-Allstar | Allstar | SQ202507290147-Allstar // SQ202507290151-Allstar | 2025-12-04 | 2025-11-27 | Completed | 2025-07-28 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-11-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070822 |  | 2025-07-09 | 2025-07-30 | Completed | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-30 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-23 | 2025-08-29 | 2025-08-25 | 2025-08-25 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-23 | 2025-08-29 | 2025-09-07 | 2025-09-07 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-25 | 2025-08-23 | 2025-08-29 | 2025-09-08 | 2025-09-08 | ROYSTON//AHHOLE/6000038561 | 2025-08-23 | 2025-08-29 | 2025-08-25 | 2025-08-25 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-21 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202505020435-GTSB | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | AB.RAHMAN//BIN MAT NOOH/6237001519
7354B_HU | Kg. Tamu Darat | DU00005244058 | Sabah | Sabah | 6.262804 | 116.448733 |  |  |  | JUN 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 2+0 0.6m/1.2m XMC3E NE: 1) 1xISM8 card 2) 1x18GHz XMC5D Sub B Lo 3) 1x18GHz 0.6m MDD FE: 1) 1x18GHz XMC5D Sub B Hi 2) 1x18GHz 1.2m MDD | MW Swap | Swap existing 1+0 to 2+0 link Reuse ISM8 card at FE site due to no slot. Commision new link using ISM8 slot 2 first NE (7354B RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Migrate traffic to new 2+0 link 4) Dismantle existing link FE (7407A RTN01): 1) Reuse existing ISM8 card at slot 4 2) Commision new link using ISM8 slot 2 first 3) Migrate traffic to new 2+0 link 4) Dismantle existing link | NE (7354B RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Migrate traffic to new 2+0 link 4) Dismantle existing link | FE (7407A RTN01): 1) Reuse existing ISM8 card at slot 4 2) Commision new link using ISM8 slot 2 first 3) Migrate traffic to new 2+0 link 4) Dismantle existing link | XMC5D | MDD | 18G | 0.6m | 1.2m | NR services | SQ202509300151-NR Services | NR services | SQ202509300159-NR Services // SQ202509300167-NR Services | 2026-01-22 | 2026-01-15 | Completed | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-12 | 2026-01-19 | 2026-01-12 | 2026-01-12 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080132 | Cancel DO (30 days) | 2025-08-02 | 2025-09-26 | Completed | 2025-08-01 | 2025-08-02 | 2025-08-01 | 2025-09-26 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-16 | 2025-11-16 | 2025-10-16 | 2025-10-17 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-10-16 | 2025-11-16 | 2025-10-16 | 2025-10-21 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-10-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-21 | 2025-10-16 | 2025-11-16 | 2025-10-16 | 2025-10-25 | RALPH O'BRYAN HILARY7167000030 | 2025-02-18: 2025-10-16; 2025-02-28: 2025-11-16; 2025-03-10: 2025-10-16; 2025-03-10: 2025-10-17 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
4122D_HU | Taman Anjung Tawas Sinaran | DU00005244059 | Northern | Perak | 4.660111 | 101.110050 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO | MW Swap | MW SWAP LINK 4122D-4536A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM_954MBPS_XMC3E_SUB_A_0.74KM DISMANTLE EXISTING LINK 4122D-4536A MW1 IMPACTED: 4122D | 1. INSTALL NEW RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK 4122D-4536A MW1 | 1. INSTALL NEW RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK 4122D-4536A MW1 6. PATCH IDU TO NEW CP PORT AND DO PORT LAG | XMC3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202506050553-Magicell | Magicell | SQ202506180131-Magicell // SQ202506180135-Magicell // SQ202507290130-Magicell | 2025-07-04 | 2025-07-04 | Completed | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052827 |  | 2025-05-29 | 2025-05-30 | Completed | 2025-05-28 | 2025-05-29 | 2025-05-28 | 2025-05-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-17 | 2026-06-25 | 2025-06-17 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-06-17 | 2026-06-25 | 2025-06-17 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-18 | 2025-06-17 | 2026-06-25 | 2025-06-17 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-06-17 | 2026-06-25 | 2025-06-17 | 2025-06-17 | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
4730A_HU | Behrang (Trunk) | DU00005244060 | Northern | Perak | 3.772770 | 101.442051 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | DONE UNDER 2480A_HU DU | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4942C_HU | Pasir Panjang Manjong (REL) | DU00005244061 | Northern | Perak | 4.170748 | 100.682628 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap | MW SWAP LINK 4942C-4405A WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_778MBPS_XMC3E_SUB_B_3.04KM DISMANTLE EXISTING LINK IMPACTED: 4942C | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK 6. PATCH NEW IDU TO 4405A RTN01 | XMC3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202507030709-Magicell | Magicell | SQ202506230474-Magicell // SQ202506230478-Magicell | 2025-11-27 | 2025-11-26 | Completed | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061396 |  | 2025-06-14 | 2025-06-18 | Completed | 2025-06-13 | 2025-06-14 | 2025-06-13 | 2025-06-18 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-25 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-23 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-26 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-20 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505020432-GCI | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
7544B_HU | KKIP Timur | DU00005244062 | Sabah | Sabah | 6.091614 | 116.184886 |  |  |  |  | In Plan | TI in plan |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G 2+0 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 4) 1x18GHz 0.6m DP FE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 4) 1x18GHz 0.6m DP | MW Parallel Link | Add parallel 2+0 to carry 7544B traffic NE (7544B): 1) Install new RTN910A 2) Install new link at new RTN 7-ISM8 3) Transfer 7544B traffic to new link FE (7060A RTN01): 1) Add ISM8 card slot 4 2) Install new link at 4-ISM8 3) Transfer 7544B traffic to new link | NE (7544B): 1) Install new RTN910A 2) Install new link at new RTN 7-ISM8 3) Transfer 7544B traffic to new link | FE (7060A RTN01): 1) Add ISM8 card slot 4 2) Install new link at 4-ISM8 3) Transfer 7544B traffic to new link | XMC3E | MAC DP | 18G | 0.6m | 0.6m | NR services | SQ202504170485-NR Services | NR services | SQ202505240116-NR Services // SQ202505240118-NR Services | 2025-05-09 | 2025-05-07 | Completed | 2025-04-10 | 2025-04-16 | 2025-04-13 | 2025-04-13 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-15 | 2025-04-18 | 2025-04-15 | 2025-04-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-15 | 2025-04-18 | 2025-04-15 | 2025-04-15 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-07 | 2025-05-09 | 2025-05-07 | 2025-05-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051568 |  | 2025-05-16 | 2025-05-16 | Completed | 2025-05-15 | 2025-05-16 | 2025-05-15 | 2025-05-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-29 | 2025-06-02 | 2025-05-29 | 2025-06-02 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-06-02 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-23 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-06-02 | RALPH O'BRYAN HILARY7167000030 | 2025-06-19: 2025-05-22; 2025-06-19: 2025-05-22; 2025-06-19: 2025-05-22; 2025-06-20: 2025-05-22 |  |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
W00027_HU | W066F_W00027OD_SGPENCHALA2 | DU00005244063 | Central | Kuala Lumpur | 3.161200 | 101.622800 |  | APR 25 |  | APR 25 | DO | Doable, just waiting material | ZTE | 00. Integrated/RFS Done | 21/4/2025 : MAXIS COMMUNICATION BERHAD - AESTHETIC MONOPOLE 45M LAND - NE site W00027 W066F_W00027OD_SGPENCHALA2, EDOTCO (M) SDN BHD - TOWER 91M LAND - FE site B00632 B061N_B00632OD_BKTLANJAN | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap |  | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH NEW IDU TO OB FIBER 6. DISMANTLE EXISTING LINK | 3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202504280360-Magicell | Magicell | SQ202505190296-Magicell // SQ202505190304-Magicell | 2025-06-05 | 2025-06-04 | Completed | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-16 | 2025-05-17 | 2025-05-16 | 2025-05-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-04 | 2025-06-05 | 2025-06-04 | 2025-06-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050950 |  | 2025-05-14 | 2025-06-04 | Completed | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-06-04 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-06-04 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-06-04 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-06-04 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-17 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
4475B_HU | Sg Manik | DU00005244064 | Northern | Perak | 4.037890 | 101.048000 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Solution done on 4586B-4475B TX Mini Project (DU00005043106) | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4939A_HU | Merbok | DU00005244065 | Northern | Kedah | 5.722980 | 100.413000 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | CANCEL/DROP DUE TO UNDER DU 4304D_HU | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4092D_HU | Kamunting Industrial Area | DU00005244066 | Northern | Perak | 4.908130 | 100.712890 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M Site Impacted : 4092D. NE_4092D 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1 XMC_3E , Sub A & B_Lo x1. FE_4759B 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1 XMC_3E , Sub A & B_Hi x1. | MW Swap | Existing SM link 23G_1+0_56M Swap existing link to 23G_2+0_112M Site Impacted : 4092D. NE_4092D 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Sevice cross connect and EPLA. 5.Migrate traffic to new link 23G_2+0_112M 6.Decomm existing SM link. Ensure no traffic before decomm. FE_4759B 1>Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A . 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Service cross connect and EPLA. 5.Traffic migrate to new 23G_2+0_112M link. 6.Decomm existing SM link.Ensure no traffic before decomm. | Existing SM link 23G_1+0_56M Swap existing link to 23G_2+0_112M Site Impacted : 4092D. NE_4092D 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Sevice cross connect and EPLA. 5.Migrate traffic to new link 23G_2+0_112M 6.Decomm existing SM link. Ensure no traffic before decomm. | Existing SM link 23G_1+0_56M Swap existing link to 23G_2+0_112M Site Impacted : 4092D. FE_4759B 1>Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A . 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Service cross connect and EPLA. 5.Traffic migrate to new 23G_2+0_112M link. 6.Decomm existing SM link.Ensure no traffic before decomm. | XMC_3E | MAC | 23G | 0.6 | 0.6 | NWAVE | SQ202507160641-N-Wave | NWAVE | SQ202506190726-N-Wave // SQ202506190735-N-Wave | 2025-11-27 | 2025-11-26 | Completed | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-23 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061163 |  | 2025-06-12 | 2025-06-13 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-19 | 2025-06-26 | 2025-06-19 | 2025-06-20 | ABDUL LATIF//ARSHAD/6000026740 | NWAVE TI | 2025-06-19 | 2025-06-26 | 2025-06-19 | 2025-06-20 | ABDUL LATIF//ARSHAD/6000026740 | NWAVE TI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-07-15 | 2025-06-19 | 2025-06-26 | 2025-06-19 | 2025-07-01 | ABDUL LATIF//ARSHAD/6000026740 | 2025-06-19 | 2025-06-26 | 2025-06-19 | 2025-06-20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | CHEONG/SENG/WAH/7018000306
4578C_HU | Taman Sg Bakap | DU00005244067 | Northern | Penang | 5.237069 | 100.497144 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M. NE_4578C 15G_DP_1.2M(MDD) x1. ISM8- x2. XMC_5D , Sub B_Lo x1. FE_4188A 15G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub B_Hi x1 | MW Swap | Existing link 15G_4+0_28M. (Old version equipment). Swap to 15G_4+0_28M config , it will become 15G_6+0_28M with 15G_2+0_28M refer to ( 4578C_HU_1 , DU00005509291). Site Impacted : 4578C NE_4578C 1.Install 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub B_Lo for ant 2 with CA config. 4.Create service cross connect , CA and EPLA. 5.Migrate traffic to new 15G_6+0_28M.(15G_2+0 & 15G_4+0_CA). 6.Decom existing MW link 15G_4+0_28M. FE_4188A 1.Install 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub B_Hi for ant 2 with CA config. 4.Create service cross connect , CA and EPLA. 5.Create New In Band DCN. 6.Traffic migrate to new 15G_6+0_28M.(15G_2+0 & 15G_4+0_CA). 7.Decomm existing MW link 15G_4+0_28M. Current link required to reroute new FE_4234B/P00360 due to Old FE 4188A have space constraint issue. Redeploy equipment to new FE_4234B/P00360. NE_4578C 1.Install 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub B_Lo for ant 2 with CA config. 4.Create service cross connect , CA and EPLA. 5.Migrate traffic to new 15G_6+0_28M.(15G_2+0 & 15G_4+0_CA). 6.Decom existing MW link 15G_4+0_28M. FE_4234B/P00360 1.Redeploy equipment 15G_4+0_28M link from 4578C-4188A to 4578C-4234B/P00360. 2.Install 15G_DP_1.2M(MDD). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub B_Hi for ant 2 with CA config. 5.Create service cross connect , CA and EPLA. 6.Create New In Band DCN. 7.Enable GE1, ETH patching to Cisco Fiber port Gi 0/0/8. 8.Traffic migrate to new 15G_6+0_28M with EPLA 15G_2+0_28M. 9.Decomm existing MW link 15G_4+0_28M. | Existing link 15G_4+0_28M. (Old version equipment). Swap to 15G_4+0_28M config , it will become 15G_6+0_28M with 15G_2+0_28M refer to ( 4578C_HU_1 , DU00005509291). Site Impacted : 4578C NE_4578C 1.Install 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub B_Lo for ant 2 with CA config. 4.Create service cross connect , CA and EPLA. 5.Migrate traffic to new 15G_6+0_28M.(15G_2+0 & 15G_4+0_CA). 6.Decom existing MW link 15G_4+0_28M. Current link required to reroute new FE_4234B/P00360 due to Old FE 4188A have space constraint issue. Redeploy equipment to new FE_4234B/P00360. NE_4578C 1.Install 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub B_Lo for ant 2 with CA config. 4.Create service cross connect , CA and EPLA. 5.Migrate traffic to new 15G_6+0_28M.(15G_2+0 & 15G_4+0_CA). 6.Decom existing MW link 15G_4+0_28M. | Existing link 15G_4+0_28M. (Old version equipment). Swap to 15G_4+0_28M config , it will become 15G_6+0_28M with 15G_2+0_28M refer to ( 4578C_HU_1 , DU00005509291). Site Impacted : 4578C FE_4188A 1.Install 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub B_Hi for ant 2 with CA config. 4.Create service cross connect , CA and EPLA. 5.Create New In Band DCN. 6.Traffic migrate to new 15G_6+0_28M.(15G_2+0 & 15G_4+0_CA). 7.Decomm existing MW link 15G_4+0_28M. Current link required to reroute new FE_4234B/P00360 due to Old FE 4188A have space constraint issue. Redeploy equipment to new FE_4234B/P00360. FE_4234B/P00360 1.Redeploy equipment 15G_4+0_28M link from 4578C-4188A to 4578C-4234B/P00360. 2.Install 15G_DP_1.2M(MDD). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_5D , Sub B_Hi for ant 2 with CA config. 5.Create service cross connect , CA and EPLA. 6.Create New In Band DCN. 7.Enable GE1, ETH patching to Cisco Fiber port Gi 0/0/8. 8.Traffic migrate to new 15G_6+0_28M with EPLA 15G_2+0_28M. 9.Decomm existing MW link 15G_4+0_28M. | XMC_5D | MDD | 15G | 1.2 | 1.2 | NWAVE | SQ202505240072-N-Wave | NWAVE | SQ202505190421-N-Wave // SQ202505190428-N-Wave | 2026-02-13 | 2026-02-12 | Completed | 2025-05-21 | 2025-05-28 | 2025-05-21 | 2025-07-15 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-21 | 2025-05-28 | 2026-02-06 | 2026-02-06 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-11 | 2026-02-10 | 2026-02-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051490 |  | 2025-05-15 | 2025-05-17 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-21 | 2025-05-28 | 2025-05-21 | 2025-05-30 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-05-21 | 2025-05-28 | 2025-05-21 | 2025-07-06 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-11 | 2025-05-21 | 2025-05-28 | 2025-05-21 | 2026-01-29 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | 2025-05-18 | 2025-05-26 | 2025-05-18 | 2025-05-20 | 2025-05-21 | 2025-05-28 | 2025-05-21 |  | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505190519-GCI | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | CHEONG/SENG/WAH/7018000306
7196A_HU | Jalan Sin On | DU00005244068 | Sabah | Sabah | 4.282762 | 117.916300 |  |  |  | JUN 25 | In Plan | TI DONE | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+PAC | 15G_4+0_1.2/1.2 MDD_SB A 2x ISM8 | MW Hardware Upgrade | MW HARDWARE UPGRADE 7726B-7196A FROM 15G_1+0 TO 15G_4+0_CA. EXISITNG 18G LINK SHIFT SLOT FROM SLOT 3_ISM8 TO SLOT 7. | MW HARDWARE UPGRADE 7726B-7196A FROM 15G_1+0 TO 15G_4+0_CA. NE: 7726B 1. Reuse exisiting RTN910A. 2. Install 1xISM8 at Slot 4. 3. Reuse exisitng antenna. 4. Configure 15G_4+0_CA_800M. 5. existing 18G link swift slort and port from Slot 3 to Slot 7. | MW HARDWARE UPGRADE 7726B-7196A FROM 15G_1+0 TO 15G_4+0_CA. FE: 7196A 1. Reuse exisiting RTN910A. 2. Install 1xISM8 at Slot 4. 3. Reuse exisitng antenna. 4. Configure 15G_4+0_CA_800M. 5. existing 18G link swift slort and port from Slot 3 to Slot 7. | [5 empty] | NR services | SQ202505020374-NR Services | NR services | SQ202506130270-NR Services // SQ202506130278-NR Services | 2025-04-30 | 2025-04-25 | Completed | 2025-04-21 | 2025-04-28 | 2025-04-24 | 2025-04-24 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-23 | 2025-04-30 | 2025-04-25 | 2025-04-25 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-25 | 2025-04-30 | 2025-04-25 | 2025-04-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-25 | 2025-04-30 | 2025-04-25 | 2025-04-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051622 |  | 2025-05-17 | 2025-05-19 | Completed | 2025-05-16 | 2025-05-17 | 2025-05-16 | 2025-05-19 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-15 | WILFRED BALANG7167000026 | NR Service TI | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-15 | WILFRED BALANG7167000026 | NR Service TI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-16 | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-19 | WILFRED BALANG7167000026 | 2025-05-14: 2025-06-13; 2025-05-14: 2025-07-13; 2025-05-14: 2025-06-13; 2025-05-17: 2025-06-14 |  |  | 2025-07-24 | 2025-08-24 | 2025-07-24 | 2025-07-24 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
K00023_HU | K002A_K00023OD_CB_SERAKO | DU00005244069 | Northern | Kedah | 5.680833 | 100.862583 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Site K00023 with link ID NT05527 no longer exist , current new link ID is NT06195 , current NT06195 SM link config 18G_2+0_112M and utilization Max 30%. (Reuse existing TX) under TX Rollout solution (DU00002880863). | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
W00023_HU | W066H_W00023OD_JLNAIRPANAS | DU00005244070 | Central | Kuala Lumpur | 3.194182 | 101.711699 |  | APR 25 |  | APR 25 | DO | Pending edotco approval | ZTE | 00. Integrated/RFS Done | 21/4/2025 : EDOTCO (M) SDN BHD - TRIPOD 6M ROOFTOP - NE site W00023 W066H_W00023OD_JLNAIRPANAS, EDOTCO (M) SDN BHD - INBUILDING - FE site W00418 W066K_W00418IB_KLINTERNATIONAL | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap | MW SWAP LINK W00023-W00418 WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_256QAM_1778MBPS_XMC3E_SUB_A & B_3.18KM FE PATCH NEW RTN 910A TO CELOM W00418 OB FIBER IMPACTED: W00023 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. PATCH NEW RTN 910A TO CELOM W00418 OB FIBER 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202504280360-Magicell | Magicell | SQ202505160548-Magicell // SQ202505160554-Magicell // SQ202505270616-Magicell | 2025-05-24 | 2025-05-23 | Completed | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-19 | 2025-05-20 | 2025-05-19 | 2025-05-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-23 | 2025-05-24 | 2025-05-23 | 2025-05-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050951 |  | 2025-05-14 | 2025-05-15 | Completed | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-15 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-15 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-15 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-19 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-15 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | CHEONG/SENG/WAH/7018000306
4540D_HU | Kg Tebuk Yan | DU00005244071 | Northern | Perak | 4.414321 | 100.638981 | [7 empty] | 00. Integrated/RFS Done | 22/07: TI Started 24/07: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_56M NE_4540D New 23G_DP_0.6M(MAC)+OMT x1. New RTN910A x1. New XMC_3, Sub A&B_Hi x2. FE_4383A New 23G_DP_1.2M(MS) x1. New RTN910A x1. New XMC_3, Sub A&B_Lo x2. New FlexiWG 23G x2. | MW Swap | Existing HW MW Link 15G_1+0_28M. Swap existing HW MW Link with new HW MW Link 23G_2+0_56M_512QAM_EPLA. Site Impacted : 4540D. NE_4540D 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN02) x1. Configure it. 3.Install new XMC_3, Sub A&B_Hi x2. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A(RTN02). 6.Migrate traffic to new link in which BBU 4540D will be patching to port 8-EM6-1 of new RTN910A(RTN02). Configure it. 7.Later, may decom existing HW MW Link 15G_1+0_28M, 4540D(RTN01)-4383A(RTN03). FE_4383A 1.Install new 23G_DP_1.2M(MS) x1. 2.Install new RTN910A(RTN04) x1. Configure it. 3.Install new XMC_3, Sub A&B_Lo x2. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of new RTN910A(RTN04) and patching to existing PTN/Cisco A00133. Request new port at PTN/Cisco and new vlan services from ZTE IPRAN team for 4540D. Configure it. 6.Later, may decom existing HW MW Link 15G_1+0_28M, 4540D(RTN01)-4383A(RTN03). | Existing HW MW Link 15G_1+0_28M. Swap existing HW MW Link with new HW MW Link 23G_2+0_56M_512QAM_EPLA. Site Impacted : 4540D. NE_4540D 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN02) x1. Configure it. 3.Install new XMC_3, Sub A&B_Hi x2. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A(RTN02). 6.Migrate traffic to new link in which BBU 4540D will be patching to port 8-EM6-1 of new RTN910A(RTN02). Configure it. 7.Later, may decom existing HW MW Link 15G_1+0_28M, 4540D(RTN01)-4383A(RTN03). | Existing HW MW Link 15G_1+0_28M. Swap existing HW MW Link with new HW MW Link 23G_2+0_56M_512QAM_EPLA. Site Impacted : 4540D. FE_4383A 1.Install new 23G_DP_1.2M(MS) x1. 2.Install new RTN910A(RTN04) x1. Configure it. 3.Install new XMC_3, Sub A&B_Lo x2. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of new RTN910A(RTN04) and patching to existing PTN/Cisco A00133. Request new port at PTN/Cisco and new vlan services from ZTE IPRAN team for 4540D. Configure it. 6.Later, may decom existing HW MW Link 15G_1+0_28M, 4540D(RTN01)-4383A(RTN03). | XMC_3 | MAC & MS | 23G | 23G_DP_0.6M(MAC)+OMT x1. | 23G_DP_1.2M(MS) x1. | GCI | SQ202507160591-GCI | GCI | SQ202507230772-GCI // SQ202507230777-GCI // SQ202508140739-GCI | 2025-12-02 | 2025-11-26 | Completed | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-07 | 2025-08-14 | 2025-08-07 | 2025-08-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Manager | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071550 |  | 2025-07-17 | 2025-07-17 | Completed | 2025-07-16 | 2025-07-17 | 2025-07-16 | 2025-07-17 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-23 | 2025-08-06 | 2025-07-23 | 2025-08-04 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2025-07-23 | 2025-08-06 | 2025-07-23 | 2025-08-04 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-24 | 2025-07-23 | 2025-08-06 | 2025-07-23 | 2025-08-04 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2025-07-23 | 2025-08-06 | 2025-07-23 | 2025-07-23 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB
W00320_HU | W066V_W00663IB2_TMWHOLESALE | DU00005244072 | Central | Kuala Lumpur | 3.116310 | 101.663810 |  |  |  |  | Cancel / Drop | Change to DU W00004_HU | ZTE | 00. Site Out/Drop | 18/4/2025 : CHANGE TO W00004_HU DUE TO NE W00004_HUAND FE W00320 |  |  |  | Cancel / Drop | CHANGE TO W00004_HU DUE TO NE W00004_HU AND FE W00320 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4043D_HU | Kampung Ikan (REL) | DU00005244073 | Northern | Pahang | 4.571594 | 101.385098 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | MW HU closed by MSP WK12 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7246C_HU | Wismas (REL) | DU00005244074 | Sabah | Sabah | 6.045868 | 116.150141 |  |  |  |  | RFS |  |  | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | To perform remote upgrade from 56MHz to 112MHz | To perform remote upgrade from 56MHz to 112MHz | To perform remote upgrade from 56MHz to 112MHz |  |  | 18G | [8 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2025-05-29 | 2025-06-29 | 2025-05-29 | 2025-05-29 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
1771C_HU | Parit 8 Gambut | DU00005244075 | Central | Selangor | 3.694266 | 101.048248 |  |  |  |  | Cancel / Drop | Issue close by MSP | ZTE | 00. Site Out/Drop | 14/4/2025 : No need proceed, HU close by MSP |  |  |  | Cancel / Drop | Closed by MSP WK14 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4466A_HU | Taman Rakyat RDD | DU00005244076 | Northern | Perak | 4.921788 | 100.724654 | [7 empty] | 00. Integrated/RFS Done | WK27 | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M NE_4466A. 18G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Lo x1. FE_4457A 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Hi x1. | MW Parallel Link | Existing link 18G_2+0_112M Install parallel link 18G_2+0_112M to serve for child site 4438D. Site Impacted : 4438D NE_4466A. 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Lo. 4.Create service cross connect and EPLA. 5.Migrate existing 4438D link to new parallel link 18G_2+0_112M. 6.No decomm existing link. FE_4457A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross connect and EPLA. 5.Create In Band DCN & Port Physical LAG. 6.Enable GE1 , ETH Patching to Fiber_Ibeam. 7.No Decomm existing link. | Existing link 18G_2+0_112M Install parallel link 18G_2+0_112M to serve for child site 4438D. Site Impacted : 4438D NE_4466A. 1.Install new 18G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Lo. 4.Create service cross connect and EPLA. 5.Migrate existing 4438D link to new parallel link 18G_2+0_112M. 6.No decomm existing link. | Existing link 18G_2+0_112M Install parallel link 18G_2+0_112M to serve for child site 4438D. Site Impacted : 4438D FE_4457A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross connect and EPLA. 5.Create In Band DCN & Port Physical LAG. 6.Enable GE1 , ETH Patching to Fiber_Ibeam. 7.No Decomm existing link. | XMC_5D | MDD | 18G | 1.2 | 0.6 | MTK | SQ202510070048-MTK | MTK | SQ202510070044-MTK // SQ202510070047-MTK | 2025-12-09 | 2025-12-02 | Completed | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | AMIRUL SYAHRINI BIN MOHD ZIN6000023342 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-21 | 2025-10-14 | 2025-10-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-29 | 2025-10-22 | 2025-10-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092653 |  | 2025-09-27 | 2025-09-29 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-02 | 2025-10-15 | 2025-10-03 | 2025-10-07 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-10-02 | 2025-10-15 | 2025-10-03 | 2026-01-19 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-08 | 2025-10-02 | 2025-10-15 | 2025-10-18 | 2026-01-19 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-05-14: 2025-10-02; 2025-05-14: 2025-10-15; 2025-05-14: 2025-10-18; 2025-05-15: 2026-01-17 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB
4416B_HU | Sg Klah | DU00005244077 | Northern | Perak | 3.985761 | 101.361832 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M_256QAM_CA&EPLA NE_4416B New 15G_1.2M(MDD) x1. New RTN910A x1. New ISM8 x1. New XMC_5D, Sub B_Lo x1. FE_4731A New 15G_1.2M(MDD) x1. New RTN910A x1. New ISM8 x1. XMC_5D, Sub B_Hi x1. | MW Swap | Link Existing HW 15G_1+0_28M_256QAM Swap existing HW link to new HW 15G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4416B(4196R & 4786B - during remove existing cascading and perform new cascading again) NE_4416B 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN04). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN04). Configure it. 5.Configure DCN Inband. 6.Enable port 8-EM6-1 of RTN910A(RTN04) and patching to BBU 4416B. Configure it. 7.Migrate RAN traffic to new HW MW link 15G_4+0_28MHz_256QAM_CA&EPLA. Configure it. 8.Later, may decom existing HW MW Link 4416B(RTN03)-4731A(RTN01). FE_4731A 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN05). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN05). Configure it. 5.Configure DCN Inband. 6.Disable port 6-EM6T-1 & 6-EM6T-2 of RTN950(RTN01). 7.Remove cascading in between RTN950(RTN01)-RTN910A(RTN01) & RTN950(RTN01)-RTN910A(RTN07). 8.Enable port and perform cascading in between port 8-EM6-1 of new RTN910A(RTN05) & port 8-EM6-2 of existing RTN910A(RTN02). Configure it. 9.Enable port and perform cascading in between port 8-EM6-2 of new RTN910A(RTN05) & port 8-EG6-2 of existing RTN910A(RTN07). Configure it. 10.Migrate RAN traffic to new HW MW link 15G_4+0_28MHz_256QAM_CA&EPLA. Configure it. 11.Later, may decom existing HW MW Link 4416B(RTN03)-4731A(RTN01). | Link Existing HW 15G_1+0_28M_256QAM Swap existing HW link to new HW 15G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4416B(4196R & 4786B - during remove existing cascading and perform new cascading again) NE_4416B 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN04). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN04). Configure it. 5.Configure DCN Inband. 6.Enable port 8-EM6-1 of RTN910A(RTN04) and patching to BBU 4416B. Configure it. 7.Migrate RAN traffic to new HW MW link 15G_4+0_28MHz_256QAM_CA&EPLA. Configure it. 8.Later, may decom existing HW MW Link 4416B(RTN03)-4731A(RTN01). | Link Existing HW 15G_1+0_28M_256QAM Swap existing HW link to new HW 15G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4416B(4196R & 4786B - during remove existing cascading and perform new cascading again) FE_4731A 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN05). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN05). Configure it. 5.Configure DCN Inband. 6.Disable port 6-EM6T-1 & 6-EM6T-2 of RTN950(RTN01). 7.Remove cascading in between RTN950(RTN01)-RTN910A(RTN01) & RTN950(RTN01)-RTN910A(RTN07). 8.Enable port and perform cascading in between port 8-EM6-1 of new RTN910A(RTN05) & port 8-EM6-2 of existing RTN910A(RTN02). Configure it. 9.Enable port and perform cascading in between port 8-EM6-2 of new RTN910A(RTN05) & port 8-EG6-2 of existing RTN910A(RTN07). Configure it. 10.Migrate RAN traffic to new HW MW link 15G_4+0_28MHz_256QAM_CA&EPLA. Configure it. 11.Later, may decom existing HW MW Link 4416B(RTN03)-4731A(RTN01). | XMC_5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | NWAVE | SQ202504280496-N-Wave | NWAVE | SQ202505240112-N-Wave // SQ202505240115-N-Wave | 2025-08-13 | 2025-08-07 | Completed | 2025-05-26 | 2025-05-30 | 2025-05-26 | 2025-05-26 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-26 | 2025-05-30 | 2025-05-26 | 2025-06-26 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-26 | 2025-05-30 | 2025-05-26 | 2025-08-01 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050931 |  | 2025-05-10 | 2025-05-17 | Completed | 2025-05-09 | 2025-05-10 | 2025-05-09 | 2025-05-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-26 | 2025-05-30 | 2025-05-26 | 2025-05-26 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-05-26 | 2025-05-30 | 2025-05-26 | 2025-05-30 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | AKMAL//BIN RAZALI/6794000078 |  | 2025-05-27 | 2025-05-26 | 2025-05-30 | 2025-05-26 | 2025-07-15 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2025-05-26 | 2025-05-30 | 2025-05-26 | 2025-05-27 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202504140802-GTSB
K00421_HU | K002A_K00421OD_WENG | DU00005244078 | Northern | Kedah | 5.836578 | 100.902350 | [7 empty] | 00. Integrated/RFS Done | 24/5 : CO Done | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M to become 15G_6+0_28M with 15G_2+0_28M refer to K00421_HU_1 under DU Code DU00005509292. NE_K00421. 15G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub_A_Hi x1. FE_K00442 15G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Lo x1. | MW Parallel Link | Existing link 13G_2+0_28M. Install parallel link 15G_4+0_28M to become 15G_6+0_28M with 15G_2+0_28M refer to K00421_HU_1 under DU Code DU00005509292. Site Impacted : K00421 , K00959 (EB). NE_K00421. 1.Install new 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub_A_Hi for ant 2 with CA config. 4.Create service cross connect , CA and EPLA. 5.Traffic migrate to new link. FE_K00442 1.Install new 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Lo for ant 2 with CA config. 4.Create service cross connect , CA and EPLA. 5.Create new In Band DCN. 6.Traffic migrate to new link. | Existing link 13G_2+0_28M. Install parallel link 15G_4+0_28M to become 15G_6+0_28M with 15G_2+0_28M refer to K00421_HU_1 under DU Code DU00005509292. Site Impacted : K00421 , K00959 (EB). NE_K00421. 1.Install new 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub_A_Hi for ant 2 with CA config. 6.Create service cross connect , CA and EPLA. 7.Enable GE1 , K00421_BBU traffic migrate to new parallel link 15G_6+0_28M. 8.No decom existing MW link due to support for K00959 (EB) site. FE_K00442 1.Install new 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Lo for ant 2 with CA config. 4.Create service cross connect , CA and EPLA. 5.Create new In Band DCN. 6.No decomm existing MW link due to support for K00959(EB) site. | Existing link 13G_2+0_28M. Install parallel link 15G_4+0_28M to become 15G_6+0_28M with 15G_2+0_28M refer to K00421_HU_1 under DU Code DU00005509292. Site Impacted : K00421 , K00959 (EB). NE_K00421. 1.Install new 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub_A_Hi for ant 2 with CA config. 6.Create service cross connect , CA and EPLA. 7.Enable GE1 , K00421_BBU traffic migrate to new parallel link 15G_6+0_28M. 8.No decom existing MW link due to support for K00959 (EB) site. FE_K00442 1.Install new 15G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Lo for ant 2 with CA config. 4.Create service cross connect , CA and EPLA. 5.Create new In Band DCN. 6.No decomm existing MW link due to support for K00959(EB) site. | XMC_5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202504280482-Magicell | Magicell | SQ202505240109-Magicell // SQ202505240110-Magicell // SQ202506030700-Magicell | 2026-01-23 | 2026-01-23 | Completed | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051487 |  | 2025-05-15 | 2025-05-16 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2026-01-28 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | Magicell TI | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-06-22 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | Magicell TI | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-07-02 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | 2025-05-14: 2025-05-21; 2025-05-14: 2025-05-21; 2025-05-14: 2025-05-21; 2025-05-15: 2025-05-26 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505190519-GCI | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | CHEONG/SENG/WAH/7018000306
3921B_HU | Bandar Bukit Mahkota | DU00005244079 | Central | Selangor | 2.868578 | 101.817298 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 1X 15G 0.6M DP ANTENNA 1X 15G 1.2M DP ANTENNA 1x ODU 15G XMC3 SUB A HI 1X ODU 15G XMC3 SUB A LO 1x ODU 15G XMC3 SUB B HI 1X ODU 15G XMC3 SUB B LO | MW Parallel Link | MW SWAP LINK 3921B-2400A WITH HUAWEI_15G_2+0_0.6M/1.2M_DP_28MHZ_512QAM_448MBPS_XMC3_SUB_A & B_4.77KM_EPLA WITH EXISTING 15G 4+0 IMPACTED: 3921B, 2413A, 1591H | 1. REUSE EXISTING IDU RTN910 SLOT 7 2. INSTALL NEW 15G 0.6M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM EPLA WITH EXISTING 15G 4+0 | 1. REUSE EXISTING IDU RTN910 SLOT 7 2. INSTALL NEW 15G 0.6M DP ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM EPLA WITH EXISTING 15G 4+0 5. PATCH TO NEW CP PORT AND DO PORT LAG | XMC3 | MAC | 15G | 0.6 | 1.2 | Magicell | SQ202504280360-Magicell | Magicell | SQ202505190296-Magicell // SQ202505190304-Magicell | 2025-07-30 | 2025-07-29 | Completed | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-16 | 2025-07-17 | 2025-07-16 | 2025-07-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-29 | 2025-07-30 | 2025-07-29 | 2025-07-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050949 |  | 2025-05-14 | 2025-05-27 | Completed | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-27 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-27 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-19 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-22 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-05-14: 2025-05-14; 2025-05-14: 2025-05-14; 2025-05-14: 2025-05-14; 2025-05-15: 2025-05-16 |  |  | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | HSU//MYET CHAE/6799000011
7502A_HU | Tabin Wildlife Centre | DU00005244080 | Sabah | Sabah | 5.191675 | 118.503085 |  |  |  |  | Drop/Cancel |  |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Upgrade under DU 7502A DU00002880866 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4234A_HU | Jalan Tasek Valdor | DU00005244081 | Northern | Penang | 5.247520 | 100.499420 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Drop Under NIC ; 4125D_POSTMOCN MW IDU Patching | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505020432-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
3497A10_EVT | pBTS Kinabutan Garden (REL) | DU00006152284 | Sabah | Sabah | 4.260696 | 117.948335 | [13 empty] | Planning and integration support only for event site 3497A10 PBTS KINABUTAN GARDEN (REL) Tx route: 3497A10-7617A-LL-7205A 1) Share port with 7617A at 7205A 2) New NE ID NE IDU 3497A10 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
3186B10_EVT | PBTS BBMR PRN SABAH 2025 | DU00006159836 | Sabah | Sabah | 6.233380 | 116.193350 | [13 empty] | Planning and integration support only for event site 3186B10 PBTS BBMR PRN SABAH 2025 Tx route: 3186B10-7636A-LL-7000A 1) Share port with 7636A at 7000A 2) New NE ID NE IDU 3186B10 RTN01 3) New NE ID FE IDU 7636A RTN02 4) At far end 7636A patch GE1 RTN02 to GE1 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
1770A_AD | Tmn Rinching | DU00006191899 | Central | Selangor | 2.929752 | 101.851631 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 1KM 2x Patch Cord(Pair) | MW IDU Patching | 1) To patch IDU 1770A-TAMAN RINCHING-RTN05 3rd Leg port GE1 and GE2 to port gi0/2/26, gi0/2/27 1770A-MAC-001 2) Configure MW link to follow existing 1851B-1770A 3rd leg protection 3) Configure DCN with main and standby GNE | 1) To patch IDU 1770A-TAMAN RINCHING-RTN05 3rd Leg port GE1 and GE2 to port gi0/2/26, gi0/2/27 1770A-MAC-001 2) Configure MW link to follow existing 1851B-1770A 3rd leg protection 3) Configure DCN with main and standby GNE | [6 empty] | MTK | SQ202510220678-MTK | MTK | SQ202510220646-MTK | 2026-01-21 | 2026-01-21 | Completed | 2025-12-17 | 2026-01-15 | 2026-01-15 | 2026-01-15 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102323 |  | 2025-10-24 | 2025-10-25 | Completed | 2025-10-23 | 2025-10-24 | 2025-10-23 | 2025-10-25 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-12-12 | 2026-01-08 | 2026-01-08 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-11-27 | 2025-12-12 | 2026-01-06 | 2026-01-09 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-02 | 2025-11-27 | 2025-12-12 | 2026-01-12 | 2026-01-12 | RIDHUAN//BIN MANSOR/8225000011 | 2025-05-14: 2025-11-27; 2025-05-14: 2025-12-12; 2025-05-14: 2025-11-27; 2025-05-15: 2025-11-27 |  |  | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202510300390-GCI | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | CHEONG/SENG/WAH/7018000306
1851B_AD | Rinching Tengah (KJS) | DU00006191900 | Central | Selangor | 2.914596 | 101.856837 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 1KM 2x Patch Cord(Pair) | MW IDU Patching | 1) To patch IDU 1851B-RINCHING TENGAH-RTN19 3RD LEG port GE1 and GE2 to port gi0/2/16, gi0/2/17 1851B-MAC-001 2) Configure MW link to follow existing 1851B-1770A 3rd leg protection 3) Configure DCN with main and standby GNE | 1) To patch IDU 1851B-RINCHING TENGAH-RTN19 3RD LEG port GE1 and GE2 to port gi0/2/16, gi0/2/17 1851B-MAC-001 2) Configure MW link to follow existing 1851B-1770A 3rd leg protection 3) Configure DCN with main and standby GNE | N/A | [5 empty] | MTK | SQ202510220678-MTK | MTK | SQ202510220646-MTK | 2026-02-04 | 2026-02-05 | Completed | 2025-12-17 | 2026-01-15 | 2026-01-15 | 2026-01-15 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-23 | 2026-01-24 | 2026-01-23 | 2026-01-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-23 | 2026-01-24 | 2026-01-23 | 2026-01-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102322 |  | 2025-10-24 | 2025-10-25 | Completed | 2025-10-23 | 2025-10-24 | 2025-10-23 | 2025-10-25 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-31 | 2026-01-14 | 2026-01-08 | 2026-01-08 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-12-31 | 2026-01-14 | 2026-01-03 | 2026-01-09 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-02 | 2025-12-31 | 2026-01-14 | 2026-01-12 | 2026-01-12 | RIDHUAN//BIN MANSOR/8225000011 | 2025-05-14: 2025-12-31; 2025-05-14: 2026-01-14; 2025-05-14: 2026-01-03; 2025-05-15: 2026-01-08 |  |  | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202510300390-GCI | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
9179Z_AD | Rumah Tujang | DU00005976595 | Sarawak | Sarawak | 1.996111 | 111.902639 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M_512QAM_EPLA NE_9179Z New 18G_DP_1.2M(MAC)+OMT x1. Re-use existing RTN910AF(RTN01) New XMC_3E, Sub A&B_Hi x2. FE_9379A New 18G_DP_1.2M(MAC)+OMT x1. Re-use existing RTN910AF(RTN02) New XMC_3E, Sub A&B_Lo x2. | MW Swap | ****IMPORTANT NOTE: 1.EXISTING HW MW LINK 18G_1+0_112M HAVING RSL DEGRADATION(-50~-55dBM) AND INTERFERENCE(TX & RX MODULATION SCHEME MISMATCH) ISSUE-ALREADY TRIGGER ZTE RAVIN FOR TRIGGERING NOC). 2.SUBCON "MANDATORY" TO CHECK FIRST LOS CLEARANCES AT SITE. 3.ENSURE SPACING AVAILABLE TO MOUNT NEW ANTENNA 1.2M/1.2M AT NE & FE. 4.IF CONFIRM NO ISSUE WITH LOS CLEARANCES AND ISSUE WITH INTERFERENCE "ONLY", THEN MAY PROCEED WITH INSTALLATION.**** Existing HW MW link 18G_1+0_112M. MW Hardware Upgrade for existing link to new HW MW Link 18G_2+0_112M_EPLA. Later, decom existing 18G ODU & Antenna ONLY. Site Impacted : 9179Z, 9056Z, 9248Z, 9057Z & 9037Z. NE_9179Z 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Reuse existing RTN910AF(RTN01). 3.Install new XMC_3E, Sub A&B_Hi x2. 4.Reuse existing ISM8 Slot 07 Port 1 & 2. Build new HW MW Link 18G_2+0_112M_EPLA. 5.Reuse existing Vlan DCN & Vlan Services. 6.Later, decom existing 18G ODU & 18G Antenna ONLY. FE_9379A 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Reuse existing RTN910AF(RTN02). 3.Install new XMC_3E, Sub A&B_Lo x2. 4.Reuse existing ISM8 Slot 07 Port 1 & 2. Build new HW MW Link 18G_2+0_112M_EPLA. 5.Reuse existing Vlan DCN & Vlan Services. 6.Re-use existing xD existing IBeam port. 7.Later, decom existing 18G ODU & 18G Antenna ONLY. | ****IMPORTANT NOTE: 1.EXISTING HW MW LINK 18G_1+0_112M HAVING RSL DEGRADATION(-50~-55dBM) AND INTERFERENCE(TX & RX MODULATION SCHEME MISMATCH) ISSUE-ALREADY TRIGGER ZTE RAVIN FOR TRIGGERING NOC). 2.SUBCON "MANDATORY" TO CHECK FIRST LOS CLEARANCES AT SITE. 3. IF CONFIRM NO ISSUE WITH LOS CLEARANCES AND ISSUE WITH INTERFERENCE "ONLY", THEN MAY PROCEED WITH INSTALLATION.**** Existing HW MW link 18G_1+0_112M. MW Hardware Upgrade for existing link to new HW MW Link 18G_2+0_112M_EPLA. Later, decom existing 18G ODU & Antenna ONLY. Site Impacted : 9179Z, 9056Z, 9248Z, 9057Z & 9037Z. NE_9179Z 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Reuse existing RTN910AF(RTN01). 3.Install new XMC_3E, Sub A&B_Hi x2. 4.Reuse existing ISM8 Slot 07 Port 1 & 2. Build new HW MW Link 18G_2+0_112M_EPLA. 5.Reuse existing Vlan DCN & Vlan Services. 6.Later, decom existing 18G ODU & 18G Antenna ONLY. | ****IMPORTANT NOTE: 1.EXISTING HW MW LINK 18G_1+0_112M HAVING RSL DEGRADATION(-50~-55dBM) AND INTERFERENCE(TX & RX MODULATION SCHEME MISMATCH) ISSUE-ALREADY TRIGGER ZTE RAVIN FOR TRIGGERING NOC). 2.SUBCON "MANDATORY" TO CHECK FIRST LOS CLEARANCES AT SITE. 3. IF CONFIRM NO ISSUE WITH LOS CLEARANCES AND ISSUE WITH INTERFERENCE "ONLY", THEN MAY PROCEED WITH INSTALLATION.**** Existing HW MW link 18G_1+0_112M. MW Hardware Upgrade for existing link to new HW MW Link 18G_2+0_112M_EPLA. Later, decom existing 18G ODU & Antenna ONLY. Site Impacted : 9179Z, 9056Z, 9248Z, 9057Z & 9037Z. FE_9379A 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Reuse existing RTN910AF(RTN02). 3.Install new XMC_3E, Sub A&B_Lo x2. 4.Reuse existing ISM8 Slot 07 Port 1 & 2. Build new HW MW Link 18G_2+0_112M_EPLA. 5.Reuse existing Vlan DCN & Vlan Services. 6.Re-use existing xD existing IBeam port. 7.Later, decom existing 18G ODU & 18G Antenna ONLY. | XMC_3E | MAC | 18G | 18G_1.2M(MAC)+OMT x1. | 18G_1.2M(MAC)+OMT x1. | Trintel | SQ202603180360-Trintel | YPTT | SQ202605050456-YPTT // SQ202605050475-YPTT |  |  | Ongoing | 2025-12-15 | 2025-12-18 | 2025-12-15 | 2025-12-18 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26032627 |  | 2026-03-27 |  | Ongoing | 2026-03-26 | 2026-03-27 | 2026-03-26 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-10 | 2026-04-30 | 2026-04-10 |  | LEONARD JEE6794000059 | YPTT TI | 2026-04-10 | 2026-04-30 | 2026-04-10 |  | LEONARD JEE6794000059 | YPTT TI | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-25 | 2026-04-10 | 2026-04-30 | 2026-04-10 |  | LEONARD JEE6794000059 | 2025-05-14: 2026-04-10; 2025-05-14: 2026-04-30; 2025-05-14: 2026-04-10; 2025-05-15: 2026-04-11 | [7 empty] | GTSB | SQ202510100649-GTSB | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | AB.RAHMAN//BIN MAT NOOH/6237001519
3546A42_EVT | MBTS_HARI KEBANGSAAN SABAH 2025 | DU00005976596 | Sabah | Sabah | 5.974868 | 116.067591 | [13 empty] | Planning and integration support only for event site 3546A42 MBTS_HARI KEBANGSAAN SABAH 2025 Tx route: 3546A42-7822A-LL-7000A 1) Share port with 7822A at 7000A 2) New NE ID FE IDU 7822A RTN03 3) New NE ID NE IDU 3546A42 RTN01 4) Transfer 7822A BBU to RTN03. Patch RTN03 to RTN02 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
7996B58_EVT | MBTS HARI SABAH 2025 | DU00005976597 | Sabah | Sabah | 5.980500 | 116.076208 | [13 empty] | Planning and integration support only for event site 7996B58 MBTS HARI SABAH 2025 Tx route: 7996B58-7036A 1) New port IBEAM at 7036A-MAC-001 Pos Malaysia 2) New DCN IP 7036A RTN03 3) New DCN VLAN 7036A RTN03 4) New NE ID FE IDU 7036A RTN03 5) New NE ID NE IDU 7996B58 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
7180D5_EVT | LBTS_HARI KEBANGSAAN SABAH 2025 | DU00005976598 | Sabah | Sabah | 5.975548 | 116.068444 | [13 empty] | Planning and integration support only for event site 7180D5 LBTS_HARI KEBANGSAAN SABAH 2025 Tx route: 7180D5-7809A-LL-7000A 1) Share port with 7809A at 7000A 2) New DCN IP 7809A RTN01 3) New DCN VLAN 7809A RTN01 4) New NE ID FE IDU 7809A RTN01 5) New NE ID NE IDU 7180D5 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
2258A_AD | BatuCave 26 | DU00006538169 | Central | Selangor | 3.239750 | 101.677620 | [7 empty] | 03. TSS Only |  | TSS |  | 18G_1+0_512Q_112Mhz_889Mbps NE: 1x RTN910 1x 0.6m_18G_SP MAC ant 1x ODU XMC-3E 18G sb-A_Lo FE: 1x RTN910 1x 0.6m_18G_SP MAC ant 1x ODU XMC-3E 18G sb-A_Hi 1x Patch cord and SFP (IBEAM) | MW New Link / Reroute | 19 Jan 2026: CD informed drop via whatsapp group on 18 Jan 2026 due to fiber rectification completed. Claim up to TSS only Install new link HW 18G_1+0_512Q_112Mhz_889Mbps_1.88km Existing TX using fiber Required new port IPRAN at FE 1002A Impact site: 2258A | NE: 1. Install RTN910 2. Install 0.6m_18G_SP MAC ant 3. Install 18G XMC-3E sb A_Lo 4. Configure link 18G 1+0 112Mhz 512QAM | FE: 1. Install RTN910 2. Install 0.6m_18G_SP MAC ant 3. Install 18G XMC-3E sb A_Lo 4. Configure link 18G 1+0 112Mhz 512QAM 5. Connect to new port IBEAM | XMC-3E | 18/25 | 18G | 0.6 | 0.6 | GTSB | SQ202601160707-GTSB | GTSB | No PR required-Work at TSS only | 2026-03-02 | 2026-02-23 | Completed | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-02-02 | 2026-01-19 | 2026-01-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-26 | 2026-02-02 | 2026-01-26 | 2026-01-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO | 2026-01-18 |  | Ongoing | 2026-01-17 | 2026-01-18 | 2026-01-17 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202601210792-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q00701_PL_2 | Q143A_Q00701OD_CB_RHSAMBAU | DU00006538170 | Sarawak | Sarawak | 1.262900 | 111.404400 | [9 empty] | TSS+AA+TI |  | 15G_2+0_28M_256QAM_EPLA NE_Q00701 New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(NEID 178-48065). New ISM8 x2. New XMC_5D Pro, Sub B_Lo x1. New IF cables with suitable length and type x1 RUN. FE_Q00404 New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(NEID 178-48068). New ISM8 x2. New XMC_5D Pro, Sub B_Hi x1. New IF cables with suitable length and type x1 RUN. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO CHECK LOS OK & PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL SOLUTION DU Q00701_PL_2 IF ITEM 1 & 2 NOT FULFILL. 4.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_1(TX MINI). 3RD - DU 9223A_PL(TX MINI). 4TH - DU Q00701_PL_2(TX MINI). 5TH - Q00701(NIC).**** Existing HW MW Link_ID SW03670, 8G_4+0_28MHZ_2048QAM_EPLA_968. Build new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. Later, combine existing HW MW Link_ID SW03670, 8G_4+0_28MHZ_2048QAM_EPLA_968 and new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. and become 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. Site Impacted : Q00701 & Q01569. NE_Q00701 1.Install 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 178-48065) and insert ISM8 x1 into slot 04. 3.Also, swap existing ISM6 slot 03 to new ISM8. In order to ensure 6+0 EPLA succes configure between all slot. 4.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 5.Lay new x1 RUN of IF cables for build new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. 6.Later, combine existing HW MW Link_ID SW03670, 8G_4+0_28MHZ_2048QAM_EPLA_968 and new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. and become HW MW Link_ID SW03670, 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. 7.After complete combine HW MW Link_ID SW03670, 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. 8.Migrate traffic Q00701 & Q01569 via HW MW Link_ID SW03670, 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. 9.Ensure proceed to perform DU Q00701 under NIC task in order to divert traffics Q00701 & Q01569 to xD(9223A-LL-9999A). 10.Request new xD Vlan DCN and Vlan Services. FE_Q00404/9223A 1.Install 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 178-48065) and insert ISM8 x1 into slot 04. 3.Also, swap existing ISM6 slot 03 to new ISM8. In order to ensure 6+0 EPLA succes configure between all slot. 4.Install new XMC_5D Pro, Sub B_Hi x1. Configure it. 5.Lay new x1 RUN of IF cables for build new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. 6.Later, combine existing HW MW Link_ID SW03670, 8G_4+0_28MHZ_2048QAM_EPLA_968 and new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. and become HW MW Link_ID SW03670, 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. 7.After complete combine HW MW Link_ID SW03670, 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. 8.Ensure proceed to perform DU Q00701 under NIC task in order to divert traffics Q00701 & Q01569 to xD(9223A-LL-9999A). 9.Request new xD Vlan DCN and Vlan Services. | ****IMPORTANT NOTE: 1.RECOMMENDED TO CHECK LOS OK & PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL SOLUTION DU Q00701_PL_2 IF ITEM 1 & 2 NOT FULFILL. 4.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_1(TX MINI). 3RD - DU 9223A_PL(TX MINI). 4TH - DU Q00701_PL_2(TX MINI). 5TH - Q00701(NIC).**** Existing HW MW Link_ID SW03670, 8G_4+0_28MHZ_2048QAM_EPLA_968. Build new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. Later, combine existing HW MW Link_ID SW03670, 8G_4+0_28MHZ_2048QAM_EPLA_968 and new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. and become 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. Site Impacted : Q00701 & Q01569. NE_Q00701 1.Install 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 178-48065) and insert ISM8 x1 into slot 04. 3.Also, swap existing ISM6 slot 03 to new ISM8. In order to ensure 6+0 EPLA succes configure between all slot. 4.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 5.Lay new x1 RUN of IF cables for build new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. 6.Later, combine existing HW MW Link_ID SW03670, 8G_4+0_28MHZ_2048QAM_EPLA_968 and new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. and become HW MW Link_ID SW03670, 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. 7.After complete combine HW MW Link_ID SW03670, 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. 8.Migrate traffic Q00701 & Q01569 via HW MW Link_ID SW03670, 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. 9.Ensure proceed to perform DU Q00701 under NIC task in order to divert traffics Q00701 & Q01569 to xD(9223A-LL-9999A). 10.Request new xD Vlan DCN and Vlan Services. | ****IMPORTANT NOTE: 1.RECOMMENDED TO CHECK LOS OK & PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE TO INSTALL 1.2M ANTENNA DISH AT NE & FE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. 3.DO NOT INSTALL SOLUTION DU Q00701_PL_2 IF ITEM 1 & 2 NOT FULFILL. 4.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q00701_PL(TX MINI). 2ND - DU Q00701_PL_1(TX MINI). 3RD - DU 9223A_PL(TX MINI). 4TH - DU Q00701_PL_2(TX MINI). 5TH - Q00701(NIC).**** Existing HW MW Link_ID SW03670, 8G_4+0_28MHZ_2048QAM_EPLA_968. Build new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. Later, combine existing HW MW Link_ID SW03670, 8G_4+0_28MHZ_2048QAM_EPLA_968 and new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. and become 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. Site Impacted : Q00701 & Q01569. FE_Q00404/9223A 1.Install 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(NEID 178-48065) and insert ISM8 x1 into slot 04. 3.Also, swap existing ISM6 slot 03 to new ISM8. In order to ensure 6+0 EPLA succes configure between all slot. 4.Install new XMC_5D Pro, Sub B_Hi x1. Configure it. 5.Lay new x1 RUN of IF cables for build new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. 6.Later, combine existing HW MW Link_ID SW03670, 8G_4+0_28MHZ_2048QAM_EPLA_968 and new HW MW Link Q00701-Q00404, 15G_2+0_28MHZ_256QAM_EPLA_400M. and become HW MW Link_ID SW03670, 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. 7.After complete combine HW MW Link_ID SW03670, 8G&15G_6+0_28MHZ_2048QAM&256QAM_EPLA_1368M. 8.Ensure proceed to perform DU Q00701 under NIC task in order to divert traffics Q00701 & Q01569 to xD(9223A-LL-9999A). 9.Request new xD Vlan DCN and Vlan Services. | XMC_5D Pro | MDD | 15G | 15G_1.2M(MDD) x1 | 15G_1.2M(MDD) x1 | NR Services | SQ202601280710-NR Services | YPTT |  |  |  | Ongoing | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-16 | 2026-03-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601210805-GTSB
1781B_AD | TmnBahtera | DU00006538171 | Central | Selangor | 3.250614 | 101.690801 | [7 empty] | 03. TSS Only |  | TSS |  | 18G_2+0_112M_512QAM_EPLA NE_1781B New 18G_0.6M(MDD) x1. New RTN910AF(RTN02). New XMC_5D Pro, Sub B_Lo x1. New CAT6 cable x2. FE_1009A New 18G_0.6M(MDD) x1. New RTN910AF(RTN06). New XMC_5D Pro, Sub B_Hi x1. New CAT6 cable x2.(consider 2x 1G electrical port at IBeam available) | MW New Link / Reroute | Install new HW MW Link 1781B-1009A, 18G_2+0_112MHZ_512QAM_EPLA. Site Impacted : 1781B, 3090B & 1705H. NE_1781B 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Build new HW MW Link 1781B-1009A, 18G_2+0_112MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910A(RTN02) and patching to existing BBU 1781B. Configure it. 6.Enable port 8-EM6-2 of new RTN910A(RTN02) and patching to existing NLOS RTN510A(NEID 180-45126). Configure it. 7.Request new xD vlan dcn and vlan services. 8.Migrate traffics 1781B, 3090B,1861K & 1705H via new HW Link 1781B-1009A, 18G_2+0_112MHZ_512QAM_EPLA. FE_1009A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN06) x1. 3.Install new XMC_5D Pro, Sub B_Hi x1. Configure it. 4.Build new HW MW Link 1781B-1009A, 18G_2+0_112MHZ_512QAM_EPLA. 5.Request new xD vlan dcn and vlan services. 6.Request new 2x electrical ports at IBeam from ZTE IPRAN Team. Enable it. 7.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910A(RTN06) and perform LAG 2x port of IDU-IBeam. 8.Migrate traffics 1781B, 3090B & 1705H into new 2x port LAG at IBeam. | Install new HW MW Link 1781B-1009A, 18G_2+0_112MHZ_512QAM_EPLA. Site Impacted : 1781B, 3090B & 1705H. NE_1781B 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Build new HW MW Link 1781B-1009A, 18G_2+0_112MHZ_512QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910A(RTN02) and patching to existing BBU 1781B. Configure it. 6.Enable port 8-EM6-2 of new RTN910A(RTN02) and patching to existing NLOS RTN510A(NEID 180-45126). Configure it. 7.Request new xD vlan dcn and vlan services. 8.Migrate traffics 1781B, 3090B,1861K & 1705H via new HW Link 1781B-1009A, 18G_2+0_112MHZ_512QAM_EPLA. | Install new HW MW Link 1781B-1009A, 18G_2+0_112MHZ_512QAM_EPLA. Site Impacted : 1781B, 3090B & 1705H. FE_1009A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN06) x1. 3.Install new XMC_5D Pro, Sub B_Hi x1. Configure it. 4.Build new HW MW Link 1781B-1009A, 18G_2+0_112MHZ_512QAM_EPLA. 5.Request new xD vlan dcn and vlan services. 6.Request new 2x electrical ports at IBeam from ZTE IPRAN Team. Enable it. 7.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910A(RTN06) and perform LAG 2x port of IDU-IBeam. 8.Migrate traffics 1781B, 3090B & 1705H into new 2x port LAG at IBeam. | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | GTSB | SQ202601160707-GTSB | GTSB | No PR required-Work at TSS only | 2026-03-02 | 2026-02-23 | Completed | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-02-03 | 2026-01-20 | 2026-01-20 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-26 | 2026-02-02 | 2026-01-26 | 2026-01-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011726 |  | 2026-01-18 | 2026-01-19 | Completed | 2026-01-17 | 2026-01-18 | 2026-01-17 | 2026-01-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | 2026-02-10 | 2026-02-10 | [31 empty] | GTSB | SQ202601210792-GTSB
1377A_AD | TmnSri Batu Caves | DU00006538172 | Central | Selangor | 3.234963 | 101.686895 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_0.6M/0.6M_MDD_112MHZ_256QAM_1556MBPS_XMC5D_SUB_B | MW New Link / Reroute | MW NEW LINK/REROUTE 1377A-1002A WITH HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_256QAM_1556MBPS_XMC5D_SUB_B_LINK_2.82KM IMPACTED: 1377A, 1128D | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 2G | XMC5D | MDD | 18G | 0.6 | 0.6 | GTSB | SQ202601160707-GTSB | GTSB | SQ202601160736-GTSB // SQ202601160739-GTSB | 2026-02-02 | 2026-01-21 | Completed | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-02-02 | 2026-01-19 | 2026-01-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-22 | 2026-01-21 | 2026-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011711 |  | 2026-01-18 | 2026-01-19 | Completed | 2026-01-17 | 2026-01-18 | 2026-01-17 | 2026-01-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-01-26 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-01-26 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-20 | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-01-24 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-05-14: 2026-01-19; 2025-05-14: 2026-01-31; 2025-05-14: 2026-01-19; 2025-05-15: 2026-01-19 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601210773-GCI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | EZRIN TASNIM BIN ABDUL GANI6798000128
1776B_AD | TmnSelaseh | DU00006538173 | Central | Selangor | 3.229305 | 101.697051 | [7 empty] | 00. Site Out/Drop |  | NA |  |  |  | Hold. CD will try to perform fiber reroute first | [7 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1780B_AD | TmnSri Gombak Fasa 8 | DU00006538174 | Central | Selangor | 3.248727 | 101.706347 | [7 empty] | 00. Site Out/Drop |  | NA |  |  |  | Hold. CD will try to perform fiber reroute first | [7 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1187B_AD | Tmn IndustriBolton | DU00006538175 | Central | Selangor | 3.240772 | 101.696068 | [7 empty] | 00. Site Out/Drop |  | NA |  |  |  | Hold. CD will try to perform fiber reroute first | [7 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3630C_AD | PangsapuriMesra Tmn Industri Bolton | DU00006538176 | Central | Selangor | 3.246500 | 101.693100 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M_512QAM NE_3630C New 23G_SP_0.6M(MAC) x1. New RTN910AF(RTN01). New XMC_3E, Sub A_Lo x1. New CAT6 cable x1. FE_B00528/1818K New 23G_SP_0.6M(MAC) x1. New RTN910AF(RTN01). New XMC_3E, Sub A_Hi x1. New CAT6 cable x1. | MW New Link / Reroute | Install new HW MW Link 3630C-B00528/1818K, 23G_1+0_112MHZ_512QAM. Later, decom existing HW MW Link 3630C-1006A, 23G_1+0_55MHZ_256QAM. Site Impacted : 3630C. NE_3630C 1.Install new 23G_SP_0.6M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching existing BBU 3630C to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new xC vlan dcn and vlan services. 7.Migrate traffic 3630C via new HW MW Link 3630C-B00528/1818K, 23G_1+0_112MHZ_512QAM. 8.Decom existing HW MW Link 3630C-1006A, 23G_1+0_55MHZ_256QAM. FE_B00528/1818K 1.Install new 23G_SP_0.6M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to new port(Ge0/2/3) of Cisco Router(PTN ID 70069). Configure it. 6.Request new xC vlan dcn and vlan services. 7.Migrate traffic 3630C via new HW MW Link 3630C-B00528/1818K, 23G_1+0_112MHZ_512QAM. 8.Decom existing HW MW Link 3630C-1006A, 23G_1+0_55MHZ_256QAM. | Install new HW MW Link 3630C-B00528/1818K, 23G_1+0_112MHZ_512QAM. Later, decom existing HW MW Link 3630C-1006A, 23G_1+0_55MHZ_256QAM. Site Impacted : 3630C. NE_3630C 1.Install new 23G_SP_0.6M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching existing BBU 3630C to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new xC vlan dcn and vlan services. 7.Migrate traffic 3630C via new HW MW Link 3630C-B00528/1818K, 23G_1+0_112MHZ_512QAM. 8.Decom existing HW MW Link 3630C-1006A, 23G_1+0_55MHZ_256QAM. | Install new HW MW Link 3630C-B00528/1818K, 23G_1+0_112MHZ_512QAM. Later, decom existing HW MW Link 3630C-1006A, 23G_1+0_55MHZ_256QAM. Site Impacted : 3630C. FE_B00528/1818K 1.Install new 23G_SP_0.6M(MAC) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new XMC_3E, Sub A_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to new port(Ge0/2/3) of Cisco Router(PTN ID 70069). Configure it. 6.Request new xC vlan dcn and vlan services. 7.Migrate traffic 3630C via new HW MW Link 3630C-B00528/1818K, 23G_1+0_112MHZ_512QAM. 8.Decom existing HW MW Link 3630C-1006A, 23G_1+0_55MHZ_256QAM. | XMC_3E | MAC | 23G | 23G_SP_0.6M(MAC) x1 | 23G_SP_0.6M(MAC) x1 | GTSB | SQ202601160707-GTSB // SQ202601190053-GTSB | GTSB | SQ202601190047-GTSB // SQ202601190048-GTSB | 2026-03-02 | 2026-02-23 | Completed | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-20 | 2026-02-03 | 2026-01-20 | 2026-01-20 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-26 | 2026-02-02 | 2026-01-26 | 2026-01-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011713 |  | 2026-01-18 | 2026-01-20 | Completed | 2026-01-17 | 2026-01-18 | 2026-01-17 | 2026-01-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-01-20 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-01-20 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-19 | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-01-23 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-01-19 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601210792-GTSB
3965B_AD | SurauAn-Naim Samudra | DU00006538177 | Central | Selangor | 3.229371 | 101.692561 | [7 empty] | 00. Site Out/Drop |  | NA |  |  |  | Hold. CD will try to perform fiber reroute first | [7 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1128D_AD | TmnPerind | DU00006538178 | Central | Selangor | 3.230650 | 101.684000 | [7 empty] | 00. Site Out/Drop |  | NA |  |  |  | Hold. CD will try to perform fiber reroute first | [7 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3090B_AD | PinggiranBatu Caves (REL) | DU00006538179 | Central | Selangor | 3.253452 | 101.694483 | [7 empty] | 00. Site Out/Drop |  | NA |  |  |  | Hold. CD will try to perform fiber reroute first | [7 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
R00048_HU | R001C_R00048OD_KOLEJDAHLIA | DU00006560880 | Northern | Perlis | 6.449036 | 100.283019 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 18G_1+0_112M with 128QAM. Remote Upgrade to 18G_1+0_112M with 512QAM. Changed Modulation from 128QAM to 512QAM. Site Impacted : 4329K/R00048 | Existing link 18G_1+0_112M with 128QAM. Remote Upgrade to 18G_1+0_112M with 512QAM. Changed Modulation from 128QAM to 512QAM. Site Impacted : 4329K/R00048 | Existing link 18G_1+0_112M with 128QAM. Remote Upgrade to 18G_1+0_112M with 512QAM. Changed Modulation from 128QAM to 512QAM. Site Impacted : 4329K/R00048 | XMC_3E | MAC | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601290549-GCI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | CHEONG/SENG/WAH/7018000306
1608B_HU | PuncakAlam Tower | DU00006560881 | Central | Selangor | 3.219154 | 101.428474 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW Swap | MW SWAP LINK 1608B-2069B WITH HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_128QAM_1352MBPS_XMC5D_SUB_A_LINK_3.21KM IMPACTED: 1608B,1020L DISMANTLE EXISTING LINK | 1. INSTALL NEW 1PCS ISM8 CARD SLOT 3 AT EXISTING 1608B RTN02 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW 1PCS ISM8 CARD SLOT 4 AT EXISTING 2069B RTN03 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM 5. DISMANTLE EXISTING LINK | XMC5D | MDD | 18G | 0.6 | 0.6 | GCI | SQ202602230131-GCI | GCI | SQ202602230123-GCI // SQ202602230127-GCI |  |  | Ongoing | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022305 |  | 2026-02-24 | 2026-02-26 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-10 | 2026-03-02 | 2026-03-03 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-03-03 | 2026-03-10 | 2026-03-02 | 2026-03-16 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-11 | 2026-03-03 | 2026-03-10 | 2026-03-02 | 2026-03-16 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2026-03-03 | 2026-03-10 | 2026-03-02 | 2026-03-10 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | NG HONG JIE7018000036 | Logistic Team | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601290544-GCI | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
7210R_HU | Kg.Senang Hati | DU00006560882 | Sabah | Sabah | 4.506467 | 118.573314 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Hardware Upgrade to XMC_3E with 18G_1+0_112M. Site Impacted : 7210R. NE_7210R. XMC_3E , Sub A_Hi x1. FE_7209A. XMC_3E , Sub A_Lo x1. | MW Hardware Upgrade | Existing link 18G_1+0_56M with XMC_3 ODU Hardware Upgrade to XMC_3E with 18G_1+0_112M. Site Impacted : 7210R. NE_7210R. 1.Hardware upgrade from XMC_3 to XMC_3E , Sub A_Hi. 2.Config parameters and realignment if necessary. 3.Decomm existing XMC_3 only. FE_7209A. 1.Hardware upgrade from XMC_3 to XMC_3E , Sub A_Lo. 2.Config parameters and realignment if necessary. 3.Decomm existing XMC_3 only. | Existing link 18G_1+0_56M with XMC_3 ODU Hardware Upgrade to XMC_3E with 18G_1+0_112M. Site Impacted : 7210R. NE_7210R. 1.Hardware upgrade from XMC_3 to XMC_3E , Sub A_Hi. 2.Config parameters and realignment if necessary. 3.Decomm existing XMC_3 only. | Existing link 18G_1+0_56M with XMC_3 ODU Hardware Upgrade to XMC_3E with 18G_1+0_112M. Site Impacted : 7210R. FE_7209A. 1.Hardware upgrade from XMC_3 to XMC_3E , Sub A_Lo. 2.Config parameters and realignment if necessary. 3.Decomm existing XMC_3 only. | XMC_3E | MAC | 18G | 1.2 | 0.6 | NR services | SQ202603060636-NR Services | NR services | SQ202602160087-NR Services // SQ202602160089-NR Services | 2026-04-02 | 2026-04-02 | Completed | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-03-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-03-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26021231 |  | 2026-02-13 | 2026-02-28 | Completed | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-28 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-15 | 2026-03-15 | 2026-02-15 | 2026-02-28 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-15 | 2026-03-15 | 2026-02-15 | 2026-02-28 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-05 | 2026-02-15 | 2026-03-15 | 2026-02-15 | 2026-03-09 | RALPH O'BRYAN HILARY7167000030 | 2025-05-14: 2026-02-15; 2025-05-14: 2026-03-15; 2025-05-14: 2026-02-15; 2025-05-15: 2026-02-28 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202601290563-GCI | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | CHEONG/SENG/WAH/7018000306
7014D_HU | Kg Tambun Laut | DU00006560883 | Sabah | Sabah | 6.526519 | 116.756430 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Perform MW Hardware Upgrade 18G_1+0_110MHZ_512QAM. NE_7014D Re-use existing 18G_SP_0.6M(MAC) x1. Re-use existing RTN910AF(RTN01, NEID 9-35964). New XMC_3E, Sub B_Hi x1. FE_7951A Re-use existing 18G_SP_0.6M(MAC) x1. Re-use existing RTN910AF(RTN01, NEID 9-37338). New XMC_3E, Sub B_Lo x1. New IF cable with suitable length and type x1 RUN. | MW Hardware Upgrade | Perform MW Hardware Upgrade 18G_1+0_110MHZ_512QAM. Later, decom existing ODU XMC-3 at NE(7014D) & FE(7951A). Also, decom existing RTN910AF(RTN02, NEID 9-35965) ONLY at FE(7951A). Site Impacted : 7014D. NE_7014D 1.Re-use existing 18G_SP_0.6M(MAC) x1. 2.Decom existing ODU XMC-3 and replace with new XMC_3E, Sub B_Hi x1. 3.Re-use existing RTN910AF(RTN01, NEID 9-35964). 4.Build new HW MW Link 18G_1+0_110MHZ_512QAM. 5.Re-use existing Vlan DCN & Vlan Services. 6.Migrate traffic 7014D into new HW MW Link 18G_1+0_110MHZ_512QAM. FE_7951A 1.Re-use existing 18G_SP_0.6M(MAC) x1. 2.Decom existing ODU XMC-3 and replace with new XMC_3E, Sub B_Lo x1. 3.Re-use existing RTN910AF(RTN01, NEID 9-37338) and decom existing RTN910AF(RTN02, NEID 9-35965). 4.Lay new IF cable from ODU XMC-3E to slot 07 Port 1 of existing RTN910AF(RTN01, NEID 9-37338). 5.Build new HW MW Link 18G_1+0_110MHZ_512QAM. 6.Re-use existing Vlan DCN & Vlan Services. 7.Migrate traffic 7014D into existing port of IBeam at CP(7000A). | Perform MW Hardware Upgrade 18G_1+0_110MHZ_512QAM. Later, decom existing ODU XMC-3 at NE(7014D) & FE(7951A). Also, decom existing RTN910AF(RTN02, NEID 9-35965) ONLY at FE(7951A). Site Impacted : 7014D. NE_7014D 1.Re-use existing 18G_SP_0.6M(MAC) x1. 2.Decom existing ODU XMC-3 and replace with new XMC_3E, Sub B_Hi x1. 3.Re-use existing RTN910AF(RTN01, NEID 9-35964). 4.Build new HW MW Link 18G_1+0_110MHZ_512QAM. 5.Re-use existing Vlan DCN & Vlan Services. 6.Migrate traffic 7014D into new HW MW Link 18G_1+0_110MHZ_512QAM. | Perform MW Hardware Upgrade 18G_1+0_110MHZ_512QAM. Later, decom existing ODU XMC-3 at NE(7014D) & FE(7951A). Also, decom existing RTN910AF(RTN02, NEID 9-35965) ONLY at FE(7951A). Site Impacted : 7014D. FE_7951A 1.Re-use existing 18G_SP_0.6M(MAC) x1. 2.Decom existing ODU XMC-3 and replace with new XMC_3E, Sub B_Lo x1. 3.Re-use existing RTN910AF(RTN01, NEID 9-37338) and decom existing RTN910AF(RTN02, NEID 9-35965). 4.Lay new IF cable from ODU XMC-3E to slot 07 Port 1 of existing RTN910AF(RTN01, NEID 9-37338). 5.Build new HW MW Link 18G_1+0_110MHZ_512QAM. 6.Re-use existing Vlan DCN & Vlan Services. 7.Migrate traffic 7014D into existing port of IBeam at CP(7000A). | XMC_3E | MAC | 18G | Re-use existing 18G_SP_0.6M(MAC) | Re-use existing 18G_SP_0.6M(MAC) | NR services | SQ202604100662-NR Services | NR services | SQ202604060625-NR Services // SQ202604060627-NR Services |  |  | Ongoing | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031155 |  | 2026-03-12 | 2026-03-18 | Completed | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-18 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-06 | 2026-05-06 | 2026-04-06 | 2026-04-13 | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-04-06 | 2026-05-06 | 2026-04-06 | 2026-04-13 | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-09 | 2026-04-06 | 2026-05-06 | 2026-04-06 | 2026-04-13 | MIKE MICRON DOLIK6000068237 | 2025-05-14: 2026-04-06; 2025-05-14: 2026-05-06; 2025-05-14: 2026-04-06; 2025-05-15: 2026-04-07 | [7 empty] | GTSB | SQ202601290613-GTSB
N00215_HU | TMPORT DICKSON | DU00006560884 | Southern | Sembilan | 2.518300 | 101.825100 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC | ZTE 18G_1+0_0.6/0.6_112_512_sub A | MW Remote Upgrade | Upgrade remotely Bandwith 55Mhz to 112Mhz 512QAM |  |  | A |  | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [22 empty] | GTSB | SQ202601290646-GTSB | 2026-02-21 | 2026-02-21 | 2026-02-21 | 2026-02-21 | AB.RAHMAN//BIN MAT NOOH/6237001519
Q01886_HU | Q139A_Q01886OD_KGSLABISENGKAM | DU00006560885 | Sarawak | Sarawak | 1.138800 | 110.556820 | [9 empty] | TSS+AA+TI+Dismantle |  | 18G_2+0_110M_256QAM_EPLA NE_9367K/Q01886 New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 17-18001). New XMC_5D Pro, Sub B_Hi x1. New IF cables with suitable length and type x2 RUN. FE_Q00503 New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 17-28001). New XMC_5D Pro, Sub B_Hi x1. New IF cables with suitable length and type x2 RUN. | MW Swap | Existing HW MW Link 9367K/Q01886-Q00503, 18G_1+0_55MHZ_256QAM. Swap existing with new HW MW Link 9367K/Q01886-Q00503, 18G_2+0_110MHZ_256QAM_EPLA. Later, may decom ODU and Antenna ONLY for existing HW MW Link 9367K/Q01886-Q00503, 18G_1+0_55MHZ_256QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 17-18001) at NE and existing RTN910AF(RTN01, NEID 17-28001) at FE. Site Impacted : 9367K/Q01886. NE_9367K/Q01886 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 17-18001). 3.Install new XMC_5D Pro, Sub B_Hi x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN01, NEID 17-18001) ISM8 slot 07 Port 1 & 2 . Build new HW MW Link 9367K/Q01886-Q00503, 18G_2+0_110MHZ_256QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Migrate traffic 9367K/Q01886 to new HW MW Link 9367K/Q01886-Q00503, 18G_2+0_110MHZ_256QAM_EPLA. 6.Later, may decom ODU and Antenna ONLY for existing HW MW Link 9367K/Q01886-Q00503, 18G_1+0_55MHZ_256QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 17-18001) at NE and existing RTN910AF(RTN01, NEID 17-28001) at FE. FE_Q00503 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 17-28001). 3.Install new XMC_5D Pro, Sub B_Lo x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN01, NEID 17-28001) ISM8 slot 07 Port 1 & 2 . Build new HW MW Link 9367K/Q01886-Q00503, 18G_2+0_110MHZ_256QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Migrate traffic 9367K/Q01886 to existing port at PTN/Cisco S00503. 6.Later, may decom ODU and Antenna ONLY for existing HW MW Link 9367K/Q01886-Q00503, 18G_1+0_55MHZ_256QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 17-18001) at NE and existing RTN910AF(RTN01, NEID 17-28001) at FE. | Existing HW MW Link 9367K/Q01886-Q00503, 18G_1+0_55MHZ_256QAM. Swap existing with new HW MW Link 9367K/Q01886-Q00503, 18G_2+0_110MHZ_256QAM_EPLA. Later, may decom ODU and Antenna ONLY for existing HW MW Link 9367K/Q01886-Q00503, 18G_1+0_55MHZ_256QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 17-18001) at NE and existing RTN910AF(RTN01, NEID 17-28001) at FE. Site Impacted : 9367K/Q01886. NE_9367K/Q01886 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 17-18001). 3.Install new XMC_5D Pro, Sub B_Hi x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN01, NEID 17-18001) ISM8 slot 07 Port 1 & 2 . Build new HW MW Link 9367K/Q01886-Q00503, 18G_2+0_110MHZ_256QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Migrate traffic 9367K/Q01886 to new HW MW Link 9367K/Q01886-Q00503, 18G_2+0_110MHZ_256QAM_EPLA. 6.Later, may decom ODU and Antenna ONLY for existing HW MW Link 9367K/Q01886-Q00503, 18G_1+0_55MHZ_256QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 17-18001) at NE and existing RTN910AF(RTN01, NEID 17-28001) at FE. | Existing HW MW Link 9367K/Q01886-Q00503, 18G_1+0_55MHZ_256QAM. Swap existing with new HW MW Link 9367K/Q01886-Q00503, 18G_2+0_110MHZ_256QAM_EPLA. Later, may decom ODU and Antenna ONLY for existing HW MW Link 9367K/Q01886-Q00503, 18G_1+0_55MHZ_256QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 17-18001) at NE and existing RTN910AF(RTN01, NEID 17-28001) at FE. Site Impacted : 9367K/Q01886. FE_Q00503 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 17-28001). 3.Install new XMC_5D Pro, Sub B_Lo x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN01, NEID 17-28001) ISM8 slot 07 Port 1 & 2 . Build new HW MW Link 9367K/Q01886-Q00503, 18G_2+0_110MHZ_256QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Migrate traffic 9367K/Q01886 to existing port at PTN/Cisco S00503. 6.Later, may decom ODU and Antenna ONLY for existing HW MW Link 9367K/Q01886-Q00503, 18G_1+0_55MHZ_256QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 17-18001) at NE and existing RTN910AF(RTN01, NEID 17-28001) at FE. | XMC-5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | GCI | SQ202605050435-GCI | GCI | SQ202605050411-GCI // SQ202605050426-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030638 |  | 2026-03-19 |  | Ongoing | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. |  | Assigned | Ongoing |  | 2026-03-12 | 2026-03-19 |  |  | MAN BIN HARUN7167000009 | NR Service TI | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | NR Service TI | [7 empty] | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | 2025-05-14: 2026-03-12; 2025-05-14: 2026-03-19; 2025-05-14: 2026-03-12 | [7 empty] | GTSB | SQ202601290629-GTSB
S00994_AD | S099A_S00994OD_T3_KGSINULIHAN | DU00006566511 | Sabah | Sabah | 5.297480 | 116.393120 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH cat 6 cable x1. | MW IDU Patching | Offload traffic from xC LL S00989 to xD LL 7701B due to congestion Remarks: Require POI 1) Patch MW link SB02663 S00994_KAMPUNG SINULIHAN - S00989_KAMPUNG TONGULUN JAYA at FE site to xD LL 7701B 2) SB02663 FE RTN910A patching to 7701B_RTN01_GE6 3) Migrate traffic S00994 to 7701B 4) Tx route before: S00994-S00989 5) Tx route after: S00994-7701B 6) Impact site: S00994 Remarks: Require POI |  | Offload traffic from xC LL S00989 to xD LL 7701B due to congestion Remarks: Require POI 1) Patch MW link SB02663 S00994_KAMPUNG SINULIHAN - S00989_KAMPUNG TONGULUN JAYA at FE site to xD LL 7701B 2) SB02663 FE RTN910A patching to 7701B_RTN01_GE6 3) Migrate traffic S00994 to 7701B 4) Tx route before: S00994-S00989 5) Tx route after: S00994-7701B 6) Impact site: S00994 Remarks: Require POI | [5 empty] | NR services | SQ202602160101-NR Services | NR services | SQ202602130278-NR Services |  |  | Ongoing | 2026-02-14 | 2026-02-14 | 2026-02-14 | 2026-02-14 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-03-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-03-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-03-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26020456 |  | 2026-02-05 | 2026-02-10 | Completed | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-10 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-10 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-02-15 | 2026-02-15 | 2026-02-15 | 2026-02-15 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-15 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-10 | LEONARD//EDUAN/6000038538 | 2025-05-14: 2026-02-09; 2025-05-14: 2026-03-09; 2025-05-14: 2026-02-09; 2025-05-15: 2026-02-09 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202602120118-GCI | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | CHEONG/SENG/WAH/7018000306
Q02235_HU_1 | SK SUNGAI BURIBAKONG 1 | DU00006566512 | Sarawak | Sarawak | 4.205450 | 114.076930 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M_512QAM_EPLA NE_Q02235 New 15G_1.2M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x1. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x2. FE_Q02310 New 15G_1.2M(MDD)+Dual Coupler x1. New RTN910AF(RTN02). New ISM8 x1. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. | MW Swap | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q02310_HU. 2ND - DU Q02235_HU_1.**** Existing SM MW Link_SW04223, Q02235-Q02310, 13G_1+0_28MHZ_512QAM. MW Swap to new HW MW Link Q02235-Q02310, 15G_4+0_28MHZ_512QAM_EPLA. Later, decom existing SM MW Link_SW04223, Q02235-Q02310 MW1, 13G_1+0_28MHZ_512QAM. Site Impacted : Q02235, Q02234 & Q02236. NE_Q02235 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF and perform patching to existing BBU. 5.Enable port 8-EM6-2 of new RTN910AF and perform new cascading with LAN 2 of existing SM IDU AGS20(IP Address 10.127.203.55) of existing SM MW Link_SW04225, Q02236-Q02235 MW1. 6.Request new xC Vlan DCN and re-use existing Vlan Services. 7.Migrate traffics Q02235, Q02234 & Q02236 via new HW MW Link Q02235-Q02310, 15G_4+0_28MHZ_512QAM_EPLA. 8.Later, decom existing SM MW Link_SW04223, Q02235-Q02310 MW1, 13G_1+0_28MHZ_512QAM. FE_Q02310 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Enable port 8-EM6-2 of new RTN910AF(RTN01) under 1st DU Q02310_HU of new HW MW Link Q02310-Q01732, 18G_1+0_110MHZ_512QAM_EPLA. 6.Request new xC Vlan DCN and re-use existing Vlan Services. 7.Migrate traffics Q02235, Q02234 & Q02236 via new HW MW Link Q02235-Q02310, 15G_4+0_28MHZ_512QAM_EPLA. 8.Later, decom existing SM MW Link_SW04223, Q02235-Q02310 MW1, 13G_1+0_28MHZ_512QAM. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q02310_HU. 2ND - DU Q02235_HU_1.**** Existing SM MW Link_SW04223, Q02235-Q02310, 13G_1+0_28MHZ_512QAM. MW Swap to new HW MW Link Q02235-Q02310, 15G_4+0_28MHZ_512QAM_EPLA. Later, decom existing SM MW Link_SW04223, Q02235-Q02310 MW1, 13G_1+0_28MHZ_512QAM. Site Impacted : Q02235, Q02234 & Q02236. NE_Q02235 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF and perform patching to existing BBU. 5.Enable port 8-EM6-2 of new RTN910AF and perform new cascading with LAN 2 of existing SM IDU AGS20(IP Address 10.127.203.55) of existing SM MW Link_SW04225, Q02236-Q02235 MW1. 6.Request new xC Vlan DCN and re-use existing Vlan Services. 7.Migrate traffics Q02235, Q02234 & Q02236 via new HW MW Link Q02235-Q02310, 15G_4+0_28MHZ_512QAM_EPLA. 8.Later, decom existing SM MW Link_SW04223, Q02235-Q02310 MW1, 13G_1+0_28MHZ_512QAM. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU Q02310_HU. 2ND - DU Q02235_HU_1.**** Existing SM MW Link_SW04223, Q02235-Q02310, 13G_1+0_28MHZ_512QAM. MW Swap to new HW MW Link Q02235-Q02310, 15G_4+0_28MHZ_512QAM_EPLA. Later, decom existing SM MW Link_SW04223, Q02235-Q02310 MW1, 13G_1+0_28MHZ_512QAM. Site Impacted : Q02235, Q02234 & Q02236. FE_Q02310 1.Install new 15G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN02). 5.Enable port 8-EM6-2 of new RTN910AF(RTN01) under 1st DU Q02310_HU of new HW MW Link Q02310-Q01732, 18G_1+0_110MHZ_512QAM_EPLA. 6.Request new xC Vlan DCN and re-use existing Vlan Services. 7.Migrate traffics Q02235, Q02234 & Q02236 via new HW MW Link Q02235-Q02310, 15G_4+0_28MHZ_512QAM_EPLA. 8.Later, decom existing SM MW Link_SW04223, Q02235-Q02310 MW1, 13G_1+0_28MHZ_512QAM. | XMC_5D Pro | MDD | 15G | 15G_1.2M(MDD)+Dual Coupler x1 | 15G_1.2M(MDD)+Dual Coupler x1 | NR Services | SQ202603180539-NR Services | NR Services | SQ202603180535-NR Services // SQ202603180535-NR Services |  |  | Ongoing | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030639 |  | 2026-03-19 |  | Ongoing | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. |  | Assigned | Ongoing |  | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | NR Service TI | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | NR Service TI | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-17 | 2026-03-12 | 2026-03-19 | 2026-03-12 |  | MAN BIN HARUN7167000009 | 2025-05-14: 2026-03-12; 2025-05-14: 2026-03-19; 2025-05-14: 2026-03-12; 2025-05-15: 2026-03-14 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202602120283-GTSB
9289B-9330B | Times Square Bintulu RT | DU00004299845 | Sarawak | Sarawak | 3.197614 | 113.088123 |  | FEB 25 |  |  |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_9289B 18G_DP_0.6m(MAC)+OMT x1. XMC_3E , Sub_B_Hi x2. FE_9330B 18G_DP_0.6m(MAC)+OMT x1. XMC_3E , Sub_B_Lo x2. | MW Swap | Existing link 18G_1+0_112M. Swap existing to 18G_2+0_112M Site Impacted: 9289B. NE_9289B 1.Install new 18G_DP_0.6m. 2.Reuse existing 9289B_RTN01 and config to 7_ISM8-2+0. 3.Install a new XMC_3E , Sub_B_Hi. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new link 18G_2+0_112M. 6.Decom existing ODU and Ant. FE_9330B 1.Install new 18G_DP_0.6m. 2.Reuse existing 9330B_RTN01 and config to 7_ISM8-2+0. 3.Install a new XMC_3E , Sub_B_Lo. 4.Enable EPLA and service cross connect. 5.Traffic migrate to new link 18G_2+0_112M. 6.Decom existing ODU and Ant. | [7 empty] | Allstar | SQ202504210307-Allstar | Allstar | SQ202503200288-Allstar // SQ202503200295-Allstar // SQ202504260202-Allstar | 2025-05-28 | 2025-06-12 | Completed | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-06-12 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-04-24 | 2025-04-25 | 2025-04-24 | 2025-04-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-24 | 2025-04-25 | 2025-04-24 | 2025-04-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-28 | 2025-05-02 | 2025-04-28 | 2025-04-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020603 |  | 2025-02-07 | 2025-02-25 | Completed | 2025-02-06 | 2025-02-07 | 2025-02-06 | 2025-02-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-28 | 2025-03-06 | 2025-03-06 | 2025-03-24 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-02-28 | 2025-03-06 | 2025-03-24 | 2025-03-24 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-19 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-03-19 | 2025-02-28 | 2025-03-06 | 2025-03-22 | 2025-03-22 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | 2025-02-28 | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-19 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-06-19 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI_AA | SQ202510300174-GCI | 2025-10-23 | 2025-10-23 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
2049B-2901A | Taman Mas Sepang (Celcom) | DU00004299846 | Central | Selangor | 2.968462 | 101.581551 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 29/10: Cutover done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | Software upgrade to 18G_2+0_112M_256QAM | MW Remote Upgrade | Existing link 18G_2+0_56M Software upgarde to 18G_2+0_112M_256QAM | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | SHUJAAT//ALI/6800000124 | [17 empty] | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
7420B-7434B | Mile 20 Sdk | DU00004299847 | Sabah | Sabah | 5.859491 | 117.862963 |  |  |  |  | RFS | Pending RFS declare | ZTE | 00. Integrated/RFS Done | DO ready | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M. NE_7420B 13G_DP_1.2m(MS) x1. XMC_3 , Sub B_Lo x2 XMC_3 , Sub A_Lo x2. Coupler x2 Waveguide x 2. ISM8 x 2. FE_7434B 13G_DP_1.2m(MS) x1. XMC_3 , Sub_B_Hi x2 XMC_3 , Sub A_Hi x2. RTN910A x1. ISM8 x2. Coupler x2. Waveguide x2. | MW Swap | Existing link 13G_2+0_28M. Swap existing link to 13G_4+0_28M. Site Impacted : 7420B. NE_7420B 1.Install 13G_DP_1.2m(MS). 2.Install new XMC_3-4+0 , Sub B & A_Lo. 3.Install Coupler + Waveguide. 4.Reuse existing 7420B_RTN01. 5.Install 3_ISM8 and 4_ISM8 into existing 7420B_RTN01. 6.Create EPLA and service cross connect. 7.Migrate traffic to new link. 8.Decom existing Ant and ODU. FE_7434B 1.Install 13G_DP_1.2m(MS). 2.Install new XMC_3-4+0 , Sub_B A_Hi. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install 3_ISM8 and 4_ISM8. 5.Install Coupler + Waveguide. 6.Create EPLA and service cross connect. 7.Migrate traffic to new link. 8.Decom existing Ant , ODU and IDU. | Existing link 13G_2+0_28M. Swap existing link to 13G_4+0_28M. Site Impacted : 7420B. NE_7420B 1.Install 13G_DP_1.2m(MS). 2.Install new XMC_3-4+0 , Sub B & A_Lo. 3.Install Coupler + Waveguide. 4.Reuse existing 7420B_RTN01. 5.Install 3_ISM8 and 4_ISM8 into existing 7420B_RTN01. 6.Create EPLA and service cross connect. 7.Migrate traffic to new link. 8.Decom existing Ant and ODU. | Existing link 13G_2+0_28M. Swap existing link to 13G_4+0_28M. Site Impacted : 7420B. FE_7434B 1.Install 13G_DP_1.2m(MS). 2.Install new XMC_3-4+0 , Sub_B A_Hi. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install 3_ISM8 and 4_ISM8. 5.Install Coupler + Waveguide. 6.Create EPLA and service cross connect. 7.Migrate traffic to new link. 8.Decom existing Ant , ODU and IDU. | XMC_3 | MS | 13G | 1.2 | 1.2 | NR services | SQ202502260432-NR Services | NR services | SQ202504080129-NR Services // SQ202504080132-NR Services // SQ202504260199-NR Services | 2025-07-11 | 2025-07-07 | Completed | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022310 |  | 2025-02-24 | 2025-02-24 | Completed | 2025-02-23 | 2025-02-24 | 2025-02-23 | 2025-02-24 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-12 | 2025-03-31 | 2025-03-12 | 2025-03-16 | ANUAR BIN BASRI6000002574 | NR Service TI | 2025-03-07 | 2025-03-31 | 2025-03-07 | 2025-03-16 | ANUAR BIN BASRI6000002574 | NR Service TI | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-17 | 2025-03-07 | 2025-03-31 | 2025-03-07 | 2025-03-24 | ANUAR BIN BASRI6000002574 | 2025-03-07 | 2025-03-31 | 2025-03-07 | 2025-03-12 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GCI_AA | SQ202510300170-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
4012D-4644A | ISTANA BUKIT MALUT (CELCOM) | DU00004299848 | Northern | Kedah | 6.313284 | 99.784546 |  |  | WK45-48 | NOV 24 |  |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Swap existing link to new 15G_4+0_28M_CA. NE_4012D 1.Install new 15G_DP_1.2m(MDD) x1. 2.Install new ISM8 x2. 3.Install new XMC_5D,Sub_B_Lo x1. FE_4644A 1.Install new 15G_DP_1.2m(MDD) x1. 2.Install new RTN910A x1. 3.Install ISM8 x2. 4.Install new XMC_5D,Sub_B_Hi x1. | MW Swap | Existing link 15G_1+0_28M. Swap existing link to new 15G_4+0_28M_CA. Site Impacted: 1571B,4012D. NE_4012D 1.Install new 15G_DP_1.2m(MDD). 2.Reuse existing RTN01. 3.Install new 3_ISM8 & 4_ISM8. 4.Install new XMC_5D,Sub_B_Lo. 5.Config EPLA , CA and service cross connect. 6.Migrate service to new link.(4012D & 1571B). 7.Decom existing ODU and ant. FE_4644A 1.Install new 15G_DP_1.2m(MDD). 2.Install new RTN910A. 3.Install 3_ISM8 & 4_ISM8. 4.Install new XMC_5D,Sub_B_Hi. 5.Config EPLA, CA and service cross connect. 6.Create In-Band DCN and Enable GE1. 7.Patching GE1 to PFS. 8.Traffic migrate to new link (4012D & 1571B). 9.Decom existing ODU , ISV3 and ANT. | [7 empty] | GCI | SQ202411180371-GCI | GCI | SQ202411150562-GCI // SQ202505210152-GCI // SQ202508140738-GCI | 2025-10-25 | 2025-10-24 | Completed | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022657 |  | 2025-02-27 | 2025-03-14 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-03-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2025-05-24 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2025-07-06 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-05-19 | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2026-03-31 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | 2025-02-28: 2025-03-24; 2025-03-06: 2025-03-31; 2025-03-06: 2025-03-24; 2025-03-06: 2025-05-16 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506050701-GCI | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
4174A-4000A | LBSB Factory | DU00004299849 | Northern | Penang | 5.354917 | 100.408861 |  |  | WK45-48 | NOV 24 |  |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Swap existing link to 15G_4+0_28M_CA. NE_4147A. 1.Install 15G_DP_0.6m(MDD) x1. 2.Install new XMC_5D, Sub_B_Lo x1. 3.Install new RTN910A x1. 4.Install new ISM8 x2. FE_4000A. 1.Install 15G_DP_1.2m(MDD) x1. 2.Install new XMC_5D, Sub_B_Hi x1. 3.Install new RTN910A x1. 4.Install new ISM8 x2. | MW Swap | Existing link 15G_1+0_28M. Swap existing link to 15G_4+0_28M_CA. Site Impacted: 4174A. NE_4174A. 1.Install 15G_DP_0.6m(MDD). 2.Install new XMC_5D, Sub_B_Lo. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 to config 4+0_CA. 5.Enable EPLA , CA and service cross connect. 6.Migrate traffic to new link. 7.Decom existing MW link. FE_4000A. 1.Install 15G_DP_1.2m(MDD). 2.Install new XMC_5D, Sub_B_Hi. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install new 3_ISM8 and 4_ISM8 to configure 4+0_CA. 5.Enable EPLA,CA and service cross connect. 6.Enable GE port and create In-Band DCN. 7.Patching ETH cable to PFS port. 8.Decom existing MW link. | Existing link 15G_1+0_28M. Swap existing link to 15G_4+0_28M_CA. Site Impacted: 4174A. NE_4174A. 1.Install 15G_DP_0.6m(MDD). 2.Install new XMC_5D, Sub_B_Lo. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 to config 4+0_CA. 5.Enable EPLA , CA and service cross connect. 6.Migrate traffic to new link. 7.Decom existing MW link. | Existing link 15G_1+0_28M. Swap existing link to 15G_4+0_28M_CA. Site Impacted: 4174A. FE_4000A. 1.Install 15G_DP_1.2m(MDD). 2.Install new XMC_5D, Sub_B_Hi. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install new 3_ISM8 and 4_ISM8 to configure 4+0_CA. 5.Enable EPLA,CA and service cross connect. 6.Enable GE port and create In-Band DCN. 7.Patching ETH cable to PFS port. 8.Decom existing MW link. | [5 empty] | CCSMY | SQ202411180356-CCS | CCSMY | SQ202411150552-CCS // SQ202504260175-CCS |  |  | Ongoing | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25022092 |  | 2025-02-21 | 2025-03-16 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-03-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-06 | 2025-03-31 | 2025-03-06 | 2025-03-16 | MUHAMMAD//AWAIS/7021000082 | CCS TI | 2025-03-06 | 2025-03-31 | 2025-03-06 | 2025-04-16 | MUHAMMAD//AWAIS/7021000082 | CCS TI | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-13 | 2025-03-06 | 2025-03-31 | 2025-03-06 | 2025-04-09 | MUHAMMAD//AWAIS/7021000082 | 2025-03-06 | 2025-03-31 | 2025-03-06 | 2025-03-17 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
9004C-9106A | Batu 5 Bintulu | DU00004299850 | Sarawak | Sarawak | 3.193403 | 113.095606 | [6 empty] | ZTE | 00. Integrated/RFS Done | 29/10: Cutover done 23/10: Interim solution: To proceed with SW Upgrade activity | AA | PAC | Existing link 18G_1+0_56M Software upgrade to 18G_1+0_112M_256QAM | MW Remote Upgrade | Existing 18G_1+0_56M with XMC_3E. Software upgrade to 18G_1+0_256QAM 112M. | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2024-12-04 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2025-02-21 | 2025-03-21 | 2025-02-21 | 2025-02-21 | NURUL//NADIA BINTI ABDULLAH/6800000045
3313C-1082A | Jalan Sidang | DU00004299851 | Central | Selangor | 2.939386 | 101.326464 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 13/11: Cutover done 29/10: 3313C odu v cannot support 112, and the card used in ism6, need hardware upgrade | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_3313C RTN910A x1. 23G_XMC_3 , Sub A & B_Lo x2. FE_1082A XMC_3-2+0 , Sub_A & B_Hi x2. | MW Hardware Upgrade | Existing link 23G_2+0_56M. Swap existing link to 23G_2+0_112M due to remote software upgrade not support. Site Impacted: 3313C. NE_3313C 1.Reuse existing 23G_DP_0.6m ant. 2.Install new RTN910A,7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new 23G_XMC_3-2+0 , Sub A & B_Lo 4.Enable EPLA & Service cross connect. 5.Migrate traffic to new hardware upgrade link. 6.Decom existing IDU & ODU. FE_1082A 1.Reuse existing 23G_DP_0.6m ant. 2.Reuse existing 1082A_RTN08 ,7_ISM8-2+0. 3.Install new XMC_3-2+0 , Sub_A & B_Hi. 4.Enable EPLA & service cross connect. 5.Migrate traffic to new hardware upgrade link. 6.Decom existing 23G ODU. | [7 empty] | GTSB | SQ202411140220-GTSB | GTSB | SQ202411150545-GTSB // SQ202504260131-GTSB | 2024-12-06 | 2024-12-05 | Completed | 2024-11-19 | 2024-12-03 | 2024-11-19 | 2024-11-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-20 | 2024-11-21 | 2024-11-20 | 2024-11-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-20 | 2024-11-21 | 2024-11-20 | 2024-11-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-12-05 | 2024-12-06 | 2024-12-05 | 2024-12-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24103032 |  | 2024-10-31 | 2024-11-05 | Completed | 2024-10-30 | 2024-10-31 | 2024-10-30 | 2024-11-05 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-13 | 2024-11-30 | 2024-11-13 | 2024-11-15 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2024-11-13 | 2024-11-30 | 2024-11-13 | 2024-11-15 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2024-11-13 | 2024-11-13 | 2024-11-13 | 2024-11-13 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-11-13 | 2024-11-30 | 2024-11-13 | 2024-11-13 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2024-11-13 | 2024-11-30 | 2024-11-13 | 2024-11-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
4821C-4017B | Pulau Betong PDC (REL) | DU00004299852 | Northern | Penang | 5.307987 | 100.204149 |  |  | WK45-48 | NOV 24 |  |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M_CA. NE_4821C. 1.Install 15G_DP_1.2m(MDD) x1. 2.Install new ISM8 x2. 3.Install new XMC_5D ,Sub_B_Lo x1. NE_4017B 1.Install 15G_DP_0.6m(MDD) x1. 2.Install new ISM8 x2 3.Install new XMC_5D, Sub_B_Hi x1. | MW Swap | Existing link 15G_2+0_28M Swap existing link to 15G_4+0_28M_CA. Site Impacted: 4821C. NE_4821C. 1.Install 15G_DP_1.2m(MDD). 2.Reuse existing 4821C_RTN01. 3.Install new 3_ISM8 and 4_ISM8 with CA config. 4.Install new XMC_5D ,Sub_B_Lo. 5.Enable EPLA,CA and service cross connect. 6.Migrate traffic to new link. 7.Decom existing ODU and ant. FE_4017B 1.Install 15G_DP_0.6m(MDD). 2.Reuse existing 4017B_RTN04. 3.Install new 3_ISM8 and 4_ISM8 with CA config. 4.Install new XMC_5D, Sub_B_Hi. 5.Enable EPLA,CA and service cross connect. 6.Decom existing ODU and ant. | Existing link 15G_2+0_28M Swap existing link to 15G_4+0_28M_CA. Site Impacted: 4821C. NE_4821C. 1.Install 15G_DP_1.2m(MDD). 2.Reuse existing 4821C_RTN01. 3.Install new 3_ISM8 and 4_ISM8 with CA config. 4.Install new XMC_5D ,Sub_B_Lo. 5.Enable EPLA,CA and service cross connect. 6.Migrate traffic to new link. 7.Decom existing ODU and ant. | Existing link 15G_2+0_28M Swap existing link to 15G_4+0_28M_CA. Site Impacted: 4821C. FE_4017B 1.Install 15G_DP_0.6m(MDD). 2.Reuse existing 4017B_RTN04. 3.Install new 3_ISM8 and 4_ISM8 with CA config. 4.Install new XMC_5D, Sub_B_Hi. 5.Enable EPLA,CA and service cross connect. 6.Decom existing ODU and ant. | XMC_5D | MDD | 14669.000 14725.000 14781.000 14837.000 | 1.2 | 0.6 | CCSMY | SQ202411180356-CCS | CCSMY | SQ202411150552-CCS // SQ202504260175-CCS | 2025-10-25 | 2025-10-24 | Completed | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022650 |  | 2025-02-27 | 2025-03-07 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-03-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-03 | 2025-03-28 | 2025-03-03 | 2025-03-07 | Saleem//Muhammed/7021000077 | CCS TI | 2025-03-03 | 2025-03-28 | 2025-03-03 | 2025-03-07 | Saleem//Muhammed/7021000077 | CCS TI | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-05 | 2025-03-03 | 2025-03-28 | 2025-03-03 | 2025-03-21 | Saleem//Muhammed/7021000077 | 2025-03-03 | 2025-03-28 | 2025-03-03 | 2025-03-11 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-20 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
2641B-1073A_1 | Desa Alam | DU00004299853 | Central | Selangor | 3.088384 | 101.486711 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 27/2/2025 : Cutover done 26/2/2025 : Cutover done with issue child site alarm 25/2/2025 : Installation complete, pending alignment 13/1/2025 : EDGEPOINT INFRA - 30M Monopole - NE site 2641B Desa Alam, FIBERAIL SDN BHD - 45M 3 Legged Tower - FE site 1073A KTM Padang Jawa | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Hot Swap existing link to 18G_2+0_112M. NE_2641B. 1.Install new 18G_DP_0.6m(MDD) x1. 2.Install new 18G XMC_5D ODU x1. FE_1073A 1.Install new 18G_DP_1.2m(MDD) x1. 2.Install new 18G XMC_5D ODU x1. | MW Swap | Existing link 15G_4+0_28M Hot Swap existing link to 18G_2+0_112M. Site Impacted: 2641B,1524C. NE_2641B. 1.Install new 18G_DP_0.6m(MDD). 2.Reuse existing 2641B_RTN01. 3.Reuse 3_ISM8-2+0.(2641B-DESA ALAM-RTN01). 4.Install new 18G XMC_5D ODU. 5.Configure EPLA and service cross connect. 6.Config 18G_2+0_112M. 7.Traffic migrate to new link(2641B & 1524C). 8.Decom existing 15G XMC_5D ODU , Ant and 4_ISM8. FE_1073A 1.Install new 18G_DP_1.2m(MDD). 2.Reuse existing 1073A_RTN07 , 7_ISM8-2+0, 3.Install new 18G XMC_5D ODU. 4.Config 18G_2+0_112M. 5.Configure EPLA and service cross connect. 6.Traffic migrate to new link (2641B & 1524C). 7.Reuse existing In-Band DCN 8.Decom existing 15G XMC_5D ODU , Ant , and 3 & 4_ISM8. | [7 empty] | GCI | SQ202503060118-GCI | GCI | SQ202503050449-GCI // SQ202504150088-GCI | 2025-07-05 | 2025-07-03 | Completed | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010847 | 18G 0.6/1.2 2+0. wip P.Dismantle 18G 0.6 & 1.2 DP antenna ⏸️ | 2025-01-09 | 2025-01-18 | Completed | 2025-01-08 | 2025-01-09 | 2025-01-17 | 2025-01-18 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2025-03-04 | 2025-02-24 | 2025-02-25 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-25 | 2025-03-04 | 2025-02-24 | 2025-03-03 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-27 | 2025-02-25 | 2025-03-04 | 2025-02-24 | 2025-02-28 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-02-25 | 2025-03-04 | 2025-02-24 | 2025-02-25 | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358
4375B_AD | Kg Rambai Tujuh (KJS_ZED) RCD | DU00006488128 | Northern | Perak | 4.689446 | 100.981693 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M_256QAM NE_4375B New 18G_1.2M(MDD) x1. New RTN910AF(RTN02). New XMC_5D Pro, Sub A_Lo x1. New CAT6 cable x1. FE_4314K/A01138 New 18G_1.2M(MDD) x1. New ISM8 x1. New XMC_5D Pro, Sub A_Hi x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.MANDATORY TO INSTALL DU A01138_AD FIRST AS NEW UPLINK HW MW LINK 4314K-4379A AND NEW DOWN LINK 4375B-4314K WILL SHARE IDU RTN910AF(RTN02).**** Existing HW MW Link 4375B-4374B, 15G_2+0_28MHZ. Install new HW MW Link 4375B-4314K, 18G_1+0_112MHZ_256QAM. Later, decom existing HW MW Link 4375B-4374B, 15G_2+0_28MHZ. Site Impacted : 4375B. NE_4375B 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching traffic to port 8-EM6-1 of new RTN910A(RTN02). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic 4375B via new HW MW Link 4375B-4314K, 18G_1+0_112MHZ_256QAM. 8.Decom existing HW MW Link 4375B-4374B, 15G_2+0_28MHZ. FE_4314K/A01138 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02) under DU A01138. Insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Request new xD vlan dcn and vlan services. 5.Migrate traffic 4375B via new port of IBeam CP 4379A similar port with uplink traffic 4314K. 6.Decom existing HW MW Link 4375B-4374B, 15G_2+0_28MHZ. | ****IMPORTANT NOTE: 1.MANDATORY TO INSTALL DU A01138_AD FIRST AS NEW UPLINK HW MW LINK 4314K-4379A AND NEW DOWN LINK 4375B-4314K WILL SHARE IDU RTN910AF(RTN02).**** Existing HW MW Link 4375B-4374B, 15G_2+0_28MHZ. Install new HW MW Link 4375B-4314K, 18G_1+0_112MHZ_256QAM. Later, decom existing HW MW Link 4375B-4374B, 15G_2+0_28MHZ. Site Impacted : 4375B. NE_4375B 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching traffic to port 8-EM6-1 of new RTN910A(RTN02). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic 4375B via new HW MW Link 4375B-4314K, 18G_1+0_112MHZ_256QAM. 8.Decom existing HW MW Link 4375B-4374B, 15G_2+0_28MHZ. | ****IMPORTANT NOTE: 1.MANDATORY TO INSTALL DU A01138_AD FIRST AS NEW UPLINK HW MW LINK 4314K-4379A AND NEW DOWN LINK 4375B-4314K WILL SHARE IDU RTN910AF(RTN02).**** Existing HW MW Link 4375B-4374B, 15G_2+0_28MHZ. Install new HW MW Link 4375B-4314K, 18G_1+0_112MHZ_256QAM. Later, decom existing HW MW Link 4375B-4374B, 15G_2+0_28MHZ. Site Impacted : 4375B. FE_4314K/A01138 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02) under DU A01138. Insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Request new xD vlan dcn and vlan services. 5.Migrate traffic 4375B via new port of IBeam CP 4379A similar port with uplink traffic 4314K. 6.Decom existing HW MW Link 4375B-4374B, 15G_2+0_28MHZ. | XMC_5D Pro | MDD | 18G | 18G_1.2M(MDD) x1 | 18G_1.2M(MDD) x1 | GTSB | SQ202512300376-GTSB | GTSB | SQ202512300360-GTSB // SQ202512300366-GTSB | 2026-01-28 | 2026-01-30 | Completed | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122948 |  | 2025-12-30 | 2025-12-30 | Completed | 2025-12-29 | 2025-12-30 | 2025-12-29 | 2025-12-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2026-01-09 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2026-01-09 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-01 | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2026-01-12 | HAMZAH BIN ABDUL MUTALIF6799000301 | 2025-02-28: 2025-12-30; 2025-03-06: 2025-12-30; 2025-03-06: 2025-12-30; 2025-03-06: 2026-01-08 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512290820-GTSB
A01138_AD | A041A_A01138OD_KG_MENORA_KK | DU00006488129 | Northern | Perak | 4.713329 | 100.944070 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M_256QAM_EPLA. NE_4314K/A01138 New 18G_1.2M(MDD) x1. New RTN910AF(RTN02). New XMC_5D Pro, Sub B_Hi x1. New CAT6 cable x1. FE_4379A New 18G_1.2M(MDD) x1. New RTN910AF(RTN08). New XMC_5D Pro, Sub B_Lox1. New CAT6 cable x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.MANDATORY TO INSTALL DU A01138_AD FIRST AS NEW UPLINK HW MW LINK 4314K-4379A AND NEW DOWN LINK 4375B-4314K WILL SHARE IDU RTN910AF(RTN02).**** Install new HW MW Link 4314K-4379A, 18G_2+0_112MHZ_256QAM_EPLA. Later, decom existing HW MW Link 4314K-4374B. Site Impacted : 4314K. NE_4314K/A01138 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching traffic to port 8-EM6-1 of new RTN910A(RTN02). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic 4314K via new HW MW Link 4314K-4379A, 18G_2+0_112MHZ_256QAM_EPLA. 8.Decom existing HW MW Link 4314K-4374B. FE_4379A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02) under DU A01138. Insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Request new xD vlan dcn and vlan services. 5.Request new IBeam port at CP 4379A. 6.Migrate traffic 4314K via new port of IBeam CP 4379A. 7.Decom existing HW MW Link 4314K-4374B. | ****IMPORTANT NOTE: 1.MANDATORY TO INSTALL DU A01138_AD FIRST AS NEW UPLINK HW MW LINK 4314K-4379A AND NEW DOWN LINK 4375B-4314K WILL SHARE IDU RTN910AF(RTN02).**** Install new HW MW Link 4314K-4379A, 18G_2+0_112MHZ_256QAM_EPLA. Later, decom existing HW MW Link 4314K-4374B. Site Impacted : 4314K. NE_4314K/A01138 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910A(RTN02) x1. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN02). 5.Patching traffic to port 8-EM6-1 of new RTN910A(RTN02). Configure it. 6.Request new xD vlan dcn and vlan services. 7.Migrate traffic 4314K via new HW MW Link 4314K-4379A, 18G_2+0_112MHZ_256QAM_EPLA. 8.Decom existing HW MW Link 4314K-4374B. | ****IMPORTANT NOTE: 1.MANDATORY TO INSTALL DU A01138_AD FIRST AS NEW UPLINK HW MW LINK 4314K-4379A AND NEW DOWN LINK 4375B-4314K WILL SHARE IDU RTN910AF(RTN02).**** Install new HW MW Link 4314K-4379A, 18G_2+0_112MHZ_256QAM_EPLA. Later, decom existing HW MW Link 4314K-4374B. Site Impacted : 4314K. FE_4379A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02) under DU A01138. Insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Request new xD vlan dcn and vlan services. 5.Request new IBeam port at CP 4379A. 6.Migrate traffic 4314K via new port of IBeam CP 4379A. 7.Decom existing HW MW Link 4314K-4374B. | XMC_5D Pro | MDD | 18G | 18G_1.2M(MDD) x1 | 18G_1.2M(MDD) x1 | GTSB | SQ202512300376-GTSB | GTSB | SQ202512300360-GTSB // SQ202512300366-GTSB | 2026-01-28 | 2026-01-29 | Completed | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122947 |  | 2025-12-30 | 2025-12-30 | Completed | 2025-12-29 | 2025-12-30 | 2025-12-29 | 2025-12-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2026-01-09 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2026-01-09 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-01 | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2026-01-12 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | 2025-02-28: 2025-12-30; 2025-03-06: 2025-12-30; 2025-03-06: 2025-12-30; 2025-03-06: 2026-01-02 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512290820-GTSB
7438B_IPR | Mile 75 SBC | DU00006159839 | Sabah | Sabah | 5.648371 | 117.288623 | [7 empty] | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1343A_LOS | Assam Jawa | DU00006159840 | Central | Selangor | 3.055611 | 101.497715 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW New Link / Reroute | MW NEW LINK/REROUTE 1343A-2041A WITH HUAWEI_18G_1+0_0.6M/0.6M_MDD_112MHZ_1024QAM_954MBPS_XMC5D_SUB_A_1.19KM IMPACTED: 1343A DISMANTLE EXISTING LINK 1343A-1073A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18GG 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK 1343A-1073A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18GG 1+0 112MHZ 1024QAM 5. PATCH IDU TO XC B00165 OB FIBER 6. DISMANTLE EXISTING LINK 1343A-1073A | XMC5D | MDD | 18G | 0.6 | 0.6 | GCI | SQ202512120099-GCI | GCI | SQ202512240253-GCI // SQ202512240258-GCI | 2025-12-19 | 2025-12-19 | Completed | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121307 |  | 2026-01-14 | 2025-12-16 | Completed | 2025-12-13 | 2026-01-14 | 2025-12-13 | 2025-12-16 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-17 | 2025-12-20 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-18 | 2025-12-25 | 2025-12-17 | 2025-12-20 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-19 | 2025-12-18 | 2025-12-25 | 2025-12-17 | 2025-12-24 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-12-18 | 2025-12-25 | 2025-12-17 | 2025-12-19 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510100626-GCI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
7575A_IPR | Berkat Setia | DU00006159841 | Sabah | Sabah | 5.716650 | 117.619160 | [7 empty] | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7324A_IPR | Mile 8 Kg Taviu | DU00006159842 | Sabah | Sabah | 5.649308 | 117.075379 | [7 empty] | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7498A_IPR | Kg Tanjong Aru | DU00006159843 | Sabah | Sabah | 5.346206 | 115.239492 | [7 empty] | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7110A_IPR | Kg Melewar | DU00006159844 | Sabah | Sabah | 5.254450 | 118.050045 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 4x1G SFP Optical 1KM 4x Patch Cord(Pair) | IPRAN Port Upgrade | 7110A 2x 1G PORT 7110A/7110A-LL-7570A INSTALL 2x 1G SFP OPTICAL AT CTS LL PORT 4 PORT ODU : E2K C,1 C,2 (1ST GE) C,3 C.4 (2ND GE) 7648 - SHELF0 (SUBRACK) - 1 -K1EX10-P:6 (1ST GE) 7648 - SHELF0 (SUBRACK) - 1 -K1EX10-P:8 (2ND GE) 7648-D_MELEWAR / M_PARS_1800 II PRO INSTALL 2x 1G SFP OPTICAL AT HW 7110A RTN03 17-EG6-5(PORT-5) & 17-EG6-5(PORT-5) PATCHING OPTICAL PATCH CORD LL PORT ETH to HW 7110A RTN03 17-EG6-5(PORT-5) & 17-EG6-5(PORT-5) RECONFIGURE TRAFFIC FOR ALL SITES: 7110A, 7107K, 7010P, 7807E | 7110A 2x 1G PORT 7110A/7110A-LL-7570A INSTALL 2x 1G SFP OPTICAL AT CTS LL PORT 4 PORT ODU : E2K C,1 C,2 (1ST GE) C,3 C.4 (2ND GE) 7648 - SHELF0 (SUBRACK) - 1 -K1EX10-P:6 (1ST GE) 7648 - SHELF0 (SUBRACK) - 1 -K1EX10-P:8 (2ND GE) 7648-D_MELEWAR / M_PARS_1800 II PRO INSTALL 2x 1G SFP OPTICAL AT HW 7110A RTN03 17-EG6-5(PORT-5) & 17-EG6-5(PORT-5) PATCHING OPTICAL PATCH CORD LL PORT ETH to HW 7110A RTN03 17-EG6-5(PORT-5) & 17-EG6-5(PORT-5) RECONFIGURE TRAFFIC FOR ALL SITES: 7110A, 7107K, 7010P, 7807E | [6 empty] | GCI | SQ202605050389-GCI | GCI | SQ202604150160-GCI // SQ202604200228-GCI |  |  | Ongoing | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26040312 |  | 2026-04-04 | 2026-04-09 | Completed | 2026-04-03 | 2026-04-04 | 2026-04-03 | 2026-04-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-05 | 2026-04-30 | 2026-04-05 | 2026-04-09 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-04-05 | 2026-04-30 | 2026-04-05 | 2026-04-21 | RAI//JORDAN RICHARD RIBU/7018000190 | GCI TI | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-05 | 2026-04-30 | 2026-04-05 | 2026-04-21 | RAI//JORDAN RICHARD RIBU/7018000190 | 2025-02-28: 2026-04-05; 2025-03-06: 2026-04-30; 2025-03-06: 2026-04-05; 2025-03-06: 2026-04-09 | [7 empty] | GCI | SQ202603270343-GCI | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | EZRIN TASNIM BIN ABDUL GANI6798000128
7476A_IPR | Kg Padiwan 2 | DU00006159845 | Sabah | Sabah | 4.998166 | 116.466720 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IPRAN port upgrade to 10G at 7476A. NE_7476A New SFP Module 10G with 10Km 1310nm or suitable SFP Module x2(For HW RTN910AF and CTS). New Optical Patch Cord cable with suitable type and length. | IPRAN Port Upgrade | ****IMPORTANT NOTE: 1.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILD SITES. 2.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** IPRAN Port Upgrade from existing Optical 1G to 10G port at 7476A. Site Impacted : 2788B18, 7339C, 7443A, 7476A, 7461A, 7063C & 7198R. NE_7476A 1.Enable port 8-EM6-3 of existing RTN910AF(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910AF(RTN01) to CTS(Request from ZTE IPRAN team). 4.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffics 2788B18, 7339C, 7443A, 7476A, 7461A, 7063C & 7198R into new 10G port at 8-EM6-3 of existing RTN910AF(RTN01). | ****IMPORTANT NOTE: 1.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILD SITES. 2.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** IPRAN Port Upgrade from existing Optical 1G to 10G port at 7476A. Site Impacted : 2788B18, 7339C, 7443A, 7476A, 7461A, 7063C & 7198R. NE_7476A 1.Enable port 8-EM6-3 of existing RTN910AF(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910AF(RTN01) to CTS(Request from ZTE IPRAN team). 4.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffics 2788B18, 7339C, 7443A, 7476A, 7461A, 7063C & 7198R into new 10G port at 8-EM6-3 of existing RTN910AF(RTN01). | [6 empty] | NR services | SQ202602250627-NR Services | NR services | SQ202602130278-NR Services |  |  | Ongoing | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-17 | 2026-03-24 | 2026-03-17 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26020506 |  | 2026-02-06 | 2026-02-14 | Completed | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-14 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-15 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-16 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-03-05 | RALPH O'BRYAN HILARY7167000030 | 2025-02-28: 2026-02-09; 2025-03-06: 2026-03-09; 2025-03-06: 2026-02-09; 2025-03-06: 2026-02-13 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511280936-GTSB
7538A_IPR | Kg Kiansom | DU00006159846 | Sabah | Sabah | 5.258414 | 115.166228 | [7 empty] | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
B00027_HU | TMN_BKT_SUBANG 2 | DU00005521273 | Central | Selangor | 3.168800 | 101.517611 | [7 empty] | 00. Site Out/Drop | 20/5: Completed under TX Mini B00027-B01841 | TSS |  | 23G_1+0_112MHz_512QAM_0.6M/0.6M_SUB B_889MBPS | MW Swap | FOR TSS ONLY MW SWAP LINK W00027-B01841 WITH HUAWEI_23G_1+0_112MHz_512QAM_0.6M/0.6M_SUB B EPLA WITH EXISTING LINK NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. TRANSFER ODU FROM EXISTING LINK TO NEW LINK 6. DISMANTLE ANTENNA AND IDU FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. IDU PATCHING TO 1365B 6. TRANSFER ODU FROM EXISTING LINK TO NEW LINK 7. DISMANTLE EXISTING ANTENNA AND IDU | [7 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505190510-GCI | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
4412D_HU | Bandar Baru Setia Awan | DU00005525677 | Northern | Perak | 4.220030 | 100.777400 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_110M_EPLA NE_4412D New 18G_1.2M(MDD) x1. New RTN910A(RTN01) x1. New XMC_5D, Sub B_Lo x1. New Optical SFP Module 1Km, 1310nm x2.(1x BBU & 1x new RTN910A) New Fiber Patch Cord Cables with suitable quantity, type and length. FE_4457C New 18G_1.2M(MDD) x1. New RTN910A(RTN01) x1. New XMC_5D, Sub B_Hi x1. New CAT6 Cable with suitable length x1. New Optical SFP Module 1Km, 1310nm x2.(1x existing RTN910A & 1x new RTN910A) New Fiber Patch Cord Cables with suitable quantity, type and length. | MW Swap | Existing SM MW Link 15G_4+0_28M_1024QAM_880M. Swap existing SM MW Link with new HW MW Link 18G_2+0_112M_512QAM_EPLA. **10G will be use at BBU, new RTN910A(4412D) and existing and new RTN910A(4457C).** Later, decom existing SM MW Link 15G_4+0_28M_1024QAM_880M. Site Impacted : 4412D. NE_4412D 1.Install New 18G_1.2M(MDD) x1. 2.Install New RTN910A(RTN01) x1. 3.Install new XMC_3, Sub B_Lo x1. Configure it. 4.Configure DCN Inband. 5.Re-use existing vlan services. 6.Enable port 8-EM6-3 of new RTN910A(RTN01) and insert Optical SFP Module 10G 1Km 1310nm. 7.Insert Optical SFP Module 10G 1Km 1310nm into BBU 4412D. 8.Patching port 8-EM6-3 of new RTN910A(RTN01) to 10G port of BBU 4412D. 9.Migrate traffic to new link new HW MW Link 18G_2+0_112M_512QAM_EPLA. Configure it. 10.Later, decom existing SM MW Link 15G_4+0_28M_1024QAM_880M. FE_4457C 1.Install New 18G_1.2M(MDD) x1. 2.Install New RTN910A(RTN02) x1. 3.Install new XMC_5D, Sub B_Hi x1. Configure it. 4.Configure DCN Inband. 5.Re-use existing vlan services and existing IBeam port at CP 4939C. 6.Enable port 8-EM6-3 of new RTN910A(RTN02) and insert Optical SFP Module 10G 1Km 1310nm. 7.Enable port 8-EM6-3 of existing RTN910A(RTN01) and insert Optical SFP Module 10G 1Km 1310nm. 8.Disable port 8-EM6-2 of existing RTN910A(RTN01). 9.Remove cascade at port 8-EM6-2 of existing RTN910A(RTN01) in which IDU of existing SM MW Link 15G_4+0_28M_1024QAM_880M currently connected to it. 10.Perform new cascading port 8-EM6-3 of new RTN910A(RTN02) to port 8-EM6-3 of existing RTN910A(RTN01). 11.Migrate traffic to new link new HW MW Link 18G_2+0_112M_512QAM_EPLA. Configure it. 12.Later, decom existing SM MW Link 15G_4+0_28M_1024QAM_880M. | Existing SM MW Link 15G_4+0_28M_1024QAM_880M. Swap existing SM MW Link with new HW MW Link 18G_2+0_112M_512QAM_EPLA. **10G will be use at BBU, new RTN910A(4412D) and existing and new RTN910A(4457C).** Later, decom existing SM MW Link 15G_4+0_28M_1024QAM_880M. Site Impacted : 4412D. NE_4412D 1.Install New 18G_1.2M(MDD) x1. 2.Install New RTN910A(RTN01) x1. 3.Install new XMC_3, Sub B_Lo x1. Configure it. 4.Configure DCN Inband. 5.Re-use existing vlan services. 6.Enable port 8-EM6-3 of new RTN910A(RTN01) and insert Optical SFP Module 10G 1Km 1310nm. 7.Insert Optical SFP Module 10G 1Km 1310nm into BBU 4412D. 8.Patching port 8-EM6-3 of new RTN910A(RTN01) to 10G port of BBU 4412D. 9.Migrate traffic to new link new HW MW Link 18G_2+0_112M_512QAM_EPLA. Configure it. 10.Later, decom existing SM MW Link 15G_4+0_28M_1024QAM_880M. | Existing SM MW Link 15G_4+0_28M_1024QAM_880M. Swap existing SM MW Link with new HW MW Link 18G_2+0_112M_512QAM_EPLA. **10G will be use at BBU, new RTN910A(4412D) and existing and new RTN910A(4457C).** Later, decom existing SM MW Link 15G_4+0_28M_1024QAM_880M. Site Impacted : 4412D. FE_4457C 1.Install New 18G_1.2M(MDD) x1. 2.Install New RTN910A(RTN02) x1. 3.Install new XMC_5D, Sub B_Hi x1. Configure it. 4.Configure DCN Inband. 5.Re-use existing vlan services and existing IBeam port at CP 4939C. 6.Enable port 8-EM6-3 of new RTN910A(RTN02) and insert Optical SFP Module 10G 1Km 1310nm. 7.Enable port 8-EM6-3 of existing RTN910A(RTN01) and insert Optical SFP Module 10G 1Km 1310nm. 8.Disable port 8-EM6-2 of existing RTN910A(RTN01). 9.Remove cascade at port 8-EM6-2 of existing RTN910A(RTN01) in which IDU of existing SM MW Link 15G_4+0_28M_1024QAM_880M currently connected to it. 10.Perform new cascading port 8-EM6-3 of new RTN910A(RTN02) to port 8-EM6-3 of existing RTN910A(RTN01). 11.Migrate traffic to new link new HW MW Link 18G_2+0_112M_512QAM_EPLA. Configure it. 12.Later, decom existing SM MW Link 15G_4+0_28M_1024QAM_880M. | XMC-5D | MDD | 18G | New 18G_0.6M(MDD) | New 18G_1.2M(MDD) | Magicell | SQ202508200574-Magicell | Magicell | SQ202510010665-Magicell // SQ202510010666-Magicell // SQ202511260115-Magicell // SQ202512190079-Magicell | 2025-12-02 | 2025-11-26 | Completed | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092722 |  | 2025-09-30 | 2025-10-18 | Completed | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-18 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-18 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-18 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-08 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-18 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-06 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | NG HONG JIE7018000036 | Logistic Team | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB
4576A_LOS | Bukit Pagar Tapah | DU00004569481 | Northern | Perak | 4.186050 | 101.254110 |  |  | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_4576A 18G_0.6m(MDD) x1. RTN910A,7_ISM8-2+0 x1. XMC_5D-2+0 , Sub_B_H x1i. FE_A00076 18G_0.6m(MDD) x1. RTN910A,7_ISM8-2+0 x1 XMC_5D-2+0 , Sub_B_Lo x1. | MW New Link / Reroute | 1.Solution : Raise up / Relocate ant height at 4576A in order to obtained clear LOS block towards existing FE sites. 2. Solution : Link Reroute to new FE A00076 due to LOS block. Site Impacted: 4576A. NE_4576A 1.Install new 18G_0.6m(MDD). 2.Install new RTN910A,7_ISM8-2+0(RTN no provide by MSP). 3.Install new XMC_5D-2+0 , Sub_B_Hi. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new FE route with new MW link. 6.Decom existing MW link (4576A-4442A) FE_A00076 1.Install new 18G_0.6m(MDD). 2.Install new RTN910A,7_ISM8-2+0(RTN no provide by MSP team). 3.Install new XMC_5D-2+0 , Sub_B_Lo. 4.Enable EPLA and service cross connect. 5.Migrate tarffic to new FE route with new MW link. 6.Create New In Band DCN. 7.Decom existing MW link (4442A-4576A). | [7 empty] | GCI | SQ202412120234-GCI | GCI | SQ202412120232-GCI // SQ202504150095-GCI // SQ202511060446-GCI | 2025-08-21 | 2025-08-20 | Completed | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-17 | 2025-01-17 | 2025-01-17 | 2025-01-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-07 | 2025-08-08 | 2025-08-07 | 2025-08-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24121211 |  | 2024-12-13 | 2025-01-13 | Completed | 2024-12-12 | 2024-12-13 | 2024-12-12 | 2025-01-13 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-27 | 2025-01-10 | 2024-12-27 | 2025-01-13 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-12-27 | 2025-01-10 | 2024-12-27 | 2025-01-13 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2024-12-31 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-12-27 | 2025-01-10 | 2024-12-27 | 2025-01-08 | team21gcitechnicalteam21gcitechnical | 2025-09-30: 2024-12-27; 2025-09-30: 2025-01-10; 2025-09-30: 2024-12-27; 2025-10-06: 2024-12-27 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358 |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01928-Q00658 | Q118B_Q01928OD_SOPSEBAUH | DU00004621587 | Sarawak | Sarawak | 3.044208 | 113.206907 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G 2+0 1.2m/1.2 MDD NE: 1) 1xRTN910A 2) 1x13GHz XMC5D Sub B Hi 3) 1x13GHz 1.2m MDD FE: 1) 1xRTN910A 2) 1x13GHz XMC5D Sub B Lo 3) 1x13GHz 1.2m MDD | MW Swap | Existing link Huawei SW03111 (Q01928-Q00658) To swap Existing link Huawei 13GHz 1+0 with new Huawei link 13GHz 2+0 To use XMC5D for easy upgrade in future. Impacted sites: Q01928 Current Tx route: Q01928-Q00658 New Tx route: Q01928-Q00658 NE (Q01928): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8 3) Migrate traffic to new link 4) Decom existing link FE (Q00658): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8 3) Migrate traffic to new link 4) Decom existing link | [7 empty] | Trintel | SQ202502260453-Trintel | Allstar | SQ202504240798A-Allstar // SQ202504240801-Allstar // SQ202504260202-Allstar | 2025-02-28 | 2025-02-26 | Completed | 2025-02-20 | 2025-02-24 | 2025-02-20 | 2025-02-24 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-02-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-02-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250408A4 |  | 2025-04-09 | 2025-04-10 | Completed | 2025-04-08 | 2025-04-09 | 2025-04-08 | 2025-04-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-15 | 2025-04-21 | 2025-04-21 | 2025-04-25 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-04-15 | 2025-04-21 | 2025-04-21 | 2025-04-30 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | Allstar TI | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-24 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-04-15 | 2025-04-21 | 2025-05-13 | 2025-05-13 | SYLVESTER//SANGIN ANAK LAMADA/6798000162 | 2025-04-15 | 2025-04-21 | 2025-04-17 | 2025-04-17 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-11 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
S01343-S00174 | S112A_S01343OD_KGGAMBARONWEST | DU00004654565 | Sabah | Sabah | 5.639120 | 117.176110 |  |  |  |  | RFS | Plan RFS | ZTE | 00. Integrated/RFS Done |  | AA | PAC | NA | MW Remote Upgrade | Existing Link 18G_1+0_56M , Remote software upgrade to 18G_1+0_112M. | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016 | GCI_AA | SQ202510300170-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | CHEONG/SENG/WAH/7018000306
7547B-7261A | KKIP Barat | DU00004654566 | Sabah | Sabah | 6.092959 | 116.154550 |  |  |  |  | RFS | Pending RFS declare | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_7547B 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. FE_7261A/S00034. 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E,Sub A & B_Lo x2.. | MW Swap | Existing link Loss Comm. Swap existing to 23G_2+0_112M. Site Impacted : 7547B NE_7547B 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install XMC_3E , Sub A & B_Hi. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new link. 6.Decom existing MW link. FE_7261A/S00034. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install XMC_3E,Sub A & B_Lo. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new link. 6.Create new In band DCN. 7.Decom existing MW link. | [7 empty] | NR services | SQ202502060432-NR Services | NR services | SQ202504260112-NR Services // SQ202504260119-NR Services // SQ202504260199-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-28 | 2025-01-31 | 2025-01-28 | 2025-01-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-28 | 2025-01-31 | 2025-01-28 | 2025-01-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031921 |  | 2025-03-21 | 2025-03-24 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-24 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-27 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-29 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-04-09 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GCI_AA | SQ202510300170-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | CHEONG/SENG/WAH/7018000306
S00909-S00488 | S105B_S00909OD_RANCANGANPADAS | DU00004654567 | Sabah | Sabah | 5.984730 | 118.018770 |  |  |  | JUN 25 | Plan TI | TI DONE | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_7120K 18G_DP_0.6m(MAC) x1. XMC_3E-2+0 , Sub A & B_Lo x1. ISM8 x1. FE_S00488. 18G_DP_0.6m(MAC) x1. XMC_3E-2+0 , Sub A & B_Hi x1. ISM8 x1. | MW Swap | Existing link 15G_2+0_28M. Swap existing link to 18G_2+0_112M Site Impacted: 7120K NE_7120K 1.Install a new 18G_DP_0.6m(MAC). 2.Install XMC_3E-2+0 , Sub A & B_Lo. 3.Reuse existing 7120K_RTN01. 4.Install a new 3_ISM8-2+0. 5.Enable EPLA and service cross connect. 6.Traffic migrate to new link. 7.Decom existing Ant and ODU. FE_S00488. 1.Install a new 18G_DP_0.6m(MAC). 2.Install XMC_3E-2+0 , Sub A_& BHi. 3.Reuse existing S00488_RTN01. 4.Install a new 3_ISM8-2+0. 5.Enable EPLA and service cross connect. 6.Traffic migrate to new link. 7.Decom existing Ant and ODU. | [7 empty] | NR services | SQ202502060432-NR Services | NR services | SQ202506230491-NR Services // SQ202506230499-NR Services | 2025-02-21 | 2025-02-17 | Completed | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-04 | 2025-02-07 | 2025-02-04 | 2025-02-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-04 | 2025-02-04 | 2025-02-04 | 2025-02-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250611BL |  | 2025-06-12 | 2025-06-12 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-12 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-21 | 2025-07-21 | 2025-06-21 | 2025-06-24 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-06-21 | 2025-07-21 | 2025-06-21 | 2025-06-24 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2025-06-21 | 2025-07-21 | 2025-06-21 | 2025-07-03 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-06-21 | 2025-07-21 | 2025-06-21 | 2025-06-21 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2025-07-24 | 2025-08-24 | 2025-07-24 | 2025-07-24 | MASDIANA//BINTI BEDIN/6801000016 | GCI_AA | SQ202510300170-GCI | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | CHEONG/SENG/WAH/7018000306
S00663-S00656 | S00663_SLDB PLANTATION | DU00004654568 | Sabah | Sabah | 5.040972 | 116.094500 |  |  |  |  | Pending BOM | Pending site BOM | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M_CA. Site Impacted : S00663. 13G_DP_1.2m(MDD) x1. XMC_5D x1. RTN910A x1 ISM8 x2. FE_S00656. 13G_DP_1.2m(MDD) x1. XMC_5D x1. ISM8 x2. | MW Swap | Existing link 13G_2+0_28M Swap existing link to 13G_4+0_28M_CA. Site Impacted : S00663. 1.Install a new 13G_DP_1.2m(MDD). 2.Install new XMC_5D-4+0_CA. 3.Install new RTN910A. (RTN no provide by MSP). version limit. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing S00663_RTN01. 5.Create EPLA , service cross connect and CA. 6.Traffic migrate to new link. 7.Decom existing IDU , ODU and Ant. FE_S00656. 1.Install a new 13G_DP_1.2m(MDD). 2.Install new XMC_5D-4+0_CA. 3.Reuse existing S00656_RTN01. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing S00656_RTN01. 5.Create EPLA , service cross connect and CA. 6.Traffic migrate to new link. 7. Decom existing ODU and Ant. | [7 empty] | MTK | SQ202502260428-MTK | NR services | SQ202507290140-NR Services // SQ202507290144-NR Services | 2025-05-23 | 2025-05-21 | Completed | 2025-02-19 | 2025-02-26 | 2025-02-19 | 2025-02-26 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-04 | 2025-03-07 | 2025-03-04 | 2025-03-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-04 | 2025-03-07 | 2025-03-04 | 2025-03-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-21 | 2025-05-23 | 2025-05-21 | 2025-05-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071526 |  | 2025-07-16 | 2025-07-28 | Completed | 2025-07-15 | 2025-07-16 | 2025-07-15 | 2025-07-28 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-28 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-28 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-07-27 | 2025-07-27 | 2025-07-27 | 2025-07-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-27 | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-08-16 | RALPH O'BRYAN HILARY7167000030 | 2025-07-26 | 2025-08-26 | 2025-07-26 | 2025-07-26 | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | tseping//wang/6819000006 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI_AA | SQ202510300170-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | CHEONG/SENG/WAH/7018000306
4016E_AD | Royale ChulanPenang | DU00006762391 | Northern | Penang | 5.417203 | 100.343600 | [21 empty] | GCI | SQ202604220819-GCI | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604280413-GCI
7554B_HU_1 | Batu 86Sandakan (REL) | DU00006762392 | Sabah | Sabah | 5.640763 | 117.195204 | [7 empty] | 05. TI WIP |  | TSS+TI |  | NE_7554B New ISM8 x2. New 13G, XMC_3, Sub B_Lo x1. FE_7438B New ISM8 x2. New 13G, XMC_3, Sub B_Hi x1. | MW Hardware Upgrade | ****IMPORTANT NOTE: PLEASE APPLY CRQ FOR ALL EB RELATED SITES AS MENTION AT IMPACTED SITE BELOW. DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET**** Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7554B, 7105Z, 7709E, 7635E, 7636E, 7647E, 7626E, 7627E, 7726E, 7653E, 7643E, 7711E & 7637E. NE_7554B 1.Change existing x2 ISV3 to x2 ISM8 at Slot 01 & 03 and terminate existing IF cables at Port 1 for Slot 01 & 03. 2.Change existing XMC-2(ODU 21) to new XMC-3 and terminate existing IF cable. 3.Re-arrange slot vs modem as per below: - Slot 02(ISV3 - to 7105Z) shift to Slot 05(ISM8 - to 7438B) and vise versa. - Slot 04(ISM8 - to 7105Z) shift to Slot 06(ISM8 - to 7438B) and vise versa. 4.Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. FE_7438B 1.Change existing x2 ISV3 to x2 ISM8 at Slot 01 & 03 and terminate existing IF cables at Port 1 for Slot 01 & 03. 2.Change existing XMC-2(ODU 21) to new XMC-3 and terminate existing IF cable. 3.Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: PLEASE APPLY CRQ FOR ALL EB RELATED SITES AS MENTION AT IMPACTED SITE BELOW. DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET**** Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7554B, 7105Z, 7709E, 7635E, 7636E, 7647E, 7626E, 7627E, 7726E, 7653E, 7643E, 7711E & 7637E. NE_7554B 1.Change existing x2 ISV3 to x2 ISM8 at Slot 01 & 03 and terminate existing IF cables at Port 1 for Slot 01 & 03. 2.Change existing XMC-2(ODU 21) to new XMC-3 and terminate existing IF cable. 3.Re-arrange slot vs modem as per below: - Slot 02(ISV3 - to 7105Z) shift to Slot 05(ISM8 - to 7438B) and vise versa. - Slot 04(ISM8 - to 7105Z) shift to Slot 06(ISM8 - to 7438B) and vise versa. 4.Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: PLEASE APPLY CRQ FOR ALL EB RELATED SITES AS MENTION AT IMPACTED SITE BELOW. DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET**** Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : 7554B, 7105Z, 7709E, 7635E, 7636E, 7647E, 7626E, 7627E, 7726E, 7653E, 7643E, 7711E & 7637E. FE_7438B 1.Change existing x2 ISV3 to x2 ISM8 at Slot 01 & 03 and terminate existing IF cables at Port 1 for Slot 01 & 03. 2.Change existing XMC-2(ODU 21) to new XMC-3 and terminate existing IF cable. 3.Later, combine existing HW MW Link 7554B-7438B, 13G_4+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 7554B-7438B, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_512QAM_EPLA. | [5 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042990 |  | 2026-04-30 |  | Ongoing | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-23 | 2026-05-23 | 2026-04-23 |  | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-04-23 | 2026-05-23 | 2026-04-23 |  | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | [7 empty] | 2026-04-23 | 2026-05-23 | 2026-04-23 |  | IBRAHIM//BIN SAHABU/7167000007 | 2025-03-24: 2026-04-23; 2025-03-24: 2026-05-23; 2025-03-24: 2026-04-23 | [7 empty] | GTSB | SQ202604280434-GTSB
4154B_AD | PintalTali St | DU00006762393 | Northern | Penang | 5.416051 | 100.335038 | [9 empty] | TSS+AA+TI+Dismantle |  | 2X RTN910A 2X 23G 0.3M DP ANTENNA 2x ODU 23G XMC3 SUB A HI 2x ODU 23G XMC3 SUB A LO | MW New Link / Reroute | MW NEW LINK/REROUTE 4154B-4123K WITH HUAWEI_23G_1+0_0.3M/0.3M_DP_112MHZ_256QAM_778MBPS_XMC3E_SUB_A_LINK_0.63KM DISMANTLE EXISTING LINK 4154B-4012A IMPACTED: 4154B | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK 4154B-4012A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 256QAM 5. PATCH TO LL PORT 6. DISMANTLE EXISTING LINK 4154B-4012A | XMC3 | MAC | 23G | 0.3 | 0.3 | GCI | SQ202604220819-GCI | GCI | SQ202605070533-GCI // SQ202605070538-GCI |  |  | Ongoing | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050112 |  | 2026-05-04 | 2026-05-05 | Completed | 2026-05-01 | 2026-05-04 | 2026-05-01 | 2026-05-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-05 | 2026-05-31 | 2026-05-05 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-05-05 | 2026-05-31 | 2026-05-05 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | [7 empty] | 2026-05-05 | 2026-05-31 | 2026-05-05 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2025-03-24: 2026-05-05; 2025-03-24: 2026-05-31; 2025-03-24: 2026-05-05; 2025-03-24: 2026-05-07 | [7 empty] | GCI | SQ202604280413-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
1836A_AD | Sunway Micro 1 | DU00006762394 | Central | Selangor | 3.072837 | 101.608020 | [8 empty] | 29/4: No MRCF due to relocate antenna only | TSS+AA+TI+Dismantle | L1+ATP+PAC | New IF cables 2x RUN | MW New Link / Reroute | Relocation 1st antenna 23G_0.6m at 1836A. | Relocation 1st antenna 23G_0.6m at 1836A. |  | XMC-3 | HAC | 23G | 0.6M | 0.6M | GTSB | SQ202604290755-GTSB | GTSB | SQ202604290740-GTSB // SQ202604290749-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042811 |  | 2026-04-29 |  | Ongoing | 2026-04-28 | 2026-04-29 | 2026-04-28 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-27 | 2026-04-30 | 2026-04-26 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-04-27 | 2026-04-30 | 2026-04-26 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | AZRUL FIKRAM BIN MOHD THANI6237000863 |  | 2026-04-28 | 2026-04-27 | 2026-04-30 | 2026-04-26 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-03-24: 2026-04-27; 2025-03-24: 2026-04-30; 2025-03-24: 2026-04-26; 2025-03-24: 2026-04-27 | [7 empty] | GTSB | SQ202604280393-GTSB
P00681_AD | P032A_P00681OD_KOMP_PENJARA_JAWI | DU00006762395 | Northern | Penang | 5.195922 | 100.531700 | [9 empty] | TSS+AA+TI+Dismantle |  | 2X RTN910A 1x ODU 23G XMC3 SUB B HI 1x ODU 23G XMC3 SUB B LO | MW New Link / Reroute | MW NEW LINK REROUTE P00681-4223A WITH HUAWEI_23G_1+0_1.2M/1.2M_DP_112MHZ_256QAM_778MBPS_XMC3_SUB_B_LINK_2.94KM PATCH TO XC P00019 TM LL DISMANTLE EXISTING LINK P00681-P00110 IMPACTED: P00681 | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 1.2M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK P00681-P00110 | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 1.2M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 256QAM 5. PATCH TO XC TM LL P00019 6. DISMANTLE EXISTING LINK P00681-P00110 | XMC3 | DP MS | 23G | 1.2 | 1.2 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050717 |  | 2026-05-08 |  | Ongoing | 2026-05-07 | 2026-05-08 | 2026-05-07 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280413-GCI | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
4068D_AD | KoperasiPolis Diraja Pinang | DU00006762396 | Northern | Penang | 5.411652 | 100.323585 | [9 empty] | TSS+AA+TI+Dismantle |  | 2X RTN910A 2X 23G 0.3M DP ANTENNA 1x ODU 23G XMC3E SUB B HI 1x ODU 23G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK REROUTE 4068D-P00044 WITH HUAWEI_23G_1+0_0.3M/0.3M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB_B_LINK_0.73KM PATCH TO XC P00044 TM LL DISMANTLE EXISTING LINK 4068D-4012A IMPACTED: 4068D | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 4068D-4012A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. PATCH TO TM LL P00044 6. DISMANTLE EXISTING LINK 4068D-4012A | XMC3E | DP | 23G | 0.3 | 0.3 | GCI | SQ202604220819-GCI | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050721 |  | 2026-05-08 |  | Ongoing | 2026-05-07 | 2026-05-08 | 2026-05-07 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280413-GCI | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
4675C_AD | JalanTransfer | DU00006762397 | Northern | Penang | 5.421584 | 100.331074 | [9 empty] | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | Existing link 23G_1+0_56M route to new FE 4145K due to dismantling of site 4102A. New MW link config 23G_1+0_112M. Site Impacted : 4675C. NE_4675C 1.Install new 23G_DP_0.3M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Traffic migrate to new link and New Fe routing. 6.decom existing MW link. FE_P00416. 1.Install new 23G_DP_0.3M(MAC). 2.Install new RTN910A , 7_ISM81+0. 3.Install new XMC_3E Sub A_Lo. 4.Create service cross connect and New Inband DCN. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. | Existing link 23G_1+0_56M route to new FE 4145K due to dismantling of site 4102A. New MW link config 23G_1+0_112M. Site Impacted : 4675C. NE_4675C 1.Install new 23G_DP_0.3M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Traffic migrate to new link and New Fe routing. 6.decom existing MW link. | Existing link 23G_1+0_56M route to new FE 4145K due to dismantling of site 4102A. New MW link config 23G_1+0_112M. Site Impacted : 4675C. FE_P00416. 1.Install new 23G_DP_0.3M(MAC). 2.Install new RTN910A , 7_ISM81+0. 3.Install new XMC_3E Sub A_Lo. 4.Create service cross connect and New Inband DCN. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. | XMC_3E | MAC | 23G | 0.3 | 0.3 | GCI | SQ202604220819-GCI | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050714 |  | 2026-05-08 |  | Ongoing | 2026-05-07 | 2026-05-08 | 2026-05-07 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-11 | 2026-05-31 | 2026-05-11 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-05-11 | 2026-05-31 | 2026-05-11 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | [7 empty] | 2026-05-11 | 2026-05-31 | 2026-05-11 |  | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-03-24: 2026-05-11; 2025-03-24: 2026-05-31; 2025-03-24: 2026-05-11 | [7 empty] | GCI | SQ202604280413-GCI | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | CHEONG/SENG/WAH/7018000306
4263D_AD | SingerJln Dato Keramat (REL) | DU00006762398 | Northern | Penang | 5.413161 | 100.319367 | [9 empty] | TSS+AA+TI+Dismantle |  | 23G_2+0_112M NE_4263D 23G_DP_0.3M(MAC) x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. FE_4143K/P00388. 23G_DP_0.3M(MAC) x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. | MW New Link / Reroute | Existing link reroute to new FE 4143K due to existing FE 4102A will be decom. New link config with 23G_2+0_112M Site Impacted : 4263D NE_4263D 1.Install new 23G_DP_0.3M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and New FE routing. 6.Decom existing MW link. FE_4143K/P00388. 1.Install new 23G_DP_0.3M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. | Existing link reroute to new FE 4143K due to existing FE 4102A will be decom. New link config with 23G_2+0_112M Site Impacted : 4263D NE_4263D 1.Install new 23G_DP_0.3M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and New FE routing. 6.Decom existing MW link. | Existing link reroute to new FE 4143K due to existing FE 4102A will be decom. New link config with 23G_2+0_112M Site Impacted : 4263D FE_4143K/P00388. 1.Install new 23G_DP_0.3M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE routing. 5.Create New Inband DCN. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | XMC_3E | MAC | 23G | 0.3 | 0.3 | GCI | SQ202604220819-GCI | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050510 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280413-GCI | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | CHEONG/SENG/WAH/7018000306
1836A_AD_1 | SunwayMicro 1 | DU00006762399 | Central | Selangor | 3.072837 | 101.608020 | [8 empty] | 29/4: No MRCF due to relocate antenna only | TSS+AA+TI+Dismantle | L1+ATP+PAC | New IF cables 2x RUN | MW New Link / Reroute | Relocation 2nd antenna 23G_0.6m at 1836A. | Relocation 2nd antenna 23G_0.6m at 1836A. |  | XMC-3 | HAC | 23G | 0.6M | 0.6M | GTSB | SQ202604290755-GTSB | GTSB | SQ202605050349-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2026-04-27 | 2026-04-30 | 2026-04-26 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-04-27 | 2026-04-30 | 2026-04-26 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | AZRUL FIKRAM BIN MOHD THANI6237000863 |  | 2026-04-28 | 2026-04-27 | 2026-04-30 | 2026-04-26 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-03-24: 2026-04-27; 2025-03-24: 2026-04-30; 2025-03-24: 2026-04-26; 2025-03-24: 2026-04-27 | [7 empty] | GTSB | SQ202604280393-GTSB
S00992-S00596 | KAMPUNG MOSOPOH | DU00003508812 | Sabah | Sabah | 5.124854 | 116.388300 |  |  | WK20 | MAY 24 | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | 17/5: D2: Cutover done. Pending NMS to xD 15/5: MOS & TI WIP | TSS+AA+TI | L1+ATP+PAC | 4x ISM8 Card | MW Hardware Upgrade | NE: 1. Reuse existing IDU 910A. Install 2x ISM8 Card at Slot 3 & Slot 4. 2. Reuse existing 1.8m MDD Antenna. 3. Reuse existing XMC5D ODU. Adding another 2+0 config. 4. Configure link 13G 4+0 CA. FE: NE: 1. Reuse existing IDU 910A. Install 2x ISM8 Card at Slot 3 & Slot 4. 2. Reuse existing 1.8m MDD Antenna. 3. Reuse existing XMC5D ODU. Adding another 2+0 config. 4. Configure link 13G 4+0 CA. | [7 empty] | Seri Pancar | SQ202409030650-Seri Pancar // SQ202409120134-Seri Pancar | Magicell | SQ202409120165-Magicell | 2024-05-10 | 2024-05-06 | Completed | 2024-04-22 | 2024-04-26 | 2024-04-25 | 2024-04-25 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-02 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-02 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-05-06 | 2024-05-10 | 2024-05-06 | 2024-05-06 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24051335 |  | 2024-05-14 | 2024-05-14 | Completed | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-15 | 2024-05-31 | 2024-05-14 | 2024-05-18 | SONLEE//BERNABAS/7018000158 | Magicell TI | 2024-05-15 | 2024-05-31 | 2024-05-14 | 2024-05-18 | SONLEE//BERNABAS/7018000158 | Magicell TI | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2024-09-04 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-05-15 | 2024-05-31 | 2024-05-14 | 2024-06-19 | SONLEE//BERNABAS/7018000158 | 2025-03-24: 2024-05-15; 2025-03-24: 2024-05-31; 2025-03-24: 2024-05-14; 2025-03-24: 2024-05-16 |  |  | 2024-11-30 | 2024-12-30 | 2024-11-30 | 2024-11-30 | ASTI//GANIS PUTRIANI/6237001358
7324A | Mile 8 Kg Taviu | DU00004234266 | Sabah | Sabah | 5.649308 | 117.075379 |  |  |  |  | Drop/Cancel | Solution Issue | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | 7324A is LL site. Currently no port congestion. 7324A also not associated with any MW links in latest GOP high utilization list | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1802A-1251A | Sungai Wang | DU00004234267 | Central | Kuala Lumpur | 3.144744 | 101.711065 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 29/10: D3: Cutover done 24/10: TI FE done, Pending acces approval BM NE 22/10: EB CRQ approved. MOS & TI Plan 24/10 after 3770B | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 1+0 0.6m/0.6m XMC3 NE: 1) 1xRTN910A 2) 1x23GHz XMC3E Sub B Lo 3) 1x23GHz 0.6m SP FE: 1) 1xRTN910A 2) 1x23GHz XMC3E Sub B Hi 3) 1x23GHz 0.6m SP | MW Swap | Existing link Huawei 1802A-1251A To swap Existing EOS link 23GHz 1+0 with new 23GHz 1+0 112MHz Impacted sites: 1802A Current Tx route: 1802A-1251A New Tx route: 1802A-1251A NE (1802A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link FE (1251A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Patch new RTN GE1 to new CP port 4) Migrate 1802A traffic to new link. Create DCN 5) Decom existing link | [7 empty] | YPTT | SQ202411140256-YPTT | YPTT | SQ202411120060-YPTT |  |  | Ongoing | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24100866 |  | 2024-10-09 | 2024-10-11 | Completed | 2024-10-08 | 2024-10-09 | 2024-10-08 | 2024-10-11 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-23 | 2024-11-22 | 2024-10-23 | 2024-12-30 | NORDIN/BIN/MAT REJAB/6794000106 | YPTT TI | 2024-10-23 | 2024-11-22 | 2024-10-23 |  | NORDIN/BIN/MAT REJAB/6794000106 | YPTT TI | 2024-10-29 | 2024-10-29 | 2024-10-29 | 2024-10-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-10-23 | 2024-11-22 | 2024-10-23 | 2024-11-02 | NORDIN/BIN/MAT REJAB/6794000106 | 2024-10-23 | 2024-11-22 | 2024-10-23 | 2024-10-29 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-12 | NG HONG JIE7018000036 | Logistic Team | 2024-11-11 | 2024-12-11 | 2024-11-11 | 2024-11-11 | ASTI//GANIS PUTRIANI/6237001358
S00348-7053C | S098C_S00348OD_TENGAHNIPAH | DU00004234268 | Sabah | Sabah | 5.039789 | 118.381384 | [7 empty] | 00. Integrated/RFS Done | 5/11: Cutover done. Post-CO T/S ongoing 4/11: MOS & Pre-installation in progress | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 1+0 112MHz 0.6m/0.6m XMC3 NE: 1) 1xRTN910A 2) 1x23GHz XMC3 Sub A Lo 3) 1x23GHz 0.6m SP FE: 1) 1xISM8 card 2) 1x23GHz XMC3 Sub A Hi 3) 1x23GHz 0.6m SP | MW New Link / Reroute | Existing link SM MW SB03022 (S00348-S01608) To replace with new Huawei S00348-7053C 23GHz 1+0 112MHz Impacted sites: S00348 Current Tx route: S00348-S01608-S00845-S00339 New Tx route: S00348-7053C-LL-7100A NE (S00348): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link (SM SB03022) FE (7053C): 1) Install new ISM8 card at RTN02 slot 3 2) Install new link at RTN02 3-ISM8-1 3) Migrate traffic to new link 4) Decom existing link (SM SB03022) | [7 empty] | NR services | SQ202411120053-NR Services | NR services | SQ202411120063-NR Services // SQ202504260199-NR Services | 2024-11-30 | 2024-11-29 | Completed | 2024-11-04 | 2024-11-04 | 2024-11-04 | 2024-11-04 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-04 | 2024-11-08 | 2024-11-04 | 2024-11-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-04 | 2024-11-08 | 2024-11-04 | 2024-11-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-29 | 2024-11-30 | 2024-11-29 | 2024-11-29 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241024AK |  | 2024-10-25 | 2024-11-01 | Completed | 2024-10-24 | 2024-10-25 | 2024-10-24 | 2024-11-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-01 | 2024-11-30 | 2024-11-01 | 2024-11-04 | WILFRED BALANG7167000026 | NR Service TI | 2024-11-01 | 2024-11-30 | 2024-11-01 | 2024-11-04 | WILFRED BALANG7167000026 | NR Service TI | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-11-01 | 2024-11-30 | 2024-11-01 | 2024-11-05 | WILFRED BALANG7167000026 | 2024-11-01 | 2024-11-30 | 2024-11-01 | 2024-11-02 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-27 | tseping//wang/6819000006 | Logistic Team | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
2443A-1964B | Ijok (CELCOM) | DU00004234269 | Central | Selangor | 3.296836 | 101.447680 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 9/10: RSL rectifiction & patch list done. Under monitoring 1/10: Magicel to rectifiy link patch list 2443A_PostMOCN not done by NERA | TSS+AA+TI+Dismantle | L1+ATP+PAC | 15G 4+0 1.2m/1.2m MDD XMC5D sub A NE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 15G XMC5D sub A Hi 4) 1 x 15G 1.2m MDD FE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 15G XMC5D sub A Lo 4) 1 x 15G 1.2m MDD | MW Swap | To relocate antenna to new tower leg. To install new antenna, ODU and IF cable to minimize downtime To decom existing antenna + ODU Impact sites: 2443A, B01925 NE (2443A) - Install new antenna on new tower leg - Lay new IF cable - Migrate traffic to new link FE (1964B) - Install new antenna on new tower leg - Lay new IF cable - Migrate traffic to new link | [7 empty] | Magicell | SQ202411140233-Magicell | Magicell | SQ202410280579-Magicell // SQ202504260146-Magicell // SQ202504300095-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-12-12 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-04 | 2025-11-05 | 2025-11-04 | 2025-11-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24101612 |  | 2024-10-19 | 2024-10-24 | Completed | 2024-10-18 | 2024-10-19 | 2024-10-18 | 2024-10-24 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-09 | 2024-10-31 | 2024-10-09 | 2024-11-26 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2024-10-09 | 2024-10-31 | 2024-10-09 | 2024-11-26 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | Magicell TI | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-03 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-10-09 | 2024-10-31 | 2024-10-09 | 2024-11-21 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | 2025-03-24: 2024-10-09; 2025-03-24: 2024-10-31; 2025-03-24: 2024-10-09; 2025-03-24: 2024-10-09 |  |  | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
1704B-1362A | WPH RESOURCES MR | DU00004234270 | Central | Selangor | 3.104125 | 101.551211 |  |  | W49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 20/12: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE_1704B_RTN02. 1. Install new DP 0.6m antenna x1.(MDD) 2. Install XMC_5D , Sub_A_Lo x1. FE_1362A. 1.Install new DP 0.6m antenna x1.(MDD) 2.Install XMC_5D , Sub_A_Hi x1. | MW Swap | Existing link 18G_1+0_112Mhz Swap existing link from 18G_1+0_112Mhz SP to 18G_2+0_112Mhz with DP 0.6m. Site Impacted: 1704B,3621A,1314H. NE_1704B_RTN02. 1.Install new DP 0.6m antenna.(MDD) 2.Configure existing 7_ISM8_1+0 to 2+0 with EPLA. 3.Install XMC_5D. 4.Decom existing SP 0.6m and XMC_3 ODU. FE_1362A. 1.Install new DP 0.6m antenna.(MDD) 2.Configure existing 7_ISM8_1_0 to 2+0 with EPLA. 3.Install XMC_5D and config. 4.Decom existing SP 0.6m and XMC_3 ODU. | [7 empty] | Magicell | SQ202411140233-Magicell | Magicell | SQ202411150549-Magicell // SQ202504260146-Magicell | 2025-02-25 | 2025-02-24 | Completed | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-13 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-19 | 2024-12-19 | 2024-12-19 | 2024-12-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-14 | 2025-02-15 | 2025-02-14 | 2025-02-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-24 | 2025-02-25 | 2025-02-24 | 2025-02-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24110843 |  | 2024-11-09 | 2024-11-15 | Completed | 2024-11-08 | 2024-11-09 | 2024-11-08 | 2024-11-15 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-20 | 2024-12-31 | 2024-12-20 | 2025-01-06 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2024-12-20 | 2024-12-31 | 2024-12-20 | 2025-01-06 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-12-20 | 2024-12-31 | 2024-12-20 | 2024-12-28 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2024-12-20 | 2024-12-31 | 2024-12-20 | 2024-12-20 | 2025-01-10 | 2025-01-10 | 2025-01-10 | 2025-01-10 | NG HONG JIE7018000036 | Logistic Team | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
Q01414_SL | BAU-VQ_PATRICKLIBAU_E_Q01414 | DU00005399684 | Sarawak | Sarawak | 3.825556 | 113.789167 | [6 empty] | ZTE | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB
4381B_SL | Lumut Power Plant | DU00005399685 | Northern | Perak | 4.384103 | 100.588878 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [8 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250424BU |  | 2025-04-25 |  | Ongoing | 2025-04-24 | 2025-04-25 | 2025-04-24 |  | NAYOMI THAKSHILA6819000029 | Warehouse Team | MORRISON EXPRESS (MALAYSIA) SDN. BHD. |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202506050646-GTSB
4778C_AD | Taman Pengkalan Sentosa | DU00006418340 | Northern | Perak | 4.523700 | 101.058100 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_512Q_28Mhz_448Mbps NE: 1x 0.6m MAC 15G ant 1x ODU 15G_XMC-3 sb A and B FE: Re-use existing currently on air at site | MW Swap | Install new antenna at lower tier, decom existing antenna at Maxis tier. Swap only at NE by install new antenna and ODU IF onnect to ISM8 slot 7 port 1 and 2 FE will remain Alignment after swap anttena at NE Decom antenna and ODU at NE only. | Install new antenna at lower tier, decom existing antenna at Maxis tier. Install new OUD sb A and B Lo IF onnect to ISM8 slot 7 port 1 and 2 Configure 15G_2+0 _EPLA Decom existing antenna and ODU | No installation required, only re-alignment | XMC-3 | MAC | 15G | 0.6m | 1.2m | GTSB | SQ202512160971-GTSB | GTSB | SQ202512160957-GTSB // SQ202512160962-GTSB |  |  | Ongoing | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-30 | 2026-05-07 | 2026-04-30 | 2026-05-01 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121313 |  | 2026-01-14 | 2025-12-17 | Completed | 2025-12-13 | 2026-01-14 | 2025-12-13 | 2025-12-17 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2026-01-20 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2026-01-26 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-23 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2026-01-24 | HAMZAH BIN ABDUL MUTALIF6799000301 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2026-01-21 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | NG HONG JIE7018000036 | Logistic Team | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512180096-GTSB | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | AB.RAHMAN//BIN MAT NOOH/6237001519
4586A-4428B_1 | Tmn Berkat Taiping | DU00005114490 | Northern | Perak | 4.868210 | 100.687110 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Solution released under4586A-4428B_3 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505070167-GTSB
4332H_LOS | 99 Speedmart KH Tmn Angsana | DU00005114491 | Northern | Kedah | 5.624895 | 100.504890 | [7 empty] | 03. TSS Only |  | TSS |  | NLOS RTN510 NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Link reroute to new FE 4623A due to LOS Block existing FE site. NLOS RTN9510. NE_4332H Site Impacted : 4332H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio.(4332H - 4152D). FE_4623A 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.ETH cable direct patching to existing 4623A_RTN02_GE3 ( ID : 27942). 6.Traffic migrate to new route FE site. 7.Decom existing NLOS Radio, (4152D-4332H). | Link reroute to new FE 4623A due to LOS Block existing FE site. NLOS RTN9510. NE_4332H Site Impacted : 4332H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio.(4332H - 4152D). | Link reroute to new FE 4623A due to LOS Block existing FE site. NLOS RTN9510 Site Impacted : 4332H FE_4623A 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.ETH cable direct patching to existing 4623A_RTN02_GE3 ( ID : 27942). 6.Traffic migrate to new route FE site. 7.Decom existing NLOS Radio, (4152D-4332H). | [5 empty] | GCI | SQ202504240792-GCI | GCI |  | 2025-11-11 | 2025-11-10 | Completed | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-24 | 2025-07-23 | 2025-07-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505190519-GCI | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | CHEONG/SENG/WAH/7018000306
4755C-4034A | Setia Vista | DU00005114492 | Northern | Penang | 5.340809 | 100.268255 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M Site Impacted : 4755C. NE_4755C 23G_DP_0.6M(MAC)+OMT x1. XMC_3E , Sub A & B_Lo x2. ISM8 x1. FE_4034A 23G_DP_0.6M(MAC)+OMT x1. XMC_3E , Sub A & B_Hi x2. ISM8 x1. | MW Swap | Existing link 23G_1+0_112M. Swap existing to 23G_2+0_112M Site Impacted : 4755C. NE_4755C 1.Install 23G_DP_0.6M(MAC)+OMT. 2.Install new XMC_3E , Sub A & B_Lo. 3.Reuse existing 4755C_RTN01. 4.Install new 3_ISM8-2+0 into existing 4755C_RTN01. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 23G_2+0_112M. 7.Decom existing Ant and ODU. FE_4034A 1.Install 23G_DP_0.6M(MAC)+OMT. 2.Install new XMC_3E , Sub A & B_Hi. 3.Reuse existing 4034A_RTN04. 4.Install new 3_ISM8-2+0 into existing 4034A_RTN04. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 23G_2+0_112M. 7.Decom existing Ant & ODU. | Existing link 23G_1+0_112M. Swap existing to 23G_2+0_112M Site Impacted : 4755C. NE_4755C 1.Install 23G_DP_0.6M(MAC)+OMT. 2.Install new XMC_3E , Sub A & B_Lo. 3.Reuse existing 4755C_RTN01. 4.Install new 3_ISM8-2+0 into existing 4755C_RTN01. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 23G_2+0_112M. 7.Decom existing Ant and ODU. | Existing link 23G_1+0_112M. Swap existing to 23G_2+0_112M Site Impacted : 4755C. FE_4034A 1.Install 23G_DP_0.6M(MAC)+OMT. 2.Install new XMC_3E , Sub A & B_Hi. 3.Reuse existing 4034A_RTN04. 4.Install new 3_ISM8-2+0 into existing 4034A_RTN04. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link 23G_2+0_112M. 7.Decom existing Ant & ODU. | XMC_3E | MAC | 23G | 0.6 | 0.6 | CCSMY | SQ202504210258-CCS | CCSMY | SQ202505070581-CCS // SQ202505070632-CCS | 2025-10-25 | 2025-10-24 | Completed | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032001 |  | 2025-03-21 | 2025-04-12 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-04-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-06 | 2025-05-31 | 2025-05-06 | 2025-05-08 | HASHIM//BIN AHMAD ZAIDI/7021000032 | CCS TI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-06-04 | HASHIM//BIN AHMAD ZAIDI/7021000032 | CCS TI | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-05-06 | 2025-05-31 | 2025-05-06 | 2025-06-02 | HASHIM//BIN AHMAD ZAIDI/7021000032 | 2025-05-06 | 2025-05-31 | 2025-05-06 | 2025-05-10 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
1582B-1436B | pBTS Kaw Perindustrian TPG | DU00003290921 | Central | Selangor | 2.914092 | 101.465432 | WK05 | JAN 24 | WK09 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_0.6m/0.6m_SP_1+0_56MHz | MW Swap | NE: Install: 1. Antenna: Install new 18G 0.6m DP A18D06MDD-3NX x 1 2. ODU: Install XMC-5D Sub-band A x 2 3. IDU: Install new RTN910A x 1, named RTN01 4. IF card: New RTN910A Built-in Slot 7 5. IF cables: Connect IF cable x 1 from the new ODUs to Slot 7 6. Configure: Link 1582B RTN01->1436B RTN03 1+0 112MHz 7. Disconnect BBU 1582B and connect to new RTN01 GE1. Dismantle/ Remain: 1. Dismantle old NEC link (antenna, ODU, IDU, IF cables) FE: Install: 1. Antenna: Install new 18G 0.6m DP A18D06MDD-3NX x 1 2. ODU: Install XMC-5D Sub-band A x 2 3. IDU: Use existing RTN03 4. IF card: Install new ISM8 card at Slot 3 5. IF cables: Connect IF cable x 1 from the new ODUs to Slot 3 6. Configure: Link 1582B RTN01->1436B RTN03 1+0 112MHz 7. DCN IP and VLAN: Not required Dismantle/ Remain: 1. Dismantle old SIAE link (antenna, ODU, IDU, IF cables) | [7 empty] | MTK | SQ202402270782-MTK | MTK | SQ202402270725-MTK | 2024-09-20 | 2024-09-19 | Completed | 2024-01-29 | 2024-02-02 | 2024-01-31 | 2024-01-31 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-02-20 | 2024-02-21 | 2024-02-20 | 2024-02-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-09-04 | 2024-09-05 | 2024-09-04 | 2024-09-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24022216 |  | 2024-02-23 | 2024-02-26 | Completed | 2024-02-22 | 2024-02-23 | 2024-02-22 | 2024-02-26 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-27 | 2024-03-05 | 2024-02-26 | 2024-04-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2024-02-27 | 2024-03-05 | 2024-02-27 | 2024-02-29 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-02-27 | 2024-03-05 | 2024-02-29 | 2024-02-29 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI |  | 2024-02-27 | 2024-03-05 | 2024-02-26 | 2024-03-02 | RIDHUAN//BIN MANSOR/8225000011 | 2024-02-27 | 2024-03-05 | 2024-02-26 | 2024-02-27 | 2024-02-27 | 2024-03-31 | 2024-04-16 | 2024-04-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
1404C-1080A | Lebuh Damar Merah | DU00003290922 | Central | Selangor | 2.981947 | 101.425298 | WK06 | MAR 24 | WK09 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Huawei ODU 23G XMC-3 112MHz | MW Hardware Upgrade | Swap to 112MHz ODU, set BW to 112MHz | [7 empty] | GTSB | SQ202409100255-GTSB | GTSB | SQ202403040121-GTSB // SQ202409110350-GTSB | 2024-08-30 | 2024-08-29 | Completed | 2024-02-05 | 2024-02-05 | 2024-02-27 | 2024-02-27 | FAHRURRADZI HELMY BIN SUHAIZAD6799000123 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2024-03-06 | 2024-03-07 | 2024-03-06 | 2024-03-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-06 | 2024-03-07 | 2024-03-06 | 2024-03-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021901 |  | 2024-02-20 | 2024-02-28 | Completed | 2024-02-19 | 2024-02-20 | 2024-02-19 | 2024-02-28 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | angahmeal@gmail.comangahmeal@gmail.com | GTSB TI | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | angahmeal@gmail.comangahmeal@gmail.com | GTSB TI | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | C.PRATHABAN///6798000081 |  |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-03-03 | angahmeal@gmail.comangahmeal@gmail.com | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4527D-4820C | Klebang Ria 2 (REL) | DU00003290923 | Northern | Perak | 4.676564 | 101.115014 |  |  | WK04 | JAN 24 | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | #N/A | AA | PAC | Remote upgrade to 112MHz | MW Remote Upgrade | [8 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-01-22 | 2024-01-27 | 2024-01-23 | 2024-01-23 | RONALD SHAN A/L AMBUROSE6800000089 | [17 empty] | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-19 | NURUL//NADIA BINTI ABDULLAH/6800000045
4726C-4154A | Jln Sg Nyior (REL) | DU00003290924 | Northern | Penang | 5.396845 | 100.367113 | WK04 | JAN 24 |  |  | Planning | Link Engineering Report WIP | ZTE | 00. Site Out/Drop | 0127 Pending TSSR submission from GCI | TSS |  |  | Cancel / Drop | Upgrade under NIC DU: 4726C_PostMOCN | [13 empty] | Ongoing | 2024-01-29 | 2024-01-29 | 2024-01-24 | 2025-12-22 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [7 empty] | 2024-02-05 | 2024-02-09
4398C-4034A | Bukit Relau 2 Telestructure | DU00003290925 | Northern | Penang | 5.339467 | 100.252676 | WK05 | MAR 24 | WK13 | MAR 24 | TI | Pending plan | ZTE | 00. Integrated/RFS Done | 26/3: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_SP_1+0_110MHz | MW Swap | NE: Install: 1. Antenna: Install new 23G 0.6m SP A23S06MAC-3NX x 1 2. ODU: Install XMC-3 112MHz Sub-band B x 1 3. IDU: Install new RTN910A x 1, named RTN01 (new NE ID: 23938) 4. IF card: New RTN910A Built-in Slot 7-1 5. IF cable: Connect new IF cable x 1 from the new ODU to Slot 7-1 6. Configure: Link 4398C RTN01->4034A RTN05 1+0 112MHz 890Mbps 7. Disconnect BBU 4398C and connect to RTN01 GE1. Dismantle/ Remain: 1. Dismantle old NEC link (antenna, ODU, IDU, IF cables) FE: Install: 1. Antenna: Install new 23G 0.6m SP A23S06MAC-3NX x 1 2. ODU: Install XMC-3 112MHz Sub-band B x 1 3. IDU: Existing RTN910A, RTN05 4. IF card: Install new ISM8 x 1 at Slot 3 5. IF cable: Connect new IF cable x 1 from the new ODU to Slot 3-1 6. Configure: Link 4398C RTN01->4034A RTN05 1+0 112MHz 890Mbps 7. DCN IP and VLAN: Not required Dismantle/ Remain: 1. Dismantle old NEC link (antenna, ODU, IDU, IF cables) | [7 empty] | GCI | SQ202404030074-GCI | GCI | SQ202409100506-GCI | 2024-11-26 | 2024-11-26 | Completed | 2024-01-31 | 2024-01-31 | 2024-03-26 | 2024-03-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-08-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24030666 |  | 2024-03-07 | 2024-03-19 | Completed | 2024-03-06 | 2024-03-07 | 2024-03-06 | 2024-03-19 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | 2024-09-23 | 2024-10-05 | 2024-09-23 | 2024-09-23 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-04-09 | 2025-04-30 | 2025-04-09 | 2025-05-04 | SAFUAN//BIN YUSOFF/6800000178 | 2025-04-09 | 2025-04-30 | 2025-04-09 | 2025-08-05 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
4386A-4409A | Lumut Port RDD | DU00003290926 | Northern | Perak | 4.238433 | 100.675027 | WK10 | MAR 24 | WK09 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_1.2m/1.2m_DP_3+0_28MHz | MW Swap | NE 1. Install new 15G MDD antenna 1.2m x 1 2. Install ISM8 at Slot 3 and Slot 4, x 2 3. Install new ODU 15G XMC-5D Sub band A x 1 4. Install new IDU RTN910A x 1 5. Configure 15G 4+0 28MHz CA 6. Dismantle existing link FE 1. Install new 15G MDD antenna 1.2m x 1 2. Install ISM8 at Slot 3 and Slot 4, x 2 3. Install new ODU 15G XMC-5D Sub band A x 1 4. Install new IDU RTN910A x 1 5. Configure 15G 4+0 28MHz CA 6. Patching new IDU to new CP port 7. Dismantle existing link # | [7 empty] | GCI | SQ202403110198-GCI | GCI | SQ202402160379-GCI // SQ202409100506-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-01-31 | 2024-01-31 | 2024-03-01 | 2024-03-01 | RASYIDI BIN ZAKARIA6800000132 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020906 |  | 2024-02-10 | 2024-02-13 | Completed | 2024-02-09 | 2024-02-10 | 2024-02-09 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-27 | 2024-03-01 | 2024-02-27 | 2024-03-01 | LATCHUMI//GANTAN A/L THANGAMANI/6800000182 | GCI TI | 2024-02-27 | 2024-03-01 | 2024-02-27 | 2024-03-01 | LATCHUMI//GANTAN A/L THANGAMANI/6800000182 | GCI TI | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-27 | 2024-02-29 | 2024-03-04 | 2024-03-04 | LATCHUMI//GANTAN A/L THANGAMANI/6800000182 | 2024-02-27 | 2024-02-29 | 2024-03-01 | 2024-03-01 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
9033C-9419B | Lorong Sukun | DU00003290927 | Sarawak | Sarawak | 2.247914 | 111.855919 | WK06 | FEB 24 | WK17 | MAY 24 | RFS |  | ZTE | 00. Integrated/RFS Done | 16/5: D2: Cutover done 14/5: MOS & TI WIP. Plan CO by 17/5 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_0.6m/0.6m_SP_1+0_56MHz | MW Swap | NE: 1. Antenna: Install new 0.6 SP MAC model x 1 2. ODU: Install XMC-3 112MHz Sub-band A x 1 3. IDU: Install new RTN910A x 1 4. IF card: Built-in Slot 7 5. Configure 23G 1+0 112MHz 890Mbps 6. BBU re-patch to this new RTN01 7. Decom old NEC link FE: 1. Antenna: Install new 0.6 SP MAC model x 1 2. ODU: Install XMC-3 112MHz Sub-band A x 1 3. IDU: Install new RTN910A x 1 and patch to router port 4. IF card: Built-in Slot 7 5. Configure 23G 1+0 112MHz 890Mbps 6. Decom old NEC link | [7 empty] | Trintel | SQ202402130359-Trintel | Datasco | SQ202407020298-Datasco | 2024-03-29 | 2024-03-25 | Completed | 2024-01-30 | 2024-01-31 | 2024-02-05 | 2024-02-06 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-22 | 2024-02-23 | 2024-02-22 | 2024-02-22 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-25 | 2024-03-29 | 2024-03-25 | 2024-03-25 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24050832 |  | 2024-05-09 | 2024-05-09 | Completed | 2024-05-08 | 2024-05-09 | 2024-05-08 | 2024-05-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-11 | 2024-05-17 | 2024-05-17 | 2024-05-17 | Chiew Hua Kai7019000037 | Datasco TI | 2024-05-11 | 2024-05-17 | 2024-05-11 | 2024-05-17 | Chiew Hua Kai7019000037 | Datasco TI | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-05-11 | 2024-05-17 | 2024-05-21 | 2024-05-21 | Chiew Hua Kai7019000037 | 2024-05-11 | 2024-05-17 | 2024-05-12 | 2024-05-12 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-12-13 | 2025-01-13 | 2024-12-13 | 2024-12-13 | ASTI//GANIS PUTRIANI/6237001358
9279B-9368A | Lorong Salim | DU00003290928 | Sarawak | Sarawak | 2.258588 | 111.870663 | WK05 | JAN 24 | WK16 | APR 24 | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | 6/4: D3: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_0.6m/0.6m_SP_1+0_56MHz | MW Swap | NE: 1. Antenna: Install new 0.6 SP MAC model x 1 2. ODU: Install XMC-3 112MHz Sub-band B x 1 3. IDU: Install new RTN910A x 1 4. IF card: Built-in Slot 7 5. BBU re-patch to this new RTN01 6. Decom old NEC link FE: 1. Antenna: Install new 0.6 SP MAC model x 1 2. ODU: Install XMC-3 112MHz Sub-band B x 1 3. IDU: Install new RTN910A x 1 and patch to router port 4. IF card: Built-in Slot 7 5. Decom old NEC link | [7 empty] | Trintel | SQ202402130359-Trintel | Datasco | SQ202404030681-Datasco | 2024-03-22 | 2024-03-23 | Completed | 2024-01-30 | 2024-01-31 | 2024-01-25 | 2024-01-29 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-02-19 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-23 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240314BG |  | 2024-03-15 | 2024-03-20 | Completed | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-30 | 2024-04-04 | 2024-04-18 | 2024-04-18 | Chiew Hua Kai7019000037 | Datasco TI | 2024-03-30 | 2024-06-30 | 2024-04-18 | 2024-05-17 | Chiew Hua Kai7019000037 | Datasco TI | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-30 | 2024-04-04 | 2024-04-21 | 2024-04-21 | Chiew Hua Kai7019000037 | 2024-03-30 | 2024-04-04 | 2024-04-01 | 2024-04-01 | 2024-04-28 | 2024-04-28 | 2024-04-28 | 2024-04-28 | CHONG QIEW LEK7018000038 | Logistic Team | 2024-07-30 | 2024-08-30 | 2024-07-30 | 2024-07-30 | ASTI//GANIS PUTRIANI/6237001358
3300B_AD | Jln 1_13a (REL) | DU00006488376 | Central | Kuala Lumpur | 3.088810 | 101.673870 | [7 empty] | 03. Pending TSSR Submission | [13 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25123088 |  | 2025-12-31 |  | Ongoing | 2025-12-30 | 2025-12-31 | 2025-12-30 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202601290544-GCI | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | CHEONG/SENG/WAH/7018000306
7401A_IPR_1 | RTM Station | DU00006488377 | Sabah | Sabah | 6.359369 | 116.420833 | [7 empty] | 02. Pending Access |  | TSS+TI |  | 1G SFP Module x 4 Fiber Patch Cord x 2 pairs | MW IDU Patching | Perform LAG at CP site for IDU 7401A-RTM-Station-RTN05 to 7401A-MAC-001 RTM Station Site Impacted : 7337B,7334B,7217H. 1) Patch IDU 7401A GE5 and GE6 to new CP port (to use optical since no extra electrical port at IDU) 2) Create LAG | Perform LAG at CP site for IDU 7401A-RTM-Station-RTN05 to 7401A-MAC-001 RTM Station Site Impacted : 7337B,7334B,7217H. 1) Patch IDU 7401A GE5 and GE6 to new CP port (to use optical since no extra electrical port at IDU) 2) Create LAG | [12 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512290826-GCI | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | CHEONG/SENG/WAH/7018000306
4174A_HU_1 | LBSBFactory | DU00006488524 | Northern | Penang | 5.354917 | 100.408861 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 18G_2+0_55M_512QAM_450M. MW Remote Upgrade to HW 18G_2+0_110M_512QAM_1778M. Site Impacted : 4333C. NE_4174A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(512QAM). FE_4000A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(512QAM). | Link Existing HW 18G_2+0_55M_512QAM_450M. MW Remote Upgrade to HW 18G_2+0_110M_512QAM_1778M. Site Impacted : 4333C. NE_4174A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(512QAM). | Link Existing HW 18G_2+0_55M_512QAM_450M. MW Remote Upgrade to HW 18G_2+0_110M_512QAM_1778M. Site Impacted : 4333C. FE_4000A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(512QAM). | XMC-3 | HS | 18G | 18G_1.2M(HS) x1 | 18G_1.2M(HS) x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601070337-GTSB
4729D_HU | TamanDesa Aman | DU00006488525 | Northern | Perak | 5.091639 | 100.480345 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_55M_512QAM_EPLA NE_4729D New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-28071). New XMC_5D Pro, Sub A_Hi x1. FE_4399A New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN04, NEID 9-28072). New XMC_5D Pro, Sub A_Lo x1. | MW Swap | Existing HW MW Link_4729D-4399A, 18G_1+0_55MHZ_512QAM_450M. MW Swap to new HW MW Link 4729D-4399A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom Antenna, ODU of HW MW Link 4729D-4399A, 18G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 9-28071) and RTN910AF(RTN04, NEID 9-28072). Site Impacted : 4733D. NE_4729D 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-28071). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 4729D via new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA. 6.Later, decom Antenna, ODU of HW MW Link 4729D-4399A, 18G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 9-28071) and RTN910AF(RTN04, NEID 9-28072). FE_4399A 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-28071). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 4729D via existing port of IBeam at CP 4391A. 6.Later, decom Antenna, ODU of HW MW Link 4729D-4399A, 18G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 9-28071) and RTN910AF(RTN04, NEID 9-28072). | Existing HW MW Link_4729D-4399A, 18G_1+0_55MHZ_512QAM_450M. MW Swap to new HW MW Link 4729D-4399A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom Antenna, ODU of HW MW Link 4729D-4399A, 18G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 9-28071) and RTN910AF(RTN04, NEID 9-28072). Site Impacted : 4733D. NE_4729D 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-28071). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 4729D via new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA. 6.Later, decom Antenna, ODU of HW MW Link 4729D-4399A, 18G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 9-28071) and RTN910AF(RTN04, NEID 9-28072). | Existing HW MW Link_4729D-4399A, 18G_1+0_55MHZ_512QAM_450M. MW Swap to new HW MW Link 4729D-4399A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom Antenna, ODU of HW MW Link 4729D-4399A, 18G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 9-28071) and RTN910AF(RTN04, NEID 9-28072). Site Impacted : 4733D. FE_4399A 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-28071). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 4729D via existing port of IBeam at CP 4391A. 6.Later, decom Antenna, ODU of HW MW Link 4729D-4399A, 18G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 9-28071) and RTN910AF(RTN04, NEID 9-28072). | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | GTSB | SQ202601150547-GTSB | GTSB | SQ202601150530-GTSB // SQ202601150542-GTSB | 2026-03-02 | 2026-02-23 | Completed | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-02-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011530 |  | 2026-01-16 | 2026-01-17 | Completed | 2026-01-15 | 2026-01-16 | 2026-01-15 | 2026-01-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-01-23 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-02-13 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-25 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-25 | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-02-11 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-01-23 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601070337-GTSB
7260R_HU | SimpangMengayau | DU00006488526 | Sabah | Sabah | 7.028600 | 116.748100 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI |  | 18G_1+0_112M. NE_7260R 18G_SP_1.2M(MAC) x1. XMC_3E , Sub B_Hi x1. FE_7393A. 18G_SP_1.2M(MAC). XMC_3E , Sub B_Lo x1. | MW Parallel Link | Existing link 18G_1+0_56M. Install parallel link 18G_1+0_112M. Site impacted : 7260R , 7263R NE_7260R 1.Install new 18G_SP_1.2M(MAC). 2.Reuse existing 7260R_RTN01 , 7_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decom MW link. FE_7393A. 1.Install new 18G_SP_1.2M(MAC). 2.Reuse existing 7393A_RTN01 , 7_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decom MW link. | Existing link 18G_1+0_56M. Install parallel link 18G_1+0_112M. Site impacted : 7260R , 7263R NE_7260R 1.Install new 18G_SP_1.2M(MAC). 2.Reuse existing 7260R_RTN01 , 7_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decom MW link. | Existing link 18G_1+0_56M. Install parallel link 18G_1+0_112M. Site impacted : 7260R , 7263R FE_7393A. 1.Install new 18G_SP_1.2M(MAC). 2.Reuse existing 7393A_RTN01 , 7_ISM8-1+0 , port 2. 3.Install new XMC_3E , Sub B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new parallel link. 6.No decom MW link. | XMC_3E | MAC | 18 | 1.2 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601070322-GCI | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | CHEONG/SENG/WAH/7018000306
3459B_HU | Tower3 Podium IB | DU00006488527 | Central | Pahang | 3.425041 | 101.794939 | [7 empty] | 02. Pending Access |  | TSS+AA+TI |  | 23G_2+0_112M NE_3459B 23G_DP_0.3M(MAC) x1. ISM8 x1. XMC_3E , Sub A&B_Lo x2. FE_2388A. 23G_DP_0.3M(MAC) x1. ISM8 x1. XMC_3E , Sub A&B_Hi x2. | MW Parallel Link | Existing link 23G_1+0_112M Install parallel link 23G_2+0_112M Site Impacted : 3459B,3322B,3459C NE_3459B 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing 3459B_RTN01. 3.Install new 3_ISM8-2+0 into existing 3459B_RTN01. 4.Install new XMC_3E , Sub A&B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW. FE_2388A. 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing 2388A_RTN06. 3.Install new 3_ISM8-2+0 into existing 2388A_RTN06. 4.Install new XMC_3E , Sub A&B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW. | Existing link 23G_1+0_112M Install parallel link 23G_2+0_112M Site Impacted : 3459B,3322B,3459C. NE_3459B 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing 3459B_RTN01. 3.Install new 3_ISM8-2+0 into existing 3459B_RTN01. 4.Install new XMC_3E , Sub A&B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW. | Existing link 23G_1+0_112M Install parallel link 23G_2+0_112M Site Impacted : 3459B,3322B,3459C. FE_2388A. 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing 2388A_RTN06. 3.Install new 3_ISM8-2+0 into existing 2388A_RTN06. 4.Install new XMC_3E , Sub A&B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. 7.No decom MW. | XMC_3E | MAC | 23G | 0.3 | 0.3 | MTK | SQ202601210097-MTK | MTK | SQ202601210072-MTK // SQ202601210080-MTK |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26010602 |  | 2026-01-07 | 2026-01-22 | Completed | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202601070316-GCI | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | CHEONG/SENG/WAH/7018000306
3784A_HU | Pangsapuri AlamPerdana | DU00006488528 | Central | Selangor | 3.257219 | 101.449400 | [7 empty] | 05. Doable |  | AA |  |  | MW Remote Upgrade | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(1396E) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** Link Existing HW 18G_2+0_55M_512QAM_428M. MW Remote Upgrade to HW 18G_2+0_110M_256QAM_1556M. Site Impacted : 3784A & 1396E(EB Site). NE_3784A 1.Existing ODU XMC-5D pro(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(256QAM). FE_2531A 1.Existing ODU XMC-5D pro(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(256QAM). | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(1396E) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** Link Existing HW 18G_2+0_55M_512QAM_428M. MW Remote Upgrade to HW 18G_2+0_110M_256QAM_1556M. Site Impacted : 3784A & 1396E(EB Site). NE_3784A 1.Existing ODU XMC-5D pro(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(256QAM). | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(1396E) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** Link Existing HW 18G_2+0_55M_512QAM_428M. MW Remote Upgrade to HW 18G_2+0_110M_256QAM_1556M. Site Impacted : 3784A & 1396E(EB Site). FE_2531A 1.Existing ODU XMC-5D pro(equipped 112MHz) may remotely upgrade from 55MHz to BW 112MHz(256QAM). | XMC-5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601070335-GTSB
1771C_HU_1 | Parit8 Gambut | DU00006488529 | Central | Selangor | 3.694266 | 101.048248 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 2X RTN910A 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB A HI 1x ODU 15G XMC5D SUB A LO | MW New Link / Reroute | MW NEW LINK 1771C-B01348 WITH HUAWEI_15G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_A__WITH CA_LINK_2.88KM IMPACTED: 1771C DISMANTLE EXISTING LINK 1771C-B00695 | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK 1771C-B00695 | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK 1771C-B00695 | XMC5D | MDD | 15G | 1.2 | 1.2 | GCI | SQ202601210056-GCI | GCI | SQ202601210049-GCI // SQ202601210050-GCI |  |  | Ongoing | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010735 |  | 2026-01-08 | 2026-01-14 | Completed | 2026-01-07 | 2026-01-08 | 2026-01-07 | 2026-01-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-25 | 2026-02-23 | 2026-02-27 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-27 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-23 | 2026-01-26 | 2026-02-02 | 2026-01-25 | 2026-03-06 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2026-01-26 | 2026-02-02 | 2026-01-25 | 2026-01-26 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601070316-GCI | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
R00023_HU_1 | R001B_R00023OD_KUALAPERLIS | DU00006488530 | Northern | Perlis | 6.383942 | 100.152053 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_110M_128QAM_EPLA NE_R00023 New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN04, NEID 44-13960). New XMC_5D Pro, Sub A_Lo x1. New IF cables with suitable length and type x2 RUN. FE_R00028/4323K New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 44-23960). New XMC_5D Pro, Sub A_Hi x1. New IF cables with suitable length and type x2 RUN. | MW Swap | Existing HW MW Link R00023(RTN04, NEID 44-13960)-R00028/4323K(RTN02, NEID 44-23960), 13G_6+0_28MHZ_512QAM_CA. Swap existing HW MW Link R00023(RTN04, NEID 44-13960)-R00028/4323K(RTN02, NEID 44-23960), 13G_2+0_28MHZ_512QAM_CA slot 07 Port 1 & 2 with new HW MW Link R00023-R00028/4323K, 18G_2+0_110MHZ_128QAM_EPLA. Become new HW MW Link 13G&18G_6+0_28MHZ&110MHZ_512QAM&128QAM_EPLA. Site Impacted : 4608B & 4135H. NE_R00023 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN04, NEID 44-13960) and re-use existing ISM8 slot 07 Port 1 & 2. 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN04, NEID 44-13960) ISM8 slot 07 Port 1 & 2 . 4.Build new HW MW R00023-R00028/4323K, 18G_2+0_110MHZ_128QAM_EPLA and combine with existing 13G_4+0_28MHZ_512QAM_CA ISM8 slot 03 & slot 04 become HW MW R00023-R00028/4323K, 13G&18G_6+0_28MHZ&110MHZ_512QAM&128QAM_EPLA. 5.Re-use existing xC Vlan DCN & Vlan Services. 6.Migrate traffics 4608B & 4135H to new HW MW Link R00023-R00028/4323K, 18G_2+0_110MHZ_512QAM_EPLA. 7.Later decom existing HW MW Link R00023(RTN04, NEID 44-13960)-R00028/4323K(RTN02, NEID 44-23960), 13G_2+0_28MHZ_512QAM_CA. FE_R00028/4323K 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 44-23960) and re-use existing ISM8 slot 07 Port 1 & 2. 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN02, NEID 44-23960) ISM8 slot 07 Port 1 & 2 . 4.Build new HW MW R00023-R00028/4323K, 18G_2+0_110MHZ_128QAM_EPLA and combine with existing 13G_4+0_28MHZ_512QAM_CA ISM8 slot 03 & slot 04 become HW MW R00023-R00028/4323K, 13G&18G_6+0_28MHZ&110MHZ_512QAM&128QAM_EPLA. 5.Re-use existing xC Vlan DCN & Vlan Services. 6.Migrate traffics 4608B & 4135H to existing port at PTN/Cisco Router. 7.Later decom existing HW MW Link R00023(RTN04, NEID 44-13960)-R00028/4323K(RTN02, NEID 44-23960), 13G_2+0_28MHZ_512QAM_CA. | Existing HW MW Link R00023(RTN04, NEID 44-13960)-R00028/4323K(RTN02, NEID 44-23960), 13G_6+0_28MHZ_512QAM_CA. Swap existing HW MW Link R00023(RTN04, NEID 44-13960)-R00028/4323K(RTN02, NEID 44-23960), 13G_2+0_28MHZ_512QAM_CA slot 07 Port 1 & 2 with new HW MW Link R00023-R00028/4323K, 18G_2+0_110MHZ_128QAM_EPLA. Become new HW MW Link 13G&18G_6+0_28MHZ&110MHZ_512QAM&128QAM_EPLA. Site Impacted : 4608B & 4135H. NE_R00023 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN04, NEID 44-13960) and re-use existing ISM8 slot 07 Port 1 & 2. 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN04, NEID 44-13960) ISM8 slot 07 Port 1 & 2 . 4.Build new HW MW R00023-R00028/4323K, 18G_2+0_110MHZ_128QAM_EPLA and combine with existing 13G_4+0_28MHZ_512QAM_CA ISM8 slot 03 & slot 04 become HW MW R00023-R00028/4323K, 13G&18G_6+0_28MHZ&110MHZ_512QAM&128QAM_EPLA. 5.Re-use existing xC Vlan DCN & Vlan Services. 6.Migrate traffics 4608B & 4135H to new HW MW Link R00023-R00028/4323K, 18G_2+0_110MHZ_512QAM_EPLA. 7.Later decom existing HW MW Link R00023(RTN04, NEID 44-13960)-R00028/4323K(RTN02, NEID 44-23960), 13G_2+0_28MHZ_512QAM_CA. | Existing HW MW Link R00023(RTN04, NEID 44-13960)-R00028/4323K(RTN02, NEID 44-23960), 13G_6+0_28MHZ_512QAM_CA. Swap existing HW MW Link R00023(RTN04, NEID 44-13960)-R00028/4323K(RTN02, NEID 44-23960), 13G_2+0_28MHZ_512QAM_CA slot 07 Port 1 & 2 with new HW MW Link R00023-R00028/4323K, 18G_2+0_110MHZ_128QAM_EPLA. Become new HW MW Link 13G&18G_6+0_28MHZ&110MHZ_512QAM&128QAM_EPLA. Site Impacted : 4608B & 4135H. FE_R00028/4323K 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 44-23960) and re-use existing ISM8 slot 07 Port 1 & 2. 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN and terminate to existing RTN910AF(RTN02, NEID 44-23960) ISM8 slot 07 Port 1 & 2 . 4.Build new HW MW R00023-R00028/4323K, 18G_2+0_110MHZ_128QAM_EPLA and combine with existing 13G_4+0_28MHZ_512QAM_CA ISM8 slot 03 & slot 04 become HW MW R00023-R00028/4323K, 13G&18G_6+0_28MHZ&110MHZ_512QAM&128QAM_EPLA. 5.Re-use existing xC Vlan DCN & Vlan Services. 6.Migrate traffics 4608B & 4135H to existing port at PTN/Cisco Router. 7.Later decom existing HW MW Link R00023(RTN04, NEID 44-13960)-R00028/4323K(RTN02, NEID 44-23960), 13G_2+0_28MHZ_512QAM_CA. | XMC-5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | GTSB | SQ202601150547-GTSB | GTSB | SQ202601150530-GTSB // SQ202601150542-GTSB |  |  | Ongoing | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022620 |  | 2026-02-27 | 2026-03-05 | Completed | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-03-05 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-05 | 2026-03-29 | 2026-03-05 | 2026-03-09 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-03-05 | 2026-03-29 | 2026-03-05 | 2026-03-10 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-06 | 2026-03-05 | 2026-03-29 | 2026-03-05 | 2026-03-11 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2024-02-27: 2026-03-05; 2024-02-29: 2026-03-29; 2024-03-01: 2026-03-05; 2024-03-01: 2026-03-07 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601070337-GTSB
4116R_HU | Kg.Sungai Baru | DU00006488531 | Northern | Kedah | 5.689300 | 100.398500 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 2X RTN910A 1X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1x ODU 15G XMC5D SUB B LO | MW Swap | MW SWAP LINK 4116R-4939A WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_B_WITH CA_LINK_4.94KM IMPACTED: 4116R DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING | XMC5D | MDD | 15G | 0.6 | 1.2 | GCI | SQ202601210141-GCI | GCI | SQ202601190066-GCI // SQ202601190068-GCI // SQ202603270199-GCI | 2026-02-23 | 2026-02-23 | Completed | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010733 |  | 2026-01-08 | 2026-01-09 | Completed | 2026-01-07 | 2026-01-08 | 2026-01-07 | 2026-01-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-16 | 2026-01-20 | 2026-01-16 | 2026-01-17 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-01-16 | 2026-01-20 | 2026-01-16 | 2026-01-21 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-17 | 2026-01-16 | 2026-01-20 | 2026-01-16 | 2026-01-23 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2026-01-16 | 2026-01-20 | 2026-01-16 | 2026-01-17 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601070319-GCI | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
A00800_HU | A042A_A00800OD_MN_KGCHEMPAKA | DU00006488532 | Northern | Perak | 4.921650 | 100.825658 |  |  |  |  | 29/1: FE pending install due to access issue(landslide). Dont hv altenative routre(comfirmed by FF & Maxis FOD |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 2X RTN910A 2X 13G 1.2M MDD ANTENNA 1x ODU 13G XMC5D SUB A HI 1x ODU 13G XMC5D SUB A LO | MW Swap | MW SWAP LINK A00800-4584A WITH HUAWEI_13G_4+0_1.2M/1.2M_MDD_28MHZ_256QAM_800MBPS_XMC5D_SUB_A_WITH CA_LINK_7.5KM IMPACTED: A00800 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM WITH CA 5. DISMANTLE EXISTING | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM WITH CA 5. DISMANTLE EXISTING | XMC5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202601210141-GCI | GCI | SQ202601130185-GCI // SQ202601130189-GCI | 2026-03-14 | 2026-03-13 | Completed | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010737 |  | 2026-01-08 | 2026-01-09 | Completed | 2026-01-07 | 2026-01-08 | 2026-01-07 | 2026-01-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-18 | 2026-01-13 | 2026-03-15 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-01-13 | 2026-01-18 | 2026-01-13 | 2026-03-15 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | GCI TI | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-16 | 2026-01-13 | 2026-01-18 | 2026-01-13 | 2026-03-17 | MUHAMMAD SYAIRUL HAFIZI BIN MOHD AZHAR6800000248 | 2024-02-27: 2026-01-13; 2024-02-29: 2026-01-18; 2024-03-01: 2026-01-13; 2024-03-01: 2026-03-07 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601070319-GCI | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | EZRIN TASNIM BIN ABDUL GANI6798000128
3433B1_HU | pBTSFinisar Klebang (M ) | DU00006488533 | Northern | Perak | 4.669220 | 101.129690 | [7 empty] | 00. Site Out/Drop |  | NA |  | 18G_2+0_55M_512QAM_EPLA NE_3433B1 New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-30586). New XMC_5D Pro, Sub A_Hi x1. FE_4496A New 18G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-30577). New XMC_5D Pro, Sub A_Lo x1. | Cancel / Drop | 25 Feb 2026: Site 3433B1 already replaced with permanent site 4831D. Existing link/equipment from PBTS 3433B1 relocated to 4831D. Link will be upgraded/rerouted under DU 4831D_HU Existing HW MW Link_3433B1-4496A, 18G_1+0_55MHZ_128QAM_342M. MW Swap to new HW MW Link 3433B1-4496A, 18G_2+0_55MHZ_512QAM_900M. Later, decom Antenna, ODU ONLY of 3433B1-4496A, 18G_1+0_55MHZ_128QAM_342M. Anyway, do not decom RTN910AF(RTN01, NEID 9-30586) and RTN910AF(RTN01, NEID 9-30577). Site Impacted : 3433B1. NE_3433B1 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-30586). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 3433B1 via new HW MW Link 3433B1-4496A, 18G_2+0_55MHZ_512QAM_900M. 6.Later, decom Antenna, ODU ONLY of 3433B1-4496A, 18G_1+0_55MHZ_128QAM_342M. Anyway, do not decom RTN910AF(RTN01, NEID 9-30586) and RTN910AF(RTN01, NEID 9-30577). FE_4399A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-30577). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 3433B1 via existing port of IBeam. 6.Later, decom Antenna, ODU ONLY of 3433B1-4496A, 18G_1+0_55MHZ_128QAM_342M. Anyway, do not decom RTN910AF(RTN01, NEID 9-30586) and RTN910AF(RTN01, NEID 9-30577). | Existing HW MW Link_3433B1-4496A, 18G_1+0_55MHZ_128QAM_342M. MW Swap to new HW MW Link 3433B1-4496A, 18G_2+0_55MHZ_512QAM_900M. Later, decom Antenna, ODU ONLY of 3433B1-4496A, 18G_1+0_55MHZ_128QAM_342M. Anyway, do not decom RTN910AF(RTN01, NEID 9-30586) and RTN910AF(RTN01, NEID 9-30577). Site Impacted : 3433B1. NE_3433B1 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-30586). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 3433B1 via new HW MW Link 3433B1-4496A, 18G_2+0_55MHZ_512QAM_900M. 6.Later, decom Antenna, ODU ONLY of 3433B1-4496A, 18G_1+0_55MHZ_128QAM_342M. Anyway, do not decom RTN910AF(RTN01, NEID 9-30586) and RTN910AF(RTN01, NEID 9-30577). | Existing HW MW Link_3433B1-4496A, 18G_1+0_55MHZ_128QAM_342M. MW Swap to new HW MW Link 3433B1-4496A, 18G_2+0_55MHZ_512QAM_900M. Later, decom Antenna, ODU ONLY of 3433B1-4496A, 18G_1+0_55MHZ_128QAM_342M. Anyway, do not decom RTN910AF(RTN01, NEID 9-30586) and RTN910AF(RTN01, NEID 9-30577). Site Impacted : 3433B1. FE_4399A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-30577). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Re-use existing xD Vlan DCN and Vlan Services. 5.Migrate traffic 3433B1 via existing port of IBeam. 6.Later, decom Antenna, ODU ONLY of 3433B1-4496A, 18G_1+0_55MHZ_128QAM_342M. Anyway, do not decom RTN910AF(RTN01, NEID 9-30586) and RTN910AF(RTN01, NEID 9-30577). | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_1.2M(MDD) x1 | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202601070337-GTSB
S01611_HU | S091A_S01611OD_DESAKIMLOONGRESOURCES | DU00006488534 | Sabah | Sabah | 5.665636 | 117.684500 | [7 empty] | 05. Doable |  | TSS+AA+TI |  | 15G_4+0_28M_512QAM_EPLA NE_S01611/7139K New 15G_1.2M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x2 RUN. FE_S00175/7171K New 15G_1.2M(MDD)+Dual Coupler x1. New RTN910AF. New ISM8 x2. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x2 RUN. | MW Parallel Link | Existing Huawei MW Link 15G_2+0_28MHZ_512QAM_EPLA. Build new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. Later, combine existing Huawei MW Link 15G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : S01611/7139K. NE_S01611/7139K 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Swap existing RTN910AF(RTN01, NEID 16-13244) with new RTN910AF and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Lay new IF cables with suitable length and type x2 RUN. 5.Build new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. 6.Re-use existing Vlan DCN and Vlan Services. 7.Later, combine existing Huawei MW Link 15G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_512QAM_EPLA. 8.Migrate traffic S01611/7139K via new 15G_6+0_28MHZ_512QAM_EPLA. FE_S00175/7171K 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Swap existing (RTN01, NEID 16-23244) with new RTN910AF and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new IF cables with suitable length and type x2 RUN. 5.Build new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. 6.Re-use existing Vlan DCN and Vlan Services. 7.Later, combine existing Huawei MW Link 15G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_512QAM_EPLA. 8.Migrate traffic S01611/7139K via existing port of PTN/Cisco Router. | Existing Huawei MW Link 15G_2+0_28MHZ_512QAM_EPLA. Build new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. Later, combine existing Huawei MW Link 15G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : S01611/7139K. NE_S01611/7139K 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Swap existing RTN910AF(RTN01, NEID 16-13244) with new RTN910AF and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Lay new IF cables with suitable length and type x2 RUN. 5.Build new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. 6.Re-use existing Vlan DCN and Vlan Services. 7.Later, combine existing Huawei MW Link 15G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_512QAM_EPLA. 8.Migrate traffic S01611/7139K via new 15G_6+0_28MHZ_512QAM_EPLA. | Existing Huawei MW Link 15G_2+0_28MHZ_512QAM_EPLA. Build new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. Later, combine existing Huawei MW Link 15G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_512QAM_EPLA. Site Impacted : S01611/7139K. FE_S00175/7171K 1.Install 15G_1.2M(MDD)+Dual Coupler x1. 2.Swap existing (RTN01, NEID 16-23244) with new RTN910AF and insert ISM8 x2 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Lay new IF cables with suitable length and type x2 RUN. 5.Build new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. 6.Re-use existing Vlan DCN and Vlan Services. 7.Later, combine existing Huawei MW Link 15G_2+0_28MHZ_512QAM_EPLA and new parallel HW MW Link S01611/7139K-S00175/7171K 15G_4+0_28M_512QAM_EPLA. Become 15G_6+0_28MHZ_512QAM_EPLA. 8.Migrate traffic S01611/7139K via existing port of PTN/Cisco Router. | XMC_5D Pro | MDD | 15G | 15G_1.2M(MDD)+Dual Coupler x1 | 15G_1.2M(MDD)+Dual Coupler x1 | NR services |  | NR services | SQ202604150279-NR Services // SQ202604150286-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031153 |  | 2026-03-12 | 2026-03-27 | Completed | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-27 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-04-25 | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-04-15 | 2026-05-15 | 2026-04-15 |  | MIKE MICRON DOLIK6000068237 | NR Service TI | [7 empty] | 2026-04-15 | 2026-05-15 | 2026-04-15 |  | MIKE MICRON DOLIK6000068237 | 2024-02-27: 2026-04-15; 2024-02-29: 2026-05-15; 2024-03-01: 2026-04-15; 2024-03-01: 2026-04-25 | [7 empty] | GTSB | SQ202601070339-GTSB
Q02212_HU | KG SKIAT BARU | DU00006488535 | Sarawak | Sarawak | 1.387510 | 110.192110 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 4xIF CABLE WITH ACCESSORIES | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK Q02212-9334A FROM 13G_2+0_1.8M/1.8M_MDD_28MHZ_256QAM TO HUAWEI_13G_4+0_1.8M/1.8M_MDD_28MHZ_256QAM_773MBPS_XMC5D_SUB_A & B_LINK_14.7KM IMPACTED: Q02212 | 1. REUSE EXISTING IDU RTN01 2. REUSE EXISTING 13G 1.8M MDD ANTENNA 3. ADD IF CABLE ODU SUB A (SLOT 3) AND CONFIGURE POLAR V (256QAM) - EXISTING SLOT 3 USING H POLAR 4. ADD IF CABLE ODU SUB B (SLOT 7) AND CONFIGURE POLAR H (128QAM) - EXISTING SLOT 7 USING V POLAR 5. CONFIGURE LINK 13G 4+0 28MHZ | 1. REUSE EXISTING IDU RTN03 2. REUSE EXISTING 13G 1.8M MDD ANTENNA 3. ADD IF CABLE ODU SUB A (SLOT 3) AND CONFIGURE POLAR V (256QAM) - EXISTING SLOT 3 USING H POLAR 4. ADD IF CABLE ODU SUB B (SLOT 7) AND CONFIGURE POLAR H (128QAM) - EXISTING SLOT 7 USING H POLAR 5. CONFIGURE LINK 13G 4+0 28MHZ | XMC5D | MDD | 13G | 1.8 | 1.8 | Allstar | SQ202602250663-Allstar | Allstar | SQ202602090139-Allstar // SQ202602090142-Allstar |  |  | Ongoing | 2026-05-07 | 2026-05-13 | 2026-05-07 | 2026-05-07 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-05-07 | 2026-05-13 | 2026-05-07 | 2026-05-07 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-05-06 | 2026-05-07 | 2026-05-06 | 2026-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-08 | 2026-05-09 | 2026-05-08 |  | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. |  | Assigned | Ongoing | To be Submitted |  | DOWMY26013005 |  | 2026-01-31 |  | Ongoing | 2026-01-30 | 2026-01-31 | 2026-01-30 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-02-03 | 2026-02-09 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-02-03 | 2026-02-09 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-02-04 | 2026-02-03 | 2026-02-09 |  |  | BONG NEE NYEEbong.allstar@gmail.com | 2024-02-27: 2026-02-03; 2024-02-29: 2026-02-09; 2024-03-01: 2026-02-04; 2024-03-01: 2026-02-04 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202601070323-GCI | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | EZRIN TASNIM BIN ABDUL GANI6798000128
7137D_LOS | Kampung Tinusa | DU00006493359 | Sabah | Sabah | 5.892802 | 118.076337 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 1X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB A HI 1x ODU 15G XMC5D SUB A LO | MW New Link / Reroute | MW NEW LINK REROUTE 7137D-7573A WITH HUAWEI_15G_2+0_0.6M/1.2M_MDD_28MHZ_512QAM(V)256QAM(H)_424MBPS_XMC5D_SUB_A_LINK_6.7KM IMPACTED: 7137D DISMANTLE EXISTING LINK 7137D-7124A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. DISMANTLE EXISTING LINK 7137D-7124A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. PATCH TO LL 6. DISMANTLE EXISTING LINK 7137D-7124A | XMC5D | MDD | 15G | 0.6 | 1.2 |  |  | NR services | SQ202603170069-NR Services // SQ202603170077-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030335 |  | 2026-03-04 | 2026-03-15 | Completed | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-14 | 2026-03-31 | 2026-03-14 | 2026-03-16 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-03-14 | 2026-03-31 | 2026-03-14 | 2026-03-28 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2026-03-14 | 2026-03-31 | 2026-03-14 | 2026-04-06 | IBRAHIM//BIN SAHABU/7167000007 | 2026-03-14 | 2026-03-31 | 2026-03-14 | 2026-03-28 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202602120118-GCI | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
W01336_LOS | W066F_W01336OD_PALIMBAYAN_INDAH | DU00006493360 | Central | Kuala Lumpur | 3.172278 | 101.627125 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M_512QAM NE_1452K/W01336 New 23G_DP_0.6(MAC) x1. Re_use existing RTN910AF(RTN01, NEID 33-10001). New XMC_3E, Sub B_Lo x1. FE_W00027 New 23G_DP_0.6(MAC) x1. Re_use existing RTN910AF(RTN01, NEID 33-16990). New ISM8 x1. New XMC_3E, Sub B_Hi x1. | MW New Link / Reroute | Existing HW MW Link 1452K/W01336-W00057/1389B, 23G_1+0_112MHZ_128QAM. Reroute to new HW MW Link 1452K/W01336-1357K/W00027, 23G_1+0_112MHZ_512QAM. Later, decom existing HW MW Link 1452K/W01336-W00057/1389B, 23G_1+0_112MHZ_128QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 33-10001) at 1452K/W01336. Site Impacted : 1452K/W01336. NE_1452K/W01336 1.Install new 23G_DP_0.6(MAC) x1. 2.Re_use existing RTN910AF(RTN01, NEID 33-10001). 3.Install new XMC_3E, Sub B_Lo x1. Configure it. 4.Request new xC Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Migrate traffic 1452K/W01336 via new HW MW Link 1452K/W01336-1357K/W00027, 23G_1+0_112MHZ_512QAM. 6.Later, decom existing HW MW Link 1452K/W01336-W00057/1389B, 23G_1+0_112MHZ_128QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 33-10001) at 1452K/W01336. FE_1357K/W00027 1.Install new 23G_DP_0.6(MAC) x1. 2.Re_use existing RTN910AF(RTN01, NEID 33-16990). Insert new ISM8 into slot 03. 3.Install new XMC_3E, Sub B_Hi x1. Configure it. 4.Request new xC Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Migrate traffics 1452K/W01336 at PTN/Cisco Router B00632 in which similar port with 1357K/W00027. 6.Later, decom existing HW MW Link 1452K/W01336-W00057/1389B, 23G_1+0_112MHZ_128QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 33-10001) at 1452K/W01336. | Existing HW MW Link 1452K/W01336-W00057/1389B, 23G_1+0_112MHZ_128QAM. Reroute to new HW MW Link 1452K/W01336-1357K/W00027, 23G_1+0_112MHZ_512QAM. Later, decom existing HW MW Link 1452K/W01336-W00057/1389B, 23G_1+0_112MHZ_128QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 33-10001) at 1452K/W01336. Site Impacted : 1452K/W01336. NE_1452K/W01336 1.Install new 23G_DP_0.6(MAC) x1. 2.Re_use existing RTN910AF(RTN01, NEID 33-10001). 3.Install new XMC_3E, Sub B_Lo x1. Configure it. 4.Request new xC Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Migrate traffic 1452K/W01336 via new HW MW Link 1452K/W01336-1357K/W00027, 23G_1+0_112MHZ_512QAM. 6.Later, decom existing HW MW Link 1452K/W01336-W00057/1389B, 23G_1+0_112MHZ_128QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 33-10001) at 1452K/W01336. | Existing HW MW Link 1452K/W01336-W00057/1389B, 23G_1+0_112MHZ_128QAM. Reroute to new HW MW Link 1452K/W01336-1357K/W00027, 23G_1+0_112MHZ_512QAM. Later, decom existing HW MW Link 1452K/W01336-W00057/1389B, 23G_1+0_112MHZ_128QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 33-10001) at 1452K/W01336. Site Impacted : 1452K/W01336. FE_1357K/W00027 1.Install new 23G_DP_0.6(MAC) x1. 2.Re_use existing RTN910AF(RTN01, NEID 33-16990). Insert new ISM8 into slot 03. 3.Install new XMC_3E, Sub B_Hi x1. Configure it. 4.Request new xC Vlan DCN and Vlan services from ZTE IPRAN Team. 5.Migrate traffics 1452K/W01336 at PTN/Cisco Router B00632 in which similar port with 1357K/W00027. 6.Later, decom existing HW MW Link 1452K/W01336-W00057/1389B, 23G_1+0_112MHZ_128QAM. Anyway, do not decom existing RTN910AF(RTN01, NEID 33-10001) at 1452K/W01336. | XMC_3E | MAC | 23G | 23G_DP_0.6(MAC) x1 | 23G_DP_0.6(MAC) x1 | GTSB | SQ202601130167-GTSB | GTSB | SQ202601160487-GTSB // SQ202601160493-GTSB | 2026-03-02 | 2026-02-23 | Completed | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | MOHD//BADRIZ BIN NANANG/6799000311 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-29 | 2026-01-15 | 2026-01-15 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-29 | 2026-01-22 | 2026-01-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010906 |  | 2026-01-10 | 2026-01-16 | Completed | 2026-01-09 | 2026-01-10 | 2026-01-09 | 2026-01-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-16 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-17 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-15 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-02-10 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-16 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601070335-GTSB
7226B_HU_1 | Harmony Industrial Park | DU00006500948 | Sabah | Sabah | 6.015419 | 116.148019 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X RTN910A 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB A HI 1x ODU 18G XMC5D SUB A LO | MW Swap | MW SWAP LINK 7226B-7154A WITH HUAWEI_18G_2+0_0.6M/0.6M_MDD_112MHZ_256QAM_1556MBPS_XMC5D_SUB_A_LINK_2.56KM IMPACTED: 7226B,7650A, 7078H DISMANTLE EXISTING LINK EXCEPT NE IDU | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING EXCEPT IDU | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 2G 6. DISMANTLE EXISTING | XMC5D | MDD | 18G | 0.6 | 0.6 | NR services |  | NR services | SQ202604220814-NR Services // SQ202604230198-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022336 |  | 2026-02-24 | 2026-02-26 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-26 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-05-04 | RANA//WAQAS/6000006187 | NR Service TI | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-05-04 | RANA//WAQAS/6000006187 | NR Service TI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-21 | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-05-04 | RANA//WAQAS/6000006187 | 2026-01-14: 2026-04-15; 2026-01-14: 2026-05-15; 2026-01-14: 2026-04-15; 2026-01-16: 2026-04-18 | [7 empty] | GCI | SQ202601070322-GCI | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
9709A_EB | Similajau | DU00006511577 | Sarawak | Sarawak | 3.366540 | 113.437450 | [9 empty] | TSS+TI |  | 1x 910A RTN (prioritize re-deploy IDU with CSHR board for 4xGE electrical port availability) | IDU-IPRAN | 1x 910A RTN (prioritize re-deploy IDU with CSHR board for 4xGE electrical port availability) 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | 1x 910A RTN (prioritize re-deploy IDU with CSHR board for 4xGE electrical port availability) 1) To install new IDU for EB sites 2) New IDU will connect to new SACOFA port (port info to be provided later by CD) 3) To prepare 3 GE ports (electrical) 4) In case RTN910A with CSHRF is installed, to inform CD to provide electrical SFP 5) To establish new DCN | [12 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601210786-GCI | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
9542A_EB | Beluru Town | DU00006511578 | Sarawak | Sarawak | 3.976328 | 114.099708 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_9542A OPTION 01. New RTN910A(old type hardware version) in which having built in CSHR board(not CSHRF board) and with 4xGE electrical port availability.(1x for Sacofa LL and 3x for EB traffics) New CAT6 cables with suitable length x4. OPTION 02. Anyway, if no RTN910A(old type hardware version) but RTN910AF(new type hardware version) ONLY available in which having built in CSHRF board and with 2xGE electrical port and 2xGE optical port availability. Require below material. New CAT6 cables with suitable length x2. New Optical SFP Module 1.25G/1G 1310nm 10Km x4.(For IDU Huawei & ZTE BBU) New Optical Patchcord with suitable type and length x2. | IPRAN Port Upgrade | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(9245E, 9243E & 9091E) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** IDU-IPRAN Port re-engineering with new Sacofa LL(port info to be provided later by CD) Site Impacted : 9245E, 9243E & 9091E. OPTION 01 NE_9542A(4x Electrical port available in RTN910A) 1.Install new HW RTN910A(old type hardware version) in which having built in CSHR board and with 4xGE electrical port availability.(1x for Sacofa LL and 3x for EB traffics) 2.Enable port 8-EG6-1 and patching to new Sacofa LL(port info to be provided later by CD) using new CAT6 cable with suitable length. 3.Enable port 8-EG6-2 and patching to BBU 9245E(electrical port) using new CAT6 cable with suitable length. 4.Enable port 8-EG6-3 and patching to BBU 9243E(electrical port) using new CAT6 cable with suitable length. 5.Enable port 8-EG6-4 and patching to BBU 9091E(electrical port) using new CAT6 cable with suitable length. 6.Request new xD Vlan DCN & Vlan services. 7.Migrate EB traffics 9245E, 9243E & 9091E to new IBeam port at CP 9074A. OPTION 02 NE_9542A(2x Electrical port and 2x Optical port available in RTN910AF) 1.Install new HW RTN910A(new type hardware version) in which having built in CSHRF board and with 2xGE electrical port availability(1x for Sacofa LL and 1x for EB traffic 9245E) and with 2xGE optical port availability(1x 9243E and 1x 9091E ). 2.Enable port 8-EM6-1 and patching to new Sacofa LL(port info to be provided later by CD) using new CAT6 cable with suitable length. 3.Enable port 8-EM6-2 and patching to BBU 9245E(electrical port) using new CAT6 cable with suitable length. 4.Enable port 8-EM6-5 and patching to BBU 9243E. Insert both ports with Optical SFP Module 1.25G/1G 1310nm 10Km. 5.Enable port 8-EM6-6 and patching to BBU 9091E. Insert both ports with Optical SFP Module 1.25G/1G 1310nm 10Km. 6.Request new xD Vlan DCN & Vlan services. 7.Migrate EB traffics 9245E, 9243E & 9091E to new IBeam port at CP 9074A. | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(9245E, 9243E & 9091E) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** IDU-IPRAN Port re-engineering with new Sacofa LL(port info to be provided later by CD) Site Impacted : 9245E, 9243E & 9091E. OPTION 01 NE_9542A(4x Electrical port available in RTN910A) 1.Install new HW RTN910A(old type hardware version) in which having built in CSHR board and with 4xGE electrical port availability.(1x for Sacofa LL and 3x for EB traffics) 2.Enable port 8-EG6-1 and patching to new Sacofa LL(port info to be provided later by CD) using new CAT6 cable with suitable length. 3.Enable port 8-EG6-2 and patching to BBU 9245E(electrical port) using new CAT6 cable with suitable length. 4.Enable port 8-EG6-3 and patching to BBU 9243E(electrical port) using new CAT6 cable with suitable length. 5.Enable port 8-EG6-4 and patching to BBU 9091E(electrical port) using new CAT6 cable with suitable length. 6.Request new xD Vlan DCN & Vlan services. 7.Migrate EB traffics 9245E, 9243E & 9091E to new IBeam port at CP 9074A. OPTION 02 NE_9542A(2x Electrical port and 2x Optical port available in RTN910AF) 1.Install new HW RTN910A(new type hardware version) in which having built in CSHRF board and with 2xGE electrical port availability(1x for Sacofa LL and 1x for EB traffic 9245E) and with 2xGE optical port availability(1x 9243E and 1x 9091E ). 2.Enable port 8-EM6-1 and patching to new Sacofa LL(port info to be provided later by CD) using new CAT6 cable with suitable length. 3.Enable port 8-EM6-2 and patching to BBU 9245E(electrical port) using new CAT6 cable with suitable length. 4.Enable port 8-EM6-5 and patching to BBU 9243E. Insert both ports with Optical SFP Module 1.25G/1G 1310nm 10Km. 5.Enable port 8-EM6-6 and patching to BBU 9091E. Insert both ports with Optical SFP Module 1.25G/1G 1310nm 10Km. 6.Request new xD Vlan DCN & Vlan services. 7.Migrate EB traffics 9245E, 9243E & 9091E to new IBeam port at CP 9074A. | [6 empty] | Allstar | SQ202601280703-Allstar | Allstar | SQ202601280698-Allstar | 2026-03-02 | 2026-02-23 | Completed | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-09 | 2026-02-03 | 2026-02-03 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011544 |  | 2026-01-16 | 2026-01-17 | Completed | 2026-01-15 | 2026-01-16 | 2026-01-15 | 2026-01-17 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-17 | 2026-01-23 | 2026-02-13 | 2026-02-13 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-17 | 2026-01-23 | 2026-02-13 | 2026-02-13 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-21 | 2026-01-17 | 2026-01-23 | 2026-02-11 | 2026-02-11 | ROYSTON//AHHOLE/6000038561 | 2026-01-14: 2026-01-17; 2026-01-14: 2026-01-23; 2026-01-14: 2026-01-19; 2026-01-16: 2026-01-19 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202601210805-GTSB
4706D_AD | Residence TNB Habu | DU00006514799 | Northern | Pahang | 4.438741 | 101.389273 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC | - | MW Remote Upgrade | MW Remote Upgrade from 56MHz to 112MHz 512QAM | Set bandwidth to 112MHz and 512QAM | Set bandwidth to 112MHz and 512QAM | XMC-3 | 60/40 | 23G | 1.2 | 0.6 | In-House |  | In-House |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601210796-GTSB | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | LIM//WEI CHONG/6798000110
9646B_HU_1 | KG BATU DANAU LIMBANG | DU00006514800 | Sarawak | Sarawak | 4.653250 | 114.842690 | [9 empty] | TSS+AA+TI |  | 13G_4+0_28M NE_9646B 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D_Sub B_Lo x1. FE_9288A 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D_Sub B_Lo x1. | MW Parallel Link | Existing link 13G_2+0_28M. Install parallel link 13G_4+0_28M to become 13G_6+0_28M with EPLA 13G_2+0_28M under DU ID 9646B_HU ( DU Code : DU00006461307). Site Impacted : 9288R , 9287R , 9252Z , BBU E/// , SW03633. NE_9646B 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. (New RTN910A refer to DU ID 9646B_HU). 3.Install new XMC_5D_Sub B_Lo 4.Create service cross connect and EPLA. 5.Traffic migrate to new 13G_6+0_28M link. 6.No MW Decomm. FE_9288A 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. (New RTN910A refer to DU ID 9646B_HU). 3.Install new XMC_5D_Sub B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new 13G_6+0_28M link. 6. No MW Decomm. | Existing link 13G_2+0_28M. Install parallel link 13G_4+0_28M to become 13G_6+0_28M with EPLA 13G_2+0_28M under DU ID 9646B_HU ( DU Code : DU00006461307). Site Impacted : 9288R , 9287R , 9252Z , BBU E/// , SW03633. NE_9646B 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. (New RTN910A refer to DU ID 9646B_HU). 3.Install new XMC_5D_Sub B_Lo 4.Create service cross connect and EPLA. 5.Traffic migrate to new 13G_6+0_28M link. 6.No MW Decomm. | Existing link 13G_2+0_28M. Install parallel link 13G_4+0_28M to become 13G_6+0_28M with EPLA 13G_2+0_28M under DU ID 9646B_HU ( DU Code : DU00006461307). Site Impacted : 9288R , 9287R , 9252Z , BBU E/// , SW03633. FE_9288A 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. (New RTN910A refer to DU ID 9646B_HU). 3.Install new XMC_5D_Sub B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new 13G_6+0_28M link. 6. No MW Decomm. | XMC_5D | MDD | 13G | 1.2 | 1.2 | Trintel | SQ202601300958-Trintel |  |  |  |  | Ongoing | 2026-01-16 | 2026-01-31 | 2026-01-16 | 2026-01-23 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-18 | 2026-01-18 | 2026-01-18 |  | Fiona Wan Yen Chin7667000028 | Trintel TI | TRINTEL (M) SDN. BHD. |  | Assigned | Ongoing |  | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started |  | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | JERRY SONLEY SALI7667000071 | Trintel TI | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | JERRY SONLEY SALI7667000071 | Trintel TI | [7 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | JERRY SONLEY SALI7667000071 | 2026-01-14: 2026-01-15; 2026-01-14: 2026-01-15; 2026-01-14: 2026-01-15 | [7 empty] | GCI | SQ202601290571-GCI | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | CHEONG/SENG/WAH/7018000306
9347B | Sg Asap | DU00005073324 | Sarawak | Sarawak | 3.058021 | 113.923633 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1xCat6 cable | BBU Patching | Patch 9347B BBU to xD LL | Patch 9347B BBU to xD LL | [6 empty] | Magicell | SQ202503190735-Magicell | Magicell | SQ202504210228-Magicell // SQ202504260208-Magicell | 2025-04-25 | 2025-04-22 | Completed | 2025-03-07 | 2025-03-31 | 2025-03-10 | 2025-03-10 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-22 | 2025-04-25 | 2025-04-22 | 2025-04-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-22 | 2025-04-25 | 2025-04-22 | 2025-04-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25030333 |  | 2025-03-04 | 2025-03-04 | Completed | 2025-03-03 | 2025-03-04 | 2025-03-03 | 2025-03-04 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-07 | 2025-03-14 | 2025-03-07 | 2025-04-11 | WATSON ANAK MAMBA7018000213 | Magicell TI | 2025-03-07 | 2025-03-14 | 2025-03-07 | 2025-04-11 | WATSON ANAK MAMBA7018000213 | Magicell TI | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  | 2025-04-09 | 2025-03-07 | 2025-03-14 | 2025-03-07 | 2025-04-09 | WATSON ANAK MAMBA7018000213 | 2026-01-14: 2025-03-07; 2026-01-14: 2025-03-14; 2026-01-14: 2025-03-07; 2026-01-16: 2025-03-07 |  |  | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
Q00865-Q00254 | BKT SETIAM | DU00003202350 | Sarawak | Sarawak | 2.969012 | 112.929410 | 2023 | JAN 24 | WK17 | MAY 24 | Drop | Pass to Huawei |  | 03. TSS Only | 8/2/2024 : Need to re-survey. Information not complete | TSS |  | 8GHz_2.4m/2.4m_DP_2+0_29.65MHz | MW Parallel Link | [8 empty] | Datasco | SQ202402130365-Datasco | Datasco | No PR required-Work at TSS only |  |  | Ongoing | 2023-12-18 | 2023-12-20 | 2023-12-27 | 2023-12-27 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. |  | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | 1229 SA>> NE & FE TP Approved | [8 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7646C-7209A | DMart (REL) | DU00003282777 | Sabah | Sabah | 4.479854 | 118.610167 | WK05 | JAN 24 | WK16 | APR 24 | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | 22/4: D4: Cutover done 20/4: D4: Continue TI. Spillover 19/4: D3: Alignment WIP, continue 20/4 17/4: D2: TI done, pending alignment & cutover | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_MS_2+0_112MHz | MW Swap | [8 empty] | Seri Pancar | SQ202402130369-Seri Pancar | GTSB | SQ202409120182-GTSB | 2024-02-16 | 2024-02-15 | Completed | 2024-01-25 | 2024-01-31 | 2024-01-28 | 2024-01-28 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-15 | 2024-02-16 | 2024-02-15 | 2024-02-15 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240405C3 |  | 2024-04-06 | 2024-04-15 | Completed | 2024-04-05 | 2024-04-06 | 2024-04-05 | 2024-04-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-16 | 2024-04-30 | 2024-04-15 | 2024-04-22 | AHMAD//AL HADI BIN KARIMUN/6799000119 | GTSB TI | 2024-04-16 | 2024-04-30 | 2024-04-15 | 2024-04-30 | AHMAD//AL HADI BIN KARIMUN/6799000119 | GTSB TI | 2024-04-22 | 2024-04-23 | 2024-04-23 | 2024-04-23 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2024-04-16 | 2024-04-30 | 2024-04-15 | 2024-05-13 | AHMAD//AL HADI BIN KARIMUN/6799000119 | 2024-04-16 | 2024-04-30 | 2024-04-15 | 2024-04-18 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
3242D-4475A | Masjid Jamek Sultan Hisyamuddin | DU00003282778 | Central | Selangor | 3.770980 | 100.985374 | WK11 | MAR 24 |  | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_0.6/0.6_DP_2+0_112MHZ_SUB A | MW Swap | NE 1. INSTALL NEW IDU RTN 910A 2. INSTALL NEW 23G 0.6M MDD DP ANTENNA 3. INSTALL NEW 23G 112MHZ XMC-5D ODU SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. DISMANTLE EXISTING LINK FE 1. INSTALL NEW IDU RTN 910A 2. INSTALL NEW 23G 0.6M MDD DP ANTENNA 3. INSTALL NEW 23G 112MHZ XMC-5D ODU SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. DISMANTLE EXISTING LIN | [7 empty] | Nera | SQ202403260087-Nera | Nera | SQ202402270732-Nera | 2024-05-31 | 2024-05-27 | Completed | 2024-03-14 | 2024-03-21 | 2024-03-14 | 2024-03-15 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | NERA (MALAYSIA) SDN. BHD. |  | Assigned | Completed |  | 2024-03-14 | 2024-04-15 | 2024-05-13 | 2024-05-13 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | NERA (MALAYSIA) SDN. BHD. |  | Assigned | Completed |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-27 | 2024-05-31 | 2024-05-27 | 2024-05-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020323 |  | 2024-02-05 | 2024-03-05 | Completed | 2024-02-03 | 2024-02-05 | 2024-02-03 | 2024-03-05 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-14 | 2024-03-21 | 2024-03-14 | 2024-03-14 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | 2024-03-14 | 2024-03-21 | 2024-03-14 | 2024-03-14 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | 2024-03-14 | 2024-03-21 | 2024-03-14 | 2024-03-14 | RONALD SHAN A/L AMBUROSE6800000089 | Nera TI |  | 2024-03-14 | 2024-03-21 | 2024-03-05 | 2024-03-25 | AZIZAH//BINTI A.RAHMAN/7670000012 | 2024-03-14 | 2024-03-21 | 2024-03-05 | 2024-03-14 | 2024-10-11 | 2024-10-11 | 2024-10-11 | 2024-10-11 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4477A-4475A | Bagan Nakhoda Omar | DU00003282779 | Central | Selangor | 3.773655 | 100.884133 | WK10 | MAR 24 | WK10 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI | L1+ATP+PAC | 2X 13G_1.2/1.2 DP_2+0_28MHZ | MW Parallel Link | NE 1. INSTALL NEW RTN 910A + 2 UNIT ISM8 CARD 2. INSTALL 2X NEW 13G 1.2 MDD ANTENNA 3. INSTALL 2X NEW 13G XMC-5D ODU SUB BAND A & B 4. CONFIGURE LINK 2X 13G 2+0 28MHZ 5. EPLA BOTH 13G 2+0 LINK 6. MIGRATE 4477A BBU TO NEW RTN 910A FE 1. INSTALL NEW RTN 910A + 2 UNIT ISM8 CARD 2. INSTALL 2X NEW 13G 1.2 MDD ANTENNA 3. INSTALL 2X NEW 13G XMC-5D ODU SUB BAND A & B 4. CONFIGURE LINK 2X 13G 2+0 28MHZ 5. EPLA BOTH 13G 2+0 LINK 6. MIGRATE 4477A BBU TO NEW RTN 910A | [7 empty] | Nera | SQ202403120266-Nera | Nera | SQ202402270732-Nera | 2024-08-16 | 2024-08-15 | Completed | 2024-03-04 | 2024-03-06 | 2024-03-04 | 2024-03-05 | MOHD//KHALID IZHAR BIN SUBOH/7670000009 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-27 | 2024-03-28 | 2024-03-27 | 2024-03-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-27 | 2024-03-28 | 2024-03-27 | 2024-03-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-08-15 | 2024-08-16 | 2024-08-15 | 2024-08-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021902 |  | 2024-02-20 | 2024-03-05 | Completed | 2024-02-19 | 2024-02-20 | 2024-02-19 | 2024-03-05 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-04 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-07 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-11 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | 2026-01-14: 2024-03-04; 2026-01-14: 2024-03-31; 2026-01-14: 2024-03-04; 2026-01-16: 2024-03-06 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
7417B-7272A | Grand Merdeka IB | DU00003282780 | Sabah | Sabah | 6.061603 | 116.180509 | WK04 | JAN 24 | WK09 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_MS_1+0_112MHz | MW Swap | [8 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202403220526-NR Services | 2025-07-04 | 2025-06-30 | Completed | 2024-01-22 | 2024-01-22 | 2024-01-22 | 2024-01-22 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-01 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-01 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2025-06-30 | 2025-07-04 | 2025-06-30 | 2025-06-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240220AV |  | 2024-03-02 | 2024-03-01 | Completed | 2024-03-01 | 2024-03-02 | 2024-03-01 | 2024-03-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-29 | 2024-03-29 | 2024-02-28 | 2024-02-29 | RONNEY//LOUIS LUSIN/7167000022 | NR Service TI | 2024-02-29 | 2024-03-29 | 2024-02-28 | 2024-02-29 | RONNEY//LOUIS LUSIN/7167000022 | NR Service TI | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-29 | 2024-03-29 | 2024-02-28 | 2024-03-13 | RONNEY//LOUIS LUSIN/7167000022 | 2024-02-29 | 2024-03-29 | 2024-02-28 | 2024-02-29 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-03-19 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
1365B-1359A | Tmn Bukit Subang (REL) | DU00003282781 | Central | Selangor | 3.171290 | 101.507870 | WK09 | MAR 24 | WK09 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI | L1+ATP+PAC |  | MW Parallel Link | NE 1. INSTALL NEW RTN 910A + 1 UNIT ISM8 CARD 2. INSTALL NEW 18G 0.6MM MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB BAND A 4.CONFIGURE LINK 18G 2+0 112MHZ 5. SHIFT 2776B-1365B IF CABLE AND CONFIGURATION FROM RTN03 3-ISM8-1 TO NEW RTN910A 7-ISM8-1 FE 1.INSTALL NEW RTN 910A 2.INSTALL NEW 18G 0.6MM MDD ANTENNA 3.INSTALL NEW 18G XMC-5D SUB BAND A 4.CONFIGURE LINK 18G 2+0 112MHZ 5.PATCH NEW RTN 910A TO NEW CP PORT | [7 empty] | MTK | SQ202404020435-MTK | MTK | SQ202402190118-MTK | 2024-04-09 | 2024-04-16 | Completed | 2024-02-26 | 2024-03-31 | 2024-03-25 | 2024-03-25 | MOHD//GHADAFI BIN ISMAIL/8225000014 |  | MTK COMMUNICATION SDN. BHD. |  | Unassigned | Completed |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-04-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020134 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-04-25 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-02-26 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-02-29 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2026-01-14: 2024-02-24; 2026-01-14: 2024-02-29; 2026-01-14: 2024-02-24; 2026-01-16: 2024-02-29 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
3298A-1080A | pBTS Bandar Botanic (M) | DU00003282782 | Central | Selangor | 2.989340 | 101.425410 | WK08 | MAR 24 | WK08 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+AA+TI | L1+ATP+PAC | 23G_0.6m&0.6m_SP_1+0_112MHz | MW Parallel Link | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/20 NE 1- Install New IDU 910A. 2- Install New 1+0 ODU. 3- Install New 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- Patch 3298A BBU to new Parallel link. FE 1- Install New IDU 910A. 2- Install New 1+0 ODU. 3- Install New 0.6m Antenna . 4- Configure link 1+0_900M_512QAM_112MHz. 5- To provide new port at PTN. Required DCN VLAN | [7 empty] | MTK | SQ202407050120-MTK | MTK | SQ202402270725-MTK // SQ202409110359-MTK | 2024-05-06 | 2024-05-06 | Completed | 2024-02-19 | 2024-03-31 | 2024-04-16 | 2024-04-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | MTK COMMUNICATION SDN. BHD. |  | Assigned | Completed |  | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-02 | 2024-05-06 | 2024-05-02 | 2024-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24021426 |  | 2024-02-15 | 2024-02-19 | Completed | 2024-02-14 | 2024-02-15 | 2024-02-14 | 2024-02-19 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-22 | 2024-02-29 | 2024-02-22 | 2024-04-25 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2024-02-22 | 2024-02-29 | 2024-02-22 | 2024-02-29 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2024-02-24 | 2024-02-24 | 2024-02-24 | 2024-02-24 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI |  | 2024-02-22 | 2024-02-29 | 2024-02-22 | 2024-03-14 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | 2024-02-22 | 2024-02-29 | 2024-02-22 | 2024-03-14 | 2024-02-21 | 2024-06-30 |  |  | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
3297C-1110A | Sapura Kemuning (REL) | DU00003282783 | Central | Selangor | 3.003121 | 101.497873 | WK08 | FEB 24 | WK08 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | DCN VLAN : 414, PORT NUMBER : GigabitEthernet0/2/20 NE 1. Reuse Existing RTN910A (RTN01) 2. Reuse Existing ISM 6 Card at Slot 7 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub B) 4. Swap Existing SP Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHZ FE 1. Install New RTN910A 2. Dismantle 1 pcs of ISV 3 Card from RTN01 (RTN950) (Slot 4) 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub B) 4. Swap Existing SP Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHZ | [7 empty] | Allstar | SQ202402270775-Allstar | Allstar | SQ202402190097-Allstar // SQ202510070055-Allstar | 2024-05-28 | 2024-05-27 | Completed | 2024-02-19 | 2024-02-23 | 2024-02-19 | 2024-02-21 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-20 | 2024-03-21 | 2024-03-20 | 2024-03-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-27 | 2024-05-28 | 2024-05-27 | 2024-05-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020119 |  | 2024-02-02 | 2024-02-03 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-23 | ISTIKHAR//AHMAD/6798000193 | Allstar TI | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-29 | ISTIKHAR//AHMAD/6798000193 | Allstar TI | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-03-14 | ISTIKHAR//AHMAD/6798000193 | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-03-14 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
9716B-9385B | Masjid Darul Istiqomah | DU00003282784 | Sarawak | Sarawak | 2.244793 | 111.849390 | WK25 | JUN 24 |  |  |  | Pending DO | ZTE | 00. Integrated/RFS Done | 25/7: D2: Cutover done 24/7: MOS & TI In Plan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | NE: 1. Reuse Existing RTN910A (RTN01) 2. Reuse Existing ISM 8 Card at Slot 7 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub B) 4. Swap Existing SP Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHz FE: 1. Reuse Existing RTN910A (RTN01) 2. Reuse Existing ISM 8 Card at Slot 7 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub B) 4. Swap Existing SP Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHz | [7 empty] | Trintel | SQ202402130359-Trintel | Datasco | SQ202408140613-Datasco | 2024-03-08 | 2024-03-04 | Completed | 2024-01-25 | 2024-01-26 | 2024-01-28 | 2024-01-29 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-30 | 2024-01-31 | 2024-01-30 | 2024-01-30 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-30 | 2024-01-31 | 2024-01-30 | 2024-01-30 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-04 | 2024-03-08 | 2024-03-04 | 2024-03-04 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24070809 |  | 2024-07-09 | 2024-07-16 | Completed | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-07-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-07-24 | 2024-07-31 | 2024-08-01 | 2024-08-01 | Chiew Hua Kai7019000037 |  | 2024-07-24 | 2024-07-31 | 2024-08-01 | 2024-08-16 | Chiew Hua Kai7019000037 |  | 2024-07-25 | 2024-07-25 | 2024-08-14 | 2024-08-14 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-07-24 | 2024-07-31 | 2024-08-14 | 2024-08-14 | Chiew Hua Kai7019000037 | 2024-07-24 | 2024-07-31 | 2024-07-25 | 2024-07-25 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-08 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-09-26 | 2024-10-26 | 2024-09-26 | 2024-09-26 | ASTI//GANIS PUTRIANI/6237001358
1028C-1110A | Bukit Rimau | DU00003282785 | Central | Selangor | 2.994277 | 101.518909 | WK08 | MAR 24 | WK08 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 1+0 0.6m/0.6m 112MHz XMC-5D 256QAM | MW Swap | NE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M MDD ANTENNA 3. INSTALL NEW 23G XMC-5D SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. DISMANTLE EXISTING LINK FE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M MDD ANTENNA 3. INSTALL NEW 23G XMC-5D SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 5. DISMANTLE EXISTING LINK 6. PATCH NEW RTN 910A TO CP PORT | [7 empty] | MTK | SQ202407050120-MTK | MTK | SQ202402190118-MTK | 2024-10-19 | 2024-10-18 | Completed | 2024-02-19 | 2024-06-30 | 2024-04-22 | 2024-04-22 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | MTK COMMUNICATION SDN. BHD. |  | Assigned | Completed |  | 2024-10-16 | 2024-10-17 | 2024-10-16 | 2024-10-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-16 | 2024-10-17 | 2024-10-16 | 2024-10-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-18 | 2024-10-19 | 2024-10-18 | 2024-10-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020133 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-19 | 2024-02-26 | 2024-02-19 | 2024-02-19 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-02-19 | 2024-02-26 | 2024-02-20 | 2024-02-20 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-02-19 | 2024-02-26 | 2024-02-29 | 2024-02-29 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI |  | 2024-02-19 | 2024-02-26 | 2024-03-02 | 2024-03-02 | RIDHUAN//BIN MANSOR/8225000011 | 2024-02-19 | 2024-02-26 | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-03-31 | 2024-04-16 | 2024-04-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 | MTK TI | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7671B-7206A | Bandar Sri Indah | DU00003282786 | Sabah | Sabah | 4.267369 | 118.012702 | WK04 | JAN 24 | WK11 | MAR 24 | RFS | Pending L1 | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | [8 empty] | Seri Pancar | SQ202402130369-Seri Pancar | GTSB | SQ202403220520-GTSB | 2024-02-09 | 2024-02-07 | Completed | 2024-01-21 | 2024-01-21 | 2024-01-21 | 2024-01-21 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-01-25 | 2024-01-31 | 2024-01-25 | 2024-01-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-25 | 2024-01-31 | 2024-01-25 | 2024-01-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-07 | 2024-02-09 | 2024-02-07 | 2024-02-07 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24030470 |  | 2024-03-05 | 2024-03-05 | Completed | 2024-03-04 | 2024-03-05 | 2024-03-04 | 2024-03-05 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-11 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-11 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-18 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | 2024-03-08 | 2024-03-31 | 2024-03-08 | 2024-03-09 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-04-08 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
2674C-1087A | Kg Rantau Panjang | DU00003282787 | Central | Selangor | 3.058439 | 101.409700 | WK05 | JAN 24 | WK08 | FEB 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 23/3: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz_0.6m/0.6m_MDD_1+0_110MHz | MW Swap | NE 1. Reuse Existing RTN910A (RTN01) 2. Reuse Existing ISM 8 Card at Slot 7 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub A) 4. Swap Existing SP Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHz FE 1. Reuse Existing RTN910A (RTN05) 2. Reuse Existing ISM 8 Card at Slot 7 3. Swap Existing Huawei ODU with new XMC 5D 18GHz 1+0 110MHz ODU (Sub A) 4. Swap Existing SP Huawei Antenna with New Huawei 18GHz 0.6m DP MDD Antenna 5. Configure link as 18GHz 1+0 110MHz | [7 empty] | Nera | SQ202402140179-Nera | Nera | SQ202402190127-Nera | 2024-04-26 | 2024-04-29 | Completed | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | NUR//AFIQAH BINTI MOHD ROSDI/7670000015 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-31 | 2024-02-01 | 2024-02-08 | 2024-02-08 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2024-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020143 |  | 2024-02-02 | 2024-02-06 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  |  | Assigned | Completed |  | 2024-03-21 | 2024-03-31 | 2024-03-21 | 2024-03-21 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-03-21 | 2024-03-31 | 2024-02-21 | 2024-02-23 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | Nera TI | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | NUR//AFIQAH BINTI MOHD ROSDI/7670000015 |  |  | 2024-03-21 | 2024-03-31 | 2024-03-21 | 2024-03-27 | MOHD//SYAZWAN BIN MOHD YAZIZ/7670000011 | 2024-03-21 | 2024-03-31 | 2024-03-21 | 2024-03-25 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
4481A-4476B | Sek Agama Rakyat Nurul Sera Ma | DU00003282788 | Northern | Perak | 4.177783 | 100.652360 | WK05 | JAN 24 | WK08 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_1.2,1.2 DP_28MHz | MW Swap | NE 1- Install IDU 910A. 2- Install 4+0 ODU. 3- Swap 1.2m Antenna with new HW 1.2m Antenna. 4- Configure link 4+0_800M_256QAM FE 1- New IDU 910A. 2- Install 4+0 ODU and configure EPLA 3- Swap1.2m Antenna with new HW 1.2m Antenna. 4- Configure link 4+0_800M_256QAM. 5- To provide new port at PTN. Required DCN VLAN | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402160379-GCI // SQ202409100506-GCI | 2024-03-31 | 2024-03-27 | Completed | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-11 | 2024-02-29 | 2024-02-11 | 2024-02-23 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020351 |  | 2024-02-06 | 2024-02-13 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-02-22 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-02-23 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-03-05 | ANWAR//BIN ABDUL RASID/6800000149 | 2026-01-14: 2024-02-14; 2026-01-14: 2024-02-29; 2026-01-14: 2024-02-14; 2026-01-16: 2024-02-22 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
3041C-2631A | Idaman Sentosa (REL) | DU00003282789 | Central | Selangor | 3.012800 | 101.474952 | WK05 | JAN 24 | WK10 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz 2+0 0.6m/0.6m 112MHz XMC-5D 256QAM | MW Swap | NE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND B 4. CONFIGURE LINK 23G 2+0 112MHZ 5. DISMANTLE EXISTING LINK FE 1. INSTALL NEW RTN 910A 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 SUB BAND B 4. CONFIGURE LINK 23G 2+0 112MHZ 5. DISMANTLE EXISTING LINK 6. PATCH NEW RTN 910A TO CP PORT | [7 empty] | Nera | SQ202402140179-Nera | Nera | SQ202402270732-Nera // SQ202511180054-GTSB (Nera) | 2024-06-15 | 2024-06-14 | Completed | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | NUR//AFIQAH BINTI MOHD ROSDI/7670000015 |  | NERA (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-31 | 2024-02-01 | 2024-02-08 | 2024-02-08 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2024-03-05 | 2024-03-06 | 2024-03-05 | 2024-03-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-06-14 | 2024-06-15 | 2024-06-14 | 2024-06-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020321 |  | 2024-03-11 | 2024-03-04 | Completed | 2024-03-04 | 2024-03-11 | 2024-02-03 | 2024-03-04 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | NERA (MALAYSIA) SDN. BHD. |  | Assigned | Completed |  | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-04 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-07 | AZIZAH//BINTI A.RAHMAN/7670000012 | Nera TI | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | SengKee Seow10241846 |  |  | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-19 | AZIZAH//BINTI A.RAHMAN/7670000012 | 2024-03-04 | 2024-03-31 | 2024-03-04 | 2024-03-05 | 2024-10-24 | 2024-10-24 | 2024-10-24 | 2024-10-24 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7267C-7154A | UCA 2 | DU00003282790 | Sabah | Sabah | 6.038581 | 116.164819 | WK02 | JAN 24 | WK07 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_SP_1+0_112MHz | MW Hardware Upgrade | DCN VLAN : 415, PORT NUMBER : GigabitEthernet0/2/1 NE 1. Reuse Existing RTN910A 2. Configure link as 23GHz 1+0 112MHz FE 1. Install New RTN910A 2. Dismantle 1 pcs of ISV 3 Card from RTN01 (RTN950) 3. Configure link as 23GHz 1+0 112MH | [7 empty] | Magicell | SQ202402130373-Magicell | NR services | SQ202402210514-NR Services // SQ202409050206-NR Services | 2025-07-04 | 2025-06-30 | Completed | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. |  | Unassigned | Completed |  | 2024-01-22 | 2024-01-23 | 2024-01-22 | 2024-01-24 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-22 | 2024-01-26 | 2024-01-23 | 2024-01-23 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2025-06-30 | 2025-07-04 | 2025-06-30 | 2025-06-30 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021307 |  | 2024-02-14 | 2024-02-14 | Completed | 2024-02-13 | 2024-02-14 | 2024-02-13 | 2024-02-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-17 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-17 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-02-19 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-20 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2024-02-15 | 2024-02-29 | 2024-02-14 | 2024-02-17 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | tseping//wang/6819000006 | Logistic Team | 2024-09-25 | 2024-10-25 | 2024-09-25 | 2024-09-25 | ASTI//GANIS PUTRIANI/6237001358
3750A | UITM Kejuruteraan | DU00003282791 | Central | Selangor | 3.073530 | 101.499100 | WK06 | FEB 24 | WK06 | FEB 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+TI | L1+ATP+PAC |  | BBU Patching | [8 empty] | MTK | SQ202402140176-MTK | MTK | SQ202402190118-MTK | 2025-05-20 | 2025-05-19 | Completed | 2024-02-02 | 2024-02-02 | 2024-02-05 | 2024-02-05 | FIRDAUS//BIN TAJALDIN/6237000322 |  |  |  | Unassigned | Completed |  | 2025-05-08 | 2025-05-09 | 2025-05-08 | 2025-05-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-08 | 2025-05-09 | 2025-05-08 | 2025-05-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-19 | 2025-05-20 | 2025-05-19 | 2025-05-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24013156 |  | 2024-02-01 | 2024-02-01 | Completed | 2024-01-31 | 2024-02-01 | 2024-01-31 | 2024-02-01 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-03 | 2024-02-29 | 2024-02-03 | 2024-02-05 | MOHD//GHADAFI BIN ISMAIL/8225000014 | MTK TI | 2024-02-03 | 2024-02-29 | 2024-02-03 | 2024-02-05 | MOHD//GHADAFI BIN ISMAIL/8225000014 | MTK TI | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-05 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  |  | 2024-02-03 | 2024-02-29 | 2024-02-03 | 2024-02-07 | MOHD//GHADAFI BIN ISMAIL/8225000014 | 2026-01-14: 2024-02-03; 2026-01-14: 2024-02-29; 2026-01-14: 2024-02-03; 2026-01-16: 2024-02-05 |  |  | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050696-GCI | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
7025C-7093B | Jalan Puri Warisan | DU00003282792 | Sabah | Sabah | 6.016217 | 116.134750 | WK06 | FEB 24 | WK07 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW Hardware Upgrade | NE 1. Reuse Existing RTN910A 2. Swap Existing ODU with new XMC 3 23GHz 1+0 110MHz ODU (Sub A) 3. Configure link as 23GHz 1+0 112MHz FE 1. Reuse Existing RTN910A 2. Swap Existing ODU with new XMC 3 23GHz 1+0 110MHz ODU (Sub A) 3. Configure link as 23GHz 1+0 112MHz | [7 empty] | Seri Pancar | SQ202402130369-Seri Pancar | NR services | SQ202402210514-NR Services | 2024-09-20 | 2024-09-19 | Completed | 2024-02-01 | 2024-02-01 | 2024-02-03 | 2024-02-03 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-01 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-01 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24021303 |  | 2024-02-14 | 2024-02-14 | Completed | 2024-02-13 | 2024-02-14 | 2024-02-13 | 2024-02-14 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-02-16 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-02-15 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-02-16 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2024-02-14 | 2024-02-29 | 2024-02-14 | 2024-02-17 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | tseping//wang/6819000006 | Logistic Team | 2024-09-25 | 2024-10-25 | 2024-09-25 | 2024-09-25 | ASTI//GANIS PUTRIANI/6237001358
4125C-4480B | Bercham Flats | DU00003282793 | Northern | Perak | 4.638284 | 101.134164 | WK05 | JAN 24 | WK07 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_0.6,0.6 SP_110MHz | MW Swap | NE 1- Install IDU 910A. 2- Install 1+0 ODU. 3- Swap 0.6m Antenna with new HW 0.6m Antenna. 4- Configure link 1+0_889M_512QAM FE 1- New IDU 910A. 2- Install 1+0 ODU and configure EPLA with existing 1+0 ODU. 3- Swap 0.6m Antenna with new HW 0.6m Antenna. 4- Configure link 1+0_889M_512QAM. 5- To provide new port at PTN. Required DCN VLAN | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402160379-GCI | 2024-08-21 | 2024-08-21 | Completed | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-27 | 2024-03-27 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020352 |  | 2024-02-06 | 2024-02-13 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-02-16 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-02-21 | ANWAR//BIN ABDUL RASID/6800000149 | GCI TI | 2024-02-17 | 2024-02-17 | 2024-02-17 | 2024-02-17 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-02-22 | ANWAR//BIN ABDUL RASID/6800000149 | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-02-17 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
1964B-1156A | Kg Bt Badong | DU00003282794 | Central | Selangor | 3.345818 | 101.412113 | WK14 | APR 24 | WK13 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 5/4: D3: Cutover done 4/4: D2: Continue TI. Cutover in plan 2/4: EB CRQ approved | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1.2/0.6_DP_2+0_110MHZ | MW Swap | NE 1. INSTALL NEW IDU RTN 910A 2. INSTALL NEW 18G 1.2M MDD DP ANTENNA 3. INSTALL NEW 18G 110MHZ XMC-5D ODU SUB BAND B 4. CONFIGURE LINK 18G 2+0 110MHZ 5. DISMANTLE EXISTING LINK FE 1. INSTALL NEW IDU RTN 910A 2. INSTALL NEW 18G 0.6M MDD DP ANTENNA 3. INSTALL NEW 18G 110MHZ XMC-5D ODU SUB BAND B 4. CONFIGURE LINK 18G 2+0 110MHZ 5. DISMANTLE EXISTING LIN | [7 empty] | Allstar | SQ202404170262-Allstar | Allstar | SQ202402190097-Allstar // SQ202510070055-Allstar | 2024-05-17 | 2024-05-16 | Completed | 2024-02-26 | 2024-03-01 | 2024-03-02 | 2024-03-27 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-03-01 | 2024-03-31 | 2024-03-26 | 2024-03-26 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. |  | Unassigned | Completed |  | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  |  | Assigned | Completed |  | 2024-05-16 | 2024-05-17 | 2024-05-16 | 2024-05-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020118 |  | 2024-02-02 | 2024-02-03 | Completed | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-03 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-04-05 | 2024-04-30 | 2024-04-05 | 2024-04-18 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | Allstar TI | 2024-04-05 | 2024-04-30 | 2024-04-05 | 2024-05-08 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | Allstar TI | 2024-04-04 | 2024-04-04 | 2024-04-05 | 2024-04-05 | KII//YEE TERNG/6800000113 |  |  | 2024-04-05 | 2024-04-30 | 2024-04-05 | 2024-06-03 | MUHAMMAD//SYUQRI BIN MOHD YUSRI/6798000210 | 2024-04-05 | 2024-04-30 | 2024-04-05 | 2024-06-20 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | NG HONG JIE7018000036 | Logistic Team | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
7650B-7610A | USP PattonHill | DU00003282795 | Sabah | Sabah | 4.416867 | 117.871618 | WK04 | JAN 24 | WK09 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13GHz_1.2m/1.2m_MDD_2+0_28MHz | MW Parallel Link | [8 empty] | Seri Pancar | SQ202402130369-Seri Pancar | GTSB | SQ202409120182-GTSB (have dismantle) | 2024-02-02 | 2024-02-01 | Completed | 2024-01-24 | 2024-01-31 | 2024-01-24 | 2024-01-24 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-01-26 | 2024-01-31 | 2024-01-26 | 2024-01-26 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-26 | 2024-01-31 | 2024-01-26 | 2024-01-26 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-01 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240220AW |  | 2024-11-20 | 2024-11-20 | Completed | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-20 | NUR/WAFA/MIJONG/6871000001 |  | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-02-29 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-02-29 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | GTSB TI | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-05 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-03-03 | MOHD//ISWANSHAH BIN KAMARING/6799000135 | 2024-02-24 | 2024-02-29 | 2024-02-24 | 2024-02-28 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-04-08 | tseping//wang/6819000006 | Logistic Team | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
3656B-3723C | Taman Mulia | DU00003282796 | Central | Selangor | 3.008620 | 101.475084 |  | MAR 24 | WK10 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23GHz_0.6m/0.6m_MS_1+0_112MHz | MW Swap | NE 1. Reuse Existing RTN910A (RTN01) 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Swap Existing SM ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 4. Swap Existing SM Antenna with New Huawei 23GHz 0.6m DP MS Antenna 5. Configure link as 23GHz 1+0 112MHz 6. Dismantle Existing SM MW Link FE 1. Reuse Existing RTN910A (RTN01) 2. Install New 1 pcs of ISM 8 Card at Slot 3 3. Swap Existing SM ODU with new XMC 3 23GHz 1+0 112MHz ODU (Sub B) 4. Swap Existing SM Antenna with New Huawei 23GHz 0.6m DP MS Antenna 5. Configure link as 23GHz 1+0 112MHz 6. Dismantle Existing SM MW Link | [7 empty] | Perwira | SQ202407050123-Perwira | Perwira | SQ202409120151-Perwira | 2024-08-23 | 2024-08-22 | Completed | 2024-02-28 | 2024-02-28 | 2024-03-06 | 2024-03-06 | WB80041943 |  | PERWIRA ENERGY SDN. BHD. |  | Unassigned | Completed |  | 2024-07-16 | 2024-07-17 | 2024-07-16 | 2024-07-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-07-16 | 2024-07-17 | 2024-07-16 | 2024-07-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020322 |  | 2024-02-05 | 2024-03-05 | Completed | 2024-02-03 | 2024-02-05 | 2024-02-03 | 2024-03-05 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-07 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-04 | 2024-09-30 | 2024-03-06 |  | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-03-06 | 2024-03-31 | 2024-03-06 | 2024-03-11 | RIO//RINALDI BIN YUNDARI/7238000002 | 2026-01-14: 2024-03-06; 2026-01-14: 2024-03-31; 2026-01-14: 2024-03-06; 2026-01-16: 2024-03-11 |  |  | 2024-04-17 | 2024-04-30 | 2024-04-17 | 2024-04-17 | NURFIKA//BINTI IBRAHIM/6237001402
3258C_AD | Persiaran Hampshire Streetlight (REL) | DU00006151539 | Central | Kuala Lumpur | 3.161102 | 101.716518 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.3M MAC ANTENNA 1x ODU 23G XMC3 SUB B HI 1x ODU 23G XMC3 SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE 3258C-1029B WITH HUAWEI_23G_1+0_0.3M/0.3M_DP_112MHZ_512QAM_889MBPS_XMC3_SUB_B_0.3KM IMPACTED: 3258C DISMANTLE EXISTING LINK 3258C-1468B | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M MAC ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 3258C-1468B | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M MAC ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK 3258C-1468B | XMC3 | MAC | 23G | 0.3 | 0.3 | GTSB | SQ202511270680-GTSB // SQ202512160952-GTSB | GTSB | SQ202512010569-GTSB // SQ202512010581-GTSB | 2025-12-11 | 2025-12-10 | Completed | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-12-11 | 2025-11-27 | 2025-11-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251125BK |  | 2025-12-26 | 2025-11-27 | Completed | 2025-11-25 | 2025-12-26 | 2025-11-25 | 2025-11-27 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-12-22 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2025-11-27 | 2025-11-27 | 2025-11-27 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-29 | 2025-11-27 | 2025-11-27 | 2025-11-27 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2025-11-27 | 2025-11-27 | 2025-11-27 |  | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202510100626-GCI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | EZRIN TASNIM BIN ABDUL GANI6798000128
2601B_LOS | Jalan Jurunilai | DU00006152190 | Central | Selangor | 3.089719 | 101.563257 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_2601B 23G_SP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub B_Hi x1. FE_1432B. 23G_SP_0.6M(MAC) x1. RTN910Ax1. XMC_3E , Sub B_Lo x1. | MW New Link / Reroute | Link existing 2601B with 23G_1+0_56M reroute to new FE 1432B due to LOS Block. Link config 23G_1+0_112M with new FE routing. Site Impacted : 2601B. NE_2601B 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. (RTN no provide by OPS team). 3.Install new XMC_3E , Sub B_Hi. 4.Create cross connect and traffic migrate to new FE routing. 5.Decom existing MW link. FE_1432B. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub B_Lo. 4.Create service cross connect and New Inband DCN. 5.Traffic migrate to new link and new FE routing. 6.Decom existing SM link. | Link existing 2601B with 23G_1+0_56M reroute to new FE 1432B due to LOS Block. Link config 23G_1+0_112M with new FE routing. Site Impacted : 2601B. NE_2601B 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. (RTN no provide by OPS team). 3.Install new XMC_3E , Sub B_Hi. 4.Create cross connect and traffic migrate to new FE routing. 5.Decom existing MW link. | Link existing 2601B with 23G_1+0_56M reroute to new FE 1432B due to LOS Block. Link config 23G_1+0_112M with new FE routing. Site Impacted : 2601B. FE_1432B. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub B_Lo. 4.Create service cross connect and New Inband DCN. 5.Traffic migrate to new link and new FE routing. 6.Decom existing SM link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202510070040-GCI | MTK | SQ202510240588-MTK // SQ202510240598-MTK | 2025-11-11 | 2025-11-10 | Completed | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-29 | 2025-10-28 | 2025-10-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102320 |  | 2025-10-24 | 2025-10-25 | Completed | 2025-10-23 | 2025-10-24 | 2025-10-23 | 2025-10-25 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-28 | 2025-11-14 | 2025-10-29 | 2025-10-29 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-10-28 | 2025-11-14 | 2025-11-04 | 2025-12-20 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-29 | 2025-10-29 | 2025-11-14 | 2025-12-26 | 2025-12-26 | RIDHUAN//BIN MANSOR/8225000011 | 2026-01-14: 2025-10-13; 2026-01-14: 2025-10-20; 2026-01-14: 2025-10-13; 2026-01-16: 2025-10-13 |  |  | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202510100626-GCI | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | CHEONG/SENG/WAH/7018000306
3621A_LOS | Monfort Boys Town (REL) | DU00005499725 | Central | Selangor | 3.087488 | 101.554422 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M_512QAM NE_3621A New 23G_DP_0.6M(MAC)+OMT x1. New RTN910A x1. New XMC_3E, Sub B_Hi x1. FE_2061A New 23G_DP_0.6M(MAC)+OMT x1. New RTN910A x1. New XMC_3E, Sub B_Lo x1. New CAT6 Cable with suitable length x1. | MW New Link / Reroute | Link Existing HW MW 3621A-1704B, 18G_1+0_112M. Build new HW MW Link 3621A-2061A, 23G_1+0_112MHz_512QAM. Later, decom existing HW MW 3621A-1704B, 18G_1+0_112M. **IMPORTANT NOTE: WHEN PLAN DECOM EXISTING HW MW 3621A-1704B, 18G_1+0_112M, PLEASE ENSURE NLOS RTN510A(1704B-->1314H) IF EXIST(CURRENTLY LOSS COMM), NEED TO RECASCADING WITH PORT 8-EM6-2 OF RTN910A(RTN02) AT 1704B). LATER CAN DECOM RTN910A FOR MW LINK 1704B-->3621A). Site Impacted : 3621A. NE_3621A 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN02). 3.Install XMC_3E , Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of new RTN910A(RTN02). 6.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 7.Request new xD vlan services from ZTE IPRAN Team. 8.Migrate traffic to new MW Link. 9.Decom existing HW MW 3621A-1704B, 18G_1+0_112M. Ensure no other traffic before decom existing HW MW 3621A-1704B, 18G_1+0_112M. FE_2061A 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new 1x RTN910A(RTN02). 3.Install XMC_3E , Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of new RTN910A(RTN02). 6.Enable port 8-EM6-2 of existing RTN910(RTN01). 7.Cascading port 8-EM6-1 of new RTN910A(RTN02) to port 8-EM6-2 of existing RTN910(RTN01). Configure it. 8.Request new xD vlan services from ZTE IPRAN Team. 9.Migrate traffic 3621A to CP(1233B) same port at IBeam as 2061A. 10.Decom existing HW MW 3621A-1704B, 18G_1+0_112M. Ensure no other traffic before decom existing HW MW 3621A-1704B, 18G_1+0_112M. | Link Existing HW MW 3621A-1704B, 18G_1+0_112M. Build new HW MW Link 3621A-2061A, 23G_1+0_112MHz_512QAM. Later, decom existing HW MW 3621A-1704B, 18G_1+0_112M. **IMPORTANT NOTE: WHEN PLAN DECOM EXISTING HW MW 3621A-1704B, 18G_1+0_112M, PLEASE ENSURE NLOS RTN510A(1704B-->1314H) IF EXIST(CURRENTLY LOSS COMM), NEED TO RECASCADING WITH PORT 8-EM6-2 OF RTN910A(RTN02) AT 1704B). LATER CAN DECOM RTN910A FOR MW LINK 1704B-->3621A). Site Impacted : 3621A. NE_3621A 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910A(RTN02). 3.Install XMC_3E , Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of new RTN910A(RTN02). 6.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 7.Request new xD vlan services from ZTE IPRAN Team. 8.Migrate traffic to new MW Link. 9.Decom existing HW MW 3621A-1704B, 18G_1+0_112M. Ensure no other traffic before decom existing HW MW 3621A-1704B, 18G_1+0_112M. | Link Existing HW MW 3621A-1704B, 18G_1+0_112M. Build new HW MW Link 3621A-2061A, 23G_1+0_112MHz_512QAM. Later, decom existing HW MW 3621A-1704B, 18G_1+0_112M. **IMPORTANT NOTE: WHEN PLAN DECOM EXISTING HW MW 3621A-1704B, 18G_1+0_112M, PLEASE ENSURE NLOS RTN510A(1704B-->1314H) IF EXIST(CURRENTLY LOSS COMM), NEED TO RECASCADING WITH PORT 8-EM6-2 OF RTN910A(RTN02) AT 1704B). LATER CAN DECOM RTN910A FOR MW LINK 1704B-->3621A). Site Impacted : 3621A. FE_2061A 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new 1x RTN910A(RTN02). 3.Install XMC_3E , Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of new RTN910A(RTN02). 6.Enable port 8-EM6-2 of existing RTN910(RTN01). 7.Cascading port 8-EM6-1 of new RTN910A(RTN02) to port 8-EM6-2 of existing RTN910(RTN01). Configure it. 8.Request new xD vlan services from ZTE IPRAN Team. 9.Migrate traffic 3621A to CP(1233B) same port at IBeam as 2061A. 10.Decom existing HW MW 3621A-1704B, 18G_1+0_112M. Ensure no other traffic before decom existing HW MW 3621A-1704B, 18G_1+0_112M. | XMC_3E | MAC | 23G | 23G_DP_0.6M(MAC)+OMT x1. | 23G_DP_0.6M(MAC)+OMT x1. | GTSB | SQ202505140479-GTSB | GTSB | SQ202505210135-GTSB // SQ202505210139-GTSB | 2025-06-13 | 2025-06-13 | Completed | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-27 | 2025-06-10 | 2025-05-27 | 2025-05-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052160 |  | 2025-05-22 | 2025-05-28 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-08 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-08 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-28 | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-08 | Aminuddin bin che azibA0563734967123169280 | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-05-28 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050638-GCI | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
1600H_LOS | 99 Speedmart RANTAU PANJANG | DU00005499726 | Central | Selangor | 3.070619 | 101.412443 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS RTN510 NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Link reroute to new FE 1202B due to LOS Block. NLOS Radio RTN510 Site Impacted : 1600H. NE_1600H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio (1600H-NLOS-1780A). FE_1202B 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create Service cross connect. 5.GE port , patching the ETH cable to existing 1202B_RTN02 (ID : 32346) 6.Traffic migrate to new FE. 7.Decom existing NLOS Radio (1780A-NLOS-1600H). | Link reroute to new FE 1202B due to LOS Block. NLOS Radio RTN510 Site Impacted : 1600H. NE_1600H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio (1600H-NLOS-1780A). | Link reroute to new FE 1202B due to LOS Block. NLOS Radio RTN510 Site Impacted : 1600H. FE_1202B 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create Service cross connect. 5.GE port , patching the ETH cable to existing 1202B_RTN02 (ID : 32346) 6.Traffic migarte to new FE. 7.Decom existing NLOS Radio (1780A-NLOS-1600H). | [5 empty] | GTSB | SQ202505140479-GTSB | GTSB | SQ202505270151-GTSB // SQ202505270156-GTSB | 2025-07-05 | 2025-07-03 | Completed | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-04 | 2025-06-18 | 2025-06-04 | 2025-06-04 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052642 |  | 2025-05-27 | 2025-05-31 | Completed | 2025-05-26 | 2025-05-27 | 2025-05-26 | 2025-05-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-08 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-08 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-30 | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-07-02 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-05-29 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050638-GCI | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | CHEONG/SENG/WAH/7018000306
1477A_LOS | Safari Lagoon | DU00005499727 | Central | Selangor | 3.111510 | 101.743450 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_1477A. 23G_DP_0.6M(HS) x1.. RTN910A x1. XMC_3E , sub B_Hi x1. FE_B00482. 23G_DP_0.6M(HS) x1.. ISM8 x1. XMC_3E , Sub B_Lo x1. | MW New Link / Reroute | Link reroute to new FE B00482 due to LOS Block. 23G_2+0_112M Site Impacted 1447A , 2250A , 2876A , 1152C , 1393H. NE_1477A. 1.Install new 23G_DP_0.6M(HS). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , sub B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE routing. FE_B00482. 1.Install new 23G_DP_0.6M(HS). 2.Reuse existing B00482_RTN910A (ID : 14583) 3.Install new 3_ISM8-2+0 into existing B00482 RTN910A (ID : 14583). 4.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link and new FE routing. | Link reroute to new FE B00482 due to LOS Block. 23G_2+0_112M Site Impacted 1447A , 2250A , 2876A , 1152C , 1393H. NE_1477A. 1.Install new 23G_DP_0.6M(HS). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , sub B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE routing. | Link reroute to new FE B00482 due to LOS Block. 23G_2+0_112M Site Impacted 1447A , 2250A , 2876A , 1152C , 1393H. FE_B00482. 1.Install new 23G_DP_0.6M(HS). 2.Reuse existing B00482_RTN910A (ID : 14583) 3.Install new 3_ISM8-2+0 into existing B00482 RTN910A (ID : 14583). 4.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link and new FE routing. | XMC_3E | HS | 23G | 0.6 | 0.6 | GTSB | SQ202505140479-GTSB | GTSB | SQ202505270151-GTSB // SQ202505270156-GTSB | 2025-07-03 | 2025-07-02 | Completed | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-30 | 2025-06-13 | 2025-05-30 | 2025-05-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-02 | 2025-07-03 | 2025-07-02 | 2025-07-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052734 |  | 2025-05-28 | 2025-05-29 | Completed | 2025-05-27 | 2025-05-28 | 2025-05-27 | 2025-05-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-02 | 2025-06-30 | 2025-06-02 | 2025-06-04 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-06-02 | 2025-06-30 | 2025-06-02 | 2025-06-08 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-04 | 2025-06-02 | 2025-06-30 | 2025-06-02 | 2025-06-10 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2026-01-14: 2025-06-02; 2026-01-14: 2025-06-30; 2026-01-14: 2025-06-02; 2026-01-16: 2025-06-04 |  |  | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050638-GCI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | CHEONG/SENG/WAH/7018000306
4410K_HU_1 | K002A_K00168OD_BUKIT9 | DU00005509289 | Northern | Kedah | 5.586150 | 100.680948 |  |  |  |  | TI IN PLAN | ZTE |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M to become 13G_6+0_28M , with DU ID 4410K_HU the DU ID DU00005172955. NE_4410K. 13G_DP_1.2M(MDD) x1. RTN910A x1 XMC_5D , Sub B_Hi x1 FE_4986A. 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Hi x1. | MW Parallel Link | Existing link 15G_6+0_28M Install parallel link 13G_2+0_28M to become 13G_6+0_28M , with 13G_4+0_28M refer to DU ID 4410K_HU the DU ID DU00005172955. Site Impacted : 4410K , 4635A , 4622C. This parallel link install to support for 4635A - 4410K parallel link. NE_4410K. 1.Install new 13G_DP_1.2M(MDD). 2.Install RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install XMC_5D , Sub B_Hi for ant 1. 4.Create service cross connect , CA and EPLA for 6+0 link. 5.Enable GE1 , ETH Patching to 2nd new RTN910A_GE1. 6.No decom existing MW link. FE_4986A. 1.Install new 13G_DP_1.2M(MDD). 2.Install RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install XMC_5D , Sub B_Hi for ant 1. 4.Create service cross connect , CA and EPLA for 6+0 link. 5.Create New In Band DCN. 8.No decom existing MW link. | Existing link 15G_6+0_28M Install parallel link 13G_2+0_28M to become 13G_6+0_28M , with 13G_4+0_28M refer to DU ID 4410K_HU the DU ID DU00005172955. Site Impacted : 4410K , 4635A , 4622C. This parallel link install to support for 4635A - 4410K parallel link. NE_4410K. 1.Install new 13G_DP_1.2M(MDD). 2.Install RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install XMC_5D , Sub B_Hi for ant 1. 4.Create service cross connect , CA and EPLA for 6+0 link. 5.Enable GE1 , ETH Patching to 2nd new RTN910A_GE1. 6.No decom existing MW link. | Existing link 15G_6+0_28M Install parallel link 13G_2+0_28M to become 13G_6+0_28M , with 13G_4+0_28M refer to DU ID 4410K_HU the DU ID DU00005172955. Site Impacted : 4410K , 4635A , 4622C. This parallel link install to support for 4635A - 4410K parallel link. FE_4986A. 1.Install new 13G_DP_1.2M(MDD). 2.Install RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install XMC_5D , Sub B_Hi for ant 1. 4.Create service cross connect , CA and EPLA for 6+0 link. 5.Create New In Band DCN. 8.No decom existing MW link. | XMC_5D | MDD | 13G | 1.2 | 1.2 | CCSMY | SQ202507180614-CCS | CCSMY | SQ202505300205-CCS // SQ202505300210-CCS |  |  | Ongoing | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-24 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25051476 |  | 2025-05-15 | 2025-05-19 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-23 | 2025-07-23 | 2025-05-23 | 2025-05-23 | CHEN TAK//EOH YANG/7021000004 |  | 2025-05-23 | 2025-06-14 | 2025-05-23 | 2025-07-11 | CHEN TAK//EOH YANG/7021000004 |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2026-04-27 | 2026-04-30 | 2026-04-27 |  | MOHAMMAD FAIZ BIN AHMAD6000068531 | 2026-01-14: 2026-04-27; 2026-01-14: 2026-04-30; 2026-01-14: 2026-04-27; 2026-01-16: 2026-05-06 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505190519-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | CHEONG/SENG/WAH/7018000306
4304D_HU_1 | Tanjong Dawai(Maxis)(REL) | DU00005509290 | Northern | Kedah | 5.679330 | 100.369350 |  |  |  |  | Integrated/RFS | ZTE |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to DU Code DU00005172937. NE_4304D. 13G_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Lo x1. FE_4939A. 13G_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Hi x1. | MW Swap | Existing link 15G_4+0_28M. Swap existing 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to DU ID 4304D_HU (DU Code DU00005172937). Site Impacted : 4304D. NE_4304D. 1.Install new 13G_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0 (RTN no. provide by MSP team). 3.Install new XMC_5D , Sub B_Lo for ant 1. 4.Create service cross connect and EPLA for 6+0 link. 7.Traffic migrate to new MW link 13G_6+0_28M. 8.Decom existing IDU , ODU and Ant. FE_4939A. 1.Install new 13G_1.2M(MDD). 2.Install new RTN910A , 7_ISm8-2+0 (RTN no. provide by MSP team). 3.Install new XMC_5D , Sub B_Hi for ant 1. 4.Create service cross connect and EPLA for 6+0 link. 7.Create New In Band DCN. 8.Traffic migrate to new MW link 13G_6+0_28M. 9.Decom existing Ant , ODU and 3_ISM8. | Existing link 15G_4+0_28M. Swap existing 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to DU ID 4304D_HU (DU Code DU00005172937). Site Impacted : 4304D. NE_4304D. 1.Install new 13G_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0 (RTN no. provide by MSP team). 3.Install new XMC_5D , Sub B_Lo for ant 1. 4.Create service cross connect and EPLA for 6+0 link. 7.Traffic migrate to new MW link 13G_6+0_28M. 8.Decom existing IDU , ODU and Ant. FE_4939A. 1.Install new 13G_1.2M(MDD). 2.Install new RTN910A , 7_ISm8-2+0 (RTN no. provide by MSP team). 3.Install new XMC_5D , Sub B_Hi for ant 1. 4.Create service cross connect and EPLA for 6+0 link. 7.Create New In Band DCN. 8.Traffic migrate to new MW link 13G_6+0_28M. 9.Decom existing Ant , ODU and 3_ISM8. | Existing link 15G_4+0_28M. Swap existing 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to DU ID 4304D_HU (DU Code DU00005172937). Site Impacted : 4304D. NE_4304D. 1.Install new 13G_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0 (RTN no. provide by MSP team). 3.Install new XMC_5D , Sub B_Lo for ant 1. 4.Create service cross connect and EPLA for 6+0 link. 7.Traffic migrate to new MW link 13G_6+0_28M. 8.Decom existing IDU , ODU and Ant. FE_4939A. 1.Install new 13G_1.2M(MDD). 2.Install new RTN910A , 7_ISm8-2+0 (RTN no. provide by MSP team). 3.Install new XMC_5D , Sub B_Hi for ant 1. 4.Create service cross connect and EPLA for 6+0 link. 7.Create New In Band DCN. 8.Traffic migrate to new MW link 13G_6+0_28M. 9.Decom existing Ant , ODU and 3_ISM8. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202505240071-GCI | GCI | SQ202505190405-GCI // SQ202505190415-GCI // SQ202508200129-GCI | 2025-12-03 | 2025-12-03 | Completed | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051481 |  | 2025-05-15 | 2025-05-16 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-05-23 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-05-23 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-21 | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-06-03 | SAFUAN//BIN YUSOFF/6800000178 | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-05-19 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505190519-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | CHEONG/SENG/WAH/7018000306
4578C_HU_1 | Taman Sg Bakap | DU00005509291 | Northern | Penang | 5.237069 | 100.497144 | [7 empty] | 03. TSS Only | 24/9 transfer this to DU 4578C_AD as relocation. Material will DM to 4578C_AD. SOW Need to change to from MW SWAP to MW New Link Reroute | TSS |  | 15G_2+0_28M. NE_4578C 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1 FE_4188A 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing link 15G_4+0_28M. Install New link 15G_2+0_28M to become 15G_6+0_28M with 15G_4+0_28M refer to ( 4578C_HU , DU00005244067). Site Impacted : 4578C NE_4578C 1.Install 15G_DP_1.2M(MDD). 2.Install new RTN910A ,7_ISM8-2+0 (RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo for ant 1. 4.Create service cross connect and EPLA. 5.Migrate traffic to new 15G_6+0_28M. (15G_2+0 + 15G_4+0_CA). FE_4188A 1.Install 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0(RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Hi for ant 1. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.Traffic migrate to new 15G_6+0_28M.(15G_2+0 + 15G_4+0_CA). Current link required to reroute new FE_4234B/P00360 due to Old FE 4188A have space constraint issue. Redeploy equipment to new FE_4234B/P00360. NE_4578C 1.Install 15G_DP_1.2M(MDD). 2.Install new RTN910A ,7_ISM8-2+0 (RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo for ant 1. 4.Create service cross connect and EPLA. 5.Migrate traffic to new 15G_6+0_28M with EPLA 15G_4+0_CA. FE_4234B/P00360 1.Redeploy equipment 15G_2+0_28M link from FE 4188A to 4234B/P00360 2.Install 15G_DP_1.2M(MDD). 3.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by MSP team). 4.Install new XMC_5D , Sub A_Hi for ant 1. 5.Create service cross connect and EPLA. 6.Create New In Band DCN. 7.Enable GE1, ETH patching to Cisco Fiber port Gi 0/0/8. 8.Traffic migrate to new 15G_6+0_28M with EPLA 15G_4+0_CA. | Existing link 15G_4+0_28M. Install new link 15G_2+0_28M to become 15G_6+0_28M with 15G_4+0_28M refer to ( 4578C_HU , DU00005244067). Site Impacted : 4578C NE_4578C 1.Install 15G_DP_1.2M(MDD). 2.Install new RTN910A ,7_ISM8-2+0 (RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Migrate traffic to new 15G_6+0_28M with EPLA 15G_4+0_CA. | Existing link 15G_4+0_28M. Install new link 15G_2+0_28M to become 15G_6+0_28M with 15G_4+0_28M refer to ( 4578C_HU , DU00005244067). Site Impacted : 4578C FE_4188A 1.Install 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0(RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Hi for ant 1. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.Traffic migrate to new 15G_6+0_28M.(15G_2+0 + 15G_4+0_CA). Current link required to reroute new FE_4234B/P00360 due to Old FE 4188A have space constraint issue. Redeploy equipment to new FE_4234B/P00360. FE_4234B/P00360 1.Redeploy equipment 15G_2+0_28M link from FE 4188A to 4234B/P00360 2.Install 15G_DP_1.2M(MDD). 3.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by MSP team). 4.Install new XMC_5D , Sub A_Hi for ant 1. 5.Create service cross connect and EPLA. 6.Create New In Band DCN. 7.Enable GE1, ETH patching to Cisco Fiber port Gi 0/0/8. 8.Traffic migrate to new 15G_6+0_28M with EPLA 15G_4+0_CA. | XMC_5D | MDD | 15G | 1.2 | 1.2 | NWAVE | SQ202505240072-N-Wave | NWAVE | No PR required-Work at TSS only | 2025-12-03 | 2025-12-03 | Completed | 2025-05-20 | 2025-05-27 | 2025-05-20 | 2025-07-15 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-20 | 2025-05-27 | 2025-10-01 | 2025-10-01 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051491 |  | 2025-05-15 | 2025-05-17 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-20 | 2025-05-27 | 2025-05-20 | 2025-05-20 | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | 2025-05-20 | 2025-05-27 |  |  |  | NWAVE TI | [7 empty] | 2025-05-20 | 2025-05-27 | 2025-05-20 |  | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | 2025-05-20 | 2025-05-27 | 2025-05-20 |  | 2025-05-20 | 2025-05-27 | 2025-05-20 |  | MOHAMAD ZULKIFLI BIN ABDUL RAHIM6000021151 | NWAVE TI | [5 empty] | GCI | SQ202505190519-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | CHEONG/SENG/WAH/7018000306
K00421_HU_1 | WENG | DU00005509292 | Northern | Kedah | 5.836429 | 100.902311 | [7 empty] | 00. Integrated/RFS Done | 24/5 : CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_28M to become 15G_6+0_28M with 15G_4+0_28M refer to K00421_HU under DU code DU00005244078 NE_K00421. 15G_DP_1.2M(MDD). RTN910A x1. XMC_5D , Sub_B_Hi x1. FE_K00442 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Lo x1. | MW Swap | Existing link 13G_2+0_28M. Swap existing link to 15G_2+0_28M to become 15G_6+0_28M with EPLA 15G_4+0_28M refer to K00421_HU under DU Code DU00005244078 Site Impacted : K00421 , K00959 (EB). NE_K00421. 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub_B_Hi for ant 1. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 8.Decom existing SM MW link. Ensure all traffic migrated before decom. FE_K00442 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Lo for ant 1. 4.Create service cross connect and EPLA. 5.Create new In Band DCN. 6.Decom existing SM MW link. Ensure all traffic migrated before decom. | Existing link 13G_2+0_28M. Install parallel link 15G_2+0_28M Site Impacted : K00421 , K00959 (EB). NE_K00421. 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub_B_Hi for ant 1. 4.Create service cross connect and EPLA. 5.Enable GE1 , K00421_BBU traffic migrate to new parallel link 15G_6+0_28M. 8.No decom existing MW link due to support for K00959 (EB) site. | Existing link 13G_2+0_28M. Install parallel link 15G_2+0_28M Site Impacted : K00421 , K00959 (EB). FE_K00442 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Lo for ant 1. 4.Create service cross connect and EPLA. 5.Create new In Band DCN. 6.No decom existing MW link due to support for K00959 (EB) site. | XMC_5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202506050553-Magicell | Magicell | SQ202505240109-Magicell // SQ202505240110-Magicell // SQ202506030700-Magicell // SQ202506260731-Magicell // SQ202507300770-Magicell | 2025-12-10 | 2025-12-10 | Completed | 2025-06-03 | 2025-06-04 | 2025-06-03 | 2025-06-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051488 |  | 2025-05-15 | 2025-05-16 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-07-17 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | Magicell TI | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-07-17 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | Magicell TI | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-07-17 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-06-27 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | NG HONG JIE7018000036 | Logistic Team | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505190519-GCI | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | CHEONG/SENG/WAH/7018000306
A00508_HU | BKTCHAWI | DU00005509293 | Northern | Perak | 4.110511 | 100.960911 |  |  |  |  | TI IN PLAN | ZTE | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to A00508-A00458 (DU Code DU00003883707) NE_A00508 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. FE_A00458 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing link 13G_2+0_28M Install parallel link to 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to A00508-A00458 (DU Code DU00003883707). Site Impacted : A00508 , A00970. NE_A00508 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0 3.Install new XMC_5D , Sub A_Lo for ant 1. 4.Create service cross connect , CA and EPLA for 6+0 links. 5.Enable GE1 , A00508_BBU traffic migrate to new parallel link 13G_6+0_28M. 6.No decom existing SM link. FE_A00458 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi for ant 1 4.Create service cross connect , CA and EPLA for 6+0 links. 5.Traffic migrate to new 13G_6+0_28M. 6.Create new In band DCN. 7.No decom existing MW link. | Existing link 13G_2+0_28M Install parallel link to 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to A00508-A00458 (DU Code DU00003883707). Site Impacted : A00508 , A00970. NE_A00508 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0 3.Install new XMC_5D , Sub A_Lo for ant 1. 4.Create service cross connect , CA and EPLA for 6+0 links. 5.Enable GE1 , A00508_BBU traffic migrate to new parallel link 13G_6+0_28M. 6.No decom existing SM link. | Existing link 13G_2+0_28M Install parallel link to 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to A00508-A00458 (DU Code DU00003883707). Site Impacted : A00508 , A00970. FE_A00458 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Hi for ant 1 4.Create service cross connect , CA and EPLA for 6+0 links. 5.Traffic migrate to new 13G_6+0_28M. 6.Create new In band DCN. 7.No decom existing MW link. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GTSB | SQ202505290469-GTSB | GTSB | SQ202505290482-GTSB // SQ202505290490-GTSB | 2025-12-03 | 2025-12-03 | Completed | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051485 |  | 2025-05-15 | 2025-05-29 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-06-25 | FAZAL ABBAS6799000222 | GTSB TI | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-06-21 | FAZAL ABBAS6799000222 | GTSB TI | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-04 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-06-26 | FAZAL ABBAS6799000222 | 2025-05-21: 2025-05-30; 2025-05-21: 2025-05-30; 2025-05-21: 2025-05-30; 2025-06-27: 2025-05-31 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505190519-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | CHEONG/SENG/WAH/7018000306
4959A_HU_1 | Tunjang | DU00005509294 | Northern | Kedah | 6.283209 | 100.376308 | [6 empty] | ZTE | 00. Integrated/RFS Done | 15/07: CO Done | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to 4959A_HU (DU Code DU00005172959). NE_4959A 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. FE_4665A 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing link 15G_6+0_28M Install parallel link 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to 4959A_HU (DU Code DU00005172959). Site Impacted : 4959A , 4672B NE_4959A 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by MSP team). 3.Install XMC_5D , Sub A_Lo for ant 1. 4.Create service cross connect , CA and EPLA for new parallel link 13G_6+0_28M. 7.Enable GE1 , 4959A_BBU traffic migarte to new parallel link. 8.No decom existing 15G_6+0_28M link. FE_4665A 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide MSP team). 4.Install XMC_5D , Sub A_Hi for ant 1. 6.Create service cross connect , CA and EPLA for new parallel link 13G_6+0_28M. 7.Create new In Band DCN. 8.No decom existing 15G_6+0_28M link. | Existing link 15G_6+0_28M Install parallel link 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to 4959A_HU (DU Code DU00005172959). Site Impacted : 4959A , 4672B NE_4959A 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. (RTN no provide by MSP team). 3.Install XMC_5D , Sub A_Lo for ant 1. 4.Create service cross connect , CA and EPLA for new parallel link 13G_6+0_28M. 7.Enable GE1 , 4959A_BBU traffic migarte to new parallel link. 8.No decom existing 15G_6+0_28M link. | Existing link 15G_6+0_28M Install parallel link 13G_2+0_28M to become 13G_6+0_28M with 13G_4+0_28M refer to 4959A_HU (DU Code DU00005172959). Site Impacted : 4959A , 4672B FE_4665A 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide MSP team). 4.Install XMC_5D , Sub A_Hi for ant 1. 6.Create service cross connect , CA and EPLA for new parallel link 13G_6+0_28M. 7.Create new In Band DCN. 8.No decom existing 15G_6+0_28M link. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202507180621-GCI | GCI | SQ202505240106-GCI // SQ202505240107-GCI | 2025-12-03 | 2025-12-03 | Completed | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051482 |  | 2025-05-15 | 2025-05-16 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-27 | 2025-05-31 | 2025-05-27 | 2025-07-21 | MUHAMMAD IRFAN BIN SAHARRIZA6800000201 | GCI TI | 2025-05-27 | 2025-05-31 | 2025-05-27 | 2025-07-21 | MUHAMMAD IRFAN BIN SAHARRIZA6800000201 | GCI TI | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-15 | 2025-05-27 | 2025-05-31 | 2025-05-27 | 2026-04-01 | MUHAMMAD IRFAN BIN SAHARRIZA6800000201 | 2025-05-21: 2025-05-27; 2025-05-21: 2025-05-31; 2025-05-21: 2025-05-27; 2025-06-27: 2025-07-15 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505190519-GCI | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | CHEONG/SENG/WAH/7018000306
1415H_1_AD | 99 Speedmart JLN CHERAS | DU00005327920 | Central | Kuala Lumpur | 3.129380 | 101.720215 |  | APR 25 |  | APR 25 | DO | Doable, just waiting material | ZTE | 00. Integrated/RFS Done | 21/4/2025 : Digi OB - Small Cell - NE site 1415H 99 Speedmart JLN CHERAS, Digi OB - 3M Boom - RT - FE site 1063B BERJAYA TIME SQUARE | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | New NLOS RTN510 equipment NE_1415H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_1063B 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH cable / LAN Cable. | MW New Link / Reroute | Link reroute to new FE W00201 with new NLOS RTN510 equipment due to LOS block. NE_1415H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. FE_1063B 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.ETH cable patching to existing Fiber_Ibeam. 6.Decom existing NLOS Radio | Link reroute to new FE W00201 with new NLOS RTN510 equipment due to LOS block. NE_1415H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio. | Link reroute to new FE W00201 with new NLOS RTN510 equipment due to LOS block. FE_1063B 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.ETH cable patching to existing Fiber_Ibeam. 6.Decom existing NLOS Radio | [5 empty] | Magicell | SQ202504240460-Magicell | Magicell | SQ202504240449-Magicell // SQ202504240452-Magicell | 2025-05-23 | 2025-05-22 | Completed | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-27 | 2025-04-27 | 2025-04-27 | 2025-04-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-22 | 2025-05-23 | 2025-05-22 | 2025-05-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25042201 |  | 2025-04-23 | 2025-04-23 | Completed | 2025-04-22 | 2025-04-23 | 2025-04-22 | 2025-04-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-05-08 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-05-08 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-01 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-07-03 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-05-07 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | CHEONG/SENG/WAH/7018000306
7365B_HU_2 | Richard Lind Tower SBC | DU00005692775 | Sabah | Sabah | 5.341290 | 118.482297 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW Swap | To replace existing antenna as part of troubleshooting. No DO required, has been take under 7365B_HU_1 | To replace existing antenna as part of troubleshooting. No DO required, has been take under 7365B_HU_1 | To replace existing antenna as part of troubleshooting. No DO required, has been take under 7365B_HU_1 | [5 empty] | NR services | SQ202510010672-NR Services | NR services | SQ202507030721-NR Services // SQ202507030731-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Disabled | 2025-06-20 | 2025-07-20 | 2025-06-20 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. |  | Assigned | Disabled |  | 2025-06-20 | 2025-07-20 | 2025-06-20 |  | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-06-20 | 2025-07-20 | 2025-06-20 | 2025-09-03 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | NR Service TI | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-29 | 2025-06-20 | 2025-07-20 | 2025-06-20 | 2025-09-16 | AG//FIKRI IZUDDIN BIN MURJIM/7167000008 | 2025-04-24: 2025-06-20; 2025-04-24: 2025-07-20; 2025-04-24: 2025-06-20; 2025-05-07: 2025-06-25 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | HSU//MYET CHAE/6799000011
4662B_HU | Padang Terap | DU00006593426 | Northern | Kedah | 6.320690 | 100.665110 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | Perform upgrade 15G_3+0_28MHZ_256QAM_EPLA to 15G_6+0_28MHZ_256QAM_CA. NE_4662B Re-use existing 15G_1.2M(MDD)+Dual Coupler x1. Re-use existing RTN910AF(RTN04, NEID 9-38762). Re-use existing 15G ODU XMC-5D Pro(Sub Band A 23-MODU). New ISM8 x1.(for slot 4) Re-use existing IF cable(Re-arrange IF between ISM8 slot 7, slot 3 & slot 4) FE_4999A Re-use existing 15G_1.2M(MDD)+Dual Coupler x1. Re-use existing RTN910AF(RTN04, NEID 9-38762). Re-use existing 15G ODU XMC-5D Pro(Sub Band A 23-MODU). New ISM8 x1.(for slot 4) Re-use existing IF cable(Re-arrange IF between ISM8 slot 7, slot 3 & slot 4) New CAT6 cable x1. | MW Hardware Upgrade | Perform upgrade 15G_3+0_28MHZ_256QAM_EPLA to 15G_6+0_28MHZ_256QAM_CA. Site Impacted : 4662B. NE_4662B 1.Re-use existing 15G_DP_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN04, NEID 9-38762) and insert new ISM8 into slot 04. 3.Re-arrange INDOOR existing IF cables currently terminated at ISM8 slot 07 Port 1 & 2 and ISM8 slot 03 Port 1 as below: -Shifting existing IF cable at ISM8 slot 07 Port 1 to ISM8 slot 03 Port 1. -Shifting existing IF cable at ISM8 slot 07 Port 2 to ISM8 slot 04 Port 1. -Shifting existing IF cable at ISM8 slot 03 Port 1 to ISM8 slot 07 Port 1. 4.Re-config at slot 07 Port 1 as 15G_2+0_28MHZ_256QAM_CA. 5.Re-config at slot 03 Port 1 and slot 04 Port 1 as 15G_4+0_28MHZ_256QAM_CA. 6.Later combine all 3x 15G_2+0_28MHZ_256QAM_CA become 15G_6+0_28MHZ_256QAM_CA. 7.Re-use existing Vlan DCN and Vlan Services. 8.Migrate traffic 4662B into new HW MW Link 15G_6+0_28MHZ_256QAM_CA. FE_4999A 1.Re-use existing 15G_DP_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN11, NEID 9-38763) and insert new ISM8 into slot 04. 3.Re-arrange INDOOR existing IF cables currently terminated at ISM8 slot 07 Port 1 & 2 and ISM8 slot 03 Port 1 as below: -Shifting existing IF cable at ISM8 slot 07 Port 1 to ISM8 slot 03 Port 1. -Shifting existing IF cable at ISM8 slot 07 Port 2 to ISM8 slot 04 Port 1. -Shifting existing IF cable at ISM8 slot 03 Port 1 to ISM8 slot 07 Port 1. 4.Re-config at slot 07 Port 1 as 15G_2+0_28MHZ_256QAM_CA. 5.Re-config at slot 03 Port 1 and slot 04 Port 1 as 15G_4+0_28MHZ_256QAM_CA. 6.Later combine all 3x 15G_2+0_28MHZ_256QAM_CA become 15G_6+0_28MHZ_256QAM_CA. 7.Re-use existing Vlan DCN and Vlan Services. 8.Request new port 1G(electrical) at IBeam. 9.Enable port 8-EM6-2 of existing RTN910AF(RTN11, NEID 9-38763). 10.Patching new CAT6 cable in between new port 1G(electrical) at IBeam and new port 8-EM6-2 of existing RTN910AF(RTN11, NEID 9-38763). 11.Perform LAG at 2x port(existing and new) at RTN910AF(RTN11, NEID 9-38763) and IBeam. 12.Migrate traffic 4662B into 2x LAG at IBeam. | Perform upgrade 15G_3+0_28MHZ_256QAM_EPLA to 15G_6+0_28MHZ_256QAM_CA. Site Impacted : 4662B. NE_4662B 1.Re-use existing 15G_DP_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN04, NEID 9-38762) and insert new ISM8 into slot 04. 3.Re-arrange INDOOR existing IF cables currently terminated at ISM8 slot 07 Port 1 & 2 and ISM8 slot 03 Port 1 as below: -Shifting existing IF cable at ISM8 slot 07 Port 1 to ISM8 slot 03 Port 1. -Shifting existing IF cable at ISM8 slot 07 Port 2 to ISM8 slot 04 Port 1. -Shifting existing IF cable at ISM8 slot 03 Port 1 to ISM8 slot 07 Port 1. 4.Re-config at slot 07 Port 1 as 15G_2+0_28MHZ_256QAM_CA. 5.Re-config at slot 03 Port 1 and slot 04 Port 1 as 15G_4+0_28MHZ_256QAM_CA. 6.Later combine all 3x 15G_2+0_28MHZ_256QAM_CA become 15G_6+0_28MHZ_256QAM_CA. 7.Re-use existing Vlan DCN and Vlan Services. 8.Migrate traffic 4662B into new HW MW Link 15G_6+0_28MHZ_256QAM_CA. | Perform upgrade 15G_3+0_28MHZ_256QAM_EPLA to 15G_6+0_28MHZ_256QAM_CA. Site Impacted : 4662B. FE_4999A 1.Re-use existing 15G_DP_1.2M(MDD)+Dual Coupler. 2.Re-use existing RTN910AF(RTN11, NEID 9-38763) and insert new ISM8 into slot 04. 3.Re-arrange INDOOR existing IF cables currently terminated at ISM8 slot 07 Port 1 & 2 and ISM8 slot 03 Port 1 as below: -Shifting existing IF cable at ISM8 slot 07 Port 1 to ISM8 slot 03 Port 1. -Shifting existing IF cable at ISM8 slot 07 Port 2 to ISM8 slot 04 Port 1. -Shifting existing IF cable at ISM8 slot 03 Port 1 to ISM8 slot 07 Port 1. 4.Re-config at slot 07 Port 1 as 15G_2+0_28MHZ_256QAM_CA. 5.Re-config at slot 03 Port 1 and slot 04 Port 1 as 15G_4+0_28MHZ_256QAM_CA. 6.Later combine all 3x 15G_2+0_28MHZ_256QAM_CA become 15G_6+0_28MHZ_256QAM_CA. 7.Re-use existing Vlan DCN and Vlan Services. 8.Request new port 1G(electrical) at IBeam. 9.Enable port 8-EM6-2 of existing RTN910AF(RTN11, NEID 9-38763). 10.Patching new CAT6 cable in between new port 1G(electrical) at IBeam and new port 8-EM6-2 of existing RTN910AF(RTN11, NEID 9-38763). 11.Perform LAG at 2x port(existing and new) at RTN910AF(RTN11, NEID 9-38763) and IBeam. 12.Migrate traffic 4662B into 2x LAG at IBeam. |  |  | 15G |  |  | GTSB | SQ202602230050-GTSB | GTSB | SQ202602230039-GTSB // SQ202602230045-GTSB |  |  | Ongoing | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022317 |  | 2026-02-24 | 2026-02-28 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-04 | 2026-03-31 | 2026-03-04 | 2026-03-05 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-03-04 | 2026-03-31 | 2026-03-04 | 2026-03-05 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-11 | 2026-03-04 | 2026-03-31 | 2026-03-04 | 2026-03-18 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-04-24: 2026-03-04; 2025-04-24: 2026-03-31; 2025-04-24: 2026-03-04; 2025-05-07: 2026-03-05 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202602120266-GTSB
4183D_HU | JalanSungai Pinang Balik Pulau | DU00006593427 | Northern | Penang | 5.360670 | 100.223260 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_55M_512QAM_EPLA NE_4183D New 18G_0.6M(MDD)x1. New RTN910AF(RTN02). New XMC_5D Pro, Sub A_Hi x1. New CAT6 cable x1. FE_4034A New 18G_0.6M(MDD)x1. Re-use existing RTN910AF(RTN08, NEID 9-30634). New XMC_5D Pro, Sub A_Lo x1. | MW Swap | Existing HW MW Link 4183D-4034A, 18G_1+0_55MHZ_512QAM. MW Swap HW MW Link 4183D-4034A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link 4183D-4034A, 18G_1+0_55MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN08, NEID 9-30634) at 4034A. Site Impacted : 4183D. NE_4183D. 1.Install new 18G_0.6M(MDD)x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Build new HW MW Link 4183D-4034A, 18G_2+0_55MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffics 4183D via new HW MW Link 4183D-4034A, 18G_2+0_55MHZ_512QAM_EPLA. 7.Later, decom existing HW MW Link 4183D-4034A, 18G_1+0_55MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN08, NEID 9-30634) at 4034A. FE_4034A. 1.Install new 18G_0.6M(MDD)x1. 2.Re-use existing RTN910AF(RTN08, NEID 9-30634). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Build new HW MW Link 4183D-4034A, 18G_2+0_55MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Re-use existing IBeam port. 7.Migrate traffics 4183D via existing port at IBeam(CP 4034A). 8.Later, decom existing HW MW Link 4183D-4034A, 18G_1+0_55MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN08, NEID 9-30634) at 4034A. | Existing HW MW Link 4183D-4034A, 18G_1+0_55MHZ_512QAM. MW Swap HW MW Link 4183D-4034A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link 4183D-4034A, 18G_1+0_55MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN08, NEID 9-30634) at 4034A. Site Impacted : 4183D. NE_4183D. 1.Install new 18G_0.6M(MDD)x1. 2.Install new RTN910AF(RTN02). 3.Install new XMC_5D Pro, Sub A_Hi x1. Configure it. 4.Build new HW MW Link 4183D-4034A, 18G_2+0_55MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Migrate traffics 4183D via new HW MW Link 4183D-4034A, 18G_2+0_55MHZ_512QAM_EPLA. 7.Later, decom existing HW MW Link 4183D-4034A, 18G_1+0_55MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN08, NEID 9-30634) at 4034A. | Existing HW MW Link 4183D-4034A, 18G_1+0_55MHZ_512QAM. MW Swap HW MW Link 4183D-4034A, 18G_2+0_55MHZ_512QAM_EPLA. Later, decom existing HW MW Link 4183D-4034A, 18G_1+0_55MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN08, NEID 9-30634) at 4034A. Site Impacted : 4183D. FE_4034A. 1.Install new 18G_0.6M(MDD)x1. 2.Re-use existing RTN910AF(RTN08, NEID 9-30634). 3.Install new XMC_5D Pro, Sub A_Lo x1. Configure it. 4.Build new HW MW Link 4183D-4034A, 18G_2+0_55MHZ_512QAM_EPLA. 5.Re-use existing xD Vlan DCN and Vlan Services. 6.Re-use existing IBeam port. 7.Migrate traffics 4183D via existing port at IBeam(CP 4034A). 8.Later, decom existing HW MW Link 4183D-4034A, 18G_1+0_55MHZ_512QAM. Anyway, do not decom existing RTN910AF(RTN08, NEID 9-30634) at 4034A. | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD)x1 | 18G_0.6M(MDD)x1 | GTSB | SQ202602250576-GTSB | GTSB | SQ202602250458-GTSB // SQ202602250535-GTSB |  |  | Ongoing | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-17 | 2026-03-28 | 2026-03-17 | 2026-03-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-11 | 2026-05-04 | 2026-05-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022342 |  | 2026-02-24 | 2026-02-26 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-04 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-05 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-05 | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-11 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-04 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202602120266-GTSB
9000B24_EVT | PBTS KATIAU REL | DU00006593428 | Sabah | Sabah | 5.873230 | 116.059500 | [13 empty] | Planning and integration support only for event site 9000B24_EVT PBTS KATIAU REL Tx route: 9000B24/9000B24-7640A-LL-7000A 1) Share port with 7640A at 7000A 2) New NE ID NE IDU 9000B24 RTN01 3) At far end to install MW link at existing 7640A-KGTOMBOVO-RTN03 7-ISM8-1 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [42 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 |  | CHEONG/SENG/WAH/7018000306
1009C_HU | Kampung TelokGong | DU00006593429 | Central | Selangor | 2.929200 | 101.369800 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M. NE_1009C. 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D Pro , Sub A_Hi x1. FE_1082A. 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D Pro , Sub A_Lo x1. | MW Parallel Link | Existing link 18G_1+0_112M. Install parallel link 13G_4+0_28M. Site impcated : 3087B , 1009C NE_1009C. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 1009C_RTN01.Transfer IF from 3_ISM8-1+0 port 1 to 7_ISM8-1+0 port 2. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 1009C_RTN01. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA with existing MW link. 6.Traffic migrate to new parallel link. 7.No decomm existing MW. FE_1082A. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 1082A_RTN05. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 1082A_RTN05. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA with existing MW link. 6.Traffic migrate to new parallel link. 7.No decomm existing MW. | Existing link 18G_1+0_112M. Install parallel link 13G_4+0_28M. Site impcated : 3087B , 1009C NE_1009C. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 1009C_RTN01.Transfer IF from 3_ISM8-1+0 port 1 to 7_ISM8-1+0 port 2. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 1009C_RTN01. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA with existing MW link. 6.Traffic migrate to new parallel link. 7.No decomm existing MW. | Existing link 18G_1+0_112M. Install parallel link 13G_4+0_28M. Site impcated : 3087B , 1009C FE_1082A. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 1082A_RTN05. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 1082A_RTN05. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA with existing MW link. 6.Traffic migrate to new parallel link. 7.No decomm existing MW. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GTSB | SQ202602230036-GTSB | GTSB | SQ202602230027-GTSB // SQ202602230033-GTSB | 2026-04-29 | 2026-04-22 | Completed | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-15 | 2026-04-29 | 2026-04-15 | 2026-04-15 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022712 |  | 2026-02-28 | 2026-03-09 | Completed | 2026-02-27 | 2026-02-28 | 2026-02-27 | 2026-03-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-11 | 2026-03-31 | 2026-03-11 | 2026-04-17 | SYLVESTER JULUS6000068068 | GTSB TI | 2026-03-11 | 2026-03-31 | 2026-03-11 | 2026-04-17 | SYLVESTER JULUS6000068068 | GTSB TI | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-16 | 2026-03-11 | 2026-03-31 | 2026-03-11 | 2026-04-20 | SYLVESTER JULUS6000068068 | 2025-04-24: 2026-03-11; 2025-04-24: 2026-03-31; 2025-04-24: 2026-03-11; 2025-05-07: 2026-03-12 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602120113-GCI | 2026-02-11 | 2026-02-11 | 2026-02-04 | 2026-02-04 | CHEONG/SENG/WAH/7018000306
7281B_HU | UCA2 | DU00006593430 | Sabah | Sabah | 6.045522 | 116.164833 | [7 empty] | 05. Doable |  | TSS+AA+TI+Dismantle |  | 23G_2+0_112M_512QAM_EPLA. NE_7281B New 23G_DP_0.6M(MAC)+OMT x1. Re-use existing RTN910A(RTN02, NEID 9-43217). New IF cables with suitable length and type x2 RUN. New XMC_3E, Sub B_Hi x2. FE_7154A New 23G_DP_0.6M(MAC)+OMT x1. Re-use existing RTN910AF(RTN06, NEID 9-43984). New IF cables with suitable length and type x2 RUN. New XMC_3E, Sub B_Lo x2. New CAT6 cable x1. | MW Swap | [8 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042874 |  | 2026-04-30 |  | Ongoing | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202602120275-GTSB
7113D_HU | kglingkudau belangingi | DU00006593431 | Sabah | Sabah | 5.329386 | 116.162676 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 18G_1+0_56M Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M. Site Impacted : 7113D | Existing link 18G_1+0_56M Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M. Site Impacted : 7113D | Existing link 18G_1+0_56M Remote Software Upgrade from 18G_1+0_56M to 18G_1+0_112M. Site Impacted : 7113D | XMC_5D | MDD | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202602120118-GCI | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | CHEONG/SENG/WAH/7018000306
7312B_HU | TanjungBatu Laut | DU00006593432 | Sabah | Sabah | 4.260700 | 117.876800 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI+Dismantle |  | 2X RTN910A 1X 23G 0.3M DP ANTENNA 1X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3 SUB B HI 1x ODU 23G XMC3 SUB B LO | MW Swap | MW SWAP LINK 7312B-7197A WITH HUAWEI_23G_1+0_0.3M/0.6M_DP_112MHZ_S56QAM_778MBPS_XMC3_SUB_B_LINK_0.80KM IMPACTED: 7312B DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | XMC3 | MAC | 23G | 0.3 | 0.6 | GTSB |  | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042867 |  | 2026-04-30 |  | Ongoing | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202602120118-GCI | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
1240A-1122A | Bkt Baja (Celcom) | DU00004410976 | Central | Selangor | 2.906040 | 101.615480 | WK03 | JAN 25 | WK03 | JAN 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 15/1/2025 : Cutover done 14/1/2025 : Installation complete, alignment WIP | TSS+AA+TI | L1+ATP+PAC | 1240A-1122A (New parallel link for 13G_4+0_28M_CA). NE_1240A 13G_DP_1.8m(MDD) x1. 13G_XMC_5D , Sub_B_Hi x1. ISM8 x2. FE_1122A. 13G_DP_1.8m(MDD) x1. 13G_XMC_5D , Sub_B_Lo x1. RTN910A x1. ISM8 x2. | MW Parallel Link | 1240A-1122A (New parallel link for 13G_4+0_28M_CA). NE_1240A 1.Install new 13G_DP_1.8m(MDD). 2.Install new 13G_XMC_5D config as 4+0_CA. 3.Reuse new 1240A_RTN910A. 4.Install 3_ISM8 & 4_ISMA8 with 4+0_CA config. 5.Create EPLA, Service Cross Connect and CA. 6.Traffic 1694C migrate to this new parallel link. 7.No decom due to establish for new parallel link. FE_1122A. 1.Install new 13G_DP_1.8m(MDD). 2.Install new 13G_XMC_5D config as 4+0_CA. 3.Install new RTN910A.(RTN no provide by MSP team). 4.Install 3_ISM8 & 4_ISM8 with 4+0_CA config. 5.Create EPLA,service cross connect and CA. 6.Traffic 1694C migrate to new parallel link 1240A-1122A. 7.Create In-Band DCN. 8.No decom due to establish for new parallel link. | [7 empty] | Magicell | SQ202501140157-Magicell | Magicell | SQ202412180538-Magicell // SQ202504260146-Magicell | 2025-03-04 | 2025-03-03 | Completed | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2025-01-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-09 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-19 | 2025-02-20 | 2025-02-19 | 2025-02-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-03 | 2025-03-04 | 2025-03-03 | 2025-03-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24121807 |  | 2024-12-19 | 2025-02-07 | Completed | 2024-12-18 | 2024-12-19 | 2024-12-18 | 2025-02-07 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-13 | 2025-01-25 | 2025-01-13 | 2025-02-07 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-01-13 | 2025-01-25 | 2025-01-13 | 2025-02-07 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-15 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-01-13 | 2025-01-25 | 2025-01-13 | 2025-01-15 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-04-24: 2025-01-13; 2025-04-24: 2025-01-25; 2025-04-24: 2025-01-13; 2025-05-07: 2025-02-21 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
7699B-7602A_1 | Kg Sungai Imam | DU00005165467 | Sabah | Sabah | 4.312595 | 117.837042 |  |  |  | JUN 25 | TI DONE | TI in plan | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1 x XMC3E 18G Sub B Lo 1 x XMC3E 18G Sub B Hi | MW Hardware Upgrade | Replace existing ODU with new XMC3E ODU for 112MHz upgrade NE (7699B): 1) Replace ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade FE (7602A): 1) Replace ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade | NE (7699B): 1) Replace ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade | FE (7602A): 1) Replace ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade | XMC3E |  | 18G |  |  | NR services | SQ202504240795-NR Services | NR services | SQ202505240116-NR Services // SQ202505240118-NR Services | 2025-04-30 | 2025-05-02 | Completed | 2025-04-21 | 2025-04-28 | 2025-04-22 | 2025-04-22 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-28 | 2025-04-22 | 2025-04-22 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-23 | 2025-04-25 | 2025-04-23 | 2025-04-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-23 | 2025-04-30 | 2025-05-02 | 2025-05-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051569 |  | 2025-05-16 | 2025-05-16 | Completed | 2025-05-15 | 2025-05-16 | 2025-05-15 | 2025-05-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-11 | MUHAMMAD ROBBIL AKRIZAN//BIN SHAARI/7167000044 | NR Service TI | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-07-22 | MUHAMMAD ROBBIL AKRIZAN//BIN SHAARI/7167000044 | NR Service TI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | AKMAL//BIN RAZALI/6794000078 |  |  | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-11-04 | MUHAMMAD ROBBIL AKRIZAN//BIN SHAARI/7167000044 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-07-21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016
7699B-7602A | Kg Sungai Imam | DU00005165468 | Sabah | Sabah | 4.312595 | 117.837042 |  |  |  | JUN 25 | TI DONE | TI in plan | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1 x XMC3E 18G Sub B Lo 1 x XMC3E 18G Sub B Hi | MW Hardware Upgrade | Replace existing ODU with new XMC3E ODU for 112MHz upgrade NE (7699B): 1) Replace ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade FE (7602A): 1) Replace ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade | NE (7699B): 1) Replace ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade | FE (7602A): 1) Replace ODU with new XMC3E 2) Change IF working mode to IS8 3) Perform 112MHz upgrade | XMC3E |  | 18G |  |  | NR services | SQ202504240795-NR Services | NR services | SQ202505240116-NR Services // SQ202505240118-NR Services | 2025-04-30 | 2025-08-11 | Completed | 2025-04-21 | 2025-04-28 | 2025-04-22 | 2025-04-22 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-28 | 2025-04-22 | 2025-04-22 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-23 | 2025-04-25 | 2025-04-23 | 2025-04-23 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-23 | 2025-04-30 | 2025-08-11 | 2025-08-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051570 |  | 2025-05-16 | 2025-05-16 | Completed | 2025-05-15 | 2025-05-16 | 2025-05-15 | 2025-05-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-11 | MUHAMMAD ROBBIL AKRIZAN//BIN SHAARI/7167000044 | NR Service TI | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-07-22 | MUHAMMAD ROBBIL AKRIZAN//BIN SHAARI/7167000044 | NR Service TI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | AKMAL//BIN RAZALI/6794000078 |  |  | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-11-04 | MUHAMMAD ROBBIL AKRIZAN//BIN SHAARI/7167000044 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-07-21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016
2443A_HU | Ijok (CELCOM) | DU00005165469 | Central | Selangor | 3.296836 | 101.447680 | WK13 | MAR 25 | WK13 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 24/3/2025 : Cutover done 21/3/2025 : Cutover done with RSL issue 20/3/2025 : Installation complete, alignment WIP 19/3/2025 : NE installation complete, pending install FE site 18/3/2025 : EDOTCO(M)-CSU - Tower - NE site 2443A Ijok (CELCOM), Digi OB - 45M Tower - FE site 1964B Kg Bt Badong | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 15G 4+0 1.2m/1.2m MDD XMC5D sub A NE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 15G XMC5D sub B Hi 4) 1 x 15G 1.2m MDD FE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 15G XMC5D sub B Lo 4) 1 x 15G 1.2m MDD | MW New Link / Reroute | To relocate antenna to new tower leg. To install new antenna, ODU and IF cable to minimize downtime To decom existing antenna + ODU Impact sites: 2443A, B01925 NE (2443A) - Install new antenna on new tower leg - Lay new IF cable - Migrate traffic to new link FE (1964B) - Install new antenna on new tower leg - Lay new IF cable - Migrate traffic to new link | [7 empty] | MTK | SQ202503270797-MTK | MTK | SQ202503280456-MTK // SQ202503280461-MTK // SQ202504260152-MTK | 2025-05-24 | 2025-05-23 | Completed | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-06 | 2025-05-07 | 2025-05-06 | 2025-05-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-07 | 2025-05-08 | 2025-05-07 | 2025-05-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-23 | 2025-05-24 | 2025-05-23 | 2025-05-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031276 |  | 2025-03-13 | 2025-03-14 | Completed | 2025-03-12 | 2025-03-13 | 2025-03-12 | 2025-03-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-19 | 2025-04-08 | 2025-03-19 | 2025-04-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-03-19 | 2025-04-08 | 2025-03-19 | 2025-04-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-24 | 2025-03-19 | 2025-03-31 | 2025-04-08 | 2025-04-08 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-03-19 | 2025-03-31 | 2025-03-20 | 2025-03-20 | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | CHEONG/SENG/WAH/7018000306
1967B_HU | Sg Terap (CELCOM) | DU00005167459 | Central | Selangor | 3.394670 | 101.216307 |  | APR 25 |  | APR 25 | DO | Ragu will check material on hand 15G or 13G | ZTE | 00. Integrated/RFS Done | 19/3/2025 : EDOTCO(M)-CSU - 45M 4 Legged Tower - NE site 1967B Sg Terap (CELCOM), Digi OB - 60M 4 Legged Tower - FE site 1153A Permatang K Selangor | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1X ODU 15G XMC5D SUB B LO | MW Swap | MW SWAP LINK 1967B-1153A WITH HUAWEI_15G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB B_WITH CA_5.32KM IMPACTED: 1967B DISMANTLE EXISTING LINK | 1. INSTALL NEW 2PCS ISM8 AT EXISTING RTN910 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW 2PCS ISM8 AT EXISTING RTN910 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK | XMC5D | MDD | 15G | 1.2 | 1.2 | GCI | SQ202504280336-GCI | GCI | SQ202505240078-GCI // SQ202505240080-GCI // SQ202506160505-GCI | 2025-07-02 | 2025-07-01 | Completed | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-04 | 2025-06-05 | 2025-06-04 | 2025-06-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050946 |  | 2025-05-10 | 2025-05-16 | Completed | 2025-05-09 | 2025-05-10 | 2025-05-09 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-20 | 2025-05-26 | 2025-05-19 | 2025-05-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-05-20 | 2025-05-26 | 2025-05-19 | 2025-05-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-21 | 2025-05-20 | 2025-05-26 | 2025-05-19 | 2025-05-30 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-05-20 | 2025-05-26 | 2025-05-19 | 2025-05-20 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202507080517-GCI | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | EZRIN TASNIM BIN ABDUL GANI6798000128
2473A_HU | Kg Ijok | DU00005167460 | Central | Selangor | 3.312196 | 101.383804 |  | APR 25 |  | JUN 25 | TI | Doable | ZTE | 00. Integrated/RFS Done | 19/3/2025 : SBC KJS - Tower - NE site 2473A Kg Ijok, Digi OB - 45M Monopole - FE site 1161A Bkt Rotan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 13G 1.2M MAC ANTENNA 1x ODU 13G XMC3 SUB A HI 1X ODU 13G XMC3 SUB A LO 1x ODU 13G XMC3 SUB B HI 1X ODU 13G XMC3 SUB B LO | MW Parallel Link | MW PARALLEL LINK 2473A-1161A WITH HUAWEI_13G_2+0_1.2M/1.2M_MAC_28MHZ_512QAM_450MBPS_XMC3_SUB A & B_EPLA WITH EXISTING LINK_5.32KM IMPACTED: 2473A, 1072L DISMANTLE EXISTING IDU | 1. INSTALL NEW RTN910 2. INSTALL NEW 13G 1.2M MAC ANTENNA 3. INSTALL NEW ODU 13G XMC3 112MHZ SUB A & B 4. SHIFT ISM8 CARD FROM EXISTING IDU TO NEW IDU SLOT 3 4. CONFIGURE LINK 13G 2+0 28MHZ 512QAM EPLA WITH EXISTING LINK 5. DISMANTLE EXISTING IDU | 1. INSTALL NEW RTN910 2. INSTALL NEW 13G 1.2M MAC ANTENNA 3. INSTALL NEW ODU 13G XMC3 112MHZ SUB A & B 4. SHIFT ISM8 CARD FROM EXISTING IDU TO NEW IDU SLOT 3 4. CONFIGURE LINK 13G 2+0 28MHZ 512QAM EPLA WITH EXISTING LINK 5. DISMANTLE EXISTING IDU | XMC3 | MAC | 13G | 1.2 | 1.2 | GTSB | SQ202504170454-GTSB | GTSB | SQ202504230133-GTSB // SQ202504230141-GTSB | 2025-10-08 | 2025-10-07 | Completed | 2025-04-07 | 2025-06-28 | 2025-06-28 | 2025-06-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-13 | 2025-05-27 | 2025-05-13 | 2025-05-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25042123 |  | 2025-04-22 | 2025-04-29 | Completed | 2025-04-21 | 2025-04-22 | 2025-04-21 | 2025-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-02 | 2025-05-31 | 2025-06-28 | 2025-06-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-05-02 | 2025-05-31 | 2025-06-28 | 2025-06-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-19 | 2025-05-02 | 2025-05-31 | 2025-06-26 | 2025-06-26 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-05-02 | 2025-05-31 | 2025-05-02 | 2025-05-02 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
2441A_HU | Kg Padang Balang (Asiaspace) | DU00005167461 | Central | Kuala Lumpur | 3.212202 | 101.698640 | WK15 | APR 25 | WK15 | APR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 10/4/2025 : Cutover done 9/4/2025 : Cutover WIP 28/3/2025 : Installation complete, pending cutover 19/3/2025 : EDGEPOINT INFRA - 45M Monopole - NE site 2441A Kg Padang Balang (Asiaspace), Digi OB - 3M Boom - RT - FE site 2070B Sri Gombak (TX) | TSS+AA+TI | L1+ATP+PAC | 2X RTN910 1X 18G 0.6M DP ANTENNA 1X 18G 1.2M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Parallel Link | MW PARALLEL LINK 2441A-2070B WITH HUAWEI_18G_2+0_0.6M/1.2M_DP_112MHZ_256QAM_1556MBPS_XMC3E_SUB A & B_3.8KM CASCADE IDU 1418K/W00848-2441A TO NEW IDU CASCADE IDU 1326K/W01535-2441A TO NEW IDU CASCADE IDU SM 1455K/W01345-2441A TO NEW IDU | 1. INSTALL NEW RTN910 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. CASCADE IDU 1418K/W00848-2441A TO NEW IDU 6. CASCADE IDU 1326K/W01535-2441A TO NEW IDU 7. CASCADE IDU SM 1455K/W01345-2441A TO NEW IDU | 1. INSTALL NEW RTN910 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG | XMC3E | MAC | 18G | 0.6 | 1.2 | GCI | SQ202504210238-GCI | GCI | SQ202504210061-GCI // SQ202504210069-GCI // SQ202505150098-GCI | 2025-05-14 | 2025-05-15 | Completed | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031547 |  | 2025-03-17 | 2025-03-27 | Completed | 2025-03-15 | 2025-03-17 | 2025-03-15 | 2025-03-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-28 | 2025-04-04 | 2025-03-27 | 2025-04-23 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-28 | 2025-04-04 | 2025-03-27 | 2025-04-23 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-04-09 | 2025-03-28 | 2025-04-04 | 2025-03-27 | 2025-04-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-06-09: 2025-03-28; 2025-06-09: 2025-04-04; 2025-06-09: 2025-03-27; 2025-07-21: 2025-03-28 |  |  | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202506050715-GTSB
2362B_HU | Daching Ilir | DU00005167462 | Southern | Sembilan | 2.887050 | 101.896670 |  |  |  |  | RFS | Cutover done | ZTE | 00. Integrated/RFS Done | 26/3/2025 : Cutover done | AA | PAC | N/A | MW Remote Upgrade | Existing link Huawei 2362B RTN05-1851B RTN16 Existing 1+0 link using MODU To enable CA and create 2+0 CA link Impacted sites: 2362B,2361B Tx route: 2362B-1851B NE (2362B): 1) Set IF conflux and enable CA 2) Configure 2nd link 3) Create EPLA 2+0 CA FE (1851B): 1) Set IF conflux and enable CA 2) Configure 2nd link 3) Create EPLA 2+0 CA | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-26 | [15 empty] | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300179-GCI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
3243D_HU | Taman Seri | DU00005167463 | Central | Selangor | 3.673520 | 100.977379 | WK11 | MAR 25 | WK11 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 14/3/2025 : Cutover done 12/3/2025 : ARGUS INTAN - 24M Lampole - NE site 3243D Taman Seri, Digi OB - Tower - FE site 4474A Sg Besar | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X 18G 0.6M SP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO | MW Swap | MW SWAP LINK 3243D-4474A WITH HUAWEI_18G_1+0_0.6M/0.6M_SP_112MHZ_256QAM_778MBPS_XMC3E_SUB A_3.14KM DISMANTLE EXISTING LINK IMPACTED: 3243D | 1. REUSE EXISTING IDU RTN910A 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 3. INSTALL NEW 18G 0.6M SP ANTENNA 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU RTN910A 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 3. INSTALL NEW 18G 0.6M SP ANTENNA 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202503190656-GCI | GCI | SQ202503200144-GCI // SQ202503200149-GCI // SQ202504150088-GCI | 2025-04-07 | 2025-04-07 | Completed | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031157 |  | 2025-03-12 | 2025-03-15 | Completed | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-14 | 2025-03-21 | 2025-03-13 | 2025-03-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-14 | 2025-03-21 | 2025-03-13 | 2025-03-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-14 | 2025-03-14 | 2025-03-21 | 2025-03-13 | 2025-03-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-14 | 2025-03-21 | 2025-03-13 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
3404A_HU | Telok Gong (REL) | DU00005167464 | Central | Selangor | 2.954729 | 101.382961 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Solution & BOQ , refer to 3404B_HU (DU00005172932) | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505070146-GCI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | EZRIN TASNIM BIN ABDUL GANI6798000128
3141C_HU | Manipal Hospital IB | DU00005167465 | Central | Selangor | 3.009942 | 101.431765 | WK13 | APR 25 |  | APR 25 | TI | Pending PTW approval | ZTE | 00. Integrated/RFS Done | 12/3/2025 : MAXIS - In-Building System - NE site 3141C Manipal Hospital IB, Digi OB - 3M RT - Wall Mounted Pole - FE site 1080A WIT | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 1X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO | MW Parallel Link | MW PARALLEL LINK 3141C-1080A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB A_2.13KM_EPLA WITH EXISTING LINK NE TRANSFER EXISTING 18G 2+0 IF CABLE TO NEW IDU AND CREATE EPLA WITH NEW LINK IMPACTED: 3141C, 1634B | 1. INSTALL NEW IDU RTN910A AND INSTALL 1PCS ISM8 CARD SLOT 4 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. TRANSFER EXISTING 18G 2+0 IF CABLE TO NEW IDU SLOT 4 AND CREATE EPLA WITH NEW LINK | 1. INSTALL NEW ISM8 CARD AT EXISTING IDU SLOT 3 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM AND EPLA WITH EXISTING LINK 5. PATCH TO NEW CP PORT AND DO PORT LAG | XMC3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202504280336-GCI | GCI | SQ202505280601-GCI // SQ202505280604-GCI | 2025-06-26 | 2025-06-25 | Completed | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-17 | 2025-06-18 | 2025-06-17 | 2025-06-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-25 | 2025-06-26 | 2025-06-25 | 2025-06-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031159 |  | 2025-03-12 | 2025-03-13 | Completed | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-06-04 | 2025-05-27 | 2025-06-11 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-05-28 | 2025-06-04 | 2025-05-27 | 2025-06-11 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | AKMAL//BIN RAZALI/6794000078 |  | 2025-05-29 | 2025-05-28 | 2025-06-04 | 2025-05-27 | 2025-06-11 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-06-09: 2025-05-28; 2025-06-09: 2025-06-04; 2025-06-09: 2025-05-27; 2025-07-21: 2025-05-28 |  |  | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202507080517-GCI | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | EZRIN TASNIM BIN ABDUL GANI6798000128
3682C_HU | Surau Firdaus | DU00005167466 | Central | Selangor | 3.279706 | 101.470536 |  | APR 25 |  | APR 25 | DO | Doable, just waiting material | ZTE | 00. Integrated/RFS Done | 19/3/2025 : STEALTH - 24M Lampole - NE site 3682C Surau Firdaus, MAXIS - 60M 4 Legged Tower - FE site 1424A Maxis Tower Batu Arang | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 1X RTN910 1X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB A HI 1X ODU 15G XMC5D SUB A LO | MW Swap | MW SWAP LINK 3682C-1424A WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB A_3.92KM IMPACTED: 3682C *RAWANG CLUSTER CANT INSTALL 18G | 1. INSTALL NEW 2PCS ISM8 CARD AT SLOT 3 & 4 2. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 3. INSTALL NEW 15G 0.6M MDD ANTENNA 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 AND NEW 2PCS ISM8 CARD AT SLOT 3 & 4 2. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 3. INSTALL NEW 15G 0.6M MDD ANTENNA 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. CASCADE NEW IDU TO EXISTING IDU 6. DISMANTLE EXISTING LINK | XMC5D | MDD | 15G | 0.6 | 1.2 | Magicell | SQ202503270787-Magicell | Magicell | SQ202504260059-Magicell // SQ202504260060-Magicell // SQ202507300766-Magicell // SQ202509180708-Magicell |  |  | Ongoing | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25042267 |  | 2025-04-23 | 2025-04-25 | Completed | 2025-04-22 | 2025-04-23 | 2025-04-22 | 2025-04-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-24 | 2026-04-10 | 2025-04-24 | 2025-05-05 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-04-24 | 2026-04-10 | 2025-04-24 | 2025-05-08 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-22 | 2025-04-24 | 2026-04-10 | 2025-04-24 | 2025-05-27 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-04-24 | 2026-04-10 | 2025-04-24 | 2025-05-07 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
1479E_LOS | Brainy Bunch Elementary Montessori | DU00005167467 | Central | Selangor | 3.221351 | 101.740210 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_1479E. 23G_SP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A _Lo x1. FE_2839C. 23G_SP_0.6M(MAC) x1. ISM8 x1. XMC_3E , Sub A _Hi x1. | MW New Link / Reroute | Link reroute to new FE 2839C due to existing link LOS BLOCK. Link reroute to new FE 2839C with 23G_1+0_112M Site Impacted : 1479E NE_1479E. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Decom existing MW link (1479E - 1794B).Ensure all that traffic migrated to new link and new FE route before decom. FE_2839C. 1.Install new 23G_SP_0.6M(MAC). 2.Reuse existing 2893C_RTN01 ( NE ID : 22508). 3.Install new 3_ISM8-1+0 into existing 2893C_RTN01. 4.Install new XMC_3E , Sub A _Hi. 5.Create service cross connect and EPLA for all service. 6.Decom existing MW link (1794B -1479E). Ensure all that traffic migrated to new link and new FE route before decom. | Link reroute to new FE 2839C due to existing link LOS BLOCK. Link reroute to new FE 2839C with 23G_1+0_112M Site Impacted : 1479E NE_1479E. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A _Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Decom existing MW link (1479E - 1794B).Ensure all that traffic migrated to new link and new FE route before decom. | Link reroute to new FE 2839C due to existing link LOS BLOCK. Link reroute to new FE 2839C with 23G_1+0_112M Site Impacted : 1479E NE_1479E. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Decom existing MW link (1479E - 1794B).Ensure all that traffic migrated to new link and new FE route before decom. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202504240787-GTSB | GTSB | SQ202505050130-GTSB // SQ202505050134-GTSB | 2025-11-11 | 2025-11-10 | Completed | 2025-04-24 | 2025-05-02 | 2025-05-02 | 2025-05-02 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-09 | 2025-05-23 | 2025-05-09 | 2025-05-09 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050538 |  | 2025-05-06 | 2025-05-08 | Completed | 2025-05-05 | 2025-05-06 | 2025-05-05 | 2025-05-08 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-31 | 2025-07-14 | 2025-07-30 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-07-14 | 2025-07-31 | 2025-07-14 | 2025-07-30 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  | 2025-07-16 | 2025-07-14 | 2025-07-31 | 2025-07-14 | 2025-07-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-07-14 | 2025-07-31 | 2025-07-14 | 2025-07-15 | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | NG HONG JIE7018000036 | Logistic Team | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202505070146-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | CHEONG/SENG/WAH/7018000306
2583A_HU | Sg Besar 2 (Maxis) | DU00005167468 | Central | Selangor | 3.697499 | 100.963423 |  | APR 25 |  | APR 25 | DO | Doable, just waiting material | ZTE | 00. Integrated/RFS Done | 20/3/2025 : MAXIS - 60M 3 Legged Tower - NE site 2583A Sg Besar 2 (Maxis), Digi OB - Tower - FE site 4474A Sg Besar, DIGI TELECOMMUNICATIONS SDN BHD - TOWER 45M LAND - Patching site B00074 B062B_B00074OD_JLNHJHARUN | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1x New CAT6 CABLE WITH SUITABLE LENGTH 2X RTN910 1X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB A HI 1X ODU 15G XMC5D SUB A LO | MW Swap | MW SWAP LINK SM 2583A-4474A MW1 WITH HUAWEI_15G_2+0_0.6M/1.2M_MDD_28MHZ_512QAM_448MBPS_XMC5D_SUB A_5.9KM FE IDU PATCHING AT 4474A TO XC B00074 OB FIBER DISMANTLE EXISTING LINK IMPACTED: 2583A | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 3. INSTALL NEW 15G 0.6M DP ANTENNA 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 3. INSTALL NEW 15G 1.2M MDD ANTENNA 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. PATCH NEW IDU TO XC B00074 OB FIBER 6. DISMANTLE EXISTING LINK | XMC5D | MDD | 15G | 0.6 | 1.2 | MTK | SQ202504280387-MTK | MTK | SQ202505160564-MTK // SQ202505160571-MTK | 2025-06-25 | 2025-06-25 | Completed | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-24 | 2025-06-25 | 2025-06-24 | 2025-06-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050954 |  | 2025-05-10 | 2025-05-13 | Completed | 2025-05-09 | 2025-05-10 | 2025-05-09 | 2025-05-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-13 | 2025-05-31 | 2025-05-13 | 2025-05-16 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-05-13 | 2025-05-31 | 2025-05-13 | 2025-05-16 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-13 | 2025-05-31 | 2025-05-20 | 2025-05-20 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-05-13 | 2025-05-31 | 2025-05-16 | 2025-05-16 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202507080517-GCI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
3569B_HU | Sg Rasau Toll Shoplot | DU00005167469 | Central | Selangor | 3.063792 | 101.488243 |  | APR 25 |  | APR 25 | DO | Doable, just waiting material | ZTE | 00. Integrated/RFS Done | 19/3/2025 : Digi OB - 3M Bipod - RT - NE site 3569B Sg Rasau Toll Shoplot, Digi OB - 45M 3 Legged Tower - FE site 1071A Chi Liung | TSS+AA+TI | L1+ATP+PAC | 1X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1X ODU 15G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL LINK 3569B RTN02-1071A RTN12 WITH HUAWEI_15G_2+0_0.6M/1.2M_MDD_28MHZ_512QAM_448MBPS_XMC5D_SUB B_3.76KM_EPLA WITH EXISTING 4+0 IMPACTED: 3569B | 1. REUSE EXISTING IDU RTN02 2. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 3. INSTALL NEW 15G 1.2M MDD ANTENNA 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM EPLA WITH EXISTING LINK 4+0 | 1. REUSE EXISTING IDU RTN12 2. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 3. INSTALL NEW 15G 1.2M MDD ANTENNA 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM EPLA WITH EXISTING LINK 4+0 5. PATCH TO NEW CP PORT AND DO PORT LAG | XMC5D | MDD | 15 | 0.6 | 1.2 | Magicell | SQ202504170467-Magicell | Magicell | SQ202504260059-Magicell // SQ202504260060-Magicell | 2025-04-25 | 2025-04-25 | Completed | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-25 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25042268 |  | 2025-04-23 | 2025-04-25 | Completed | 2025-04-22 | 2025-04-23 | 2025-04-22 | 2025-04-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-29 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-05-05 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-05-08 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-06-09: 2025-04-28; 2025-06-09: 2025-04-28; 2025-06-09: 2025-04-28; 2025-07-21: 2025-04-29 |  |  | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202504140802-GTSB | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | MAZELAN BIN RAMLI6798000096
2277A_HU | Masjid Al-Muhtadin | DU00005167470 | Central | Selangor | 3.194856 | 101.595955 | WK12 | MAR 25 | WK12 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 19/3/2025 : Cutover done 12/3/2025 : SBC KJS - 24M Lampole - NE site 2277A Masjid Al-Muhtadin, Digi OB - 45M Tower - FE site 1049B MSC Damansara (Kepong MSC) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK 2277A-1049B WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB A & B_1.32KM DISMANTLE EXISTING LINK IMPACTED: 2277A, 1301H | 1. REUSE EXISTING IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202503270731-GCI | GCI | SQ202503200144-GCI // SQ202503200149-GCI // SQ202504150088-GCI | 2025-04-12 | 2025-04-15 | Completed | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-07 | 2025-04-08 | 2025-04-07 | 2025-04-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-11 | 2025-04-12 | 2025-04-11 | 2025-04-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031357 |  | 2025-03-14 | 2025-03-19 | Completed | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-19 | 2025-03-25 | 2025-03-18 | 2025-03-19 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-19 | 2025-03-25 | 2025-03-18 | 2025-03-25 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-19 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-03-19 | 2025-03-25 | 2025-03-18 | 2025-03-19 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-19 | 2025-03-25 | 2025-03-18 | 2025-03-19 | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
1266C_HU | Bandar Putera 2 | DU00005167471 | Central | Selangor | 2.970122 | 101.511024 | WK12 | MAR 25 | WK12 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 21/3/2025 : Cutover done 20/3/2025 : NE installation complete, FE installation WIP 19/3/2025 : NAZA COMMUNICATIONS - 30M Monopole - NE site 1266C Bandar Putera 2, Digi OB - 30M 4 Legged Tower - FE site 1110A Berjaya Industrial Park | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK 1266C-1110A WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB A & B_1.55KM DISMANTLE EXISTING LINK IMPACTED: 1266C | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202504170454-GTSB | GTSB | SQ202503240695-GTSB // SQ202503240700-GTSB // SQ202504260131-GTSB | 2025-04-15 | 2025-04-15 | Completed | 2025-03-28 | 2025-04-11 | 2025-03-28 | 2025-03-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Completed |  | 2025-03-28 | 2025-04-11 | 2025-03-28 | 2025-03-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-07 | 2025-04-08 | 2025-04-07 | 2025-04-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031347 |  | 2025-03-14 | 2025-03-24 | Completed | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-24 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-24 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-21 | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-04-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-04-15 | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
1012C_HU | Masjid Al-Islah | DU00005167472 | Central | Selangor | 2.964800 | 101.386310 | WK12 | MAR 25 | WK12 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 21/3/2025 : Cutover done 20/3/2025 : Installation complete, alignment WIP 19/3/2025 : SBC KJS - Tower - NE site 1012C Masjid Al-Islah, Digi OB - 60M 3 Legged Tower - FE site 1627B Pulau Indah Highway(ZED) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK 1012C-1627B WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB A & B_1.71KM DISMANTLE EXISTING LINK IMPACTED: 1012C | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. PATCH TO EXISTING PORT 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202504170454-GTSB | GTSB | SQ202503240695-GTSB // SQ202503240700-GTSB // SQ202504260131-GTSB | 2025-04-16 | 2025-04-15 | Completed | 2025-03-28 | 2025-03-30 | 2025-03-28 | 2025-03-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-28 | 2025-04-11 | 2025-03-28 | 2025-03-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-07 | 2025-04-08 | 2025-04-07 | 2025-04-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-15 | 2025-04-16 | 2025-04-15 | 2025-04-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031345 |  | 2025-03-14 | 2025-03-24 | Completed | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-24 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-24 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-20 | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-25 | Aminuddin bin che azibA0563734967123169280 | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-20 | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
2695B_HU | Taman Bayu Permai | DU00005167473 | Central | Selangor | 3.314789 | 101.533610 | WK13 | MAR 25 | WK13 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 24/3/2025 : Cutover done 22/3/2025 : Plan to change IDU/ODU at NE and FE site - CRQ approved, cancel proceed due to not receive keys 21/3/2025 : Plan to change IDU/ODU at NE and FE site - CRQ approved, cancel proceed spillover 19/3/2025 : Digi OB - 3M Bipod - RT - NE site 2695B Taman Bayu Permai, Digi OB - 60M 4 Legged Tower - FE site 2001B Kg Sg Bakau Rawang(ZED) | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 2X ISM8 CARD 1X RTN910 1x ODU 23G XMC3 SUB B HI 1X ODU 23G XMC3 SUB B LO | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 2695B-2001B (HORIZONTAL POLAR ONLY) WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_778MBPS_XMC3_SUB B_1.3KM CONFIGURE LINK 23G 1+0 112MHZ 512QAM EPLA WITH EXISTING LINK 1+0 VERTICAL POLAR IMPACTED: 2695B | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW ODU 23G XMC3 112MHZ SUB B AT HORIZONTAL POLAR 3. REUSE EXISTING 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM EPLA WITH EXISTING LINK 1+0 VERTICAL POLAR 5. DISMANTLE EXISTING ODU HORIZONTAL | 1. INSTALL NEW RTN910 WITH 2PCS ISM8 CARD AT SLOT 3 & 4 2. INSTALL NEW ODU 23G XMC3 112MHZ SUB B AT HORIZONTAL POLAR 3. REUSE EXISTING 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM EPLA WITH EXISTING LINK 1+0 VERTICAL POLAR AT SLOT 7 6. SHIFT IF CABLE EXISTING LINK 2001B-1413A 4+0 AT 2001B RTN05 TO NEW IDU SLOT 3 AND 4 7. DISMANTLE EXISTING IDU 2001B RTN05 AND ODU HORIZONTAL | XMC3 | MS | 23G | 0.6 | 0.6 | Magicell | SQ202504170467-Magicell | Magicell | SQ202503280442-Magicell // SQ202503280449-Magicell // SQ202504260146-Magicell | 2025-08-19 | 2025-08-18 | Completed | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 | NUR FATIHAH BINTI AYOB7018000236 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-06 | 2025-08-07 | 2025-08-06 | 2025-08-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-19 | 2025-08-18 | 2025-08-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031421 |  | 2025-03-15 | 2025-03-20 | Completed | 2025-03-14 | 2025-03-15 | 2025-03-14 | 2025-03-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-20 | 2026-03-25 | 2025-03-20 | 2025-04-08 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-03-20 | 2026-03-25 | 2025-03-20 | 2025-04-08 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-24 | 2025-03-20 | 2026-03-25 | 2025-03-20 | 2025-04-07 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-03-20 | 2026-03-25 | 2025-03-20 | 2025-03-24 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
1149A_HU | KJS Bukit Beruntung | DU00005167474 | Central | Selangor | 3.412976 | 101.541967 |  |  |  |  | Cancel / Drop | Done under DU 1149A-1066A TX Mini | ZTE | 00. Site Out/Drop | 12/3/2025 : No need proceed. Done under DU 1149A-1066A TX Mini |  |  |  | Cancel / Drop | CANCEL/DROP DUE TO HU SOLUTION DONE UNDER 1149A-3761A TX MINI PROJECT | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3219B_HU | Cheras Sentral IB | DU00005167475 | Central | Kuala Lumpur | 3.078548 | 101.744812 | WK12 | MAR 25 | WK12 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 19/3/2025 : Cutover done 13/3/2025 : UMOBILE - In-Building System - NE site 3219B Cheras Sentral IB, Digi OB - 3M Boom - RT - FE site 2448A Asmah Tower | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK 3219B-2448A SM MW1 WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB A & B_1.53KM DISMANTLE EXISTING LINK IMPACTED: 2448A, 1034B | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE NEW LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE NEW LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202504170467-Magicell | Magicell | SQ202503200170-Magicell // SQ202503200172-Magicell // SQ202504260146-Magicell | 2026-01-06 | 2026-01-05 | Completed | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-05 | 2026-01-06 | 2026-01-05 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031165 |  | 2025-03-12 | 2025-03-27 | Completed | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-17 | 2026-03-11 | 2025-03-17 | 2025-03-27 | MOHD//SAFRI BIN ARIF/7018000166 |  | 2025-03-17 | 2026-03-11 | 2025-03-17 | 2025-03-27 | MOHD//SAFRI BIN ARIF/7018000166 |  | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-19 | 2025-03-17 | 2026-03-11 | 2025-03-17 | 2025-03-24 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-03-17 | 2026-03-11 | 2025-03-17 | 2025-03-20 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
1360C_HU | Antara Gapi LP | DU00005167476 | Central | Selangor | 3.425395 | 101.636089 | WK13 | MAR 25 | WK13 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 26/3/2025 : Cutover done 25/3/2025 : FE installation complete, pending install NE site 24/3/2025 : Plan install NE and FE site - CRQ approved, cancel proceed 20/3/2025 : BANGKIT SETIA - 24M Lampole - NE site 1360C Antara Gapi LP, Digi OB - Tower - FE site 1145A Batang Kali | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 4X ISM8 CARD 1X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1X ODU 15G XMC5D SUB B LO | MW Swap | MW SWAP LINK 1360C-1145A WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_256QAM_800MBPS_XMC5D_SUB B_4.63KM DISMANTLE EXISTING LINK REUSE EXISTING CHANNEL 9 AND 11 IMPACTED: 1360C, 1895H | 1. REUSE EXISTING RTN910 2. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 3. INSTALL NEW 15G 0.6M MDD ANTENNA 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM 5. REUSE EXISTING CHANNEL 9 AND 11 6. DISMANTLE EXISTING LINK | 1. REUSE EXISTING RTN910 2. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 3. INSTALL NEW 15G 0.6M MDD ANTENNA 4. CONFIGURE LINK 15G 4+0 28MHZ 256QAM 5. REUSE EXISTING CHANNEL 9 AND 11 6. REPATCH TO EXISTING PORT 7. DISMANTLE EXISTING LINK | XMC5D | MDD | 15G | 0.6 | 1.2 | MTK | SQ202503270797-MTK | MTK | SQ202503280456-MTK // SQ202503280461-MTK // SQ202504260152-MTK | 2025-05-24 | 2025-05-23 | Completed | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-08 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-07 | 2025-05-08 | 2025-05-07 | 2025-05-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-08 | 2025-05-09 | 2025-05-08 | 2025-05-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-23 | 2025-05-24 | 2025-05-23 | 2025-05-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031329 |  | 2025-03-14 | 2025-03-14 | Completed | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-08 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-08 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-27 | 2025-03-25 | 2025-04-15 | 2025-05-06 | 2025-05-06 | RIDHUAN//BIN MANSOR/8225000011 | 2025-03-25 | 2025-04-15 | 2025-03-27 | 2025-03-27 | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | CHEONG/SENG/WAH/7018000306
3876C_HU | Taman Klang Utama | DU00005167477 | Central | Selangor | 3.081484 | 101.416883 | WK13 | MAR 25 | WK13 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 25/3/2025 : Cutover done 24/3/2025 : Cutover WIP 21/3/2025 : Installation complete, pending alignment 20/3/2025 : FE site installation WIP, delay due to raining day 19/3/2025 : NE installation complete, pending install FE site 18/3/2025 : NST DATA - 24M Lampole - NE site 3876C Taman Klang Utama, Digi OB - 45M 4 Legged Tower - FE site 1087A Rantau Panjang | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC5D SUB B HI 1X ODU 18G XMC5D SUB B LO | MW Parallel Link | MW PARALLEL LINK 3876C-1087A WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_64QAM_1150MBPS_XMC3E_SUB B_3.76KM_EPLA WITH EXISTING 4+0 IMPACTED: 3876C, 1899H, 1626H | 1. INSTALL NEW ISM8 CARD AT SLOT 4 EXISTING IDU 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 64QAM EPLA WITH EXISTING LINK 4+0 | 1. INSTALL NEW ISM8 CARD AT SLOT 4 EXISTING IDU 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 64QAM EPLA WITH EXISTING LINK 4+0 5. PATCH TO NEW CP PORT AND DO PORT LAG | XMC3E | DP | 18G | 0.6 | 0.6 | GTSB | SQ202504170454-GTSB | GTSB | SQ202503280401-GTSB // SQ202503280435-GTSB // SQ202504260131-GTSB | 2025-05-14 | 2025-05-15 | Completed | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-04-09 | 2025-04-23 | 2025-04-09 | 2025-04-09 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031326 |  | 2025-03-14 | 2025-03-28 | Completed | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-28 | ERVIN CHRISTOPHER//AL ALFANSO/6799000302 | GTSB TI | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-06-28 | ERVIN CHRISTOPHER//AL ALFANSO/6799000302 | GTSB TI | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-03-24 | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-07-15 | ERVIN CHRISTOPHER//AL ALFANSO/6799000302 | 2025-06-09: 2025-03-19; 2025-06-09: 2025-03-19; 2025-06-09: 2025-03-19; 2025-07-21: 2025-07-15 |  |  | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202504140801-GCI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | EZRIN TASNIM BIN ABDUL GANI6798000128
3765A_HU | Masjid Bandar Utama Batang Kali (REL) | DU00005167478 | Central | Selangor | 3.458302 | 101.655134 |  |  |  |  | Cancel / Drop | Done under DU 3765A_PostMOCN TX NIC | ZTE | 00. Site Out/Drop | 12/3/2025 : No need proceed. Done under DU 3765A_PostMOCN TX NIC |  |  |  | Cancel / Drop | CANCEL/DROP DUE TO SOLUTION DONE UNDER 3765A_PostMOCN NIC Project | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9353A_IPR | Song | DU00005690537 | Sarawak | Sarawak | 2.008057 | 112.542438 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 19/8/2025 : EPMS Ravin have issue to update EPMS 18/8/2025 : Cutover done, pending declare | TSS+TI | L1+ATP+PAC | NE_9353A 2 X 10G SFP Optical Fiber Patch Cord x1 pair. | IDU-IPRAN | 9353A_RTN01 10G port For 9712A/9712A-LL-9074A Install 1X 10G SFP Optical at SACOFA Port SFP_10Ge-1-3-3 Install 1 x 10G SFP Optical 9353A_RTN01 at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE SFP_10Ge-1-3-3 to HW 9353A RTN01 8-EM6-3(PORT-3). Remain existing patching for 9603C_NEC_P4 at GE 2. Reconfigure all the traffic to new GE port 3 at RTN01 and Sacofa Port SFP_10Ge-1-3-3. | 9353A_RTN01 10G port For 9712A/9712A-LL-9074A Install 1X 10G SFP Optical at SACOFA Port SFP_10Ge-1-3-3 Install 1 x 10G SFP Optical 9353A_RTN01 at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE SFP_10Ge-1-3-3 to HW 9353A RTN01 8-EM6-3(PORT-3). Remain existing patching for 9603C_NEC_P4 at GE 2. Reconfigure all the traffic to new GE port 3 at RTN01 and Sacofa Port SFP_10Ge-1-3-3. | [6 empty] | Allstar | SQ202507300533-Allstar | Allstar | SQ202507290151-Allstar // SQ202512170142-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-30 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071848 |  | 2025-07-19 | 2025-08-07 | Completed | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-08-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-17 | 2025-08-24 | 2025-08-26 | 2025-08-26 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-17 | 2025-08-24 | 2025-08-26 | 2025-08-26 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-08-17 | 2025-08-24 | 2025-08-26 | 2025-08-26 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-17; 2025-06-09: 2025-08-24; 2025-06-09: 2025-08-17; 2025-07-21: 2025-08-17 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | CHEONG/SENG/WAH/7018000306
9460B_IPR | Saka | DU00005690538 | Sarawak | Sarawak | 1.369416 | 111.568777 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9460B RTN02 10G Port 9460B-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-5 Install 1 10G SFP Optical at HW 9460B RTN02 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-4-5 to HW 9460B RTN02 8-EM6-3(PORT-3) Patch RTN02 8-EM6-2(Rename as BBU 9460B) for Traffic 9460B Remain Patch 8-EM6-2(To RTN01 GE2) for DCN 9561B (later to decom) Reconfigure Traffic for All 3 Sites; 9460B, 9939A , 9561B (DCN) Site affected : 9640B 9939A 9561B (DCN) | 9460B RTN02 10G Port 9460B-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-5 Install 1 10G SFP Optical at HW 9460B RTN02 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-4-5 to HW 9460B RTN02 8-EM6-3(PORT-3) Patch RTN02 8-EM6-2(Rename as BBU 9460B) for Traffic 9460B Remain Patch 8-EM6-2(To RTN01 GE2) for DCN 9561B (later to decom) Reconfigure Traffic for All 3 Sites; 9460B, 9939A , 9561B (DCN) Site affected : 9640B 9939A 9561B (DCN) | N/A | [5 empty] | Allstar | SQ202507180633-Allstar | Allstar | SQ202507140740-Allstar // SQ202512170142-Allstar | 2025-12-10 | 2025-12-10 | Completed | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-09 | 2025-12-10 | 2025-12-09 | 2025-12-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070356 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-12 | 2025-07-18 | 2025-07-12 | 2025-07-12 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-12 | 2025-07-18 | 2025-07-12 | 2025-07-15 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-14 | 2025-07-12 | 2025-07-18 | 2025-07-15 | 2025-07-15 | KENISTON//ANAK SPANCER/6798000184 | 2025-06-09: 2025-07-12; 2025-06-09: 2025-07-18; 2025-06-09: 2025-07-12; 2025-07-21: 2025-07-12 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9214B_IPR | Desa Ilmu 3G Den | DU00005690539 | Sarawak | Sarawak | 1.448079 | 110.452861 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Optical 10KM x2 Fiber Patch Cord x 1 Pair | BBU Patching | NE_9214B Cur Cap: 1000 1G to 10G Optical Port BBU 10G Port to be assign by Ops team and swap room team. BBU PATCHING to sacofa 10Ge_1-4-5. Reconfigure traffic to the new port 10Ge_1-4-5. | NE_9214B Cur Cap: 1000 1G to 10G Optical Port BBU 10G Port to be assign by Ops team and swap room team. BBU PATCHING to sacofa 10Ge_1-4-5. Reconfigure traffic to the new port 10Ge_1-4-5. | [6 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507040587-Allstar | 2025-11-25 | 2025-11-24 | Completed | 2025-07-03 | 2025-07-03 | 2025-07-15 | 2025-07-15 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250624FK |  | 2025-06-26 | 2025-07-02 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-26 | 2025-07-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-07-03 | 2025-07-09 | 2025-07-07 | 2025-07-08 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-03 | 2025-07-09 | 2025-07-07 | 2025-07-07 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-08 | 2025-07-03 | 2025-07-09 | 2025-07-15 | 2025-07-15 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-06-09: 2025-07-03; 2025-06-09: 2025-07-09; 2025-06-09: 2025-07-03; 2025-07-21: 2025-07-03 |  |  | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | CHEONG/SENG/WAH/7018000306
9107A_IPR | Tanjong Kidurong (SACOFA) | DU00005690540 | Sarawak | Sarawak | 3.275141 | 113.083716 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G Optical SFP Module x2 Patch Cord Fiber x 1 pair. | IDU-IPRAN | 9107A_RTN05 10G port For 9107A/9107A-LL-9106A Install 1 x 10G SFP Optical at SACOFA Port SFP_10Ge-1-4-5 Install 1 x 10G SFP Optical at 9107A_RTN05 at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE SFP_10Ge-1-4-5 to HW 9107A RTN05 8-EM6-3(PORT-3). Remain existing patching at GE 2 for BBU 9107A , GE 5 to RTN_9050E and GE 6 to RTN 9635B. Reconfigure all the traffic to new GE port at RTN05_GE3 and Sacofa Port SFP_10Ge-1-4-5. | 9107A_RTN05 10G port For 9107A/9107A-LL-9106A Install 1 x 10G SFP Optical at SACOFA Port SFP_10Ge-1-4-5 Install 1 x 10G SFP Optical at 9107A_RTN05 at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE SFP_10Ge-1-4-5 to HW 9107A RTN05 8-EM6-3(PORT-3). Remain existing patching at GE 2 for BBU 9107A , GE 5 to RTN_9050E and GE 6 to RTN 9635B. Reconfigure all the traffic to new GE port at RTN05_GE3 and Sacofa Port SFP_10Ge-1-4-5. | [6 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-24 | 2025-07-24 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070962 |  | 2025-07-10 | 2025-07-15 | Completed | 2025-07-09 | 2025-07-10 | 2025-07-09 | 2025-07-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-25 | 2025-07-31 | 2025-07-30 | 2025-07-30 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-26 | 2025-07-25 | 2025-07-31 | 2025-07-31 | 2025-07-31 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-25; 2025-06-09: 2025-07-31; 2025-06-09: 2025-07-26; 2025-07-21: 2025-07-26 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | CHEONG/SENG/WAH/7018000306
7690A_IPR | Sipitang-Tenom Highway | DU00005690541 | Sabah | Sabah | 4.995106 | 115.554500 | [7 empty] | 07. Solution Changed | [5 empty] | On hold the study, according to ZTE instruction. | On hold the study, according to ZTE instruction | [12 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202506160757-GCI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | CHEONG/SENG/WAH/7018000306
9069B_IPR | TM Matang Jaya | DU00005690542 | Sarawak | Sarawak | 1.582199 | 110.304100 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9069B RTN01 10G PORT 9069B/Q00109-LL Install 1 10G SFP Optical at SACOFA Port 10GE 1-2-3 – with sfp Install 1 10G SFP Optical at HW 9069B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-3 to HW 9069B RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(to RTN02 GE5) Reconfigure Traffic for All 3 Sites; 9069B, 9971A, 9677B | 9069B RTN01 10G PORT 9069B/Q00109-LL Install 1 10G SFP Optical at SACOFA Port 10GE 1-2-3 – with sfp Install 1 10G SFP Optical at HW 9069B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-3 to HW 9069B RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(to RTN02 GE5) Reconfigure Traffic for All 3 Sites; 9069B, 9971A, 9677B | N/A | [5 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar | 2025-12-18 | 2025-12-17 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082842 |  | 2025-08-29 | 2025-09-12 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-12 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-03 | 2025-10-09 | 2025-10-03 | 2025-10-03 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-03 | 2025-10-09 | 2025-10-09 | 2025-10-09 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-03 | 2025-10-03 | 2025-10-09 | 2025-10-06 | 2025-10-07 | ROYSTON//ANAK RAMSY/6798000228 | 2025-06-09: 2025-10-03; 2025-06-09: 2025-10-09; 2025-06-09: 2025-10-03; 2025-07-21: 2025-10-03 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | EZRIN TASNIM BIN ABDUL GANI6798000128
9503A_IPR | Bekenu | DU00005690543 | Sarawak | Sarawak | 4.060340 | 113.841280 | [6 empty] | ZTE | 00. Site Out/Drop | 4/8/2025 : Drop by GOP Norizal |  |  |  |  | According to ZTE , Pass to Huawei For IPRAN Upgrade | According to ZTE , Pass to Huawei For IPRAN Upgrade | [12 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202506160760-GCI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | CHEONG/SENG/WAH/7018000306
7187A_IPR | Sapong SBC | DU00005690544 | Sabah | Sabah | 5.055052 | 115.945590 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1G Optical Module x 2. Fiber Patch Cord x 1 Pair | IDU-IPRAN | 7187A_RTN01 1G Optical port For 7187A/7187A-LL-7000A Install 1 x 1G SFP Optical at CTS Port SL:1 - K1EX10 - PORT: 6 Install 1 x 1G SFP Optical at existing 7187A_RTN01 at Ge Port 3. Patching Optical Patch Cord at CTS Port (SL:1 - K1EX10 - PORT: 6) to existing HW 7187A_RTN01_ 8-EM6-3(PORT-3). Create Physical LAG to existing GE1. Create service cross connect. Reconfigure all the traffic to new LAG port. | 7187A_RTN01 1G Optical port For 7187A/7187A-LL-7000A Install 1 x 1G SFP Optical at CTS Port SL:1 - K1EX10 - PORT: 6 Install 1 x 1G SFP Optical at existing 7187A_RTN01 at Ge Port 3. Patching Optical Patch Cord at CTS Port (SL:1 - K1EX10 - PORT: 6) to existing HW 7187A_RTN01_ 8-EM6-3(PORT-3). Create Physical LAG to existing GE1. Create service cross connect. Reconfigure all the traffic to new LAG port. | [6 empty] | NR services | SQ202507100500-NR Services | NR services | SQ202507140729-NR Services | 2025-11-01 | 2025-10-31 | Completed | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-11-01 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062808 |  | 2025-06-29 | 2025-07-01 | Completed | 2025-06-28 | 2025-06-29 | 2025-06-28 | 2025-07-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-11 | 2025-07-14 | 2025-07-11 | 2025-07-14 | WILFRED BALANG7167000026 | NR Service TI | 2025-07-11 | 2025-07-14 | 2025-07-11 | 2025-07-14 | WILFRED BALANG7167000026 | NR Service TI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-10 | 2025-07-03 | 2025-08-03 | 2025-07-03 | 2025-07-17 | WILFRED BALANG7167000026 | 2025-06-09: 2025-07-03; 2025-06-09: 2025-08-03; 2025-06-09: 2025-07-03; 2025-07-21: 2025-07-07 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | CHEONG/SENG/WAH/7018000306
9032A_IPR | Semongok | DU00005690545 | Sarawak | Sarawak | 1.398977 | 110.335555 | [6 empty] | ZTE | 00. Integrated/RFS Done | 13/9/2025 : Cutover done 12/9/2025 : Installation done, pending cutover | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 1xRTN910 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | MW Hardware Upgrade | 9032A RTN01 10G PORT 9032A/9032A-LL-9999A SWAP RTN01 TO NEW RTN910A DUE TO 10G PORT Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Install 1 10G SFP Optical at HW 9032A NEW RTN 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9032A NEW RTN 8-EM6-3(PORT-3) Reconfigure Traffic for All 3 Sites: 9032A, 9577B, 9245B | 9032A RTN01 10G PORT 9032A/9032A-LL-9999A SWAP RTN01 TO NEW RTN910A DUE TO 10G PORT Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Install 1 10G SFP Optical at HW 9032A NEW RTN 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9032A NEW RTN 8-EM6-3(PORT-3) Reconfigure Traffic for All 3 Sites: 9032A, 9577B, 9245B | N/A | [5 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508270996-Allstar // SQ202508271004-Allstar | 2025-12-18 | 2025-12-17 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082843 |  | 2025-08-29 | 2025-09-12 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-12 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-12 | 2025-09-18 | 2025-10-17 | 2025-10-17 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-12 | 2025-09-18 | 2025-10-13 | 2025-10-17 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-13 | 2025-09-12 | 2025-09-18 | 2025-10-05 | 2025-10-17 | ROYSTON//ANAK RAMSY/6798000228 | 2025-09-12 | 2025-09-18 | 2025-09-12 | 2025-09-12 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
9230B_IPR | Hospital Mukah Sacofa | DU00005690546 | Sarawak | Sarawak | 2.901780 | 112.078980 | [6 empty] | ZTE | 05. Doable |  | TSS+TI |  | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IPRAN Port Upgrade | 9230B 10G PORT 9230B/9230B-LL-9368A Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9230B BBU Reconfigure Traffic for All Sites: 9230B | 9230B 10G PORT 9230B/9230B-LL-9368A Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9230B BBU Reconfigure Traffic for All Sites: 9230B | N/A | [5 empty] | Allstar | SQ202509090120-Allstar | Allstar | SQ202509090327-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250908A3 |  | 2025-09-09 | 2025-09-24 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202507250611-GCI | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
9135A_IPR | Zeninth Minth Cinema | DU00005690547 | Sarawak | Sarawak | 2.306658 | 111.836803 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 21/8/2025 : Cutover done 20/8/2025 : Pending cutover, waiting Sacofa upgrade service 19/8/2025 : Plan to do BBU Patching - cancel proceed due to not request SR | TSS+TI | L1+ATP+PAC | 10G SFP Module x2. Fiber patch cord x 1 (Pair). | BBU Patching | NE_9135A BBU Patching 9135A-LL-9368A Current Cap : 1000. 1G to 10G Optical Port BBU 10G Port to be assign by Ops team and swap room team. BBU Patching to sacofa Port 10Ge_1-2-1. Reconfigure traffic to the new port 10Ge_1-2-1. | NE_9135A BBU Patching 9135A-LL-9368A Current Cap : 1000. 1G to 10G Optical Port BBU 10G Port to be assign by Ops team and swap room team. BBU Patching to sacofa Port 10Ge_1-2-1. Reconfigure traffic to the new port 10Ge_1-2-1. | [6 empty] | Allstar | SQ202507300533-Allstar | Allstar | SQ202507290151-Allstar // SQ202512170142-Allstar | 2025-09-23 | 2025-09-23 | Completed | 2025-07-31 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-19 | 2025-09-20 | 2025-09-19 | 2025-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-09-20 | 2025-09-19 | 2025-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071849 |  | 2025-07-19 | 2025-08-07 | Completed | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-08-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-19 | 2025-08-26 | 2025-08-26 | 2025-08-26 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-08-19 | 2025-08-26 | 2025-08-26 | 2025-08-26 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-19; 2025-06-09: 2025-08-26; 2025-06-09: 2025-08-19; 2025-07-21: 2025-08-19 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | CHEONG/SENG/WAH/7018000306
9197A_IPR | Debak Junction(Celcom) | DU00005690548 | Sarawak | Sarawak | 1.604742 | 111.433104 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1xRTN910A 2x10G SFP Optical 1KM 2x Patch Cord(Pair) | IDU-IPRAN | 9197A RTN01 10G Port 9197A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-2-16. Install a new RTN910A.(RTN no provide by OPS team). Install 1 10G SFP Optical at HW 9197A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-16 to HW 9197A RTN01 8-EM6-3(PORT-3) Patch 8-EM6-2(BBU ETH0) for Traffic 9197A Site affected : 9197A | 9197A RTN01 10G Port 9197A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-2-16 Install a new RTN910A.(RTN no provide by OPS team). Install 1 10G SFP Optical at HW 9197A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-16 to HW 9197A RTN01 8-EM6-3(PORT-3) Patch 8-EM6-2(BBU ETH0) for Traffic 9197A Site affected : 9197A | N/A | [5 empty] | Allstar | SQ202507180633-Allstar | Allstar | SQ202507160775-Allstar // SQ202512170142-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-17 | 2025-07-31 | 2025-07-23 | 2025-07-23 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070352 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-20 | 2025-07-14 | 2025-07-15 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-14 | 2025-07-20 | 2025-09-07 | 2025-10-27 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-27 | 2025-07-14 | 2025-07-20 | 2025-10-30 | 2025-10-30 | MICHEAL//BICKSON ANAK BANING/6798000201 | 2025-06-09: 2025-07-14; 2025-06-09: 2025-07-20; 2025-06-09: 2025-07-15; 2025-07-21: 2025-07-15 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202506160760-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9418A_IPR | Pang Stungkor | DU00005690549 | Sarawak | Sarawak | 1.479140 | 109.957105 | [6 empty] | ZTE | 00. Integrated/RFS Done | 8/10/2025 : Port ready. Port info TBC. update by sacofa 11/9/2025 : Hold - LAG full. Need to upgrade/add LAG by GOP | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9418A RTN01 10G PORT 9418A/9418A-LL-9999A Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Install 1 10G SFP Optical at HW 9418A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9418A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All 4 Sites: 9418A, 9778B, 9776B, 9782B | 9418A RTN01 10G PORT 9418A/9418A-LL-9999A Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Install 1 10G SFP Optical at HW 9418A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9418A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All 4 Sites: 9418A, 9778B, 9776B, 9782B | [6 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar | 2025-12-18 | 2025-12-17 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082844 |  | 2025-08-29 | 2025-09-10 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-11 | 2025-09-17 | 2025-09-11 | 2025-09-11 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-11 | 2025-09-17 | 2025-10-15 | 2025-10-15 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-10 | 2025-09-11 | 2025-09-17 | 2025-10-14 | 2025-10-14 | ROYSTON//ANAK RAMSY/6798000228 | 2025-06-09: 2025-09-11; 2025-06-09: 2025-09-17; 2025-06-09: 2025-09-11; 2025-07-21: 2025-09-11 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
9294A_IPR | Marudi | DU00005690550 | Sarawak | Sarawak | 4.192695 | 114.338228 | [6 empty] | ZTE | 00. Integrated/RFS Done | 22/9/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 10G SFP Optical x2 Optical Patch Cord x 1 Pair | IDU-IPRAN | Site affected Q02312 Q01131 9294A Install a 1G port at RTN_03 and set up LAG, since onsite it was found that the existing Sacofa port is 10G. NE_9294A_RTN03 10G existing port For 9294A-LL-9074A (10G existing connection from Ibeam to Sacofa) Install 1 x 1G SFP Optical at 9294A-MAC-001 MARUDI Install 1 x 1G SFP Optical at 9294A_RTN03 at GE5. Patching Optical Patch Cord at GE0/2/24 to HW 9294A RTN03_ 8-EM6-5(PORT-5). Configure LAG Port for Both 8-EG6-5(PORT-5) & 8-EG6-1(PORT-1) Reconfigure Traffic for All impacted site | Site affected Q02312 Q01131 9294A Install a 1G port at RTN_03 and set up LAG, since onsite it was found that the existing Sacofa port is 10G. NE_9294A_RTN03 10G existing port For 9294A-LL-9074A (10G existing connection from Ibeam to Sacofa) Install 1 x 1G SFP Optical at 9294A-MAC-001 MARUDI Install 1 x 1G SFP Optical at 9294A_RTN03 at GE5. Patching Optical Patch Cord at GE0/2/24 to HW 9294A RTN03_ 8-EM6-5(PORT-5). Configure LAG Port for Both 8-EG6-5(PORT-5) & 8-EG6-1(PORT-1) Reconfigure Traffic for All impacted site | [6 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar // SQ202512170142-Allstar | 2025-12-18 | 2025-12-17 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082845 |  | 2025-08-29 | 2025-09-10 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-28 | 2025-09-22 | 2025-09-22 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-22 | 2025-09-28 | 2025-10-13 | 2025-10-13 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-22 | 2025-09-22 | 2025-09-28 | 2025-10-05 | 2025-10-11 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-09-22; 2025-06-09: 2025-09-28; 2025-06-09: 2025-09-22; 2025-07-21: 2025-09-22 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | CHEONG/SENG/WAH/7018000306
9054A_IPR | Asa Jaya(SACOFA) | DU00005690551 | Sarawak | Sarawak | 1.544498 | 110.611708 | [6 empty] | ZTE | 00. Integrated/RFS Done | 13/9/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9054A RTN01 10G PORT 9054A-LL-9999A Install 1 10G SFP Optical at SACOFA Port 1-2-1 Install 1 10G SFP Optical at HW 9054A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-2-1 to HW 9054A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All 3 Sites: 9054A, 9831B, 9832B | 9054A RTN01 10G PORT 9054A-LL-9999A Install 1 10G SFP Optical at SACOFA Port 1-2-1 Install 1 10G SFP Optical at HW 9054A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-2-1 to HW 9054A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All 3 Sites: 9054A, 9831B, 9832B | N/A | [5 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar | 2025-12-18 | 2025-12-17 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082846 |  | 2025-08-29 | 2025-09-10 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-10 | 2025-09-16 | 2025-09-18 | 2025-09-18 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-10 | 2025-09-16 | 2025-09-18 | 2025-09-18 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-10 | 2025-09-10 | 2025-09-16 | 2025-09-16 | 2025-09-16 | ROYSTON//ANAK RAMSY/6798000228 | 2025-06-09: 2025-09-10; 2025-06-09: 2025-09-16; 2025-06-09: 2025-09-10; 2025-07-21: 2025-09-10 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
9230A_IPR | Bayai | DU00005690552 | Sarawak | Sarawak | 1.135219 | 111.502611 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9230A RTN01 10G Port 9230A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-1 Install 1 10G SFP Optical at HW 9230A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-4-1 to HW 9230A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU) for Traffic 9230A Reconfigure Traffic for All 2 Sites; 9230A, 9512B Site affected : 9230A 9512A | 9230A RTN01 10G Port 9230A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-1 Install 1 10G SFP Optical at HW 9230A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-4-1 to HW 9230A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU) for Traffic 9230A Reconfigure Traffic for All 2 Sites; 9230A, 9512B Site affected : 9230A 9512A | N/A | [5 empty] | Allstar | SQ202507180633-Allstar | Allstar | SQ202507140740-Allstar // SQ202512170142-Allstar | 2025-10-30 | 2025-10-30 | Completed | 2025-07-17 | 2025-07-31 | 2025-07-17 | 2025-07-17 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070355 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-10 | 2025-07-16 | 2025-07-10 | 2025-07-10 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-10 | 2025-07-16 | 2025-07-11 | 2025-07-11 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-11 | 2025-07-10 | 2025-07-16 | 2025-07-14 | 2025-07-14 | KENISTON//ANAK SPANCER/6798000184 | 2025-06-09: 2025-07-10; 2025-06-09: 2025-07-16; 2025-06-09: 2025-07-11; 2025-07-21: 2025-07-11 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9190A_IPR | Desa Ria | DU00005690553 | Sarawak | Sarawak | 1.459631 | 111.561953 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 9190A_RTN01 10G SFP Optical x2. Optical Patch Cord x 1 Pair | IDU-IPRAN | Site affected 9234R 9224R 9227R 9190A 9190A_RTN01 10G port For 9190A-LL-9999A Install 1 x 10G SFP Optical at SACOFA Port 10GE_1-2-5 Install 1 x 10G SFP Optical at 9190A_RTN01 at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE_1-2-5 to HW 9190A RTN01_ 8-EM6-3(PORT-3). Remaining existing ETH LAN patching from 9190A_RTN02 to 9190A_RTN01. Reconfigure all the traffic to new GE port at RTN01 and Sacofa Port SFP_10GE_1-2-5. | 9190A_RTN01 10G port For 9190A-LL-9999A Install 1 x 10G SFP Optical at SACOFA Port 10GE_1-2-5 Install 1 x 10G SFP Optical at 9190A_RTN01 at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE_1-2-5 to HW 9190A RTN01_ 8-EM6-3(PORT-3). Remaining existing ETH LAN patching from 9190A_RTN02 to 9190A_RTN01. Reconfigure all the traffic to new GE port at RTN01 and Sacofa Port SFP_10GE_1-2-5. | [6 empty] | Allstar | SQ202507180633-Allstar | Allstar | SQ202507190105-Allstar // SQ202512170142-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-17 | 2025-07-31 | 2025-07-17 | 2025-07-17 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070350 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-20 | 2025-07-21 | 2025-07-24 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-14 | 2025-07-20 | 2025-07-18 | 2025-07-23 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-22 | 2025-07-14 | 2025-07-20 | 2025-07-26 | 2025-07-26 | MICHEAL//BICKSON ANAK BANING/6798000201 | 2025-06-09: 2025-07-14; 2025-06-09: 2025-07-20; 2025-06-09: 2025-07-16; 2025-07-21: 2025-07-16 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | CHEONG/SENG/WAH/7018000306
9195A_IPR | Ulu Krain Junction | DU00005690554 | Sarawak | Sarawak | 1.752155 | 111.401068 | [6 empty] | ZTE | 00. Integrated/RFS Done | 0717: Sacofa port changed to 1-3-3 | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9195A RTN01 10G Port 9195A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-3 Install 1 10G SFP Optical at HW 9195A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-4-3 to HW 9192A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(To-9192A eNodeB) for Traffic 9192A Reconfigure Traffic for All 3 Sites; 9195A, 9590B , 9589B Site affected : 9192A 9223R | 9195A RTN01 10G Port 9195A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-3 Install 1 10G SFP Optical at HW 9195A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-4-3 to HW 9192A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(To-9192A eNodeB) for Traffic 9192A Reconfigure Traffic for All 3 Sites; 9195A, 9590B , 9589B Site affected : 9192A 9223R | N/A | [5 empty] | Allstar | SQ202507180633-Allstar | Allstar | SQ202507190105-Allstar // SQ202512170142-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-17 | 2025-07-31 | 2025-07-23 | 2025-07-23 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070360 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-16 | 2025-07-22 | 2025-07-17 | 2025-07-17 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-16 | 2025-07-22 | 2025-07-17 | 2025-07-21 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-17 | 2025-07-16 | 2025-07-22 | 2025-07-29 | 2025-07-29 | MICHEAL//BICKSON ANAK BANING/6798000201 | 2025-06-09: 2025-07-16; 2025-06-09: 2025-07-22; 2025-06-09: 2025-07-17; 2025-07-21: 2025-07-17 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9701C_IPR | Kapit 2 Secondary School | DU00005690555 | Sarawak | Sarawak | 2.009910 | 112.928000 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 18/8/2025 : Plan to do BBU Patching - cancel proceed due to no info new route | TSS+TI | L1+ATP+PAC | 10G Optic SFP Module x2 Fiber Patch Cord x 1 pair. | BBU Patching | Site affected 9701C NE_9701C Cur Cap: 1000 1G to 10G Optical Port BBU 10G Port to be assign by Ops team and swap room team. BBU PATCHING to Sacofa Port 10GE-1-4-1. Reconfigure traffic to the new port 10GE-1-4-1. | Site affected 9701C NE_9701C Cur Cap: 1000 1G to 10G Optical Port BBU 10G Port to be assign by Ops team and swap room team. BBU PATCHING to Sacofa Port 10GE-1-4-1. Reconfigure traffic to the new port 10GE-1-4-1. | [6 empty] | Allstar | SQ202507300533-Allstar | Allstar | SQ202507290151-Allstar // SQ202512170142-Allstar | 2026-02-23 | 2026-02-23 | Completed | 2025-07-30 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071850 |  | 2025-07-19 | 2025-08-07 | Completed | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-08-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-17 | 2025-08-24 | 2025-08-18 | 2025-08-18 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-17 | 2025-08-24 | 2025-09-07 | 2025-11-14 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-12-27 | 2025-12-27 | 2025-12-27 | 2025-12-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-27 | 2025-08-17 | 2025-08-24 | 2025-12-29 | 2025-12-29 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-17; 2025-06-09: 2025-08-24; 2025-06-09: 2025-08-18; 2025-07-21: 2025-08-18 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | CHEONG/SENG/WAH/7018000306
9351B_IPR | BDA Housing Kidurong MP | DU00005690556 | Sarawak | Sarawak | 3.233402 | 113.074482 | [6 empty] | ZTE | 00. Integrated/RFS Done | 27/8/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9351B RTN01 10G PORT 9351B/9351B-LL-9106A Install 1 10G SFP Optical at SACOFA Port 1-2-5 Install 1 10G SFP Optical at HW 9351B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-5 to HW 9351B RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-1(to BBU 9351B) Reconfigure Traffic for All 2 Sites: 9351B,9692A | 9351B RTN01 10G PORT 9351B/9351B-LL-9106A Install 1 10G SFP Optical at SACOFA Port 1-2-5 Install 1 10G SFP Optical at HW 9351B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-5 to HW 9351B RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-1(to BBU 9351B) Reconfigure Traffic for All 2 Sites: 9351B,9692A | N/A | [5 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar // SQ202512170142-Allstar |  |  | Ongoing | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-02 | 2026-02-08 | 2026-02-02 | 2026-02-02 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082847 |  | 2025-08-29 | 2025-09-24 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-29 | 2026-02-04 | 2026-01-29 | 2026-01-29 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-29 | 2026-02-04 | 2026-01-30 | 2026-01-30 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-27 | 2026-01-29 | 2026-02-04 | 2026-02-11 | 2026-02-11 | KENISTON//ANAK SPANCER/6798000184 | 2025-06-09: 2026-01-29; 2025-06-09: 2026-02-04; 2025-06-09: 2026-01-29; 2025-07-21: 2026-01-29 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | EZRIN TASNIM BIN ABDUL GANI6798000128
9192A_IPR | Spaoh Junction(TM-Sacofa) | DU00005690557 | Sarawak | Sarawak | 1.536516 | 111.490485 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9192A RTN01 10G Port 9192A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-3 Install 1 10G SFP Optical at HW 9192A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-4-3 to HW 9192A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(To-9192A eNodeB) for Traffic 9192A Reconfigure Traffic for All 2 Sites; 9192A, 9223R Site affected : 9192A 9223R | 9192A RTN01 10G Port 9192A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-3 Install 1 10G SFP Optical at HW 9192A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-4-3 to HW 9192A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(To-9192A eNodeB) for Traffic 9192A Reconfigure Traffic for All 2 Sites; 9192A, 9223R Site affected : 9192A 9223R | N/A | [5 empty] | Allstar | SQ202507180633-Allstar | Allstar | SQ202507160775-Allstar // SQ202512170142-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-17 | 2025-07-31 | 2025-07-23 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070351 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-20 | 2025-07-15 | 2025-07-15 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-14 | 2025-07-20 | 2025-07-15 | 2025-07-16 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-15 | 2025-07-14 | 2025-07-20 | 2025-07-29 | 2025-07-29 | MICHEAL//BICKSON ANAK BANING/6798000201 | 2025-06-09: 2025-07-14; 2025-06-09: 2025-07-20; 2025-06-09: 2025-07-15; 2025-07-21: 2025-07-15 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
7980B_IPR | Pekan Nabalu | DU00005690558 | Sabah | Sabah | 6.036541 | 116.455593 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G Optical Module x 2 Fiber Patch Cord x 1 pair | IDU-IPRAN | 7980B_RTN01 10G Optical port For 7980B-LL-7000A Install 1 x 10G SFP Optical at CTS Port SL:1 - K1EX10 - PORT: 3 Install 1 x 10G SFP Optical at existing 7980B_RTN01 at Ge Port 6 ( Swap existing 1G Optical_CTS STBY to 10G Optical). Patching Optical Patch Cord at CTS Port (SL:1 - K1EX10 - PORT: 3) to existing HW 7980B_RTN01_ 8-EM6-6(PORT-6). Reconfigure all the traffic to new 10G Optical port at CTS Port SL:1 - K1EX10 - PORT: 3 and 7980B_RTN01 at Optical Ge Port 6. | 7980B_RTN01 10G Optical port For 7980B-LL-7000A Install 1 x 10G SFP Optical at CTS Port SL:1 - K1EX10 - PORT: 3 Install 1 x 10G SFP Optical at existing 7980B_RTN01 at Ge Port 6 ( Swap existing 1G Optical_CTS STBY to 10G Optical). Patching Optical Patch Cord at CTS Port (SL:1 - K1EX10 - PORT: 3) to existing HW 7980B_RTN01_ 8-EM6-6(PORT-6). Reconfigure all the traffic to new 10G Optical port at CTS Port SL:1 - K1EX10 - PORT: 3 and 7980B_RTN01 at Optical Ge Port 6. | [6 empty] | NR services | SQ202507140732-NR Services | NR services | SQ202507140729-NR Services | 2025-11-01 | 2025-10-31 | Completed | 2025-07-13 | 2025-07-13 | 2025-07-13 | 2025-07-13 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-11-01 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250708A3 |  | 2025-07-09 | 2025-07-09 | Completed | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-12 | 2025-07-16 | 2025-07-12 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-12 | 2025-07-16 | 2025-07-12 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-11 | 2025-07-11 | 2025-08-11 | 2025-07-11 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-11; 2025-06-09: 2025-08-11; 2025-06-09: 2025-07-11; 2025-07-21: 2025-07-15 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | CHEONG/SENG/WAH/7018000306
9114A_IPR | Tatau Bazaar | DU00005690559 | Sarawak | Sarawak | 2.881411 | 112.852137 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 1/10/2025 : Plan to do IDU-IPRAN - Cancel proceed due to access pending approval 29/9/2025 : Plan to do IDU-IPRAN - Cancel proceed 27/8/2025 : Plan to do IDU-IPRAN - cancel proceed 30/7/2025 : Plan to do IDU-IPRAN - Cancel proceed due to need PTW maxis | TSS+TI | L1+ATP+PAC | 10G Optice SFP Module x 2 Fiber patch cord x 1 Pair ETH LAN Cable x1. | IDU-IPRAN | Site Affected 9114A 3295B5 Traffic carry on NEC MW link 3952B/3952B-9114A-LL-9106A. NE_9114A 10G Optical Port for 9114A-LL-9106A. Reuse existing 9114A_RTN01. (According to actual site info). Transfer BBU from NEC IDU to new RTN910A_GE1. Cascade NEC IDU to new RTN910A_GE2. Install 1 x 10G SFP Optical at SACOFA Port 10GE-1-2-2. Install 1 x 10G SFP Optical at 9114A_RTN910A Port GE3. Patching Optical Patch Cord at SACOFA Port 10GE-1-2-2 to HW 9114A RTN910A_ 8-EM6-3(PORT-3). Create New In Band DCN Reconfigure traffic to the Sacofa port 10GE-1-2-2 and new RTN910A Port 3. | Site Affected 9114A 3295B5 Traffic carry on NEC MW link 3952B/3952B-9114A-LL-9106A. NE_9114A 10G Optical Port for 9114A-LL-9106A. Reuse existing 9114A_RTN01. (According to actual site info). Transfer BBU from NEC IDU to new RTN910A_GE1. Cascade NEC IDU to new RTN910A_GE2. Install 1 x 10G SFP Optical at SACOFA Port 10GE-1-2-2. Install 1 x 10G SFP Optical at 9114A_RTN910A Port GE3. Patching Optical Patch Cord at SACOFA Port 10GE-1-2-2 to HW 9114A RTN910A_ 8-EM6-3(PORT-3). Create New In Band DCN Reconfigure traffic to the Sacofa port 10GE-1-2-2 and new RTN910A Port 3. | [6 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar | 2025-12-18 | 2025-12-17 | Completed | 2025-07-29 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070963 |  | 2025-07-10 | 2025-07-15 | Completed | 2025-07-09 | 2025-07-10 | 2025-07-09 | 2025-07-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-30 | 2025-08-06 | 2025-09-07 | 2025-09-07 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-30 | 2025-08-06 | 2025-09-08 | 2025-10-20 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-17 | 2025-07-30 | 2025-08-06 | 2025-10-19 | 2025-10-19 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-30; 2025-06-09: 2025-08-06; 2025-06-09: 2025-07-30; 2025-07-21: 2025-07-30 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202506160760-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | CHEONG/SENG/WAH/7018000306
7335A_IPR | Mesilau | DU00005690560 | Sabah | Sabah | 6.028909 | 116.607122 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1G Optical Module x2 Fiber Patch cord x 1 pair | BBU Patching | Current ZTE BBU patching to 7335A_RTN04 (GE2) and 7335A_RTN04 (GE1) patching to CTS NE_7335A Current Cap : 1000. BBU 1G Optical Port to be assign by Ops team and swap room team. BBU Patching to CTS Port SL:1 4- K1EX10 - PORT: 7. Reconfigure traffic to the new Optical CTS port SL:1 4- K1EX10 - PORT: 7 and New BBU Optical Port. | Current ZTE BBU patching to 7335A_RTN04 (GE2) and 7335A_RTN04 (GE1) patching to CTS NE_7335A Current Cap : 1000. BBU 1G Optical Port to be assign by Ops team and swap room team. BBU Patching to CTS Port SL:1 4- K1EX10 - PORT: 7. Reconfigure traffic to the new Optical CTS port SL:1 4- K1EX10 - PORT: 7 and New BBU Optical Port. | [6 empty] | NR services | SQ202508070526-NR Services | NR services | SQ202507160774-NR Services | 2025-11-10 | 2025-11-10 | Completed | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062806 |  | 2025-06-29 | 2025-07-01 | Completed | 2025-06-28 | 2025-06-29 | 2025-06-28 | 2025-07-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-16 | 2025-08-16 | 2025-07-16 | 2025-07-17 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-16 | 2025-08-16 | 2025-07-16 | 2025-07-18 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-17 | 2025-07-16 | 2025-08-16 | 2025-07-16 | 2025-07-18 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-16; 2025-06-09: 2025-08-16; 2025-06-09: 2025-07-16; 2025-07-21: 2025-07-17 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | CHEONG/SENG/WAH/7018000306
9431A_IPR | Kg Sebigo | DU00005690561 | Sarawak | Sarawak | 1.652604 | 109.790736 | [6 empty] | ZTE | 00. Integrated/RFS Done | 8/10/2025 : Port ready 1-4-1 update by sacofa pic 18/9/2025 : Plan to do IDU-IPRAN - Hold due to Sacofa Tejas not yet ready for 10G port | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9431A RTN01 10G PORT 9431A/9431A-LL-9999A Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Install 1 10G SFP Optical at HW 9431A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9431A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All 4 Sites: 9431A, 9775B, 9544B, 9229B | 9431A RTN01 10G PORT 9431A/9431A-LL-9999A Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Install 1 10G SFP Optical at HW 9431A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9431A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All 4 Sites: 9431A, 9775B, 9544B, 9229B | N/A | [5 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar | 2025-12-18 | 2025-12-17 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082848 |  | 2025-08-29 | 2025-09-12 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-12 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-18 | 2025-09-24 | 2025-09-18 | 2025-09-18 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-18 | 2025-09-24 | 2025-10-15 | 2025-10-15 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-10 | 2025-09-18 | 2025-09-24 | 2025-10-14 | 2025-10-14 | ROYSTON//ANAK RAMSY/6798000228 | 2025-06-09: 2025-09-18; 2025-06-09: 2025-09-24; 2025-06-09: 2025-09-18; 2025-07-21: 2025-09-18 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
9384A_IPR | Jalan Wong Kin Huo | DU00005690562 | Sarawak | Sarawak | 2.290411 | 111.847677 | [6 empty] | ZTE | 00. Integrated/RFS Done | 21/8/2025 : Cutover done 20/8/2025 : Plan to do IDU-IPRAN - cancel proceed 19/8/2025 : Plan to do IDU-IPRAN - hold due to sacofa not available for support | TSS+TI | L1+ATP+PAC | 10G Optical SFP Module x 2 Fiber Patch Cord x 1 Pair. | IDU-IPRAN | Site affected 9384A 9274B 9384A_RTN01 10G port For 9384A-LL-9368A Install 1 x 10G SFP Optical at SACOFA Port 10GE-1-4-1 Install 1 x 10G SFP Optical at 9384A_RTN01 at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE-1-4-1 to HW 9384A RTN01_ 8-EM6-3(PORT-3). Reconfigure all the traffic to new GE port at RTN03 and Sacofa Port SFP_10GE-1-4-1. | Site affected 9384A 9274B 9384A_RTN01 10G port For 9384A-LL-9368A Install 1 x 10G SFP Optical at SACOFA Port 10GE-1-4-1 Install 1 x 10G SFP Optical at 9384A_RTN01 at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE-1-4-1 to HW 9384A RTN01_ 8-EM6-3(PORT-3). Reconfigure all the traffic to new GE port at RTN03 and Sacofa Port SFP_10GE-1-4-1. | [6 empty] | Allstar | SQ202507300533-Allstar | Allstar | SQ202507290151-Allstar // SQ202512170142-Allstar | 2025-11-25 | 2025-11-26 | Completed | 2025-07-24 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071851 |  | 2025-07-19 | 2025-08-07 | Completed | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-08-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-19 | 2025-08-26 | 2025-08-26 | 2025-08-26 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-08-19 | 2025-08-26 | 2025-08-26 | 2025-08-26 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-19; 2025-06-09: 2025-08-26; 2025-06-09: 2025-08-19; 2025-07-21: 2025-08-19 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160760-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | CHEONG/SENG/WAH/7018000306
9466A_IPR | Kg Kuap | DU00005690563 | Sarawak | Sarawak | 1.405611 | 110.366639 | [6 empty] | ZTE | 00. Site Out/Drop |  | TSS+TI |  | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IPRAN Port Upgrade | 9466A 10G PORT 9466A/9466A-LL-9999A Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9466A BBU Reconfigure Traffic for All Sites: 9466A | 9466A 10G PORT 9466A/9466A-LL-9999A Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9466A BBU Reconfigure Traffic for All Sites: 9466A | N/A | [5 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250908A4 |  | 2025-09-09 | 2025-09-12 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-12 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202507250611-GCI | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
9341B_IPR | Kemena Industrial (Shin Yang) | DU00005690564 | Sarawak | Sarawak | 3.146970 | 113.082800 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G Optical SFP Module x 2 Fiber Patch Cord x 1 pair | BBU Patching | Site Affected 9341B NE_9341B 1G to 10G Optical Port BBU 10G Port to be assign by Ops team and swap room team. BBU PATCHING to Sacofa Port 10GE-1-1-3 Reconfigure traffic to the new port 10GE-1-1-3. | Site Affected 9341B NE_9341B 1G to 10G Optical Port BBU 10G Port to be assign by Ops team and swap room team. BBU PATCHING to Sacofa Port 10GE-1-1-3 Reconfigure traffic to the new port 10GE-1-1-3. | [6 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-25 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070964 |  | 2025-07-10 | 2025-07-15 | Completed | 2025-07-09 | 2025-07-10 | 2025-07-09 | 2025-07-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-17 | 2025-07-23 | 2025-07-17 | 2025-07-17 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-17 | 2025-07-23 | 2025-07-17 | 2025-07-21 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-18 | 2025-07-17 | 2025-07-23 | 2025-07-21 | 2025-07-21 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-17; 2025-06-09: 2025-07-23; 2025-06-09: 2025-07-17; 2025-07-21: 2025-07-17 |  |  | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | CHEONG/SENG/WAH/7018000306
9182B_IPR | Bukit Kemuyang | DU00005690565 | Sarawak | Sarawak | 2.335943 | 111.959372 | [6 empty] | ZTE | 00. Integrated/RFS Done | 16/8/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 10G Optical SFP Module x 2. Fiber Patch Cord x 1 pair | IDU-IPRAN | Site affected 9182B 9013K/Q00172 Q00787 9182B_RTN01 10G port For 9182B/9182B-LL-9368A Install 1 x 10G SFP Optical at SACOFA Port 10GE-1-3-4 Install 1 x 10G SFP Optical at 9182B_RTN01 at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE-1-3-4 to HW 9182B RTN01_ 8-EM6-3(PORT-3). Reconfigure all the traffic to new GE port at RTN03 and Sacofa Port SFP_10GE-1-3-4. | Site affected 9182B 9013K/Q00172 Q00787 9182B_RTN01 10G port For 9182B/9182B-LL-9368A Install 1 x 10G SFP Optical at SACOFA Port 10GE-1-3-4 Install 1 x 10G SFP Optical at 9182B_RTN01 at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE-1-3-4 to HW 9182B RTN01_ 8-EM6-3(PORT-3). Reconfigure all the traffic to new GE port at RTN03 and Sacofa Port SFP_10GE-1-3-4. | [6 empty] | Allstar | SQ202507300533-Allstar | Allstar | SQ202507290151-Allstar // SQ202512170142-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-25 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-19 | 2025-09-20 | 2025-09-19 | 2025-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-09-20 | 2025-09-19 | 2025-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071852 |  | 2025-07-19 | 2025-08-07 | Completed | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-08-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-15 | 2025-08-22 | 2025-08-16 | 2025-08-16 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-15 | 2025-08-22 | 2025-08-21 | 2025-08-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-16 | 2025-08-15 | 2025-08-22 | 2025-08-20 | 2025-08-20 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-15; 2025-06-09: 2025-08-22; 2025-06-09: 2025-08-16; 2025-07-21: 2025-08-16 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | CHEONG/SENG/WAH/7018000306
9704A_IPR | Debak (SACOFA) | DU00005690566 | Sarawak | Sarawak | 1.554758 | 111.422468 | [6 empty] | ZTE | 00. Integrated/RFS Done | 11/8/2025 : Plan to do IDU-IPRAN - Cancel proceed due to raining day | TSS+TI | L1+ATP+PAC | 10G Optical SFP Module x 2 Fiber Patch Cord x 1 Pair. | IDU-IPRAN | 9704A_RTN02 10G port For 9704A/9704A-LL-9999A Install 1 x 10G SFP Optical at SACOFA Port 10GE-1-4-5 Install 1 x 10G SFP Optical at 9704A_RTN02 at Ge Port 3. (Utilize RTN02 due to RTN01 Not support optical port). Patching Optical Patch Cord at SACOFA Port 10GE-1-4-5 to HW 9704A RTN02_ 8-EM6-3(PORT-3). Transfer BBU 9704A_RTN01_GE2 to 9704A_RTN02_GE2. Transfer sacofa 3rd leg config and patching to 9704A_RTN02_GE5. Reconfigure all the traffic to new GE port at RTN03 and Sacofa Port SFP_10GE-1-4-5. Ensure all services or traffic transfer to 9704A_RTN02 ( ID : 24393) , before disconnected the ETH LAN cable between 9704A_RTN01 & RTN02. | 9704A_RTN02 10G port For 9704A/9704A-LL-9999A Install 1 x 10G SFP Optical at SACOFA Port 10GE-1-4-5 Install 1 x 10G SFP Optical at 9704A_RTN02 at Ge Port 3. (Utilize RTN02 due to RTN01 Not support optical port). Patching Optical Patch Cord at SACOFA Port 10GE-1-4-5 to HW 9704A RTN02_ 8-EM6-3(PORT-3). Transfer BBU 9704A_RTN01_GE2 to 9704A_RTN02_GE2. Transfer sacofa 3rd leg config and patching to 9704A_RTN02_GE5. Reconfigure all the traffic to new GE port at RTN03 and Sacofa Port SFP_10GE-1-4-5. Ensure all services or traffic transfer to 9704A_RTN02 ( ID : 24393) , before disconnected the ETH LAN cable between 9704A_RTN01 & RTN02. | [6 empty] | Allstar | SQ202507180633-Allstar | Allstar | SQ202507160775-Allstar // SQ202512170142-Allstar | 2025-11-25 | 2025-11-26 | Completed | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070357 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-20 | 2025-07-15 | 2025-07-15 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-14 | 2025-07-20 | 2025-07-15 | 2025-07-15 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-15 | 2025-07-14 | 2025-07-20 | 2025-07-30 | 2025-07-30 | MICHEAL//BICKSON ANAK BANING/6798000201 | 2025-06-09: 2025-07-14; 2025-06-09: 2025-07-20; 2025-06-09: 2025-07-15; 2025-07-21: 2025-07-15 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | CHEONG/SENG/WAH/7018000306
9401B_IPR | Mukah NTS MP | DU00005690567 | Sarawak | Sarawak | 2.892144 | 112.088988 | [6 empty] | ZTE | 00. Site Out/Drop | 3/9/2025 : GOP Norizal ask for urgent site 4/8/2025 : Drop by GOP Norizal | TSS+TI |  | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9401B RTN01 10G PORT 9401B Install 1 10G SFP Optical at SACOFA Port 10GE-1-2-1 Install 1 10G SFP Optical at HW 9401B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE-1-2-1 to HW 9401B RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(to BBU 9401B) Reconfigure Traffic for All 2 Sites: 9401B,9193B, 9629B | 9401B RTN01 10G PORT 9401B Install 1 10G SFP Optical at SACOFA Port 10GE-1-2-1 Install 1 10G SFP Optical at HW 9401B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE-1-2-1 to HW 9401B RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(to BBU 9401B) Reconfigure Traffic for All 2 Sites: 9401B,9193B, 9629B | N/A | [5 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY250908A5 |  | 2025-09-09 | 2025-09-30 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-30 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202507250611-GCI | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | EZRIN TASNIM BIN ABDUL GANI6798000128
7639B_IPR | Cowie Bay (7639B) | DU00005690568 | Sabah | Sabah | 4.242787 | 117.902993 |  |  |  |  | DONE |  |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1G SFP Optical Module x 4 Optical Patch Cord x 2 Pairs | IDU-IPRAN | Site affected 7639B (RAN Site) NE_7639B Install new RTN910. (RTN no provide by Ops team and swap team). BBU existing patching transfer to new RTN910A , Port GE1. RTN910A , Optical Port 3 patching to CTS Optical Port SL-5-EG4C-PORT 1 RTN910A , Optical Port 4 Patching to CTS Optical Port SL-5-EG4C-PORT 2 Create Physical LAG Port and create new In band DCN. Reconfigure traffic to the new Optical CTS port SL-5-EG4C-PORT 1 and Port 2. | Site affected 7639B ( Dummy Topology , no child sites , RAN site) NE_7639B Install new RTN910. (RTN no provide by Ops team and swap team). BBU existing patching transfer to new RTN910A , Port GE1. RTN910A , Optical Port 3 patching to CTS Optical Port SL-5-EG4C-PORT 1 RTN910A , Optical Port 4 Patching to CTS Optical Port SL-5-EG4C-PORT 2 Reconfigure traffic to the new Optical CTS port SL-5-EG4C-PORT 1 and Port 2. | [6 empty] | NR services | SQ202510090436-NR Services | NR services | SQ202507190103-NR Services | 2025-11-11 | 2025-11-10 | Completed | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062807 |  | 2025-06-29 | 2025-07-01 | Completed | 2025-06-28 | 2025-06-29 | 2025-06-28 | 2025-07-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-03 | 2025-11-03 | 2025-10-03 | 2025-10-03 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-03 | 2025-11-03 | 2025-10-03 | 2025-10-07 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-06 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-06 | 2025-10-03 | 2025-11-03 | 2025-10-03 | 2025-10-07 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-10-03; 2025-06-09: 2025-11-03; 2025-06-09: 2025-10-03; 2025-07-21: 2025-10-03 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | CHEONG/SENG/WAH/7018000306
9028B_IPR | Moyan Height | DU00005690569 | Sarawak | Sarawak | 1.528450 | 110.251784 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module_10KM x 2. Fiber Patch Cord x 1Pair. RTN910A x 1. | IDU-IPRAN | Site affected 9621B 9028B 9028B_RTN01 10G port For 9028B/9028B-LL-9999A Swap existing RTN910A to the latest version RTN910A due to not support for 10G port. (RTN no will be provide by Ops team) Install 1 x 10G SFP Optical at SACOFA Port 10GE-1-2-3 Install 1 x 10G SFP Optical at new RTN910A at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE-1-2-3 to new HW 9028B RTN910A_ 8-EM6-3(PORT-3). Reconfigure MW link parameter , service cross connect and New Inband DCN. Reconfigure all the traffic to new GE port 3 and Sacofa Port SFP_10GE-1-2-3. | Site affected 9621B 9028B 9028B_RTN01 10G port For 9028B/9028B-LL-9999A Swap existing RTN910A to the latest version RTN910A due to not support for 10G port. (RTN no will be provide by Ops team) Install 1 x 10G SFP Optical at SACOFA Port 10GE-1-2-3 Install 1 x 10G SFP Optical at new RTN910A at Ge Port 3. Patching Optical Patch Cord at SACOFA Port 10GE-1-2-3 to new HW 9028B RTN910A_ 8-EM6-3(PORT-3). Reconfigure MW link parameter , service cross connect and New Inband DCN. Reconfigure all the traffic to new GE port 3 and Sacofa Port SFP_10GE-1-2-3. | [6 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507080939-Allstar | 2025-11-25 | 2025-11-27 | Completed | 2025-07-08 | 2025-07-08 | 2025-07-15 | 2025-07-15 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070145 |  | 2025-07-02 | 2025-07-02 | Completed | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-07 | 2025-07-13 | 2025-07-07 | 2025-07-07 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-07 | 2025-07-13 | 2025-07-07 | 2025-07-09 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-08 | 2025-07-07 | 2025-07-13 | 2025-07-09 | 2025-07-09 | KENISTON//ANAK SPANCER/6798000184 | 2025-06-09: 2025-07-07; 2025-06-09: 2025-07-13; 2025-06-09: 2025-07-07; 2025-07-21: 2025-07-07 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | CHEONG/SENG/WAH/7018000306
7407A_IPR | Kg.Taginambur | DU00005690570 | Sabah | Sabah | 6.229093 | 116.446084 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) 1xIDU RTN910 | MW Hardware Upgrade | 7407A RTN01 10G PORT 7407A/7407A-CTS LL-7000A (THIS LINK CARRY EB SITE 7831E) 1. INSTALL NEW IDU RTN910 2. TRANSFER IF CABLE 7770B-7407A EXISTING RTN01 SLOT 7 TO NEW IDU SLOT 7 3. TRANSFER ISM8 CARD 7352B-7407A EXISTING RTN01 SLOT 3 TO NEW IDU SLOT 3 4. TRANSFER ISM8 CARD 7354B-7407A EXISTING RTN01 SLOT 4 TO NEW IDU SLOT 4 5. REPATCH BBU FROM EXISTING RTN01 TO NEW IDU 6. DECOM EXISTING IDU 6. INSTALL 1 10G SFP OPTICAL AT CTS PORT SL:12- K1EX10 - PORT: 3 7. INSTALL 1 10G SFP OPTICAL AT NEW HW 7407A RTN 8-EM6-3 8. PATCHING OPTICAL PATCH CORD CTS PORT SL:12- K1EX10 - PORT: 3 TO NEW HW 7407A RTN 8-EM6-3 9. RECONFIGURE TRAFFIC FOR ALL 6 SITES SITE AFFECTED : 7407A 7354B 7831E 7352B 7770B S01405 | 7407A RTN01 10G PORT 7407A/7407A-CTS LL-7000A (THIS LINK CARRY EB SITE 7831E) 1. INSTALL NEW IDU RTN910 2. TRANSFER IF CABLE 7770B-7407A EXISTING RTN01 SLOT 7 TO NEW IDU SLOT 7 3. TRANSFER ISM8 CARD 7352B-7407A EXISTING RTN01 SLOT 3 TO NEW IDU SLOT 3 4. TRANSFER ISM8 CARD 7354B-7407A EXISTING RTN01 SLOT 4 TO NEW IDU SLOT 4 5. REPATCH BBU FROM EXISTING RTN01 TO NEW IDU 6. INSTALL 1 10G SFP OPTICAL AT CTS PORT SL:12- K1EX10 - PORT: 3 7. INSTALL 1 10G SFP OPTICAL AT NEW HW 7407A RTN 8-EM6-3 8. PATCHING OPTICAL PATCH CORD CTS PORT SL:12- K1EX10 - PORT: 3 TO NEW HW 7407A RTN 8-EM6-3 9. RECONFIGURE TRAFFIC FOR ALL 6 SITES SITE AFFECTED : 7407A 7354B 7831E 7352B 7770B S01405 | N/A | [5 empty] | NR services | SQ202603170086-NR Services | NR services | SQ202507300478-NR Services // SQ202507300483-NR Services | 2026-03-13 | 2026-03-12 | Completed | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071932 |  | 2025-07-24 | 2025-07-28 | Completed | 2025-07-23 | 2025-07-24 | 2025-07-23 | 2025-07-28 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-26 | 2025-08-26 | 2025-07-26 | 2025-07-28 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-26 | 2025-08-26 | 2025-07-26 | 2025-07-28 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-28 | 2025-07-26 | 2025-08-26 | 2025-07-26 | 2025-08-06 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-26; 2025-06-09: 2025-08-26; 2025-06-09: 2025-07-26; 2025-07-21: 2025-07-26 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
7330A_IPR | Bundutuhan | DU00005690571 | Sabah | Sabah | 5.969099 | 116.532500 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 7330A RTN01 2x1G PORT 7330A/7330A-CTS LL-7000A 1. INSTALL 1 1G SFP OPTICAL AT CTS PORT SL:1 - K1EX10 - PORT: 6 2. INSTALL 1 1G SFP OPTICAL AT HW 7330A RTN01 8-EM6-5 3. PATCHING OPTICAL PATCH CORD CTS PORT SL:1 - K1EX10 - PORT: 6 TO HW 7330A RTN01 8-EM6-5 4. CONFIG 2G LAG AT RTN910 5. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 7330A 6. RECONFIGURE TRAFFIC FOR ALL 4 SITES SITE AFFECTED : 7330A S00502 S01629 S01662 | 7330A RTN01 2x1G PORT 7330A/7330A-CTS LL-7000A 1. INSTALL 1 1G SFP OPTICAL AT CTS PORT SL:1 - K1EX10 - PORT: 6 2. INSTALL 1 1G SFP OPTICAL AT HW 7330A RTN01 8-EM6-5 3. PATCHING OPTICAL PATCH CORD CTS PORT SL:1 - K1EX10 - PORT: 6 TO HW 7330A RTN01 8-EM6-5 4. CONFIG 2G LAG AT RTN910 5. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 7330A 6. RECONFIGURE TRAFFIC FOR ALL 4 SITES SITE AFFECTED : 7330A S00502 S01629 S01662 | N/A | [5 empty] | NR services | SQ202507140732-NR Services | NR services | SQ202507160774-NR Services | 2025-11-01 | 2025-10-31 | Completed | 2025-07-13 | 2025-07-13 | 2025-07-13 | 2025-07-13 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-11-01 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250708A2 |  | 2025-08-11 | 2025-07-15 | Completed | 2025-07-11 | 2025-08-11 | 2025-07-11 | 2025-07-15 | NUR/WAFA/MIJONG/6871000001 | NR Service TI | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-13 | 2025-07-15 | 2025-07-13 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-13 | 2025-07-15 | 2025-07-13 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-15 | 2025-07-11 | 2025-08-11 | 2025-07-11 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-11; 2025-06-09: 2025-08-11; 2025-06-09: 2025-07-11; 2025-07-21: 2025-07-15 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
9579A_IPR | Miri Tudan Housing | DU00005690572 | Sarawak | Sarawak | 4.500956 | 114.035890 | [6 empty] | ZTE | 00. Integrated/RFS Done | 9/9/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9579A RTN02 10G PORT 9579A/9579A-LL-9074A Install 1 10G SFP Optical at SACOFA Port 1-1-3 Install 1 10G SFP Optical at HW 9579A RTN02 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-1-3 to HW 9579A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All 2 Sites: 9579A, 9701B | 9579A RTN02 10G PORT 9579A/9579A-LL-9074A Install 1 10G SFP Optical at SACOFA Port 1-1-3 Install 1 10G SFP Optical at HW 9579A RTN02 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-1-3 to HW 9579A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All 2 Sites: 9579A, 9701B | N/A | [5 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar // SQ202512170142-Allstar | 2025-12-25 | 2026-01-05 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082850 |  | 2025-08-29 | 2025-09-10 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-09 | 2025-09-15 | 2025-09-18 | 2025-09-18 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-09 | 2025-09-15 | 2025-09-18 | 2025-09-18 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-09 | 2025-09-09 | 2025-09-15 | 2025-09-16 | 2025-09-16 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-09-09; 2025-06-09: 2025-09-15; 2025-06-09: 2025-09-10; 2025-07-21: 2025-09-10 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
7931A_IPR | Hospital Kunak | DU00005690573 | Sabah | Sabah | 4.674992 | 118.234829 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) 1xIDU RTN910 | MW Hardware Upgrade | 7931A RTN01 10G PORT 7931A/7931A-LL-7205A 1. INSTALL NEW IDU RTN910 2. TRANSFER ISM8 CARD 3181B-7931A EXISTING RTN01 RTN950 SLOT 2 TO NEW IDU SLOT 3 3. SHIFT IF CABLE 7939B-7931A EXISTING RTN01 RTN950 SLOT 4-1 AND 4-2 TO NEW IDU SLOT 7-1 AND 7-2 4. REPATCH BBU FROM EXISTING RTN01 TO NEW IDU 5. INSTALL 1 10G SFP OPTICAL AT CTS PORT SL:11 - K1EX10 - PORT: 4 6. INSTALL 1 10G SFP OPTICAL AT NEW RTN910 HW 7931A RTN01 8-EM6-5 7. PATCHING OPTICAL PATCH CORD CTS PORT SL:11 - K1EX10 - PORT: 4 TO NEW RTN910 HW 7931A RTN01 8-EM6-5 8. DECOM IDU RTN950 9. RECONFIGURE TRAFFIC FOR ALL 5 SITES SITE AFFECTED : 3181B 7939B S01052 S00351 7931B | 7931A RTN01 10G PORT 7931A/7931A-LL-7205A 1. INSTALL NEW IDU RTN910 2. TRANSFER ISM8 CARD 3181B-7931A EXISTING RTN01 RTN950 SLOT 2 TO NEW IDU SLOT 3 3. SHIFT IF CABLE 7939B-7931A EXISTING RTN01 RTN950 SLOT 4-1 AND 4-2 TO NEW IDU SLOT 7-1 AND 7-2 4. REPATCH BBU FROM EXISTING RTN01 TO NEW IDU 5. INSTALL 1 10G SFP OPTICAL AT CTS PORT SL:11 - K1EX10 - PORT: 4 6. INSTALL 1 10G SFP OPTICAL AT NEW RTN910 HW 7931A RTN01 8-EM6-5 7. PATCHING OPTICAL PATCH CORD CTS PORT SL:11 - K1EX10 - PORT: 4 TO NEW RTN910 HW 7931A RTN01 8-EM6-5 8. DECOM IDU RTN950 9. RECONFIGURE TRAFFIC FOR ALL 5 SITES SITE AFFECTED : 3181B 7939B S01052 S00351 7931B | N/A | [5 empty] | NR services | SQ202508270926-NR Services | NR services | SQ202508200592-NR Services // SQ202508200595-NR Services | 2026-03-13 | 2026-03-12 | Completed | 2025-08-25 | 2025-08-27 | 2025-08-25 | 2025-08-27 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071933 |  | 2025-07-24 | 2025-08-21 | Completed | 2025-07-23 | 2025-07-24 | 2025-07-23 | 2025-08-21 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-08-21 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-08-21 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-21 | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-08-22 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-08-18 | 2025-09-18 | 2025-08-18 | 2025-08-21 | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | tseping//wang/6819000006 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
9333B_IPR | Rh James | DU00005690574 | Sarawak | Sarawak | 2.740235 | 112.661791 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 22/8/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9333B RTN01 10G PORT 9333B/9333B-LL-9106A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA 1-4-1 2. INSTALL 1 10G SFP OPTICAL AT HW 9333B RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA 1-4-1 TO HW 9333B RTN01 8-EM6-3 4. REMAIN BBU PATCHING AT PORT 2 RTN01 5. RECONFIGURE TRAFFIC SITE AFFECTED : 9333B | 9333B RTN01 10G PORT 9333B/9333B-LL-9106A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA 1-4-1 2. INSTALL 1 10G SFP OPTICAL AT HW 9333B RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA 1-4-1 TO HW 9333B RTN01 8-EM6-3 4. REMAIN BBU PATCHING AT PORT 2 RTN01 5. RECONFIGURE TRAFFIC SITE AFFECTED : 9333B | N/A | [5 empty] | Allstar | SQ202508070530-Allstar | Allstar | SQ202508070574-Allstar // SQ202512170142-Allstar | 2025-11-25 | 2025-11-27 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080797 |  | 2025-08-08 | 2025-08-27 | Completed | 2025-08-07 | 2025-08-08 | 2025-08-07 | 2025-08-27 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-22 | 2025-08-28 | 2025-08-26 | 2025-08-29 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-22 | 2025-08-28 | 2025-08-26 | 2025-08-26 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-22 | 2025-08-22 | 2025-08-28 | 2025-09-01 | 2025-09-01 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-22; 2025-06-09: 2025-08-28; 2025-06-09: 2025-08-22; 2025-07-21: 2025-08-22 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
9099A_IPR | Lambir (Celcom) | DU00005690575 | Sarawak | Sarawak | 4.303598 | 114.017996 | [6 empty] | ZTE | 00. Integrated/RFS Done | 19/9/2025 : Hold due to Sacofa port not ready | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IPRAN Port Upgrade | 9099A RTN01 10G PORT 9099A/9099A-LL-9074A Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Install 1 10G SFP Optical at HW 9099A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9099A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All Sites: 9099A, 9590A, 9721B, 9739C | 9099A RTN01 10G PORT 9099A/9099A-LL-9074A Install 1 10G SFP Optical at SACOFA Port TBC (PENDING PORT INFO) Install 1 10G SFP Optical at HW 9099A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port TBC (PENDING PORT INFO) to HW 9099A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All Sites: 9099A, 9590A, 9721B, 9739C | N/A | [5 empty] | Allstar | SQ202509090120-Allstar | Allstar | SQ202509090327-Allstar // SQ202512170142-Allstar | 2026-02-05 | 2026-02-04 | Completed | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-30 | 2026-02-05 | 2026-01-30 | 2026-01-30 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250908A6 |  | 2025-09-09 | 2025-09-24 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-17 | 2026-01-31 | 2026-01-17 | 2026-02-19 | RICKY/ANAK/JACK/6000033453 | Allstar TI | 2026-01-17 | 2026-01-31 | 2026-01-17 | 2026-02-19 | RICKY/ANAK/JACK/6000033453 | Allstar TI | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-23 | 2026-01-17 | 2026-01-31 | 2026-01-17 | 2026-02-19 | RICKY/ANAK/JACK/6000033453 | 2025-06-09: 2026-01-17; 2025-06-09: 2026-01-31; 2025-06-09: 2026-01-17; 2025-07-21: 2026-01-17 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
9201B_IPR | Kota Samarahan 2 MP | DU00005690576 | Sarawak | Sarawak | 1.462209 | 110.482802 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9201B RTN02 10G PORT 9201B/9201B-SACOFA LL-9999A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-4-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9201B RTN02 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-4-3 TO HW 9201B RTN02 8-EM6-3 4. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 9201B 5. RECONFIGURE TRAFFIC FOR ALL 2 SITES: 9201B & 9176B SITE AFFECTED : 9201B 9176B | 9201B RTN02 10G PORT 9201B/9201B-SACOFA LL-9999A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-4-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9201B RTN02 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-4-3 TO HW 9201B RTN02 8-EM6-3 4. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 9201B 5. RECONFIGURE TRAFFIC FOR ALL 2 SITES: 9201B & 9176B SITE AFFECTED : 9201B 9176B | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507080939-Allstar | 2025-11-25 | 2025-11-28 | Completed | 2025-07-05 | 2025-07-05 | 2025-07-15 | 2025-07-15 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250624FL |  | 2025-06-26 | 2025-07-01 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-25 | 2025-07-01 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-07-05 | 2025-07-11 | 2025-07-05 | 2025-07-05 | KENISTON//ANAK SPANCER/6798000184 | Allstar RF | 2025-07-05 | 2025-07-11 | 2025-07-07 | 2025-07-07 | KENISTON//ANAK SPANCER/6798000184 | Allstar RF | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-05 | 2025-07-05 | 2025-07-11 | 2025-07-09 | 2025-07-09 | KENISTON//ANAK SPANCER/6798000184 | 2025-06-09: 2025-07-05; 2025-06-09: 2025-07-11; 2025-06-09: 2025-07-05; 2025-07-21: 2025-07-05 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
9712A_IPR | Bkt Dabei (Celcom) | DU00005690577 | Sarawak | Sarawak | 4.190690 | 114.439520 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 23/9/2025 : Plan to do IDU-IPRAN - Hold - Sacofa need do interpatching for provision on new service 22/9/2025 : Plan to do IDU-IPRAN - Re-plan due to stuck at site 9294A_IPR 10/9/2025 : CD ask hold until get Sacofa port info (Access road issue) | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9712A RTN01 10G Port 9712A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port SFP+ SL1P10 Install 1 10G SFP Optical at HW 9712A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE SFP+ SL1P10 to HW 9712A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU) for Traffic 9712A Remain Patch 8-EM6-1(To NEC-P3) for Traffic ? To Verify once Visible (NE 9712A Currently Loss Monitoring Since 9-June-2025) Reconfigure Traffic for All 3 Sites; 9712A, 9296A, 9591B & NEC If Required Site affected : 9712A 9296A 9591B | 9712A RTN01 10G Port 9712A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port SFP+ SL1P10 Install 1 10G SFP Optical at HW 9712A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE SFP+ SL1P10 to HW 9712A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU) for Traffic 9712A Remain Patch 8-EM6-1(To NEC-P3) for Traffic ? To Verify once Visible (NE 9712A Currently Loss Monitoring Since 9-June-2025) Reconfigure Traffic for All 3 Sites; 9712A, 9296A, 9591B & NEC If Required Site affected : 9712A 9296A 9591B | N/A | [5 empty] | Allstar | SQ202508040504-Allstar | Allstar | SQ202508040526-Allstar // SQ202512170142-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080521 |  | 2025-08-06 | 2025-08-27 | Completed | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-27 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-28 | 2025-12-05 | 2025-12-05 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-22 | 2025-09-28 | 2025-12-19 | 2025-12-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-12 | 2025-09-22 | 2025-09-28 | 2025-12-17 | 2025-12-17 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-09-22; 2025-06-09: 2025-09-28; 2025-06-09: 2025-09-23; 2025-07-21: 2025-09-23 |  |  | 2025-12-23 | 2026-01-23 | 2025-12-23 | 2025-12-23 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202506160762-GCI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9185A_IPR | Betong(SACOFA) | DU00005690578 | Sarawak | Sarawak | 1.412616 | 111.526991 | [6 empty] | ZTE | 00. Integrated/RFS Done | 31/7/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9185A RTN01 10G PORT 9185A-SACOFA LL-9999A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-4-5 2. INSTALL 1 10G SFP OPTICAL AT HW 9185A RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-4-5 TO HW 9185A RTN01 8-EM6-3 4. RECONFIGURE TRAFFIC FOR ALL 7 SITES: 9185A, 9228R, 9025R, 9233R, 9219R, 9225R, 9465B(NEC) (BBU WILL REPATCH FROM NEC EQUIPMENT TO 9185A RTN01 USING DU 9185A_IPR_1) SITE AFFECTED : 9185A 9228R 9025R 9233R 9219R 9225R 9465B | 9185A RTN01 10G PORT 9185A-SACOFA LL-9999A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-4-5 2. INSTALL 1 10G SFP OPTICAL AT HW 9185A RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-4-5 TO HW 9185A RTN01 8-EM6-3 4. RECONFIGURE TRAFFIC FOR ALL 7 SITES: 9185A, 9228R, 9025R, 9233R, 9219R, 9225R, 9465B(NEC) (BBU WILL REPATCH FROM NEC EQUIPMENT TO 9185A RTN01 USING DU 9185A_IPR_1) SITE AFFECTED : 9185A 9228R 9025R 9233R 9219R 9225R 9465B | N/A | [5 empty] | Allstar | SQ202507180633-Allstar | Allstar | SQ202507160775-Allstar // SQ202512170142-Allstar | 2026-01-14 | 2026-01-13 | Completed | 2025-07-17 | 2025-07-31 | 2025-07-17 | 2025-07-17 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070348 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-20 | 2025-07-16 | 2025-07-16 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-14 | 2025-07-20 | 2025-09-07 | 2025-09-07 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-31 | 2025-07-14 | 2025-07-20 | 2025-12-17 | 2025-12-17 | MICHEAL//BICKSON ANAK BANING/6798000201 | 2025-06-09: 2025-07-14; 2025-06-09: 2025-07-20; 2025-06-09: 2025-07-16; 2025-07-21: 2025-07-16 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
9053A_IPR | Unimas 2(SACOFA) | DU00005690579 | Sarawak | Sarawak | 1.462020 | 110.427341 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IPRAN Port Upgrade | 9053A RTN01 10G PORT 9053A/9053A-LL-9999A Install 1 10G SFP Optical at SACOFA Port 10GE 1-2-3 Install 1 10G SFP Optical at HW 9053A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-3 to HW 9053A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All Sites: 9053A, 9031C, 9457B | 9053A RTN01 10G PORT 9053A/9053A-LL-9999A Install 1 10G SFP Optical at SACOFA Port 10GE 1-2-3 Install 1 10G SFP Optical at HW 9053A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-3 to HW 9053A RTN01 8-EM6-3(PORT-3) Reconfigure Traffic for All Sites: 9053A, 9031C, 9457B | N/A | [5 empty] | Allstar | SQ202509090120-Allstar | Allstar | SQ202509090327-Allstar // SQ202602040270-Allstar | 2025-12-19 | 2025-12-19 | Completed | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250908A7 |  | 2025-09-09 | 2025-09-12 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-12 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-30 | 2025-10-25 | 2025-10-25 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-24 | 2025-10-30 | 2025-11-04 | 2025-11-04 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-10-24 | 2025-10-30 | 2025-11-10 | 2025-11-10 | ROYSTON//ANAK RAMSY/6798000228 | 2025-06-09: 2025-10-24; 2025-06-09: 2025-10-30; 2025-06-09: 2025-10-24; 2025-07-21: 2025-10-24 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202507250611-GCI | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
9534A_IPR | Kg Riam Jaya | DU00005690580 | Sarawak | Sarawak | 4.346042 | 113.996818 | [6 empty] | ZTE | 00. Integrated/RFS Done | 10/9/2025 : Plan to do IDU-IPRAN - cancel proceed due to sacofa port not ready 9/9/2025 : Plan to do IDU-IPRAN - cancel proceed due to stuck at site 9579A_IPR | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9534A RTN01 10G PORT 9534A/9534A-LL-9074A Install 1 10G SFP Optical at SACOFA Port ETH_1-3-4 Install 1 10G SFP Optical at HW 9534A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port ETH_1-3-4 to HW 9534A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-1(to BBU 9534A) Reconfigure Traffic for All 2 Sites: 9534A,9026C | 9534A RTN01 10G PORT 9534A/9534A-LL-9074A Install 1 10G SFP Optical at SACOFA Port ETH_1-3-4 Install 1 10G SFP Optical at HW 9534A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port ETH_1-3-4 to HW 9534A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-1(to BBU 9534A) Reconfigure Traffic for All 2 Sites: 9534A,9026C | N/A | [5 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar // SQ202512170142-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082857 |  | 2025-08-29 | 2025-09-10 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-09 | 2025-09-15 | 2025-12-19 | 2025-12-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-09 | 2025-09-15 | 2025-12-19 | 2025-12-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-10 | 2025-09-09 | 2025-09-15 | 2025-12-17 | 2025-12-17 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-09-09; 2025-06-09: 2025-09-15; 2025-06-09: 2025-11-06; 2025-07-21: 2025-11-06 |  |  | 2025-12-23 | 2026-01-23 | 2025-12-23 | 2025-12-23 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202507250611-GCI | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | EZRIN TASNIM BIN ABDUL GANI6798000128
9077A_IPR | Luak Bay | DU00005690581 | Sarawak | Sarawak | 4.344662 | 113.973943 | [7 empty] | 00. Integrated/RFS Done | 3/9/2025 : Cutover done | TSS+AA+TI | L1+ATP+PAC | NE_9077A. 10G SFP Module x2. ISM8 x1. Fiber Patch cord x 1 pairs | IDU-IPRAN | Site affected 9077A , 9722B , 9023C NE_9077A. 1.Install new 10G SFP Module at 9077A_RTN02_GE3 (ID : 23507). 2.Install new 10G SFP Module at new sacofa Port 10G_1-2-5. 3.Install new 4_ISM8-1+0 into existing 9077A_RTN02 (ID : 23507). Carry child site 9722B. 4.Transfer IF cable , from existing 4_ISM8-1+0_9077A_RTN01 (ID : 20231) to new 4_ISM8-1+0_9077A_RTN02 (ID : 23507). 5.Patching Fiber patch cord from 9077A_RTN02_GE3 (ID : 23507) to new sacofa port 10G_1-2-5. 6.Disconnect existing LAN cable to Old sacofa port and disable unused port. 7.Create service cross connect and migrate entire traffic to new sacofa port 10G_1-2-5. 8.Create New In Band DCN. | Site affected 9077A , 9722B , 9023C NE_9077A. 1.Install new 10G SFP Module at 9077A_RTN02_GE3 (ID : 23507). 2.Install new 10G SFP Module at new sacofa Port 10G_1-2-5. 3.Install new 4_ISM8-1+0 into existing 9077A_RTN02 (ID : 23507). Carry child site 9722B. 4.Transfer IF cable , from existing 4_ISM8-1+0_9077A_RTN01 (ID : 20231) to new 4_ISM8-1+0_9077A_RTN02 (ID : 23507). 5.Patching Fiber patch cord from 9077A_RTN02_GE3 (ID : 23507) to new sacofa port 10G_1-2-5. 6.Disconnect existing LAN cable to Old sacofa port and disable unused port. 7.Create service cross connect and migrate entire traffic to new sacofa port 10G_1-2-5. | [6 empty] | Allstar | SQ202508200601-Allstar | Allstar | SQ202508200599-Allstar // SQ202512170142-Allstar | 2025-12-25 | 2026-01-05 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-23 | 2025-12-22 | 2025-12-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081383 |  | 2025-08-14 | 2025-08-27 | Completed | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-27 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-03 | 2025-09-09 | 2025-09-18 | 2025-09-18 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-03 | 2025-09-09 | 2025-09-18 | 2025-09-18 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-03 | 2025-09-03 | 2025-09-09 | 2025-09-16 | 2025-09-16 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-09-03; 2025-06-09: 2025-09-09; 2025-06-09: 2025-09-05; 2025-07-21: 2025-09-05 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | CHEONG/SENG/WAH/7018000306
9524A_IPR | TM Tanjung Lobang | DU00005690582 | Sarawak | Sarawak | 4.364360 | 113.975730 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9524A RTN01 10G Port 9524A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port 1-3-3 Install 1 10G SFP Optical at HW 9524A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-3-3 to HW 9524A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(TO-NEC 3175B Port2) for Traffic 3175B (NEC MW) Remain Patch 8-EM6-1(To-9524A BBU ETH0) for Traffic 9524A (BBU) Reconfigure Traffic for All 3 Sites; 9524A, 9946A & 3175B4 Site affected : 9524A 9946A 3175B4 | 9524A RTN01 10G Port 9524A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port 1-3-3 Install 1 10G SFP Optical at HW 9524A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-3-3 to HW 9524A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(TO-NEC 3175B Port2) for Traffic 3175B (NEC MW) Remain Patch 8-EM6-1(To-9524A BBU ETH0) for Traffic 9524A (BBU) Reconfigure Traffic for All 3 Sites; 9524A, 9946A & 3175B4 Site affected : 9524A 9946A 3175B4 | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-09 | 2025-07-09 | 2025-07-15 | 2025-07-15 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250624FI |  | 2025-06-26 | 2025-07-01 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-26 | 2025-07-01 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-07-10 | 2025-07-16 | 2025-07-10 | 2025-07-10 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-10 | 2025-07-16 | 2025-07-09 | 2025-07-11 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-10 | 2025-07-10 | 2025-07-16 | 2025-07-15 | 2025-07-15 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-10; 2025-06-09: 2025-07-16; 2025-06-09: 2025-07-10; 2025-07-21: 2025-07-10 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9100A_IPR | Sg Dalam | DU00005690583 | Sarawak | Sarawak | 4.341685 | 114.013651 | [6 empty] | ZTE | 00. Integrated/RFS Done | 10/9/2025 : Cutover done 9/9/2025 : Plan to do IDU-IPRAN - cancel proceed due to stuck at site 9579A_IPR | TSS+TI | L1+ATP+PAC | Site affected 9100A , 9579B NE_9100A RTN910AF x1. 10G SFP Module x2. Fiber Patch Cords x 2 pairs. | IDU-IPRAN | Site affected 9100A , 9579B NE_9100A 1.Swap existing 9100A_RTN01 to new RTN910AF due to not support 10G SFP Module. 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 10G SFP at new RTN910A_GE3. 4.Install new 10G SFP at new Sacofa Port. Pending Port info from Sacofa. 5.Patching fiber patch cord from RTN910A_GE3 to new sacofa port. 6.Disconnect existing LAN cable to Old sacofa port and disable unused port. 7.Create cross connect and tarffic migrate to new sacofa port. | Site affected 9100A , 9579B NE_9100A 1.Swap existing 9100A_RTN01 to new RTN910AF due to not support 10G SFP Module. 2.Install new RTN910A.(RTN no provide by OPS team). 3.Install new 10G SFP at new RTN910A_GE3. 4.Install new 10G SFP at new Sacofa Port. Pending Port info from Sacofa. 5.Patching fiber patch cord from RTN910A_GE3 to new sacofa port. 6.Disconnect existing LAN cable to Old sacofa port and disable unused port. 7.Create cross connect and traffic migrate to new sacofa port. | [6 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar // SQ202512170142-Allstar | 2025-12-19 | 2025-12-19 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082859 |  | 2025-08-29 | 2025-09-10 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-09 | 2025-09-15 | 2025-09-18 | 2025-09-18 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-09 | 2025-09-15 | 2025-09-18 | 2025-09-18 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-10 | 2025-09-09 | 2025-09-15 | 2025-09-16 | 2025-09-16 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-09-09; 2025-06-09: 2025-09-15; 2025-06-09: 2025-09-09; 2025-07-21: 2025-09-09 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | CHEONG/SENG/WAH/7018000306
9346A_IPR | Sungai Tapang | DU00005690584 | Sarawak | Sarawak | 1.475402 | 110.345620 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9346A RTN01 10G PORT 9346A/9346A-SACOFA LL-9999A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-4-5 2. INSTALL 1 10G SFP OPTICAL AT HW 9346A RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-4-5 TO HW 9346A RTN01 8-EM6-3 4. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 9346A 5. RECONFIGURE TRAFFIC FOR ALL 2 SITES: 9346A, 9989A SITE AFFECTED : 9346A 9989A | 9346A RTN01 10G PORT 9346A/9346A-SACOFA LL-9999A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-4-5 2. INSTALL 1 10G SFP OPTICAL AT HW 9346A RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-4-5 TO HW 9346A RTN01 8-EM6-3 4. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 9346A 5. RECONFIGURE TRAFFIC FOR ALL 2 SITES: 9346A, 9989A SITE AFFECTED : 9346A 9989A | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507020686-Allstar | 2025-10-31 | 2025-10-31 | Completed | 2025-07-01 | 2025-07-01 | 2025-07-11 | 2025-07-11 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062503 |  | 2025-06-26 | 2025-07-02 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-26 | 2025-07-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-07-01 | 2025-07-07 | 2025-07-08 | 2025-07-09 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-01 | 2025-07-07 | 2025-07-01 | 2025-07-02 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-01 | 2025-07-01 | 2025-07-07 | 2025-07-03 | 2025-07-03 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-06-09: 2025-07-01; 2025-06-09: 2025-07-07; 2025-06-09: 2025-07-01; 2025-07-21: 2025-07-01 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
9349A_IPR | Gunung Haji Baki VOR(SACOFA) | DU00005690585 | Sarawak | Sarawak | 1.471656 | 110.301363 | [6 empty] | ZTE | 00. Integrated/RFS Done | 19/9/2025 : Cutover done 12/9/2025 : Plan to do IDU-IPRAN - Cancel proceed due to stuck at site 9032A_IPR | TSS+AA+TI | L1+ATP+PAC | 10G SFP Module x1. Fiber patch cord x 1 pairs. ISM8 x1. | IDU-IPRAN | Site affected 9349A , 9582B , 9166B NE_9349A 1.Install new 10G SFP Module at 9349A_RTN02_GE3 (ID : 24252). 2.New Sacofa Port 10GE 1-2-1 – with sfp 3.Install new 3_ISM8-1+0 into existing 9349A_RTN02 (ID : 24252). Carry child site 9282B. 4.Transfer existing IF cable from 9349A_RTN01_7_ISM8-1+0 (ID : 20008) to new 3_ISM8-1+0_9349A_RTN02 (ID : 24252). 5.Patching Fiber patch cord 10G from 9349A_RTN02_GE3 to New sacofa Port 10G_1-2-1. 6.Disconnect existing LAN cable to Old sacofa port and disable unused port. 7.Create cross connect and migrate entire traffic to new sacofa port 10G_1-2-1, 8.Create new Inband DCN. | Site affected 9349A , 9582B , 9166B NE_9349A 1.Install new 10G SFP Module at 9349A_RTN02_GE3 (ID : 24252). 2.New Sacofa Port 10GE 1-2-1 – with sfp 3.Install new 3_ISM8-1+0 into existing 9349A_RTN02 (ID : 24252). Carry child site 9282B. 4.Transfer existing IF cable from 9349A_RTN01_7_ISM8-1+0 (ID : 20008) to new 3_ISM8-1+0_9349A_RTN02 (ID : 24252). 5.Patching Fiber patch cord 10G from 9349A_RTN02_GE3 to New sacofa Port 10G_1-2-1. 6.Disconnect existing LAN cable to Old sacofa port and disable unused port. 7.Create cross connect and migrate entire traffic to new sacofa port 10G_1-2-1, 8.Create new Inband DCN. | [6 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar | 2025-12-19 | 2025-12-19 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082861 |  | 2025-08-29 | 2025-09-12 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-12 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-09-26 | 2025-09-19 | 2025-09-19 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-19 | 2025-09-26 | 2025-10-15 | 2025-10-15 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-19 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 2025-10-14 | ROYSTON//ANAK RAMSY/6798000228 | 2025-06-09: 2025-09-19; 2025-06-09: 2025-09-26; 2025-06-09: 2025-09-19; 2025-07-21: 2025-09-19 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | CHEONG/SENG/WAH/7018000306
9125A_IPR | Bkt Tunggong | DU00005690586 | Sarawak | Sarawak | 3.048315 | 112.936752 | [6 empty] | ZTE | 00. Site Out/Drop | 27/8/2025 : Plan to do BBU Patching - cancel proceed | TSS+TI |  | NE_9125A. 10G SFP x2. Fiber patch cord x 1 pairs. | BBU Patching | Site affected 9125A ( BBU IPRAN) NE_9125A/Q00258. 1.Install new 10G SFP Module at 9125A_BBU , port will be assign by OPS team. 2.Install new 10G SFP Module at Sacofa new port 10G_1-3-3. 3.9125A BBU direct patching to sacofa new port 10G_1-3-3. 4.Traffic and VLAN configure accordingly. | Site affected 9125A ( BBU IPRAN) NE_9125A/Q00258. 1.Install new 10G SFP Module at 9125A_BBU , port will be assign by OPS team. 2.Install new 10G SFP Module at Sacofa new port 10G_1-3-3. 3.9125A BBU direct patching to sacofa new port 10G_1-3-3. 4.Traffic and VLAN configure accordingly. | [6 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25082862 |  | 2025-08-29 | 2025-09-10 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202507250611-GCI | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | CHEONG/SENG/WAH/7018000306
9439A_IPR | Kpg. Gita 2 MP | DU00005690587 | Sarawak | Sarawak | 1.562880 | 110.316190 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module x2. ISM8 x2. Fiber patch cord x1 pairs. | IDU-IPRAN | Site affected 9439A , 9089B , 9014B2 , 9107B NE_9439A 1.Install new 10G SFP Module at existing 9439A_RTN02_GE3 (ID : 22207). 2.Install new 4_ISM8-1+0 into existing 9439A_RTN02 (ID : 22207). 3.Install new 10G SFP Module at new 10G port 1-2-2. 4.Patching Fiber patch cord from 9439A_RTN02_GE3 to new Sacofa 10G port 1-2-2. 5.Disconnect existing LAN cable to Old Sacofa port and disable unused port. 6.Create service cross connect and traffic migrate to new sacofa port. | Site affected 9439A , 9089B , 9014B2 , 9107B NE_9439A 1.Install new 10G SFP Module at existing 9439A_RTN02_GE3 (ID : 22207). 2.Install new 4_ISM8-1+0 into existing 9439A_RTN02 (ID : 22207). 3.Install new 10G SFP Module at new Sacofa 10G Port 1-2-2. 4.Patching Fiber patch cord from 9439A_RTN02_GE3 to new Sacofa 10G port 1-2-2. 5.Disconnect existing LAN cable to Old Sacofa port and disable unused port. 6.Create service cross connect and traffic migrate to new sacofa port. | [6 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar |  |  | Ongoing | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082863 |  | 2025-08-29 | 2025-09-12 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-12 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-28 | 2025-11-03 | 2025-10-28 | 2025-10-28 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-10-28 | 2025-11-03 | 2025-11-03 | 2025-11-03 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-28 | 2025-10-28 | 2025-11-03 | 2025-11-02 | 2025-11-02 | BONG NEE NYEEbong.allstar@gmail.com | 2025-06-09: 2025-10-28; 2025-06-09: 2025-11-03; 2025-06-09: 2025-10-28; 2025-07-21: 2025-10-28 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202507250611-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | CHEONG/SENG/WAH/7018000306
9215A_IPR | Jln Meradong Pasi | DU00005690588 | Sarawak | Sarawak | 2.081262 | 111.610347 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 20/8/2025 : Cutover done 19/8/2025 : Plan to do BBU Patching - cancel proceed | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | N/A | [5 empty] | Allstar | SQ202507300533-Allstar | Allstar | SQ202507290151-Allstar // SQ202512170142-Allstar | 2025-09-22 | 2025-09-22 | Completed | 2025-07-29 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071853 |  | 2025-07-19 | 2025-08-07 | Completed | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-08-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-19 | 2025-08-26 | 2025-08-20 | 2025-08-20 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-19 | 2025-08-26 | 2025-08-21 | 2025-08-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-20 | 2025-08-19 | 2025-08-26 | 2025-08-20 | 2025-08-20 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-19; 2025-06-09: 2025-08-26; 2025-06-09: 2025-08-20; 2025-07-21: 2025-08-20 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
7286A_IPR | Alam Mesra | DU00005690589 | Sabah | Sabah | 6.033280 | 116.130648 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 7286A RTN01 2x1G PORT 7286A/7286A-CTS LL-7000A 1. INSTALL 1 1G SFP OPTICAL AT CTS PORT SL:1 - K1EX10 - PORT: 6 2. INSTALL 1 1G SFP OPTICAL AT HW 7931A RTN01 8-EM6-5 3. PATCHING OPTICAL PATCH CORD CTS PORT SL:1 - K1EX10 - PORT: 6 TO HW 7286A RTN01 8-EM6-5 4. CONFIG 2G LAG AT RTN01 RTN910 5. REMAIN PATCH 8-EM6-1(to BBU01) FOR TRAFFIC 7330A 6. RECONFIGURE TRAFFIC FOR ALL 3 SITES SITE AFFECTED : 7286A 7085B 7018L | 7286A RTN01 2x1G PORT 7286A/7286A-CTS LL-7000A 1. INSTALL 1 1G SFP OPTICAL AT CTS PORT SL:1 - K1EX10 - PORT: 6 2. INSTALL 1 1G SFP OPTICAL AT HW 7931A RTN01 8-EM6-5 3. PATCHING OPTICAL PATCH CORD CTS PORT SL:1 - K1EX10 - PORT: 6 TO HW 7286A RTN01 8-EM6-5 4. CONFIG 2G LAG AT RTN01 RTN910 5. REMAIN PATCH 8-EM6-1(to BBU01) FOR TRAFFIC 7330A 6. RECONFIGURE TRAFFIC FOR ALL 3 SITES SITE AFFECTED : 7286A 7085B 7018L | N/A | [5 empty] | NR services | SQ202507140732-NR Services | NR services | SQ202507100570-NR Services | 2025-11-01 | 2025-10-31 | Completed | 2025-07-13 | 2025-07-13 | 2025-07-13 | 2025-07-13 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-11-01 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070898 |  | 2025-08-10 | 2025-07-14 | Completed | 2025-07-10 | 2025-08-10 | 2025-07-12 | 2025-07-14 | NUR/WAFA/MIJONG/6871000001 | NR Service TI | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-12 | 2025-07-16 | 2025-07-12 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-12 | 2025-07-16 | 2025-07-12 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-10 | 2025-07-10 | 2025-08-10 | 2025-07-10 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-10; 2025-06-09: 2025-08-10; 2025-06-09: 2025-07-10; 2025-07-21: 2025-07-15 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
9379A_IPR | Julau Town | DU00005690590 | Sarawak | Sarawak | 2.031141 | 111.913584 | [6 empty] | ZTE | 00. Integrated/RFS Done | 15/8/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) 1xCAT6 CABLE (SUITABLE LENGTH) | IDU-IPRAN | 9379A RTN02 10G PORT 9379A/9379A-SACOFA LL-9368A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-3-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9379A RTN02 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-3-3 TO HW 9379A RTN02 8-EM6-3 4. CASCADE IDU 9379A RTN02 AND RTN01 TO CONFIGURE ALL USING 10G PORT 5. RECONFIGURE TRAFFIC FOR ALL 7 SITES SITE AFFECTED : 9037Z 9056Z 9057Z 9179Z 9248Z 9379A 9691A | 9379A RTN02 10G PORT 9379A/9379A-SACOFA LL-9368A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-3-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9379A RTN02 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-3-3 TO HW 9379A RTN02 8-EM6-3 4. CASCADE IDU 9379A RTN02 AND RTN01 TO CONFIGURE ALL USING 10G PORT 5. RECONFIGURE TRAFFIC FOR ALL 7 SITES SITE AFFECTED : 9037Z 9056Z 9057Z 9179Z 9248Z 9379A 9691A | N/A | [5 empty] | Allstar | SQ202508200601-Allstar | Allstar | SQ202508200599-Allstar // SQ202512170142-Allstar | 2025-10-31 | 2025-10-31 | Completed | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Manager | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081384 |  | 2025-08-14 | 2025-09-29 | Completed | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-09-29 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-15 | 2025-08-21 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-15 | 2025-08-21 | 2025-08-19 | 2025-08-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-16 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-16 | 2025-08-15 | 2025-08-21 | 2025-08-20 | 2025-08-20 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-15; 2025-06-09: 2025-08-21; 2025-06-09: 2025-08-18; 2025-07-21: 2025-08-18 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
9314A_IPR | Sungei Moyan | DU00005690591 | Sarawak | Sarawak | 1.497817 | 110.248827 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9314A RTN02 10G PORT 9314A/9314A-SACOFA LL-9999A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 10Ge-1-2-5 2. INSTALL 1 10G SFP OPTICAL AT HW 9314A RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 10Ge-1-2-5 TO HW 9314A RTN01 8-EM6-3 4. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 9314A 5. RECONFIGURE TRAFFIC FOR ALL 2 SITES SITE AFFECTED : 9305B 9314A | 9314A RTN02 10G PORT 9314A/9314A-SACOFA LL-9999A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 10Ge-1-2-5 2. INSTALL 1 10G SFP OPTICAL AT HW 9314A RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 10Ge-1-2-5 TO HW 9314A RTN01 8-EM6-3 4. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 9314A 5. RECONFIGURE TRAFFIC FOR ALL 2 SITES SITE AFFECTED : 9305B 9314A | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507080939-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-08 | 2025-07-08 | 2025-07-15 | 2025-07-15 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070146 |  | 2025-07-02 | 2025-07-02 | Completed | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-08 | 2025-07-14 | 2025-07-08 | 2025-07-08 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-08 | 2025-07-14 | 2025-07-07 | 2025-07-08 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-08 | 2025-07-08 | 2025-07-14 | 2025-07-09 | 2025-07-09 | KENISTON//ANAK SPANCER/6798000184 | 2025-06-09: 2025-07-08; 2025-06-09: 2025-07-14; 2025-06-09: 2025-07-08; 2025-07-21: 2025-07-08 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
9198A_IPR | Saratok 2 (TM-Sacofa) | DU00005690592 | Sarawak | Sarawak | 1.753741 | 111.343094 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9198A RTN02 10G PORT 9198A/9198A-SACOFA LL-9368A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-3-4 2. INSTALL 1 10G SFP OPTICAL AT HW 9198A RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-3-4 TO HW 9198A RTN01 8-EM6-3 4. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 9198A 5. RECONFIGURE TRAFFIC FOR ALL 2 SITES SITE AFFECTED : 9198A 9788B | 9198A RTN02 10G PORT 9198A/9198A-SACOFA LL-9368A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-3-4 2. INSTALL 1 10G SFP OPTICAL AT HW 9198A RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-3-4 TO HW 9198A RTN01 8-EM6-3 4. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 9198A 5. RECONFIGURE TRAFFIC FOR ALL 2 SITES SITE AFFECTED : 9198A 9788B | N/A | [5 empty] | Allstar | SQ202507250120-Allstar | Allstar | SQ202507190105-Allstar // SQ202512170142-Allstar | 2025-11-25 | 2025-11-28 | Completed | 2025-07-23 | 2025-07-31 | 2025-07-23 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070353 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-16 | 2025-07-22 | 2025-07-17 | 2025-07-17 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-16 | 2025-07-22 | 2025-07-17 | 2025-07-21 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-17 | 2025-07-16 | 2025-07-22 | 2025-07-22 | 2025-07-22 | MICHEAL//BICKSON ANAK BANING/6798000201 | 2025-06-09: 2025-07-16; 2025-06-09: 2025-07-22; 2025-06-09: 2025-07-17; 2025-07-21: 2025-07-17 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
9725C_IPR | SAMALAJU PRESS METAL (REL) | DU00005690593 | Sarawak | Sarawak | 3.550944 | 113.313167 | [6 empty] | ZTE | 00. Integrated/RFS Done | 26/9/2025 : Plan to do IDU-IPRAN - Hold due to losscom 29/8/2025 : Plan to do IDU-IPRAN - cancel proceed due to existing alarm need to clear (TT) 28/8/2025 : Plan to do IDU-IPRAN - cancel proceed | TSS+TI | L1+ATP+PAC | 10G SFP Module x2. Fiber patch cord x1 pairs. | IDU-IPRAN | Site affected 9725C , 9257R , 9130B , SW04170 NE_9725C 1.Install new 10G SFP Module at existing 9275C_RTN01_GE3. 2.Install new 10G SFP Module at new Sacofa Port ETH 1-3-3 3.Patching Fiber patch cord from 9275C_RTN01_GE3 to New sacofa port ETH 1-3-3. 4.Disconnect existing LAN cable at Old Sacofa port and disable unused port. 5.Create service cross connect and entire traffic migrate to new sacofa port ETH 1-3-3. | Site affected 9725C , 9257R , 9130B , SW04170 NE_9725C 1.Install new 10G SFP Module at existing 9275C_RTN01_GE3. 2.Install new 10G SFP Module at new Sacofa Port ETH 1-3-3. 3.Patching Fiber patch cord from 9275C_RTN01_GE3 to New sacofa port ETH 1-3-3. 4.Disconnect existing LAN cable at Old Sacofa port and disable unused port. 5.Create service cross connect and entire traffic migrate to new sacofa port ETH 1-3-3. | NA | [5 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar |  |  | Ongoing | 2026-04-21 | 2026-04-27 | 2026-04-21 | 2026-04-21 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-21 | 2026-04-27 | 2026-04-21 | 2026-04-21 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25082864 |  | 2025-08-29 | 2025-09-10 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-28 | 2026-01-31 | 2026-01-28 | 2026-02-27 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2026-01-28 | 2026-01-31 | 2026-01-28 | 2026-02-27 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-02-27 | 2026-01-28 | 2026-01-31 | 2026-01-28 | 2026-03-01 | ROYSTON//ANAK RAMSY/6798000228 | 2025-06-09: 2026-01-28; 2025-06-09: 2026-01-31; 2025-06-09: 2026-01-28; 2025-07-21: 2026-01-28 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | CHEONG/SENG/WAH/7018000306
7569A_IPR | Mile 32 Checkpoint Sandakan | DU00005690594 | Sabah | Sabah | 5.758910 | 117.759201 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 7569A RTN01 2x1G PORT 7569A/7569A-CTS LL-7124A 1. INSTALL 1 1G SFP OPTICAL AT CTS SHELF0 (2-C) SL:1 - V3E224 - PORT:18 2. INSTALL 1 1G SFP OPTICAL AT HW 7569A RTN01 8-EM6-5 3. PATCHING OPTICAL PATCH CORD CTS SHELF0 (2-C) SL:1 - V3E224 - PORT:18 TO HW 7569A RTN01 8-EM6-5 4. CONFIG 2G LAG AT RTN01 RTN910 5. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 7569A 6. RECONFIGURE TRAFFIC FOR ALL 3 SITES SITE AFFECTED : 7569A 7560B 7246R | 7569A RTN01 2x1G PORT 7569A/7569A-CTS LL-7124A 1. INSTALL 1 1G SFP OPTICAL AT CTS SHELF0 (2-C) SL:1 - V3E224 - PORT:18 2. INSTALL 1 1G SFP OPTICAL AT HW 7569A RTN01 8-EM6-5 3. PATCHING OPTICAL PATCH CORD CTS SHELF0 (2-C) SL:1 - V3E224 - PORT:18 TO HW 7569A RTN01 8-EM6-5 4. CONFIG 2G LAG AT RTN01 RTN910 5. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 7569A 6. RECONFIGURE TRAFFIC FOR ALL 3 SITES SITE AFFECTED : 7569A 7560B 7246R | N/A | [5 empty] | NR services | SQ202507300491-NR Services | NR services | SQ202507190103-NR Services | 2025-11-11 | 2025-11-10 | Completed | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-15 | 2025-10-16 | 2025-10-15 | 2025-10-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070897 |  | 2025-07-09 | 2025-07-09 | Completed | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-17 | 2025-08-17 | 2025-07-17 | 2025-07-18 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-17 | 2025-08-17 | 2025-07-17 | 2025-07-21 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-18 | 2025-07-17 | 2025-08-17 | 2025-07-17 | 2025-07-21 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-17; 2025-06-09: 2025-08-17; 2025-06-09: 2025-07-17; 2025-07-21: 2025-07-18 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
9709A_IPR | Similajau | DU00005690595 | Sarawak | Sarawak | 3.366210 | 113.437354 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 1/8/2025 : Cutover done 31/7/2025 : Plan to do IDU-IPRAN - Cancel proceed | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) 1xCAT6 CABLE (SUITABLE LENGTH) | IDU-IPRAN | 9709A RTN01 10G PORT 9709A/9709A-SACOFA LL-9106A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-1-4 2. INSTALL 1 10G SFP OPTICAL AT HW 9709A RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-1-4 TO HW 9709A RTN01 8-EM6-3 4. PATCH BBU FROM NEC TO 9709A RTN01 5. RECONFIGURE TRAFFIC FOR ALL 6 SITES SITE AFFECTED : 9003R 9004R 9256R 9269R 9346B 9709A | 9709A RTN01 10G PORT 9709A/9709A-SACOFA LL-9106A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-1-4 2. INSTALL 1 10G SFP OPTICAL AT HW 9709A RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-1-4 TO HW 9709A RTN01 8-EM6-3 4. PATCH BBU FROM NEC TO 9709A RTN01 5. RECONFIGURE TRAFFIC FOR ALL 6 SITES SITE AFFECTED : 9003R 9004R 9256R 9269R 9346B 9709A | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar | 2025-11-25 | 2025-11-28 | Completed | 2025-07-28 | 2025-07-28 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Manager | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070965 |  | 2025-07-10 | 2025-07-15 | Completed | 2025-07-09 | 2025-07-10 | 2025-07-09 | 2025-07-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-31 | 2025-08-06 | 2025-07-31 | 2025-07-31 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-31 | 2025-08-06 | 2025-08-06 | 2025-08-06 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-01 | 2025-07-31 | 2025-08-06 | 2025-08-06 | 2025-08-06 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-31; 2025-06-09: 2025-08-06; 2025-06-09: 2025-07-31; 2025-07-21: 2025-07-31 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160762-GCI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
9355B_IPR | Kidurong Ind (Celcom) | DU00005690596 | Sarawak | Sarawak | 3.247877 | 113.094521 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 27/8/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) 1xCAT6 CABLE (SUITABLE LENGTH) | IDU-IPRAN | 9355B RTN01 10G PORT 9355B/9355B-SACOFA LL-9106A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 10GE-1-1-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9355B RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 10GE-1-1-3 TO HW 9355B RTN01 8-EM6-3 4. PATCH BBU FROM NEC TO 9355B RTN01 5. RECONFIGURE TRAFFIC FOR ALL 3 SITES SITE AFFECTED : 9355B 9764B 9973A | 9355B RTN01 10G PORT 9355B/9355B-SACOFA LL-9106A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 10GE-1-1-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9355B RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 10GE-1-1-3 TO HW 9355B RTN01 8-EM6-3 4. PATCH BBU FROM NEC TO 9355B RTN01 5. RECONFIGURE TRAFFIC FOR ALL 3 SITES SITE AFFECTED : 9355B 9764B 9973A | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar // SQ202512170142-Allstar | 2025-11-11 | 2025-11-10 | Completed | 2025-07-23 | 2025-07-23 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070966 |  | 2025-07-10 | 2025-07-15 | Completed | 2025-07-09 | 2025-07-10 | 2025-07-09 | 2025-07-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-29 | 2025-08-04 | 2025-07-29 | 2025-07-29 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-29 | 2025-08-04 | 2025-09-03 | 2025-09-03 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-26 | 2025-07-29 | 2025-08-04 | 2025-09-02 | 2025-09-02 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-29; 2025-06-09: 2025-08-04; 2025-06-09: 2025-07-29; 2025-07-21: 2025-07-29 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | EZRIN TASNIM BIN ABDUL GANI6798000128
9645B_IPR | Trusan | DU00005690597 | Sarawak | Sarawak | 4.788747 | 115.275051 |  |  |  | AUG 25 |  |  |  | 06. Other Issue | 18/9/2025 : Plan to do IDU-IPRAN - Hold due to Sacofa port not ready 17/9/2025 : Plan to do IDU-IPRAN - Cancel proceed due to not receive keys 13/9/2025 : Plan to do IDU-IPRAN - Re-plan due to Sacofa team not available 12/9/2025 : Plan to do IDU-IPRAN - Re-plan tomorrow due to CRQ late approved | TSS+TI |  | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9645B RTN01 10G Port 9645B-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port 10Ge-SL1P6 Install 1 10G SFP Optical at HW 9645BA RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10Ge-SL1P6 to HW 9645B RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-1(to BBU01) for Traffic 9645B Reconfigure Traffic for All 2 Sites; 9645B & 9258Z Site affected : 9645B 9258Z | 9645B RTN01 10G Port 9645B-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port 10Ge-SL1P6 Install 1 10G SFP Optical at HW 9645BA RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10Ge-SL1P6 to HW 9645B RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-1(to BBU01) for Traffic 9645B Reconfigure Traffic for All 2 Sites; 9645B & 9258Z Site affected : 9645B 9258Z | N/A | [5 empty] | REDTONE | SQ202601160540-Redtone | REDTONE | SQ202601160529-Redtone |  |  | Ongoing | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | Roy//Lee/6000056316 |  | REDTONE ENGINEERING & NETWORK SERVICES SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | Roy//Lee/6000056316 |  | REDTONE ENGINEERING & NETWORK SERVICES SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080518 |  | 2025-08-06 | 2025-08-21 | Completed | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-03-10 | 2026-02-25 | 2026-02-25 | JUDIH//LAJIUM/6000057179 | REDTONE TI | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | JUDIH//LAJIUM/6000057179 | REDTONE TI | [7 empty] | 2026-02-24 | 2026-03-10 | 2026-03-16 | 2026-03-16 | JUDIH//LAJIUM/6000057179 | 2025-06-09: 2026-02-24; 2025-06-09: 2026-03-10; 2025-06-09: 2026-02-25; 2025-07-21: 2026-02-27 | [7 empty] | GCI | SQ202506160765-GCI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9380B_IPR | Teku Commercial Centre MP | DU00005690598 | Sarawak | Sarawak | 2.346968 | 111.843451 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 16/8/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | N/A | [5 empty] | Allstar | SQ202507300533-Allstar | Allstar | SQ202507290151-Allstar // SQ202512170142-Allstar | 2025-11-25 | 2025-11-28 | Completed | 2025-07-26 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Manager | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071854 |  | 2025-07-19 | 2025-08-07 | Completed | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-08-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-15 | 2025-08-22 | 2025-08-16 | 2025-08-16 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-15 | 2025-08-22 | 2025-08-19 | 2025-08-19 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-16 | 2025-08-15 | 2025-08-22 | 2025-08-19 | 2025-08-19 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-15; 2025-06-09: 2025-08-22; 2025-06-09: 2025-08-16; 2025-07-21: 2025-08-16 |  |  | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
9506A_IPR | Pakat | DU00005690599 | Sarawak | Sarawak | 3.931357 | 113.925065 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9506A RTN02 10G PORT 9506A/9506A-SACOFA LL-9074A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-3-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9506A RTN02 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-3-3 TO HW 9506A RTN02 8-EM6-3 4. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 9506A 5. RECONFIGURE TRAFFIC FOR ALL 2 SITES: 9506A, 9571A SITE AFFECTED : 9506A 9571A | 9506A RTN02 10G PORT 9506A/9506A-SACOFA LL-9074A 1. INSTALL 1 10G SFP OPTICAL AT SACOFA PORT 1-3-3 2. INSTALL 1 10G SFP OPTICAL AT HW 9506A RTN02 8-EM6-3 3. PATCHING OPTICAL PATCH CORD SACOFA PORT 1-3-3 TO HW 9506A RTN02 8-EM6-3 4. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 9506A 5. RECONFIGURE TRAFFIC FOR ALL 2 SITES: 9506A, 9571A SITE AFFECTED : 9506A 9571A | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar | 2025-10-30 | 2025-10-30 | Completed | 2025-07-10 | 2025-07-10 | 2025-07-24 | 2025-07-24 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250624FF |  | 2025-06-26 | 2025-07-01 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-26 | 2025-07-01 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-07-09 | 2025-07-15 | 2025-07-09 | 2025-07-09 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-09 | 2025-07-15 | 2025-07-08 | 2025-07-09 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-09 | 2025-07-09 | 2025-07-15 | 2025-07-15 | 2025-07-15 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-09; 2025-06-09: 2025-07-15; 2025-06-09: 2025-07-09; 2025-07-21: 2025-07-09 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
9224A_IPR | Sri Aman Town | DU00005690600 | Sarawak | Sarawak | 1.236579 | 111.460980 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | N/A | [5 empty] | Allstar | SQ202507250120-Allstar | Allstar | SQ202507140740-Allstar // SQ202512170142-Allstar | 2025-10-30 | 2025-10-30 | Completed | 2025-07-23 | 2025-07-31 | 2025-07-23 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070354 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-10 | 2025-07-16 | 2025-07-11 | 2025-07-11 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-10 | 2025-07-16 | 2025-07-11 | 2025-07-11 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-11 | 2025-07-10 | 2025-07-16 | 2025-07-15 | 2025-07-15 | KENISTON//ANAK SPANCER/6798000184 | 2025-06-09: 2025-07-10; 2025-06-09: 2025-07-16; 2025-06-09: 2025-07-11; 2025-07-21: 2025-07-11 |  |  | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
7444A_IPR | Kg Biah | DU00005690601 | Sabah | Sabah | 5.272672 | 116.161238 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 4x1G SFP Optical 10KM 4x Patch Cord(Pair) | IDU-IPRAN | 7444A RTN01 2x1G PORT 7444A/7444A-CTS LL-7000A 1. INSTALL 1 1G SFP OPTICAL AT CTS SL- 2 - K1EX10 - PORT 9 2. INSTALL 1 1G SFP OPTICAL AT CTS SL-2 - K1EX10 - PORT 10 3. INSTALL 1 1G SFP OPTICAL AT HW 7444A RTN01 8-EM6-5 4. INSTALL 1 1G SFP OPTICAL AT HW 7444A RTN01 8-EM6-6 5. PATCHING OPTICAL PATCH CORD CTS SL- 2 - K1EX10 - PORT 9 SL-2 - K1EX10 - PORT 10 TO HW 7444A RTN01 8-EM6-5 6. CONFIG 2G LAG AT RTN01 RTN910 7. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 7444A 8. RECONFIGURE TRAFFIC FOR ALL 2 SITES SITE AFFECTED : 7444A 7199R | 7444A RTN01 2x1G PORT 7444A/7444A-CTS LL-7000A 1. INSTALL 1 1G SFP OPTICAL AT CTS SL- 2 - K1EX10 - PORT 9 2. INSTALL 1 1G SFP OPTICAL AT CTS SL-2 - K1EX10 - PORT 10 3. INSTALL 1 1G SFP OPTICAL AT HW 7444A RTN01 8-EM6-5 4. INSTALL 1 1G SFP OPTICAL AT HW 7444A RTN01 8-EM6-6 5. PATCHING OPTICAL PATCH CORD CTS SL- 2 - K1EX10 - PORT 9 SL-2 - K1EX10 - PORT 10 TO HW 7444A RTN01 8-EM6-5 6. CONFIG 2G LAG AT RTN01 RTN910 7. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 7444A 8. RECONFIGURE TRAFFIC FOR ALL 2 SITES SITE AFFECTED : 7444A 7199R | N/A | [5 empty] | NR services | SQ202507160651-NR Services | NR services | SQ202507160774-NR Services | 2025-10-31 | 2025-10-31 | Completed | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070896 |  | 2025-07-09 | 2025-07-09 | Completed | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-12 | 2025-07-16 | 2025-07-12 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-12 | 2025-07-16 | 2025-07-12 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-14 | 2025-07-14 | 2025-08-14 | 2025-07-14 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-14; 2025-06-09: 2025-08-14; 2025-06-09: 2025-07-14; 2025-07-21: 2025-07-15 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
7214A_IPR | Tunggol Tinggi | DU00005690602 | Sabah | Sabah | 5.101261 | 115.567384 | [5 empty] | NO IDU decomm at site due to hardware limitation issue(confirm by Tx Support-Syukri) |  | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) 1xIDU RTN910 | MW Hardware Upgrade | 7214A RTN01 10G PORT 7214A/7214A-CTS LL-7000A 1. INSTALL NEW IDU RTN910 2. SHIFT IF CABLE 7389A-7214A EXISTING RTN01 RTN910 SLOT 7-1 TO NEW IDU SLOT 7-1 3. REPATCH BBU FROM EXISTING RTN01 TO NEW IDU 4. INSTALL 1 10G SFP OPTICAL AT CTS SL:1 - K1EX10 - PORT: 3 5. INSTALL 1 10G SFP OPTICAL AT HW 7214A RTN01 8-EM6-5 6. PATCHING OPTICAL PATCH CORD CTS SL:1 - K1EX10 - PORT: 3 TO HW 7214A RTN01 8-EM6-5 DECOM EXISTING IDU 7. RECONFIGURE TRAFFIC FOR ALL 4 SITES SITE AFFECTED : 7214A 7389A 7162R S01329 | 7214A RTN01 10G PORT 7214A/7214A-CTS LL-7000A 1. INSTALL NEW IDU RTN910 2. SHIFT IF CABLE 7389A-7214A EXISTING RTN01 RTN910 SLOT 7-1 TO NEW IDU SLOT 7-1 3. REPATCH BBU FROM EXISTING RTN01 TO NEW IDU 4. INSTALL 1 10G SFP OPTICAL AT CTS SL:1 - K1EX10 - PORT: 3 5. INSTALL 1 10G SFP OPTICAL AT HW 7214A RTN01 8-EM6-5 6. PATCHING OPTICAL PATCH CORD CTS SL:1 - K1EX10 - PORT: 3 TO HW 7214A RTN01 8-EM6-5 DECOM EXISTING IDU 7. RECONFIGURE TRAFFIC FOR ALL 4 SITES SITE AFFECTED : 7214A 7389A 7162R S01329 | N/A | [5 empty] | NR services | SQ202507310869-NR Services | NR services | SQ202507290140-NR Services // SQ202507290144-NR Services | 2025-09-18 | 2025-09-17 | Completed | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-17 | 2025-09-18 | 2025-09-17 | 2025-09-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-17 | 2025-09-18 | 2025-09-17 | 2025-09-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-17 | 2025-09-18 | 2025-09-17 | 2025-09-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072247 |  | 2025-07-23 | 2025-10-13 | Completed | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-10-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-28 | 2025-08-28 | 2025-07-28 | 2025-10-13 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-28 | 2025-08-28 | 2025-07-28 | 2025-07-31 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-29 | 2025-07-28 | 2025-08-28 | 2025-07-28 | 2025-07-31 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-28; 2025-06-09: 2025-08-28; 2025-06-09: 2025-07-28; 2025-07-21: 2025-07-29 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
9223A_IPR | Temudok Sri Aman-Core(Celcom) | DU00005690603 | Sarawak | Sarawak | 1.167829 | 111.473619 | [7 empty] | 00. Site Out/Drop | 0620: CD completed the integration with GOP. | TSS+TI |  | 1xRTN910A 2xSFP 10G 1km 1 pair patch cord 1xCat6 cable | IDU-IPRAN | 9223A LL upgraded to use 10G port. 1) Install new RTN910A 2) Patch 10G port to SACOFA LL 10G port 3) Patch 9223A BBU to new RTN GE1 4) Create DCN | 9223A LL upgraded to use 10G port. 1) Install new RTN910A 2) Patch 10G port to SACOFA LL 10G port 3) Patch 9223A BBU to new RTN GE1 4) Create DCN | [6 empty] | NR Services | No PR required-Site drop/cancel | NR Services | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | Cancel DO | 2025-06-20 |  | Ongoing | 2025-06-19 | 2025-06-20 | 2025-06-19 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing
9204B_IPR | TM Jalan Muara Tuang | DU00005690604 | Sarawak | Sarawak | 1.456371 | 110.493968 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9204B RTN01 10G Port 9204B-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-1 Install 1 10G SFP Optical at HW 9204B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-4-1 to HW 9204B RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU 9204B) for Traffic 9204B Reconfigure Traffic for All 3 Sites; 9204B,9029B,9528B, & Q00760(Pending MW IDU Switching) Site affected : 9204B 9029B 9528B Q00760(Pending MW IDU Switching) | 9204B RTN01 10G Port 9204B-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-1 Install 1 10G SFP Optical at HW 9204B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-4-1 to HW 9204B RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU 9204B) for Traffic 9204B Reconfigure Traffic for All 3 Sites; 9204B,9029B,9528B, & Q00760(Pending MW IDU Switching) Site affected : 9204B 9029B 9528B Q00760(Pending MW IDU Switching) | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar | 2025-11-25 | 2025-11-28 | Completed | 2025-07-08 | 2025-07-08 | 2025-07-15 | 2025-07-15 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250624FM |  | 2025-06-26 | 2025-07-10 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-25 | 2025-07-10 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI |  | 1.00 | Assigned | Completed |  | 2025-07-07 | 2025-07-23 | 2025-07-07 | 2025-07-11 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-09 | MOK//CHUANG YONG/6799000076 |  | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-08 | 2025-07-07 | 2025-07-23 | 2025-07-09 | 2025-07-09 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-06-09: 2025-07-08; 2025-06-09: 2025-07-14; 2025-06-09: 2025-07-08; 2025-07-21: 2025-07-08 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
7395B_IPR | Tg Labian SBC | DU00005690605 | Sabah | Sabah | 5.173592 | 119.237897 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 7395B RTN01 2x1G PORT 7395B/7395B-CTS LL-7100A 1. INSTALL 1 1G SFP OPTICAL AT CTS SL:1 - K1EX10 - PORT: 6 2. INSTALL 1 1G SFP OPTICAL AT HW 7395B RTN01 8-EM6-5 3. PATCHING OPTICAL PATCH CORD CTS SL:1 - K1EX10 - PORT: 6 TO HW 7395B RTN01 8-EM6-5 4. CONFIG 2G LAG AT RTN01 RTN910 5. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 7569A 6. RECONFIGURE TRAFFIC FOR ALL 3 SITES SITE AFFECTED : 7395B 7223R 7224R | 7395B RTN01 2x1G PORT 7395B/7395B-CTS LL-7100A 1. INSTALL 1 1G SFP OPTICAL AT CTS SL:1 - K1EX10 - PORT: 6 2. INSTALL 1 1G SFP OPTICAL AT HW 7395B RTN01 8-EM6-5 3. PATCHING OPTICAL PATCH CORD CTS SL:1 - K1EX10 - PORT: 6 TO HW 7395B RTN01 8-EM6-5 4. CONFIG 2G LAG AT RTN01 RTN910 5. REMAIN PATCH 8-EM6-2(to BBU01) FOR TRAFFIC 7569A 6. RECONFIGURE TRAFFIC FOR ALL 3 SITES SITE AFFECTED : 7395B 7223R 7224R | N/A | [5 empty] | NR services | SQ202507230743-NR Services | NR services | SQ202507190103-NR Services | 2025-10-31 | 2025-10-31 | Completed | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-08-01 | 2025-07-31 | 2025-07-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-31 | 2025-08-01 | 2025-07-31 | 2025-07-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250708A1 |  | 2025-07-09 | 2025-07-09 | Completed | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-21 | 2025-08-21 | 2025-07-21 | 2025-07-21 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-21 | 2025-08-21 | 2025-07-21 | 2025-07-22 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-21 | 2025-07-21 | 2025-08-21 | 2025-07-21 | 2025-07-21 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-21; 2025-06-09: 2025-08-21; 2025-06-09: 2025-07-21; 2025-07-21: 2025-07-21 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
9964A_IPR | Unimas (REL) | DU00005690606 | Sarawak | Sarawak | 1.458582 | 110.449531 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP module x2. ISM8 x2. Fiber Patch Cord x 1 pairs | IDU-IPRAN | Site affected 9964A , 9030C , 9316K , 9315K/Q01051 , 9314K NE_9964A 1.Install new 10G SFP module at existing 9964A_RTN01_GE3 (ID : 24212). 2.Install new 10G SFP Module at new Sacofa 10G Port_1-3-3. 3.Install new 3_ISM8 and 4_ISM8 into existing 9964A_RTN01 (ID : 24212). 4.Transfer traffic 9315K/Q01051 (IF cable) to new 3_ISM8 at existing 9964A_RTN01. 5.Transfer traffic 9314K (IF cable) to new 4_ISM8 at existing 9964A_RTN01. 6.Patching Fiber patch cord from 9964A_RTN01_GE3 to new 10G Sacofa port_1-3-3. 7.Disconnect existing LAN cable to Old Sacofa port and disable unused port. 8.Create service cross connect and migrate entire traffic to new sacofa 10G port_1-3-3. | Site affected 9964A , 9030C , 9316K , 9315K/Q01051 , 9314K NE_9964A 1.Install new 10G SFP module at existing 9964A_RTN01_GE3 (ID : 24212). 2.Install new 10G SFP Module at new Sacofa 10G Port_1-3-3. 3.Install new 3_ISM8 and 4_ISM8 into existing 9964A_RTN01 (ID : 24212). 4.Transfer traffic 9315K/Q01051 (IF cable) to new 3_ISM8 at existing 9964A_RTN01. 5.Transfer traffic 9314K (IF cable) to new 4_ISM8 at existing 9964A_RTN01. 6.Patching Fiber patch cord from 9964A_RTN01_GE3 to new 10G Sacofa port_1-3-3. 7.Disconnect existing LAN cable to Old Sacofa port and disable unused port. 8.Create service cross connect and migrate entire traffic to new sacofa 10G port_1-3-3. | [6 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar | 2026-01-14 | 2026-01-13 | Completed | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082865 |  | 2025-08-29 | 2025-09-12 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-12 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-30 | 2025-10-24 | 2025-10-24 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-24 | 2025-10-30 | 2025-10-30 | 2025-10-30 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-24 | 2025-10-24 | 2025-10-30 | 2025-10-30 | 2025-10-30 | ROYSTON//ANAK RAMSY/6798000228 | 2025-06-09: 2025-10-24; 2025-06-09: 2025-10-30; 2025-06-09: 2025-10-24; 2025-07-21: 2025-10-24 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202507250611-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | CHEONG/SENG/WAH/7018000306
9446A_IPR | Serikin(Sacofa) | DU00005690607 | Sarawak | Sarawak | 1.329220 | 110.005730 | [6 empty] | ZTE | 00. Site Out/Drop |  | TSS+TI |  | 10G SFP module x2. Fiber patch cord x1 pairs | IDU-IPRAN | Site affected 9446A , 9539B NE_9446A. 1.Install new 10G SFP module at existing 9446A_RTN01_GE3 (ID : 20552). 2.Install new 10G SFP module at new Sacofa Port.Pending Port info from Sacofa. 3.Patching Fiber patch cord from 9446A_RTN01_GE3 to new sacofa port. 4.Disconnect existing LAN cable to Old sacofa port and disable unused port. 5.Create service cross connect and migrate traffic new sacofa port. | Site affected 9446A , 9539B NE_9446A. 1.Install new 10G SFP module at existing 9446A_RTN01_GE3 (ID : 20552). 2.Install new 10G SFP module at new Sacofa Port.Pending Port info from Sacofa. 3.Patching Fiber patch cord from 9446A_RTN01_GE3 to new sacofa port. 4.Disconnect existing LAN cable to Old sacofa port and disable unused port. 5.Create service cross connect and migrate traffic new sacofa port. | [6 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25082866 |  | 2025-08-29 | 2025-09-12 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-12 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202507250611-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | CHEONG/SENG/WAH/7018000306
7343A_IPR | SMK Tambunan | DU00005690608 | Sabah | Sabah | 5.723281 | 116.401028 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 7343A RTN01 10G Port 7343A-LL CTS-7000A Install 1 10G SFP Optical at SACOFA Port SL:1 - K1EX10 - PORT: 2 Install 1 10G SFP Optical at HW 7343A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE SL:1 - K1EX10 - PORT: 2 to HW 7343A RTN01 8-EM6-3(PORT-3) Transfer Patch from 7343A RTN02 8-EM6-1(to ZTE BBU ETH5) to 7343A RTN01 8-EM6-1(Rename as BBU 7343A) Remain Patch 8-EM6-5(to RTN02 GE5) for Traffic xxxxA Remain Patch 8-EM6-6(to RTN03 GE5) for Traffic xxxxA Remove LAG Port Configuration 8-EM6-1 & 8-EM6-2 Reconfigure Traffic for All 3 Sites; 7343A, 7288R, 7358A, 7344A, 7435A, 7568B & 7329C Site affected : 7343A 7288R 7358A 7344A 7435A 7568B 7329C | 7343A RTN01 10G Port 7343A-LL CTS-7000A Install 1 10G SFP Optical at SACOFA Port SL:1 - K1EX10 - PORT: 2 Install 1 10G SFP Optical at HW 7343A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE SL:1 - K1EX10 - PORT: 2 to HW 7343A RTN01 8-EM6-3(PORT-3) Transfer Patch from 7343A RTN02 8-EM6-1(to ZTE BBU ETH5) to 7343A RTN01 8-EM6-1(Rename as BBU 7343A) Remain Patch 8-EM6-5(to RTN02 GE5) for Traffic xxxxA Remain Patch 8-EM6-6(to RTN03 GE5) for Traffic xxxxA Remove LAG Port Configuration 8-EM6-1 & 8-EM6-2 Reconfigure Traffic for All 3 Sites; 7343A, 7288R, 7358A, 7344A, 7435A, 7568B & 7329C Site affected : 7343A 7288R 7358A 7344A 7435A 7568B 7329C | N/A | [5 empty] | NR services | SQ202507160651-NR Services | NR services | SQ202507140729-NR Services | 2025-11-01 | 2025-10-31 | Completed | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-16 | 2025-07-17 | 2025-07-16 | 2025-07-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-16 | 2025-07-17 | 2025-07-16 | 2025-07-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-11-01 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250708A4 |  | 2025-07-09 | 2025-07-09 | Completed | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-12 | 2025-07-16 | 2025-07-12 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-12 | 2025-07-16 | 2025-07-12 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-14 | 2025-07-14 | 2025-08-14 | 2025-07-14 | 2025-07-15 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-14; 2025-06-09: 2025-08-14; 2025-06-09: 2025-07-14; 2025-07-21: 2025-07-15 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9105A_IPR | Kemena (SACOFA) | DU00005690609 | Sarawak | Sarawak | 3.151466 | 113.100311 | [6 empty] | ZTE | 00. Integrated/RFS Done | 30/9/2025 : Cutover done 29/9/2025 : Plan to do IDU-IPRAN - Cancel proceed | TSS+AA+TI | L1+ATP+PAC | NE_9105A 10G SFP Module x2. ISM8 x2. Fiber patch cord x 1 (pairs). | IDU-IPRAN | Site affected 9718B , 9266R , 9254R , 9105A , 9999B. 9999B-9105A is using NEC link. NE_9105A 1.Install new 10G SFP Module at 9105A_RTN02_GE3 (ID : 24070). 2.Install new 10G SFP at new Sacofa Port 10G_1-4-1. 3.Install new 3_ISM8-2+0 into existing 9105A_RTN02 (ID : 24070). Carry child site 9254R. 4.Install new 4_ISM8-2+0 into existing 9105A_RTN02 (ID 24070).Carry child site 9266R. 5.Transfer existing IF cable from 9105A_RTN01_7_ISM8-2+0 (ID 20494) to new 3_ISM8-2+0 into existing 9105A_RTN02 (ID : 24070). 6.Transfer existing IF cable from 9105A_RTN03_7_ISM8-2+0 (ID 22812) to new 4_ISM8-2+0 into existing 9105A_RTN02 (ID : 24070). 7.Disconnect existing LAN cable to Old sacaofa port and disable unused port. 8.Patching Fiber patch cord 10G port from 9105A_RTN02_GE3 (ID : 24070) to new Sacofa Port 10G_1-4-1. 9.Create cross connect and migrate entire traffic to new sacofa port 10GE_1-4-1. 10.Create New In band DCN. | Site affected 9718B , 9266R , 9254R , 9105A , 9999B. 9999B-9105A is using NEC link. NE_9105A 1.Install new 10G SFP Module at 9105A_RTN02_GE3 (ID : 24070). 2.Install new 10G SFP at new Sacofa Port 10G_1-4-1. 3.Install new 3_ISM8-2+0 into existing 9105A_RTN02 (ID : 24070). Carry child site 9254R. 4.Install new 4_ISM8-2+0 into existing 9105A_RTN02 (ID 24070).Carry child site 9266R. 5.Transfer existing IF cable from 9105A_RTN01_7_ISM8-2+0 (ID 20494) to new 3_ISM8-2+0 into existing 9105A_RTN02 (ID : 24070). 6.Trafsfer existing IF cable from 9105A_RTN03_7_ISM8-2+0 (ID 22812) to new 4_ISM8-2+0 into existing 9105A_RTN02 (ID : 24070). 7.Disconnect existing LAN cable to Old sacaofa port and disable unused port. 8.Patching Fiber patch cord 10G port from 9105A_RTN02_GE3 (ID : 24070) to new Sacofa Port 10G_1-4-1. 9.Create cross connect and migrate entire traffic to new sacofa port 10GE_1-4-1. 10.Create New Inband DCN. | [6 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar // SQ202512170142-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082867 |  | 2025-08-29 | 2025-09-10 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-29 | 2025-10-06 | 2025-09-30 | 2025-09-30 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-13 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-30 | 2025-09-29 | 2025-10-06 | 2025-10-05 | 2025-10-11 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-09-29; 2025-06-09: 2025-10-06; 2025-06-09: 2025-09-30; 2025-07-21: 2025-09-30 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250611-GCI | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | CHEONG/SENG/WAH/7018000306
9362A_IPR | Oya | DU00005690610 | Sarawak | Sarawak | 2.857960 | 111.876380 | [7 empty] | 05. Doable |  | TSS+TI |  | NE_9326A 10G SFP Module x2 Fiber patch cord x1 (pairs) | BBU Patching | Site Affected 9326A NE_9326A 1.Install new 10G SFP Module at new sacofa port 10G_1-4-1. 2.Install new 10G SFP Module at 9326A_BBU ( port will be provide by OPS team). 3.Patching Fiber patch cord 10G from 9326A_BBU to new sacofa port 10G_1-4-1. | Site Affected 9326A NE_9326A 1.Install new 10G SFP Module at new sacofa port 10G_1-4-1. 2.Install new 10G SFP Module at 9326A_BBU ( port will be provide by OPS team). 3.Patching Fiber patch cord 10G from 9326A_BBU to new sacofa port 10G_1-4-1. | [6 empty] | Allstar | SQ202508200601-Allstar | Allstar | SQ202508200599-Allstar // SQ202512170142-Allstar |  |  | Ongoing | 2026-04-29 | 2026-05-05 | 2026-04-29 | 2026-04-29 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-05-05 | 2026-04-29 | 2026-04-29 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25081385 |  | 2025-08-14 | 2025-09-29 | Completed | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-09-29 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-30 | 2025-11-20 | 2025-11-20 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-10-24 | 2025-10-30 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | [7 empty] | 2025-10-24 | 2025-10-30 |  |  | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-10-24; 2025-06-09: 2025-10-30; 2025-06-09: 2025-11-20; 2025-07-21: 2025-11-20 | [7 empty] | GCI | SQ202507250611-GCI | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | CHEONG/SENG/WAH/7018000306
9641A_IPR | Long Tuma | DU00005690611 | Sarawak | Sarawak | 4.809721 | 115.405400 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 18/9/2025 : Plan to do IDU-IPRAN - Hold due to Sacofa port not ready 13/9/2025 : Plan to do IDU-IPRAN - Re-plan due to Sacofa team not available 12/9/2025 : Plan to do IDU-IPRAN - Re-plan tomorrow due to CRQ late approved | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9641A RTN01(Under DU 9641A_EB) - Understanding that using RTN910A with CSHRF (with 10G Port-Ready) 10G Port 9641A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port sfp+ sl1p3 Install 1 10G SFP Optical at HW 9641A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port sfp+ sl1p3 to HW 9641A RTN01 8-EM6-3(PORT-3) (Old Port GE1 to Existing LL Port to be Dismantle and Shut Down) Transfer Patch EB Site to Any RTN Port Available (Suggestion GE1 port) Transfer Patch BBU to Any RTN Port Available (Suggestion GE2 port) Transfer Patch NEC IDU to Any RTN Port Available (Suggestion GE4 port) - Require Electrical SFP Reconfigure Traffic for All Sites | 9641A RTN01(Under DU 9641A_EB) - Understanding that using RTN910A with CSHRF (with 10G Port-Ready) 10G Port 9641A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port sfp+ sl1p3 Install 1 10G SFP Optical at HW 9641A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port sfp+ sl1p3 to HW 9641A RTN01 8-EM6-3(PORT-3) (Old Port GE1 to Existing LL Port to be Dismantle and Shut Down) Transfer Patch EB Site to Any RTN Port Available (Suggestion GE1 port) Transfer Patch BBU to Any RTN Port Available (Suggestion GE2 port) Transfer Patch NEC IDU to Any RTN Port Available (Suggestion GE4 port) - Require Electrical SFP Reconfigure Traffic for All Sites | N/A | [5 empty] | REDTONE | SQ202601160540-Redtone | REDTONE | SQ202601160529-Redtone | 2026-01-23 | 2026-01-23 | Completed | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | CHAI//SONG YU/6237000310 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080519 |  | 2025-08-06 | 2025-08-21 | Completed | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-28 | 2026-02-26 | 2026-02-26 | ALEXANDER SIGAR BALANG7667000013 | REDTONE TI | 2026-01-14 | 2026-01-28 | 2026-02-19 | 2026-02-27 | ALEXANDER SIGAR BALANG7667000013 | REDTONE TI | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-01-14 | 2026-01-28 | 2026-02-19 | 2026-03-01 | ALEXANDER SIGAR BALANG7667000013 | 2025-06-09: 2026-01-14; 2025-06-09: 2026-01-28; 2025-06-09: 2026-01-26; 2025-07-21: 2026-01-27 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
7623B_IPR | Bandar Fajar Harapan | DU00005690612 | Sabah | Sabah | 5.230101 | 119.203286 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 7623B RTN06 10G Port 7623B-LL CTS-7100A 1. 7623B_IPR : LL 10G Port Upgrade to CTS - Install 1 10G SFP Optical at SACOFA Port SL:14 -K1EX10- PORT: 5 - Install 1 10G SFP Optical at HW 7623B RTN06 8-EM6-3(PORT-3) - Patching Optical Patch Cord SACOFA Port 10GE SL:14 -K1EX10- PORT: 5 to HW 7623B RTN06 8-EM6-3(PORT-3) 2. 7623B_IPR_1 : BBU Patching to RTN06 (Additional DU) - Transfer Patch from 7623B RTN05 8-EM6-1(to 2G,3G,4G BBU) to 7623B RTN06 8-EM6-1(Rename as BBU 7623B) 3. 7623B_IPR_2 : Hardware Upgrade (10G Port RTN04-RTN06 & Decom RTN02 RTN950A) i. 10G Port Upgrade to 7623B RTN04 to 7623B RTN06 - Install 1 10G SFP Optical at HW 7623B RTN04 8-EM6-4(PORT-4) - Rename as Cascade RTN04 to RTN06 - Install 1 10G SFP Optical at HW 7623B RTN06 8-EM6-4(PORT-4) - Rename as Cascade RTN06 to RTN04 - Patching Optical Patch Cord HW 7623B RTN04 8-EM6-4(PORT-4) to HW 7623B RTN06 8-EM6-4(PORT-4) ii. Decom 7623B RTN02 IDU RTN950A Reconfigure Traffic for All 10 Sites; 7623B, 7146K, 7363B, 7109K, 7357B, 7511A, 7510A, 7475B, S00331 & 7482B Site affected : 7623B 7146K 7363B 7109K 7357B 7511A 7510A 7475B S00331 7482B | 7623B RTN06 10G Port 7623B-LL CTS-7100A 1. 7623B_IPR : LL 10G Port Upgrade to CTS - Install 1 10G SFP Optical at SACOFA Port SL:14 -K1EX10- PORT: 5 - Install 1 10G SFP Optical at HW 7623B RTN06 8-EM6-3(PORT-3) - Patching Optical Patch Cord SACOFA Port 10GE SL:14 -K1EX10- PORT: 5 to HW 7623B RTN06 8-EM6-3(PORT-3) 2. 7623B_IPR_1 : BBU Patching to RTN06 (Additional DU) - Transfer Patch from 7623B RTN05 8-EM6-1(to 2G,3G,4G BBU) to 7623B RTN06 8-EM6-1(Rename as BBU 7623B) 3. 7623B_IPR_2 : Hardware Upgrade (10G Port RTN04-RTN06 & Decom RTN02 RTN950A) i. 10G Port Upgrade to 7623B RTN04 to 7623B RTN06 - Install 1 10G SFP Optical at HW 7623B RTN04 8-EM6-4(PORT-4) - Rename as Cascade RTN04 to RTN06 - Install 1 10G SFP Optical at HW 7623B RTN06 8-EM6-4(PORT-4) - Rename as Cascade RTN06 to RTN04 - Patching Optical Patch Cord HW 7623B RTN04 8-EM6-4(PORT-4) to HW 7623B RTN06 8-EM6-4(PORT-4) ii. Decom 7623B RTN02 IDU RTN950A Reconfigure Traffic for All 10 Sites; 7623B, 7146K, 7363B, 7109K, 7357B, 7511A, 7510A, 7475B, S00331 & 7482B Site affected : 7623B 7146K 7363B 7109K 7357B 7511A 7510A 7475B S00331 7482B | N/A | [5 empty] | NR services | SQ202507230743-NR Services | NR services | SQ202507190103-NR Services | 2026-02-13 | 2026-02-12 | Completed | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-08-01 | 2025-07-31 | 2025-07-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-31 | 2025-08-01 | 2025-07-31 | 2025-07-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250708A0 |  | 2025-07-09 | 2025-07-09 | Completed | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-21 | 2025-08-21 | 2025-07-21 | 2025-07-21 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-21 | 2025-08-21 | 2025-07-21 | 2025-07-22 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-21 | 2025-07-21 | 2025-08-21 | 2025-07-21 | 2025-07-27 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-21; 2025-06-09: 2025-08-21; 2025-06-09: 2025-07-21; 2025-07-21: 2025-07-24 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
7073A_IPR | Wisma Wong Wo Lo | DU00005690613 | Sabah | Sabah | 5.299399 | 115.241062 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 2x Patch Cord(Pair) | IDU-IPRAN | 7073A RTN01 1G x2 (LAG) Port 7073A-LL CTS-7100A Install 1 x 1G SFP Optical at CTS Port SL3-EG4C-PORT: 3 Install 1 x 1G SFP Optical at HW 7073A RTN01 8-EG6-5(PORT-5) - Name as LAG2 to CTS Port SL3-EG4C-PORT: 3 Patching Optical Patch Cord CTS Port SL3-EG4C-PORT: 3 to HW 7073A RTN01 8-EG6-5(PORT-5) Remain Patch 8-EG6-1(CTS - Rename as LAG1 to CTS Port (M)) Remain Patch 8-EG6-2(To RTN02 GE1) For Traffic 7151D Transfer Patch from 7073A RTN02 8-EG6-2(To Port BBU01) to 7073A RTN01 8-EG6-3 For Traffic 7073A - Rename as BBU 7073A Configure LAG Port for Both 8-EG6-5(PORT-5) & 8-EG6-1(PORT-1) Reconfigure Traffic for All 3 Sites; 7073A, 7151D & 7272C Site affected : 7073A 7151D 7272C | 7073A RTN01 1G x2 (LAG) Port 7073A-LL CTS-7100A Install 1 x 1G SFP Optical at CTS Port SL3-EG4C-PORT: 3 Install 1 x 1G SFP Optical at HW 7073A RTN01 8-EG6-5(PORT-5) - Name as LAG2 to CTS Port SL3-EG4C-PORT: 3 Patching Optical Patch Cord CTS Port SL3-EG4C-PORT: 3 to HW 7073A RTN01 8-EG6-5(PORT-5) Remain Patch 8-EG6-1(CTS - Rename as LAG1 to CTS Port (M)) Remain Patch 8-EG6-2(To RTN02 GE1) For Traffic 7151D Transfer Patch from 7073A RTN02 8-EG6-2(To Port BBU01) to 7073A RTN01 8-EG6-3 For Traffic 7073A - Rename as BBU 7073A Configure LAG Port for Both 8-EG6-5(PORT-5) & 8-EG6-1(PORT-1) Reconfigure Traffic for All 3 Sites; 7073A, 7151D & 7272C Site affected : 7073A 7151D 7272C | N/A | [5 empty] | NR services | SQ202508040498-NR Services | NR services | SQ202507190103-NR Services | 2025-11-10 | 2025-11-10 | Completed | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070899 |  | 2025-07-09 | 2025-07-09 | Completed | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-04 | 2025-09-04 | 2025-08-04 | 2025-08-04 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-08-04 | 2025-09-04 | 2025-08-04 | 2025-08-05 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-05 | 2025-08-04 | 2025-09-04 | 2025-08-04 | 2025-08-06 | RALPH O'BRYAN HILARY7167000030 | 2025-06-09: 2025-08-04; 2025-06-09: 2025-09-04; 2025-06-09: 2025-08-04; 2025-07-21: 2025-08-04 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9468A_IPR | Kem Putra Sentosa | DU00005690614 | Sarawak | Sarawak | 1.801574 | 109.770429 | [6 empty] | ZTE | 00. Integrated/RFS Done | 8/10/25: Port Ready 1-2-2 update by sacofa PIC 11/9/2025 : Hold - LAG full. Need to upgrade/add LAG by GOP | TSS+TI | L1+ATP+PAC | NE_9468A 10G SFP module x4. ISM8 x2. Fiber patch cord x 2 pairs | MW IDU Patching | Site affected : 9468A , 9299B , 9064R , 9476P/Q01786 , 9341K/Q01686 , Q01687. NE_9468A 1.Install new 10G SFP module at existing 9468A_RTN01_GE3 & GE4 (ID : 24187). 2.Install new 10G SFP module at new Sacofa Port. Pending Sacofa port info. 3.Install 10G SFP module at existing 9468A_RTN04_GE3. 4.Install new 3_ISM8-1+0 into existing 9468A_RTN01 (ID: 24187), and move the IF cable from 9468A_RTN02 (ID: 24200) to 9468A_RTN01 to carry traffic for the 9476P/Q01786 and 9341K/Q01686 sites. 5.Install new 4_ISM8-1+0 into existing 9468A_RTN01 (ID : 24187), and move the IF cable from 9468A_RTN04 (ID : 24391) to 9468A_RTN01 to carry traffic for the 9789B. 6.Patching Fiber patch cord from 10G 9468A_RTN01_GE4 to 9468A_RTN04_GE3. (IDU Interconnect). 7.Patching Fiber patch cord from 10G 9468A_RTN01_GE3 to 10G new sacofa port. 8.Disconnect ETH cable to Old Sacofa & Cisco Ports & Old Interconnect IDU LAN cable and disable unused port. 9.Create service cross connect and migrate entire traffic to new sacofa port. | Site affected : 9468A , 9299B , 9064R , 9476P/Q01786 , 9341K/Q01686 , Q01687. NE_9468A 1.Install new 10G SFP module at existing 9468A_RTN01_GE3 & GE4 (ID : 24187). 2.Install new 10G SFP module at new Sacofa Port. Pending Sacofa port info. 3.Install 10G SFP module at existing 9468A_RTN04_GE3. 4.Install new 3_ISM8-1+0 into existing 9468A_RTN01 (ID: 24187), and move the IF cable from 9468A_RTN02 (ID: 24200) to 9468A_RTN01 to carry traffic for the 9476P/Q01786 and 9341K/Q01686 sites. 5.Install new 4_ISM8-1+0 into existing 9468A_RTN01 (ID : 24187), and move the IF cable from 9468A_RTN04 (ID : 24391) to 9468A_RTN01 to carry traffic for the 9789B. 6.Patching Fiber patch cord from 10G 9468A_RTN01_GE4 to 9468A_RTN04_GE3. (IDU Interconnect). 7.Patching Fiber patch cord from 10G 9468A_RTN01_GE3 to 10G new sacofa port. 8.Disconnect ETH cable to Old Sacofa & Cisco Ports & Old Interconnect IDU LAN cable and disable unused port. 9.Create service cross connect and migrate entire traffic to new sacofa port. | [6 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar | 2025-12-22 | 2025-12-23 | Completed | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082868 |  | 2025-08-29 | 2025-09-10 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-15 | 2025-10-21 | 2025-10-16 | 2025-10-16 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-15 | 2025-10-21 | 2025-10-20 | 2025-10-20 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-17 | 2025-10-15 | 2025-10-21 | 2025-10-24 | 2025-10-24 | ROYSTON//ANAK RAMSY/6798000228 | 2025-06-09: 2025-10-15; 2025-06-09: 2025-10-21; 2025-06-09: 2025-10-16; 2025-07-21: 2025-10-16 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202507250611-GCI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | CHEONG/SENG/WAH/7018000306
9734B_IPR | Park City Commercial 2 (REL) | DU00005690615 | Sarawak | Sarawak | 3.186917 | 113.039100 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar | 2025-11-25 | 2025-11-28 | Completed | 2025-07-21 | 2025-07-21 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070967 |  | 2025-07-10 | 2025-07-15 | Completed | 2025-07-09 | 2025-07-10 | 2025-07-09 | 2025-07-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-28 | 2025-08-04 | 2025-07-30 | 2025-07-30 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-28 | 2025-08-04 | 2025-07-30 | 2025-07-30 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-29 | 2025-07-28 | 2025-08-04 | 2025-07-31 | 2025-07-31 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-28; 2025-06-09: 2025-08-04; 2025-06-09: 2025-07-28; 2025-07-21: 2025-07-28 |  |  | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9151B_IPR | TM Demak Laut (REL) | DU00005690616 | Sarawak | Sarawak | 1.589837 | 110.411181 | [6 empty] | ZTE | 00. Site Out/Drop |  | TSS+TI |  | NE_9151B_RTN01. 10G SFP x2. ISM8 x1 Fiber patch cord x1 (pairs). | IDU-IPRAN | Site affected 9325K/Q01669 , 9160B NE_9151B_RTN01 1.Install new 10G SFP Module at 9151B_RTN01_GE3 (ID : 24117). 2.Install new 10G SFP Module at new Sacofa port 10GE 1-2-1 – with sfp. 3.Install new 3_ISM8 into existing 9151B_RTN01 (ID : 24117).Carry child site 9106B. 4.Transfer IF cable from existing 9151B_RTN02 (ID : 24297) ,7_ISM8-1+0 to 9151B_RTN01 (ID : 24117) , 3_ISM8-1+0. 7.Disconnect existing LAN cable to Old sacaofa port and disable unused port. 8.Patching Fiber patch cord 10G port from 9151B_RTN01_GE3 (ID : 24117) to new Sacofa Port 10G_1-2-1. 9.Create cross connect and migrate entire traffic to new sacofa port 10GE_1-2-1. 10.Create New In band DCN. | Site affected 9325K/Q01669 , 9160B NE_9151B_RTN01 1.Install new 10G SFP Module at 9151B_RTN01_GE3 (ID : 24117). 2.Install new 10G SFP Module at new Sacofa port 10GE 1-2-1 – with sfp. 3.Install new 3_ISM8 into existing 9151B_RTN01 (ID : 24117).Carry child site 9106B. 4.Transfer IF cable from existing 9151B_RTN02 (ID : 24297) ,7_ISM8-1+0 to 9151B_RTN01 (ID : 24117) , 3_ISM8-1+0. 7.Disconnect existing LAN cable to Old sacaofa port and disable unused port. 8.Patching Fiber patch cord 10G port from 9151B_RTN01_GE3 (ID : 24117) to new Sacofa Port 10G_1-2-1. 9.Create cross connect and migrate entire traffic to new sacofa port 10GE_1-2-1. 10.Create New In band DCN. | [6 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25082871 |  | 2025-08-29 | 2025-09-12 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-12 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202507250611-GCI | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | CHEONG/SENG/WAH/7018000306
9542A_IPR | Beluru Town | DU00005690617 | Sarawak | Sarawak | 3.976328 | 114.099708 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 15/8/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9542A RTN02 10G Port 9542A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port 10Ge-1-4-1 Install 1 10G SFP Optical at HW 9542A RTN02 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 10Ge-1-4-1 to HW 9542A RTN02 8-EM6-3(PORT-3) Remain Patch 8-EM6-1(NEC 9966A P3) for Traffic 9966A Transfer Patch BBU 9542A from NEC Port to HUAWEI 9542A RTN02 Patch 8-EM6-2(Rename as BBU 9542A) for Traffic 9542A - To Verify at NEC On Site Reconfigure Traffic for All 2 Sites; 9542A & 9966A Site affected : 9542A 9966A | 9542A RTN02 10G Port 9542A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port 10Ge-1-4-1 Install 1 10G SFP Optical at HW 9542A RTN02 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 10Ge-1-4-1 to HW 9542A RTN02 8-EM6-3(PORT-3) Remain Patch 8-EM6-1(NEC 9966A P3) for Traffic 9966A Transfer Patch BBU 9542A from NEC Port to HUAWEI 9542A RTN02 Patch 8-EM6-2(Rename as BBU 9542A) for Traffic 9542A - To Verify at NEC On Site Reconfigure Traffic for All 2 Sites; 9542A & 9966A Site affected : 9542A 9966A | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar | 2025-11-25 | 2025-11-28 | Completed | 2025-07-11 | 2025-07-11 | 2025-07-15 | 2025-07-15 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250624FG |  | 2025-06-26 | 2025-07-01 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-26 | 2025-07-01 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-20 | 2025-07-14 | 2025-07-14 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-14 | 2025-07-20 | 2025-08-19 | 2025-08-19 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-16 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-16 | 2025-07-14 | 2025-07-20 | 2025-08-17 | 2025-08-17 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-14; 2025-06-09: 2025-07-20; 2025-06-09: 2025-07-14; 2025-07-21: 2025-07-14 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9272A_IPR | Bintangor Sacofa | DU00005690618 | Sarawak | Sarawak | 2.167348 | 111.633090 | [6 empty] | ZTE | 00. Integrated/RFS Done | 20/8/2025 : Cutover done, pending NMS only to declare 19/8/2025 : Plan to do IDU-IPRAN - cancel proceed | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9272A RTN01 10G Port 9272A-LL SACOFA-9368A Install 1 10G SFP Optical at SACOFA Port 1-2-16 Install 1 10G SFP Optical at HW 9272A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-16 to HW 9272A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU) for Traffic 9272A Reconfigure Traffic for All 4 Sites; 9272A, 9030R, 9015R & 9697C Site affected : 9272A 9030R 9015R 9697C | 9272A RTN01 10G Port 9272A-LL SACOFA-9368A Install 1 10G SFP Optical at SACOFA Port 1-2-16 Install 1 10G SFP Optical at HW 9272A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-16 to HW 9272A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU) for Traffic 9272A Reconfigure Traffic for All 4 Sites; 9272A, 9030R, 9015R & 9697C Site affected : 9272A 9030R 9015R 9697C | N/A | [5 empty] | Allstar | SQ202507300533-Allstar | Allstar | SQ202507290151-Allstar // SQ202512170142-Allstar | 2025-09-22 | 2025-09-22 | Completed | 2025-07-29 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071857 |  | 2025-07-19 | 2025-08-07 | Completed | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-08-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-19 | 2025-08-26 | 2025-08-20 | 2025-08-20 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-19 | 2025-08-26 | 2025-08-26 | 2025-08-26 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-08-19 | 2025-08-26 | 2025-08-26 | 2025-08-26 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-19; 2025-06-09: 2025-08-26; 2025-06-09: 2025-08-20; 2025-07-21: 2025-08-20 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
7669B_IPR | Kg Melati | DU00005690619 | Sabah | Sabah | 4.372755 | 117.821326 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 7669B RTN01 10G Port 7669BA-LL CTS-7205A Install 1 10G SFP Optical at CTS Port SL:2 - K1EX10 - PORT:2 Install 1 10G SFP Optical at HW 7669B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port SL:2 - K1EX10 - PORT:2 to HW 7669B RTN01 8-EM6-3(PORT-3) Transfer Patch from 7669B RTN04 7-EM10-1 (BBU 7669B) to 7669B RTN01 8-EM6-5 (Rename as BBU 7669B) ; BBU Port To Reuse SFP Electrical from 7669B RTN01 8-EM6-6 Remain Patch 7669B RTN01 8-EM6-1(Rename as Cascade to RTN04) Remain Patch 7669B RTN01 8-EM6-1(Rename as Cascade to RTN02) Reconfigure Traffic for All 7 Sites; 7669B, S01957, 7622A, 7642B, 7667B, 7642B & 7029K Impacted Sites : 7669B S01957 7622A 7642B 7667B 7642B 7029K | 7669B RTN01 10G Port 7669BA-LL CTS-7205A Install 1 10G SFP Optical at CTS Port SL:2 - K1EX10 - PORT:2 Install 1 10G SFP Optical at HW 7669B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port SL:2 - K1EX10 - PORT:2 to HW 7669B RTN01 8-EM6-3(PORT-3) Transfer Patch from 7669B RTN04 7-EM10-1 (BBU 7669B) to 7669B RTN01 8-EM6-5 (Rename as BBU 7669B) ; BBU Port To Reuse SFP Electrical from 7669B RTN01 8-EM6-6 Remain Patch 7669B RTN01 8-EM6-1(Rename as Cascade to RTN04) Remain Patch 7669B RTN01 8-EM6-1(Rename as Cascade to RTN02) Reconfigure Traffic for All 7 Sites; 7669B, S01957, 7622A, 7642B, 7667B, 7642B & 7029K Impacted Sites : 7669B S01957 7622A 7642B 7667B 7642B 7029K | N/A | [5 empty] | NR services | SQ202508250338-NR Services | NR services | SQ202507190103-NR Services | 2025-11-11 | 2025-11-10 | Completed | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250708A5 |  | 2025-07-09 | 2025-07-09 | Completed | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-18 | 2025-08-18 | 2025-07-18 | 2025-08-20 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-07-18 | 2025-08-18 | 2025-07-18 | 2025-08-20 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-20 | 2025-07-18 | 2025-08-18 | 2025-07-18 | 2025-08-20 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-07-18; 2025-06-09: 2025-08-18; 2025-06-09: 2025-07-18; 2025-07-21: 2025-08-20 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9364A_IPR | Ulu Sg Merah (SACOFA) | DU00005690620 | Sarawak | Sarawak | 2.329164 | 111.864771 | [6 empty] | ZTE | 00. Integrated/RFS Done | 16/8/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9364A RTN01 10G Port 9364A-LL SACOFA-9368A Install 1 10G SFP Optical at SACOFA Port 10GE-1-2-1 Install 1 10G SFP Optical at HW 9364A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE-1-2-1 to HW 9364A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-4(to 9280B Port 4) for Traffic 9364A & 9280B Reconfigure Traffic for All 3 Sites; 9364A, 9715B & 9280B Site affected : 9364A 9715B 9280B | 9364A RTN01 10G Port 9364A-LL SACOFA-9368A Install 1 10G SFP Optical at SACOFA Port 10GE-1-2-1 Install 1 10G SFP Optical at HW 9364A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE-1-2-1 to HW 9364A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-4(to 9280B Port 4) for Traffic 9364A & 9280B Reconfigure Traffic for All 3 Sites; 9364A, 9715B & 9280B Site affected : 9364A 9715B 9280B | N/A | [5 empty] | Allstar | SQ202507300533-Allstar | Allstar | SQ202507290151-Allstar // SQ202512170142-Allstar | 2025-11-25 | 2025-11-28 | Completed | 2025-07-28 | 2025-07-31 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071859 |  | 2025-07-19 | 2025-08-07 | Completed | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-08-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-15 | 2025-08-22 | 2025-08-16 | 2025-08-16 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-15 | 2025-08-22 | 2025-08-21 | 2025-08-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-16 | 2025-08-15 | 2025-08-22 | 2025-08-20 | 2025-08-20 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-08-15; 2025-06-09: 2025-08-22; 2025-06-09: 2025-08-16; 2025-07-21: 2025-08-16 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9200A_IPR | Kg Alit | DU00005690621 | Sarawak | Sarawak | 1.934183 | 111.169678 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP x2. Fiber patch cord x1 pairs | IDU-IPRAN | Site affected 9033R. NE_9200A 1.Install new 10G SFP module at existing 9200A_RTN02_GE3 (ID : 20445). 2.Install new 10G SFP module at new Sacofa Port.Pending Port info from Sacofa. 3.Patching Fiber patch cord from 9200A_RTN02_GE3 to new sacofa port. 4.Disconnect existing LAN cable to Old Sacofa port and disable unused port. 5.Create service cross connect and all traffic migrate to new sacofa port. | [7 empty] | Allstar | SQ202508270919-Allstar | Allstar | SQ202508271004-Allstar // SQ202512170142-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082872 |  | 2025-08-29 | 2025-09-24 | Completed | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-17 | 2025-10-23 | 2025-10-17 | 2025-10-17 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-10-17 | 2025-10-23 | 2025-11-06 | 2025-11-06 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-05 | 2025-10-17 | 2025-10-23 | 2025-11-10 | 2025-11-10 | ROYSTON//AHHOLE/6000038561 | 2025-06-09: 2025-10-17; 2025-06-09: 2025-10-23; 2025-06-09: 2025-10-17; 2025-07-21: 2025-10-17 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202507250611-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | CHEONG/SENG/WAH/7018000306
9186A_IPR | Saratok Town(SACOFA) | DU00005690622 | Sarawak | Sarawak | 1.740736 | 111.339937 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9186A RTN01 10G Port 9186A-LL SACOFA-9368A Install 1 10G SFP Optical at SACOFA Port 1-4-5 Install 1 10G SFP Optical at HW 9186A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-4-5 to HW 9186A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-1(Node B) for Traffic 9186A Reconfigure Traffic for All 3 Sites; 9186A, 9602A & 9991A Site affected : 9186A 9602A 9991A | 9186A RTN01 10G Port 9186A-LL SACOFA-9368A Install 1 10G SFP Optical at SACOFA Port 1-4-5 Install 1 10G SFP Optical at HW 9186A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-4-5 to HW 9186A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-1(Node B) for Traffic 9186A Reconfigure Traffic for All 3 Sites; 9186A, 9602A & 9991A Site affected : 9186A 9602A 9991A | N/A | [5 empty] | Allstar | SQ202507250120-Allstar | Allstar | SQ202507190105-Allstar // SQ202512170142-Allstar | 2025-11-25 | 2025-11-24 | Completed | 2025-07-23 | 2025-07-23 | 2025-08-14 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070349 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-16 | 2025-07-22 | 2025-07-16 | 2025-07-16 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-16 | 2025-07-22 | 2025-07-16 | 2025-07-21 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-17 | 2025-07-16 | 2025-07-22 | 2025-07-22 | 2025-07-22 | MICHEAL//BICKSON ANAK BANING/6798000201 | 2025-06-09: 2025-07-16; 2025-06-09: 2025-07-22; 2025-06-09: 2025-07-16; 2025-07-21: 2025-07-16 |  |  | 2025-09-19 | 2025-09-30 | 2025-09-19 | 2025-09-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9342A_IPR | Institut Latihan Perindustrian | DU00005690623 | Sarawak | Sarawak | 1.493810 | 110.413660 |  |  |  | JUL 25 |  | 0704 : Sacofa change port to 1-4-5 | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9342A RTN01 10G Port 9342A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 10GE 1-2-1 Install 1 10G SFP Optical at HW 9342A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-1 to HW 9342A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU) for Traffic 9342A Reconfigure Traffic for All 2 Sites; 9342A & 9639B Site affected : 9342A 9639B | 9342A RTN01 10G Port 9342A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 10GE 1-2-1 Install 1 10G SFP Optical at HW 9342A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-1 to HW 9342A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU) for Traffic 9342A Reconfigure Traffic for All 2 Sites; 9342A & 9639B Site affected : 9342A 9639B | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507080939-Allstar | 2025-11-25 | 2025-11-24 | Completed | 2025-07-04 | 2025-07-04 | 2025-07-15 | 2025-07-15 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062501 |  | 2025-06-26 | 2025-07-02 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-26 | 2025-07-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-07-04 | 2025-07-10 | 2025-07-04 | 2025-07-04 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-04 | 2025-07-10 | 2025-07-07 | 2025-07-07 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-04 | 2025-07-04 | 2025-07-10 | 2025-07-09 | 2025-07-09 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-06-09: 2025-07-04; 2025-06-09: 2025-07-10; 2025-06-09: 2025-07-04; 2025-07-21: 2025-07-04 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
7517A_IPR | Kg Wawasan (Celcom) | DU00005690624 | Sabah | Sabah | 5.051531 | 118.328398 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 4x1G SFP Optical 4x Patch Cord(Pair) | IDU-IPRAN | 7517A RTN01 1G x2 (LAG) Port 7517A-LL CTS-7100A Install 1 x 1G SFP Optical at CTS Port SL-3-EG4C-Port 2 Install 1 x 1G SFP Optical at CTS Port SL-3-EG4C-Port 3 Install 1 x 1G SFP Optical at HW 7517A RTN01 8-EG6-5(PORT-5) - Name as LAG1 to CTS Port SL-3-EG4C-Port 2 Install 1 x 1G SFP Optical at HW 7517A RTN01 8-EG6-6(PORT-6) - Name as LAG2 to CTS Port SL-3-EG4C-Port 3 Patching Optical Patch Cord CTS Port SL-3-EG4C-Port 2 to HW 7517A RTN01 8-EG6-5(PORT-5) Patching Optical Patch Cord CTS Port SL-3-EG4C-Port 3 to HW 7517A RTN01 8-EG6-6(PORT-6) Remain Patch 8-EG6-1(BBU 7517A) for Traffic 7517A Remain Patch 8-EG6-3(To RTN02 GE1) For Traffic 7387B Remain Patch 8-EG6-4(To RTN03 GE1) For Traffic 7105D Configure LAG Port for Both 8-EG6-5(PORT-5) & 8-EG6-6(PORT-6) Reconfigure Traffic for All 3 Sites; 7517A, 7387B & 7105D Site affected : 7517A 7387B 7105D | 7517A RTN01 1G x2 (LAG) Port 7517A-LL CTS-7100A Install 1 x 1G SFP Optical at CTS Port SL-3-EG4C-Port 2 Install 1 x 1G SFP Optical at CTS Port SL-3-EG4C-Port 3 Install 1 x 1G SFP Optical at HW 7517A RTN01 8-EG6-5(PORT-5) - Name as LAG1 to CTS Port SL-3-EG4C-Port 2 Install 1 x 1G SFP Optical at HW 7517A RTN01 8-EG6-6(PORT-6) - Name as LAG2 to CTS Port SL-3-EG4C-Port 3 Patching Optical Patch Cord CTS Port SL-3-EG4C-Port 2 to HW 7517A RTN01 8-EG6-5(PORT-5) Patching Optical Patch Cord CTS Port SL-3-EG4C-Port 3 to HW 7517A RTN01 8-EG6-6(PORT-6) Remain Patch 8-EG6-1(BBU 7517A) for Traffic 7517A Remain Patch 8-EG6-3(To RTN02 GE1) For Traffic 7387B Remain Patch 8-EG6-4(To RTN03 GE1) For Traffic 7105D Configure LAG Port for Both 8-EG6-5(PORT-5) & 8-EG6-6(PORT-6) Reconfigure Traffic for All 3 Sites; 7517A, 7387B & 7105D Site affected : 7517A 7387B 7105D | N/A | [5 empty] | NR services | SQ202507230743-NR Services | NR services | SQ202507190103-NR Services | 2025-11-01 | 2025-10-31 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-11-01 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062804 |  | 2025-06-29 | 2025-07-01 | Completed | 2025-06-28 | 2025-06-29 | 2025-06-28 | 2025-07-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-19 | 2025-08-19 | 2025-07-19 | 2025-07-19 | WILFRED BALANG7167000026 | NR Service TI | 2025-07-19 | 2025-08-19 | 2025-07-19 | 2025-07-22 | WILFRED BALANG7167000026 | NR Service TI | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-19 | 2025-07-19 | 2025-08-19 | 2025-07-19 | 2025-07-21 | WILFRED BALANG7167000026 | 2025-06-09: 2025-07-19; 2025-06-09: 2025-08-19; 2025-06-09: 2025-07-19; 2025-07-21: 2025-07-19 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9507A_IPR | Bakam | DU00005690625 | Sarawak | Sarawak | 4.260950 | 113.935730 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) 1x LAN CABLE | IDU-IPRAN | 9507A RTN01 10G Port 9507A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port 1-2-16 Install 1 10G SFP Optical at HW 9507A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-16 to HW 9507A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(9509A_NEC-LAN4) for Traffic 9509A Transfer Patch BBU 9507A from NEC Port to HUAWEI 9507A RTN01 Patch 8-EM6-1(Rename as BBU 9507A) for Traffic 9507A - To Verify at NEC On Site Reconfigure Traffic for All 5 Sites; 9507A, 9692C, 9509A, 9558A, 9557A Site affected : 9507A 9692C 9509A 9558A 9557A | 9507A RTN01 10G Port 9507A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port 1-2-16 Install 1 10G SFP Optical at HW 9507A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 10GE 1-2-16 to HW 9507A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(9509A_NEC-LAN4) for Traffic 9509A Transfer Patch BBU 9507A from NEC Port to HUAWEI 9507A RTN01 Patch 8-EM6-1(Rename as BBU 9507A) for Traffic 9507A - To Verify at NEC On Site Reconfigure Traffic for All 5 Sites; 9507A, 9692C, 9509A, 9558A, 9557A Site affected : 9507A 9692C 9509A 9558A 9557A | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507080939-Allstar | 2025-11-01 | 2025-10-31 | Completed | 2025-07-07 | 2025-07-07 | 2025-07-14 | 2025-07-14 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-11-01 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250624FH |  | 2025-06-26 | 2025-07-01 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-26 | 2025-07-01 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-13 | 2025-07-07 | 2025-07-07 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-07 | 2025-07-13 | 2025-07-07 | 2025-07-08 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-08 | 2025-07-07 | 2025-07-13 | 2025-07-09 | 2025-07-09 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-07; 2025-06-09: 2025-07-13; 2025-06-09: 2025-07-07; 2025-07-21: 2025-07-07 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9059B_IPR | Desa Ilmu MP | DU00005690626 | Sarawak | Sarawak | 1.453670 | 110.457680 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9059B RTN01 10G Port 9059B-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-3-3 Install 1 10G SFP Optical at HW 9059B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-3-3 to HW 9059B RTN01 8-EM6-3(PORT-3) Transfer Patch from NEC Port Carry BBU 9059B to 8-EM6-1(Rename as BBU 9059B) for Traffic 9059B Remain Patch 8-EM6-2(Cascade NEC Port 3) for Traffic 9302B Reconfigure Traffic for All 3 Sites; 9059B, 9302B & 9876A Site affected : 9059B 9302B 9876A | 9059B RTN01 10G Port 9059B-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-3-3 Install 1 10G SFP Optical at HW 9059B RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-3-3 to HW 9059B RTN01 8-EM6-3(PORT-3) Transfer Patch from NEC Port Carry BBU 9059B to 8-EM6-1(Rename as BBU 9059B) for Traffic 9059B Remain Patch 8-EM6-2(Cascade NEC Port 3) for Traffic 9302B Reconfigure Traffic for All 3 Sites; 9059B, 9302B & 9876A Site affected : 9059B 9302B 9876A | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507030736-Allstar | 2026-01-14 | 2026-01-13 | Completed | 2025-07-02 | 2025-07-02 | 2025-07-15 | 2025-07-15 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062502 |  | 2025-06-26 | 2025-07-02 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-26 | 2025-07-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-08 | 2025-07-02 | 2025-07-02 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-02 | 2025-07-08 | 2025-07-02 | 2025-07-02 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-02 | 2025-07-02 | 2025-07-08 | 2025-07-10 | 2025-07-10 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-06-09: 2025-07-02; 2025-06-09: 2025-07-08; 2025-06-09: 2025-07-02; 2025-07-21: 2025-07-02 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9085A_IPR | Holiday Park | DU00005690627 | Sarawak | Sarawak | 4.323753 | 113.972735 |  |  |  | JUL 25 |  |  | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) 1x LAN Cable | IDU-IPRAN | 9085A RTN01 10G Port 9085A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port 1-3-3 Install 1 10G SFP Optical at HW 9085A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-3-3 to HW 9085A RTN01 8-EM6-3(PORT-3) Transfer Patch from 9085A RTN02 8-EM6-2(9085 BBU) to 9085A RTN01 8-EM6-2(**Rename as 9085A BBU) for Traffic 9085A Remain Patch 8-EM6-1(Cascade to RTN02) for Traffic 9928A Reconfigure Traffic for All 3 Sites; 9085A, 9928A & 9933A Site affected : 9085A 9933A 9928A | 9085A RTN01 10G Port 9085A-LL SACOFA-9074A Install 1 10G SFP Optical at SACOFA Port 1-3-3 Install 1 10G SFP Optical at HW 9085A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-3-3 to HW 9085A RTN01 8-EM6-3(PORT-3) Transfer Patch from 9085A RTN02 8-EM6-2(9085 BBU) to 9085A RTN01 8-EM6-2(**Rename as 9085A BBU) for Traffic 9085A Remain Patch 8-EM6-1(Cascade to RTN02) for Traffic 9928A Reconfigure Traffic for All 3 Sites; 9085A, 9928A & 9933A Site affected : 9085A 9933A 9928A | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507080939-Allstar | 2025-11-25 | 2025-11-24 | Completed | 2025-07-08 | 2025-07-08 | 2025-07-15 | 2025-07-15 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-10-22 | 2025-10-23 | 2025-10-22 | 2025-10-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250624FJ |  | 2025-06-26 | 2025-07-01 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-26 | 2025-07-01 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-13 | 2025-07-08 | 2025-07-08 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-07 | 2025-07-13 | 2025-07-07 | 2025-07-08 | TONI//ANAK KUMBONG/6798000163 | Allstar TI | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-08 | 2025-07-07 | 2025-07-13 | 2025-07-09 | 2025-07-09 | TONI//ANAK KUMBONG/6798000163 | 2025-06-09: 2025-07-07; 2025-06-09: 2025-07-13; 2025-06-09: 2025-07-08; 2025-07-21: 2025-07-08 |  |  | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
7219A_IPR | Kg Merintaman | DU00005690628 | Sabah | Sabah | 5.060199 | 115.549785 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2x1G SFP Optical 2x Patch Cord(Pair) | IDU-IPRAN | 7219A RTN01 1G x2 (LAG) Port 7219A-LL CTS-7000A Install 1 x 1G SFP Optical at CTS Port SL:1 - K1EX10 - PORT: 8 Install 1 x 1G SFP Optical at HW 7219A RTN01 8-EG6-5(PORT-5) - Name as LAG2 to CTS Port SL3-EG4C-PORT: 3 Patching Optical Patch Cord CTS Port SL:1 - K1EX10 - PORT: 8 to HW 7219A RTN01 8-EG6-5(PORT-5) Remain Patch 8-EG6-1(CTS - Rename as LAG1 to CTS Port (M)) Remain Patch 8-EG6-2(BBU 7219A) For Traffic 7219A Transfer Patch from 7073A RTN02 8-EG6-2(To Port BBU01) to 7073A RTN01 8-EG6-3 For Traffic 7073A - Rename as BBU 7073A Configure LAG Port for Both 8-EG6-5(PORT-5) & 8-EG6-1(PORT-1) Reconfigure Traffic for All 2 Sites; 7219A & 7698B Site affected : 7219A 7698A 2x1G SFP Optical 2x Patch Cord(Pair) | 7219A RTN01 1G x2 (LAG) Port 7219A-LL CTS-7000A Install 1 x 1G SFP Optical at CTS Port SL:1 - K1EX10 - PORT: 8 Install 1 x 1G SFP Optical at HW 7219A RTN01 8-EG6-5(PORT-5) - Name as LAG2 to CTS Port SL3-EG4C-PORT: 3 Patching Optical Patch Cord CTS Port SL:1 - K1EX10 - PORT: 8 to HW 7219A RTN01 8-EG6-5(PORT-5) Remain Patch 8-EG6-1(CTS - Rename as LAG1 to CTS Port (M)) Remain Patch 8-EG6-2(BBU 7219A) For Traffic 7219A Transfer Patch from 7073A RTN02 8-EG6-2(To Port BBU01) to 7073A RTN01 8-EG6-3 For Traffic 7073A - Rename as BBU 7073A Configure LAG Port for Both 8-EG6-5(PORT-5) & 8-EG6-1(PORT-1) Reconfigure Traffic for All 2 Sites; 7219A & 7698B Site affected : 7219A 7698A 2x1G SFP Optical 2x Patch Cord(Pair) | N/A | [5 empty] | NR services | SQ202510010672-NR Services | NR services | SQ202507190103-NR Services | 2025-12-16 | 2025-12-16 | Completed | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062802 |  | 2025-06-29 | 2025-07-01 | Completed | 2025-06-28 | 2025-06-29 | 2025-06-28 | 2025-07-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-10-22 | 2025-09-22 | 2025-09-22 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-09-22 | 2025-10-22 | 2025-09-22 | 2025-09-22 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | 2025-09-22 | 2025-09-22 | 2025-10-22 | 2025-09-22 | 2025-09-22 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-06-09: 2025-09-22; 2025-06-09: 2025-10-22; 2025-06-09: 2025-09-22; 2025-07-21: 2025-09-22 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160757-GCI | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
9321A_IPR | Politeknik Matang (SACOFA) | DU00005690629 | Sarawak | Sarawak | 1.632817 | 110.196634 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 8/8/2025 : Fallback due to pending sacofa confirm core 7/8/2025 : Plan to do IDU-IPRAN - Cancel proceed due to not receive keys | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9321A RTN01 10G Port 9321A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-15 Install 1 10G SFP Optical at HW 9321A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-4-15 to HW 9321A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU 9321A) for Traffic 9321A Reconfigure Traffic for All 2 Sites; 9321A & 9140B Site affected : 9321A 9140B | 9321A RTN01 10G Port 9321A-LL SACOFA-9999A Install 1 10G SFP Optical at SACOFA Port 1-4-15 Install 1 10G SFP Optical at HW 9321A RTN01 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port 1-4-15 to HW 9321A RTN01 8-EM6-3(PORT-3) Remain Patch 8-EM6-2(BBU 9321A) for Traffic 9321A Reconfigure Traffic for All 2 Sites; 9321A & 9140B Site affected : 9321A 9140B | N/A | [5 empty] | Allstar | SQ202507100507-Allstar | Allstar | SQ202507100577-Allstar // SQ202512170142-Allstar | 2026-02-23 | 2026-02-23 | Completed | 2025-08-08 | 2025-08-08 | 2025-09-07 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-02 | 2026-02-08 | 2026-02-02 | 2026-02-02 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070144 |  | 2025-07-02 | 2025-07-02 | Completed | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-09 | 2025-07-15 | 2025-07-09 | 2025-07-09 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2025-07-09 | 2025-07-15 | 2026-01-21 | 2026-01-21 | KENISTON//ANAK SPANCER/6798000184 | Allstar TI | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-08 | 2025-07-09 | 2025-07-15 | 2026-01-24 | 2026-01-24 | KENISTON//ANAK SPANCER/6798000184 | 2025-06-09: 2025-07-09; 2025-06-09: 2025-07-15; 2025-06-09: 2025-07-09; 2025-07-21: 2025-07-09 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
Q00794_IPR | Q139A_Q00794OD_CB_TMTEBAKANG | DU00005697823 | Sarawak | Sarawak | 1.099668 | 110.506535 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1X LAN Cable | MW IDU Patching | Split traffic at SW03690 Q00794_TM TEBAKANG GE1 to 30228-TMTEBAKANG-ACC1 GigabitEthernet 0/0/2 Patch IDU Huawei SW03690 Q00794_TM TEBAKANG GE2 to new PTN port and transfer traffic from sites below: 1) Q02333_KAMPUNG_KRUSEN_MAWANG 2) Q02331_KAMPUNG_LOBANG_BT_MAWANG 3) Q02332_KAMPUNG_PAYAU_BRUS | Split traffic at SW03690 Q00794_TM TEBAKANG GE1 to 30228-TMTEBAKANG-ACC1 GigabitEthernet 0/0/2 Patch IDU Huawei SW03690 Q00794_TM TEBAKANG GE2 to new PTN port and transfer traffic from sites below: 1) Q02333_KAMPUNG_KRUSEN_MAWANG 2) Q02331_KAMPUNG_LOBANG_BT_MAWANG 3) Q02332_KAMPUNG_PAYAU_BRUS | N/A | [5 empty] | Trintel | SQ202507160744-Trintel | Allstar | SQ202507190105-Allstar | 2025-07-30 | 2025-07-29 | Completed | 2025-07-10 | 2025-07-12 | 2025-07-10 | 2025-07-12 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-07-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-07-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-29 | 2025-07-30 | 2025-07-29 | 2025-07-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071301 |  | 2025-07-14 | 2025-07-18 | Completed | 2025-07-13 | 2025-07-14 | 2025-07-13 | 2025-07-18 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-18 | 2025-07-24 | 2025-07-18 | 2025-07-18 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-18 | 2025-07-24 | 2025-07-21 | 2025-07-21 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-22 | 2025-07-18 | 2025-07-24 | 2025-07-21 | 2025-07-21 | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-06-09: 2025-07-18; 2025-06-09: 2025-07-24; 2025-06-09: 2025-07-18; 2025-07-21: 2025-07-18 |  |  | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
4277B_IPR | Kuala Kedah 2 (Celcom) | DU00005697824 | Northern | Kedah | 6.103185 | 100.300473 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | N/A | [5 empty] | GTSB | SQ202507230737-GTSB | GTSB | SQ202506200681-GTSB | 2025-08-15 | 2025-08-14 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-14 | 2025-08-15 | 2025-08-14 | 2025-08-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061363 |  | 2025-06-14 | 2025-06-18 | Completed | 2025-06-13 | 2025-06-14 | 2025-06-13 | 2025-06-18 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | AMIRUL AFIF BIN MANSOR6000002563 | GTSB TI | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | AMIRUL AFIF BIN MANSOR6000002563 | GTSB TI | 2025-06-20 | 2025-06-23 | 2025-06-20 | 2025-06-23 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-07-27 | DEEVAN//RAJ A/L CHANDRASEGARAN/6799000193 | 2025-06-09: 2025-06-20; 2025-06-09: 2025-06-20; 2025-06-09: 2025-06-20; 2025-07-21: 2025-07-24 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506160754-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
4300A_IPR | Bertam (REL) | DU00005697825 | Northern | Penang | 5.521933 | 100.482471 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | N/A | [5 empty] | GCI | SQ202506300690-GCI | GCI | SQ202506200677-GCI | 2025-07-17 | 2025-07-22 | Completed | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061361 |  | 2025-06-14 | 2025-06-19 | Completed | 2025-06-13 | 2025-06-14 | 2025-06-13 | 2025-06-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-20 | 2025-06-30 | 2025-06-20 | 2025-07-01 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2025-06-20 | 2025-06-30 | 2025-06-20 | 2025-06-25 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-06-20 | 2025-06-30 | 2025-06-20 | 2025-07-01 | JUTI//ANAK RICHARD/6800000216 | 2025-06-09: 2025-06-20; 2025-06-09: 2025-06-30; 2025-06-09: 2025-06-20; 2025-07-21: 2025-06-23 |  |  | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506160754-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
K00119_IPR | K009A_K00119OD_JKRKUALANERANG | DU00005697826 | Northern | Kedah | 6.251197 | 100.614711 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1X LAN Cable | MW IDU Patching | Split traffic at NT05659 GNE JkrKualaNerang LAN1 to 60087-JKRKUALANERANG-ACC1 GigabitEthernet 0/0/16 Patch IDU SM NT05659 GNE JkrKualaNerang LAN3 to new PTN port and transfer traffic from sites below: 1) K01074_KG_MUSA 2) K01072OD_KG_TONG_TELU All sites above are using HUAWEI BBU. Require assistant from OSS to verify site status during reengineering work | Split traffic at NT05659 GNE JkrKualaNerang LAN1 to 60087-JKRKUALANERANG-ACC1 GigabitEthernet 0/0/16 Patch IDU SM NT05659 GNE JkrKualaNerang LAN3 to new PTN port and transfer traffic from sites below: 1) K01074_KG_MUSA 2) K01072OD_KG_TONG_TELU All sites above are using HUAWEI BBU. Require assistant from OSS to verify site status during reengineering work | N/A | [5 empty] | CCSMY | SQ202507160586-CCS | CCSMY | SQ202507100562-CCS | 2025-11-19 | 2025-11-18 | Completed | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-11 | 2025-09-12 | 2025-09-11 | 2025-09-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061365 |  | 2025-06-14 | 2025-06-19 | Completed | 2025-06-13 | 2025-06-14 | 2025-06-13 | 2025-06-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-10 | 2025-07-31 | 2025-07-10 | 2025-07-11 | MOHD//FADZRI BIN SUFIAN/7021000033 | CCS TI | 2025-07-10 | 2025-07-31 | 2025-07-10 | 2025-07-11 | MOHD//FADZRI BIN SUFIAN/7021000033 | CCS TI | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-11 | 2025-07-10 | 2025-07-31 | 2025-07-10 | 2025-07-15 | MOHD//FADZRI BIN SUFIAN/7021000033 | 2025-06-09: 2025-07-10; 2025-06-09: 2025-07-31; 2025-06-09: 2025-07-10; 2025-07-21: 2025-07-11 |  |  | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506160754-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
Q00485_AD | Q126A_Q00485OD_BATUDANAU | DU00005697827 | Sarawak | Sarawak | 4.653327 | 114.842669 |  |  |  | AUG 25 |  |  |  | 00. Integrated/RFS Done | 4/8/2025 : Together with RAN, BBU not yet ZTE | TSS+TI | L1+ATP+PAC |  | BBU Patching | 1. BBU Patching to xD 9646B-9288A | Need to patch BBU to use xD MW link 9646B-9288A | [6 empty] | CCSMY | SQ202507250125-CCS | CCSMY | SQ202508040528-CCS | 2025-11-17 | 2025-11-10 | Completed | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | Hermanwijaya bin suardi7021000085 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-08-01 | 2025-07-31 | 2025-07-31 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25080516 |  | 2025-08-06 | 2025-08-21 | Completed | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [13 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-13 | [15 empty] | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507190089-GTSB | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | HSU//MYET CHAE/6799000011
B02425_LOS | B061A_B02425OD_JLNSETIAGEMILANG | DU00005697828 | Central | Selangor | 3.128470 | 101.466980 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2x RTN910A 1x ODU XMC3E 18G SB B H 1x ODU XMC3E 18G SB B L 1X 18G 0.6m DP MAC Antenna 1X 18G 1.2m DP MAC Antenna | MW New Link / Reroute | MW New Link/Reroute B02425 to New FE 1099A (Due to LOS Block) NE: 1) INSTALL NEW RTN910A 2) INSTALL NEW 18G 1+0 110MHz ODU XMC3E SUB BAND B 3) INSTALL NEW ANTENNA 18G 0.6M 4) MIGRATE B02425 TRAFFIC to NEW LINK 5) Decom Exsiting Link B02425-B01127 FE: 1) INSTALL NEW RTN910A (OPS TEAM TO ASSIGN NEW RTN NUMBER) 2) INSTALL NEW 18G 1+0 110MHz ODU XMC3E SUB BAND B 3) INSTALL NEW ANTENNA 18G 1.2M 4) Configer B02425 TRAFFIC to NEW LINK 5) PATCH NEW IDU TO NEW CP PORT AND ESTABLISH NEW DCN 6) Decom Exsiting Link B02425-B01127 | MW New Link/Reroute B02425 to New FE 1099A (Due to LOS Block) NE: 1) INSTALL NEW RTN910A 2) INSTALL NEW 18G 1+0 110MHz ODU XMC3E SUB BAND B 3) INSTALL NEW ANTENNA 18G 0.6M 4) MIGRATE B02425 TRAFFIC to NEW LINK 5) Decom Exsiting Link B02425-B01127 | MW New Link/Reroute B02425 to New FE 1099A (Due to LOS Block) FE: 1) INSTALL NEW RTN910A (OPS TEAM TO ASSIGN NEW RTN NUMBER) 2) INSTALL NEW 18G 1+0 110MHz ODU XMC3E SUB BAND B 3) INSTALL NEW ANTENNA 18G 1.2M 4) Configer B02425 TRAFFIC to NEW LINK 5) PATCH NEW IDU TO NEW CP PORT AND ESTABLISH NEW DCN 6) Decom Exsiting Link B02425-B01127 | XMC3E | DP MAC | 18G | 0.6 | 1.2 | GTSB | SQ202506130132-GTSB | GTSB | SQ202506250183-GTSB // SQ202506250191-GTSB | 2025-09-18 | 2025-09-19 | Completed | 2025-07-28 | 2025-08-11 | 2025-07-28 | 2025-07-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-28 | 2025-08-11 | 2025-07-28 | 2025-07-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-04 | 2025-08-05 | 2025-08-04 | 2025-08-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-17 | 2025-09-18 | 2025-09-17 | 2025-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072104 |  | 2025-07-23 | 2025-07-23 | Completed | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-23 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-12-22 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2026-01-26 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-01 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2026-01-24 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2026-01-21 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160751-GCI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
Q01548_AD | Q126A_Q01548OD_MN_LUBAITENGAH | DU00005697829 | Sarawak | Sarawak | 4.633570 | 114.926390 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 25/9/2025 : Cutover done 12/9/2025 : Installation complete, pending cutover due to IDU not support 11/9/2025 : Installation complete, pending cutover | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1x RTN910A(for NE) 1X ISM8 (for FE) 2x 1.2m MDD Antenna (15G) 1x ODU 15G XMC-5D sb A Hi 1x ODU 15G XMC-5D sb A_Lo | MW New Link / Reroute | Install new mw linkQ01548-9252Z with Huawei_15G_2+0_28mhz_512QAM_448Mbps_1.2/1.2m_MDD_XMC-5D sb A_4.57km Impact site: Q01548 Decom existing link SW03633 | NE: 1. Install ISM8 card to existing RTN910A slot3 2. Install new 15G 1.2m MDD Antenna 3. Install new 15G XMC-5D sb A 4. Configure link 15G 2+0_ 28MHZ 512QAM Decom existing link SW03633 | FE: 1. Install new RTN910A 2. Install new 15G 1.2m MDD Antenna 3. Install new 15G XMC-5D sb A 4. Configure link 15G 2+0_ 28MHZ 512QAM | XMC-5D | MDD | 15G | 1.2m | 1.2m | CCSMY | SQ202507250125-CCS | Trintel | SQ202509090366-Trintel // SQ202509090378-Trintel | 2025-08-15 | 2025-08-11 | Completed | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | Hermanwijaya bin suardi7021000085 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-11 | 2025-08-15 | 2025-08-11 | 2025-08-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Full Site DR | 2025-08-14 | 2025-08-21 | Completed | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-21 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-10 | PATRIK WEI ANAK EDUIN7667000018 | Trintel TI | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-10-10 | PATRIK WEI ANAK EDUIN7667000018 | Trintel TI | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-10 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-10-12 | PATRIK WEI ANAK EDUIN7667000018 | 2025-07-31: 2025-09-08; 2025-07-31: 2025-09-08; 2025-07-31: 2025-09-08; 2026-01-21: 2025-09-10 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202507080651-GTSB | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | AB.RAHMAN//BIN MAT NOOH/6237001519
9373B_LOS | Hock Peng MP | DU00005697830 | Sarawak | Sarawak | 2.316319 | 111.830429 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Duplicate with 9037C_LOS | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202506160765-GCI | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | CHEONG/SENG/WAH/7018000306
W00850_LOS | W066Q_W00850OD_PR_KM7MEXHWY | DU00005697831 | Central | Kuala Lumpur | 3.090680 | 101.697060 | [7 empty] | 00. Integrated/RFS Done | 9/7/25-No LOS | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+1_112M. NE_1419K/W00850 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. FE_1299A 23G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. | MW New Link / Reroute | W00850 link reroute to new FE 1229A due to the existing FE LOS Block by building. Link configuration 23G_1+1_112M. Site Impacted : 1419K/W00850 NE_1419K/W00850 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+1 , configure to 1+1 Hot Standby. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and configure 1+1 link. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link (1419K/W00850 - 2011A) FE_1299A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 1299A_RTN910A_RTN01 (ID : 26566). 3.Install new 3_ISM8-1+1 into existing 1299A_RTN910A_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and configure 1+1 link. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link ( 2011A -1419K/W00850) | W00850 link reroute to new FE 1229A due to the existing FE LOS Block by building Link configuration 23G_1+1_112M. Site Impacted : 1419K/W00850 NE_1419K/W00850 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+1 , configure to 1+1 Hot Standby. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and configure 1+1 link. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link (1419K/W00850 - 2011A) | W00850 link reroute to new FE 1229A due to the existing FE LOS Block by building Link configuration 23G_1+1_112M. Site Impacted : 1419K/W00850 FE_1299A 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Reuse existing 1299A_RTN910A_RTN01 (ID : 26566). 3.Install new 3_ISM8-1+1 into existing 1299A_RTN910A_RTN01. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and configure 1+1 link. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link ( 2011A -1419K/W00850) | XMC_3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202506130130-GCI | GCI | SQ202508270936-GCI // SQ202508270942-GCI | 2025-09-18 | 2025-09-19 | Completed | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-24 | 2025-07-23 | 2025-07-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-17 | 2025-09-18 | 2025-09-17 | 2025-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082034 |  | 2025-08-21 | 2025-08-22 | Completed | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-25 | 2025-09-01 | 2025-08-24 | 2025-09-17 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-08-25 | 2025-09-01 | 2025-08-24 | 2025-10-14 | Ragunalan//A/L L.Krisnan6000006720 | GCI TI | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-08-26 | 2025-08-25 | 2025-09-01 | 2025-08-24 | 2025-11-06 | Ragunalan//A/L L.Krisnan6000006720 | 2025-08-25 | 2025-09-01 | 2025-08-24 | 2025-08-26 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160751-GCI | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | CHEONG/SENG/WAH/7018000306
Q01057_IPR | Q126A_Q01057OD_JLNBUANGSIOL | DU00005697832 | Sarawak | Sarawak | 4.760365 | 115.006799 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 6/8/2025 : Cutover done 1/8/2025 : MW IDU Patching hold due to need SFP Electrical 31/7/2025 : Plan to do MW IDU Patching - Cancel proceed | TSS+TI | L1+ATP+PAC | 1X LAN Cable | MW IDU Patching | Split traffic at SW03654 Q01057_JLN BUANG SIOL GE1 to 30089-KGBUANGSIOL-ACC1 GigabitEthernet 0/0/1 Patch IDU Huawei SW03654 Q01057_JLN BUANG SIOL GE2 to new PTN port and transfer traffic from sites below: 1) Q00320 TMN PERTAMA 2) Q00325 TMN BOYAN 3) Q00577 BATU BIAH 4) Q00318 TEDUNGAN All sites above are using ERICSSON BBU. Require assistant from OSS to verify site status during reengineering work | Split traffic at SW03654 Q01057_JLN BUANG SIOL GE1 to 30089-KGBUANGSIOL-ACC1 GigabitEthernet 0/0/1 Patch IDU Huawei SW03654 Q01057_JLN BUANG SIOL GE2 to new PTN port and transfer traffic from sites below: 1) Q00320 TMN PERTAMA 2) Q00325 TMN BOYAN 3) Q00577 BATU BIAH 4) Q00318 TEDUNGAN All sites above are using ERICSSON BBU. Require assistant from OSS to verify site status during reengineering work | N/A | [5 empty] | CCSMY | SQ202509040281-CCS | CCSMY | SQ202507290157-CCS |  |  | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25071411 |  | 2025-07-15 | 2025-07-25 | Completed | 2025-07-14 | 2025-07-15 | 2025-07-14 | 2025-07-25 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-01 | 2025-08-27 | 2025-08-01 |  | Hermanwijaya bin suardi7021000085 | CCS TI | [6 empty] | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-08-01 | 2025-08-27 | 2025-08-01 |  | Hermanwijaya bin suardi7021000085 | 2025-07-31: 2025-08-01; 2025-07-31: 2025-08-27; 2025-07-31: 2025-08-01 |  |  | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506160765-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
4857B_IPR | Bandar Wawasan | DU00005697833 | Northern | Kedah | 6.291780 | 100.418000 | [7 empty] | 00. Integrated/RFS Done | 24/06: CO Done | TSS+TI | L1+ATP+PAC | 1X LAN Cable | MW IDU Patching | Split traffic at NT05913 GNE BdrWawasan LAN1 to 60033-BDRWAWASAN-ACC1 GigabitEthernet 0/0/3 Patch IDU SM NT05913 GNE BdrWawasan LAN3 to new PTN port and transfer traffic from sites below: 1) 4143A_BUKITNAPOH3 | Split traffic at NT05913 GNE BdrWawasan LAN1 to 60033-BDRWAWASAN-ACC1 GigabitEthernet 0/0/3 Patch IDU SM NT05913 GNE BdrWawasan LAN3 to new PTN port and transfer traffic from sites below: 1) 4143A_BUKITNAPOH3 | N/A | [5 empty] | GTSB | SQ202507230737-GTSB | GTSB | SQ202506250218-GTSB | 2025-11-19 | 2025-11-20 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061825 |  | 2025-06-19 | 2025-06-18 | Completed | 2025-06-18 | 2025-06-19 | 2025-06-18 | 2025-06-18 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | AMIRUL AFIF BIN MANSOR6000002563 | GTSB TI | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | AMIRUL AFIF BIN MANSOR6000002563 | GTSB TI | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-07-27 | DEEVAN//RAJ A/L CHANDRASEGARAN/6799000193 | 2025-07-31: 2025-06-24; 2025-07-31: 2025-06-24; 2025-07-31: 2025-06-24; 2026-01-21: 2025-07-24 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506160754-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
2436A_IPR | Bukit Beruntung (CELCOM) | DU00005697834 | Central | Selangor | 3.433820 | 101.576520 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x1G SFP Optical 2x Patch Cord(Pair) | MW IDU Patching | Split traffic at 2436A-BUKIT BERUNTUNG (CELCOM)-RTN02 GE5 to 70656-BKTBERUNTUNG-ACC1 GigabitEthernet 0/0/9 Patch IDU Huawei 2436A-BUKIT BERUNTUNG (CELCOM)-RTN02 GE6 to new PTN port and transfer traffic from sites below: 1) 3588C_SURAU_TMN_WIDURI | Split traffic at 2436A-BUKIT BERUNTUNG (CELCOM)-RTN02 GE5 to 70656-BKTBERUNTUNG-ACC1 GigabitEthernet 0/0/9 Patch IDU Huawei 2436A-BUKIT BERUNTUNG (CELCOM)-RTN02 GE6 to new PTN port and transfer traffic from sites below: 1) 3588C_SURAU_TMN_WIDURI | N/A | [5 empty] | Magicell | SQ202506130135-Magicell | Magicell | SQ202506130143-Magicell | 2025-08-16 | 2025-08-18 | Completed | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-12 | 2025-08-13 | 2025-08-12 | 2025-08-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-15 | 2025-08-16 | 2025-08-15 | 2025-08-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061351 |  | 2025-06-14 | 2025-06-18 | Completed | 2025-06-13 | 2025-06-14 | 2025-06-13 | 2025-06-18 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-03 | 2026-07-16 | 2025-07-03 | 2025-07-18 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-07-03 | 2026-07-16 | 2025-07-03 | 2025-07-18 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-07-06 | 2025-07-06 | 2025-07-06 | 2025-07-06 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-06 | 2025-07-03 | 2026-07-16 | 2025-07-03 | 2025-07-18 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | 2025-07-31: 2025-07-03; 2025-07-31: 2026-07-16; 2025-07-31: 2025-07-03; 2026-01-21: 2025-07-03 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160751-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
2118B_IPR | Bandar teknologi kajang 1 | DU00005697835 | Central | Selangor | 2.962760 | 101.822100 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | N/A | [5 empty] | Magicell | SQ202506130135-Magicell | Magicell | SQ202506130143-Magicell | 2025-11-19 | 2025-11-18 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-05 | 2025-08-04 | 2025-08-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061355 |  | 2025-06-14 | 2025-06-18 | Completed | 2025-06-13 | 2025-06-14 | 2025-06-13 | 2025-06-18 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-18 | ASYRAF//BIN MOHAMAD/7018000171 | Magicell TI | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-18 | ASYRAF//BIN MOHAMAD/7018000171 | Magicell TI | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-18 | ASYRAF//BIN MOHAMAD/7018000171 | 2025-07-31: 2025-07-08; 2025-07-31: 2025-07-08; 2025-07-31: 2025-07-08; 2026-01-21: 2025-07-09 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506160751-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
W01526_HU | W066J_W01526OD_KERAMATWANGSA2 | DU00005163094 | Central | Kuala Lumpur | 3.181314 | 101.748844 |  |  |  | JUN 25 |  |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 23G_1+0_56M NE_W00130 New XMC_3, Sub A_Hi x1. New FlexiWG 23G x1. New IF cable with suitable length. FE_B01313 New XMC_3, Sub A_Lo x2. New FlexiWG 23G x1. New IF cable with suitable length. | MW Hardware Upgrade | Link Existing HW 23G_1+0_56M. MW Hardware Upgrade by adding 2nd channel to existing HW 23G_1+0_56M_512QAM become HW 23G_2+0_56M_512QAM_EPLA. Site Impacted : W01526. NE_W01526 1.Install new 23G XMC_3 , Sub A_Hi. Configure it. 2.Lay new suitable length of IF cable from new ODU(23G XMC_3) to existing ISM8 port 2(Horizontal) at RTN910A(RTN12). 3.Configure HW 23G_2+0_56M_512QAM_EPLA for new channel and existing channel. Total new capacity will be 900Mbps. FE_B01313 1.Install new 23G XMC_3 , Sub A_Hi. Configure it. 2.Lay new suitable length of IF cable from new ODU(23G XMC_3) to existing ISM8 port 2(Horizontal) at RTN910A(RTN12). 3.Configure HW 23G_2+0_56M_512QAM_EPLA for new channel and existing channel. Total new capacity will be 900Mbps. | Link Existing HW 23G_1+0_56M. MW Hardware Upgrade by adding 2nd channel to existing HW 23G_1+0_56M_512QAM become HW 23G_2+0_56M_512QAM_EPLA. Site Impacted : W01526. NE_W01526 1.Install new 23G XMC_3 , Sub A_Hi. Configure it. 2.Lay new suitable length of IF cable from new ODU(23G XMC_3) to existing ISM8 port 2(Horizontal) at RTN910A(RTN12). 3.Configure HW 23G_2+0_56M_512QAM_EPLA for new channel and existing channel. Total new capacity will be 900Mbps. | Link Existing HW 23G_1+0_56M. MW Hardware Upgrade by adding 2nd channel to existing HW 23G_1+0_56M_512QAM become HW 23G_2+0_56M_512QAM_EPLA. Site Impacted : W01526. FE_B01313 1.Install new 23G XMC_3 , Sub A_Hi. Configure it. 2.Lay new suitable length of IF cable from new ODU(23G XMC_3) to existing ISM8 port 2(Horizontal) at RTN910A(RTN12). 3.Configure HW 23G_2+0_56M_512QAM_EPLA for new channel and existing channel. Total new capacity will be 900Mbps. | XMC_3 | MAC | 23G | Reuse Existing 23G_DP_0.6M(MAC) | Reuse Existing 23G_DP_0.6M(MAC) | Magicell | SQ202506250168-Magicell | Magicell | SQ202505300199-Magicell // SQ202505300201-Magicell | 2025-11-28 | 2025-11-22 | Completed | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-16 | 2025-07-15 | 2025-07-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-21 | 2025-11-28 | 2025-11-21 | 2025-11-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250520AH |  | 2025-05-21 | 2025-05-23 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-25 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-25 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-05 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-25 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-07-31: 2025-06-03; 2025-07-31: 2025-06-03; 2025-07-31: 2025-06-03; 2026-01-21: 2025-06-05 |  |  | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202505070162-GTSB
1566C_HU | Surau Kemuning Utama (REL 2) | DU00005163095 | Central | Selangor | 3.016746 | 101.542272 | WK12 | MAR 25 | WK12 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 22/3/2025 : Cutover done 21/3/2025 : FE installation complete, NE installation WIP 20/3/2025 : Plan install NE and FE site - CRQ approved, cancel proceed due late BM approved to enter site 13/3/2025 : SBC KJS - 20M Lampole - NE site 1566C Surau Kemuning Utama (REL 2), Digi OB - 3M Boom - RT - FE site 1710B Seksyen 27_89 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK 1566C RTN01-1710B RTN02 WITH HUAWEI_23G_2+0_0.6M/0.6M_MDD_112MHZ_512QAM_1778MBPS_XMC3E_SUB A & B_1.82KM DISMANTLE EXISTING LINK AT FE, CHECK IF WE CAN USE EXISTING 1710B RTN01 OR NOT (SEEMS LIKE PREVIOUSLY DEDICATE FOR EB 1206E) IMPACTED: 1556C, 1184D, B02725 | 1. INSTALL NEW RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. REPATCH CASCADE B02725-1556C IDU TO NEW LINK IDU 6. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202503270787-Magicell | Magicell | SQ202503240702-Magicell // SQ202503240705-Magicell // SQ202504260146-Magicell // SQ202512120102-Magicell | 2025-08-19 | 2025-08-18 | Completed | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-18 | 2025-08-19 | 2025-08-18 | 2025-08-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031356 |  | 2025-03-14 | 2025-03-17 | Completed | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-21 | 2026-03-06 | 2025-03-21 | 2025-04-08 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 |  | 2025-03-21 | 2026-03-06 | 2025-03-21 | 2025-04-08 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-21 | 2025-03-21 | 2026-03-06 | 2025-03-21 | 2025-04-08 | AZRI MUADZ-DZAN A'IMULLAH BIN AHMAD7018000303 | 2025-03-21 | 2026-03-06 | 2025-03-21 | 2025-03-22 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
3215A_HU | TAMAN TERATAI MEWAH | DU00005163096 | Central | Kuala Lumpur | 3.201058 | 101.710376 | WK11 | MAR 25 | WK11 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 13/3/2025 : Cutover done 12/3/2025 : Installation complete, pending cutover due to IDU need to change 11/3/2025 : Digi OB - 3M Boom - RT - NE site 3215A TAMAN TERATAI MEWAH, Digi OB - 6M RT - Boom - FE site 1253A Plaza Pengkalen | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap | MW SWAP LINK 3215A-1253A 1+0 SLOT 4 WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_64QAM_1150MBPS_XMC3E_SUB A & B_3.74KM_ EPLA WITH EXISTING 4+0 SLOT 7 & 3 PATCH TO NEW PORT AND DO PORT LAG DISMANTLE EXISTING LINK IMPACTED: 3215A, 1339C | 1. REUSE EXISTING RTN910A SLOT 4 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 64QAM EPLA WITH EXISTING LINK 4+0 5. DISMANTLE EXISTING LINK 1+0 ONLY EXCEPT IDU | 1. REUSE EXISTING RTN910A SLOT 4 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 64QAM EPLA WITH EXISTING LINK 4+0 5. PATCH TO NEW PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK 1+0 ONLY EXCEPT IDU | XMC3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202503190656-GCI | GCI | SQ202503200144-GCI // SQ202503200149-GCI // SQ202504150088-GCI | 2025-04-07 | 2025-04-07 | Completed | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250306AF |  | 2025-03-07 | 2025-03-15 | Completed | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-12 | 2025-03-19 | 2025-03-11 | 2025-03-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-12 | 2025-03-19 | 2025-03-11 | 2025-03-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-13 | 2025-03-12 | 2025-03-19 | 2025-03-11 | 2025-03-13 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-12 | 2025-03-19 | 2025-03-11 | 2025-03-12 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
3562A_HU | pBTS Country Heights | DU00005163097 | Central | Selangor | 2.996432 | 101.744964 | WK13 | MAR 25 | WK13 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 25/3/2025 : Cutover done 24/3/2025 : Installation complete, alignment WIP 12/3/2025 : Digi OB - pBTS 18 meter - NE site 3562A pBTS Country Heights, MAXIS - 45M 3 Legged Tower - FE site 1837B UPM TimeCell | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO 1x ODU 23G XMC3E SUB B HI | MW Swap | MW SWAP LINK 3562A3-1837B WITH HUAWEI_23G_1+0_0.6M/0.6M_SP_112MHZ_512QAM_889MBPS_XMC3E_SUB B_2.18KM DISMANTLE EXISTING LINK IMPACTED: 3562A3 | 1. REUSE EXISTING RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 3. INSTALL NEW 23G 0.6M SP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. REUSE EXISTING RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 3. INSTALL NEW 23G 0.6M SP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202504170453-GCI | GCI | SQ202503280384-GCI // SQ202503280397-GCI // SQ202504150088-GCI | 2025-05-07 | 2025-05-07 | Completed | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250306AH |  | 2025-03-07 | 2025-03-25 | Completed | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-03-31 | 2025-03-23 | 2025-03-25 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-24 | 2025-03-31 | 2025-03-23 | 2025-04-19 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-24 | 2025-03-24 | 2025-03-31 | 2025-03-23 | 2025-05-02 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-24 | 2025-03-31 | 2025-03-23 | 2025-03-24 | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
4150D_LOS | Gold Coast Condominium | DU00005782920 | Northern | Penang | 5.338635 | 100.309996 | [7 empty] | 06. Other Issue | 8/9: pending TP submission 26/8: pending access for survey | TSS+AA+TI+Dismantle |  | 23G_2+0_112M. NE_4150D. 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. FE_4049B. 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. | MW New Link / Reroute | Link reroute to new FE 4049B due to existing link LOS Block. Install new link / reroute with 23G_2+0_112M. Site Impacted : 4150D and Maxis BW. NE_4150D. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.All traffic migrate to new link and new FE routing. 6.Decom existing MW (4150D-4678C/P00331). FE_4049B. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.All traffic migrate to new link and new FE routing. 6.Create new In band DCN. 7.Decom existing MW link (4678C/P00331-4150D). | Link reroute to new FE 4049B due to existing link LOS Block. Install new link / reroute with 23G_2+0_112M. Site Impacted : 4150D and Maxis BW. NE_4150D. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.All traffic migrate to new link and new FE routing. 6.Decom existing MW (4150D-4678C/P00331). | Link reroute to new FE 4049B due to existing link LOS Block. Install new link / reroute with 23G_2+0_112M. Site Impacted : 4150D and Maxis BW. FE_4049B. 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.All traffic migrate to new link and new FE routing. 6.Create new In band DCN. 7.Decom existing MW link (4678C/P00331-4150D). | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202507040581-GTSB | MTK |  |  |  | Ongoing | [8 empty] | Unassigned | Not started |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25092694 |  | 2025-09-27 | 2025-09-30 | Completed | 2025-09-26 | 2025-09-27 | 2025-09-26 | 2025-09-30 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202507190085-GCI | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | CHEONG/SENG/WAH/7018000306
Q01461_AD | NG MENDAMIT | DU00005782921 | Sarawak | Sarawak | 4.450670 | 114.936960 |  |  |  | AUG 25 |  |  |  | 06. Other Issue | 11/9/2025 : FE no LOS | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | NO LOS ( (To perform LOS survey for reroute due to existing link affected by TM BKT SAGAN landslide issue) |  |  | XMC_5D_ SB B |  | 15 | 1.2 | 1.2 | CCSMY | SQ202507300497-CCS // SQ202511040226-CCS | CCSMY |  |  |  | Ongoing | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | Hermanwijaya bin suardi7021000085 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | LOS CLEAR Q01459,Q01490 | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507190089-GTSB | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | HSU//MYET CHAE/6799000011
9024H_LOS | Taiyo Yuden (Sarawak) Sdn Bhd | DU00005782922 | Sarawak | Sarawak | 1.527750 | 110.406270 |  |  |  | AUG 25 |  |  | ZTE | 06. Other Issue |  | TSS+TI+Dismantle |  | ETH Cable x 1 | MW New Link / Reroute | Based on actual TSS LOS survey. FE 9459A , Initial antenna location proceed to relocate at the peak platform of the structure. |  | Relocate the existing location of the anttena to the peak platform of the structure. | [5 empty] | Trintel | SQ202509040637-Trintel | Trintel | SQ202510150639-Trintel | 2025-10-15 | 2025-10-14 | Completed | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-30 | 2025-10-01 | 2025-09-30 | 2025-09-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-10-01 | 2025-09-30 | 2025-09-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102141 |  | 2025-10-22 | 2025-10-28 | Completed | 2025-10-21 | 2025-10-22 | 2025-10-21 | 2025-10-28 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 |  | JERRY SONLEY SALI7667000071 | Trintel TI | 2025-10-28 | 2025-10-28 | 2025-10-28 |  | JERRY SONLEY SALI7667000071 | Trintel TI | [7 empty] | 2025-10-28 | 2025-10-28 | 2025-10-28 |  | JERRY SONLEY SALI7667000071 | 2025-07-31: 2025-10-28; 2025-07-31: 2025-10-28; 2025-07-31: 2025-10-28; 2026-01-21: 2025-10-29 | [7 empty] | GCI | SQ202507190086-GCI | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | CHEONG/SENG/WAH/7018000306
Q01490_AD | NG DAMIT | DU00005782923 | Sarawak | Sarawak | 4.489642 | 114.907830 |  |  |  | AUG 25 |  |  |  | 06. Other Issue | 11/9/2025 : FE no LOS | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | NO LOS Q01490 to Q01459 Los block ❌ Q01490 to Q01548 Los Block ❌ Q01490 to Q01461 Los Block (To perform LOS survey for reroute due to existing link affected by TM BKT SAGAN landslide issue) | [7 empty] | CCSMY | SQ202507300497-CCS // SQ202511040226-CCS | CCSMY |  |  |  | Ongoing | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | Hermanwijaya bin suardi7021000085 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | NO LOS CLEAR | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507190089-GTSB | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | HSU//MYET CHAE/6799000011
Q02056_AD | RH AGIH | DU00005782924 | Sarawak | Sarawak | 4.391530 | 114.907660 |  |  |  | AUG 25 |  |  |  | 06. Other Issue | 11/9/2025 : FE no LOS | TSS+AA+TI+Dismantle |  |  | MW New Link / Reroute | NO LOS (To perform LOS survey for reroute due to existing link affected by TM BKT SAGAN landslide issue) | [7 empty] | CCSMY | SQ202507300497-CCS // SQ202511040226-CCS | CCSMY |  |  |  | Ongoing | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | Hermanwijaya bin suardi7021000085 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | LOS CLEAR Q01461,Q01490 | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507190089-GTSB | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | HSU//MYET CHAE/6799000011
1593H_LOS | 99 Speedmart KAPAR INDAH | DU00005789177 | Central | Selangor | 3.095456 | 101.383480 | [7 empty] | 06. Other Issue | 18/3/2026: BBU down | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS RTN510 NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | 1593H reroute to new FE 1084A due to existing link LOS Block. Relocate the existing Boon bracket to the location with LOS clear towards 1084A. Site Impacted : 1593H. NE_1593H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio. FE_1084A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.Traffic migrate to new route FE site and with new NLOS. 6.ETH cable patching to Ibeam Fiber Port. 7.Decom existing NLOS Radio | 1593H reroute to new FE 1084A due to existing link LOS Block. Site Impacted : 1593H. NE_1593H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio. | 1593H reroute to new FE 1084A due to existing link LOS Block. Site Impacted : 1593H. FE_1084A. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.Traffic migrate to new route FE site and with new NLOS. 6.ETH cable patching to Ibeam Fiber Port. 7.Decom existing NLOS Radio | [5 empty] | Magicell | SQ202507090484-Magicell | Magicell | SQ202507250421-Magicell // SQ202507250427-Magicell | 2025-11-11 | 2025-11-10 | Completed | 2025-07-11 | 2025-07-11 | 2025-07-10 | 2025-07-11 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-23 | 2025-07-22 | 2025-07-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071164 |  | 2025-07-12 | 2025-07-15 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-07 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2026-04-30 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  |  | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2026-04-30 | AHMAD RASHIDI BIN SAFRI7018000135 | 2025-07-31: 2025-10-06; 2025-07-31: 2025-10-06; 2025-07-31: 2025-10-06; 2026-01-21: 2026-04-28 | [7 empty] | GCI | SQ202507190083-GCI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | CHEONG/SENG/WAH/7018000306
4698A_IPR | Gurun Batu Lima | DU00005796381 | Northern | Kedah | 5.818024 | 100.525886 | [7 empty] | 00. Integrated/RFS Done | 22/07: CO Done | TSS+TI | L1+ATP+PAC | 1.10G Fiber SFP Module x 2 2.Fiber patch cord x 2 pairs | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) | [6 empty] | GCI | SQ202507250118-GCI | GCI | SQ202507230777-GCI | 2025-11-19 | 2025-11-18 | Completed | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-06 | 2025-08-05 | 2025-08-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071151 |  | 2025-07-12 | 2025-07-15 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-21 | 2025-08-04 | 2025-07-21 | 2025-07-24 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-07-21 | 2025-08-04 | 2025-07-21 | 2025-07-21 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-22 | 2025-07-21 | 2025-08-04 | 2025-07-21 | 2025-07-24 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-07-31: 2025-07-21; 2025-07-31: 2025-08-04; 2025-07-31: 2025-07-21; 2026-01-21: 2025-07-22 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507190085-GCI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | CHEONG/SENG/WAH/7018000306
W00778_IPR | MENARA MAXIS SEGAR PANDAN UTAMA | DU00005796382 | Central | Kuala Lumpur | 3.129302 | 101.754433 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | Upgrade patching from IDU to PTN 1G to 10G. Existing: Huawei RTN910A W00778_MENARA MAXISEGAR - 1619K/B00482_TMN KENCANA (PANDAN) GE1 to 70043-MAXISEGAR-AGGB01.celcom.com.my/GigabitEthernet0/6/0 Integration team to assign new port at IDU and PTN during migration | Upgrade patching from IDU to PTN 1G to 10G. Existing: Huawei RTN910A W00778_MENARA MAXISEGAR - 1619K/B00482_TMN KENCANA (PANDAN) GE1 to 70043-MAXISEGAR-AGGB01.celcom.com.my/GigabitEthernet0/6/0 Integration team to assign new port at IDU and PTN during migration | [6 empty] | GTSB | SQ202507090488-GTSB | GTSB | SQ202507090495-GTSB | 2025-11-19 | 2025-11-18 | Completed | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-14 | 2025-08-28 | 2025-08-14 | 2025-08-14 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-14 | 2025-08-15 | 2025-08-14 | 2025-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071162 |  | 2025-07-12 | 2025-07-22 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-01 | 2025-08-31 | 2025-08-01 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-08-01 | 2025-08-31 | 2025-08-01 | 2025-08-06 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-01 | 2025-08-01 | 2025-08-31 | 2025-08-01 | 2025-08-06 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-07-31: 2025-08-01; 2025-07-31: 2025-08-31; 2025-07-31: 2025-08-01; 2026-01-21: 2025-08-01 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507190083-GCI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | EZRIN TASNIM BIN ABDUL GANI6798000128
4967A_1_HU | Karangan(Mxs) | DU00005375391 | Northern | Kedah | 5.422820 | 100.663550 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | IF cable & Waveguide x1 | MW Swap | Decom existing ant and relocate to the highest Location in order to obtain LOS clearance. Swap waveguide suspect damaged | Decom existing ant , relocate to the highest ant location | Decom existing ant and relocate the ant to the highest ant location. | [5 empty] | GCI | SQ202504280464-GCI | GCI | SQ202505280628-GCI | 2026-01-28 | 2026-01-30 | Completed | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-19 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051598 |  | 2025-05-16 | 2025-06-10 | Completed | 2025-05-15 | 2025-05-16 | 2025-05-15 | 2025-06-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [7 empty] | 2025-05-09 | 2025-05-31 | 2025-05-09 | 2025-07-06 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | GCI TI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-27 | 2025-05-09 | 2025-05-31 | 2025-05-09 | 2026-02-26 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | 2025-07-31: 2025-05-09; 2025-07-31: 2025-05-31; 2025-07-31: 2025-05-09; 2026-01-21: 2025-05-23 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
W00253_HU | JLN PUDU LAMA | DU00004153893 | Central | Kuala Lumpur | 3.144069 | 101.707728 |  |  |  | JUN 25 |  |  |  | 00. Integrated/RFS Done | 20/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_W00130 New 18G_0.6M(MDD) x1. New RTN910A x1. New XMC_5D, Sub A_Hi x2. FE_W00253 New 18G_0.6M(MDD) x1. New RTN910A x1. New XMC_5D, Sub A_Lo x2. | MW Swap | Link Existing SM 23G_1+0_56M Swap existing link to new HW 18G_2+0_112M_512QAM_EPLA Site Impacted : W00103, W01399, Smallcell Jalan Changkat Alor NE_W00103 1.Install new 18G_0.6M(MDD). 2.Install new RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D , Sub A_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Enable port 8-EM6-2 of new RTN910A(RTN01). 6.Patching port LAN 1 of SM IDU ALCPlus2e(Link ID CT10178) MW Link W01399-W00103 to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 7.Patching port LAN 1 of SM IDU ALFOPlus of Smallcell Jalan Changkat Alor to port 8-EM6-2 of new RTN910A(RTN01). Configure it. 8.Reuse existing Vlan Services and migrate RAN traffic to new MW link. 9.Configure DCN Inband for RTN01. 10.Later, decom existing SM 23G_1+0_56M. FE_W00253 1.Install new 18G_0.6M(MDD). 2.Install new RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D , Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing Cisco port gi0/0/1(Reused). Configure it. 6.Reuse existing Vlan Services. 7.Configure DCN Inband for RTN01. 8.Later, decom existing SM 23G_1+0_56M. | Link Existing SM 23G_1+0_56M Swap existing link to new HW 18G_2+0_112M_512QAM_EPLA Site Impacted : W00103, W01399, Smallcell Jalan Changkat Alor NE_W00103 1.Install new 18G_0.6M(MDD). 2.Install new RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D , Sub A_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Enable port 8-EM6-2 of new RTN910A(RTN01). 6.Patching port LAN 1 of SM IDU ALCPlus2e(Link ID CT10178) MW Link W01399-W00103 to port 8-EM6-1 of new RTN910A(RTN01). Configure it. 7.Patching port LAN 1 of SM IDU ALFOPlus of Smallcell Jalan Changkat Alor to port 8-EM6-2 of new RTN910A(RTN01). Configure it. 8.Reuse existing Vlan Services and migrate RAN traffic to new MW link. 9.Configure DCN Inband for RTN01. 10.Later, decom existing SM 23G_1+0_56M. | Link Existing SM 23G_1+0_56M Swap existing link to new HW 18G_2+0_112M_512QAM_EPLA Site Impacted : W00103, W01399, Smallcell Jalan Changkat Alor FE_W00253 1.Install new 18G_0.6M(MDD). 2.Install new RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D , Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching port 8-EM6-1 of new RTN910A(RTN01) to existing Cisco port gi0/0/1(Reused). Configure it. 6.Reuse existing Vlan Services. 7.Configure DCN Inband for RTN01. 8.Later, decom existing SM 23G_1+0_56M. | XMC_5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_0.6M(MDD) x1. | Magicell | SQ202506250168-Magicell | Magicell | SQ202505300199-Magicell // SQ202505300201-Magicell | 2026-01-28 | 2026-02-03 | Completed | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-02-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250520AI |  | 2025-05-21 | 2025-05-23 | Completed | 2025-05-20 | 2025-05-21 | 2025-05-20 | 2025-05-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-08-13 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-08-13 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-10 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-08-13 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-10 | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202505070162-GTSB
B02499_LOS | B058E_B02499OD_JLNSKLHKGJENJAROM | DU00005623350 | Central | Selangor | 2.884510 | 101.518034 | [7 empty] | 03. TSS Only | site should use PTN | TSS |  |  | MW New Link / Reroute | [8 empty] | GTSB | SQ202506120231-GTSB | GTSB | No PR required-Work at TSS only | 2025-12-23 | 2025-12-16 | Completed | 2025-08-11 | 2025-08-25 | 2025-08-11 | 2025-08-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-11 | 2025-08-25 | 2025-08-11 | 2025-08-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-11 | 2025-08-18 | 2025-08-11 | 2025-08-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050643-GTSB
2009B_IPR | Tmn Ehsan (KJS) | DU00005623351 | Central | Selangor | 3.224040 | 101.625080 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | Upgrade 10G port at NE(RTN910A-RTN01) & FE(IBeam-RTN910C). NE_2009B New SFP Module 10G with 10Km 1310nm or suitable SFP Module(get advise from ZTE IPRAN Team). New Optical Patch Cord cable with suitable type and length(get advise from ZTE IPRAN Team). FE_1309A New SFP Module 10G with 10Km 1310nm or suitable SFP Module(get advise from ZTE IPRAN Team). New Optical Patch Cord cable with suitable type and length(get advise from ZTE IPRAN Team). | IPRAN Port Upgrade | IPRAN Port Upgrade from existing Optical 1G to 10G port at NE(RTN910A-RTN01) & FE(IBeam-RTN910C). Site Impacted : 2009B, 3584B_4, 1545B & 1778H. NE_2009B. 1.Enable port 8-EM6-3 of existing RTN910A(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01) to ODF. 4.Request new vlan services if needed from ZTE IPRAN Team. 5.Disable port 8-EM6-6 of existing RTN910A(RTN01) and remove existing Optical Patch cord. FE_1309A. 1.Insert new suitable SFP Module 10G into IBeam port. Please obtain info from ZTE IPRAN Team for new 10G port. 2.Patching Optical Patch Cord cable from IBeam(RTN910C) to ODF. 3.Request new vlan services if needed from ZTE IPRAN Team. | IPRAN Port Upgrade from existing Optical 1G to 10G port at NE(RTN910A-RTN01) & FE(IBeam-RTN910C). Site Impacted : 2009B, 3584B_4, 1545B & 1778H. NE_2009B. 1.Enable port 8-EM6-3 of existing RTN910A(RTN01). 2.Insert new suitable SFP Module 10G. Configure it. 3.Patching Optical Patch Cord cable from port 8-EM6-3 of existing RTN910A(RTN01) to ODF. 4.Request new vlan services if needed from ZTE IPRAN Team. 5.Disable port 8-EM6-6 of existing RTN910A(RTN01) and remove existing Optical Patch cord. | IPRAN Port Upgrade from existing Optical 1G to 10G port at NE(RTN910A-RTN01) & FE(IBeam-RTN910C). Site Impacted : 2009B, 3584B_4, 1545B & 1778H. FE_1309A. 1.Insert new suitable SFP Module 10G into IBeam port. Please obtain info from ZTE IPRAN Team for new 10G port. 2.Patching Optical Patch Cord cable from IBeam(RTN910C) to ODF. 3.Request new vlan services if needed from ZTE IPRAN Team. | [5 empty] | GTSB | SQ202507010378-GTSB | GTSB | SQ202507010373-GTSB | 2025-11-14 | 2025-11-07 | Completed | 2025-07-16 | 2025-07-30 | 2025-07-16 | 2025-07-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-16 | 2025-07-30 | 2025-07-16 | 2025-07-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-18 | 2025-07-25 | 2025-07-18 | 2025-07-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-14 | 2025-11-07 | 2025-11-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070406 |  | 2025-07-06 | 2025-07-10 | Completed | 2025-07-05 | 2025-07-06 | 2025-07-05 | 2025-07-10 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-10 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-10 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-09 | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-15 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2025-06-03: 2025-07-08; 2025-06-03: 2025-07-08; 2025-06-03: 2025-07-08; 2025-06-10: 2025-07-09 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506050643-GTSB
1140A-1235A | Celcom Tanjung Sepat | DU00003883703 | Central | Selangor | 2.658281 | 101.569213 |  |  |  |  | Cancel / Drop | Done under DU 3920B_PostMOCN TX NIC | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 3920B_PostMOCN TX NIC |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3502A7-K00215 | pBTS Tikam Batu (KM) | DU00003883704 | Northern | Kedah | 5.587585 | 100.437283 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 23/9: HU Solution done under K00015_PostMOCN 27/8: pBTS to be relocated. Not proceed with HU Solutions | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_3502A_7 New 23G_0.6M(MAC)+OMT x1. Re-use existing RTN910A x1. New XMC_3, Sub B_Hi x1. FE_4289B New 23G_1.2M(MS) x1. Re-use existing RTN910A x1. New XMC_3, Sub B_Lo x1. | MW Swap | Existing HW MW Link 23G_1+0_56M_1024QAM_480M. Swap existing HW MW Link with new HW MW Link 23G_1+0_112M_512QAM_889M. Later, decom existing 23G ODU and 23G antenna ONLY of HW MW Link 23G_1+0_56M_1024QAM_480M. Do not decom RTN910A at both NE(3502A_7) and at FE(4289B). Site Impacted : 3502A_7. NE_3502A_7 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub B_Hi x1. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link new HW MW Link 23G_1+0_112M_512QAM_889M. Configure it. 6.Later, decom existing 23G ODU and 23G antenna ONLY of HW MW Link 23G_1+0_56M_1024QAM_480M. Do not decom RTN910A at both NE(3502A_7) and at FE(4289B). FE_4289B/K00215 1.Install new 23G_1.2M(MS) x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub B_Lo x1. Configure it. 4.Re-use existing vlan services and existing port at IBeam. 5.Migrate traffic to new link new HW MW Link 23G_1+0_112M_512QAM_889M. Configure it. 6.Later, decom existing 23G ODU and 23G antenna ONLY of HW MW Link 23G_1+0_56M_1024QAM_480M. Do not decom RTN910A at both NE(3502A_7) and at FE(4289B). | Existing HW MW Link 23G_1+0_56M_1024QAM_480M. Swap existing HW MW Link with new HW MW Link 23G_1+0_112M_512QAM_889M. Later, decom existing 23G ODU and 23G antenna ONLY of HW MW Link 23G_1+0_56M_1024QAM_480M. Do not decom RTN910A at both NE(3502A_7) and at FE(4289B). Site Impacted : 3502A_7. NE_3502A_7 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub B_Hi x1. Configure it. 4.Re-use existing vlan services. 5.Migrate traffic to new link new HW MW Link 23G_1+0_112M_512QAM_889M. Configure it. 6.Later, decom existing 23G ODU and 23G antenna ONLY of HW MW Link 23G_1+0_56M_1024QAM_480M. Do not decom RTN910A at both NE(3502A_7) and at FE(4289B). | Existing HW MW Link 23G_1+0_56M_1024QAM_480M. Swap existing HW MW Link with new HW MW Link 23G_1+0_112M_512QAM_889M. Later, decom existing 23G ODU and 23G antenna ONLY of HW MW Link 23G_1+0_56M_1024QAM_480M. Do not decom RTN910A at both NE(3502A_7) and at FE(4289B). Site Impacted : 3502A_7. FE_4289B/K00215 1.Install new 23G_1.2M(MS) x1. 2.Re-use existing RTN910A. 3.Install new XMC_3, Sub B_Lo x1. Configure it. 4.Re-use existing vlan services and existing port at IBeam. 5.Migrate traffic to new link new HW MW Link 23G_1+0_112M_512QAM_889M. Configure it. 6.Later, decom existing 23G ODU and 23G antenna ONLY of HW MW Link 23G_1+0_56M_1024QAM_480M. Do not decom RTN910A at both NE(3502A_7) and at FE(4289B). | XMC_3 | MAC & MS | 23G | 23G_0.6M(MAC)+OMT x1. | 23G_1.2M(MS) x1. | MTK | SQ202509030937-MTK | MTK | SQ202509030928-MTK // SQ202509030932-MTK |  |  | Ongoing | 2025-09-09 | 2025-09-30 | 2026-04-03 | 2026-04-03 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY251001AW |  | 2025-10-03 | 2025-10-09 | Completed | 2025-10-02 | 2025-10-03 | 2025-10-01 | 2025-10-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-23 | 2026-03-03 | 2026-03-03 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2026-01-09 | 2026-01-23 | 2026-03-03 | 2026-03-04 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-12 | 2026-01-09 | 2026-01-23 | 2026-03-04 | 2026-03-04 | DZULFAIZAL//BIN MAULUF/8225000001 | 2026-01-09 | 2026-01-23 | 2026-02-26 | 2026-02-26 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505070167-GTSB
4986C-4637A | Taman Melati SP | DU00003883705 | Northern | Kedah | 5.657504 | 100.486262 | WK36-40 | SEP 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 4/12: D2: Cutover done. Post-CO alarm clearance ongoing 2/12: TI Done, pending CO due SFP issue | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 0.6m/0.6m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz 0.6m SP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz 0.6m SP | MW Swap | Existing link Huawei 4986C-4637A-01_ZNIC To swap Existing link 23GHz 1+0 56MHz with new Huawei link 18GHz 1+0 112MHz Impacted sites: 4986C NE (4986C): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link FE (4637A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Patch new RTN to new xC PTN port (ops team to assign new port) 4) Migrate traffic to new link. Create new DCN 5) Decom existing link | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202411150562-GCI // SQ202504150095-GCI | 2025-12-03 | 2025-12-03 | Completed | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2024-12-04 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112590 |  | 2024-11-26 | 2024-12-09 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2024-12-09 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2024-12-09 | Ling/Tao6800000135 |  | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2024-12-20 | Ling/Tao6800000135 |  | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-12-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2024-12-10 | Ling/Tao6800000135 | 2026-01-09: 2024-12-02; 2026-01-23: 2024-12-02; 2026-02-26: 2024-12-02; 2026-02-26: 2024-12-02 |  |  | 2024-12-19 | 2025-01-19 | 2024-12-19 | 2024-12-19 | ASTI//GANIS PUTRIANI/6237001358
3557B-1099A | Surau Ar-Rahman Presint Inang | DU00003883706 | Central | Selangor | 3.080208 | 101.429410 |  |  |  |  | Cancel / Drop | TX Sow change to cancel / drop | ZTE | 00. Site Out/Drop | 6/3/2025 : TX Sow change to cancel / drop |  |  |  | Cancel / Drop | MW Link has been reroute by MSP | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
A00508-A00458 | A044A_A00508OD_BKTCHAWI | DU00003883707 | Northern | Perak | 4.110432 | 100.960681 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | TI IN PLAN | ZTE | ZTE | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU 10/06: CO Done | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M refer to A00508_HU (DU Code DU00005509293) NE_A00508 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub B_Lo x1. FE_A00458 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub B_Hi x1. | MW Parallel Link | Existing link 13G_2+0_28M Install parallel link to 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M refer to A00508_HU (DU Code DU00005509293). Site Impacted : A00508 , A00970. NE_A00508 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config 3.Install new XMC_5D , Sub B_Lo for ant 2 with CA. 4.Create service cross connect , CA and EPLA for 6+0 links. 5.Enable GE1 , A00508_BBU traffic migrate to new parallel link 13G_6+0_28M. 6.No decom existing SM link. FE_A00458 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub B_Hi for ant 2 with CA. 4.Create service cross connect , CA and EPLA for 6+0 links. 5.Traffic migrate to new 13G_6+0_28M. 6.Create new In band DCN. 7.No decom existing MW link. | Existing link 13G_2+0_28M Install parallel link to 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M refer to A00508_HU (DU Code DU00005509293). Site Impacted : A00508 , A00970. NE_A00508 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config 3.Install new XMC_5D , Sub B_Lo for ant 2 with CA. 4.Create service cross connect , CA and EPLA for 6+0 links. 5.Enable GE1 , A00508_BBU traffic migrate to new parallel link 13G_6+0_28M. 6.No decom existing SM link. | Existing link 13G_2+0_28M Install parallel link to 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M refer to A00508_HU (DU Code DU00005509293). Site Impacted : A00508 , A00970. FE_A00458 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub B_Hi for ant 2 with CA. 4.Create service cross connect , CA and EPLA for 6+0 links. 5.Traffic migrate to new 13G_6+0_28M. 6.Create new In band DCN. 7.No decom existing MW link. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GTSB | SQ202504280474-GTSB | GTSB | SQ202506120256-GTSB // SQ202506120258-GTSB | 2025-12-03 | 2025-12-03 | Completed | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051484 |  | 2025-05-15 | 2025-05-29 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-02 | 2025-06-03 | 2025-06-03 | 2025-06-25 | KANNAN A/L RAMACHANDRAN6799000115 |  | 2025-06-02 | 2025-06-03 | 2025-06-02 | 2025-07-06 | KANNAN A/L RAMACHANDRAN6799000115 |  | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-10 | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2026-02-27 | HAFIZ AMEER HAMZA//MUHAMMAD NAWAZ/6000028652 | 2026-01-09: 2025-07-16; 2026-01-23: 2025-07-16; 2026-02-26: 2025-07-16 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505070152-GCI | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | CHEONG/SENG/WAH/7018000306
4489B-4546A | Heritage Hotel RDD | DU00003883708 | Northern | Perak | 4.595210 | 101.100090 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | 4489B-4546A MW5 not exist in NMS. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4466A-4457A_2 | Anak Bukit | DU00003883709 | Northern | Kedah | 4.921788 | 100.724710 | WK36-40 | SEP 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 23/9: Pending Site BoM | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112Mhz to 2+0_112Mhz with EPLA. NE 1. ISM8 x 1. 2. XMC_3E x 2 (A,B_Lo). 3. ant DP1.2m_(MAC)+OMT x1. FE 1. XMC_3E x 2 (A,B_Hi). 2. ant DP 0.6m_(MAC)+OMT x1. | MW Swap | Swap existing link 18G_1+0_112Mhz to 2+0_112Mhz with EPLA. Site Impacted : 4438D,4567D. NE_4466A 1.Install new 4_ISM8 to configure 2+0. 2.Reuse existing 4466A_RTN 3.Swap existing 1+0 XMC_3 ODU to 2 x XMC_3E for 2+0 config. 4.Apply EPLA 5.Install new 1.2m DP antenna_(MAC)+OMT. 6.Decom existing antenna + ODU. FE_4457A 1.Swap existing 1+0 XMC_3 ODU to 2 x XMC_3E for 2+0 config. 2.Upgrade existing 7_ISM8 1+0 to 2+0 configuration. 3.Apply EPLA. 4.Install new 18G_ 0.6m DP antenna_(MAC)+OMT. 5.LAG physical port GE1&2. 6.Decom existing XMC_3 ODU + Antenna. | Swap existing link 18G_1+0_112Mhz to 2+0_112Mhz with EPLA. Site Impacted : 4438D,4567D. NE_4466A 1.Install new 4_ISM8 to configure 2+0. 2.Transfer existing link 7_ISM8-1+0 to 4_ISM8 upgrade to 2+0_112Mhz direct towards 4457A. 3.Swap existing 1+0 XMC_3 ODU to 2 x XMC_3E for 2+0 config. 4.Apply EPLA 5.Install new 1.2m DP antenna_(MAC)+OMT. 6.Decom existing antenna + ODU. | Swap existing link 18G_1+0_112Mhz to 2+0_112Mhz with EPLA. Site Impacted : 4438D,4567D. FE_4457A 1.Swap existing 1+0 XMC_3 ODU to 2 x XMC_3E for 2+0 config. 2.Upgrade existing 7_ISM8 1+0 to 2+0 configuration. 3.Apply EPLA. 4.Install new 18G_ 0.6m DP antenna_(MAC)+OMT. 5.LAG physical port GE1&2. 6.Decom existing XMC_3 ODU + Antenna. | XMC_3E | MAC | 17920.000 18250.000 | 1.2M | 0.6M | CCSMY | SQ202411140303-CCS | CCSMY | SQ202411150552-CCS // SQ202504260175-CCS |  |  | Ongoing | 2025-02-10 | 2025-02-21 | 2025-02-12 | 2025-05-22 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY241125AA |  | 2024-11-26 | 2025-02-25 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2025-02-25 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-02-25 | ZEESHAN IQBAL//MUHAMMAD IQBAL/6000003306 | CCS TI | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-07-06 | ZEESHAN IQBAL//MUHAMMAD IQBAL/6000003306 | CCS TI | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2026-03-31 | ZEESHAN IQBAL//MUHAMMAD IQBAL/6000003306 | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-07-18 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | NG HONG JIE7018000036 | Logistic Team | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358
3027C-1099A | Sg Kapar Industrial (REL) | DU00003883710 | Central | Selangor | 3.102880 | 101.400110 |  |  | WK49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 19/12: Solution released, plan execution by Tx Ops | AA | PAC | NA | MW Remote Upgrade | Existing link 18G_2+0_56M Remote Software Upgrade to 18G_2+0_112M , Alrm required to overcome in advance. | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-21 | MOHD//AMIR BIN SAMSI/6799000184 | [17 empty] | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
4923A-4416A | Tanjung Malim 2 | DU00003883711 | Northern | Selangor | 3.694640 | 101.513385 | WK36-40 | SEP 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 10/12: D3: Cutover done 6/12: MOS & TI In plan 29/10: 4923A cannot due, due to hardware issue, card using isv3 cannot 112MHz | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_4923A 23G_DP_0.6m(MAC) x1. XMC_3-2+0 , Sub_A & B_Hi x2. FE_4416A. 23G_DP_0.6m(MAC) x1. RTN910A x1 XMC_3 , Sub_A & B_Lo x2. | MW Swap | Existing link 23G_1+0_56M Swap existing link 23G_2+0_112M due to Not Support Remote Software upgrade. Site impacted: 4923A. NE_4923A 1.Install new 23G_DP_0.6m(MAC). 2.Reuse existing 4923A_RTN01, 7_ISM8-2+0. 3.Install new XMC_3-2+0 , Sub_A & B_Hi. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new link. 6.Decom existing Ant & ODU. FE_4416A. 1.Insatll new 23G_DP_0.6m(MAC). 2.Install new RTN910A.7_ISM8-2+0. 3.Install new XMC_3 , Sub_A & B_Lo. 4.Enable EPLA & service cross connect. 5.Enable GE port patching to Ibeam and create In Band DCN. 5.Migrate traffic to new link. 6.Decom existing MW link (4416A-4923A). | [7 empty] | GCI | SQ202412230238-GCI | GCI | SQ202412100376-GCI // SQ202504150095-GCI | 2025-12-04 | 2025-12-03 | Completed | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-12-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-18 | 2024-12-18 | 2024-12-18 | 2024-12-18 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241105C7 |  | 2024-12-15 | 2024-12-15 | Completed | 2024-12-15 | 2024-12-15 | 2024-12-15 | 2024-12-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-09 | 2024-12-31 | 2024-12-09 | 2024-12-15 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-12-09 | 2024-12-31 | 2024-12-09 | 2024-12-15 | team21gcitechnicalteam21gcitechnical | GCI TI | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-12-09 | 2024-12-31 | 2024-12-09 | 2024-12-12 | team21gcitechnicalteam21gcitechnical | 2024-12-09 | 2024-12-31 | 2024-12-09 | 2024-12-10 | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | NG HONG JIE7018000036 | Logistic Team | 2024-12-19 | 2025-01-19 | 2024-12-19 | 2024-12-19 | ASTI//GANIS PUTRIANI/6237001358
4027C-4476B | Bt 10 Lekir | DU00003883712 | Northern | Perak | 4.124462 | 100.766985 |  | JUL 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 22/10: Pending Site DO | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112Mhz NE_4027C 18G_DP_1.2M (MAC)+OMT x1. RTN910A x1. XMC_3E , Sub_ A & B x2. FE_4476B 18G_DP_1.2M (MAC)+OMT x1. RTN910A x1. XMC_3E , Sub_A & B x2. | MW Parallel Link | Install new parallel link 18G_2+0_112Mhz. Site Impacted: 4027C,4199R. NE_4027C 1.Install new 18G_DP_1.2M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0 to configure as 2+0.(RTN No provide by MSP team). 3.Install new XMC_3E , Sub A & B config as 2+0. 5.Create service cross connect and enable EPLA. 6.Enable GE 1 , migrate 4027C BBU traffic to new parallel link 18G_2+0_112M. 7.No decom existing MW link due to install new parallel link. FE_4476B 1.Install new 18G_DP_1.2M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0 to configure as 2+0.(RTN No provide by MSP team). 3.Install new XMC_3E , Sub A & B config as 2+0. 5.Create service cross connect and enable EPLA. 6.Enable GE1 , patching to Ibeam and create new In-band DCN. 7.No decom existing MW link due to install new parallel link. | [7 empty] | GCI | SQ202411140311-GCI | GCI | SQ202411150562-GCI // SQ202504150095-GCI | 2025-12-04 | 2025-12-03 | Completed | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24122733 |  | 2024-12-28 | 2025-02-11 | Completed | 2024-12-27 | 2024-12-28 | 2024-12-27 | 2025-02-11 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-04 | 2025-02-28 | 2025-02-04 | 2025-02-11 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | GCI TI | 2025-02-04 | 2025-02-28 | 2025-02-04 | 2025-03-09 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | GCI TI | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-05 | 2025-02-04 | 2025-02-28 | 2025-02-04 | 2025-03-06 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | 2026-01-09: 2025-02-04; 2026-01-23: 2025-02-28; 2026-02-26: 2025-02-04; 2026-02-26: 2025-03-05 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
4685A-4966A | Taman Selasih | DU00003883713 | Northern | Kedah | 5.376430 | 100.536640 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Site Out/Drop | 15/8: Pending BoQ, TX SoW Details |  |  |  | Cancel / Drop | DU00002749396 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4466A-4457A_3 | Anak Bukit | DU00003883714 | Northern | Kedah | 4.921788 | 100.724710 | WK36-40 | SEP 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 14/10: Pending Site DO | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 0.6m/1.2m XMC3E NE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub B Hi 3) 1x18GHz 0.6m SP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub B Lo 3) 1x18GHz 1.2m SP | MW Swap | Existing link SM 4466A-4457A MW2. To swap SM link with new Huawei link 1+0 112MHz (reuse existing SM MW frequency channel) Impacted sites: 4466A,4251H NE (4466A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 (reuse existing SM MW frequency channel) 3) Transfer 4466A BBU to new RTN GE1 4) Transfer NLOS 4251H to new RTN GE2 5) Decom SM link FE (4457A): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 (reuse existing SM MW frequency channel) 3) Patch new RTN to new CP port (ops team to assign new port) 4) Migrate traffic 4466A and 4251H to new link 5) Create new DCN for RTN and migrate existing DCN for NLOS 6) Decom SM link | [7 empty] | CCSMY | SQ202411140303-CCS | CCSMY | SQ202411260109-CCS // SQ202504260175-CCS |  |  | Ongoing | 2025-02-10 | 2025-02-21 | 2025-02-12 | 2025-05-22 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY241125AC |  | 2024-11-26 | 2025-02-25 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2025-02-25 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-10 | 2024-12-27 | 2025-02-20 | 2025-02-25 | ZEESHAN IQBAL//MUHAMMAD IQBAL/6000003306 | CCS TI | 2025-03-07 | 2025-03-31 | 2025-03-07 | 2025-07-06 | ZEESHAN IQBAL//MUHAMMAD IQBAL/6000003306 | CCS TI | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-03-07 | 2025-03-31 | 2025-03-07 | 2026-03-31 | ZEESHAN IQBAL//MUHAMMAD IQBAL/6000003306 | 2026-01-09: 2025-03-07; 2026-01-23: 2025-03-31; 2026-02-26: 2025-03-07; 2026-02-26: 2025-07-18 |  |  | 2025-03-13 | 2025-04-13 | 2025-03-13 | 2025-03-13 | ASTI//GANIS PUTRIANI/6237001358
4466A-4457A_1 | Anak Bukit | DU00003883715 | Northern | Kedah | 4.921788 | 100.724710 | WK36-40 | SEP 24 | W49-52 | DEC 24 |  |  |  | 00. Integrated/RFS Done | 23/9: Pending Site BoM | TSS+AA+TI | L1+ATP+PAC | 18G_1+0_112Mhz to 2+0_112Mhz with EPLA. NE_4466A_RTN03 1.XMC_5D x1 (Sub B_Hi). 2.DP 1.2m ant x1. 3.ISM8 x1 FE_4457A_RTN05 1.XMC_5D x1 (Sub B_Lo). 2.DP 0.6m ant x1. 3.ISM8 x1. | MW Parallel Link | Existing link 18G_1+0_112Mhz , new parallel link 18G_2+0_112M Hardware upgrade with 18G_1+0_112Mhz to config 2+0_112Mhz with EPLA. Site Impacted: 4424A,4466A,4565D. NE_4466A_RTN03 1.Install New IF cable to existing XMC_5D to configure 2+0_112M. 2.Apply EPLA. 3.Reuse existing DP_ antenna (MDD). FE_4457A_RTN05 1.Install new IF cable to existing XMC_5D to configure 2+0_112M. 2.Apply EPLA. 3.Reuse existing DP_ antenna (MDD). 4.LAG physical port GE 1&2. | [7 empty] | CCSMY | SQ202411140303-CCS | CCSMY | SQ202411260109-CCS // SQ202504260175-CCS |  |  | Ongoing | 2025-02-10 | 2025-02-21 | 2025-02-12 | 2025-05-22 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY241125A8 |  | 2024-11-26 | 2025-02-15 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2025-02-15 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-12-23 | 2024-12-31 | 2024-12-23 | 2025-02-15 | ZEESHAN IQBAL//MUHAMMAD IQBAL/6000003306 | CCS TI | 2024-12-23 | 2024-12-31 | 2024-12-23 | 2025-07-06 | ZEESHAN IQBAL//MUHAMMAD IQBAL/6000003306 | CCS TI | 2025-01-07 | 2025-01-07 | 2025-01-07 | 2025-01-07 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-12-23 | 2024-12-31 | 2024-12-23 | 2025-09-20 | ZEESHAN IQBAL//MUHAMMAD IQBAL/6000003306 | 2026-01-09: 2025-08-06; 2026-01-23: 2025-08-31; 2026-02-26: 2025-08-06; 2026-02-26: 2025-09-18 |  |  | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
7030B-7013A | Kg Kuap | DU00003883716 | Sabah | Sabah | 6.906567 | 116.836180 |  |  |  |  | DT February |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3 SUB A HI 1x ODU 23G XMC3 SUB A LO | MW Parallel Link | MW PARALLEL LINK 7030B-7013A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3_SUB_A_LINK_1.12KM IMPACTED: 7030B, 7351C, 7654C EPLA EXISTING LINK 23G 2+0 WITH NEW LINK | 1. INSTALL NEW ISM8 CARD AT SLOT 4 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM EPLA WITH EXISTING 23G 2+0 LINK | 1. INSTALL NEW ISM8 CARD AT SLOT 3 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM EPLA WITH EXISTING 23G 2+0 LINK 5. PATCH TO NEW 10G PORT | XMC3 | MAC | 23G | 0.6 | 0.6 | NR services | SQ202604200373-NR Services | NR services | SQ202604200353-NR Services // SQ202604200358-NR Services |  |  | Ongoing | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022338 |  | 2026-02-24 | 2026-04-20 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-04-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-14 | 2026-05-14 | 2026-04-14 | 2026-04-20 | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-04-14 | 2026-05-14 | 2026-04-14 | 2026-04-24 | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-17 | 2026-04-14 | 2026-05-14 | 2026-04-14 | 2026-04-24 | MIKE MICRON DOLIK6000068237 | 2026-01-09: 2026-04-14; 2026-01-23: 2026-05-14; 2026-02-26: 2026-04-14; 2026-02-26: 2026-04-16 | [7 empty] | GCI | SQ202512170731-GCI | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | EZRIN TASNIM BIN ABDUL GANI6798000128
9696A-9356B | Taman Ria 1 MP | DU00003883717 | Sarawak | Sarawak | 3.190606 | 113.041593 |  |  |  |  | Cancel / Drop | 04/6: Not in GOp list |  | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050659-GTSB | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | HSU//MYET CHAE/6799000011
2436A-1145A | Bukit Beruntung (CELCOM) | DU00003883718 | Central | Selangor | 3.433820 | 101.576520 | WK36-40 | SEP 24 | WK36-40 | SEP 24 | Cancel / Drop | MSP still observe | ZTE | 00. Site Out/Drop | 28/2/2025 : Under observation 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | [8 empty] | Allstar | No PR required-Site drop/cancel | Allstar | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9366B-9106A | DSS BINTULU | DU00003907199 | Sarawak | Sarawak | 3.202715 | 113.057276 | [6 empty] | ZTE | 00. Integrated/RFS Done | 6/11: D2: Cutover done. Post-CO T/S ongoing 4/11: MOS & Pre-installation in progress 21/10: Urgent to upgrade. Lastmile site to MOCN. Pending Site DO | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_0.6/0.6_SP_SB A | MW Swap | SWAP MW LINK 9366B-9106A WITH HUAWEI_18GHZ_1+0_56MHZ_0.6M NE: 1. Swap existing NEC with HW RTN910A. 2. Swap existing ODU with XMC-3E_SB A. 3. Swap existing Antenna with 18G_0.6_SP. 4. Configure 18G_1+0_0.6/0.6M_55MHz. FE: 1. Swap existing NEC with HW RTN910A. 2. Swap existing ODU with XMC-3E_SB A. 3. Swap existing Antenna with 18G_0.6_SP. 4. Configure 18G_1+0_0.6/0.6M_55MHz. | [7 empty] | Datasco | SQ202410100839-Datasco | Trintel | SQ202411120064-Trintel // SQ202504260214-Trintel | 2024-10-18 | 2024-10-16 | Completed | 2024-10-07 | 2024-10-07 | 2024-10-07 | 2024-10-09 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-08 | 2024-10-11 | 2024-10-08 | 2024-10-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-08 | 2024-10-11 | 2024-10-08 | 2024-10-08 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-16 | 2024-10-18 | 2024-10-16 | 2024-10-16 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24102382 |  | 2024-10-24 | 2024-10-31 | Completed | 2024-10-23 | 2024-10-24 | 2024-10-23 | 2024-10-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-04 | 2024-12-04 | 2024-11-05 | 2024-11-05 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2024-11-04 | 2024-12-04 | 2024-11-04 | 2024-11-07 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2024-11-07 | 2024-11-07 | 2024-11-07 | 2024-11-07 | SHUJAAT//ALI/6800000124 |  |  | 2024-11-04 | 2024-12-04 | 2024-11-07 | 2024-11-07 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2024-11-04 | 2024-12-04 | 2024-11-04 | 2024-11-04 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
4608B_AD | Tebing Tinggi | DU00006277835 | Northern | Perlis | 6.408957 | 100.137610 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X 10G SFP 2X RTN910A 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB B HI 1x ODU 18G XMC5D SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE LINK 4608B-R00023 WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC5D_SUB_B_3.01KM IMPACTED: 4608B DISMANTLE EXISTING LINK 4608B-4604A (CHECK THERE IS 2 LINK TO DISMANTLE) REROUTING LINK DUE TO JBA KUALA PERLIS NEED TO DECOM UPLINK R00023-R00028 NEED TO UPGRADE FIRST DU R00023_AD | 1. INSTALL NEW IDU RTN 910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 4608B-4604A (CHECK THERE IS 2 LINK TO DISMANTLE) | 1. INSTALL NEW IDU RTN 910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 4608B-4604A (CHECK THERE IS 2 LINK TO DISMANTLE) 6. 10G SFP AT IDU TO IDU DUE TO CAPACITY MORE THAN 1G | XMC5D | MDD | 18G | 0.6 | 0.6 | Magicell | SQ202511270710-Magicell // SQ20260429056-Magicell | Magicell | SQ202511260111-Magicell // SQ202511260115-Magicell | 2025-12-05 | 2025-12-04 | Completed | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-04 | 2025-12-05 | 2025-12-04 | 2025-12-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251117A1 |  | 2025-12-13 | 2025-11-20 | Completed | 2025-11-18 | 2025-12-13 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-29 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  | 2025-12-01 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-03 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-28 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511130557-GCI | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01477-Q00061 | SC RIVEREDGE | DU00003465010 | Sarawak | Sarawak | 1.558380 | 110.324055 | WK19 | MAY 24 |  |  | Drop | Pass to Huawei | ZTE | 03. TSS Only | 7/2/2024 : NE site does not have any existing cabinet to house the normal RTN solution, also only AC power available at NE. Need to discuss with CD for the possible approach | TSS |  | 23GHz_0.6m/0.6m_MS_1+0_112MHz | MW Swap | DCN VLAN : 408, PORT NUMBER : GigabitEthernet0/9/5 Please conduct TSS 1st especially at NE site, Q01477 to determine whether the existing power source / outlet can power up the newly proposed IDU or not | [7 empty] | Trintel | SQ202403220491-Trintel |  |  | 2024-04-05 | 2024-04-03 | Completed | 2024-03-07 | 2024-03-08 | 2024-03-07 | 2024-03-08 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-04-03 | 2024-04-05 | 2024-04-03 | 2024-04-03 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-03 | 2024-04-05 | 2024-04-03 | 2024-04-03 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-03 | 2024-04-05 | 2024-04-03 | 2024-04-03 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1253A | Plaza Pengkalen | DU00003470926 | Central | Kuala Lumpur | 3.182377 | 101.682287 | WK17 | APR 24 |  | MAR 24 | Cancel / Drop | Pending TX OPS update EPMS. DONE in 3552A NIC | ZTE | 00. Site Out/Drop | DONE in 3552A NIC (Datasco) |  |  | 1) 2xsuitable Fiber 10G SFP SM 1550 40km Module. 2) 2xsuitable Fiber Patch Cord cable required. 3) 1Xsuitable Electrical SFP Module. 4) 4XCAT6 Cable | Cancel / Drop | 10G IPRAN port upgrade at 1253A(PFS) and at 3552A(Existing RTN910A-RTN01). NE Site(3552A) at RTN910A-RTN01(NE ID : 42300): 1) Insert new Fiber SFP module 10G SFP SM 1550 40km at port 8-EM6-3(Port 3) RTN01. 2)Lay new suitable Fiber patch cord cable from ODF to new 10G port 8-EM6-3(Port 3) RTN01. FE Site(1412A) at 1253A-PFS1: 1) Insert new Fiber SFP module 10G SFP SM 1550 40km at xgei_11/1(10G Port). 2) Lay new suitable Fiber patch cord cable to xgei_11/1(10G Port) from ODF. Other Info: 1) New vlan services required for all sites(3552A, 2425A, 1378C, 3618C, 1716C, 1296A, 3986B, 1330C, 3110B, 3225C, 1386H & 1726H. 2) New vlan DCN required for RTN910A(RTN01) NE ID 42300. | [7 empty] | Perwira | No PR required-Site drop/cancel | Perwira | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24022721 |  | 2024-02-28 | 2024-03-06 | Completed | 2024-02-27 | 2024-02-28 | 2024-02-27 | 2024-03-06 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed
4640A | SP Plaza | DU00003470927 | Northern | Kedah | 5.645572 | 100.488428 |  |  |  |  | Planning | Pending BOQ Solution | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1230A | Tmn Perindustrian Sg Buloh | DU00003470928 | Central | Selangor | 3.168240 | 101.570650 |  |  | WK22 | JUN 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 10/7: D1: Cutover done. Task update done in TX Rollout 4/7: FE site key missing (room reno). FF not available | TSS+TI | L1+ATP+PAC | 2x new suitable Fiber 1G SFP SM 1550 40km Module 2x Fiber Patch Cord cable | IDU-IPRAN | 1G IPRAN port upgrade at IBeam 1230A and RTN04 at 1364A. FE (1230A) at IBeam: 1) Insert new Fiber SFP module 1G SF at new 1G port GE (GE0/2/0). 2) Re-patching existing Fiber patch cord cable to new 1G port (GE0/2/0). NE (1364A) at Huawei IDU 950A RTN04: 1) Insert new Fiber SFP module 1G SFP SM 1550 40km at 8-EM6-3(Port 3). 2) Re-patching existing Fiber patch cord cable to 8-EM6-3(Port 3). Impact sites:1198H,1229B,1364A,2586B,2587B | [7 empty] | Allstar | SQ202409110347-Allstar | Allstar | SQ202408080487-Allstar | 2024-08-23 | 2024-08-22 | Completed | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-02 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-01 | 2024-07-31 | 2024-07-02 | 2024-07-02 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-07-16 | 2024-07-17 | 2024-07-16 | 2024-07-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24060493 |  | 2024-06-05 | 2024-06-12 | Completed | 2024-06-04 | 2024-06-05 | 2024-06-04 | 2024-06-12 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-07-12 | 2024-07-31 | 2024-07-12 | 2024-11-19 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | Allstar TI | 2024-07-12 | 2024-07-31 | 2024-07-12 | 2024-09-23 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | Allstar TI | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2024-07-12 | 2024-07-31 | 2024-07-12 | 2024-10-01 | KHAIRUL//ASYRAF BIN AHMAD/6798000205 | 2025-11-25: 2024-07-12; 2025-11-25: 2024-07-31; 2025-11-25: 2024-07-12; 2025-11-28: 2024-07-19 |  |  | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358
1157A | Sg. Nibong | DU00003470929 | Central | Selangor | 3.606306 | 101.063480 |  |  |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP |  |  | 2x 1xnew suitable Fiber 10G SFP SM 1550 40km Module 2x Fiber Patch Cord cable | Cancel / Drop | 10G IPRAN port upgrade at IBeam 1157A and RTN03 at 1157A. FE (1157A) at IBeam: 1) Insert new Fiber SFP module 10G SF at new 10G port GE (to be advised). 2) Re-patching existing Fiber patch cord cable to new 10G port (to be advised). NE (1157A) at Huawei IDU 910A RTN03: 1) Insert new Fiber SFP module 10G SFP SM 1550 40km at 8-EM6-3(Port 3). 2) Re-patching existing Fiber patch cord cable to 8-EM6-3(Port 3). Impact sites: 1119K,3439B_15,3639B_2,1163A,1771C,2637A,1165A | [7 empty] | MTK | No PR required-Site drop/cancel | MTK | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9384B | Sibu Jaya MP | DU00003470930 | Sarawak | Sarawak | 2.239014 | 111.976634 | WK13 | MAR 24 |  |  |  | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | 10/6: Link Drop. SOW done by MSP | TSS+TI |  | At NE(4678A) 1) Request 1xElectrical 1G SFP. 2) 1xCAT6 cable with suitable length(if really required) | IDU-IPRAN | New 1G IPRAN Electrical port at IBeam 9384B for RTN01(Existing RTN910A). This will carry traffic 9063C. NE (9384B) at RTN01(Existing RTN910A): 1) Remove current cascading between RTN01 8-EG6-1 and RTN03 8-EM6-1 at 9384B. 2) Insert new Electrical SFP module 1G to existing RTN01 8-EG6-1. 3) Lay and patching 1xCAT6 cable from existing RTN01 8-EG6-1 to IBeam port GE0/2/30. NE (9384B) at IBeam: 1) Insert new Electrical SFP module 1G to IBeam port GE0/2/30. 2) Lay and patching 1xCAT6 cable from IBeam port GE0/2/30 to existing RTN01 8-EG6-1. Other Info: 1) New vlan services required for site 4261B. 2) New IP and vlan DCN required for RTN01(Existing RTN910A) at 9384B. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24100735 |  | 2024-10-08 | 2024-10-09 | Completed | 2024-10-07 | 2024-10-08 | 2024-10-07 | 2024-10-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-14 | 2024-10-31 |  |  | Aaron//anak Meta/7019000019 | Datasco TI | 2024-03-25 | 2024-03-27
1236A | Labu Lanjut | DU00003470931 | Central | Selangor | 2.793320 | 101.711164 | WK13 | MAR 24 | WK13 | MAR 24 | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 29/3: D1: Cutover done | TSS+TI | L1+ATP+PAC | At NE(3213B) 1) Request 1xRTN910AF. 2) Request 1xISM8. At FE(1236A) 1) Request 1xRTN910AF. 2) Request 1xISM8. 3) Request 1xElectrical 1G SFP. 4) 3xCAT6 cable with suitable length(if really required) | IDU-IPRAN | New 1G IPRAN port at IBeam 1236A for RTN12(New RTN910AF) and 3213B RTN01(NEW RTN910AF). From existing 18GHz 4+0 56MHz EPLA, shifting IF Cable from card ISV3 slot 3/5 at 3213B(RTN03) and ISV3 slot 3/4 at 1236A(RTN05) to slot 7 at 3213B(RTN01) and 1236A(RTN12). Become 2 link 2+0 with capacity at least (406+406) Mbps=812Mbps. This New MW Link will carry traffic 3213B, 1488A & NLOS 1655H. NE (3213B) at RTN01(NEW RTN910AF): 1) Install new RTN910AF(RTN01). 2) Shift IF Cable from card ISV3 slot 3/5 at 3213B(RTN03) to slot 7 at 3213B(RTN01) become 2+0 56MHz EPLA. 3) Recascading BBU 3213B from existing RTN950(RTN03) slot 17-EG6-2 to new RTN910AF(RTN01) slot 8-EM6-1. 4) Recascading NLOS IDU 1655H from existing RTN950(RTN03) slot 17-EG6-3 to new RTN910AF(RTN01) slot 8-EM6-2. 5) Also, child site 1488A need to shifting IF cable from ISM8 slot 7 Port 1 of existing RTN910AF(RTN04) to "new" ISM8 slot 3 Port 1 of new RTN910AF(RTN01). FE (1236A) at RTN12(New RTN910AF): 1) Install new RTN910AF(RTN12). 2) Shift IF Cable from card ISV3 slot 3/4 at 1236A(RTN05) to slot 7 at 1236A(RTN12) become 2+0 56MHz EPLA. 3) Lay and patching 1xCAT6 cable from new RTN12 8-EM6-5(Combo 1G Electrical) to new 1G Electrical IBeam port. NE (1236A) at IBeam: 1) Request new 1G Electrical port at IBeam. IPRAN Nazril need to advise on new 1G IBeam Electrical port. 2) Insert new Electrical SFP module 1G. 3) Lay and patching 1xCAT6 cable from new 1G Electrical IBeam port to new RTN12 8-EM6-5(Combo 1G Electrical). Other Info: 1) New vlan services required for sites 3213B, 1488A & NLOS 1655H. 2) New IP & vlan DCN required for RTN12(RTN910AF) at 1236A. | [7 empty] | Perwira | SQ202407050123-Perwira | Perwira | SQ202407050175-Perwira | 2024-09-20 | 2024-09-19 | Completed | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | WB80041943 |  | PERWIRA ENERGY SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | WB80041943 |  | PERWIRA ENERGY SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-08-14 | 2024-08-15 | 2024-08-14 | 2024-08-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24030721 |  | 2024-03-08 | 2024-03-18 | Completed | 2024-03-07 | 2024-03-08 | 2024-03-07 | 2024-03-18 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-03-29 | 2024-03-31 | 2024-03-29 | 2024-04-04 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-29 | 2024-03-31 | 2024-03-29 | 2024-04-30 | RIO//RINALDI BIN YUNDARI/7238000002 | Perwira TI | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-05-08 | MOHAMAD//NAZRIL HISYAM BIN RUSLI/6237001080 |  |  | 2024-03-29 | 2024-03-31 | 2024-03-29 | 2024-05-09 | RIO//RINALDI BIN YUNDARI/7238000002 | 2025-11-25: 2024-03-29; 2025-11-25: 2024-03-31; 2025-11-25: 2024-03-29; 2025-11-28: 2024-03-29 |  |  | 2024-06-19 | 2024-07-19 | 2024-06-19 | 2024-06-20 | ASTI//GANIS PUTRIANI/6237001358
1412A | Bkt Tadun | DU00003470932 | Central | Selangor | 3.254563 | 101.546984 | WK13 | MAR 24 |  |  | Cancel / Drop | Drop. Pass to MSP | ZTE | 00. Site Out/Drop | Drop. Pass to MSP | TSS |  | At CP(1412A) 1) 2xsuitable Fiber 10G SFP SM 1550 40km Module. 2) 2xsuitable Fiber Patch Cord cable required. | Cancel / Drop | 10G IPRAN port upgrade at IBeam 1412A for RTN03(Existing RTN910A). NE (1412A-MAC-001) at IBeam: 1) Insert new Fiber SFP module 10G SFP SM 1550 40km at port GE0/2/13. 2)Lay new suitable Fiber patch cord cable to new 10G port GE0/2/13. NE (1412A) at Huawei RTN 910A(RTN03): 1) Insert new Fiber SFP module 10G SFP SM 1550 40km at 8-EM6-3(Port 3). 2) Lay new suitable Fiber patch cord cable to 8-EM6-3(Port 3) from ODF. Other Info: 1) New vlan services required for all sites(2476B, 3256A, 3403C & 3688C). 2) New IP and vlan DCN required for RTN01(RTN910A). | [7 empty] | Perwira | No PR required-Site drop/cancel | Perwira | No PR required-Site drop/cancel |  |  | Ongoing | 2024-04-03 | 2024-04-03 | 2024-04-04 |  | Muhammad//Norfikri Bin Ramlee/7238000003 |  | PERWIRA ENERGY SDN. BHD. | 1.00 | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | No SFP 10G and patch cord E2K 15m |  |  | Not started | [8 empty] | Unassigned | Not started
1049B | MSC Damansara (Kepong MSC) | DU00003470933 | Central | Selangor | 3.203840 | 101.604090 |  | MAY 24 | WK13 |  | Cancel / Drop | SOW change Drop | ZTE | 00. Site Out/Drop | 21/3: 10G SFP issue |  |  |  | Cancel / Drop | Port Upgrade by 10G. New port GE0/3/1 | [7 empty] | Perwira | No PR required-Site drop/cancel | Perwira | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9281B-9239B | Rantau Panjang Sibu | DU00003501511 | Sarawak | Sarawak | 2.355177 | 111.869477 | WK16 | MAR 24 | WK19 | MAY 24 | RFS |  | ZTE | 00. Integrated/RFS Done | 7/5: D2: Cutover done 6/5: D1: TI WIP. Continue 7/5 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18GHz 0.6m/1.2m_1+0_110MHz | MW Swap | MW Swap Huawei 18G 1+0 0.6m&0.6m 56MHz to 18G 1+0 0.6M&1.2m 110MHz NE: 1. Reuse existing RTN910A . 2.Remain existing ODU. 3. Remain Antenna HW 0.6m. 4. Configure link as 18GHz 1+0 110MHz FE: 1. Reuse existing RTN910A and ISM8. 2. Remain existing ODU. 3. Swap Existing Huawei Antenna with New Huawei 18GHz 1.2m SP Antenna. 4. Configure link as 18GHz 1+0 110MHz. | [7 empty] | Trintel | SQ202403220491-Trintel | Datasco | SQ202407020298-Datasco | 2024-03-29 | 2024-03-25 | Completed | 2024-03-07 | 2024-03-08 | 2024-03-07 | 2024-03-08 | ADELINA//JACY INJAN ANAK JACKSON/7667000012 |  | TRINTEL (M) SDN. BHD. |  | Unassigned | Completed |  | 2024-03-25 | 2024-03-29 | 2024-03-25 | 2024-03-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-25 | 2024-03-29 | 2024-03-25 | 2024-03-25 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-03-25 | 2024-03-29 | 2024-03-25 | 2024-03-25 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY240424A8 |  | 2024-04-25 | 2024-05-02 | Completed | 2024-04-24 | 2024-04-25 | 2024-04-24 | 2024-05-02 | YEK/PIK/NGUK/6871000002 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-05-03 | 2024-05-08 | 2024-05-29 | 2024-05-29 | Chiew Hua Kai7019000037 | Datasco TI | 2024-05-03 | 2024-05-08 | 2024-05-06 | 2024-05-07 | Chiew Hua Kai7019000037 | Datasco TI | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-05-03 | 2024-05-08 | 2024-05-07 | 2024-05-07 | Chiew Hua Kai7019000037 | 2024-05-03 | 2024-05-08 | 2024-05-06 | 2024-05-06 | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | CHONG QIEW LEK7018000038 | Warehouse Team | 2024-12-13 | 2025-01-13 | 2024-12-13 | 2024-12-13 | ASTI//GANIS PUTRIANI/6237001358
9370B-9363A | Sekuau Sibu | DU00003501512 | Sarawak | Sarawak | 2.349192 | 112.131684 |  |  |  |  | RFS | Frequency Issue | ZTE | 00. Site Out/Drop | 6/5: BoQ ready, Pending BoM 30/4: Req assign subcon for TSS & TI | TSS |  | 13GHz 1.8m/1.8m_MDD_2+0 | MW Parallel Link | Cancel/Drop. Traffic 9036R diverted to xC under DU 9036R_PostMOCN MW Parallel Link 13GHz 1.8m/1.8m_MDD_2+0 NE: 1. Reuse existing IDU and add new 1xISM8 at slot 3. 2. Install new ODU XMC_5D 13G. 3. Install new Antenna 1.8m MDD. 4. Configure 13G_2+0_28Mhz_400M. FE: 1. Reuse existing IDU and add new 1xISM8 at slot 3. 2. Install new ODU XMC_5D 13G. 3. Install new Antenna 1.8m MDD. 4. Configure 13G_2+0_28Mhz_400M. | [7 empty] | Trintel | SQ202409180629-Trintel | ZTE | No PR required-Site drop/cancel | 2024-09-11 | 2024-09-11 | Completed | 2024-05-13 | 2024-09-11 | 2024-05-13 | 2024-09-11 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-05-13 | 2024-05-17 | 2024-05-13 | 2024-05-13 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-06-24 | 2024-06-28 | 2024-06-24 | 2024-06-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-06-24 | 2024-06-28 | 2024-06-24 | 2024-06-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9103C-9239B | Jalan Bahagia Selatan | DU00003501513 | Sarawak | Sarawak | 2.357098 | 111.854974 |  |  | WK11 | MAR 24 | PAC | PAC WIP | ZTE | 00. Integrated/RFS Done | Cutover done | AA | PAC |  | MW Remote Upgrade | REMOTE UPGRADE FOR MW 9103C-9239B: CHANGE FROM HUAWEI_23G_1+0_56MHZ TO 1+0_112MHZ | [7 empty] | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | C.PRATHABAN///6798000081 | [17 empty] | 2024-09-26 | 2024-10-26 | 2024-09-26 | 2024-09-26 | ASTI//GANIS PUTRIANI/6237001358
2157A-3007A | PVKL (REL) | DU00004199068 | Central | Kuala Lumpur | 3.148390 | 101.715640 |  |  |  |  | Cancel / Drop | Site Using Fiber | ZTE | 00. Site Out/Drop | 23/10: BAU sites using Fiber. Proceed DR materials | TSS |  | 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_XMC3_SUB A_889MBPS | MW New Link / Reroute | MW NEW LINK 2157A-3007A 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_XMC3_SUB A_889MBPS_DISTANCE 0.19KM TX ROUTE: 2157A-3007A-2175A-LL-2021B NE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 112MHZ SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM FE: 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW 23G XMC-3 112MHZ SUB BAND A 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. CASCADE TO RTN01 3007A | [7 empty] | GTSB | SQ202511180084-GTSB | Datasco | No PR required-Work at TSS only | 2024-09-28 | 2024-10-01 | Completed | [8 empty] | Unassigned | Disabled |  | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2024-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2024-09-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-27 | 2024-09-28 | 2024-09-27 | 2024-10-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24101059 |  | 2024-10-11 |  | Ongoing | 2024-10-10 | 2024-10-11 | 2024-10-10 |  | jac | Warehouse Team |  |  | Assigned | Ongoing | [40 empty] | GCI_AA | SQ202510300160-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00509-Q00268_1 | Q132A_Q00509OD_CB_MYYBTUTRUNK | DU00004199069 | Sarawak | Sarawak | 3.497110 | 113.580110 | [6 empty] | ZTE | 00. Integrated/RFS Done | 24/10: Cutover done | TSS+TI | L1+ATP+PAC | FE: 1) 2 x SFP 1G 10km 2) 1 pair patch cord | MW IDU Patching | Congestion at IDU 9149R/Q00268-TT844-RTN01 GE4 to PTN 30157-TT844 To divert site Q01815 to other IDU/CP port. Impact site: Q01815 NE (Q00509/9073K): 1) Remain existing FE (Q00268/9149R): 1) At IDU 9073K/Q00509-MYYBTUTRUNK-RTN01, patch GE6 (optical) to new PTN port (ops team to assign new port) 2) Divert Q01815 to new port | [7 empty] | Trintel | SQ202410280528-Trintel | Trintel | SQ202410280612-Trintel | 2024-10-31 | 2024-10-25 | Completed | 2024-10-23 | 2024-10-24 | 2024-10-23 | 2024-10-23 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-24 | 2024-10-25 | 2024-10-24 | 2024-10-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-24 | 2024-10-25 | 2024-10-24 | 2024-10-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-25 | 2024-10-31 | 2024-10-25 | 2024-10-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24102148 |  | 2024-10-22 | 2024-10-22 | Completed | 2024-10-21 | 2024-10-22 | 2024-10-21 | 2024-10-22 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-23 | 2024-10-25 | 2024-10-23 | 2024-10-30 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2024-10-23 | 2024-10-25 | 2024-10-23 | 2024-10-23 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-10-23 | RONALD SHAN A/L AMBUROSE6800000089 |  |  | 2024-10-23 | 2024-10-25 | 2024-10-23 | 2024-10-23 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | 2025-11-25: 2024-10-23; 2025-11-25: 2024-10-25; 2025-11-25: 2024-10-23; 2025-11-28: 2024-10-23 |  |  | 2024-11-28 | 2024-12-28 | 2024-11-28 | 2024-11-28 | ASTI//GANIS PUTRIANI/6237001358
Q00672_IPR | Q141A_Q00672OD_CB_PKNSIMUNJAN | DU00006535520 | Sarawak | Sarawak | 1.383822 | 110.760558 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2x PATCH CORD | MW IDU Patching | Split traffic at IDU Huawei Q00672-PKN SIMUNJAN-RTN01 to PTN 30077-PKNSIMUNJAN Patch IDU Q00672 RTN01 GE2 to PTN 30077-PKNSIMUNJAN new port and transfer site Q01022 to new PTN port Impact site: 1) Q01022 T3_KGSEMALATONG | Split traffic at IDU Huawei Q00672-PKN SIMUNJAN-RTN01 to PTN 30077-PKNSIMUNJAN Patch IDU Q00672 RTN01 GE2 to PTN 30077-PKNSIMUNJAN new port and transfer site Q01022 to new PTN port Impact site: 1) Q01022 T3_KGSEMALATONG | [6 empty] | Trintel | SQ202603040038-Trintel | Trintel | SQ202602130323-Trintel |  |  | Ongoing | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started |  | 2026-02-27 | 2026-02-28 | 2026-02-27 | 2026-02-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26020920 |  | 2026-02-10 | 2026-02-09 | Completed | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Chin Sun Lun7667000040 | Trintel TI | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-03-04 | Chin Sun Lun7667000040 | Trintel TI | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-02 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-03-02 | Chin Sun Lun7667000040 | 2025-11-25: 2026-02-10; 2025-11-25: 2026-02-10; 2025-11-25: 2026-02-10; 2025-11-28: 2026-02-12 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202601210786-GCI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
K00623_HU | K009A_K00623OD_MN_KGMACHANG | DU00006538516 | Northern | Kedah | 6.115403 | 100.663394 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M_1028QAM_CA NE_K00623 New 13G_1.2M(MDD) x1. New RTN910AF(RTN01). New ISM8 x1. New XMC_5, Sub B_Hi x1. New CAT6 cable x1. FE_4979B New 13G_1.2M(MDD) x1. New RTN910AF(RTN05) x1. New ISM8 x1. New XMC_5, Sub B_Lo x1. New CAT6 cable x1. | MW New Link / Reroute | Existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Reroute to new HW MW Link K00623-4749B, 13G_4+0_28MHZ_1024QAM_CA. Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Site Impacted : K00623. NE_K00623 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01). 4.Install new XMC_5, Sub B_Hi x2. Configure it. 5.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 6.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 7.Migrate traffic K00623 via new HW MW Link K00623-4749B, 13G_4+0_28MHZ_1024QAM_CA. 8.Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. FE_4979B 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN05) and insert new ISM8 x1 into slot 03 of new RTN910AF(RTN05). 3.Install new XMC_5, Sub B_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN05). 5.Enable port 8-EM6-2 of new RTN910AF(RTN03, NEID 9-36240). 6.Perform cascading in between port 8-EM6-1 of new RTN910AF(RTN05) and port 8-EM6-2 of new RTN910AF(RTN03, NEID 9-36240). 7.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 8.Migrate traffics K00623 at IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). Seem no other traffic backhaul to IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). K00781 traffic also plan to divert into same port at IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). 9.Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. | Existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Reroute to new HW MW Link K00623-4749B, 13G_4+0_28MHZ_1024QAM_CA. Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Site Impacted : K00623. NE_K00623 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Insert new ISM8 x1 into slot 03 of new RTN910AF(RTN01). 4.Install new XMC_5, Sub B_Hi x2. Configure it. 5.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU. 6.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 7.Migrate traffic K00623 via new HW MW Link K00623-4749B, 13G_4+0_28MHZ_1024QAM_CA. 8.Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. | Existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Reroute to new HW MW Link K00623-4749B, 13G_4+0_28MHZ_1024QAM_CA. Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. Site Impacted : K00623. FE_4979B 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN05) and insert new ISM8 x1 into slot 03 of new RTN910AF(RTN05). 3.Install new XMC_5, Sub B_Lo x2. Configure it. 4.Enable port 8-EM6-1 of new RTN910AF(RTN05). 5.Enable port 8-EM6-2 of new RTN910AF(RTN03, NEID 9-36240). 6.Perform cascading in between port 8-EM6-1 of new RTN910AF(RTN05) and port 8-EM6-2 of new RTN910AF(RTN03, NEID 9-36240). 7.Request new xD Vlan DCN and Vlan services from ZTE IPRAN Team. 8.Migrate traffics K00623 at IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). Seem no other traffic backhaul to IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). K00781 traffic also plan to divert into same port at IBeam(CP 4999A RTN910AF-RTN08 NEID 9-36243). 9.Later, decom existing SM MW Link_ID NT05626, K00623-K00206, 18G_1+0_55MHZ_2048QAM. | XMC_5D | MDD | 13G | 13G_1.2M(MDD) x1. | 13G_1.2M(MDD) x1. | GTSB | SQ202601210163-GTSB | GTSB | SQ202601210154-GTSB // SQ202601210159-GTSB | 2026-03-20 | 2026-03-17 | Completed | 2026-01-16 | 2026-01-31 | 2026-01-16 | 2026-01-22 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Completed |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-06 | 2026-03-13 | 2026-03-06 | 2026-03-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-20 | 2026-03-13 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Material DM from 4979B_HU |  |  | Disabled | [8 empty] | Unassigned | Disabled |  | 2026-01-16 | 2026-01-31 | 2026-01-16 | 2026-01-22 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2026-01-16 | 2026-01-31 | 2026-01-16 | 2026-01-22 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | GTSB TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-22 | 2026-01-16 | 2026-01-31 | 2026-01-16 | 2026-02-06 | MUHAMMAD SYAIRUL HIJJAZ//BIN MOHD AZHAR/6000049458 | 2025-11-25: 2026-01-16; 2025-11-25: 2026-01-31; 2025-11-25: 2026-01-16; 2025-11-28: 2026-01-17 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202602260616-GTSB
1446A_LOS | Southasiaeng | DU00006574258 | Central | Selangor | 3.158950 | 101.751200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M. NE_1446A. 23G_SP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A_Lo x1. FE_1733A. 23G_SP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A_Hi x1. | MW New Link / Reroute | Link reroute to new FE 1733A due to existing link LOS Block. Install new link 23G_1+0_112M. Site Impacted : 1446A. NE_1446A. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic migrate to new MW link and new FE routing. 6.Decom existing MW link. FE_1733A. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Enable GE1 , ETH patching to existing 1733A_RTN02_GE1 6.Traffic migrate to new MW link and new FE routing. 7.Decom existing MW link. | Link reroute to new FE 1733A due to existing link LOS Block. Install new link 23G_1+0_112M. Site Impacted : 1446A. NE_1446A. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic migrate to new MW link and new FE routing. 6.Decom existing MW link. | Link reroute to new FE 1733A due to existing link LOS Block. Install new link 23G_1+0_112M. Site Impacted : 1446A. FE_1733A. 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Enable GE1 , ETH patching to existing 1733A_RTN02_GE1 6.Traffic migrate to new MW link and new FE routing. 7.Decom existing MW link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202601300950-GTSB | GTSB | SQ202602100617-GTSB // SQ202602100636-GTSB |  |  | Ongoing | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-05 | 2026-03-19 | 2026-03-05 | 2026-03-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26020511 |  | 2026-02-06 | 2026-02-07 | Completed | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-12 | 2026-02-28 | 2026-02-12 | 2026-02-13 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2026-02-12 | 2026-02-28 | 2026-02-12 | 2026-02-24 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2026-02-14 | 2026-02-14 | 2026-02-14 | 2026-02-14 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-14 | 2026-02-12 | 2026-02-28 | 2026-02-12 | 2026-02-26 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2026-02-12 | 2026-02-28 | 2026-02-12 | 2026-02-13 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602120113-GCI | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | CHEONG/SENG/WAH/7018000306
1710B_IPR | Seksyen27_89 | DU00006574259 | Central | Selangor | 3.010270 | 101.557370 | [9 empty] | TSS+TI |  | 4x1G SFP 10KM 2X PATCHCORD | MW IDU Patching | IDU Fiber 1710B-FIBER-1349A port upgrade to 10G Impact sites: 1710B, 1566C, B02725, 1184D Require 1G SFP and patch cord (2G LAG PORT). Current 1G SFP is IDU 10km NE (1710B RTN01): 1) Install 1G SFP 2PCS (2G LAG) at 1710B RTN01 2) Upgrade IDU Fiber 1710B-FIBER-1349A to 2G LAG PORT 3) Remove existing 1G connection FE (1349A): 1) Install 1G SFP 2PCS (2G LAG) at 1349A-MAC-001 JBA Ebor (ops team to assign port) 2) Upgrade IDU Fiber 1710B-FIBER-1349A to 2G LAG PORT 3) Remove existing 1G connection | NE (1710B RTN01): 1) Install 1G SFP 2PCS (2G LAG) at 1710B RTN01 2) Upgrade IDU Fiber 1710B-FIBER-1349A to 2G LAG PORT 3) Remove existing 1G connection | FE (1349A): 1) Install 1G SFP 2PCS (2G LAG) at 1349A-MAC-001 JBA Ebor (ops team to assign port) 2) Upgrade IDU Fiber 1710B-FIBER-1349A to 2G LAG PORT 3) Remove existing 1G connection | [5 empty] | GTSB | SQ202601300950-GTSB | GTSB | SQ202601300942-GTSB | 2026-03-13 | 2026-03-12 | Completed | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-03-11 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26013021 |  | 2026-01-31 | 2026-02-07 | Completed | 2026-01-30 | 2026-01-31 | 2026-01-30 | 2026-02-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-02-19 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-02-19 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | [7 empty] | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-02-19 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-11-25: 2026-02-10; 2025-11-25: 2026-02-28; 2025-11-25: 2026-02-10; 2025-11-28: 2026-02-11 | [7 empty] | GCI | SQ202602120113-GCI | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
4565D_HU_1 | Kg Changkat Larah | DU00006574260 | Northern | Perak | 4.935150 | 100.724000 | [7 empty] | 05. Doable |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | XMC_3E ODU NE_4565D. XMC_3E , Sub B_Hi x1 . FE_4424A. XMC_3E , Sub B_Lo x1 | MW Hardware Upgrade | Existing link 18G_1+0_56M. Hardware upgrade to XMC_3E ODU with config 18G_1+0_112M. Old ODU is XMC_3 (Low Power Not Meeting KPI). Site Impacted : 4565D. NE_4565D. 1.Swap XMC_3 to XMC_3E , Sub B_Hi. 2.Configure 18G_1+0_112M with 512QAM. 3.If RSL not meeting , realignment is required. 4.Decomm Existing XMC_3 ODU only. FE_4424A. 1.Swap XMC_3 to XMC_3E , Sub B_Lo.. 2.Configure 18G_1+0_112M with 512QAM. 3.If RSL not meeting , realignment is required. 4.Decomm existing XMC_3 ODU only. | Existing link 18G_1+0_56M. Hardware upgrade to XMC_3E ODU with config 18G_1+0_112M. Old ODU is XMC_3 (Low Power Not Meeting KPI). Site Impacted : 4565D. NE_4565D. 1.Swap XMC_3 to XMC_3E , Sub B_Hi.. 2.Configure 18G_1+0_112M with 512QAM. 3.If RSL not meeting , realignment is required. 4.Decomm Existing XMC_3 ODU only. | Existing link 18G_1+0_56M. Hardware upgrade to XMC_3E ODU with config 18G_1+0_112M. Old ODU is XMC_3 (Low Power Not Meeting KPI). Site Impacted : 4565D. FE_4424A. 1.Swap XMC_3 to XMC_3E , Sub B_Lo. 2.Configure 18G_1+0_112M with 512QAM. 3.If RSL not meeting , realignment is required. 4.Decomm existing XMC_3 ODU only. | XMC_3E | XMC | 18G | 0.6 | 0.6 | GTSB | SQ202603130704-GTSB | GTSB | SQ202603130700-GTSB // SQ202603130703-GTSB |  |  | Ongoing | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26031070 |  | 2026-03-11 | 2026-03-17 | Completed | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-07 | 2026-04-30 | 2026-04-07 | 2026-04-14 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-04-07 | 2026-04-30 | 2026-04-07 | 2026-04-14 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-07 | 2026-04-07 | 2026-04-30 | 2026-04-07 | 2026-04-14 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2025-11-25: 2026-04-07; 2025-11-25: 2026-04-30; 2025-11-25: 2026-04-07; 2025-11-28: 2026-04-07 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202603170124-GCI | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | CHEONG/SENG/WAH/7018000306
2640A_IPR | Sek16Industry Area | DU00006574261 | Central | Selangor | 3.055763 | 101.510340 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module x 2 Fiber patch cord x 2 pairs. | MW IDU Patching | IDU Fiber 2640A-FIBER-1342A port upgrade to 10G Impact sites: 2640A, 1793A, 1434B, 3982B Require 10G SFP and patch cord. Current 1G SFP is IDU 10km NE (2640A RTN01): 1) Install 10G SFP at 2640A RTN01 2) Upgrade IDU Fiber 2640A-FIBER-1342A to 10G 3) Remove existing 1G connection and disable unused port. FE (1342A): 1) Install 10G SFP at 1342A-MAC-002 MBSA (ops team to assign port. Recommend 0/2/2) 2) Upgrade IDU Fiber 2640A-FIBER-1342A to 10G 3) Remove existing 1G connection and disable unused port. | IDU Fiber 2640A-FIBER-1342A port upgrade to 10G Impact sites: 2640A, 1793A, 1434B, 3982B. Require 10G SFP and patch cord. Current 1G SFP is IDU 10km. NE (2640A RTN01): 1) Install 10G SFP at 2640A RTN01 2) Upgrade IDU Fiber 2640A-FIBER-1342A to 10G 3) Remove existing 1G connection and disable unused port. | IDU Fiber 2640A-FIBER-1342A port upgrade to 10G. Impact sites: 2640A, 1793A, 1434B, 3982B. Require 10G SFP and patch cord. Current 1G SFP is IDU 10km FE (1342A): 1) Install 10G SFP at 1342A-MAC-002 MBSA (ops team to assign port. Recommend 0/2/2) 2) Upgrade IDU Fiber 2640A-FIBER-1342A to 10G 3) Remove existing 1G connection and disable unused port. | [5 empty] | GTSB | SQ202601300950-GTSB | GTSB | SQ202601300942-GTSB | 2026-03-02 | 2026-02-25 | Completed | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-02-13 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-16 | 2026-03-02 | 2026-02-16 | 2026-02-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-19 | 2026-02-20 | 2026-02-19 | 2026-02-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26013020 |  | 2026-01-31 | 2026-02-07 | Completed | 2026-01-30 | 2026-01-31 | 2026-01-30 | 2026-02-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-02-13 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-02-13 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-11 | 2026-02-10 | 2026-02-28 | 2026-02-10 | 2026-02-12 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2025-11-25: 2026-02-10; 2025-11-25: 2026-02-28; 2025-11-25: 2026-02-10; 2025-11-28: 2026-02-11 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602120113-GCI | 2026-01-30 | 2026-02-06 | 2026-01-30 | 2026-01-30 | CHEONG/SENG/WAH/7018000306
9283A_IPR | BukitTiong-Core | DU00006574262 | Sarawak | Sarawak | 4.881264 | 115.395869 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_9283A New CAT6 cable with suitable length(IDU HW to IBeam) x1. | MW IDU Patching | Request new 2nd of IBeam port and perform 2x 1G LAG for boths port at IDU & IBeam. Site Impacted: 9289A, 9056C, 9649B & 9663B. NE_9283A 1.Enable port 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-20656). 2.Request new 2nd port 1G(electrical) of IBeam(9283A-MAC-001) from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-20656) and new 2nd port 1G(electrical) of IBeam. 4.Create and configure LAG between 2xport 1G(existing and new) of IDU-IBeam. 5.Traffics 9289A, 9056C, 9649B & 9663B will backhaul into 2x 1G LAG of IDU-IBeam. | Request new 2nd of IBeam port and perform 2x 1G LAG for boths port at IDU & IBeam. Site Impacted: 9289A, 9056C, 9649B & 9663B. NE_9283A 1.Enable port 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-20656). 2.Request new 2nd port 1G(electrical) of IBeam(9283A-MAC-001) from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN03, NEID 9-20656) and new 2nd port 1G(electrical) of IBeam. 4.Create and configure LAG between 2xport 1G(existing and new) of IDU-IBeam. 5.Traffics 9289A, 9056C, 9649B & 9663B will backhaul into 2x 1G LAG of IDU-IBeam. | [6 empty] | Redtone | SQ202603060647-Redtone | Redtone | SQ202603060646-Redtone |  |  | Ongoing | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Roy//Lee/6000056316 |  | REDTONE ENGINEERING & NETWORK SERVICES SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | Roy//Lee/6000056316 |  | REDTONE ENGINEERING & NETWORK SERVICES SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-07 | 2026-04-14 | 2026-04-07 | 2026-04-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | [5 empty] | Unassigned | Ongoing | To be Submitted |  | DOWMY26020924 |  | 2026-02-10 | 2026-03-11 | Completed | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-03-11 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-03-10 | 2026-03-05 | 2026-03-12 | JUDIH//LAJIUM/6000057179 | REDTONE TI | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Roy//Lee/6000056316 |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-02-24 | 2026-03-10 | 2026-03-16 | 2026-03-16 | JUDIH//LAJIUM/6000057179 | 2025-11-25: 2026-02-24; 2025-11-25: 2026-03-10; 2025-11-25: 2026-02-24; 2025-11-28: 2026-03-05 |  |  | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-24 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202602120283-GTSB
4772B_HU | Kilang Gula Cuping | DU00005172922 | Northern | Perlis | 6.543171 | 100.299361 |  |  |  |  | Integrated/RFS Done |  |  | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 13G_3+0_28M_256_CA&EPLA. MW Remote Upgrade from HW 13G_3+0_28M_256_CA&EPLA to HW 13G_4+0_28M_256_CA&EPLA. Site Impacted : 4772B. NE_4772B 1.Use existing equipment and remote configure from HW 13G_3+0_28M_256_CA&EPLA to HW 13G_4+0_28M_256_CA&EPLA. 2.4th channel will be 13115 and horizontal polarization. If having interferences, may try to swap with existing channel that belong to vertical polarization like channel 13031 or 13059. FE_4606B 1.Use existing equipment and remote configure from HW 13G_3+0_28M_256_CA&EPLA to HW 13G_4+0_28M_256_CA&EPLA. 2.4th channel will be 12849 and horizontal polarization. If having interferences, may try to swap with existing channel that belong to vertical polarization like channel 12765 or 12793. | Link Existing HW 13G_3+0_28M_256_CA&EPLA. MW Remote Upgrade from HW 13G_3+0_28M_256_CA&EPLA to HW 13G_4+0_28M_256_CA&EPLA. Site Impacted : 4772B. NE_4772B 1.Use existing equipment and remote configure from HW 13G_3+0_28M_256_CA&EPLA to HW 13G_4+0_28M_256_CA&EPLA. 2.4th channel will be 13115 and horizontal polarization. If having interferences, may try to swap with existing channel that belong to vertical polarization like channel 13031 or 13059. | Link Existing HW 13G_3+0_28M_256_CA&EPLA. MW Remote Upgrade from HW 13G_3+0_28M_256_CA&EPLA to HW 13G_4+0_28M_256_CA&EPLA. Site Impacted : 4772B. FE_4606B 1.Use existing equipment and remote configure from HW 13G_3+0_28M_256_CA&EPLA to HW 13G_4+0_28M_256_CA&EPLA. 2.4th channel will be 12849 and horizontal polarization. If having interferences, may try to swap with existing channel that belong to vertical polarization like channel 12765 or 12793. |  |  | 13G |  |  | ZTE | No PR required-Remote Upgrade | ZTE | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 | [17 empty] | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB | 2026-01-17 | 2026-01-17 | 2026-01-17 | 2026-01-17 | AB.RAHMAN//BIN MAT NOOH/6237001519
4462B_HU | Grik Town (Maxis) | DU00005172923 | Northern | Perak | 5.426721 | 101.137358 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M NE_4462B 18G_DP_0.6M(MDD) x1. 1SM8 x1. XMC_5D , Sub A_Hi x1. FE_4794B 18G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Lo x1. | MW Parallel Link | Existing 18G_2+0_56M Install parallel link 18G_2+0_112M Site Impacted : 4462B , 4257H , 4796B NE_4462B 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4462B_RTN02. 3.Install new 3_ISM8-2+0 into existing 4462B_RTN02. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA new 2+0_112M and existing 2+0_56M. 6.No decom existing MW link. FE_4794B 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4794B_RTN02. 3.Install new 3_ISM8-2+0 into existing 4794B_RTN02. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA new 2+0_112M and existing 2+0_56M. 6.No decom existing MW link. | Existing 18G_2+0_56M Install parallel link 18G_2+0_112M Site Impacted : 4462B , 4257H , 4796B NE_4462B 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4462B_RTN02. 3.Install new 3_ISM8-2+0 into existing 4462B_RTN02. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA new 2+0_112M and existing 2+0_56M. 6.No decom existing MW link. | Existing 18G_2+0_56M Install parallel link 18G_2+0_112M Site Impacted : 4462B , 4257H , 4796B FE_4794B 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4794B_RTN02. 3.Install new 3_ISM8-2+0 into existing 4794B_RTN02. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA new 2+0_112M and existing 2+0_56M. 6.No decom existing MW link. | XMC_5D | MDD | 18G | 0.6 | 0.6 | GCI | SQ202504210266-GCI | GCI | SQ202504210115-GCI // SQ202504210118-GCI // SQ202505150106-GCI | 2025-08-09 | 2025-08-12 | Completed | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-08 | 2025-08-09 | 2025-08-08 | 2025-08-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032031 |  | 2025-03-21 | 2025-03-21 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-08 | 2025-04-30 | 2025-04-08 | 2025-04-15 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | GCI TI | 2025-04-08 | 2025-04-30 | 2025-04-08 | 2025-04-20 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | GCI TI | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-11 | 2025-04-08 | 2025-04-30 | 2025-04-08 | 2025-05-02 | AHNAF HASAN/BIN/MOHAMAD KHADRI/7539000050 | 2025-11-25: 2025-04-08; 2025-11-25: 2025-04-30; 2025-11-25: 2025-04-08; 2025-11-28: 2025-04-09 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | CHEONG/SENG/WAH/7018000306
4694A_HU | Bedong | DU00005172924 | Northern | Kedah | 5.737780 | 100.511090 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | 4694A_PostMOCN (DU00004561153). Need to drop for upgrade in Mini Project due to Cheong already release solution 23G_2+0_112MHZ. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4955B_HU | Tawar | DU00005172925 | Northern | Kedah | 5.599221 | 100.770421 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M_256QAM CA&EPLA NE_4955B 15G_1.2M(MDD) x1. RTN910A x1. ISM8 x1 XMC_5D, Sub B_Lo x1. FE_4956B 15G_1.2M(MDD) x1. RTN910A x1. ISM8 x1 XMC_5D, Sub B_Hi x1. | MW Parallel Link | Adding new MW parallel Link HW 15G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4955B. NE_4955B 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN03). Configure it. 3.Insert 1xISM8 into slot 03. Configure it. 4.Install new 1x XMC_5D, Sub B_Lo. 5.Configure CA & EPLA and become 15G_4+0_28MHz_256Q_CA&EPLA. 6.Configure DCN Inband. 7.Migrate traffic to new link in which BBU 4955B will patching to port 8-EM6-1 of RTN910A(RTN03). Configure it. 8.Do not decom existing HW MW Link 4955B(RTN01)-4956B(RTN01) in order for backhauling traffic child site 4533D ONLY. FE_4956B 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN03). Configure it. 3.Insert 1xISM8 into slot 03. Configure it. 4.Install new 1x XMC_5D, Sub B_Hi. 5.Configure CA & EPLA and become 15G_4+0_28MHz_256Q_CA&EPLA. 6.Configure DCN Inband. 7.Request new port at IBeam from ZTE IPRAN team and patching to port 8-EM6-1 of RTN910A(RTN03). 8.Do not decom existing HW MW Link 4955B(RTN01)-4956B(RTN01) in order for backhauling traffic child site 4533D ONLY. | Adding new MW parallel Link HW 15G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4955B. NE_4955B 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN03). Configure it. 3.Insert 1xISM8 into slot 03. Configure it. 4.Install new 1x XMC_5D, Sub B_Lo. 5.Configure CA & EPLA and become 15G_4+0_28MHz_256Q_CA&EPLA. 6.Configure DCN Inband. 7.Migrate traffic to new link in which BBU 4955B will patching to port 8-EM6-1 of RTN910A(RTN03). Configure it. 8.Do not decom existing HW MW Link 4955B(RTN01)-4956B(RTN01) in order for backhauling traffic child site 4533D ONLY. | Adding new MW parallel Link HW 15G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4955B. FE_4956B 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN03). Configure it. 3.Insert 1xISM8 into slot 03. Configure it. 4.Install new 1x XMC_5D, Sub B_Hi. 5.Configure CA & EPLA and become 15G_4+0_28MHz_256Q_CA&EPLA. 6.Configure DCN Inband. 7.Request new port at IBeam from ZTE IPRAN team and patching to port 8-EM6-1 of RTN910A(RTN03). 8.Do not decom existing HW MW Link 4955B(RTN01)-4956B(RTN01) in order for backhauling traffic child site 4533D ONLY. | XMC_5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | CCSMY | SQ202504210258-CCS | CCSMY | SQ202504210107-CCS // SQ202504210102-CCS // SQ202504260175-CCS | 2025-12-17 | 2025-12-16 | Completed | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032020 |  | 2025-03-21 | 2025-03-22 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-08 | 2025-04-30 | 2025-04-08 | 2025-04-14 | IMRAN//JAVED/7021000061 | CCS TI | 2025-04-08 | 2025-04-30 | 2025-04-08 | 2025-04-14 | IMRAN//JAVED/7021000061 | CCS TI | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-11 | 2025-04-08 | 2025-04-30 | 2025-04-08 | 2025-05-04 | IMRAN//JAVED/7021000061 | 2025-11-25: 2025-04-08; 2025-11-25: 2025-04-30; 2025-11-25: 2025-04-08; 2025-11-28: 2025-05-06 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | EZRIN TASNIM BIN ABDUL GANI6798000128
4638B_HU | Dusun Pengapit | DU00005172926 | Northern | Kedah | 5.896050 | 100.669180 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1x New CAT6 cable with suitable length | MW IDU Patching | MW IDU Patching need to perform by diverting child site traffic 4119R(Non NIC) from existing HW MW Link 4119R(RTN01)-4638B(RTN04) to xC PTN K00260. K00260 is Pair Colo with 4638B. Traffic 4638B previously already diverted to K00260. Site Impacted : 4119R. NE_4638B/K00260 1.Disable port 8-EG6-1 of RTN910A(RTN03). 2.Remove cascading between RTN03(port 8-EG6-1) and RTN04(port 8-EM6-1). 3.Request new port of xC PTN K00260 from ZTE IPRAN team. 4.Patching new 1x CAT6 cable from RTN04(port 8-EM6-1) to new port of xC PTN K00260. 5.Configure DCN Inband for RTN04 and new xC VLAN services for migration traffic for 4119R thru xC Host. 6.Later, may decom existing HW MW link 4638B(RTN03)-4639B(RTN01). 7.Be aware, at 4638B may decom IDU, ODU & antenna. Anyway, at 4639B may decom ODU & antenna ONLY as IDU(RTN910A-RTN01) had been share with another MW Link 4996B(RTN01)-4639B(RTN01). FE_4639B. 1.Once, successful migration/diverting child site 4119R. Later, may decom existing HW MW link 4638B(RTN03)-4639B(RTN01). 2.Be aware, at 4638B may decom IDU, ODU & antenna. Anyway, at 4639B may decom ODU & antenna ONLY as IDU(RTN910A-RTN01) had been share with another MW Link 4996B(RTN01)-4639B(RTN01). | MW IDU Patching need to perform by diverting child site traffic 4119R(Non NIC) from existing HW MW Link 4119R(RTN01)-4638B(RTN04) to xC PTN K00260. K00260 is Pair Colo with 4638B. Traffic 4638B previously already diverted to K00260. Site Impacted : 4119R. NE_4638B/K00260 1.Disable port 8-EG6-1 of RTN910A(RTN03). 2.Remove cascading between RTN03(port 8-EG6-1) and RTN04(port 8-EM6-1). 3.Request new port of xC PTN K00260 from ZTE IPRAN team. 4.Patching new 1x CAT6 cable from RTN04(port 8-EM6-1) to new port of xC PTN K00260. 5.Configure DCN Inband for RTN04 and new xC VLAN services for migration traffic for 4119R thru xC Host. 6.Later, may decom existing HW MW link 4638B(RTN03)-4639B(RTN01). 7.Be aware, at 4638B may decom IDU, ODU & antenna. Anyway, at 4639B may decom ODU & antenna ONLY as IDU(RTN910A-RTN01) had been share with another MW Link 4996B(RTN01)-4639B(RTN01). | MW IDU Patching need to perform by diverting child site traffic 4119R(Non NIC) from existing HW MW Link 4119R(RTN01)-4638B(RTN04) to xC PTN K00260. K00260 is Pair Colo with 4638B. Traffic 4638B previously already diverted to K00260. Site Impacted : 4119R. FE_4639B. 1.Once, successful migration/diverting child site 4119R. Later, may decom existing HW MW link 4638B(RTN03)-4639B(RTN01). 2.Be aware, at 4638B may decom IDU, ODU & antenna. Anyway, at 4639B may decom ODU & antenna ONLY as IDU(RTN910A-RTN01) had been share with another MW Link 4996B(RTN01)-4639B(RTN01). | [5 empty] | CCSMY | SQ202505050040-CCS | CCSMY | SQ202505050151-CCS | 2025-09-30 | 2025-09-30 | Completed | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032048 |  | 2025-03-21 | 2025-03-21 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-09 | 2025-05-23 | 2025-05-09 | 2025-06-04 | SAFDAR//HUSSAIN TALIB/7021000081 | CCS TI | 2025-05-09 | 2025-05-23 | 2025-05-09 | 2025-06-04 | SAFDAR//HUSSAIN TALIB/7021000081 | CCS TI | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-09 | 2025-05-09 | 2025-05-23 | 2025-05-09 | 2025-06-02 | SAFDAR//HUSSAIN TALIB/7021000081 | 2025-05-09 | 2025-05-23 | 2025-05-09 | 2025-05-10 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | NG HONG JIE7018000036 | Logistic Team | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250716-GCI | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
4616C_HU | Masjid Puteri Jaya | DU00005172927 | Northern | Kedah | 5.611820 | 100.551270 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_1+0_56M NE_4616C New 18G_SP_0.6M(MAC)+OMT x1. New 1xISM8 New XMC_3, Sub A_Hi x1. FE_4770A New 18G_SP_1.2M(MAC)+OMT x1. New 1xISM8 New XMC_3, Sub A_Lo x1. | MW Parallel Link | Link Existing HW 15G&18G_2+0_28M&56M_EPLA. Build new MW Parallel Link HW 18G_1+0_56M and configure EPLA with existing HW 15G&18G_2+0_28M&56M. Later, configuration will be 15G&18G_3+0_28M&56M_EPLA. Site Impacted : 4616C. NE_4616C 1.Install new New 18G_SP_0.6M(MAC)+OMT x1. 2.Install new 1x XMC_3 , Sub B_Hi and lay new IF/RG8 cables, configure and terminate it. 3.Insert new 1x ISM8 into existing RTN910A(RTN01) on slot 03. 4.Build new MW Parallel Link HW 18G_1+0_56M and configure EPLA with existing HW 15G&18G_2+0_28M&56M. Configure it. 5.Later, new configuration will be 15G&18G_3+0_28M&56M_EPLA. FE_4770A 1.Install new New 18G_SP_1.2M(MAC)+OMT x1. 2.Install new 1x XMC_3 , Sub B_Lo and lay new IF/RG8 cables, configure and terminate it. 3.Insert new 1x ISM8 into existing RTN910A(RTN14) on slot 04. 4.Build new MW Parallel Link HW 18G_1+0_56M and configure EPLA with existing HW 15G&18G_2+0_28M&56M. Configure it. 5.Later, new configuration will be 15G&18G_3+0_28M&56M_EPLA. | Link Existing HW 15G&18G_2+0_28M&56M_EPLA. Build new MW Parallel Link HW 18G_1+0_56M and configure EPLA with existing HW 15G&18G_2+0_28M&56M. Later, configuration will be 15G&18G_3+0_28M&56M_EPLA. Site Impacted : 4616C. NE_4616C 1.Install new New 18G_SP_0.6M(MAC)+OMT x1. 2.Install new 1x XMC_3 , Sub B_Hi and lay new IF/RG8 cables, configure and terminate it. 3.Insert new 1x ISM8 into existing RTN910A(RTN01) on slot 03. 4.Build new MW Parallel Link HW 18G_1+0_56M and configure EPLA with existing HW 15G&18G_2+0_28M&56M. Configure it. 5.Later, new configuration will be 15G&18G_3+0_28M&56M_EPLA. | Link Existing HW 15G&18G_2+0_28M&56M_EPLA. Build new MW Parallel Link HW 18G_1+0_56M and configure EPLA with existing HW 15G&18G_2+0_28M&56M. Later, configuration will be 15G&18G_3+0_28M&56M_EPLA. Site Impacted : 4616C. FE_4770A 1.Install new New 18G_SP_1.2M(MAC)+OMT x1. 2.Install new 1x XMC_3 , Sub B_Lo and lay new IF/RG8 cables, configure and terminate it. 3.Insert new 1x ISM8 into existing RTN910A(RTN14) on slot 04. 4.Build new MW Parallel Link HW 18G_1+0_56M and configure EPLA with existing HW 15G&18G_2+0_28M&56M. Configure it. 5.Later, new configuration will be 15G&18G_3+0_28M&56M_EPLA. | XMC_3 | MAC | 18G | 18G_SP_0.6M(MAC)+OMT x1. | 18G_SP_1.2M(MAC)+OMT x1. | CCSMY | SQ202504210258-CCS | CCSMY | SQ202504210107-CCS // SQ202504210102-CCS // SQ202504260175-CCS | 2025-12-04 | 2025-12-03 | Completed | 2025-04-16 | 2025-04-17 | 2025-04-16 | 2025-04-17 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032009 |  | 2025-03-21 | 2025-04-12 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-04-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-17 | 2025-04-30 | 2025-05-15 | 2025-05-15 | MUHAMMAD//AWAIS/7021000082 | CCS TI | 2025-04-17 | 2025-04-30 | 2025-05-15 | 2025-05-15 | MUHAMMAD//AWAIS/7021000082 | CCS TI | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-04-17 | 2025-04-30 | 2025-04-25 | 2025-04-25 | MUHAMMAD//AWAIS/7021000082 | 2025-11-25: 2025-04-17; 2025-11-25: 2025-04-30; 2025-11-25: 2025-04-17; 2025-11-28: 2025-04-17 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509250641-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
A00021_HU | A041A_A00021OD_CB_JENALIK | DU00005172928 | Northern | Perak | 4.969000 | 100.928800 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | FE_A00041 At Cisco Router 1x New Cisco Optical SFP Module 1310nm 10G 10Km. 1x Optical patch cord with suitable type and length. At Huawei IDU RTN950A 1x New HW Optical SFP Module 1310nm 10G 10Km. | IPRAN Port Upgrade | FE_A00041 At Cisco/PTN 1.Request new port from ZTE IPRAN team. ZTE IPRAN suggest to use 10G port TE 0/0/26. 2.Insert 1x new Cisco Optical SFP Module 1310nm 10G 10Km. Configure it. 3.Patching Optical Patch cord fiber LC-LC to Cisco Router/PTN and lay & terminate to HW RTN950A port 17-SLF2EM6-5. 4.Disable existing 1G port(unused) at Cisco Router in which use previously. 5.Migrate/divert traffics A00021, A00272, A01113 & A01060 to new 10G port TE 0/0/26. At Huawei RTN950A. 1.Enable 10G port 17-SLF2EM6-5. 2.Insert 1x new HW Optical SFP Module 1310nm 10G 10Km. Configure it. 3.Terminate Optical Patch cord fiber LC-LC from Cisco Router/PTN. 4.Disable existing 1G port(unused) 17-SLF2EM6-3. 5.Migrate/divert traffics A00021, A00272, A01113 & A01060 to new 10G port TE 0/0/26. |  | FE_A00041 At Cisco/PTN 1.Request new port from ZTE IPRAN team. ZTE IPRAN suggest to use 10G port TE 0/0/26. 2.Insert 1x new Cisco Optical SFP Module 1310nm 10G 10Km. Configure it. 3.Patching Optical Patch cord fiber LC-LC to Cisco Router/PTN and lay & terminate to HW RTN950A port 17-SLF2EM6-5. 4.Disable existing 1G port(unused) at Cisco Router in which use previously. 5.Migrate/divert traffics A00021, A00272, A01113 & A01060 to new 10G port TE 0/0/26. At Huawei RTN950A. 1.Enable 10G port 17-SLF2EM6-5. 2.Insert 1x new HW Optical SFP Module 1310nm 10G 10Km. Configure it. 3.Terminate Optical Patch cord fiber LC-LC from Cisco Router/PTN. 4.Disable existing 1G port(unused) 17-SLF2EM6-3. 5.Migrate/divert traffics A00021, A00272, A01113 & A01060 to new 10G port TE 0/0/26. | [5 empty] | CCSMY | SQ202504280454-CCS | CCSMY | SQ202504280735-CCS | 2025-09-30 | 2025-09-30 | Completed | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032016 |  | 2025-03-21 | 2025-03-22 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-16 | 2025-04-30 | 2025-04-16 | 2025-04-16 | CHEN TAK//EOH YANG/7021000004 | CCS TI | 2025-04-16 | 2025-04-30 | 2025-04-16 | 2025-04-16 | CHEN TAK//EOH YANG/7021000004 | CCS TI | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-04-30 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-04-16 | 2025-04-30 | 2025-04-16 | 2025-05-04 | CHEN TAK//EOH YANG/7021000004 | 2025-11-25: 2025-04-16; 2025-11-25: 2025-04-30; 2025-11-25: 2025-04-16; 2025-11-28: 2025-04-16 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507250716-GCI
4312A_HU | Bidor (NS highwa | DU00005172929 | Northern | Perak | 4.104850 | 101.303320 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M_CA&EPLA NE_4312A 13G_1.8M(MDD) x1. RTN910A x1. ISM8 x1. XMC_5D, Sub B_Hi x1. FE_4442A 13G_1.8M(MDD) x1. RTN910A x1. ISM8 x1. XMC_5D, Sub B_Lo x1. | MW Swap | Link Existing SM 13G_2+0_28M_LAG. Swap existing link to new HW 13G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4312A, 4314A & 4190H. NE_4312A 1.Install new 13G_1.8M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN01). 4.Install new 1x XMC_5D, Sub B_Hi. Configure it. 5.Configure DCN Inband. 6.Reuse existing port that belong to SM MW Link 4312A-4442A MW1 at IBeam. 7.Migrate traffic to new link in which BBU will patching to port 8-EM6-1. Configure it. 8.Patching port 8-EM6-2 to SM IDU AGS20(LAN 3) of existing SM MW Link 4312A-4314A MW1 . 9.Later, decom existing SM MW link 4312A-4442A MW1 if no other traffic backhaul via this link. FE_4442A 1.Install new 13G_1.8M(MDD) x1. 2.Install new 1xRTN910A(RTN12). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN12). 4.Install new 1x XMC_5D, Sub B_Lo. Configure it. 5.Configure DCN Inband. 6.Reuse existing port that belong to SM MW Link 4312A-4442A MW1 at IBeam and patching at port 8-EM6-1 of RTN910A(RTN12). 7.Later, decom existing SM MW link 4312A-4442A MW1 if no other traffic backhaul via this link. | Link Existing SM 13G_2+0_28M_LAG. Swap existing link to new HW 13G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4312A, 4314A & 4190H. NE_4312A 1.Install new 13G_1.8M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN01). 4.Install new 1x XMC_5D, Sub B_Hi. Configure it. 5.Configure DCN Inband. 6.Reuse existing port that belong to SM MW Link 4312A-4442A MW1 at IBeam. 7.Migrate traffic to new link in which BBU will patching to port 8-EM6-1. Configure it. 8.Patching port 8-EM6-2 to SM IDU AGS20(LAN 3) of existing SM MW Link 4312A-4314A MW1 . 9.Later, decom existing SM MW link 4312A-4442A MW1 if no other traffic backhaul via this link. | Link Existing SM 13G_2+0_28M_LAG. Swap existing link to new HW 13G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4312A, 4314A & 4190H. FE_4442A 1.Install new 13G_1.8M(MDD) x1. 2.Install new 1xRTN910A(RTN12). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN12). 4.Install new 1x XMC_5D, Sub B_Lo. Configure it. 5.Configure DCN Inband. 6.Reuse existing port that belong to SM MW Link 4312A-4442A MW1 at IBeam and patching at port 8-EM6-1 of RTN910A(RTN12). 7.Later, decom existing SM MW link 4312A-4442A MW1 if no other traffic backhaul via this link. | XMC_5D | MDD | 13G | 13G_1.8M(MDD) x1. | 13G_1.8M(MDD) x1. | Magicell | SQ202505280558-Magicell | Magicell | SQ202504230253-Magicell // SQ202504230255-Magicell // SQ202505230422-Magicell | 2025-12-09 | 2025-12-02 | Completed | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-31 | 2025-07-24 | 2025-07-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041376 |  | 2025-04-14 | 2025-04-15 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-13 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-24 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-06-03 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-11-25: 2025-05-08; 2025-11-25: 2025-05-08; 2025-11-25: 2025-05-08; 2025-11-28: 2025-05-08 |  |  | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202507250724-GTSB
4188D_HU | Jalan Cassia 3A Kg Raja | DU00005172930 | Northern | Pahang | 4.556667 | 101.414821 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Solution already provided under TX Rollout 4188D (DU00002962556) | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2480A_HU | NS HW KM390.9 (MAXIS) | DU00005172931 | Northern | Perak | 3.718202 | 101.475547 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M_CA. NE_2480A. 13G_DP_1.2M(MDD) x1. XMC_5D , Sub A_Hi x1. ISM8 x2. FE_4730A. 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Lo x1. | MW Swap | Existing link 13G_2+0_28M Swap existing to 13G_4+0_28M_CA. Site Impacted : 2480A , 1678H. NE_2480A. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 2480A_RTN01. 3.Install new XMC_5D , Sub A_Hi with CA config. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 2480A_RTN01 for CA config. 5.Create cross connect , CA and EPLA new 13G_4+0 and existing 13G_2+0. 6.No decom existing MW link. FE_4730A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo with CA config. 4.Transfer existing 13G_2+0 IF cables to new RTN910A ,7_ISM8-2+0. 5.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into New RTN910A. 6.Create cross connect , CA and EPLA new 13G_4+0 and existing 13G_2+0. 7.Create New In Band DCN. 8.No decom existing MW link. | Existing link 13G_2+0_28M Swap existing to 13G_4+0_28M_CA. Site Impacted : 2480A , 1678H. NE_2480A. 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 2480A_RTN01. 3.Install new XMC_5D , Sub A_Hi with CA config. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 2480A_RTN01 for CA config. 5.Create cross connect , CA and EPLA new 13G_4+0 and existing 13G_2+0. 6.No decom existing MW link. | Existing link 13G_2+0_28M Swap existing to 13G_4+0_28M_CA. Site Impacted : 2480A , 1678H. FE_4730A. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub A_Lo with CA config. 4.Transfer existing 13G_2+0 IF cables to new RTN910A ,7_ISM8-2+0. 5.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into New RTN910A. 6.Create cross connect , CA and EPLA new 13G_4+0 and existing 13G_2+0. 7.Create New In Band DCN. 8.No decom existing MW link. | XMC_5D | MDD | 13G | 1.2 | 1.2 | Magicell | SQ202504170480-Magicell | Magicell | SQ202505050154-Magicell // SQ202505050157-Magicell // SQ202507290130-Magicell | 2025-05-26 | 2025-05-26 | Completed | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032041 |  | 2025-03-21 | 2025-04-09 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-04-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-27 | 2026-03-05 | 2025-03-27 | 2025-05-05 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 |  | 2025-03-27 | 2026-03-05 | 2025-03-27 | 2025-06-03 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-03 | 2025-03-27 | 2026-03-05 | 2025-03-27 | 2025-06-14 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-11-25: 2025-03-27; 2025-11-25: 2026-03-05; 2025-11-25: 2025-03-27; 2025-11-28: 2025-06-03 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202506050727-GTSB
3404B_HU | Syabas Bangi Lama | DU00005172932 | Central | Selangor | 2.896875 | 101.792034 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Parallel Link | MW PARALLEL LINK 3404B-2400A WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_128QAM_1352MBPS_XMC3E_SUB_A_3.56KM IMPACTED: 3404B, 2997C, 1643K | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM 5. CASCADE 3404B RTN01 AND RTN04 TO BRING TRAFFIC 2997C AND 1643K 6. PATCH BBU TO NEW LINK IDU | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 18G 2+0 112MHZ 128MHZ 5. PATCH IDU TO NEW CP PORT AND DO PORT LAG | XMC3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202504280360-Magicell | Magicell | SQ202505190296-Magicell // SQ202505190304-Magicell | 2025-06-25 | 2025-06-25 | Completed | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050952 |  | 2025-05-14 | 2025-05-26 | Completed | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-26 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-26 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-19 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-23 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-11-25: 2025-05-14; 2025-11-25: 2025-05-14; 2025-11-25: 2025-05-14; 2025-11-28: 2025-05-16 |  |  | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505190510-GCI | 2025-05-04 | 2025-05-04 | 2025-05-04 | 2025-05-04 | EZRIN TASNIM BIN ABDUL GANI6798000128
1892B_HU | NS HW KM435(Maxis) | DU00005172933 | Central | Selangor | 3.380000 | 101.559900 |  | APR 25 |  | JUN 25 | TI | Doable | ZTE | 03. TSS Only | 24/3/2025 : MAXIS - 60M 3 Legged Tower - NE site 1892B NS HW KM435(Maxis), Digi OB - Tower - FE site 1413A KTM Rawang | TSS |  | 2X 13G 1.2M DP ANTENNA 1x ODU 13G XMC3 SUB A HI 1X ODU 13G XMC3 SUB A LO | MW Parallel Link | 07 Jan 2026: Drop due to access issue at 1413A. TSS only. Traffic offload planned under DU 1892B_HU_1 MW PARALLEL LINK 1892B-1413A WITH HUAWEI_13G_2+0_1.2M/1.M_DP_28MHZ_512QAM_450MBPS_XMC3_SUB A_6.94KM_EPLA WITH EXISTING 15G 4+0 IMPACTED: 1892B, 2007B, 1019R | 1. REUSE EXISTING RTN910 2. INSTALL NEW 13G 1.2M DP ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A 3. CONFIGURE LINK 13G 2+0 28MHZ 512QAM EPLA WITH EXISTING 15G 4+0 | 1. REUSE EXISTING RTN910 2. INSTALL NEW 13G 1.2M DP ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A 3. CONFIGURE LINK 13G 2+0 28MHZ 512QAM EPLA WITH EXISTING 15G 4+0 4. PATCH TO NEW CP PORT AND DO PORT LAG | XMC3 | MAC | 13G | 1.2 | 1.2 | Magicell | SQ202504240791-Magicell | Magicell | No PR required-Work at TSS only | 2025-06-17 | 2025-06-30 | Completed | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-16 | 2025-06-17 | 2025-06-17 | 2025-06-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25042122 |  | 2025-04-22 | 2025-04-23 | Completed | 2025-04-21 | 2025-04-22 | 2025-04-21 | 2025-04-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202506050715-GTSB
4767A_HU | Tmn Gunung bintang | DU00005172934 | Northern | Kedah | 6.072805 | 100.365359 | [7 empty] | 00. Integrated/RFS Done | 17/04 : CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M. NE_4767A 18G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Hi x1. RTN910A x 1. FE_4663B 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. | MW Swap | Existing link 18G_1+0_56M (Unable remote software upgrade). Swap existing to 18G_2+0_112M. Site Impacted : 4767A. NE_4767A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A due to existing RTN faulty. 3.Install new 3_ISM8-2+0 into existing 4767A_RTN01. 4.Install new XMC_5D , Sub A_Hi 5.Create service cross connect and EPLA. 6.Traffic migrate to new MW link. 7.Decom existing ODU and Ant. FE_4663B 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no. provide by MSP team). 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link. 6.Create new In Band DCN. 7.Create phys LAG GE1 & GE2 conect to Ibeam_Fiber Port. 7.Decom existing 2_ISV3 , ODU and Ant. | Existing link 18G_1+0_56M (Unable remote software upgrade). Swap existing to 18G_2+0_112M. Site Impacted : 4767A. NE_4767A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A due to existing RTN faulty. 3.Install new 3_ISM8-2+0 into existing 4767A_RTN01. 4.Install new XMC_5D , Sub A_Hi 5.Create service cross connect and EPLA. 6.Traffic migrate to new MW link. 7.Decom existing ODU and Ant. | Existing link 18G_1+0_56M (Unable remote software upgrade). Swap existing to 18G_2+0_112M. Site Impacted : 4767A. FE_4663B 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no. provide by MSP team). 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW link. 6.Create new In Band DCN. 7.Create phys LAG GE1 & GE2 conect to Ibeam_Fiber Port. 7.Decom existing 2_ISV3 , ODU and Ant. | XMC_5D | MDD | 18G | 0.6 | 0.6 | CCSMY | SQ202504210258-CCS | CCSMY | SQ202504210107-CCS // SQ202504210102-CCS // SQ202504260175-CCS |  |  | Ongoing | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25032006 |  | 2025-03-21 | 2025-03-22 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-10 | 2025-04-30 | 2025-04-10 | 2025-04-18 | HASHIM//BIN AHMAD ZAIDI/7021000032 | CCS TI | 2025-04-10 | 2025-04-30 | 2025-04-10 | 2025-04-18 | HASHIM//BIN AHMAD ZAIDI/7021000032 | CCS TI | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-17 | 2025-04-10 | 2025-04-30 | 2025-04-10 | 2025-05-07 | HASHIM//BIN AHMAD ZAIDI/7021000032 | 2025-04-10 | 2025-04-30 | 2025-04-10 | 2025-05-06 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | CHEONG/SENG/WAH/7018000306
3500A12_HU | pBTS Kg Rapak | DU00005172935 | Sabah | Sabah | 5.960080 | 116.677884 |  |  |  | JUN 25 |  | TI DONE | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_0.6/0.6_SP_SB B | MW Swap | MW SWAP 3500A12-7321A WITH 18G_1+0_0.6/0.6_SB B. DISMANTLE EXISITNG 15G LINK. | MW SWAP 3500A12-7321A WITH 18G_1+0_0.6/0.6_SB B. NE: 1. Reuse existing RTN910A. 2. Swap exisiing ODU with 18G_XMC_3E_SB B. 3. Swap exisiting antenna with 18G_0.6m_SP. 4.Configure 18G_1+0_0.6_256QAM. 5. Dismantle 15G link. | MW SWAP 3500A12-7321A WITH 18G_1+0_0.6/0.6_SB B. FE: 1. Reuse existing RTN910A. 2. Swap exisitng ISV3 with ISM8 at slot 3. 3. Swap exisiing ODU with 18G_XMC_3E_SB B. 4. Swap exisiting antenna with 18G_0.6m_SP. 5.Configure 18G_1+0_0.6_256QAM. 6. Dismantle 15G link. | XMC-3E SB B | SP |  | 0.6 | 0.6 | NR services | SQ202504210288-NR Services | NR services | SQ202506250225-NR Services // SQ202506250231-NR Services | 2025-05-09 | 2025-05-02 | Completed | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-02 | 2025-05-09 | 2025-05-02 | 2025-05-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061208 |  | 2025-07-24 | 2025-06-28 | Completed | 2025-06-24 | 2025-07-24 | 2025-06-24 | 2025-06-28 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-24 | 2025-07-24 | 2025-06-24 | 2025-06-28 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-06-24 | 2025-07-24 | 2025-06-24 | 2025-07-06 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-11 | 2025-06-24 | 2025-07-24 | 2025-06-24 | 2025-07-24 | RALPH O'BRYAN HILARY7167000030 | 2025-06-24 | 2025-07-24 | 2025-06-24 | 2025-06-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | tseping//wang/6819000006 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | HSU//MYET CHAE/6799000011
3503A11_HU | pBTS South Sekinchan | DU00005172936 | Central | Selangor | 3.497958 | 101.104027 | WK12 | MAR 25 | WK12 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 20/3/2025 : Cutover done 19/3/2025 : NE installation complete, FE installation WIP 18/3/2025 : Digi OB - 25M PBTS - NE site 3503A11 pBTS South Sekinchan, Digi OB - 60M 4 Legged Tower - FE site 1154A Sekinchan | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap | MW SWAP LINK 3503A-1154A WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_778MBPS_XMC3E_SUB B_3.03KM DISMANTLE EXISTING LINK IMPACTED: 3503A | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 1+0 112MHZ 128QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 1+0 112MHZ 128QAM 5. DISMANTLE EXISTING LINK 6. PATCH TO NEW CP PORT | XMC3E | MAC | 18G | 0.6 | 0.6 | GTSB | SQ202503270782-GTSB | GTSB | SQ202503240695-GTSB // SQ202503240700-GTSB // SQ202504260131-GTSB | 2025-04-24 | 2025-04-23 | Completed | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-25 | 2025-04-22 | 2025-03-25 | 2025-03-25 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-07 | 2025-04-08 | 2025-04-07 | 2025-04-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-23 | 2025-04-24 | 2025-04-23 | 2025-04-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031198 |  | 2025-03-12 | 2025-03-24 | Completed | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-24 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-24 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-20 | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-21 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-21 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
4304D_HU | Tanjong Dawai(Maxis)(REL) | DU00005172937 | Northern | Kedah | 5.679330 | 100.369350 |  |  |  |  | Integrated/RFS | ZTE |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M with refer to 4304D_HU_1 (DU Code DU00005509290. NE_4304D. 13G_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Lo x1. FE_4939A. 13G_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing link 15G_4+0_28M. Add Parallel Link 13G_4+0_28M to become 13G_6+0 with 13G_2+0_28M refer to DU Code DU00005509290. Site Impacted : 4304D. NE_4304D. 1.Install new 13G_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Lo with CA for ant 2. 6.Create service cross connect and EPLA for 6+0 link. 7.Traffic migrate to new MW link 13G_6+0_28M. 8.Decom existing IDU , ODU and Ant. FE_4939A. 1.Install new 13G_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Hi with CA for ant 2. 6.Create service cross connect and EPLA for 6+0 link. 7.Create New In Band DCN. 8.Traffic migrate to new MW link 13G_6+0_28M. 9.Decom existing Ant , ODU and 3_ISM8. | Existing link 15G_4+0_28M. Add Parallel Link 13G_4+0_28M to become 13G_6+0 with 13G_2+0_28M refer to DU Code DU00005509290. Site Impacted : 4304D. NE_4304D. 1.Install new 13G_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Lo with CA for ant 2. 6.Create service cross connect and EPLA for 6+0 link. 7.Traffic migrate to new MW link 13G_6+0_28M. 8.Decom existing IDU , ODU and Ant. | Existing link 15G_4+0_28M. Add Parallel Link 13G_4+0_28M to become 13G_6+0 with 13G_2+0_28M refer to DU Code DU00005509290. Site Impacted : 4304D. FE_4939A. 1.Install new 13G_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install new XMC_5D , Sub A_Hi with CA for ant 2. 6.Create service cross connect and EPLA for 6+0 link. 7.Create New In Band DCN. 8.Traffic migrate to new MW link 13G_6+0_28M. 9.Decom existing Ant , ODU and 3_ISM8. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202504280464-GCI | GCI | SQ202505190405-GCI // SQ202505190415-GCI | 2025-12-04 | 2025-12-03 | Completed | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051479 |  | 2025-05-15 | 2025-05-16 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-05-23 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-05-23 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-21 | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-06-03 | SAFUAN//BIN YUSOFF/6800000178 | 2025-03-19: 2025-05-19; 2025-03-19: 2025-05-31; 2025-03-19: 2025-05-19; 2025-03-21: 2025-05-19 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505070152-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | CHEONG/SENG/WAH/7018000306
4947A_HU | Kota Kuala Muda | DU00005172938 | Northern | Kedah | 5.589173 | 100.373127 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M. NE_4947A 13G_DP_1.2M(MS) x1. ISM8 x2. XMC_5D , Sub A_Lo x1. XMC_5D , Sub B_Lo x2. Coupler x1. FE_4272A 13G_DP_1.2M(MS) x1. Coupler x1. ISM8 x2. XMC_5D , Sub A_Hi x1. XMC_5D , Sub B_Hi x1. | MW Parallel Link | Existing link 15G_2+0_28M. Install Parallel link to 13G_4+0_28M. Site Impacted : 4117R. NE_4947A 1.Install new 13G_DP_1.2M(MS). 2.Reuse existing 4947A_RTN01. 3.Install new 2_ISM8-2+0 and 4_ISM8-2+0 into existing 4947A_RTN01. 4.Install XMC_5D , Sub A_Lo for V. 5.Install XMC_5D , Sub B_Lo for H. 6.Create service cross connect and EPLA with new 13G_4+0 and existing 15G_2+0. 7.No decom existing MW link. FE_4272A 1.Install new 13G_DP_1.2M(MS). 2.Reuse existing 4272A_RTN07. 3.Install new 4_ISM8-2+0 and 6_ISM8-2+0 into existing 4272A_RTN07. 4.Install XMC_5D , Sub A_Hi for V. 5.Install XMC_5D , Sub B_Hi for H. 6.Create service cross connect and EPLA with new 13G_4+0 and existing 15G_2+0. 7.No decom existing MW link. | Existing link 15G_2+0_28M. Install Parallel link to 13G_4+0_28M. Site Impacted : 4117R. NE_4947A 1.Install new 13G_DP_1.2M(MS). 2.Reuse existing 4947A_RTN01. 3.Install new 2_ISM8-2+0 and 4_ISM8-2+0 into exsiting 4947A_RTN01. 4.Install XMC_5D , Sub A_Lo for V. 5.Install XMC_5D , Sub B_Lo for H. 6.Create service cross connect and EPLA with new 13G_4+0 and existing 15G_2+0. 7.No decom existing MW link. | Existing link 15G_2+0_28M. Install Parallel link to 13G_4+0_28M. Site Impacted : 4117R. FE_4272A 1.Install new 13G_DP_1.2M(MS). 2.Reuse existing 4272A_RTN07. 3.Install new 4_ISM8-2+0 and 6_ISM8-2+0 into existing 4272A_RTN07. 4.Install XMC_5D , Sub A_Hi for V. 5.Install XMC_5D , Sub B_Hi for H. 6.Create service cross connect and EPLA with new 13G_4+0 and existing 15G_2+0. 7.No decom existing MW link. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202504210266-GCI | GCI | SQ202504260066-GCI // SQ202504260070-GCI // SQ202505150106-GCI | 2025-10-30 | 2025-11-20 | Completed | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-30 | 2025-11-20 | 2025-11-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041372 |  | 2025-04-14 | 2025-04-15 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-21 | 2025-04-30 | 2025-04-21 | 2025-05-13 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-04-21 | 2025-04-30 | 2025-04-21 | 2025-05-06 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-25 | 2025-04-21 | 2025-04-30 | 2025-04-21 | 2025-05-04 | SAFUAN//BIN YUSOFF/6800000178 | 2025-03-19: 2025-04-21; 2025-03-19: 2025-04-30; 2025-03-19: 2025-04-21; 2025-03-21: 2025-04-22 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | CHEONG/SENG/WAH/7018000306
4672C_HU | Idaman Lavendar | DU00005172939 | Northern | Penang | 5.331271 | 100.272489 |  |  |  |  | 00. Integrated/RFS Done | ZTE | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_4672C 18G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Hi x1. FE_4034A 18G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Lo x1. | MW Swap | Existing link 18G_1+0_112M & 15G_1+0_28M with EPLA. Swap existing 15G_1+0_28M to 18G_2+0_112M with EPLA existing 18G_1+0_112M. Site Impacted : 4672C. NE_4672C 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4672C_RTN01. 3.Install new 4_ISM8-2+0 into existing 4672C_RTN01. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA with new 18G_2+0 and existing 18G_1+0. 6.Decom existing 3_ISM8 , ODU and Ant. FE_4034A 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4034A_RTN11 3.Install new 4_ISM8-2+0 into existing 4034A_RTN01. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA with new 18G_2+0 and existing 18G_1+0. 6.Decom existing 3_ISM8 , ODU and Ant. | Existing link 18G_1+0_112M & 15G_1+0_28M with EPLA. Swap existing 15G_1+0_28M to 18G_2+0_112M with EPLA existing 18G_1+0_112M. Site Impacted : 4672C. NE_4672C 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4672C_RTN01. 3.Install new 4_ISM8-2+0 into existing 4672C_RTN01. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA with new 18G_2+0 and existing 18G_1+0. 6.Decom existing 3_ISM8 , ODU and Ant. | Existing link 18G_1+0_112M & 15G_1+0_28M with EPLA. Swap existing 15G_1+0_28M to 18G+2_0_112M with EPLA existing 18G_1+0_112M. Site Impacted : 4672C. FE_4034A 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 4034A_RTN11 3.Install new 4_ISM8-2+0 into existing 4034A_RTN01. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA with new 18G_2+0 and existing 18G_1+0. 6.Decom existing 3_ISM8 , ODU and Ant. | XMC_5D | MDD | 18G | 0.6 | 0.6 | GTSB | SQ202504280474-GTSB | GTSB | SQ202505280074-GTSB // SQ202505280077-GTSB | 2025-12-04 | 2025-12-03 | Completed | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25042902 |  | 2025-04-30 | 2025-06-02 | Completed | 2025-04-29 | 2025-04-30 | 2025-04-29 | 2025-06-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-06-02 | YASIR//ABBAS/6799000106 | GTSB TI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-06-13 | YASIR//ABBAS/6799000106 | GTSB TI | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-03 | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-06-12 | YASIR//ABBAS/6799000106 | 2025-03-19: 2025-05-28; 2025-03-19: 2025-05-28; 2025-03-19: 2025-05-28; 2025-03-21: 2025-05-28 |  |  | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506160754-GCI | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | CHEONG/SENG/WAH/7018000306
4994A_HU | Kodiang | DU00005172940 | Northern | Kedah | 6.392275 | 100.311142 |  |  |  |  | TI IN PLAN | ZTE |  | 00. Integrated/RFS Done | 26/6 : TI Started 26/6 : BEE HIVE detected onsite, pending email to NOC for HSSE matters 10/07: CO Done | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M NE_4994A 15G_DP_1.2M(MAC)+OMT x1. XMC_3 , Sub A & B_Lo x2. ISM8 x1 FE_4606B 15G_DP_1.2M(MAC)+OMT x1. XMC_3 , Sub A & B_Hi x2. ISM8 x1. | MW Parallel Link | Existing link 15G_4+0_28M with EPLA Install parallel link 15G_2+0_28M with EPLA existing MW link. Site Impacted : 4994A. NE_4994A 1.Install new 15G_DP_1.2M(MAC)+OMT. 2.Install new XMC_3 , Sub A & B_Lo. 3.Reuse existing 4994A_RTN03. 4.Install new 3_ISM8-2+0 into existing 4994A_RTN03. 5.Create service cross connect and EPLA with existing 4+0 MW link. 6.No decom existing MW link. FE_4606B 1.Install mew 15G_DP_1.2M(MAC)+OMT. 2.Install new XMC_3 , Sub A & B_Hi. 3.Reuse existing 4606B_RTN08. 4.Install new 4_ISM8-2+0 into existing 4606B_RTN08. 5.Create service cross connect and EPLA with existing 4+0 MW link. 6.No decom existing MW link. | Existing link 15G_4+0_28M with EPLA Install parallel link 15G_2+0_28M with EPLA existing MW link. Site Impacted : 4994A. NE_4994A 1.Install new 15G_DP_1.2M(MAC)+OMT. 2.Install new XMC_3 , Sub A & B_Lo. 3.Reuse existing 4994A_RTN03. 4.Install new 3_ISM8-2+0 into existing 4994A_RTN03. 5.Create service cross connect and EPLA with existing 4+0 MW link. 6.No decom existing MW link. | Existing link 15G_4+0_28M with EPLA Install parallel link 15G_2+0_28M with EPLA existing MW link. Site Impacted : 4994A. FE_4606B 1.Install mew 15G_DP_1.2M(MAC)+OMT. 2.Install new XMC_3 , Sub A & B_Hi. 3.Reuse existing 4606B_RTN08. 4.Install new 4_ISM8-2+0 into existing 4606B_RTN08. 5.Create service cross connect and EPLA with existing 4+0 MW link. 6.No decom existing MW link. | XMC_3 | MAC | 15G | 1.2 | 1.2 | GTSB | SQ202504280474-GTSB | GTSB | SQ202505290482-GTSB // SQ202505290490-GTSB | 2025-08-15 | 2025-08-14 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-08-04 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-14 | 2025-08-15 | 2025-08-14 | 2025-08-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051486 |  | 2025-05-15 | 2025-05-29 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-07-22 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-07-22 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-10 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-07-28 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2025-03-19: 2025-06-26; 2025-03-19: 2025-06-26; 2025-03-19: 2025-06-26; 2025-03-21: 2025-07-29 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
P00711_HU | P033C_P00711OD_PENANG_SCIENCE_PARK | DU00005172941 | Northern | Penang | 5.289448 | 100.442080 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M NE_P00711 New 18G_0.6M(MDD) x1. New RTN910A. New XMC_5D, Sub B_Hi x2. FE_P00002 New 18G_0.6M(MDD) x1. New RTN910A. New XMC_5D, Sub B_Lo x2. | MW Swap | Link Existing HW 18G_1+0_56M. Swap existing link to 18G_2+0_56M_512QAM_EPLA. Site Impacted : P00711. NE_P00711 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A. Configure it. 3.Install XMC_5D, Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A. 6.Migrate traffic to new link in which BBU P00711 will be patching to port 8-EM6-1 of RTN910A. Configure it. 7.Decom existing HW MW link P00711-P00002, if no other traffic backhauled. FE_P00002 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A. Configure it. 3.Install XMC_5D, Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A and patching to existing port at Cisco/PTN. Configure it. 6.Decom existing HW MW link P00711-P00002, if no other traffic backhauled. | Link Existing HW 18G_1+0_56M. Swap existing link to 18G_2+0_56M_512QAM_EPLA. Site Impacted : P00711. NE_P00711 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A. Configure it. 3.Install XMC_5D, Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A. 6.Migrate traffic to new link in which BBU P00711 will be patching to port 8-EM6-1 of RTN910A. Configure it. 7.Decom existing HW MW link P00711-P00002, if no other traffic backhauled. | Link Existing HW 18G_1+0_56M. Swap existing link to 18G_2+0_56M_512QAM_EPLA. Site Impacted : P00711. FE_P00002 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A. Configure it. 3.Install XMC_5D, Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A and patching to existing port at Cisco/PTN. Configure it. 6.Decom existing HW MW link P00711-P00002, if no other traffic backhauled. | XMC_5D | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | CCSMY | SQ202504280454-CCS | CCSMY | SQ202505240083-CCS // SQ202505240104-CCS | 2025-12-09 | 2025-12-02 | Completed | 2025-05-03 | 2025-05-03 | 2025-05-03 | 2025-05-03 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | MOHAMAD//NAJIB/7021000024 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-09-02 | 2025-08-26 | 2025-08-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25042915 |  | 2025-04-30 | 2025-05-10 | Completed | 2025-04-29 | 2025-04-30 | 2025-04-29 | 2025-05-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-21 | Saleem//Muhammed/7021000077 | CCS TI | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | Saleem//Muhammed/7021000077 | CCS TI | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-21 | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-27 | Saleem//Muhammed/7021000077 | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | NG HONG JIE7018000036 | Logistic Team | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202509250697-GTSB | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | AB.RAHMAN//BIN MAT NOOH/6237001519
4058A_HU | Mutiara View Complex | DU00005172942 | Northern | Penang | 5.378919 | 100.302640 | [7 empty] | 00. Integrated/RFS Done | 25/6: CO done. | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M. NE_4058A 15G_DP_1.2M(MS) x1. RTN910A x1. ISM8 x2. XMC_3 , Sub A & B_Lo x1. FE_4031A 15G_DP_1.2M(MS) x1. RTN910A x1. ISM8 x2. XMC_3 , Sub A & B_Hi x1. ETH Cable x1. | MW Swap | Existing link 15G_2+0_28M Swap existing link to 15G_4+0_28M due to the FE 4031A Landlord not allow to add additional equipment's prior team proceed the installation. Site Impacted : 4058A , 4553D. NE_4058A 1.Install new 15G_DP_1.2M(MS). 2.Install new RTN910A (RTN no provide by MSP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install coupler + Waveguide. 5.Install new XMC_3 , Sub A & B_Lo. 6.Create service cross connect , EPLA and CA. 7.Traffic migrate to new link 15G_4+0_28M (4058A & 4031A). 8.Decom existing MW link. FE_4031A 1.Install new 15G_DP_1.2M(MS). 2.Install new RTN910A(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_3 , Sub A & B_Hi. 5.Install coupler + Waveguide. 6.Create service cross connect , EPLA and CA. 7.Create new In Band DCN. 8.Traffic migrate to new MW link 15G_4+0_28M. (4058A & 4031A) 9.Decom existing MW link , perform Hot Swap. | Existing link 15G_2+0_28M Swap existing link to 15G_4+0_28M due to the FE 4031A Landlord not allow to add additional equipment's prior team proceed the installation. Site Impacted : 4058A , 4553D. NE_4058A 1.Install new 15G_DP_1.2M(MS). 2.Install new RTN910A (RTN no provide by MSP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install coupler + Waveguide. 5.Install new XMC_3 , Sub A & B_Lo. 6.Create service cross connect , EPLA and CA. 7.Traffic migrate to new link 15G_4+0_28M (4058A & 4031A). 8.Decom existing MW link. | Existing link 15G_2+0_28M Swap existing link to 15G_4+0_28M due to the FE 4031A Landlord not allow to add additional equipment's prior team proceed the installation. Site Impacted : 4058A , 4553D. FE_4031A 1.Install new 15G_DP_1.2M(MS). 2.Install new RTN910A(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install new XMC_3 , Sub A & B_Hi. 5.Install coupler + Waveguide. 6.Create service cross connect , EPLA and CA. 7.Create new In Band DCN. 8.Traffic migrate to new MW link 15G_4+0_28M. (4058A & 4031A) 9.Decom existing MW link , perform Hot Swap. | XMC_3 | MAC | 15G | 1.2 | 1.2 | GCI | SQ202507040579-GCI | GCI | SQ202504260066-GCI // SQ202504260070-GCI // SQ202505150106-GCI // SQ202508140738-GCI // SQ202508140739-GCI | 2025-10-25 | 2025-10-24 | Completed | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041373 |  | 2025-04-14 | 2025-04-15 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-22 | 2025-04-30 | 2025-04-22 | 2025-07-14 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-04-22 | 2025-04-30 | 2025-04-22 | 2025-07-06 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | AKMAL//BIN RAZALI/6794000078 |  | 2025-06-25 | 2025-04-22 | 2025-04-30 | 2025-04-22 | 2025-07-29 | MOHD FAIZ BIN MD YUNUS6800000186 | 2025-04-22 | 2025-04-30 | 2025-04-22 | 2025-07-14 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507250716-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | CHEONG/SENG/WAH/7018000306
4484B_HU | Temoh Station-100Q4 RDC | DU00005172943 | Northern | Perak | 4.241471 | 101.187969 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M_256Q&64Q CA&EPLA NE_4484B 15G_1.2M(MDD) x1. RTN910A x1. ISM8 x1. XMC_5D, Sub B_Hi x1. FE_4442A 15G_1.2M(MDD) x1. RTN910A x1. ISM8 x1. XMC_5D, Sub B_Lo x1. | MW Parallel Link | Adding new MW parallel Link HW 15G_4+0_28M_256QAM&64QAM_CA&EPLA. Site Impacted : 4484B. NE_4484B 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN02). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN02). 4.Install new 1x XMC_5D, Sub B_Hi. Configure combination 2 vertical channels using 256QAM and 2 horizontal channels using 64QAM. 5.Configure CA & EPLA and become 15G_4+0_28MHz_256Q&64Q_CA&EPLA. 6.Configure DCN Inband. 7.Migrate traffic to new link in which BBU 4484B will patching to port 8-EM6-1 of RTN910A(RTN02). Configure it. 8.Do not decom existing HW MW Link 4484A(RTN01)-4442A(RTN02) in order for backhauling traffic child site 4176R ONLY. FE_4442A 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN13). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN13). 4.Install new 1x XMC_5D, Sub B_Lo. Configure combination 2 vertical channels using 256QAM and 2 horizontal channels using 64QAM. 5.Configure CA & EPLA and become 15G_4+0_28MHz_256Q&64Q_CA&EPLA. 6.Configure DCN Inband. 7.Request new port at IBeam from ZTE IPRAN team and patching to port 8-EM6-1 of RTN910A(RTN13). 8.Do not decom existing HW MW Link 4484A(RTN01)-4442A(RTN02) in order for backhauling traffic child site 4176R ONLY. | Adding new MW parallel Link HW 15G_4+0_28M_256QAM&64QAM_CA&EPLA. Site Impacted : 4484B. NE_4484B 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN02). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN02). 4.Install new 1x XMC_5D, Sub B_Hi. Configure combination 2 vertical channels using 256QAM and 2 horizontal channels using 64QAM. 5.Configure CA & EPLA and become 15G_4+0_28MHz_256Q&64Q_CA&EPLA. 6.Configure DCN Inband. 7.Migrate traffic to new link in which BBU 4484B will patching to port 8-EM6-1 of RTN910A(RTN02). Configure it. 8.Do not decom existing HW MW Link 4484A(RTN01)-4442A(RTN02) in order for backhauling traffic child site 4176R ONLY. | Adding new MW parallel Link HW 15G_4+0_28M_256QAM&64QAM_CA&EPLA. Site Impacted : 4484B. FE_4442A 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN13). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN13). 4.Install new 1x XMC_5D, Sub B_Lo. Configure combination 2 vertical channels using 256QAM and 2 horizontal channels using 64QAM. 5.Configure CA & EPLA and become 15G_4+0_28MHz_256Q&64Q_CA&EPLA. 6.Configure DCN Inband. 7.Request new port at IBeam from ZTE IPRAN team and patching to port 8-EM6-1 of RTN910A(RTN13). 8.Do not decom existing HW MW Link 4484A(RTN01)-4442A(RTN02) in order for backhauling traffic child site 4176R ONLY. | XMC_5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | Magicell | SQ202503270808-Magicell | Magicell | SQ202503280499-Magicell // SQ202503280504-Magicell // SQ202504260184-Magicell // SQ202507290130-Magicell | 2025-12-05 | 2025-12-04 | Completed | 2025-03-26 | 2025-03-26 | 2025-03-25 | 2025-03-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-04 | 2025-12-05 | 2025-12-04 | 2025-12-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032072 |  | 2025-03-21 | 2025-03-21 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2025-04-07 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2025-04-07 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-27 | 2025-03-24 | 2025-03-31 | 2025-03-24 | 2025-04-09 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-03-19: 2025-03-24; 2025-03-19: 2025-03-31; 2025-03-19: 2025-03-24; 2025-03-21: 2025-04-07 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402
4334A_HU | Kuala Kurau Town RDD | DU00005172944 | Northern | Perak | 5.022510 | 100.431920 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_4+0_28M_CA&EPLA NE_4334A 13G_1.8M(MDD) x1. RTN910A x1. New ISM8 x1. XMC_5D, Sub B_Hi x1. FE_4331A 13G_1.8M(MDD) x1. RTN910A x1. New ISM8 x1. XMC_5D, Sub B_Lo x1. | MW Swap | Link Existing SM 13G_2+0_28M_LAG. Swap existing link to new HW 13G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4334A & 4335A. NE_4334A 1.Install new 13G_1.8M(MDD) x1. 2.Install new 1xRTN910A(RTN05). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN05). 4.Install new 1x XMC_5D, Sub B_Hi. Configure it. 5.Configure DCN Inband. 6.Reuse existing port that belong to SM MW Link 4334A-4331A MW4 at IBeam. 7.Migrate traffic to new link in which BBU will patching to port 8-EM6-1. 8.Patching port 8-EM6-2 to RTN910A(RTN04) port 8-EM6-1. 9.Decom existing SM MW link 4334A-4331A MW4. FE_4331A 1.Install new 13G_1.8M(MDD) x1. 2.Install new 1xRTN910A(RTN05). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN05). 4.Install new 1x XMC_5D, Sub B_Lo. Configure it. 5.Configure DCN Inband. 6.Reuse existing port that belong to SM MW Link 4334A-4331A MW4 at IBeam and patching at port 8-EM6-1 of RTN910A(RTN05). 7.Decom existing SM MW link 4334A-4331A MW4. | Link Existing SM 13G_2+0_28M_LAG. Swap existing link to new HW 13G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4334A & 4335A. NE_4334A 1.Install new 13G_1.8M(MDD) x1. 2.Install new 1xRTN910A(RTN05). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN05). 4.Install new 1x XMC_5D, Sub B_Hi. Configure it. 5.Configure DCN Inband. 6.Reuse existing port that belong to SM MW Link 4334A-4331A MW4 at IBeam. 7.Migrate traffic to new link in which BBU will patching to port 8-EM6-1. 8.Patching port 8-EM6-2 to RTN910A(RTN04) port 8-EM6-1. 9.Decom existing SM MW link 4334A-4331A MW4. | Link Existing SM 13G_2+0_28M_LAG. Swap existing link to new HW 13G_4+0_28M_256QAM_CA&EPLA. Site Impacted : 4334A & 4335A. FE_4331A 1.Install new 13G_1.8M(MDD) x1. 2.Install new 1xRTN910A(RTN05). Configure it. 3.Insert new 1xISM8 into slot 03 of RTN910A(RTN05). 4.Install new 1x XMC_5D, Sub B_Lo. Configure it. 5.Configure DCN Inband. 6.Reuse existing port that belong to SM MW Link 4334A-4331A MW4 at IBeam and patching at port 8-EM6-1 of RTN910A(RTN05). 7.Decom existing SM MW link 4334A-4331A MW4. | XMC_5D | MDD | 13G | 13G_1.8M(MDD) x1. | 13G_1.8M(MDD) x1. | Magicell | SQ202506050553-Magicell | Magicell | SQ202504260072-Magicell // SQ202504260076-Magicell // SQ202505230422-Magicell | 2025-12-09 | 2025-12-02 | Completed | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-25 | 2025-09-01 | 2025-08-25 | 2025-08-25 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041377 |  | 2025-04-14 | 2025-04-15 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-21 | 2025-04-21 | 2025-04-20 | 2025-05-05 | Azam/Azri/Roslan/7018000276 | Magicell TI | 2025-04-21 | 2025-04-21 | 2025-04-20 | 2025-07-06 | Azam/Azri/Roslan/7018000276 | Magicell TI | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-04-21 | 2025-04-21 | 2025-04-20 | 2025-08-19 | Azam/Azri/Roslan/7018000276 | 2025-03-19: 2025-04-21; 2025-03-19: 2025-04-21; 2025-03-19: 2025-04-20; 2025-03-21: 2025-04-21 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202509250697-GTSB | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | AB.RAHMAN//BIN MAT NOOH/6237001519
4969A_HU | Sungai Kob | DU00005172945 | Northern | Kedah | 5.429180 | 100.644020 |  |  |  |  | Integrated/RFS | ZTE |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M NE_4969A. 15G_DP_1.2M(MS) x1. ISM8 x1. XMC_3E , Sub B_Lo x1. FE_4968A 15G_DP_1.2M(MS) x1. ISM8 x1. XMC_3E , Sub B_Hi x1. | MW Parallel Link | Existing link 13G_2+0_28M & 15G_2+0_28M with EPLA. Install parallel link 15G_2+0_28M with EPLA to existing 13G_2+0_28M and 15G_2+0_28M.. Site Impacted : 3508A. NE_4969A. 1.Install new 15G_DP_1.2M(MS). 2.Reuse existing 4969A_RTN02. 3.Install new 6_ISM8-2+0 into existing 4969A_RTN02. 4.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect and EPLA with existing MW links. 6.No decomm existing link. FE_4968A 1.Install new 15G_DP_1.2M(MS). 2.Reuse existing 4968A_RTN03. 3.Install new 4_ISM8-2+0 into existing 4968A_RTN03. 4.Install new XMC_3E , Sub B_Hi. 5.Create service cross connect and EPLA with existing MW link. 6.No decomm existing MW link. | Existing link 13G_2+0_28M & 15G_2+0_28M with EPLA. Install parallel link 15G_2+0_28M with EPLA to existing 13G_2+0_28M and 15G_2+0_28M.. Site Impacted : 3508A. NE_4969A. 1.Install new 15G_DP_1.2M(MS). 2.Reuse existing 4969A_RTN02. 3.Install new 6_ISM8-2+0 into existing 4969A_RTN02. 4.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect and EPLA with existing MW links. 6.No decomm existing link. | Existing link 13G_2+0_28M & 15G_2+0_28M with EPLA. Install parallel link 15G_2+0_28M with EPLA to existing 13G_2+0_28M and 15G_2+0_28M.. Site Impacted : 3508A. FE_4968A 1.Install new 15G_DP_1.2M(MS). 2.Reuse existing 4968A_RTN03. 3.Install new 4_ISM8-2+0 into existing 4968A_RTN03. 4.Install new XMC_3E , Sub B_Hi. 5.Create service cross connect and EPLA with existing MW link. 6.No decomm existing MW link. | XMC_5D | MDD | 15G | 1.2 | 1.2 | GCI | SQ202506180103-GCI | GCI | SQ202504260066-GCI // SQ202504260070-GCI // SQ202506240302-GCI | 2025-08-09 | 2025-08-12 | Completed | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-08 | 2025-08-09 | 2025-08-08 | 2025-08-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041374 |  | 2025-04-14 | 2025-04-15 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-13 | 2025-05-31 | 2025-05-13 | 2025-05-24 | IBRAHIM BIN ABU BAKAR6000019123 | GCI TI | 2025-05-13 | 2025-05-31 | 2025-05-13 | 2025-07-06 | IBRAHIM BIN ABU BAKAR6000019123 | GCI TI | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-05-28 | 2025-05-13 | 2025-05-31 | 2025-05-13 | 2026-02-09 | IBRAHIM BIN ABU BAKAR6000019123 | 2025-03-19: 2025-05-13; 2025-03-19: 2025-05-31; 2025-03-19: 2025-05-13; 2025-03-21: 2025-05-16 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | CHEONG/SENG/WAH/7018000306
4945A_HU | Kg Pokok Assam(ZED) | DU00005172946 | Northern | Kedah | 5.584751 | 100.468916 | [7 empty] | 00. Site Out/Drop |  |  |  | 13G_6+0_28M NE_4945A 13G_DP_1.2M(MDD) x2. RTN 910A x1 ISM8 x2. XMC_5D , Sub B_Hi x1. XMC_5D , Sub A_Hi x1. FE_4273A. 13G_DP_1.2M(MDD) x2. RTN910A x1. ISM8 x2. XMC_5D , Sub B_Lo x1. XMC_5D , Sub A_Lo x1. | Cancel / Drop | Solution same under TX Rollout (4945A & 4945A_Additional) DU Code : DU00005565097 & DU00002752147 ). |  |  | XMC_5D | MDD | 13G | 1.2 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4537D_HU | Kg Teluk Jamat | DU00005172947 | Northern | Kedah | 6.135998 | 100.453076 | [7 empty] | 00. Integrated/RFS Done | 21/05: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_28M_EPLA NE_4537D 15G_DP_0.6M(MAC)+OMT x1. 1xRTN910A. XMC_3, Sub A & B_Hi x2. FE_4678A 15G_DP_1.2M(MAC)+OMT x1. 1xRTN910A. XMC_3, Sub A & B_Lo x2. | MW Swap | Link Existing SM 15G_1+0_28M Swap existing link to new HW 15G_2+0_28M_512QAM_EPLA Site Impacted : 4537D NE_4537D 1.Install new 15G_DP_0.6M(MAC)+OMT. 2.Install new 1xRTN910A(RTN02). Configure it. 3.Install new 2x XMC_3 , Sub A & B_Hi. Configure it. 4.Configure DCN Inband. 5.Request new port at IBeam from ZTE IPRAN team. 6.Migrate traffic to new link in which BBU will patching to port 8-EM6-1. 7.Decom existing MW link 4537D(RTN01)-4678A(RTN12). May decom IDU,ODU & Ant. FE_4678A 1.Install new 15G_DP_1.2M(MAC)+OMT. 2.Install new 1xRTN910A(RTN09). Configure it. 3.Install new 2x XMC_3 , Sub A & B_Lo. Configure it. 4.Configure DCN Inband. 5.Request new port at IBeam and request from ZTE IPRAN team. 6.Migrate traffic to new link. 7.Decom existing MW link 4537D(RTN01)-4678A(RTN12). May decom ODU & Ant ONLY and do not decom existing IDU(RTN12) as it shared with MW Link 3153B_9(RTN01)-4678A(RTN12). | Link Existing SM 15G_1+0_28M Swap existing link to new HW 15G_2+0_28M_512QAM_EPLA Site Impacted : 4537D NE_4537D 1.Install new 15G_DP_0.6M(MAC)+OMT. 2.Install new 1xRTN910A(RTN02). Configure it. 3.Install new 2x XMC_3 , Sub A & B_Hi. Configure it. 4.Configure DCN Inband. 5.Request new port at IBeam from ZTE IPRAN team. 6.Migrate traffic to new link in which BBU will patching to port 8-EM6-1. 7.Decom existing MW link 4537D(RTN01)-4678A(RTN12). May decom IDU,ODU & Ant. | Link Existing SM 15G_1+0_28M Swap existing link to new HW 15G_2+0_28M_512QAM_EPLA Site Impacted : 4537D FE_4678A 1.Install new 15G_DP_1.2M(MAC)+OMT. 2.Install new 1xRTN910A(RTN09). Configure it. 3.Install new 2x XMC_3 , Sub A & B_Lo. Configure it. 4.Configure DCN Inband. 5.Request new port at IBeam from ZTE IPRAN team. 6.Migrate traffic to new link. 7.Decom existing MW link 4537D(RTN01)-4678A(RTN12). May decom ODU & Ant ONLY and do not decom existing IDU(RTN12) as it shared with MW Link 3153B_9(RTN01)-4678A(RTN12). | XMC_3 | MAC | 15G | 15G_DP_0.6M(MAC)+OMT x1. | 15G_DP_1.2M(MAC)+OMT x1. | GCI | SQ202504280464-GCI | GCI | SQ202505240106-GCI // SQ202505240107-GCI // SQ202508140739-GCI | 2025-11-26 | 2025-11-20 | Completed | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-19 | 2025-11-26 | 2025-11-19 | 2025-11-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051483 |  | 2025-05-15 | 2025-05-16 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-21 | 2025-05-31 | 2025-05-21 | 2025-05-24 | MOHD SHAHRAIN/BIN/MOHD SHKERY/6000002587 | GCI TI | 2025-05-21 | 2025-05-31 | 2025-05-21 | 2025-06-28 | MOHD SHAHRAIN/BIN/MOHD SHKERY/6000002587 | GCI TI | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-01 | 2025-05-21 | 2025-05-31 | 2025-05-21 | 2025-07-07 | MOHD SHAHRAIN/BIN/MOHD SHKERY/6000002587 | 2025-05-21 | 2025-05-31 | 2025-05-21 | 2025-05-22 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | NG HONG JIE7018000036 | Logistic Team | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB
K00806_HU | K002A_K00806OD_T3_KG_DALAM_WANG | DU00005172948 | Northern | Kedah | 5.699826 | 100.887396 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_56M NE_K00806 New 18G_DP_1.2M(MAC)+OMT x1. New RTN910A x1. New XMC_3, Sub A&B_Hi x2. FE_K00023 New 18G_DP_1.2M(MAC)+OMT x1. New RTN910A x1. New XMC_3, Sub A&B_Lo x2. | MW Parallel Link | Link Existing SM 18G_1+0_56M. Adding new HW MW Parallel Link 18G_2+0_56M_512QAM_EPLA. Site Impacted : K00806 & K00966. NE_K00806 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910A. Configure it. 3.Install new XMC_3, Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A. 6.Migrate traffic to new link in which BBU K00806 will be patching to port 8-EM6-1 of RTN910A. Configure it. 7.Do not decom existing SM MW link K00806-K00023(Link ID NT04636) as it will carry EB Redtone(K00966). FE_K00023 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910A. Configure it. 3.Install new XMC_3, Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A and patching to existing SM MW Link K00023-K00185(Link ID NT05336) and enable LAN port 1 . Configure it. 6.Do not decom existing SM MW link K00806-K00023(Link ID NT04636) as it will carry EB Redtone(K00966). | Link Existing SM 18G_1+0_56M. Adding new HW MW Parallel Link 18G_2+0_56M_512QAM_EPLA. Site Impacted : K00806 & K00966. NE_K00806 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910A. Configure it. 3.Install new XMC_3, Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A. 6.Migrate traffic to new link in which BBU K00806 will be patching to port 8-EM6-1 of RTN910A. Configure it. 7.Do not decom existing SM MW link K00806-K00023(Link ID NT04636) as it will carry EB Redtone(K00966). | Link Existing SM 18G_1+0_56M. Adding new HW MW Parallel Link 18G_2+0_56M_512QAM_EPLA. Site Impacted : K00806 & K00966. FE_K00023 1.Install new 18G_DP_1.2M(MAC)+OMT x1. 2.Install new RTN910A. Configure it. 3.Install new XMC_3, Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A and patching to existing SM MW Link K00023-K00185(Link ID NT05336) and enable LAN port 1 . Configure it. 6.Do not decom existing SM MW link K00806-K00023(Link ID NT04636) as it will carry EB Redtone(K00966). | XMC_3 | MAC | 18G | 18G_DP_1.2M(MAC)+OMT x1. | 18G_DP_1.2M(MAC)+OMT x1. | CCSMY | SQ202504210258-CCS | CCSMY | SQ202504210107-CCS // SQ202504210102-CCS // SQ202504260175-CCS |  |  | Ongoing | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25032115 |  | 2025-03-22 | 2025-04-08 | Completed | 2025-03-21 | 2025-03-22 | 2025-03-21 | 2025-04-08 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-18 | 2025-04-26 | 2025-04-18 | 2025-05-07 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2025-04-18 | 2025-04-26 | 2025-04-18 | 2025-05-30 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2025-04-19 | 2025-04-19 | 2025-04-19 | 2025-04-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-19 | 2025-04-18 | 2025-04-26 | 2025-04-18 | 2025-06-11 | Arif//Afif Bin Mohd Zabidi/7021000041 | 2025-03-19: 2025-04-18; 2025-03-19: 2025-04-26; 2025-03-19: 2025-04-18; 2025-03-21: 2025-04-18 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 |  | Assign Subcon
2476A_HU | Sg Serai (Maxis) | DU00005172949 | Central | Selangor | 3.284510 | 101.549880 | WK12 | MAR 25 | WK12 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 19/3/2025 : Cutover done 17/3/2025 : Installation complete, alignment WIP 12/3/2025 : MAXIS - 45M 3 Legged Tower - NE site 2476A Sg Serai (Maxis), Digi OB - 60M 4 Legged Tower - FE site 1412A Bkt Tadun | TSS+AA+TI | L1+ATP+PAC | 2X 10G SFP 2X ISM8 CARD 1X RTN910 1X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Parallel Link | MW PARALLEL LINK 2476A-1412A WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_128QAM_1352MBPS_XMC3E_SUB A & B_3.33KM_EPLA WITH EXISTING 15G 4+0 LINK NE TRANSFER EXISTING 18G 2+0 IF CABLE TO NEW IDU AND CREATE EPLA WITH NEW LINK IMPACTED: 2476A, 3256A, 3403C, 3688C | 1. INSTALL NEW IDU RTN910A AND INSTALL 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM 5. TRANSFER EXISTING 15G 4+0 IF CABLE TO NEW IDU SLOT 3 & 4 AND CREATE EPLA WITH NEW LINK 6. INSTALL 10G SFP AT PORT RTN04 AND NEW IDU | 1. REUSE EXISTING RTN910 SLOT 7 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM AND EPLA WITH EXISTING LINK | XMC3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202503270731-GCI | GCI | SQ202503200144-GCI // SQ202503200149-GCI // SQ202504150088-GCI | 2025-04-16 | 2025-04-15 | Completed | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-07 | 2025-04-08 | 2025-04-07 | 2025-04-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-15 | 2025-04-16 | 2025-04-15 | 2025-04-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031161 |  | 2025-03-12 | 2025-03-12 | Completed | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-12 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-17 | 2025-03-24 | 2025-03-16 | 2025-03-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-17 | 2025-03-24 | 2025-03-16 | 2025-03-25 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-17 | 2025-03-17 | 2025-03-24 | 2025-03-16 | 2025-03-18 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-17 | 2025-03-24 | 2025-03-16 | 2025-03-17 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
4696A_HU | Jenun(ZED) | DU00005172950 | Northern | Kedah | 5.907531 | 100.474741 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M_512QAM_EPLA NE_4696A New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-27926). Re-use existing ISM8 Slot 07. New XMC_5D Pro, Sub B_Lo x1. FE_4771A New 15G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN05, NEID 9-41688). Re-use existing ISM8 Slot 07. New XMC_5D Pro, Sub B_Hi x1. | MW Parallel Link | Existing HW MW Link 4696A-4771A, 13G_4+0_28MHZ_256QAM_CA. Build new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4696A-4771A, 13G_4+0_28MHZ_256QAM_CA and new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. Site Impacted : 4696A. NE_4696A 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-27926) and re-use existing ISM8 Slot 07 Port 1 & 2. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Re-use existing xD Vlan DCN & Vlan services. 5.Later, combine existing HW MW Link 4696A-4771A, 13G_4+0_28MHZ_256QAM_CA and new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. FE_4771A 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN05, NEID 9-41688) and re-use existing ISM8 Slot 07 Port 1 & 2. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Re-use existing port at IBeam. 5.Later, combine existing HW MW Link 4696A-4771A, 13G_4+0_28MHZ_256QAM_CA and new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. | Existing HW MW Link 4696A-4771A, 13G_4+0_28MHZ_256QAM_CA. Build new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4696A-4771A, 13G_4+0_28MHZ_256QAM_CA and new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. Site Impacted : 4696A. NE_4696A 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-27926) and re-use existing ISM8 Slot 07 Port 1 & 2. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Re-use existing xD Vlan DCN & Vlan services. 5.Later, combine existing HW MW Link 4696A-4771A, 13G_4+0_28MHZ_256QAM_CA and new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. | Existing HW MW Link 4696A-4771A, 13G_4+0_28MHZ_256QAM_CA. Build new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4696A-4771A, 13G_4+0_28MHZ_256QAM_CA and new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. Site Impacted : 4696A. FE_4771A 1.Install new 15G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN05, NEID 9-41688) and re-use existing ISM8 Slot 07 Port 1 & 2. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Re-use existing port at IBeam. 5.Later, combine existing HW MW Link 4696A-4771A, 13G_4+0_28MHZ_256QAM_CA and new HW MW Parallel Link 4696A-4771A, 15G_2+0_28MHZ_512QAM_EPLA. Become 13G&15G_6+0_28MHZ_256QAM&512QAM_EPLA. | XMC-5D Pro | MDD | 15G | 15G_1.2M(MDD) x1 | 15G_1.2M(MDD) x1 | GCI | SQ202601210141-GCI | GCI | SQ202601210098-GCI // SQ202601210138-GCI | 2026-03-17 | 2026-03-10 | Completed | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011447 |  | 2026-01-15 | 2026-01-15 | Completed | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-25 | 2026-01-19 | 2026-01-28 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-01-19 | 2026-01-25 | 2026-01-19 | 2026-01-28 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | AKMAL//BIN RAZALI/6794000078 |  |  | 2026-01-19 | 2026-01-25 | 2026-01-19 | 2026-01-28 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2025-03-19: 2026-01-19; 2025-03-19: 2026-01-25; 2025-03-19: 2026-01-19; 2025-03-21: 2026-01-19 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202601070337-GTSB
4947B_HU | Kg TokSenik | DU00005172951 | Northern | Kedah | 6.329706 | 99.771369 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x2. | IDU-IPRAN | 4947B is Colo site with K00449. Site Impacted : 1568B_11 1. 4947B/K00449 existing IDU direct patching to GE port Gei 0 / 2 / 2. 2. (To Cater link 4741A_RTN02 to 4741A_RTN01 with Phy LAG port). |  | 4947B is colo site with K00449. Site Impacted : 1568B_11 1. 4947B/K00449 existing IDU direct patching to GE port Gei 0 / 2 / 2. 2. (To Cater link 4741A_RTN02 to 4741A_RTN01 with Phy LAG port). | [5 empty] | GCI | SQ202504280464-GCI | GCI | SQ202504260070-GCI | 2025-10-25 | 2025-10-24 | Completed | 2025-05-02 | 2025-05-02 | 2025-05-02 | 2025-05-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-02 | 2025-05-02 | 2025-05-02 | 2025-05-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-25 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041643 |  | 2025-04-17 | 2025-04-19 | Completed | 2025-04-16 | 2025-04-17 | 2025-04-16 | 2025-04-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-28 | 2025-05-09 | 2025-04-28 | 2025-05-02 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-04-28 | 2025-05-09 | 2025-04-28 | 2025-05-06 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-04-30 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-30 | 2025-04-28 | 2025-05-09 | 2025-04-28 | 2025-05-04 | ANAS FIKRI ADHA BIN RAZMI6000009598 | 2025-03-19: 2025-04-28; 2025-03-19: 2025-05-09; 2025-03-19: 2025-04-28; 2025-03-21: 2025-05-03 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI
K00556_HU | K012A_K00556OD_KGTUPAI | DU00005172952 | Northern | Kedah | 5.765482 | 100.712971 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Link ID NT05533 no traffic anymore. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1102B_AD | Jalan Parlimen | DU00005172953 | Central | Kuala Lumpur | 3.147177 | 101.681455 | WK12 | MAR 25 | WK12 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 20/3/2025 : Cutover done 19/3/2025 : EDGEPOINT INFRA - 30M Lampole - NE site 1102B Jalan Parlimen, SKYLINE TECHNOLOGY - 18M Lampole - FE site 1391C Jalan Duta (REL) | TSS+TI | L1+ATP+PAC | LAN/Fiber Cable | BBU Patching | At NE BBU Patching 1102B to Digi MW 1102B-1391C (Reuse Existing link No Traffic). Tx Route : 1102B-1391C-1058B/W00138 | [7 empty] | GTSB | SQ202504170454-GTSB | GTSB | SQ202503240700-GTSB // SQ202504260131-GTSB | 2025-05-09 | 2025-05-09 | Completed | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-04-22 | 2025-05-06 | 2025-04-22 | 2025-04-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031194 |  | 2025-03-12 | 2025-03-24 | Completed | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-24 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-24 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-24 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-20 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  | 2025-03-20 | 2025-03-19 | 2025-03-31 | 2025-03-19 | 2025-03-20 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2025-03-19: 2025-03-19; 2025-03-19: 2025-03-31; 2025-03-19: 2025-03-19; 2025-03-21: 2025-03-20 |  |  | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202505070162-GTSB
3265A_HU | VLSGBURUNG | DU00005172954 | Central | Selangor | 3.466670 | 101.133320 | WK15 | APR 25 | WK15 | APR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 10/4/2025 : Cutover done 8/4/2025 : Installation complete, pending alignment 7/4/2025 : NE installation complete, pending install FE site 19/3/2025 : CELCOM (M) Rainbow - 30M Monopole - NE site 3265A VLSGBURUNG, Digi OB - 60M 4 Legged Tower - FE site 1154A Sekinchan | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 2X 15G 1.2M MCC ANTENNA 1x ODU 15G XMC5D SUB A HI 1X ODU 15G XMC5D SUB A LO | MW Parallel Link | MW PARALLEL LINK 3265A-1154A WITH HUAWEI_15G_2+0_1.2M/1.2M_MS/MAC_28MHZ_512QAM_448MBPS_XMC3_SUB A_3.76KM_EPLA WITH EXISTING 2+0 IMPACTED: 3265A | 1. INSTALL NEW ISM8 CARD AT SLOT 3 EXISTING IDU 2. INSTALL NEW ODU 15G XMC3 28MHZ SUB A 3. INSTALL NEW 15G 1.2M MS ANTENNA 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM EPLA WITH EXISTING LINK | 1. INSTALL NEW ISM8 CARD AT SLOT 3 EXISTING IDU 2. INSTALL NEW ODU 15G XMC3 28MHZ SUB A 3. INSTALL NEW 15G 1.2M MAC ANTENNA 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM EPLA WITH EXISTING LINK | XMC3 | MS/MAC | 15G | 1.2 | 1.2 | GCI | SQ202504170453-GCI | GCI | SQ202504210061-GCI // SQ202504210069-GCI // SQ202505150098-GCI | 2025-05-14 | 2025-05-15 | Completed | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032079 |  | 2025-03-21 | 2025-03-27 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-07 | 2025-04-14 | 2025-04-07 | 2025-04-16 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-04-07 | 2025-04-14 | 2025-04-07 | 2025-05-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-04-10 | 2025-04-07 | 2025-04-14 | 2025-04-07 | 2025-05-27 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-19: 2025-04-07; 2025-03-19: 2025-04-14; 2025-03-19: 2025-04-07; 2025-03-21: 2025-04-07 |  |  | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202504140802-GTSB | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | MAZELAN BIN RAMLI6798000096
4410K_HU | K002A_K00168OD_BUKIT9 | DU00005172955 | Northern | Kedah | 5.586150 | 100.680948 |  |  |  |  | TI IN PLAN | ZTE |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M to become 13G_6+0 with DU ID 4410K_HU_1 refer to DU Code (DU00005509289) NE_4410K. 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Hi x1. FE_4986A. 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing link 15G_6+0_28M Install parallel link 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M DU ID 4410K_HU_1 refer to (DU Code DU00005509289). Site Impacted : 4410K , 4635A , 4622C. This parallel link install to support for 4635A - 4410K. NE_4410K. 1.Install new 13G_DP_1.2M(MDD). 3.Install 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install XMC_5D , Sub A_Hi for ant 2 with CA config. 6.Create service cross connect , CA and EPLA for 6+0 link. 7.Enable GE1 , ETH Patching to 2nd new RTN910A_GE1. 8.No decom existing MW link. FE_4986A. 1.Install new 13G_DP_1.2M(MDD). 2.Install 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install XMC_5D , Sub A_Hi for ant 2 with CA config. 4.Create service cross connect , CA and EPLA for 6+0 link. 5.Create New In Band DCN. 6.No decom existing MW link. | Existing link 15G_6+0_28M Install parallel link 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M DU ID 4410K_HU_1 refer to (DU Code DU00005509289). Site Impacted : 4410K , 4635A , 4622C. This parallel link install to support for 4635A - 4410K parallel link. NE_4410K. 1.Install new 13G_DP_1.2M(MDD). 3.Install 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 4.Install XMC_5D , Sub A_Hi for ant 2 with CA config. 6.Create service cross connect , CA and EPLA for 6+0 link. 7.Enable GE1 , ETH Patching to 2nd new RTN910A_GE1. 8.No decom existing MW link. | Existing link 15G_6+0_28M Install parallel link 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M DU ID 4410K_HU_1 refer to (DU Code DU00005509289). Site Impacted : 4410K , 4635A , 4622C. This parallel link install to support for 4635A - 4410K parallel link. FE_4986A. 1.Install new 13G_DP_1.2M(MDD). 2.Install 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install XMC_5D , Sub A_Hi for ant 2 with CA config. 4.Create service cross connect , CA and EPLA for 6+0 link. 5.Create New In Band DCN. 6.No decom existing MW link. | XMC_5D | MDD | 13G | 1.2 | 1.2 | CCSMY | SQ202504280454-CCS | CCSMY | SQ202505240083-CCS // SQ202505240104-CCS | 2025-07-18 | 2025-07-21 | Completed | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-24 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-21 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051475 |  | 2025-05-15 | 2025-05-19 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-05-31 | 2025-05-28 | 2025-06-04 | IMRAN//JAVED/7021000061 | CCS TI | 2025-05-28 | 2025-05-31 | 2025-05-28 | 2025-06-04 | IMRAN//JAVED/7021000061 | CCS TI | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-28 | 2025-05-31 | 2025-05-28 | 2025-06-11 | IMRAN//JAVED/7021000061 | 2025-03-19: 2025-05-28; 2025-03-19: 2025-05-31; 2025-03-19: 2025-05-28; 2025-03-21: 2025-05-28 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505070152-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | CHEONG/SENG/WAH/7018000306
R00023_HU | R001B_R00023OD_KUALAPERLIS | DU00005172956 | Northern | Perlis | 6.383942 | 100.152053 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Need to Cancel/Drop due to utilization only 58%. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
3778A_HU | Jalan Tebuk Sri Makmur | DU00005172957 | Central | Selangor | 3.632969 | 101.042631 | WK15 | APR 25 | WK15 | APR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 8/4/2025 : Cutover done 25/3/2025 : Plan install ISM8 at NE and FE site - CRQ approved, cancel proceed spillover tomorrow 19/3/2025 : SBC KJS - Tower - NE site 3778A Jalan Tebuk Sri Makmur, Digi OB - 45M 3 Legged Tower - FE site 1157A Sg. Nibong | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X ISM8 CARD 1x ODU 15G XMC5D SUB B HI 1X ODU 15G XMC5D SUB B LO | MW Hardware Upgrade | MW HARDWARE UPGRADE LINK 3778A-1157A WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB A & B_3.76KM EXISTING SLOT 4 HAVE PROBLEM IMPACTED: 3778A | 1. REUSE EXISTING RTN910 2. CHECK IF CABLE FOR SLOT 4 3. INSTALL NEW CARD ISM8 AT SLOT 4 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA | 1. REUSE EXISTING RTN910 2. CHECK IF CABLE FOR SLOT 4 3. INSTALL NEW CARD ISM8 AT SLOT 4 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA | 5D | MDD | 15G | 0.6 | 1.2 | GTSB | SQ202504170454-GTSB | GTSB | SQ202504210072-GTSB // SQ202504210076-GTSB // SQ202504260131-GTSB | 2025-05-14 | 2025-05-15 | Completed | 2025-04-28 | 2025-05-12 | 2025-04-28 | 2025-04-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-04-28 | 2025-05-12 | 2025-04-28 | 2025-04-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031195 |  | 2025-03-12 | 2025-03-17 | Completed | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-08 | 2025-04-30 | 2025-04-08 | 2025-06-08 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-04-08 | 2025-04-30 | 2025-04-08 | 2025-05-06 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-08 | 2025-04-08 | 2025-04-30 | 2025-04-08 | 2025-04-16 | Aminuddin bin che azibA0563734967123169280 | 2025-04-08 | 2025-04-30 | 2025-04-08 | 2025-04-08 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202506050715-GTSB
K00704_HU | K005D_K00704OD_TMNSRIBAYU | DU00005172958 | Northern | Kedah | 5.718150 | 100.545988 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M NE_K00704 New 18G_0.6M(MDD) x1. New RTN910A x1. New XMC_5D, Sub A_Hi x1. FE_K00153 New 18G_0.6M(MDD) x1. New RTN910A x1. New XMC_5D, Sub A_Lo x1. | MW Swap | Link Existing SM 18G_1+0_56M. Swap existing link to 18G_2+0_56M_256AM_EPLA. Site Impacted : K00704. NE_K00704 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A. Configure it. 3.Install new XMC_5D, Sub A_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A. 6.Migrate traffic to new link in which BBU K00704 will be patching to port 8-EM6-1 of RTN910A. Configure it. 7.Decom existing SM MW link K00704-K00153, if no other traffic backhauled. FE_K00153 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A. Configure it. 3.Install new XMC_5D, Sub A_Lo. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A and patching to existing port at Cisco/PTN. Configure it. 6.Decom existing SM MW link K00704-K00153, if no other traffic backhauled. | Link Existing SM 18G_1+0_56M. Swap existing link to 18G_2+0_56M_256AM_EPLA. Site Impacted : K00704. NE_K00704 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A. Configure it. 3.Install new XMC_5D, Sub A_Hi. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A. 6.Migrate traffic to new link in which BBU K00704 will be patching to port 8-EM6-1 of RTN910A. Configure it. 7.Decom existing SM MW link K00704-K00153, if no other traffic backhauled. | Link Existing SM 18G_1+0_56M. Swap existing link to 18G_2+0_56M_256AM_EPLA. Site Impacted : K00704. FE_K00153 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A. Configure it. 3.Install new XMC_5D, Sub A_Lo. Configure it. 4.Create new In Band DCN. 5.Enable port 8-EM6-1 of RTN910A and patching to existing port at Cisco/PTN. Configure it. 6.Decom existing SM MW link K00704-K00153, if no other traffic backhauled. | XMC_5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_0.6M(MDD) x1. | Magicell | SQ202505160534-Magicell | Magicell | SQ202505130147-Magicell // SQ202505130151-Magicell // SQ202511030393-Magicell |  |  | Ongoing | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25042916 |  | 2025-05-10 | 2025-05-22 | Completed | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-22 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-22 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | Magicell TI | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-14 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | Magicell TI | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-13 | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-22 | MUHAMMAD SAFWAN AZIZI BIN AHMAD ZULFA6000019089 | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-12 | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | NG HONG JIE7018000036 | Logistic Team | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202509250697-GTSB | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | AB.RAHMAN//BIN MAT NOOH/6237001519
4959A_HU | Tunjang | DU00005172959 | Northern | Kedah | 6.283209 | 100.376308 | [6 empty] | ZTE | 00. Integrated/RFS Done | 15/07: CO Done | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M refer to 4959A_HU_1 (DU Code DU00005509294). NE_4959A 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub B_Lo x1. FE_4665A 13G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub B_Hi x1. | MW Parallel Link | Existing link 15G_6+0_28M Install parallel link 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M refer to 4959A_HU_1 (DU Code DU00005509294). Site Impacted : 4959A , 4672B NE_4959A 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install XMC_5D , Sub B_Lo for ant 2 with CA config. 4.Create service cross connect , CA and EPLA for new parallel link 13G_6+0_28M. 5.Enable GE1 , 4959A_BBU traffic migarte to new parallel link. 6.No decom existing 15G_6+0_28M link. FE_4665A 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install XMC_5D , Sub B_Hi for ant 2 with CA config. 4.Create service cross connect , CA and EPLA for new parallel link 13G_6+0_28M. 5.Create new In Band DCN. 6.No decom existing 15G_6+0_28M link. | Existing link 15G_6+0_28M Install parallel link 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M refer to 4959A_HU_1 (DU Code DU00005509294). Site Impacted : 4959A , 4672B NE_4959A 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install XMC_5D , Sub B_Lo for ant 2 with CA config. 4.Create service cross connect , CA and EPLA for new parallel link 13G_6+0_28M. 5.Enable GE1 , 4959A_BBU traffic migarte to new parallel link. 6.No decom existing 15G_6+0_28M link. | Existing link 15G_6+0_28M Install parallel link 13G_4+0_28M to become 13G_6+0_28M with 13G_2+0_28M refer to 4959A_HU_1 (DU Code DU00005509294). Site Impacted : 4959A , 4672B FE_4665A 1.Install new 13G_DP_1.2M(MDD). 2.Install new 3_ISM8-2+0 and 4_ISM8-2+0 with CA config. 3.Install XMC_5D , Sub B_Hi for ant 2 with CA config. 4.Create service cross connect , CA and EPLA for new parallel link 13G_6+0_28M. 5.Create new In Band DCN. 6.No decom existing 15G_6+0_28M link. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202504280464-GCI | GCI | SQ202505240106-GCI // SQ202505240107-GCI | 2025-12-03 | 2025-12-03 | Completed | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051480 |  | 2025-05-15 | 2025-05-16 | Completed | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-27 | 2025-05-31 | 2025-05-27 | 2025-07-21 | MUHAMMAD IRFAN BIN SAHARRIZA6800000201 | GCI TI | 2025-05-27 | 2025-05-31 | 2025-05-27 | 2025-07-21 | MUHAMMAD IRFAN BIN SAHARRIZA6800000201 | GCI TI | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-15 | 2025-05-27 | 2025-05-31 | 2025-05-27 | 2026-04-01 | MUHAMMAD IRFAN BIN SAHARRIZA6800000201 | 2025-05-10: 2025-05-27; 2025-05-10: 2025-05-31; 2025-05-10: 2025-05-27; 2025-05-12: 2025-07-15 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505070152-GCI | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | CHEONG/SENG/WAH/7018000306
4281B_HU | Felcra Weng | DU00005172960 | Northern | Kedah | 5.836610 | 100.902290 |  |  |  |  | Integrated/RFS Done |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G_2+0_28M NE_4281B 13G_DP_1.2M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Hi x1. FE_4959B 13G_DP_1.2M(MDD) x1. RTN910 x1. ISM8 x1. XMC_5D , Sub A_Lo x1. | MW Parallel Link | Existing link 13G_2+0_28M Install parallel link 13G_2+0_28M with EPLA to the current 2+0 link. Site Impacted : 4281B. NE_4281B 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4281B_RTN02 3.Install new 4_ISM8-2+0 with EPLA to the cusrrent 2+0 link. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA to the current 2+0 link. 6.No decom existing MW link. FE_4959B 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910 , 7_ISM8-2+0.(RTN no. provide by MSP team). 3.Install new 3_ISM8-2+0 into new RTN910. 4.Existing (3_ISM8-2+0) IF cable tranfer to new 3_ISM8-2+0 RTN910. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA to the current 2+0 link. 6.Enable GE1 , ETH cable patching to exiting_4959B_RTN03 (GE2). 7.Decom existing 3_ISM8 board only. | Existing link 13G_2+0_28M Install parallel link 13G_2+0_28M with EPLA to the current 2+0 link. Site Impacted : 4281B. NE_4281B 1.Install new 13G_DP_1.2M(MDD). 2.Reuse existing 4281B_RTN02 3.Install new 4_ISM8-2+0 with EPLA to the cusrrent 2+0 link. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA to the current 2+0 link. 6.No decom existing MW link. | Existing link 13G_2+0_28M Install parallel link 13G_2+0_28M with EPLA to the current 2+0 link. Site Impacted : 4281B. FE_4959B 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910 , 7_ISM8-2+0.(RTN no. provide by MSP team). 3.Install new 3_ISM8-2+0 into new RTN910. 4.Existing (3_ISM8-2+0) IF cable tranfer to new 3_ISM8-2+0 RTN910. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA to the current 2+0 link. 6.Enable GE1 , ETH cable patching to exiting_4959B_RTN03 (GE2). 7.Decom existing 3_ISM8 board only. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GTSB | SQ202504170477-GTSB | GTSB | SQ202504210127-GTSB // SQ202504210133-GTSB // SQ202504260178-GTSB | 2025-12-17 | 2025-12-16 | Completed | 2025-03-19 | 2025-03-21 | 2025-04-10 | 2025-04-10 | BARANEEDARAN//A/L SELVADASS SEBASTIN/6799000111 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-29 | 2025-05-10 | 2025-04-29 | 2025-08-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032063 |  | 2025-03-21 | 2025-03-25 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-10-09 | ALI RAZA AKBAR ALI6799000298 | GTSB TI | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-06-13 | ALI RAZA AKBAR ALI6799000298 | GTSB TI | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-11 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-04-19 | ALI RAZA AKBAR ALI6799000298 | 2025-05-10: 2025-03-24; 2025-05-10: 2025-03-24; 2025-05-10: 2025-03-24; 2025-05-12: 2025-04-12 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300164-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
4967A_HU | Karangan(Mxs) | DU00005172961 | Northern | Kedah | 5.422820 | 100.663550 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M with CA. NE_4967A. ISM8 x1. FE_4685B ISM8 x1. | MW Hardware Upgrade | Existing link 13G_4+0_28M. Hardware upgrade to 13G_4+0_28M with CA. Current RSL is acceptable -31/-32 dbm. Site Impacted : 4967A. NE_4967A. 1.Reuse existing 13G_DP_1.8M(MDD). 2.Reuse existing 4967A_RTN01. 3.Install new 4_ISM8 into existing 4967A_RTN01. 4.Reuse existing XMC_5D-2+0 , upgrade to XMC_5D-4+0 via CA config. 5.Transfer existing 2nd IF cable from 3_ISM8 to new 4_ISM8 in order to convert existing 2+0 to 4+0_CA. 6.Create service cross connect , CA and EPLA new 4+0_CA link and existing 2+0 link. 7.No decom existing MW link. FE_4685B 1.Reuse existing 13G_DP_1.8M(MDD). 2.Reuse existing 4685B_RTN02. 3.Install new 4_ISM8 into existing 4685B_RTN02. 4.Reuse existing XMC_5D-2+0 , upgrade to XMC_5D-4+0 via CA config. 5.Transfer existing 2nd IF cable from 3_ISM8 to new 4_ISM8 in order to convert existing 2+0 to 4+0_CA. 6.Create service cross connect , CA and EPLA new 4+0_CA link and existing 2+0 link. 7.No decom existing MW link. | Existing link 13G_4+0_28M. Hardware upgrade to 13G_4+0_28M with CA. Current RSL is acceptable -31/-32 dbm. Site Impacted : 4967A. NE_4967A. 1.Reuse existing 13G_DP_1.8M(MDD). 2.Reuse existing 4967A_RTN01. 3.Install new 4_ISM8 into existing 4967A_RTN01. 4.Reuse existing XMC_5D-2+0 , upgrade to XMC_5D-4+0 via CA config. 5.Transfer existing 2nd IF cable from 3_ISM8 to new 4_ISM8 in order to convert existing 2+0 to 4+0_CA. 6.Create service cross connect , CA and EPLA new 4+0_CA link and existing 2+0 link. 7.No decom existing MW link. | Existing link 13G_4+0_28M. Hardware upgrade to 13G_4+0_28M with CA. Current RSL is acceptable -31/-32 dbm. Site Impacted : 4967A. FE_4685B 1.Reuse existing 13G_DP_1.8M(MDD). 2.Reuse existing 4685B_RTN02. 3.Install new 4_ISM8 into existing 4685B_RTN02. 4.Reuse existing XMC_5D-2+0 , upgrade to XMC_5D-4+0 via CA config. 5.Transfer existing 2nd IF cable from 3_ISM8 to new 4_ISM8 in order to convert existing 2+0 to 4+0_CA. 6.Create service cross connect , CA and EPLA new 4+0_CA link and existing 2+0 link. 7.No decom existing MW link. | XMC_5D | MDD | 13G | 1.8 | 1.8 | GCI | SQ202505240071-GCI | GCI | SQ202504230248-GCI // SQ202504230250-GCI // SQ202505150106-GCI | 2025-10-30 | 2025-10-29 | Completed | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-30 | 2025-10-29 | 2025-10-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032033 |  | 2025-03-21 | 2025-03-21 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-28 | 2025-03-31 | 2025-03-28 | 2025-04-09 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | GCI TI | 2025-03-28 | 2025-03-31 | 2025-03-28 | 2025-07-06 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | GCI TI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-27 | 2025-03-28 | 2025-03-31 | 2025-03-28 | 2026-02-24 | NOOR SYAHREENA BINTI MD NOR HAMKA6800000196 | 2025-05-10: 2025-03-28; 2025-05-10: 2025-03-31; 2025-05-10: 2025-03-28; 2025-05-12: 2025-03-29 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | EZRIN TASNIM BIN ABDUL GANI6798000128
9124B_AD | ParadiseGarden | DU00006806852 | Sarawak | Sarawak | 1.439400 | 110.329700 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01295_AD | Q135A_Q01295OD_TMNCINMUK | DU00006806853 | Sarawak | Sarawak | 1.423280 | 110.343800 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9188A_AD | Pusa(Celcom) | DU00006806854 | Sarawak | Sarawak | 1.626610 | 111.292255 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7484B_AD | Kg Sungai Rotan | DU00006806855 | Sabah | Sabah | 5.614280 | 117.858900 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1411H_LOS | 99 SpeedmartBDR PARKLANDS 1 | DU00006806856 | Central | Selangor | 2.972516 | 101.461195 | [21 empty] | GTSB |  | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7893A_AD | TamanJaya Keningau | DU00006806857 | Sabah | Sabah | 5.346119 | 116.169298 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2531A_IPR | Puas PuncakAlam 2A | DU00006806858 | Central | Selangor | 3.243331 | 101.424817 | [9 empty] | TSS+AA+TI |  | 10G SFP Module x1 Fiber Patch Cord x 1 pairs. | BBU Patching | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) Impact site: 2531A | Change patching BBU to PTN from 1G to 10G port (ops team and swap room to assign PTN and BBU port) Impact site: 2531A | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050711 |  | 2026-05-08 |  | Ongoing | 2026-05-07 | 2026-05-08 | 2026-05-07 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [42 empty] | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | CHEONG/SENG/WAH/7018000306
4185B_AD | NorthAvenue | DU00006810917 | Northern | Penang | 5.424903 | 100.325340 | [21 empty] | GTSB |  | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4810A_AD | Eastern&OrientalHotel | DU00006810918 | Northern | Penang | 5.423317 | 100.335815 | [21 empty] | GTSB |  | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2069B_AD | WT_UITMPNCKALAM | DU00005945490 | Central | Selangor | 3.204196 | 101.453258 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | Install new link 18G_2+0_112M. NE_2069B 18G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. FE_2648B. 18G_DP_0.6(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo 2. | MW New Link / Reroute | New link install to the new FE 2648B to enable a potential upstream link upgrade, providing support for the 1220D sites. (Refer DU ID 1220D_REL). Existing TX route 2069B - 1612B , dis 3.9KM. NEW TX Route : 2069B - 2648B . dis 2.3KM. Install new link 18G_2+0_112M. Site Impacted : 1220D , 1434H , 3447C. NE_2069B 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.( RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.No link to be decom. FE_2648B. 1.Install new 18G_DP_0.6(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.No link to be decom. | New link install to the new FE 2648B to enable a potential upstream link upgrade, providing support for the 1220D sites. (Refer DU ID 1220D_REL). Existing TX route 2069B - 1612B , dis 3.9KM. NEW TX Route : 2069B - 2648B . dis 2.3KM. Install new link 18G_2+0_112M. Site Impacted : 1220D , 1434H , 3447C. NE_2069B 1.Install new 18G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.( RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.No link to be decom. | New link install to the new FE 2648B to enable a potential upstream link upgrade, providing support for the 1220D sites. (Refer DU ID 1220D_REL). Existing TX route 2069B - 1612B , dis 3.9KM. NEW TX Route : 2069B - 2648B . dis 2.3KM. Install new link 18G_2+0_112M. Site Impacted : 1220D , 1434H , 3447C. FE_2648B. 1.Install new 18G_DP_0.6(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Create New In Band DCN. 6.No link to be decom. | XMC_3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202508140178-Magicell | Magicell | SQ202511260090-Magicell // SQ202511260101-Magicell | 2025-10-01 | 2025-09-30 | Completed | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-19 | 2025-09-20 | 2025-09-19 | 2025-09-19 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-10-01 | 2025-09-30 | 2025-09-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251118AP |  | 2025-11-19 | 2025-11-20 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2026-01-07 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2026-03-12 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-07 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2026-03-12 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | 2025-05-10: 2025-12-10; 2025-05-10: 2025-12-10; 2025-05-10: 2025-12-10; 2025-05-12: 2026-03-09 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202508150527-GCI | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | CHEONG/SENG/WAH/7018000306
2043B_AD | Mas Cargo | DU00006476081 | Central | Selangor | 2.733240 | 101.716720 | [7 empty] | 02. Pending Access |  | TSS+AA+TI |  | TX Mini Project, 2043B-B00550, 15G 2+0 CA, 1+0 NCA, ODU XMC-5D 28MHz Sub band A x 2, RTN910A x 2, ISM8 x 2, A15D12MDD-3NX x 1, A15D12MDD-3NX x 1, Ant ht NE/FE: 40m/40m, Each MODU install 2 IF cables | MW Parallel Link | Install MW Parallel Link 15G 1.2DP/1.2DP dish, Direct mount, ODU Sub band A | Install 15G 1.2DP dish, 2+0 CA, 1+0 NCA, NE TX high, ODU XMC-5D Sub band A x 1, IDU RTN910A x 1, ISM8 x 1, Each MODU install 2 IF cables; IDU patching not required; Migration into new link: BBU 1171L | Install 15G 1.2DP dish, 2+0 CA, 1+0 NCA, FE TX low, ODU XMC-5D Sub band A x 1, IDU RTN910A x 1, ISM8 x 1, Each MODU install 2 IF cables; IDU patching to CISCO new port | XMC-5D | 40/40 | 15G | 1.2 | 1.2 | GTSB | SQ202601130167-GTSB | GTSB | SQ202601130155-GTSB // SQ202601130159-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25122618 |  | 2026-01-31 |  | Ongoing | 2025-12-26 | 2026-01-31 | 2025-12-26 |  | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202512290816-GTSB | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-26 | LIM//WEI CHONG/6798000110
4632B_AD | LubukSaga | DU00006615053 | Northern | Kedah | 5.560245 | 100.559285 | [7 empty] | 05. Doable |  | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 2X RTN910A 2X 13G 1.2M MDD ANTENNA 1x ODU 13G XMC5D SUB B HI 1x ODU 13G XMC5D SUB B LO | MW New Link / Reroute | MW NEW LINK REROUTE 4632B-4148A WITH HUAWEI_15G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC5D_SUB_B_WITH_CA_LINK_4.85KM IMPACTED: 4632B DISMANTLE EXISTING LINK 4632B RTN03-4281A RTN06 Reroute site to new CP 4148A to offload existing CP site 4281A | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK 4632B RTN03-4281A RTN06 | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK 4632B RTN03-4281A RTN06 | XMC5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202602230142-GCI | GCI | SQ202602230133-GCI // SQ202602230136-GCI | 2026-03-13 | 2026-03-13 | Completed | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26031336 |  | 2026-03-14 | 2026-03-26 | Completed | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-30 | 2026-04-30 | 2026-03-30 |  | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2026-03-30 | 2026-04-30 | 2026-03-30 |  | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | [7 empty] | 2026-03-30 | 2026-04-30 | 2026-03-30 |  | MUHAMAD ARIFF BIN KHASIM6800000179 | 2025-05-10: 2026-03-30; 2025-05-10: 2026-04-30; 2025-05-10: 2026-03-30; 2025-05-12: 2026-03-30 | [7 empty] | GCI | SQ202602260562-GCI | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
4227C_AD | Kg Tok Dik | DU00006615054 | Northern | Kedah | 5.511864 | 100.540471 | [7 empty] | 04. Pending DO | 16/4: MC | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_110M_256QAM_EPLA. NE_4227C New 18G_0.6M(MAC)+OMT x1. New RTN910AF(RTN04). New ISM8 x2. New IF cables with suitable length and type x2 RUN. New XMC_3E, Sub A_Lo x2. New CAT6 cable x1. FE_4148A/K00224 New 18G_0.6M(MAC)+OMT x1. New RTN910AF(RTN03). New ISM8 x2. New IF cables with suitable length and type x2 RUN. New XMC_3E, Sub A_Hi x2. New SFP Module 10G 10Km 1310nm x1(IDU Huawei) & suitable SFP Module 10G x1(PTN/Cisco). New Optical Patchcord with suitable type and length x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1. PLEASE PERFORM DU AS PER SEQUENCES BELOW. 1ST DU 4227C_AD - 18G_2+0_110MHZ_256QAM_EPLA. 2ND DU 4227C_AD_1 - 23G_2+0_110MHZ_256QAM_EPLA. 2.LATER COMBINE 18G_2+0_110MHZ_256QAM_EPLA & 23G_2+0_110MHZ_256QAM_EPLA, BECOME 18G&23G_4+0_110MHZ_256QAM_EPLA**** Existing 2x HW MW Links as stated below: 1.4227C(RTN03, NEID 9-23782)-4281A(RTN03, NEID 9-23781), 18G_2+0_110MHZ_256QAM_EPLA. 2.4227C(RTN11, NEID 99-12902)-4281A(RTN02, NEID 99-30206), 18G_1+0_110MHZ_512QAM. Install new MW Link/Reroute HW MW Link 4227C-4148A, 18G_2+0_110MHZ_256QAM_EPLA. Later, after DU 4227C_AD & DU 4227C_AD_1 completed, may decom existing 2x HW MW Links 18G_2+0_110MHZ_256QAM_EPLA and 18G_1+0_110MHZ_512QAM. Site Impacted : 4227C & 4007D. NE_4227C 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN04) x1 and insert new x2 ISM8 into slot 03 & 04. 3.Install XMC_3E, Sub A_Lo x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4227C-4148A, 18G_2+0_110MHZ_256QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN04). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN04) to existing BBU(4227C). 8.Request new xC Vlan DCN and Vlan Services. 9.Migrate traffics 4227C(DU 4227C_AD) & 4007D(DU 4227C_AD_1) via new combination HW MW Link 4227C-4148A, 18G&23G_4+0_110/112MHZ_256QAM_EPLA 10.Later, after DU 4227C_AD & DU 4227C_AD_1 completed, may decom existing 2x HW MW Links 18G_2+0_110MHZ_256QAM_EPLA and 18G_1+0_110MHZ_512QAM. - 4227C(RTN03, NEID 9-23782)-4281A(RTN03, NEID 9-23781), 18G_2+0_110MHZ_256QAM_EPLA. - 4227C(RTN11, NEID 99-12902)-4281A(RTN02, NEID 99-30206), 18G_1+0_110MHZ_512QAM. FE_4148A/K00224 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN03) x1 and insert new x2 ISM8 into slot 03 & 04. 3.Install XMC_3E, Sub A_Hi x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4227C-4148A, 18G_2+0_110MHZ_256QAM_EPLA. 6.Insert new SFP Module 10G with 10Km 1310nm x1 into port 8-EM6-3(Optical) of new RTN910AF(RTN03). Enable it. 7.Request new 1x 10G port of PTN/Cisco from ZTE IPRAN Team. 8.Perform patching port 8-EM6-3(Optical) of new RTN910AF(RTN03) to new 1x 10G port of PTN/Cisco(K00224). 9.Request new xC Vlan DCN and Vlan Services. 10.Migrate traffics 4227C & 4007D via new 1x 10G port of PTN/Cisco(K00224). 11.Later, after DU 4227C_AD & DU 4227C_AD_1 completed, may decom existing 2x HW MW Links 18G_2+0_110MHZ_256QAM_EPLA and 18G_1+0_110MHZ_512QAM. - 4227C(RTN03, NEID 9-23782)-4281A(RTN03, NEID 9-23781), 18G_2+0_110MHZ_256QAM_EPLA. - 4227C(RTN11, NEID 99-12902)-4281A(RTN02, NEID 99-30206), 18G_1+0_110MHZ_512QAM. | ****IMPORTANT NOTE: 1. PLEASE PERFORM DU AS PER SEQUENCES BELOW. 1ST DU 4227C_AD - 18G_2+0_110MHZ_256QAM_EPLA. 2ND DU 4227C_AD_1 - 23G_2+0_110MHZ_256QAM_EPLA. 2.LATER COMBINE 18G_2+0_110MHZ_256QAM_EPLA & 23G_2+0_110MHZ_256QAM_EPLA, BECOME 18G&23G_4+0_110MHZ_256QAM_EPLA**** Existing 2x HW MW Links as stated below: 1.4227C(RTN03, NEID 9-23782)-4281A(RTN03, NEID 9-23781), 18G_2+0_110MHZ_256QAM_EPLA. 2.4227C(RTN11, NEID 99-12902)-4281A(RTN02, NEID 99-30206), 18G_1+0_110MHZ_512QAM. Install new MW Link/Reroute HW MW Link 4227C-4148A, 18G_2+0_110MHZ_256QAM_EPLA. Later, after DU 4227C_AD & DU 4227C_AD_1 completed, may decom existing 2x HW MW Links 18G_2+0_110MHZ_256QAM_EPLA and 18G_1+0_110MHZ_512QAM. Site Impacted : 4227C & 4007D. NE_4227C 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN04) x1 and insert new x2 ISM8 into slot 03 & 04. 3.Install XMC_3E, Sub A_Lo x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4227C-4148A, 18G_2+0_110MHZ_256QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN04). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN04) to existing BBU(4227C). 8.Request new xC Vlan DCN and Vlan Services. 9.Migrate traffics 4227C(DU 4227C_AD) & 4007D(DU 4227C_AD_1) via new combination HW MW Link 4227C-4148A, 18G&23G_4+0_110/112MHZ_256QAM_EPLA 10.Later, after DU 4227C_AD & DU 4227C_AD_1 completed, may decom existing 2x HW MW Links 18G_2+0_110MHZ_256QAM_EPLA and 18G_1+0_110MHZ_512QAM. - 4227C(RTN03, NEID 9-23782)-4281A(RTN03, NEID 9-23781), 18G_2+0_110MHZ_256QAM_EPLA. - 4227C(RTN11, NEID 99-12902)-4281A(RTN02, NEID 99-30206), 18G_1+0_110MHZ_512QAM. | ****IMPORTANT NOTE: 1. PLEASE PERFORM DU AS PER SEQUENCES BELOW. 1ST DU 4227C_AD - 18G_2+0_110MHZ_256QAM_EPLA. 2ND DU 4227C_AD_1 - 23G_2+0_110MHZ_256QAM_EPLA. 2.LATER COMBINE 18G_2+0_110MHZ_256QAM_EPLA & 23G_2+0_110MHZ_256QAM_EPLA, BECOME 18G&23G_4+0_110MHZ_256QAM_EPLA**** Existing 2x HW MW Links as stated below: 1.4227C(RTN03, NEID 9-23782)-4281A(RTN03, NEID 9-23781), 18G_2+0_110MHZ_256QAM_EPLA. 2.4227C(RTN11, NEID 99-12902)-4281A(RTN02, NEID 99-30206), 18G_1+0_110MHZ_512QAM. Install new MW Link/Reroute HW MW Link 4227C-4148A, 18G_2+0_110MHZ_256QAM_EPLA. Later, after DU 4227C_AD & DU 4227C_AD_1 completed, may decom existing 2x HW MW Links 18G_2+0_110MHZ_256QAM_EPLA and 18G_1+0_110MHZ_512QAM. Site Impacted : 4227C & 4007D. FE_4148A/K00224 1.Install new 18G_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN03) x1 and insert new x2 ISM8 into slot 03 & 04. 3.Install XMC_3E, Sub A_Hi x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4227C-4148A, 18G_2+0_110MHZ_256QAM_EPLA. 6.Insert new SFP Module 10G with 10Km 1310nm x1 into port 8-EM6-3(Optical) of new RTN910AF(RTN03). Enable it. 7.Request new 1x 10G port of PTN/Cisco from ZTE IPRAN Team. 8.Perform patching port 8-EM6-3(Optical) of new RTN910AF(RTN03) to new 1x 10G port of PTN/Cisco(K00224). 9.Request new xC Vlan DCN and Vlan Services. 10.Migrate traffics 4227C & 4007D via new 1x 10G port of PTN/Cisco(K00224). 11.Later, after DU 4227C_AD & DU 4227C_AD_1 completed, may decom existing 2x HW MW Links 18G_2+0_110MHZ_256QAM_EPLA and 18G_1+0_110MHZ_512QAM. - 4227C(RTN03, NEID 9-23782)-4281A(RTN03, NEID 9-23781), 18G_2+0_110MHZ_256QAM_EPLA. - 4227C(RTN11, NEID 99-12902)-4281A(RTN02, NEID 99-30206), 18G_1+0_110MHZ_512QAM. | XMC_3E | MAC | 18G | 18G_0.6M(MAC)+OMT x1 | 18G_0.6M(MAC)+OMT x1 | GCI | SQ202602250659-GCI | GCI | SQ202602250651-GCI // SQ202602250654-GCI |  |  | Ongoing | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-02-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-06 | 2026-04-13 | 2026-04-06 | 2026-04-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040911 |  | 2026-04-10 | 2026-04-16 | Completed | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-05-02 | 2026-04-23 | 2026-04-23 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-04-23 | 2026-05-02 | 2026-04-23 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-30 | 2026-04-23 | 2026-05-02 | 2026-04-23 |  | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2025-05-10: 2026-04-23; 2025-05-10: 2026-05-02; 2025-05-10: 2026-04-23; 2025-05-12: 2026-04-24 | [7 empty] | GTSB | SQ202602260616-GTSB
4346H_LOS | 99 Speedmart PGTmn Pekaka | DU00006615055 | Northern | Penang | 5.140028 | 100.491111 | [7 empty] | 02. Pending Access |  | TSS+TI+Dismantle |  | NLOS Radio (RTN510). NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | NLOS Link reroute to new FE 3867C due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 4346H NE_4346H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (4346H-NLOS-4176A). FE_A00570/4562K 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new Inband DCN. 5.Traffic migrate to new route FE and with new NLOS radio. 6.ETH cable patching to CP Fiber port. 7.Decom existing NLOS Radio (4346H-NLOS-4176A). | NLOS Link reroute to new FE 3867C due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 4346H NE_4346H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (4346H-NLOS-4176A). | NLOS Link reroute to new FE 3867C due to existing FE being LOS Block. Install new NLOS radio. Site Impacted : 4346H FE_A00570/4562K 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new Inband DCN. 5.Traffic migrate to new route FE and with new NLOS radio. 6.ETH cable patching to CP Fiber port. 7.Decom existing NLOS Radio (4346H-NLOS-4176A). | [5 empty] | GCI | SQ202602230142-GCI | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202602260562-GCI | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | EZRIN TASNIM BIN ABDUL GANI6798000128
4243B_AD | kgSelamat (REL) | DU00006615056 | Northern | Penang | 5.507125 | 100.523581 | [7 empty] | 04. Pending DO | 16/4: MC | TSS+AA+TI+Dismantle |  | 13G_4+0_28M_1024QAM_CA NE_4243B New 13G_1.2M(MDD) x1. New RTN910AF(RTN02). New ISM8 x2. New IF cables with suitable length and type x2 RUN. New XMC_5D Pro, Sub A_Lo x1. New CAT6 cable x1. FE_4148A/K00224 New 13G_1.2M(MDD) x1. New RTN910AF(RTN04). New ISM8 x2. New IF cables with suitable length and type x2 RUN. New XMC_5D Pro, Sub A_Hi x1. New CAT6 cable x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G WITH BW 28MHZ IN ORDER TO ENSURE CHANNEL AVAILABILITY AT CP.**** Existing 2x HW MW Links as stated below: 1.4243B(RTN01, NEID 9-27568)-4281A(RTN02, NEID 9-27567), 23G_1+0_112MHZ_1024QAM. Later, perform decom once new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD) ready. 2.4243B(RTN04, NEID 9-30141)-4683A(RTN13, NEID 9-30140), 13G_4+0_28MHZ_512QAM_EPLA. Later, perform decom once new MW Parallel HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD_1) ready. Site Impacted : 4243B(DU 4243B_AD) & 4578D(DU 4243B_AD_1). NE_4243B 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN02) and insert new ISM8 x2 into slot 03 & slot 04. 3.Install XMC_5D Pro, Sub A_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN02). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN02) to existing BBU(4243B). 8.Request new xC Vlan DCN and Vlan Services. 9.Migrate traffics 4243B via new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA. 10.Later, decom existing 4243B(RTN01, NEID 9-27568)-4281A(RTN02, NEID 9-27567), 23G_1+0_112MHZ_1024QAM. FE_4148A/K00224 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04) x1 and insert new ISM8 x2 into slot 03 & slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA. 6.Request new 1x 1G(Electrical) port of PTN/Cisco(K00224) from ZTE IPRAN Team and also request new xC Vlan DCN and Vlan Services. 7.Enable port 8-EM6-1 of new RTN910AF(RTN04). 8.Perform patching port 8-EM6-1 of new RTN910AF(RTN02) to new 1x 1G(Electrical) port of PTN/Cisco. 9.Migrate traffics 4243B via new 1x 1G(Electrical) port of PTN/Cisco(K00224). 10.Later, decom existing 4243B(RTN01, NEID 9-27568)-4281A(RTN02, NEID 9-27567), 23G_1+0_112MHZ_1024QAM. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G WITH BW 28MHZ IN ORDER TO ENSURE CHANNEL AVAILABILITY AT CP.**** Existing 2x HW MW Links as stated below: 1.4243B(RTN01, NEID 9-27568)-4281A(RTN02, NEID 9-27567), 23G_1+0_112MHZ_1024QAM. Later, perform decom once new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD) ready. 2.4243B(RTN04, NEID 9-30141)-4683A(RTN13, NEID 9-30140), 13G_4+0_28MHZ_512QAM_EPLA. Later, perform decom once new MW Parallel HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD_1) ready. Site Impacted : 4243B(DU 4243B_AD) & 4578D(DU 4243B_AD_1). NE_4243B 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN02) and insert new ISM8 x2 into slot 03 & slot 04. 3.Install XMC_5D Pro, Sub A_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN02). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN02) to existing BBU(4243B). 8.Request new xC Vlan DCN and Vlan Services. 9.Migrate traffics 4243B via new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA. 10.Later, decom existing 4243B(RTN01, NEID 9-27568)-4281A(RTN02, NEID 9-27567), 23G_1+0_112MHZ_1024QAM. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G WITH BW 28MHZ IN ORDER TO ENSURE CHANNEL AVAILABILITY AT CP.**** Existing 2x HW MW Links as stated below: 1.4243B(RTN01, NEID 9-27568)-4281A(RTN02, NEID 9-27567), 23G_1+0_112MHZ_1024QAM. Later, perform decom once new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD) ready. 2.4243B(RTN04, NEID 9-30141)-4683A(RTN13, NEID 9-30140), 13G_4+0_28MHZ_512QAM_EPLA. Later, perform decom once new MW Parallel HW MW Link 4243B(RTN04)-4148A(RTN05), 13G_4+0_28MHZ_1024QAM_CA(under DU 4243B_AD_1) ready. Site Impacted : 4243B(DU 4243B_AD) & 4578D(DU 4243B_AD_1). FE_4148A/K00224 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04) x1 and insert new ISM8 x2 into slot 03 & slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 port 1 and slot 04 port 1. 5.Build new MW Link/Reroute HW MW Link 4243B(RTN02)-4148A(RTN04), 13G_4+0_28MHZ_1024QAM_CA. 6.Request new 1x 1G(Electrical) port of PTN/Cisco(K00224) from ZTE IPRAN Team and also request new xC Vlan DCN and Vlan Services. 7.Enable port 8-EM6-1 of new RTN910AF(RTN04). 8.Perform patching port 8-EM6-1 of new RTN910AF(RTN02) to new 1x 1G(Electrical) port of PTN/Cisco. 9.Migrate traffics 4243B via new 1x 1G(Electrical) port of PTN/Cisco(K00224). 10.Later, decom existing 4243B(RTN01, NEID 9-27568)-4281A(RTN02, NEID 9-27567), 23G_1+0_112MHZ_1024QAM. | XMC_5D Pro | MDD | 13G | 13G_1.2M(MDD) x1 | 13G_1.2M(MDD) x1 | GCI | SQ202602250659-GCI | GCI | SQ202602250651-GCI // SQ202602250654-GCI |  |  | Ongoing | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-03 | 2026-04-10 | 2026-04-03 | 2026-04-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040913 | X | 2026-04-30 |  | Ongoing | 2026-04-17 | 2026-04-30 | 2026-04-17 |  | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Assigned | Ongoing |  | 2026-04-17 | 2026-04-30 | 2026-04-17 |  | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | 2026-04-17 | 2026-04-30 | 2026-04-17 |  | MUHAMAD ARIFF BIN KHASIM6800000179 | GCI TI | [7 empty] | 2026-04-17 | 2026-04-30 | 2026-04-17 |  | MUHAMAD ARIFF BIN KHASIM6800000179 | 2025-05-10: 2026-04-17; 2025-05-10: 2026-04-30; 2025-05-10: 2026-04-17; 2025-05-12: 2026-04-17 | [7 empty] | GTSB | SQ202602260616-GTSB
4337C_AD | Terap(REL) | DU00006615057 | Northern | Kedah | 5.545166 | 100.540514 | [7 empty] | 04. Pending DO |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1x ODU 18G XMC3ECSUB A LO | MW New Link / Reroute | MW NEW LINK REROUTE 4337C-4148A WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_778MBPS_XMC3E_SUB_A_LINK_3.96KM IMPACTED: 4337C DISMANTLE EXISTING LINK 4337C-4632B Reroute site to new CP 4148A to offload existing CP site 4281A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK 4337C-4148A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK 4337C-4148A | XMC3E | DP | 15G | 0.6 | 0.6 | GCI | SQ202602230142-GCI | GCI | SQ202602230133-GCI // SQ202602230136-GCI | 2026-03-27 | 2026-03-13 | Completed | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-02-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26040909 |  | 2026-04-10 | 2026-04-09 | Completed | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-10 | 2026-04-30 | 2026-04-10 | 2026-05-04 | Muhamad//Asraf Bin Mohd Nor/6800000125 | GCI TI | 2026-04-10 | 2026-04-30 | 2026-04-10 | 2026-05-04 | Muhamad//Asraf Bin Mohd Nor/6800000125 | GCI TI | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-02 | 2026-04-10 | 2026-04-30 | 2026-04-10 | 2026-05-04 | Muhamad//Asraf Bin Mohd Nor/6800000125 | 2026-04-10 | 2026-04-30 | 2026-04-10 | 2026-04-10 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | NG HONG JIE7018000036 | Logistic Team | [5 empty] | GCI | SQ202602260562-GCI | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
7261A_IPR | Kg. Salut(Celcom) | DU00006615058 | Sabah | Sabah | 6.103110 | 116.164410 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_7261A/S00034 New SFP Module 10G 10Km 1310nm x1(IDU Huawei) & SFP Module 10G x1(PTN/Cisco). New Optical Patchcord with suitable type and length x1. | MW IDU Patching | Perform upgrade IDU & PTN 1G to 10G and patching. Site Impacted: 7547B, 7087L & 7017D. NE_7261A 1.Disable port 8-EM6-1(1G Electrical) of existing RTN910AF(RTN01, NEID 16-29499). 2.Disable existing port PTN 20025-SALUT GE0/0/7. 3.Disconnect/remove existing CAT6 cable port 8-EM6-1(1G Electrical) of existing RTN910AF(RTN01, NEID 16-29499) and existing port PTN 20025-SALUT GE0/0/7. 4.Insert new SFP Module 10G 1310nm 10Km x1 into port 8-EM6-3 of existing RTN910AF(RTN01, NEID 16-29499). Enable and configure it. 5.Request new IBeam port 10G at existing PTN 20025 from ZTE IPRAN Team. 6.Insert new suitable SFP Module 10G into new IBeam port 10G at existing PTN 20025. 7.Patching port 8-EM6-3 of existing RTN910AF(RTN01, NEID 16-29499) to new IBeam port 10G at existing PTN 20025. Configure it. 8.Request new xC Vlan DCN & Vlan Services. 9.Migrate Traffics 7547B, 7087L & 7017D will backhaul into new IBeam port 10G at existing PTN 20025. | Perform upgrade IDU & PTN 1G to 10G and patching. Site Impacted: 7547B, 7087L & 7017D. NE_7261A 1.Disable port 8-EM6-1(1G Electrical) of existing RTN910AF(RTN01, NEID 16-29499). 2.Disable existing port PTN 20025-SALUT GE0/0/7. 3.Disconnect/remove existing CAT6 cable port 8-EM6-1(1G Electrical) of existing RTN910AF(RTN01, NEID 16-29499) and existing port PTN 20025-SALUT GE0/0/7. 4.Insert new SFP Module 10G 1310nm 10Km x1 into port 8-EM6-3 of existing RTN910AF(RTN01, NEID 16-29499). Enable and configure it. 5.Request new IBeam port 10G at existing PTN 20025 from ZTE IPRAN Team. 6.Insert new suitable SFP Module 10G into new IBeam port 10G at existing PTN 20025. 7.Patching port 8-EM6-3 of existing RTN910AF(RTN01, NEID 16-29499) to new IBeam port 10G at existing PTN 20025. Configure it. 8.Request new xC Vlan DCN & Vlan Services. 9.Migrate Traffics 7547B, 7087L & 7017D will backhaul into new IBeam port 10G at existing PTN 20025. | [6 empty] | NR services | SQ202603170086-NR Services | NR services | SQ202603030376-NR Services |  |  | Ongoing | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26022634 |  | 2026-02-27 | 2026-03-10 | Completed | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-03-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-04-03 | 2026-03-03 | 2026-03-10 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-03-03 | 2026-04-03 | 2026-03-03 | 2026-03-10 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-03-10 | 2026-03-03 | 2026-04-03 | 2026-03-03 | 2026-03-09 | LEONARD//EDUAN/6000038538 | 2025-05-10: 2026-03-03; 2025-05-10: 2026-04-03; 2025-05-10: 2026-03-03; 2025-05-12: 2026-03-03 |  |  | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202602260632-GTSB
4831D_HU | FinisarKlebang (M ) | DU00006631547 | Northern | Perak | 4.669502 | 101.130072 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_110M_512QAM_EPLA NE_4831D New 18G_0.6M(MDD) x1. New RTN910AF(RTN01). New IF cables with suitable length and type x2 RUN. New XMC_5D Pro, Sub B_Hi x1. New CAT6 cable x1. FE_4541A New 18G_0.6M(MDD) x1. New RTN910AF(RTN04). New IF cables with suitable length and type x2 RUN. New XMC_5D Pro, Sub B_Lo x1. New CAT6 cable x2. | MW New Link / Reroute | Install new MW Link/Reroute HW MW Link 4831D-4541A, 18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : 4831D. NE_4831D 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install XMC_5D Pro, Sub B_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 Port 1 & 2. 5.Build new MW Link/Reroute HW MW Link 4831D-4541A, 18G_2+0_110MHZ_512QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN01). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN01) to BBU(4831D). 8.Request new xD Vlan DCN and Vlan Services. 9.Migrate traffic 4831D to new MW Link/Reroute HW MW Link 4831D-4541A, 18G_2+0_110MHZ_512QAM_EPLA. FE_4541A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN04). 3.Install XMC_5D Pro, Sub B_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 Port 1 & 2. 5.Build new MW Link/Reroute HW MW Link 4831D-4541A, 18G_2+0_110MHZ_512QAM_EPLA. 6.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN04). 7.Request new 2x 1G(Electrical) port at IBeam. 8.Perform patching port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN04) and new 2x 1G(Electrical) port at IBeam. 9.Perform 2x 1G LAG in between 2x port at IDU HW RTN910AF(RTN04) and at IBeam. 10.Request new xD Vlan DCN and Vlan Services. 11.Migrate traffic 4831D to 2x 1G LAG port IBeam. | Install new MW Link/Reroute HW MW Link 4831D-4541A, 18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : 4831D. NE_4831D 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01). 3.Install XMC_5D Pro, Sub B_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 Port 1 & 2. 5.Build new MW Link/Reroute HW MW Link 4831D-4541A, 18G_2+0_110MHZ_512QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN01). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN01) to BBU(4831D). 8.Request new xD Vlan DCN and Vlan Services. 9.Migrate traffic 4831D to new MW Link/Reroute HW MW Link 4831D-4541A, 18G_2+0_110MHZ_512QAM_EPLA. | Install new MW Link/Reroute HW MW Link 4831D-4541A, 18G_2+0_110MHZ_512QAM_EPLA. Site Impacted : 4831D. FE_4541A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN04). 3.Install XMC_5D Pro, Sub B_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 Port 1 & 2. 5.Build new MW Link/Reroute HW MW Link 4831D-4541A, 18G_2+0_110MHZ_512QAM_EPLA. 6.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN04). 7.Request new 2x 1G(Electrical) port at IBeam. 8.Perform patching port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN04) and new 2x 1G(Electrical) port at IBeam. 9.Perform 2x 1G LAG in between 2x port at IDU HW RTN910AF(RTN04) and at IBeam. 10.Request new xD Vlan DCN and Vlan Services. 11.Migrate traffic 4831D to 2x 1G LAG port IBeam. | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | GTSB | SQ202603040037-GTSB | GTSB | SQ202603030407-GTSB // SQ202603030416-GTSB |  |  | Ongoing | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-18 | 2026-04-01 | 2026-03-18 | 2026-03-18 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-05 | 2026-05-12 | 2026-05-05 | 2026-05-05 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030408 |  | 2026-03-05 | 2026-03-09 | Completed | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-09 | 2026-03-31 | 2026-03-09 | 2026-03-10 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-03-09 | 2026-03-31 | 2026-03-09 | 2026-04-01 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-11 | 2026-03-09 | 2026-03-31 | 2026-03-09 | 2026-03-31 | HAMZAH BIN ABDUL MUTALIF6799000301 | 2025-05-10: 2026-03-09; 2025-05-10: 2026-03-31; 2025-05-10: 2026-03-09; 2025-05-12: 2026-03-10 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202602260616-GTSB
9833B_HU | KpgLebaan | DU00006631548 | Sarawak | Sarawak | 2.274200 | 111.667100 | [13 empty] | HOLD 9833B_HU. NEED TO DO Q01209_AD AND 9833B_AD DONE FIRST. MONITOR IF HIGH UTILIZATION STILL OCCUR OR NOT. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202602260597-GCI
4689D_HU_2 | Klebang RiaShoplot | DU00006631549 | Northern | Perak | 4.684497 | 101.108180 | [7 empty] | 05. TI WIP |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_55M_512QAM_EPLA NE_4689D New 18G_0.6M(MDD) x1. New RTN910AF(RTN02). New XMC_5D Pro, Sub A_Hi x1. New ISM8 x2. New IF cables with suitable length and type x4 RUN.(x2 RUN for new 18G 2+0 and x2 RUN for existing 15G 4+0) New CAT6 cable with suitable length x1. FE_4346A New 18G_0.6M(MDD) x1. New RTN910AF(RTN11). New XMC_5D Pro, Sub A_Lo x1. New ISM8 x2. New IF cables with suitable length and type x4 RUN.(x2 RUN for new 18G 2+0 and x2 RUN for existing 15G 4+0) New CAT6 cable with suitable length x2. | MW Swap | Existing HW MW Link 4689D(RTN01, NEID 9-24434)-4346A(RTN10, NEID 9-24435), 15G_4+0_28MHZ_512QAM_CA. Swap existing HW MW Link 4689D-4346A ODU & Antenna ONLY, 18G 1+0 55MHZ(not visible in NMS) after remove IF cable from 4689D(RTN01, NEID 9-24434) and 4346A(RTN10, NEID 9-24435) with new HW MW Link 4689D(New RTN910AF(RTN02))-4346A(New RTN910AF(RTN11)), 18G_2+0_55MHZ_512QAM_EPLA. Therfore, combine existing HW MW Link 15G_4+0_28MHZ_512QAM_CA and new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA and become new HW MW Link 15G&18G_6+0_28MHZ&55MHZ_512QAM_EPLA. Later, may decom existing RTN910A(RTN01, NEID 9-24434) ONLY at 4689D and existing RTN910A(RTN10, NEID 9-24435) ONLY at 4346A. Site Impacted : 4689D. NE_4689D 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN02) and insert new ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN and terminate to new RTN910AF(RTN02) ISM8 slot 07 Port 1 & 2 . Build new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA. 4.Disconnect/remove existing IF cable from slot 03 Port 1 and slot 04 Port 1 of existing RTN910A(RTN01, NEID 9-24434). 5.Lay new IF cables from slot 03 Port 1 and slot 04 Port 1 of new RTN910AF(RTN02) to port IF1 & IF2 of existing ODU 15G(23-Modu). 6.Therefore, combine existing HW MW Link 15G_4+0_28MHZ_512QAM_CA and new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA and become new HW MW Link 15G&18G_6+0_28MHZ&55MHZ_512QAM_EPLA. 7.Enable port 8-EM6-1 of new RTN910AF(RTN02) and patching to existing BBU(4689D). 8.Request new xD Vlan DCN & Vlan Services. 9.Migrate traffic 4689D to new HW MW Link 15G&18G_6+0_28MHZ&55MHZ_512QAM_EPLA. 10.Later, decom existing RTN910A(RTN01, NEID 9-24434) ONLY at 4689D and existing RTN910A(RTN10, NEID 9-24435) ONLY at 4346A. FE_4346A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN11) and insert new ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN and terminate to new RTN910AF(RTN11) ISM8 slot 07 Port 1 & 2 . Build new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA. 4.Disconnect/remove existing IF cable from slot 03 Port 1 and slot 04 Port 1 of existing RTN910A(RTN10, NEID 9-24435). 5.Lay new IF cables from slot 03 Port 1 and slot 04 Port 1 of new RTN910AF(RTN11) to port IF1 & IF2 of existing ODU 15G(23-Modu). 6.Therefore, combine existing HW MW Link 15G_4+0_28MHZ_512QAM_CA and new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA and become new HW MW Link 15G&18G_6+0_28MHZ&55MHZ_512QAM_EPLA. 7.Enable port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN11). 8.Port 8-EM6-1 of new RTN910AF(RTN11) will be patching to existing port 1G(Electrical) of IBeam. 9.Port 8-EM6-2 of new RTN910AF(RTN11) will be patching 2nd new port 1G(Electrical) of IBeam. Please request from ZTE IPRAN team. 10.Perform 2x 1G LAG in between 2x port at IDU HW RTN910AF and at IBeam. 11.Request new xD Vlan DCN & Vlan Services. 12.Migrate traffic 4689D to 2x 1G LAG port IBeam. 13.Later, decom existing RTN910A(RTN01, NEID 9-24434) ONLY at 4689D and existing RTN910A(RTN10, NEID 9-24435) ONLY at 4346A. | Existing HW MW Link 4689D(RTN01, NEID 9-24434)-4346A(RTN10, NEID 9-24435), 15G_4+0_28MHZ_512QAM_CA. Swap existing HW MW Link 4689D-4346A ODU & Antenna ONLY, 18G 1+0 55MHZ(not visible in NMS) after remove IF cable from 4689D(RTN01, NEID 9-24434) and 4346A(RTN10, NEID 9-24435) with new HW MW Link 4689D(New RTN910AF(RTN02))-4346A(New RTN910AF(RTN11)), 18G_2+0_55MHZ_512QAM_EPLA. Therfore, combine existing HW MW Link 15G_4+0_28MHZ_512QAM_CA and new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA and become new HW MW Link 15G&18G_6+0_28MHZ&55MHZ_512QAM_EPLA. Later, may decom existing RTN910A(RTN01, NEID 9-24434) ONLY at 4689D and existing RTN910A(RTN10, NEID 9-24435) ONLY at 4346A. Site Impacted : 4689D. NE_4689D 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN02) and insert new ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN and terminate to new RTN910AF(RTN02) ISM8 slot 07 Port 1 & 2 . Build new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA. 4.Disconnect/remove existing IF cable from slot 03 Port 1 and slot 04 Port 1 of existing RTN910A(RTN01, NEID 9-24434). 5.Lay new IF cables from slot 03 Port 1 and slot 04 Port 1 of new RTN910AF(RTN02) to port IF1 & IF2 of existing ODU 15G(23-Modu). 6.Therefore, combine existing HW MW Link 15G_4+0_28MHZ_512QAM_CA and new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA and become new HW MW Link 15G&18G_6+0_28MHZ&55MHZ_512QAM_EPLA. 7.Enable port 8-EM6-1 of new RTN910AF(RTN02) and patching to existing BBU(4689D). 8.Request new xD Vlan DCN & Vlan Services. 9.Migrate traffic 4689D to new HW MW Link 15G&18G_6+0_28MHZ&55MHZ_512QAM_EPLA. 10.Later, decom existing RTN910A(RTN01, NEID 9-24434) ONLY at 4689D and existing RTN910A(RTN10, NEID 9-24435) ONLY at 4346A. | Existing HW MW Link 4689D(RTN01, NEID 9-24434)-4346A(RTN10, NEID 9-24435), 15G_4+0_28MHZ_512QAM_CA. Swap existing HW MW Link 4689D-4346A ODU & Antenna ONLY, 18G 1+0 55MHZ(not visible in NMS) after remove IF cable from 4689D(RTN01, NEID 9-24434) and 4346A(RTN10, NEID 9-24435) with new HW MW Link 4689D(New RTN910AF(RTN02))-4346A(New RTN910AF(RTN11)), 18G_2+0_55MHZ_512QAM_EPLA. Therfore, combine existing HW MW Link 15G_4+0_28MHZ_512QAM_CA and new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA and become new HW MW Link 15G&18G_6+0_28MHZ&55MHZ_512QAM_EPLA. Later, may decom existing RTN910A(RTN01, NEID 9-24434) ONLY at 4689D and existing RTN910A(RTN10, NEID 9-24435) ONLY at 4346A. Site Impacted : 4689D. FE_4346A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN11) and insert new ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN and terminate to new RTN910AF(RTN11) ISM8 slot 07 Port 1 & 2 . Build new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA. 4.Disconnect/remove existing IF cable from slot 03 Port 1 and slot 04 Port 1 of existing RTN910A(RTN10, NEID 9-24435). 5.Lay new IF cables from slot 03 Port 1 and slot 04 Port 1 of new RTN910AF(RTN11) to port IF1 & IF2 of existing ODU 15G(23-Modu). 6.Therefore, combine existing HW MW Link 15G_4+0_28MHZ_512QAM_CA and new HW MW Link 18G_2+0_55MHZ_512QAM_EPLA and become new HW MW Link 15G&18G_6+0_28MHZ&55MHZ_512QAM_EPLA. 7.Enable port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN11). 8.Port 8-EM6-1 of new RTN910AF(RTN11) will be patching to existing port 1G(Electrical) of IBeam. 9.Port 8-EM6-2 of new RTN910AF(RTN11) will be patching 2nd new port 1G(Electrical) of IBeam. Please request from ZTE IPRAN team. 10.Perform 2x 1G LAG in between 2x port at IDU HW RTN910AF and at IBeam. 11.Request new xD Vlan DCN & Vlan Services. 12.Migrate traffic 4689D to 2x 1G LAG port IBeam. 13.Later, decom existing RTN910A(RTN01, NEID 9-24434) ONLY at 4689D and existing RTN910A(RTN10, NEID 9-24435) ONLY at 4346A. | XMC-5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | GTSB | SQ202603040037-GTSB | GTSB | SQ202603030407-GTSB // SQ202603030416-GTSB |  |  | Ongoing | [8 empty] | Unassigned | Not started |  | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030410 |  | 2026-03-05 | 2026-03-09 | Completed | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-09 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-09 | 2026-03-31 | 2026-03-09 | 2026-03-11 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-03-09 | 2026-03-31 | 2026-03-09 |  | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  | 2026-04-09 | 2026-03-09 | 2026-03-31 | 2026-03-09 |  | HAMZAH BIN ABDUL MUTALIF6799000301 | 2025-05-10: 2026-03-09; 2025-05-10: 2026-03-31; 2025-05-10: 2026-03-09; 2025-05-12: 2026-03-11 | [7 empty] | GTSB | SQ202602260616-GTSB
1771C-B00695 | Parit 8 Gambut | DU00004066646 | Central | Selangor | 3.694266 | 101.048248 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 22/8: D3: Cutover done. Post-CO T/shooting WIP 20/8: D2: TI WIP. CO in plan. Main power failure. FE Site down | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G 2+0 1.2m/1.2m XMC3 NE: 1) 1xISM8 2) 1x15GHz XMC3 Sub A Hi 3) 1x18GHz XMC3 Sub B Hi 4) 1x15GHz 1.2m DP FE: 1) 1xISM8 2) 1x15GHz XMC3 Sub A Lo 3) 1x18GHz XMC3 Sub B Lo 4) 1x15GHz 1.2m DP | MW New Link / Reroute | To reroute 1771C. Existing: 1771C-1165A-1157A New: 1771C-B00695-4475A Impacted site: 1771C NE (1771C): 1) Install new ISM8 card at RTN01 slot 3 2) Install new link at RTN01 3-ISM8 3) Migrate 1771C to new link 4) Decom 1771C-1165A FE (B00695): 1) Install new ISM8 card at RTN01 slot 4 2) Install new link at RTN01 4-ISM8 3) Migrate 1771C to new link 4) Decom 1771C-1165A | [7 empty] | MTK | SQ202408300801-MTK | MTK | SQ202408140523-MTK | 2024-10-05 | 2024-10-04 | Completed | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2024-08-23 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-09-30 | 2024-10-01 | 2024-09-30 | 2024-09-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-09-30 | 2024-10-01 | 2024-09-30 | 2024-09-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-04 | 2024-10-05 | 2024-10-04 | 2024-10-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY240812BJ |  | 2024-08-13 | 2024-08-14 | Completed | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-14 | TYNG ERN//SLEW/6871000006 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-08-19 | 2024-08-31 | 2024-08-19 | 2024-08-23 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-08-19 | 2024-08-31 | 2024-08-19 | 2024-08-23 | RIDHUAN//BIN MANSOR/8225000011 | MTK TI | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2024-08-19 | 2024-08-31 | 2024-08-19 | 2024-09-03 | RIDHUAN//BIN MANSOR/8225000011 | 2024-08-19 | 2024-08-31 | 2024-08-19 | 2024-08-19 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | NG HONG JIE7018000036 | Logistic Team | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | NURFIKA//BINTI IBRAHIM/6237001402
4947A_HU_1 | Kota Kuala Muda | DU00005468854 | Northern | Kedah | 5.589173 | 100.373127 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | Existing link 15G_2+0_28M + 13G_4+0_28M Hardware upgrade from legacy RTN to new RTN910A and configure EPLA to 6+0 links. NE_4947A RTN910A x1. 15G_XMC_3 , Sub_B_Lo x2. FE_4272A RTN910A x1. 15G_XMC_3 , Sub B_Hi x2. | MW Hardware Upgrade | Existing link 15G_2+0_28M + 13G_4+0_28M Hardware upgrade from legacy RTN to new RTN910A and configure EPLA to 6+0 links. Site Impacted : 4117R. NE_4947A 1.Install new RTN910A.(RTN no provide by GOB team). 2.Transfer existing 13G_4+0_28M , 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A 3.Transfer existing 15G_2+0_28M , IF cable from 3_ISV3 & 5_ISV3 to new RTN910A , 7_ISM8-2+0. 4.Swap existing 15G_XMC_2 to new 15G_XMC_3 , Sub_B_Lo. 5.Create service cross connect and EPLA with 13G_4+0 and 15G_2+0 6.Traffic migrate to new link with EPLA 13G_4+0 and 15G_2+0 configuration. 7.Reuse existing 13G ant and 15G ant. 8.Decom existing 15G ODU and RTN950A (ID : 13360).Ensure all traffic migrate to new link and new RTN910A before decom. FE_4272A 1.Install new RTN910A.(RTN no provide by GOB team) 2.Transfer existing 13G_4+0_28M , 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 3.Transfer existing 15G_2+0_28M , IF cable from 3_ISV3 & 5_ISV3 to new RTN 910A , 7_ISM8-2+0. 4.Swap existing 15G_XMC_2 to new 15G_XMC_3 , Sub B_Hi. 5.Create service cross connect and EPLA with 13G_4+0 and 15G_2+0. 6.Traffic migrate to new link with EPLA 13G_4+0 and 15_2+0 configuration. 7.Reuse existing 13G ant and 15G ant. 8.Decom existing 15G ODU and RTN950A (ID : 13518). Ensure all traffic migrate to new link and new RTN910A before decom. | Existing link 15G_2+0_28M + 13G_4+0_28M Hardware upgrade from legacy RTN to new RTN910A and configure EPLA to 6+0 links. Site Impacted : 4117R. NE_4947A 1.Install new RTN910A.(RTN no provide by GOB team). 2.Transfer existing 13G_4+0_28M , 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A 3.Transfer existing 15G_2+0_28M , IF cable from 3_ISV3 & 5_ISV3 to new RTN910A , 7_ISM8-2+0. 4.Swap existing 15G_XMC_2 to new 15G_XMC_3 , Sub_B_Lo. 5.Create service cross connect and EPLA with 13G_4+0 and 15G_2+0 6.Traffic migrate to new link with EPLA 13G_4+0 and 15G_2+0 configuration. 7.Reuse existing 13G ant and 15G ant. 8.Decom existing 15G ODU and RTN950A (ID : 13360).Ensure all traffic migrate to new link and new RTN910A before decom. | Existing link 15G_2+0_28M + 13G_4+0_28M Hardware upgrade from legacy RTN to new RTN910A and configure EPLA to 6+0 links. Site Impacted : 4117R. FE_4272A 1.Install new RTN910A.(RTN no provide by GOB team) 2.Transfer existing 13G_4+0_28M , 3_ISM8-2+0 and 4_ISM8-2+0 into new RTN910A. 3.Transfer existing 15G_2+0_28M , IF cable from 3_ISV3 & 5_ISV3 to new RTN 910A , 7_ISM8-2+0. 4.Swap existing 15G_XMC_2 to new 15G_XMC_3 , Sub B_Hi. 5.Create service cross connect and EPLA with 13G_4+0 and 15G_2+0. 6.Traffic migrate to new link with EPLA 13G_4+0 and 15_2+0 configuration. 7.Reuse existing 13G ant and 15G ant. 8.Decom existing 15G ODU and RTN950A (ID : 13518). Ensure all traffic migrate to new link and new RTN910A before decom. | [5 empty] | GCI | SQ202505200530-GCI | GCI | SQ202505190405-GCI // SQ202505190415-GCI | 2025-10-29 | 2025-10-29 | Completed | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25050932 |  | 2025-05-10 | 2025-05-14 | Completed | 2025-05-09 | 2025-05-10 | 2025-05-09 | 2025-05-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-05-19 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-06-07 | SAFUAN//BIN YUSOFF/6800000178 | GCI TI | 2025-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-18 | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-06-20 | SAFUAN//BIN YUSOFF/6800000178 | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-05-19 | 2025-10-05 | 2025-10-05 | 2025-10-05 | 2025-10-05 | NG HONG JIE7018000036 | Logistic Team | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202505190519-GCI | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | CHEONG/SENG/WAH/7018000306
7212B_AD | Pekan Tg Aru | DU00005468855 | Sabah | Sabah | 5.954543 | 116.056414 |  |  |  | JUN 25 | Material collection | Material collection | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_7212B 23G_DP_0.6M(MAC)+ OMT x1. RTN910A x1. XMC_3 , Sub A & B_Lo x2. FE_7143B 23G_DP_0.6M(MAC)+OMT x1. XMC_3 , Sub A & B_Hi x2. ISM8 x1. | MW New Link / Reroute | Link reroute to new FE 7254A due to 7236A – Tg Aru (Building structure will be to demolish). Site Impacted : 7212B NE_7212B 1.Install new 23G_DP_0.6M(MAC)+ OMT. 2.Install new RTN910A , 7_ISM2-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create cross connect and EPLA. 5.Traffic migarte to new link and new FE route. 6.Decom existing MW link (7212B - 7236A). FE_7254A 1.Install new 23G_DP_0.3M(MAC)+OMT. 2.Install new XMC_3E , Sub A & B_Hi. 3.Reuse existing 7254A_RTN01 (NE ID : 43340). 4.Install 3_ISM8-2+0. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new link and new FE route. 7.Decom existing MW link ( 7236A - 7212B). | Link reroute to new FE 7254A due to 7236A – Tg Aru (Building structure will be to demolish). Site Impacted : 7212B NE_7212B 1.Install new 23G_DP_0.3M(MAC)+ OMT. 2.Install new RTN910A , 7_ISM2-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create cross connect and EPLA. 5.Traffic migarte to new link and new FE route. 6.Decom existing MW link (7212B - 7236A). | Link reroute to new FE 7254A due to 7236A – Tg Aru (Building structure will be to demolish). Site Impacted : 7212B FE_7254A 1.Install new 23G_DP_0.3M(MAC)+OMT. 2.Install new XMC_3E , Sub A & B_Hi. 3.Reuse existing 7254A_RTN01 (NE ID : 43340). 4.Install 3_ISM8-2+0. 5.Create service cross connect and EPLA with existing link. 6.Traffic migrate to new link and new FE route. 7.Decom existing MW link ( 7236A - 7212B). | XMC_3 | MAC | 23G | 0.6 | 0.6 | NR services | SQ202506300707-NR Services | NR services | SQ202505240116-NR Services // SQ202505240118-NR Services // SQ202507210355-NR Services | 2025-07-09 | 2025-07-08 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-25 | 2025-06-26 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-08 | 2025-07-07 | 2025-07-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-07 | 2025-07-08 | 2025-07-07 | 2025-07-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-08 | 2025-07-09 | 2025-07-08 | 2025-07-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051571 |  | 2025-05-16 | 2025-05-16 | Completed | 2025-05-15 | 2025-05-16 | 2025-05-15 | 2025-05-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-04 | 2025-07-06 | 2025-07-04 | 2025-07-06 | RALPH O'BRYAN HILARY7167000030 |  | 2025-07-04 | 2025-07-06 | 2025-07-04 | 2025-07-06 | RALPH O'BRYAN HILARY7167000030 |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-04 | 2025-07-03 | 2025-08-03 | 2025-07-03 | 2025-07-12 | RALPH O'BRYAN HILARY7167000030 | 2025-07-03 | 2025-08-03 | 2025-07-03 | 2025-07-03 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | tseping//wang/6819000006 | Logistic Team | 2025-07-24 | 2025-08-24 | 2025-07-24 | 2025-07-24 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506050641-GCI | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | CHEONG/SENG/WAH/7018000306
2876A_LOS | Tmn Sri Bahtera | DU00005468856 | Central | Kuala Lumpur | 3.105289 | 101.737415 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M NE_2876A 18G_DP_0.6M(MDD) x1. RTN910A x1. XMC_5D , Sub A x1. FE_1264A, 18G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_5D , Sub A _Lo x1. | MW New Link / Reroute | Link reroute to new FE 1264A due to LOS block. 18G_2+0_112M Site Impacted : 2876A NE_2876A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Decom existng MW link (2876A - 1477A_RTN01). FE_1264A, 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Create new In Band DCN. 7.Decom existing MW link (1447A_RTN01 - 2876A). | Link reroute to new FE 1264A due to LOS block. 18G_2+0_112M Site Impacted : 2876A NE_2876A 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Decom existng MW link (2876A - 1477A_RTN01). | Link reroute to new FE 1264A due to LOS block. 18G_2+0_112M Site Impacted : 2876A FE_1264A, 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE route. 6.Create new In Band DCN. 7.Decom existing MW link (1447A_RTN01 - 2876A). | XMC_5D | MDD | 18G | 0.6 | 0.6 | GTSB | SQ202505140479-GTSB | GTSB | SQ202505270151-GTSB // SQ202505270156-GTSB | 2025-07-05 | 2025-07-03 | Completed | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-27 | 2025-06-10 | 2025-05-27 | 2025-05-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-05 | 2025-07-02 | 2025-07-03 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052830 |  | 2025-05-29 | 2025-06-11 | Completed | 2025-05-28 | 2025-05-29 | 2025-05-28 | 2025-06-11 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-11 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-11 | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-11 | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-18 | Aminuddin bin che azibA0563734967123169280 | 2025-05-28 | 2025-06-30 | 2025-05-28 | 2025-06-11 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050638-GCI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | CHEONG/SENG/WAH/7018000306
7581A_HU | Kg Paris 2 | DU00005507981 | Sabah | Sabah | 5.292910 | 118.006900 |  |  |  |  | RFS | RFS |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x Cat6 cable | MW IDU Patching | Patch 7581A RTN05 GE2 to new GE port at 7581A-MAC-001 and create LAG | Patch 7581A RTN05 GE2 to new GE port at 7581A-MAC-001 and create LAG | N/A | [5 empty] | NR services | SQ202505240073-NR Services | NR services | SQ202505240118-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-05-18 | 2025-05-20 | 2025-05-18 | 2025-05-20 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-22 | 2025-05-23 | 2025-05-22 | 2025-05-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051574 |  | 2025-05-16 | 2025-05-16 | Completed | 2025-05-15 | 2025-05-16 | 2025-05-15 | 2025-05-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-20 | 2025-06-21 | 2025-05-20 | 2025-05-20 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-05-20 | 2025-06-21 | 2025-05-20 | 2025-05-26 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 | SHAHARIN BIN RUSLAN6799000052 |  | 2025-05-20 | 2025-05-20 | 2025-06-21 | 2025-05-20 | 2025-07-17 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-05-10: 2025-05-20; 2025-05-10: 2025-06-21; 2025-05-10: 2025-05-20; 2025-05-12: 2025-05-23 |  |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506050733-GTSB | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | HSU//MYET CHAE/6799000011
1393H_LOS | 99 Speedmart PANDAN PERDANA 1 | DU00005541095 | Central | Selangor | 3.112694 | 101.742497 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS Radio NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Link reroute to new FE 1619K/B00482 due to LOS Block. Install New NLOS RTN510. Site Impacted : 1393H. NE_1393H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migarte to new route FE site. 6.Decom existing NLOS radio (1393H - NLOS - 1152C). FE_1619K/B00482 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect 5.ETH cable direct patching to existing 1619K/B00482 IDU (ID : 14583). 6.Decom existing NLOS Radio (1152C - NLOS - 1393H) | Link reroute to new FE 1619K/B00482 due to LOS Block. Install New NLOS RTN510. Site Impacted : 1393H. NE_1393H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migarte to new route FE site. 6.Decom existing NLOS radio (1393H - NLOS - 1152C). | Link reroute to new FE 1619K/B00482 due to LOS Block. Install New NLOS RTN510. Site Impacted : 1393H. FE_1619K/B00482 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect 5.ETH cable direct patching to existing 1619K/B00482 IDU (ID : 14583). 6.Decom existing NLOS Radio (1152C - NLOS - 1393H) | [5 empty] | GTSB | SQ202505140479-GTSB | GTSB | SQ202505270151-GTSB // SQ202505270156-GTSB | 2025-11-11 | 2025-11-10 | Completed | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-05 | 2025-06-19 | 2025-06-05 | 2025-06-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052648 |  | 2025-05-27 | 2025-05-28 | Completed | 2025-05-26 | 2025-05-27 | 2025-05-26 | 2025-05-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-30 | 2025-06-30 | 2025-05-30 | 2025-06-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-05-30 | 2025-06-30 | 2025-05-30 | 2025-06-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-12 | 2025-05-30 | 2025-06-30 | 2025-05-30 | 2025-06-26 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-05-30 | 2025-06-30 | 2025-05-30 | 2025-06-12 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050638-GCI | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | CHEONG/SENG/WAH/7018000306
7226B_HU | Harmony Industrial Park | DU00005541096 | Sabah | Sabah | 6.015419 | 116.148019 |  |  |  |  | Material collection | Material collection | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G 1+0 110MHz 0.6m/0.6m SP MAC XMC-3E Sub B 889Mbps 2.56Km 2X RTN 910A 2X 18G 0.6m SP MAC ANTENNA 1X 18G XMC-3E SUB B HI 1X 18G XMC-3E SUB B LO | MW Parallel Link | Add New MW Parallel Link 7226B-7154A With HUAWEI_18G_1+0_110MHz_0.6M_SUB B_2.56Km to Carry 7224B Traffic Only IMPACTED SITES: 7224B,7650A,7078H NE 7226B 1. Install New RTN910A 2. Install New 18G 0.6m SP MAC Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service & Patch Traffic 7224B to New Link FE 7154A 1. Install New RTN910A 2. Install New 18G 0.6m SP MAC Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service & Patch to New Port at HW iBEAM | Add New MW Parallel Link 7226B-7154A With HUAWEI_18G_1+0_110MHz_0.6M_SUB B_2.56Km to Carry 7224B Traffic Only IMPACTED SITES: 7224B,7650A,7078H NE 7226B 1. Install New RTN910A 2. Install New 18G 0.6m SP MAC Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service & Patch Traffic 7224B to New Link | Add New MW Parallel Link 7226B-7154A With HUAWEI_18G_1+0_110MHz_0.6M_SUB B_2.56Km to Carry 7224B Traffic Only IMPACTED SITES: 7224B,7650A,7078H FE 7154A 1. Install New RTN910A 2. Install New 18G 0.6m SP MAC Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service & Patch to New Port at HW iBEAM | XMC-3E | SP MAC | 18G | 0.6m | 0.6m | NR services | SQ202506260776-NR Services | NR services | SQ202507100566-NR Services // SQ202507100570-NR Services | 2026-03-14 | 2026-03-13 | Completed | 2025-06-25 | 2025-06-26 | 2025-06-25 | 2025-06-26 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25060714 |  | 2025-06-08 | 2025-06-10 | Completed | 2025-06-07 | 2025-06-08 | 2025-06-07 | 2025-06-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-06 | 2025-07-08 | 2025-07-06 | 2025-07-08 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-07-06 | 2025-07-08 | 2025-07-06 | 2025-07-08 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-08 | 2025-07-03 | 2025-08-03 | 2025-07-03 | 2025-07-14 | RALPH O'BRYAN HILARY7167000030 | 2025-05-10: 2025-07-03; 2025-05-10: 2025-08-03; 2025-05-10: 2025-07-03; 2025-05-12: 2025-07-07 |  |  | 2025-07-24 | 2025-08-24 | 2025-07-24 | 2025-07-24 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202505190529-GCI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
4084B_HU | Kg Tok Bedu | DU00005541097 | Northern | Penang | 5.501330 | 100.484690 | [7 empty] | 00. Integrated/RFS Done | 07/07: CO Done | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M_CA NE_4084B 15G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D , Sub A_Lo x1. FE_4273A. 15G_DP_1.2M(MDD) x1. XMC_5D , Sub A_Hi x1. ISM8 x2. | MW Parallel Link | Existing link 18G_2+0_56M. Remote Software Upgrade Not Support. Install paralell link 15G_4+0_28M_CA Site Impacted : 4084B. NE_4084B 1.Install new 15G_DP_1.2M(MDD). 2.Reuse existing 4048B_RTN03 (ID: 41810). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 4048B_RTN03. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA with eixsting 18G_2+0. 6.Traffic migrate to new parallel link and existing link. 7.No decom existing MW link. FE_4273A. 1.Install new 15G_DP_1.2M(MDD). 2.Reuse existing 4273A_RTN11 (ID : 41811). 3.Install new XMC_5D , Sub A_Hi. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 4273A_RTN11. 5.Create service cross connect and EPLA with existing 18G_2+0. 6.Traffic migrate to new parallel link and existing link. 7.No decom existing MW link. | Existing link 18G_2+0_56M. Remote Software Upgrade Not Support. Install paralell link 15G_4+0_28M_CA Site Impacted : 4084B. NE_4084B 1.Install new 15G_DP_1.2M(MDD). 2.Reuse existing 4048B_RTN03 (ID: 41810). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 4048B_RTN03. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect and EPLA with eixsting 18G_2+0. 6.Traffic migrate to new parallel link and existing link. 7.No decom existing MW link. | Existing link 18G_2+0_56M. Remote Software Upgrade Not Support. Install paralell link 15G_4+0_28M_CA Site Impacted : 4084B. FE_4273A. 1.Install new 15G_DP_1.2M(MDD). 2.Reuse existing 4273A_RTN11 (ID : 41811). 3.Install new XMC_5D , Sub A_Hi. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 4273A_RTN11. 5.Create service cross connect and EPLA with existing 18G_2+0. 6.Traffic migrate to new parallel link and existing link. 7.No decom existing MW link. | XMC_5D | MDD | 15G | 1.2 | 1.2 | MTK | SQ202507080865-MTK | MTK | SQ202507080926-MTK // SQ202507080930-MTK | 2025-12-04 | 2025-12-03 | Completed | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061186 |  | 2025-06-12 | 2025-06-16 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-04 | 2025-07-23 | 2025-07-04 | 2025-07-07 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-07-04 | 2025-07-23 | 2025-07-04 | 2025-07-18 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | MTK TI | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-07 | 2025-07-05 | 2025-07-17 | 2025-07-15 | 2025-07-16 | PARTHIPPAN//A/L PONNUSAMY/8225000009 | 2025-05-10: 2025-07-05; 2025-05-10: 2025-07-17; 2025-05-10: 2025-07-07; 2025-05-12: 2025-07-07 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202505190519-GCI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | CHEONG/SENG/WAH/7018000306
9515A_HU | Pasar Lutong MP | DU00005541098 | Sarawak | Sarawak | 4.467380 | 114.008570 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 1+0 110MHz 0.6m/0.6m SP MAC XMC-3E Sub B 889Mbps 1.78Km 2X RTN 910A 2X 18G 0.6m SP MAC ANTENNA 1X 18G XMC-3E SUB B HI 1X 18G XMC-3E SUB B LO | MW Swap | SWAP MW LINK 9703B-9515A With HUAWEI_18G_1+0_110MHz_0.6M_SUB B_1.78Km EXISTING MW CFG: HW_15GHZ_1+0_28MHZ_207Mbps IMPACTED SITES: 9515A,9703B,Q01279 NE 9703B 1. Install New RTN910A 2. Install New 18G 0.6m SP MAC Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service & Repatch BBU 9703B 6. Dismantle Existing Link xD 9703B-9515A FE 9515A 1. Install New RTN910A 2. Install New 18G 0.6m SP MAC Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service & Repatch to SACOFA EG6-1, BBU 9515A EG6-2, xC Q00773 EG6-6 & EG6-5 6. Dismantle Existing Link xD 9703B-9515A | SWAP MW LINK 9703B-9515A With HUAWEI_18G_1+0_110MHz_0.6M_SUB B_1.78Km EXISTING MW CFG: HW_15GHZ_1+0_28MHZ_207Mbps IMPACTED SITES: 9515A,9703B,Q01279 NE 9703B 1. Install New RTN910A 2. Install New 18G 0.6m SP MAC Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service & Repatch BBU 9703B 6. Dismantle Existing Link xD 9703B-9515A | SWAP MW LINK 9703B-9515A With HUAWEI_18G_1+0_110MHz_0.6M_SUB B_1.78Km EXISTING MW CFG: HW_15GHZ_1+0_28MHZ_207Mbps IMPACTED SITES: 9515A,9703B,Q01279 FE 9515A 1. Install New RTN910A 2. Install New 18G 0.6m SP MAC Antenna 3. Install New 1+0 18G XMC-3E Sub B 4. Configure Link 18G 1+0 110Mhz 5. Create Service & Repatch to SACOFA EG6-1, BBU 9515A EG6-2, xC Q00773 EG6-6 & EG6-5 6. Dismantle Existing Link xD 9703B-9515A | XMC-3E | SP MAC | 18G | 0.6m | 0.6m | Allstar | SQ202506260783-Allstar | iEzzpro | SQ202511210032-Iezzpro // SQ202511210033-Iezzpro // SQ202512190090-Iezzpro |  |  | Ongoing | 2025-06-24 | 2025-06-25 | 2025-06-25 | 2025-06-25 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25111878 |  | 2025-11-19 | 2025-11-20 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-22 | Hairil Nizam//Maliki/6000033206 | Iezzpro TI | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2026-01-08 | Hairil Nizam//Maliki/6000033206 | Iezzpro TI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-11-25 | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2026-01-09 | Hairil Nizam//Maliki/6000033206 | 2025-05-10: 2025-11-22; 2025-05-10: 2025-11-29; 2025-05-10: 2025-11-22; 2025-05-12: 2025-11-24 |  |  | 2025-12-17 | 2026-01-17 | 2025-12-17 | 2025-12-17 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202505190538-GCI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
1799A_HU | Seksyen 11 | DU00005541099 | Central | Selangor | 3.072193 | 101.526024 |  |  |  | JUN 25 |  |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X ISM8 CARD 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Parallel Link | MW PARALLEL LINK 1799A-1431B WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_1.06KM IMPACTED: 1075C, 3364C, 1758H | 1. INSTALL NEW ISM8 AT SLOT 3 RTN02 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. TRANSFER IF CABLE FROM EXISTING RTN02 7-1 TO RTN03 7-2 CREATE EPLA LINK 1799A RTN03-1431B RTN03 | 1. INSTALL NEW ISM8 AT SLOT 3 RTN01 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. TRANSFER IF CABLE FROM EXISTING RTN01 7-1 TO RTN03 7-2 CREATE EPLA LINK 1799A RTN03-1431B RTN03 | XMC3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202505240068-Magicell | Magicell | SQ202506030427-Magicell // SQ202506030430-Magicell | 2025-06-13 | 2025-06-12 | Completed | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-29 | 2025-05-30 | 2025-05-29 | 2025-05-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-12 | 2025-06-13 | 2025-06-12 | 2025-06-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052166 |  | 2025-06-03 | 2025-07-18 | Completed | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-07-18 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-07-18 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-07-18 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-10 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-07-18 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-05-10: 2025-06-03; 2025-05-10: 2025-06-03; 2025-05-10: 2025-06-03; 2025-05-12: 2025-06-09 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202505190510-GCI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | EZRIN TASNIM BIN ABDUL GANI6798000128
7615A_HU | Wisma Pang | DU00005541100 | Sabah | Sabah | 4.243713 | 117.885500 |  |  |  |  | Drop/Cancel |  |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | CANCEL DUE TO SOLUTION DONE UNDER DU 7615A_PostMOCN | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202505190529-GCI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
3694A_HU | Kolam Air Country Height Kajang | DU00005541101 | Central | Selangor | 2.982757 | 101.751171 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap | MW SWAP LINK 3694A-1777A WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_64QAM_1150MBPS_XMC3E_SUB_A & B_3.86KM DISMANTLE EXISTING LINK IMPACTED: 3694A, 3353A | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 64QAM 5. DISMANTLE EXISTING LINK 6. PATCH EXISTING IDU TO NEW IDU | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 64QAM 5. DISMANTLE EXISTING LINK 6. PATCH TO NEW CP PORT AND DO PORT LAG | XMC3E | MAC | 18G | 0.6 | 0.6 | Magicell | SQ202506200650-Magicell | Magicell | SQ202505280608-Magicell // SQ202505280610-Magicell | 2026-01-20 | 2026-01-21 | Completed | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-24 | 2025-06-25 | 2025-06-24 | 2025-06-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052167 |  | 2025-05-27 | 2025-05-30 | Completed | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-30 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-30 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-30 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-05-29 | 2025-05-29 | 2025-05-29 | 2025-05-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-29 | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-06-03 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-30 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | NG HONG JIE7018000036 | Logistic Team | 2025-07-25 | 2025-08-25 | 2025-07-25 | 2025-07-25 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202505190510-GCI | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | EZRIN TASNIM BIN ABDUL GANI6798000128
7115K_HU | RAMOKGBAHAGIA | DU00005541102 | Sabah | Sabah | 5.791500 | 118.028400 |  |  |  |  | TI DONE |  | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 1X RTN910 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Hardware Upgrade | MW HARDWARE LINK 7115K/S00834-7457B FROM 18G_1+0_0.6M/0.6M_DP_56MHZ_512QAM_449MBPS TO 18G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB A & B_0.493KM | 1) INSTALL NEW RTN910A (CHECK EXISTING IDU SEEMS HAVE FAN ALARM) 2. REUSE EXISTING 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B AT EXISTING ANTENNA 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM EPLA WITH EXISTING SUB A | 1) REUSE EXISTING IDU RTN910 2. REUSE EXISTING 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB B AT EXISTING ANTENNA 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM EPLA WITH EXISTING SUB A | XMC3E | MAC | 18G | 0.6 | 0.6 | NR services | SQ202506250177-NR Services | NR services | SQ202506160529-NR Services // SQ202506160577-NR Services | 2025-11-26 | 2025-11-25 | Completed | 2025-06-13 | 2025-06-14 | 2025-06-13 | 2025-06-14 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-03 | 2025-07-02 | 2025-07-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25060713 |  | 2025-06-08 | 2025-06-10 | Completed | 2025-06-07 | 2025-06-08 | 2025-06-07 | 2025-06-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-14 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-14 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-14 | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-19 | IBRAHIM//BIN SAHABU/7167000007 | 2025-05-27: 2025-06-13; 2025-05-27: 2025-07-13; 2025-05-27: 2025-06-13; 2025-05-30: 2025-06-14 |  |  | 2025-07-24 | 2025-08-24 | 2025-07-24 | 2025-07-24 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202505190529-GCI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
4119C_LOS | Kelebang 2 | DU00005066721 | Northern | Kedah | 6.325904 | 99.807180 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M NE_4119C. 18G_SP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A_Lo x1.. FE_4012D/K00813 18G_SP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A_Hi x1. | MW New Link / Reroute | Link reroute to new FE 4012D/K00813 due to existing FE LOS Block. Site Impacted : 4119C & K00865. NE_4119C. 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Enable GE1 for 4119C BBU patching and 6.Enable GE2 ETH interconnect SM link from K00865/4119C existing Link . 7.Migrate traffic to new link and new route FE sites. 8.Decom existing MW link (4119C_RTN01-4118C). FE_4012D/K00813 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Create new In band DCN 6.Enable GE1 , ETH patching to existing SM link (NT05094). 7.Migrate traffic to new link and new route FE site. 8.Decom existing ODU , 2_ISU2 and ANT (4118C-4119C). | Link reroute to new FE 4012D/K00813 due to existing FE LOS Block. Site Impacted : 4119C & K00865. NE_4119C. 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Enable GE1 for 4119C BBU patching and 6.Enable GE2 ETH interconnect SM link from K00865/4119C existing Link . 7.Migrate traffic to new link and new route FE sites. 8.Decom existing MW link (4119C_RTN01-4118C). | Link reroute to new FE 4012D/K00813 due to existing FE LOS Block. Site Impacted : 4119C & K00865. FE_4012D/K00813 1.Install new 18G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Create new In band DCN 6.Enable GE1 , ETH patching to existing SM link (NT05094). 7.Migrate traffic to new link and new route FE site. 8.Decom existing ODU , 2_ISU2 and ANT (4118C-4119C). | XMC_3E | MAC | 18G | 0.6M | 0.6M | GCI | SQ202507230735-GCI | GCI | SQ202506160513-GCI // SQ202506160540-GCI | 2026-01-23 | 2026-01-23 | Completed | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052634 |  | 2025-05-27 | 2025-05-27 | Completed | 2025-05-26 | 2025-05-27 | 2025-05-26 | 2025-05-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-17 | 2025-06-30 | 2025-06-17 | 2025-08-13 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-06-17 | 2025-06-30 | 2025-06-17 | 2025-07-06 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-06-17 | 2025-06-30 | 2025-06-17 | 2025-12-22 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-06-17 | 2025-06-30 | 2025-06-17 | 2025-06-29 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | NG HONG JIE7018000036 | Logistic Team | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506050639-GCI | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | CHEONG/SENG/WAH/7018000306
2349A_LOS_1 | SS 22a LP | DU00005137298 | Central | Selangor | 3.128820 | 101.611326 | WK10 | MAR 25 | WK10 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 7/3/2025 : Cutover done 6/3/2025 : Survey LOS activity WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW New Link / Reroute | Link reroute to new FE 1490A with 23G_1+0_112M due to LOS block. 23G_1+0_112M Site Impacted : 2349A NE_2349A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Hi. 4.Traffic migrate to new route and new link. 5.Decom existing MW link. FE_1490A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create new In Band DCN 5.Traffic migrate to new route and new link. | NE_2349A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Hi. 4.Traffic migrate to new route and new link. 5.Decom existing MW link. | FE_1490A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create new In Band DCN 5.Traffic migrate to new route and new link. | XMC_3 | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202503190663-GTSB | GTSB | SQ202503200152-GTSB // SQ202503200154-GTSB // SQ202504260131-GTSB | 2025-07-02 | 2025-07-01 | Completed | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-19 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-10 | 2025-03-24 | 2025-03-10 | 2025-03-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-05 | 2025-05-06 | 2025-05-05 | 2025-05-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25030356 |  | 2025-03-06 | 2025-03-24 | Completed | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-24 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-24 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-24 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  | 2025-03-07 | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-11 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-07 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-20 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI
3811A-1122A | Jalan Bunga Pekan (Banting) | DU00005137299 | Central | Selangor | 2.812883 | 101.501393 | WK10 | MAR 25 | WK10 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 7/3/2025 : Cutover done 6/3/2025 : Installation complete, pending alignment 5/3/2025 : NE installation complete, pending install FE site | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M NE_3811A 15G_DP_0.6M(MDD) x2. RTN910A x1. ISM8 x1. XMC_5D , Sub A & B_L0 x2. FE_1122A. 15G_DP_1.2M(MDD) x2. RTN910A x1. ISM8 x1. XMC_5D , Sub A & B_Hi x2. Electrical SFP Module x 2. ETH Cable x 1. | MW Swap | MW Swap 15G_4+0_28M NE_3811A 1.Install new 2 x 15G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0. 4.Install XMC_5D , Sub A & B_L0 to ant 1 and ant 2 respectively. 5.Create service cross connect and EPLA to 4+0 config. 6. Decomm existing link FE_1122A. 1.Install new 2x 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0. 4.Install XMC_5D , Sub A & B_Hi to ant 1 and ant 2 respectively. 5.Create New In Band DCN. 6.Create service cross connect and EPLA to 4+0 config. 7.Enable GE1 , ETH patching to Fiber_IBeam Port.(Gei 0/2/3). 8. Decomm existing link | MW Swap link 15G_4+0_28M NE_3811A 1.Install new 2 x 15G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0. 4.Install XMC_5D , Sub A & B_L0 to ant 1 and ant 2 respectively. 5.Create service cross connect and EPLA to 4+0 config. 6. Decomm existing link | MW Swap link 15G_4+0_28M FE_1122A. 1.Install new 2x 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0(RTN no provide by MSP team). 3.Install new 3_ISM8-2+0. 4.Install XMC_5D , Sub A & B_Hi to ant 1 and ant 2 respectively. 5.Create New In Band DCN. 6.Create service cross connect and EPLA to 4+0 config. 7.Enable GE1 , ETH patching to Fiber_IBeam Port.(Gei 0/2/3). 8. Decomm existing link | XMC_5D | MDD | 15G | 0.6 | 1.2 | GCI | SQ202503190656-GCI | GCI | SQ202503200144-GCI // SQ202503200149-GCI // SQ202504150088-GCI | 2025-07-02 | 2025-07-01 | Completed | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-12 | 2025-03-13 | 2025-03-12 | 2025-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022811 |  | 2025-03-01 | 2025-03-03 | Completed | 2025-02-28 | 2025-03-01 | 2025-02-28 | 2025-03-03 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-05 | 2025-03-12 | 2025-03-05 | 2025-03-06 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-05 | 2025-03-12 | 2025-03-05 | 2025-03-07 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-07 | 2025-03-05 | 2025-03-12 | 2025-03-05 | 2025-03-10 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-05 | 2025-03-12 | 2025-03-05 | 2025-03-05 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
3186B12_EVT | ​PBTS BBMR 2025 | DU00006437923 | Sabah | Sabah | 6.233380 | 116.193350 | [13 empty] | Planning and integration support only for event site 3186B12 PBTS BBMR 2025 Tx route: 3186B12/3186B12-7636A-LL-7000A 1) Share port with 7636A at 7000A 2) New NE ID NE IDU 3186B12 RTN01 3) New NE ID FE IDU 7636A RTN02 4) At far end 7636A patch GE1 RTN02 to GE1 RTN01 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
1869B_HU_1 | KJS Kg Semarang(KJS) | DU00006442562 | Central | Selangor | 2.871390 | 101.695840 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1x ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO 2x 10G SFP 2x PATCH CORD | MW New Link / Reroute | MW NEW LINK 1869B-2058B WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_256QAM_1778MBPS_XMC3E_SUB_A & B_LINK_2.08KM IMPACTED: 3251C, 3393A, 2736C NEW LINK CARRY 3251C, 3393A, 2736C TRAFFIC FE PATCH TO FIBER XC B00246 DISMANTLE LINK 1879B RTN04-2417A RTN04 | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK 1879B RTN04-2417A RTN04 6. NEW LINK CARRY 3251C, 3393A, 2736C TRAFFIC | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK 1879B RTN04-2417A RTN04 6. PATCH TO NEW CP PORT 10G XC B00246 7. NEW LINK CARRY 3251C, 3393A, 2736C TRAFFIC | XMC3E | DP | 23G | 0.6 | 0.6 | GCI | SQ202601150350-GCI | GCI | SQ202601080364-GCI // SQ202601080370-GCI // SQ202602040539-GCI | 2026-02-20 | 2026-02-25 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-14 | 2026-01-15 | 2026-01-14 | 2026-01-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-19 | 2026-02-20 | 2026-02-19 | 2026-02-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25122911 |  | 2025-12-30 | 2025-12-31 | Completed | 2025-12-29 | 2025-12-30 | 2025-12-29 | 2025-12-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-06 | 2026-01-13 | 2026-01-06 | 2026-01-06 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-06 | 2026-01-13 | 2026-01-06 | 2026-01-11 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-08 | 2026-01-06 | 2026-01-13 | 2026-01-06 | 2026-01-13 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2026-01-06 | 2026-01-13 | 2026-01-06 | 2026-01-06 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512241121-GCI
1914H_AD | Taman Permata (REL) | DU00006442563 | Central | Selangor | 3.206586 | 101.752074 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X PATCHCORD | MW IDU Patching | Patch 1914H NLOS at FE site to B00038 PTN/LL Proposed Tx route: 1914H-NLOS-B00038 |  | Patch 1914H NLOS at FE site to B00038 PTN/LL Proposed Tx route: 1914H-NLOS-B00038 | [5 empty] | GCI | SQ202601280642-GCI | GCI | SQ202601080370-GCI | 2026-02-23 | 2026-02-23 | Completed | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123092 |  | 2025-12-31 | 2025-12-31 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2025-12-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-21 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-26 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-22 | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-26 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-03-06: 2026-01-21; 2025-03-06: 2026-01-28; 2025-03-06: 2026-01-21; 2025-03-07: 2026-01-22 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602120113-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
7076B_AD | Kg Nobusong | DU00006449101 | Sabah | Sabah | 6.700512 | 116.649187 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cat 6 LAN Cable x 1 | MW IDU Patching | IDU Patching 7076B-KG NOBUSONG-RTN01 ( ID : 36084) to IDU 7250P-T3 KG NOBUSONG-RTN01 (ID : 35099). Site Impacted : 7252R Priority proceed for IDU Patching before MW Hardware upgrade , refer DU ID S00934_HU. | IDU Patching 7076B-KG NOBUSONG-RTN01 ( ID : 36084) to IDU 7250P-T3 KG NOBUSONG-RTN01 (ID : 35099). Site Impacted : 7252R Priority proceed for IDU Patching before MW Hardware upgrade , refer DU ID S00934_HU. | [6 empty] | NR services | SQ202601220792-NR Services | NR services | SQ202601220785-NR Services | 2026-02-03 | 2026-02-04 | Completed | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011635 |  | 2026-01-17 | 2026-01-20 | Completed | 2026-01-16 | 2026-01-17 | 2026-01-16 | 2026-01-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-02 | 2026-03-02 | 2026-02-02 | 2026-02-07 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-02-02 | 2026-03-02 | 2026-02-02 | 2026-02-07 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-03 | 2026-02-02 | 2026-03-02 | 2026-02-02 | 2026-02-11 | LEONARD//EDUAN/6000038538 | 2025-03-06: 2026-02-02; 2025-03-06: 2026-03-02; 2025-03-06: 2026-02-02; 2025-03-07: 2026-02-02 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | CHEONG/SENG/WAH/7018000306
S00934_HU | S096A_S00934OD_T3_KGNOBUSONG | DU00006449102 | Sabah | Sabah | 6.700493 | 116.649118 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE_7250P/S00934 ISM8 x1. FE_S00939. ISM8 x1. | MW Hardware Upgrade | Transfer 2+0 link 7076B-7341B to S00934-S00939 and create EPLA 6+0. Site Impacted : 7252R , 7076B **Priority IDU patching , refer DU ID 7076B_AD , before proceed MW Hardware Upgrade. ** Check RSL and existing ant size , if RSL not meet LB , realignment is required. NE_7250P/S00934 1.Reuse existing 7250P/S00934_RTN01. 2.Install new 4_ISM8-2+0 into existing 7250P/S00934_RTN01. 3.Transfer 2+0 link 7076B_RTN02 to 7250P/S00934_RTN01. 4.Create service cross connect and EPLA with existing MW link. 5.Decom 7076B_RTN02_IDU only. FE_S00939. 1.Reuse existing S00939_RTN03. 2.Install new 4_ISM8-2+0 into existing S00939_RTN03. 3.Transfer 2+0 link 7341B_RTN03 to S00939_RTN03. 4.Create service cross connect and EPLA with existing MW link. 5.Decom 7341B_RTN03_IDU only. | Transfer 2+0 link 7076B-7341B to S00934-S00939 and create EPLA 6+0. Site Impacted : 7252R , 7076B Priority IDU patching , refer DU ID 7076B_AD , before proceed MW Hardware Upgrade. NE_7250P/S00934 1.Reuse existing 7250P/S00934_RTN01. 2.Install new 4_ISM8-2+0 into existing 7250P/S00934_RTN01. 3.Transfer 2+0 link 7076B_RTN02 to 7250P/S00934_RTN01. 4.Create service cross connect and EPLA with existing MW link. 5.Decom 7076B_RTN02_IDU only. FE_S00939. 1.Reuse existing S00939_RTN03. 2.Install new 4_ISM8-2+0 into existing S00939_RTN03. 3.Transfer 2+0 link 7341B_RTN03 to S00939_RTN03. 4.Create service cross connect and EPLA with existing MW link. 5.Decom 7341B_RTN03_IDU only. | Transfer 2+0 link 7076B-7341B to S00934-S00939 and create EPLA 6+0. Site Impacted : 7252R , 7076B Priority IDU patching , refer DU ID 7076B_AD , before proceed MW Hardware Upgrade. NE_7250P/S00934 1.Reuse existing 7250P/S00934_RTN01. 2.Install new 4_ISM8-2+0 into existing 7250P/S00934_RTN01. 3.Transfer 2+0 link 7076B_RTN02 to 7250P/S00934_RTN01. 4.Create service cross connect and EPLA with existing MW link. 5.Decom 7076B_RTN02_IDU only. FE_S00939. 1.Reuse existing S00939_RTN03. 2.Install new 4_ISM8-2+0 into existing S00939_RTN03. 3.Transfer 2+0 link 7341B_RTN03 to S00939_RTN03. 4.Create service cross connect and EPLA with existing MW link. 5.Decom 7341B_RTN03_IDU only. | [5 empty] | NR services | SQ202601220792-NR Services | NR services | SQ202601220781-NR Services // SQ202601220785-NR Services // SQ202603180545-NR Services | 2026-02-04 | 2026-02-04 | Completed | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011634 |  | 2026-01-17 | 2026-01-20 | Completed | 2026-01-16 | 2026-01-17 | 2026-01-16 | 2026-01-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-02 | 2026-03-02 | 2026-02-02 | 2026-02-02 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-02-02 | 2026-03-02 | 2026-02-02 | 2026-02-07 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2026-02-02 | 2026-03-02 | 2026-02-02 | 2026-04-07 | LEONARD//EDUAN/6000038538 | 2026-02-02 | 2026-03-02 | 2026-02-02 | 2026-02-02 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | tseping//wang/6819000006 | Logistic Team | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-18 | CHEONG/SENG/WAH/7018000306
4991A_IPR | UUM | DU00006449103 | Northern | Kedah | 6.457932 | 100.499451 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_4991A New CAT6 cable with suitable length(IDU HW to IBeam) x1. | MW IDU Patching | Perform LAG for 2x port(existing & new) of IDU & IBeam. Site Impacted: 4660B. NE_4991A 1.Enable port 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-12324). 2.Request new IBeam port from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-12324) and new IBeam port. 4.Create LAG between 2xport(existing & new) of IDU-IBeam. 5.Traffic 4660B will backhaul into LAG of IDU-IBeam. | Perform LAG for 2x port(existing & new) of IDU & IBeam. Site Impacted: 4660B. NE_4991A 1.Enable port 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-12324). 2.Request new IBeam port from ZTE IPRAN team and enable port. 3.Patching port 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-12324) and new IBeam port. 4.Create LAG between 2xport(existing & new) of IDU-IBeam. 5.Traffic 4660B will backhaul into LAG of IDU-IBeam. | [6 empty] | GCI | SQ202601280647-GCI | GCI | SQ202601080374-GCI | 2026-03-17 | 2026-03-10 | Completed | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-27 | 2026-03-06 | 2026-02-27 | 2026-02-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123089 |  | 2025-12-31 | 2026-01-02 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-21 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-21 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-21 | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-24 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-03-06: 2026-01-21; 2025-03-06: 2026-01-28; 2025-03-06: 2026-01-21; 2025-03-07: 2026-01-21 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512241144-GTSB
Q01930_HU | Q130A_Q01930OD_TINBARAPMILL | DU00006449104 | Sarawak | Sarawak | 4.025438 | 114.277000 | [9 empty] | TSS+AA+TI |  | 13G_2+0_28M_1024QAM_EPLA NE_Q01930 New 13G_1.8M(MDD) x1. Re-use existing RTN910AF(NEID 82-11930). New ISM8 x1. New XMC_5D Pro, Sub B_Lo x1. FE_Q01129 New 13G_1.8M(MDD) x1. Re-use existing RTN910AF(NEID 82-21930). New ISM8 x1. New XMC_5D Pro, Sub B_Hi x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(ENT SOP TIN BARAP MILL) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** Existing HW MW Link Q01930-Q01129, 7G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. Later, combine existing HW MW Link Q01930-Q01129, 7G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. Become 8G&13G_4+0_28MHZ_512QAM&1024QAM_EPLA. Site Impacted : Q01930 & ENT SOP TIN BARAP MILL. NE_Q01930 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910AF(NEID 82-11930) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Later, combine existing HW MW Link Q01930-Q01129, 7G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. Become 8G&13G_4+0_28MHZ_512QAM&1024QAM_EPLA. FE_Q01129 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910AF(NEID 82-21930) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Later, combine existing HW MW Link Q01930-Q01129, 7G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. Become 8G&13G_4+0_28MHZ_512QAM&1024QAM_EPLA. | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(ENT SOP TIN BARAP MILL) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** Existing HW MW Link Q01930-Q01129, 7G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. Later, combine existing HW MW Link Q01930-Q01129, 7G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. Become 8G&13G_4+0_28MHZ_512QAM&1024QAM_EPLA. Site Impacted : Q01930 & ENT SOP TIN BARAP MILL. NE_Q01930 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910AF(NEID 82-11930) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Build new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Later, combine existing HW MW Link Q01930-Q01129, 7G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. Become 8G&13G_4+0_28MHZ_512QAM&1024QAM_EPLA. | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(ENT SOP TIN BARAP MILL) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET.**** Existing HW MW Link Q01930-Q01129, 7G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. Later, combine existing HW MW Link Q01930-Q01129, 7G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. Become 8G&13G_4+0_28MHZ_512QAM&1024QAM_EPLA. Site Impacted : Q01930 & ENT SOP TIN BARAP MILL. FE_Q01129 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910AF(NEID 82-21930) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Build new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. 4.Re-use existing xC Vlan DCN & Vlan Services. 5.Later, combine existing HW MW Link Q01930-Q01129, 7G_2+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link Q01930-Q01129, 13G_2+0_28MHZ_1024QAM_EPLA. Become 8G&13G_4+0_28MHZ_512QAM&1024QAM_EPLA. | XMC-5D Pro | MDD | 13G | 13G_1.8M(MDD) x1 | 13G_1.8M(MDD) x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202512241150-GTSB
9595C_AD | KualaSangan 2 | DU00006502507 | Sarawak | Sarawak | 2.764468 | 112.970172 | [9 empty] | TSS |  |  | MW New Link / Reroute | According To TSS Survey , resulting this site is drop due to LOS is Visible for 9027K & 9068P only. Instruction given from GOP. Note : 1. 9027K Existing TX Route : 9027K/Q00690-Q00865-Q00254. Under CP offload plan as well. New TX Route : 9027K/Q00690 - 9595C. Only LOS is visible to 9595C. 2.9068P / Q02271 Existing TX Route : 9068P/Q02271-9027K-Q00865-Q00254. | [7 empty] | Trintel | SQ202602250671-Trintel |  |  | 2026-02-25 | 2026-02-25 | Completed | 2026-01-24 | 2026-01-31 | 2026-01-24 | 2026-01-29 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-30 | 2026-01-31 | 2026-01-30 | 2026-01-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-30 | 2026-01-31 | 2026-01-30 | 2026-01-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601070323-GCI | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | CHEONG/SENG/WAH/7018000306
Q01122_AD | Q144A_Q01122OD_T3_RHMANDAU | DU00006502508 | Sarawak | Sarawak | 2.940300 | 112.890000 | [9 empty] | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 2X RTN910A 1X 15G 0.6M MDD ANTENNA 1X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB B HI 1x ODU 15G XMC5D SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE Q01122-9115A WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_256QAM_800MBPS_XMC5D_SUB_B_WITH CA_LINK_5.4KM DISMANTLE EXISTING LINK Q01122-Q00254 | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 15G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK Q01122-Q00254 | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO LL 6. DISMANTLE EXISTING LINK Q01122-Q00254 | XMC5D | MDD | 15G | 0.6 | 0.6 | Trintel | SQ202601300958-Trintel |  |  | 2026-02-04 | 2026-02-05 | Completed | 2026-01-23 | 2026-01-31 | 2026-01-23 | 2026-01-28 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-28 | 2026-01-29 | 2026-01-28 | 2026-01-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-28 | 2026-01-29 | 2026-01-28 | 2026-01-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601070323-GCI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01123_AD | Q144A_Q01123OD_T3_KEMKELABU | DU00006502509 | Sarawak | Sarawak | 2.852400 | 113.015700 | [9 empty] | TSS |  |  | MW New Link / Reroute | CANCEL/DROP (CLAIM TSS ONLY) NO LOS DURING SURVEY GOP DECLARED LOS BLOCK/DROP FOR THIS SITE | [7 empty] | Trintel | SQ202603130195-Trintel |  |  | 2026-03-13 | 2026-03-12 | Completed | 2026-01-25 | 2026-01-31 | 2026-01-25 | 2026-02-04 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601070323-GCI
Q01121_AD | Q144A_Q01121OD_CB_KUALAANAU | DU00006502510 | Sarawak | Sarawak | 2.935200 | 112.827500 | [9 empty] | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 2X RTN910A 2X 13G 2.4M MS ANTENNA 2x ODU 13G XMC3 SUB A HI 2x ODU 13G XMC3 SUB A LO 2x ODU 13G XMC3 SUB B HI 2x ODU 13G XMC3 SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE Q01121-9115A WITH HUAWEI_13G_4+0_1.8M/1.8M_MS_28MHZ_256QAM_800MBPS_XMC3_SUB_A&B_WITH CA_LINK_12.0KM IMPACTED: Q01121 DISMANTLE EXISTING LINK Q01121-Q00865 | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MS ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A&B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK Q01121-Q00865 | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MS ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A&B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO LL 9115A 6. DISMANTLE EXISTING LINK Q01121-Q00865 | XMC3 | MS | 13G | 1.8 | 1.8 | Trintel | SQ202601300958-Trintel |  |  |  |  | Ongoing | 2026-01-23 | 2026-01-31 | 2026-01-23 | 2026-01-28 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-10 | 2026-03-10 | 2026-02-10 | 2026-02-10 | CHRISTINE IVY ANAK GIRIN7667000067 | Trintel TI | TRINTEL (M) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-04-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601070323-GCI | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00269_AD | Q142A_Q00269OD_RH_DINGON | DU00006502511 | Sarawak | Sarawak | 2.840140 | 112.781700 | [9 empty] | TSS+AA+TI |  | 13G_4+0_28M. NE_Q00269. 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Lo x1. FE_9178A/Q00259 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Hi x1. | MW New Link / Reroute | Link reroute to new FE Q02082 due to existing CP off loading. Install new link with 13G_4+0_28M. Site Impacted : Q00269 , Q02084 (SW03224). NE_Q00269. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Enable GE1 , transfer existing 9441P/Q00269_RTN01_GE2 to New RTN910A_GE1. carry Q02084. 6.Enable GE2 , ETH Patching Q00269_BBU. 7.Create service cross connect , CA and EPLA. 8.All traffic migrate to new link and new FE routing. 9.Decomm existing MW link (Q00269-Q00865). FE_9071P/Q02082. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Create new Inband DCN. 7.Enable GE1 , ETH patching to existing SM link IDU (9071P/Q02082-9114A) 8.All traffic migrate to new link and new FE routing and create POI (Maintain USP MONC) 9.Decomm existing MW link (Q00865-Q00269). | Link reroute to new FE Q02082 due to existing CP off loading. Install new link with 13G_4+0_28M. Site Impacted : Q00269 , Q02084 (SW03224). NE_Q00269. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Enable GE1 , transfer existing 9441P/Q00269_RTN01_GE2 to New RTN910A_GE1. carry Q02084. 6.Enable GE2 , ETH Patching Q00269_BBU. 7.Create service cross connect , CA and EPLA. 8.All traffic migrate to new link and new FE routing. 9.Decomm existing MW link (Q00269-Q00865). | Link reroute to new FE Q02082 due to existing CP off loading. Install new link with 13G_4+0_28M. Site Impacted : Q00269 , Q02084 (SW03224). FE_9071P/Q02082. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Create new Inband DCN. 7.Enable GE1 , ETH patching to existing SM link IDU (9071P/Q02082-9114A) 8.All traffic migrate to new link and new FE routing and create POI (Maintain USP MONC). 9.Decomm existing MW link (Q00865-Q00269). | XMC_5D Pro | MDD | 13G | 1.2 | 1.2 | Trintel | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601070323-GCI | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | CHEONG/SENG/WAH/7018000306
Q00690_AD | Q144A_Q00690OD_CB_KUALASANGAN | DU00006502512 | Sarawak | Sarawak | 2.751661 | 112.965904 | [9 empty] | TSS |  |  | MW New Link / Reroute | DROP SITE. ACCORDING TO GOP, NO SUITABLE FE CANDIDATE. 1 CLEAR LOS BUT TO SAME EXISTING CP | [7 empty] | Trintel | SQ202602250671-Trintel |  |  | 2026-02-28 | 2026-02-23 | Completed | 2026-01-24 | 2026-01-31 | 2026-01-24 | 2026-01-29 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-29 | 2026-02-28 | 2026-01-29 | 2026-01-29 | CHRISTINE IVY ANAK GIRIN7667000067 | Trintel TI | TRINTEL (M) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202601070323-GCI | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
2669A4_LOS | pBTS Desa Aman 2 ( R ) | DU00006502513 | Central | Kuala Lumpur | 3.207280 | 101.599320 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB B HI 1x ODU 23G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE 2669A4-1385B WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM_954MBPS_XMC3E_SUB_B_LINK_1.28KM IMPACTED: 2669A4 DISMANTLE EXISTING LINK 2669A4-1384B | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING 2669A4-1384B | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING 2669A4-1384B EXCEPT FE IDU | XMC3E | MAC | 23G | 0.6 | 0.6 | GCI | SQ202601210056-GCI | GCI | SQ202601210049-GCI // SQ202601210050-GCI | 2026-02-04 | 2026-02-05 | Completed | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-23 | 2026-01-24 | 2026-01-23 | 2026-01-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011618 |  | 2026-02-17 | 2026-01-20 | Completed | 2026-01-16 | 2026-02-17 | 2026-01-16 | 2026-01-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-20 | 2026-01-27 | 2026-01-20 | 2026-01-26 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-20 | 2026-01-27 | 2026-01-20 | 2026-01-26 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-22 | 2026-01-20 | 2026-01-27 | 2026-01-20 | 2026-01-27 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2026-01-20 | 2026-01-27 | 2026-01-20 | 2026-01-22 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601070316-GCI | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-15 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00262_AD | Q138A_Q00262OD_CB_BKTTT | DU00006502514 | Sarawak | Sarawak | 2.798444 | 112.679056 | [9 empty] | TSS+AA+TI |  | 15G_4+0_28M. NE_Q00262 15G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D Pro , Sub A_Hi x1. FE_9333B 15G_DP_1.2M(MDD) x1. ISM8 x2. XMC_5D Pro , Sub A_Lo x1. | MW New Link / Reroute | Link reroute to new FE 9333B due to existing CP off loading. Install new link with config 15G_4+0_28M. Site Impacted :Q00262. NE_Q00262 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D Pro , Sub A_Hi 4.Enable GE1 , Patching Q00262_BBU. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Decomm existing SW03059. FE_9333B 1.Install new 15G_DP_1.2M(MDD). 2.Reuse 9333B_RTN01 (ID : 35513). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 9333B_RTN01. 4.Install new XMC_5D Pro , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Create POI 8.Decom existing 3_ISM8-2+0 , ODU & ANT only. Remain RTN910A to support SW03337. | Link reroute to new FE 9333B due to existing CP off loading. Install new link with config 15G_4+0_28M. Site Impacted :Q00262. NE_Q00262 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D Pro , Sub A_Hi 4.Enable GE1 , Patching Q00262_BBU. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Decomm existing SW03059. | Link reroute to new FE 9333B due to existing CP off loading. Install new link with config 15G_4+0_28M. Site Impacted :Q00262. FE_9333B 1.Install new 15G_DP_1.2M(MDD). 2.Reuse 9333B_RTN01 (ID : 35513). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0 into existing 9333B_RTN01. 4.Install new XMC_5D Pro , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Create POI. 8.Decom existing 3_ISM8-2+0 , ODU & ANT only. Remain RTN910A to support SW03337. | XMC_5D Pro | MDD | 15G | 1.2 | 1.2 | Trintel | SQ202601300958-Trintel | Iezzpro | SQ202604300677-Iezzpro // SQ202604300686-Iezzpro | 2026-03-10 | 2026-02-12 | Completed | 2026-01-28 | 2026-01-31 | 2026-01-28 | 2026-01-28 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-10 | 2026-03-10 | 2026-02-10 | 2026-02-10 | CHRISTINE IVY ANAK GIRIN7667000067 | Trintel TI | TRINTEL (M) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26042788 |  | 2026-04-28 | 2026-05-01 | Completed | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-05-01 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-01 | 2026-06-01 | 2026-05-01 | 2026-05-05 | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | 2026-05-01 | 2026-06-01 | 2026-05-01 | 2026-05-05 | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | [7 empty] | 2026-05-01 | 2026-06-01 | 2026-05-01 |  | MOHAMAD TARMIZI//ISWANDI/6000060946 | 2025-03-06: 2026-05-01; 2025-03-06: 2026-06-01; 2025-03-06: 2026-05-01; 2025-03-07: 2026-05-01 | [7 empty] | GCI | SQ202601070323-GCI | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-25 | CHEONG/SENG/WAH/7018000306
Q00471_AD | Q144A_Q00471OD_CB_LDGWOODMAN | DU00006502515 | Sarawak | Sarawak | 3.010693 | 112.916321 | [9 empty] | TSS+AA+TI |  | 4X ISM8 CARD 2X RTN910A 2X 13G 1.2M MDD ANTENNA 1x ODU 13G XMC5DPRO SUB B HI 1x ODU 13G XMC5DPRO SUB B LO | MW New Link / Reroute | --FREQUENCY SCANNING NEEDED DUE TO 3 EXISTING PARALLEL LINK AT SITE-- MW NEW LINK/REROUTE Q00471-Q01114 WITH HUAWEI_13G_4+0_1.2M/1.2M_MDD_28MHZ_512QAM_800MBPS_XMC5D_SUB_B_WITH CA_LINK_9.9KM IMPACTED: Q00471 | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA | 1. INSTALL NEW IDU RTN910 WITH 2PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA | XMC5D | MDD | 13G | 1.2 | 1.2 | Trintel | SQ202602040291-Trintel | Iezzpro |  | 2026-03-13 | 2026-03-12 | Completed | 2026-01-28 | 2026-02-07 | 2026-01-28 | 2026-01-31 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-10 | 2026-03-10 | 2026-02-10 | 2026-02-10 | CHRISTINE IVY ANAK GIRIN7667000067 | Trintel TI | TRINTEL (M) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26050534 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202601070323-GCI | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
7542B_AD | Tuaran I | DU00006502516 | Sabah | Sabah | 6.179957 | 116.223204 | [7 empty] | 08. Pending RFS |  | TSS+AA+TI+Dismantle |  | 18G_4+0_112M_512QAM_CA NE_7542B New 18G_1.2M(MDD) x1. New RTN910AF(RTN03). New ISM8 x1. New IF cables with suitable length and type x2 RUN. New XMC_5D Pro, Sub A_Lo x1. New CAT6 cable x3. New SFP Module 1G with 10Km 1310nm x2(For cascading IDU-IDU). New Optical Patch Cord cable x2 with suitable type and length. FE_7238A New 18G_1.2M(MDD) x1. New RTN910AF(RTN04). New ISM8 x1. New IF cables with suitable length and type x2 RUN. New XMC_5D Pro, Sub A_Hi x1. New SFP Module 10G with 10Km 1310nm x2(For patching IDU-IBeam). New Optical Patch Cord cable x1 with suitable type and length. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(7846E) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 18G WITH BW 110MHZ IN ORDER TO ENSURE CHANNEL AVAILABILITY AT CP.**** Existing 2x HW MW Links as stated below: 1.7542B(RTN01, NEID 9-43177)-7634A(RTN01, NEID 9-43382), 23G_2+0_56MHZ_512QAM_EPLA. 2.7542B(RTN02, NEID 9-18751)-7634A(RTN01, NEID 9-43382), 18G_1+0_110MHZ_512QAM. Install new HW MW Link 7542B-7238A, 18G_4+0_110MHZ_512QAM_CA. Later, decom existing 2x HW MW Links 23G_2+0_56MHZ_512QAM_EPLA and 18G_1+0_110MHZ_512QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-18751) at NE(7542B). Site Impacted : 7542B, 7011C, 7316B, 7114H, 7846E & 7321H. NE_7542B 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN03) x1 and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 port 1 and slot 03 port 1. 5.Build new HW MW Link 7542B-7238A, 18G_4+0_110MHZ_512QAM_CA. 6.Enable port 8-EM6-1, port 8-EM6-2 of new RTN910AF(RTN03). 7.Insert new SFP Module 1G with 10Km 1310nm x1 into port 8-EM6-5(Optical) & port 8-EM6-6(Optical) of new RTN910AF(RTN03). Enable it. 8.Insert new SFP Module 1G with 10Km 1310nm x1 into port 8-EM6-5(Optical) & port 8-EM6-6(Optical) of existing RTN910AF(RTN02, NEID 9-18751). Enable it. 9.Perform patching port 8-EM6-1 of new RTN910AF(RTN03) to existing BBU(7542B). 10.Perform cascading between port 8-EM6-2 of new RTN910AF(RTN03) to NLOS 7542B-7846E(RTN510, NEID 150-27246). 11.Perform cascading between port 8-EM6-5(Optical) & port 8-EM6-6(Optical) of new RTN910AF(RTN03) to port 8-EM6-5(Optical) & port 8-EM6-6(Optical) of existing RTN910AF(RTN02, NEID 9-18751). Configure 2x 1G(Optical) LAG for IDU-IDU. 12.Enable port 8-EM6-1 and 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-18751). 13.Perform cascading port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-18751) to NLOS 7542B-7114H(RTN510, NEID 180-29590). 14.Perform cascading port 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-18751) to NLOS 7542B-7321H(RTN510, NEID 189-36812). 15.Request new xD Vlan DCN and Vlan Services. 16.Migrate traffics 7542B, 7011C, 7316B, 7114H, 7846E & 7321H via new HW MW Link 7542B-7238A, 18G_4+0_110MHZ_512QAM_CA. 17.Later, decom existing 2x HW MW Links 23G_2+0_56MHZ_512QAM_EPLA and 18G_1+0_110MHZ_512QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-18751) at NE(7542B). FE_7238A 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04) x1 and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 port 1 and slot 03 port 1. 5.Build new HW MW Link 7542B-7238A, 18G_4+0_110MHZ_512QAM_CA. 6.Insert new SFP Module 10G with 10Km 1310nm x1 into port 8-EM6-3(Optical) of new RTN910AF(RTN04). Enable it. 7.Request new 1x 10G port of IBeam from ZTE IPRAN Team. 8.Perform patching port 8-EM6-3(Optical) of new RTN910AF(RTN04) to new 1x 10G port of IBeam. 9.Request new xD Vlan DCN and Vlan Services. 10.Migrate traffics 7542B, 7011C, 7316B, 7114H, 7846E & 7321H via new 1x 10G port of IBeam. 11.Later, decom existing 2x HW MW Links 23G_2+0_56MHZ_512QAM_EPLA and 18G_1+0_110MHZ_512QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-18751) at NE(7542B). | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(7846E) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 18G WITH BW 110MHZ IN ORDER TO ENSURE CHANNEL AVAILABILITY AT CP.**** Existing 2x HW MW Links as stated below: 1.7542B(RTN01, NEID 9-43177)-7634A(RTN01, NEID 9-43382), 23G_2+0_56MHZ_512QAM_EPLA. 2.7542B(RTN02, NEID 9-18751)-7634A(RTN01, NEID 9-43382), 18G_1+0_110MHZ_512QAM. Install new HW MW Link 7542B-7238A, 18G_4+0_110MHZ_512QAM_CA. Later, decom existing 2x HW MW Links 23G_2+0_56MHZ_512QAM_EPLA and 18G_1+0_110MHZ_512QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-18751) at NE(7542B). Site Impacted : 7542B, 7011C, 7316B, 7114H, 7846E & 7321H. NE_7542B 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN03) x1 and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Lo x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 port 1 and slot 03 port 1. 5.Build new HW MW Link 7542B-7238A, 18G_4+0_110MHZ_512QAM_CA. 6.Enable port 8-EM6-1, port 8-EM6-2 of new RTN910AF(RTN03). 7.Insert new SFP Module 1G with 10Km 1310nm x1 into port 8-EM6-5(Optical) & port 8-EM6-6(Optical) of new RTN910AF(RTN03). Enable it. 8.Insert new SFP Module 1G with 10Km 1310nm x1 into port 8-EM6-5(Optical) & port 8-EM6-6(Optical) of existing RTN910AF(RTN02, NEID 9-18751). Enable it. 9.Perform patching port 8-EM6-1 of new RTN910AF(RTN03) to existing BBU(7542B). 10.Perform cascading between port 8-EM6-2 of new RTN910AF(RTN03) to NLOS 7542B-7846E(RTN510, NEID 150-27246). 11.Perform cascading between port 8-EM6-5(Optical) & port 8-EM6-6(Optical) of new RTN910AF(RTN03) to port 8-EM6-5(Optical) & port 8-EM6-6(Optical) of existing RTN910AF(RTN02, NEID 9-18751). Configure 2x 1G(Optical) LAG for IDU-IDU. 12.Enable port 8-EM6-1 and 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-18751). 13.Perform cascading port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-18751) to NLOS 7542B-7114H(RTN510, NEID 180-29590). 14.Perform cascading port 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-18751) to NLOS 7542B-7321H(RTN510, NEID 189-36812). 15.Request new xD Vlan DCN and Vlan Services. 16.Migrate traffics 7542B, 7011C, 7316B, 7114H, 7846E & 7321H via new HW MW Link 7542B-7238A, 18G_4+0_110MHZ_512QAM_CA. 17.Later, decom existing 2x HW MW Links 23G_2+0_56MHZ_512QAM_EPLA and 18G_1+0_110MHZ_512QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-18751) at NE(7542B). | ****IMPORTANT NOTE: 1.PLEASE APPLY CRQ FOR EB(7846E) & DO NOT PROCEED UPGRADING IF CRQ NOT OBTAIN YET. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 18G WITH BW 110MHZ IN ORDER TO ENSURE CHANNEL AVAILABILITY AT CP.**** Existing 2x HW MW Links as stated below: 1.7542B(RTN01, NEID 9-43177)-7634A(RTN01, NEID 9-43382), 23G_2+0_56MHZ_512QAM_EPLA. 2.7542B(RTN02, NEID 9-18751)-7634A(RTN01, NEID 9-43382), 18G_1+0_110MHZ_512QAM. Install new HW MW Link 7542B-7238A, 18G_4+0_110MHZ_512QAM_CA. Later, decom existing 2x HW MW Links 23G_2+0_56MHZ_512QAM_EPLA and 18G_1+0_110MHZ_512QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-18751) at NE(7542B). Site Impacted : 7542B, 7011C, 7316B, 7114H, 7846E & 7321H. FE_7238A 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04) x1 and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A_Hi x1. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 port 1 and slot 03 port 1. 5.Build new HW MW Link 7542B-7238A, 18G_4+0_110MHZ_512QAM_CA. 6.Insert new SFP Module 10G with 10Km 1310nm x1 into port 8-EM6-3(Optical) of new RTN910AF(RTN04). Enable it. 7.Request new 1x 10G port of IBeam from ZTE IPRAN Team. 8.Perform patching port 8-EM6-3(Optical) of new RTN910AF(RTN04) to new 1x 10G port of IBeam. 9.Request new xD Vlan DCN and Vlan Services. 10.Migrate traffics 7542B, 7011C, 7316B, 7114H, 7846E & 7321H via new 1x 10G port of IBeam. 11.Later, decom existing 2x HW MW Links 23G_2+0_56MHZ_512QAM_EPLA and 18G_1+0_110MHZ_512QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-18751) at NE(7542B). | XMC-5D Pro | MDD | 18G | 18G_1.2M(MDD) x1 | 18G_1.2M(MDD) x1 | NR services | SQ202603060636-NR Services | NR services | SQ202603170069-NR Services // SQ202603170077-NR Services |  |  | Ongoing | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-23 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26030334 |  | 2026-03-04 | 2026-03-15 | Completed | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-13 | 2026-04-13 | 2026-03-13 | 2026-03-15 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-03-13 | 2026-04-13 | 2026-03-13 | 2026-03-27 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | [7 empty] | 2026-03-13 | 2026-04-13 | 2026-03-13 | 2026-04-08 | RALPH O'BRYAN HILARY7167000030 | 2025-03-06: 2026-03-13; 2025-03-06: 2026-04-13; 2025-03-06: 2026-03-13; 2025-03-07: 2026-03-13 | [7 empty] | GTSB | SQ202601070339-GTSB
1892B_HU_1 | NS HW KM435(Maxis) | DU00006511576 | Central | Selangor | 3.380000 | 101.559900 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cat 6 x1 | BBU Patching | Offload traffic from HU link (1892B_RTN02) to no traffic link (1892B_RTN01) Patch 1892B BBU to 1892B_RTN01_GE1. Impacted site: 1) 1892B | Offload traffic from HU link (1892B_RTN02) to no traffic link (1892B_RTN01) Patch 1892B BBU to 1892B_RTN01_GE1. Impacted site: 1) 1892B | [6 empty] | GCI | SQ202602230131-GCI | GCI | SQ202602230127-GCI | 2026-03-13 | 2026-03-12 | Completed | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-06 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26022312 |  | 2026-02-24 | 2026-02-26 | Completed | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-10 | 2026-03-02 | 2026-03-06 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-03-03 | 2026-03-10 | 2026-03-02 | 2026-03-06 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-03-03 | 2026-03-10 | 2026-03-02 | 2026-03-06 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-03-06: 2026-03-03; 2025-03-06: 2026-03-10; 2025-03-06: 2026-03-02; 2025-03-07: 2026-03-06 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202601210773-GCI | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | CHEONG/SENG/WAH/7018000306
7328H11_EVT | IMACRO HARVESTFESTIVAL LAUNCHING CEREMONY 2026 € | DU00006773269 | Sabah | Sabah | 5.731103 | 115.934240 | [13 empty] | Planning and integration support only for event site 7328H11_EVT IMACRO HARVEST FESTIVAL LAUNCHING CEREMONY 2026 Tx route: 7328H11/7328H11-7535A 1) Share port with 7550A at 7535A-MAC-001 Sapat Mogon 2) 9-35865 NE ID FE IDU 7535A RTN03 3) 9-27243 NE ID NE IDU 7328H11 RTN01 Cascade to RTN03 and transfer existing NLOS to new IDU | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q00389_AD | Q141A_Q00389OD_CB_TMSEBUYAU | DU00006786657 | Sarawak | Sarawak | 1.514700 | 110.933600 | [21 empty] | YPTT | [5 empty] | Ongoing | 2026-05-11 | 2026-05-30 | 2026-05-11 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. |  | Assigned | Ongoing |  | 2026-05-11 | 2026-05-30 | 2026-05-11 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. |  | Assigned | Ongoing |  | 2026-05-11 | 2026-05-30 | 2026-05-11 |  | CARLOS OLLERENSHAW IKOM ANAK DENNIS RICHARD6794000080 | YPTT TI | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. |  | Assigned | Ongoing | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [25 empty] | 2025-03-06: 2026-05-11; 2025-03-06: 2026-05-30; 2025-03-06: 2026-05-11 | [7 empty] | GTSB | SQ202605060269-GTSB
B02922_AD | B064H_B02922OD_JLNSENTOSA11TERASJERNANG3 | DU00006786658 | Central | Selangor | 2.912943 | 101.753076 | [11 empty] | ZTE MW 18G_1+0_112M NE_B02922. 18G_SP_0.6M x1 NR9150 x1 SRU2 , Sub A_Lo x1. FE_1841B 18G_SP_0.6M x1. NR9150 x1. SRU2 , Sub A_Hi x1. | MW New Link / Reroute | Existing link 18G_1+0_112M reroute to new FE 1841B due to Pemutihan site. New config with ZTE MW 18G_1+0_112M Site Impacted : B02922. NE_B02922. 1.Install new 18G_SP_0.6M 2.Install new NR9150 3.Install new SRU2 , Sub A_Lo. 4.Create Service cross connect. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. FE_1841B 1.Install new 18G_SP_0.6M. 2.Install new NR9150 3.Install new SRU2 , Sub A_Hi. 4.Create service cross connect & new Inband DCN. 5.Enable GE4 , ETH patchinng to existing 1841B_RTN01. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | Existing link 18G_1+0_112M reroute to new FE 1841B due to Pemutihan site. New config with ZTE MW 18G_1+0_112M Site Impacted : B02922. NE_B02922. 1.Install new 18G_SP_0.6M 2.Install new NR9150 3.Install new SRU2 , Sub A_Lo. 4.Create Service cross connect. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. | Existing link 18G_1+0_112M reroute to new FE 1841B due to Pemutihan site. New config with ZTE MW 18G_1+0_112M Site Impacted : B02922. FE_1841B 1.Install new 18G_SP_0.6M. 2.Install new NR9150 3.Install new SRU2 , Sub A_Hi. 4.Create service cross connect & new Inband DCN. 5.Enable GE4 , ETH patchinng to existing 1841B_RTN01. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | SRU2 | SP | 18G | 0.6 | 0.6 | GTSB | SQ202604290755-GTSB | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202605060248-GCI | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | CHEONG/SENG/WAH/7018000306
1834B_AD | BangiLama | DU00006786659 | Central | Selangor | 2.896554 | 101.781386 | [9 empty] | TSS+AA+TI+Dismantle |  | 2X 1G SFP 2X RTN910A 1X 23G 0.3M MAC ANTENNA 1X 23G 1.2M MS ANTENNA 1x ODU 23G XMC3E SUB A HI 1x ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1x ODU 23G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE 1834B-2501A WITH HUAWEI_23G_2+0_0.3M/1.2M_MAC_112MHZ_256QAM_1556MBPS_XMC3E_SUB_A & B_LINK_2.11KM DISMANTLE EXISTING LINK 1834B-1057A IMPACTED: 1834B,1532H | 1. INSTALL NEW RTN910 2. INSTALL NEW 23G 0.3M MAC ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK 1834B-1057A | 1. INSTALL NEW RTN910 2. INSTALL NEW 23G 1.2M MS ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 256QAM 5. PATCH TO NEW FIBER PORT AND DO PORT LAG 2G 6. DISMANTLE EXISTING LINK 1834B-1057A | XMC3E | MAC | 23G | 0.3 | 1.2 | GTSB | SQ202604290755-GTSB | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202605060248-GCI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | EZRIN TASNIM BIN ABDUL GANI6798000128
1134B_AD | Bt 22 Sg Lui | DU00006786660 | Central | Selangor | 3.159190 | 101.905000 | [9 empty] | TSS+TI+Dismantle |  | 2X RTN910A 2X 18G 0.6M MAC ANTENNA 1x ODU 18G XMC3E SUB A HI 1x ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1x ODU 18G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE 1134B-B02448 WITH HUAWEI_18G_2+0_0.6M/0.6M_SP_112MHZ_128QAM_1352MBPS_XMC3E_SUB_A & B_WITH CA_LINK_2.45KM DISMANTLE EXISTING LINK 1134B-B00445 IMPACTED: 1134B | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M SP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM 5. DISMANTLE EXISTING LINK 1134B-B00445 | NE: 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M SP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 128QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK 1134B-B00445 | XMC3E | MAC | 18G | 0.6 | 0.6 | GTSB | SQ202604290755-GTSB | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202605060248-GCI | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | EZRIN TASNIM BIN ABDUL GANI6798000128
3014A_AD | BDR DAMAIPERDANA 2 | DU00006786661 | Central | Selangor | 3.044981 | 101.736534 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | IF cable x1 | MW Swap | NE_3014A. Relocate MW from MW at bottom tier to top tier due to complaint from site owner (KJS). 1. Relocate MW ant to top tier link to 1039A. (0.6m) 2. Relocate MW ant to top tier link to 3640A. (0.6m) | NE_3014A. Relocate MW from MW at bottom tier to top tier due to complaint from site owner (KJS). 1. Relocate MW ant to top tier link to 1039A.(0.6M) 2. Relocate MW ant to top tier link to 3640A.(0.6M) | [6 empty] | Magicell | SQ202605070532-Magicell | Magicell |  |  |  | Ongoing | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050312 |  | 2026-05-04 | 2026-05-06 | Completed | 2026-05-03 | 2026-05-04 | 2026-05-03 | 2026-05-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-06 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-06 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | AZRUL FIKRAM BIN MOHD THANI6237000863 |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-06 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | 2025-03-06: 2026-04-30; 2025-03-06: 2026-04-30; 2025-03-06: 2026-04-30; 2025-03-07: 2026-04-30 | [7 empty] | GCI | SQ202605060248-GCI | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | CHEONG/SENG/WAH/7018000306
2070B_IPR | Sri Gombak (TX) | DU00006786662 | Central | Selangor | 3.244528 | 101.710361 | [9 empty] | TSS+TI |  | 2X 1G SFP 2X LAN CABLE (SUITABLE LENGTH) | MW IDU Patching | Perform LAG at CP site for IDU 2070B-SRI GOMBAK (TX)-RTN03 to 2070B-MAC-001 Gombak TX 1) Patch IDU 2070B RTN03 GE2 to new CP port 2) Create LAG 3) Impact sites: 2467A, 2307A | Perform LAG at CP site for IDU 2070B-SRI GOMBAK (TX)-RTN03 to 2070B-MAC-001 Gombak TX 1) Patch IDU 2070B RTN03 GE2 to new CP port 2) Create LAG 3) Impact sites: 2467A, 2307A | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050111 |  | 2026-05-04 | 2026-05-06 | Completed | 2026-05-01 | 2026-05-04 | 2026-05-01 | 2026-05-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202604280391-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
1396E_AD | ForesightIndustries Puncak Alam | DU00006786663 | Central | Selangor | 3.247320 | 101.448340 | [21 empty] | GTSB | SQ202604290755-GTSB | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202605060248-GCI
B02503_AD | B064H_B02503OD_KUIS | DU00006786664 | Central | Selangor | 2.890869 | 101.783750 | [11 empty] | 23G_2+0_112M. NE_B02503. 23G_DP_0.3M(MAC) x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2.. FE_1834B. 23G_DP_0.3M(MAC) x1. ISM8 x1 XMC_3E , Sub A & B_Lo x2. | MW New Link / Reroute | Existing link 18G_2+0_112M reroute to new FE 1834B due to Pemutihan. New config with 23G_2+0_112M. Site Impacted : B02503. NE_B02503. 1.Install new 23G_DP_0.3M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. FE_1834B. 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing 1834B_RTN02 , 4_ISM8-2+0. 3.Install new 4_SIM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | Existing link 18G_2+0_112M reroute to new FE 1834B due to Pemutihan. New config with 23G_2+0_112M. Site Impacted : B02503. NE_B02503. 1.Install new 23G_DP_0.3M(MAC). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. | Existing link 18G_2+0_112M reroute to new FE 1834B due to Pemutihan. New config with 23G_2+0_112M. Site Impacted : B02503. FE_1834B. 1.Install new 23G_DP_0.3M(MAC). 2.Reuse existing 1834B_RTN02 , 4_ISM8-2+0. 3.Install new 4_SIM8-2+0. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | XMC_3E | MAC | 23G | 0.3 | 0.3 | GTSB | SQ202604290755-GTSB | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202605060248-GCI | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | CHEONG/SENG/WAH/7018000306
1145B_AD | UKMFakulti Pendidikan (JBA) | DU00006786665 | Central | Selangor | 2.922029 | 101.775526 | [9 empty] | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 2X RTN910A 1X 15G 0.6M MS ANTENNA 1X 15G 1.2M MS ANTENNA 2x ODU 15G XMC3 SUB A HI 2x ODU 15G XMC3 SUB A LO 2x ODU 15G XMC3 SUB B HI 2x ODU 15G XMC3 SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE 1145B-1058A WITH HUAWEI_15G_4+0_0.6M/1.2M_MDD_28MHZ_512QAM_896MBPS_XMC3_SUB_A & B_WITH CA_LINK_3.99KM DISMANTLE EXISTING LINK 1145B-3023C IMPACTED: 1145B | 1. INSTALL NEW RTN910 WITH 2 PCS ISM8 AT SLOT 3 AND 4 2. INSTALL NEW 15G 0.6M MS ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK 1145B-3023C | 1. INSTALL NEW RTN910 WITH 2 PCS ISM8 AT SLOT 3 AND 4 2. INSTALL NEW 15G 1.2M MS ANTENNA 3. INSTALL NEW ODU 15G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK 1145B-3023C | XMC3 | MS | 15G | 0.6 | 1.2 | GTSB | SQ202604290755-GTSB | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202605060248-GCI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | EZRIN TASNIM BIN ABDUL GANI6798000128
3032L_HU | Tmn Bayu Indera Lukut | DU00005955440 | Southern | Sembilan | 2.578350 | 101.860880 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 4X ISM8 CARD 2X 15G 1.2M MDD ANTENNA 1x ODU 15G XMC5D SUB A HI 1X ODU 15G XMC5D SUB A LO | MW Parallel Link | MW PARALLEL LINK 3032L-1760A WITH HUAWEI_15G_4+0_1.2M/1.2M_DP_28MHZ_512QAM_896MBPS_XMC5D_WITH CA_SUB_A_EPLA WITH EXISTING 1+0_6.3KM IMPACTED: 3032L | 1. INSTALL 2PCS ISM8 AT EXISTING RTN SLOT 3 AND 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. EPLA WITH EXISTING 1+0 | 1. INSTALL 2PCS ISM8 AT EXISTING RTN SLOT 3 AND 4 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 15G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 15G 4+0 28MHZ 512QAM WITH CA 5. EPLA WITH EXISTING 1+0 | XMC5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202508290713-Magicell | Magicell | SQ202509020145-Magicell // SQ202509020147-Magicell // SQ202602220062-Magicell | 2025-12-06 | 2025-12-10 | Completed | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-05 | 2025-12-06 | 2025-12-05 | 2025-12-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082836 |  | 2025-09-09 | 2025-10-29 | Completed | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-10-29 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-10-29 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-10-29 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-11 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-10-28 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-03-06: 2025-09-09; 2025-03-06: 2025-09-09; 2025-03-06: 2025-09-09; 2025-03-07: 2025-09-18 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202508150538-GCI | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | EZRIN TASNIM BIN ABDUL GANI6798000128
9088A_IPR | CURTINSACOFA | DU00005963794 | Sarawak | Sarawak | 4.505464 | 114.010071 | [7 empty] | 00. Integrated/RFS Done | 4/9/2025 : Cutover done, pending declare 3/9/2025 : Plan to do IDU-IPRAN - Fallback due to time limited | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9088A RTN01 10G PORT 9088A-LL-9074A SWAP RTN01 TO NEW RTN910A DUE TO NEED 10G PORT Install 1 10G SFP Optical at SACOFA Port 1-3-15 / TB-Core 11&12 Install 1 10G SFP Optical at HW 9088A NEW RTN 8-EM6-3(PORT-3) Remove LAG Port Configuration 8-EM6-1 & 8-EM6-2 Reconfigure Traffic for All 4 Sites: 9088A, 9601A, 9702B, 2666A | 9088A RTN01 10G PORT 9088A-LL-9074A SWAP RTN01 TO NEW RTN910A DUE TO 10G PORT Install 1 10G SFP Optical at SACOFA Port 1-3-15 / TB-Core 11&12 Install 1 10G SFP Optical at HW 9088A NEW RTN 8-EM6-3(PORT-3) Remove LAG Port Configuration 8-EM6-1 & 8-EM6-2 Reconfigure Traffic for All 4 Sites: 9088A, 9601A, 9702B, 2666A | N/A | [5 empty] | Allstar | SQ202509040277-Allstar | Allstar | SQ202509020140-Allstar // SQ202512170142-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082413 |  | 2025-08-25 | 2025-08-27 | Completed | 2025-08-24 | 2025-08-25 | 2025-08-24 | 2025-08-27 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-02 | 2025-09-08 | 2025-09-18 | 2025-09-18 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-02 | 2025-09-08 | 2025-09-18 | 2025-09-18 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-05 | 2025-09-02 | 2025-09-08 | 2025-09-16 | 2025-09-16 | ROYSTON//AHHOLE/6000038561 | 2025-03-06: 2025-09-02; 2025-03-06: 2025-09-08; 2025-03-06: 2025-09-08; 2025-03-07: 2025-09-08 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202508150536-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
9556A_IPR | Miri Port | DU00005963795 | Sarawak | Sarawak | 4.559936 | 114.038521 | [7 empty] | 00. Integrated/RFS Done | 4/9/2025 : Cutover done 3/9/2025 : Plan to do IDU-IPRAN - Cancel proceed due to stuck at site 9088A_IPR | TSS+TI | L1+ATP+PAC | 2x10G SFP Optical 10KM 2x Patch Cord(Pair) | IDU-IPRAN | 9556A RTN01 10G PORT 9556A/9556A-LL-9074A SWAP RTN01 TO NEW RTN910A DUE TO 10G PORT Install 1 10G SFP Optical at SACOFA Port 1-1-4 Install 1 10G SFP Optical at HW 9556A NEW RTN 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port1-1-4 to HW 9556A NEW RTN 8-EM6-3(PORT-3) Reconfigure Traffic for All 2 Sites: 9556A, 9592A | 9556A RTN01 10G PORT 9556A/9556A-LL-9074A SWAP RTN01 TO NEW RTN910A DUE TO 10G PORT Install 1 10G SFP Optical at SACOFA Port 1-1-4 Install 1 10G SFP Optical at HW 9556A NEW RTN 8-EM6-3(PORT-3) Patching Optical Patch Cord SACOFA Port1-1-4 to HW 9556A NEW RTN 8-EM6-3(PORT-3) Reconfigure Traffic for All 2 Sites: 9556A, 9592A | [6 empty] | Allstar | SQ202509040277-Allstar | Allstar | SQ202509020140-Allstar // SQ202512170142-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082414 |  | 2025-08-25 | 2025-08-27 | Completed | 2025-08-24 | 2025-08-25 | 2025-08-24 | 2025-08-27 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-02 | 2025-09-08 | 2025-10-17 | 2025-10-17 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-02 | 2025-09-08 | 2025-10-17 | 2025-10-17 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-04 | 2025-09-02 | 2025-09-08 | 2025-10-05 | 2025-10-17 | ROYSTON//AHHOLE/6000038561 | 2025-03-06: 2025-09-02; 2025-03-06: 2025-09-08; 2025-03-06: 2025-09-19; 2025-03-07: 2025-09-19 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202508150536-GCI | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
9494A_IPR | Kg Bayor | DU00005963796 | Sarawak | Sarawak | 1.236640 | 110.291530 | [7 empty] | 00. Integrated/RFS Done | 10/9/2025 : Vandalism site | TSS+TI | L1+ATP+PAC | NE_9494A 10G SFP module x2. Fiber Patch Cord x 1 pairs. | MW IDU Patching | Site Impacted : 9187R , 9494A NE_9494A 1.Install new 10G SFP module at existing 9494A_RTN01_GE3 (ID : 24053). 2.Install new 10G SFP module at 10G new Sacofa Port Ge_1-2-2. 3.Patching Fiber patch cord from 9494A_RTN01_GE3 to new sacofa port 10G Ge_1-2-2. 4.Disconnect existing LAN cable to Old sacofa port and disable unused port. 5.Create service cross connect and migrate entire traffic to new sacofa port Ge_1-2-2. | Site Impacted : 9187R , 9494A NE_9494A 1.Install new 10G SFP module at existing 9494A_RTN01_GE3 (ID : 24053). 2.Install new 10G SFP module at 10G new Sacofa Port Ge_1-2-2. 3.Patching Fiber patch cord from 9494A_RTN01_GE3 to new sacofa port 10G Ge_1-2-2. 4.Disconnect existing LAN cable to Old sacofa port and disable unused port. 5.Create service cross connect and migrate entire traffic new sacofa port Ge_1-2-2. | [6 empty] | Allstar | SQ202510090453-Allstar | Allstar | SQ202510090446-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-10-29 | 2025-10-29 | 2025-10-29 | 2025-10-29 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-12 | 2025-12-18 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251008BC |  | 2025-10-09 | 2025-10-10 | Completed | 2025-10-08 | 2025-10-09 | 2025-10-08 | 2025-10-10 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-07 | 2025-10-14 | 2025-08-28 | 2025-10-21 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-21 | ROYSTON//ANAK RAMSY/6798000228 | Allstar TI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-07 | 2025-10-07 | 2025-10-14 | 2025-08-28 | 2025-10-21 | ROYSTON//ANAK RAMSY/6798000228 | 2025-03-06: 2025-10-07; 2025-03-06: 2025-10-14; 2025-03-06: 2025-08-28; 2025-03-07: 2025-10-07 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202508150536-GCI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | CHEONG/SENG/WAH/7018000306
9493A_IPR | Kg Bengoh | DU00005963797 | Sarawak | Sarawak | 1.238974 | 110.262857 | [7 empty] | 00. Integrated/RFS Done | 9/9/2025 : Cutover done | TSS+TI | L1+ATP+PAC | NE_9493A 10G SFP module x4. Fiber Patch cord x 2 pairs | MW IDU Patching | Site Impacted : 9493A , 9497A , 9196R , 9185R , 9186R , 9184R , 9193R , 9498A. NE_9493A 1.Install new 10G SFP module at existing 9493A_RTN01_GE3 & GE4 ( ID : 20311). 2.Install new 10G SFP module at 10G new Sacofa Port Ge_1-4-1. 3.Install new 10G SFP module at existing 9493A_RTN02_GE3 ( ID : 20826). 4.Patching Fiber patch cord from 9493A_RTN01_GE3 to New Sacofa Port Ge_1-4-1. 5.Patching Fiber patch cord from 9493A_RTN02_GE3 to 9493A_RTN01_GE4 ( IDU interconnect). 6.Disconnect existing LAN cable connect to Old LL port & Old IDU Interconnect cable and disable unused port. 7.Create cross connect and migrate entire traffic to 10G New Sacoaf Port Ge_1-4-1. | Site Impacted : 9493A , 9497A , 9196R , 9185R , 9186R , 9184R , 9193R , 9498A. NE_9493A 1.Install new 10G SFP module at existing 9493A_RTN01_GE3 & GE4 ( ID : 20311). 2.Install new 10G SFP module at 10G new Sacofa Port Ge_1-4-1. 3.Install new 10G SFP module at existing 9493A_RTN02_GE3 ( ID : 20826). 4.Patching Fiber patch cord from 9493A_RTN01_GE3 to New Sacofa Port Ge_1-4-1. 5.Patching Fiber patch cord from 9493A_RTN02_GE3 to 9493A_RTN01_GE4 ( IDU interconnect). 6.Disconnect existing LAN cable connect to Old LL port & Old IDU Interconnect cable and disable unused port. 7.Create cross connect and migrate entire traffic to 10G New Sacoaf Port Ge_1-4-1. | [6 empty] | Trintel | SQ202509040637-Trintel | Trintel | SQ202509040617-Trintel | 2025-11-11 | 2025-11-10 | Completed | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-11 | 2025-09-12 | 2025-09-11 | 2025-09-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-11 | 2025-09-12 | 2025-09-11 | 2025-09-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25082320 |  | 2025-08-24 | 2025-09-08 | Completed | 2025-08-23 | 2025-08-24 | 2025-08-23 | 2025-09-08 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-09 | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-09 | MATTHEW//ANAK ARON/6000043057 | Trintel TI | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-09 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-09 | MATTHEW//ANAK ARON/6000043057 | 2025-03-06: 2025-09-08; 2025-03-06: 2025-09-08; 2025-03-06: 2025-09-08; 2025-03-07: 2025-09-09 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202508150536-GCI | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | CHEONG/SENG/WAH/7018000306
7729B-7512A | Pemodalan | DU00004980562 | Sabah | Sabah | 5.518029 | 118.444436 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | DO ready | TSS+AA+TI | L1+ATP+PAC | 15G 2+0 1.2m/1.2m MDD XMC5D sub A NE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 15G XMC5D sub A Hi 4) 1 x 15G 1.2m MDD FE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 15G XMC5D sub A Lo 4) 1 x 15G 1.2m MDD | MW Parallel Link | Install new parallel 2+0 link for 7729B traffic only. Use XMC5D in case need to upgrade to 4+0 in future. Impact sites: 7729B Tx route: 7729B-7512A-7585A NE (7729B): 1) Install new RTN910A 2) Add ISM8 card at new RTN slot 3 and 4 3) Install new link V at 3-ISM8-1 4) Install new link H at 4-ISM8-1 5) Configure 2+0 (no CA) link. 6) Migrate 7729B traffic to new link FE (7512A): 1) Install new RTN910A 2) Add ISM8 card at new RTN slot 3 and 4 3) Install new link V at 3-ISM8-1 4) Install new link H at 4-ISM8-1 5) Configure 2+0 (no CA) link. 6) Patch new RTN GE1 to existing RTN05 GE3 7) Migrate 7729B traffic to new link/route | NE (7729B): 1) Install new RTN910A 2) Add ISM8 card at new RTN slot 3 and 4 3) Install new link V at 3-ISM8-1 4) Install new link H at 4-ISM8-1 5) Configure 2+0 (no CA) link. 6) Migrate 7729B traffic to new link | FE (7512A): 1) Install new RTN910A 2) Add ISM8 card at new RTN slot 3 and 4 3) Install new link V at 3-ISM8-1 4) Install new link H at 4-ISM8-1 5) Configure 2+0 (no CA) link. 6) Patch new RTN GE1 to existing RTN05 GE3 7) Migrate 7729B traffic to new link/route | XMC5D | MDD | 15G | 1.2m | 1.2m | NR services | SQ202504080161-NR Services | NR services | SQ202504080097-NR Services // SQ202504080100-NR Services // SQ202504260199-NR Services | 2025-07-11 | 2025-07-10 | Completed | 2025-02-19 | 2025-02-26 | 2025-02-24 | 2025-02-24 | MUHD//KHAIRUL NIZAM/7023000104 | NR Service TI | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-17 | 2025-03-21 | 2025-03-19 | 2025-03-19 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-25 | 2025-04-21 | 2025-04-21 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-10 | 2025-07-11 | 2025-07-10 | 2025-07-10 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021589 |  | 2025-02-16 | 2025-02-18 | Completed | 2025-02-15 | 2025-02-16 | 2025-02-15 | 2025-02-18 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-03-04 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-03-04 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-03-04 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | 2025-03-06: 2025-02-24; 2025-03-06: 2025-02-28; 2025-03-06: 2025-02-24; 2025-03-07: 2025-03-04 |  |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016
9199A-9200A | Kabong Bazaar | DU00004980563 | Sarawak | Sarawak | 1.803158 | 111.116450 | [7 empty] | 00. Integrated/RFS Done | 0617: Site fiberized. 2605: Doable. Pending material DT. | TSS+AA+TI | L1+ATP+PAC | 13G 2+0 1.8m/1.8m MAC DP XMC3 sub A/B NE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 13G XMC3 sub A Lo 4) 1 x 13G XMC3 sub B Lo 5) 1 x 13G 1.8m MAC DP FE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 13G XMC3 sub A Hi 4) 1 x 13G XMC3 sub B Hi 5) 1 x 13G 1.8m MAC DP | MW Parallel Link | Install parallel 2+0 link EPLA with existing 4+0 link to create 6+0 Impact sites: 9199A,9033R Tx route: 9199A/9199A-9200A-LL-9368A NE (9199A): 1) Swap existing RTN01 with new RTN910A 2) Install new 2xISM8 at slot 3 and 4 3) Transfer existing link RTN01 7-ISM6 to new RTN 7-ISM8 4) Transfer existing RTN01 3-ISV3 to new RTN 3-ISM8-1 5) Transfer existing RTN01 4-ISV3 to new RTN 3-ISM8-2 6) Install new link at new RTN 4-ISM8 7) Configure 6+0 EPLA 8) Migrate 9199A to new link FE (9200A): 1) Swap existing RTN01 with new RTN910A 2) Install new 2xISM8 at slot 3 and 4 3) Transfer existing link RTN01 7-ISM6 to new RTN 7-ISM8 4) Transfer existing RTN01 3-ISV3 to new RTN 3-ISM8-1 5) Transfer existing RTN01 4-ISV3 to new RTN 3-ISM8-2 6) Install new link at new RTN 4-ISM8 7) Configure 6+0 EPLA 8) New RTN GE1 to SACOFA LL 9) New RTN GE2 to RTN02 GE1 10) Reconfigure DCN using old RTN setting | NE (9199A): 1) Swap existing RTN01 with new RTN910A 2) Install new 2xISM8 at slot 3 and 4 3) Transfer existing link RTN01 7-ISM6 to new RTN 7-ISM8 4) Transfer existing RTN01 3-ISV3 to new RTN 3-ISM8-1 5) Transfer existing RTN01 4-ISV3 to new RTN 3-ISM8-2 6) Install new link at new RTN 4-ISM8 7) Configure 6+0 EPLA 8) Migrate 9199A to new link | FE (9200A): 1) Swap existing RTN01 with new RTN910A 2) Install new 2xISM8 at slot 3 and 4 3) Transfer existing link RTN01 7-ISM6 to new RTN 7-ISM8 4) Transfer existing RTN01 3-ISV3 to new RTN 3-ISM8-1 5) Transfer existing RTN01 4-ISV3 to new RTN 3-ISM8-2 6) Install new link at new RTN 4-ISM8 7) Configure 6+0 EPLA 8) New RTN GE1 to SACOFA LL 9) New RTN GE2 to RTN02 GE1 10) Reconfigure DCN using old RTN setting | XMC3 | MAC DP | 13G | 1.8m | 1.8m | Trintel | SQ202502260453-Trintel | iEzzpro | SQ202601220796-Iezzpro // SQ202601220797-Iezzpro | 2025-02-28 | 2025-02-26 | Completed | 2025-02-17 | 2025-02-18 | 2025-02-17 | 2025-02-18 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-02-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112627 |  | 2025-11-27 | 2025-12-23 | Completed | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-12-23 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-03-10 | MOHAMAD TARMIZI//ISWANDI/6000060946 | Iezzpro TI | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-27 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-03-10 | MOHAMAD TARMIZI//ISWANDI/6000060946 | 2025-03-06: 2026-01-09; 2025-03-06: 2026-01-09; 2025-03-06: 2026-01-09; 2025-03-07: 2026-03-09 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402
9425A-9441A_1 | KUCHING DIGI CENTER | DU00004980564 | Sarawak | Sarawak | 1.554087 | 110.332175 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | NE: 1. 23G XMC3 112MHz sub B Lo 2. 23GHz balanced coupler 3. IF cable + accessories FE: 1. 23G XMC3 112MHz sub B Hi 2. 23GHz balanced coupler 3. IF cable + accessories | MW Hardware Upgrade | Upgrade existing 1+0 link to 1+1 for redundancy purpose NE(9425A): 1) Add 23G coupler and second ODU at existing antenna 2) Install new IF cable for new ODU from RTN01 7-ISM8-2 3) Increase Tx power. Configure link as 1+1 FE(9441A): 1) Add 23G coupler and second ODU at existing antenna 2) Install new IF cable for new ODU from RTN01 7-ISM8-2 3) Increase Tx power. Configure link as 1+1 | NE(9425A): 1) Add 23G coupler and second ODU at existing antenna 2) Install new IF cable for new ODU from RTN01 7-ISM8-2 3) Increase Tx power. Configure link as 1+1 | FE(9441A): 1) Add 23G coupler and second ODU at existing antenna 2) Install new IF cable for new ODU from RTN01 7-ISM8-2 3) Increase Tx power. Configure link as 1+1 | XMC3 |  | 23G | 23G Balance Coupler | 23G Balance Coupler | Trintel | SQ202503060206-Trintel | Trintel | SQ202503050499-Trintel // SQ202504260214-Trintel | 2025-03-14 | 2025-03-12 | Completed | 2025-02-26 | 2025-02-27 | 2025-02-26 | 2025-02-27 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-12 | 2025-03-14 | 2025-03-12 | 2025-03-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-12 | 2025-03-14 | 2025-03-12 | 2025-03-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-12 | 2025-03-14 | 2025-03-12 | 2025-03-12 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250219AD |  | 2025-02-20 | 2025-02-24 | Completed | 2025-02-19 | 2025-02-20 | 2025-02-19 | 2025-02-24 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2025-03-25 | 2025-02-26 | 2025-02-26 | Chin Sun Lun7667000040 | Trintel TI | 2025-02-25 | 2025-03-25 | 2025-02-26 | 2025-03-10 | Chin Sun Lun7667000040 | Trintel TI | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-02-25 | 2025-03-25 | 2025-03-21 | 2025-03-21 | Chin Sun Lun7667000040 | 2025-03-06: 2025-02-25; 2025-03-06: 2025-03-25; 2025-03-06: 2025-03-10; 2025-03-07: 2025-03-10 |  |  | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
7648C-7124A | Kampung Mangkalinau | DU00004980565 | Sabah | Sabah | 5.871088 | 118.088094 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | DO ready | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G 2+0 0.6m/1.2m XMC3E NE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz XMC3E Sub B Lo 3) 1x18GHz 0.6m DP FE: 1) 1xISM8 card 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz XMC3E Sub B Hi 3) 1x18GHz 1.2m DP | MW Swap | Swap existing 1+0 to 2+0 link Impact sites: 7648C Tx route: 7648C-7124A NE (7648C RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 7648C to new 2+0 link 5) Dismantle existing link FE (7124A RTN17): 1) Add new ISM8 card at RTN17 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 7648C to new 2+0 link 5) Dismantle existing link | NE (7648C RTN01): 1) Add new ISM8 card at existing RTN01 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 7648C to new 2+0 link 5) Dismantle existing link | FE (7124A RTN17): 1) Add new ISM8 card at RTN17 slot 3 2) Install new link at 3-ISM8 3) Reuse existing channel (V) at new link 4) Migrate 7648C to new 2+0 link 5) Dismantle existing link | XMC3E | MAC DP | 18G | 0.6m | 1.2m | NR services | SQ202502060432-NR Services | NR services | SQ202504080097-NR Services // SQ202504080100-NR Services // SQ202504260199-NR Services | 2025-09-04 | 2025-09-04 | Completed | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-04 | 2025-02-07 | 2025-02-04 | 2025-02-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-04 | 2025-02-04 | 2025-02-04 | 2025-02-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021570 |  | 2025-02-19 | 2025-02-17 | Completed | 2025-02-01 | 2025-02-19 | 2025-02-17 | 2025-02-17 | NUR/WAFA/MIJONG/6871000001 | Logistic Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-02-25 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-02-25 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-02-25 | 2025-02-28 | 2025-02-28 | 2025-02-28 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-03-05 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-03-05 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016
4170B_LOS | Tmn Hutchings | DU00004985698 | Northern | Penang | 5.398873 | 100.311058 | [7 empty] | 00. Integrated/RFS Done | 23/07: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_4170B New 23G_0.3M(MAC)+OMT x1. Reuse existing RTN910A(RTN01). New XMC_3E, Sub A_Hi x1. FE_4086A New 23G_0.6M(MAC)+OMT x1. New RTN910A x1. New XMC_3E, Sub A_Lo x1. New CAT6 Cable with suitable length x1. | MW New Link / Reroute | Existing HW MW Link 4170B(RTN01)-4126B(RTN01), 18G_1+0_56M_512QAM. Install new HW MW Link 4170B(RTN01)-4086A(RTN02), 23G_1+0_112M_512QAM. Decom existing HW MW Link 4170B(RTN01)-4126B(RTN01), 18G_1+0_56M_512QAM. But do not decom RTN910A at 4170B & 4126B. Site Impacted : 4170B. NE_4170B 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01). 3.Install new 1x XMC_3e, Sub A_Hi. Configure it. 4.Request new xD vlan services from ZTE IPRAN Team. 5.Migrate traffic to new link. 6.Decom existing HW MW Link 4170B(RTN01)-4126B(RTN01), 18G_1+0_56M_512QAM. But do not decom RTN910A at 4170B(RTN01)(will reuse for new HW MW Link 4170B(RTN01)-4086A(RTN02), 18G_1+0_112M_512QAM). FE_4086A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new 1xRTN910A(RTN02). Configure it. 3.Install new 1x XMC_3E, Sub A_Lo. Configure it. 4.Create new In Band DCN. 5.Request new xD vlan services and new port of IBeam from ZTE IPRAN Team. 6.Enable port 8-EM6-1 of new RTN910A(RTN02). 7.Patching port 8-EM6-1 of new RTN910A(RTN02) and new port of IBeam. Configure it. 8.Migrate traffic 4170B to the new port at IBeam. 9.Decom existing HW MW Link 4170B(RTN01)-4126B(RTN01), 18G_1+0_56M_512QAM. But do not decom RTN910A at 4126B(RTN01)(as other child site(4633D) sharing RTN910A(RTN01)) . | Existing HW MW Link 4170B(RTN01)-4126B(RTN01), 18G_1+0_56M_512QAM. Install new HW MW Link 4170B(RTN01)-4086A(RTN02), 23G_1+0_112M_512QAM. Decom existing HW MW Link 4170B(RTN01)-4126B(RTN01), 18G_1+0_56M_512QAM. But do not decom RTN910A at 4170B & 4126B. Site Impacted : 4170B. NE_4170B 1.Install new 23G_0.3M(MAC)+OMT x1. 2.Re-use existing RTN910A(RTN01). 3.Install new 1x XMC_3e, Sub A_Hi. Configure it. 4.Request new xD vlan services from ZTE IPRAN Team. 5.Migrate traffic to new link. 6.Decom existing HW MW Link 4170B(RTN01)-4126B(RTN01), 18G_1+0_56M_512QAM. But do not decom RTN910A at 4170B(RTN01)(will reuse for new HW MW Link 4170B(RTN01)-4086A(RTN02), 18G_1+0_112M_512QAM). | Existing HW MW Link 4170B(RTN01)-4126B(RTN01), 18G_1+0_56M_512QAM. Install new HW MW Link 4170B(RTN01)-4086A(RTN02), 23G_1+0_112M_512QAM. Decom existing HW MW Link 4170B(RTN01)-4126B(RTN01), 18G_1+0_56M_512QAM. But do not decom RTN910A at 4170B & 4126B. Site Impacted : 4170B. FE_4086A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Install new 1xRTN910A(RTN02). Configure it. 3.Install new 1x XMC_3E, Sub A_Lo. Configure it. 4.Create new In Band DCN. 5.Request new xD vlan services and new port of IBeam from ZTE IPRAN Team. 6.Enable port 8-EM6-1 of new RTN910A(RTN02). 7.Patching port 8-EM6-1 of new RTN910A(RTN02) and new port of IBeam. Configure it. 8.Migrate traffic 4170B to the new port at IBeam. 9.Decom existing HW MW Link 4170B(RTN01)-4126B(RTN01), 18G_1+0_56M_512QAM. But do not decom RTN910A at 4126B(RTN01)(as other child site(4633D) sharing RTN910A(RTN01)) . | XMC-3E | MAC | 23G | 23G_0.3M(MAC)+OMT x1. | 23G_0.6M(MAC)+OMT x1. | GCI | SQ202506100567-GCI | GCI | SQ202507190095-GCI // SQ202507190096-GCI | 2025-07-31 | 2025-07-23 | Completed | 2025-06-05 | 2025-06-06 | 2025-06-05 | 2025-06-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-22 | 2025-07-31 | 2025-07-22 | 2025-07-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25062649 |  | 2025-06-27 | 2025-07-10 | Completed | 2025-06-26 | 2025-06-27 | 2025-06-26 | 2025-07-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-22 | 2025-08-05 | 2025-07-22 | 2025-07-22 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-07-22 | 2025-08-05 | 2025-07-22 | 2025-07-22 | ANAS FIKRI ADHA BIN RAZMI6000009598 | GCI TI | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-23 | 2025-07-22 | 2025-08-05 | 2025-07-22 | 2025-07-28 | ANAS FIKRI ADHA BIN RAZMI6000009598 | 2025-03-06: 2025-07-22; 2025-03-06: 2025-08-05; 2025-03-06: 2025-07-22; 2025-03-07: 2025-07-22 |  |  | 2025-08-27 | 2025-09-27 | 2025-08-27 | 2025-08-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB
4214B_LOS | Seri Hussein | DU00004985699 | Northern | Penang | 5.406081 | 100.309728 |  |  |  |  | 6/2: pending ne & fe ptw maxis& BM |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M NE_4214B New 18G_0.6M(MS) x1. New RTN910A x1. New XMC_3, Sub A_Lo x2. FE_4054A New 18G_0.6M(MS) x1. New RTN910A x1. New XMC_3, Sub A_Hi x2. New CAT6 Cable with suitable length x1. | MW New Link / Reroute | Link Existing NEC 23G_1+0_56M_256QAM. Build new HW MW Link 18G_2+0_56M_512QAM_EPLA. Site Impacted : 4214B. NE_4214B 1.Install new 18G_0.6M(MS). 2.Install new RTN910A(RTN01). Configure it. 3.Install new 2x XMC_3 , Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new Vlan Services and migrate RAN traffic to new HW MW Link 18G_2+0_56M_512QAM_EPLA. 7.Configure DCN Inband for RTN01. 8.Later, decom existing NEC 23G_1+0_56M_256QAM. FE_4054A 1.Install new 18G_0.6M(MS). 2.Install new RTN910A(RTN04). Configure it. 3.Install new 2x XMC_3 , Sub A_Hi. Configure it. 4.Request new IBeam port from ZTE IPRAN Team and enable it. 5.Enable port 8-EM6-1 of new RTN910A(RTN04). 6.Patching port 8-EM6-1 of new RTN910A(RTN04) to new port of IBeam. Configure it. 7.Request new Vlan Services and migrate RAN traffic . 8.Configure DCN Inband for RTN910A(RTN04). 9.Later, decom existing NEC 23G_1+0_56M_256QAM. | Link Existing NEC 23G_1+0_56M_256QAM. Build new HW MW Link 18G_2+0_56M_512QAM_EPLA. Site Impacted : 4214B. NE_4214B 1.Install new 18G_0.6M(MS). 2.Install new RTN910A(RTN01). Configure it. 3.Install new 2x XMC_3 , Sub A_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Request new Vlan Services and migrate RAN traffic to new HW MW Link 18G_2+0_56M_512QAM_EPLA. 7.Configure DCN Inband for RTN01. 8.Later, decom existing NEC 23G_1+0_56M_256QAM. | Link Existing NEC 23G_1+0_56M_256QAM. Build new HW MW Link 18G_2+0_56M_512QAM_EPLA. Site Impacted : 4214B. FE_4054A 1.Install new 18G_0.6M(MS). 2.Install new RTN910A(RTN04). Configure it. 3.Install new 2x XMC_3 , Sub A_Hi. Configure it. 4.Request new IBeam port from ZTE IPRAN Team and enable it. 5.Enable port 8-EM6-1 of new RTN910A(RTN04). 6.Patching port 8-EM6-1 of new RTN910A(RTN04) to new port of IBeam. Configure it. 7.Request new Vlan Services and migrate RAN traffic . 8.Configure DCN Inband for RTN910A(RTN04). 9.Later, decom existing NEC 23G_1+0_56M_256QAM. | XMC_3 | MS | 18G | 18G_0.6M(MS) x1. | 18G_0.6M(MS) x1. | GCI | SQ202506120252-GCI | GCI | SQ202603130693-GCI // SQ202603130696-GCI | 2025-09-17 | 2025-09-10 | Completed | 2025-06-05 | 2025-06-06 | 2025-06-05 | 2025-06-05 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-03 | 2025-08-03 | 2025-08-03 | 2025-08-03 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-19 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-10 | 2025-09-17 | 2025-09-10 | 2025-09-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25072953 |  | 2025-07-30 | 2025-07-31 | Completed | 2025-07-29 | 2025-07-30 | 2025-07-29 | 2025-07-31 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-04 | 2026-03-31 | 2026-03-04 | 2026-03-09 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-03-04 | 2026-03-31 | 2026-03-04 | 2026-04-07 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | AKMAL//BIN RAZALI/6794000078 |  | 2026-03-06 | 2026-03-04 | 2026-03-31 | 2026-03-04 | 2026-04-07 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-03-06: 2026-03-04; 2025-03-06: 2026-03-31; 2025-03-06: 2026-03-04; 2025-03-07: 2026-03-31 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506050646-GTSB
2901A | Saujana Putra (Watertank) | DU00004992758 | Central | Selangor | 2.957096 | 101.582449 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 18/2/2025 : Cutover done 7/2/2025 : EDGEPOINT INFRA - 30M Monopole - FE site 2901A Saujana Putra (Watertank) | TSS+TI | L1+ATP+PAC | -10G SFP x1. - Fiber Patch Cord x 1 pair. | MW IDU Patching | Util 100% of 1G Port. 2901A_RTN02 , GE1 transfer to GE3 Optical with 10G SFP Module + 1 Pair Patch Cord Fiber cables. | Util 100% of 1G Port. 2901A_RTN02 , GE1 transfer to GE3 Optical with 10G SFP Module + 1 Pair Patch Cord Fiber cables. | [6 empty] | Magicell | SQ202502260376-Magicell | Magicell | SQ202502270723-Magicell // SQ202504260146-Magicell | 2025-04-07 | 2025-04-07 | Completed | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020435 |  | 2025-02-05 | 2025-02-10 | Completed | 2025-02-04 | 2025-02-05 | 2025-02-04 | 2025-02-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-02-19 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-02-27 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-18 | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-04-11 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | 2025-03-06: 2025-02-18; 2025-03-06: 2025-02-28; 2025-03-06: 2025-02-18; 2025-03-07: 2025-03-10 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
1921B_1 | Jugra Banting(Smart) | DU00004992759 | Central | Selangor | 2.815263 | 101.449552 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 17/2/2025 : Cutover done 10/2/2025 : SBC KJS - 60M 4 Legged Tower - NE site 1921B Jugra Banting(Smart) | TSS+TI | L1+ATP+PAC | - 10G SFP x1. - Fiber Patch Cord x 1 pair. | MW IDU Patching | Util 100% of 1G Port. Transfer existing GE2 to GE4 Optical with 10G SFP Module + 1 Pair Patch Cord Fiber cables. | Util 100% of 1G Port. Transfer existing GE2 to GE4 Optical with 10G SFP Module + 1 Pair Patch Cord Fiber cables. | [6 empty] | Magicell | SQ202502260376-Magicell | Magicell | SQ202502180514-Magicell // SQ202504260146-Magicell | 2025-03-04 | 2025-03-03 | Completed | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-25 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-02-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-03 | 2025-03-04 | 2025-03-03 | 2025-03-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020438 |  | 2025-02-05 | 2025-02-06 | Completed | 2025-02-04 | 2025-02-05 | 2025-02-04 | 2025-02-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-17 | 2025-02-28 | 2025-02-17 | 2025-02-18 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-02-17 | 2025-02-28 | 2025-02-17 | 2025-02-27 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-02-17 | 2025-02-28 | 2025-02-17 | 2025-03-13 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | 2025-03-06: 2025-02-17; 2025-03-06: 2025-02-28; 2025-03-06: 2025-02-17; 2025-03-07: 2025-03-10 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
2901A_1 | Saujana Putra (Watertank) | DU00004992760 | Central | Selangor | 2.957096 | 101.582449 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 18/2/2025 : Cutover done 7/2/2025 : EDGEPOINT INFRA - 30M Monopole - NE site 2901A Saujana Putra (Watertank), CELCOM (M) - Tower - FE site 2049B Taman Mas Sepang(Celcom) | TSS+TI | L1+ATP+PAC | - 10G SFP x1. - Fiber Patch Cord x 1 pair. | MW IDU Patching | Util 100% of 1G Port. 2901A_RTN01 , GE1 transfer to GE3 Optical with 10G SFP Module + 1 Pair Patch Cord Fiber cables. | Util 100% of 1G Port. 2901A_RTN01 , GE1 transfer to GE3 Optical with 10G SFP Module + 1 Pair Patch Cord Fiber cables. | [6 empty] | Magicell | SQ202502260376-Magicell | Magicell | SQ202502270723-Magicell // SQ202504260146-Magicell | 2025-03-20 | 2025-03-20 | Completed | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-19 | 2025-03-20 | 2025-03-19 | 2025-03-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020439 |  | 2025-02-05 | 2025-02-06 | Completed | 2025-02-04 | 2025-02-05 | 2025-02-04 | 2025-02-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-02-19 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-02-27 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-18 | 2025-02-18 | 2025-02-28 | 2025-02-18 | 2025-03-13 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | 2025-03-06: 2025-02-18; 2025-03-06: 2025-02-28; 2025-03-06: 2025-02-18; 2025-03-07: 2025-03-10 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
1921B | Jugra Banting(Smart) | DU00004992761 | Central | Selangor | 2.815263 | 101.449552 | WK08 | FEB 25 | WK08 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 17/2/2025 : Cutover done 10/2/2025 : SBC KJS - 60M 4 Legged Tower - NE site 1921B Jugra Banting(Smart) | TSS+TI | L1+ATP+PAC | - 10G SFP x1. - Fiber Patch Cord x 1 pairs. | MW IDU Patching | 1921B_RTN02 , GE1 transfer to GE4 optical with 10G SFP Module + 1 Pair Patch Cord Fiber cables. | 1921B_RTN02 , GE1 transfer to GE4 optical with 10G SFP Module + 1 Pair Patch Cord Fiber cables. | [6 empty] | Magicell | SQ202503060127-Magicell | Magicell | SQ202502180514-Magicell // SQ202504260146-Magicell | 2025-12-25 | 2026-01-05 | Completed | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-27 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-28 | 2025-02-28 | 2025-02-28 | 2025-02-28 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25020440 |  | 2025-02-05 | 2025-02-06 | Completed | 2025-02-04 | 2025-02-05 | 2025-02-04 | 2025-02-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-17 | 2025-02-28 | 2025-02-17 | 2025-02-18 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-02-17 | 2025-02-28 | 2025-02-17 | 2025-02-27 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-17 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-02-17 | 2025-02-28 | 2025-02-17 | 2025-03-13 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | 2025-03-06: 2025-02-17; 2025-03-06: 2025-02-28; 2025-03-06: 2025-02-17; 2025-03-07: 2025-03-10 |  |  | 2025-03-11 | 2025-04-11 | 2025-03-11 | 2025-03-11 | ASTI//GANIS PUTRIANI/6237001358
7452B | Tmn Megah SBC | DU00004999263 | Sabah | Sabah | 5.874527 | 118.038080 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP and patch cord | MW IDU Patching | 7452B RTN01-RTN04 congested. To replace with 10G port Tx route: 7452B-LL-7124A Impact sites: 7312H,S00412,S01344 NE (7452B): 1) Existing connection: RTN01 GE1 to RTN04 GE1 2) Change to: RTN01 GE4 to RTN04 GE4 (10G) | NE (7452B): 1) Existing connection: RTN01 GE1 to RTN04 GE1 2) Change to: RTN01 GE4 to RTN04 GE4 (10G) | [6 empty] | NR services | SQ202502060432-NR Services | NR services | SQ202503050193-NR Services // SQ202504260199-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-04 | 2025-02-07 | 2025-02-04 | 2025-02-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-04 | 2025-02-04 | 2025-01-28 | 2025-02-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250220BZ |  | 2025-02-21 | 2025-02-24 | Completed | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-24 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-06 | 2025-03-31 | 2025-03-06 | 2025-06-13 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-03-06 | 2025-03-31 | 2025-03-06 | 2025-06-13 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-03-06 | 2025-03-31 | 2025-03-06 | 2025-03-12 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2025-03-06: 2025-03-06; 2025-03-06: 2025-03-31; 2025-03-06: 2025-03-06; 2025-03-07: 2025-03-10 |  |  | 2025-04-23 | 2025-05-23 | 2025-04-23 | 2025-04-23 | MASDIANA//BINTI BEDIN/6801000016
7203A | Pasir Putih | DU00004999264 | Sabah | Sabah | 4.298264 | 117.859164 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done |  | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 1xISM8 card | MW Hardware Upgrade | 7203A RTN02 GE1 to RTN01 GE2 congested. To transfer MW link for child site 7686B and 7725B to RTN02 and remove cascade RTN02-RTN01. Tx route: 7203A-LL-7205A Impact site: 7686B,7725B,7803E NE (7203A): 1) Install new ISM8 card at RTN02 slot 3 2) Transfer link from RTN01 7-ISM6-1 to RTN02 3-ISM8-1 3) Transfer link from RTN01 7-ISM6-2 to RTN02 3-ISM8-2 4) Remove connection RTN02-RTN01 5) Patch RTN02 GE1 to NLOS (for link to 7803E) 6) Decom RTN01 | NE (7203A): 1) Install new ISM8 card at RTN02 slot 3 2) Transfer link from RTN01 7-ISM6-1 to RTN02 3-ISM8-1 3) Transfer link from RTN01 7-ISM6-2 to RTN02 3-ISM8-2 4) Remove connection RTN02-RTN01 5) Patch RTN02 GE1 to NLOS (for link to 7803E) 6) Decom RTN01 | [6 empty] | NR services | SQ202502120362-NR Services | NR services | SQ202502270741-NR Services // SQ202504260199-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-02-11 | 2025-02-11 | 2025-02-11 | 2025-02-11 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-11 | 2025-02-14 | 2025-02-11 | 2025-02-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-11 | 2025-02-14 | 2025-02-11 | 2025-02-11 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021367 |  | 2025-02-15 | 2025-02-15 | Completed | 2025-02-14 | 2025-02-15 | 2025-02-14 | 2025-02-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-21 | 2025-03-08 | 2025-02-21 | 2025-02-21 | RAMLAN//BIN ROSLAN/6000002578 | NR Service TI | 2025-02-21 | 2025-03-08 | 2025-02-21 | 2025-02-21 | RAMLAN//BIN ROSLAN/6000002578 | NR Service TI | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  | 2025-02-24 | 2025-02-21 | 2025-03-08 | 2025-02-21 | 2025-03-03 | RAMLAN//BIN ROSLAN/6000002578 | 2025-02-21 | 2025-03-08 | 2025-02-21 | 2025-03-03 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | tseping//wang/6819000006 | Logistic Team | 2025-04-23 | 2025-05-23 | 2025-04-23 | 2025-04-23 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
2882A_PORT | RSC2 & 3 Indoor | DU00006731046 | Central | Pahang | 3.425401 | 101.792141 | [9 empty] | TSS+TI |  | Fiber 10G SF Module x2 Fiber Patch Cord x 1 pairs | MW Re-engineering | Re-enginnering RTN04-RTN03 from 1G port to 10G port Site Impacted : 1027A , 3825B , 1026A. NE_2882A 1.Enable GE3 , 2882A_RTN03. 2.Enable GE3 , 2882A_RTN04. 3.Install SFP Module and Fiber patch cord interconnect between RTN03 & RTN04. | Re-enginnering RTN04-RTN03 from 1G port to 10G port Site Impacted : 1027A , 3825B , 1026A. NE_2882A 1.Enable GE3 , 2882A_RTN03. 2.Enable GE3 , 2882A_RTN04. 3.Install SFP Module and Fiber patch cord interconnect between RTN03 & RTN04. | [6 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050522 |  | 2026-05-06 |  | Ongoing | 2026-05-05 | 2026-05-06 | 2026-05-05 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604150406-GCI | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | CHEONG/SENG/WAH/7018000306
7000D_PORT | KampungSimunul | DU00006731047 | Sabah | Sabah | 4.469602 | 118.619610 | [7 empty] | 05. Doable |  | TSS+TI |  | Fiber 10G SFP Module x2. Fiber Patch Cord x1 pairs. | MW Re-engineering | Re-engineering BBU used 10G. Site Impacted : 7000D. NE_7000D. 1.Enable GE3 , 7000D_RTN01. 2.BBU_7000D Port 10G Patching to 7000D_RTN01_GE3. 3.Remove existing ETH pacthing and disable unused port. | Re-engineering BBU used 10G. Site Impacted : 7000D. NE_7000D. 1.Enable GE3 , 7000D_RTN01. 2.BBU_7000D Port 10G Patching to 7000D_RTN01_GE3. 3.Remove existing ETH pacthing and disable unused port. | [6 empty] | GCI |  | GCI | SQ202604230180-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041462 |  | 2026-04-15 | 2026-04-18 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-18 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202604150440-GCI | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | CHEONG/SENG/WAH/7018000306
7063D_PORT | TAMANSABANA (REL) | DU00006773257 | Sabah | Sabah | 5.374173 | 116.156300 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | TRANSFER BBU FROM 7063D RTN01 8-EM6-1 TO 10G PORT 8-EM6-3 IMPACTED SITE: 7063D | TRANSFER BBU FROM 7063D RTN01 8-EM6-1 TO 10G PORT 8-EM6-3 IMPACTED SITE: 7063D | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050429 |  | 2026-05-05 | 2026-05-10 | Completed | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-07 | 2026-06-07 | 2026-05-07 | 2026-05-10 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-05-07 | 2026-06-07 | 2026-05-07 | 2026-05-10 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-05-07 | 2026-06-07 | 2026-05-07 | 2026-05-10 | LEONARD//EDUAN/6000038538 | 2025-03-06: 2026-05-07; 2025-03-06: 2026-06-07; 2025-03-06: 2026-05-07; 2025-03-07: 2026-05-08 | [7 empty] | GCI | SQ202604280429-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
R00023_PORT | R001B_R00023OD_KUALAPERLIS | DU00006731049 | Northern | Perlis | 6.383942 | 100.152053 | [7 empty] | 00. Site Out/Drop | 24/4: Site to fiberize | TSS+TI |  | NE_R00023 New SFP Module 1G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Perform LAG 2x 1G(Optical) for RTN03 & RTN04. Site Impacted : 4608B, 4135H & 3543A149. NE_R00023 1.Enable port 8-EM6-6 of existing RTN910AF(RTN03, NEID 44-23959). Insert suitable SFP Module 1G 10Km 1310nm. Configure it. 2.Enable port 8-EM6-6 of existing RTN910AF(RTN04, NEID 44-13960). Insert suitable SFP Module 1G 10Km 1310nm. Configure it. 3.Perform new cascading in between port 8-EM6-6 of existing RTN910AF(RTN03, NEID 44-23959) and port 8-EM6-6 of existing RTN910AF(RTN04, NEID 44-13960). 4.Perform 2x 1G(Optical) LAG port 8-EM6-5 & 8-EM6-6 of existing RTN910AF(RTN03, NEID 44-23959) and existing port 8-EM6-5 & 8-EM6-6 of existing RTN910AF(RTN04, NEID 44-13960). 5.Migrate traffics 4608B, 4135H & 3543A149 via 2x 1G(Optical) LAG and still using existing port of IBeam at CP(R00028). | Perform LAG 2x 1G(Optical) for RTN03 & RTN04. Site Impacted : 4608B, 4135H & 3543A149. NE_R00023 1.Enable port 8-EM6-6 of existing RTN910AF(RTN03, NEID 44-23959). Insert suitable SFP Module 1G 10Km 1310nm. Configure it. 2.Enable port 8-EM6-6 of existing RTN910AF(RTN04, NEID 44-13960). Insert suitable SFP Module 1G 10Km 1310nm. Configure it. 3.Perform new cascading in between port 8-EM6-6 of existing RTN910AF(RTN03, NEID 44-23959) and port 8-EM6-6 of existing RTN910AF(RTN04, NEID 44-13960). 4.Perform 2x 1G(Optical) LAG port 8-EM6-5 & 8-EM6-6 of existing RTN910AF(RTN03, NEID 44-23959) and existing port 8-EM6-5 & 8-EM6-6 of existing RTN910AF(RTN04, NEID 44-13960). 5.Migrate traffics 4608B, 4135H & 3543A149 via 2x 1G(Optical) LAG and still using existing port of IBeam at CP(R00028). | [6 empty] | GTSB |  | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604150433-GTSB
7589A_PORT | Kg.Lot M | DU00006731050 | Sabah | Sabah | 5.635690 | 117.822400 | [9 empty] | TSS+TI |  | - | MW Re-engineering | Re-engineering CTS port to RTN02 Site impact: 7589A,7086Z,7484B Re-patch 7589A BBU from RTN02 Slot 17 port 1 to RTN03 Slot 8 port 2 Re-patch LL cable from RTN01 Slot 6 port 1 to RTN02 Slot 17 port 1 | Re-patch 7589A BBU from RTN02 Slot 17 port 1 to RTN03 Slot 8 port 2 Re-patch LL cable from RTN01 Slot 6 port 1 to RTN02 Slot 17 port 1 | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050448 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604150447-GTSB | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | LIM//WEI CHONG/6798000110
7445A_PORT | KgApin | DU00006731048 | Sabah | Sabah | 5.470040 | 116.277510 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7445A RTN03-RTN02 10G 10G PORT IDU RTN03-RTN02 1. INSTALL 1 10G SFP OPTICAL AT HW 7445A RTN03 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7445A RTN02 8-EM6-3 3. PATCHING PATCH CORD 7445A RTN03 8-EM6-3 TO HW 7445A RTN02 8-EM6-3 4. REMOVE CASCADE BETWEEN RTN01-RTN02 4. RECONFIGURE TRAFFIC IMPACTED SITE: 7445A, 3428B_4, 7334K, 7336C | 7445A RTN03-RTN02 10G 10G PORT IDU RTN03-RTN02 1. INSTALL 1 10G SFP OPTICAL AT HW 7445A RTN03 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7445A RTN02 8-EM6-3 3. PATCHING PATCH CORD 7445A RTN03 8-EM6-3 TO HW 7445A RTN02 8-EM6-3 4. REMOVE CASCADE BETWEEN RTN01-RTN02 4. RECONFIGURE TRAFFIC IMPACTED SITE: 7445A, 3428B_4, 7334K, 7336C | [6 empty] | NR services |  | NR services | SQ202604230198-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041464 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-05-10 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-05-10 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-15 | 2026-05-15 | 2026-04-15 | 2026-05-10 | LEONARD//EDUAN/6000038538 | 2025-03-06: 2026-04-15; 2025-03-06: 2026-05-15; 2025-03-06: 2026-04-15; 2025-03-07: 2026-05-07 | [7 empty] | GCI | SQ202604150440-GCI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
9225A_PORT | SMKSri Aman | DU00006731052 | Sarawak | Sarawak | 1.210188 | 111.475616 | [9 empty] | TSS+TI | L1+ATP+PAC | NE_9225A New SFP Module 10G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Perform upgrade 1G(Electrical) to 10G(Optical)for RTN03 & RTN02. Site Impacted : 9225A & 9633B. NE_9225A 1.Disable port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-24409). 2.Disable port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-24190). 3.Disconnect/remove existing cascading in between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-24409) and port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-24190). 4.Enable port 8-EM6-3 of existing RTN910AF(RTN03, NEID 9-24409). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 5.Enable port 8-EM6-4 of existing RTN910AF(RTN02, NEID 9-24190). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 6.Perform cascading in between port 8-EM6-3 of existing RTN910AF(RTN03, NEID 9-24409) and port 8-EM6-4 of existing RTN910AF(RTN02, NEID 9-24190) using Optical patch cord. 7.Migrate traffics 9225A & 9633B via 10G(Optical) cascaded and still using existing port of IBeam at CP(9999A). | Perform upgrade 1G(Electrical) to 10G(Optical)for RTN03 & RTN02. Site Impacted : 9225A & 9633B. NE_9225A 1.Disable port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-24409). 2.Disable port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-24190). 3.Disconnect/remove existing cascading in between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-24409) and port 8-EM6-1 of existing RTN910AF(RTN02, NEID 9-24190). 4.Enable port 8-EM6-3 of existing RTN910AF(RTN03, NEID 9-24409). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 5.Enable port 8-EM6-4 of existing RTN910AF(RTN02, NEID 9-24190). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 6.Perform cascading in between port 8-EM6-3 of existing RTN910AF(RTN03, NEID 9-24409) and port 8-EM6-4 of existing RTN910AF(RTN02, NEID 9-24190) using Optical patch cord. 7.Migrate traffics 9225A & 9633B via 10G(Optical) cascaded and still using existing port of IBeam at CP(9999A). | [6 empty] | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220807-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041441 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-06 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-05-06 | 2026-05-12 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-06 | 2026-05-06 | 2026-05-12 |  |  | ROYSTON//AHHOLE/6000038561 | 2025-03-06: 2026-05-06; 2025-03-06: 2026-05-12; 2025-03-06: 2026-05-06; 2025-03-07: 2026-05-06 | [7 empty] | GTSB | SQ202604200059-GTSB
7030B_PORT_1 | KgKuap | DU00006731053 | Sabah | Sabah | 6.906567 | 116.836180 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW Re-engineering | 7030B BBU TRANSFER FROM RTN01 TO RTN02 OTHER DU: 7030B_PORT: 1G LAG BETWEEN RTN01-RTN02 | 7030B BBU TRANSFER FROM RTN01 TO RTN02 OTHER DU: 7030B_PORT: 1G LAG BETWEEN RTN01-RTN02 | [6 empty] | NR services | SQ202604240988-NR Services | NR services | SQ202604230198-NR Services |  |  | Ongoing | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-23 | 2026-04-24 | 2026-04-23 | 2026-04-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041467 |  | 2026-04-15 | 2026-04-20 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-17 | 2026-05-17 | 2026-04-17 | 2026-04-20 | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-04-17 | 2026-05-17 | 2026-04-17 | 2026-04-20 | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-18 | 2026-04-17 | 2026-05-17 | 2026-04-17 | 2026-04-20 | MIKE MICRON DOLIK6000068237 | 2025-03-06: 2026-04-17; 2025-03-06: 2026-05-17; 2025-03-06: 2026-04-17; 2025-03-07: 2026-04-18 | [7 empty] | GCI | SQ202604150440-GCI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
9288A_PORT | Tedungan(SACOFA) | DU00006731054 | Sarawak | Sarawak | 4.731470 | 114.801514 | [9 empty] | TSS+TI | L1+ATP+PAC | NE_9288A New SFP Module 10G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Perform upgrade 1G(Electrical) to 10G(Optical)for RTN05 & RTN01. Site Impacted : 9277R, 9772B, 9280R, 9646B, 9290R, 9252Z, 9287R, 9288R & Q01548. NE_9288A 1.Disable port 8-EM6-2 of existing RTN910AF(RTN05, NEID 9-24456). 2.Disable port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-20775). 3.Disconnect/remove existing cascading in between port 8-EM6-2 of existing RTN910AF(RTN05, NEID 9-24456) and port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-20775). 4.Enable port 8-EM6-3 of existing RTN910AF(RTN05, NEID 9-24456). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 5.Enable port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-20775). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 6.Perform cascading in between port 8-EM6-3 of existing RTN910AF(RTN05, NEID 9-24456) and port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-20775) using Optical patch cord. 7.Migrate traffics 9277R, 9772B, 9280R, 9646B, 9290R, 9252Z, 9287R, 9288R & Q01548 via 10G(Optical) cascaded and still using existing port of IBeam at CP(9284A). | Perform upgrade 1G(Electrical) to 10G(Optical)for RTN05 & RTN01. Site Impacted : 9277R, 9772B, 9280R, 9646B, 9290R, 9252Z, 9287R, 9288R & Q01548. NE_9288A 1.Disable port 8-EM6-2 of existing RTN910AF(RTN05, NEID 9-24456). 2.Disable port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-20775). 3.Disconnect/remove existing cascading in between port 8-EM6-2 of existing RTN910AF(RTN05, NEID 9-24456) and port 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-20775). 4.Enable port 8-EM6-3 of existing RTN910AF(RTN05, NEID 9-24456). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 5.Enable port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-20775). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 6.Perform cascading in between port 8-EM6-3 of existing RTN910AF(RTN05, NEID 9-24456) and port 8-EM6-3 of existing RTN910AF(RTN01, NEID 9-20775) using Optical patch cord. 7.Migrate traffics 9277R, 9772B, 9280R, 9646B, 9290R, 9252Z, 9287R, 9288R & Q01548 via 10G(Optical) cascaded and still using existing port of IBeam at CP(9284A). | [6 empty] | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220807-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041442 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-21 | 2026-04-27 | 2026-04-21 | 2026-04-21 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-04-21 | 2026-04-27 | 2026-04-28 | 2026-04-28 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-21 | 2026-04-27 | 2026-04-28 | 2026-04-28 | ROYSTON//AHHOLE/6000038561 | 2025-03-06: 2026-04-21; 2025-03-06: 2026-04-27; 2025-03-06: 2026-04-21; 2025-03-07: 2026-04-21 | [7 empty] | GTSB | SQ202604200059-GTSB
9519A_PORT | TamanTunku MP | DU00006731055 | Sarawak | Sarawak | 4.317780 | 113.993000 | [9 empty] | TSS+TI | L1+ATP+PAC | NE_9519A New SFP Module 10G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Perform upgrade 1G(Electrical) to 10G(Optical)for RTN03 & RTN01. Site Impacted : 9519A & 9584A. NE_9519A 1.Disable port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23614). 2.Disable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-20237). 3.Disconnect/remove existing cascading in between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23614) and port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-20237). 4.Enable port 8-EM6-3 of existing RTN910AF(RTN03, NEID 9-23614). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 5.Enable port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20237). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 6.Perform cascading in between port 8-EM6-3 of existing RTN910AF(RTN03, NEID 9-23614) and port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20237) using Optical patch cord. 7.Migrate traffics 9519A & 9584A via 10G(Optical) cascaded and still using existing port of IBeam at CP(9074A). | Perform upgrade 1G(Electrical) to 10G(Optical)for RTN03 & RTN01. Site Impacted : 9519A & 9584A. NE_9519A 1.Disable port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23614). 2.Disable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-20237). 3.Disconnect/remove existing cascading in between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23614) and port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-20237). 4.Enable port 8-EM6-3 of existing RTN910AF(RTN03, NEID 9-23614). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 5.Enable port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20237). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 6.Perform cascading in between port 8-EM6-3 of existing RTN910AF(RTN03, NEID 9-23614) and port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20237) using Optical patch cord. 7.Migrate traffics 9519A & 9584A via 10G(Optical) cascaded and still using existing port of IBeam at CP(9074A). | [6 empty] | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220807-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041443 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-05-05 | 2026-04-29 | 2026-04-29 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-04-29 | 2026-05-05 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-29 | 2026-04-29 | 2026-05-05 |  |  | ROYSTON//AHHOLE/6000038561 | 2025-03-06: 2026-04-29; 2025-03-06: 2026-05-05; 2025-03-06: 2026-04-29; 2025-03-07: 2026-04-29 | [7 empty] | GTSB | SQ202604200059-GTSB
9200B_PORT | Sebuyau(Sacofa) | DU00006731056 | Sarawak | Sarawak | 1.514675 | 110.933571 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x patch cord | MW Re-engineering | Re-enginnering BBU to RTN02 from 1G port to 10G port Site impact: 9200B Remove connection BBU to RTN02 EM6 port 1 Patch cable and SFP 10G at BBU to RTN02 (sebuya) EM6 port 3 | Remove connection BBU to RTN02 EM6 port 1 Patch cable and SFP 10G at BBU to RTN02 (sebuya) EM6 port 3 | [6 empty] | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220807-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041445 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604200059-GTSB | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | AB.RAHMAN//BIN MAT NOOH/6237001519
7726B_PORT | SurauKurnia Jaya | DU00006731057 | Sabah | Sabah | 4.247603 | 117.940070 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x patch cord | MW Re-engineering | Re-enginnering BBU from RTN02 Slot 8 Port 1 GE port to Slot 8 Port 3 10GE port Site impact: 7726B Insert 10GE SFP into RTN02 Slot 8 Port 3 BBU re-patch to RTN02 Slot 8 Port 3 | Insert 10GE SFP into RTN02 Slot 8 Port 3 BBU re-patch to RTN02 Slot 8 Port 3 | [6 empty] | GTSB |  | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042866 |  | 2026-04-30 |  | Ongoing | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604150447-GTSB | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | LIM//WEI CHONG/6798000110
7765B_PORT | KgMinihas | DU00006731058 | Sabah | Sabah | 6.014857 | 116.735260 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x Optical cable | MW Re-engineering | Re-enginnering RTN01-RTN02 from 1G port to 10G port Site impact: 7765B, 7959B, 7822E Patch cable from RTN01 EM6 port 5 to RTN02 EM6 port 3 remove connection RTN01 EM6 port 1 to RTN02 EM6 port 2 | Patch cable from RTN01 EM6 port 5 to RTN02 EM6 port 3 Remove connection RTN01 EM6 port 1 to RTN02 EM6 port 2 | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042870 |  | 2026-04-30 | 2026-05-02 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-05-02 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604150447-GTSB | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | AB.RAHMAN//BIN MAT NOOH/6237001519
7386B_PORT | KgWawasan | DU00006731059 | Sabah | Sabah | 5.037023 | 118.331118 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7386B RTN02-RTN01 10G 10G PORT IDU RTN02-RTN01 1. INSTALL 1 10G SFP OPTICAL AT HW 7386B RTN02 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7386B RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD 7386B RTN02 8-EM6-3 TO HW 7386B RTN02 8-EM6-3 4. RECONFIGURE TRAFFIC IMPACTED SITE: 7386B, 7056C, 7276B, 3512A_7 | 7386B RTN02-RTN01 10G 10G PORT IDU RTN02-RTN01 1. INSTALL 1 10G SFP OPTICAL AT HW 7386B RTN02 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7386B RTN01 8-EM6-3 3. PATCHING OPTICAL PATCH CORD 7386B RTN02 8-EM6-3 TO HW 7386B RTN02 8-EM6-3 4. RECONFIGURE TRAFFIC IMPACTED SITE: 7386B, 7056C, 7276B, 3512A_7 | [6 empty] | GTSB | SQ202605050403-GTSB | GTSB | SQ202605050395-GTSB |  |  | Ongoing | [8 empty] | Unassigned | Not started |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | PAVITRAN AL CHINNAKOLANDAY6799000150 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26041463 |  | 2026-05-30 | 2026-04-29 | Completed | 2026-04-23 | 2026-05-30 | 2026-04-23 | 2026-04-29 | MOHD AIRELL SHAH6000044820 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-23 | 2026-05-30 | 2026-04-23 | 2026-04-29 | MOHD AIRELL SHAH6000044820 | GTSB TI | 2026-04-23 | 2026-05-30 | 2026-04-23 | 2026-04-29 | MOHD AIRELL SHAH6000044820 | GTSB TI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-28 | 2026-04-23 | 2026-05-30 | 2026-04-23 | 2026-04-29 | MOHD AIRELL SHAH6000044820 | 2025-03-06: 2026-04-23; 2025-03-06: 2026-05-30; 2025-03-06: 2026-04-23; 2025-03-07: 2026-04-28 | [7 empty] | GCI | SQ202604150440-GCI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
9055B_PORT | 7Mile Bazaar MP | DU00006731060 | Sarawak | Sarawak | 1.468240 | 110.326992 | [9 empty] | TSS+TI | L1+ATP+PAC | 2x SFP 1G 1x Patch cable | MW Re-engineering | Re-engineering connection for BBU 9055B from RTN03 EM6 port 2 to RTN01 EM6 port 1 | Reconnect BBU 9055B from RTN03 ISM8 port 2 to RTN01 ISM8 port 1 | [6 empty] | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220807-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041446 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-04-22 | 2026-04-28 |  |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-22 | 2026-04-22 | 2026-04-28 |  |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-03-06: 2026-04-22; 2025-03-06: 2026-04-28; 2025-03-06: 2026-04-22; 2025-03-07: 2026-04-22 | [7 empty] | GTSB | SQ202604200059-GTSB | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | AB.RAHMAN//BIN MAT NOOH/6237001519
4991B_PORT | ParitPanjang | DU00006731061 | Northern | Kedah | 5.707904 | 100.741725 | [9 empty] | TSS+TI |  | 10G SFP Module x2. Fiber Patch Cords x 1 pairs | MW Re-engineering | Re-engineering RTN04-RTN03 10G & RTN01-RTN03 remove existing cascade. Site Impacted : 4636B , 4505K and 4991B. NE_4991B 1.Enable GE3 , 4991B_RTN04. 2.Enable GE3 , 4991B_RTN03. 3.Patching Fiber patch cords between RTN03 & RTN04. 4.Disconnect existing ETN cable between RTN01 & RTN03 and disable unused port. | Re-engineering RTN04-RTN03 10G & RTN01-RTN03 remove existing cascade. Site Impacted : 4636B , 4505K and 4991B. NE_4991B 1.Enable GE3 , 4991B_RTN04. 2.Enable GE3 , 4991B_RTN03. 3.Patching Fiber patch cords between RTN03 & RTN04. 4.Disconnect existing ETN cable between RTN01 & RTN03 and disable unused port. | [6 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050513 |  | 2026-05-08 |  | Ongoing | 2026-05-07 | 2026-05-08 | 2026-05-07 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604150423-GCI | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | CHEONG/SENG/WAH/7018000306
7085A_PORT | KgSg Bangat-100Q4 | DU00006731062 | Sabah | Sabah | 5.314120 | 115.224560 | [7 empty] | 05. Doable |  | TSS+TI+Dismantle |  | 1X RTN910 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | SWAP RTN910 WITH NEW RTN910A 1. SWAP EXISTING RTN910A 2. PATCH BBU TO 10G 8-EM6-3 3. RECONFIGURE TRAFFIC | SWAP RTN910 WITH NEW RTN910A 1. SWAP EXISTING RTN910A 2. PATCH BBU TO 10G 8-EM6-3 3. RECONFIGURE TRAFFIC | [6 empty] | NR services |  | NR services | SQ202604230198-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041469 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202604150440-GCI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
7623B_PORT | BandarFajar Harapan | DU00006731063 | Sabah | Sabah | 5.230057 | 119.204792 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x patch cord 1x IDU RTN910AF | MW Re-engineering | Re-engineering, 1. Swap IDU RTN03 with RTN910AF model to support 10GE SFP. 2. Patch RTN05 Slot 8 Port 3 to RTN03 Slot Slot 8 Port 3 10GE connection. 3. Reroute traffic from RTN05-RTN06 GE connection to RTN05 to RTN03 10GE connection. 4. Remove RTN05-RTN06 cascade. Site impact: 7219R,7475B | 1. Survey on site at 7623B RTN05 port connection to RTN03 port until LL port. 2. Swap IDU RTN03 with RTN910AF model to support 10GE SFP. 3. Patch RTN05 Slot 8 Port 3 to RTN03 Slot Slot 8 Port 3 10GE connection. 4. Reroute traffic from RTN05-RTN06 GE connection to RTN05 to RTN03 10GE connection. 4. Remove RTN05-RTN06 cascade. Site impact: 7219R,7475B | [6 empty] | GTSB |  | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042865 |  | 2026-04-30 |  | Ongoing | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604150447-GTSB | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | LIM//WEI CHONG/6798000110
3142B_PORT | IOICity Mall | DU00006731064 | Central | Selangor | 2.970534 | 101.713893 | [9 empty] | TSS+TI |  | 10G SF Module x 3. Fiber Patch Cords x 3 pairs. RTN910AF x1. | MW Re-engineering | BBU upgrade to 10G. Existing 3142B_RTN01 upgrade to RTN910AF. Site Impacted : 3142B NE_3142B 1.BBU_1 Upgrade to 10G SFP. 2.BBU_1 Patching to new RTN910AF_GE3 with 10G SFP. 3.TDC 1 , patching to GE4 with 10G SFP. 4.Remove existing ETH cable and disable unused port. 5.All patching with Fiber patch cords. | BBU upgrade to 10G. Existing 3142B_RTN01 upgrade to RTN910AF. Site Impacted : 3142B NE_3142B 1.BBU_1 Upgrade to 10G SFP. 2.BBU_1 Patching to new RTN910AF_GE3 with 10G SFP. 3.TDC 1 , patching to GE4 with 10G SFP. 4.Remove existing ETH cable and disable unused port. 5.All patching with Fiber patch cords. | [6 empty] | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604150406-GCI | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | CHEONG/SENG/WAH/7018000306
K01074_PORT | JEN1_0008V_K01074_Kg.Musa | DU00006731065 | Northern | Kedah | 6.231485 | 100.668723 | [9 empty] | TSS+TI |  | NE_K01074 New CAT6 cable x1. | MW Re-engineering | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K01074_PORT_3. 2ND - DU K01074_PORT_2. 3RD - DU K01074_PORT_1. 4TH - DU K01074_PORT. 2.AFTER DU K01074_PORT, DU K01074_PORT_1, DU K01074_PORT_2 & DU K01074_PORT_3 COMPLETED, MAY DECOM EXISTING HW MW LINK K01074-K00406**** MW Re-engineering at K01074 in order to divert all child sites belong to K01074 to PTN/Cisco at K01074. Site Impacted : K01072. NE_K01074 1.Enable port 8-EM6-1 of existing RTN910AF(RTN04, NEID 220-41474). 2.Request new PTN/Cisco 1G(Electrical) port from ZTE IPRAN team at K01074. 3.Perform new patching in between port 8-EM6-1 of existing RTN910AF(RTN04, NEID 220-41474) and new PTN/Cisco port from ZTE IPRAN team at K01074. 4.Request new xC Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffic K01072 into new port of PTN/Cisco. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K01074_PORT_3. 2ND - DU K01074_PORT_2. 3RD - DU K01074_PORT_1. 4TH - DU K01074_PORT. 2.AFTER DU K01074_PORT, DU K01074_PORT_1, DU K01074_PORT_2 & DU K01074_PORT_3 COMPLETED, MAY DECOM EXISTING HW MW LINK K01074-K00406**** MW Re-engineering at K01074 in order to divert all child sites belong to K01074 to PTN/Cisco at K01074. Site Impacted : K01072. NE_K01074 1.Enable port 8-EM6-1 of existing RTN910AF(RTN04, NEID 220-41474). 2.Request new PTN/Cisco 1G(Electrical) port from ZTE IPRAN team at K01074. 3.Perform new patching in between port 8-EM6-1 of existing RTN910AF(RTN04, NEID 220-41474) and new PTN/Cisco port from ZTE IPRAN team at K01074. 4.Request new xC Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffic K01072 into new port of PTN/Cisco. | [6 empty] | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050469 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604150433-GTSB
S00733_PORT | S091A_S00733OD_SGSEGAMACOUNTRYC | DU00006731066 | Sabah | Sabah | 5.310700 | 118.463000 | [7 empty] | 05. Doable |  | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | TRANSFER BBU FROM S00733 8-EM6-1 TO 10G PORT 8-EM6-3 | TRANSFER BBU FROM S00733 8-EM6-1 TO 10G PORT 8-EM6-3 | [6 empty] | GCI |  | GCI | SQ202604230180-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041460 |  | 2026-04-15 | 2026-04-18 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-18 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202604150440-GCI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
4372B_PORT | PadangRengas(ZED) | DU00006731067 | Northern | Perak | 4.776717 | 100.850275 | [9 empty] | TSS+TI |  | 10G SFP Module x1. Fiber patch cord x 1 pairs. | MW Re-engineering | Re-engineering RTN01-RTN02 10G at 4372B. Site Impacted : 4372B , 4438B , 4371B and 4019R. NE_4372B 1.Enable GE4 , 4372B_RTN01. 2.Enable GE4 , 4372B_RTN02. 3.Install SFP Module and Patching Fiber patch cord between RTN01 & RTN02. 4.Disconnect existing ETH cables and disable unused port. | Re-engineering RTN01-RTN02 10G at 4372B. Site Impacted : 4372B , 4438B , 4371B and 4019R. NE_4372B 1.Enable GE4 , 4372B_RTN01. 2.Enable GE4 , 4372B_RTN02. 3.Install SFP Module and Patching Fiber patch cord between RTN01 & RTN02. 4.Disconnect existing ETH cables and disable unused port. | [6 empty] | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050472 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604150423-GCI | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | CHEONG/SENG/WAH/7018000306
7328A_PORT | KgNapang | DU00006731051 | Sabah | Sabah | 6.040973 | 116.736649 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X 1G SFP 2X LAN CABLE (SUITABLE LENGTH) | MW Re-engineering | 7328A RTN02-RTN01 1G LAG 1G LAG PORT IDU RTN02-RTN01 1. INSTALL 1 1G SFP OPTICAL AT HW 7328A RTN02 8-EM6-3 2. INSTALL 1 1G SFP OPTICAL AT HW 7328A RTN01 8-EG6-6 3. PATCHING LAN 7328A RTN02 8-EM6-2 TO HW 7328A RTN01 8-EG6-6 4. RECONFIGURE TRAFFIC 1G LAG BETWEEN IDU IMPACTED SITE: 7328A, 7765B, 7959B, 7822E | 7328A RTN02-RTN01 1G LAG 1G LAG PORT IDU RTN02-RTN01 1. INSTALL 1 1G SFP OPTICAL AT HW 7328A RTN02 8-EM6-3 2. INSTALL 1 1G SFP OPTICAL AT HW 7328A RTN01 8-EG6-6 3. PATCHING LAN 7328A RTN02 8-EM6-2 TO HW 7328A RTN01 8-EG6-6 4. RECONFIGURE TRAFFIC 1G LAG BETWEEN IDU IMPACTED SITE: 7328A, 7765B, 7959B, 7822E | [6 empty] | NR services |  | NR services | SQ202604230198-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041471 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-15 | 2026-05-15 | 2026-04-15 |  | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-04-15 | 2026-05-15 | 2026-04-15 |  | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-04-15 | 2026-05-15 | 2026-04-15 |  | LEONARD//EDUAN/6000038538 | 2025-03-06: 2026-04-15; 2025-03-06: 2026-05-15; 2025-03-06: 2026-04-15; 2025-03-07: 2026-05-05 | [7 empty] | GCI | SQ202604150440-GCI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
7518B_PORT | MasjidTinosa | DU00006731069 | Sabah | Sabah | 5.887008 | 118.091800 | [9 empty] | TSS+TI |  | 1. RTN910AF x1 2. 10G SFP Module x2. 3.Fiber Patch cord x 1 pairs. | BBU Patching | NE_7518B 1. 7518B_RTN01 Hardware upgrade RTN910AF 2. 7518B_BBU upgrade to 10G Fiber patch cord to New RTN910AF_GE3. | NE_7518B 1. 7518B_RTN01 Hardware upgrade RTN910AF 2. 7518B_BBU upgrade to 10G Fiber patch cord to New RTN910AF_GE3. | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050450 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-08 | 2026-06-08 | 2026-05-08 |  | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-05-08 | 2026-06-08 | 2026-05-08 |  | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | [7 empty] | 2026-05-08 | 2026-06-08 | 2026-05-08 |  | IBRAHIM//BIN SAHABU/7167000007 | 2025-03-06: 2026-05-08; 2025-03-06: 2026-06-08; 2025-03-06: 2026-05-08; 2025-03-07: 2026-05-09 | [7 empty] | GCI | SQ202604150440-GCI | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | CHEONG/SENG/WAH/7018000306
7030B_PORT | KgKuap | DU00006731070 | Sabah | Sabah | 6.906567 | 116.836180 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X 1G SFP 2X LAN CABLE (SUITABLE LENGTH) | MW Re-engineering | 7030B RTN02-RTN01 1G 1G LAG PORT IDU RTN02-RTN01 1. INSTALL 1 1G SFP OPTICAL AT HW 7030B RTN02 8-EM6-2 2. INSTALL 1 1G SFP OPTICAL AT HW 7030B RTN01 8-EM6-5 3. PATCHING LAN 7030B RTN02 8-EM6-2 TO HW 7030B RTN01 8-EM6-5 4. RECONFIGURE TRAFFIC 1G LAG BETWEEN IDU RTN02-RTN01 IMPACTED SITE: 7030B, 7351C, 7654C OTHER DU: 7030B_PORT_1: TRANSFER BBU 7030B FROM RTN01 TO RTN02 | 7030B RTN02-RTN01 1G 1G LAG PORT IDU RTN02-RTN01 1. INSTALL 1 1G SFP OPTICAL AT HW 7030B RTN02 8-EM6-2 2. INSTALL 1 1G SFP OPTICAL AT HW 7030B RTN01 8-EM6-5 3. PATCHING LAN 7030B RTN02 8-EM6-2 TO HW 7030B RTN01 8-EM6-5 4. RECONFIGURE TRAFFIC 1G LAG BETWEEN IDU RTN02-RTN01 IMPACTED SITE: 7030B, 7351C, 7654C OTHER DU: 7030B_PORT_1: TRANSFER BBU 7030B FROM RTN01 TO RTN02 | [6 empty] | NR services | SQ202604240988-NR Services | NR services | SQ202604230198-NR Services |  |  | Ongoing | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-23 | 2026-04-24 | 2026-04-23 | 2026-04-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041468 |  | 2026-04-15 | 2026-04-20 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-20 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-17 | 2026-05-17 | 2026-04-17 | 2026-04-20 | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-04-17 | 2026-05-17 | 2026-04-17 | 2026-04-20 | MIKE MICRON DOLIK6000068237 | NR Service TI | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-18 | 2026-04-17 | 2026-05-17 | 2026-04-17 | 2026-04-20 | MIKE MICRON DOLIK6000068237 | 2025-03-06: 2026-04-17; 2025-03-06: 2026-05-17; 2025-03-06: 2026-04-17; 2025-03-07: 2026-04-17 | [7 empty] | GCI | SQ202604150440-GCI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
7648C_PORT | KampungMangkalinau | DU00006731071 | Sabah | Sabah | 5.871088 | 118.088094 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x patch cord | MW Re-engineering | Re-enginnering BBU from RTN01 Slot 8 Port 1 GE port to Slot 8 Port 3 10GE port Site impact: 7648C Insert 10GE SFP into RTN01 Slot 8 Port3 BBU re-patch to RTN01 Slot 8 Port3 | Insert 10GE SFP into RTN01 Slot 8 Port3 BBU re-patch to RTN01 Slot 8 Port3 | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042871 |  | 2026-04-30 | 2026-05-02 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-05-02 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GTSB | SQ202604150447-GTSB | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | LIM//WEI CHONG/6798000110
7365B_PORT | CBRICHARDLIND | DU00006731072 | Sabah | Sabah | 5.341290 | 118.482297 | [7 empty] | 05. Doable |  | TSS+TI |  | 2X 10G SFP 2X PATCH CORD (SUITABLE LENGTH) | MW Re-engineering | 7365B RTN07-RTN01 10G 10G PORT IDU RTN07-RTN01 REMOVE CASCADE BETWEEN RTN01-RTN02 1. INSTALL 1 10G SFP OPTICAL AT HW 7365B RTN07 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7365B RTN01 8-EM6-4 3. PATCHING PATCH CORD 7365B RTN07 8-EM6-3 TO HW 7365B RTN01 8-EM6-4 4. REMOVE CASCADE BETWEEN RTN01-RTN02 5. RECONFIGURE TRAFFIC | 7365B RTN07-RTN01 10G 10G PORT IDU RTN07-RTN01 REMOVE CASCADE BETWEEN RTN01-RTN02 1. INSTALL 1 10G SFP OPTICAL AT HW 7365B RTN07 8-EM6-3 2. INSTALL 1 10G SFP OPTICAL AT HW 7365B RTN01 8-EM6-4 3. PATCHING PATCH CORD 7365B RTN07 8-EM6-3 TO HW 7365B RTN01 8-EM6-4 4. REMOVE CASCADE BETWEEN RTN01-RTN02 5. RECONFIGURE TRAFFIC | [6 empty] | GCI |  | GCI | SQ202604230180-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041461 |  | 2026-04-15 | 2026-04-18 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-18 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202604150440-GCI | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | EZRIN TASNIM BIN ABDUL GANI6798000128
7493B_PORT | Morisem2 | DU00006731073 | Sabah | Sabah | 5.417540 | 118.350500 | [9 empty] | TSS+TI |  | 2x SFP 10G 1x patch cord | MW Re-engineering | Re-enginnering RTN09-RTN08 from 1G port to 10G port Site impact: 7365B,7383B,S01999,S02000 Patch cable from RTN09 Slot 8 port 3 to RTN08 Slot 8 port 3 Remove connection RTN09 Slot 8 port 1 to RTN08 Slot 8 port 2 | 1. Patch cable from RTN09 Slot 8 port 3 to RTN08 Slot 8 port 3 10GE 2. Reroute traffic to 10GE link 3. Remove connection RTN09 Slot 8 port 1 to RTN08 Slot 8 port 2 | [6 empty] | GTSB |  | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042864 |  | 2026-04-30 |  | Ongoing | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604150447-GTSB | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | LIM//WEI CHONG/6798000110
9055B_PORT_2 | 7Mile Bazaar MP | DU00006731074 | Sarawak | Sarawak | 1.468240 | 110.326992 | [9 empty] | TSS+TI | L1+ATP+PAC | 2x SFP 10G 1x Optical cable | MW Re-engineering | Re-enginnering RTN02-RTN01 from 1G port to 10G port Site impact: 9055B, 9006C, 9307B Patch cable from RTN02 EM6 port 3 to RTN01 EM6 port 4 remove connection RTN02 EM6 port 1 to RTN01 EM6 port 2 | Patch cable from RTN02 EM6 port 3 to RTN01 EM6 port 4 remove connection RTN02 EM6 port 1 to RTN01 EM6 port 2 | [6 empty] | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220807-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041447 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-04-22 | 2026-04-28 |  |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-22 | 2026-04-22 | 2026-04-28 |  |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-03-06: 2026-04-22; 2025-03-06: 2026-04-28; 2025-03-06: 2026-04-22; 2025-03-07: 2026-04-22 | [7 empty] | GTSB | SQ202604200059-GTSB | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | AB.RAHMAN//BIN MAT NOOH/6237001519
9429A_PORT | TmnMaliha 2 MP | DU00006731075 | Sarawak | Sarawak | 1.553428 | 110.248991 | [9 empty] | TSS+TI |  | NE_9429A New SFP Module 10G 10Km 1310nm x2(IDU Huawei). New Optical Patchcord with suitable type and length x1. | MW Re-engineering | Perform upgrade 1G(Electrical) to 10G(Optical)for RTN02 & RTN01. Site Impacted : 9429A & 9009C. NE_9429A 1.Disable port 8-EM6-2 of existing RTN910AF(RTN02, NEID 17-23222). 2.Disable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-20248). 3.Disconnect/remove existing cascading in between port 8-EM6-2 of existing RTN910AF(RTN02, NEID 17-23222) and port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-20248). 4.Enable port 8-EM6-3 of existing RTN910AF(RTN02, NEID 17-23222). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 5.Enable port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20248). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 6.Perform cascading in between port 8-EM6-3 of existing RTN910AF(RTN02, NEID 17-23222) and port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20248) using Optical patch cord. 7.Migrate traffics 9429A & 9009C via 10G(Optical) cascaded and still using existing port of IBeam at CP(9999A). | Perform upgrade 1G(Electrical) to 10G(Optical)for RTN02 & RTN01. Site Impacted : 9429A & 9009C. NE_9429A 1.Disable port 8-EM6-2 of existing RTN910AF(RTN02, NEID 17-23222). 2.Disable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-20248). 3.Disconnect/remove existing cascading in between port 8-EM6-2 of existing RTN910AF(RTN02, NEID 17-23222) and port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-20248). 4.Enable port 8-EM6-3 of existing RTN910AF(RTN02, NEID 17-23222). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 5.Enable port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20248). Insert suitable SFP Module 10G 10Km 1310nm. Configure it. 6.Perform cascading in between port 8-EM6-3 of existing RTN910AF(RTN02, NEID 17-23222) and port 8-EM6-4 of existing RTN910AF(RTN01, NEID 9-20248) using Optical patch cord. 7.Migrate traffics 9429A & 9009C via 10G(Optical) cascaded and still using existing port of IBeam at CP(9999A). | [6 empty] | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220807-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041448 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-17 | 2026-04-23 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2026-04-17 | 2026-04-23 |  |  | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | [7 empty] | 2026-04-17 | 2026-04-23 |  |  | BONG NEE NYEEbong.allstar@gmail.com | 2025-03-06: 2026-04-17; 2025-03-06: 2026-04-23; 2025-03-06: 2026-04-18; 2025-03-07: 2026-04-18 | [7 empty] | GTSB | SQ202604200059-GTSB
9055B_PORT_1 | 7Mile Bazaar MP | DU00006731076 | Sarawak | Sarawak | 1.468240 | 110.326992 | [9 empty] | TSS+TI | L1+ATP+PAC | 4x SFP 1G 2x Patch cable | MW Re-engineering | Config LAG 1G port RTN03 and RTN01 Remove Cascade cable RTN03-RTN02 site impact: 9055B, 9006C, 9307B Patch cable from RTN03 port 5&6 to RTN01 EM6 port 5&6 Remove connection RTN03 port 1 to RTN02 port 2 Config LAG port 5&6 RTN03 and port 5&6 RTN01 | Patch cable from RTN03 port 5&6 to RTN01 EM6 port 5&6 Remove connection RTN03 port 1 to RTN02 port 2 Config LAG port 5&6 RTN03 and port 5&6 RTN01 | [6 empty] | Allstar | SQ202604220808-Allstar | Allstar | SQ202604220807-Allstar |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041449 |  | 2026-04-15 | 2026-04-16 | Completed | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-16 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-04-22 | 2026-04-28 |  |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | Allstar TI | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-22 | 2026-04-22 | 2026-04-28 |  |  | Hadi Mazrol bin Siduphadimazrol@gmail.com | 2025-03-06: 2026-04-22; 2025-03-06: 2026-04-28; 2025-03-06: 2026-04-22; 2025-03-07: 2026-04-22 | [7 empty] | GTSB | SQ202604200059-GTSB | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | AB.RAHMAN//BIN MAT NOOH/6237001519
7565A_PORT | Kg.Tinosa | DU00006731077 | Sabah | Sabah | 5.890677 | 118.082220 | [9 empty] | TSS+TI+Dismantle |  | 1X ISM8 CARD | MW Re-engineering | Hardware upgrade add ISM8 at RTN04 slot 4 and shift link 7518B-7565A to RTN04 4-ISM8 DISMANTLE EXISTING RTN03 | Hardware upgrade add ISM8 at RTN04 slot 4 and shift link 7518B-7565A to RTN04 4-ISM8 DISMANTLE EXISTING RTN03 | [6 empty] | NR services |  | NR services |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050451 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-08 | 2026-06-08 | 2026-05-08 |  | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-05-08 | 2026-06-08 | 2026-05-08 |  | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | [7 empty] | 2026-05-08 | 2026-06-08 | 2026-05-08 |  | IBRAHIM//BIN SAHABU/7167000007 | 2025-03-06: 2026-05-08; 2025-03-06: 2026-06-08; 2025-03-06: 2026-05-08; 2025-03-07: 2026-05-09 | [7 empty] | GCI | SQ202604150440-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
4948B_LOS | Kg Pida 3 | DU00006731087 | Northern | Kedah | 6.278111 | 100.314723 | [9 empty] | TSS+AA+TI+Dismantle |  | 13G_4+0_CA_28M NE_4948B 13G_DP_1.2M(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub A_Lo x1. FE_4937B. 13G_DP_1.2M x1 RTN910A x1. ISM8 x2. XMC_5D , Sub A_Hi x1. | MW New Link / Reroute | Existing link reroute to new FE 4937B due to existing link LOS Block. New Link config with 13G_4+0_CA_28M + 15G_2+0_28M to config EPLA 6+0 link. ** 15G_2+0_28M under DU ID 4948B_LOS_1. Site Impacted : 4856B. NE_4948B 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 3_ISM8-2+0 and 4_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect , CA and EPLA. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. FE_4937B. 1.Install new 13G_DP_1.2M 2.Install new RTN910A , 3_ISM8-2+0 and $_ISM8-2+0. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Create new Inband DCN. 7.Traffic migrate to new link and new FE routing. 8.Decom existing MW link. | Existing link reroute to new FE 4937B due to existing link LOS Block. New Link config with 13G_4+0_CA_28M + 15G_2+0_28M to config EPLA 6+0 link. ** 15G_2+0_28M under DU ID 4948B_LOS_1. Site Impacted : 4856B. NE_4948B 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A , 3_ISM8-2+0 and 4_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect , CA and EPLA. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. | Existing link reroute to new FE 4937B due to existing link LOS Block. New Link config with 13G_4+0_CA_28M + 15G_2+0_28M to config EPLA 6+0 link. ** 15G_2+0_28M under DU ID 4948B_LOS_1. Site Impacted : 4856B. FE_4937B. 1.Install new 13G_DP_1.2M 2.Install new RTN910A , 3_ISM8-2+0 and $_ISM8-2+0. 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect , CA and EPLA. 6.Create new Inband DCN. 7.Traffic migrate to new link and new FE routing. 8.Decom existing MW link. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202605070541-GCI | GCI |  |  |  | Ongoing | 2026-05-01 | 2026-05-01 | 2026-05-01 |  | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Assigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604150423-GCI | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | CHEONG/SENG/WAH/7018000306
B00695_PORT | B062A_B00695OD_PT13SGPJG | DU00006731088 | Central | Selangor | 3.726250 | 101.078970 | [9 empty] | TSS+TI |  | ETH Cat 6 cable x1. | MW Re-engineering | Re-engineering RTN02-RTN01 with LAG config. Site Impacted : 2637A NE_B00695 1.Enable GE1 , B00695_RTN01 2.Enable GE2 , B00695_RTN02 3.Create LAG between RTN01 & RTN02 with existing GE port and new GE port. | Re-engineering RTN02-RTN01 with LAG config. Site Impacted : 2637A NE_B00695 1.Enable GE1 , B00695_RTN01 2.Enable GE2 , B00695_RTN02 3.Create LAG between RTN01 & RTN02 with existing GE port and new GE port. | [6 empty] | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042024 |  | 2026-04-21 | 2026-04-29 | Completed | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202604150406-GCI | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | CHEONG/SENG/WAH/7018000306
3447C_LOS_1 | Eco Grandeur | DU00006753340 | Central | Selangor | 3.226230 | 101.457110 | [9 empty] | TSS+TI+Dismantle | L1+ATP+MRCF+PAC | 1X 23G 0.3M MAC ANTENNA 1x ODU 23G XMC3E SUB A HI 1x ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1x ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP NE ANTENNA AND ODU LINK 3447C-1220D FROM 23G_2+0_0.6M/1.2M_DP_56MHZ_512QAM TO HUAWEI_23G_2+0_0.3M/1.2M_DP\DP_56MHZ_512QAM_900MBPS_XMC3E_SUB_A&B_LINK_2.74KM INSTALL NEW NE ANTENNA 23G 0.3M AT TIER 2(LOWER THAN EXISTING). DISMANTLE NE ANTENNA AND ODU AT TIER 1. IMPACTED: 3447C | 1. REUSE EXISTING RTN910 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU SUB A AND SUB B 4. CONFIGURE LINK 23G 2+0 56MHZ_512QAM | 1. REUSE EXISTING RTN910 2. REUSE EXISTING 23G 1.2M MS ANTENNA 3. INSTALL NEW ODU SUB A AND SUB B 4. CONFIGURE LINK 23G 2+0 56MHZ_512QAM | XMC3E | MAC | 23G | 0.3 | 1.2 | Magicell | SQ202604290758-Magicell | Magicell | SQ202604240950-Magicell // SQ202604240958-Magicell |  |  | Ongoing | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041741 |  | 2027-04-08 |  | Ongoing | 2026-04-20 | 2027-04-08 | 2026-04-20 |  | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Warehouse Team | MAGICELL SDN. BHD. |  | Assigned | Ongoing |  | 2026-04-20 | 2027-04-08 | 2026-04-20 |  | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 |  | 2026-04-20 | 2027-04-08 | 2026-04-20 |  | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | AKMAL//BIN RAZALI/6794000078 |  | 2026-04-23 | 2026-04-20 | 2027-04-08 | 2026-04-20 |  | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | 2025-03-06: 2026-04-20; 2025-03-06: 2027-04-08; 2025-03-06: 2026-04-20; 2025-03-07: 2026-04-22 | [7 empty] | GCI | SQ202604200052-GCI | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
4370A_IPR | Tmn Kampar Perdana | DU00006723468 | Northern | Perak | 4.348170 | 101.157550 | [9 empty] | TSS+TI |  | NE_4370A New suitable SFP Module 10G 10Km 1310nm x1(IDU Huawei). New Optical Patchcord with suitable type and length x1.(If required) FE_4516A New suitable SFP Module 10G 10Km 1310nm x1(IBeam). New Optical Patchcord with suitable type and length x1.(If required) | MW IDU Patching | Perform upgrade for existing HW IDU & IBeam from 1G(Optical) to 10G(Optical) and perform patching. Site Impacted: 4178C, 4159D, 4893B & 4352B. Do not divert traffic 4370A, let's keep current TX Route 4370A/A00488-A00155. NE_4370A 1.Disable port 8-EM6-5(1G Optical) of existing RTN910AF(RTN03, NEID 9-36187). 2.Disconnect/remove existing Optical patch cord cable from port 8-EM6-5(1G Optical) of existing RTN910AF(RTN03, NEID 9-36187). 3.Insert new SFP Module 10G 1310nm 10Km x1 and enable port 8-EM6-3(10G Optical) of existing RTN910AF(RTN03, NEID 9-36187).Configure it. 5.Re-patching existing Optical patch cord cable to port 8-EM6-3(10G Optical) of existing RTN910AF(RTN03, NEID 9-36187). 6.Please cross check with ZTE IPRAN team whether existing xD Vlan DCN & Vlan Services can be re-use. If NO, request new xD Vlan DCN & Vlan Services. 7.Migrate traffics 4178C, 4159D, 4893B & 4352B ONLY into new IBeam port 10G at IBeam(CP 4516A). FE_4516A 1.Disconnect/remove existing Optical patch cord from existing port 1G(Optical). 2.Request new 10G(Optical) port from ZTE IPRAN Team and insert new suitable Optical SFP Module 10G 10Km 1310nm. Configure it. 3.Re-patching existing Optical patch cord to new 10G(Optical) port. Configure it. 4.Please cross check with ZTE IPRAN team whether existing xD Vlan DCN & Vlan Services can be re-use. If NO, request new xD Vlan DCN & Vlan Services. 5.Migrate traffics 4178C, 4159D, 4893B & 4352B ONLY into new IBeam port 10G at IBeam(CP 4516A). | Perform upgrade for existing HW IDU & IBeam from 1G(Optical) to 10G(Optical) and perform patching. Site Impacted: 4178C, 4159D, 4893B & 4352B. Do not divert traffic 4370A, let's keep current TX Route 4370A/A00488-A00155. NE_4370A 1.Disable port 8-EM6-5(1G Optical) of existing RTN910AF(RTN03, NEID 9-36187). 2.Disconnect/remove existing Optical patch cord cable from port 8-EM6-5(1G Optical) of existing RTN910AF(RTN03, NEID 9-36187). 3.Insert new SFP Module 10G 1310nm 10Km x1 and enable port 8-EM6-3(10G Optical) of existing RTN910AF(RTN03, NEID 9-36187).Configure it. 5.Re-patching existing Optical patch cord cable to port 8-EM6-3(10G Optical) of existing RTN910AF(RTN03, NEID 9-36187). 6.Please cross check with ZTE IPRAN team whether existing xD Vlan DCN & Vlan Services can be re-use. If NO, request new xD Vlan DCN & Vlan Services. 7.Migrate traffics 4178C, 4159D, 4893B & 4352B ONLY into new IBeam port 10G at IBeam(CP 4516A). | Perform upgrade for existing HW IDU & IBeam from 1G(Optical) to 10G(Optical) and perform patching. Site Impacted: 4178C, 4159D, 4893B & 4352B. Do not divert traffic 4370A, let's keep current TX Route 4370A/A00488-A00155. FE_4516A 1.Disconnect/remove existing Optical patch cord from existing port 1G(Optical). 2.Request new 10G(Optical) port from ZTE IPRAN Team and insert new suitable Optical SFP Module 10G 10Km 1310nm. Configure it. 3.Re-patching existing Optical patch cord to new 10G(Optical) port. Configure it. 4.Please cross check with ZTE IPRAN team whether existing xD Vlan DCN & Vlan Services can be re-use. If NO, request new xD Vlan DCN & Vlan Services. 5.Migrate traffics 4178C, 4159D, 4893B & 4352B ONLY into new IBeam port 10G at IBeam(CP 4516A). | [5 empty] | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040827 |  | 2026-05-31 | 2026-05-08 | Completed | 2026-05-08 | 2026-05-31 | 2026-05-08 | 2026-05-08 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-06 | 2026-05-31 | 2026-05-06 | 2026-05-08 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-05-08 | 2026-05-31 | 2026-05-08 | 2026-05-08 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 | GCI TI | [7 empty] | 2026-05-06 | 2026-05-31 | 2026-05-06 | 2026-05-08 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-03-06: 2026-05-06; 2025-03-06: 2026-05-31; 2025-03-06: 2026-05-06; 2025-03-07: 2026-05-06 | [7 empty] | GTSB | SQ202604100700-GTSB
1487C_HU | Pandan Capitol | DU00006723469 | Central | Selangor | 3.129481 | 101.754168 | [9 empty] | AA | PAC |  | MW Remote Upgrade | Link Existing HW 23G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 23G_1+0_112M_1024QAM_954M. Site Impacted : 1487C. NE_1487C 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 56MHz to BW 112MHz(1024QAM). FE_1281A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 56MHz to BW 112MHz(1024QAM). | Link Existing HW 23G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 23G_1+0_112M_1024QAM_954M. Site Impacted : 1487C. NE_1487C 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 56MHz to BW 112MHz(1024QAM). | Link Existing HW 23G_1+0_56M_512QAM_450M. MW Remote Upgrade to HW 23G_1+0_112M_1024QAM_954M. Site Impacted : 1487C. FE_1281A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 56MHz to BW 112MHz(1024QAM). | XMC-3 | SLU0623DD6B | 23G | 0.6m | 0.6m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-27 | [20 empty] | GTSB | SQ202604100695-GTSB
7013C_HU | Taman Pertama | DU00006723470 | Sabah | Sabah | 5.866489 | 118.071439 | [9 empty] | TSS+AA+TI+Dismantle |  | 18G_4+0_55M_512QAM_CA NE_7013C New 18G_0.6M(MDD) x1. New RTN910AF(RTN01). New XMC_5D Pro, Sub A_Hi x1. New ISM8 x2. New IF cables with suitable length and type x2 RUN. New CAT6 cable with suitable length x1. FE_7139A New 18G_0.6M(MDD) x1. New RTN910AF(RTN03). New XMC_5D Pro, Sub A_Lo x1. New ISM8 x2. New IF cables with suitable length and type x2 RUN. New CAT6 cable with suitable length x1. | MW Swap | Existing HW MW Link 7013C-7139A, 18G_1+0_55MHZ_512QAM. Swap existing to new 7013C-7139A, 18G_4+0_55MHZ_512QAM_CA. Later, may decom existing 7013C-7139A, 18G_1+0_55MHZ_512QAM. Site Impacted : 7013C. NE_7013C 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01) and insert new ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN. Build new HW MW Link 7013C-7139A, 18G_4+0_55MHZ_512QAM_CA. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU(7013C). 5.Re-use existing xD Vlan DCN & Vlan Services. 6.Migrate traffic 7013C to new HW MW Link 7013C-7139A, 18G_4+0_55MHZ_512QAM_CA. 7.Later, decom existing 7013C-7139A, 18G_1+0_55MHZ_512QAM. FE_7139A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN03) and insert new ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN. Build new HW MW Link 7013C-7139A, 18G_4+0_55MHZ_512QAM_CA. 4.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN03). 5.Enable port 17-EG6-3 and 17-EG6-4 of existing RTN950A(RTN01, NEID 9-19252). 6.Port 8-EM6-1 of new RTN910AF(RTN03) will be cascade to port 17-EG6-3 of existing RTN950A(RTN01, NEID 9-19252). 7.Port 8-EM6-2 of new RTN910AF(RTN03) will be cascade to port 17-EG6-4 of existing RTN950A(RTN01, NEID 9-19252). 8.Perform 2x 1G(Electrical) LAG in between 2x port at new RTN910AF(RTN03) and existing RTN950A(RTN01, NEID 9-19252). 9.Re-use existing xD Vlan DCN & Vlan Services. 10.Migrate traffic 7013C to existing port at IBeam(CP 7570A). 11.Later, decom existing 7013C-7139A, 18G_1+0_55MHZ_512QAM. | Existing HW MW Link 7013C-7139A, 18G_1+0_55MHZ_512QAM. Swap existing to new 7013C-7139A, 18G_4+0_55MHZ_512QAM_CA. Later, may decom existing 7013C-7139A, 18G_1+0_55MHZ_512QAM. Site Impacted : 7013C. NE_7013C 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN01) and insert new ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A_Hi x1 and lay new IF cable x2 RUN. Build new HW MW Link 7013C-7139A, 18G_4+0_55MHZ_512QAM_CA. 4.Enable port 8-EM6-1 of new RTN910AF(RTN01) and patching to existing BBU(7013C). 5.Re-use existing xD Vlan DCN & Vlan Services. 6.Migrate traffic 7013C to new HW MW Link 7013C-7139A, 18G_4+0_55MHZ_512QAM_CA. 7.Later, decom existing 7013C-7139A, 18G_1+0_55MHZ_512QAM. | Existing HW MW Link 7013C-7139A, 18G_1+0_55MHZ_512QAM. Swap existing to new 7013C-7139A, 18G_4+0_55MHZ_512QAM_CA. Later, may decom existing 7013C-7139A, 18G_1+0_55MHZ_512QAM. Site Impacted : 7013C. FE_7139A 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN03) and insert new ISM8 x2 into slot 03 and slot 04. 3.Install new XMC_5D Pro, Sub A_Lo x1 and lay new IF cable x2 RUN. Build new HW MW Link 7013C-7139A, 18G_4+0_55MHZ_512QAM_CA. 4.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN03). 5.Enable port 17-EG6-3 and 17-EG6-4 of existing RTN950A(RTN01, NEID 9-19252). 6.Port 8-EM6-1 of new RTN910AF(RTN03) will be cascade to port 17-EG6-3 of existing RTN950A(RTN01, NEID 9-19252). 7.Port 8-EM6-2 of new RTN910AF(RTN03) will be cascade to port 17-EG6-4 of existing RTN950A(RTN01, NEID 9-19252). 8.Perform 2x 1G(Electrical) LAG in between 2x port at new RTN910AF(RTN03) and existing RTN950A(RTN01, NEID 9-19252). 9.Re-use existing xD Vlan DCN & Vlan Services. 10.Migrate traffic 7013C to existing port at IBeam(CP 7570A). 11.Later, decom existing 7013C-7139A, 18G_1+0_55MHZ_512QAM. | XMC-5D Pro | MDD | 18G | 18G_0.6M(MDD) x1 | 18G_0.6M(MDD) x1 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604100702-GTSB
4124R_HU | Kg Charok Padang | DU00006723471 | Northern | Kedah | 5.794918 | 100.708351 | [7 empty] | 05. Doable |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 4124R-4622B ZTE MW 18G_1+0_1.2M/1.2M_DP_56MHZ_512QAM TO 18G_1+0_1.2M/1.2M_DP_112MHZ_512QAM_SUB B_889MBPS IMPACTED SITE: 4124R | MW REMOTE UPGRADE LINK 4124R-4622B ZTE MW 18G_1+0_1.2M/1.2M_DP_56MHZ_512QAM TO 18G_1+0_1.2M/1.2M_DP_112MHZ_512QAM_SUB B_889MBPS IMPACTED SITE: 4124R | MW REMOTE UPGRADE LINK 4124R-4622B ZTE MW 18G_1+0_1.2M/1.2M_DP_56MHZ_512QAM TO 18G_1+0_1.2M/1.2M_DP_112MHZ_512QAM_SUB B_889MBPS IMPACTED SITE: 4124R | XMC3E | MAC | 18G | 1.2 | 1.2 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-27 | [20 empty] | GCI | SQ202604100697-GCI | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | EZRIN TASNIM BIN ABDUL GANI6798000128
3804A_HU | Alam Jaya Commercial Centre | DU00006723472 | Central | Selangor | 3.241062 | 101.446008 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI |  | 15G_2+0_28M 15G_DP_0.6M(MDD) x1. ISM8 x1 XMC_5D , Sub A_Lo x1. FE_2069B. 15G_DP_0.6M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Hi x1. | MW Parallel Link | Existing Link 15G_2+0_28M Install Parallel link 15G_2+0_28M Site Impacted : 3804A. NE_3804A 1.Install new 15G_DP_0.6M(MDD). 2.Reuse existing 3804A_RTN01 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Create Service cross connect and EPLA. 6.Migrate traffic to new parallel link. 7.No decom MW link. FE_2069B. 1.Install new 15G_DP_0.6M(MDD). 2.Reuse existing 2069B_RTN04 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA. 6.Migrate traffic to new parallel link. 7.No decom MW link. | Existing Link 15G_2+0_28M Install Parallel link 15G_2+0_28M. NE_3804A Site Impacted : 3804A. 1.Install new 15G_DP_0.6M(MDD). 2.Reuse existing 3804A_RTN01 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Create Service cross connect and EPLA. 6.Migrate traffic to new parallel link. 7.No decom MW link. | Existing Link 15G_2+0_28M Install Parallel link 15G_2+0_28M Site Impacted : 3804A. FE_2069B. 1.Install new 15G_DP_0.6M(MDD). 2.Reuse existing 2069B_RTN04 , 3_ISM8-2+0. 3.Install new 3_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA. 6.Migrate traffic to new parallel link. 7.No decom MW link. | XMC_5D | MDD | 15G | 0.6 | 0.6 | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604100691-GCI | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | CHEONG/SENG/WAH/7018000306
K01074_PORT_3 | JEN1_0008V_K01074_Kg.Musa | DU00006746698 | Northern | Kedah | 6.231485 | 100.668723 | [9 empty] | TSS+TI |  | NE_K01074 New CAT6 cable x1. | MW Re-engineering | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K01074_PORT_3. 2ND - DU K01074_PORT_2. 3RD - DU K01074_PORT_1. 4TH - DU K01074_PORT. 2.AFTER DU K01074_PORT, DU K01074_PORT_1, DU K01074_PORT_2 & DU K01074_PORT_3 COMPLETED, MAY DECOM EXISTING HW MW LINK K01074-K00406**** MW Re-engineering at K01074 in order to divert all child sites belong to K01074 to PTN/Cisco at K01074. Site Impacted : K01070. NE_K01074 1.Enable port 8-EM6-1 of existing RTN910AF(RTN02, NEID 4-26096). 2.Request new PTN/Cisco 1G(Electrical) port from ZTE IPRAN team at K01074. 3.Perform new patching in between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 4-26096) and new PTN/Cisco port from ZTE IPRAN team at K01074. 4.Request new xC Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffic K01070 into new port of PTN/Cisco. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K01074_PORT_3. 2ND - DU K01074_PORT_2. 3RD - DU K01074_PORT_1. 4TH - DU K01074_PORT. 2.AFTER DU K01074_PORT, DU K01074_PORT_1, DU K01074_PORT_2 & DU K01074_PORT_3 COMPLETED, MAY DECOM EXISTING HW MW LINK K01074-K00406**** MW Re-engineering at K01074 in order to divert all child sites belong to K01074 to PTN/Cisco at K01074. Site Impacted : K01070. NE_K01074 1.Enable port 8-EM6-1 of existing RTN910AF(RTN02, NEID 4-26096). 2.Request new PTN/Cisco 1G(Electrical) port from ZTE IPRAN team at K01074. 3.Perform new patching in between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 4-26096) and new PTN/Cisco port from ZTE IPRAN team at K01074. 4.Request new xC Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffic K01070 into new port of PTN/Cisco. | [6 empty] | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050476 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280373-GTSB
S00464_AD | S093F_S00464OD_CENTRALPLAZA | DU00006746699 | Sabah | Sabah | 5.951110 | 116.072900 | [9 empty] | TSS+AA+TI+Dismantle |  | 23G_1+0_112M_512QAM. NE_7071K/S00464 New 23G_0.6M(MAC) x1. New RTN910AF(RTN02). New IF cables with suitable length and type x1 RUN. New XMC_3E, Sub A_Hi x1. New CAT6 cable x1. FE_7229C New 23G_0.6M(MAC) x1. New RTN910AF(RTN02). New IF cables with suitable length and type x1 RUN. New XMC_3E, Sub A_Lo x1. New CAT6 cable x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU S00464_AD. 2ND - DU 7710B_AD.**** Existing HW MW Link 7071K/S00464-7135B, 23G_1+0_56MHZ_512QAM. Install new MW Link/Reroute HW MW Link 7071K/S00464-7229C, 23G_1+0_112MHZ_512QAM. Later, decom existing HW MW Link 7071K/S00464-7135B, 23G_1+0_56MHZ_512QAM. Site Impacted : 7071K/S00464. NE_7071K/S00464 1.Install new 23G_0.6M(MAC) x1. 2.Install new RTN910AF(RTN02) x1. 3.Install XMC_3E, Sub A_Hi x1. 4.Lay new IF cables with suitable length and type x1 RUN at slot 07 Port 1. 5.Build new MW Link/Reroute HW MW Link 7071K/S00464-7229C, 23G_1+0_112MHZ_512QAM. 6.Enable port 8-EM6-1 of new RTN910AF(RTN02). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN02) to existing BBU(7071K/S00464) 8.Request new xD Vlan DCN and Vlan Services. 9.Migrate traffic 7071K/S00464 via new MW Link/Reroute HW MW Link 7071K/S00464-7229C, 23G_1+0_112MHZ_512QAM. 10.Later, decom existing HW MW Link 7071K/S00464-7135B, 23G_1+0_56MHZ_512QAM. FE_7229C 1.Install new 23G_0.6M(MAC) x1. 2.Install new RTN910AF(RTN02) x1. 3.Install XMC_3E, Sub A_Lo x1. 4.Lay new IF cables with suitable length and type x1 RUN at slot 07 Port 1. 5.Build new MW Link/Reroute HW MW Link 7071K/S00464-7229C, 23G_1+0_112MHZ_512QAM. 6.Enable port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN02). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN02) to existing CTS LL. 8.Perform patching port 8-EM6-2 of new RTN910AF(RTN02) to existing BBU(7229C). 9.Request new xD Vlan DCN and Vlan Services. 10.Migrate traffic 7071K/S00464 via existing port at IBeam(CP 7000A) similar port with traffic 7229C. 11.Later, decom existing HW MW Link 7071K/S00464-7135B, 23G_1+0_56MHZ_512QAM. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU S00464_AD. 2ND - DU 7710B_AD.**** Existing HW MW Link 7071K/S00464-7135B, 23G_1+0_56MHZ_512QAM. Install new MW Link/Reroute HW MW Link 7071K/S00464-7229C, 23G_1+0_112MHZ_512QAM. Later, decom existing HW MW Link 7071K/S00464-7135B, 23G_1+0_56MHZ_512QAM. Site Impacted : 7071K/S00464. NE_7071K/S00464 1.Install new 23G_0.6M(MAC) x1. 2.Install new RTN910AF(RTN02) x1. 3.Install XMC_3E, Sub A_Hi x1. 4.Lay new IF cables with suitable length and type x1 RUN at slot 07 Port 1. 5.Build new MW Link/Reroute HW MW Link 7071K/S00464-7229C, 23G_1+0_112MHZ_512QAM. 6.Enable port 8-EM6-1 of new RTN910AF(RTN02). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN02) to existing BBU(7071K/S00464) 8.Request new xD Vlan DCN and Vlan Services. 9.Migrate traffic 7071K/S00464 via new MW Link/Reroute HW MW Link 7071K/S00464-7229C, 23G_1+0_112MHZ_512QAM. 10.Later, decom existing HW MW Link 7071K/S00464-7135B, 23G_1+0_56MHZ_512QAM. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU S00464_AD. 2ND - DU 7710B_AD.**** Existing HW MW Link 7071K/S00464-7135B, 23G_1+0_56MHZ_512QAM. Install new MW Link/Reroute HW MW Link 7071K/S00464-7229C, 23G_1+0_112MHZ_512QAM. Later, decom existing HW MW Link 7071K/S00464-7135B, 23G_1+0_56MHZ_512QAM. Site Impacted : 7071K/S00464. FE_7229C 1.Install new 23G_0.6M(MAC) x1. 2.Install new RTN910AF(RTN02) x1. 3.Install XMC_3E, Sub A_Lo x1. 4.Lay new IF cables with suitable length and type x1 RUN at slot 07 Port 1. 5.Build new MW Link/Reroute HW MW Link 7071K/S00464-7229C, 23G_1+0_112MHZ_512QAM. 6.Enable port 8-EM6-1 & 8-EM6-2 of new RTN910AF(RTN02). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN02) to existing CTS LL. 8.Perform patching port 8-EM6-2 of new RTN910AF(RTN02) to existing BBU(7229C). 9.Request new xD Vlan DCN and Vlan Services. 10.Migrate traffic 7071K/S00464 via existing port at IBeam(CP 7000A) similar port with traffic 7229C. 11.Later, decom existing HW MW Link 7071K/S00464-7135B, 23G_1+0_56MHZ_512QAM. | XMC_3E | MAC | 23G | 23G_0.6M(MAC) x1 | 23G_0.6M(MAC) x1 | Seri Pancar | SQ202604290792-Seri Pancar |  |  |  |  | Ongoing | 2026-04-23 | 2026-04-30 | 2026-04-23 | 2026-04-23 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604280376-GTSB
B02214_AD | B063B_B02214OD_LCCTROUNDABOUT | DU00006746700 | Central | Selangor | 2.725771 | 101.725832 | [9 empty] | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 2X RTN910A 1X 13G 0.6M MS ANTENNA 1X 13G 1.8M MS ANTENNA 2x ODU 13G XMC3 SUB A HI 2x ODU 13G XMC3 SUB A LO 2x ODU 13G XMC3 SUB B HI 2x ODU 13G XMC3 SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE B02214-1236A WITH HUAWEI_13G_4+0_0.6M/1.8M_MS_28MHZ_128QAM_692MBPS_XMC3_SUB_A & B_WITH CA_LINK_7.70KM DISMANTLE EXISTING LINK B02214-B00503 IMPACTED: B02214 | 1. INSTALL NEW IDU RTN910 AND 2 PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 0.6M MS ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 13G 4+0 28MHZ 128QAM WITH EPLA 6. DISMANTLE EXISTING LINK B02214-B00503 | 1. INSTALL NEW IDU RTN910 AND 2 PCS ISM8 SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MS ANTENNA 3. INSTALL NEW ODU 13G XMC3 28MHZ SUB A & B 4. CONFIGURE LINK 13G 4+0 28MHZ 128QAM WITH EPLA 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK B02214-B00503 | XMC3 | MS | 13G | 0.6 | 1.8 | GTSB | SQ202604220810-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Ongoing | 2026-04-29 | 2026-05-13 | 2026-04-29 | 2026-04-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-05-13 | 2026-04-29 | 2026-04-29 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26050461 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-05-10 | 2026-05-31 | 2026-05-10 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-05-10 | 2026-05-31 | 2026-05-10 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | [7 empty] | 2026-05-10 | 2026-05-31 | 2026-05-10 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-03-06: 2026-05-10; 2025-03-06: 2026-05-31; 2025-03-06: 2026-05-10 | [7 empty] | GCI | SQ202604200052-GCI | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | EZRIN TASNIM BIN ABDUL GANI6798000128
B00892_AD | B063B_B00892IB_SKYCHEFS | DU00006746701 | Central | Selangor | 2.731100 | 101.718500 | [21 empty] | GTSB | SQ202604220810-GTSB | GTSB |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604200052-GCI
9261E_AD | Dcabin PressMetal Bintulu | DU00006746702 | Sarawak | Sarawak | 3.542509 | 113.372821 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_110M_256QAM_EPLA NE_9261E New 18G_DP_0.6M(MAC) x1. Re-use existing RTN910AF(RTN01, NEID 9-35591). New XMC_3E , Sub B_Lo x2. New IF cables 2x RUN with suitable type and length. FE_9363B New 18G_1.2M(MS) x1. New F,exi WG 18G x2. Re-use existing RTN910AF(RTN08, NEID 9-35592). New XMC_3E , Sub B_Hi x2. New IF cables 2x RUN with suitable type and length. New CAT6 cable x1. | MW Swap | ****IMPORTANT NOTE: 1.PLEASE REQUEST CRQ BEFORE PROCEED IMPLEMENTATION & GET APPROVAL FROM CD/GOP EB MANAGEMENT. 2.PLEASE CHECK LOS TOWARD FE IN ORDER TO REALLY ENSURE NO PARTIALLY BLOCK OCCUR FROM NE TO FE AND VICE VERSA.**** Existing HW MW Link 9261E-9363B, 15G_2+0_28MHZ_1024QAM_EPLA_448M. MW Swap to new HW MW Link 9261E-9363B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. Later, decom Antenna, ODU ONLY of HW MW Link 9261E-9363B, 15G_2+0_28MHZ_1024QAM_EPLA_448M. Anyway, do not decom existing RTN910AF(RTN01, NEID 9-35591) & existing RTN910AF(RTN08, NEID 9-35592). Site Impacted : 9261E. NE_9261E 1.Install new 18G_DP_0.6M(MAC) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-35591). 3.Install new XMC_3E , Sub B_Lo x2. Configure it. 4.Re-use existing xD Vlan dcn and Vlan services. 5.Migrate traffic 9261E via new HW MW Link 9261E-9363B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. 6.Later, decom Antenna, ODU ONLY of HW MW Link 9261E-9363B, 15G_2+0_28MHZ_1024QAM_EPLA_448M. Anyway, do not decom existing RTN910AF(RTN01, NEID 9-35591) & existing RTN910AF(RTN08, NEID 9-35592). FE_9363B 1.Install new 18G_1.2M(MS) x1. 2.Re-use existing RTN910AF(RTN08, NEID 9-35592). 3.Install new XMC_3E , Sub B_Hi x2. Configure it. 4.Re-use existing xD Vlan dcn and Vlan services. 5.Enable port 8-EM6-2 of existing RTN910AF(RTN08, NEID 9-35592). 6.Request new port 1G(Electrical) at IBeam from ZTE IPRAN Team. 7.Perform patching in between port 8-EM6-2 of existing RTN910AF(RTN08, NEID 9-35592) and new port 1G(Electrical) at IBeam. 8.Perform 2x LAG in between port 8-EM6-1 & 8-EM6-2 of existing RTN910AF(RTN08, NEID 9-35592) and existing port & new port of IBeam. 9.Migrate traffic 9261E via 2x LAG to IBeam. 10.Later, decom Antenna, ODU ONLY of HW MW Link 9261E-9363B, 15G_2+0_28MHZ_1024QAM_EPLA_448M. Anyway, do not decom existing RTN910AF(RTN01, NEID 9-35591) & existing RTN910AF(RTN08, NEID 9-35592). | ****IMPORTANT NOTE: 1.PLEASE REQUEST CRQ BEFORE PROCEED IMPLEMENTATION & GET APPROVAL FROM CD/GOP EB MANAGEMENT. 2.PLEASE CHECK LOS TOWARD FE IN ORDER TO REALLY ENSURE NO PARTIALLY BLOCK OCCUR FROM NE TO FE AND VICE VERSA.**** Existing HW MW Link 9261E-9363B, 15G_2+0_28MHZ_1024QAM_EPLA_448M. MW Swap to new HW MW Link 9261E-9363B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. Later, decom Antenna, ODU ONLY of HW MW Link 9261E-9363B, 15G_2+0_28MHZ_1024QAM_EPLA_448M. Anyway, do not decom existing RTN910AF(RTN01, NEID 9-35591) & existing RTN910AF(RTN08, NEID 9-35592). Site Impacted : 9261E. NE_9261E 1.Install new 18G_DP_0.6M(MAC) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-35591). 3.Install new XMC_3E , Sub B_Lo x2. Configure it. 4.Re-use existing xD Vlan dcn and Vlan services. 5.Migrate traffic 9261E via new HW MW Link 9261E-9363B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. 6.Later, decom Antenna, ODU ONLY of HW MW Link 9261E-9363B, 15G_2+0_28MHZ_1024QAM_EPLA_448M. Anyway, do not decom existing RTN910AF(RTN01, NEID 9-35591) & existing RTN910AF(RTN08, NEID 9-35592). | ****IMPORTANT NOTE: 1.PLEASE REQUEST CRQ BEFORE PROCEED IMPLEMENTATION & GET APPROVAL FROM CD/GOP EB MANAGEMENT. 2.PLEASE CHECK LOS TOWARD FE IN ORDER TO REALLY ENSURE NO PARTIALLY BLOCK OCCUR FROM NE TO FE AND VICE VERSA.**** Existing HW MW Link 9261E-9363B, 15G_2+0_28MHZ_1024QAM_EPLA_448M. MW Swap to new HW MW Link 9261E-9363B, 18G_2+0_110MHZ_256QAM_EPLA_1556M. Later, decom Antenna, ODU ONLY of HW MW Link 9261E-9363B, 15G_2+0_28MHZ_1024QAM_EPLA_448M. Anyway, do not decom existing RTN910AF(RTN01, NEID 9-35591) & existing RTN910AF(RTN08, NEID 9-35592). Site Impacted : 9261E. FE_9363B 1.Install new 18G_1.2M(MS) x1. 2.Re-use existing RTN910AF(RTN08, NEID 9-35592). 3.Install new XMC_3E , Sub B_Hi x2. Configure it. 4.Re-use existing xD Vlan dcn and Vlan services. 5.Enable port 8-EM6-2 of existing RTN910AF(RTN08, NEID 9-35592). 6.Request new port 1G(Electrical) at IBeam from ZTE IPRAN Team. 7.Perform patching in between port 8-EM6-2 of existing RTN910AF(RTN08, NEID 9-35592) and new port 1G(Electrical) at IBeam. 8.Perform 2x LAG in between port 8-EM6-1 & 8-EM6-2 of existing RTN910AF(RTN08, NEID 9-35592) and existing port & new port of IBeam. 9.Migrate traffic 9261E via 2x LAG to IBeam. 10.Later, decom Antenna, ODU ONLY of HW MW Link 9261E-9363B, 15G_2+0_28MHZ_1024QAM_EPLA_448M. Anyway, do not decom existing RTN910AF(RTN01, NEID 9-35591) & existing RTN910AF(RTN08, NEID 9-35592). | XMC_3E | MAC & MS | 18G | 18G_DP_0.6M(MAC) x1 | 18G_1.2M(MS) x1 | YPTT | SQ202604230191-YPTT | YPTT | SQ202604230183-YPTT // SQ202604230187-YPTT |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26041601 |  | 2026-04-17 | 2026-04-18 | Completed | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-04-18 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-26 | 2026-04-30 | 2026-04-26 | 2026-04-26 | JORDAN CHIN ZHEN WOON6794000058 | YPTT TI | 2026-04-21 | 2026-05-09 | 2026-04-21 |  | NORAZHARI BIN MOHAMAD SALIM6794000032 | YPTT TI | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-21 | 2026-04-21 | 2026-05-09 | 2026-04-21 |  | NORAZHARI BIN MOHAMAD SALIM6794000032 | 2025-03-06: 2026-04-21; 2025-03-06: 2026-05-09; 2025-03-06: 2026-04-21 | [7 empty] | GTSB | SQ202604280383-GTSB
K01074_PORT_2 | JEN1_0008V_K01074_Kg.Musa | DU00006746703 | Northern | Kedah | 6.231485 | 100.668723 | [9 empty] | TSS+TI |  | NE_K01074 New CAT6 cable x1. | MW Re-engineering | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K01074_PORT_3. 2ND - DU K01074_PORT_2. 3RD - DU K01074_PORT_1. 4TH - DU K01074_PORT. 2.AFTER DU K01074_PORT, DU K01074_PORT_1, DU K01074_PORT_2 & DU K01074_PORT_3 COMPLETED, MAY DECOM EXISTING HW MW LINK K01074-K00406**** MW Re-engineering at K01074 in order to divert all child sites belong to K01074 to PTN/Cisco at K01074. Site Impacted : K01068. NE_K01074 1.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 4-26102). 2.Request new PTN/Cisco 1G(Electrical) port from ZTE IPRAN team at K01074. 3.Perform new patching in between port 8-EM6-1 of existing RTN910AF(RTN01, NEID 4-26102) and new PTN/Cisco port from ZTE IPRAN team at K01074. 4.Request new xC Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffic K01068 into new port of PTN/Cisco. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K01074_PORT_3. 2ND - DU K01074_PORT_2. 3RD - DU K01074_PORT_1. 4TH - DU K01074_PORT. 2.AFTER DU K01074_PORT, DU K01074_PORT_1, DU K01074_PORT_2 & DU K01074_PORT_3 COMPLETED, MAY DECOM EXISTING HW MW LINK K01074-K00406**** MW Re-engineering at K01074 in order to divert all child sites belong to K01074 to PTN/Cisco at K01074. Site Impacted : K01068. NE_K01074 1.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 4-26102). 2.Request new PTN/Cisco 1G(Electrical) port from ZTE IPRAN team at K01074. 3.Perform new patching in between port 8-EM6-1 of existing RTN910AF(RTN01, NEID 4-26102) and new PTN/Cisco port from ZTE IPRAN team at K01074. 4.Request new xC Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffic K01068 into new port of PTN/Cisco. | [6 empty] | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050478 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280373-GTSB
K01074_PORT_1 | JEN1_0008V_K01074_Kg.Musa | DU00006746704 | Northern | Kedah | 6.231485 | 100.668723 | [9 empty] | TSS+TI |  | NE_K01074 New CAT6 cable x1. | MW Re-engineering | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K01074_PORT_3. 2ND - DU K01074_PORT_2. 3RD - DU K01074_PORT_1. 4TH - DU K01074_PORT. 2.AFTER DU K01074_PORT, DU K01074_PORT_1, DU K01074_PORT_2 & DU K01074_PORT_3 COMPLETED, MAY DECOM EXISTING HW MW LINK K01074-K00406**** MW Re-engineering at K01074 in order to divert all child sites belong to K01074 to PTN/Cisco at K01074. Site Impacted : K01073. NE_K01074 1.Enable port 8-EM6-1 of existing RTN910AF(RTN05, NEID 4-26108). 2.Request new PTN/Cisco 1G(Electrical) port from ZTE IPRAN team at K01074. 3.Perform new patching in between port 8-EM6-1 of existing RTN910AF(RTN05, NEID 4-26108) and new PTN/Cisco port from ZTE IPRAN team at K01074. 4.Request new xC Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffic K01073 into new port of PTN/Cisco. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K01074_PORT_3. 2ND - DU K01074_PORT_2. 3RD - DU K01074_PORT_1. 4TH - DU K01074_PORT. 2.AFTER DU K01074_PORT, DU K01074_PORT_1, DU K01074_PORT_2 & DU K01074_PORT_3 COMPLETED, MAY DECOM EXISTING HW MW LINK K01074-K00406**** MW Re-engineering at K01074 in order to divert all child sites belong to K01074 to PTN/Cisco at K01074. Site Impacted : K01073. NE_K01074 1.Enable port 8-EM6-1 of existing RTN910AF(RTN05, NEID 4-26108). 2.Request new PTN/Cisco 1G(Electrical) port from ZTE IPRAN team at K01074. 3.Perform new patching in between port 8-EM6-1 of existing RTN910AF(RTN05, NEID 4-26108) and new PTN/Cisco port from ZTE IPRAN team at K01074. 4.Request new xC Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffic K01073 into new port of PTN/Cisco. | [6 empty] | GTSB | SQ202605070547-GTSB | GTSB | SQ202605070546-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050481 |  | 2026-05-05 |  | Ongoing | 2026-05-04 | 2026-05-05 | 2026-05-04 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GTSB | SQ202604280373-GTSB
7710B_AD | CentralPlaza | DU00006746705 | Sabah | Sabah | 5.950860 | 116.072480 | [9 empty] | TSS+AA+TI+Dismantle |  | 23G_2+0_112M_512QAM_EPLA. NE_7710B New 23G_DP_0.6M(MAC)+OMT x1. New RTN910AF(RTN02). New IF cables with suitable length and type x2 RUN. New XMC_3E, Sub A&B_Lo x2. New CAT6 cable x1. FE_7229C New 23G_DP_0.6M(MAC)+OMT x1. Re-use new RTN910AF(RTN02) belong to DU S00464_AD. New IF cables with suitable length and type x2 RUN. New XMC_3E, Sub A&B_Hi x2. New ISM8 x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU S00464_AD. 2ND - DU 7710B_AD.**** Existing HW MW Link 7710B-7135B, 23G_2+0_112MHZ_512QAM_EPLA. Install new MW Link/Reroute HW MW Link 7710B-7229C, 23G_2+0_112MHZ_512QAM_EPLA. Later, decom existing HW MW Link 7710B-7135B, 23G_2+0_112MHZ_512QAM_EPLA. Site Impacted : 7710B. NE_7710B 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02) x1. 3.Install XMC_3E, Sub A&B_Lo x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 Port 1&2. 5.Build new MW Link/Reroute HW MW Link 7710B-7229C, 23G_2+0_112MHZ_512QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN02). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN02) to existing BBU(7710B). 8.Request new xD Vlan DCN and Vlan Services. 9.Migrate traffic 7710B via new MW Link/Reroute HW MW Link 7710B-7229C, 23G_2+0_112MHZ_512QAM_EPLA. 10.Later, decom existing HW MW Link 7710B-7135B, 23G_2+0_112MHZ_512QAM_EPLA. FE_7229C 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Re-use new RTN910AF(RTN02) belong to DU S00464_AD and insert new ISM8 x1 into slot 03. 3.Install XMC_3E, Sub A&B_Hi x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 Port 1&2. 5.Build new MW Link/Reroute HW MW Link 7710B-7229C, 23G_2+0_112MHZ_512QAM_EPLA. 6.Request new xD Vlan DCN and Vlan Services. 7.Migrate traffic 7710B via existing port at IBeam(CP 7000A) similar port with traffic 7229C. 8.Later, decom existing HW MW Link 7710B-7135B, 23G_2+0_112MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU S00464_AD. 2ND - DU 7710B_AD.**** Existing HW MW Link 7710B-7135B, 23G_2+0_112MHZ_512QAM_EPLA. Install new MW Link/Reroute HW MW Link 7710B-7229C, 23G_2+0_112MHZ_512QAM_EPLA. Later, decom existing HW MW Link 7710B-7135B, 23G_2+0_112MHZ_512QAM_EPLA. Site Impacted : 7710B. NE_7710B 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Install new RTN910AF(RTN02) x1. 3.Install XMC_3E, Sub A&B_Lo x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 07 Port 1&2. 5.Build new MW Link/Reroute HW MW Link 7710B-7229C, 23G_2+0_112MHZ_512QAM_EPLA. 6.Enable port 8-EM6-1 of new RTN910AF(RTN02). 7.Perform patching port 8-EM6-1 of new RTN910AF(RTN02) to existing BBU(7710B). 8.Request new xD Vlan DCN and Vlan Services. 9.Migrate traffic 7710B via new MW Link/Reroute HW MW Link 7710B-7229C, 23G_2+0_112MHZ_512QAM_EPLA. 10.Later, decom existing HW MW Link 7710B-7135B, 23G_2+0_112MHZ_512QAM_EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU S00464_AD. 2ND - DU 7710B_AD.**** Existing HW MW Link 7710B-7135B, 23G_2+0_112MHZ_512QAM_EPLA. Install new MW Link/Reroute HW MW Link 7710B-7229C, 23G_2+0_112MHZ_512QAM_EPLA. Later, decom existing HW MW Link 7710B-7135B, 23G_2+0_112MHZ_512QAM_EPLA. Site Impacted : 7710B. FE_7229C 1.Install new 23G_DP_0.6M(MAC)+OMT x1. 2.Re-use new RTN910AF(RTN02) belong to DU S00464_AD and insert new ISM8 x1 into slot 03. 3.Install XMC_3E, Sub A&B_Hi x2. 4.Lay new IF cables with suitable length and type x2 RUN at slot 03 Port 1&2. 5.Build new MW Link/Reroute HW MW Link 7710B-7229C, 23G_2+0_112MHZ_512QAM_EPLA. 6.Request new xD Vlan DCN and Vlan Services. 7.Migrate traffic 7710B via existing port at IBeam(CP 7000A) similar port with traffic 7229C. 8.Later, decom existing HW MW Link 7710B-7135B, 23G_2+0_112MHZ_512QAM_EPLA. | XMC_3E | MAC | 23G | 23G_DP_0.6M(MAC)+OMT x1 | 23G_DP_0.6M(MAC)+OMT x1 | Seri Pancar | SQ202604290792-Seri Pancar |  |  |  |  | Ongoing | 2026-04-23 | 2026-04-30 | 2026-04-23 | 2026-04-23 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-05-04 | 2026-05-11 | 2026-05-04 | 2026-05-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-04 | 2026-05-11 | 2026-05-04 | 2026-05-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-06 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604280376-GTSB
7013A_IPR | Jln Airport | DU00005610715 | Sabah | Sabah | 6.913645 | 116.843388 |  |  |  |  | TI DONE |  |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1 x cat6 cable | IDU-IPRAN | Patch 7013A RTN04 GE2 to new IPRAN port and create LAG | Patch 7013A RTN04 GE2 to new IPRAN port and create LAG | [6 empty] | NR services | SQ202506230395-NR Services | NR services | SQ202506200691-NR Services | 2025-07-11 | 2025-07-07 | Completed | 2025-06-19 | 2025-06-20 | 2025-06-19 | 2025-06-20 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | AZRI//BIN ABDULLAH/6799000073 | Design and Material Team | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | AZRI//BIN ABDULLAH/6799000073 | Design and Material Team | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25060712 |  | 2025-06-08 | 2025-06-10 | Completed | 2025-06-07 | 2025-06-08 | 2025-06-07 | 2025-06-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-20 | 2025-07-20 | 2025-06-20 | 2025-06-20 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-06-20 | 2025-07-20 | 2025-06-20 | 2025-06-20 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-20 | 2025-06-20 | 2025-07-20 | 2025-06-20 | 2025-06-23 | RALPH O'BRYAN HILARY7167000030 | 2025-03-06: 2025-06-20; 2025-03-06: 2025-07-20; 2025-03-06: 2025-06-20; 2025-03-07: 2025-06-20 |  |  | 2025-07-24 | 2025-08-24 | 2025-07-24 | 2025-07-24 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507080638-GTSB | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | AB.RAHMAN//BIN MAT NOOH/6237001519
4958A_HU | Pokok Sena Kedah(Celcom) | DU00006301134 | Northern | Kedah | 6.155900 | 100.519130 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC |  | MW Hardware Upgrade | Hardware upgrade from 23G_3+0_112M to 23G_4+0_112M.To support 4700D , 4701D and 4958A. Existing link 23G_1+0_112M to support.4700D & 4701D. Site Impacted : 4700D , 4701D and 4958A. NE_4958A. 1.Reuse existing 4958A_RTN 11. 2.Transfer existing 4958A_RTN06-3_ISM8-1+0 to 4958A_RTN11-4_ISM8-1+0 , to support 4700D. 3.Transfer existing 4958A_RTN06- IF cable from 3_ISM8-1+0 to 4958A_RTN11- 7_ISM8-1+0 , port 2. Hardware upgrade from 23G_3+0_112M to 23G_4+0_112M for upstream link. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to upgrade MW link 23G_4+0_112M. 6.Decom 4958A_RTN 06 ONLY. FE_4292B 1.Reuse existing 4292B_RTN02. 2.Transfer 4292B_RTN03 the IF cable 7_ISM8 port 1 to 4292B_RTN02 the 7_ISM8 port2.Hardware upgrade from 23G_3+0_112M to 23G_4+0_112M for upstream link. 3.Remain Fiber CP port and DCN. 4.Remove existing LAN cable interconnect between 4292B_RTN02 & RTN03 and disable unused port. 5.Decom 4292B_RTN03 ONLY. | Hardware upgrade from 23G_3+0_112M to 23G_4+0_112M.To support 4700D , 4701D and 4958A. Existing link 23G_1+0_112M to support.4700D & 4701D. Site Impacted : 4700D , 4701D and 4958A. NE_4958A. 1.Reuse existing 4958A_RTN 11. 2.Transfer existing 4958A_RTN06-3_ISM8-1+0 to 4958A_RTN11-4_ISM8-1+0 , to support 4700D. 3.Transfer existing 4958A_RTN06- IF cable from 3_ISM8-1+0 to 4958A_RTN11- 7_ISM8-1+0 , port 2. Hardware upgrade from 23G_3+0_112M to 23G_4+0_112M for upstream link. 4.Create service cross connect and EPLA with existing link. 5.Traffic migrate to upgrade MW link 23G_4+0_112M. 6.Decom 4958A_RTN 06 ONLY. | Hardware upgrade from 23G_3+0_112M to 23G_4+0_112M.To support 4700D , 4701D and 4958A. Existing link 23G_1+0_112M to support.4700D & 4701D. Site Impacted : 4700D , 4701D and 4958A. FE_4292B 1.Reuse existing 4292B_RTN02. 2.Transfer 4292B_RTN03 the IF cable 7_ISM8 port 1 to 4292B_RTN02 the 7_ISM8 port2.Hardware upgrade from 23G_3+0_112M to 23G_4+0_112M for upstream link. 3.Remain Fiber CP port and DCN. 4.Remove existing LAN cable interconnect between 4292B_RTN02 & RTN03 and disable unused port. 5.Decom 4292B_RTN03 ONLY. | [5 empty] | GTSB | SQ202512300554-GTSB | GTSB | SQ202512160957-GTSB // SQ202512240260-GTSB | 2026-02-23 | 2026-02-23 | Completed | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | MOHD//BADRIZ BIN NANANG/6799000311 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251118AN |  | 2025-11-19 | 2025-11-20 | Completed | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-16 | UWAIS AL QARNI BIN HISHAMUDIN6799000241 | GTSB TI | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-15 | UWAIS AL QARNI BIN HISHAMUDIN6799000241 | GTSB TI | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-13 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-16 | UWAIS AL QARNI BIN HISHAMUDIN6799000241 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-14 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511130557-GCI | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | CHEONG/SENG/WAH/7018000306
3615B_AD | Lorong Bakong Tlk Pulai | DU00006317408 | Central | Selangor | 3.039306 | 101.439201 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Remote upgrade to from 395.5M to 500M as per requested from CD. NE_3615B Upgrade 512QAM_56Mhz to 112M FE_1017A Upgrade 512QAM_56Mhz to 112M | NE_3615B Upgrade 512QAM_56Mhz to 112Mhz | FE_1017A Upgrade 512QAM_56Mhz to 112M | [5 empty] | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-11-22 | 2025-11-22 | 2025-11-22 | 2025-11-22 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202511130554-GCI | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | CHEONG/SENG/WAH/7018000306
9964A_PL | Unimas (REL) | DU00006317409 | Sarawak | Sarawak | 1.458582 | 110.449531 | [9 empty] | TSS+TI |  | ETH LAN Cable x1 | BBU Patching | Transfer 9964A_BBU from 9964A_RTN02 to 9964A_RTN01 | NE_9964A 1.9964A_BBU transfer from RTN02 to RTN01. | [6 empty] | Allstar | SQ202603180484-Allstar | Allstar | SQ202603180480-Allstar |  |  | Ongoing | 2026-04-29 | 2026-05-05 | 2026-04-29 | 2026-04-29 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-05-05 | 2026-04-29 | 2026-04-29 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26030630 |  | 2026-03-07 | 2026-03-31 | Completed | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-31 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-16 | 2026-03-23 | 2026-03-31 | 2026-03-31 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-03-16 | 2026-03-23 |  |  | ROYSTON//AHHOLE/6000038561 | Allstar TI | [7 empty] | 2026-03-16 | 2026-03-23 |  |  | ROYSTON//AHHOLE/6000038561 | 2026-01-07: 2026-03-16; 2026-01-07: 2026-03-23; 2026-01-07: 2026-03-16; 2026-01-14: 2026-03-16 | [7 empty] | GCI | SQ202511130570-GCI | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | CHEONG/SENG/WAH/7018000306
7376K1_EVT | DCABIN LABUANINTERNATIONAL SEA CHALLENGE 2026 | DU00006758176 | Sabah | Labuan | 5.275925 | 115.254833 | [13 empty] | Planning and integration support only for event site 7376K1_EVT DCABIN LABUAN INTERNATIONAL SEA CHALLENGE 2026 Tx route: 7376K1/7376K1-7084A 1) New port at 7084A-MAC-001 IOFC 2) New NE ID FE IDU 7084A (ops to assign RTN number) 3) New NE ID NE IDU 7376K1 RTN01 2) New DCN IP 7084A (ops to assign RTN number) 3) New DCN VLAN 7084A (ops to assign RTN number) | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
1037L_AD | Taman MeruMurni | DU00006789105 | Central | Selangor | 3.138352 | 101.451216 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M NE_1037L 18G_DP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A_HI x1. FE_B00399. 18G_DP_1.2M(MAC) x1. RTN910A x1. XMC_3E , Sub A_Lo x1. | MW New Link / Reroute | Link reroute to new FE B00399 with 18G_1+0_112M Site Impacted : 1037L NE_1037L 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_HI. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW (1037L-1099A). FE_B00399. 1.Install new 18G_DP_1.2M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Create New Inband DCN 6.Traffic migrate to new link. 7.Decom existing MW (1099A-1037L). | Link reroute to new FE B00399 with 18G_1+0_112M Site Impacted : 1037L NE_1037L 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_HI. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW (1037L-1099A). | Link reroute to new FE B00399 with 18G_1+0_112M Site Impacted : 1037L FE_B00399. 1.Install new 18G_DP_1.2M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Create New Inband DCN 6.Traffic migrate to new link. 7.Decom existing MW (1099A-1037L). | XMC_3E | MAC | 18G | 0.6 | 1.2 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042936 |  | 2026-04-30 |  | Ongoing | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-04 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | Aminuddin bin che azibA0563734967123169280 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-04-30 | [7 empty] | GCI | SQ202605060248-GCI | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | CHEONG/SENG/WAH/7018000306
3888B_AD | ShellTmn Meru Jaya | DU00006789106 | Central | Selangor | 3.118490 | 101.438227 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | TX Mini Project, 3888B-B00399, 23G 2+0, ODU XMC-3 112MHz Sub band A x 2, RTN910A x 2, A23D03MAC-3NX x 1, A23D03MAC-3NX x 1, Ant ht NE/FE: 24m/35m | MW New Link / Reroute | 1. Install MW New Link 2. Decom existing MW | 1. Install 23G 0.3DP dish, 2+0, ODU TX high, ODU XMC-3 Sub band A x 1, IDU RTN910A x 1; IDU patching BBU; Migration into new link: BBU 3888B 2. Decom existing MW 3888B-1099A | Install 23G 0.3DP dish, 2+0, ODU TX low, ODU XMC-3 Sub band A x 1, IDU RTN910A x 1; IDU patching to CISCO new port | XMC-3 | MAC | 23G | 0.3 | 0.3 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042928 |  | 2026-04-30 | 2026-04-29 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-04 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-30; 2026-01-14: 2026-04-30 | [7 empty] | GTSB | SQ202605060264-GTSB | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | LIM//WEI CHONG/6798000110
3002A9_AD | pBTSPahang Pharmacy | DU00006789107 | Central | Selangor | 3.116031 | 101.447534 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | TX Mini Project, 3002A9-B00399, 23G 1+0, ODU XMC-3 112MHz Sub band A x 2, RTN910A x 2, A23D06MAC-3NX x 1, A23D06MAC-3NX x 1, Ant ht NE/FE: 24m/35m | MW New Link / Reroute | Install MW New Link | Install 23G 0.6DP dish, 1+0, ODU TX high, ODU XMC-3 Sub band A x 1, IDU RTN910A x 1; IDU patching BBU; Migration into new link: BBU 3002A9 | Install 23G 0.6DP dish, 1+0, ODU TX low, ODU XMC-3 Sub band A x 1, IDU RTN910A x 1; IDU patching to CISCO new port | XMC-3 | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042921 |  | 2026-04-30 | 2026-04-29 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-07 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-05-02 | [7 empty] | GTSB | SQ202605060264-GTSB | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | LIM//WEI CHONG/6798000110
3580C_AD | PersiaranSetia Prima | DU00006789108 | Central | Selangor | 3.091481 | 101.455155 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | TX Mini Project, 3580C-B00399, 18G 1+0 Non CA, ODU XMC-5D 110MHz Sub band B x 2, RTN910A x 2, A18D06MDD-3NX x 1, A18D06MDD-3NX x 1, Ant ht NE/FE: 24m/35m, Each MODU install 1 IF cable | MW New Link / Reroute | Install MW New Link | Install 18G 0.6DP dish, 1+0 Non CA, ODU TX high, ODU XMC-5D Sub band B x 1, IDU RTN910A x 1, Each MODU install 1 IF cable; IDU patching BBU; Migration into new link: BBU 3580C | Install 18G 0.6DP dish, 1+0 Non CA, ODU 0, ODU XMC-5D Sub band B x 1, IDU RTN910A x 1, Each MODU install 1 IF cable; IDU patching to CISCO new port | XMC-5D | MDD | 18G | 0.6 | 0.6 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042949 |  | 2026-04-30 | 2026-04-29 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-07 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-05-01 | [7 empty] | GTSB | SQ202605060264-GTSB | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | LIM//WEI CHONG/6798000110
3175A_AD | JalanSetia Prima | DU00006789109 | Central | Selangor | 3.100196 | 101.443974 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | TX Mini Project, 3175A-B00399, 23G 1+0, ODU XMC-3 112MHz Sub band B x 2, RTN910A x 2, A23D06MAC-3NX x 1, A23D06MAC-3NX x 1, Ant ht NE/FE: 24m/35m | MW New Link / Reroute | Install MW New Link | Install 23G 0.6DP dish, 1+0, ODU TX high, ODU XMC-3 Sub band B x 1, IDU RTN910A x 1; IDU patching BBU; Migration into new link: BBU 1673C,3175A | Install 23G 0.6DP dish, 1+0, ODU TX low, ODU XMC-3 Sub band B x 1, IDU RTN910A x 1; IDU patching to CISCO new port | XMC-3 | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042927 |  | 2026-04-30 | 2026-04-29 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMMAD//NORSAZLI BIN ABDULLAH/6799000208 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMMAD//NORSAZLI BIN ABDULLAH/6799000208 | GTSB TI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-07 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMMAD//NORSAZLI BIN ABDULLAH/6799000208 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-05-01 | [7 empty] | GTSB | SQ202605060264-GTSB | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | LIM//WEI CHONG/6798000110
1132C_AD | JalanKhamis | DU00006789110 | Central | Selangor | 3.130615 | 101.428167 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M NE_1132C 18G_DP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub B_HI x1. FE_B00399. 18G_DP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub B_Lo x1 | MW New Link / Reroute | Link reroute to new FE B00399 with 18G_1+0_112M Site Impacted : 1132C , 2931A NE_1132C 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_HI. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW (1132C-1099A). FE_B00399. 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link. 7.Decom existing MW link (1099A-1132C). | Link reroute to new FE B00399 with 18G_1+0_112M Site Impacted : 1132C , 2931A NE_1132C 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_HI. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW (1132C-1099A). | Link reroute to new FE B00399 with 18G_1+0_112M Site Impacted : 1132C , 2931A FE_B00399. 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new link. 7.Decom existing MW link (1099A-1132C). | XMC_3E | MAC | 18G | 0.6 | 0.6 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042939 |  | 2026-04-30 | 2026-04-29 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | Aminuddin bin che azibA0563734967123169280 | GTSB TI | 2026-05-03 | 2026-05-03 | 2026-05-03 | 2026-05-03 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-03 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | Aminuddin bin che azibA0563734967123169280 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-05-01 | [7 empty] | GCI | SQ202605060248-GCI | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | CHEONG/SENG/WAH/7018000306
1243C_AD | JalanSetia Murni | DU00006789111 | Central | Selangor | 3.111312 | 101.452753 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3 SUB A HI 1x ODU 23G XMC3 SUB A LO 1x ODU 23G XMC3 SUB B HI 1x ODU 23G XMC3 SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE 1243C-B00399 WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3_SUB_A & B_LINK_1.06KM DISMANTLE EXISTING LINK 1243C-1099A IMPACTED: 1243C | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 1243C-1099A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 1243C-1099A 6. PATCH 1G LAG PORT TO B00399 OB FIBER | XMC3 | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042918 |  | 2026-04-30 | 2026-04-29 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMMAD//NORSAZLI BIN ABDULLAH/6799000208 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMMAD//NORSAZLI BIN ABDULLAH/6799000208 | GTSB TI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-07 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMMAD//NORSAZLI BIN ABDULLAH/6799000208 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-05-02 | [7 empty] | GCI | SQ202605060248-GCI | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
3027C_AD | SgKapar Industrial (REL) | DU00006789112 | Central | Selangor | 3.102880 | 101.400100 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | TX Mini Project, 3027C-B00399, 18G 2+0, ODU XMC-3 110MHz Sub band B x 2, RTN910A x 2, A18D12MAC-3NX x 1, A18D12MAC-3NX x 1, Ant ht NE/FE: 24m/35m | MW New Link / Reroute | 1. Install MW New Link 2. Decom existing MW | 1. Install 18G 1.2DP dish, 2+0, ODU TX low, ODU XMC-3 Sub band B x 1, IDU RTN910A x 1; IDU patching BBU; Migration into new link: BBU 3027C 2. Decom existing MW 3027C-1099A | Install 18G 1.2DP dish, 2+0, ODU TX high, ODU XMC-3 Sub band B x 1, IDU RTN910A x 1; IDU patching to CISCO new port | XMC-3 | MAC | 18G | 1.2 | 1.2 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042945 |  | 2026-04-30 | 2026-04-29 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-07 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-05-01 | [7 empty] | GTSB | SQ202605060264-GTSB | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | LIM//WEI CHONG/6798000110
1460H_AD | 99Speedmart KLANG SENTRAL | DU00006789113 | Central | Selangor | 3.110852 | 101.438075 | [9 empty] | TSS+TI+Dismantle |  | NLOS Radio (RTN510). NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | Link reroute to new FE B00399 due to LOS Block. NLOS Radio RTN510 Site Impacted : 1460H NE_1460H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1460H-NLOS-1099A FE_B00399 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1460H-NLOS-1099A | Link reroute to new FE B00399 due to LOS Block. NLOS Radio RTN510 Site Impacted : 1460H NE_1460H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1460H-NLOS-1099A FE_B00399 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1460H-NLOS-1099A | Link reroute to new FE B00399 due to LOS Block. NLOS Radio RTN510 Site Impacted : 1460H NE_1460H 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1460H-NLOS-1099A FE_B00399 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Capture existing NLOS parameters and create service cross connect. 5.Traffic migrate to new route FE site. 6.Decom existing NLOS radio 1460H-NLOS-1099A | [5 empty] | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042913 |  | 2026-04-30 | 2026-04-29 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | [7 empty] | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-05-02 | [7 empty] | GCI | SQ202605060248-GCI | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
2640B_AD | MutiaraBkt Raja LP 1 | DU00006789114 | Central | Selangor | 3.090386 | 101.431221 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1x ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1x ODU 18G XMC3E SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE 2640B-B00399 WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_256QAM_1556MBPS_XMC3E_SUB_A & B_LINK_2.64KM DISMANTLE EXISTING LINK 2640B-1099A IMPACTED: 2640B | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK 2640B-1099A | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3 112MHZ SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ 256QAM & CREATE LAG. 5. DISMANTLE EXISTING LINK 2640B-1099A 6. PATCH 1G LAG PORT TO B00399 OB FIBER | XMC3 | MAC | 18G | 0.6 | 0.6 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042943 |  | 2026-04-30 | 2026-04-29 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-07 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-04-30 | [7 empty] | GCI | SQ202605060248-GCI | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | EZRIN TASNIM BIN ABDUL GANI6798000128
B02846_AD | B061A_B02846OD_PSNSETIAPRIMASETIAALAM2 | DU00006789115 | Central | Selangor | 3.095121 | 101.455116 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M. NE_B02846 18G_DP_0.6M(MAC) x1. RTN910A x1 XMC_3E , Sub A_HI x1. FE_B00399. 18G_DP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A_Lo x1. | MW New Link / Reroute | Link reroute to new FE B00399 with 18G_1+0_112M. Site Impacted : B02846 NE_B02846 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_HI. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW link (B02846-1099A). FE_B00399. 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW link (1099A-B02486) | Link reroute to new FE B00399 with 18G_1+0_112M. Site Impacted : B02846 NE_B02846 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_HI. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW link (B02846-1099A). | Link reroute to new FE B00399 with 18G_1+0_112M. Site Impacted : B02846 FE_B00399. 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW link (1099A-B02486) | XMC | MAC | 18G | 0.6 | 0.6 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042941 |  | 2026-04-30 | 2026-04-29 | Completed | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-07 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-05-01 | [7 empty] | GCI | SQ202605060248-GCI | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | CHEONG/SENG/WAH/7018000306
B02425_AD | B061A_B02425OD_JLNSETIAGEMILANG | DU00006789116 | Central | Selangor | 3.128470 | 101.466980 | [9 empty] | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_112M NE_B02425 18G_DP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub B_HI x1. FE_B00399. 8G_DP_1.2M(MAC) x1. RTN910A x1. XMC_3E , Sub B_Lo x1. | MW New Link / Reroute | Link reroute to new FE B00399 with 18G_1+0_112M. Site Impacted : B02846 NE_B02846 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A & B_HI. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW link (B02846-1099A). FE_B00399. 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW link (1099A-B02486) | Link reroute to new FE B00399 with 18G_1+0_112M. Site Impacted : B02846 NE_B02846 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A & B_HI. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW link (B02846-1099A). | Link reroute to new FE B00399 with 18G_1+0_112M. Site Impacted : B02846 FE_B00399. 1.Install new 18G_DP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW link (1099A-B02486) | XMC_3E | MAC | 18G | 0.6 | 1.2 | GTSB | SQ202604290755-GTSB | GTSB | SQ202605070522-GTSB // SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042934 |  | 2026-04-30 |  | Ongoing | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2026-05-03 | 2026-05-03 | 2026-05-03 | 2026-05-03 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-05-03 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2026-01-07: 2026-04-29; 2026-01-07: 2026-04-30; 2026-01-07: 2026-04-29; 2026-01-14: 2026-05-02 | [7 empty] | GCI | SQ202605060248-GCI | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | CHEONG/SENG/WAH/7018000306
W00004_HU | W066V_W00004OD_UM25THKOLEJ | DU00005399683 | Central | Kuala Lumpur | 3.128900 | 101.660600 |  | APR 25 |  | JUN 25 | DO | Pending edotco approval | ZTE | 00. Integrated/RFS Done | 21/4/2025 : EDOTCO (M) SDN BHD - TRIPOD 9M ROOFTOP - NE site W00004 W066V_W00004OD_UM25THKOLEJ, TELEKOM MALAYSIA BERHAD - INBUILDING - FE site W00320 W066V_W00663IB2_TMWHOLESALE | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M MDD ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK W00320-W00004 WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_1.44KM IMPACTED: W00320 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202504280360-Magicell | GTSB | SQ202506120579-GTSB // SQ202506120582-GTSB | 2025-07-03 | 2025-07-02 | Completed | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-27 | 2025-05-26 | 2025-05-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-02 | 2025-07-03 | 2025-07-02 | 2025-07-02 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25052165 |  | 2025-05-22 | 2025-05-23 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-04 | 2025-07-31 | 2025-07-04 | 2025-07-04 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-07-04 | 2025-07-31 | 2025-07-04 | 2025-07-10 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-09 | 2025-07-04 | 2025-07-31 | 2025-07-04 | 2026-02-26 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-07-04 | 2025-07-31 | 2025-07-04 | 2025-07-04 | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202506050696-GCI | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
7426A-7401A | Kg Tengkurus | DU00004301193 | Sabah | Sabah | 6.311590 | 116.516110 |  |  |  |  | Pending RTM Permit | Pending access at FE/RTM KB | ZTE | 02. Pending Access | 30/10: Uplink for 7332B_LOS | TSS+AA+TI |  | Parallel link for 13G_4+0_28M_1.8/1.8. NE_7426A 13G_DP_1.8m(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D , Sub_ B_Hi x1. FE_7401A 13G_DP_1.8m(MDD) x1. RTN910A x1. ISM8 x2. XMC_5D, Sub B_Lo x1. | MW Parallel Link | Parallel link for 13G_4+0_28M_CA_1.8/1.8. Site Impacted: 7332B,7772B. NE_7426A 1.Install 13G_DP_1.8m(MDD). 2.Install RTN910A 3.Install 3_ISM8-2+0 & 4_ISM8-2+0 4.Enable EPLA and service cross connect & CA. 5.Remove existing interconnect ETH cable RTN01 (GE port 1) to RTN02 (GE port 2). 6.Interconnect new ETH cable from existing RTN01(GE port1) to new RTN901A (GE port1). 7.Traffic 7332B & 7772B via this parallel link. 8.No decom due to install new parallel link. FE_7401A 1.Install 13G_DP_1.8m(MDD). 2.Install RTN910A 3.Install 3_ISM8-2+0 & 4_ISM8-2+0. 4.Enable GE port and EPLA & CA for 4+0 config. 5.Create In-Band DCN and service cross connect. 6.Traffic 7332B & 7772B via this parallel link. 7.Enable GE port patching to Ibeam. 8.No decom due to install new parallel link. | Parallel link for 13G_4+0_28M_CA_1.8/1.8. Site Impacted: 7332B,7772B. NE_7426A 1.Install 13G_DP_1.8m(MDD). 2.Install RTN910A 3.Install 3_ISM8-2+0 & 4_ISM8-2+0 4.Enable EPLA and service cross connect & CA. 5.Remove existing interconnect ETH cable RTN01 (GE port 1) to RTN02 (GE port 2). 6.Interconnect new ETH cable from existing RTN01(GE port1) to new RTN901A (GE port1). 7.Traffic 7332B & 7772B via this parallel link. 8.No decom due to install new parallel link. | Parallel link for 13G_4+0_28M_CA_1.8/1.8. Site Impacted: 7332B,7772B. FE_7401A 1.Install 13G_DP_1.8m(MDD). 2.Install RTN910A 3.Install 3_ISM8-2+0 & 4_ISM8-2+0. 4.Enable GE port and EPLA & CA for 4+0 config. 5.Create In-Band DCN and service cross connect. 6.Traffic 7332B & 7772B via this parallel link. 7.Enable GE port patching to Ibeam. 8.No decom due to install new parallel link. | [5 empty] | NR services | SQ202507300491-NR Services | NR services | SQ202507290140-NR Services // SQ202507290144-NR Services | 2025-10-31 | 2025-10-31 | Completed | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-04 | 2025-08-05 | 2025-08-04 | 2025-08-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-04 | 2025-08-05 | 2025-08-04 | 2025-08-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071525 |  | 2025-07-16 | 2025-08-01 | Completed | 2025-07-15 | 2025-07-16 | 2025-07-15 | 2025-08-01 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI_AA | SQ202510300170-GCI | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | CHEONG/SENG/WAH/7018000306
4141R-4396A | KG.KEDAI DUA | DU00004319012 | Northern | Perak | 5.022659 | 100.468410 | [7 empty] | 00. Integrated/RFS Done | 28/11: D3: Cutover done 26/11: D1: MOS & TI WIP | TSS+AA+TI | L1+ATP+PAC | 2X RTN 910A 2X 18G 1.2M DP ANTENNA 1X 18G XMC-3E SUB A HI 1X 18G XMC-3E SUB A LO 1X 18G XMC-3E SUB B HI 1X 18G XMC-3E SUB B LO 2X 10G SFP 1X PATCH CORD SET | MW Parallel Link | ADD PARALLEL MW LINK 4141R-4396A WITH HUAWEI_18G_112MHZ_2+0_1.2M_4KM (TO CARRY 4334A) MW IDU PATCHING AT 4396A & A00216, TO PATCH NEW RTN 910A TO CELCOM A00216 10G OB FIBER PORT IMPACTED SITES: N/A NE (4141R): 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW 2+0 18G XMC-3E SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ FE (4396A): 1. INSTALL NEW RTN 910A 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW 2+0 18G XMC-3E SUB A & B 4. CONFIGURE LINK 18G 2+0 112MHZ5 5. PATCH NEW RTN 910A TO NEW CELCOM A00216 10G PTN PORT | [7 empty] | GTSB | SQ202411140316-GTSB | GTSB | SQ202411260119-GTSB // SQ202504260178-GTSB | 2025-12-23 | 2025-12-23 | Completed | 2024-12-02 | 2024-12-02 | 2024-12-04 | 2024-12-05 | BARANEEDARAN//A/L SELVADASS SEBASTIN/6799000111 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24112242 |  | 2024-11-23 |  | Ongoing | 2024-11-22 | 2024-11-23 | 2024-11-22 |  | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-18 | FAZAL ABBAS6799000222 | GTSB TI | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-31 | FAZAL ABBAS6799000222 | GTSB TI | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2025-01-13 | FAZAL ABBAS6799000222 | 2026-01-07: 2024-11-27; 2026-01-07: 2024-11-27; 2026-01-07: 2024-11-27; 2026-01-14: 2026-01-30 |  |  | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
2727A-1362A_1 | Extreme Park Shah Alam | DU00004319013 | Central | Selangor | 3.086592 | 101.541617 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 8/11: Cutover done | TSS+TI | L1+ATP+PAC |  | MW Re-engineering | 1. Reengineering 2727A IDU RTN01 910A to 2727A IDU RTN02 910A. Impact site 2727A, 1790A, & 2598B. 2. Remain SIAE 2727A-1362A MW1 to carry NLOS 1603H site only. | [7 empty] | Datasco | SQ202411180344-Datasco | Datasco | SQ202411120058-Datasco // SQ202504260127-Datasco |  |  | Ongoing | 2024-11-09 | 2024-11-09 | 2024-11-09 | 2024-11-09 | MOHAMAD//ZULFAKAAR BIN SHAMSUDIN/7019000075 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | MOHAMAD//ZULFAKAAR BIN SHAMSUDIN/7019000075 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY241105C8 |  |  |  | Disabled | [8 empty] | Unassigned | Disabled |  | 2024-11-07 | 2024-11-07 | 2024-11-07 | 2025-02-25 | NORSHAMSUDIN//BIN DAUD/7019000007 | Datasco TI | 2024-11-07 | 2024-11-07 | 2024-11-07 |  | NORSHAMSUDIN//BIN DAUD/7019000007 | Datasco TI | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | SHUJAAT//ALI/6800000124 |  |  | 2024-11-07 | 2024-11-07 | 2024-11-07 | 2024-11-09 | NORSHAMSUDIN//BIN DAUD/7019000007 | 2026-01-07: 2024-11-07; 2026-01-07: 2024-11-07; 2026-01-07: 2024-11-07; 2026-01-14: 2024-11-09 |  |  | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202512180092-GTSB
3469C5 | pBTS Taman Indah Jaya | DU00004322408 | Central | Selangor | 3.073260 | 101.630591 |  |  |  |  | Cancel / Drop | Done under DU 3469C5_Additional TX NIC | ZTE | 00. Site Out/Drop | 28/2/2025 : No need proceed. Done under DU 3469C5_Additional TX NIC |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7647C-7209A | Taman Miramas Semporna | DU00004345185 | Sabah | Sabah | 4.466030 | 118.601960 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_7647C 23G_DP_0.6m(MAC) x1. RTN910A x1. ISM8- x1. XCM_3E , Sub A & B_Lo x2. FE_7209A. 23G_DP_0.6m(MAC) x1. XCM_3E-2+0 , sub A & B_Hi x2. ISM8- x1. | MW Swap | Existing MW link 18G_2+0_56M. Remote Software Upgrade Not Support due to hardware limitation. Swap existing link to 23G_2+0_112M. Site Impacted: 7647C,9004B. NE_7647C 1.Install new 23G_DP_0.6m(MAC). 2.Install new RTN910A. (RTN no provide by MSP team). 3.Install 3_ISM8-2+0. 4.Install XMC_3E-2+0 , sub A & B_Lo. 5.Tranfer existing IF Cable 7647C_RTN01_7_ISM8-1+0 to new RTN910A_7_ISM8-1+0.(9004B). 6.Migrate traffic from 7647C-7290A to new link 23G_2+0_112M. 7.Enable EPLA and service cross connect. 8.Decom existing MW link. FE_7209A. 1.Install new 23G_DP_0.6m(MAC). 2.Install new XCM_3E-2+0 , sub A & B_Hi. 3.Reuse existing 7209A_RTN01. 4.Install 3_ISM8-2+0 into existing 7209A_RTN01. 5.Enable EPLA , service cross connect and LAG Physical port. 6.Remain existing In-Band DCN. 7.Traffic migrate to new MW link. 8.Decom existing Ant and ODU. | [7 empty] | NR services | SQ202502260432-NR Services | NR services | SQ202502270741-NR Services // SQ202504260199-NR Services | 2025-09-04 | 2025-09-04 | Completed | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-02-25 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-02-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-02-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021539 |  | 2025-02-16 | 2025-02-18 | Completed | 2025-02-15 | 2025-02-16 | 2025-02-15 | 2025-02-18 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-20 | 2025-02-28 | 2025-02-20 | 2025-02-22 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-02-20 | 2025-02-28 | 2025-02-20 | 2025-02-22 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-02-23 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-23 | 2025-02-20 | 2025-02-28 | 2025-02-20 | 2025-02-27 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | 2025-02-20 | 2025-02-28 | 2025-02-20 | 2025-02-22 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016
4607C_HU | Kg Raja New Township | DU00005206084 | Northern | Perak | 4.558429 | 101.414746 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1x New CAT6 cable with suitable length | IPRAN Port Upgrade | IPRAN Port Upgrade need to perform in order to ensure air capacity from existing HW MW Link 4607C(RTN01)-4574A(RTN05) 15G_6+0_512QM_EPLA(1344Mbps), will also apply at 2x 1G IBeam port. Site Impacted : 4607C & 4161D. FE_4574A. 1.Enable port 8-EM6-2 of existing RTN910A(RTN05) for existing HW MW Link 4574A(RTN05)-4607C(RTN01) 15G_6+0_512QM_EPLA. 2.Enable 2nd new 1G port(electrical) of IBeam and request from ZTE IPRAN Team. 3.Patching CAT6 cable in between port 8-EM6-2 of existing RTN910A(RTN05) and new IBeam port. 4.Perform LAG between IBeam port(existing and new). Configure it. |  | IPRAN Port Upgrade need to perform in order to ensure air capacity from existing HW MW Link 4067C(RTN01)-4574A(RTN05) 15G_6+0_512QM_EPLA(1344Mbps), will also apply at 2x 1G IBeam port. Site Impacted : 4607C & 4161D. FE_4574A. 1.Enable port 8-EM6-2 of existing RTN910A(RTN05) for existing HW MW Link 4574A(RTN05)-4607C(RTN01) 15G_6+0_512QM_EPLA. 2.Enable 2nd new 1G port(electrical) of IBeam and request from ZTE IPRAN Team. 3.Patching CAT6 cable in between port 8-EM6-2 of existing RTN910A(RTN05) and new IBeam port. 4.Perform LAG between IBeam port(existing and new). Configure it. | [5 empty] | GCI | SQ202506200655-GCI | GCI | SQ202506190693-GCI | 2025-07-04 | 2025-07-04 | Completed | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-04 | 2025-07-02 | 2025-07-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061156 |  | 2025-06-12 | 2025-06-13 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-18 | 2025-06-30 | 2025-06-18 | 2025-06-24 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2025-06-18 | 2025-06-30 | 2025-06-18 | 2025-06-24 | JUTI//ANAK RICHARD/6800000216 | GCI TI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-18 | 2025-06-18 | 2025-06-30 | 2025-06-18 | 2025-07-05 | JUTI//ANAK RICHARD/6800000216 | 2026-01-07: 2025-06-18; 2026-01-07: 2025-06-30; 2026-01-07: 2025-06-18; 2026-01-14: 2025-07-15 |  |  | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505070167-GTSB
2476A_1_HU | Sg Serai (Maxis) | DU00005206085 | Central | Selangor | 3.284510 | 101.549880 | WK13 | MAR 25 | WK13 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 26/3/2025 : Cutover done 25/3/2025 : Installation complete, alignment WIP 19/3/2025 : MAXIS - 45M 3 Legged Tower - NE site 2476A Sg Serai (Maxis), Digi OB - 60M 4 Legged Tower - FE site 1412A Bkt Tadun | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 1X 18G 1.2M DP ANTENNA 1X 18G 0.6M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Swap | MW SWAP LINK 2476A-1412A WITH HUAWEI_18G_2+0_1.2M/0.6M_DP_112MHZ_128QAM_1352MBPS_XMC3E_SUB A & B_3.33KM IMPACTED: 3256A, 2673B, 2746C DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 1.2M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. CONFIGURE LINK 18G 2+0 112MHZ 128QAM 4. DISMANTLE EXISTING LINK | 1. INSTALL NEW RTN910 2. INSTALL NEW 18G 0.6M DP ANTENNA 3. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. CONFIGURE LINK 18G 2+0 112MHZ 128QAM 4. PATCH TO NEW CP PORT AND DO PORT LAG 5. DISMANTLE EXISTING LINK | XMC3E | MAC | 18G | 0.6 | 0.6 | GCI | SQ202504170453-GCI | GCI | SQ202503280384-GCI // SQ202503280397-GCI // SQ202504150088-GCI | 2025-05-15 | 2025-05-14 | Completed | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-05 | 2025-05-06 | 2025-05-05 | 2025-05-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-14 | 2025-05-15 | 2025-05-14 | 2025-05-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032081 |  | 2025-03-21 | 2025-03-22 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-25 | 2025-03-31 | 2025-03-25 | 2025-03-25 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-25 | 2025-03-31 | 2025-03-25 | 2025-04-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-27 | 2025-03-25 | 2025-03-31 | 2025-03-25 | 2025-04-12 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-25 | 2025-03-31 | 2025-03-25 | 2025-03-25 | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202506050696-GCI | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | CHEONG/SENG/WAH/7018000306
B01214_LOS | B061D_B01214OD_KM14FEDHWY | DU00005206086 | Central | Selangor | 3.072960 | 101.548820 | WK17 | APR 25 | WK17 | APR 25 | TI | Need spider skylift approval | ZTE | 00. Integrated/RFS Done | 21/4/2025 : NE installation complete, pending install FE due to need spider skylift 9/4/2025 : CELCOM AXIATA BERHAD - MINI STRUCTURE 20M LAND - NE site B01214 B061D_B01214OD_KM14FEDHWY, Digi OB - 3M Boom - RT - FE site 1376A KL North | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_B01214 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. FE_1367A 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Hi x2. | MW New Link / Reroute | Link reroute to new FE B01173 due to existing link LOS Block New link install 23G_2+0_112M. Site Impacted : B01214 NE_B01214 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Migrate traffic to new FE route and new link 23G_2+0_112M. 6.Decomm SM link ( BT3 SHLM - KM14 FED HWY )_CT10636 FE_B01173 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Enable GE port . ETH patching to existing SM link._(CT09869). 6.Create new In Band DCN. 6.Traffic migrate to new FE and new link 23G_2+)_112M. 7.Decomm SM link ( KM14 FED HWY - BT3 SHLM)_CT10636. | Link reroute to new FE B01173 due to existing link LOS Block New link install 23G_2+0_112M. Site Impacted : B01214 NE_B01214 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0.. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Migrate traffic to new FE route and new link 23G_2+0_112M. 6.Decomm SM link ( BT3 SHLM - KM14 FED HWY )_CT10636 | Link reroute to new FE B01173 due to existing link LOS Block New link install 23G_2+0_112M. Site Impacted : B01214 FE_B01173 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Enable GE port . ETH patching to existing SM link._(CT09869). 6.Create new In Band DCN. 6.Traffic migrate to new FE and new link 23G_2+)_112M. 7.Decomm SM link ( KM14 FED HWY - BT3 SHLM)_CT10636. | XMC_3E | MAC | 23G | 0.6 | 0.6 | Magicell | SQ202504170467-Magicell | Magicell | SQ202504260059-Magicell // SQ202504260060-Magicell | 2025-08-21 | 2025-08-20 | Completed | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-15 | 2025-08-16 | 2025-08-15 | 2025-08-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25040912 |  | 2025-04-10 | 2025-04-10 | Completed | 2025-04-09 | 2025-04-10 | 2025-04-09 | 2025-04-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-21 | 2026-04-16 | 2025-04-21 | 2025-05-05 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-04-21 | 2026-04-16 | 2025-04-21 | 2025-07-18 | MOHD//SAFRI BIN ARIF/7018000166 | Magicell TI | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-31 | 2025-04-21 | 2026-04-16 | 2025-04-21 | 2025-07-18 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-04-21 | 2026-04-16 | 2025-04-21 | 2025-04-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-06-26 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
7365B_HU | Richard Lind Tower SBC | DU00005206087 | Sabah | Sabah | 5.341290 | 118.482297 |  |  |  |  | RFS | TI DONE |  | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 23G_2+0_0.6/0.6_DP _SB A 2x 10G SFP | MW New Link / Reroute | BUILD NEW MW LINK 7365B-S00334 WITH 23G_2+0_0.3/0.3_DP SB A Carry traffic 7493B,7365B,7113K,7383K. Need 10G port at FE | BUILD NEW MW LINK 7365B-S00334 WITH 23G_2+0_0.3/0.3_DP SB A NE: 1. Install new RTN910A. 2. Install new XMC-3_SB A. 3. Install new antenna 23G_0.3m_DP. 4. Configure 23G_2+0_0.3m_EPLA. | BUILD NEW MW LINK 7365B-S00334 WITH 23G_2+0_0.3/0.3_DP SB A FE: 1. Install new RTN910A. 2. Install new XMC-3_SB A. 3. Install new antenna 23G_0.3m_DP. 4. Configure 23G_2+0_0.3m_EPLA. 5. Configure 10G port at rounter. | [5 empty] | NR services | SQ202504240795-NR Services | NR services | SQ202504260112-NR Services // SQ202504260119-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-04-21 | 2025-04-25 | 2025-04-23 | 2025-04-23 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-21 | 2025-04-28 | 2025-04-24 | 2025-04-24 | MUHD//KHAIRUL NIZAM/7023000104 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-25 | 2025-04-30 | 2025-04-25 | 2025-04-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250414BD |  | 2025-04-15 | 2025-04-21 | Completed | 2025-04-14 | 2025-04-15 | 2025-04-14 | 2025-04-21 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-22 | 2025-05-17 | 2025-04-22 | 2025-05-08 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-04-22 | 2025-05-17 | 2025-04-22 | 2025-05-08 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-05-20 | 2025-04-22 | 2025-05-17 | 2025-04-22 | 2025-05-20 | RALPH O'BRYAN HILARY7167000030 | 2026-01-07: 2025-04-22; 2026-01-07: 2025-05-17; 2026-01-07: 2025-04-22; 2026-01-14: 2025-04-24 |  |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
4084B_PL | Kg Tok Bedu | DU00005259253 | Northern | Penang | 5.501333 | 100.484694 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1xCat6 cable | BBU Patching | Patch 4084B BBU to existing xD HW MW 4084B(RTN03)-4273A(RTN11). Site Impacted : 4084B. *Do not touch traffics for 4441D & 4574C as these traffics still remain backhaul to xC PTN P00337* NE_4084B 1.Enable port 8-EM6-1 of RTN910A(RTN03). 2.Migrate traffic 4084B to existing xD HW MW 4084B(RTN03)-4273A(RTN11) in which BBU 4084B will patching to port 8-EM6-1 of RTN910A(RTN03). Configure it. FE_4273A 1.Ensure port 8-EM6-1 of RTN910A(RTN11) still in enable status and still have connectivity to IBeam port. 2.Migrate traffic 4084B from xC host(P00337) to xD host(4273A). | Patch 4084B BBU to existing xD HW MW 4084B(RTN03)-4273A(RTN11). Site Impacted : 4084B. *Do not touch traffics for 4441D & 4574C as these traffics still remain backhaul to xC PTN P00337* NE_4084B 1.Enable port 8-EM6-1 of RTN910A(RTN03). 2.Migrate traffic 4084B to existing xD HW MW 4084B(RTN03)-4273A(RTN11) in which BBU 4084B will patching to port 8-EM6-1 of RTN910A(RTN03). Configure it. | Patch 4084B BBU to existing xD HW MW 4084B(RTN03)-4273A(RTN11). Site Impacted : 4084B. *Do not touch traffics for 4441D & 4574C as these traffics still remain backhaul to xC PTN P00337* FE_4273A 1.Ensure port 8-EM6-1 of RTN910A(RTN11) still in enable status and still have connectivity to IBeam port. 2.Migrate traffic 4084B from xC host(P00337) to xD host(4273A). | [5 empty] | CCSMY | SQ202504210258-CCS | CCSMY | SQ202504210102-CCS // SQ202504260175-CCS | 2025-11-28 | 2025-11-27 | Completed | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-28 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | 2025-09-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2025-05-06 | 2025-05-06 | Completed | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-06 | NOR AMIRUL SYAFIQ BIN ROSE HAIZI6000015290 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-28 | 2025-03-31 | 2025-03-28 | 2025-05-06 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2025-03-28 | 2025-03-31 | 2025-03-28 | 2025-05-06 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-04-07 | 2025-03-28 | 2025-03-31 | 2025-03-28 | 2025-05-04 | Arif//Afif Bin Mohd Zabidi/7021000041 | 2026-01-07: 2025-03-28; 2026-01-07: 2025-03-31; 2026-01-07: 2025-03-28; 2026-01-14: 2025-04-18 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509250641-GCI | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | EZRIN TASNIM BIN ABDUL GANI6798000128
9185A_IPR_1 | Betong(SACOFA) | DU00005727362 | Sarawak | Sarawak | 1.412616 | 111.526991 | [6 empty] | ZTE | 00. Integrated/RFS Done | 31/7/2025 : Cutover done | TSS+TI | L1+ATP+PAC | 1xCAT6 CABLE (SUITABLE LENGTH) | BBU Patching | BBU PATCHING FROM NEC EQUIPMENT TO 9185A RTN01 (NEED TO UPGRADE TO 10G PORT FIRST 9185A_IPR) | BBU PATCHING FROM NEC EQUIPMENT TO 9185A RTN01 (NEED TO UPGRADE TO 10G PORT FIRST 9185A_IPR) | N/A | [5 empty] | Allstar | SQ202507250120-Allstar | Allstar | SQ202507190105-Allstar | 2025-12-26 | 2025-12-29 | Completed | 2025-07-23 | 2025-07-31 | 2025-08-14 | 2025-09-07 | STEWARD//ANAK KINO/6798000182 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-19 | 2025-12-25 | 2025-12-19 | 2025-12-22 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070358 |  | 2025-07-04 | 2025-07-09 | Completed | 2025-07-03 | 2025-07-04 | 2025-07-03 | 2025-07-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-14 | 2025-07-20 | 2025-11-29 | 2025-11-29 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-14 | 2025-07-20 | 2025-09-07 | 2025-09-07 | MICHEAL//BICKSON ANAK BANING/6798000201 | Allstar TI | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-31 | 2025-07-14 | 2025-07-20 | 2025-12-17 | 2025-12-17 | MICHEAL//BICKSON ANAK BANING/6798000201 | 2026-01-07: 2025-07-14; 2026-01-07: 2025-07-20; 2026-01-07: 2025-12-02; 2026-01-14: 2025-12-02 |  |  | 2025-08-26 | 2025-08-31 | 2025-08-26 | 2025-08-26 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202507080541-GCI | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
4206K_HU | TMNLEMBAHPERMAI | DU00005727363 | Northern | Kedah | 5.713011 | 100.522004 | [7 empty] | 00. Integrated/RFS Done | 25/06 CO Done | AA | PAC | NA | MW Remote Upgrade | Remote Software Upgrade to 18G_1+0_112M Site Impacted : 4206K NE_4206K 1.Config to 512QAM with 112M. FE_4627A. 1.Config to 512QAM with 112M. | Remote Software Upgrade to 18G_1+0_112M Site Impacted : 4206K NE_4206K 1.Config to 512QAM with 112M. | Remote Software Upgrade to 18G_1+0_112M Site Impacted : 4206K FE_4627A. 1.Config to 512QAM with 112M. | XMC_3E | MAC | 18G | 0.6 | 0.6 | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 | [17 empty] | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202507080524-GCI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | CHEONG/SENG/WAH/7018000306
B02503_HU_1 | B064H_B02503OD_KUIS | DU00005727364 | Central | Selangor | 2.890869 | 101.783750 | [7 empty] | 00. Site Out/Drop |  | NA | NA |  | MW Hardware Upgrade | [8 empty] | Magicell | No PR required-Work done at B02503_HU | Magicell | No PR required-Work done at B02503_HU |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  |  | 2025-06-25 | 2025-06-25 | Completed | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | NUR FATIHAH BINTI AYOB7018000236 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-25 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 |  | 2025-06-25 | 2025-06-25 | 2025-06-25 |  | NUR FATIHAH BINTI AYOB7018000236 | [7 empty] | 2025-06-26 | 2025-06-23 | 2026-06-17 | 2025-06-16 | 2025-07-15 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2026-01-07: 2025-06-23; 2026-01-07: 2026-06-17; 2026-01-07: 2025-06-16; 2026-01-14: 2025-06-30 | [7 empty] | GTSB | SQ202507080560-GTSB
7975A_HU | Seaventures Mabul | DU00005727365 | Sabah | Sabah | 4.253611 | 118.633238 | [9 empty] | TSS+AA+TI+Dismantle |  | 2x IDU RTN910A 2X 2.4m_DP_MAC Antenna (7G) 1x ODU 7G XMC-3 SB_J Hi 1x ODU 7G XMC-3 SB_J Lo 1x ODU 7G XMC-3 SB_L Hi 1x ODU 7G XMC-3 SB_L Lo | MW Swap | Install new mw link 7975A-7626B with Huawei 7G_2+0_28mhz_512QAM_424Mbps_2.4/2.4m_DP_MAC_XMC-3 sb J&L_21.6km. This link will be swap with existing 13G_1+1 Config EPLA new link Impact site: 7975A Decom existing link HW 13G_1+1 | NE: 1. Install new RTN910A 2. Install new 7G 2.4m DP Antenna 3. Install new 7G XMC-3 sb J&L 4. Configure link 7G 2+0_28MHZ_512QAM with EPLA 5. Dismantle existing link HW 13G_1+1 | FE: 1. Install new RTN910A 2. Install new 7G 2.4m DP Antenna 3. Install new 7G XMC-3 sb J&L 4. Configure link 7G 2+0_28MHZ_512QAM with EPLA 5. Dismantle existing link HW 13G_1+1 | XMC-3 | MAC | 7G | 2.4m | 2.4m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202507080638-GTSB | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AB.RAHMAN//BIN MAT NOOH/6237001519
C00007_AD | C046C_C00007OD_BKTCINCIN | DU00006705322 | Central | Pahang | 3.434419 | 101.784243 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
C00538_AD | C046C_C00538OD_KM4GENTING | DU00006705323 | Central | Pahang | 3.410200 | 101.783700 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
2833A_AD_1 | FirstWorld Hotel Indoor | DU00006705324 | Central | Pahang | 3.425396 | 101.794359 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
C00007_AD_1 | C046C_C00007OD_BKTCINCIN | DU00006705325 | Central | Pahang | 3.434419 | 101.784243 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
1016A_AD | GentingRia Aprtment | DU00006705326 | Central | Pahang | 3.419951 | 101.790568 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
C00011_AD | C046C_C00011OD_RESORTHOTELSL | DU00006705327 | Central | Selangor | 3.422128 | 101.793042 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
C00014_AD | C046C_C00014IB_GENTINGSTAFF3 | DU00006705328 | Central | Pahang | 3.425800 | 101.793600 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
2684A20_AD | pBTSKg Matupang | DU00006705329 | Sabah | Sabah | 5.793952 | 116.818765 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | Perform MW IDU patching FE_S00567/7435B New CAT6 cable x1. | MW IDU Patching | ****IMPORTANT NOTE: 1. PLEASE PERFORM DU AS PER SEQUENCES BELOW. 1ST DU 2684A20_AD. 2ND DU S00567_AD. **** Perform MW IDU Patching in between HW IDU and CTS LL. Site Impacted: 2684A20. FE_7128P/S00567/7435B 1.Disable port 8-EM6-1 of existing RTN910AF(RTN02, NEID 16-27131) and port 8-EM6-2 of existing RTN910AF(NEID 88-12567). 2.Disconnect/remove existing cascading between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 16-27131) and port 8-EM6-2 of existing RTN910AF(NEID 88-12567). 3.Disconnect existing CTS LL(7435B-LL-7000A) from existing BBU(if still connected to BBU). 4.Perform patching in between existing CTS LL(7435B-LL-7000A) and port 8-EM6-1 of existing RTN910AF(RTN02, NEID 16-27131). Enable and configure it. 5.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 6.Migrate traffic 2684A20 into existing port at IBeam(CP 7000A) as per traffic 7435B use port at IBeam before. |  | ****IMPORTANT NOTE: 1. PLEASE PERFORM DU AS PER SEQUENCES BELOW. 1ST DU 2684A20_AD. 2ND DU S00567_AD. **** Perform MW IDU Patching in between HW IDU and CTS LL. Site Impacted: 2684A20. FE_7128P/S00567/7435B 1.Disable port 8-EM6-1 of existing RTN910AF(RTN02, NEID 16-27131) and port 8-EM6-2 of existing RTN910AF(NEID 88-12567). 2.Disconnect/remove existing cascading between port 8-EM6-1 of existing RTN910AF(RTN02, NEID 16-27131) and port 8-EM6-2 of existing RTN910AF(NEID 88-12567). 3.Disconnect existing CTS LL(7435B-LL-7000A) from existing BBU(if still connected to BBU). 4.Perform patching in between existing CTS LL(7435B-LL-7000A) and port 8-EM6-1 of existing RTN910AF(RTN02, NEID 16-27131). Enable and configure it. 5.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 6.Migrate traffic 2684A20 into existing port at IBeam(CP 7000A) as per traffic 7435B use port at IBeam before. | [5 empty] | NR services | SQ202604100662-NR Services | NR services | SQ202604100658-NR Services |  |  | Ongoing | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040208 |  | 2026-04-03 | 2026-04-09 | Completed | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-07 | 2026-05-07 | 2026-04-07 | 2026-04-09 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-04-07 | 2026-05-07 | 2026-04-07 | 2026-04-20 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-13 | 2026-04-07 | 2026-05-07 | 2026-04-07 | 2026-04-20 | LEONARD//EDUAN/6000038538 | 2026-01-07: 2026-04-07; 2026-01-07: 2026-05-07; 2026-01-07: 2026-04-07; 2026-01-14: 2026-04-08 | [7 empty] | GTSB | SQ202604030182-GTSB
1771B_AD | GohtongJaya | DU00006705330 | Central | Selangor | 3.400320 | 101.767320 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
2833A_AD | FirstWorld Hotel Indoor | DU00006705331 | Central | Pahang | 3.425396 | 101.794359 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
B01690_AD | B065B_B01690OD_T3_KGHULUTAMU | DU00006705332 | Central | Selangor | 3.463920 | 101.694720 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
C00540_AD | B065B_C00540OD_KM2GENTING | DU00006705333 | Central | Selangor | 3.415997 | 101.784531 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
C00020_AD | C046C_C00020IB_HIGHLANDHOTEL | DU00006705334 | Central | Pahang | 3.424100 | 101.793800 | [21 empty] | MTK |  | MTK |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604030172-GTSB
S00567_AD | S104A_S00567OD_CB_KGSAGINDAIBARU | DU00006705335 | Sabah | Sabah | 5.847055 | 116.815754 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | Perform BBU patching NE_7128P/S00567 New CAT6 cable x1. | BBU Patching | ****IMPORTANT NOTE: 1. PLEASE PERFORM DU AS PER SEQUENCES BELOW. 1ST DU 2684A20_AD. 2ND DU S00567_AD. **** Perform BBU Patching in between HW IDU and RAN BBU. Later, may decom existing HW MW Link 7128P/S00567(NEID 88-12567)-7119R/S00383(NEID 88-22567), 15G_2+0_28MHZ_1024QAM_EPLA. Site Impacted: 7128P/S00567. NE_7128P/S00567/7435B 1.Disable port 8-EM6-1 and 8-EM6-2 of existing RTN910AF(NEID 88-12567). 2.Disconnect existing BBU(7128P/S00567) from port 8-EM6-1 of existing RTN910AF(NEID 88-12567). 3.Perform patching in between existing BBU(7128P/S00567) and port 8-EM6-2 of existing RTN910AF(RTN02, NEID 16-27131). Configure it. 4.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffic 7128P/S00567 into port at IBeam(CP 7000A) similar to traffic 2684A20. 6.Later, may decom existing HW MW Link 7128P/S00567(NEID 88-12567)-7119R/S00383(NEID 88-22567), 15G_2+0_28MHZ_1024QAM_EPLA. | ****IMPORTANT NOTE: 1. PLEASE PERFORM DU AS PER SEQUENCES BELOW. 1ST DU 2684A20_AD. 2ND DU S00567_AD. **** Perform BBU Patching in between HW IDU and RAN BBU. Later, may decom existing HW MW Link 7128P/S00567(NEID 88-12567)-7119R/S00383(NEID 88-22567), 15G_2+0_28MHZ_1024QAM_EPLA. Site Impacted: 7128P/S00567. NE_7128P/S00567/7435B 1.Disable port 8-EM6-1 and 8-EM6-2 of existing RTN910AF(NEID 88-12567). 2.Disconnect existing BBU(7128P/S00567) from port 8-EM6-1 of existing RTN910AF(NEID 88-12567). 3.Perform patching in between existing BBU(7128P/S00567) and port 8-EM6-2 of existing RTN910AF(RTN02, NEID 16-27131). Configure it. 4.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 5.Migrate traffic 7128P/S00567 into port at IBeam(CP 7000A) similar to traffic 2684A20. 6.Later, may decom existing HW MW Link 7128P/S00567(NEID 88-12567)-7119R/S00383(NEID 88-22567), 15G_2+0_28MHZ_1024QAM_EPLA. | [6 empty] | NR services | SQ202604100662-NR Services | NR services | SQ202604100658-NR Services |  |  | Ongoing | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26040209 |  | 2026-04-03 | 2026-04-09 | Completed | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-09 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-07 | 2026-05-08 | 2026-04-07 | 2026-04-09 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-04-07 | 2026-05-08 | 2026-04-07 | 2026-04-20 | LEONARD//EDUAN/6000038538 | NR Service TI | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-13 | 2026-04-07 | 2026-05-08 | 2026-04-07 | 2026-04-20 | LEONARD//EDUAN/6000038538 | 2026-01-07: 2026-04-07; 2026-01-07: 2026-05-08; 2026-01-07: 2026-04-07; 2026-01-14: 2026-04-08 | [7 empty] | GTSB | SQ202604030182-GTSB
9388B | Rh Semop | DU00004460603 | Sarawak | Sarawak | 2.418034 | 111.396973 | [6 empty] | ZTE | 00. Site Out/Drop | 10/9/2025 : TSSR at NIC TX, In plan |  |  | 13G_4+0_28M_CA. NE_9388B 13G_DP_1.2m(MDD) x1. XMC_5D ,Sub_B_Hi x1. ISM8 x2. FE_9366A. 13G_DP_1.2m(MDD) x1. XMC_5D, Sub_B_Lo x1. ISM8 x2. | Cancel / Drop | 31 Oct 2025: To proceed MW Swap under NIC Existing link 13G_2+0_28M Swap existing link to 13G_4+0_28M_CA Priority to establish new parallel link (9388B-9366A_1) before swap existing link to 13G_4+0_28M_CA. Site Impacted:9388B,9032R,9028R. NE_9388B 1.Install 13G_DP_1.2m(MDD). 2.Install new XMC_5D-4+0 with CA config, Sub_B_Hi. 3.Reuse existing 9388B_RTN05. 4.Install 3_ISM8-2+0 and 4_ISM8-2+0 into existing 9388B_RTN05 with CA config. 5.Enable EPLA , service cross connect and CA. 6.Remove interconnect ETH cable between RTN03 to RTN05.Traffic 9032R & 9028R migrate to new parallel link(9388B-9366A_1). 7.For traffic 9388B migrate to new link 13G_4+0_28M_CA. 8.Decom existing ODU and Ant. FE_9366A. 1.Install 13G_DP_1.2m(MDD). 2.Install new XMC_5D-4+0 with CA config, Sub_B_Lo. 3.Reuse existing 9366A_RTN02. 4.Install 3_ISM8-2+0 and 4_ISM8-2+0 into existing 9366A_RTN02 with CA config. 5.Enbale EPLA , service cross connect and CA. 6.Traffic 9388B migrate to new link 13G_4+0_28M_CA. 7.Decom existing ODU and Ant. | [7 empty] | Allstar | No PR required-Site drop/cancel | Iezzpro | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI_AA | SQ202510300174-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
3163B-4669A | pBTS Pekan Kecil Kuala Sungai | DU00004460604 | Northern | Perlis | 6.151700 | 100.321040 |  |  |  |  | Integrated/RFS Done |  |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_3163B. 23G_DP_0.6m(MAC)+OMT x1. RTN910A x1. XMC_3E-2+0,Sub A & B_Hi x2. FE_4669A 23G_DP_0.6(MAC)+OMT x1. XMC_3E-2+0, Sub A & B_Lo x2. RTN910A x1. | MW Swap | Existing link RTN910 info insufficient due to both end Loss Comm (Suspect Power Issue). Swap existing link to 23G_2+0_112M. Site impacted: 3163B. NE_3163B. 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new RTN910A,7_ISM8-2+0. 3.Install new XMC_3E-2+0,Sub A & B_Hi. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new link. 6.Decom existing link. FE_4669A 1.Install 23G_DP_0.6(MAC)+OMT. 2.Install new XMC_3E-2+0, Sub A & B_Lo. 3.Install new RTN910A,7_ISM8-2+0 4.Enable EPLA and service cross connect. 5.Create In-band DCN. 6.Migrate service to new link. 7.Decom existing MW link. | [7 empty] | GTSB | SQ202504210272-GTSB | GTSB | SQ202503280487-GTSB // SQ202503280493-GTSB // SQ202504260178-GTSB | 2025-11-28 | 2025-11-28 | Completed | 2025-06-19 | 2025-07-03 | 2025-06-19 | 2025-06-19 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-06-07 | 2025-05-28 | 2025-05-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-27 | 2025-11-28 | 2025-11-27 | 2025-11-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022164 |  | 2025-02-22 | 2025-03-26 | Completed | 2025-02-21 | 2025-02-22 | 2025-02-21 | 2025-03-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-10-13 | FAZAL ABBAS6799000222 | GTSB TI | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-05-08 | FAZAL ABBAS6799000222 | GTSB TI | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2026-03-31 | FAZAL ABBAS6799000222 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-27 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | CHEONG/SENG/WAH/7018000306
1400A-1196A | Men Mutiara PJ | DU00004460605 | Central | Selangor | 3.086985 | 101.649139 | WK10 | MAR 25 | WK10 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 4/3/2025 : Cutover done 28/2/2025 : Cutover WIP 27/2/2025 : Plan continue install NE site and cutover - CRQ approved, cancel proceed due to team have have training 26/2/2025 : FE installation complete, pending install NE site 21/1/2025 : Digi OB - 3M Boom - RT - NE site 1400A Men Mutiara PJ, Digi OB - Tower - FE site 1196A JBA Puchong | TSS+AA+TI | L1+ATP+PAC | 18G_1+0_112M XPIC NE_1400A 18G_DP_0.6m(DP) x1. XMC_3E-2+0 , Sub_B_Hi x2. FE_1196A 18G_DP_1.2m(DP) x1. XMC_3E-2+0,Sub_B_Lo x2. RTN910A x1. | MW Parallel Link | Existing link 18G_2+0_112M Establish new parallel link for 18G_2+0_112M for load balancing. Site Impacted:1181A,1956A, NE_1400A 1.Install a new 18G_DP_0.6m(MDD). 2.Install XMC_5D-2+0 , Sub_A_Hi. 3.Reuse existing 1400A_RTN02. 4.Install 3_ISM8-2+0 into existing 1400A_RTN02. 5.Enable EPLA and Service cross connect. 6.Traffic 1181A & 1956A migrate to new parallel link 18G_2+0_112M. 7.Remove interconnect ETH cable between RTN02 to RTN03. FE_1196A 1.Install a new 18G_DP_1.2m(MDD). 2.Install XMC_5D-2+0,Sub_A_Lo. 3.Install new RTN910A,7_ISM8-2+0. 4.Enable EPLA and service cross connect. 5.Create new In-Band DCN. 6.Create Physical LAG to Ibeam Port. 7.No decom due to establish new parallel link for 1181A & 1956A. | [7 empty] | GTSB | SQ202502260373-GTSB | GTSB | SQ202503050457-GTSB // SQ202504260131-GTSB | 2025-04-07 | 2025-04-07 | Completed | 2025-02-25 | 2025-03-31 | 2025-02-25 | 2025-03-28 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Completed |  | 2025-03-07 | 2025-04-04 | 2025-03-07 | 2025-03-07 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-07 | 2025-04-07 | 2025-04-07 | 2025-04-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25021926 |  | 2025-02-20 | 2025-02-25 | Completed | 2025-02-19 | 2025-02-20 | 2025-02-19 | 2025-02-25 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2025-03-31 | 2025-02-25 | 2025-03-13 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-02-25 | 2025-03-31 | 2025-02-25 | 2025-05-30 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-04 | 2025-02-25 | 2025-03-31 | 2025-02-25 | 2025-06-10 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-03-21: 2025-02-25; 2025-03-21: 2025-03-31; 2025-03-21: 2025-02-25; 2025-03-27: 2025-02-28 |  |  | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358
1793A_LOS | Sek 17 Shah Alam | DU00004460671 | Central | Selangor | 3.046770 | 101.505610 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 27/11: D2: Continue TI 26/11: D1: MOS & TI WIP | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_1793A 23G_SP_0.6m(MAC) x1. RTN910A x1. XMC_3E-1+0 , Sub A _Hi x1. FE_2640A 23G_SP_0.6m(MAC) x1. RTN910A x1. XMC_3E-1+0 , Sub A_Lo x1. | MW New Link / Reroute | Link reroute to new FE 2640A with 23G_1+0_112M due to LOS Block. NE_1793A 1.Install new 23G_SP_0.6m(MAC). 2.Install new RTN910A, 7_ISM8-1+0 (RTN no provide by MSP team). 3.Install new XMC_3E-1+0 , Sub A _Hi. 4.Create EPLA and service cross connect. 5.Traffic migarte to new route FE site. 6.DEcom existing MW link. FE_2640A 1.Install new 23G_SP_0.6m(MAC). 2.Install new RTN910A,7_ISM8-1+0 (RTN no provide by MSP team). 3.Install new XMC_3E-1+0 , Sub A_Lo. 4.Enable GE1 , ETH cable patching to existing 2640A_RTN01 (GE2). 5.Create EPLA and service cross connect. 6.Traffic migrate to new link. | [7 empty] | YPTT | SQ202411190745-YPTT | YPTT | SQ202411250784-YPTT // SQ202504260171-YPTT |  |  | Ongoing | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MD//ERWAN BIN ROHMAN/6794000008 |  | YONGPENG TELECOM TECHNOLOGY (M) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24112533 |  | 2024-11-26 | 2024-12-30 | Completed | 2024-11-25 | 2024-11-26 | 2024-11-25 | 2024-12-30 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-26 | 2025-11-30 | 2024-11-26 | 2024-12-30 | AKMAL//BIN RAZALI/6794000078 | YPTT TI | 2024-11-26 | 2025-11-30 | 2024-11-26 | 2026-01-13 | AKMAL//BIN RAZALI/6794000078 | YPTT TI | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-11-26 | 2025-11-30 | 2024-11-26 | 2024-11-29 | AKMAL//BIN RAZALI/6794000078 | 2024-11-26 | 2025-11-30 | 2024-11-26 | 2024-11-27 | 2025-01-10 | 2025-01-10 | 2025-01-10 | 2025-01-10 | NG HONG JIE7018000036 | Logistic Team | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358
3888A_1 | Jalan Conlay | DU00004502324 | Central | Kuala Lumpur | 3.150191 | 101.717029 |  |  | W49-52 | DEC 24 | Cancel / Drop | SOW change Drop | ZTE | 00. Site Out/Drop |  |  |  | NA | Cancel / Drop | The 3888A_1 is the FE site plan to support for W01461_LOS. Now W01461 site to decom. Therefore , the direct patching from IDU to IPRAN (IDU-IPRAN) is not required and TX SOW will be changed from IDU_IPRAN to Cancel / Drop. | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
Q01596_EB | QS50225_4_1-KGSRIARJUNA | DU00004502338 | Sarawak | Sarawak | 1.405430 | 110.323220 | [7 empty] | 00. Integrated/RFS Done | 24/9/2025 : Cutover done 23/9/2025 : Plan to do MW IDU Relocation - Re-plan due to shortage material 22/9/2025 : Plan to do MW IDU Relocation - Re-plan due to shortage material | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC HW_RTN910A 2+0 MW link Q01596-Q00132 to xD Cabinet. | [7 empty] | MTK | SQ202412180531-MTK | Trintel | SQ202509090366-Trintel // SQ202509090378-Trintel | 2025-01-10 | 2025-01-06 | Completed | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-12-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-06 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090873 |  | 2025-09-09 | 2025-09-22 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-22 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-22 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-30 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-09-24 | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-30 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | 2025-03-21: 2025-09-22; 2025-03-21: 2025-09-30; 2025-03-21: 2025-09-22; 2025-03-27: 2025-09-22 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019
Q01380_EB | Q124E_Q01380OD_KGPAYAMEBI | DU00004502339 | Sarawak | Sarawak | 1.407980 | 110.280120 | [6 empty] | ZTE | 00. Integrated/RFS Done | 23/9/2025 : Cutover done, pending declare due to NE losscom and not yet patching - BBU not ZTE 22/9/2025 : Plan to do MW IDU Relocation - Re-plan due to shortage material | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | At FE: - Relocate xC SM_ALC+2E 1+0 MW link SW03011to xD Cabinet. | [7 empty] | MTK | SQ202412230346-MTK | Trintel | SQ202509090366-Trintel // SQ202509090378-Trintel | 2025-10-31 | 2025-10-28 | Completed | 2024-12-18 | 2024-12-26 | 2024-12-18 | 2024-12-23 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090874 |  | 2025-09-09 | 2025-09-22 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-22 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-22 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-30 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | Trintel TI | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | MOHD//AMIR BIN SAMSI/6799000184 |  |  | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-30 | MUHAMAD//NASRULLAH BIN JALAIMAN/7667000080 | 2025-03-21: 2025-09-22; 2025-03-21: 2025-09-30; 2025-03-21: 2025-09-22; 2025-03-27: 2025-09-22 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019
Q01902_EB | Q140A_Q01902OD_ULUSGMERAH3 | DU00004502340 | Sarawak | Sarawak | 2.332761 | 111.843399 | [7 empty] | 00. Integrated/RFS Done | 06/10/2025 :SM AlcPlus2e Q01902-Q00668 IDU Done relocate, Pending Patching due need plan to swap to RTN IDU(Huawei) as existing BBU already 10G direct patching to Tejas Sacofa | TSS+TI | L1+ATP+PAC |  | MW IDU Relocation | Update 07 Oct 2025: 1) To complete until relocation SOW only. BBU xD at FE already using 10G patch direct to SACOFA LL. Unable to patch to relocated SM IDU 2) Patching work to be done under DU Q01902_HU (Tx Mini Project) At FE: - Relocate xC SM_ALC+2E 1+0 MW link SW03052 to xD Cabinet. - Patching xD LL and BBU to newly Relocate xC SM_ALC+2E POI Needed : No | [7 empty] | MTK | SQ202412180531-MTK | Trintel | SQ202509090366-Trintel // SQ202509090378-Trintel | 2024-12-20 | 2024-12-18 | Completed | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-12-16 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090875 |  | 2025-09-09 | 2025-10-08 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-10-08 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-10 | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | Trintel TI | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-10 | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | Trintel TI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-07 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-11 | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | 2025-03-21: 2025-10-01; 2025-03-21: 2025-10-01; 2025-03-21: 2025-10-01; 2025-03-27: 2025-10-06 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019
7514B-7124A | IJM BATU5 | DU00004525449 | Sabah | Sabah | 5.866052 | 118.054060 |  |  |  |  | RFS | DONE | ZTE | 00. Integrated/RFS Done | DO ready | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_112M. NE_7514B 18G_DP_1.2m(MAC)+OMT x1. XMC_3E-2+0,Sub_A_Lo x1. ISM8 x1. FE_7124A. 18G_DP_1.2m(MAC)+OMT x1. XMC_3E-2+0,Sub_A_Hi x1. ISM8 x1. | MW Parallel Link | Existing link 18G_1+0_112M Establish new parallel link 18G_2+0_112M. Site Impacted: 7836A,7557A. NE_7514B 1.Install 18G_DP_1.2m(MAC)+OMT. 2.Install new XMC_3E-2+0,Sub_A_Lo. 3.Reuse existing 7514B_RTN02. 4.Install 4_ISM8-2+0. 5.Create EPLA with existing 1+0 link and service cross connect. 6.Traffci migrate to new parallel link with EPLA existing 1+0 link. (7836A & 7557A). 7.No decom due to install new parallel link. FE_7124A. 1.Install 18G_DP_1.2m(MAC)+OMT. 2.Install new XMC_3E-2+0,Sub_A_Hi. 3.Reuse existing 7124A_RTN14. 4.Install 3_ISM8-2+0. 5.Create EPLA with existing 1+0 link and service cross connect. 6.Traffic migrate to new parallel link with EPLA existing 1+0 link.(7836A & 7557A). 7.No decom due to install new parallel link. | Existing link 18G_1+0_112M Establish new parallel link 18G_2+0_112M. Site Impacted: 7836A,7557A. NE_7514B 1.Install 18G_DP_1.2m(MAC)+OMT. 2.Install new XMC_3E-2+0,Sub_A_Lo. 3.Reuse existing 7514B_RTN02. 4.Install 4_ISM8-2+0. 5.Create EPLA with existing 1+0 link and service cross connect. 6.Traffci migrate to new parallel link with EPLA existing 1+0 link. (7836A & 7557A). 7.No decom due to install new parallel link. | Existing link 18G_1+0_112M Establish new parallel link 18G_2+0_112M. Site Impacted: 7836A,7557A. FE_7124A. 1.Install 18G_DP_1.2m(MAC)+OMT. 2.Install new XMC_3E-2+0,Sub_A_Hi. 3.Reuse existing 7124A_RTN14. 4.Install 3_ISM8-2+0. 5.Create EPLA with existing 1+0 link and service cross connect. 6.Traffic migrate to new parallel link with EPLA existing 1+0 link.(7836A & 7557A). 7.No decom due to install new parallel link. | XMC_3E | MAC | 18G | 1.2 | 1.2 | NR services | SQ202502060432-NR Services | NR services | SQ202504080137-NR Services // SQ202504080147-NR Services // SQ202504260199-NR Services | 2025-02-07 | 2025-02-05 | Completed | 2025-02-05 | 2025-02-05 | 2025-02-05 | 2025-02-05 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-28 | 2025-01-31 | 2025-01-28 | 2025-01-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-01-28 | 2025-01-31 | 2025-01-28 | 2025-01-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-04 | 2025-02-07 | 2025-02-04 | 2025-02-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022859 |  | 2025-03-01 | 2025-03-03 | Completed | 2025-02-28 | 2025-03-01 | 2025-02-28 | 2025-03-03 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-15 | 2025-03-27 | 2025-03-27 | 2025-03-27 | WILFRED BALANG7167000026 |  | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-04-19 | WILFRED BALANG7167000026 | NR Service TI | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-27 | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-04-29 | WILFRED BALANG7167000026 | 2025-03-21: 2025-03-15; 2025-03-21: 2025-03-15; 2025-03-21: 2025-03-15; 2025-03-27: 2025-03-18 |  |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
7435A-7343A | Kg Timbou Tambunan | DU00004073909 | Sabah | Sabah | 5.695550 | 116.377490 |  |  |  | JUN 25 | Material collection | Material collection | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G 1+0 112MHz 1.2m/1.2m SP NE: 1) 1xISM8 2) 1x18GHz XMC3E Sub A Lo 3) 1x18GHz 1.2m SP FE: 1) 1xRTN910A 2) 1x18GHz XMC3E Sub A Hi 3) 1x18GHz 1.2m SP 4) 1pair SFP10G 1km and patch cord | MW Parallel Link | Existing link 7435A-7343A (7435A RTN01-7343A RTN01) Parallel link 18GHz 112MHz Impact sites: 7329C NE (7435A RTN02) 1. Install new ISM8 card at RTN02 slot 3 2. Install new link at existing new RTN02 3-ISM8-1 3. Remove RTN01-RTN02 cascade 4, Migrate 7329C to new link FE (7343A) 1. Install new RTN910A. Ops to assign RTN number 2. Install new link at new RTN 7-ISM8-1 3. Cascade new RTN to RTN01 GE3 (use 10G port due to no 1G port available) 4. Migrate 7329C to new link | NE (7435A RTN02) 1. Install new ISM8 card at RTN02 slot 3 2. Install new link at existing new RTN02 3-ISM8-1 3. Remove RTN01-RTN02 cascade 4, Migrate 7329C to new link | FE (7343A) 1. Install new RTN910A. Ops to assign RTN number 2. Install new link at new RTN 7-ISM8-1 3. Cascade new RTN to RTN01 GE3 (use 10G port due to no 1G port available) 4. Migrate 7329C to new link | [5 empty] | MTK | SQ202502180263-MTK | NR services | SQ202506300601-NR Services // SQ202506300608-NR Services | 2025-07-11 | 2025-07-07 | Completed | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-13 | AHMAD//SHAFIQ BIN ASPAR/6801000041 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-20 | 2025-02-21 | 2025-02-20 | 2025-02-20 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-07 | 2025-07-11 | 2025-07-07 | 2025-07-07 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25060715 |  | 2025-06-08 | 2025-06-10 | Completed | 2025-06-07 | 2025-06-08 | 2025-06-07 | 2025-06-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-28 | 2025-08-28 | 2025-06-28 | 2025-07-03 | WILFRED BALANG7167000026 | NR Service TI | 2025-06-28 | 2025-08-28 | 2025-06-28 | 2025-07-03 | WILFRED BALANG7167000026 | NR Service TI | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-01 | 2025-06-28 | 2025-08-28 | 2025-06-28 | 2025-07-07 | WILFRED BALANG7167000026 | 2025-03-21: 2025-06-28; 2025-03-21: 2025-08-28; 2025-03-21: 2025-06-28; 2025-03-27: 2025-07-01 |  |  | 2025-07-24 | 2025-08-24 | 2025-07-24 | 2025-07-24 | MASDIANA//BINTI BEDIN/6801000016 | GTSB_AA | SQ202510300153-GTSB
4905B-4904B | Spg Pulai KM34 | DU00004124650 | Northern | Perak | 4.557510 | 101.314110 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 12/9: CRQ approved. Cutover done 4/9: Solution released, proceed with CR application | AA | PAC |  | MW Remote Upgrade | Current solution for HU will be proceed with remote software upgrade. However BBU patching need to proceed under NIC TX Rollout solution. | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2024-11-16 | 2024-12-16 | 2024-11-16 | 2024-11-16 | ASTI//GANIS PUTRIANI/6237001358
3185A-1350A | Persiaran Aman | DU00004124651 | Central | Selangor | 3.032590 | 101.547610 |  |  | WK49-52 | DEC 24 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 19/12: Solution released, plan execution by Tx Ops | AA | PAC | NA | MW Remote Upgrade | Existing link 18G_2+0_56M Remote Software Upgrade to 18G_2+0_112M. | [7 empty] | N/A | No PR required-Remote Upgrade | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-21 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 | [17 empty] | 2025-02-14 | 2025-03-14 | 2025-02-14 | 2025-02-14 | ASTI//GANIS PUTRIANI/6237001358
4907B-4566A | Kg Palas | DU00004124652 | Northern | Perak | 4.589250 | 101.313910 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Site Out/Drop | 23/9: Modify DU 4907B-4566A to 4907B-4540B 22/9: To proceed with LOS Survey first to confirm LOS due link distance 16.8km 23/07: Pending Material Antenna | TSS |  | 4907B 1. New antenna 13G_1.8m x1 2. ODU_XMC5D ,Sub A_Hi x 2. 3. ISM8 x 1 4540B 1. New antenna 13G_1.8M x 1. 2. ODU_XMC5D , Sub A_Lo x 2. 3. New RTN910AF x 1. | MW New Link / Reroute | Rerouting 4907B-4566A to 4540B new FE site. Existing link 4907B-4566A , 13G_1+0_28M. New link 4907B-4540B , 13G_2+0_28M. LOS Survey for 4907B to 4540B is required. Swap existing 13G_28M_1+0 to 13G_28M_2+0. Site Impacted: 4542B,4905B,4904B,4907B,4906B. For 4907B , prioritize reroute the northbound link (4907B-4566A) before making intermediate link connection. NE_4907B 1.Install a new antenna 13G_1.8m + 1xODU_XMC5D ,Sub A_Hi. 2.Install a new 3_ISM8-1&2 on existing RTN910AF and configure 2+0_28Mh,link towards new FE 4540B (Rerouting 4566A to 4540B). 3.Apply EPLA & service cross connect for Slot_7 & Slot_3 on RTN910AF. FE_4540B 1.New link establish from 4540B to 4907B , 13G_28M_2+0. 2.Install new antenna 13G_1.8M + 1xODU_XMC5D , Sub A_Lo. 3.Install new RTN910AF,7_ISM8-1&2 configure as 2+0_56Mhz direct towards 4907B. 4540B-4535B created new DU link ID 4540B-4535B. Install new link 18G_112M_2+0. TSS survey is required. Site Impacted: 4542B,4905B,4904B,4907B. 4540B 1.Install new antenna 18G_1.2m + 2xODU_XMC_3E. 2.Install 3_ISM8-1&2 into existing RTN910AF and configure 2+0_112Mhz(EPLA)link towards 4535B. 3.Perfrom service cross connect and apply EPLA for slot_7 & Slot_3 on RTN910AF. 4535B_CP Site 1.Install new antenna 18G_1.2m + 2xODU_XMC_3E. 4.Install new RTN910AF , 7_ISM8-1&2 configure 2+0_112Mhz(EPLA)link towards 4540B. 5.Enable 10G_GE3 Optical port connect to IBeam / PFS or LAG 2 GE port 1 & 2. 6.Create/configure as new Inband GNE for RTN910AF(RTN convention name provide by integration team). | [7 empty] | NWAVE | SQ202508290701-N-Wave // SQ202510310495-N-Wave | NWAVE | No PR required-Work at TSS only | 2025-11-14 | 2025-11-07 | Completed | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-15 | 2025-07-15 | 2025-09-03 | 2025-09-03 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-02 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-14 | 2025-11-07 | 2025-11-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071152 |  | 2025-07-12 | 2025-07-14 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Khairul Azman Bin Din7160000001 |  | 2025-09-29 | 2025-10-29 | 2025-09-29 |  | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | [7 empty] | 2025-09-29 | 2025-10-29 | 2025-09-29 |  | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2025-03-21: 2025-09-29; 2025-03-21: 2025-10-29; 2025-03-21: 2025-09-29 | [7 empty] | GTSB_AA | SQ202510300144-GTSB
7145K-7289A | S101A_S01647OD_KGKITANGANSUGUD | DU00004124653 | Sabah | Sabah | 5.856406 | 116.101110 |  |  |  | FEB 25 | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | TI WIP | TSS+AA+TI+Dismantle | L1+ATP+PAC | Swap existing link to 23G_2+0_112M. NE_7145K 1.Install 23G_DP_0.6m(MAC)+OMT x1. 2.Install new 23G_XMC_3 , Sub_A & B_Lo x2. 3.Install new ISM8 x1. FE_7289A 1.Install new 23G_DP_0.6m(MAC)+OMT x1. 2.Install new 23G_XMC_3 , Sub_A & B_Hi x2. 3.Install new ISM8 x1 | MW Swap | Existing link 23G_1+0_56M. Need re-alignment and more cap. Swap existing link to 23G_2+0_112M. Site Impacted: 7145K. NE_7145K 1.Install 23G_DP_0.6m(MAC)+OMT. 2.Install new 23G_XMC_3 , Sub_A & B_Lo. 3.Reuse existing 7145K_RTN01 , 3_ISM8-2+0. 4.Install new 3_ISM8-2+0 into existing 7145K_RTN01. 5.Create EPLA and service cross connect. 6.Config 112M. 7.Migrate tarffic to new link. 8.Decom existing Ant and ODU. FE_7289A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new 23G_XMC_3 , Sub_A & B_Hi. 3.Reuse existing 7289A_RTN01 , 3_ISM8-2+0. 4.Install new 3_ISM8-2+0 into existing 7289A_RTN01. 5.Config 112M 6.Create EPLA and service cross connect and LAG port. 7.Traffic migrate to new link. 8.Decom existing ODU and Ant. | [7 empty] | NR services | SQ202502120362-NR Services | NR services | SQ202502270741-NR Services // SQ202504260199-NR Services | 2025-09-04 | 2025-09-04 | Completed | 2025-02-10 | 2025-02-10 | 2025-02-10 | 2025-02-10 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-05 | 2025-02-07 | 2025-02-05 | 2025-02-05 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-05 | 2025-02-07 | 2025-02-05 | 2025-02-05 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010777 |  | 2025-01-09 | 2025-01-15 | Completed | 2025-01-08 | 2025-01-09 | 2025-01-08 | 2025-01-15 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-02-22 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-02-22 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  | 2025-02-21 | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-02-27 | RALPH O'BRYAN HILARY7167000030 | 2025-03-21: 2025-01-23; 2025-03-21: 2025-01-31; 2025-03-21: 2025-01-23; 2025-03-27: 2025-02-26 |  |  | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016
4362C-4323A | Bembam Jaya | DU00004124654 | Northern | Perak | 4.463529 | 101.009610 | [7 empty] | 00. Site Out/Drop | 2/9: Pending Tx Solution for HU |  |  |  | Cancel / Drop | DU00002962697 | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
7681B-7196A | Berkeley Park | DU00004124655 | Sabah | Sabah | 4.256141 | 117.903410 |  |  | WK04 | JUN 25 | Plan TI | BOM ready/DO request/Skylift date to confirm | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Swap existing to 18G_2+0_112M. NE_7681B 1.Install new 18G_0.6m(MDD) x1. 2.Install new RTN910A x1. 3.Install new XMC_5D , Sub_B_Lo x1. FE_7196A 1.Install new 18G_1.2m(MDD) x1. 2.Install new RTN910A x1. 3.Install new XMC_5D , Sub_B_Hi x1. | MW Swap | Existing 18G_1+0_56M.Not Support for Remote Software Upgrade. Swap existing to 18G_2+0_112M. Site Impacted : 7681B. NE_7681B 1.Install new 18G_0.6m(MDD). 2.Install new RTN910A , 7_ISM8-2+0.(RTN no provide by MSP team). 3.Install new XMC_5D , Sub_B_Lo. 4.Enable EPLA and service cross connect. 5.Migrate traffic to new link. 6.Decom existing RTN,ODU and Ant. FE_7196A 1.Install new 18G_1.2m(MDD). 2.Install new RTN910A ,7_ISM8-2+0.(RTN no provide by MSP team) 3.Install new XMC_5D , Sub_B_Hi. 4.Enable GE1 port and create In-Band DCN patch to PFS. 5.Enable EPLA and service cross connect and LAG port. 6.Traffic migrate to new link. 7.Decom existing ODU , Ant and 3_ISV3.(7196A-7681B). | [7 empty] | NR services | SQ202508010581-NR Services | NR services | SQ202507190102-NR Services // SQ202507190103-NR Services | 2025-11-26 | 2025-11-25 | Completed | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250611BM |  | 2025-06-12 | 2025-06-12 | Completed | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-12 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-26 | WILFRED BALANG7167000026 | NR Service TI | 2025-08-24 | 2025-08-26 | 2025-08-24 | 2025-08-26 | WILFRED BALANG7167000026 | NR Service TI | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-07-29 | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-10-23 | WILFRED BALANG7167000026 | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-28 | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | tseping//wang/6819000006 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GCI_AA | SQ202510300170-GCI | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | CHEONG/SENG/WAH/7018000306
4536B-4346A | LAP Tanah Hitam RDD | DU00004124656 | Northern | Perak | 4.719930 | 101.149710 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Integrated/RFS Done | 23/9: Pending Site BoM | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Swap existing 2xXMC_3 ODU to 2xXMC_3E to configure 18G_2+0_112Mhz. NE_4536B_RTN01 1. 18G_XMC_3E x2 , Sub (A & B_Hi). FE_4346A_RTN05 1, 18G_XMC_3E x2 , Sub (A & B_Lo). 2, New 1.2DP ant x1 | MW Swap | Existing link 18G_2+0_56Mhz. Not support 112MHz Swap existing 2xXMC_3 ODU to 2xXMC_3E to configure 18G_2+0_112Mhz. Capture existing link parameters before swap. Site Impacted: 4538B,4536B. 4536B_RTN01 1.Swap existing 18G_XMC_3 to 18G_XMC_3E , Sub (A & B_Hi) configure to 2+0 link. 2.Configure to 2+0_112Mhz_900M. 3.Reuse existing antenna 1.2DP & 7_ISM8-1&2. 4.Decom existing XMC_3x2 4346A_RTN05 1.Swap existing 18G_XMC_3 to 18G_XMC_3E , Sub (A & B_Lo) configure to 2+0 link. 2.Install new 1.2DP ant. 3.Configure to 2+0_112Mhz_900M. 4.Reuse 7_ISM8_1&2. 5.Decom existing XMC_3x2 and antenna. | [7 empty] | CCSMY | SQ202411140303-CCS | Magicell | SQ202511190825-Magicell // SQ202511190829-Magicell | 2025-11-14 | 2025-11-07 | Completed | 2024-12-17 | 2024-12-17 | 2024-12-17 | 2024-12-17 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | ainfatinainfatin28@gmail.com |  |  | 1.00 | Unassigned | Completed |  | 2025-07-16 | 2025-07-25 | 2025-07-16 | 2025-07-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-14 | 2025-11-07 | 2025-11-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102321 |  | 2025-10-24 | 2025-10-27 | Completed | 2025-10-23 | 2025-10-24 | 2025-10-23 | 2025-10-27 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-02 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-10 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-03 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-10 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-08 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202507080632-GTSB
3373B-1735A | Jalan Pantai Permai 1 | DU00004124657 | Central | Kuala Lumpur | 3.106080 | 101.670210 | [7 empty] | 00. Integrated/RFS Done | 2/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M NE_3373B New 23G_0.6M(MAC)+OMT x1. Reuse existing RTN910A(RTN01). New XMC_3E, Sub B_Hi x1. New IF cable for 2nd channel(Horizontal) with suitable length. FE_1735A New 23G_0.6M(MAC)+OMT x1. Reuse existing RTN910A(RTN01). New XMC_3E, Sub B_Lo x1. New IF cable for 2nd channel(Horizontal) with suitable length. | MW Swap | Link Existing HW 23G_1+0_112M_512QAM. Swap existing link to new HW 23G_2+0_112M_512QAM_EPLA. Site Impacted : 3373B. NE_3373B 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_3E , Sub A_Hi. Configure new HW 23G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and migrate RAN traffic to new MW link. 5.Later, decom existing HW 23G_1+0_112M_512QAM but decom existing ODU 23G and existing antenna 23G(0.6m) ONLY. Do not decom RTN910A(RTN01). FE_1735A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Reuse existing RTN910A(RTN04). 3.Install new 1x XMC_3E , Sub A_Lo. Configure new HW 23G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and existing port at IBeam. 5.Later, decom existing HW 23G_1+0_112M_512QAM but decom existing ODU 23G and existing antenna 23G(0.6m) ONLY. Do not decom RTN910A(RTN04). | Link Existing HW 23G_1+0_112M_512QAM. Swap existing link to new HW 23G_2+0_112M_512QAM_EPLA. Site Impacted : 3373B. NE_3373B 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Reuse existing RTN910A(RTN01). 3.Install new 1x XMC_3E , Sub A_Hi. Configure new HW 23G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and migrate RAN traffic to new MW link. 5.Later, decom existing HW 23G_1+0_112M_512QAM but decom existing ODU 23G and existing antenna 23G(0.6m) ONLY. Do not decom RTN910A(RTN01). | Link Existing HW 23G_1+0_112M_512QAM. Swap existing link to new HW 23G_2+0_112M_512QAM_EPLA. Site Impacted : 3373B. FE_1735A 1.Install new 23G_0.6M(MAC)+OMT x1. 2.Reuse existing RTN910A(RTN04). 3.Install new 1x XMC_3E , Sub A_Lo. Configure new HW 23G_2+0_112M_512QAM_EPLA. 4.Reuse existing Vlan Services and existing port at IBeam. 5.Later, decom existing HW 23G_1+0_112M_512QAM but decom existing ODU 23G and existing antenna 23G(0.6m) ONLY. Do not decom RTN910A(RTN04). | XMC_3E | MAC | 23G | 23G_0.6M(MAC)+OMT x1. | 23G_0.6M(MAC)+OMT x1. | GCI | SQ202506190612-GCI | GCI | SQ202506190647-GCI // SQ202506190656-GCI | 2025-11-29 | 2025-11-22 | Completed | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-19 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25061993 |  | 2025-06-20 | 2025-06-21 | Completed | 2025-06-19 | 2025-06-20 | 2025-06-19 | 2025-06-21 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-08 | 2025-07-15 | 2025-07-07 | 2025-07-08 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-08 | 2025-07-15 | 2025-07-07 | 2025-07-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-09 | 2025-07-08 | 2025-07-15 | 2025-07-07 | 2025-07-17 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-07-08 | 2025-07-15 | 2025-07-07 | 2025-07-08 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202505280699-GTSB
7594A-7492A | Rancha Rancha 2 | DU00004124658 | Sabah | Sabah | 5.249022 | 115.236710 |  |  |  |  | DONE UNDER NIC | DONE under NIC |  | 07. Solution Changed | 22/10: Pending Site DO 2/9: Pending Tx Solution for HU 3/2: TI plan under NIC |  |  | Install new parallel link with Config 23G_2+0_112M. NE_7594A. 1.Install new 23G_DP_0.6m(MAC) + OMT x1. 2.Install new XMC_3_2+0 , Sub_A & B_Hi x2. 3.Install new RTN910A x1. FE_7492A 1.Install new 23G_DP_0.6m(MAC)+OMT x1. 2.Install new XMC_3_2+0,Sub_A & B_Lo x2. 3.Install new RTN910 x1. | Under NIC | Existing link 23G_1+0_56M.Not Support Remote Upgrade. Install new parallel link with Config 23G_2+0_112M. Site Impacted: 7594A. NE_7594A. 1.Install new 23G_DP_0.6m(MAC) + OMT. 2.Install new XMC_3_2+0 , Sub_A & B_Hi. 3.Install new RTN910A,7_ISM8-2+0.(RTN no provide by MSP team). 4.Create EPLA and service cross connect. 5.Enable GE1 for BBU patching and migrate traffic to new parallel link. 6.No link decom due to child site for 7848E & 7624E via existing MW link. FE_7492A 1.Install new 23G_DP_0.6m(MAC)+OMT. 2.Install new XMC_3_2+0,Sub_A & B_Lo. 3.Install new RTN910,7_ISM8-2+0.(RTN no provide by MSP team). 4.Create EPLA and service cross connect. 5.Enable GE1 interconnect ETH cable to existing 7492A_RTN02 (GE3). 6.No link decom due to 2 child sites via existing MW link. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI_AA | SQ202510300170-GCI | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | CHEONG/SENG/WAH/7018000306
2737C-3092A | ELITE KM 33.8 (REL) | DU00004124659 | Central | Selangor | 2.846075 | 101.684210 |  |  |  |  | FAC | FAC done | ZTE | 00. Integrated/RFS Done | 6/11: Cutover done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Swap existing 13G_1+0_28M to 18G_1+0_112M NE_2737C 1.Install new 18G_XMC_3E, Sub_B_Hi x1. 2.Install new RTN910A x1. FE_3092A 1.Install new 18G_XMC_3E, Sub_B_Lo x1. | MW Swap | Existing Link 13G_1+0_28M Swap existing 13G_1+0_28M to 18G_1+0_112M. Site Impacted : 2737C. NE_2737C 1.Install new 18G_SP_0.6 ant. 2.Install new 18G_XMC_3E,Sub_B_Hi. 3.Install new RTN910A, 7_ISM8-1+0. 4.Config to 18G_112M. 5.Create EPLA and service cross connect. 6.Migrate traffic to new RTN910A. 7.Decom existing 13G RTN & Ant + ODU. FE_3092A 1.Install new 18G_SP_0.6 ant. 2.Install new 18G_XMC_3E, Sub_B_Lo. 3.Reuse RTN950A,2_ISM8-1+0 connect IF cable to new 18G_XMC_5D ODU. 4.Config to 18G_112M. 5.Decom existing 13G_Ant & ODU. | [7 empty] | GTSB | SQ202411060156-GTSB | GTSB | SQ202411060160-GTSB // SQ202412240349-GTSB // SQ202504260131-GTSB | 2024-12-06 | 2024-12-05 | Completed | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-11-16 | 2024-11-30 | 2024-11-16 | 2024-11-16 | laina@girobumi.com.mylaina@girobumi.com.my | GTSB TI |  | 1.00 | Assigned | Completed |  | 2024-11-20 | 2024-11-21 | 2024-11-20 | 2024-11-20 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-12-05 | 2024-12-06 | 2024-12-05 | 2024-12-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24103033 |  | 2024-10-31 | 2024-11-05 | Completed | 2024-10-30 | 2024-10-31 | 2024-10-30 | 2024-11-05 | yap//hweebwen/6871000023 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-11-05 | 2024-11-30 | 2024-11-15 | 2024-11-15 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2024-11-05 | 2024-11-30 | 2024-11-15 | 2024-11-15 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2024-11-06 | 2024-11-06 | 2024-11-06 | 2024-11-06 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2024-11-05 | 2024-11-30 | 2024-11-09 | 2024-11-09 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2024-11-05 | 2024-11-30 | 2024-11-06 | 2024-11-06 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | NG HONG JIE7018000036 | Logistic Team | 2024-11-21 | 2024-12-21 | 2024-11-21 | 2024-11-21 | ASTI//GANIS PUTRIANI/6237001358
9046Z-9156A_1 | KampungSekai | DU00004124660 | Sarawak | Sarawak | 2.823103 | 112.195110 | [7 empty] | 00. Site Out/Drop | 2/10: HW already implemented 4+0 at site and the site already being cutover |  |  | 2x ISM8 4x SB A,B | Cancel / Drop | Link upgraded by other vendor "MW Hardware Upgrade 9046Z-9156A_13G_4+0_1.8/1.8_DP_SB A,B NE: 1. Reuse existing RTN910A and ISM8 at slot 3. 2. Reuse exiting ODU and add additional XMC-3E (SB A,B). 3. Reuse existing Antenna_13G_1.8m_DP. 4. Configure 13G_4+0_1.8m_512QAM_EPLA FE: 1. Reuse existing RTN910A and ISM8 at slot 3. 2. Reuse exiting ODU and add additional XMC-3E (SB A,B). 3. Reuse existing Antenna_13G_1.8m_DP. 4. Configure 13G_4+0_1.8m_512QAM_EPLA" | [9 empty] | Magicell | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24082902 |  | 2024-08-30 | 2024-09-06 | Completed | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-09-06 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-02 | 2024-10-09 | 2024-10-02 | 2025-02-07 | ALBERT//GOH CHIN SIANG/7018000169 | Magicell TI | 2024-10-02 | 2024-10-09 | 2024-10-02 |  | ALBERT//GOH CHIN SIANG/7018000169 | Magicell TI | [7 empty] | 2024-10-02 | 2024-10-09 | 2024-10-02 |  | ALBERT//GOH CHIN SIANG/7018000169 | 2025-11-29: 2024-10-02; 2025-11-29: 2024-10-09; 2025-11-29: 2024-10-02
4904B-4907B | Pos Slim | DU00004124661 | Northern | Perak | 4.554917 | 101.299410 | WK36-40 | SEP 24 | WK36-40 | SEP 24 |  |  |  | 00. Site Out/Drop | 23/9: Pending Site BoM | TSS |  | Follow solution under TX Rollout project_4904B BBU PATCHING AT 4904B, TO USE CELCOM A00564 OB FIBER IMPACTED SITES: 4904B | Cancel / Drop | follow solution under TX Rollout project_4904B | [13 empty] | Ongoing | 2025-04-16 | 2025-04-16 | 2025-04-16 |  | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Ongoing | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4445K-4985A | K002A_K00442OD_KGTERABAK | DU00005157240 | Northern | Kedah | 5.773393 | 100.888901 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+PAC | IF cable | MW Swap | Raise Up ant location to get the acceptable RSL figure. | [7 empty] | Magicell | SQ202504210275-Magicell | Magicell | SQ202503200278-Magicell // SQ202504260184-Magicell // SQ202511030393-Magicell | 2026-02-24 | 2026-02-25 | Completed | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-25 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25030734 |  | 2025-03-08 | 2025-03-19 | Completed | 2025-03-07 | 2025-03-08 | 2025-03-07 | 2025-03-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-17 | 2026-03-19 | 2025-03-17 | 2025-03-19 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 |  | 2025-03-17 | 2026-03-19 | 2025-03-17 | 2025-04-08 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 |  | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-03-17 | 2025-03-17 | 2026-03-19 | 2025-03-17 | 2025-04-09 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | 2025-11-29: 2025-03-17; 2025-11-29: 2026-03-19; 2025-11-29: 2025-03-17; 2025-12-08: 2025-03-17 |  |  | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | CHEONG/SENG/WAH/7018000306
2038B_HU | North Klang Industrial (Celcom) | DU00005157241 | Central | Selangor | 3.007073 | 101.374473 | WK12 | APR 25 | WK12 | APR 25 | TI | RSL -42 due to FE antenna install a bit low (Space constrain) | ZTE | 03. TSS Only | 14/4/2025 : RSL not yet done due to need move up antenna or re-route 21/3/2025 : Cancel proceed due to not clear instruction 20/3/2025 : Cutover done with RSL -42 12/3/2025 : CELCOM (M) - 50M Tower - NE site 2038B North Klang Industrial (Celcom), Digi OB - 45M 3 Legged Tower - FE site 1082A West Port Lot 5692 | TSS |  | 1X IDU RTN910A | MW Hardware Upgrade | CHANGE IDU AT NE DUE TO EXISTING USING OLD VERSION IDU | [7 empty] | GCI | SQ202505130130-GCI | GCI | No PR required-Work at TSS only | 2025-05-24 | 2025-05-23 | Completed | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-13 | 2025-05-14 | 2025-05-13 | 2025-05-13 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-23 | 2025-05-24 | 2025-05-23 | 2025-05-23 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25041717 |  | 2025-04-18 |  | Ongoing | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing |  | 2025-03-20 | 2025-03-27 | 2025-03-19 |  | SYEDMOHAMAD//FARISAIMAN/6800000274 | GCI TI | 2025-03-20 | 2025-03-27 | 2025-03-19 |  | SYEDMOHAMAD//FARISAIMAN/6800000274 | GCI TI | [7 empty] | 2025-03-20 | 2025-03-27 | 2025-03-19 |  | SYEDMOHAMAD//FARISAIMAN/6800000274 | 2025-11-29: 2025-03-20; 2025-11-29: 2025-03-27; 2025-11-29: 2025-03-19; 2025-12-08: 2025-03-20 | [7 empty] | GCI | SQ202506050696-GCI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | CHEONG/SENG/WAH/7018000306
W00482_LOS | BSARSHOWROOM | DU00005157242 | Central | Kuala Lumpur | 3.131182 | 101.671243 | WK10 | MAR 25 | WK10 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 6/3/2025 : Cutover done 5/3/2025 : NE installation complete, pending install FE site | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_W00482. 23G_DP_0.6M(MAC) x1. RTN910A , 7_ISM8-1+0 x1. XMC_3E , Sub B_Hi x1. FE_2606A 23G_DP_0.6M(MAC) x1. RTN910A , 7_ISM8-1+0 x1. XMC_3E , Sub B_Lo x1. | MW New Link / Reroute | Link reroute to new FE 2606A due to existing FE LOS Block. Site Impacted : W00482. 23G_1+0_112M NE_W00482. 1.Link install 23G_SP_0.6M(MAC)+ OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create cross connect and EPLA. 5.Traffic migrate to new link and new tx route. 6.Decom existing MW (W00482-W01296)_CT09279.Ensure trafiic complete migrate before decom. FE_1052B 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_3E , Sub B_Lo. 4.Create cross connect and EPLA. 5.Create new In Band DCN. 6.Traffic migrate to new link and new TX route. 7.Decom existing MW (W01296-W00482)_CT09279.Ensure traffic complete migrate before decom. | Link reroute to new FE 2606A due to existing FE LOS Block. Site Impacted : W00482. 23G_1+0_112M NE_W00482. 1.Link install 23G_SP_0.6M(MAC)+ OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub B_Hi. 4.Create cross connect and EPLA. 5.Traffic migrate to new link and new tx route. 6.Decom existing MW (W00482-W01296)_CT09279.Ensure trafiic complete migrate before decom. | Link reroute to new FE 2606A due to existing FE LOS Block. Site Impacted : W00482. 23G_1+0_112M FE_1052B 1.Install new 23G_SP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8-2+0. 3.Install XMC_3E , Sub B_Lo. 4.Create cross connect and EPLA. 5.Create new In Band DCN. 6.Traffic migrate to new link and new TX route. 7.Decom existing MW (W01296-W00482)_CT09279.Ensure traffic complete migrate before decom. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202503060123-GTSB | GTSB | SQ202503200152-GTSB // SQ202503200154-GTSB // SQ202504260131-GTSB | 2025-12-04 | 2025-12-03 | Completed | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-28 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | Girobumi Technologies SDN. BHD. |  | Assigned | Completed |  | 2025-03-22 | 2025-04-05 | 2025-03-22 | 2025-03-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25030346 |  | 2025-03-05 | 2025-03-24 | Completed | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-24 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-24 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-24 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-06 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-12 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-07 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GCI | SQ202511280798-GCI | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
A00500-A00077 | CHANGKATSULAIMAN | DU00005159812 | Northern | Perak | 3.976310 | 101.288710 | [7 empty] | 03. TSS Only |  | TSS |  | TSS LOS Survey Only | MW New Link / Reroute | Existing TX route A00500/4418B-A00077 facing LOS Block Issue , propose TSS LOS survey and new FE reroute with candidate LOS is clear. SOW Details for TX reroute / new link refer to DU ID 4418B_AD , DU code : DU00005239883. | Perform TSS LOS survey | [6 empty] | Magicell | SQ202506030423-Magicell | Magicell | No PR required-Work at TSS only | 2025-12-23 | 2025-12-16 | Completed | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-10 | 2025-09-17 | 2025-09-11 | 2025-09-11 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506050646-GTSB
4574C_HU | Tingkat Selamat 3 | DU00005159829 | Northern | Penang | 5.497480 | 100.505390 | [7 empty] | 00. Site Out/Drop |  |  |  | 18G_1+0_112M NE_4574C New 18G_SP_1.2M(MAC)+OMT x1. New RTN910A. New XMC_3E , Sub A_Hi x1. FE_4084B New 18G_SP_1.2M(MAC)+OMT x1. New RTN910A. New XMC_3E , Sub A_Lo x1. | Cancel / Drop | Link Existing SM 23G_1+0_56M. Swap existing link to 18G_1+0_112M_512QAM. Site Impacted : 4441D. NE_4574C 1.Install new 18G_SP_1.2M(MAC)+OMT x1. 2.Install new RTN910A(RTN04). Configure it. 3.Install XMC_3E , Sub B_Hi. Configure it. 4.Create new In Band DCN. 6.Enable port 8-EM6-1 of RTN910A(RTN04). 7.Cascading at port 8-EM6-1 of RTN910A(RTN04) and at port 8-EM6-1 of RTN910A(RTN02) 8.Decom existing MW link 4574C(RTN950A-RTN01)-4084B(RTN950-RTN01). FE_4084B 1.Install new 18G_SP_1.2M(MAC)+OMT x1. 2.Install new RTN910A(RTN04). Configure it. 3.Install XMC_3E , Sub B_Lo. Configure it. 4.Create new In Band DCN. 6.Enable port 8-EM6-1 of RTN910A(RTN04). 7.Cascading at port 8-EM6-1 of RTN910A(RTN04) and at port 8-EM6-1 of RTN910A(RTN03) 8.Decom existing MW link 4574C(RTN950A-RTN01)-4084B(RTN950-RTN01). | Link Existing SM 23G_1+0_56M. Swap existing link to 18G_1+0_112M_512QAM. Site Impacted : 4441D. NE_4574C 1.Install new 18G_SP_1.2M(MAC)+OMT x1. 2.Install new RTN910A(RTN04). Configure it. 3.Install XMC_3E , Sub B_Hi. Configure it. 4.Create new In Band DCN. 6.Enable port 8-EM6-1 of RTN910A(RTN04). 7.Cascading at port 8-EM6-1 of RTN910A(RTN04) and at port 8-EM6-1 of RTN910A(RTN02) 8.Decom existing MW link 4574C(RTN950A-RTN01)-4084B(RTN950-RTN01). | Link Existing SM 23G_1+0_56M. Swap existing link to 18G_1+0_112M_512QAM. Site Impacted : 4441D. FE_4084B 1.Install new 18G_SP_1.2M(MAC)+OMT x1. 2.Install new RTN910A(RTN04). Configure it. 3.Install XMC_3E , Sub B_Lo. Configure it. 4.Create new In Band DCN. 6.Enable port 8-EM6-1 of RTN910A(RTN04). 7.Cascading at port 8-EM6-1 of RTN910A(RTN04) and at port 8-EM6-1 of RTN910A(RTN03) 8.Decom existing MW link 4574C(RTN950A-RTN01)-4084B(RTN950-RTN01). | XMC_3E | MAC | 18G | 18G_SP_1.2M(MAC)+OMT x1. | 18G_SP_1.2M(MAC)+OMT x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4593B_HU | Lambor Kiri RDD | DU00005159830 | Northern | Perak | 4.270810 | 100.896070 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1x New CAT6 cable with suitable length | MW IDU Patching | MW IDU Patching need to perform at 4395B & A00033 in order to diverting traffic 4365B from existing xD HW MW Link 4365B(RTN01)-4593B(RTN02) to xC existing HW MW Link A00033(RTN01)-A00474(RTN01). 4593B is Pair Colo with A00033. Site Impacted : 4365B. NE_4593B/A00033 1.Disable RTN01(port 8-EG6-3) of existing HW MW Link 4593B(RTN01)-4734A(RTN02). 2.Remove cascading between RTN01(port 8-EG6-3) and RTN02(port 8-EM6-1) at 4593B. 3.Patching new 1x CAT6 cable at 4593B RTN02(port 8-EM6-1) of existing xD MW Link 4365B(RTN01)-4593B(RTN02) to existing xC HW MW Link A00033(RTN01)-A00474(RTN01) at A00033 RTN01(port 8-EM6-2). Configure it. 4.Configure DCN Inband for RTN02 of 4365B(RTN01)-4593B(RTN02) and new VLAN services for 4365B backhaul to xC Host. 5.Migrate 4365B traffic to new CP/PTN A00474. 6.Decom existing HW MW link 4593B(RTN01)-4734A(RTN02). | MW IDU Patching need to perform at 4395B & A00033 in order to diverting traffic 4365B from existing xD HW MW Link 4365B(RTN01)-4593B(RTN02) to xC existing HW MW Link A00033(RTN01)-A00474(RTN01). 4593B is Pair Colo with A00033. Site Impacted : 4365B. NE_4593B/A00033 1.Disable RTN01(port 8-EG6-3) of existing HW MW Link 4593B(RTN01)-4734A(RTN02). 2.Remove cascading between RTN01(port 8-EG6-3) and RTN02(port 8-EM6-1) at 4593B. 3.Patching new 1x CAT6 cable at 4593B RTN02(port 8-EM6-1) of existing xD MW Link 4365B(RTN01)-4593B(RTN02) to existing xC HW MW Link A00033(RTN01)-A00474(RTN01) at A00033 RTN01(port 8-EM6-2). Configure it. 4.Configure DCN Inband for RTN02 of 4365B(RTN01)-4593B(RTN02) and new VLAN services for 4365B backhaul to xC Host. 5.Migrate 4365B traffic to new CP/PTN A00474. 6.Decom existing HW MW link 4593B(RTN01)-4734A(RTN02). | [6 empty] | CCSMY | SQ202505050040-CCS | CCSMY | SQ202505050151-CCS | 2025-08-13 | 2025-08-07 | Completed | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-18 | 2025-07-25 | 2025-07-18 | 2025-07-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-28 | 2025-08-06 | 2025-07-28 | 2025-07-28 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032038 |  | 2025-04-25 | 2025-04-18 | Completed | 2025-03-24 | 2025-04-25 | 2025-03-20 | 2025-04-18 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-04-25 | 2025-06-04 | 2025-06-04 | SADDAM HUSIN SAMPANG BIN GHAZALI7018000304 | Magicell TI | 2025-05-13 | 2025-05-31 | 2025-05-13 | 2025-06-04 | Saleem//Muhammed/7021000077 | CCS TI | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-13 | 2025-05-31 | 2025-05-13 | 2025-06-02 | Saleem//Muhammed/7021000077 | 2025-05-13 | 2025-05-31 | 2025-05-13 | 2025-05-13 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | NG HONG JIE7018000036 | Logistic Team | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202509250697-GTSB
4442B_HU | Kuala Terla | DU00005159831 | Northern | Pahang | 4.548830 | 101.414790 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | DU00002885627. Already release design by Radzman under NIC. NIC DU for TX not implemented yet. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
4026L_HU | Sri Bayu | DU00005159832 | Northern | Penang | 5.296340 | 100.256150 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M NE_4026L 23G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E, Sub B_Lo x1. FE_4992C 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E, Sub B_Hi x1. | MW Swap | Link Existing SM 23G_1+0_56M. Swap existing SM MW Link to new HW MW Link 18G_1+0_112M. Site Impacted : 4026L. NE_4026L 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A(RTN01). Configure it. 3.Install XMC_3E , Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Decom existing SM MW link 4026L-4992C MW1. FE_4992C 1.Install new 23G_DP_0.6M(MAC). 2.Insert new 1x ISM8 into existing RTN910A(RTN01) slot 03. Configure it. 3.Install XMC_3E , Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Re-use existing port at CP(4063A) 7.Decom existing SM MW link 4026L-4992C MW1. | Link Existing SM 23G_1+0_56M. Swap existing SM MW Link to new HW MW Link 18G_1+0_112M. Site Impacted : 4026L. NE_4026L 1.Install new 23G_DP_0.6M(MAC). 2.Install new RTN910A(RTN01). Configure it. 3.Install XMC_3E , Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Decom existing SM MW link 4026L-4992C MW1. | Link Existing SM 23G_1+0_56M. Swap existing SM link to new HW MW Link 18G_1+0_112M. Site Impacted : 4026L. FE_4992C 1.Install new 23G_DP_0.6M(MAC). 2.Insert new 1x ISM8 into existing RTN910A(RTN01) slot 03. Configure it. 3.Install XMC_3E , Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Re-use existing port at CP(4063A) 7.Decom existing SM MW link 4026L-4992C MW1. | XMC_3E | MAC | 23G | 23G_DP_0.6M(MAC)+OMT x1. | 23G_DP_0.6M(MAC)+OMT x1. | CCSMY | SQ202504210258-CCS | CCSMY | SQ202504210107-CCS // SQ202504210102-CCS // SQ202504260175-CCS |  |  | Ongoing | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25032003 |  | 2025-03-21 | 2025-03-22 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-07 | 2025-04-30 | 2025-04-07 | 2025-04-11 | HASHIM//BIN AHMAD ZAIDI/7021000032 | CCS TI | 2025-04-07 | 2025-04-30 | 2025-04-07 | 2025-04-11 | HASHIM//BIN AHMAD ZAIDI/7021000032 | CCS TI | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-04-08 | 2025-04-07 | 2025-04-30 | 2025-04-07 | 2025-04-25 | HASHIM//BIN AHMAD ZAIDI/7021000032 | 2025-04-07 | 2025-04-30 | 2025-04-07 | 2025-04-08 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | NG HONG JIE7018000036 | Logistic Team | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 |  | Assign Subcon
4940C_HU | Jay Series Condo (Rel) | DU00005159833 | Northern | Penang | 5.391150 | 100.295190 |  |  |  |  | TI IN PLAN | ZTE |  | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M_EPLA NE_4940C 18G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E, Sub A & B_Hi x2. FE_4007B 18G_DP_1.2M(MAC)+OMT x1. RTN910A x1. XMC_3E, Sub A & B_Lo x2. | MW Swap | Link Existing HW MW Link 23G_1+0_56M. Swap Existing HW MW Link to New HW MW Link 18G_2+0_56M_EPLA. Site Impacted : 4940C & 4801D. NE_4940C 1.Install new 1x 18G_DP_0.6M(MAC)+OMC. 2.Install new 1x RTN910A(RTN03). Configure it. 3.Install new 1x XMC_3E , Sub A & B_Hi. Configure it. 4.Create new In Band DCN. 5.Migrate traffic to new link in which BBU will patching to port 8-EM6-1. 6.Patching port 8-EM6-2 to RTN910A(RTN02) port 8-EM6-1. 7.Later, decom Existing HW MW Link 23G_1+0_56M(IDU, ODU & Ant). FE_4007B 1.Install new 1x 18G_DP_1.2M(MAC)+OMC. 2.Install new 1x RTN910A(RTN05). Configure it. 3.Install XMC_3E , Sub A & B_Lo. Configure it. 4.Create new In Band DCN. 5.Request new port at IBeam from ZTE IPRAN team. Not suggest to use existing port due to capacity will exceed 1G. Thus, require new port at IBeam. 6.Migrate traffic to new link. 7.Later, decom Existing HW MW Link 23G_1+0_56M(ODU & Ant Only). But do not "decom IDU" as IDU shared with HW MW Link 4007B-4310C. | Link Existing HW MW Link 23G_1+0_56M. Swap Existing HW MW Link to New HW MW Link 18G_2+0_56M_EPLA. Site Impacted : 4940C & 4801D. NE_4940C 1.Install new 1x 18G_DP_0.6M(MAC)+OMC. 2.Install new 1x RTN910A(RTN03). Configure it. 3.Install new 1x XMC_3E , Sub A & B_Hi. Configure it. 4.Create new In Band DCN. 5.Migrate traffic to new link in which BBU will patching to port 8-EM6-1. 6.Patching port 8-EM6-2 to RTN910A(RTN02) port 8-EM6-1. 7.Later, decom Existing HW MW Link 23G_1+0_56M(IDU, ODU & Ant). | Link Existing HW MW Link 23G_1+0_56M. Swap Existing HW MW Link to New HW MW Link 18G_2+0_56M_EPLA. Site Impacted : 4940C & 4801D. FE_4007B 1.Install new 1x 18G_DP_1.2M(MAC)+OMC. 2.Install new 1x RTN910A(RTN05). Configure it. 3.Install XMC_3E , Sub A & B_Lo. Configure it. 4.Create new In Band DCN. 5.Request new port at IBeam from ZTE IPRAN team. Not suggest to use existing port due to capacity will exceed 1G. Thus, require new port at IBeam. 6.Migrate traffic to new link. 7.Later, decom Existing HW MW Link 23G_1+0_56M(ODU & Ant Only). But do not "decom IDU" as IDU shared with HW MW Link 4007B-4310C. | XMC_3E | MAC | 18G | 18G_DP_0.6M(MAC)+OMT x1. | 18G_DP_1.2M(MAC)+OMT x1. | GTSB | SQ202504280474-GTSB | GTSB | SQ202505280074-GTSB // SQ202505280077-GTSB | 2025-08-26 | 2025-08-27 | Completed | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-08-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032035 |  | 2025-03-21 | 2025-03-22 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-10-13 | YASIR//ABBAS/6799000106 | GTSB TI | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-07-24 | YASIR//ABBAS/6799000106 | GTSB TI | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-06-19 | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2026-02-27 | YASIR//ABBAS/6799000106 | 2025-03-05: 2025-05-28; 2025-03-05: 2025-05-28; 2025-03-05: 2025-05-28; 2025-03-07: 2025-06-10 |  |  | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB
4010D_HU | Kg Sri Acheh Setiawan (REL) | DU00005159834 | Northern | Perak | 4.241969 | 100.686259 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+PAC | 18G_2+0_56M_EPLA NE_4010D 18G_0.6M(MDD) x1. RTN910A x1. XMC_5D, Sub B_Hi x1. FE_4409A 18G_0.6M(MDD) x1. RTN910A x1. XMC_5D, Sub B_Lo x1. | MW Swap | Link Existing HW MW Link 23G_1+0_56M. Swap Existing HW MW Link to New HW MW Link 18G_2+0_56M_EPLA. Site Impacted : 4010D. NE_4010D 1.Install new 1x 18G_0.6M(MDD). 2.Install new 1x RTN910A(RTN02). Configure it. 3.Install new 1x XMC_5D , Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Later, decom Existing HW MW Link 4010D(RTN910A-RTN01)-4409A(RTN910A-RTN02), 23G_1+0_56M(IDU, ODU & Ant). FE_4409A 1.Install new 1x 18G_0.6M(MDD). 2.Install new 1x RTN910A(RTN02). Configure it. 3.Install 1x XMC_5D , Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Reuse existing port at IBeam. 6.Migrate traffic to new link. 7.Later, decom Existing HW MW Link 4010D(RTN910A-RTN01)-4409A(RTN910A-RTN02), 23G_1+0_56M(IDU, ODU & Ant). | Link Existing HW MW Link 23G_1+0_56M. Swap Existing HW MW Link to New HW MW Link 18G_2+0_56M_EPLA. Site Impacted : 4010D. NE_4010D 1.Install new 1x 18G_0.6M(MDD). 2.Install new 1x RTN910A(RTN02). Configure it. 3.Install new 1x XMC_5D , Sub B_Hi. Configure it. 4.Create new In Band DCN. 5.Migrate traffic to new link. 6.Later, decom Existing HW MW Link 4010D(RTN910A-RTN01)-4409A(RTN910A-RTN02), 23G_1+0_56M(IDU, ODU & Ant). | Link Existing HW MW Link 23G_1+0_56M. Swap Existing HW MW Link to New HW MW Link 18G_2+0_56M_EPLA. Site Impacted : 4010D. FE_4409A 1.Install new 1x 18G_0.6M(MDD). 2.Install new 1x RTN910A(RTN02). Configure it. 3.Install 1x XMC_5D , Sub B_Lo. Configure it. 4.Create new In Band DCN. 5.Reuse existing port at IBeam. 6.Migrate traffic to new link. 7.Later, decom Existing HW MW Link 4010D(RTN910A-RTN01)-4409A(RTN910A-RTN02), 23G_1+0_56M(IDU, ODU & Ant). | XMC_3E | MAC | 18G | 18G_DP_0.6M(MAC)+OMT x1. | 18G_DP_1.2M(MAC)+OMT x1. | GCI | SQ202504280464-GCI | GCI | SQ202505280624-GCI // SQ202505280628-GCI // SQ202508140739-GCI | 2025-12-04 | 2025-11-27 | Completed | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-11-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25051998 |  | 2025-05-20 | 2025-05-23 | Completed | 2025-05-19 | 2025-05-20 | 2025-05-19 | 2025-05-23 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-27 | 2025-06-07 | 2025-05-27 | 2025-06-11 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-05-27 | 2025-06-07 | 2025-05-27 | 2025-06-11 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-27 | 2025-05-27 | 2025-06-07 | 2025-05-27 | 2025-06-11 | MOHD SAIDI BIN ABD RAZAK6800000181 | 2025-03-05: 2025-05-27; 2025-03-05: 2025-06-07; 2025-03-05: 2025-05-27; 2025-03-07: 2025-05-28 |  |  | 2025-08-19 | 2025-09-19 | 2025-08-19 | 2025-08-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB_AA | SQ202510300144-GTSB
4011D_HU | Jalan Tepi Sungai (REL) | DU00005159835 | Northern | Perak | 3.875700 | 100.933870 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X 18G 0.6M MDD ANTENNA 1X 18G XMC-5D SUB B HI 1X 18G XMC-5D SUB B LO | MW Parallel Link | ADD PARALLEL MW LINK 4011D-4740B WITH HUAWEI_18G_112MHZ_1+0_0.6M_2.95KM PATCH FE IDU TO NEW 2X1G LAG CP PORT EXISTING CFG: HW_18G_1+0_56MHZ IMPACTED SITES: 4011D | 1. REUSE EXISTING RTN01(9-41957) 7-ISM8-2 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. EPLA EXISTING 18G 1+0 56MHZ WITH NEW 18G 1+0 112MHZ | 1. REUSE EXISTING RTN03(9-41956) 7-ISM8-2 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW 18G XMC-5D SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 5. EPLA EXISTING 18G 1+0 56MHZ WITH NEW 18G 1+0 112MHZ 6. PATCH RTN03(9-41956) TO NEW 2X1G LAG CP PORT | XMC_5D | MDD | 18G | 0.6 | 0.6 | GCI | SQ202504170476-GCI | GCI | SQ202503280474-GCI // SQ202503280484-GCI // SQ202505150106-GCI | 2025-10-30 | 2025-10-29 | Completed | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-04-09 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-29 | 2025-10-30 | 2025-10-29 | 2025-10-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25032029 |  | 2025-03-21 | 2025-03-21 | Completed | 2025-03-20 | 2025-03-21 | 2025-03-20 | 2025-03-21 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-26 | 2025-03-31 | 2025-03-26 | 2025-04-09 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-03-26 | 2025-03-31 | 2025-03-26 | 2025-04-18 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-03-26 | 2025-03-31 | 2025-03-26 | 2025-04-11 | MOHD SAIDI BIN ABD RAZAK6800000181 | 2025-03-05: 2025-03-26; 2025-03-05: 2025-03-31; 2025-03-05: 2025-03-26; 2025-03-07: 2025-03-26 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202506050701-GCI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | MOHAMMAD//HIDIR BIN HUSAINI/6798000109
4623A_HU | Swee Aik Hardware | DU00005159836 | Northern | Kedah | 5.636810 | 100.496220 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | 4623A (DU00002749278). Need to drop for upgrade in Mini Project due to Radzman already release solution 23G_2+0_112MHZ. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
2448A_HU | Asmah Tower | DU00005165795 | Central | Kuala Lumpur | 3.080890 | 101.731210 | WK13 | MAR 25 |  | MAR 25 | Cancel / Drop | Done under DU 3219B_HU | ZTE | 00. Site Out/Drop | 22/3/2025 : No need proceed. Done under DU 3219B_HU 19/3/2025 : UMOBILE - In-Building System - NE site 3219B Cheras Sentral IB, Digi OB - 3M Boom - RT - FE site 2448A Asmah Tower |  |  | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | Cancel / Drop | MW SWAP LINK 3219B-2448A SM MW1 WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB A & B_1.53KM DISMANTLE EXISTING LINK IMPACTED: 2448A, 1034B | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE NEW LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 23G 0.6M DP ANTENNA 4. CONFIGURE NEW LINK 23G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25031358 |  | 2025-03-14 | 2025-03-22 | Completed | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI_AA | SQ202510300160-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
2836A_HU | IKEA Mutiara Damansara | DU00005165796 | Central | Selangor | 3.156450 | 101.612780 | WK13 | MAR 25 | WK13 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 26/3/2025 : Cutover done 25/3/2025 : Cutover done with issue ODU and RSL -40 13/3/2025 : MAXIS - In-Building System - NE site 2836A IKEA Mutiara Damansara, TELEFLOW - 3M Bipod - RT - FE site 1336A Balai Islam TTDI | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO | MW Swap | MW SWAP LINK 2836A-1336A WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM_889MBPS_XMC3E_SUB A_0.54KM DISMANTLE EXISTING LINK IMPACTED: 2836A | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3 112MHZ SUB A 3. REUSE EXISTING 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910A 2. INSTALL NEW ODU 23G XMC3 112MHZ SUB A 3. REUSE EXISTING 23G 0.6M DP ANTENNA 4. CONFIGURE LINK 23G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 6. REPATCH TO EXISTING CP PORT | XMC3 | MAC | 23 | 0.6 | 0.6 | Magicell | SQ202504170467-Magicell | Magicell | SQ202503280442-Magicell // SQ202503280449-Magicell // SQ202504260146-Magicell | 2025-06-03 | 2025-06-04 | Completed | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 | NUR FATIHAH BINTI AYOB7018000236 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25031167 |  | 2025-03-12 | 2025-03-13 | Completed | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-24 | 2026-03-16 | 2025-03-24 | 2025-04-08 | MOHD//SAFRI BIN ARIF/7018000166 |  | 2025-03-24 | 2026-03-16 | 2025-03-24 | 2025-04-08 | MOHD//SAFRI BIN ARIF/7018000166 |  | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-03-25 | 2025-03-24 | 2026-03-16 | 2025-03-24 | 2025-05-17 | MOHD//SAFRI BIN ARIF/7018000166 | 2025-03-24 | 2026-03-16 | 2025-03-24 | 2025-03-25 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202506050715-GTSB
2663B_HU | Kesas Bdr Puteri Klang | DU00005165797 | Central | Selangor | 2.980753 | 101.479996 | WK11 | MAR 25 | WK11 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 14/3/2025 : Cutover done 13/3/2025 : NE installation complete, FE installation WIP 12/3/2025 : SBC KJS - 45M Tower - NE site 2663B Kesas Bdr Puteri Klang, Digi OB - 30M 4 Legged Tower - FE site 1110A Berjaya Industrial Park | TSS+AA+TI | L1+ATP+PAC | 3X ISM8 CARD 1X RTN910 1X 18G 0.6M DP ANTENNA 1X 18G 1.2M DP ANTENNA 1x ODU 18G XMC3E SUB A HI 1X ODU 18G XMC3E SUB A LO 1x ODU 18G XMC3E SUB B HI 1X ODU 18G XMC3E SUB B LO | MW Parallel Link | MW PARALLEL LINK 2663B RTN01-1110A RTN09 WITH HUAWEI_18G_2+0_0.6M/1.2M_DP_112MHZ_256QAM_1556MBPS_XMC3E_SUB A & B_3.74KM_EPLA WITH EXISTING LINK 1+0 SHIFT IF CABLE EXISTING LINK 2663B-1110A TO NEW IDU SLOT 3 SHIFT IF CABLE CHILDSITE LINK 3051C-2663B TO NEW IDU SLOT 7 IMPACTED: 2935A, 2725B, 2672A, 3051C | 1. INSTALL NEW IDU RTN910A AND INSTALL 2PCS ISM8 AT SLOT 3 & 4 2. INSTALL NEW ODU 18G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 0.6M DP ANTENNA 5. SHIFT IF CABLE EXISTING LINK 2663B-1110A TO NEW IDU SLOT 3 4. CONFIGURE NEW LINK 18G 2+0 112MHZ 256QAM AT SLOT 4 AND EPLA WITH EXISTING LINK 6. SHIFT IF CABLE CHILDSITE LINK 3051C-2663B TO NEW IDU SLOT 7 | 1. REUSE EXISTING IDU RTN910A AND INSTALL 1PCS ISM8 AT SLOT 3 2. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 3. INSTALL NEW 18G 1.2M DP ANTENNA 4. CONFIGURE NEW LINK 18G 2+0 112MHZ 256QAM AT SLOT 3 AND EPLA WITH EXISTING LINK 5. PATCH TO NEW CP PORT AND DO PORT UPGRADE | XMC3E | MAC | 18G | 0.6 | 1.2 | GCI | SQ202503190656-GCI | GCI | SQ202503200144-GCI // SQ202503200149-GCI // SQ202504150088-GCI | 2025-12-25 | 2026-01-05 | Completed | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250306B2 |  | 2025-03-07 | 2025-03-15 | Completed | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-13 | 2025-03-19 | 2025-03-12 | 2025-03-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-13 | 2025-03-19 | 2025-03-12 | 2025-03-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | GCI TI | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-14 | 2025-03-13 | 2025-03-19 | 2025-03-12 | 2025-03-15 | SALEEM//MUHAMMAD ZAHID/6800000208 | 2025-03-13 | 2025-03-19 | 2025-03-12 | 2025-03-13 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | NG HONG JIE7018000036 | Logistic Team | 2025-05-08 | 2025-06-08 | 2025-05-08 | 2025-05-08 | ASTI//GANIS PUTRIANI/6237001358 | GCI_AA | SQ202510300160-GCI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
1034B_LOS_1 | Tmn Len Seng Cheras | DU00006591521 | Central | Kuala Lumpur | 3.070022 | 101.749426 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB B HI 1x ODU 18G XMC5D SUB B LO | MW New Link / Reroute | MW NEW LINK/REROUTE 1034B-W00677 WITH HUAWEI_18G_1+0_0.6M/0.6M_MDD_112MHZ_512QAM_889MBPS_XMC5D_SUB_B_LINK_2.22KM IMPACTED: 1034B DISMANTLE EXISTING LINK 1034B-3219B TX ROUTE(BEFORE): 1034B/1034B-3219B-2448A TX ROUTE(AFTER): 1034B/1034B-W00677 | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 1034B-3219B | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK 1034B-3219B 6. PATCH TO NEW CP PORT | XMC5D | MDD | 18G | 0.6 | 0.6 | GTSB | SQ202602050394-GTSB | GTSB | SQ202602090100-GTSB // SQ202602090103-GTSB | 2026-02-25 | 2026-02-12 | Completed | 2026-02-11 | 2026-02-25 | 2026-02-11 | 2026-02-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-11 | 2026-02-25 | 2026-02-11 | 2026-02-11 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-11 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26020513 |  | 2026-02-06 | 2026-02-07 | Completed | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-07 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-24 | 2026-02-28 | 2026-02-24 | 2026-03-05 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-02-24 | 2026-02-28 | 2026-02-24 | 2026-03-05 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | AKMAL//BIN RAZALI/6794000078 |  | 2026-02-27 | 2026-02-24 | 2026-02-28 | 2026-02-24 | 2026-03-18 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-03-05: 2026-02-24; 2025-03-05: 2026-02-28; 2025-03-05: 2026-02-24; 2025-03-07: 2026-02-26 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202602120113-GCI | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
2002B_LOS | ​Country Homes 2 | DU00006400487 | Central | Selangor | 3.328190 | 101.526990 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_112M. 2002B , 1331H. NE_2002B 23G_SP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A_Lo x1. FE_3256A 23G_SP_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A_Hi x1. | MW New Link / Reroute | Link Reroute to new FE 3256A due to existing FE being LOS Block. Install new MW link with config 23G_1+0_112M. Site Impacted : 2002B , 1331H. NE_2002B 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7-ISM8-1+0.( RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Enable GE1 , ETH patching existing NLOS , carry 1331H. 6.Traffic migrate to new MW link and New FE routing. 7.Decom existing SM link ( 2002B-2432A MW1). FE_3256A 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Enable GE1 , ETH patching to existing 3256A_RTN03_GE1. 6.Traffic migrate to new MW link and New FE routing. 7.Decom existing SM link (2432A-2002B MW1). | Link Reroute to new FE 3256A due to existing FE being LOS Block. Install new MW link with config 23G_1+0_112M. Site Impacted : 2002B , 1331H. NE_2002B 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7-ISM8-1+0.( RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Enable GE1 , ETH patching existing NLOS , carry 1331H. 6.Traffic migrate to new MW link and New FE routing. 7.Decom existing SM link ( 2002B-2432A MW1). | Link Reroute to new FE 3256A due to existing FE being LOS Block. Install new MW link with config 23G_1+0_112M. Site Impacted : 2002B , 1331H. FE_3256A 1.Install new 23G_SP_0.6M(MAC). 2.Install new RTN910A , 7_ISM8-1+0.(RTN no provide by OPS team). 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect. 5.Enable GE1 , ETH patching to existing 3256A_RTN03_GE1. 6.Traffic migrate to new MW link and New FE routing. 7.Decom existing SM link (2432A-2002B MW1). | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202512160952-GTSB | GTSB | SQ202512160942-GTSB // SQ202512160947-GTSB | 2026-01-23 | 2026-01-22 | Completed | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-17 | 2025-12-31 | 2025-12-17 | 2025-12-17 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121312 |  | 2026-01-14 | 2025-12-18 | Completed | 2025-12-13 | 2026-01-14 | 2025-12-13 | 2025-12-18 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-18 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-19 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-18 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-22 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-19 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170715-GCI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | CHEONG/SENG/WAH/7018000306
Q00122_IPR | ​Q117A_Q00122OD_CB_TMSPAOH | DU00006400488 | Sarawak | Sarawak | 1.536516 | 111.490485 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New SFP Module 1.25G/1G 1310nm 10Km x2.(For IDU Huawei & Cisco Router) New Optical Patchcord with suitable type and length x1. | MW IDU Patching | Perform re-engineering by doing migration at Q00122 RTN910AF(NEID 82-33382) of existing HW MW Link_ID SW03506, Q00977-Q00122. Site Impacted: Q00997/9259P ONLY. NE_Q00122 1.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into port 8-EM6-5 of RTN910AF(NEID 82-33382). Enable port. 2.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into new port Gi0/0/4 of Cisco Router(PTN ID 30209). Enable port. 3.Patching port 8-EM6-5 of RTN910AF(NEID 82-33382) and new port Gi0/0/4 of Cisco Router(PTN ID 30209). 4.Request new xC Vlan services for traffic Q00997/9259P ONLY. 5.Divert traffics Q00997/9259P ONLY to new port of port Gi0/0/4 of Cisco Router(PTN ID 30209). | Perform re-engineering by doing migration at Q00122 RTN910AF(NEID 82-33382) of existing HW MW Link_ID SW03506, Q00977-Q00122. Site Impacted: Q00997/9259P ONLY. NE_Q00122 1.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into port 8-EM6-5 of RTN910AF(NEID 82-33382). Enable port. 2.Insert new Optical SFP Module 1.25G/1G 1310nm 10Km into new port Gi0/0/4 of Cisco Router(PTN ID 30209). Enable port. 3.Patching port 8-EM6-5 of RTN910AF(NEID 82-33382) and new port Gi0/0/4 of Cisco Router(PTN ID 30209). 4.Request new xC Vlan services for traffic Q00997/9259P ONLY. 5.Divert traffics Q00997/9259P ONLY to new port of port Gi0/0/4 of Cisco Router(PTN ID 30209). | [6 empty] | Allstar | SQ202601150559-Allstar | Allstar | SQ202601080404-Allstar |  |  | Ongoing | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-21 | 2026-04-27 | 2026-04-21 | 2026-04-21 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25122954 |  | 2025-12-31 | 2026-01-03 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-03 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-19 | 2026-01-13 | 2026-01-13 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-13 | 2026-01-19 | 2026-02-27 | 2026-02-27 | ROYSTON//AHHOLE/6000038561 | Allstar TI | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-13 | 2026-01-13 | 2026-01-19 | 2026-03-01 | 2026-03-01 | ROYSTON//AHHOLE/6000038561 | 2025-12-17: 2026-01-13; 2025-12-17: 2026-01-19; 2025-12-17: 2026-02-27; 2025-12-19: 2026-02-27 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202512180102-GTSB
Q00509-Q00268 | MYY BTU TRUNK | DU00003661301 | Sarawak | Sarawak | 3.497000 | 113.580100 |  | DEC 24 |  | JUN 25 |  |  | ZTE | 06. Other Issue | 24/9/2025 : Plan to do MW Swap - Team do NIC at same site 19/9/2025 : Plan to do MW Swap - Cancel proceed due to material not match with solution 20/9: Pending Site BoM. Req regional to verifty on materials availability | TSS+AA+TI |  | 13G_4+0_28M_256QAM_EPLA NE_Q00509 New 13G_1.2M(MDD)+ Dual Coupler x1. New RTN910AF x1. New ISM8 x1. New XMC_5D, Sub A&B_Hi x1. New CAT6 cable x2. New IF Cable with suitable length x4 Run. FE_Q00268 New 13G_1.8M(MDD)+ Dual Coupler x1. New RTN910AF x1. New ISM8 x1. New XMC_5D, Sub A&B_Lo x1. New Optical SFP Module 1G/1.25G 10Km 1310nm(at RTN and Cisco) x2. New Optical Patch Cord with suitable type and length x1. New IF Cable with suitable length x4 Run. | MW Parallel Link | ***IMPORTANT NOTE:*** 1.PHYSICAL FREQ SCANNING REQUIRE IN ORDER TO OBTAIN FREE CHANNEL FROM INTERFERENCES. Existing HW MW Link Q00509-Q00268, 4+0 combination 7G_2+0_28MHZ_2048QAM_454 & 13G_2+0_28MHZ_512QAM_414 with 2x antenna. Build new HW MW Parallel Link Q00509-Q00268, 13G_4+0_28MHZ_256QAM_EPLA and perform Load Balancing Traffic in between existing HW MW Link and New HW MW Link. Do not decom existing HW MW Link Q00509-Q00268, 4+0 combination 7G_2+0_28MHZ_2048QAM_454 & 13G_2+0_28MHZ_512QAM_414 with 2x antenna. Site Impacted : Q00268 & Q00509. Be careful at Cisco Q00268 having existing EB connectivity such as Q02113(PEKAKA ESTATE EB), Q02116(SDP CHARTQUEST ESTATE EB) & Q00757(PPB PALM OIL SAREMAS). NE_Q00509 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF x1 and insert new ISM8 x1 into slot 03 of new RTN910AF. 3.Install new XMC_5D, Sub A&B_Hi x1. 4.Build HW MW Parallel Link Q00509-Q00268, 13G_4+0_28MHZ_256QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910AF. 6.Enable port 8-EM6-2 of new RTN910AF. 7.Shifting BBU Q00509 from existing RTN910AF(NEID 35136) to port 8-EM6-1 of new RTN910AF of new HW MW Parallel Link Q00509-Q00268. 8.Disable port 8-EM6-2 of existing RTN910AF(NEID 35136). 9.Disconnect existing cascade between port 8-EM6-5 of existing RTN910AF(NEID 21675) & port 8-EM6-5 of existing RTN910AF(NEID 35136). 10.Disable port 8-EM6-5 of existing RTN910AF(NEID 35136). 11.Perform cascading between port 8-EM6-1 of existing RTN910AF(NEID 21675) and port 8-EM6-2 of new RTN910AF. 12.Request new Vlan DCN and new Vlan Services for traffic Q00509 & Q00675 ONLY as these traffic will backhaul via HW MW Parallel Link Q00509-Q00268, 13G_4+0_28MHZ_256QAM_EPLA. 13.Be careful at Cisco Q00268 having existing EB connectivity such as Q02113(PEKAKA ESTATE EB), Q02116(SDP CHARTQUEST ESTATE EB) & Q00757(PPB PALM OIL SAREMAS). FE_Q00268 1.Install new 13G_1.8M(MDD)+Dual Coupler x1. 2.Install new RTN910AF x1 and insert new ISM8 x1 into slot 03 of new RTN910AF. 3.Install New XMC_5D, Sub A&B_Lo x1. 4.Build HW MW Parallel Link Q00509-Q00268, 13G_4+0_28MHZ_256QAM_EPLA. 5.Enable port 8-EM6-5 of new RTN910AF and insert new Optical SFP Module 1.25G 10Km 1310nm. 6.Request from ZTE IPRAN team for new port at existing Cisco/PTN and insert new Optical SFP Module 1G 10Km 1310nm. 7.Patching port 8-EM6-5 of new RTN910AF and new port at existing Cisco/PTN. 8.Request new Vlan DCN and new Vlan Services for traffic Q00509 & Q00675 ONLY. 9.Be careful at Cisco Q00268 having existing EB connectivity such as Q02113(PEKAKA ESTATE EB), Q02116(SDP CHARTQUEST ESTATE EB) & Q00757(PPB PALM OIL SAREMAS). | ***IMPORTANT NOTE:*** 1.PHYSICAL FREQ SCANNING REQUIRE IN ORDER TO OBTAIN FREE CHANNEL FROM INTERFERENCES. Existing HW MW Link Q00509-Q00268, 4+0 combination 7G_2+0_28MHZ_2048QAM_454 & 13G_2+0_28MHZ_512QAM_414 with 2x antenna. Build new HW MW Parallel Link Q00509-Q00268, 13G_4+0_28MHZ_256QAM_EPLA and perform Load Balancing Traffic in between existing HW MW Link and New HW MW Link. Do not decom existing HW MW Link Q00509-Q00268, 4+0 combination 7G_2+0_28MHZ_2048QAM_454 & 13G_2+0_28MHZ_512QAM_414 with 2x antenna. Site Impacted : Q00268 & Q00509. Be careful at Cisco Q00268 having existing EB connectivity such as Q02113(PEKAKA ESTATE EB), Q02116(SDP CHARTQUEST ESTATE EB) & Q00757(PPB PALM OIL SAREMAS). NE_Q00509 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF x1 and insert new ISM8 x1 into slot 03 of new RTN910AF. 3.Install new XMC_5D, Sub A&B_Hi x1. 4.Build HW MW Parallel Link Q00509-Q00268, 13G_4+0_28MHZ_256QAM_EPLA. 5.Enable port 8-EM6-1 of new RTN910AF. 6.Enable port 8-EM6-2 of new RTN910AF. 7.Shifting BBU Q00509 from existing RTN910AF(NEID 35136) to port 8-EM6-1 of new RTN910AF of new HW MW Parallel Link Q00509-Q00268. 8.Disable port 8-EM6-2 of existing RTN910AF(NEID 35136). 9.Disconnect existing cascade between port 8-EM6-5 of existing RTN910AF(NEID 21675) & port 8-EM6-5 of existing RTN910AF(NEID 35136). 10.Disable port 8-EM6-5 of existing RTN910AF(NEID 35136). 11.Perform cascading between port 8-EM6-1 of existing RTN910AF(NEID 21675) and port 8-EM6-2 of new RTN910AF. 12.Request new Vlan DCN and new Vlan Services for traffic Q00509 & Q00675 ONLY as these traffic will backhaul via HW MW Parallel Link Q00509-Q00268, 13G_4+0_28MHZ_256QAM_EPLA. 13.Be careful at Cisco Q00268 having existing EB connectivity such as Q02113(PEKAKA ESTATE EB), Q02116(SDP CHARTQUEST ESTATE EB) & Q00757(PPB PALM OIL SAREMAS). | ***IMPORTANT NOTE:*** 1.PHYSICAL FREQ SCANNING REQUIRE IN ORDER TO OBTAIN FREE CHANNEL FROM INTERFERENCES. Existing HW MW Link Q00509-Q00268, 4+0 combination 7G_2+0_28MHZ_2048QAM_454 & 13G_2+0_28MHZ_512QAM_414 with 2x antenna. Build new HW MW Parallel Link Q00509-Q00268, 13G_4+0_28MHZ_256QAM_EPLA and perform Load Balancing Traffic in between existing HW MW Link and New HW MW Link. Do not decom existing HW MW Link Q00509-Q00268, 4+0 combination 7G_2+0_28MHZ_2048QAM_454 & 13G_2+0_28MHZ_512QAM_414 with 2x antenna. Site Impacted : Q00268 & Q00509. Be careful at Cisco Q00268 having existing EB connectivity such as Q02113(PEKAKA ESTATE EB), Q02116(SDP CHARTQUEST ESTATE EB) & Q00757(PPB PALM OIL SAREMAS). FE_Q00268 1.Install new 13G_1.8M(MDD)+Dual Coupler x1. 2.Install new RTN910AF x1 and insert new ISM8 x1 into slot 03 of new RTN910AF. 3.Install New XMC_5D, Sub A&B_Lo x1. 4.Build HW MW Parallel Link Q00509-Q00268, 13G_4+0_28MHZ_256QAM_EPLA. 5.Enable port 8-EM6-5 of new RTN910AF and insert new Optical SFP Module 1.25G 10Km 1310nm. 6.Request from ZTE IPRAN team for new port at existing Cisco/PTN and insert new Optical SFP Module 1G 10Km 1310nm. 7.Patching port 8-EM6-5 of new RTN910AF and new port at existing Cisco/PTN. 8.Request new Vlan DCN and new Vlan Services for traffic Q00509 & Q00675 ONLY. 9.Be careful at Cisco Q00268 having existing EB connectivity such as Q02113(PEKAKA ESTATE EB), Q02116(SDP CHARTQUEST ESTATE EB) & Q00757(PPB PALM OIL SAREMAS). | XMC-5D | MDD | 13G | 13G_1.2M(MDD)+ Dual Coupler x1 | 13G_1.8M(MDD)+ Dual Coupler x1 | Datasco | SQ202412040275-Datasco | Trintel | SQ202510090481-Trintel // SQ202511260571-Trintel | 2025-02-28 | 2025-02-27 | Completed | 2024-12-04 | 2024-12-05 | 2024-12-13 | 2024-12-13 | HERALD GELMA ANAK JIFFERY7019000017 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-02-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-02-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-02-27 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY241120A2 |  | 2024-11-21 | 2025-04-07 | Completed | 2024-11-20 | 2024-11-21 | 2024-11-20 | 2025-04-07 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-08 | 2025-05-08 | 2025-10-30 | 2025-10-30 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI | 2025-04-08 | 2025-05-08 | 2025-10-29 | 2026-01-07 | MOHAMAD//HAMDI BIN HAMAT/7667000003 | Trintel TI |  |  |  |  | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-05-03 | AINA MARINI//ATON/6794000115 | 2025-12-17: 2025-04-08; 2025-12-17: 2025-05-08; 2025-12-17: 2025-10-30; 2025-12-19: 2025-10-30
1423H_AD | 99 Speedmart TMN MIDAH 2 | DU00006394388 | Central | Kuala Lumpur | 3.103160 | 101.732200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | FE_W01116 1.New CAT6 cable with suitable length(IDU HW NLOS to Cisco) x1. 2.Request electrical SFP Module for Cisco Router x1. (NLOS only have electrical interface) | MW IDU Patching | Perform MW IDU(NLOS) Patching at FE W01116. Site Impacted : 1423H. FE_W01116 1.Disconnect/remove cascading fromexisting HW MW Link 1996A-1465A and existing 1423H-NLOS-1996A. In which in cascading between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-48038) and port 2-EG3-3(NLOS PE). 2.Perform new patching port 2-EG3-3(NLOS PE) and port Gi0/0/2 of existing xC PTN_ID 70194. 3.Request new xC Vlan DCN & Vlan Services for NLOS 1423H from ZTE IPRAN team. 4.Migrate NLOS 1423H traffic to new port Gi0/0/2 of existing xC PTN_ID 70194. |  | Perform MW IDU(NLOS) Patching at FE W01116. Site Impacted : 1423H. FE_W01116 1.Disconnect/remove cascading fromexisting HW MW Link 1996A-1465A and existing 1423H-NLOS-1996A. In which in cascading between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-48038) and port 2-EG3-3(NLOS PE). 2.Perform new patching port 2-EG3-3(NLOS PE) and port Gi0/0/2 of existing xC PTN_ID 70194. 3.Request new xC Vlan DCN & Vlan Services for NLOS 1423H from ZTE IPRAN team. 4.Migrate NLOS 1423H traffic to new port Gi0/0/2 of existing xC PTN_ID 70194. | [5 empty] | GCI | SQ202601210056-GCI | GCI | SQ202601150338-GCI | 2026-02-27 | 2026-02-23 | Completed | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011218 |  | 2026-01-13 | 2026-01-14 | Completed | 2026-01-12 | 2026-01-13 | 2026-01-12 | 2026-01-14 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-12 | 2026-01-19 | 2026-01-12 | 2026-01-21 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-12 | 2026-01-19 | 2026-01-12 | 2026-01-21 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-23 | 2026-01-12 | 2026-01-19 | 2026-01-12 | 2026-01-24 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-12-17: 2026-01-12; 2025-12-17: 2026-01-19; 2025-12-17: 2026-01-12; 2025-12-19: 2026-01-12 |  |  | 2026-04-26 | 2026-05-24 | 2026-04-26 | 2026-04-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202512180092-GTSB
K00978_LOS | K005C_K00978OD_BDRAMANJAYA_SP | DU00006394389 | Northern | Kedah | 5.668080 | 100.522220 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1x ODU 23G XMC3E SUB A LO | MW New Link / Reroute | MW NEW LINK REROUTE K00978-4798C WITH HUAWEI_23G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM_954MBPS_XMC3E_SUB_A_LINK_1.85KM IMPACTED: K00978 DISMANTLE EXISTING LINK K00978-K00253 | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING K00978-K00253 | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING K00978-K00253 | XMC3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202512300376-GTSB | GTSB | SQ202601160508-GTSB // SQ202601160515-GTSB | 2026-01-31 | 2026-01-22 | Completed | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-21 | 2026-01-22 | 2026-01-21 | 2026-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26011531 |  | 2026-01-16 | 2026-01-17 | Completed | 2026-01-15 | 2026-01-16 | 2026-01-15 | 2026-01-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-02-13 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-02-13 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-22 | 2026-01-19 | 2026-01-31 | 2026-01-19 | 2026-02-11 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2025-12-17: 2026-01-19; 2025-12-17: 2026-01-31; 2025-12-17: 2026-01-19; 2025-12-19: 2026-01-20 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202512170724-GCI | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q02330_AD | Kampung Muara Sawai | DU00006407167 | Sarawak | Sarawak | 2.503340 | 111.708990 | [7 empty] | 00. Integrated/RFS Done | 10/12/2025 : Cutover done 9/12/025 : Pointing WIP 8/12/2025 : Plan to do MW IDU Patching - Cancel due team go survey site Redtone | TSS+TI | L1+ATP+PAC | FE_9375B/Q00585 New CAT6 cable x2. | MW IDU Patching | ****IMPORTANT NOTE: 1.MANDATORY FOR ENSURE SACOFA LL(9375B-LL-9368A) HAVING SUFFICIENT CAPACITY BEFORE PERFORM DIVERTING TRAFFIC Q02330 TO 9375B-LL-9368A**** Perform MW IDU Patching at FE 9375B/Q00585. Site Impacted : Q02330. FE_9375B/Q00585 1.Disconnect/remove existing xC Cisco/PTN Q00585 from port 8-EM6-1 of existing RTN910AF(NEID 82-22330) of HW MW Link Q00585-Q00585-02_HBAU_Project. 2.Enable port 8-EM6-2 of existing RTN910AF(NEID 82-22330). 3.Enable port 4-EG4-3 of existing RTN910AF(NEID 9-20364). 4.Perform new patching port 8-EM6-2 of existing RTN910AF(NEID 82-22330) and port 4-EG4-3 of existing RTN910AF(NEID 9-20364). 5.Request new xD Vlan DCN & Vlan Services for Q02330 from ZTE IPRAN team. 6.Migrate Q02330 traffic to existing IBeam port at CP(9368A) in which similar to traffics such as 9375B, 9048Z & 9038H. |  | ****IMPORTANT NOTE: 1.MANDATORY FOR ENSURE SACOFA LL(9375B-LL-9368A) HAVING SUFFICIENT CAPACITY BEFORE PERFORM DIVERTING TRAFFIC Q02330 TO 9375B-LL-9368A**** Perform MW IDU Patching at FE 9375B/Q00585. Site Impacted : Q02330. FE_9375B/Q00585 1.Disconnect/remove existing xC Cisco/PTN Q00585 from port 8-EM6-1 of existing RTN910AF(NEID 82-22330) of HW MW Link Q00585-Q00585-02_HBAU_Project. 2.Enable port 8-EM6-2 of existing RTN910AF(NEID 82-22330). 3.Enable port 4-EG4-3 of existing RTN910AF(NEID 9-20364). 4.Perform new patching port 8-EM6-2 of existing RTN910AF(NEID 82-22330) and port 4-EG4-3 of existing RTN910AF(NEID 9-20364). 5.Request new xD Vlan DCN & Vlan Services for Q02330 from ZTE IPRAN team. 6.Migrate Q02330 traffic to existing IBeam port at CP(9368A) in which similar to traffics such as 9375B, 9048Z & 9038H. | [5 empty] | Trintel | SQ202512170187-Trintel | Trintel | SQ202512170184-Trintel |  |  | Ongoing | 2025-12-09 | 2026-03-31 | 2025-12-09 | 2026-03-04 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-17 | 2026-03-24 | 2026-03-17 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  |  | 2025-12-01 | 2025-12-01 | Completed | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | KENNY//CARLSON ANAK PETER/6000058860 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-09 | 2025-12-31 | 2025-12-09 | 2025-12-09 | KENNY//CARLSON ANAK PETER/6000058860 |  | 2025-12-09 | 2025-12-31 | 2025-12-09 | 2026-03-06 | KENNY//CARLSON ANAK PETER/6000058860 |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-03-04 | MOHAMMAD//IZWAN BIN ANUAR/7667000024 | 2025-12-17: 2026-03-06; 2025-12-17: 2026-03-07; 2025-12-17: 2026-03-06; 2025-12-19: 2026-03-06 |  |  | 2025-12-23 | 2026-01-23 | 2025-12-23 | 2025-12-23 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GTSB | SQ202512180102-GTSB
4272A_1_HU | Permatang Bera 2 | DU00005386213 | Northern | Penang | 5.509877 | 100.384527 | [5 empty] | TI WIP | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M_256QAM_CA&EPLA LINK 2 NE_4272A New 15G_1.2M(MDD) x1. New ISM8 x1. New XMC_5D, Sub B_Hi x1. FE_4276A New 15G_1.2M(MDD) x1. New ISM8 x1. New XMC_5D, Sub B_Lo x1. | MW Parallel Link | Adding new MW parallel Link HW(LINK 1 - 15G_4+0_28M_256QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_256QAM_CA&EPLA) and final become 15G_6+0_28M_256QAM_CA&EPLA with total capacity 1200Mbps. Perform LAG for 2x 1G port at IBeam. LINK 1 use 4272A_HU and LINK 2 use 4272A_1_HU. 2 separate DU will be created. Site Impacted : 4272A & 4286A. LINK 2 NE_4272A 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN04). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_256QAM_CA&EPLA. 5.Do not decom existing HW MW Link 4272A(RTN11)-4276A(RTN11) as its still backhauling existing traffic for child site 4631D ONLY. FE_4276A 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN05). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_256QAM_CA&EPLA. 5.Do not decom existing HW MW Link 4272A(RTN11)-4276A(RTN11) as its still backhauling existing traffic for child site 4631D ONLY. | Adding new MW parallel Link HW(LINK 1 - 15G_4+0_28M_256QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_256QAM_CA&EPLA) and final become 15G_6+0_28M_256QAM_CA&EPLA with total capacity 1200Mbps. Perform LAG for 2x 1G port at IBeam. LINK 1 use 4272A_HU and LINK 2 use 4272A_1_HU. 2 separate DU will be created. Site Impacted : 4272A & 4286A. LINK 2 NE_4272A 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN04). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_256QAM_CA&EPLA. 5.Do not decom existing HW MW Link 4272A(RTN11)-4276A(RTN11) as its still backhauling existing traffic for child site 4631D ONLY. | Adding new MW parallel Link HW(LINK 1 - 15G_4+0_28M_256QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_256QAM_CA&EPLA) and final become 15G_6+0_28M_256QAM_CA&EPLA with total capacity 1200Mbps. Perform LAG for 2x 1G port at IBeam. LINK 1 use 4272A_HU and LINK 2 use 4272A_1_HU. 2 separate DU will be created. Site Impacted : 4272A & 4286A. LINK 2 FE_4276A 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN05). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_256QAM_CA&EPLA. 5.Do not decom existing HW MW Link 4272A(RTN11)-4276A(RTN11) as its still backhauling existing traffic for child site 4631D ONLY. | XMC_5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | CCSMY | SQ202504280454-CCS | CCSMY | SQ202505240083-CCS // SQ202505240104-CCS | 2025-12-04 | 2025-11-27 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-21 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | ainfatinainfatin28@gmail.com |  |  | 1.00 | Unassigned | Completed |  | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-11-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25042973 |  | 2025-04-30 | 2025-05-19 | Completed | 2025-04-29 | 2025-04-30 | 2025-04-29 | 2025-05-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-22 | 2025-05-31 | 2025-05-22 | 2025-06-04 | Muhammad Afiq Bin Mat Jalil7539000007 | CCS TI | 2025-05-22 | 2025-05-31 | 2025-05-22 | 2025-07-11 | Muhammad Afiq Bin Mat Jalil7539000007 | CCS TI | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2025-05-22 | 2025-05-31 | 2025-05-22 | 2026-03-31 | Muhammad Afiq Bin Mat Jalil7539000007 | 2025-12-17: 2025-05-22; 2025-12-17: 2025-05-31; 2025-12-17: 2025-05-22; 2025-12-19: 2025-07-04 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB_AA | SQ202510300144-GTSB
A00505_HU_1 | A040D_A00505OD_CB_KGBLANGKOR_RCC | DU00005591141 | Northern | Perak | 4.371803 | 101.058007 | [7 empty] | 00. Integrated/RFS Done | 04/07: CO Done | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0-28M to become 15G_6+0_28M with EPLA 15G_4+0_28M under DU Code DU00005180195. NE_A00505 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Lo x1. FE_A00155. 15G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub B_Hi x1. | MW Swap | Existing SM link 13G_4+0_28M_XPIC Swap existing SM link to 15G_2+0-28M to become 15G_6+0_28M with EPLA 15G_4+0_28M under DU Code DU00005180195. Site Impacted : A00505. NE_A00505 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Lo for ant 1. 4.Create service cross connect and EPLA. 7.BBU patching to new link. 8.Decom existing SM link (NT04994).Ensure no other traffic carry with existing SM link before decom. FE_A00155. 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Hi for ant 1. 4.Create service cross connect and EPLA. 5.Create new In band DCN. 6.Traffic migrate to new link. 7.Decom existing SM link (NT04994).Ensure no other traffic carry with existing SM link before decom. | Existing SM link 13G_4+0_28M_XPIC Swap existing SM link to 15G_2+0-28M to become 15G_6+0_28M with EPLA 15G_4+0_28M under DU Code DU00005180195. Site Impacted : A00505. NE_A00505 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Lo for ant 1. 4.Create service cross connect and EPLA. 7.BBU patching to new link. 8.Decom existing SM link (NT04994).Ensure no other traffic carry with existing SM link before decom. | Existing SM link 13G_4+0_28M_XPIC Swap existing SM link to 15G_2+0-28M to become 15G_6+0_28M with EPLA 15G_4+0_28M under DU Code DU00005180195. Site Impacted : A00505. FE_A00155. 1.Install new 15G_DP_1.2M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Hi for ant 1. 4.Create service cross connect and EPLA. 5.Create new In band DCN. 6.Traffic migrate to new link. 7.Decom existing SM link (NT04994).Ensure no other traffic carry with existing SM link before decom. | XMC_5D | MDD | 15G | 1.2 | 1.2 | Magicell | SQ202507080855-Magicell | Magicell | SQ202507020676-Magicell // SQ202507020682-Magicell | 2026-01-20 | 2026-01-19 | Completed | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  |  | 2025-07-02 | 2025-07-21 | Completed | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-21 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-07-21 | 2025-07-22 | 2025-07-21 | 2025-07-21 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AKMAL//BIN RAZALI/6794000078 |  | 2025-07-04 | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-19 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-12 | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | NG HONG JIE7018000036 | Logistic Team | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202506050639-GCI | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | CHEONG/SENG/WAH/7018000306
1320H_AD | 99 Speedmart SAUJANA UTAMA | DU00006771317 | Central | Selangor | 3.202358 | 101.484400 | [9 empty] | TSS+TI |  | ETH cat g cable x1 | MW IDU Patching | Patching NLOS FE to B00616 xC backhaul |  | Patching NLOS FE to B00616 xC backhaul | [5 empty] | GTSB | SQ202605070527-GTSB | GTSB | SQ202605070523-GTSB |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26050110 |  | 2026-05-04 |  | Ongoing | 2026-05-01 | 2026-05-04 | 2026-05-01 |  | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280391-GCI | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | CHEONG/SENG/WAH/7018000306
K00228_HU | K010A_K00228OD_CB_SUNGAITIANG | DU00005495381 | Northern | Kedah | 5.967481 | 100.555200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_28M_128QAM_CA&EPLA LINK 2 NE_K00228 New 15G_1.2M(MDD) x1. New ISM8 x1. New XMC_5D, Sub B_Hi x1. FE_K00258 New 15G_1.2M(MDD) x1. New ISM8 x1. New XMC_5D, Sub B_Lo x1. | MW Swap | Existing SM Link 13G_2+0_28MHz_2048QAM_LAG(NT04824) Swap existing link with new MW HW(LINK 1 - 15G_4+0_28M_128QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_128QAM_CA&EPLA) and final become 15G_6+0_28M_128QAM_CA&EPLA with total capacity 1038Mbps. Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). LINK 1 use K00228_HU and LINK 2 use K00228_HU_1. Therefore, 2 separate DU will be created. Site Impacted : K00228. LINK 1 NE_K00228 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub A_Hi. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN01). Configure it. 5.Configure CA & EPLA for LINK 1 & LINK 2(see below) and become 15G_6+0_28MHz_128QAM_CA&EPLA. 6.Please configure modulation 128QAM ONLY for all channels. 7.Configure DCN Inband. 8.Enable port 8-EM6-2 of RTN910A(RTN01) and patching to BBU K00228. 9.Migrate RAN Traffics(K00228)traffic to new HW MW link 15G_6+0_28MHz_128QAM_CA&EPLA. Configure it. 10.Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). FE_K00258 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub A_Lo. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN01). Configure it. 5.Configure CA & EPLA for LINK 1 & LINK 2(see below) and become 15G_6+0_28MHz_128QAM_CA&EPLA. 6.Please configure modulation 128QAM ONLY for all channels. 7.Configure DCN Inband. 8.Later, perform cascading in between port 8-EM6-1 of existing RTN910A(RTN01) & LAN port 2 of existing SM Link K00258-K00149(NT05523). Configure it. 9.Migrate RAN Traffics(K00228)traffic to new HW MW link 15G_6+0_28MHz_128QAM_CA&EPLA. Configure it. 10.Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). LINK 2 NE_K00228 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_128QAM_CA&EPLA. 5.Please configure modulation 128QAM ONLY for all channels. 6.Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). FE_K00258 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_128QAM_CA&EPLA. 5.Please configure modulation 128QAM ONLY for all channels. 6.Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). | Existing SM Link 13G_2+0_28MHz_2048QAM_LAG(NT04824) Swap existing link with new MW HW(LINK 1 - 15G_4+0_28M_128QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_128QAM_CA&EPLA) and final become 15G_6+0_28M_128QAM_CA&EPLA with total capacity 1038Mbps. Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). LINK 1 use K00228_HU and LINK 2 use K00228_HU_1. Therefore, 2 separate DU will be created. Site Impacted : K00228. LINK 1 NE_K00228 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub A_Hi. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN01). Configure it. 5.Configure CA & EPLA for LINK 1 & LINK 2(see below) and become 15G_6+0_28MHz_128QAM_CA&EPLA. 6.Please configure modulation 128QAM ONLY for all channels. 7.Configure DCN Inband. 8.Enable port 8-EM6-2 of RTN910A(RTN01) and patching to BBU K00228. 9.Migrate RAN Traffics(K00228)traffic to new HW MW link 15G_6+0_28MHz_128QAM_CA&EPLA. Configure it. 10.Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). | Existing SM Link 13G_2+0_28MHz_2048QAM_LAG(NT04824) Swap existing link with new MW HW(LINK 1 - 15G_4+0_28M_128QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_128QAM_CA&EPLA) and final become 15G_6+0_28M_128QAM_CA&EPLA with total capacity 1038Mbps. Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). LINK 1 use K00228_HU and LINK 2 use K00228_HU_1. Therefore, 2 separate DU will be created. Site Impacted : K00228. LINK 1 FE_K00258 1.Install new 15G_1.2M(MDD) x1. 2.Install new 1xRTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub A_Lo. Configure it. 4.Insert new ISM8 x1 into slot 03 of RTN910A(RTN01). Configure it. 5.Configure CA & EPLA for LINK 1 & LINK 2(see below) and become 15G_6+0_28MHz_128QAM_CA&EPLA. 6.Please configure modulation 128QAM ONLY for all channels. 7.Configure DCN Inband. 8.Later, perform cascading in between port 8-EM6-1 of existing RTN910A(RTN01) & LAN port 2 of existing SM Link K00258-K00149(NT05523). Configure it. 9.Migrate RAN Traffics(K00228)traffic to new HW MW link 15G_6+0_28MHz_128QAM_CA&EPLA. Configure it. 10.Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). | XMC_5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | GCI | SQ202505240071-GCI | GCI | SQ202505190405-GCI // SQ202505190415-GCI | 2026-03-20 | 2026-03-17 | Completed | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-20 | 2026-03-13 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250507AS |  | 2025-05-08 | 2025-05-13 | Completed | 2025-05-07 | 2025-05-08 | 2025-05-07 | 2025-05-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-05-19 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-07-06 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-16 | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2026-02-24 | MOHD FAIZ BIN MD YUNUS6800000186 | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2026-02-14 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | NG HONG JIE7018000036 | Logistic Team | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB_AA | SQ202510300144-GTSB
4403B_HU | Simpang Dua Manjung-100Q4 | DU00005495382 | Northern | Perak | 4.200910 | 100.723720 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [8 empty] | Magicell | No PR required-Site drop/cancel | Magicell | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [25 empty] | 2025-08-04: 2026-02-04; 2025-08-04: 2026-02-04; 2025-08-04: 2026-02-04; 2025-08-04: 2026-02-04 | NG HONG JIE7018000036 | Logistic Team | [5 empty] | GTSB | SQ202506050646-GTSB | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | MAZELAN BIN RAMLI6798000096
K00228_HU_1 | K010A_K00228OD_CB_SUNGAITIANG | DU00005495383 | Northern | Kedah | 5.967481 | 100.555200 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M_128QAM_CA&EPLA LINK 1 NE_K00228 New 15G_1.2M(MDD) x1. New RTN910A x1. New ISM8 x1. New XMC_5D, Sub A_Hi x1. FE_K00258 New 15G_1.2M(MDD) x1. New RTN910A x1. New ISM8 x1. XMC_5D, Sub A_Lo x1. | MW Swap | Existing SM Link 13G_2+0_28MHz_2048QAM_LAG(NT04824) Swap existing link with new MW HW(LINK 1 - 15G_4+0_28M_128QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_128QAM_CA&EPLA) and final become 15G_6+0_28M_128QAM_CA&EPLA with total capacity 1038Mbps. Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). LINK 1 use K00228_HU and LINK 2 use K00228_HU_1. Therefore, 2 separate DU will be created. Site Impacted : K00228. LINK 2 NE_K00228 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_128QAM_CA&EPLA. 5.Please configure modulation 128QAM ONLY for all channels. 6.Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). FE_K00258 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_128QAM_CA&EPLA. 5.Please configure modulation 128QAM ONLY for all channels. 6.Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). | Existing SM Link 13G_2+0_28MHz_2048QAM_LAG(NT04824) Swap existing link with new MW HW(LINK 1 - 15G_4+0_28M_128QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_128QAM_CA&EPLA) and final become 15G_6+0_28M_128QAM_CA&EPLA with total capacity 1038Mbps. Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). LINK 1 use K00228_HU and LINK 2 use K00228_HU_1. Therefore, 2 separate DU will be created. Site Impacted : K00228. LINK 2 NE_K00228 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_128QAM_CA&EPLA. 5.Please configure modulation 128QAM ONLY for all channels. 6.Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). | Existing SM Link 13G_2+0_28MHz_2048QAM_LAG(NT04824) Swap existing link with new MW HW(LINK 1 - 15G_4+0_28M_128QAM_CA&EPLA + LINK 2 - 15G_2+0_28M_128QAM_CA&EPLA) and final become 15G_6+0_28M_128QAM_CA&EPLA with total capacity 1038Mbps. Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). LINK 1 use K00228_HU and LINK 2 use K00228_HU_1. Therefore, 2 separate DU will be created. Site Impacted : K00228. LINK 2 FE_K00258 1.Install new 15G_1.2M(MDD) x1. 2.Insert new ISM8 x1 into slot 04 of RTN910A(RTN01). Configure it. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Configure CA & EPLA for LINK 1(see above) & LINK 2 and become 15G_6+0_28MHz_128QAM_CA&EPLA. 5.Please configure modulation 128QAM ONLY for all channels. 6.Do not decom existing SM MW Link K00228-K00258(NT04824) if still backhauling existing traffic for child site K00364. May ONLY proceed decom existing SM MW Link K00228-K00258(NT04824) if K00364 already MOCN and replaced by its pair colo(4676B). | XMC_5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | GCI | SQ202505240071-GCI | GCI | SQ202505190405-GCI // SQ202505190415-GCI |  |  | Ongoing | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-26 | 2026-04-02 | 2026-05-04 | 2026-05-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250507AT |  | 2025-05-08 | 2025-05-13 | Completed | 2025-05-07 | 2025-05-08 | 2025-05-07 | 2025-05-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-05-19 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2025-07-06 | MOHD FAIZ BIN MD YUNUS6800000186 | GCI TI | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-05-16 | 2025-05-15 | 2025-05-31 | 2025-05-15 | 2026-02-14 | MOHD FAIZ BIN MD YUNUS6800000186 | 2025-07-02: 2025-05-15; 2025-07-02: 2025-05-31; 2025-07-02: 2025-05-15; 2025-07-12: 2026-02-14 |  |  | 2025-06-19 | 2025-06-30 | 2025-06-19 | 2025-06-19 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB_AA | SQ202510300144-GTSB
4390A_HU | Jalan Segari-Damai Laut RCC | DU00006331656 | Northern | Perak | 4.282510 | 100.628940 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_55M_256QAM_EPLA NE_4390A New 18G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN01 - NEID 9-41080). New ISM8 x1. New XMC_5D, Sub A_Lo x1. FE_4407B New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01 - NEID 99-41081). New ISM8 x1. New XMC_5D, Sub A_Lo x1. | MW Parallel Link | Existing HW MW Link 4390A-4407B, 15G_3+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA. Later, combine existing HW MW Link 4390A-4407B, 15G_3+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA become 4390A-4407B, 15G&18G_5+0_28MHZ&56MHZ_512QAM&256QAM_EPLA. Site Impacted : 4390A & 4030C. NE_4390A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01 - NEID 9-41080). Insert new ISM8 into slot 04. 3.Install new XMC_5D, Sub A_Hi x1. 4.Build new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA. 5.Later, combine existing HW MW Link 4390A-4407B, 15G_3+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA become 4390A-4407B, 15G&18G_5+0_28MHZ&56MHZ_512QAM&256QAM_EPLA. FE_4407B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01 - NEID 99-41081). Insert new ISM8 into slot 04. 3.Install new XMC_5D, Sub A_Lo x1. 4.Build new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA. 5.Later, combine existing HW MW Link 4390A-4407B, 15G_3+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA become 4390A-4407B, 15G&18G_5+0_28MHZ&56MHZ_512QAM&256QAM_EPLA. | Existing HW MW Link 4390A-4407B, 15G_3+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA. Later, combine existing HW MW Link 4390A-4407B, 15G_3+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA become 4390A-4407B, 15G&18G_5+0_28MHZ&56MHZ_512QAM&256QAM_EPLA. Site Impacted : 4390A & 4030C. NE_4390A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN01 - NEID 9-41080). Insert new ISM8 into slot 04. 3.Install new XMC_5D, Sub A_Hi x1. 4.Build new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA. 5.Later, combine existing HW MW Link 4390A-4407B, 15G_3+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA become 4390A-4407B, 15G&18G_5+0_28MHZ&56MHZ_512QAM&256QAM_EPLA. | Existing HW MW Link 4390A-4407B, 15G_3+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA. Later, combine existing HW MW Link 4390A-4407B, 15G_3+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA become 4390A-4407B, 15G&18G_5+0_28MHZ&56MHZ_512QAM&256QAM_EPLA. Site Impacted : 4390A & 4030C. FE_4407B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01 - NEID 99-41081). Insert new ISM8 into slot 04. 3.Install new XMC_5D, Sub A_Lo x1. 4.Build new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA. 5.Later, combine existing HW MW Link 4390A-4407B, 15G_3+0_28MHZ_512QAM_EPLA and new HW MW Parallel Link 4390A-4407B, 18G_2+0_55MHZ_256QAM_EPLA become 4390A-4407B, 15G&18G_5+0_28MHZ&56MHZ_512QAM&256QAM_EPLA. | XMC-5D | MDD | 18G | 18G_1.2M(MDD) x1. | 18G_0.6M(MDD) x1. | GCI | SQ202512170161-GCI | GCI | SQ202512020089-GCI // SQ202512020091-GCI | 2026-01-14 | 2026-01-07 | Completed | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251125B6 |  | 2025-12-26 | 2025-11-28 | Completed | 2025-11-25 | 2025-12-26 | 2025-11-25 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-06 | 2025-12-11 | 2025-12-06 | 2025-12-13 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2025-12-06 | 2025-12-11 | 2025-12-06 | 2025-12-13 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-08 | 2025-12-06 | 2025-12-11 | 2025-12-06 | 2025-12-19 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2025-07-02: 2025-12-06; 2025-07-02: 2025-12-11; 2025-07-02: 2025-12-06; 2025-07-12: 2025-12-08 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280932-GTSB
7343B_HU | Kg Kebayu | DU00006331657 | Sabah | Sabah | 6.142600 | 116.448910 | [7 empty] | 04. Pending DO |  | TSS+AA+TI |  | 13G_4+0_28M_512QAM_CA NE_7343B New 13G_1.2M(MDD) x1. New RTN910AF(RTN02). New ISM8 x1. New XMC_5D Pro, Sub B_Hi x1. New IF cables with suitable length x2 RUN. New CAT6 cable x1. FE_7980B New 13G_1.2M(MDD) x1. New RTN910AF(RTN04). New ISM8 x1. New XMC_5D Pro, Sub B_Lo x1. New CAT6 cable x1. New IF cables with suitable length x2 RUN. | MW Parallel Link | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE FOR MOUNTING 1.2M ANTENNA DISH SIZE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY**** Existing HW MW Link 7343B-7980B, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7343B-7980B, 13G_4+0_28M_512QAM_CA. Site Impacted : 7343B. NE_7343B 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN02) and insert ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Parallel Link 7343B-7980B, 13G_4+0_28MHZ_512QAM_CA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Enable port 8-EM6-1 of new RTN910AF(RTN02). 6.Shifting and patching existing BBU 7343B from port 17-EG6-1 of existing RTN950A(RTN01, NEID 9-19248) to port 8-EM6-1 of new RTN910AF(RTN02). 7.Re-use existing xD Vlan services. 8.Migrate 7343B via new HW MW Parallel Link 7343B-7980B, 13G_4+0_28MHZ_512QAM_CA. FE_7980B 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04) and insert ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Lo x2. Build new HW MW Parallel Link 7343B-7980B, 13G_4+0_28MHZ_512QAM_CA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Enable port 8-EM6-1 of new RTN910AF(RTN04). 6.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-38136). 7.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN04) and port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-38136). 8.Re-use existing xD Vlan services. 9.Migrate 7343B via existing IBeam port at CP 7000A. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE FOR MOUNTING 1.2M ANTENNA DISH SIZE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY**** Existing HW MW Link 7343B-7980B, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7343B-7980B, 13G_4+0_28M_512QAM_CA. Site Impacted : 7343B. NE_7343B 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN02) and insert ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Parallel Link 7343B-7980B, 13G_4+0_28MHZ_512QAM_CA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Enable port 8-EM6-1 of new RTN910AF(RTN02). 6.Shifting and patching existing BBU 7343B from port 17-EG6-1 of existing RTN950A(RTN01, NEID 9-19248) to port 8-EM6-1 of new RTN910AF(RTN02). 7.Re-use existing xD Vlan services. 8.Migrate 7343B via new HW MW Parallel Link 7343B-7980B, 13G_4+0_28MHZ_512QAM_CA. | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE FOR MOUNTING 1.2M ANTENNA DISH SIZE. 2.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY**** Existing HW MW Link 7343B-7980B, 13G_4+0_28MHZ_512QAM_EPLA. Build new HW MW Parallel Link 7343B-7980B, 13G_4+0_28M_512QAM_CA. Site Impacted : 7343B. FE_7980B 1.Install new 13G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04) and insert ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Lo x2. Build new HW MW Parallel Link 7343B-7980B, 13G_4+0_28MHZ_512QAM_CA. 4.Lay new IF cable with suitable length and type x2 RUN. 5.Enable port 8-EM6-1 of new RTN910AF(RTN04). 6.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-38136). 7.Perform cascading between port 8-EM6-1 of new RTN910AF(RTN04) and port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-38136). 8.Re-use existing xD Vlan services. 9.Migrate 7343B via existing IBeam port at CP 7000A. | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD) x1. | 13G_1.2M(MDD) x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202511280936-GTSB
7349C_HU | Kampung Bawang | DU00006331658 | Sabah | Sabah | 6.126227 | 116.285630 | [7 empty] | 00. Integrated/RFS Done |  | NA | PAC |  | MW Remote Upgrade | Link Existing HW 15G_2+0_28MHZ_512QAM_EPLA & existing HW 13G_1+0_28MHZ_512QAM. MW Remote Upgrade by perform EPLA for existing HW 15G_2+0_28MHZ_512QAM_EPLA & existing HW 13G_1+0_28MHZ_512QAM, become HW 13G&15G_3+0_28MHZ_512QAM_EPLA. Site Impacted : 7349C. NE_7349C 1.MW Remote Upgrade by perform EPLA for existing HW 15G_2+0_28MHZ_512QAM_EPLA(Slot 07 of RTN910AF-RTN01, NEID 9-43538) & existing HW 13G_1+0_28MHZ_512QAM(Slot 04 of RTN910AF-RTN01, NEID 9-43538). 2.Become HW 13G&15G_3+0_28MHZ_512QAM_EPLA. FE_7032C 1.MW Remote Upgrade by perform EPLA for existing HW 15G_2+0_28MHZ_512QAM_EPLA(Slot 07 of RTN910AF-RTN01, NEID 9-43184) & existing HW 13G_1+0_28MHZ_512QAM(Slot 04 of RTN910AF-RTN01, NEID 9-43184). 2.Become HW 13G&15G_3+0_28MHZ_512QAM_EPLA. | Link Existing HW 15G_2+0_28MHZ_512QAM_EPLA & existing HW 13G_1+0_28MHZ_512QAM. MW Remote Upgrade by perform EPLA for existing HW 15G_2+0_28MHZ_512QAM_EPLA & existing HW 13G_1+0_28MHZ_512QAM, become HW 13G&15G_3+0_28MHZ_512QAM_EPLA. Site Impacted : 7349C. NE_7349C 1.MW Remote Upgrade by perform EPLA for existing HW 15G_2+0_28MHZ_512QAM_EPLA(Slot 07 of RTN910AF-RTN01, NEID 9-43538) & existing HW 13G_1+0_28MHZ_512QAM(Slot 04 of RTN910AF-RTN01, NEID 9-43538). 2.Become HW 13G&15G_3+0_28MHZ_512QAM_EPLA. | Link Existing HW 15G_2+0_28MHZ_512QAM_EPLA & existing HW 13G_1+0_28MHZ_512QAM. MW Remote Upgrade by perform EPLA for existing HW 15G_2+0_28MHZ_512QAM_EPLA & existing HW 13G_1+0_28MHZ_512QAM, become HW 13G&15G_3+0_28MHZ_512QAM_EPLA. Site Impacted : 7349C. FE_7032C 1.MW Remote Upgrade by perform EPLA for existing HW 15G_2+0_28MHZ_512QAM_EPLA(Slot 07 of RTN910AF-RTN01, NEID 9-43184) & existing HW 13G_1+0_28MHZ_512QAM(Slot 04 of RTN910AF-RTN01, NEID 9-43184). 2.Become HW 13G&15G_3+0_28MHZ_512QAM_EPLA. | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-25 | 2026-01-25 | 2026-01-25 | 2026-01-25 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-25 | [15 empty] | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511280936-GTSB
K01074_HU | K009A_K01074OD_Kg_Musa | DU00006331659 | Northern | Kedah | 6.231485 | 100.668723 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M_1024QAM_EPLA NE_K01074 New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN04, 220-41474). New ISM8 x1. New XMC_5D, Sub A_Hi x1. FE_4859B New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN02, 9-13570). New ISM8 x1. New XMC_5D, Sub A_Lo x1. | MW New Link / Reroute | ****IMPORTANT NOTE: DUE TO ALL RAN TRAFFICS STILL NOT MOCN YET (HW RAN BBU). THEREFORE, PERMANENT SOLUTION NEED TO IMPLEMENT BY DOING AS PER BELOW: 1.BUILD FIRST MW NEW LINK/REROUTE HW MW Link K01074-4859B AS PER BELOW MENTIONED. 2.IF CD/GOP DECIDE HW RAN CAN BE REPLACED BY ZTE RAN(MOCN), THUS NO POI LAYER 2 REQUIRED FROM XD TO XC HOST. AWAITING FEEDBACK FROM ZTE KK CHOW. 3.IF CD/GOP DECIDE TO STICK TO HW RAN (NO MOCNIZE), THUS ALL HW RAN TRAFFICS NEED TO DIVERT TO XC HOST BY USING POI LAYER 2.**** Existing HW MW Link K01074-K00406, 18G_2+0_55M_1024QAM_900M. Install MW New Link/Reroute HW MW Link K01074-4859B, 18G_2+0_110M_1024QAM_1908M_EPLA. Later, decom existing HW MW Link K01074-K00406, 18G_2+0_55M_1024QAM_900M. Site Impacted : K01074, K01072, K01070, K01068 & K01073. NE_K01074 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN04, 220-41474). Insert new ISM8 x1 into slot 04. 3.Install new XMC_5D, Sub A_Hi x1. Configure it. 4.Build new HW MW Link K01074-4859B, 18G_2+0_110M_1024QAM_1908M_EPLA. 5.Request new xD Vlan DCN & new Vlan services for traffics K01074, K01072, K01070, K01068 & K01073 from ZTE IPRAN Team. 6.Migrate traffics K01074, K01072, K01070, K01068 & K01073 to new HW MW Link K01074-4859B, 18G_2+0_110M_1024QAM_1908M_EPLA. 7.Later, decom existing HW MW Link K01074-K00406, 18G_2+0_55M_1024QAM_900M. FE_4859B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN02, 9-13570). Insert new ISM8 x1 into slot 03. 3.Install new XMC_5D, Sub A_Lo x1. Configure it. 4.Build new HW MW Link K01074-4859B, 18G_2+0_110M_1024QAM_1908M_EPLA. 5.Request new xD Vlan DCN & new Vlan services for traffics K01074, K01072, K01070, K01068 & K01073 from ZTE IPRAN Team. 6.Migrate traffics K01074, K01072, K01070, K01068 & K01073 to existing IBeam port at CP 4999A in which similar to existing traffics such as 4859B, 4025P, 4720B & 4426K. 7.Later, decom existing HW MW Link K01074-K00406, 18G_2+0_55M_1024QAM_900M. | ****IMPORTANT NOTE: DUE TO ALL RAN TRAFFICS STILL NOT MOCN YET (HW RAN BBU). THEREFORE, PERMANENT SOLUTION NEED TO IMPLEMENT BY DOING AS PER BELOW: 1.BUILD FIRST MW NEW LINK/REROUTE HW MW Link K01074-4859B AS PER BELOW MENTIONED. 2.IF CD/GOP DECIDE HW RAN CAN BE REPLACED BY ZTE RAN(MOCN), THUS NO POI LAYER 2 REQUIRED FROM XD TO XC HOST. AWAITING FEEDBACK FROM ZTE KK CHOW. 3.IF CD/GOP DECIDE TO STICK TO HW RAN (NO MOCNIZE), THUS ALL HW RAN TRAFFICS NEED TO DIVERT TO XC HOST BY USING POI LAYER 2.**** Existing HW MW Link K01074-K00406, 18G_2+0_55M_1024QAM_900M. Install MW New Link/Reroute HW MW Link K01074-4859B, 18G_2+0_110M_1024QAM_1908M_EPLA. Later, decom existing HW MW Link K01074-K00406, 18G_2+0_55M_1024QAM_900M. Site Impacted : K01074, K01072, K01070, K01068 & K01073. NE_K01074 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN04, 220-41474). Insert new ISM8 x1 into slot 04. 3.Install new XMC_5D, Sub A_Hi x1. Configure it. 4.Build new HW MW Link K01074-4859B, 18G_2+0_110M_1024QAM_1908M_EPLA. 5.Request new xD Vlan DCN & new Vlan services for traffics K01074, K01072, K01070, K01068 & K01073 from ZTE IPRAN Team. 6.Migrate traffics K01074, K01072, K01070, K01068 & K01073 to new HW MW Link K01074-4859B, 18G_2+0_110M_1024QAM_1908M_EPLA. 7.Later, decom existing HW MW Link K01074-K00406, 18G_2+0_55M_1024QAM_900M. | ****IMPORTANT NOTE: DUE TO ALL RAN TRAFFICS STILL NOT MOCN YET (HW RAN BBU). THEREFORE, PERMANENT SOLUTION NEED TO IMPLEMENT BY DOING AS PER BELOW: 1.BUILD FIRST MW NEW LINK/REROUTE HW MW Link K01074-4859B AS PER BELOW MENTIONED. 2.IF CD/GOP DECIDE HW RAN CAN BE REPLACED BY ZTE RAN(MOCN), THUS NO POI LAYER 2 REQUIRED FROM XD TO XC HOST. AWAITING FEEDBACK FROM ZTE KK CHOW. 3.IF CD/GOP DECIDE TO STICK TO HW RAN (NO MOCNIZE), THUS ALL HW RAN TRAFFICS NEED TO DIVERT TO XC HOST BY USING POI LAYER 2.**** Existing HW MW Link K01074-K00406, 18G_2+0_55M_1024QAM_900M. Install MW New Link/Reroute HW MW Link K01074-4859B, 18G_2+0_110M_1024QAM_1908M_EPLA. Later, decom existing HW MW Link K01074-K00406, 18G_2+0_55M_1024QAM_900M. Site Impacted : K01074, K01072, K01070, K01068 & K01073. FE_4859B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910A(RTN02, 9-13570). Insert new ISM8 x1 into slot 03. 3.Install new XMC_5D, Sub A_Lo x1. Configure it. 4.Build new HW MW Link K01074-4859B, 18G_2+0_110M_1024QAM_1908M_EPLA. 5.Request new xD Vlan DCN & new Vlan services for traffics K01074, K01072, K01070, K01068 & K01073 from ZTE IPRAN Team. 6.Migrate traffics K01074, K01072, K01070, K01068 & K01073 to existing IBeam port at CP 4999A in which similar to existing traffics such as 4859B, 4025P, 4720B & 4426K. 7.Later, decom existing HW MW Link K01074-K00406, 18G_2+0_55M_1024QAM_900M. | XMC_5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_0.6M(MDD) x1. | GTSB | SQ202512160971-GTSB | GTSB | SQ202512160957-GTSB // SQ202512160962-GTSB | 2026-03-20 | 2026-03-17 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-02-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-13 | 2026-03-20 | 2026-03-13 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121310 |  | 2026-01-14 | 2025-12-31 | Completed | 2025-12-13 | 2026-01-14 | 2025-12-13 | 2025-12-31 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-31 | 2026-01-09 | 2026-01-11 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-09 | 2026-01-31 | 2026-01-09 | 2026-01-17 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | AKMAL//BIN RAZALI/6794000078 |  |  | 2026-01-09 | 2026-01-31 | 2026-01-09 | 2026-03-03 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-07-02: 2026-01-09; 2025-07-02: 2026-01-31; 2025-07-02: 2026-01-09; 2025-07-12: 2026-01-12 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280932-GTSB
4947A_HU_2 | Kota Kuala Muda | DU00006331660 | Northern | Kedah | 5.589331 | 100.373029 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 2X LAN CABLE | MW IDU Patching | MW IDU PATCHING AT NE 4947A RTN01 (CARRY 4117R TRAFFIC) TO 4947A RTN02 IMPACTED SITE: 4117R | MW IDU PATCHING AT NE 4947A RTN01 (CARRY 4117R TRAFFIC) TO 4947A RTN02 IMPACTED SITE: 4117R | [6 empty] | GTSB | SQ202512160971-GTSB | GTSB | SQ202512010617-GTSB | 2026-01-22 | 2026-01-22 | Completed | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-17 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2026-01-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112662 |  | 2025-12-27 | 2025-11-28 | Completed | 2025-11-27 | 2025-12-27 | 2025-11-26 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-15 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-16 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2025-07-02: 2025-12-11; 2025-07-02: 2025-12-11; 2025-07-02: 2025-12-11; 2025-07-12: 2025-12-13 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280776-GCI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | EZRIN TASNIM BIN ABDUL GANI6798000128
S00770_HU | S097A_S00770OD_CB_BANDAUAUMKAR | DU00006331661 | Sabah | Sabah | 4.762655 | 117.829197 | [7 empty] | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202511280806-GCI
K00116_HU | K006B_K00116OD_ASUN | DU00006331662 | Northern | Kedah | 6.331120 | 100.420770 |  |  |  |  | 6/2: fe pending tm ptw(tmchanglun) 23/2: FE can enter after 2/3 |  |  | 05. Doable |  | TSS+AA+TI+Dismantle |  | 4X ISM8 CARD 2X RTN910A 2X 13G 1.8M MDD ANTENNA 1x ODU 13G XMC5D SUB B HI 1x ODU 13G XMC5D SUB B LO | MW Swap | MW PARALLEL UPGRADE LINK K00116-K00230 WITH HUAWEI_13G_4+0_1.8M/1.8M_MDD_28MHZ_512QAM_896MBPS_XMC5D_WITH CA_SUB_B_10.1KM IMPACTED: K00116 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 AT SLOT 3&4 2. INSTALL NEW 13G 1.8M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 AT SLOT 3&4 2. INSTALL NEW 13G 1.8M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB B 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO NEW CP PORT 6. DISMANTLE EXISTING LINK | XMC5D | MDD | 13G | 1.8 | 1.8 | GCI |  | GCI | SQ202512020089-GCI // SQ202512020091-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25112705 |  | 2025-12-27 | 2025-11-28 | Completed | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202511280776-GCI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
7666A_HU | Taman Mulia | DU00006331663 | Sabah | Sabah | 4.258611 | 117.908667 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_112M. NE_7666A. 18G_DP_0.6M(MDD). RTN910A x1 XMC_5D , Sub A_Lo x1. FE_7196A 18G_DP_1.2M(MDD) x1. ISM8 x1. XMC_5D , Sub A_Hi x1. | MW Swap | Existing link 18G_1+0_56M.Remote Software Not Support Swap existing link to 18G_2+0_112M. Site Impacted : 7057C , 7666A , 7117D , 7066C. NE_7666A. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching to existing 7666A_RTN02. 6.Enable GE2 , ETH patching to existing 7666A_RTN03. 7.All traffic migrate to new MW link. 8.Decom existing MW link (IDU , ODU and Ant). FE_7196A 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 910A_RTN12. 3.Install new 4_ISM8-2+0 into existing 910A_RTN12. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA. 6.All traffic migrate to new MW link. 7.Decom existing ANT and ODU only. | Existing link 18G_1+0_56M.Remote Software Not Support Swap existing link to 18G_2+0_112M. Site Impacted : 7057C , 7666A , 7117D , 7066C. NE_7666A. 1.Install new 18G_DP_0.6M(MDD). 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_5D , Sub A_Lo. 4.Create service cross connect and EPLA. 5.Enable GE1 , ETH patching to existing 7666A_RTN02. 6.Enable GE2 , ETH patching to existing 7666A_RTN03. 7.All traffic migrate to new MW link. 8.Decom existing MW link (IDU , ODU and Ant). | Existing link 18G_1+0_56M.Remote Software Not Support Swap existing link to 18G_2+0_112M. Site Impacted : 7057C , 7666A , 7117D , 7066C. FE_7196A 1.Install new 18G_DP_1.2M(MDD). 2.Reuse existing 910A_RTN12. 3.Install new 4_ISM8-2+0 into existing 910A_RTN12. 4.Install new XMC_5D , Sub A_Hi. 5.Create service cross connect and EPLA. 6.All traffic migrate to new MW link. 7.Decom existing ANT and ODU only. | XMC_5D | MDD | 18G | 0.6 | 1.2 | Seri Pancar | SQ202602040268-Seri Pancar | GTSB | SQ202602130249-GTSB // SQ202602130265-GTSB | 2026-02-28 | 2026-02-05 | Completed | 2026-02-04 | 2026-02-28 | 2026-02-04 | 2026-02-04 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26020457 |  | 2026-02-05 | 2026-02-10 | Completed | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-08 | 2026-02-28 | 2026-02-08 | 2026-02-10 | MOHD AIRELL SHAH6000044820 | GTSB TI | 2026-02-08 | 2026-02-28 | 2026-02-08 | 2026-02-10 | MOHD AIRELL SHAH6000044820 | GTSB TI | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-12 | 2026-02-08 | 2026-02-28 | 2026-02-08 | 2026-02-25 | MOHD AIRELL SHAH6000044820 | 2025-07-02: 2026-02-08; 2025-07-02: 2026-02-28; 2025-07-02: 2026-02-08; 2025-07-12: 2026-02-10 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202511280806-GCI | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | CHEONG/SENG/WAH/7018000306
4982B_HU_1 | Selarong Panjang | DU00006331664 | Northern | Kedah | 5.404690 | 100.686915 | [7 empty] | 04. Pending DO |  | TSS+AA+TI+Dismantle |  | 13G_4+0_28M_512QAM_EPLA(WO CA) NE_4982B New 13G_1.2M(MDD)+Dual Coupler x1. New RTN910AF(RTN04). New ISM8 x1. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x2. FE_K00416/4202K New 13G_1.2M(MDD)+Dual Coupler x1. New RTN910AF(RTN07). New ISM8 x1. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type x4 RUN. New CAT6 cable x1. | MW New Link / Reroute | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. BOTH DU K00416_HU_1 & DU 4982B_HU_1 PROPOSE TO USE 13GHZ CHANNEL. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K00416_HU_1. 2ND - DU 4982B_HU_1.**** Existing HW MW Link 4982B-4986A, 13G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Link 4982B-4202K/K00416, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). Later, decom existing HW MW Link 4982B-4986A, 13G_2+0_28MHZ_512QAM_EPLA. Site Impacted : 4982B & 4135R. NE_4982B 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN04) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel Link 4982B-4202K/K00416, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). 4.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN04). 5.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-23737). 6.Repatch BBU/RAN 4982B from 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-23737) to 8-EM6-1 of new RTN910AF(RTN04). 7.Perform cascading in between 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-23737) to 8-EM6-2 of new RTN910AF(RTN04). 8.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 9.Migrate traffics 4982B & 4135R into new HW MW Link 4982B-4202K/K00416, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). 10.Later, decom existing HW MW Link 4982B-4986A, 13G_2+0_28MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-23737) at 4982B(Re-used). FE_K00416/4202K 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN07) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel Link 4982B-4202K/K00416, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). 4.Enable port 8-EM6-1 of new RTN910AF(RTN07). 5.Enable port 8-EM6-1 of new RTN910AF(RTN06).(under DU K00416_HU_1) 6.Perform new cascading in between port 8-EM6-1 of new RTN910AF(RTN07) and port 8-EM6-1 of new RTN910AF(RTN06). 7.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 8.Migrate traffics 4982B & 4135R into new 2x electrical port of 1G(LAG) at IBeam CP 4968A. 9.Later, decom existing HW MW Link 4982B-4986A, 13G_2+0_28MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-23737) at 4982B(Re-used). | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. BOTH DU K00416_HU_1 & DU 4982B_HU_1 PROPOSE TO USE 13GHZ CHANNEL. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K00416_HU_1. 2ND - DU 4982B_HU_1.**** Existing HW MW Link 4982B-4986A, 13G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Link 4982B-4202K/K00416, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). Later, decom existing HW MW Link 4982B-4986A, 13G_2+0_28MHZ_512QAM_EPLA. Site Impacted : 4982B & 4135R. NE_4982B 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN04) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Build new HW MW Parallel Link 4982B-4202K/K00416, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). 4.Enable port 8-EM6-1 and 8-EM6-2 of new RTN910AF(RTN04). 5.Enable port 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-23737). 6.Repatch BBU/RAN 4982B from 8-EM6-1 of existing RTN910AF(RTN01, NEID 9-23737) to 8-EM6-1 of new RTN910AF(RTN04). 7.Perform cascading in between 8-EM6-2 of existing RTN910AF(RTN01, NEID 9-23737) to 8-EM6-2 of new RTN910AF(RTN04). 8.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 9.Migrate traffics 4982B & 4135R into new HW MW Link 4982B-4202K/K00416, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). 10.Later, decom existing HW MW Link 4982B-4986A, 13G_2+0_28MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-23737) at 4982B(Re-used). | ****IMPORTANT NOTE: 1.RECOMMENDED TO PERFORM FREQUENCY SCANNING FOR 13G CHANNELS IN ORDER TO ENSURE CHANNEL AVAILABILITY. BOTH DU K00416_HU_1 & DU 4982B_HU_1 PROPOSE TO USE 13GHZ CHANNEL. 2.MANDATORY TO PERFORM DU IN SEQUENCES AS PER BELOW: 1ST - DU K00416_HU_1. 2ND - DU 4982B_HU_1.**** Existing HW MW Link 4982B-4986A, 13G_2+0_28MHZ_512QAM_EPLA. Build new HW MW Link 4982B-4202K/K00416, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). Later, decom existing HW MW Link 4982B-4986A, 13G_2+0_28MHZ_512QAM_EPLA. Site Impacted : 4982B & 4135R. FE_K00416/4202K 1.Install new 13G_1.2M(MDD)+Dual Coupler x1. 2.Install new RTN910AF(RTN07) and insert ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Build new HW MW Parallel Link 4982B-4202K/K00416, 13G_4+0_28MHZ_512QAM_EPLA(WO CA). 4.Enable port 8-EM6-1 of new RTN910AF(RTN07). 5.Enable port 8-EM6-1 of new RTN910AF(RTN06).(under DU K00416_HU_1) 6.Perform new cascading in between port 8-EM6-1 of new RTN910AF(RTN07) and port 8-EM6-1 of new RTN910AF(RTN06). 7.Request new xD Vlan DCN and Vlan Services from ZTE IPRAN Team. 8.Migrate traffics 4982B & 4135R into new 2x electrical port of 1G(LAG) at IBeam CP 4968A. 9.Later, decom existing HW MW Link 4982B-4986A, 13G_2+0_28MHZ_512QAM_EPLA. Anyway, do not decom RTN910AF(RTN01, NEID 9-23737) at 4982B(Re-used). | XMC-5D Pro | MDD | 13G | 13G_1.2M(MDD)+Dual Coupler x1 | 13G_1.2M(MDD)+Dual Coupler x1 | GTSB | SQ202601130151-GTSB // SQ202605050382-GTSB | GTSB | SQ202601130143-GTSB // SQ202601130146-GTSB // SQ202601220771-GTSB // SQ202601220774-GTSB |  |  | Ongoing | 2026-01-31 | 2026-02-28 | 2026-01-31 | 2026-02-26 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-09 | 2026-04-16 | 2026-04-09 | 2026-04-09 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-21 | 2026-04-14 | 2026-04-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26012225 | Release DO for this site 22012026 //Material DM to CD USP 8055R | 2026-01-08 | 2026-01-17 | Completed | 2026-01-07 | 2026-01-08 | 2026-01-07 | 2026-01-17 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-17 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2026-01-31 | 2026-02-28 | 2026-01-31 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | [7 empty] | 2026-01-31 | 2026-02-28 | 2026-01-31 |  | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-07-02: 2026-01-31; 2025-07-02: 2026-02-28; 2025-07-02: 2026-01-31; 2025-07-12: 2026-02-13 | [7 empty] | GTSB | SQ202511280932-GTSB
K00874_HU | K005D_K00874OD_TMN_RIAMESRA2 | DU00006331665 | Northern | Kedah | 5.816265 | 100.539720 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_4+0_28M. NE_K00874 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Lo x1. ISM8 x2. FE_K00433 13G_DP_1.2M(MDD) x1. RTN910A x1. XMC_5D , Sub A_Hi x1. ISM8 x2. | MW Parallel Link | Existing link 15G_4+0_28M Install parallel link 13G_4+0_28M. Site Impacted : 4691D , K00874. NE_K00874 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new XMC_5D , Sub A_Lo. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , CA and EPLA. 6.Traffic BBU_K00874 migrate to new parallel link. 7.No MW link Decomm. FE_K00433 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new XMC_5D , Sub A_Hi 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , CA and EPLA. 6.Create New Inband DCN. 7.Traffic migrate to new parallel link. 8.No MW link Decomm. | Existing link 15G_4+0_28M Install parallel link 13G_4+0_28M. Site Impacted : 4691D , K00874. NE_K00874 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new XMC_5D , Sub A_Lo. 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , CA and EPLA. 6.Traffic BBU_K00874 migrate to new parallel link. 7.No MW link Decomm. | Existing link 15G_4+0_28M Install parallel link 13G_4+0_28M. Site Impacted : 4691D , K00874. FE_K00433 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. 3.Install new XMC_5D , Sub A_Hi 4.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 5.Create service cross connect , CA and EPLA. 6.Create New Inband DCN. 7.Traffic migrate to new parallel link. 8.No MW link Decomm. | XMC_5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202601210141-GCI | GCI | SQ202512020089-GCI // SQ202512020091-GCI | 2026-02-04 | 2026-02-05 | Completed | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112701 |  | 2025-12-27 | 2025-11-28 | Completed | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-18 | 2026-01-13 | 2026-01-16 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2026-01-13 | 2026-01-18 | 2026-01-13 | 2026-01-16 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-16 | 2026-01-13 | 2026-01-18 | 2026-01-13 | 2026-01-20 | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2025-07-02: 2026-01-13; 2025-07-02: 2026-01-18; 2025-07-02: 2026-01-13; 2025-07-12: 2026-01-13 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280776-GCI | 2025-11-26 | 2025-11-27 | 2025-11-26 | 2025-11-26 | CHEONG/SENG/WAH/7018000306
4688D_HU | Puteri Jaya 2 | DU00006331666 | Northern | Kedah | 5.608421 | 100.559054 |  |  |  |  | 6/2: power issue(site not yet handover to cd..rssi issue) |  |  | 05. Doable |  | TSS+AA+TI |  | 15G_2+0_28M_512QAM_EPLA NE_4688D New 15G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-27976). New ISM8 x1. New XMC_5D, Sub A_Hi x1. FE_4770A New 15G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN23, NEID 9-27977). New ISM8 x1. New XMC_5D, Sub A_Lo x1. | MW Parallel Link | Existing HW MW Link 4688D-4770A, 18G_1+0_55MHZ_512QAM. Build new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4688D-4770A, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. Site Impacted : 4688D. NE_4688D 1.Install new 15G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-27976). Insert ISM8 into slot 03. 3.Install new XMC_5D, Sub A_Hi x1. Build new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, perform combine existing HW MW Link 4688D-4770A, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. FE_4770A 1.Install new 15G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN23, NEID 9-27977). Insert ISM8 into slot 03. 3.Install new XMC_5D, Sub A_Lo x1. Build new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, perform combine existing HW MW Link 4688D-4770A, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. | Existing HW MW Link 4688D-4770A, 18G_1+0_55MHZ_512QAM. Build new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4688D-4770A, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. Site Impacted : 4688D. NE_4688D 1.Install new 15G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-27976). Insert ISM8 into slot 03. 3.Install new XMC_5D, Sub A_Hi x1. Build new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, perform combine existing HW MW Link 4688D-4770A, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. | Existing HW MW Link 4688D-4770A, 18G_1+0_55MHZ_512QAM. Build new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 4688D-4770A, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. Site Impacted : 4688D. FE_4770A 1.Install new 15G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN23, NEID 9-27977). Insert ISM8 into slot 03. 3.Install new XMC_5D, Sub A_Lo x1. Build new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, perform combine existing HW MW Link 4688D-4770A, 18G_1+0_55MHZ_512QAM and new HW MW Parallel Link 4688D-4770A, 15G_2+0_28MHZ_512QAM_EPLA. Become 18G&15G_3+0_55MHZ&28MHZ_512QAM_EPLA. | XMC-5D | MDD | 15G | 15G_0.6M(MDD) x1. | 15G_0.6M(MDD) x1. | GCI |  | GCI | SQ202512020089-GCI // SQ202512020091-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25112709 |  | 2025-12-27 | 2025-11-28 | Completed | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-16 | 2026-01-20 | 2026-01-16 |  | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | 2026-01-16 | 2026-01-20 | 2026-01-16 |  | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | GCI TI | [7 empty] | 2026-01-16 | 2026-01-20 | 2026-01-16 |  | AHMAD//HAIRUL HYKAL BIN AHMAD JOHAN/6800000184 | 2025-07-02: 2026-01-16; 2025-07-02: 2026-01-20; 2025-07-02: 2026-01-16 | [7 empty] | GTSB | SQ202511280932-GTSB
2189A8_HU | pBTS Kasuapan Village Gaya | DU00006331667 | Sabah | Sabah | 5.998360 | 116.061401 | [7 empty] | 05. Doable |  | TSS+AA+TI |  | 18G_1+0_112M. NE_2189A8. 18G_DP_0.6M(MDD) x1. XMC_5D , Sub B_Hi x1. FE_7814A. 18G_DP_0.6M(MDD) x1. XMC_5D , Sub B_Lo. | MW Parallel Link |  | Existing link 18G_1+0_112M Install parallel l link 18G_1+0_112M. Site Impacted 2189A8. NE_2189A8. 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 2189A8_RTN01 , 7_ISM8-1+0 Port 2. 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW EPLA link. 6.No MW to Decomm. | Existing link 18G_1+0_112M Install parallel l link 18G_1+0_112M. Site Impacted 2189A8. FE_7814A. 1.Install new 18G_DP_0.6M(MDD). 2.Reuse existing 7814A_RTN01 , 3_ISM8-1+0 Port 2. 3.Install new XMC_5D , Sub B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new MW EPLA link. 6.No MW to Decomm. | XMC_5D | MDD | 18G | 0.6 | 0.6 | NR services |  | NR services | SQ202603130155-NR Services // SQ202603130161-NR Services |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26020320 |  | 2026-02-04 | 2026-02-05 | Completed | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed | [40 empty] | GCI | SQ202511280806-GCI | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | CHEONG/SENG/WAH/7018000306
2679A14_HU | pBTS Kg Sijangkang | DU00006331668 | Central | Selangor | 2.945060 | 101.456420 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 1X RTN910A 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB B HI 1x ODU 18G XMC5D SUB B LO | MW Swap | MW SWAP UPGRADE LINK 2697A14-1923B WITH HUAWEI_18G_1+0_0.6M/0.6M_MDD_112MHZ_1024QAM_954MBPS_XMC5D_SUB_B_1.36KM IMPACTED: 2697A14 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU RTN910 SLOT 7 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK | XMC5D | MDD | 18G | 0.6 | 0.6 | GCI | SQ202512300488-GCI | GCI | SQ202512300458-GCI // SQ202512300465-GCI | 2026-01-14 | 2026-01-13 | Completed | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-13 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121672 |  | 2025-12-17 | 2025-12-19 | Completed | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-22 | 2025-12-29 | 2025-12-21 | 2025-12-27 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-22 | 2025-12-29 | 2025-12-21 | 2025-12-27 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-23 | 2025-12-22 | 2025-12-29 | 2025-12-21 | 2025-12-29 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-12-22 | 2025-12-29 | 2025-12-21 | 2025-12-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280798-GCI | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q01183_HU | Q120A_Q01183OD_T3_KUALAMATU | DU00006331669 | Sarawak | Sarawak | 2.639835 | 111.426032 | [9 empty] | TSS+AA+TI |  | 4X ISM8 CARD 2X RTN910A 2X 13G 1.8M MDD ANTENNA 1x ODU 13G XMC5D SUB A HI 1x ODU 13G XMC5D SUB A LO | MW Parallel Link | MW PARALLEL LINK Q01183-Q00659 WITH HUAWEI_13G_4+0_1.8M/1.8M_MDD_28MHZ_256QAM_800MBPS_XMC5D_SUB_A_WITH CA_LINK_12.20KM IMPACTED: 9046P/Q02299, Q02300 PATCH NEW LINK TO LL Q00659 PATCH IDU 9325K/Q01183_KUALA MATU - 9046P/Q02299_LEMANG PEK TO NEW LINK NEW LINK CARRY 9046P/Q02299, Q02300 | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 256QAM WITH CA 5. PATCH IDU 9325K/Q01183_KUALA MATU - 9046P/Q02299_LEMANG PEK TO NEW LINK | 1. INSTALL NEW IDU RTN910 AND 2PCS ISM8 CARD SLOT 3 & 4 2. INSTALL NEW 13G 1.8M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 4+0 28MHZ 512QAM WITH CA 5. PATCH TO NEW LL PORT 6. NEW LINK CARRY TRAFFIC 9046P/Q02299, Q02300 | XMC5D | MDD | 13G | 1.8 | 1.8 | Allstar | SQ202604100680-Allstar |  |  |  |  | Ongoing | 2026-04-08 | 2026-04-14 | 2026-04-08 | 2026-04-08 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-08 | 2026-04-15 | 2026-04-08 | 2026-04-08 | Roystonroy_23Roystonroy_23 |  |  | 1.00 | Unassigned | Completed |  | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-08 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-09 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202511280911-GCI | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | EZRIN TASNIM BIN ABDUL GANI6798000128
1148D_HU | Puchong Utama 7 | DU00006331670 | Central | Selangor | 2.981819 | 101.607902 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M_512QAM_EPLA NE_1148D New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-34491). New XMC_5D, Sub A_Hi x1. FE_1352B New 18G_10.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-42604). New XMC_5D, Sub A_Lo x1. | MW Swap | Existing HW MW Link_1148D-1352B, 23G_1+0_56MHZ_512QAM. MW Swap to HW MW Link 1148D-1352B, 18G_2+0_56MHZ_512QAM_EPLA. Later, decom existing antenna 23G and ODU 23G ONLY for existing HW MW Link_1148D-1352B, 23G_1+0_56MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. Site Impacted : 1148D. NE_1148D 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-34491) and reuse existing slot 07(port 1 & 2). 3.Install new XMC_5D, Sub A_Hi x1. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 1148D via new HW MW Link 1148D-1352B, 18G_2+0_56MHZ_512QAM_EPLA. 6.Later, decom existing antenna 23G and ODU 23G ONLY for existing HW MW Link_1148D-1352B, 23G_1+0_56MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. FE_1352B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-42604) and reuse existing slot 04(port 1 & 2). 3.Install new XMC_5D, Sub A_Lo x1. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 1148D via existing port at IBeam/CP 1372B. 6.Later, decom existing antenna 23G and ODU 23G ONLY for existing HW MW Link_1148D-1352B, 18G_1+0_56MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. | Existing HW MW Link_1148D-1352B, 23G_1+0_56MHZ_512QAM. MW Swap to HW MW Link 1148D-1352B, 18G_2+0_56MHZ_512QAM_EPLA. Later, decom existing antenna 23G and ODU 23G ONLY for existing HW MW Link_1148D-1352B, 23G_1+0_56MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. Site Impacted : 1148D. NE_1148D 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-34491) and reuse existing slot 07(port 1 & 2). 3.Install new XMC_5D, Sub A_Hi x1. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 1148D via new HW MW Link 1148D-1352B, 18G_2+0_56MHZ_512QAM_EPLA. 6.Later, decom existing antenna 23G and ODU 23G ONLY for existing HW MW Link_1148D-1352B, 23G_1+0_56MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. | Existing HW MW Link_1148D-1352B, 23G_1+0_56MHZ_512QAM. MW Swap to HW MW Link 1148D-1352B, 18G_2+0_56MHZ_512QAM_EPLA. Later, decom existing antenna 23G and ODU 23G ONLY for existing HW MW Link_1148D-1352B, 23G_1+0_56MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. Site Impacted : 1148D. FE_1352B 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 9-42604) and reuse existing slot 04(port 1 & 2). 3.Install new XMC_5D, Sub A_Lo x1. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 1148D via existing port at IBeam/CP 1372B. 6.Later, decom existing antenna 23G and ODU 23G ONLY for existing HW MW Link_1148D-1352B, 23G_1+0_56MHZ_512QAM. Anyway, existing RTN910AF at NE & FE will be re-used. | XMC_5D | MDD | 18G | 18G_0.6M(MADD) x1. | 18G_0.6M(MADD) x1. | GTSB | SQ202512160952-GTSB | GTSB | SQ202512160942-GTSB // SQ202512160947-GTSB | 2026-03-02 | 2026-02-23 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-02-03 | 2026-01-20 | 2026-01-20 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-01-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121311 |  | 2026-01-14 | 2025-12-31 | Completed | 2025-12-13 | 2026-01-14 | 2025-12-13 | 2025-12-31 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-13 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-13 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-13 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-02-25 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-13 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280921-GTSB
3050C8_HU | pBTS Lahar Tiang | DU00006331671 | Northern | Penang | 5.549750 | 100.479050 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X 18G 0.6M MAC ANTENNA 1x ODU 18G XMC3 SUB A HI 1x ODU 18G XMC3 SUB A LO | MW Swap | MW SWAP LINK 3050C-4279A WITH HUAWEI_18G_1+0_0.6M/0.6M_DP_112MHZ_256QAM_758MBPS_XMC3E_SUB_A_2.17KM IMPACTED: 3050C DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 0.6M MAC ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | 1. REUSE EXISTING IDU RTN910 2. INSTALL NEW 18G 0.6M MAC ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB A 4. CONFIGURE LINK 18G 1+0 112MHZ 256QAM 5. DISMANTLE EXISTING LINK | [5 empty] | GTSB | SQ202512160971-GTSB | GTSB | SQ202512160957-GTSB // SQ202512160962-GTSB | 2026-02-20 | 2026-02-25 | Completed | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-01-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-19 | 2026-02-20 | 2026-02-19 | 2026-02-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26010711 |  | 2026-01-08 | 2026-01-10 | Completed | 2026-01-07 | 2026-01-08 | 2026-01-07 | 2026-01-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-13 | AG KU NURULIKHSAN//BIN PG ANAPI/6799000310 | GTSB TI | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-01-13 | AG KU NURULIKHSAN//BIN PG ANAPI/6799000310 | GTSB TI | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-13 | 2026-01-12 | 2026-01-31 | 2026-01-12 | 2026-03-31 | AG KU NURULIKHSAN//BIN PG ANAPI/6799000310 | 2026-01-09: 2026-01-12; 2026-01-09: 2026-01-31; 2026-01-09: 2026-01-12; 2026-01-13: 2026-01-13 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280776-GCI | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q00238_HU | Q140C_Q00238OD_JLNCAUSEWAY | DU00006331672 | Sarawak | Sarawak | 2.290620 | 111.826040 | [9 empty] | TSS+AA+TI+Dismantle |  | 2X RTN910A 2X 23G 0.3M DP ANTENNA 1x ODU 23G XMC3E SUB B HI 1x ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP UPGRADE LINK Q00238-Q00181 WITH HUAWEI_23G_1+0_0.3M/0.3M_DP_112MHZ_1024QAM_954MBPS_XMC3E_SUB_B_0.31KM IMPACTED: Q00238 DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.3M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3 112MHZ SUB B 4. CONFIGURE LINK 23G 1+0 112MHZ 1024QAM 5. DISMANTLE EXISTING LINK 6. PATCH TO NEW CP PORT | XMC3E | MAC | 23G | 0.3 | 0.3 | Allstar | SQ202604220808-Allstar |  |  |  |  | Ongoing | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | ROYSTON//ANAK RAMSY/6798000228 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202511280911-GCI | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | EZRIN TASNIM BIN ABDUL GANI6798000128
7502B_HU | Ample valley | DU00006331673 | Sabah | Sabah | 5.598600 | 118.077200 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 18G_3+0_28M&110MHZ_512QAM&256QAM_EPLA MW Remote Upgrade for HW 18G_2+0_28M_512QAM_EPLA to HW 18G_2+0_55M_512QAM_EPLA. Site Impacted : 7502B, 7562B & 7242R. NE_7502B 1.MW Remote Upgrade for HW 18G_2+0_28M_512QAM_EPLA to HW 18G_2+0_55M_512QAM_EPLA. 2.Become new config as HW 18G_3+0_55M&110MHZ_512QAM&256QAM_EPLA FE_7583A 1.MW Remote Upgrade for HW 18G_2+0_28M_512QAM_EPLA to HW 18G_2+0_55M_512AM_EPLA. 2.Become new config as HW 18G_3+0_55M&110MHZ_512QAM&256QAM_EPLA | Link Existing HW 18G_3+0_28M&110MHZ_512QAM&256QAM_EPLA MW Remote Upgrade for HW 18G_2+0_28M_512QAM_EPLA to HW 18G_2+0_55M_2512QAM_EPLA. Site Impacted : 7502B, 7562B & 7242R. NE_7502B 1.MW Remote Upgrade for HW 18G_2+0_28M_512QAM_EPLA to HW 18G_2+0_55M_512QAM_EPLA. 2.Become new config as HW 18G_3+0_55M&110MHZ_512QAM&256QAM_EPLA | Link Existing HW 18G_3+0_28M&110MHZ_512QAM&256QAM_EPLA MW Remote Upgrade for HW 18G_2+0_28M_512QAM_EPLA to HW 18G_2+0_55M_512QAM_EPLA. Site Impacted : 7502B, 7562B & 7242R. FE_7583A 1.MW Remote Upgrade for HW 18G_2+0_28M_512QAM_EPLA to HW 18G_2+0_55M_512QAM_EPLA. 2.Become new config as HW 18G_3+0_55M&110MHZ_512QAM&256QAM_EPLA | [11 empty] | Not started | [7 empty] | 1.00 | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-12-09 | [15 empty] | 2025-12-24 | 2026-01-24 | 2025-12-24 | 2025-12-24 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511280936-GTSB
4457C_HU | Pekan Gurney | DU00006331674 | Northern | Perak | 4.224830 | 100.738505 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_110M_512QAM_EPLA NE_4457C New 18G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN02, 9-28158). New ISM8 x1. New XMC_5D, Sub A_Hi x1. FE_4939C New 18G_1.2M(MDD) x1. New RTN910AF(RTN04). New XMC_5D, Sub A_Lo x1. New CAT6 cable x1. | MW Parallel Link | Build new Parallel HW MW Link 18G_2+0_110M_512QAM_EPLA. Site Impacted : 4412D. NE_4457C 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02-NEID 9-28158). Insert new ISM8 x1 into slot 03. 3.Install new XMC_5D, Sub A_Hi x1. Build new Parallel HW MW Link 18G_2+0_110M_512QAM_EPLA. 4.Disconnect/remove existing cascading between port 8-EM6-3 of existing RTN910AF(RTN02-NEID 9-28158) and port 8-EM6-3 Of existing RTN910AF(RTN01-NEID 9-41694). 5.Disable both ports port 8-EM6-3 of existing RTN910AF(RTN02-NEID 9-28158) and port 8-EM6-3 Of existing RTN910AF(RTN01-NEID 9-41694). 6.Request new Vlan DCN and Vlan services. 7.Migrate traffic 4412D via new Parallel HW MW Link 18G_2+0_110M_512QAM_EPLA. FE_4939C 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04). 3.Install new XMC_5D, Sub A_Lo x1. Build new Parallel HW MW Link 18G_2+0_110M_512QAM_EPLA. 4.Enable port 8-EM6-1 of new RTN910AF(RTN04). 5.Request new IBeam port, new Vlan DCN & Vlan Services from ZTE IPRAN Team. 6.Patching port 8-EM6-1 of new RTN910AF(RTN04) to new IBeam port. 7.Migrate traffic 4412D via new port at IBeam. | Build new Parallel HW MW Link 18G_2+0_110M_512QAM_EPLA. Site Impacted : 4412D. NE_4457C 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN02-NEID 9-28158). Insert new ISM8 x1 into slot 03. 3.Install new XMC_5D, Sub A_Hi x1. Build new Parallel HW MW Link 18G_2+0_110M_512QAM_EPLA. 4.Disconnect/remove existing cascading between port 8-EM6-3 of existing RTN910AF(RTN02-NEID 9-28158) and port 8-EM6-3 Of existing RTN910AF(RTN01-NEID 9-41694). 5.Disable both ports port 8-EM6-3 of existing RTN910AF(RTN02-NEID 9-28158) and port 8-EM6-3 Of existing RTN910AF(RTN01-NEID 9-41694). 6.Request new Vlan DCN and Vlan services. 7.Migrate traffic 4412D via new Parallel HW MW Link 18G_2+0_110M_512QAM_EPLA. | Build new Parallel HW MW Link 18G_2+0_110M_512QAM_EPLA. Site Impacted : 4412D. FE_4939C 1.Install new 18G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN04). 3.Install new XMC_5D, Sub A_Lo x1. Build new Parallel HW MW Link 18G_2+0_110M_512QAM_EPLA. 4.Enable port 8-EM6-1 of new RTN910AF(RTN04). 5.Request new IBeam port, new Vlan DCN & Vlan Services from ZTE IPRAN Team. 6.Patching port 8-EM6-1 of new RTN910AF(RTN04) to new IBeam port. 7.Migrate traffic 4412D via new port at IBeam. | XMC_5D | MDD | 18G | 18G_1.2M(MDD) x1. | 18G_1.2M(MDD) x1. | GCI | SQ202512170161-GCI | GCI | SQ202512020089-GCI // SQ202512020091-GCI | 2026-01-26 | 2026-01-21 | Completed | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112657 |  | 2025-12-27 | 2025-11-28 | Completed | 2025-11-27 | 2025-12-27 | 2025-11-26 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-08 | 2025-12-13 | 2025-12-08 | 2025-12-13 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2025-12-08 | 2025-12-13 | 2025-12-08 | 2025-12-13 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | GCI TI | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-12 | 2025-12-08 | 2025-12-13 | 2025-12-08 | 2025-12-19 | MUHAMMAD MUAZ MUKMIN ABDUL HALIM6800000210 | 2026-01-09: 2025-12-08; 2026-01-09: 2025-12-13; 2026-01-09: 2025-12-08; 2026-01-13: 2025-12-10 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280932-GTSB
S00479_HU | S091A_S00479OD_LDGSANDAU | DU00006331675 | Sabah | Sabah | 5.203300 | 118.131700 | [7 empty] | 01. Pending Planning | [19 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202511280936-GTSB
1475C_HU | TAMAN HARUMANIS | DU00006331676 | Central | Selangor | 3.150712 | 101.439198 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910A 2X 18G 0.6M MDD ANTENNA 1x ODU 18G XMC5D SUB B HI 1x ODU 18G XMC5D SUB B LO | MW Swap | MW SWAP LINK 1475C-1085A WITH HUAWEI_18G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC5D_SUB_B_1.77KM IMPACTED: 1258H,1475C DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 18G 0.6M MDD ANTENNA 3. INSTALL NEW ODU 18G XMC5D 112MHZ SUB B 4. CONFIGURE LINK 18G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 2G 6. DISMANTLE EXISTING LINK EXCEPT IDU | XMC5D | MDD | 18G | 0.6 | 0.6 | GCI | SQ202512160937-GCI | GCI | SQ202512020081-GCI // SQ202512020084-GCI | 2025-12-16 | 2025-12-16 | Completed | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-15 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-16 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251125B0 |  | 2025-12-26 | 2025-11-28 | Completed | 2025-11-25 | 2025-12-26 | 2025-11-25 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-08 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-13 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | GCI TI | 2025-12-09 | 2025-12-09 | 2025-12-02 | 2025-12-09 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-09 | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-13 | UTHAYA//KUMAR AL CHANDRAN/6000059541 | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-08 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | NG HONG JIE7018000036 | Logistic Team | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280798-GCI | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | EZRIN TASNIM BIN ABDUL GANI6798000128
9164A_HU | Kg. Simboh | DU00006331677 | Sarawak | Sarawak | 1.322180 | 110.347960 | [9 empty] | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_55M_256QAM_EPLA NE_9164A New 18G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN03, NEID 9-24963). New XMC_5D, Sub A_Lo x1. FE_9313A New 18G_1.2M(MDD) x1. Re-use existing RTN910AF(RTN04, NEID 9-24964). New XMC_5D, Sub A_Hi x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Existing HW MW Link 9164A-9313A, 18G_1+0_55MHZ_512QAM_450. Build new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA. Later, combine existing HW MW Link 9164A-9313A, 18G_1+0_55MHZ_512QAM_450 & new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA become 18G_3+0_55MHZ_512QAM&256QAM_EPLA. Site Impacted : 9164A & 9352K. NE_9164A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN03, NEID 9-24963). Use existing ISM8 slot 07(Port 1 & 2). 3.Install new XMC_5D, Sub A_Lo x1. Build new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA. 4.Later, combine existing HW MW Link 9164A-9313A, 18G_1+0_55MHZ_512QAM_450 & new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_128QAM_EPLA become 18G_3+0_55MHZ_512QAM&256QAM_EPLA. FE_9313A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN04, NEID 9-24964). Use existing ISM8 slot 07(Port 1 & 2). 3.Install new XMC_5D, Sub A_Hi x1. Build new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA. 4.Later, combine existing HW MW Link 9164A-9313A, 18G_1+0_55MHZ_512QAM_450 & new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_128QAM_EPLA become 18G_3+0_55MHZ_512QAM&256QAM_EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Existing HW MW Link 9164A-9313A, 18G_1+0_55MHZ_512QAM_450. Build new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA. Later, combine existing HW MW Link 9164A-9313A, 18G_1+0_55MHZ_512QAM_450 & new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_128QAM_EPLA become 18G_3+0_55MHZ_512QAM&256QAM_EPLA. Site Impacted : 9164A & 9352K. NE_9164A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN03, NEID 9-24963). Use existing ISM8 slot 07(Port 1 & 2). 3.Install new XMC_5D, Sub A_Lo x1. Build new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA. 4.Later, combine existing HW MW Link 9164A-9313A, 18G_1+0_55MHZ_512QAM_450 & new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA become 18G_3+0_55MHZ_512QAM&256QAM_EPLA. | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE.**** Existing HW MW Link 9164A-9313A, 18G_1+0_55MHZ_512QAM_450. Build new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA. Later, combine existing HW MW Link 9164A-9313A, 18G_1+0_55MHZ_512QAM_450 & new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA become 18G_3+0_55MHZ_512QAM&256QAM_EPLA. Site Impacted : 9164A & 9352K. FE_9313A 1.Install new 18G_1.2M(MDD) x1. 2.Re-use existing RTN910AF(RTN04, NEID 9-24964). Use existing ISM8 slot 07(Port 1 & 2). 3.Install new XMC_5D, Sub A_Hi x1. Build new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA. 4.Later, combine existing HW MW Link 9164A-9313A, 18G_1+0_55MHZ_512QAM_450 & new HW MW Parallel Link 9164A-9313A, 18G_2+0_55MHZ_256QAM_EPLA become 18G_3+0_55MHZ_512QAM&256QAM_EPLA. | XMC_5D | MDD | 18G | 18G_1.2M(MDD) x1. | 18G_1.2M(MDD) x1. | Magicell | SQ202601210174-Magicell | Magicell | SQ202604150373-Magicell // SQ202604150378-Magicell |  |  | Ongoing | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-27 | 2026-04-03 | 2026-03-27 | 2026-03-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-08 | 2026-04-15 | 2026-04-08 | 2026-04-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26040831 |  | 2026-04-09 | 2026-04-13 | Completed | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-13 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-04-13 | 2026-04-30 | 2026-04-13 |  | MOHAMAD BIN KIPLI7018000212 | Magicell TI | 2026-04-13 | 2026-04-30 | 2026-04-13 |  | MOHAMAD BIN KIPLI7018000212 | Magicell TI | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-04-17 | 2026-04-13 | 2026-04-30 | 2026-04-13 |  | MOHAMAD BIN KIPLI7018000212 | 2026-01-09: 2026-04-13; 2026-01-09: 2026-04-30; 2026-01-09: 2026-04-13; 2026-01-13: 2026-04-14 | [7 empty] | GTSB | SQ202511280943-GTSB
4279A_HU | Pinang Tunggal (KJS) | DU00006331678 | Northern | Penang | 5.553310 | 100.498330 |  |  |  |  | 6/2: material at silan..need to pass to silan or wanisa 23/2: plan TI on 26/2 |  |  | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_4279A Re-use existing RTN910A(RTN03 NEID 9-41754). New ISM8 x1. IF cables with suitable length x2RUN(If existing not longer for terminating from existing RTN950A to existing RTN910A). | MW Re-engineering | ****IMPORTANT NOTE: DO NOT DECOM EXISTING HW MW LINK 23G_1+0_56M_512QAM AS PER REMARK IN NMS UNDER 1-ISV3-1.(NEED TO REMOVE THE REMARK)**** Existing HW MW link 23G_1+0_56M_512QAM & existing HW MW link 18G_1+0_55M_512QAM. MW Re-engineering required by perform EPLA between existing HW MW link 23G_1+0_56M_512QAM & existing HW MW link 18G_1+0_55M_512QAM. Site Impacted : 4279A, 4283A, 4289B & 3050C_8 NE_4279A 1.Insert new ISM8 x1 into slot 03 of RTN910A(RTN03 NEID 9-41754). 2.Shifting existing IF cables from 1-ISV3-1(HW MW link 23G_1+0_56M_512QAM) of existing RTN950A(RTN02, NEID 9-13948) and terminate into slot 03(Port 1) of RTN910A(RTN03 NEID 9-41754). 3.Shifting existing IF cables from 2-ISV3-1(HW MW link 18G_1+0_56M_512QAM) of existing RTN950A(RTN02, NEID 9-13948) and terminate into slot 03(Port 2) of RTN910A(RTN03 NEID 9-41754). 4.If existing IF cables not sufficient for shifting into RTN910A(RTN03 NEID 9-41754). Please lay new IF cables. 5.Later, perform EPLA in between slot 03(Port 1 & 2) of RTN910A(RTN03 NEID 9-41754). FE_4294A 1.Perform EPLA in between port 1(HW MW link 23G_1+0_56M_512QAM) & 2(HW MW link 18G_1+0_55M_512QAM) of 7-ISM8 of existing RTN910AF(RTN04, 9-30666). | ****IMPORTANT NOTE: DO NOT DECOM EXISTING HW MW LINK 23G_1+0_56M_512QAM AS PER REMARK IN NMS UNDER 1-ISV3-1.(NEED TO REMOVE THE REMARK)**** Existing HW MW link 23G_1+0_56M_512QAM & existing HW MW link 18G_1+0_55M_512QAM. MW Re-engineering required by perform EPLA between existing HW MW link 23G_1+0_56M_512QAM & existing HW MW link 18G_1+0_55M_512QAM. Site Impacted : 4279A, 4283A, 4289B & 3050C_8 NE_4279A 1.Insert new ISM8 x1 into slot 03 of RTN910A(RTN03 NEID 9-41754). 2.Shifting existing IF cables from 1-ISV3-1(HW MW link 23G_1+0_56M_512QAM) of existing RTN950A(RTN02, NEID 9-13948) and terminate into slot 03(Port 1) of RTN910A(RTN03 NEID 9-41754). 3.Shifting existing IF cables from 2-ISV3-1(HW MW link 18G_1+0_56M_512QAM) of existing RTN950A(RTN02, NEID 9-13948) and terminate into slot 03(Port 2) of RTN910A(RTN03 NEID 9-41754). 4.If existing IF cables not sufficient for shifting into RTN910A(RTN03 NEID 9-41754). Please lay new IF cables. 5.Later, perform EPLA in between slot 03(Port 1 & 2) of RTN910A(RTN03 NEID 9-41754). | ****IMPORTANT NOTE: DO NOT DECOM EXISTING HW MW LINK 23G_1+0_56M_512QAM AS PER REMARK IN NMS UNDER 1-ISV3-1.(NEED TO REMOVE THE REMARK)**** Existing HW MW link 23G_1+0_56M_512QAM & existing HW MW link 18G_1+0_55M_512QAM. MW Re-engineering required by perform EPLA between existing HW MW link 23G_1+0_56M_512QAM & existing HW MW link 18G_1+0_55M_512QAM. Site Impacted : 4279A, 4283A, 4289B & 3050C_8 FE_4294A 1.Perform EPLA in between port 1(HW MW link 23G_1+0_56M_512QAM) & 2(HW MW link 18G_1+0_55M_512QAM) of 7-ISM8 of existing RTN910AF(RTN04, 9-30666). | [5 empty] | GCI | SQ202603060620-GCI | GCI | SQ202512020091-GCI |  |  | Ongoing | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-17 | 2026-03-24 | 2026-03-17 | 2026-03-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-03-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112655 |  | 2025-12-27 | 2025-11-28 | Completed | 2025-11-27 | 2025-12-27 | 2025-11-26 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-03-09 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-03-09 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-03-05 | 2026-03-31 | 2026-03-05 | 2026-03-10 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2026-01-09: 2026-03-05; 2026-01-09: 2026-03-31; 2026-01-09: 2026-03-05; 2026-01-13: 2026-03-05 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280932-GTSB
7479B_HU | Genting Sekong | DU00006331679 | Sabah | Sabah | 5.561716 | 117.976530 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_28M_512QAM_EPLA(Without CA) NE_7479B New 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. Re-use existing RTN910AF(RTN02, NEID 9-43799). New ISM8 x2. New XMC_5D Pro, Sub A&B_Lo x2. New IF cables with suitable length and type 4x RUN. FE_7503B New 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. Re-use existing RTN910AF(RTN02, NEID 9-43798). New ISM8 x2. New XMC_5D Pro, Sub A&B_Hi x2. New IF cables with suitable length and type 4x RUN. | MW Swap | Existing HW MW Link_7479B-7503B, 18G_1+1 HSB_55MHZ_256QAM. MW Swap to new HW MW Link 7479B-7503B, 15G_4+0_28MHZ_512QAM_EPLA(Without CA). Combine another existing 13G_2+0_28MHZ_512QAM_EPLA with new HW MW Link 7479B-7503B, 15G_4+0_28MHZ_512QAM_EPLA(Without CA). Later, become 13G&15G_6+0_28MHZ_512QAM_EPLA. Decom Antenna, ODU and Modem(ISV3) slot 03 & 04 ONLY of HW MW Link_7479B-7503B, 18G_1+1 HSB_55MHZ_256QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-43799) and RTN910AF(RTN02, NEID 9-43798). Site Impacted : 7479B. NE_7479B 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43799) and insert 2x new ISM8 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7479B via HW MW Link 13G&15G_6+0_28MHZ_512QAM_EPLA.. 6.Later, Antenna, ODU and Modem(ISV3) slot 03 & 04 ONLY of HW MW Link_7479B-7503B, 18G_1+1 HSB_55MHZ_256QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-43799) and RTN910AF(RTN02, NEID 9-43798). FE_7503B 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43798) and insert 2x new ISM8 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7479B via HW MW Link 13G&15G_6+0_28MHZ_512QAM_EPLA.. 6.Later, Antenna, ODU and Modem(ISV3) slot 03 & 04 ONLY of HW MW Link_7479B-7503B, 18G_1+1 HSB_55MHZ_256QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-43799) and RTN910AF(RTN02, NEID 9-43798). | Existing HW MW Link_7479B-7503B, 18G_1+1 HSB_55MHZ_256QAM. MW Swap to new HW MW Link 7479B-7503B, 15G_4+0_28MHZ_512QAM_EPLA(Without CA). Combine another existing 13G_2+0_28MHZ_512QAM_EPLA with new HW MW Link 7479B-7503B, 15G_4+0_28MHZ_512QAM_EPLA(Without CA). Later, become 13G&15G_6+0_28MHZ_512QAM_EPLA. Decom Antenna, ODU and Modem(ISV3) slot 03 & 04 ONLY of HW MW Link_7479B-7503B, 18G_1+1 HSB_55MHZ_256QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-43799) and RTN910AF(RTN02, NEID 9-43798). Site Impacted : 7479B. NE_7479B 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43799) and insert 2x new ISM8 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Lo x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7479B via HW MW Link 13G&15G_6+0_28MHZ_512QAM_EPLA.. 6.Later, Antenna, ODU and Modem(ISV3) slot 03 & 04 ONLY of HW MW Link_7479B-7503B, 18G_1+1 HSB_55MHZ_256QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-43799) and RTN910AF(RTN02, NEID 9-43798). | Existing HW MW Link_7479B-7503B, 18G_1+1 HSB_55MHZ_256QAM. MW Swap to new HW MW Link 7479B-7503B, 15G_4+0_28MHZ_512QAM_EPLA(Without CA). Combine another existing 13G_2+0_28MHZ_512QAM_EPLA with new HW MW Link 7479B-7503B, 15G_4+0_28MHZ_512QAM_EPLA(Without CA). Later, become 13G&15G_6+0_28MHZ_512QAM_EPLA. Decom Antenna, ODU and Modem(ISV3) slot 03 & 04 ONLY of HW MW Link_7479B-7503B, 18G_1+1 HSB_55MHZ_256QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-43799) and RTN910AF(RTN02, NEID 9-43798). Site Impacted : 7479B. FE_7503B 1.Install new 15G_1.2M(MDD)+Flange Adapter/Dual Coupler x1. 2.Re-use existing RTN910AF(RTN02, NEID 9-43798) and insert 2x new ISM8 into slot 03 & 04. 3.Install new XMC_5D Pro, Sub A&B_Hi x2. Configure it. 4.Re-use existing xD vlan dcn and vlan services. 5.Migrate traffic 7479B via HW MW Link 13G&15G_6+0_28MHZ_512QAM_EPLA.. 6.Later, Antenna, ODU and Modem(ISV3) slot 03 & 04 ONLY of HW MW Link_7479B-7503B, 18G_1+1 HSB_55MHZ_256QAM. Anyway, do not decom RTN910AF(RTN02, NEID 9-43799) and RTN910AF(RTN02, NEID 9-43798). | XMC_5D Pro | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | Seri Pancar | SQ202602090132-Seri Pancar | NR services | SQ202603030374-NR Services // SQ202603030376-NR Services | 2026-04-21 | 2026-04-14 | Completed | 2026-02-04 | 2026-02-28 | 2026-02-12 | 2026-02-12 | JEFRIZIN BIN MORUNDANG8366000004 | Seri Pancar TI | SERI PANCAR SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-02-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-12 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-14 | 2026-04-21 | 2026-04-14 | 2026-04-14 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26021234 |  | 2026-02-13 | 2026-03-15 | Completed | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-03-15 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-03-15 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-04-05 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | AKMAL//BIN RAZALI/6794000078 |  |  | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-04-09 | IBRAHIM//BIN SAHABU/7167000007 | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-02-28 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2026-04-21 | 2026-05-21 | 2026-04-20 | 2026-04-21 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202511280936-GTSB
Q01051_HU | Q135A_Q01051OD_KOLEJSRISERAPI | DU00006331680 | Sarawak | Sarawak | 1.451250 | 110.446890 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 23G_1+0_56M_1024QAM_491M. MW Remote Upgrade to HW 23G_1+0_110M_512QAM_889M. Site Impacted : Q01051. NE_Q01051 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 56MHz to BW 112MHz(512QAM). FE_9964A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 56MHz to BW 112MHz(512QAM). | Link Existing HW 23G_1+0_56M_1024QAM_491M. MW Remote Upgrade to HW 23G_1+0_110M_512QAM_889M. Site Impacted : Q01051. NE_Q01051 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 56MHz to BW 112MHz(512QAM). | Link Existing HW 23G_1+0_56M_1024QAM_491M. MW Remote Upgrade to HW 23G_1+0_110M_512QAM_889M. Site Impacted : Q01051. FE_9964A 1.Existing ODU XMC-3(equipped 112MHz) may remotely upgrade from 56MHz to BW 112MHz(512QAM). |  |  | 23G | [8 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-26 | [15 empty] | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202511280943-GTSB
B00944_HU | B065B_B00944OD_KGGERACHIJAYA | DU00006331681 | Central | Selangor | 3.585900 | 101.695300 | [12 empty] | Existing TX | Existing SM link 8G_2+0_28M with 1024QAM. B00944-B00290 MW1 to carry B01129 or 1110K (MONC ID) one child site only. B00944 RAN already decomm. 2028A is pair B00944.Installed with HW link. 1110K/B01129 RAN ady MONC. Current Util 150M. Current TX Route : B00944-B00290-B01300 , to support B01129. | Existing TX | Existing TX | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202511280798-GCI | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | CHEONG/SENG/WAH/7018000306
S01989_HU | SK Palak | DU00006331682 | Sabah | Sabah | 7.198526 | 117.167617 | [7 empty] | 04. BOM / Material Issue |  | TSS+AA+TI |  |  | MW Parallel Link | Link Distance 23KM , 8G with SD to be propose. Hence , TSS survey and FSS is required. | Link Distance 23KM , 8G with SD to be propose. Hence , TSS survey and FSS is required. | Link Distance 23KM , 8G with SD to be propose. Hence , TSS survey and FSS is required. | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202511280806-GCI
7097Z_HU | T3E_0692_KgLubukan | DU00006331683 | Sabah | Sabah | 5.720915 | 118.113395 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M NE_7097Z 13G_DP_1.8M(MDD) x1. XMC_5D , Sub B_Lo x1. ETH CAT 6 Cable x1. FE_7124A. 13G_DP_1.8M(MDD) x1. XMC_5D , Sub B_Hi x1. | MW Parallel Link | Existing link 13G_4+0_28M. Install parallel link 13G_2+0_28M. Site Impacted : 7097Z , 7103Z , 7748B. NE_7097Z 1.Install new 13G_DP_1.8M(MDD). 2.Reuse existing 7097Z_RTN04 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Lo. 4.Create service cross connect and EPLA with existing MW link. 5.Migrate all traffic to new parallel link. 6.No MW link to decomm. FE_7124A. 1.Install new 13G_DP_1.8M(MDD). 2.Reuse existing 7124A_RTN21 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross connect and EPLA with existing MW link. 5.Create LAG port. 6.Migrate all traffic to new parallel link. 7. No MW link to decomm. | Existing link 13G_4+0_28M. Install parallel link 13G_2+0_28M. Site Impacted : 7097Z , 7103Z , 7748B. NE_7097Z 1.Install new 13G_DP_1.8M(MDD). 2.Reuse existing 7097Z_RTN04 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Lo. 4.Create service cross connect and EPLA with existing MW link. 5.Migrate all traffic to new parallel link. 6.No MW link to decomm. | Existing link 13G_4+0_28M. Install parallel link 13G_2+0_28M. Site Impacted : 7097Z , 7103Z , 7748B. FE_7124A. 1.Install new 13G_DP_1.8M(MDD). 2.Reuse existing 7124A_RTN21 , 7_ISM8-2+0. 3.Install new XMC_5D , Sub B_Hi. 4.Create service cross connect and EPLA with existing MW link. 5.Create LAG port. 6.Migrate all traffic to new parallel link. 7. No MW link to decomm. | XMC_5D | MDD | 13G | 1.8 | 1.8 | NR services | SQ202601210165-NR Services | NR services | SQ202512300312-NR Services // SQ202512300318-NR Services | 2026-02-23 | 2026-02-23 | Completed | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121767 |  | 2025-12-18 | 2025-12-21 | Completed | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-21 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-15 | 2026-02-15 | 2026-01-15 | 2026-01-16 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-01-15 | 2026-02-15 | 2026-01-15 | 2026-01-20 | IBRAHIM//BIN SAHABU/7167000007 | NR Service TI | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-01-20 | 2026-01-15 | 2026-02-15 | 2026-01-15 | 2026-01-26 | IBRAHIM//BIN SAHABU/7167000007 | 2026-01-09: 2026-01-15; 2026-01-09: 2026-02-15; 2026-01-09: 2026-01-15; 2026-01-13: 2026-01-17 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202511280806-GCI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | CHEONG/SENG/WAH/7018000306
3200C_HU | Kg Jenjarom | DU00006331684 | Central | Selangor | 2.886640 | 101.516000 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M_512QAM_EPLA NE_3200C New 15G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 9-48583). New ISM8 x1. New XMC_5D, Sub B_Lo x1. FE_1122A New 15G_0.6M(MDD) x1. New RTN910AF(RTN14). New ISM8 x1. New XMC_5D, Sub B_Hi x1. New CAT6 cable x1. Additional new IF cable x1 Run if existing IF cable short for shifting from existing ISM8 slot 07 port 1(facing to 3200C) of existing RTN910AF(RTN02, NEID 9-48584) to | MW Parallel Link | Existing HW MW Link 3200C-1122A, 23G_1+0_56MHZ_512QAM. Build new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 3200C-1122A, 23G_1+0_56MHZ_512QAM and new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. Become 23G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. Site Impacted : 3200C. NE_3200C 1.Install new 15G_0.6M(MDD) x1. 2.Re-use exsiting RTN910AF(RTN01, NEID 9-48583) insert ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Lo x1. Build new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, perform combine existing HW MW Link 3200C-1122A, 23G_1+0_56MHZ_512QAM and new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. Become 23G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. FE_1122A 1.Install new 15G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN14) and insert ISM8 into slot 03. 3.Shifting existing IF cable from existing ISM8 slot 07 port 1(facing to 3200C) of existing RTN910AF(RTN02, NEID 9-48584). 4.If existing IF cable short for terminating from existing ODU 23G to ISM8 slot 07(Port 1) of new RTN910AF(RTN14). Therefore, need to lay additional new IF cable. 5.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. 6.Enable port 8_EM6-1 of new RTN910AF(RTN14) and patching to new port of IBeam. Request new IBeam port from ZTE IPRAN team. 7.Request new xD Vlan DCN and new Vlan Services for new IBeam port. 8.Later, perform combine existing HW MW Link 3200C-1122A, 23G_1+0_56MHZ_512QAM and new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. Become 23G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. | Existing HW MW Link 3200C-1122A, 23G_1+0_56MHZ_512QAM. Build new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 3200C-1122A, 23G_1+0_56MHZ_512QAM and new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. Become 23G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. Site Impacted : 3200C. NE_3200C 1.Install new 15G_0.6M(MDD) x1. 2.Re-use exsiting RTN910AF(RTN01, NEID 9-48583) insert ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Lo x1. Build new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. 4.Later, perform combine existing HW MW Link 3200C-1122A, 23G_1+0_56MHZ_512QAM and new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. Become 23G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. | Existing HW MW Link 3200C-1122A, 23G_1+0_56MHZ_512QAM. Build new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. Later, combine existing HW MW Link 3200C-1122A, 23G_1+0_56MHZ_512QAM and new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. Become 23G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. Site Impacted : 3200C. FE_1122A 1.Install new 15G_0.6M(MDD) x1. 2.Install new RTN910AF(RTN14) and insert ISM8 into slot 03. 3.Shifting existing IF cable from existing ISM8 slot 07 port 1(facing to 3200C) of existing RTN910AF(RTN02, NEID 9-48584). 4.If existing IF cable short for terminating from existing ODU 23G to ISM8 slot 07(Port 1) of new RTN910AF(RTN14). Therefore, need to lay additional new IF cable. 5.Install new XMC_5D, Sub B_Hi x1. Build new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. 6.Enable port 8_EM6-1 of new RTN910AF(RTN14) and patching to new port of IBeam. Request new IBeam port from ZTE IPRAN team. 7.Request new xD Vlan DCN and new Vlan Services for new IBeam port. 8.Later, perform combine existing HW MW Link 3200C-1122A, 23G_1+0_56MHZ_512QAM and new HW MW Parallel Link 3200C-1122A, 15G_2+0_28MHZ_512QAM_EPLA. Become 23G&15G_3+0_56MHZ&28MHZ_512QAM_EPLA. | XMC-5D | MDD | 15G | 15G_0.6M(MDD) x1. | 15G_0.6M(MDD) x1. | GTSB | SQ202512160952-GTSB | GTSB | SQ202512010569-GTSB // SQ202512010581-GTSB | 2026-01-22 | 2026-01-15 | Completed | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-15 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25112710 |  | 2025-12-27 | 2025-11-28 | Completed | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-28 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-24 | 2025-12-02 | 2025-12-13 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2025-12-02 | 2025-12-24 | 2025-12-02 | 2025-12-30 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | GTSB TI | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-12-12 | 2025-12-02 | 2025-12-24 | 2025-12-02 | 2025-12-28 | SYED AMIRUL AFIQ BIN SYED SUHAIMI6000059292 | 2026-01-09: 2025-12-02; 2026-01-09: 2025-12-24; 2026-01-09: 2025-12-02; 2026-01-13: 2025-12-23 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280921-GTSB
4053L_HU | Taman Bersatu | DU00006331685 | Northern | Kedah | 6.247603 | 100.598206 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 18G_1+0_56M. Remote Software upgrade to 18G_1+0_112M with 512QAM. | Existing link 18G_1+0_56M. Remote Software upgrade to 18G_1+0_112M with 512QAM. | Existing link 18G_1+0_56M. Remote Software upgrade to 18G_1+0_112M with 512QAM. | [5 empty] | In-House | No PR required-Remote Upgrade | In-House | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 | [17 empty] | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280776-GCI | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | CHEONG/SENG/WAH/7018000306
9928A_HU | Jalan Aru | DU00006331686 | Sarawak | Sarawak | 4.316156 | 113.972618 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M with 512QAM. | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M with 512QAM. | Existing link 18G_1+0_56M Remote Software Upgrade to 18G_1+0_112M with 512QAM. | [11 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-01-26 | [15 empty] | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202511280911-GCI | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | CHEONG/SENG/WAH/7018000306
4412D_HU_1 | Bandar Baru Setia Awan | DU00006331687 | Northern | Perak | 4.220030 | 100.777400 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 18G_2+0_110M_256QAM_849 NE_4412D New ISM8 x1. New IF cable x1 RUN with suitable type and length. FE_4457C New ISM8 x1. New IF cable x1 RUN with suitable type and length. | MW Hardware Upgrade | Existing HW MW Link HW 18G_2+0_110M_512QAM_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 18G_2+0_110M_512QAM_EPLA and later configure new HW 18G_4+0_110M_256QAM_CA. Site Impacted : 4412D NE_4412D 1.Insert new ISM8 card into slot 03 of existing RTN910A(RTN01, NEID 9-28157). 2.Lay new IF cable x1 RUN. 3.Configure existing HW 18G_2+0_110M_512QAM_EPLA to new HW 18G_4+0_110M_256QAM_CA. FE_4457C 1.Insert new ISM8 card into slot 03 of existing RTN910A(RTN02, NEID 9-28158). 2.Lay new IF cable x1 RUN. 3.Configure existing HW 18G_2+0_110M_512QAM_EPLA to new HW 18G_4+0_110M_256QAM_CA. | Existing HW MW Link HW 18G_2+0_110M_512QAM_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 18G_2+0_110M_512QAM_EPLA and later configure new HW 18G_4+0_110M_256QAM_CA. Site Impacted : 4412D NE_4412D 1.Insert new ISM8 card into slot 03 of existing RTN910A(RTN01, NEID 9-28157). 2.Lay new IF cable x1 RUN. 3.Configure existing HW 18G_2+0_110M_512QAM_EPLA to new HW 18G_4+0_110M_256QAM_EPLA | Existing HW MW Link HW 18G_2+0_110M_512QAM_EPLA. MW Hardware Upgrade by adding another 2 new channels to existing HW 18G_2+0_110M_512QAM_EPLA and later configure new HW 18G_4+0_110M_256QAM_CA. Site Impacted : 4412D FE_4457C 1.Insert new ISM8 card into slot 03 of existing RTN910A(RTN02, NEID 9-28158). 2.Lay new IF cable x1 RUN. 3.Configure existing HW 18G_2+0_110M_512QAM_EPLA to new HW 18G_4+0_110M_256QAM_EPLA |  |  | 18G |  |  | GCI | SQ202512300535-GCI | GCI | SQ202512300527-GCI // SQ202512300531-GCI | 2026-01-27 | 2026-01-21 | Completed | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-30 | 2026-01-06 | 2025-12-30 | 2025-12-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-27 | 2026-01-20 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25121224 |  | 2026-01-14 | 2025-12-13 | Completed | 2025-12-13 | 2026-01-14 | 2025-12-12 | 2025-12-13 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-19 | 2025-12-24 | 2025-12-19 | 2025-12-27 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-12-19 | 2025-12-24 | 2025-12-19 | 2026-01-25 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-24 | 2025-12-19 | 2025-12-24 | 2025-12-19 | 2026-01-25 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2026-01-09: 2025-12-19; 2026-01-09: 2025-12-24; 2026-01-09: 2025-12-19; 2026-01-13: 2026-01-21 |  |  | 2026-03-19 | 2026-04-19 | 2026-03-19 | 2026-03-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202511280932-GTSB
R00023_AD_1 | ​R001B_R00023OD_KUALAPERLIS | DU00006331691 | Northern | Perlis | 6.383942 | 100.152053 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2X10 SFP 1KM 2X 13G 1.2M MDD ANTENNA 1x ODU 13G XMC5D SUB A HI 1x ODU 13G XMC5D SUB A LO | MW Parallel Link | MW PARALLEL LINK R00023-R00028 WITH HUAWEI_13G_2+0_1.2M/1.2M_MDD_28MHZ_512QAM_448MBPS_XMC5D_SUB_A_4.88KM IMPACTED: 4608B THIS LINK WILL BE EPLA WITH DU R00023_AD 13G 4+0 AND BECOME 6+0 THIS LINK CARRY 4608B NEW LINK | 1. REUSE EXISTING IDU FROM R00023_AD SLOT 7 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 2+0 28MHZ 512QAM 5. EPLA WITH DU R00023_AD 13G 4+0 BECOME 13G 6+0 6. THIS LINK CARRY 4608B NEW LINK | 1. REUSE EXISTING IDU FROM R00023_AD SLOT 7 2. INSTALL NEW 13G 1.2M MDD ANTENNA 3. INSTALL NEW ODU 13G XMC5D 28MHZ SUB A 4. CONFIGURE LINK 13G 2+0 28MHZ 512QAM 5. EPLA WITH DU R00023_AD 13G 4+0 BECOME 13G 6+0 6. PATCH TO NEW 10G CP PORT 7. THIS LINK CARRY 4608B NEW LINK | XMC5D | MDD | 13G | 1.2 | 1.2 | Magicell | SQ202512030583-Magicell | Magicell | SQ202511260111-Magicell // SQ202511260115-Magicell | 2025-12-04 | 2025-12-03 | Completed | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | 2025-12-03 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY251121AU |  | 2025-12-20 | 2025-11-24 | Completed | 2025-11-21 | 2025-12-20 | 2025-11-21 | 2025-11-24 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-02 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | Magicell TI | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-01 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-15 | WAN NURMISWARI BIN WAN ISMAIL6000014316 | 2026-01-09: 2025-11-25; 2026-01-09: 2025-11-25; 2026-01-09: 2025-11-25; 2026-01-13: 2025-11-28 |  |  | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202511280776-GCI | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | EZRIN TASNIM BIN ABDUL GANI6798000128
4376C-4196A | Tmn Pauh Indah | DU00003324987 | Northern | Penang | 5.375300 | 100.418040 | WK04 | JAN 24 | WK06 | FEB 24 | RFS | Pending L1 | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_1+0_0.6,0.6 SP_112MHz | MW Swap | NE 1- Install IDU 910A. 2- Install 1+0 ODU. 3- Swap 0.6m Antenna. 4- Configure link 1+0_889M_512QAM. FE 1- New IDU 910A. 2- Install 1+0 ODU and configure EPLA with existing 1+0 ODU. 3- Swap 0.6m Antenna. 4- Configure link 1+0_889M_512QAM | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402160379-GCI // SQ202406260407-GCI | 2025-10-24 | 2025-10-24 | Completed | 2024-01-26 | 2024-01-26 | 2024-01-24 | 2024-01-24 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-26 | 2024-02-29 | 2024-02-01 | 2024-02-02 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020353 |  | 2024-02-06 | 2024-02-13 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-02-16 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-02-21 | HIMAN//BIN ADAM/6800000183 | GCI TI | 2024-02-17 | 2024-02-17 | 2024-02-17 | 2024-02-17 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-03-27 | HIMAN//BIN ADAM/6800000183 | 2024-02-16 | 2024-02-29 | 2024-02-16 | 2024-02-16 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-29 | LIM//FOONG XIANG/6871000029 | Logistic Team | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
7667A-7960A | Sg Udin | DU00003324988 | Sabah | Sabah | 4.401141 | 117.718955 | WK04 | JAN 24 | WK03 | JAN 25 | RFS | TI DONE | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_2+0_1.2,1.2 DP_28Mhz | MW Swap | MW SWAP WITH 15G_2+0_1.2/1.2_SB A,B Dismantle exisitng link. | NE: 1.Reuse exisiting RTN910A. 2. Swap existing ODU with XMC-3_SB A,B. 3. Swap existing antenna with 15G_1.2m_DP. 4. Configure 15G_2+0_1.2/1.2_EPLA | FE: 1.Reuse exisiting RTN910A. 2. Swap existing ODU with XMC-3_SB A,B. 3. Swap existing antenna with 15G_1.2m_DP. 4. Configure 15G_2+0_1.2/1.2_EPLA | [5 empty] | Seri Pancar | SQ202402130369-Seri Pancar | AllStar | SQ202501210500-Allstar // SQ202504260190-Allstar | 2024-04-26 | 2024-04-23 | Completed | 2024-01-24 | 2024-01-31 | 2024-01-26 | 2024-01-26 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-01-30 | 2024-01-31 | 2024-01-30 | 2024-01-30 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-30 | 2024-01-31 | 2024-01-30 | 2024-01-30 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-04-23 | 2024-04-26 | 2024-04-23 | 2024-04-23 | AZRI//BIN ABDULLAH/6799000073 |  |  | 1.00 | Assigned | Completed | Closed |  | DOWMY25011390 |  | 2025-02-03 | 2025-02-03 | Completed | 2025-01-14 | 2025-02-03 | 2025-02-03 | 2025-02-03 | NUR/WAFA/MIJONG/6871000001 |  | DCH Technology SDN.BHD | 1.00 | Unassigned | Completed |  | 2025-01-18 | 2025-02-01 | 2025-01-18 | 2025-02-03 | CALVIN/RAY/BENEDICT/6798000250 | Allstar TI | 2025-01-18 | 2025-02-01 | 2025-01-18 | 2025-02-14 | CALVIN/RAY/BENEDICT/6798000250 | Allstar TI | 2025-02-03 | 2025-02-03 | 2025-02-03 | 2025-02-03 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-02-03 | 2025-01-18 | 2025-02-01 | 2025-01-18 | 2025-02-07 | CALVIN/RAY/BENEDICT/6798000250 | 2025-01-18 | 2025-02-01 | 2025-01-18 | 2025-02-03 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | tseping//wang/6819000006 | Logistic Team | 2025-03-25 | 2025-04-25 | 2025-03-25 | 2025-03-25 | MASDIANA//BINTI BEDIN/6801000016
7622A-7669B | Bukit Tiger | DU00003324989 | Sabah | Sabah | 4.424988 | 117.830598 | WK04 | JAN 24 | WK08 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_1.2,1.2 DP_28Mhz | MW Parallel Link | NE 1- Install IDU 910A. 2- Install 4+0 1xODU. 3- Install new HW 1.2m Antenna. 4- Install new 2 ISM8. 5- Configure link 4+0_800M_512QAM with EPLA FE 1- New IDU 910A. 2- Install 4+0 1xODU 3- Install new HW 1.2m Antenna. 4- Install new 2 ISM8. 5- Configure link 4+0_800M_512QAM with EPLA. 6- To provide new port at PTN. Required DCN VLAN. | [7 empty] | Seri Pancar | SQ202402130369-Seri Pancar | GTSB | SQ202402210517-GTSB | 2024-11-15 | 2025-09-26 | Completed | 2024-01-22 | 2024-01-31 | 2024-01-24 | 2024-01-24 | JEFRIZIN BIN MORUNDANG8366000004 |  | SERI PANCAR SDN. BHD. |  | Unassigned | Completed |  | 2024-01-29 | 2024-01-31 | 2024-01-29 | 2024-01-29 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-01-30 | 2024-01-31 | 2024-01-30 | 2024-01-30 | AZRI//BIN ABDULLAH/6799000073 |  |  |  | Unassigned | Completed |  | 2024-11-11 | 2024-11-15 | 2024-11-11 | 2025-09-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY24020514 |  | 2024-02-06 | 2024-02-07 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-07 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-08 | 2024-02-29 | 2024-02-08 | 2024-02-15 | AHMAD//AL HADI BIN KARIMUN/6799000119 | GTSB TI | 2024-02-08 | 2024-02-29 | 2024-02-08 | 2024-02-19 | AHMAD//AL HADI BIN KARIMUN/6799000119 | GTSB TI | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-08 | 2024-02-29 | 2024-02-08 | 2024-02-20 | AHMAD//AL HADI BIN KARIMUN/6799000119 | 2026-01-09: 2024-02-08; 2026-01-09: 2024-02-29; 2026-01-09: 2024-02-08; 2026-01-13: 2024-02-15 |  |  | 2024-06-26 | 2024-07-26 | 2024-06-26 | 2024-06-26 | ASTI//GANIS PUTRIANI/6237001358
4191D-4678A | Menara Zakat (REL) | DU00003324990 | Northern | Kedah | 6.120749 | 100.383638 | WK04 | JAN 24 | WK08 | FEB 24 | ATP | Online ATP WIP | ZTE | 00. Integrated/RFS Done | #N/A | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_0.6,1.2 DP_110Mhz | MW Swap | NE 1- Install IDU 910A. 2- Install 2+0 ODU and configure EPLA. 3- Swap 0.6m Antenna with new HW 0.6m Antenna. 4- Configure link 2+0_1200M_128QAM FE 1- New IDU 910A. 2- Install 2+0 ODU and configure EPLA. 3- Swap 0.6m Antenna with new HW 1.2m Antenna. 4- Configure link 2+0_1200M_128QAM. 5- To provide new port at PTN. Required DCN VLAN | [7 empty] | GCI | SQ202402080111-GCI | GCI | SQ202402160379-GCI // SQ202406260407-GCI // SQ202409100506-GCI | 2024-02-29 | 2024-02-23 | Completed | 2024-01-30 | 2024-01-30 | 2024-01-25 | 2024-01-25 | NABIL//IFWAD BIN BADRUL ASRI/6800000242 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-28 | 2024-01-28 | 2024-01-28 | 2024-01-28 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. |  | Unassigned | Completed |  | 2024-01-26 | 2024-02-29 | 2024-02-01 | 2024-02-02 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed |  | 2024-02-01 | 2024-02-29 | 2024-02-01 | 2024-02-23 | MOHD FAIZ BIN ABU BAKAR6800000092 | Design and Material Team |  | 1.00 | Assigned | Completed | Closed |  | DOWMY24020354 |  | 2024-02-06 | 2024-02-13 | Completed | 2024-02-05 | 2024-02-06 | 2024-02-05 | 2024-02-13 | TYNG ERN//SLEW/6871000006 | Warehouse Team |  | 1.00 | Assigned | Completed |  | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-20 | MUHAMMAD//NA'IF BIN MOKHTAR/6800000180 | GCI TI | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-21 | MUHAMMAD//NA'IF BIN MOKHTAR/6800000180 | GCI TI | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  |  | 2024-02-19 | 2024-02-29 | 2024-02-19 | 2024-02-27 | MUHAMMAD//NA'IF BIN MOKHTAR/6800000180 | 2026-01-09: 2024-02-19; 2026-01-09: 2024-02-29; 2026-01-09: 2024-02-19; 2026-01-13: 2024-02-20 |  |  | 2024-05-24 | 2024-06-24 | 2024-05-24 | 2024-05-24 | ASTI//GANIS PUTRIANI/6237001358
3461C | National Stadium Bkt Jalil IB 2 | DU00004249136 | Central | Kuala Lumpur | 3.053759 | 101.690998 |  |  |  |  | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 23/10: Cutover done 15/10: Survey done. Additional material requested. Pending DO | TSS+TI | L1+ATP+PAC | 2x 50m CPRI 4 x10G 1km SFP | BBU Patching | BBU Patching to xC W00430 | [7 empty] | Datasco | SQ202411140206-Datasco | Datasco | SQ202410280549-Datasco |  |  | Ongoing | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21 | MUHAMMAD TAUFIQ//ABDULLAH/7019000149 |  | DATASCO SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY24101028 |  | 2024-10-11 | 2024-10-17 | Completed | 2024-10-10 | 2024-10-11 | 2024-10-10 | 2024-10-17 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2024-10-23 | 2024-11-06 | 2024-10-23 | 2025-02-25 | NORSHAMSUDIN//BIN DAUD/7019000007 | Datasco TI | 2024-10-23 | 2024-11-06 | 2024-10-23 |  | NORSHAMSUDIN//BIN DAUD/7019000007 | Datasco TI | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-10-23 | LUQMAN//FITRI BIN SHAMSHUDDIN/6799000067 |  |  | 2024-10-23 | 2024-11-06 | 2024-10-23 | 2024-10-24 | NORSHAMSUDIN//BIN DAUD/7019000007 | 2026-01-09: 2026-03-19; 2026-01-09: 2026-03-31; 2026-01-09: 2026-03-19; 2026-01-13: 2026-03-31 |  |  | 2024-12-12 | 2025-01-12 | 2024-12-12 | 2024-12-12 | ASTI//GANIS PUTRIANI/6237001358 |  | Assign Subcon
1113A-1087A_1 | Pulau Ketam | DU00004249137 | Central | Selangor | 3.018927 | 101.252875 | WK08 | FEB 25 | WK08 | FEB 25 | TI | LOS not clear | ZTE | 03. TSS Only | 20/2/2025 : Cancel proceed due to LOS block 19/2/2025 : Ground work assemble antena 6ft activity only 13/1/2025 : Digi OB - 45M 3 Legged Tower - NE site 1113A Pulau Ketam, Digi OB - 45M 4 Legged Tower - FE site 1087A Rantau Panjang | TSS |  | 13G_1.8m&1.8m_DP_2+0_28Mhz | MW Hardware Upgrade | TSS ONLY PULAU KETAM LOS BLOCK ISSUE | [7 empty] | MTK |  | MTK | No PR required-Work at TSS only |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300116-GTSB
1628H_LOS | 99 Speedmart DESA PINGGIRAN PUTRA | DU00004249138 | Central | Kuala Lumpur | 2.900780 | 101.705899 |  |  |  |  | TSS Only | No available LOS | ZTE | 00. Site Out/Drop | 28/2/2025 : Done survey by Allstar. No LOS available 20/9: Pending Tx Solution for HU | TSS |  | Proposed Fiber due to No LOS is available Found during actual TSS LOS survey. | MW New Link / Reroute | Proposed Fiber due to No LOS is available Found during actual TSS LOS survey. | [7 empty] | Allstar | SQ202410080181-Allstar |  |  | 2025-07-02 | 2025-07-01 | Completed | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | MUHAMMAD//HAZIQ BIN AHMAD DIN/6798000191 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2024-10-07 | 2024-10-08 | 2024-10-07 | 2024-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2024-10-07 | 2024-10-08 | 2024-10-07 | 2024-10-07 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-01 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB_AA | SQ202510300116-GTSB
1753H_LOS | NLOS 99 Speedmart Tmn Kinrara | DU00004249139 | Central | Kuala Lumpur | 3.066710 | 101.650230 | WK09 | FEB 25 | WK09 | FEB 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 26/2/2025 : Cutover done 25/1/2025 : Alignment and cutover cannot done due access limit 24/1/2025 : Installation complete, pending alignment 6/1/2025 : Digi OB - Small Cell - NE site 1753H NLOS 99 Speedmart Tmn Kinrara, EDOTCO (M) SDN BHD - TRIPOD 6M LAND - FE site W00212 W066S_W00212OD_KINRARA 20/9: Pending Tx Solution for HU | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NLOS RTN510 NE_1753H 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE_W00212 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable 6. ETH / LAN Cable to patching to Fiber port. | MW New Link / Reroute | Link reroute to new FE W00212 with New NLOS RTN510. NE_1753H 1.Install new RTN510 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migarte to new route FE site. 6.Decom existing NLOS radio. FE_W00212. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect and new In band DCN. 5.ETH cable direct patching to existing Fiber. 6.Decom existing NLOS Radio | [7 empty] | GTSB | SQ202501270097-GTSB | GTSB | SQ202501030381-GTSB // SQ202504260131-GTSB | 2025-02-19 | 2025-02-10 | Completed | 2025-02-05 | 2025-02-19 | 2025-02-05 | 2025-02-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-02-04 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-04 | 2025-02-05 | 2025-02-04 | 2025-02-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-02-07 | 2025-02-08 | 2025-02-07 | 2025-02-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25010363 |  | 2025-01-04 | 2025-03-13 | Completed | 2025-01-03 | 2025-01-04 | 2025-01-03 | 2025-03-13 | Jacqueline//Kong Yie Hue/6871000040 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-03-13 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-03-13 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | GTSB TI | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-02-26 | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-04-25 | NIK MOHD HAIRIE//ZAKARIA/6799000281 | 2025-01-23 | 2025-01-31 | 2025-01-23 | 2025-01-24 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | NG HONG JIE7018000036 | Logistic Team | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358
9000B21_EVT | PBTS PESTA KUBIS KUNDASANG | DU00006020775 | Sabah | Sabah | 5.987030 | 116.575580 | [13 empty] | Planning and integration support only for event site 9000B21 PBTS PESTA KUBIS KUNDASANG Tx route: 9000B21-7390A/S01147 1) New port at PTN 20212-KUNDASANG_TOWN 2) New NE ID FE IDU 7390A RTN02 3) New DCN IP and VLAN for 7390A RTN02 4) New NE ID NE IDU 9000B21 RTN01 5) At FE 7390A to patch IDU RTN02 to PTN 20212-KUNDASANG_TOWN | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202512241128-GCI | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | EZRIN TASNIM BIN ABDUL GANI6798000128
1499H_LOS | 99 Speedmart TMN BANGI AVENUE | DU00006020776 | Central | Selangor | 2.900252 | 101.792185 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable FE 1. Nlos-OptiX RTN /PI-DC B10 /Power injector. 2. Nlos-RTN510 Microwave/4.91-5.97GHz/AP/with installation material. 3. Nlos-Microwave Antenna/AS6D03SSNF/4.9-5.97G/315mm/dual polarization/Separate Mount with bracket. 4. Nlos-DC Power Cable 2*2.5mm2/Blue/Brown 33A/600V/1000V. 5. Nlos-Symmetry Twist Cable/100ohm/SFTP CAT5E/0.53mm/24AWG/4Pairs/Black/Outdoor Cable | MW New Link / Reroute | 1499H reroute to new FE 3404B due to LOS Block. Site Impacted : 1499H. NE_1499H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (1499H - 1834B). FE_3404B. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.ETH patching to existing 3404B_RTN05_GE2 ( ID : 34955). 6.Traffic migrate to new route FE site and with new NLOS. 7.Decom existing NLOS Radio (1834B - 1499H). | 1499H reroute to new FE 3404B due to LOS Block. Site Impacted : 1499H. NE_1499H. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create service cross connect. 5.Traffic migrate to new route FE site and with New NLOS. 6.Decom existing NLOS radio (1499H - 1834B). | 1499H reroute to new FE 3404B due to LOS Block. Site Impacted : 1499H. FE_3404B. 1.Install new RTN510. 2.Install new NLOS Antenna. 3.Install new PI. 4.Create Service cross connect. 5.ETH patching to existing 3404B_RTN05_GE2 ( ID : 34955). 6.Traffic migrate to new route FE site and with new NLOS. 7.Decom existing NLOS Radio (1834B - 1499H). | [5 empty] | Magicell | SQ202509240830-Magicell | Magicell | SQ202510230920-Magicell // SQ202510230933-Magicell | 2025-11-11 | 2025-11-10 | Completed | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-10 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100758 |  | 2025-10-08 | 2025-10-09 | Completed | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-29 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-11-21 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | Magicell TI | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-31 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-11-20 | MOHD//REDZUAN BIN ZULKIFLI/7018000131 | 2026-01-09: 2025-10-15; 2026-01-09: 2025-10-15; 2026-01-09: 2025-10-15; 2026-01-13: 2025-10-31 |  |  | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202510100626-GCI | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | CHEONG/SENG/WAH/7018000306
7692A_LOS | USP Kg Mendulong | DU00005618997 | Sabah | Sabah | 4.950961 | 115.687440 |  |  |  |  | Pending SOW |  |  | 03. TSS Only |  | TSS |  |  | MW New Link / Reroute | [8 empty] | NR services | SQ202507080871-NR Services |  |  |  |  | Ongoing | 2025-07-04 | 2025-07-06 | 2025-07-04 | 2025-08-03 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280702-GTSB
2114A_AD | Soho Outdoor | DU00005618998 | Central | Kuala Lumpur | 3.175337 | 101.660204 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | New SFP Module 1.25G 1310nm 10Km x2.(For BBU 2114A and existing RTN910A of Link_ID CT10100) New Optical Patchcord with suitable type and length x1.(For BBU 2114A and existing RTN910A of Link_ID CT10100) New IF cable with suitable length x1.(For shifting existing ISM8 from RTN910A to another RTN910A) | MW Re-engineering | Perform re-engineering by doing migration for sites 2105B, 2114A, 1070B & 2791A to new CP, 2021B. **Important Note: 1. Mandatory to perform TSS in order to confirm whether 2114A & 2791A are in the same location/room or nearby each other. If YES, DU 2791A_AD, 2114A_AD and 2105B_AD can be proceed. 2. Need to perform the task in sequence accordingly - firstly do 2791A_AD follow with 2114A_AD and the last 2105B_AD. 3. 2791A_AD, 2114A_AD and 2105B_AD suggest to perform at the same day.** Site Impacted: 2105B, 2114A, 1070B & 2791A. NE_2114A 1.Ensure perform DU 2791A first. 2.Shifting existing ISM8 slot 03 from existing RTN910A/RTN02(HW MW Link 2114A-2105B) to slot 03 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). Configure it. 3.Also, shifting existing IF cable from existing ISM8 slot 03 from existing RTN910A/RTN02(HW MW Link 2114A-2105B) to slot 03 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). If short, lay new IF cable from ODU to slot 03 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 4.Disconnect existing cascading from port 8-EM6-2 of existing RTN910A/RTN02(HW MW Link 2114A-2105B) to port 8-EM6-1 of existing HW MW Link ID_CT10100(W01311-W00074). 5.Enable port 8-EM6-5 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 6.Insert new Optical SFP Module 1.25G 10Km into port 8-EM6-5 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 7.Patching BBU 2114A to port 8-EM6-5 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 8.Request new xD vlan services and vlan dcn to new CP, 2021B. 9.Migrate 2114A to new CP, 2021B. | Perform re-engineering by doing migration for sites 2105B, 2114A, 1070B & 2791A to new CP, 2021B. **Important Note: 1. Mandatory to perform TSS in order to confirm whether 2114A & 2791A are in the same location/room or nearby each other. If YES, DU 2791A_AD, 2114A_AD and 2105B_AD can be proceed. 2. Need to perform the task in sequence accordingly - firstly do 2791A_AD follow with 2114A_AD and the last 2105B_AD. 3. 2791A_AD, 2114A_AD and 2105B_AD suggest to perform at the same day.** Site Impacted: 2105B, 2114A, 1070B & 2791A. NE_2114A 1.Ensure perform DU 2791A first. 2.Shifting existing ISM8 slot 03 from existing RTN910A/RTN02(HW MW Link 2114A-2105B) to slot 03 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). Configure it. 3.Also, shifting existing IF cable from existing ISM8 slot 03 from existing RTN910A/RTN02(HW MW Link 2114A-2105B) to slot 03 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). If short, lay new IF cable from ODU to slot 03 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 4.Disconnect existing cascading from port 8-EM6-2 of existing RTN910A/RTN02(HW MW Link 2114A-2105B) to port 8-EM6-1 of existing HW MW Link ID_CT10100(W01311-W00074). 5.Enable port 8-EM6-5 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 6.Insert new Optical SFP Module 1.25G 10Km into port 8-EM6-5 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 7.Patching BBU 2114A to port 8-EM6-5 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 8.Request new xD vlan services and vlan dcn to new CP, 2021B. 9.Migrate 2114A to new CP, 2021B. | [6 empty] | Magicell | SQ202508010572-Magicell | Magicell | SQ202507190092-Magicell // SQ202509260748-Magicell | 2025-12-01 | 2025-11-26 | Completed | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-08 | 2025-08-15 | 2025-08-08 | 2025-08-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-12-01 | 2025-11-24 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070407 |  | 2025-07-06 | 2025-07-08 | Completed | 2025-07-05 | 2025-07-06 | 2025-07-05 | 2025-07-08 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-05 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-05 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-01 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-05 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | 2026-01-09: 2025-07-24; 2026-01-09: 2025-07-24; 2026-01-09: 2025-07-24; 2026-01-13: 2025-08-05 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505280699-GTSB
1309A_IPR | Ivory | DU00005618999 | Central | Selangor | 3.221047 | 101.638491 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Already MOCN. Current utilization under DU00002751999 is 40% Only. | [13 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202505280699-GTSB
1005A_AD | Tmn Melati | DU00005619000 | Central | Kuala Lumpur | 3.225550 | 101.727500 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | NE_1005A/W00184 1x New SFP Module 10G with 1Km 1310nm or suitable SFP Module(get advise from ZTE IPRAN Team). 1x Pair of new Optical Patch Cord cable with suitable type and length(get advise from ZTE IPRAN Team). | MW IDU Patching | Migrate all child sites including 1005A to xC PTN/Cisco at W00184 due to xD Fiber cut issue toward existing CP, 2070B. Site Impacted: 1005A,3142C,1151C,1401C,1724C,3246D,3509B,3707A & 1029L. NE_1005A/W00184 1.Request and new 10G port of PTN/Cisco from ZTE IPRAN Team. 2.Insert Optical SFP Module 10G with 1Km 1310nm into new port requested at PTN/Cisco. 3.Disconnect and remove the existing patch cord at existing port 8-EM6-3 of existing RTN910A(RTN06). (Patch cord from existing CP, 2070B) 4.Patching new patch cord at existing port 8-EM6-3 of existing RTN910A(RTN06) to new port at PTN/Cisco. 5.Request new xC vlan dcn and new xC vlan services from ZTE IPRAN Team for all sites impacted such as 1005A,3142C,1151C,1401C,1724C,3246D,3509B,3707A & 1029L. 6.Migrate all sites impacted to xC PTN/Cisco at W00184. | Migrate all child sites including 1005A to xC PTN/Cisco at W00184 due to xD Fiber cut issue toward existing CP, 2070B. Site Impacted: 1005A,3142C,1151C,1401C,1724C,3246D,3509B,3707A & 1029L. NE_1005A/W00184 1.Request and new 10G port of PTN/Cisco from ZTE IPRAN Team. 2.Insert Optical SFP Module 10G with 1Km 1310nm into new port requested at PTN/Cisco. 3.Disconnect and remove the existing patch cord at existing port 8-EM6-3 of existing RTN910A(RTN06). (Patch cord from existing CP, 2070B) 4.Patching new patch cord at existing port 8-EM6-3 of existing RTN910A(RTN06) to new port at PTN/Cisco. 5.Request new xC vlan dcn and new xC vlan services from ZTE IPRAN Team for all sites impacted such as 1005A,3142C,1151C,1401C,1724C,3246D,3509B,3707A & 1029L. 6.Migrate all sites impacted to xC PTN/Cisco at W00184. | [6 empty] | Magicell | SQ202507230730-Magicell | Magicell | SQ202507190092-Magicell | 2025-12-01 | 2025-11-26 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-24 | 2025-12-01 | 2025-11-24 | 2025-11-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070408 |  | 2025-07-06 | 2025-07-08 | Completed | 2025-07-05 | 2025-07-06 | 2025-07-05 | 2025-07-08 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-22 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-25 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-22 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-24 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | 2026-01-09: 2025-07-21; 2026-01-09: 2025-07-21; 2026-01-09: 2025-07-21; 2026-01-13: 2025-07-22 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505280699-GTSB
2105B_AD | Hartamas Regency | DU00005619001 | Central | Kuala Lumpur | 3.172858 | 101.663336 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW Re-engineering | Perform re-engineering by doing migration for sites 2105B, 2114A, 1070B & 2791A to new CP, 2021B. **Important Note: 1. Mandatory to perform TSS in order to confirm whether 2114A & 2791A are in the same location/room or nearby each other. If YES, DU 2791A_AD, 2114A_AD and 2105B_AD can be proceed. 2. Need to perform the task in sequence accordingly - firstly do 2791A_AD follow with 2114A_AD and the last 2105B_AD. 3. 2791A_AD, 2114A_AD and 2105B_AD suggest to perform at the same day.** Site Impacted: 2105B, 2114A, 1070B & 2791A. NE_2105B 1.Ensure perform DU 2791A and 2114A_AD. 2.Request new xD vlan services and vlan dcn to new CP, 2021B. 3.Migrate 2105B & 1070B to new CP, 2021B. | Perform re-engineering by doing migration for sites 2105B, 2114A, 1070B & 2791A to new CP, 2021B. **Important Note: 1. Mandatory to perform TSS in order to confirm whether 2114A & 2791A are in the same location/room or nearby each other. If YES, DU 2791A_AD, 2114A_AD and 2105B_AD can be proceed. 2. Need to perform the task in sequence accordingly - firstly do 2791A_AD follow with 2114A_AD and the last 2105B_AD. 3. 2791A_AD, 2114A_AD and 2105B_AD suggest to perform at the same day.** Site Impacted: 2105B, 2114A, 1070B & 2791A. NE_2105B 1.Ensure perform DU 2791A and 2114A_AD. 2.Request new xD vlan services and vlan dcn to new CP, 2021B. 3.Migrate 2105B & 1070B to new CP, 2021B. | [6 empty] | Magicell | SQ202506260667-Magicell | Magicell | SQ202506260705-Magicell | 2025-11-29 | 2025-11-22 | Completed | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-08 | 2025-08-15 | 2025-08-08 | 2025-08-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070124 |  | 2025-07-02 | 2025-07-03 | Completed | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-03 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-04 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-06 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-04 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-06 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | 2026-01-09: 2025-07-24; 2026-01-09: 2025-07-24; 2026-01-09: 2025-07-24; 2026-01-13: 2025-08-04 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505280699-GTSB
2791A_AD | Soho KL IB | DU00005619002 | Central | Kuala Lumpur | 3.175370 | 101.660210 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | New CAT6 cable with suitable length x2.(For LL and BBU 2791A) | MW IDU Patching | Perform re-engineering by doing migration for sites 2105B, 2114A, 1070B & 2791A to new CP, 2021B. **Important Note: 1. Mandatory to perform TSS in order to confirm whether 2114A & 2791A are in the same location/room or nearby each other. If YES, DU 2791A_AD, 2114A_AD and 2105B_AD can be proceed. 2. Need to perform the task in sequence accordingly - firstly do 2791A_AD follow with 2114A_AD and the last 2105B_AD. 3. 2791A_AD, 2114A_AD and 2105B_AD suggest to perform at the same day.** Site Impacted: 2105B, 2114A, 1070B & 2791A. NE_2791A 1.Enable port port 8-EM6-1 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 2.Disconnect existing TDC LL from BBU 2791A and patching to port 8-EM6-1 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 3.Enable port 8-EM6-2 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 4.Patching BBU 2791A to port 8-EM6-2 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 5.Request new xD vlan services to new CP, 2021B. 6.Create new In Band DCN for existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 7.Migrate 2791A to new CP, 2021B. | Perform re-engineering by doing migration for sites 2105B, 2114A, 1070B & 2791A to new CP, 2021B. **Important Note: 1. Mandatory to perform TSS in order to confirm whether 2114A & 2791A are in the same location/room or nearby each other. If YES, DU 2791A_AD, 2114A_AD and 2105B_AD can be proceed. 2. Need to perform the task in sequence accordingly - firstly do 2791A_AD follow with 2114A_AD and the last 2105B_AD. 3. 2791A_AD, 2114A_AD and 2105B_AD suggest to perform at the same day.** Site Impacted: 2105B, 2114A, 1070B & 2791A. NE_2791A 1.Enable port port 8-EM6-1 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 2.Disconnect existing TDC LL from BBU 2791A and patching to port 8-EM6-1 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 3.Enable port 8-EM6-2 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 4.Patching BBU 2791A to port 8-EM6-2 of existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 5.Request new xD vlan services to new CP, 2021B. 6.Create new In Band DCN for existing RTN910A of existing HW MW Link ID_CT10100(W01311-W00074). 7.Migrate 2791A to new CP, 2021B. | [6 empty] | Magicell | SQ202508010572-Magicell | Magicell | SQ202507190092-Magicell | 2025-11-29 | 2025-11-22 | Completed | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-08 | 2025-08-15 | 2025-08-08 | 2025-08-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070409 |  | 2025-07-06 | 2025-07-08 | Completed | 2025-07-05 | 2025-07-06 | 2025-07-05 | 2025-07-08 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-01 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-05 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | Magicell TI | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-08-01 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-08-05 | MUHAMMAD HAZIQ ASYRANI/BIN/FAIRUL NIZAM/7018000298 | 2026-01-09: 2025-07-24; 2026-01-09: 2025-07-24; 2026-01-09: 2025-07-24; 2026-01-13: 2025-08-02 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202505280699-GTSB
4733D_HU | Taman Sri Putra | DU00005661804 | Northern | Kedah | 6.101983 | 100.287315 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_1+0_110M_512QAM NE_4733D New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN01, NEID 44-13745). New ISM8 x1. New XMC_5D Pro, Sub B_Hi x1. FE_4277B/K00126 New 18G_0.6M(MDD) x1. Re-use existing RTN910AF(RTN02, NEID 44-23745). New ISM8 x1. New XMC_5D Pro, Sub B_Lo x1. | MW Swap | ****IMPORTANT NOTE: 1.PLEASE CHECK LOS FIRST FOR EXISTING HW MW LINK AS CURRENT MW LINK HAVING RSL DEGRADED BELOW -50DBM. JUST TO BE SURE NO LOS BLOCK BEFORE INSTALL NEW SWAP LINK.**** Existing HW MW Link_4733D-4277B, 23G_1+0_56MHZ_512QAM_450M. MW Swap to new HW MW Link 4733D-4277B, 18G_1+0_110MHZ_512QAM. Later, decom Antenna, ODU of HW MW Link_4733D-4277B, 23G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 44-13745) and RTN910AF(RTN02, NEID 44-23745). Site Impacted : 4733D. NE_4733D 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-13745) and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Configure it. 4.Re-use existing xC vlan dcn and vlan services. 5.Migrate traffic 4733D via new HW MW Link 4733D-4277B, 18G_1+0_110MHZ_512QAM. 6.Later, decom Antenna, ODU of HW MW Link_4733D-4277B, 23G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 44-13745) and RTN910AF(RTN02, NEID 44-23745). FE_4277B/K00126 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 44-23745) and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Re-use existing xC vlan dcn and vlan services. 5.Migrate traffic 4733D via existing port of PTN/Cisco Router. 6.Later, decom Antenna, ODU of HW MW Link_4733D-4277B, 23G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 44-13745) and RTN910AF(RTN02, NEID 44-23745). | ****IMPORTANT NOTE: 1.PLEASE CHECK LOS FIRST FOR EXISTING HW MW LINK AS CURRENT MW LINK HAVING RSL DEGRADED BELOW -50DBM. JUST TO BE SURE NO LOS BLOCK BEFORE INSTALL NEW SWAP LINK.**** Existing HW MW Link_4733D-4277B, 23G_1+0_56MHZ_512QAM_450M. MW Swap to new HW MW Link 4733D-4277B, 18G_1+0_110MHZ_512QAM. Later, decom Antenna, ODU of HW MW Link_4733D-4277B, 23G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 44-13745) and RTN910AF(RTN02, NEID 44-23745). Site Impacted : 4733D. NE_4733D 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN01, NEID 44-13745) and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Hi x1. Configure it. 4.Re-use existing xC vlan dcn and vlan services. 5.Migrate traffic 4733D via new HW MW Link 4733D-4277B, 18G_1+0_110MHZ_512QAM. 6.Later, decom Antenna, ODU of HW MW Link_4733D-4277B, 23G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 44-13745) and RTN910AF(RTN02, NEID 44-23745). | ****IMPORTANT NOTE: 1.PLEASE CHECK LOS FIRST FOR EXISTING HW MW LINK AS CURRENT MW LINK HAVING RSL DEGRADED BELOW -50DBM. JUST TO BE SURE NO LOS BLOCK BEFORE INSTALL NEW SWAP LINK.**** Existing HW MW Link_4733D-4277B, 23G_1+0_56MHZ_512QAM_450M. MW Swap to new HW MW Link 4733D-4277B, 18G_1+0_110MHZ_512QAM. Later, decom Antenna, ODU of HW MW Link_4733D-4277B, 23G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 44-13745) and RTN910AF(RTN02, NEID 44-23745). Site Impacted : 4733D. FE_4277B/K00126 1.Install new 18G_0.6M(MDD) x1. 2.Re-use existing RTN910AF(RTN02, NEID 44-23745) and insert new ISM8 into slot 03. 3.Install new XMC_5D Pro, Sub B_Lo x1. Configure it. 4.Re-use existing xC vlan dcn and vlan services. 5.Migrate traffic 4733D via existing port of PTN/Cisco Router. 6.Later, decom Antenna, ODU of HW MW Link_4733D-4277B, 23G_1+0_56MHZ_512QAM_450M. Anyway, do not decom RTN910AF(RTN01, NEID 44-13745) and RTN910AF(RTN02, NEID 44-23745). | XMC_5D Pro | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_0.6M(MDD) x1. | GTSB | SQ202601130151-GTSB | GTSB | SQ202601130143-GTSB // SQ202601130146-GTSB | 2026-03-02 | 2026-02-23 | Completed | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-16 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-13 | 2026-02-20 | 2026-02-13 | 2026-02-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-02-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25123094 |  | 2025-12-31 | 2026-01-10 | Completed | 2025-12-30 | 2025-12-31 | 2025-12-30 | 2026-01-10 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-15 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-15 | HAMZAH BIN ABDUL MUTALIF6799000301 | GTSB TI | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | AKMAL//BIN RAZALI/6794000078 |  | 2026-01-16 | 2026-01-14 | 2026-01-31 | 2026-01-14 | 2026-01-21 | HAMZAH BIN ABDUL MUTALIF6799000301 | 2026-01-09: 2026-01-14; 2026-01-09: 2026-01-31; 2026-01-09: 2026-01-14; 2026-01-13: 2026-01-15 |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 | 2026-04-25 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506160768-GTSB | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | MAZELAN BIN RAMLI6798000096
7586A_HU | Kg. Suan Lamba SBC | DU00005661805 | Sabah | Sabah | 5.646599 | 118.128209 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 2x ISM8 2X 1.2M MDD ANTENNA (13G) 1x ODU 13G XMC-5D SB_A HI 1x ODU 13G XMC-5D SB_A LO | MW Parallel Link | Install 13G_2+0_512Qam_28Mhz_448Mbps Parallel with existing link existing 15G_4+0 Config EPLA Impact site: 7745B, 7127K, 7747B | NE: 1. Install new ISM8 to existing RTN910A 2. Install new 13G 1.2m MDD Antenna 3. Install new 13G XMC-5D sb A 4. Configure link 13G 2+0_28MHZ_512QAM 5. Config EPLA with existing link 15G_4+0 | FE: 1. Install new ISM8 to existing RTN910A 2. Install new 13G 1.2m MDD Antenna 3. Install new 13G XMC-5D sb A 4. Configure link 13G 2+0_28MHZ_512QAM 5. Config EPLA with existing link 15G_4+0 | XMC-5D | MDD | 13G | 1.2m | 1.2m | NR services | SQ202509240996-NR Services | NR services | SQ202509240979-NR Services // SQ202509240984-NR Services | 2025-10-31 | 2025-10-28 | Completed | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-02 | 2025-10-03 | 2025-10-02 | 2025-10-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-02 | 2025-10-03 | 2025-10-02 | 2025-10-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-31 | 2025-10-28 | 2025-10-28 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250908AM |  | 2025-09-09 | 2025-09-17 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-17 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-28 | 2025-10-28 | 2025-09-28 | 2025-10-01 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-09-28 | 2025-10-28 | 2025-09-28 | 2025-10-07 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | NR Service TI | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-01 | 2025-09-28 | 2025-10-28 | 2025-09-28 | 2025-10-06 | MOHD//AZWAN SHAH BIN ABDUL HAMID/7167000017 | 2026-01-09: 2025-09-28; 2026-01-09: 2025-10-28; 2026-01-09: 2025-09-28; 2026-01-13: 2025-09-30 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506160769-GTSB | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | AB.RAHMAN//BIN MAT NOOH/6237001519
4741A_HU | Makam Mahsuri (KM Rel) | DU00005661806 | Northern | Kedah | 6.356406 | 99.773506 | [7 empty] | 00. Integrated/RFS Done | 14/07 : CO Done | AA | PAC |  | MW Remote Upgrade | Exsiting 18G_2+0_512Qam_56Mhz upgrade to 18G_2+0_256Qam_112Mhz_1556Mhz | Remote upgrade from exsiting 18G_2+0_512Qam_56Mhz upgrade to 18G_2+0_256Qam_112Mhz_1556Mhz follow LB | Remote upgrade from exsiting 18G_2+0_512Qam_56Mhz upgrade to 18G_2+0_256Qam_112Mhz_1556Mhz follow LB | XMC-5D | MDD | 18G | 0.6m | 0.6m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-07-14 | [15 empty] | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506160768-GTSB | 2025-06-29 | 2025-06-29 | 2025-06-29 | 2025-06-29 | AB.RAHMAN//BIN MAT NOOH/6237001519
4339K_HU | R001C_R00075OD_KGTANAHTIMBUL | DU00005670660 | Northern | Perlis | 6.262730 | 100.192181 | [7 empty] | 00. Integrated/RFS Done | 14/07 : CO Done | AA | PAC |  | MW Remote Upgrade | Exsiting 18G_1+0_512Qam_56Mhz upgrade to 18G_1+0_256Qam_112Mhz_778Mhz | Remote upgrade from exsiting 18G_1+0_512Qam_56Mhz upgrade to 18G_1+0_256Qam_112Mhz_778Mhz follow LB | Remote upgrade from exsiting 18G_1+0_512Qam_56Mhz upgrade to 18G_1+0_256Qam_112Mhz_778Mhz follow LB | XMC-3E | MAC | 18G | 0.6m | 0.6m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-07-14 | [15 empty] | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506160768-GTSB | 2025-06-29 | 2025-06-29 | 2025-06-29 | 2025-06-29 | AB.RAHMAN//BIN MAT NOOH/6237001519
4058P_HU | SKLAMDIN | DU00005670661 | Northern | Kedah | 6.097774 | 100.687333 | [7 empty] | 00. Integrated/RFS Done | 27/8: waiting CCS for missing item 22/8: change to MTK, mos & start install 26/8 | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2x RTN910A 2x ISM8 2X 1.2M MDD ANTENNA (15G) 1x ODU 15G XMC-5D SB_A HI 1x ODU 15G XMC-5D SB_A LO | MW Swap | Existing is 15G_1+0_229Mps_util 100% MW SWAP LINK 4058P-K00833 WITH HUAWEI_15G_2+0_28MHZ_512QAM_448Mbps_1.2M/1.2M_MDD_XMC-5D_SUB A_4.35KM Impacted Site: 4058P Dismantle existing SP antenna and old ODU | NE: 1. Install RTN910A 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND A 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. DISMANTLE existing SP antenna and old ODU | FE: 1. Install RTN910A 2. INSTALL NEW 15G 1.2M MDD ANTENNA 3. INSTALL NEW 15G XMC-5D SUB BAND A 4. CONFIGURE LINK 15G 2+0 28MHZ 512QAM 5. DISMANTLE existing SP antenna and old ODU | XMC-5D | MDD | 15G | 1.2m | 1.2m | MTK | SQ202508250295-MTK | MTK | SQ202509020120-MTK // SQ202509020136-MTK |  |  | Ongoing | 2025-09-10 | 2026-04-01 | 2026-04-01 | 2026-04-01 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | NURUL NADIRAH BINTI MOHAMAD ZAM ZAM8225000008 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25071147 |  | 2025-07-12 | 2025-07-16 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-16 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-01-09 | 2026-01-21 | 2025-09-10 | 2026-01-10 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2026-01-09 | 2026-01-21 | 2025-09-10 | 2026-03-01 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | AKMAL//BIN RAZALI/6794000078 |  | 2025-11-01 | 2026-01-09 | 2026-01-21 | 2026-03-01 | 2026-03-01 | DZULFAIZAL//BIN MAULUF/8225000001 | 2026-01-09 | 2026-01-21 | 2026-01-09 | 2026-01-09 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | NG HONG JIE7018000036 | Logistic Team | 2025-12-15 | 2026-01-15 | 2025-12-15 | 2025-12-15 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506160768-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | AB.RAHMAN//BIN MAT NOOH/6237001519
4040L_HU | Taman Merpati | DU00005670662 | Northern | Kedah | 5.380114 | 100.558292 | [7 empty] | 00. Integrated/RFS Done | 14/07 : CO Done | AA | PAC |  | MW Remote Upgrade | Link Existing HW18G_1+0_56M_512QAM. MW Remote Upgrade to HW 18G_1+0_112M_512QAM. Site Impacted : 4040L NE_4040L 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. FE_4150A 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | Link Existing HW18G_1+0_56M_512QAM. MW Remote Upgrade to HW 18G_1+0_112M_512QAM. Site Impacted : 4040L NE_4040L 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | Link Existing HW18G_1+0_56M_512QAM. MW Remote Upgrade to HW 18G_1+0_112M_512QAM. Site Impacted : 4040L FE_4150A 1.Existing ODU XMC-3E may remotely upgrade to BW 112MHz. | XMC-3E | MAC | 18G | 18G_1.2M(MAC)+OMT x1. | 18G_1.2M(MAC)+OMT x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-07-14 | [15 empty] | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506160768-GTSB | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MAZELAN BIN RAMLI6798000096
7443A_HU | Nabawan RT (REL) | DU00005670663 | Sabah | Sabah | 5.042949 | 116.429455 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_4+0_28M_512QAM_CA NE_7443A New 15G_1.2M(MDD) x1. New RTN910AF(RTN05). New ISM8 x1. New XMC_5D, Sub B_Lo x2. New CAT6 cable x1. FE_7476A New 15G_1.2M(MDD) x1. New RTN910AF(RTN06). New ISM8 x1. New XMC_5D, Sub B_Hi x2. New CAT6 cable x1. | MW Parallel Link | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILD SITES. 3.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Build new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). Site Impacted : 2788B18. NE_7443A 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN05). Insert new ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Lo x2. Build new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). 4.Enable port 8-EM6-1 of new RTN910AF(RTN05). 5.Disconnect/remove existing cascading in between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23378) and port 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-23438). 6.Perform new cascading in between port 8-EM6-1 of new RTN910AF(RTN05) and port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23378). 7.Re-use existing Vlan Services and request new Vlan DCN for RTN910AF(RTN05). 8.Migrate traffic 2788B18 via new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). FE_7476A 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN06). Insert new ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Hi x2. Build new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). 4.Enable port 8-EM6-1 of new RTN910AF(RTN06). 5.Perform new cascading in between port 8-EM6-1 of new RTN910AF(RTN06) and port 8-EM6-2 of existing RTN910AF(RTN05, NEID 9-36032). 6.Re-use existing Vlan Services and request new Vlan DCN for RTN910AF(RTN06). 7.Migrate traffic 2788B18 via new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILD SITES. 3.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Build new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). Site Impacted : 2788B18. NE_7443A 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN05). Insert new ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Lo x2. Build new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). 4.Enable port 8-EM6-1 of new RTN910AF(RTN05). 5.Disconnect/remove existing cascading in between port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23378) and port 8-EM6-2 of existing RTN910AF(RTN02, NEID 9-23438). 6.Perform new cascading in between port 8-EM6-1 of new RTN910AF(RTN05) and port 8-EM6-1 of existing RTN910AF(RTN03, NEID 9-23378). 7.Re-use existing Vlan Services and request new Vlan DCN for RTN910AF(RTN05). 8.Migrate traffic 2788B18 via new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). | ****IMPORTANT NOTE: 1.MANDATORY TO PERFORM TSS IN ORDER TO CONFIRM ANTENNA SPACING AVAILABLE AT NE & FE. 2.NEED TO PERFORM SW VERSION UPGRADE FOR EXISTING RTN950A(RTN01-NEID 19182) R21 TO R23 AND IMPACT TO ALL CHILD SITES. 3.MANDATORY TO PERFORM DU IN SEQUENCES BELOW: 1ST - DU 7443A_HU_1(LINK 1) 2ND - DU 7461A_HU_1 3RD - DU 7476A_AD & 7476A_IPR 4TH - DU 7443A_HU(LINK 2) **** Build new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). Site Impacted : 2788B18. FE_7476A 1.Install new 15G_1.2M(MDD) x1. 2.Install new RTN910AF(RTN06). Insert new ISM8 into slot 03. 3.Install new XMC_5D, Sub B_Hi x2. Build new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). 4.Enable port 8-EM6-1 of new RTN910AF(RTN06). 5.Perform new cascading in between port 8-EM6-1 of new RTN910AF(RTN06) and port 8-EM6-2 of existing RTN910AF(RTN05, NEID 9-36032). 6.Re-use existing Vlan Services and request new Vlan DCN for RTN910AF(RTN06). 7.Migrate traffic 2788B18 via new HW MW Parallel Link 7443A-7476A, 15G_4+0_28MHZ_512QAM_CA(LINK 2). | XMC-5D | MDD | 15G | 15G_1.2M(MDD) x1. | 15G_1.2M(MDD) x1. | NR services | SQ202602250627-NR Services | NR services | SQ202512300312-NR Services // SQ202512300318-NR Services |  |  | Ongoing | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-04 | 2026-03-11 | 2026-03-04 | 2026-03-04 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-03-31 | 2026-04-07 | 2026-03-31 | 2026-03-31 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25121769 |  | 2025-12-18 | 2025-12-21 | Completed | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-21 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-14 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-02-14 | RALPH O'BRYAN HILARY7167000030 | NR Service TI | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2026-02-16 | 2026-02-09 | 2026-03-09 | 2026-02-09 | 2026-03-02 | RALPH O'BRYAN HILARY7167000030 | 2026-01-09: 2026-02-09; 2026-01-09: 2026-03-09; 2026-01-09: 2026-02-09; 2026-01-13: 2026-02-14 |  |  | 2026-03-05 | 2026-04-05 | 2026-03-05 | 2026-03-05 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506160769-GTSB | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | HSU//MYET CHAE/6799000011
7208R_HU | Kg. Kabogan | DU00005670664 | Sabah | Sabah | 4.419182 | 118.611956 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G_4+0_1.2/1.2_MDD_XMC-5D_SB A 1xRTN910A 3xISM8 | MW Swap | MW SWAP 7208R-7207A WITH 15G_4+0_1.2/1.2MDD_XMC-5D_SB A | MW SWAP 7208R-7207A WITH 15G_4+0_1.2/1.2MDD_XMC-5D_SB A NE, 1. Reuse exisitng RTN910A. 2. Install 2xISM8 at slot 3 and 4 3. Install new antenna 15G_1.2MDD. 4. configure 15G_4+0_1.2_512QAM_CA. | MW SWAP 7208R-7207A WITH 15G_4+0_1.2/1.2MDD_XMC-5D_SB A FE, 1. Install new RTN910A. 2. Install 1xISM8 at slot 3. 3. Install new antenna 15G_1.2MDD. 4. configure 15G_4+0_1.2_512QAM_CA. | XMC_5D_A |  | 15 | 1.2 | 1.2 | NR services | SQ202509240996-NR Services | NR services | SQ202509240979-NR Services // SQ202509240984-NR Services | 2026-01-27 | 2026-01-21 | Completed | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | MUDZLIAH//BINTI MUSTOPHA/6798000131 |  | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-20 | 2026-01-27 | 2026-01-20 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250908AL |  | 2025-09-09 | 2025-09-13 | Completed | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-13 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-23 | 2025-11-23 | 2025-10-23 | 2025-11-26 | WILFRED BALANG7167000026 | NR Service TI | 2025-10-23 | 2025-11-23 | 2025-10-23 | 2025-11-26 | WILFRED BALANG7167000026 | NR Service TI | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-11-29 | 2025-10-23 | 2025-11-23 | 2025-10-23 | 2025-12-04 | WILFRED BALANG7167000026 | 2025-10-23 | 2025-11-23 | 2025-10-23 | 2025-11-24 | 2026-02-05 | 2026-02-19 | 2026-02-05 | 2026-02-05 | KARSHAED//BIBI BT ABDUL KARIM/7167000002 | NR Service TI | 2025-12-16 | 2026-01-16 | 2025-12-16 | 2025-12-16 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506160769-GTSB | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | HSU//MYET CHAE/6799000011
7691B_HU | TUN FUAD T3 | DU00005670665 | Sabah | Sabah | 4.620591 | 118.184266 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2xRTN910A 2xXMC-3E_SB A | MW Hardware Upgrade | MW Hardware Upgrade from 18G_56Mhz to 112MHZ. Change ODU to XMC-3E and RTN910A | MW Haredware upgrade from 18G_56Mhz to 112Mhz. NE: 1. Change exisitng RTN950 with new RTN910A. 2. Change exisitng ODU with XMC-3E_SB A. 3. Reuse exisitng 18G antenna. 4. Configure 18G_1+0_512QAM_110Mhz_889M. | MW Haredware upgrade from 18G_56Mhz to 112Mhz. FE: 1. Change exisitng RTN950 with new RTN910A. 2. Change exisitng ODU with XMC-3E_SB A. 3. Reuse exisitng 18G antenna. 4. Configure 18G_1+0_512QAM_110Mhz_889M. | [5 empty] | NR services | SQ202510090436-NR Services | NR services | SQ202509090316-NR Services // SQ202509090323-NR Services | 2025-10-10 | 2025-10-09 | Completed | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-09 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25090204 |  | 2025-09-03 | 2025-09-03 | Completed | 2025-09-02 | 2025-09-03 | 2025-09-02 | 2025-09-03 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-02 | 2025-11-02 | 2025-10-02 | 2025-10-05 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-02 | 2025-11-02 | 2025-10-02 | 2025-10-08 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-08 | 2025-10-02 | 2025-11-02 | 2025-10-02 | 2025-11-03 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-10-02 | 2025-11-02 | 2025-10-02 | 2025-10-04 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | SHAIFUL//RAHMAN BIN FAZUL RAHMAN/7167000028 | NR Service TI | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506160769-GTSB | 2025-07-08 | 2025-07-08 | 2025-07-08 | 2025-07-08 | HSU//MYET CHAE/6799000011
4533D_HU | Kg Besah | DU00005670666 | Northern | Kedah | 5.617921 | 100.753727 | [7 empty] | 00. Integrated/RFS Done | 14/07 : CO Done | AA | PAC |  | MW Remote Upgrade | Link Existing HW18G_1+0_28M_512QAM. MW Remote Upgrade to HW 18G_1+0_112M_512QAM. Site Impacted : 4533D NE_4533D 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz. FE_4955B 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz. | Link Existing HW18G_1+0_28M_512QAM. MW Remote Upgrade to HW 18G_1+0_112M_512QAM. Site Impacted : 4533D NE_4533D 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz. | Link Existing HW18G_1+0_28M_512QAM. MW Remote Upgrade to HW 18G_1+0_112M_512QAM. Site Impacted : 4533D FE_4955B 1.Existing ODU XMC-3 may remotely upgrade to BW 112MHz. | XMC-3 | HAC | 18G | 18G_1.2M(HAC) x1. | 18G_1.2M(HAC) x1. | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | MOHAMAD//HAFIZUL IKHWAN BIN RIDZUAN/7018000061 |  | 2025-07-14 | [15 empty] | 2025-09-26 | 2025-10-26 | 2025-09-26 | 2025-09-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506160768-GTSB | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MAZELAN BIN RAMLI6798000096
1013R_HU | Kg. Alah Batu | DU00005670667 | Central | Selangor | 3.798594 | 101.359370 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | Link Existing HW 18G_1+0_28M_512QAM. MW Remote Upgrade to HW 18G_1+0_56M_512QAM. Site Impacted : 1013R. NE_1013R 1.Existing ODU XMC-3E may remotely upgrade to BW 56MHz. FE_4413B 1.Existing ODU XMC-3E may remotely upgrade to BW 56MHz. | Link Existing HW 18G_1+0_28M_512QAM. MW Remote Upgrade to HW 18G_1+0_56M_512QAM. Site Impacted : 1013R. NE_1013R 1.Existing ODU XMC-3E may remotely upgrade to BW 56MHz. | Link Existing HW 18G_1+0_28M_512QAM. MW Remote Upgrade to HW 18G_1+0_56M_512QAM. Site Impacted : 1013R. FE_4413B 1.Existing ODU XMC-3E may remotely upgrade to BW 56MHz. | XMC-3E | MAC | 18G | 18G_0.6M(MAC) x1. | 18G_0.6M(MAC) x1. |  |  | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-07 | [15 empty] | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202506160766-GTSB
A00248_HU | A043B_A00248OD_TMSEGARI | DU00005670668 | Northern | Perak | 4.270385 | 100.654316 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 18G_2+0_56M_EPLA NE_A00248 New 18G_0.6M(MDD) x1. New RTN910A(RTN01). New XMC_5D, Sub B_Lo x1. FE_4709B New 18G_0.6M(MDD) x1. New RTN910A(RTN01). New XMC_5D, Sub B_Hi x1. New 2xSFP Module 1G or 10G 1310nm 10Km or 40Km(Please get info from ZTE IPRAN Team for current usage whether 4709B use 1G or 10G). New 2x pair of Fiber Patchcord with suitable type and length(or equivalent). | MW New Link / Reroute | Existing HW MW Link ID_NT02760 A00248-A00404, 15G_1+0_28MHZ_256QAM_183M. Install new HW MW Link A00248(RTN01)-4709B(RTN01), 18G_2+0_56MHZ_256QAM_EPLA. **IMPORTANT NOTE: PLEASE PROCEED PERFORM LOS SURVEY FIRST FOR A00248 TO 4709B IN ORDER TO CONFIRM LOS CLEARANCES OBTAIN 100%. IF NO LOS CLEARANCES 100%, NEED TO FIND OTHER SUITABLE CANDIDATE FOR FE SITE** Later, decom existing HW MW Link ID_NT02760 A00248-A00404, 15G_1+0_28MHZ_256QAM_183M. Site Impacted : A00248. NE_A00248 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Create new In Band DCN. 7.Request new xD vlan services and using similar port at CP/IBeam(4409A) with existing traffic(4709B). 8.Migrate traffic A00248 via new HW MW Link A00248(RTN01)-4709B(RTN01), 18G_2+0_56MHZ_256QAM_EPLA. 9.Decom existing HW MW Link ID_NT02760 A00248-A00404, 15G_1+0_28MHZ_256QAM_183M. FE_4709B 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Please obtain info from ZTE IPRAN Team whether existing traffic for 4709B using Optical 1G or 10G. 5.If Optical 1G, need to enable port 8-EM6-6 of new RTN910A(RTN01) and insert Optical SFP Module 1G. 6.Patching BBU 4709B at port 8-EM6-6 of new RTN910A(RTN01). Configure it. 7.OR if Optical 10G, need to enable port 8-EM6-4 of new RTN910A(RTN01) and insert Optical SFP Module 10G. 8.Patching BBU 4709B at port 8-EM6-4 of new RTN910A(RTN01). Configure it. 9.BBU 4709B will remain use same vlan services and using existing port at CP/IBeam(4409A). 10.Similar to uplink, if Optical 1G, need to enable port 8-EM6-5 of new RTN910A(RTN01) and insert Optical SFP Module 1G. 11.Patching existing OB Fiber at port 8-EM6-5 of new RTN910A(RTN01). Configure it. 12.OR if Optical 10G, need to enable port 8-EM6-3 of new RTN910A(RTN01) and insert Optical SFP Module 10G. 13.Patching existing OB Fiber at port 8-EM6-3 of new RTN910A(RTN01). Configure it. 14.Create new In Band DCN. 15.Request new xD vlan services and using similar port at CP/IBeam(4409A) with existing traffic(4709B). 16.Migrate traffic A00248 via new HW MW Link A00248(RTN01)-4709B(RTN01), 18G_2+0_56MHZ_256QAM_EPLA. 17.Decom existing HW MW Link ID_NT02760 A00248-A00404, 15G_1+0_28MHZ_256QAM_183M. | Existing HW MW Link ID_NT02760 A00248-A00404, 15G_1+0_28MHZ_256QAM_183M. Install new HW MW Link A00248(RTN01)-4709B(RTN01), 18G_2+0_56MHZ_256QAM_EPLA. **IMPORTANT NOTE: PLEASE PROCEED PERFORM LOS SURVEY FIRST FOR A00248 TO 4709B IN ORDER TO CONFIRM LOS CLEARANCES OBTAIN 100%. IF NO LOS CLEARANCES 100%, NEED TO FIND OTHER SUITABLE CANDIDATE FOR FE SITE** Later, decom existing HW MW Link ID_NT02760 A00248-A00404, 15G_1+0_28MHZ_256QAM_183M. Site Impacted : A00248. NE_A00248 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Lo. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Patching BBU at port 8-EM6-1 of new RTN910A(RTN01). Configure it. 6.Create new In Band DCN. 7.Request new xD vlan services and using similar port at CP/IBeam(4409A) with existing traffic(4709B). 8.Migrate traffic A00248 via new HW MW Link A00248(RTN01)-4709B(RTN01), 18G_2+0_56MHZ_256QAM_EPLA. 9.Decom existing HW MW Link ID_NT02760 A00248-A00404, 15G_1+0_28MHZ_256QAM_183M. | Existing HW MW Link ID_NT02760 A00248-A00404, 15G_1+0_28MHZ_256QAM_183M. Install new HW MW Link A00248(RTN01)-4709B(RTN01), 18G_2+0_56MHZ_256QAM_EPLA. **IMPORTANT NOTE: PLEASE PROCEED PERFORM LOS SURVEY FIRST FOR A00248 TO 4709B IN ORDER TO CONFIRM LOS CLEARANCES OBTAIN 100%. IF NO LOS CLEARANCES 100%, NEED TO FIND OTHER SUITABLE CANDIDATE FOR FE SITE** Later, decom existing HW MW Link ID_NT02760 A00248-A00404, 15G_1+0_28MHZ_256QAM_183M. Site Impacted : A00248. FE_4709B 1.Install new 18G_0.6M(MDD) x1. 2.Install new RTN910A(RTN01) x1. 3.Install new 1x XMC_5D, Sub B_Hi. Configure it. 4.Please obtain info from ZTE IPRAN Team whether existing traffic for 4709B using Optical 1G or 10G. 5.If Optical 1G, need to enable port 8-EM6-6 of new RTN910A(RTN01) and insert Optical SFP Module 1G. 6.Patching BBU 4709B at port 8-EM6-6 of new RTN910A(RTN01). Configure it. 7.OR if Optical 10G, need to enable port 8-EM6-4 of new RTN910A(RTN01) and insert Optical SFP Module 10G. 8.Patching BBU 4709B at port 8-EM6-4 of new RTN910A(RTN01). Configure it. 9.BBU 4709B will remain use same vlan services and using existing port at CP/IBeam(4409A). 10.Similar to uplink, if Optical 1G, need to enable port 8-EM6-5 of new RTN910A(RTN01) and insert Optical SFP Module 1G. 11.Patching existing OB Fiber at port 8-EM6-5 of new RTN910A(RTN01). Configure it. 12.OR if Optical 10G, need to enable port 8-EM6-3 of new RTN910A(RTN01) and insert Optical SFP Module 10G. 13.Patching existing OB Fiber at port 8-EM6-3 of new RTN910A(RTN01). Configure it. 14.Create new In Band DCN. 15.Request new xD vlan services and using similar port at CP/IBeam(4409A) with existing traffic(4709B). 16.Migrate traffic A00248 via new HW MW Link A00248(RTN01)-4709B(RTN01), 18G_2+0_56MHZ_256QAM_EPLA. 17.Decom existing HW MW Link ID_NT02760 A00248-A00404, 15G_1+0_28MHZ_256QAM_183M. | XMC_5D | MDD | 18G | 18G_0.6M(MDD) x1. | 18G_0.6M(MDD) x1. | GCI | SQ202512170161-GCI | GCI | SQ202508270947-GCI // SQ202508270956-GCI | 2026-01-26 | 2026-01-21 | Completed | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-16 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-21 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25081272 |  | 2025-08-16 | 2025-08-14 | Completed | 2025-08-15 | 2025-08-16 | 2025-08-12 | 2025-08-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-12-03 | 2025-12-09 | 2025-12-03 | 2025-12-13 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-12-03 | 2025-12-09 | 2025-12-03 | 2025-12-20 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-10 | 2025-12-03 | 2025-12-09 | 2025-12-03 | 2026-04-08 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-12-03 | 2025-12-09 | 2025-12-03 | 2025-12-20 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | NG HONG JIE7018000036 | Logistic Team | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506160768-GTSB | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | MAZELAN BIN RAMLI6798000096
4780B_HU | Felda Besout 5 | DU00005670669 | Northern | Perak | 3.717778 | 101.299773 | [7 empty] | 00. Integrated/RFS Done | 23/07: Pending Antenna 2.4/1.8 DO | TSS+AA+TI | L1+ATP+PAC | 13G_2+0_28M_EPLA NE_4780B New 13G_1.8M(MDD) x1. Re-use existing RTN910A(RTN01) New ISM8 x1. New XMC_5D, Sub B_Lo x2. FE_A00553 New 13G_1.8M(MDD) x1. New 13G FlexiWG x2. Re-use existing RTN910A(RTN02). New ISM8 x1. New XMC_5D, Sub B_Hi x2. | MW Parallel Link | Existing HW Link 13G_3+0_28MHz_256QAM_EPLA. Build new parallel link, HW MW Link 13G_2+0_28MHz_512QAM_EPLA. Combine existing HW MW Link and new HW MW Link and become HW MW Link 13G_5+0_28MHz_256QAM&512QAM_EPLA. Site Impacted : 4780B & 4051B_8. NE_4780B 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910A(RTN01). 3.Insert new ISM8 into slot 04 of existing RTN910A(RTN01). 4.Install new 2x XMC_5D, Sub B_Lo and using ISM8 slot 04 port 1 & 2 of existing RTN910A(RTN01). Configure it. 5.Configure EPLA for existing 13G_3+0_28MHz_256QAM and new 13G_2+0_28MHz_256QAM. Ensure modulation configured 256QAM. 6.Remain using existing vlan services for traffics 4780B & 4051B_8. FE_A00553 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910A(RTN02). 3.Insert new ISM8 into slot 04 of existing RTN910A(RTN02). 4.Install new 2x XMC_5D, Sub B_Hi and using ISM8 slot 04 port 1 & 2 of existing RTN910A(RTN02). Configure it. 5.Configure EPLA for existing 13G_3+0_28MHz_256QAM and new 13G_2+0_28MHz_256QAM. Ensure modulation configured 256QAM. 6.Remain using existing vlan services and existing PTN/Cisco port for traffics 4780B & 4051B_8. | Existing HW Link 13G_3+0_28MHz_256QAM_EPLA. Build new parallel link, HW MW Link 13G_2+0_28MHz_512QAM_EPLA. Combine existing HW MW Link and new HW MW Link and become HW MW Link 13G_5+0_28MHz_256QAM&512QAM_EPLA. Site Impacted : 4780B & 4051B_8. NE_4780B 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910A(RTN01). 3.Insert new ISM8 into slot 04 of existing RTN910A(RTN01). 4.Install new 2x XMC_5D, Sub B_Lo and using ISM8 slot 04 port 1 & 2 of existing RTN910A(RTN01). Configure it. 5.Configure EPLA for existing 13G_3+0_28MHz_256QAM and new 13G_2+0_28MHz_256QAM. Ensure modulation configured 256QAM. 6.Remain using existing vlan services for traffics 4780B & 4051B_8. | Existing HW Link 13G_3+0_28MHz_256QAM_EPLA. Build new parallel link, HW MW Link 13G_2+0_28MHz_512QAM_EPLA. Combine existing HW MW Link and new HW MW Link and become HW MW Link 13G_5+0_28MHz_256QAM&512QAM_EPLA. Site Impacted : 4780B & 4051B_8. FE_A00553 1.Install new 13G_1.8M(MDD) x1. 2.Re-use existing RTN910A(RTN02). 3.Insert new ISM8 into slot 04 of existing RTN910A(RTN02). 4.Install new 2x XMC_5D, Sub B_Hi and using ISM8 slot 04 port 1 & 2 of existing RTN910A(RTN02). Configure it. 5.Configure EPLA for existing 13G_3+0_28MHz_256QAM and new 13G_2+0_28MHz_256QAM. Ensure modulation configured 256QAM. 6.Remain using existing vlan services and existing PTN/Cisco port for traffics 4780B & 4051B_8. | XMC_5D | MDD | 13G | 13G_1.8M(MDD) x1 | 13G_1.8M(MDD) x1 | GCI | SQ202508290691-GCI | GCI | SQ202507290116-GCI // SQ202507290119-GCI | 2025-12-25 | 2025-12-22 | Completed | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-05 | 2025-11-12 | 2025-11-05 | 2025-11-05 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-22 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071150 |  | 2025-07-12 | 2025-07-15 | Completed | 2025-07-11 | 2025-07-12 | 2025-07-11 | 2025-07-15 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-08-04 | 2025-08-25 | 2025-08-04 | 2025-08-13 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-08-04 | 2025-08-25 | 2025-08-04 | 2025-08-21 | MOHD SAIDI BIN ABD RAZAK6800000181 | GCI TI | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | AKMAL//BIN RAZALI/6794000078 |  | 2025-08-06 | 2025-08-04 | 2025-08-25 | 2025-08-04 | 2025-08-23 | MOHD SAIDI BIN ABD RAZAK6800000181 | 2026-01-09: 2025-08-04; 2026-01-09: 2025-08-25; 2026-01-09: 2025-08-04; 2026-01-13: 2025-08-04 |  |  | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202506160768-GTSB | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | MAZELAN BIN RAMLI6798000096
7717E_HU | (7717E)IOIPLANTATIONS SYARIMO 4 (KINABATANGAN)_OB(HW) | DU00006758167 | Sabah | Sabah | 5.386000 | 117.764000 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604280429-GCI
7722E_HU | (7722E)IOIPLANTATIONS UNICO 3 (KINABATANGAN)_OB(HW) | DU00006758168 | Sabah | Sabah | 5.464000 | 118.550000 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604280429-GCI
S02002_HU | CLCLamsoon | DU00006758169 | Sabah | Sabah | 5.248308 | 118.178990 | [9 empty] | TSS+AA+TI+Dismantle |  | 13G_4+0_XPIC_512Q_28Mhz_896Mbps NE: 1x ISM8 1x ODU XMC-5D Pro sb A Lo FE: 1x ISM8 1x ODU XMC-5D Pro sb A Hi | MW Hardware Upgrade | Swap existing ODU-5D to ODU-5D PRO to config XPIC EPLA 13G_4+0_XPIC_512QAM_28Mhz_896Mbps Existing link 13G_2+0_13G_2+0 Impact site: 7010P/S02002 Please confirm at site what antenna size (if other than 1.2m pls inform planner-Rahman) | NE: 1. Install ISM8 card at slot 3 existing IDU 2. Swap existing ODU with new 13G XMC-5D Pro sb A Lo 3. Configure link 13G 4+0 XPIC 28MHZ 512QAM EPLA | FE: 1. Install ISM8 card at slot 3 existing IDU 2. Swap existing ODU with new 13G XMC-5D Pro sb A Hi 3. Configure link 13G 4+0 XPIC 28MHZ 512QAM EPLA | XMC-5D Pro | MDD | 13G | 1.2m | 1.2m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604280376-GTSB | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | AB.RAHMAN//BIN MAT NOOH/6237001519
1002E_AD | Sunway QuarryPOC | DU00006758170 | Central | Selangor | 2.980642 | 101.850300 | [9 empty] | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | IDU NLOS PATCHING AT FE 1263C FROM IDU 1263C RTN01 TO 1263C RTN02 USING ROUTE 1002E-1263C-3239D-1900B-1831B-FIBER-1048A TX ROUTE BEFORE: 1002E-1263C-1900B-1770A TX ROUTE AFTER: 1002E-1263C-3239D-1900B-1831B-FIBER-2715B | IDU NLOS PATCHING AT FE 1263C FROM IDU 1263C RTN01 TO 1263C RTN02 USING ROUTE 1002E-1263C-3239D-1900B-1831B-FIBER-1048A TX ROUTE BEFORE: 1002E-1263C-1900B-1770A TX ROUTE AFTER: 1002E-1263C-3239D-1900B-1831B-FIBER-2715B | IDU NLOS PATCHING AT FE 1263C FROM IDU 1263C RTN01 TO 1263C RTN02 USING ROUTE 1002E-1263C-3239D-1900B-1831B-FIBER-1048A TX ROUTE BEFORE: 1002E-1263C-1900B-1770A TX ROUTE AFTER: 1002E-1263C-3239D-1900B-1831B-FIBER-2715B | [5 empty] | GCI |  | GCI | SQ202605070514-GCI |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | AKMAL//BIN RAZALI/6794000078 |  | 2026-05-04 | [20 empty] | GCI | SQ202604280391-GCI | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
7743E_HU | (7743E)IOIPLANTATIONS LEEPANG 5 (KINABATANGAN)_OB(HW) | DU00006758171 | Sabah | Sabah | 5.546000 | 118.435000 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604280429-GCI
7710E_HU | (7710E)IOIPLANTATIONS MAYVIN 6 (TONGOD)_OB(HW) | DU00006758172 | Sabah | Sabah | 5.479000 | 117.379000 | [27 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202604280429-GCI
Q00518_IPR | Q136A_Q00518OD_CB_PKNROBAN | DU00006758173 | Sarawak | Sarawak | 1.885339 | 111.307224 | [9 empty] | TSS+TI |  | ETH Cat 6 cable x1. | MW IDU Patching | Split traffic at IDU Huawei SW03729 Q00518 PknRoban - Q01190 SgAntu to PTN 30264-PKNROBAN Patch IDU SW03729 Q00518 PknRoban - Q01190 GE5 to new PTN port and transfer site Q01191 to new PTN port Impact site: 1) Q01191 T3_KGGERIGAT | Split traffic at IDU Huawei SW03729 Q00518 PknRoban - Q01190 SgAntu to PTN 30264-PKNROBAN Patch IDU SW03729 Q00518 PknRoban - Q01190 GE5 to new PTN port and transfer site Q01191 to new PTN port Impact site: 1) Q01191 T3_KGGERIGAT | [6 empty] | Allstar |  | Allstar |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY26042807 |  | 2026-04-29 |  | Ongoing | 2026-04-28 | 2026-04-29 | 2026-04-28 |  | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD |  | Assigned | Ongoing | [40 empty] | GCI | SQ202604280442-GCI | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | CHEONG/SENG/WAH/7018000306
7095Z_HU | Tampasak | DU00006758174 | Sabah | Sabah | 5.287740 | 116.894430 | [9 empty] | TSS+AA+TI+Dismantle |  | 13G_4+0_XPIC_512Q_28Mhz_896Mbps NE: 1x RTN910 1x ISM8 1x 13D12MDD 1x ODU XMC-5D Pro sb A Hi 1x ODU XMC-5D Pro sb B Hi 1x Coupler FE: 1x RTN910 1x ISM8 1x 13D18MDD 1x ODU XMC-5D Pro sb A Lo 1x ODU XMC-5D Pro sb B Lo 1x Coupler | MW Swap | Install link 13G_4+0_XPIC_512QAM_28Mhz-896Mbps to be swap with existing link 13G_2+0 Existing link 13G_2+0_13G_2+0_7095Z RTN01 - 7756B RTN01 Impact site: 7757B,7094Z,7091Z,7011D,7092Z Decom existing link 13G_2+0_7095Z RTN01 - 7756B RTN01 Note: Must use different SB ODU to reuse freq ch due to limitation If no space for antenna pls check if possible for hot swap | NE: 1. Install new RTN910 2. Install ISM8 card at slot 3 at new IDU 3. Install new 13G 1.2m MDD ANTENNA 4. Install new 13G XMC-5D sb A & B Hi 5. Configure link 13G 4+0 XPIC 28MHZ 512QAM EPLA 6. Decom existing link 13G_2+0_RTN01 | FE: 1. Install new RTN910 2. Install ISM8 card at slot 3 at new IDU 3. Install new 13G 1.2m MDD ANTENNA 4. Install new 13G XMC-5D sb A & B Lo 5. Configure link 13G 4+0 XPIC 28MHZ 512QAM EPLA 6. Decom existing link 13G_2+0_RTN01 | XMC-5D Pro | MDD | 13G | 1.2m | 1.8m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604280376-GTSB | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | AB.RAHMAN//BIN MAT NOOH/6237001519
1038L_HU | TamanGong Permai | DU00006758175 | Central | Selangor | 2.969352 | 101.383984 | [9 empty] | AA |  |  | MW Remote Upgrade | Link Existing HW 18G_1+0_56M_512QAML. MW Remote Upgrade to HW 18G_1+0_112M_512QAM. Site Impacted : 1038L. NE_1038L 1.Remotely upgrade from 18G_1+0_56M_512QAML to 18G_1+0_112M_512QAM. FE_3404A 1.Remotely upgrade from 18G_1+0_56M_512QAML to 18G_1+0_112M_512QAM. | Link Existing HW 18G_1+0_56M_512QAML. MW Remote Upgrade to HW 18G_1+0_112M_512QAM. Site Impacted : 1038L. NE_1038L 1.Remotely upgrade from 18G_1+0_56M_512QAML to 18G_1+0_112M_512QAM. | Link Existing HW 18G_1+0_56M_512QAML. MW Remote Upgrade to HW 18G_1+0_112M_512QAM. Site Impacted : 1038L. FE_3404A 1.Remotely upgrade from 18G_1+0_56M_512QAML to 18G_1+0_112M_512QAM. | XMC_3E | SP | 18G | 0.6m | 0.6m | GCI |  | GCI |  |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202604280369-GTSB
1799B_IPR | Behrang Ulu | DU00006231392 | Central | Perak | 3.749675 | 101.500972 | [7 empty] | 05. TI WIP |  | TSS+TI |  | 10G SFP Module x2. Fiber Patch cord x2 pairs. | MW IDU Patching | IDU Fiber 1799B-FIBER-1701A port upgrade to 10G. Impact sites: 4924A,A01089,1126D,1107L,1114L,2774C NE (1799B): 1) Install 10G SFP at 1799B-BEHRANG ULU-RTN02 2) Upgrade IDU Fiber 1799B-FIBER-1701A to 10G 3) Remove existing 1G fiber from RTN02 FE (1701A): 1) Install 10G SFP at 1701A-MAC-001 (ops team to assign port. Recommend 0/2/1) 2) Upgrade IDU Fiber 1799B-FIBER-1701A to 10G | IDU Fiber 1799B-FIBER-1701A port upgrade to 10G. Impact sites: 4924A,A01089,1126D,1107L,1114L,2774C NE (1799B): 1) Install 10G SFP at 1799B-BEHRANG ULU-RTN02 2) Upgrade IDU Fiber 1799B-FIBER-1701A to 10G 3) Remove existing 1G fiber from RTN02 | IDU Fiber 1799B-FIBER-1701A port upgrade to 10G. Impact sites: 4924A,A01089,1126D,1107L,1114L,2774C FE (1701A): 1) Install 10G SFP at 1701A-MAC-001 (ops team to assign port. Recommend 0/2/1) 2) Upgrade IDU Fiber 1799B-FIBER-1701A to 10G | [5 empty] | Magicell | SQ202510300097-Magicell | Magicell | SQ202510300094-Magicell |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25102913 |  | 2025-10-31 | 2025-10-30 | Completed | 2025-10-30 | 2025-10-31 | 2025-10-29 | 2025-10-30 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2026-01-29 | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | 2025-11-17 | 2025-11-17 | 2025-11-17 |  | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | Magicell TI | [7 empty] | 2025-11-17 | 2025-11-17 | 2025-11-17 |  | MOHAMAD SYAFIQ BIN BEDUMAN7018000109 | 2026-01-09: 2025-11-17; 2026-01-09: 2025-11-17; 2026-01-09: 2025-11-17 | [7 empty] | GCI | SQ202510300390-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
1150A_IPR | KJS Bukit Rasa | DU00006231393 | Central | Selangor | 3.543080 | 101.641050 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 10G SFP Module x2. Fiber Patch Cord x2 Pairs | MW IDU Patching | IDU Fiber 1150A-FIBER-1146A port upgrade to 10G. Impact sites: 1150A,3643A4,B00459,1169D,B02056. NE (1150A): 1) Install 10G SFP at 1150A-KJS BUKIT RASA-RTN01. 2) Upgrade IDU Fiber 1150A-FIBER-1146A to 10G. 3) Remove existing 1G fiber from RTN01. FE (1146A): 1) Install 10G SFP at 1146A-MAC-001 (ops team to assign port) 2) Upgrade IDU Fiber 1150A-FIBER-1146A to 10G | IDU Fiber 1150A-FIBER-1146A port upgrade to 10G. Impact sites: 1150A,3643A4,B00459,1169D,B02056. NE (1150A): 1) Install 10G SFP at 1150A-KJS BUKIT RASA-RTN01. 2) Upgrade IDU Fiber 1150A-FIBER-1146A to 10G. 3) Remove existing 1G fiber from RTN01. | IDU Fiber 1150A-FIBER-1146A port upgrade to 10G. Impact sites: 1150A,3643A4,B00459,1169D,B02056. FE (1146A): 1) Install 10G SFP at 1146A-MAC-001 (ops team to assign port) 2) Upgrade IDU Fiber 1150A-FIBER-1146A to 10G | [5 empty] | Magicell | SQ202510300097-Magicell | Magicell | SQ202510300094-Magicell | 2026-01-31 | 2026-02-03 | Completed | 2025-11-21 | 2026-01-29 | 2026-01-29 | 2026-01-29 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-29 | 2026-01-30 | 2026-01-29 | 2026-01-29 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-30 | 2026-01-31 | 2026-01-30 | 2026-02-03 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102911 |  | 2025-10-30 | 2025-11-21 | Completed | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-21 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-21 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-28 | AHMAD RASHIDI BIN SAFRI7018000135 | Magicell TI | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-02-11 | AHMAD RASHIDI BIN SAFRI7018000135 | 2026-01-09: 2026-01-22; 2026-01-09: 2026-01-22; 2026-01-09: 2026-01-22; 2026-01-13: 2026-01-23 |  |  | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-15 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202510300390-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
4188A_IPR_1 | Nibong Tebal 2 | DU00006231394 | Northern | Penang | 5.166596 | 100.497963 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | 1.ETH LAN Cable x1. 2. 10G SF Module x2. 3. Fiber patch cord x 1 Pairs. | IDU-IPRAN | Perform LAG at CP site for IDU 4188A-NIBONG TEBAL 2-RTN09 to 4188A-MAC-001 Nibong Tebal 2. Impact sites: 4668C, 4101D. 1) Patch 4188A-NIBONG TEBAL 2-RTN09 new GE port to new CP port (may require optical GE due to no available electrical port at MAC) 2) Create LAG | Perform LAG at CP site for IDU 4188A-NIBONG TEBAL 2-RTN09 to 4188A-MAC-001 Nibong Tebal 2. Impact sites: 4668C, 4101D. 1) Patch 4188A-NIBONG TEBAL 2-RTN09 new GE port to new CP port (may require optical GE due to no available electrical port at MAC) 2) Create LAG | [6 empty] | GTSB | SQ202512160971-GTSB | GTSB | SQ202512160962-GTSB | 2026-01-22 | 2026-01-22 | Completed | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-29 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25102909 |  | 2025-10-30 | 2025-12-13 | Completed | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-12-13 | MHD FARID/BIN/NGADININ ADININ/6000054868 | Magicell TI | MAGICELL SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | GTSB TI | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | AKMAL//BIN RAZALI/6794000078 |  | 2025-12-09 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-13 | MUHAMMAD IQMAL AZIZI BIN MAT NAWI6799000212 | 2026-01-09: 2025-12-08; 2026-01-09: 2025-12-08; 2026-01-09: 2025-12-08; 2026-01-13: 2025-12-09 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202510300396-GCI | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | CHEONG/SENG/WAH/7018000306
2663B-1110A | Kesas Bdr Puteri Klang | DU00005020765 | Central | Selangor | 2.980750 | 101.480000 |  |  |  |  | Cancel / Drop | No need proceed | ZTE | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9566C-9188A | Baladdin (REL) | DU00005020766 | Sarawak | Sarawak | 1.631781 | 111.204366 | [6 empty] | ZTE | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 13G 2+0 1.2m/1.2m MAC DP XMC3 sub A/B NE: 1) 1 x RTN910A 2) 1 x ISM8 cards 3) 1 x 13G XMC3 sub A Hi 4) 1 x 13G XMC3 sub B Hi 5) 1 x 13G 1.2m MAC DP FE: 1) 1 x ISM8 cards 2) 1 x 13G XMC3 sub A Lo 3) 1 x 13G XMC3 sub B Lo 4) 1 x 13G 1.2m MAC DP | MW Parallel Link | Add parallel 2+0 to existing 4+0 link Swap IDU at NE to CSHRF Create 6+0 EPLA NE (9566C): 1) Swap IDU with RTN910A CSHRF 2) Transfer ISM8 slot 3 from old IDU to new IDU 3) Add ISM8 at new IDU slot 4 4) Transfer link from old IDU 7-ISM8 and 3 ISM8 to new IDU 5) Install new link at 4-ISM8 6) Create 6+0 EPLA 7) Migrate traffic to new link/IDU FE (9188A RTN04): 1) Add ISM8 at new IDU slot 4 2) Install new link at 4-ISM8 3) Create 6+0 EPLA | NE (9566C): 1) Swap IDU with RTN910A CSHRF 2) Transfer ISM8 slot 3 from old IDU to new IDU 3) Add ISM8 at new IDU slot 4 4) Transfer link from old IDU 7-ISM8 and 3 ISM8 to new IDU 5) Install new link at 4-ISM8 6) Create 6+0 EPLA 7) Migrate traffic to new link/IDU | FE (9188A RTN04): 1) Add ISM8 at new IDU slot 4 2) Install new link at 4-ISM8 3) Create 6+0 EPLA | XMC3 | MAC DP | 13G | 1.2m | 1.2m | Trintel | SQ202502260453-Trintel | NR Services | SQ202504230267-NR Services // SQ202504230268-NR Services // SQ202504260213-Services | 2025-02-28 | 2025-02-26 | Completed | 2025-02-17 | 2025-02-18 | 2025-02-17 | 2025-02-24 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-02-25 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-26 | 2025-02-28 | 2025-02-26 | 2025-02-26 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25040410 |  | 2025-04-05 | 2025-04-09 | Completed | 2025-04-04 | 2025-04-05 | 2025-04-04 | 2025-04-09 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-04-11 | 2025-04-14 | 2025-04-11 | 2025-04-25 | MOHD FIRDAUS BIN JAMALUDDIN6000006918 | NR Service TI | 2025-04-11 | 2025-04-14 | 2025-04-11 | 2025-04-30 | MOHD FIRDAUS BIN JAMALUDDIN6000006918 | NR Service TI | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-21 | RONALD SHAN A/L AMBUROSE6800000089 |  | 2025-04-16 | 2025-04-11 | 2025-04-14 | 2025-04-11 | 2025-04-30 | MOHD FIRDAUS BIN JAMALUDDIN6000006918 | 2025-04-11 | 2025-04-14 | 2025-04-11 | 2025-04-11 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-07 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-05-27 | 2025-06-27 | 2025-05-27 | 2025-05-27 | IDA//NAJEEHA BINTI MAZLAN/7018000019
7748B-7097Z | By Tigowis Estate | DU00005020767 | Sabah | Sabah | 5.748880 | 118.217785 |  |  |  |  | TI done under NIC | TI under NIC | Digi | 07. Solution Changed | MwAccessories-Coupler Bracket 13G UBR120 EHD0FD301(shortage x 4pc) |  |  | 13G 4+0 1.8m/1.8m MDD XMC5D sub B & optical 1G SFP+patchcord NE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 13G XMC5D sub B Hi 4) 1 x 13G 1.8m MDD FE: 1) 1 x RTN910A 2) 2 x ISM8 cards 3) 1 x 13G XMC5D sub B Lo 4) 1 x 13G 1.8m MDD 5) 1G SFP + Patchcords | Under NIC | Swap existing 13G 1+0 link with new 13G 4+0 CA link. Reuse existing frequency channel NE (7748B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Migrate traffic to new link 5) Decom old link FE (7097Z): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Patch new RTN GE5 to RTN04 GE5 (optical) 5) Migrate traffic to new link 6) Decom old link | NE (7748B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Migrate traffic to new link 5) Decom old link | FE (7097Z): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new ISM8 card at new RTN slot 3 and 4 3) Install new 4+0 link at 3-ISM8 and 4-ISM8 4) Patch new RTN GE5 to RTN04 GE5 (optical) 5) Migrate traffic to new link 6) Decom old link | XMC5D | MDD | 13G | 1.8m | 1.8m | [6 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started
9302B-9059B | Jln Datuk Mohd Musa | DU00005020768 | Sarawak | Sarawak | 1.451094 | 110.465333 | [6 empty] | ZTE | 00. Integrated/RFS Done | 0620: Site integrated. 2605: Pending Subcon to proceed TI. | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G 1+0 112MHz 0.6m/0.6m XMC3 NE: 1) 1xRTN910A 2) 1x23GHz XMC3 Sub A Hi 3) 1x23GHz 0.6m SP FE: 1) 1xISM8 card 2) 1x23GHz XMC3 Sub A Lo 3) 1x23GHz 0.6m SP | MW Swap | To swap Existing link NEC 23GHz 1+0 56MHz with new Huawei link 23GHz 1+0 112MHz NE (9302B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link FE (9059B RTN01): 1) Install new ISM8 card at 9059B RTN01 slot 3 2) Install new link at RTN01 3-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | NE (9302B): 1) Install new RTN910A (ops team to assign RTN number) 2) Install new link at new RTN 7-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | FE (9059B RTN01): 1) Install new ISM8 card at 9059B RTN01 slot 3 2) Install new link at RTN01 3-ISM8-1 3) Migrate traffic to new link 4) Decom existing link | XMC3 | MAC SP | 23G | 0.6m | 0.6m | Trintel | SQ202502260453-Trintel | Allstar | SQ202506230508-Allstar // SQ202506230518-Allstar // SQ202507100577-Allstar | 2025-02-28 | 2025-02-24 | Completed | 2025-02-22 | 2025-02-24 | 2025-02-22 | 2025-02-24 | Fiona Wan Yen Chin7667000028 |  | TRINTEL (M) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-02-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-02-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-02-24 | 2025-02-28 | 2025-02-24 | 2025-02-24 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250508AL |  | 2025-05-09 | 2025-06-17 | Completed | 2025-05-08 | 2025-05-09 | 2025-05-08 | 2025-06-17 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-06-17 | 2025-06-23 | 2025-06-17 | 2025-06-21 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-06-17 | 2025-06-23 | 2025-06-17 | 2025-06-21 | BONG NEE NYEEbong.allstar@gmail.com | Allstar TI | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-06-20 | 2025-06-17 | 2025-06-23 | 2025-06-27 | 2025-06-27 | BONG NEE NYEEbong.allstar@gmail.com | 2025-06-17 | 2025-06-23 | 2025-06-17 | 2025-06-17 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-07 | CHONG QIEW LEK7018000038 | Warehouse Team | 2025-07-25 | 2025-07-31 | 2025-07-25 | 2025-07-25 | NURFIKA//BINTI IBRAHIM/6237001402
7586A-7421B | Kg. Suan Lamba | DU00005020769 | Sabah | Sabah | 5.646599 | 118.128209 |  |  |  |  | RFS | TI DONE | ZTE | 00. Integrated/RFS Done | DO ready | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 15G 2+0 1.2m/1.2m MDD XMC5D sub B NE: 1) 1 x ISM8 cards 2) 1 x 15G XMC5D sub B Lo 3) 1 x 15G 1.2m MDD FE: 1) 1 x ISM8 cards 2) 1 x 15G XMC5D sub B Hi 3) 1 x 15G 1.2m MDD | MW Swap | Existing link 3+0 (1x2+0 & 1x1+0) To swap 1+0 link to 2+0, EPLA with existing 4+0 to create 4+0 To use MDD + XMC5D for future upgrade To reuse existing channel NE (7586A RTN03): 1) Swap ISV3 at RTN03 slot 4 with new ISM8 card 2) Transfer existing link from RTN03 3-ISM8-1 to 7-ISM8-1 3) Transfer existing link from RTN03 3-ISM8-2 to 7-ISM8-2 4) Install new link V at 3-ISM8-1 5) Install new link H at 4-ISM8-1 6) Configure 3-ISM8-1 and 4-ISM8-1 as 2+0 non CA 7) Create EPLA 4+0 with 7-ISM8 NE (7421B RTN04): 1) Swap ISV3 at RTN04 slot 4 with new ISM8 card 2) Transfer existing link from RTN03 3-ISM8-1 to 7-ISM8-1 3) Transfer existing link from RTN03 3-ISM8-2 to 7-ISM8-2 4) Install new link V at 3-ISM8-1 5) Install new link H at 4-ISM8-1 6) Configure 3-ISM8-1 and 4-ISM8-1 as 2+0 non CA 7) Create EPLA 4+0 with 7-ISM8 | NE (7586A RTN03): 1) Swap ISV3 at RTN03 slot 4 with new ISM8 card 2) Transfer existing link from RTN03 3-ISM8-1 to 7-ISM8-1 3) Transfer existing link from RTN03 3-ISM8-2 to 7-ISM8-2 4) Install new link V at 3-ISM8-1 5) Install new link H at 4-ISM8-1 6) Configure 3-ISM8-1 and 4-ISM8-1 as 2+0 non CA 7) Create EPLA 4+0 with 7-ISM8 | NE (7421B RTN04): 1) Swap ISV3 at RTN04 slot 4 with new ISM8 card 2) Transfer existing link from RTN03 3-ISM8-1 to 7-ISM8-1 3) Transfer existing link from RTN03 3-ISM8-2 to 7-ISM8-2 4) Install new link V at 3-ISM8-1 5) Install new link H at 4-ISM8-1 6) Configure 3-ISM8-1 and 4-ISM8-1 as 2+0 non CA 7) Create EPLA 4+0 with 7-ISM8 | XMC5D | MDD | 15G | 1.2m | 1.2m | NR services | SQ202504080153-NR Services | NR services | SQ202502270741-NR Services // SQ202504260199-NR Services | 2025-07-04 | 2025-07-02 | Completed | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-03 | 2025-03-07 | 2025-03-03 | 2025-03-03 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-03-03 | 2025-03-07 | 2025-03-03 | 2025-03-03 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-07-02 | 2025-07-04 | 2025-07-02 | 2025-07-02 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250217AC |  | 2025-02-18 | 2025-02-22 | Completed | 2025-02-17 | 2025-02-18 | 2025-02-17 | 2025-02-22 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-02-27 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-02-27 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | NR Service TI | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | NURUL//SYAFINAS BINTI MAT HASHIM/6237001070 |  | 2025-02-26 | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-02-27 | KU MUHAMMAD NAJM//BIN KU HAMDI/7167000045 | 2025-02-25 | 2025-02-28 | 2025-02-25 | 2025-02-26 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | tseping//wang/6819000006 | Logistic Team | 2025-06-13 | 2025-07-13 | 2025-06-13 | 2025-06-13 | MASDIANA//BINTI BEDIN/6801000016
4410K_1 | BUKIT9 | DU00005020770 | Northern | Kedah | 5.586150 | 100.680948 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH Cable x1. | MW IDU Patching | Util 100% of 1G port. 4410K_RTN02 to RTN01. RTN02_ GE2 to RTN01_GE2 , patching with ETH cables. | 1.4410K_RTN02. GE1 transfer to GE3 Optical with 10G SFP module + 1 Pair Patch Cord Fiber cables | [6 empty] | CCSMY | SQ202503190701-CCS | CCSMY | SQ202502270734-CCS // SQ202504260175-CCS | 2025-09-30 | 2025-09-30 | Completed | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | CHEN TAK//EOH YANG/7021000004 |  | CCS COMSERVICE (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | EOH YANG CHEN TAKeohyang@qingnitech.com |  |  | 1.00 | Unassigned | Completed |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25012499 |  | 2025-01-25 | 2025-02-04 | Completed | 2025-01-24 | 2025-01-25 | 2025-01-24 | 2025-02-04 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-02-21 | 2025-02-28 | 2025-02-21 | 2025-03-07 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2025-02-21 | 2025-02-28 | 2025-02-21 | 2025-02-21 | Arif//Afif Bin Mohd Zabidi/7021000041 | CCS TI | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  |  | 2025-02-21 | 2025-02-28 | 2025-02-21 | 2025-03-06 | Arif//Afif Bin Mohd Zabidi/7021000041 | 2026-01-09: 2025-02-21; 2026-01-09: 2025-02-28; 2026-01-09: 2025-02-21; 2026-01-13: 2025-03-05 |  |  | 2025-05-20 | 2025-05-31 | 2025-05-20 | 2025-05-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202508150516-GCI | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | EZRIN TASNIM BIN ABDUL GANI6798000128
B00436 | B061D_B00436OD_SEK152SHLM | DU00005040753 | Central | Selangor | 3.059200 | 101.529680 | WK13 | MAR 25 | WK13 | MAR 25 | RFS | Pending TSSR | ZTE | 00. Integrated/RFS Done | 27/3/2025 : Cutover done 26/3/2025 : Cutover WIP 25/3/2025 : Plan change IDU at NE site - Cancel proceed spillover tomorrow 11/3/2025 : MAXIS COMMUNICATION BERHAD - TOWER 61M LAND - NE site B00436 B061D_B00436OD_SEK152SHLM, Seksyen 15 (Opcom) - 1795A - Patching site 1795A Seksyen 15 (Opcom) | TSS+TI | L1+ATP+PAC | 1)1x Optical SFP Module 1G 1310nm 10Km(For PTN) 2)1x Optical SFP Module 1.25G 1310nm 10Km(For IDU RTN910A) 3)2x Patchcord LC-2K with suitable length(or equivalent) 4)2x CAT6 cables(if required) 5)1x RTN910A 6)1x ISM8 7)new IF/RG8 cables with suitable length(if required especially if existing had short length) for existing MW Link 2623B-1795A and existing MW Link 3839B-1795A in order for ensure ODU for each link may connect to RTN910A(RTN03) at NE(1795A). | MW Hardware Upgrade | MW IDU Patching need to be perform at 1795A&B00436(1795A-Pair Colo with B00436) Site Impacted : 1795A, 2623B & 3839B. NE_1795A & B00436 1.Install 1x new RTN910A(RTN03) and insert 1x new ISM8 into slot 03 of RTN910A(RTN03). Configure it. 2.Insert suitable 1.25G Optical SFP Module into existing port 8-EM6-5 of RTN910A(RTN03). Configure it. 3.Insert suitable 1G Optical SFP Module into existing PTN at B00436(request new port from IPRAN Team). Configure it. 4.Patching new Fiber patch cord cable from existing PTN at B00436 to port 8-EM6-5 of RTN910A(RTN03). Configure it. 5.Patching existing BBU 1795A to port 8-EM6-1 of RTN910A(RTN03). Configure it. 6.Shifting existing IF/RG8 cable for MW Link 2623B-1795A in which perform task at 1795A(RTN01 connected to 1st TDC LL) for existing ISM8 slot 03 to new ISM8 slot 03 of RTN910A(RTN03). Configure it. 7.Shifting existing IF/RG8 cable for MW Link 3898B-1795A in which perform task at 1795A(RTN01 connected to 2nd TDC LL) for existing ISM8 slot 07 port 2 to new ISM8 slot 07 port 1 of RTN910A(RTN03). Configure it. 8.Configure DCN Inband for RTN03 and new xC VLAN services for 1795A, 2623B & 3839B and backhauling via xC Host B00436(request new vlan services from IPRAN Team). | MW IDU Patching need to be perform at 1795A&B00436(1795A-Pair Colo with B00436) Site Impacted : 1795A, 2623B & 3839B. NE_1795A & B00436 1.Install 1x new RTN910A(RTN03) and insert 1x new ISM8 into slot 03 of RTN910A(RTN03). Configure it. 2.Insert suitable 1.25G Optical SFP Module into existing port 8-EM6-5 of RTN910A(RTN03). Configure it. 3.Insert suitable 1G Optical SFP Module into existing PTN at B00436(request new port from IPRAN Team). Configure it. 4.Patching new Fiber patch cord cable from existing PTN at B00436 to port 8-EM6-5 of RTN910A(RTN03). Configure it. 5.Patching existing BBU 1795A to port 8-EM6-1 of RTN910A(RTN03). Configure it. 6.Shifting existing IF/RG8 cable for MW Link 2623B-1795A in which perform task at 1795A(RTN01 connected to 1st TDC LL) for existing ISM8 slot 03 to new ISM8 slot 03 of RTN910A(RTN03). Configure it. 7.Shifting existing IF/RG8 cable for MW Link 3898B-1795A in which perform task at 1795A(RTN01 connected to 2nd TDC LL) for existing ISM8 slot 07 port 2 to new ISM8 slot 07 port 1 of RTN910A(RTN03). Configure it. 8.Configure DCN Inband for RTN03 and new xC VLAN services for 1795A, 2623B & 3839B and backhauling via xC Host B00436(request new vlan services from IPRAN Team). | [6 empty] | GTSB | SQ202504170454-GTSB | GTSB | SQ202503280401-GTSB // SQ202503280435-GTSB // SQ202504260131-GTSB | 2025-05-26 | 2025-05-26 | Completed | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-05-05 | 2025-05-19 | 2025-05-05 | 2025-05-05 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25022807 |  | 2025-03-01 | 2025-03-28 | Completed | 2025-02-28 | 2025-03-01 | 2025-02-28 | 2025-03-28 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-03-24 | 2025-04-30 | 2025-03-24 | 2025-03-28 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-03-24 | 2025-04-30 | 2025-03-24 | 2025-03-28 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-03-27 | 2025-03-24 | 2025-04-30 | 2025-03-24 | 2025-04-09 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2026-01-09: 2025-03-24; 2026-01-09: 2025-04-30; 2026-01-09: 2025-03-24; 2026-01-13: 2025-03-25 |  |  | 2025-04-11 | 2025-05-11 | 2025-04-11 | 2025-04-11 | ASTI//GANIS PUTRIANI/6237001358 | GTSB | SQ202506050715-GTSB
4670B-4669A | Kg Alor Biak | DU00005040890 | Northern | Kedah | 6.237559 | 100.330431 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+PAC |  | MW Swap | DECOM AND RE-INSTALL EXISTING 13G ANTENNA TO NEW STRUCTURE REALLIGNMENT ANTENNA AS PER EXISTING LB | DECOM AND RE-INSTALL EXISTING 13G ANTENNA TO NEW STRUCTURE REALLIGNMENT ANTENNA AS PER EXISTING LB | DECOM AND RE-INSTALL EXISTING 13G ANTENNA TO NEW STRUCTURE REALLIGNMENT ANTENNA AS PER EXISTING LB | XMC3 | DP |  | 1.8 | 1.8 | NWAVE | SQ202508140681-N-Wave | NWAVE | SQ202507290137-N-Wave // SQ202507290138-N-Wave | 2026-03-04 | 2026-03-04 | Completed | 2025-10-13 | 2025-11-13 | 2025-10-13 | 2025-10-16 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | Khairul Azman Bin Din7160000001 |  | N-WAVE TECHNOLOGIES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-25 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel Do | 2025-04-14 | 2025-06-13 | Completed | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-06-13 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-13 | 2025-11-13 | 2025-10-13 | 2025-11-24 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-10-13 | 2025-11-13 | 2025-10-13 | 2026-02-06 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-16 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-16 | 2025-10-13 | 2025-11-13 | 2025-10-13 | 2026-02-25 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | 2026-01-09: 2025-10-13; 2026-01-09: 2025-11-13; 2026-01-09: 2025-10-13; 2026-01-13: 2025-10-14 |  |  | 2025-12-26 | 2026-01-26 | 2025-12-26 | 2025-12-26 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI_AA | SQ202510300164-GCI | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | EZRIN TASNIM BIN ABDUL GANI6798000128
3738C_AD | Pinggiran Subang (REL) | DU00005765443 | Central | Selangor | 3.162134 | 101.536437 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC |  | BBU Patching | BBU Patching to xD MW | [7 empty] | GTSB | SQ202507010378-GTSB | GTSB | SQ202507010373-GTSB | 2025-11-14 | 2025-11-07 | Completed | 2025-07-16 | 2025-07-30 | 2025-07-16 | 2025-07-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-16 | 2025-07-30 | 2025-07-16 | 2025-07-16 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-07-17 | 2025-07-25 | 2025-07-17 | 2025-07-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-07 | 2025-11-14 | 2025-11-07 | 2025-11-07 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25070102 |  | 2025-07-02 | 2025-07-02 | Completed | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-06 | 2025-07-31 | 2025-07-06 | 2025-07-07 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-07-06 | 2025-07-31 | 2025-07-06 | 2025-07-10 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-09 | 2025-07-06 | 2025-07-31 | 2025-07-06 | 2025-07-15 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2026-01-09: 2025-07-06; 2026-01-09: 2025-07-31; 2026-01-09: 2025-07-06; 2026-01-13: 2025-07-07 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GTSB | SQ202507250720-GTSB
3036M_AD | DS The Gardens Micro | DU00005765444 | Central | Kuala Lumpur | 3.117955 | 101.675781 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x1 | MW IDU Patching | 1. Do the NLOS patching between 2565A and 3036M-MAC-001 (GE0/2/2) | 1. Do the NLOS patching between 2565A and 3036M-MAC-001 (GE0/2/2) | [6 empty] | Magicell | SQ202507100495-Magicell | Magicell | SQ202507100546-Magicell | 2025-11-25 | 2025-11-24 | Completed | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-08-12 | 2025-08-13 | 2025-08-12 | 2025-08-12 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25071090 |  | 2025-07-13 | 2025-07-14 | Completed | 2025-07-12 | 2025-07-13 | 2025-07-12 | 2025-07-14 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-04 | 2026-07-30 | 2025-07-04 | 2026-01-28 | ASYRAF//BIN MOHAMAD/7018000171 | Magicell TI | 2025-07-04 | 2026-07-30 | 2025-07-04 | 2025-08-05 | ASYRAF//BIN MOHAMAD/7018000171 | Magicell TI | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-10 | 2025-07-04 | 2026-07-30 | 2025-07-04 | 2025-08-05 | ASYRAF//BIN MOHAMAD/7018000171 | 2026-01-09: 2025-07-04; 2026-01-09: 2026-07-30; 2026-01-09: 2025-07-04; 2026-01-13: 2025-08-01 |  |  | 2025-08-26 | 2025-09-26 | 2025-08-26 | 2025-08-26 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202507190083-GCI | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | CHEONG/SENG/WAH/7018000306
3773C_AD | Taman Subang Damai (REL) | DU00005765445 | Central | Selangor | 3.167063 | 101.543092 | [7 empty] | 00. Site Out/Drop | 7/7/25-existing link RSL los block | NA |  |  | BBU Patching | BBU Patching to xD MW | [7 empty] | GTSB | No PR required-Site drop/cancel | GTSB | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25070103 |  | 2025-07-02 | 2025-07-02 | Completed | 2025-07-01 | 2025-07-02 | 2025-07-01 | 2025-07-02 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-07-06 | 2025-07-31 | 2025-07-06 | 2025-07-07 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-07-06 | 2025-07-31 | 2025-07-06 |  | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | [7 empty] | 2025-07-06 | 2025-07-31 | 2025-07-06 |  | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2026-01-09: 2025-07-06; 2026-01-09: 2025-07-31; 2026-01-09: 2025-07-06; 2026-01-13: 2025-07-07
9037C_LOS | Lorong Apollo Sungai Merah | DU00005765446 | Sarawak | Sarawak | 2.327628 | 111.847425 |  |  |  | AUG 25 |  |  | ZTE | 00. Integrated/RFS Done | 27/10 - Integrated on 26/10 17/10 - TI Plan start on 21.10 by subcon | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | Link config 23G_1+0_0.6M. NE_9037C 23G_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A_Lo x1. FE_9391B/Q00884 23G_0.6M(MAC) x1. RTN910A x1. XMC_3E , Sub A_Hi x1. | MW New Link / Reroute | Swap existing 18G_1+0_112M link to new FE 9391B/Q00884 due to LOS Bock. Link config 23G_1+0_0.6M. Site Impacted : 9037C. NE_9037C 1.Install new 23G_0.6M(MAC) 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. FE_9391B/Q00884 1.1.Install new 23G_0.6M(MAC) 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect & New Inband DCN. 5.Enable GE1 , ETH patching to existing 9391B_RTN01_GE5. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | Swap existing 18G_1+0_112M link to new FE 9391B/Q00884 due to LOS Bock. Site Impacted : 9037C. NE_9037C 1.Install new 23G_0.6M(MAC) 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Lo. 4.Create service cross connect. 5.Traffic migrate to new link and new FE routing. 6.Decom existing MW link. | Swap existing 18G_1+0_112M link to new FE 9391B/Q00884 due to LOS Bock. Site Impacted : 9037C. FE_9391B/Q00884 1.1.Install new 23G_0.6M(MAC) 2.Install new RTN910A , 7_ISM8-1+0. 3.Install new XMC_3E , Sub A_Hi. 4.Create service cross connect & New Inband DCN. 5.Enable GE1 , ETH patching to existing 9391B_RTN01_GE5. 6.Traffic migrate to new link and new FE routing. 7.Decom existing MW link. | XMC_3E | MAC | 23G | 0.6 | 0.6 | Iezzpro | SQ202509040356-Iezzpro | Iezzpro | SQ202510150341-Iezzpro // SQ202510150350-Iezzpro |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  | DOWMY25101331 |  | 2025-10-14 | 2025-10-22 | Completed | 2025-10-13 | 2025-10-14 | 2025-10-13 | 2025-10-22 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-24 | 2025-10-29 | 2026-03-12 | 2026-03-12 | Kevin//Tan/6000033214 | Iezzpro TI | 2025-10-24 | 2025-10-29 | 2025-11-01 | 2026-03-12 | Kevin//Tan/6000033214 | Iezzpro TI | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-10-24 | 2025-10-29 | 2026-03-16 | 2026-03-16 | Kevin//Tan/6000033214 | 2026-01-09: 2025-10-24; 2026-01-09: 2025-10-29; 2026-01-09: 2025-10-27; 2026-01-13: 2025-10-27 |  |  | 2025-11-24 | 2025-12-24 | 2025-11-24 | 2025-11-24 | IDA//NAJEEHA BINTI MAZLAN/7018000019 | GCI | SQ202507080541-GCI | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | CHEONG/SENG/WAH/7018000306
W01487_LOS | W066Z_W01487OD_JLN_CHERAS_WARISAN_CITYVIEW | DU00005765447 | Central | Kuala Lumpur | 3.126172 | 101.722240 | [7 empty] | 00. Site Out/Drop | 2/7-inform by GOP site already decomm |  |  |  | Cancel / Drop | This site drop for LOS activity because it will be decommissioning according to GOP team message. | [7 empty] | GCI | No PR required-Site drop/cancel | GCI | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GCI | SQ202507080517-GCI | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | CHEONG/SENG/WAH/7018000306
1311K_HU | BB1_SEK33SHLM2 | DU00005997224 | Central | Selangor | 3.017640 | 101.553930 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 1311K-1566C 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM IMPACTED SITE: 1311K | MW REMOTE UPGRADE LINK 1311K-1566C 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM IMPACTED SITE: 1311K | MW REMOTE UPGRADE LINK 1311K-1566C 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_1024QAM IMPACTED SITE: 1311K | [7 empty] | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-23 | [15 empty] | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509041074-GCI | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
4477C_HU | Taman Ria Jaya - KCY88 | DU00005997225 | Northern | Kedah | 5.650962 | 100.519544 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 15G_2+0_28M NE_4477C 15G_DP_0.6M(MAC)+OMT x1. ISM8 x1. XMC_3E , Sub A & B_Lo x2. FE_4770A 15G_DP_1.2M(MAC)+OMT x1. ISM8 x1 XMC_3E , Sub A & B_Hi x2. | MW Parallel Link | Existing 15G_4+0_28M Install parallel link 15G_2+0_28M Site Impacted : 4477C NE_4477C 1.Install new 15G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4477C_RTN02. 3.Install new 4_ISM8-2+0 into existing 4477C_RTN02. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new Parallel link. FE_4770A 1.Install new 15G_DP_1.2M(MAC)+OMT. 2.Reuse existing 4770A_RTN18. 3.Install new 4_ISM8-2+0 into existing 4770A_RTN18. 4.Install new XMC_3E , Sub A 7 B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. | Existing 15G_4+0_28M Install parallel link 15G_2+0_28M Site Impacted : 4477C. NE_4477C 1.Install new 15G_DP_0.6M(MAC)+OMT. 2.Reuse existing 4477C_RTN02. 3.Install new 4_ISM8-2+0 into existing 4477C_RTN02. 4.Install new XMC_3E , Sub A & B_Lo. 5.Create service cross connect and EPLA. 6.Traffic migrate to new Parallel link. | Existing 15G_4+0_28M Install parallel link 15G_2+0_28M Site Impacted : 4477C FE_4770A 1.Install new 15G_DP_1.2M(MAC)+OMT. 2.Reuse existing 4770A_RTN18. 3.Install new 4_ISM8-2+0 into existing 4770A_RTN18. 4.Install new XMC_3E , Sub A 7 B_Hi. 5.Create service cross connect and EPLA. 6.Traffic migrate to new parallel link. | [5 empty] | MTK | SQ202509100076-MTK | MTK | SQ202509100072-MTK // SQ202509100074-MTK | 2025-10-15 | 2025-10-14 | Completed | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-24 | AMIRUL SYAHRINI BIN MOHD ZIN6000023342 |  | MTK COMMUNICATION SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25091019 |  | 2025-09-11 | 2025-09-19 | Completed | 2025-09-10 | 2025-09-11 | 2025-09-10 | 2025-09-19 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-22 | 2025-09-30 | 2025-10-07 | 2025-10-07 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2025-09-22 | 2025-09-30 | 2025-10-07 | 2025-10-08 | DZULFAIZAL//BIN MAULUF/8225000001 | MTK TI | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | AKMAL//BIN RAZALI/6794000078 |  | 2025-09-29 | 2025-09-22 | 2025-09-30 | 2025-10-08 | 2025-10-08 | DZULFAIZAL//BIN MAULUF/8225000001 | 2026-01-09: 2025-09-22; 2026-01-09: 2025-09-30; 2026-01-09: 2025-10-06; 2026-01-13: 2025-10-06 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509041075-GCI | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | CHEONG/SENG/WAH/7018000306
4635A_HU_1 | Kuala Kertil | DU00005997226 | Northern | Kedah | 5.606915 | 100.651200 | [7 empty] | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | Solution changed to install parallel link at 4635A_RTN07 (Refer DU ID 4635A HU_2) due to consideration of Tower structure and spacing issue. | [7 empty] | NWAVE | No PR required-Site drop/cancel | NWAVE | No PR required-Site drop/cancel |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted |  |  | Cancel DO | 2025-09-24 | 2025-09-26 | Completed | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-26 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-10 | MOHD NAZREEN BIN ABDUL MUKTI6000022372 | NWAVE TI | [33 empty] | GCI | SQ202509041075-GCI | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | CHEONG/SENG/WAH/7018000306
Q00905_HU | BB1_Q141A_Q00905OD_CB_KGRUAN | DU00005997227 | Sarawak | Sarawak | 1.185610 | 110.891310 | [7 empty] | 01. Pending Planning |  | TSS+AA+TI |  | NE: 1x ISM8 1x 1.8m XMC antenna (7G) 1x ODU 7G_XMC sb K Lo 1x ODU 7G_XMC sb L Lo FE: 1x ISM8 1x 1.8m XMC antenna (7G) 1x ODU 7G_XMC sb K Hi 1x ODU 7G_XMC sb L Hi | MW Parallel Link | Install 7G_2+0_512Qam_28Mhz_424Mbps to be parallel with existing link HW 7G_2+0 Config EPLA existing and new link become 7G 4+0 Impact site: Q00905 (Existing link 7G_2+0_508Mbps | NE: 1. Install ISM8 card at slot 3 at existing IDU 2. Install new 7G 1.8m XMC antenna 3. Install new ODU 7G XMC sb K and L 4. Configure link 7G 2+0 28Mhz 512Qam 5. Config EPLA existing link and new link become 7G 4+0 | FE: 1. Install ISM8 card at slot 3 at existing IDU 2. Install new 7G 1.8m XMC antenna 3. Install new ODU 7G XMC sb K and L 4. Configure link 7G 2+0 28Mhz 512Qam 5. Config EPLA existing link and new link become 7G 4+0 | XMC-3 | XMC | 7G | 1.8m | 1.8m | Magicell | SQ202601210174-Magicell |  |  |  |  | Ongoing | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-04-17 | 2026-04-24 | 2026-04-17 | 2026-04-17 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Unassigned | Completed | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202509041083-GTSB | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | AB.RAHMAN//BIN MAT NOOH/6237001519
4676C_HU | Mr Diy Balik Pulau | DU00005997228 | Northern | Penang | 5.351201 | 100.234584 | [7 empty] | 00. Integrated/RFS Done |  | AA | PAC |  | MW Remote Upgrade | MW REMOTE UPGRADE LINK 4676C-4017B 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: 4676C | MW REMOTE UPGRADE LINK 4676C-4017B 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: 4676C | MW REMOTE UPGRADE LINK 4676C-4017B 23G_1+0_0.6M/0.6M_DP_56MHZ_512QAM TO 23G_1+0_0.6M/0.6M_DP_112MHZ_512QAM IMPACTED SITE: 4676C | XMC3 | 0.6 | 23G | MAC | 0.6 |  |  | In-house | No PR required-Remote Upgrade |  |  | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [13 empty] | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-09-24 | [15 empty] | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509041075-GCI | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | EZRIN TASNIM BIN ABDUL GANI6798000128
2889C_HU | Tmn Setia Balakong | DU00005997229 | Central | Selangor | 3.015380 | 101.751444 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 23G_2+0_112M. NE_2889C 23G_DP_0.6M(MAC)+OMT x1. RTN910A x1. XMC_3E , Sub A & B_Lo x2. . FE_1266B 23G_DP_0.6M(MAC)+OMT x`. RTN910A x1. 3.Install new XMC_3E , Sub A & B_Hi x2. | MW Swap | Existing link 23G_1+0_56M.Remote Software Upgrade Not Support due to alrms. Swap existing link to 23G_2+0_112M. Site Impacted : 2889C NE_2889C 1.Install new 23G_DP_0.6M(MAC)+OMT 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW link. (ODU , ANT and IDU). FE_1266B 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8_2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create new In band DCN. 6.Traffic migrate to new link. 7.Decom existing ODU and ANT Only. | Existing link 23G_1+0_56M.Remote Software Upgrade Not Support due to alrms. Swap existing link to 23G_2+0_112M. Site Impacted : 2889C NE_2889C 1.Install new 23G_DP_0.6M(MAC)+OMT 2.Install new RTN910A , 7_ISM8-2+0. 3.Install new XMC_3E , Sub A & B_Lo. 4.Create service cross connect and EPLA. 5.Traffic migrate to new link. 6.Decom existing MW link. (ODU , ANT and IDU). | Existing link 23G_1+0_56M.Remote Software Upgrade Not Support due to alrms. Swap existing link to 23G_2+0_112M. Site Impacted : 2889C FE_1266B 1.Install new 23G_DP_0.6M(MAC)+OMT. 2.Install new RTN910A , 7_ISM8_2+0. 3.Install new XMC_3E , Sub A & B_Hi. 4.Create service cross connect and EPLA. 5.Create new In band DCN. 6.Traffic migrate to new link. 7.Decom existing ODU and ANT Only. | XMC_3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202509100066-GTSB | GTSB | SQ202509100062-GTSB // SQ202509100064-GTSB | 2025-11-25 | 2025-11-24 | Completed | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. |  | Unassigned | Completed |  | 2025-10-28 | 2025-10-29 | 2025-10-28 | 2025-10-28 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25092539 |  | 2025-09-26 | 2025-10-06 | Completed | 2025-09-25 | 2025-09-26 | 2025-10-06 | 2025-10-06 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-08 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-08 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-14 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-08 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI | SQ202509041074-GCI | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | CHEONG/SENG/WAH/7018000306
4592B_HU | Ulu Dedap | DU00005997230 | Northern | Perak | 4.092106 | 100.938053 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI | L1+ATP+PAC | 4X ISM8 CARD 2X RTN910A 2X 13G 1.2M MDD ANTENNA 1x ODU 13G XMC5D SUB A HI 1X ODU 13G XMC5D SUB A LO | MW Parallel Link | Parallel link 13G_4+0_28M to support 4720D ( refer DU ID 4720D_HU). NE_4592B 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Enable GE1 , ETH LAN cable patching from new RTN910A_GE1 to 4592B_RTN01_GE1 ( ID : 23890) 6.Create service cross connect , CA and EPLA. 7.No link to be decom. FE_A00458. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.( RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Create New In band DCN. 7.No link to be decom. | Parallel link 13G_4+0_28M to support 4720D ( refer DU ID 4720D_HU). NE_4592B 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A. (RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Hi. 5.Enable GE1 , ETH LAN cable patching from new RTN910A_GE1 to 4592B_RTN01_GE1 ( ID : 23890) 6.Create service cross connect , CA and EPLA. 7.No link to be decom. | Parallel link 13G_4+0_28M to support 4720D ( refer DU ID 4720D_HU). FE_A00458. 1.Install new 13G_DP_1.2M(MDD). 2.Install new RTN910A.( RTN no provide by OPS team). 3.Install new 3_ISM8-2+0 and 4_ISM8-2+0. 4.Install new XMC_5D , Sub A_Lo. 5.Create service cross connect , CA and EPLA. 6.Create New In band DCN. 7.No link to be decom. | XMC5D | MDD | 13G | 1.2 | 1.2 | GCI | SQ202509100071-GCI | GCI | SQ202509100068-GCI // SQ202509100069-GCI | 2025-12-03 | 2025-12-02 | Completed | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-02 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  |  | Cancel DO | 2025-09-23 | 2025-09-29 | Completed | 2025-09-22 | 2025-09-23 | 2025-09-27 | 2025-09-29 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-09-30 | 2025-10-04 | 2025-09-30 | 2025-10-04 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-09-30 | 2025-10-04 | 2025-09-30 | 2025-10-04 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | GCI TI | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-02 | 2025-09-30 | 2025-10-04 | 2025-09-30 | 2025-10-16 | NORIKHWAN//ZAINI BIN MOHAMAD SALIM/6800000199 | 2025-09-30: 2025-09-30; 2025-09-30: 2025-10-04; 2025-09-30: 2025-09-30; 2025-10-08: 2025-10-01 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509041075-GCI | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | EZRIN TASNIM BIN ABDUL GANI6798000128
Q02260_HU | SK RANCANGAN SEPUPOK | DU00005997231 | Sarawak | Sarawak | 3.815751 | 113.709060 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | NE: 1x RTN910 1x ISM8 1x 1.2m XMC antenna (13G) 1x ODU 13G_XMC3 sb A Lo 1x ODU 13G_XMC3 sb B Lo FE: 1x RTN910 1x ISM8 1x 1.2m XMC antenna (13G) 1x ODU 13G_XMC3 sb A Hi 1x ODU 13G_XMC3 sb B Hi | MW Swap | Install 13G_2+0_512Qam_28Mhz_448Mbps to be swap with existing SM link 13G_1+0 Impact site: Q02260 Dismantle existing SM link | NE: 1. Install new RTM910A 2. Install new 13G 1.2m XMC ant 3. Install new 13G XMC3 sb A and B 4. Configure link 13G 2+0 28MHZ 512QAM EPLA | FE: 1. Install new RTM910A 2. Install new 13G 1.2m XMC ant 3. Install new 13G XMC3 sb A and B 4. Configure link 13G 2+0 28MHZ 512QAM EPLA 5. Connect IDU to IPRAN (existing port) | XMC-3 | XMC | 13G | 1.2m | 1.2m | Magicell | SQ202510150634-Magicell | Redtone | SQ202602090144-Redtone // SQ202602090148-Redtone | 2025-11-17 | 2025-11-10 | Completed | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | CHONG LI CHING7018000173 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | UMI NOR PADZILAH BINTI PAUZI7018000120 |  | MAGICELL SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-29 | 2025-10-31 | 2025-10-29 | 2025-10-29 | AZRI//BIN ABDULLAH/6799000073 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-10 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY26020301 |  | 2026-02-04 | 2026-02-05 | Completed | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | YEK/PIK/NGUK/6871000002 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2026-02-06 | 2026-02-13 | 2026-02-06 | 2026-02-27 | DOUGLAS/ANAK/COLIN/6000039613 | REDTONE TI | 2026-02-06 | 2026-02-13 | 2026-02-06 | 2026-02-27 | DOUGLAS/ANAK/COLIN/6000039613 | REDTONE TI | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2026-02-11 | 2026-02-06 | 2026-02-13 | 2026-02-06 | 2026-03-01 | DOUGLAS/ANAK/COLIN/6000039613 | 2025-09-30: 2026-02-06; 2025-09-30: 2026-02-13; 2025-09-30: 2026-02-06; 2025-10-08: 2026-02-08 |  |  | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-03 | NURFIKA//BINTI IBRAHIM/6237001402 | GTSB | SQ202509041083-GTSB | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | AB.RAHMAN//BIN MAT NOOH/6237001519
A00015_IPR | A037B_A00015OD_CHANGKATPETAI | DU00006040532 | Northern | Perak | 4.123000 | 101.145100 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | Split traffic at IDU SM NT05608 A00015-A00113 MW1 LAN1 to PTN 66082-CHANGKATPETAI/GigabitEthernet0/0/1 Patch IDU SM NT05608 A00015-A00113 MW1 new optical LAN port to new PTN 66082-CHANGKATPETAI optical port and transfer traffic from sites below: 1) 4447A Langkap(Celcom) * remarks: unable to propose port at IDU due to unable to login to equipment | Split traffic at IDU SM NT05608 A00015-A00113 MW1 LAN1 to PTN 66082-CHANGKATPETAI/GigabitEthernet0/0/1 Patch IDU SM NT05608 A00015-A00113 MW1 new optical LAN port to new PTN 66082-CHANGKATPETAI optical port and transfer traffic from sites below: 1) 4447A Langkap(Celcom) * remarks: unable to propose port at IDU due to unable to login to equipment | [6 empty] | GCI | SQ202509300138-GCI | GCI | SQ202510070042-GCI | 2025-11-19 | 2025-11-18 | Completed | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-10-14 | 2025-10-15 | 2025-10-14 | 2025-10-14 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-18 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100112 |  | 2025-10-02 | 2025-10-04 | Completed | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-04 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-04 | 2025-10-07 | 2025-10-04 | 2025-10-12 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-10-04 | 2025-10-07 | 2025-10-04 | 2025-10-12 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | GCI TI | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | AKMAL//BIN RAZALI/6794000078 |  | 2025-10-28 | 2025-10-04 | 2025-10-07 | 2025-10-04 | 2025-10-18 | MUHAMMAD SHAHRUL FAHMI BIN JAMINGAN6800000232 | 2025-09-30: 2025-10-04; 2025-09-30: 2025-10-07; 2025-09-30: 2025-10-04; 2025-10-08: 2025-10-04 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
7238A_IPR | Kg Berungis | DU00006040533 | Sabah | Sabah | 6.151170 | 116.215710 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC |  | MW IDU Patching | Perform LAG at CP site for IDU 7238A-KG BERUNGIS-RTN02 to 7238A-MAC-001 Kg Berungis 1) Patch 7238A-KG BERUNGIS-RTN02 GE2 to new CP port 2) Create LAG 3) Impact sites: 7028A | Perform LAG at CP site for IDU 7238A-KG BERUNGIS-RTN02 to 7238A-MAC-001 Kg Berungis 1) Patch 7238A-KG BERUNGIS-RTN02 GE2 to new CP port 2) Create LAG 3) Impact sites: 7028A | [6 empty] | NR services | SQ202510230970-NR Services | NR services | SQ202510150302-NR Services | 2026-01-14 | 2026-01-14 | Completed | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-16 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | Ally//Alistair Gerald/7167000001 |  | NR SERVICES (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-01-13 | 2026-01-14 | 2026-01-13 | 2026-01-14 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100937 |  | 2025-10-10 | 2025-10-10 | Completed | 2025-10-09 | 2025-10-10 | 2025-10-09 | 2025-10-10 | NUR/WAFA/MIJONG/6871000001 | Warehouse Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-13 | 2025-11-13 | 2025-10-13 | 2025-10-14 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-13 | 2025-11-13 | 2025-10-13 | 2025-10-14 | DATU//AZRUN BIN DATU HARUN/7167000004 | NR Service TI | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | MUHAMMAD SYUKRI//BIN ABU BAKAR/6798000241 |  | 2025-10-14 | 2025-10-13 | 2025-11-13 | 2025-10-13 | 2025-10-14 | DATU//AZRUN BIN DATU HARUN/7167000004 | 2025-09-30: 2025-10-13; 2025-09-30: 2025-11-13; 2025-09-30: 2025-10-13; 2025-10-08: 2025-10-14 |  |  | 2025-11-27 | 2025-12-27 | 2025-11-27 | 2025-11-27 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509260798-GCI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | EZRIN TASNIM BIN ABDUL GANI6798000128
1080A_IPR | WIT | DU00006040534 | Central | Selangor | 2.994022 | 101.420941 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x 1. | IDU-IPRAN | Perform LAG at CP site for IDU 1080A WIT KLANG-RTN07 to 1080A-MAC-002 WIT Klang 1) Patch 1080A WIT KLANG-RTN07 GE2 to new CP port 2) Create LAG 3) Impact sites: 3298A, 1425H | Perform LAG at CP site for IDU 1080A WIT KLANG-RTN07 to 1080A-MAC-002 WIT Klang 1) Patch 1080A WIT KLANG-RTN07 GE2 to new CP port 2) Create LAG 3) Impact sites: 3298A, 1425H | [6 empty] | GTSB | SQ202509300132-GTSB | GTSB | SQ202510090241-GTSB | 2026-03-04 | 2026-03-04 | Completed | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1.00 | Unassigned | Completed |  | 2026-02-27 | 2026-02-28 | 2026-02-27 | 2026-02-27 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-04 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY25100125 |  | 2025-10-02 | 2025-10-07 | Completed | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1.00 | Assigned | Completed |  | 2025-10-06 | 2025-10-31 | 2025-10-06 | 2025-10-13 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-10-06 | 2025-10-31 | 2025-10-06 | 2025-10-13 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | GTSB TI | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-10-07 | 2025-10-06 | 2025-10-31 | 2025-10-06 | 2025-10-11 | AHMAD//BAIHAQI BIN IDRUS/6799000143 | 2025-09-30: 2025-10-06; 2025-09-30: 2025-10-31; 2025-09-30: 2025-10-06; 2025-10-08: 2025-10-07 |  |  | 2025-10-28 | 2025-11-28 | 2025-10-28 | 2025-10-28 | MASDIANA//BINTI BEDIN/6801000016 | GCI | SQ202509260791-GCI | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | CHEONG/SENG/WAH/7018000306
4480B_IPR | Perpaduan Ria Ipoh RCC | DU00006040535 | Northern | Perak | 4.634950 | 101.142240 | [7 empty] | 00. Integrated/RFS Done |  | TSS+TI | L1+ATP+PAC | ETH LAN Cable x1 | MW IDU Patching | Existing Topology : The MW child site 4125C link to 4480B_RTN04 was patched through 4480B_RTN02 towards the 4498A CP site. Site Impacted : 4125C. NE_4480B/A00174 1.Enable GE2 at existing 4480B_RTN04 (ID : 23855). 2.ETH Patching from 4480B_RTN04_GE2 to Cisco Fiber Port Ge_0/2/1. 3.Create new In Band DCN. 4.Create a service cross-connect and migrate the BBU_4125C traffic through the MW link, to the new Cisco fiber port GE_0/2/1.. 5.Disconnect existing ETH LAN cable interconnect to 4480B_RTN02 and disconnect unused port. | Existing Topology : The MW child site 4125C link to 4480B_RTN04 was patched through 4480B_RTN02 towrads the 4498A CP site. Site Impacted : 4125C. NE_4480B/A00174 1.Enable GE2 at existing 4480B_RTN04 (ID : 23855). 2.ETH Patching from 4480B_RTN04_GE2 to Cisco Fiber Port Ge_0/2/1. 3.Create new In Band DCN. 4.Create a service cross-connect and migrate the BBU_4125C traffic through the MW link, to the new Cisco fiber port GE_0/2/1.. 5.Disconnect existing ETH LAN cable interconnect to 4480B_RTN02 and disconnect unused port. | [6 empty] | GCI | SQ202509260761-GCI | GCI | SQ202509260758-GCI | 2025-11-19 | 2025-11-20 | Completed | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Unassigned | Completed |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-20 | EZMA IDAYU BINTI MOHAMAD POZI6798000059 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1.00 | Assigned | Completed | Closed |  | DOWMY250925A5 |  | 2025-09-28 | 2025-09-25 | Completed | 2025-09-25 | 2025-09-28 | 2025-09-25 | 2025-09-25 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | GCI TI | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1.00 | Assigned | Completed |  | 2025-09-25 | 2025-09-28 | 2025-09-25 | 2025-09-25 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | GCI TI | 2025-09-25 | 2025-09-28 | 2025-09-25 | 2025-09-25 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | GCI TI | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | AKMAL//BIN RAZALI/6794000078 |  | 2025-09-26 | 2025-09-25 | 2025-09-28 | 2025-09-25 | 2025-09-28 | ABDUL//HAFIZ BIN ABDUL GHANI/6800000141 | 2025-09-30: 2025-09-25; 2025-09-30: 2025-09-28; 2025-09-30: 2025-09-25; 2025-10-08: 2025-09-25 |  |  | 2025-10-29 | 2025-11-29 | 2025-10-29 | 2025-10-29 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GCI | SQ202509260795-GCI | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | CHEONG/SENG/WAH/7018000306